## Panel Tracker
Panel Identification |  |  |  |  | Panel Specifications | [6 empty] | Excavation |  | Koden Check |  | Desanding |  | Water Stop |  | Rebar Cage |  | Tremie Pipe |  | Casting |  | Volumes |  |  | Other
Report Date | Engineer | Entry No. | Panel No. | Group | Panel Size | Guide Wall Level | Cut Off Level | Design Toe Level | Design Depth | Final Depth | Rock Hit | Start | End | Start | End | Start | End | Start | End | Start | End | Start | End | Start | End | Theo Vol | Actual Vol | Overbreak % | Downtime | Notes
05/02/26 |  |  | CN276 | G3 | 3.507 x 1.2 |  |  |  | 26.87m |  |  | 22:30hrs (02/02/26) | 16:25hrs (04/02/26) | 16:50hrs (04/02/26) | 17:35hrs (04/02/26) | 18:50hrs (04/02/26) | 21:50hrs (04/02/26) | Nil | Nil | 22:40hrs (04/02/26) | 01:45hrs (05/02/26) | 02:35hrs (05/02/26) | 02:50hrs (05/02/26) | 03:35hrs (05/02/26) | 08:35hrs (05/02/26) | 124.38m3 | 130m3 | 4.5%
29/03/26 |  |  | CN263 | G1 | 2.95m x 1.2m |  |  |  | 22.520m |  |  | 09:40hrs (28/03/26) | 11:00hrs (29/03/26) | 11:20hrs (29/03/26) | 11:45hrs (29/03/26) | 13:20hrs (29/03/26) | 14:45hrs (29/03/26) | 13:10hrs (29/03/26) | 13:30hrs (29/03/26) | 13:55hrs (29/03/26) | 14:55hrs (29/03/26) | 17:10hrs (29/03/26) | 17:25hrs (29/03/26) | 17:30hrs (29/03/26) | 19:45hrs (29/03/26) | 78.16m3 | 84m3 | 7.47% |  | NA
10/04/26 |  |  | CN260 | G1 | 2.95m x 1.2m |  |  |  | 22.956m |  |  | 23:40hrs (08/04/26) | 18:10hrs (09/04/26) | 18:35hrs (09/04/26) | 18:50hrs (09/04/26) | 21:30hrs (09/04/26) | 22:50hrs (09/04/26) |  |  | 00:00hrs (10/04/26) | 01:25hrs (10/04/26) | 01:50hrs (10/04/26) | 02:00hrs (10/04/26) | 03:00hrs (10/04/26) | 06:20hrs (10/04/26) | 83.98m3 | 93m3 | 10.74% |  | Housekeeping
16/03/26 |  |  | CN259 | G1 | 2.95m x 1.2m |  |  |  | 23.017m |  |  | 13:20hrs (14/03/26) | 14:55hrs (15/03/26) | 15:05hrs (15/03/26) | 15:35hrs (15/03/26) | 16:45hrs (15/03/26) | 18:10hrs (15/03/26) | 18:45hrs (15/03/26) | 19:10hrs (15/03/26) | 21:05hrs (15/03/26) | 22:55hrs (15/03/26) | 23:10hrs (15/03/26) | 23:25hrs (15/03/26) | 23:30hrs (15/03/26) | 02:00hrs (16/03/26) | 79.23m3 | 84m3 | 6.02% |  | Housekeeping & Preparation work
24/02/26 |  |  | CN282A | G3 | 3.0 x 1.2 |  |  |  | 26.945 m |  |  | 16:40hrs (22/02/26) | 02:45hrs (24/02/26) | 03:05hrs (24/02/26) | 03:30hrs (24/02/26) | 05:05hrs (24/02/26) | 06:45hrs (24/02/26) | 07:20hrs (24/02/26) | 07:35hrs (24/02/26) | 09:30hrs (24/02/26) | 14:55hrs (24/02/26) | 15:50hrs (24/02/26) | 16:05hrs (24/02/26) | 17:40hrs (24/02/26) | 21:40hrs (24/02/26) | 96.684 m3 | 102.00 m3 | 5.5% |  | Excavation at CN284
10/03/26 | DS |  | CN284 | G3 | 3.0m x 1.2m |  |  |  | 27.686m |  |  | 23:00hrs (08/03/26) |  | 18:15hrs (09/03/26) | 18:50hrs (09/03/26) | 20:45hrs (09/03/26) | 23:30hrs (09/03/26) | 23:50hrs (09/03/26) | 00:20hrs (10/03/26) | 01:15hrs (10/03/26) | 04:15hrs (10/03/26) | 04:35hrs (10/03/26) | 04:45hrs (10/03/26) | 07:15hrs (10/03/26) | 11:10hrs (10/03/26) | 96.53m3 | 100.00m3 | 3.59%
14/02/26 |  |  | CN290 | G3 | 2.95m x 1.2m |  |  |  | 28.76m |  |  | 20:40hrs (11/02/26) | 14:45hrs (13/02/26) | 14:55hrs (13/02/26) | 16:15hrs (13/02/26) | 17:20hrs (13/02/26) | 19:05hrs (13/02/26) | 19:40hrs (13/02/26) | 20:10hrs (13/02/26) | 20:25hrs (13/02/26) | 23:45hrs (13/02/26) | 23:55hrs (13/02/26) | 00:10hrs (14/02/26) | 01:15hrs (14/02/26) | 03:45hrs (14/02/26) | 97.49m3 | 104m3 | 6.67% |  | Housekeeping
03/03/26 |  |  | CN283 | G3 | 3.0m x 1.2m |  |  |  | 27.024m |  |  | 01:50hrs (01/03/26) | 15:30hrs (02/03/26) | 17:00hrs (02/03/26) | 18:30hrs (02/03/26) | 19:35hrs (02/03/26) | 21:50hrs (02/03/26) | 22:45hrs (02/03/26) | 23:20hrs (02/03/26) | 23:45hrs (02/03/26) | 04:45hrs (03/03/26) | 05:10hrs (03/03/26) | 05:30hrs (03/03/26) | 06:23hrs (03/03/26) | 10:45hrs (03/03/26) | 96.75m3 | 101.00m3 | 4.39% |  | Nil
14/03/26 |  |  | CN283A | G3 | 3.2m x 1.2m |  |  |  | 27.035m |  |  | 13:20hrs (11/03/26) | 04:20hrs (13/03/26) | 04:35hrs (13/03/26) | 04:50hrs (13/03/26) | 05:40hrs (13/03/26) | 07:40hrs (13/03/26) |  |  | 09:40hrs (13/03/26) | 14:55hrs (13/03/26) | 15:35hrs (13/03/26) | 16:25hrs (13/03/26) | 18:50hrs (13/03/26) | 23:40hrs (13/03/26) | 112.49m3 | 128m3 | 13.78% |  | Housekeeping
10/02/26 |  |  | CN289A | G3 | 2.95m x 1.2m |  |  |  | 28.753m |  |  | 17:30hrs (07/02/26) | 13:25hrs (09/02/26) | 16:10hrs (09/02/26) | 17:00hrs (09/02/26) | 17:45hrs (09/02/26) | 19:30hrs (09/02/26) | 20:35hrs (09/02/26) | 21:00hrs (09/02/26) | 21:40hrs (09/02/26) | 01:00hrs (10/02/26) | 01:15hrs (10/02/26) | 01:35hrs (10/02/26) | 09:40hrs (10/02/26) | 13:15hrs (10/02/26) | 99.51m3 | 101m3 | 9.73% |  | NA
04/02/26 |  |  | CN270 | G1 | 2.9m x 1m |  |  |  | 20.512m |  |  | 18:15hrs (02/02/26) | 22:50hrs (03/02/26) | 22:55hrs (03/02/26) | 23:20hrs (03/02/26) | 00:15hrs (04/02/26) | 01:40hrs (04/02/26) | 03:05hrs (04/02/26) | 04:00hrs (04/02/26) | 04:00hrs (04/02/26) | 06:25hrs (04/02/26) | 08:25hrs (04/02/26) | 09:05hrs (04/02/26) | 09:45hrs (04/02/26) | 11:00hrs (04/02/26) | 41.59m3 | 47m3 | 13% |  | NA
02/04/26 |  |  | CN262 | G1 | 2.95m x 1.2m |  |  |  | 22.55m |  |  | 20:50hrs (01/04/26) | 11:15hrs (02/04/26) | 11:25hrs (02/04/26) | 11:50hrs (02/04/26) | 14:30hrs (02/04/26) | 15:50hrs (02/04/26) | 16:20hrs (02/04/26) | 16:40hrs (02/04/26) | 17:10hrs (02/04/26) | 18:30hrs (02/04/26) | 18:50hrs (02/04/26) | 19:15hrs (02/04/26) | 19:40hrs (02/04/26) | 22:15hrs (02/04/26) | 79.12m3 | 84m3 | 6.16% |  | Housekeeping
18/03/26 |  |  | CN259A | G1 | 2.95m x 1.2m |  |  |  | 23.007m |  |  | 02:10hrs (17/03/26) | 00:10hrs (18/03/26) | 00:20hrs (18/03/26) | 00:45hrs (18/03/26) | 01:40hrs (18/03/26) | 02:40hrs (18/03/26) | 03:05hrs (18/03/26) | 03:30hrs (18/03/26) | 04:30hrs (18/03/26) | 05:35hrs (18/03/26) | 06:10hrs (18/03/26) | 06:35hrs (18/03/26) | 07:06hrs (18/03/26) | 09:30hrs (18/03/26) | 78.56m3 | 84m3 | 6.92% |  | Activities: Nil
07/02/26 |  |  | CN281A | G3 | 3.5 x 1.2 |  |  |  | 26.329 m |  |  | 17:50hrs (05/02/26) | 16:45hrs (06/02/26) | 17:05hrs (06/02/26) | 17:45hrs (06/02/26) | 19:35hrs (06/02/26) | 22:05hrs (06/02/26) | 23:00hrs (06/02/26) | 23:35hrs (06/02/26) | 23:45hrs (06/02/26) | 04:50hrs (07/02/26) | 05:00hrs (07/02/26) | 05:10hrs (07/02/26) | 06:25hrs (07/02/26) | 10:20hrs (07/02/26) | 112.01 m3 | 116.00 m3 | 3.562% |  | Nil
08/04/26 |  |  | CN261 | G1 | 5.75 x 1.2 |  |  |  | 22.55 m |  |  | 22:45hrs (03/04/26) | 02:10hrs (07/04/26) | 02:30hrs (07/04/26) | 03:00hrs (07/04/26) | 04:00hrs (07/04/26) | 06:30hrs (07/04/26) | 07:15hrs (07/04/26) | 07:40hrs (07/04/26) | 09:50hrs (07/04/26) | 16:20hrs (07/04/26) | 17:10hrs (07/04/26) | 17:40hrs (07/04/26) | 19:25hrs (07/04/26) | 23:40hrs (07/04/26) | 152.84 m3 | 166 m3 | 8.61% |  | Housekeeping
27/03/26 |  |  | CN263A | G1 | 2.95m x 1.2m |  |  |  | 22.49m |  |  | 01:25hrs (26/03/26) | 18:50hrs (26/03/26) | 18:55hrs (26/03/26) | 19:15hrs (26/03/26) | 22:05hrs (26/03/26) | 23:25hrs (26/03/26) | 23:40hrs (26/03/26) | 00:10hrs (27/03/26) | 01:25hrs (27/03/26) | 02:35hrs (27/03/26) | 02:55hrs (27/03/26) | 03:05hrs (27/03/26) | 04:00hrs (27/03/26) | 06:00hrs (27/03/26) | 78.62m3 | 84m3 | 6.84% |  | No Activity
23/02/26 |  |  | CN269A | G2 | 3.018 x 1 |  |  |  | 30.547 m |  |  | 10:25hrs (21/02/26) | 17:40hrs (22/02/26) | 18:00hrs (22/02/26) | 18:55hrs (22/02/26) | 20:45hrs (22/02/26) | 22:30hrs (22/02/26) |  |  | 23:25hrs (22/02/26) | 03:00hrs (23/02/26) | 03:20hrs (23/02/26) | 04:00hrs (23/02/26) | 04:10hrs (23/02/26) | 06:10hrs (23/02/26) | 80.033 m3 | 84 m3 | 4.96% |  | NA
11/02/26 |  |  | CN282 | G3 | 3.0m x |  |  |  | 1.2m |  |  | 21:40hrs (09/02/26) | 04:25hrs (11/02/26) | 04:35hrs (11/02/26) | 04:55hrs (11/02/26) | 06:00hrs (11/02/26) | 07:40hrs (11/02/26) | 09:30hrs (11/02/26) | 10:10hrs (11/02/26) | 10:50hrs (11/02/26) | 13:40hrs (11/02/26) | 14:10hrs (11/02/26) | 14:30hrs (11/02/26) | 15:30hrs (11/02/26) | 18:50hrs (11/02/26) | 96.31m3 | 101m3 | 4.87% |  | NA
22/02/26 |  |  | CN284A | G3 | 3.0m x 1.2m |  |  |  | 27.735m |  |  | 13:00hrs (20/02/26) |  | 18:00hrs (21/02/26) | 19:00hrs (21/02/26) | 20:30hrs (21/02/26) | 22:10hrs (21/02/26) | 00:05hrs (22/02/26) | 00:55hrs (22/02/26) | 01:50hrs (22/02/26) | 05:50hrs (22/02/26) | 06:10hrs (22/02/26) | 06:35hrs (22/02/26) | 09:30hrs (22/02/26) | 13:00hrs (22/02/26) | 97.07m3 | 105.00m3 | 9.20% |  | CR115 D-wall Progress Update. DAY SHIFT.