## All Logs
Day | Date | Main Location | Sub Location | Description / Activity | Manpower
Wed (05/01) | 05 Jan 2022 | Loyang Ave LP 178 | TR-V-L10 | Unable to locate services at current area, backfilling & will excavate next to it
Wed (05/01) | 05 Jan 2022 | Loyang Ave LP 168 | TR-V-L12 | Found StarHub, LVs (streetlight & park streetlight)
Thu (06/01) | 06 Jan 2022 | Preparation to start at LP156 |  | TR-V-L12A for starhub
Thu (06/01) | 06 Jan 2022 | Preparation to start at LP174 |  | TR-V-L10A for M1
Sat (15/01) | 15 Jan 2022 | Loyang Ave LP171 to LP173 | TR-V-R15 | Trial trench work continue to find telcom cables
Sat (15/01) | 15 Jan 2022 | Loyang Ave LP189 | TR-V-R10 | Manual excavation ongoing
Wed (19/01) | 19 Jan 2022 | TR-V-R23 | LP153 | Excavation for trial trench ongoing
Wed (19/01) | 19 Jan 2022 | TR-V-R27 | LP149 | Excavation for trial trench ongoing
Fri (21/01) | 21 Jan 2022 | TR-V-R33 | LP135 | Excavation ongoing. No services found yet
Fri (21/01) | 21 Jan 2022 | TR-V-R31 | LP137 | Found 66kV, Starhub, SingTel, HV cables
Thu (27/01) | 27 Jan 2022 | TR-V-L40 | LP118 | Trial trench completed. Backfilling in progress
Fri (28/01) | 28 Jan 2022 | LP120 |  | TR-V-L39 in progress
Fri (28/01) | 28 Jan 2022 | LP118S1 |  | TR-V-L41 yet to start. Operator went for SIC
Sat (29/01) | 29 Jan 2022 | LP122 |  | TR-V-L38 in progress
Sat (29/01) | 29 Jan 2022 | LP126 |  | TR-V-L37 in progress
Thu (03/02) | 03 Feb 2022 | LP118 |  | TR-V-L40A
Thu (03/02) | 03 Feb 2022 | LP157 |  | TR-V-R22A ongoing
Fri (04/02) | 04 Feb 2022 | Second batch tremie mix PBFC 4 hour in progress. Mix code |  | CR106-26
Fri (04/02) | 04 Feb 2022 | Trial trench at LP192 |  | TR-TFC-8A completed. Road reinstatement in progress
Fri (04/02) | 04 Feb 2022 | Trial trench at LP190 |  | TR-TFC-9A completed. Road reinstatement in progress
Wed (09/02) | 09 Feb 2022 | 1st concrete lorry on site. Casting started at 12 |  | 10PM
Wed (09/02) | 09 Feb 2022 | Now 4th truck. Progressive volume |  | 34/85m3
Wed (09/02) | 09 Feb 2022 | 5th truck casting ongoing. Progressive vol |  | 42.5/85m3
Wed (09/02) | 09 Feb 2022 | 7th truck in progress. Progressive vol |  | 59.5/85m3
Wed (09/02) | 09 Feb 2022 | Truck 9 casting. Progressive vol |  | 76.5/85m3
Wed (09/02) | 09 Feb 2022 | Truck 11 casting ongoing. Progressive vol |  | 93.5m3. Estimated 13 trucks total
Fri (11/02) | 11 Feb 2022 | TR-TFC-10D |  | Excavation for trial trench ongoing
Fri (11/02) | 11 Feb 2022 | TR-TFC-L23 | LP150 to 152 | Preparing to commence trial trenching
Fri (11/02) | 11 Feb 2022 | Cube Testing - G50 Tremie Mix PBFC | 7days | 1. Mix Code: CR106-25, * Nos. Of Test Cube tested : 9, * Specimen Dimension: (150mmx150mmx150mm), * Average Strength (N/mm^2): 56.8, 57.2, 58.3, * Mode of Failure: Satisfactory, 2. Mix Code: CR106-26 (4HRS), * Nos. Of Test Cube tested : 9, * Specimen Dimension: (150mmx150mmx150mm), * Average Strength (N/mm^2): 55.9, 58.2, 59.0, * Mode of Failure: Satisfactory, 3. Mix Code: CR106-27 (6HRS), * Nos. Of Test Cube tested : 9, * Specimen Dimension: (150mmx150mmx150mm), * Average Strength (N/mm^2): 52.2, 57.5, 57.6, * Mode of Failure: Satisfactory
Sat (12/02) | 12 Feb 2022 | TR-TFC-10D |  | Road cutting in progress
Sat (12/02) | 12 Feb 2022 | TR-V-L30 |  | Footpath hacking ongoing
Tue (15/02) | 15 Feb 2022 | TR-TFC-11E | LP191 | Road Premix hacking in progress
Tue (15/02) | 15 Feb 2022 | TR-TFC-12E | LP189 | Road Premix hacking in progress
Fri (18/02) | 18 Feb 2022 | Current status of C7 Drains |  | Installation completed. Now pending casting the sides of drain
Fri (18/02) | 18 Feb 2022 | TR-TFC-12B | LP180 | Road premix hacking in progress
Fri (18/02) | 18 Feb 2022 | TR-TFC-11B | LP186 | Road premix hacking in progress
Sat (19/02) | 19 Feb 2022 | TR-TFC-11C | LP186 | Road premix hacking in progress
Sat (19/02) | 19 Feb 2022 | TR-TFC-12C | LP180 | Road premix hacking in progress
Sat (19/02) | 19 Feb 2022 | SPT-1 |  | At depth 4-4.45m, Sample 1 collected (N-value 54)
Sat (19/02) | 19 Feb 2022 | SPT-2 |  | At depth 6-6.45m, Sample 2 collected (N-value 48)
Sat (19/02) | 19 Feb 2022 | ABH-73 | SI work | Drilling to depth 18m in progress
Sat (19/02) | 19 Feb 2022 | SPT-10 |  | At depth 22-22.45m, Sample 10 collected (75 N-value )
Thu (24/02) | 24 Feb 2022 | SPT-1 |  | At depth 4-4.45m, Sample 1 collected (N-value 5)
Fri (25/02) | 25 Feb 2022 | Loyang Ave middle lane LP179 |  | TR-TFC-14E premix hacking
Fri (25/02) | 25 Feb 2022 | Loyang Ave middle lane LP183 |  | TR-TFC-13E premix hacking
Sat (26/02) | 26 Feb 2022 | LP183 |  | TR-TFC-13F preparation ongoing
Sat (26/02) | 26 Feb 2022 | LP177 |  | TR-TFC-14F premix cutting in progress
Tue (01/03) | 01 Mar 2022 | TR-V-L27 services found |  | LV and HV slabs
Tue (01/03) | 01 Mar 2022 | TR-V-L28 services found |  | Starhub, HV and M1 PVC slab
Wed (02/03) | 02 Mar 2022 | TR-V-R24 preparing to start works. Expected services |  | LV, HV, SPTel
Wed (02/03) | 02 Mar 2022 | TR-V-R26 works started. Expected services |  | SPTel, HV, LV, EHV, Starhub
Wed (02/03) | 02 Mar 2022 | PJT Office 3rd floor |  | Setting up wall partitions ongoing
Wed (02/03) | 02 Mar 2022 | CR106 Rebar Testing | 2 March 2022 | 1. Natsteel, Tensile Test: 3 samples each (H10, H13, H16, H20, H25, H32, H40), All 21 tests passed and meet the minimum requirements, Bend & Rebend Test: 2 samples each (H10, H13, H16, H20, H25, H32, H40), All 7 bend tests are Satisfactory. No sign of visible fracture or cracks, Rebend test will be done next day (No witness required), Surface Geometry Test: 1 sample each (H10, H13, H16, H20, H25, H32, H40), This test will be done another day (No witness required), Chemical Analysis Test: Using tested sample (H10, H13, H16, H20, H25, H32, H40), This will test will be done another day (No witness required), 2. ICDAS, Tensile Test: 3 samples each (H10, H13, H16, H20, H25, H32, H40), All 21 tests passed and meet the minimum requirements, Bend & Rebend Test: 2 samples each (H10, H13, H16, H20, H25, H32, H40), All 7 bend tests are Satisfactory. No sign of visible fracture or cracks, Rebend test will be done next day (No witness required), Surface Geometry Test: 1 sample each (H10, H13, H16, H20, H25, H32, H40), This test will be done another day (No witness required), Chemical Analysis Test: Using tested sample (H10, H13, H16, H20, H25, H32, H40), This will test will be done another day (No witness required), 3. JSW, Tensile Test: 3 samples each (H10), All 3 tests passed and meet the minimum requirements, Bend & Rebend Test: 2 samples each (H10), All bend test are Satisfactory. No sign of visible fracture or cracks, Rebend test will be done next day (No witness required), Surface Geometry Test: 1 sample each (H10), This test will be done another day (No witness required), Chemical Analysis Test: Using tested sample (H10), This will test will be done another day (No witness required)
Thu (03/03) | 03 Mar 2022 | LP154 |  | TR-V-L22 in progress. Expected services: Starhub, lamp post, M1, EHV
Thu (03/03) | 03 Mar 2022 | LP156 |  | TR-V-L20 in progress. Expected services: Starhub, lamp post, M1, EHV
Thu (03/03) | 03 Mar 2022 | PJT Office 1st floor |  | Ceiling grid installation ongoing
Thu (03/03) | 03 Mar 2022 | 3rd floor |  | Wall partitions ongoing
Fri (04/03) | 04 Mar 2022 | TR-V-L6 | LP2, Loyang Way | Preparation work only, pending PTD
Fri (04/03) | 04 Mar 2022 | TR-V-L13 | LP180, Loyang Ave | Preparation work only, pending PTD
Fri (04/03) | 04 Mar 2022 | TR-V-L6 | LP2, PRD3 | Trial Trench completed. Services found: EHV, M1, LT cable, LV cable, SingTel, M1
Fri (04/03) | 04 Mar 2022 | TR-V-L13 | LP176, Loyang Ave | Trial Trench completed. Services found: LV, LT, Starhub
Sat (05/03) | 05 Mar 2022 | TR-V-L3 | LP196 | Trial trench excavation in progress. Expected services : EHV, starhub, water pipe
Sat (05/03) | 05 Mar 2022 | TR-V-L14 | LP170 | Trial trench excavation in progress. Expected services : EHV, M1, starhub
Sat (05/03) | 05 Mar 2022 | TR-V-L14 | LP170 | Trial trench completed. Services found : LV slab, LT slab, starhub
Sat (05/03) | 05 Mar 2022 | TR-V-L3 | LP196 | Trial trench completed. Services found : 1.6m dia water pipe
Sat (05/03) | 05 Mar 2022 | Loyang Ave | LP197 | Lane closed for premix rectification work for previous trial trench area. Pending premix to arrive on site
Sat (05/03) | 05 Mar 2022 | Road premix rectification works | LP197 & LP199 | Compaction of premix in progress
Sat (05/03) | 05 Mar 2022 | Soil investigation | ABH23-2 - R1 | Redo of SI work for ABH23-2 as the result obtained in the 1st SI work differ from LTA reference. A different kind of S.I hammer was used for the 2nd SI work. Drilling to 6m depth in progress
Sun (06/03) | 06 Mar 2022 | Drilling reached 26m as of now. Dongah working until 5 |  | 30PM today
Tue (08/03) | 08 Mar 2022 | Services found at TR-V-R2 |  | LT slab, LV slabs and Singtel
Tue (08/03) | 08 Mar 2022 | Services found at TR-V-L1 |  | 66kv, gas pipe, M1, Singtel and unknown pipes (2nos). Woh Hup has been informed of these unknown pipes at depth 950mm
Wed (09/03) | 09 Mar 2022 | Services found at TR-V-R4 |  | LV slab, singtel, M1
Thu (10/03) | 10 Mar 2022 | TR-TFC-15F services found |  | 66kv and water pipe
Thu (10/03) | 10 Mar 2022 | TR-TFC-16F services found |  | 66kv and water pipe
Fri (11/03) | 11 Mar 2022 | PJT Office | 2nd floor | Wall partitions setting up / plastering & painting works ongoing
Fri (11/03) | 11 Mar 2022 | PJT Office | 3rd floor | Preparing for internal staircase
Sat (12/03) | 12 Mar 2022 | PJT Office | 3rd floor | Pending internal staircase installation, continue wall partition installation/plastering & painting work
Sat (12/03) | 12 Mar 2022 | PJT Office | 2nd floor toilet | Preparing for waterproofing works
Sat (12/03) | 12 Mar 2022 | PJT Office | 2nd floor | Corridor / staircase status
Wed (23/03) | 23 Mar 2022 | TR-TF -5B | LP200 | Premix removal ongoing
Wed (23/03) | 23 Mar 2022 | TR-TFC-3B | New Loyang Link LP3 | Premix removal ongoing
Fri (25/03) | 25 Mar 2022 | TR-TFC-3D | Zone 1 | Services found - HV Slab , Gas pipe
Fri (25/03) | 25 Mar 2022 | TR-TFC-4D | Zone 1 | Services found - HV Slab , Gas pipe
Mon (28/03) | 28 Mar 2022 | Trial Trench BT-04 | Outside LTPK Temple | Road hacking in progress. For BlueTel NCE and Sewer pipe jacking
Mon (28/03) | 28 Mar 2022 | Trial Trench BT-03 | LP84 | Trench excavation in progress. For BlueTel NCE
Mon (28/03) | 28 Mar 2022 | LTA Office | Level 3 | Current status
Tue (29/03) | 29 Mar 2022 | CR106 |  | CR106 has observed pothole with water seeping out along loyang avenue towards Tampines boundnear LP 185.(near site access for PD office ), There was no trial trenched planned and conducted within vincnity of LP185 since 19/2/2022, WHDAJV is currently assessing and has informed PUB and RARL
Tue (29/03) | 29 Mar 2022 | CR106 |  | CR106 has observed pothole with water seeping out along loyang avenue towards Tampines boundnear LP 185.(near site access for PD office ), There was no trial trenched planned and conducted within vincnity of LP185 since 19/2/2022, PUB and RARL has been informed and PUB has arrived on 4.45pm. They have assessed that valve is damaged, CR106 did not have any trial trench on the valve location
Tue (29/03) | 29 Mar 2022 | CR106 |  | CR106 has observed pothole with water seeping out along loyang avenue towards Tampines boundnear LP 185.(near site access for PD office ), PUB and RARL has been informed and PUB has arrived on 4.45pm. They have assessed that valve is damaged, CR106 did not have any trial trench conducted on the valve location. There was also no trial trench planned and conducted within vincnity of LP185 since 19/2/2022
Thu (31/03) | 31 Mar 2022 | TR-TFC-24B |  | Lane marking in progress
Thu (31/03) | 31 Mar 2022 | WH office | Level 1 | Plumbing works installation in progress
Thu (31/03) | 31 Mar 2022 | WH office | Level 2 | Current status
Thu (31/03) | 31 Mar 2022 | WH office | Level 3 | Current status
Thu (31/03) | 31 Mar 2022 | PJT office 2nd floor |  | Wall tiling work in progress
Thu (31/03) | 31 Mar 2022 | PJT office level 1 |  | Screeding work in progress
Sat (02/04) | 02 Apr 2022 | TR-TFC-24D |  | Water pipe, HV, starhub
Sun (03/04) | 03 Apr 2022 | PJT Office | Level 3 | Cables installation in progress
Sun (03/04) | 03 Apr 2022 | PJT Office | Level 2 | Current status
Sun (03/04) | 03 Apr 2022 | PJT office | Level 1 | Removal of wall plastic in progress
Sun (03/04) | 03 Apr 2022 | PJT Office | Level 3 | Continual of wire installation
Mon (04/04) | 04 Apr 2022 | PJT Office | 2nd floor | Carpet installation ongoing
Mon (04/04) | 04 Apr 2022 | Exit 5 |  | Vehicles will now temporary move in via the entrance behind PJT office
Mon (04/04) | 04 Apr 2022 | PJT Office | Level 1 | Tiles installation for toilet in progress
Mon (04/04) | 04 Apr 2022 | PJT office | Level 2 | Removal of wall plastic in progress
Mon (04/04) | 04 Apr 2022 | PJT Office | Level 3 | Wire installation
Mon (04/04) | 04 Apr 2022 | WH Office | level 2 | Current status
Tue (05/04) | 05 Apr 2022 | PD Office Base Slab | 2nd portion | Inspection done, concrete ordered
Thu (07/04) | 07 Apr 2022 | PJT Office | 2nd floor | Toilets floor tile laying ongoing
Sat (09/04) | 09 Apr 2022 | LTA office | Lvl 1 | Installation of toilet equipment
Sat (09/04) | 09 Apr 2022 | LTA office | Lvl2 | Installation of floor tile for toilet
Sat (09/04) | 09 Apr 2022 | WH office | Lvl 2 & 3 | Wall partition installation in progress
Sat (09/04) | 09 Apr 2022 | Lta office | lvl2 | Toilet tiles installation
Sat (09/04) | 09 Apr 2022 | TR-TFC-1A |  | Found m1 slab @ 1m depth
Sat (09/04) | 09 Apr 2022 | TR-TFC-2A |  | Found m1 slab @ 0.8m depth
Tue (12/04) | 12 Apr 2022 | PD Office | base slab part 3 | Casting started, est total vol: 40m3
Tue (12/04) | 12 Apr 2022 | PD office base slab part 3 casting completed. Total vol |  | 52m3, G30
Tue (12/04) | 12 Apr 2022 | PD Office | base slab part 3 | Inspection completed, concrete ordered. ETA 30min
Wed (13/04) | 13 Apr 2022 | PJT Office | Lvl2 | Wire installation works ongoing for power point
Wed (13/04) | 13 Apr 2022 | PJT Office | Lvl3 | Wall tiles installation for toilet
Wed (13/04) | 13 Apr 2022 | WH office | Lvl2 | Current status
Wed (13/04) | 13 Apr 2022 | WH office | Lvl3 | Current status
Thu (14/04) | 14 Apr 2022 | PJT Office | 2nd floor | Changing of wall alignment ongoing
Thu (14/04) | 14 Apr 2022 | PJT office | 2nd floor | Female toilet shower pipes installation
Thu (14/04) | 14 Apr 2022 | PJT Office | 3rd floor toilets | Preparing for floor tiling work
Thu (14/04) | 14 Apr 2022 | WH Office | 3rd floor | Wall plastering work ongoing
Sat (16/04) | 16 Apr 2022 | Outside of PD Office | Near LP189 | Excavation in progress for power and telcom pipe laying
Sat (16/04) | 16 Apr 2022 | TR-TFC-19b | LP152 | Manual excavation in progress
Sat (16/04) | 16 Apr 2022 | LTA office | Lvl 2 | Installation of toilet equipment
Sat (16/04) | 16 Apr 2022 | LTA office | Lvl 3 | Installation of toilet tiles
Sat (16/04) | 16 Apr 2022 | WH office | Lvl1 | Current status
Sat (16/04) | 16 Apr 2022 | WH office | Lvl2 | Wire installation in progress
Sat (16/04) | 16 Apr 2022 | LTA office | Lvl3 | Current status. Continue installation of toilet tiles
Mon (18/04) | 18 Apr 2022 | WH office | Lvl1 | Preparation work for wall tiles installation
Mon (18/04) | 18 Apr 2022 | WH office | lvl 2 | Wire installation ongoing
Mon (18/04) | 18 Apr 2022 | Lta office | lvl 3 | Toilet tiles installation
Mon (18/04) | 18 Apr 2022 | LTA office | Lvl1 | Carpet works and toilet door installation
Mon (18/04) | 18 Apr 2022 | LTA office | lvl3 | Continue of toilet tiles installation
Mon (18/04) | 18 Apr 2022 | LTA office | lvl2 | Toilet walls works in progress
Wed (20/04) | 20 Apr 2022 | WH office | Lvl 2&3 | Electrical wire works installation ongoing
Wed (20/04) | 20 Apr 2022 | LTA office | Lvl3 | Toilet cubicle wall installation
Thu (21/04) | 21 Apr 2022 | LTA office | Lvl3 | Toilet cubicle wall installation
Thu (21/04) | 21 Apr 2022 | WH office | Lvl3 | Wall painting of room ongoing
Thu (21/04) | 21 Apr 2022 | LTA office | Lvl2 | Continue installation of toilet wall cubicle and toilet accessory
Fri (22/04) | 22 Apr 2022 | WH office | lvl2 | Painting works
Fri (22/04) | 22 Apr 2022 | WH office | lvl3 | Electrical installation & plastering works
Fri (22/04) | 22 Apr 2022 | LTA office | lvl3 | Toilet accessories installation
Fri (22/04) | 22 Apr 2022 | TR-TFC-17D |  | Found LV cable @ 0.65m depth
Fri (22/04) | 22 Apr 2022 | TR-TFC-20C |  | Found LV cable @ 0.65m depth
Mon (25/04) | 25 Apr 2022 | WH Office | 2nd floor | Tiling works in progress
Mon (25/04) | 25 Apr 2022 | PJT Office | 2nd floor | Pantry / toilet area
Tue (26/04) | 26 Apr 2022 | PJT Office | level 2 | Cubicle partition work in progress
Tue (26/04) | 26 Apr 2022 | PJT office | level 3 | Cubicle partition in progress
Tue (26/04) | 26 Apr 2022 | TR-TFC-21A |  | Excavation work in progress
Tue (26/04) | 26 Apr 2022 | TR-TFC-29A |  | Preparing to commence work
Wed (27/04) | 27 Apr 2022 | WH office | Lvl2 | Installation of ceiling panel
Thu (28/04) | 28 Apr 2022 | WH office | Lvl2 | Flooring works in progress
Fri (29/04) | 29 Apr 2022 | SI ABH-21 |  | Current depth at 20m. SPT-9 (20-20.45m)
Fri (29/04) | 29 Apr 2022 | Wh office | lvl1 | Electrical works installation ongoing
Wed (11/05) | 11 May 2022 | Zone 4 |  | No activity. DE143 working within their boundary
Thu (12/05) | 12 May 2022 | Zone 4 |  | No activity. DE143 working within their boundary
Fri (13/05) | 13 May 2022 | Zone 2 |  | DE143 working within their site boundary
Fri (13/05) | 13 May 2022 | Zone 1 |  | No activity of other contractor in CR106 boundary
Fri (13/05) | 13 May 2022 | Zone 4 |  | No activity. DE143 working within their boundary
Wed (18/05) | 18 May 2022 | Zone 4 |  | No activity. DE143 working within their boundary
Thu (19/05) | 19 May 2022 | Zone 4 |  | No activity of other contractors
Thu (19/05) | 19 May 2022 | Zone 3 | ABH-69 | Setting up in progress
Thu (19/05) | 19 May 2022 | R46 | LP19/1 | Area backfilled
Thu (19/05) | 19 May 2022 | L45 & L46 | LP110-112 | Area backfilled
Fri (20/05) | 20 May 2022 | Zone 4 |  | No activity
Fri (20/05) | 20 May 2022 | Zone 3 | ABH-69 | Trial trench work ongoing up till 1.5m, then will proceed with hand augering
Fri (20/05) | 20 May 2022 | TR-JTC-2 |  | Excavation ongoing
Fri (20/05) | 20 May 2022 | TR-JTC-3 |  | Excavation ongoing
Fri (20/05) | 20 May 2022 | TR-JTC-1 |  | Preparing to start trial trench work
Mon (23/05) | 23 May 2022 | TR-JTC-5 |  | Manual excavation ongoing
Mon (23/05) | 23 May 2022 | TR-JTC-4 |  | Prepare to start manual excavation, TR-JTC-4A: brick removal ongoing
Mon (23/05) | 23 May 2022 | Zone 2 |  | DE143 works in their site
Mon (23/05) | 23 May 2022 | Zone 2 |  | DE143 works along Loyang Ave LP177 Sidetable
Mon (23/05) | 23 May 2022 | ULT-2 |  | Setting up of BG36
Mon (23/05) | 23 May 2022 | Zone 1 |  | No contractor working here
Tue (24/05) | 24 May 2022 | Zone 1 |  | No other contractor working here
Tue (24/05) | 24 May 2022 | ABH-69 |  | Current depth at 36m
Tue (24/05) | 24 May 2022 | ABH-105 |  | Trial trench in progress
Wed (25/05) | 25 May 2022 | Exit 3 |  | WH setting up the noise barrier at perimeter of ULT2
Wed (25/05) | 25 May 2022 | Exit 3 |  | Setting up and connection of pipes for Desander and the slurry tank
Wed (25/05) | 25 May 2022 | ABH-69 |  | Current depth - 41.7m. Found rock at 41.2m. Coring through rock in progress (0.5m completed)
Wed (25/05) | 25 May 2022 | BH-105 |  | Manual Trial trench temporarily stopped due to rain
Wed (25/05) | 25 May 2022 | Zone 2 |  | DE143 working within their site boundary
Wed (25/05) | 25 May 2022 | Zone 4 |  | No activity. DE143 working within their boundary
Thu (26/05) | 26 May 2022 | Zone 4 |  | No activity of other contractors
Thu (26/05) | 26 May 2022 | ABH-69 |  | Current depth 44m
Thu (26/05) | 26 May 2022 | BH-105 |  | Trial trench work completed, preparing to shift to next location
Thu (26/05) | 26 May 2022 | Zone 3 |  | No works of other contractor
Thu (26/05) | 26 May 2022 | Zone 2 Loyang Ave towards TPE |  | DE143 lane closure at slow lane
Fri (27/05) | 27 May 2022 | Exit 3 |  | Bund wall installation around bentonite tank
Fri (27/05) | 27 May 2022 | Exit 3 |  | Preparation for Barricade works
Sat (28/05) | 28 May 2022 | Exit 3 |  | Continue of Bund wall installation
Sat (28/05) | 28 May 2022 | Zone 1 |  | No other contractor working at the area
Sat (28/05) | 28 May 2022 | Zone 3 |  | No other contractor working at the area
Sat (28/05) | 28 May 2022 | Zone 4 |  | No other contractor working at the area
Sat (28/05) | 28 May 2022 | Exit 3 |  | Shifting of materials for rebar cage storage on Monday
Sat (28/05) | 28 May 2022 | Exit 3 |  | Bund wall around the bentonite tank completed
Sat (28/05) | 28 May 2022 | ABH-69 |  | Backfilling in progress for completed SI
Sat (28/05) | 28 May 2022 | Zone 2 |  | No other contractor working in the area
Mon (30/05) | 30 May 2022 | Zone 4 |  | No activity from other contractors
Mon (30/05) | 30 May 2022 | BH-107 |  | Manual excavation ongoing
Mon (30/05) | 30 May 2022 | Zone 3 | towards CV | No activity by other contractor
Mon (30/05) | 30 May 2022 | Zone 3 | towards TPE | PUB contractor working Sidetable at LP135
Mon (30/05) | 30 May 2022 | Zone 2 |  | No other contractors working here
Mon (30/05) | 30 May 2022 | Zone 2 |  | DE143 working in their site
Mon (30/05) | 30 May 2022 | ULT 1&11 |  | Manual excavation for 2.4m ht hoarding work
Mon (30/05) | 30 May 2022 | PD office roofing wire mesh installation continue until 9 |  | 30pm. Thereafter housekeeping till ~10pm
Tue (31/05) | 31 May 2022 | Zone 3 | BH-70 | Machine setting up, topping up water / preparing to commence drilling work
Tue (31/05) | 31 May 2022 | Zone 3 | BH-104 | Manual excavation work in progress
Tue (31/05) | 31 May 2022 | Exit 3 |  | Spacers casting completed. QPS witnessed
Tue (31/05) | 31 May 2022 | Zone 2 |  | DE143 works in their site
Tue (31/05) | 31 May 2022 | Trial trench for ULT-2 |  | No services found
Tue (31/05) | 31 May 2022 | ULT-2 |  | Bund wall fixing around the bentonite Desander tank
Tue (31/05) | 31 May 2022 | ULT-2 |  | Strain gauge instrumentation installation on rebar cage
Tue (31/05) | 31 May 2022 | ULT-2 |  | Lowering of casing (5.5m)
Tue (31/05) | 31 May 2022 | ULT-2 |  | Continue of pre-boring to install another 3.5m casing
Tue (31/05) | 31 May 2022 | ULT-2 |  | Work stopped for the day. 2nd casing (3.5m) lowered down
Tue (31/05) | 31 May 2022 | ULT2 |  | Continue of noise barriers installation
Tue (31/05) | 31 May 2022 | Zone 2 PD office |  | Roofing wire mesh installation ongoing
Tue (31/05) | 31 May 2022 | Zone 2 | 2.4m ht site hoarding for ULT 1&11 | Manual excavation continue for footing
Tue (31/05) | 31 May 2022 | Zone 1 |  | No activity by other contractor
Tue (31/05) | 31 May 2022 | ULT 2 |  | Status of noise barrier for desander machine
Tue (31/05) | 31 May 2022 | ULT 2 |  | Instrumentation pipe preparation for installation at rebar cage for test pile
Wed (01/06) | 01 Jun 2022 | ULT-2 |  | Fresh Bentonite density check - 1.03 (Within Range)
Wed (01/06) | 01 Jun 2022 | ULT-2 |  | Fresh Bentonite viscosity check - 44.36s (Within Range)
Wed (01/06) | 01 Jun 2022 | Zone 3 |  | MH-104 manual excavation status
Wed (01/06) | 01 Jun 2022 | Zone 3 |  | AH70 soil investigation, drilling in progress at about 12m depth
Wed (01/06) | 01 Jun 2022 | Zone 3 |  | No activity observed for other contractor
Wed (01/06) | 01 Jun 2022 | ULT 2 |  | Bund wall putting up status
Wed (01/06) | 01 Jun 2022 | Zone 4 |  | No other contractor working in the boundary. Only Hi-Tech doing trial trench
Wed (01/06) | 01 Jun 2022 | Zone 2 |  | DE143 works ongoing
Wed (01/06) | 01 Jun 2022 | ULT-2 |  | Boring works in progress
Wed (01/06) | 01 Jun 2022 | ULT2 |  | Continue of noise barrier installation around the ULT-2 perimeter
Wed (01/06) | 01 Jun 2022 | Zone 3 |  | AH70 drilling continue. Around 20m depth
Wed (01/06) | 01 Jun 2022 | ULT-2 |  | Mechanic arrived on site to check on the hydraulic hose
Wed (01/06) | 01 Jun 2022 | Zone 3 |  | No activity observed for other contractor (afternoon)
Wed (01/06) | 01 Jun 2022 | 4pm |  | After checking, it was found that the hydraulic cooler was damaged instead. The mechanic is removing the current cooler and will replace with the spare part (otw to site from tuas)
Thu (02/06) | 02 Jun 2022 | ULT 2 |  | Boring continue. Current depth at 19m
Thu (02/06) | 02 Jun 2022 | ULT-2 |  | Grouting pipe installation at the rebar cage
Thu (02/06) | 02 Jun 2022 | ULT 2 |  | Kelly Bar vertically checked at 20m
Thu (02/06) | 02 Jun 2022 | ULT-2 |  | At 11.47am, the boring reached 26.5m depth. Touched G(III). An inspection with QPS will be carried out at 1pm to check on the G(III)
Thu (02/06) | 02 Jun 2022 | ULT2 |  | Current depth 26.5m from top of casing, 25.5m from GL
Thu (02/06) | 02 Jun 2022 | ULT2 |  | Continue of boring work
Thu (02/06) | 02 Jun 2022 | ULT 2 |  | Current depth at 27.4 from TOC, 26.4 from GL
Thu (02/06) | 02 Jun 2022 | ULT 2 |  | Point load test conducted with 3 specimen
Thu (02/06) | 02 Jun 2022 | ULT 2 |  | Concrete cover mold dismantling
Thu (02/06) | 02 Jun 2022 | ULT-2 |  | Bentonite checked at 5pm (Within range)
Thu (02/06) | 02 Jun 2022 | ULT2 |  | At 5.18pm - Current depth 28.6m from top of casing, 27.6m from GL. (Toe level - 29.7m from top of casing)
Thu (02/06) | 02 Jun 2022 | ULT2 |  | At 7.18pm - Current depth 29.6m from top of casing, 28.6m from GL. (Toe level - 29.77m from top of casing)
Thu (02/06) | 02 Jun 2022 | ULT2 |  | Work stopped for the day. Tomorrow will continue boring the remaining 0.17m. (Depth 29.6m/29.77m) completed
Thu (02/06) | 02 Jun 2022 | ULT-2 |  | Bentonite slurry test conducted. (Within Range)
Thu (02/06) | 02 Jun 2022 | ULT-2 |  | At 9.06am, continue of boring work from yesterday. Depth - 12m
Fri (03/06) | 03 Jun 2022 | ULT-2 |  | At 9.57am, Continue of balance boring works
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Depth reach at 30.05 from TOC, 29.05 from GL. Actual toe level at 17.05 mSHD
Fri (03/06) | 03 Jun 2022 | Zone 2 |  | DE143 working in their site boundary
Fri (03/06) | 03 Jun 2022 | Zone 2 |  | No activity from other contractor
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Preparation to lower down centrifugal pump for desanding
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Desanding starts at 13:17 hrs
Fri (03/06) | 03 Jun 2022 | ULT-2 |  | Demo for grouting pipe opening
Fri (03/06) | 03 Jun 2022 | UTL2 |  | Area preparation for koden test
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Koden Test in progress
Fri (03/06) | 03 Jun 2022 | ATT20-6 |  | Reinstated completed
Fri (03/06) | 03 Jun 2022 | X-x1 direction |  | Max inclination at 180mm, Y-Y direction:, maximum inclination 150mm, Allowable inclination: 1:75 or 13mm per meter, Allowable inclination for 30m: 400mm, *inclination for both direction is within the limit*
Fri (03/06) | 03 Jun 2022 | Zone 3 | ABH 70 | Grouting completed, casing extraction ongoing. Will shift to BH-103
Fri (03/06) | 03 Jun 2022 | Zone 3 |  | Trial trench started for BH-77
Fri (03/06) | 03 Jun 2022 | ULT-2 |  | Bentonite Slurry test
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Preparation for steel cage lowering
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Safety briefing prior to steel cage lowering
Fri (03/06) | 03 Jun 2022 | ULT 2 |  | Bottom cage lowering (12m)
Fri (03/06) | 03 Jun 2022 | ULT2 |  | Bottom cage lower down
Fri (03/06) | 03 Jun 2022 | ULT2 |  | Middle cage lifting
Mon (06/06) | 06 Jun 2022 | ULT 2 |  | Soil disposal
Mon (06/06) | 06 Jun 2022 | Zone 3 | BH-103 | Preparing to start drilling work
Mon (06/06) | 06 Jun 2022 | Zone 3 |  | No activity of other contractors
Mon (06/06) | 06 Jun 2022 | Zone 3 | BH-77 | Trial hole ongoing, setting up of 2nd rig in progress
Mon (06/06) | 06 Jun 2022 | Zone 4 |  | Today trial trench late lane closure due to TMA late arrival
Mon (06/06) | 06 Jun 2022 | Zone 4 |  | No other activity by other contractor
Mon (06/06) | 06 Jun 2022 | ULT 2 |  | Support pile boring started
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | Continue boring works for 1st support pile. Current depth from GL: 7m. Toe level: 25m from GL
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | Demob of 1200mm boring bits and casings
Mon (06/06) | 06 Jun 2022 | ULT 2 |  | Support pile boring continue. Current depth at 11m from TOC
Mon (06/06) | 06 Jun 2022 | ULT2 |  | Cement mixing for test pile base grouting. Current mix 8 nos 50kg cement ~ 0.344 m3
Mon (06/06) | 06 Jun 2022 | ULT 2 |  | Grouting tube flushing
Mon (06/06) | 06 Jun 2022 | ULT-2 | SP-06 | Pre-boring in progress, they plan to cast this tmr afternoon
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | At 7.12pm, First load arrived on site. Grade 40, Total 15m^3
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | Lowering of tremie pipe
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | At 7.26pm, casting started for (SP-2)
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | Last load reached site
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | Last load started casting at 7.57pm
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | SP(2) casing extraction
Mon (06/06) | 06 Jun 2022 | ULT-2 |  | Casting completed for SP(2) at 8.27pm
Mon (06/06) | 06 Jun 2022 | ULT 2 |  | Area preparation for Support bored pile boring
Tue (07/06) | 07 Jun 2022 | Gate 5 |  | ECM pond within acceptable level
Tue (07/06) | 07 Jun 2022 | SP 06 |  | Depth reach at 26.2m from TOC
Tue (07/06) | 07 Jun 2022 | ULT-2 |  | SP-4 Pre boring in progress
Tue (07/06) | 07 Jun 2022 | SP 06 |  | Casting started. Running volume 7.5 m3. Total ordered 14.5 m3
Tue (07/06) | 07 Jun 2022 | SP04 |  | Boring continue. Current depth at 24.5m from TOC
Tue (07/06) | 07 Jun 2022 | ULT-2 | SP4 | Casting started
Tue (07/06) | 07 Jun 2022 | ULT-2 | SP4 | 2nd lorry casting in progress
Tue (07/06) | 07 Jun 2022 | ULT 2 |  | Soil disposal
Tue (07/06) | 07 Jun 2022 | ULT2 |  | SP-06 boring continue. Current depth at 8m from TOC
Tue (07/06) | 07 Jun 2022 | ULT 2 |  | Steel plate 1st batch delivered for kentledge test. 19 nos ~95 tons
Wed (08/06) | 08 Jun 2022 | SP 03 |  | Boring in progress
Wed (08/06) | 08 Jun 2022 | Zone 2 |  | DE143 doing SI work at side table
Wed (08/06) | 08 Jun 2022 | Zone 3 |  | BH 103 SI works, current depth at 32m
Wed (08/06) | 08 Jun 2022 | ULT-2 |  | Demob of grouting machine and unused materials
Wed (08/06) | 08 Jun 2022 | Zone 3 |  | 2nd rig for SI at BH 77, current depth 14m
Wed (08/06) | 08 Jun 2022 | Zone 3 |  | No other contractor working in our boundary
Wed (08/06) | 08 Jun 2022 | ULT-2 |  | Installation of steel casing for SP(03)
Wed (08/06) | 08 Jun 2022 | ULT-2 |  | Soil disposal
Wed (08/06) | 08 Jun 2022 | ULT-2 |  | Another 11 pcs steel plate delivered. Total now on site 49 pcs ~ 245 tons
Wed (08/06) | 08 Jun 2022 | ULT-2 | SP3 | Boring works continue, current depth 20m
Wed (08/06) | 08 Jun 2022 | ULT-2 |  | Another 15 pcs steel plate delivered. Total now on site 64 pcs ~ 320 tons
Wed (08/06) | 08 Jun 2022 | ULT-2 | SP3 | Boring works completed. Current depth 26.3m from TOC. Concrete for casting ordered
Wed (08/06) | 08 Jun 2022 | SP01 |  | Boring started
Wed (08/06) | 08 Jun 2022 | ULT 2 |  | Steel plate delivery. (+44 pcs , 82 pcs / 776 pcs)
Wed (08/06) | 08 Jun 2022 | ULT-2 | SP3 | Casting started, total vol: 14.5m3 G40
Wed (08/06) | 08 Jun 2022 | ULT 2 |  | Steel casing demob from site
Thu (09/06) | 09 Jun 2022 | Zone 4 to CV |  | No works by other contractor
Thu (09/06) | 09 Jun 2022 | Zone 4 |  | DE143 working within their boundary
Thu (09/06) | 09 Jun 2022 | Zone 3 |  | BH106 sand bag removal and preparation for SI
Thu (09/06) | 09 Jun 2022 | Zone 3 |  | No activity of other contractor on both bounds
Thu (09/06) | 09 Jun 2022 | Zone 4 | LA towards TPE | Only Hi-tech working here
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | Soil disposal works
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | SP(05) Pre-boring works in progress
Thu (09/06) | 09 Jun 2022 | ULT2 |  | At 2.15pm, SP(01) toe level confirmed at 26.70m from TOC. Concrete ordered
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | 1st lorry for SP(01) arrived on 4.04pm
Thu (09/06) | 09 Jun 2022 | DO for SP | 01 | Total volume 14m^3, Grade 40
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | SP(01) Casting started at 4.14pm
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | Last Lorry for SP(01) arrived. Casting ongoing
Thu (09/06) | 09 Jun 2022 | ULT2 |  | At 5.43pm, SP(05) toe level confirmed at 26.4m from TOC. Concrete ordered
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | Soil Levelling and removal in progress
Thu (09/06) | 09 Jun 2022 | ULT-2 |  | Continue boring works for SP(01)
Fri (10/06) | 10 Jun 2022 | Zone 2 |  | DE 143 boring at Southbound for inclinometer installation
Fri (10/06) | 10 Jun 2022 | Zone 3 |  | No activity by other contractor
Fri (10/06) | 10 Jun 2022 | BH-106 |  | Drilling / SPT ongoing ~12m depth
Fri (10/06) | 10 Jun 2022 | BH-78 |  | Hand auger continue
Fri (10/06) | 10 Jun 2022 | BH-82 |  | Continue trial trench work ~1m depth
Fri (10/06) | 10 Jun 2022 | Zone 4 LA trial trench |  | Lane closed but no work yet
Fri (10/06) | 10 Jun 2022 | BH-106 |  | SPT(6), reached 14m depth
Fri (10/06) | 10 Jun 2022 | BH-78 |  | Hand auger works completed, no obstruction
Fri (10/06) | 10 Jun 2022 | ULT1 & 11 |  | HSL excavator mobbing in at 4.00pm today. 70ton crane mobbing in on Tuesday
Fri (10/06) | 10 Jun 2022 | ULT-2 |  | Shifting of BG-36 for leveling works at the test pile zone
Fri (10/06) | 10 Jun 2022 | ULT2 |  | Hardcore delivery
Fri (10/06) | 10 Jun 2022 | Zone 2 |  | DE143 afternoon also working at Southbound
Fri (10/06) | 10 Jun 2022 | ULT 1&11 |  | Hardcore levelling
Fri (10/06) | 10 Jun 2022 | Zone 2 LA LP151 |  | Repair work preparation in progress
Fri (10/06) | 10 Jun 2022 | ULT 2 |  | Hardcore levelling
Fri (10/06) | 10 Jun 2022 | ULT 2 |  | Boring accessories demobing from site
Fri (10/06) | 10 Jun 2022 | ULT 2 |  | Top soil removal and disposal. Today target to clear top soil and start hardcore laying
Fri (10/06) | 10 Jun 2022 | Zone 4 LA to CV |  | No activity from other contractor
Sat (11/06) | 11 Jun 2022 | BH-81 |  | Manual trial trenching work ongoing
Sat (11/06) | 11 Jun 2022 | BH-78 |  | SPT(8), reached 18m depth
Sat (11/06) | 11 Jun 2022 | Zone 4 |  | Trial trench works in progress at center median and side table
Sat (11/06) | 11 Jun 2022 | Zone 4 |  | No activity by other contractor
Sat (11/06) | 11 Jun 2022 | Zone 2 |  | No activity by other contractor except DE143 doing instrumentation installation works beside LP181
Sat (11/06) | 11 Jun 2022 | ULT1/11 |  | Pending mobilization of steel plates
Sat (11/06) | 11 Jun 2022 | ULT-1/11 |  | Pasting of Signages, certifications for excavator and doing check for excavator
Sat (11/06) | 11 Jun 2022 | PD office | level1 | Plumbing works
Sat (11/06) | 11 Jun 2022 | PD office | level 2 | Current status
Sat (11/06) | 11 Jun 2022 | Zone 2 |  | DE143 working within their boundary
Sat (11/06) | 11 Jun 2022 | Zone 1 |  | No activity of other contractor
Sat (11/06) | 11 Jun 2022 | ULT-2 |  | Continue of Leveling and surveying works
Sat (11/06) | 11 Jun 2022 | Zone 2 LA Bet. LP149-LP151 |  | Repair work in progress
Sat (11/06) | 11 Jun 2022 | Zone 3 |  | Trench excavation and preparation in progress for SPPG to confirm the 66kV before spiking. Monday SPPG will come down to confirm and spiking will be on Tuesday
Sat (11/06) | 11 Jun 2022 | BH-78 |  | Drilling in progress, current depth - 21m. Encountered rock at depth 20.4m
Sat (11/06) | 11 Jun 2022 | BH-81 |  | Continue of Manual trial trenching, current depth 1.2m
Sat (11/06) | 11 Jun 2022 | PD office | Lvl2 | Ceiling works
Sat (11/06) | 11 Jun 2022 | PD office | Lvl1 | Continue of plumbing works
Sat (11/06) | 11 Jun 2022 | PD office | Lvl1 | Partition works installation
Sat (11/06) | 11 Jun 2022 | ULT1/11 |  | Steel plates laying works
Sat (11/06) | 11 Jun 2022 | ULT-2 |  | Hardcore laying completed
Sat (11/06) | 11 Jun 2022 | ULT-2 |  | Shelter making - HSL office container
Sat (11/06) | 11 Jun 2022 | BH-106 |  | SI completed, current depth - 32m, SPT(15). Pending WH concurrence for termination depth
Sat (11/06) | 11 Jun 2022 | ULT-2 |  | Leveling works in progress for kentledge set up
Sat (11/06) | 11 Jun 2022 | Zone 3 |  | No activity by other contractor
Sat (11/06) | 11 Jun 2022 | BH-106 |  | SPT(10), reached 22m depth
Mon (13/06) | 13 Jun 2022 | ULT-2 |  | Plate bearing test Cycle 1 started
Mon (13/06) | 13 Jun 2022 | Zone 1 ATT23-2 |  | Trial trench in progress . Already exposed LV. Expected services to here include singtel and M1
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | ULT 1 & 11 steel plate laying for machinery access delivery
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | PD office level 2 ceiling rod installation continue
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | PD office level 1 c-purlins installation for partition wall + plumbing works
Mon (13/06) | 13 Jun 2022 | Zone 2 South bound i front of PD office |  | Road team doing maintenance work
Mon (13/06) | 13 Jun 2022 | Zone 2 SB between LP 175-181 |  | DE143 hoarding erection
Mon (13/06) | 13 Jun 2022 | ULT 1 & 11 |  | 5 nos. of settlement markers to be installed by 17 June (3 days before 20 June ULT1 boring)
Mon (13/06) | 13 Jun 2022 | ULT-2 |  | 2nd cycle loading at 300%
Mon (13/06) | 13 Jun 2022 | ULT-2 |  | Unloading of steel mat
Mon (13/06) | 13 Jun 2022 | ULT 2 |  | Today plan to conduct plate bearing test. Tomorrow to start delivery of main and secondary beam for kentledge test
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | DE143 working inside their boundary
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | DE143 working at southbound for instrumentation work
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | PD office level 1 setting out for partition installation
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | PD office level 2, installation of ceiling hanger rod
Mon (13/06) | 13 Jun 2022 | Zone 2 |  | ULT 1 &11 platform preparation works. Today PE will check the area for COS issuance
Tue (14/06) | 14 Jun 2022 | Zone 2 SB |  | DE143 installing barricade
Tue (14/06) | 14 Jun 2022 | Level 1 status |  | Continue runner / partition installation
Tue (14/06) | 14 Jun 2022 | Zone 1 LP201 | ATT23-2 | Manual excavation ongoing
Tue (14/06) | 14 Jun 2022 | Zone 1 | PD Office | Lane marking ongoing by road contractor
Tue (14/06) | 14 Jun 2022 | ULT 2 |  | Delivery of main and secondary beams
Tue (14/06) | 14 Jun 2022 | ULT 2 |  | Today plan to deliver and set up steel leg frame
Tue (14/06) | 14 Jun 2022 | Zone 2 |  | DE 143 working with in their boundary
Tue (14/06) | 14 Jun 2022 | Zone 2 |  | DE143 working at SB between LP 175-181 for hoarding installation
Tue (14/06) | 14 Jun 2022 | Zone 1 |  | No other activity by other contractor
Tue (14/06) | 14 Jun 2022 | Zone 1 | to TPE | Hi-tech preparation work
Wed (15/06) | 15 Jun 2022 | Zone 1 |  | Trial trench for ATT46-2 near LP 200 manual excavation in progress
Wed (15/06) | 15 Jun 2022 | Zone 1 |  | No other contractor working inside our boundary
Wed (15/06) | 15 Jun 2022 | BH-105 |  | SI drilling in progress. Current depth - 26.45m (SPT-12)
Wed (15/06) | 15 Jun 2022 | Zone 2 |  | No activity for other contractor
Wed (15/06) | 15 Jun 2022 | Zone 3 |  | No activity by other contractor
Wed (15/06) | 15 Jun 2022 | PD office level 1 |  | Plumbing works
Wed (15/06) | 15 Jun 2022 | PD office level 2 |  | Installation of ceiling grid
Wed (15/06) | 15 Jun 2022 | ULT 2 |  | Steel plate delivery
Wed (15/06) | 15 Jun 2022 | Zone 4 |  | Premix compaction work ongoing for trial trench
Wed (15/06) | 15 Jun 2022 | Zone 4 | to CV | No activity by other contractor
Wed (15/06) | 15 Jun 2022 | Zone 4 | to TPE | Only hi-tech working here
Wed (15/06) | 15 Jun 2022 | ULT2 |  | RTO checking setting for kentledge test
Wed (15/06) | 15 Jun 2022 | ULT 2 |  | Secondary beam delivery and installation. 10/20 on site
Wed (15/06) | 15 Jun 2022 | BG 36 |  | Plan to dismantle kelly bar, mast and rotary head. Night time to shift at ULT1 and 11
Wed (15/06) | 15 Jun 2022 | Zone 2 Loyang Ave LP151 to TPE |  | Hi-tech commence TT repair work, TMA provided
Thu (16/06) | 16 Jun 2022 | ULT 2 |  | Taking initial reading for settlement marker. Total 10 points
Thu (16/06) | 16 Jun 2022 | Zone 3 SI works |  | BH 105 drilling in progress. Current depth 32m
Thu (16/06) | 16 Jun 2022 | Zone 3 |  | BH 82 Rig 2 drilling in progress. Current depth at 28m
Thu (16/06) | 16 Jun 2022 | Zone 3 |  | No activity of other contractor on both bounds
Thu (16/06) | 16 Jun 2022 | Zone 4 Southbound |  | ATT36-3 premix removal for trial trench
Thu (16/06) | 16 Jun 2022 | Zone 4 Southbound |  | ATT21-1 premix removal for Trial Trench
Thu (16/06) | 16 Jun 2022 | Zone 4 | to CV | No activity by other contractor
Thu (16/06) | 16 Jun 2022 | Zone 4 | to TPE | Hi-tech working here
Thu (16/06) | 16 Jun 2022 | ULT2 |  | Steel plate stacking in progress for layers 1-15, 7 sets
Thu (16/06) | 16 Jun 2022 | ULT 2 |  | BG 36 boom down for dismantling of mast (2nd layer)
Thu (16/06) | 16 Jun 2022 | BH-105 |  | SPT completed, preparing to shift to BH-104. BH-104: hand auger completed
Thu (16/06) | 16 Jun 2022 | BH-82 |  | SPT completed, pending to shift to BH-81
Thu (16/06) | 16 Jun 2022 | BH-81 |  | Hand augering ongoing
Thu (16/06) | 16 Jun 2022 | BH-83 |  | Trial trench completed, pending hand augering
Thu (16/06) | 16 Jun 2022 | ULT-2 |  | Continue steel plate laying
Thu (16/06) | 16 Jun 2022 | PD Office | level 1 | Wall plastering work ongoing
Thu (16/06) | 16 Jun 2022 | PD Office | Level 2 | Setting up wall partitions ongoing
Fri (17/06) | 17 Jun 2022 | Zone 2 |  | DE143 working in their boundary. They are clearing unsuitable backfilled soil at sidetable
Fri (17/06) | 17 Jun 2022 | Zone 2 |  | No activity of other contractor
Fri (17/06) | 17 Jun 2022 | Zone 3 |  | BH 184 near LP 154 manual excavation for trial trench in progress
Fri (17/06) | 17 Jun 2022 | ULT-2 |  | Steel plate delivery
Fri (17/06) | 17 Jun 2022 | Zone 1 |  | ATT 23-1 premix hacking for trial trench in progress
Fri (17/06) | 17 Jun 2022 | ULT-2 |  | Demob of BG parts to ULT1/11
Fri (17/06) | 17 Jun 2022 | ULT1&11 |  | Works stopped for the night
Fri (17/06) | 17 Jun 2022 | PD Office | level 2 | Wall partitions setting up ongoing
Fri (17/06) | 17 Jun 2022 | ULT-2 |  | Steel plate delivery / unloading ongoing
Fri (17/06) | 17 Jun 2022 | ULT1& 2 |  | Adjusting machine parking location for counter weight installation
Sun (19/06) | 19 Jun 2022 | Zone 1 |  | No other contractor working in our boundary
Sun (19/06) | 19 Jun 2022 | PD office level 1 |  | Electrical works in progress, cable pulling
Sun (19/06) | 19 Jun 2022 | PD office level 1 |  | Wall partition painting in progress
Sun (19/06) | 19 Jun 2022 | PD office level 2 |  | Wall partition installation in progress. 70% completed
Sun (19/06) | 19 Jun 2022 | Zone 3 |  | No activity of other contractor
Sun (19/06) | 19 Jun 2022 | Zone 4 |  | No other contractor working in our boundary
Sun (19/06) | 19 Jun 2022 | ULT 2 |  | Steel plate stacking for layers 1-15 continue. Current at 8th layer
Sun (19/06) | 19 Jun 2022 | PD office level 1 |  | Cable pulling continue
Sun (19/06) | 19 Jun 2022 | PD office level 1 |  | Painting works continue
Sun (19/06) | 19 Jun 2022 | PD office level 2 |  | Partition wall rockwool installation
Sun (19/06) | 19 Jun 2022 | ULT 2 |  | Steel plate stacking contine for layers 1-15. Current at 8th-10th layer
Sun (19/06) | 19 Jun 2022 | ULT 2 |  | Stopped work for the day. Cape Engineering at PD office work until 5pm only
Sun (19/06) | 19 Jun 2022 | ULT 2 |  | Steel plater Layer 1-15 stacking in progress
Sun (19/06) | 19 Jun 2022 | Zone 2 |  | DE143 working inside their boundary
Sun (19/06) | 19 Jun 2022 | Zone 2 |  | No other contractor working in our boundary
Mon (20/06) | 20 Jun 2022 | Zone 4 |  | No activity of other contractor
Mon (20/06) | 20 Jun 2022 | Zone 3 along loyang avenue |  | Lane closure for delivery of 3rd rig for SI works
Mon (20/06) | 20 Jun 2022 | ULT 2 |  | Steel plate delivery
Mon (20/06) | 20 Jun 2022 | ULT 2 |  | Stacking of stell plate for layers 1-15. Current at 10th-12th layer
Mon (20/06) | 20 Jun 2022 | Zone 3 |  | Road repair works between LP 149-151
Mon (20/06) | 20 Jun 2022 | ZpneZone 3 |  | BH 104 Standard penetration test at 32m depth
Mon (20/06) | 20 Jun 2022 | Zone 3 |  | BH 81 drilling. Current depth at 31m
Mon (20/06) | 20 Jun 2022 | Zone 4 |  | ATT20-1 trial trench completed. Now preparing to backfill and lay premix
Tue (21/06) | 21 Jun 2022 | Zone 4 |  | ATT 20-2 between LP 113-115 premix cutting for trial trench in progress
Tue (21/06) | 21 Jun 2022 | Zone 4 |  | No activity of other contractor
Tue (21/06) | 21 Jun 2022 | Zone 3 |  | BH 107 hand augering in progress
Tue (21/06) | 21 Jun 2022 | ULT-2 |  | Unloading of steel plates in progress
Tue (21/06) | 21 Jun 2022 | BH-184 | Beside LP154 | Hand augering in progress. As of now, 0.7m/1.5m completed
Tue (21/06) | 21 Jun 2022 | BH-187 |  | Continue of manual trial trench. As of now 0.8m/1.5m completed
Tue (21/06) | 21 Jun 2022 | BH-83 |  | Commenced drilling. Current depth - 8.45m, SPT(3)
Tue (21/06) | 21 Jun 2022 | Zone 3 BH-107 |  | Drilling commenced. Current depth 4.45m, SPT (01)
Tue (21/06) | 21 Jun 2022 | ULT 2 |  | Steel plate stacking status. Layers 1-15 (190/210 pcs completed)
Tue (21/06) | 21 Jun 2022 | Trial Trench | Zone 4 | Road premix compaction in progress
Tue (21/06) | 21 Jun 2022 | Zone 4 |  | Lane open
Tue (21/06) | 21 Jun 2022 | ULT1&11 |  | Minor work / housekeeping ongoing
Tue (21/06) | 21 Jun 2022 | BH 104 |  | Depth terminated at 33.36m. Preparation for grouting works
Tue (21/06) | 21 Jun 2022 | Zone 3 |  | No activity of other contractor
Tue (21/06) | 21 Jun 2022 | Zone 3 |  | BH 81 grouting in progress
Tue (21/06) | 21 Jun 2022 | Zone 3 |  | BH 83 hand augering completed. They will shift here for drilling once BH 81 grouting complete
Wed (22/06) | 22 Jun 2022 | PD office level 1 |  | Calcium board installation for partition wall in progress
Wed (22/06) | 22 Jun 2022 | PD office level 1 |  | Wall painting in progress (2nd coat)
Wed (22/06) | 22 Jun 2022 | Zone 2 |  | DE143 working within their boundary
Wed (22/06) | 22 Jun 2022 | Zone 2 |  | No activity of other contractor
Wed (22/06) | 22 Jun 2022 | PD office level 1 |  | WH & Cape arranging to install more lights at corridor and working area
Wed (22/06) | 22 Jun 2022 | Zone 3 |  | No activity by other contractor
Wed (22/06) | 22 Jun 2022 | Zone 3 | BH-107 | Drilling ongoing, 14m depth
Wed (22/06) | 22 Jun 2022 | PD office level 2 |  | Wall partition putty application in progress
Wed (22/06) | 22 Jun 2022 | BH-83 |  | Drilling work ongoing, 16m depth
Wed (22/06) | 22 Jun 2022 | ULT1&11 |  | Desander set up in progress
Wed (22/06) | 22 Jun 2022 | Zone 4 |  | No activity of other contractor
Wed (22/06) | 22 Jun 2022 | Zone 1 |  | Road contractor working just outside our boundary
Wed (22/06) | 22 Jun 2022 | Zone 4 ATT17-6 |  | Road premix hacking in progress
Wed (22/06) | 22 Jun 2022 | Dear All Site office genset monthly maintenance today 11 |  | 30am to 12:15pm, so during this period power down in office, sorry for inconvenience, Thanks
Wed (22/06) | 22 Jun 2022 | Zone 2 |  | ATT 44-2 near LP 192 premix hacking for Trial trench
Wed (22/06) | 22 Jun 2022 | BH-83 |  | Current Depth 16.45m
Wed (22/06) | 22 Jun 2022 | ULT 1 & 11 |  | Hardcore removal for trial trench
Wed (22/06) | 22 Jun 2022 | ULT 1 |  | Trial trench manual excavation
Wed (22/06) | 22 Jun 2022 | ULT1&11 |  | Plant set up continue. Today to deliver blockwall for bundwall installation
Wed (22/06) | 22 Jun 2022 | PD office level 1 |  | Calcium board installation continue for partition wall
Wed (22/06) | 22 Jun 2022 | ULT 1 trial trench |  | Concrete slab found at 600mm depth. HSL informed WHDGJV
Wed (22/06) | 22 Jun 2022 | BH-184 |  | 3rd SI rig breakdown
Wed (22/06) | 22 Jun 2022 | ULT 11 |  | Hardcore removal for trial trench
Wed (22/06) | 22 Jun 2022 | BH-184 |  | Drilling commenced
Wed (22/06) | 22 Jun 2022 | ULT 11 |  | Trial trench no services found
Wed (22/06) | 22 Jun 2022 | PD office works continue till 9 |  | 30pm
Wed (22/06) | 22 Jun 2022 | ULT 2 |  | Steel plate stacking started for the day
Thu (23/06) | 23 Jun 2022 | ULT1 |  | Concrete slab was abandoned and burried in ground. Further excavated until 2.4m and no services found. FYI
Thu (23/06) | 23 Jun 2022 | Gate 5 sump 2 |  | Water level status. Pumping continues
Thu (23/06) | 23 Jun 2022 | ULT 2 |  | Steel plate stacking resume. Layers 23-24
Thu (23/06) | 23 Jun 2022 | BH 184 |  | Drilling continue. Current depth 22m
Thu (23/06) | 23 Jun 2022 | BH 181 |  | Trial trench in progress. Current depth 1.3m
Thu (23/06) | 23 Jun 2022 | ATT08-1 |  | Reinstatement completed, lane reopened
Thu (23/06) | 23 Jun 2022 | ULT-2 |  | Steel plate stacking ongoing. Layers 28-29
Thu (23/06) | 23 Jun 2022 | PD office | level 2 | Wall painting, partition erection ongoing
Thu (23/06) | 23 Jun 2022 | PD office | level 1 | Internal staircase erection in progress
Thu (23/06) | 23 Jun 2022 | ULT1&11 |  | Desander noise barrier installation done, barricade / access erection ongoing
Thu (23/06) | 23 Jun 2022 | ULT 2 |  | Steel plate stacking contine. Current at 23rd layer
Thu (23/06) | 23 Jun 2022 | Zone 3 |  | BH 107 SPT at 30m
Thu (23/06) | 23 Jun 2022 | BH 83 |  | Drilling continue. Depth at 31m
Thu (23/06) | 23 Jun 2022 | Zone 3 |  | No activity of other contractor
Fri (24/06) | 24 Jun 2022 | Zone 1 |  | Other contractor lane closure with in our boundary. Their work area just outside our boundary
Fri (24/06) | 24 Jun 2022 | Zone 1 |  | Bridge to junction towards CV no activity of other contractor
Fri (24/06) | 24 Jun 2022 | BH 181 |  | Trial trench manual excavation reached 1.5m
Fri (24/06) | 24 Jun 2022 | BH 184 |  | Coring in progress to 30m depth
Fri (24/06) | 24 Jun 2022 | ULT 2 |  | Steel plate stacking completed until 30 layer. 31st layer in progress
Fri (24/06) | 24 Jun 2022 | BH-55 |  | Continue manual trial trench. Current depth 1.2m
Fri (24/06) | 24 Jun 2022 | BH-80 |  | Drilling in progress. Current depth 12m, SPT (5)
Fri (24/06) | 24 Jun 2022 | ULT-2 |  | Layer 34 stacking in progress
Fri (24/06) | 24 Jun 2022 | ULT1&11 |  | Stopped for the night
Fri (24/06) | 24 Jun 2022 | ULT 2 |  | Stacking in progress for layers 27-29
Sat (25/06) | 25 Jun 2022 | Zone 1 towards CV |  | Hi-Tech preparation for trial trench works
Sun (26/06) | 26 Jun 2022 | Zone 2 |  | DE143 working inside their boundary
Sun (26/06) | 26 Jun 2022 | Zone 1 |  | No activity of other contractor
Sun (26/06) | 26 Jun 2022 | ULT1 rebar cage |  | Jack welding in progress
Sun (26/06) | 26 Jun 2022 | ULT1 |  | Rebar cage strain gauges installation
Sun (26/06) | 26 Jun 2022 | PD office level 1 |  | Partition wall putty application
Sun (26/06) | 26 Jun 2022 | PD office level 2 |  | Toilet waterproofing works
Sun (26/06) | 26 Jun 2022 | Level 2 |  | Ceiling panel installation
Sun (26/06) | 26 Jun 2022 | Level 2 |  | Electrical works. Lighting panel installation
Sun (26/06) | 26 Jun 2022 | Level 2 |  | Door frame and panel installation
Sun (26/06) | 26 Jun 2022 | Zone 3 |  | BH 56 trial trench in progress. Current depth 1.3m
Sun (26/06) | 26 Jun 2022 | Zone 3 |  | No activity of other contractor
Sun (26/06) | 26 Jun 2022 | ULT 2 |  | Reference frame installation continue
Sun (26/06) | 26 Jun 2022 | Zone 3 |  | Housekeeping by DG
Sun (26/06) | 26 Jun 2022 | ULT1&11 |  | Spacer block casting using G50
Sun (26/06) | 26 Jun 2022 | ULT1 rebar cage |  | Installation of strain gauges continue. Total 42 pcs
Sun (26/06) | 26 Jun 2022 | ULT1 rebar cage |  | Lifting point welding
Sun (26/06) | 26 Jun 2022 | Level 1 |  | Electrical panel box installation
Sun (26/06) | 26 Jun 2022 | PD office level 1 |  | Ceiling panel installation continue
Sun (26/06) | 26 Jun 2022 | PD office level 2 |  | Door ironmongery installation
Sun (26/06) | 26 Jun 2022 | ULT1&11 |  | Bundwall gap filling
Sun (26/06) | 26 Jun 2022 | Zone 3 |  | BH 56 hand augering in progress. They will stop work at 5pm
Sun (26/06) | 26 Jun 2022 | Gate 5 beside site office |  | Construction of storage area
Sun (26/06) | 26 Jun 2022 | ULT2 |  | Today no steel plate delivery and stacking. All available steel plate on site stacked yesterday
Sun (26/06) | 26 Jun 2022 | ULT2 |  | Reference frame installation in progress for dial guage
Sun (26/06) | 26 Jun 2022 | Zone 2 |  | No activity of other contractor
Mon (27/06) | 27 Jun 2022 | Arrangement for 28 June - ULT 1 works duty |  | Aldrin - 8.30am to 8pm, Saw - 8pm to 8.30am, For the next ULT 11 & kentledge duty will advise again
Tue (28/06) | 28 Jun 2022 | Zone 1 | towards CV | No activity by other contractor
Tue (28/06) | 28 Jun 2022 | Zone 1 | towards TPE | DE143 working here
Tue (28/06) | 28 Jun 2022 | Zone 1 | ATT22-1 | Excavation ongoing
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Centrifugal pump installation for desanding
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Rebar cage inspection by QPS
Tue (28/06) | 28 Jun 2022 | ULT 1 |  | Desanding completed. Koden test in progress
Tue (28/06) | 28 Jun 2022 | ULt1 |  | Koden test completed. X-axis maximum inclination 100mm. Y-axis maximum inclination 30mm. Allowable 360mm
Tue (28/06) | 28 Jun 2022 | ULT-2 |  | Current status
Tue (28/06) | 28 Jun 2022 | ULT 1 |  | Bentonite and sand content check prior to lowering of rebar cage. All results within range
Tue (28/06) | 28 Jun 2022 | ULt1 |  | Rebar cage cutting of excess length prior to lifting. Ambi now here to supervise lifting
Tue (28/06) | 28 Jun 2022 | ULt1 |  | Instrumentation verification by RTO
Tue (28/06) | 28 Jun 2022 | BH-79 |  | Hand augering in progress
Tue (28/06) | 28 Jun 2022 | ULt1 |  | Bottom cage preparation for lifting
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Bottom cage lowering
Tue (28/06) | 28 Jun 2022 | ULT-2 |  | Steel plate unloading in progress
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Middle cage lowering and lapping in progress
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Rebar cage lapping joint cannot install U-clip because of congested rebar. Instead they will do welding
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Strain guages initial reading
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Instrumentation connection completed at lapping area. Welding in progress
Tue (28/06) | 28 Jun 2022 | ULT-2 |  | Continue loading of steel plates in progress. Will update the progress status once work completed at 10PM tonight
Tue (28/06) | 28 Jun 2022 | ULT2 |  | Steel plate stacking for layers 49-50
Tue (28/06) | 28 Jun 2022 | Zone 2 |  | No work of other contractor
Tue (28/06) | 28 Jun 2022 | ULT1 |  | Steel plate arrangement to shift BG and area preparation for bunk wall construction for desanding
Tue (28/06) | 28 Jun 2022 | ULT1 rebar cages |  | Installation of grouting pipe and inclinometer in progress. Target to start lifting after lunch
Tue (28/06) | 28 Jun 2022 | PD Office | level 1 | Floor tiling / wiring work ongoing
Tue (28/06) | 28 Jun 2022 | PD Office | level 1 toilet | Wall tile installation ongoing
Wed (29/06) | 29 Jun 2022 | Zone 2 |  | DE143 working in their boundary
Wed (29/06) | 29 Jun 2022 | Zone 2 |  | No activity by other contractor
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | ACU Copper tube connection
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | Electrical works cable pulling
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | Toilet area floor tiling works
Wed (29/06) | 29 Jun 2022 | PD office level 2 |  | Odd size ceiling panel installation
Wed (29/06) | 29 Jun 2022 | Zone 1 |  | ATT03-2 hacking work for trial trench
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | Steel plate stacking resume
Wed (29/06) | 29 Jun 2022 | Zone 1 |  | Lane closure by other contractor within our boundary. Their work area just outside our boundary
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | Calibration certs for all equipment done, pending IM / survey
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | Steel plate stacking in progress
Wed (29/06) | 29 Jun 2022 | 739/776 pieces stacked as of 3 |  | 30pm
Wed (29/06) | 29 Jun 2022 | BH 79 |  | Hit rock at 21.8m. WHDA to shift rig to BH 55 after BH 79 completion
Wed (29/06) | 29 Jun 2022 | ATT16-3 |  | Premix completed, lane reopened
Wed (29/06) | 29 Jun 2022 | Pd office level 1 |  | Light panel assembly for installation
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | Cable pulling
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | Door frame and panel installation
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | Toilet floor tile installation
Wed (29/06) | 29 Jun 2022 | PD office level 1 |  | Adhesive application for floor vinyl tile
Wed (29/06) | 29 Jun 2022 | PD office level 2 |  | Painting works
Wed (29/06) | 29 Jun 2022 | FYI 6 |  | 30pm to 7:00pm power shutdown for new genset connection, because need to connect power to new genset for night shift
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | 759/776 steel plates stacked as of now, target to complete stacking by 6.30pm. Testing target to start at 7pm
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | Last plate stacked
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | Cycle 1 started at 25%, 282.5T at 7.30pm
Wed (29/06) | 29 Jun 2022 | ULT-2 |  | Waiting for day shift team to start, they are currently at ULT1 doing housekeeping (they went to take over the night shift team)
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Area preparation prior to boring. Plan to start pre-boring after lunch. Steel casing on the way to site
Thu (30/06) | 30 Jun 2022 | Zone 3 | to TPE | No activity by other contractor
Thu (30/06) | 30 Jun 2022 | Zone 3 | to CV | Only DG & Hi-tech working
Thu (30/06) | 30 Jun 2022 | BH-79 |  | Coring till 29m done, casing removal
Thu (30/06) | 30 Jun 2022 | ULT 11 |  | Rebar cage installation of instruments and welding of cage lifting point
Thu (30/06) | 30 Jun 2022 | Zone 4 | ATT16-5 | Preparing to remove premix
Thu (30/06) | 30 Jun 2022 | Zone 4 |  | Lamp post contractor working on the slow lane
Thu (30/06) | 30 Jun 2022 | PD office level 1 |  | Slab floor joint cement application
Thu (30/06) | 30 Jun 2022 | Level 1 |  | Toilet floor tile installation
Thu (30/06) | 30 Jun 2022 | PD office level 2 |  | Door panel installation
Thu (30/06) | 30 Jun 2022 | Level 2 |  | Indoor ACU installation
Thu (30/06) | 30 Jun 2022 | Level 2 |  | Housekeeping prior to carpet tile installation
Thu (30/06) | 30 Jun 2022 | Level 2 |  | Indoor ACU installation
Thu (30/06) | 30 Jun 2022 | Level 2 |  | Painting works
Thu (30/06) | 30 Jun 2022 | Level 2 staircase canopy |  | Height adjusting to 2.1m
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Steel casing on site. Unloading
Thu (30/06) | 30 Jun 2022 | Zone 1 |  | ATT03-3 premix hacking for trial trench
Thu (30/06) | 30 Jun 2022 | Zone 1 |  | Lane closure by other contractor towards TPE for tree pruning
Thu (30/06) | 30 Jun 2022 | ULT1&11 |  | 4.5m height gantry, frame installation in progress
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Borig rig casit bit for 1.3m installed
Thu (30/06) | 30 Jun 2022 | Zone 1 |  | ATT 3-3 trial trench completed. Only LV found below. Now waiting for premix
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Pre boring started
Thu (30/06) | 30 Jun 2022 | Zone 4 | ATT16-5 | Reinstatement work ongoing
Thu (30/06) | 30 Jun 2022 | Pd office level 1 |  | Lighting panel installation
Thu (30/06) | 30 Jun 2022 | PD office level 1 |  | Toilet floor tile installation continue
Thu (30/06) | 30 Jun 2022 | PD office level 1 |  | Adhesive application for vinyl tile installation
Thu (30/06) | 30 Jun 2022 | PD office level 2 |  | Carpet installation status
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Lowering of steel casing (part 1/2, 5.5/8.5m)
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Steel casing extraction for realignment
Thu (30/06) | 30 Jun 2022 | BH-79 |  | Works completed, prepare to shift rig to BH-55 tmr afternoon
Thu (30/06) | 30 Jun 2022 | Zone 4 |  | Reinstatement work completed, all lanes opened
Thu (30/06) | 30 Jun 2022 | BH-57 |  | Trial trench in progress, 1m depth
Thu (30/06) | 30 Jun 2022 | ULT11 |  | Steel casing 8.5m fully installed
Thu (30/06) | 30 Jun 2022 | Recorded settlement from 5 |  | 30-6:30 pm is 0.03mm < 0.25mm acceptable rate of settlement per hour
Thu (30/06) | 30 Jun 2022 | ULT2 |  | Taking reading for last hour of cycle 2 loading at 100%. Next loading 125% at 1412.5 tonnes
Thu (30/06) | 30 Jun 2022 | ULT2 |  | 2nd cycle loading to 125% ~1412.5 tonnes
Thu (30/06) | 30 Jun 2022 | Zone 3 |  | BH187 coring continue. Current depth at 33m
Thu (30/06) | 30 Jun 2022 | Zone 3 |  | No activity of other contractor
Thu (30/06) | 30 Jun 2022 | Zone 2 |  | DE143 working inside their boundary
Thu (30/06) | 30 Jun 2022 | Zone 4 |  | No activity by other contractor
Thu (30/06) | 30 Jun 2022 | Zone 1 |  | Lane closure towards TPE for trial trench
Thu (30/06) | 30 Jun 2022 | ULT1&11 |  | 4.5m height gantry material on site
Fri (01/07) | 01 Jul 2022 | Zone 2 |  | No activity of other contractor
Fri (01/07) | 01 Jul 2022 | ULT11 |  | Boring works in progress. Current depth at 16m from TOC
Fri (01/07) | 01 Jul 2022 | ULT11 rebar cages |  | Installation of strain guages (28/36) and inclinometer (1/2) continue
Fri (01/07) | 01 Jul 2022 | ULT11 |  | Top cage and middle cage now lapping. Left with 1 lapping for bottom and middle cage during lowering of cage
Fri (01/07) | 01 Jul 2022 | PD office level 1 |  | Floor vinyl tile installation continue 50% completed
Fri (01/07) | 01 Jul 2022 | PD office level 1 |  | Toilet floor tile pointing works in progress
Fri (01/07) | 01 Jul 2022 | PD office level 2 |  | Carpet installation continue. 45% completed
Fri (01/07) | 01 Jul 2022 | PD office level 2 |  | Toilet water ponding test for 24 hours. Tomorrow to check if have leakage
Fri (01/07) | 01 Jul 2022 | Zone 1 |  | Lane closure by Hi tech for trial trench work. No activity of other contractor
Fri (01/07) | 01 Jul 2022 | ULT-2 |  | Holding at 225% load
Fri (01/07) | 01 Jul 2022 | ULT11 |  | Depth reached at 23m. Now changing to cleaning bucket and confirm actual depth
Fri (01/07) | 01 Jul 2022 | ULT11 |  | TOC level: 26.87 mSHD, : toe level: 3.30 mSHD, Current depth on site at 23m. Balance 570mm to bore
Fri (01/07) | 01 Jul 2022 | ULT11 |  | Desanding on going
Fri (01/07) | 01 Jul 2022 | ULT-2 |  | Holding at 250%, preparing to load to 275% (3107.5tonnes)
Fri (01/07) | 01 Jul 2022 | ULT-2 |  | Loading to 275% (3107.5 tonnes)
Fri (01/07) | 01 Jul 2022 | ULT11 |  | Rebar cage and instrument inspection
Fri (01/07) | 01 Jul 2022 | PD office level 1 |  | Floor hacking for SSO
Fri (01/07) | 01 Jul 2022 | PD office level 1 |  | Toilet cubicle framing installation
Fri (01/07) | 01 Jul 2022 | PD office level 2 |  | Installation of ceiling panel continue
Fri (01/07) | 01 Jul 2022 | PD office level 2 |  | Door frame seal installation
Fri (01/07) | 01 Jul 2022 | PD office level 2 |  | Floor carpet installation status. 70% completed
Fri (01/07) | 01 Jul 2022 | Settlement as at 0220hrs within range |  | 0.03mm < 0.25mm/hr
Fri (01/07) | 01 Jul 2022 | ULT2 |  | 3rd cylce at 300% loading settlement at 0.025mm<0.25mm/hr. Next loading to jack up to 325% at 3672.5 tonnes
Fri (01/07) | 01 Jul 2022 | ULT 11 |  | Toe confirmed at depth of 23.65m from TOC
Fri (01/07) | 01 Jul 2022 | ULT-11 |  | Lowering of rebar cage
Fri (01/07) | 01 Jul 2022 | ULT-11 |  | Rebar cage lapping ongoing
Fri (01/07) | 01 Jul 2022 | Zone 3 | to CV | Road work contractor working along slow lane
Fri (01/07) | 01 Jul 2022 | Zone 3 | To TPE | No activity by other contractor
Fri (01/07) | 01 Jul 2022 | BH-79 |  | Pending depth confirmation/termination before the rig to shift to BH-55
Fri (01/07) | 01 Jul 2022 | Zone 3 |  | BH 189 Hand augering in progress. Total depth 2.7m, balance 300mm
Sat (02/07) | 02 Jul 2022 | PD office level 1 |  | Female toilet floor tile installation in progress
Sat (02/07) | 02 Jul 2022 | PD office level 1 |  | Male toilet urinal installation
Sat (02/07) | 02 Jul 2022 | PD office level 2 |  | Carpet installation status
Sat (02/07) | 02 Jul 2022 | Zone 1 |  | Lane closure by hi-tech for trial trench work. Both bounds provided with TMA. No activity of other contractor
Sat (02/07) | 02 Jul 2022 | Zone 2 |  | No activity of other contractor
Sat (02/07) | 02 Jul 2022 | BH185 |  | Manual excavation in progress. Today BH189 no work, rig operator MC as per WH report
Sat (02/07) | 02 Jul 2022 | ULT2 |  | 3rd cylce settlement reading at 350% load
Sat (02/07) | 02 Jul 2022 | BH55 |  | Drilling continue depth at 14m
Sat (02/07) | 02 Jul 2022 | ULT2 |  | 3rd cycle 350% load settlement reading at 3pm
Sat (02/07) | 02 Jul 2022 | Zone 2 |  | Npark plant pruning, soil manure fill up and grass cutting
Sat (02/07) | 02 Jul 2022 | Zone 1 |  | ATT01-1 premix laying and compaction
Sat (02/07) | 02 Jul 2022 | Zone 1 |  | ATT01-2 premix laying and compaction
Sat (02/07) | 02 Jul 2022 | ULT1&11 |  | Kelly bar from BG 36 dismantled
Sat (02/07) | 02 Jul 2022 | ULT1&11 |  | BG36 casing bit and rotary head dismantling
Sat (02/07) | 02 Jul 2022 | PD office level 1 |  | Male toilet cubicle and urinal partition installation continue
Sat (02/07) | 02 Jul 2022 | PD office level 1 |  | Painting works
Sat (02/07) | 02 Jul 2022 | PD office level 1 |  | Female toilet tiling works
Sat (02/07) | 02 Jul 2022 | PD office level 2 |  | Male toilet wall tile installation
Sat (02/07) | 02 Jul 2022 | PD office level 2 |  | Floor carpet installation continue
Sat (02/07) | 02 Jul 2022 | ULT2 |  | Taking last reading for 3rd cycle 350% loading before releasing
Sat (02/07) | 02 Jul 2022 | ULT2 |  | Final settlement reading at 350% load is 40.32mm
Sat (02/07) | 02 Jul 2022 | ULT2 |  | Taking last reading
Sat (02/07) | 02 Jul 2022 | ULT2 |  | 3rd cylce loading at 350%. Settlement reading for 14/24 hrs at 2.4mm
Sat (02/07) | 02 Jul 2022 | Zone 3 |  | BH58 manual excavation for trial trench
Sat (02/07) | 02 Jul 2022 | BH55 |  | Drilling in progress with current depth of 3.5m
Sat (02/07) | 02 Jul 2022 | Zone 3 |  | No activity of other contractor on both bounds
Sat (02/07) | 02 Jul 2022 | Zone 4 |  | No activity of other contractor
Mon (04/07) | 04 Jul 2022 | ULT2 |  | Unloading of steel plate and demob. Lifting permit checked, in order
Mon (04/07) | 04 Jul 2022 | BH189 |  | Rig shifted and preparation to start drilling
Mon (04/07) | 04 Jul 2022 | ULT1&11 |  | BG upper mast dismantled. Today to demob. BG bod to demob on friday
Mon (04/07) | 04 Jul 2022 | BH-58 |  | Trial trench in progress, offset 500mm due to concrete slab found at 1.2m depth
Mon (04/07) | 04 Jul 2022 | ULT-2 |  | Works stopped for the night, (45pcs/776pcs demob)
Mon (04/07) | 04 Jul 2022 | ULT 1/11 |  | Works stopped for the night
Mon (04/07) | 04 Jul 2022 | PD office | level 1 | Toilet wall partition ongoing
Mon (04/07) | 04 Jul 2022 | PD office | level 1 | Floor tiling work in progress
Tue (05/07) | 05 Jul 2022 | Zone 1 |  | No activity of other contractor. Lane closure by Hi tech towards CV for trial trench work
Tue (05/07) | 05 Jul 2022 | Zone 1 |  | ATT01-3 hacking work for trial trench
Tue (05/07) | 05 Jul 2022 | Zone 1 |  | ATT02-3 hacking work for trial trench
Tue (05/07) | 05 Jul 2022 | ULT2 |  | Unloading of steel plate continue. This morning sent out 30 bundles/2 truck. Total demob from site 60/776. Unloading to ground level while waiting for truck
Tue (05/07) | 05 Jul 2022 | Zone 3 |  | Other contractor telecom cable pulling
Tue (05/07) | 05 Jul 2022 | ATT01-3 |  | HV slab found
Tue (05/07) | 05 Jul 2022 | ATT02-3 |  | HV PVC slab found
Tue (05/07) | 05 Jul 2022 | PD office level 1 |  | Internet/telephone line installation
Tue (05/07) | 05 Jul 2022 | PD office level 2 |  | Male toilet tile installation
Tue (05/07) | 05 Jul 2022 | PD office level 2 |  | Female toilet screeding
Tue (05/07) | 05 Jul 2022 | PD office level 2 |  | Window sealant application
Tue (05/07) | 05 Jul 2022 | ULT-2 |  | Continue steel plate demobilisation
Tue (05/07) | 05 Jul 2022 | ULT1/11 |  | Works stopped for the night
Tue (05/07) | 05 Jul 2022 | PD office | level 2 | Blinds installation
Tue (05/07) | 05 Jul 2022 | ULT2 |  | Steel plate unloading. Today 1st truck to move out. +15 (60/776 bundles)
Tue (05/07) | 05 Jul 2022 | ULT-2 |  | Works stopped for the night. (+45, 90pcs/776pcs)
Wed (06/07) | 06 Jul 2022 | Zone 1 |  | Netlink working at lane towards TPE for telecom cable installation
Wed (06/07) | 06 Jul 2022 | Zone 2 |  | In front of shell
Wed (06/07) | 06 Jul 2022 | Zone 1 |  | No other activity of contractor
Wed (06/07) | 06 Jul 2022 | BH-189 |  | Coring in progress, current depth 29.5m
Wed (06/07) | 06 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Wed (06/07) | 06 Jul 2022 | Zone 2 |  | ATT07 lane closure for trial trench
Wed (06/07) | 06 Jul 2022 | ULT2 |  | Steel plate unloading. 3rd truck to move out. +45 (135/776 bundles)
Wed (06/07) | 06 Jul 2022 | ULT2 |  | 6th truck loading on going. +85 pcs (175/776)
Wed (06/07) | 06 Jul 2022 | Zone 2 |  | No activity of other contractor
Wed (06/07) | 06 Jul 2022 | Zone 2 |  | ATT07-1 trial trench done. Gas pipe and HV found. Preparation to open the lane
Wed (06/07) | 06 Jul 2022 | BH 56 |  | SPT 1 at 4.0m
Wed (06/07) | 06 Jul 2022 | BH-59 |  | Trial trench ongoing, 400mm depth
Wed (06/07) | 06 Jul 2022 | ULT2 |  | 7th truck moving out
Wed (06/07) | 06 Jul 2022 | ULT2 |  | 8th truck loading
Wed (06/07) | 06 Jul 2022 | ULT-2 |  | Steel plate unloading in progress
Wed (06/07) | 06 Jul 2022 | ULT1/11 |  | Works stopped for the night
Wed (06/07) | 06 Jul 2022 | ULT-2 |  | Works stopped for the night
Thu (07/07) | 07 Jul 2022 | Loyang Way | LP 4 | Lane closure for ATT-29 with two APO deployed
Thu (07/07) | 07 Jul 2022 | ULT1&11 |  | Today plan to dismantle crawler crane and demob from site
Thu (07/07) | 07 Jul 2022 | ATT29 |  | Premix cutting started
Thu (07/07) | 07 Jul 2022 | BH-189 |  | Packer test ongoing. Current: 4th period - 10mins, 554.43kPa
Thu (07/07) | 07 Jul 2022 | PD office level 1 |  | Vinyl tile installation in progress
Thu (07/07) | 07 Jul 2022 | PD office level 1 |  | Male toilet water pipe connection
Thu (07/07) | 07 Jul 2022 | PD office level 1 |  | Painting touch up
Thu (07/07) | 07 Jul 2022 | PD office level 1 |  | Low participation wall installation status. 80% completed
Thu (07/07) | 07 Jul 2022 | PD office level 2 |  | Low wall partition installation status. 70% completed
Thu (07/07) | 07 Jul 2022 | PD office level 2 |  | Toilet tile installation continue
Thu (07/07) | 07 Jul 2022 | BH-189 |  | 1st packer test completed
Thu (07/07) | 07 Jul 2022 | ULT1 |  | Steel plate unloading and demobilization continue. 6th trip on going. +83 pcs ( 282/776)
Thu (07/07) | 07 Jul 2022 | ATT29-1 |  | Premix completed
Thu (07/07) | 07 Jul 2022 | ULT1&11 |  | Crawler crane demob
Thu (07/07) | 07 Jul 2022 | PD office level 1 |  | Balance ceiling panel installation
Thu (07/07) | 07 Jul 2022 | Pd office level 2 |  | Female toilet floor tile installation
Thu (07/07) | 07 Jul 2022 | PD office level 2 |  | Furniture assembly
Thu (07/07) | 07 Jul 2022 | ULT2 |  | First truck moved out. 2nd truck loading on going. Today WH booked 5 trucks for 2 trips total of 10 trips
Thu (07/07) | 07 Jul 2022 | Zone 2 |  | No activity of other contractor
Thu (07/07) | 07 Jul 2022 | Zone 1 |  | No activity by other contractor
Fri (08/07) | 08 Jul 2022 | Zone 1 |  | No activity by other contractor
Fri (08/07) | 08 Jul 2022 | ULT1/11 |  | Pending BG demob, will be this evening. Access preparation for BG to leave the site safely
Fri (08/07) | 08 Jul 2022 | PD office | level 1 | Furniture delivery
Fri (08/07) | 08 Jul 2022 | PD office | level 1 | Toilet wall partition installation ongoing
Fri (08/07) | 08 Jul 2022 | BH-181 |  | Hand augering ongoing, rig from BH-189 shifted
Fri (08/07) | 08 Jul 2022 | Zone 2 behind PJT office |  | Area preparation for access, tomorrow WH plan to do tree felling here
Fri (08/07) | 08 Jul 2022 | BH-60 |  | Trial trench in progress
Fri (08/07) | 08 Jul 2022 | BH-56 |  | No activity, rig breakdown
Fri (08/07) | 08 Jul 2022 | ULT2 |  | 8th truck now here. Loading in progress. This truck can only carry 10 plates
Fri (08/07) | 08 Jul 2022 | Zone 2 |  | Silo and plan set up mark on site
Fri (08/07) | 08 Jul 2022 | ULT1&11 |  | BG loading to trailer done. LTA escort to come around 11pm
Fri (08/07) | 08 Jul 2022 | PD office level 2 |  | Female toilet tile installation continue
Fri (08/07) | 08 Jul 2022 | PD office level 2 |  | Female toilet cubicle installation
Fri (08/07) | 08 Jul 2022 | PD office level 2 |  | Wall PVC cladding plastic protection removal
Fri (08/07) | 08 Jul 2022 | ULT2 |  | Steel plate unloading continue
Fri (08/07) | 08 Jul 2022 | ULT2 |  | Steel plate unloading stopped for the day. Housekeeping
Fri (08/07) | 08 Jul 2022 | Zone 2 |  | DE143 working in their boundary
Fri (08/07) | 08 Jul 2022 | Zone 2 |  | No activity by other contractor
Sat (09/07) | 09 Jul 2022 | Zone 4 | LP105 | SingTel Contractor Skk doing trial trench works. DE143 within their site boundary
Sat (09/07) | 09 Jul 2022 | Zone 3 |  | No activity by other contractors at both bounds
Sat (09/07) | 09 Jul 2022 | BH-181 |  | Commenced drilling, current depth 4m. Top up of water in progress
Sat (09/07) | 09 Jul 2022 | Zone 2 |  | DE143 working in their boundary
Sat (09/07) | 09 Jul 2022 | Zone 2 |  | No activity of other contractor
Sat (09/07) | 09 Jul 2022 | Zone 1 |  | DE143 working near bus stop, LP204
Sat (09/07) | 09 Jul 2022 | ULT-1/11 |  | No activity
Sat (09/07) | 09 Jul 2022 | ULT-2 |  | Unloading of steel plates. 4th truck moved out. Total steel plates demob as of now (55nos.)
Sat (09/07) | 09 Jul 2022 | BH-181 |  | Drilling in progress. Current depth 8m
Sat (09/07) | 09 Jul 2022 | ULT 1/11 |  | HSL materials/ machinery has been cleared. Excavator shifted out
Sat (09/07) | 09 Jul 2022 | BH-185 |  | Manual trial trenching
Sat (09/07) | 09 Jul 2022 | BH-56 |  | Coring in progress. Encountered rock at 32m
Sat (09/07) | 09 Jul 2022 | ULT-2 |  | Unloading of steel plates. 5th truck moved out. Total steel plates demob as of now (65nos.)
Sat (09/07) | 09 Jul 2022 | Zone 2 | Behind PJT office | Tree felling works started. 1st part - 12 trees to be fell
Sat (09/07) | 09 Jul 2022 | ULT-2 |  | Unloading of steel plates. 2nd truck moving out. Total steel plates demob as of now (28nos.)
Sun (10/07) | 10 Jul 2022 | PJT Office Level 1 |  | CCTV cable pulling
Sun (10/07) | 10 Jul 2022 | Zone 1 |  | No activity by other contractors
Sun (10/07) | 10 Jul 2022 | Zone 4 |  | No activity by other contractors
Sun (10/07) | 10 Jul 2022 | Zone 3 |  | No activity by other contractors
Sun (10/07) | 10 Jul 2022 | PJT Office Level 3 |  | Painting works ongoing
Sun (10/07) | 10 Jul 2022 | PD Office Level 2 |  | Toilet door installation ongoing
Sun (10/07) | 10 Jul 2022 | PJT Office Level 2 |  | Painting works done for the day
Sun (10/07) | 10 Jul 2022 | Zone 2 |  | DE143 working inside
Sun (10/07) | 10 Jul 2022 | PJT Office Level 2 |  | Painting works
Mon (11/07) | 11 Jul 2022 | PD office level 2 |  | Emergency light installation
Mon (11/07) | 11 Jul 2022 | ULT2 |  | No activity
Mon (11/07) | 11 Jul 2022 | Zone 4 |  | No activity of other contractor
Mon (11/07) | 11 Jul 2022 | Pd office level 2 |  | Femal toilet all urinal installed
Mon (11/07) | 11 Jul 2022 | PD office level 2 |  | Cable pulling for e-light installation
Mon (11/07) | 11 Jul 2022 | PD office level 1 |  | Vinyl tiles installation on going
Mon (11/07) | 11 Jul 2022 | Zone 2 |  | No activity of other contractor
Mon (11/07) | 11 Jul 2022 | Zone 1 |  | No activity of other contractor
Tue (12/07) | 12 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Tue (12/07) | 12 Jul 2022 | Zone 2 |  | No activity of other contractor
Tue (12/07) | 12 Jul 2022 | Zone 2 |  | Unsuitable soil clearing continue
Tue (12/07) | 12 Jul 2022 | Zone 2 |  | Material shifting for silo continue
Tue (12/07) | 12 Jul 2022 | BH-56 |  | Coring continue, currently 36m depth
Tue (12/07) | 12 Jul 2022 | ULT-2 |  | Continue test plate demob, no more trailers for the night
Tue (12/07) | 12 Jul 2022 | ULT 1/11 |  | No activity
Tue (12/07) | 12 Jul 2022 | ULt2 |  | Steel.plate demobilization 2nd truck loading in progress
Tue (12/07) | 12 Jul 2022 | ULT-2 |  | Works stopped for the night
Tue (12/07) | 12 Jul 2022 | Zone 2 |  | Material shifting for Silo area
Tue (12/07) | 12 Jul 2022 | Zone 2 |  | Clearing of rubbish and unsuitable soil for slurry tank area
Wed (13/07) | 13 Jul 2022 | PD office level 1 |  | Wall panel L-angle plate installation
Wed (13/07) | 13 Jul 2022 | Pd office level 2 |  | Lighting cable connection
Wed (13/07) | 13 Jul 2022 | PD office level 2 |  | Outlet cable connection
Wed (13/07) | 13 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Wed (13/07) | 13 Jul 2022 | Zone 2 |  | No activity of other contractor
Wed (13/07) | 13 Jul 2022 | BH-56 |  | Grouting completed, preparing to shift rig tmr to BH-185
Wed (13/07) | 13 Jul 2022 | PD office level 1 |  | Balance ceiling panel installation continue
Wed (13/07) | 13 Jul 2022 | ULT 1/11 |  | No activity
Thu (14/07) | 14 Jul 2022 | Zone 4 |  | No activity by other contractor
Thu (14/07) | 14 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Thu (14/07) | 14 Jul 2022 | Zone 2 |  | No activity of other contractor
Thu (14/07) | 14 Jul 2022 | Zone 3 |  | No activity by other contractor
Thu (14/07) | 14 Jul 2022 | New sump 2 location |  | Installation of 4-inch pump
Thu (14/07) | 14 Jul 2022 | ULT2 |  | Balance 3 nos steel plate unloading to ground level
Thu (14/07) | 14 Jul 2022 | BH-189 |  | Coring continue, currently at 29m depth
Thu (14/07) | 14 Jul 2022 | BH-185 |  | Manual TT ongoing
Fri (15/07) | 15 Jul 2022 | ULT2 |  | Lifting still idle, HSL waiting for WHDGJV lifting engineer to be on site
Fri (15/07) | 15 Jul 2022 | ULT2 |  | 20/20 secondary beam loading on going. Ambi here stand-by
Fri (15/07) | 15 Jul 2022 | BH185 |  | Hand augering in progress. Borehole center to starhub is 1m away. Current depth 2.9m
Fri (15/07) | 15 Jul 2022 | BH181 |  | Drilling continue at 38m depth. Lugeon test at 40m later today
Fri (15/07) | 15 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Fri (15/07) | 15 Jul 2022 | Zone 2 |  | No activity of other contractor
Fri (15/07) | 15 Jul 2022 | Zone 1 |  | No activity of other contractor
Fri (15/07) | 15 Jul 2022 | Zone 1 |  | DE143 working inside their boundary
Fri (15/07) | 15 Jul 2022 | PD office level 1 |  | Kitchen counter assembly
Fri (15/07) | 15 Jul 2022 | PD office level 1 |  | Balance ceiling panel installation
Fri (15/07) | 15 Jul 2022 | ULT2 |  | 4 nos steel leg frame and 2 secondary beam demob
Sun (17/07) | 17 Jul 2022 | Zone 3 |  | No activity by other contractors
Sun (17/07) | 17 Jul 2022 | Zone 4 |  | No activity by other contractors
Sun (17/07) | 17 Jul 2022 | PD Office Level 2 |  | Room partition rectification work completed
Sun (17/07) | 17 Jul 2022 | PD Office Level 2 |  | Housekeeping ongoing
Sun (17/07) | 17 Jul 2022 | Gate 5 |  | ECM pond toeboard installation
Sun (17/07) | 17 Jul 2022 | Gate 5 |  | Marking repainting
Sun (17/07) | 17 Jul 2022 | Zone 2 |  | DE143 working within boundary
Sun (17/07) | 17 Jul 2022 | Zone 1 |  | No activity by other contractors
Mon (18/07) | 18 Jul 2022 | ULT2 area |  | Material demob continue
Mon (18/07) | 18 Jul 2022 | BH 186 |  | TT started
Mon (18/07) | 18 Jul 2022 | BH185 |  | Drilling in progress at 23m depth
Mon (18/07) | 18 Jul 2022 | BH182 |  | Drilling in progress, 4m
Mon (18/07) | 18 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Mon (18/07) | 18 Jul 2022 | Zone 2 |  | No activity of other contractor
Mon (18/07) | 18 Jul 2022 | Zone 1 |  | No activity of other contractor towards CV
Mon (18/07) | 18 Jul 2022 | Zone 1 |  | DE143 lane closure towards TPE for stop light installation work. They are working outside our boundary
Mon (18/07) | 18 Jul 2022 | PD office level 2 |  | Shifted partition wall painting
Mon (18/07) | 18 Jul 2022 | BH186 |  | Manual excavation, 400mm depth
Mon (18/07) | 18 Jul 2022 | BH185 |  | Now at 25m depth
Mon (18/07) | 18 Jul 2022 | BH182 |  | SPT at 10m depth
Mon (18/07) | 18 Jul 2022 | PD office level 2 |  | Painting continue. 2nd coat
Mon (18/07) | 18 Jul 2022 | ULT 2 |  | No activity as well
Mon (18/07) | 18 Jul 2022 | ULT1/11 |  | No activity, going to light off
Tue (19/07) | 19 Jul 2022 | Zone 4 |  | No activity by other contractor
Tue (19/07) | 19 Jul 2022 | ULT2 crane demob |  | Clearing balance steel plate at the area
Tue (19/07) | 19 Jul 2022 | ULT-2 |  | Counter weight removal ongoing
Tue (19/07) | 19 Jul 2022 | Zone 3 |  | No activity by other contractor
Wed (20/07) | 20 Jul 2022 | Zone 2 |  | No activity of other contractor
Wed (20/07) | 20 Jul 2022 | Zone 1 |  | No activity by other contractor
Wed (20/07) | 20 Jul 2022 | Zone 2 |  | DE143 working inside their boundary
Thu (21/07) | 21 Jul 2022 | Zone 2 |  | No activity by other contractor
Thu (21/07) | 21 Jul 2022 | Zone 1 |  | No activity by other contractor
Thu (21/07) | 21 Jul 2022 | Zone 3 |  | No activity of other contractor
Thu (21/07) | 21 Jul 2022 | Zone 4 |  | No activity of other contractor on both bounds
Thu (21/07) | 21 Jul 2022 | ULT1 |  | Mobilisation of materials and machinery for bidirectional test
Thu (21/07) | 21 Jul 2022 | ULT1 |  | Bidirectional test set up
Thu (21/07) | 21 Jul 2022 | PD office level 1 |  | Cabinet assembly
Thu (21/07) | 21 Jul 2022 | ULT1 |  | Setting up for testing continues
Thu (21/07) | 21 Jul 2022 | BH185 |  | Downtime 2pm till now as the core barrel was split. Replacement is on the way
Thu (21/07) | 21 Jul 2022 | BH-186 |  | TT ongoing, 1.2m depth
Thu (21/07) | 21 Jul 2022 | Rig at BH-185 |  | Current depth @ 37m, casing spoil currently fixing ongoing
Thu (21/07) | 21 Jul 2022 | BH-182 |  | Coring at 34m
Thu (21/07) | 21 Jul 2022 | ULT-2 Area |  | No activity
Fri (22/07) | 22 Jul 2022 | Zone 4 | to TPE | Singtel working here
Fri (22/07) | 22 Jul 2022 | Zone 4 | Sidetable | Singtel working here
Fri (22/07) | 22 Jul 2022 | BH-199 |  | Current TT status
Fri (22/07) | 22 Jul 2022 | BH-199 |  | Commence TT work, excavator will assist to remove the top hardcore layer, PTD signed
Fri (22/07) | 22 Jul 2022 | BH-182 |  | Currently 38m depth
Fri (22/07) | 22 Jul 2022 | BH-185 |  | Chain replacement ongoing, will resume soon. depth at 37m
Fri (22/07) | 22 Jul 2022 | BH-186 |  | No activity here
Sat (23/07) | 23 Jul 2022 | ULT-1 |  | Bi-directional testing started. Cycle 1: At 25% working load, pressure:800psi
Sat (23/07) | 23 Jul 2022 | Zone 1 - ATT43-03 | LP200,side table | Manual trial trench in progress to locate m1 cable
Sat (23/07) | 23 Jul 2022 | Zone 4 |  | SingTel working at the sidetable
Sat (23/07) | 23 Jul 2022 | Zone 3 |  | No activity of other contractor
Sat (23/07) | 23 Jul 2022 | BH-182 packer test in progress. Test depth |  | 41.39-46.39m
Sat (23/07) | 23 Jul 2022 | ULT-2 area |  | BH-197 Manual trial trenching in progress. Current depth 1m
Sat (23/07) | 23 Jul 2022 | Zone 2 |  | No activity at handover area
Sat (23/07) | 23 Jul 2022 | BH-182 |  | Termination depth - 46.4m. Preparation for grouting
Sat (23/07) | 23 Jul 2022 | BH-185 packer test in progress. Test depth |  | 40.24m-45.24m
Sat (23/07) | 23 Jul 2022 | ULT-1 Cycle 1 | Bi-directional testing | At 100% working load, pressure:2800psi. Holding time for 100% is 6hrs, current hold time is 4hrs. At around 7pm+ will start unload to 75% load
Sat (23/07) | 23 Jul 2022 | BH-182 |  | Coring in progress. Current depth - 46m
Sat (23/07) | 23 Jul 2022 | Zone 2 |  | DE143 working within their boundary. No activity at the handover area
Sat (23/07) | 23 Jul 2022 | Zone 2 |  | No activity of other contractor
Sat (23/07) | 23 Jul 2022 | Zone 1 |  | No activity of other contractor
Sat (23/07) | 23 Jul 2022 | ULT-1 |  | Preparation works for testing in progress
Sun (24/07) | 24 Jul 2022 | ULT1 | cycle 2 | @150% load
Sun (24/07) | 24 Jul 2022 | Zone 3 |  | No activity by other contractor
Sun (24/07) | 24 Jul 2022 | Zone 4 |  | No activity by other contractor
Sun (24/07) | 24 Jul 2022 | ULT 1 |  | Unloaded to 125%
Sun (24/07) | 24 Jul 2022 | ULT1 |  | Loaded to 150%, holding time for 1hr
Sun (24/07) | 24 Jul 2022 | ULT-1 | cycle 3 | Going to take last reading for 175% load & will increase to 200% load
Sun (24/07) | 24 Jul 2022 | ULT- 1 cycle 2 |  | Holding at 125% completed. Now preparing to continue to 150%, holding time is 6hrs
Sun (24/07) | 24 Jul 2022 | Zone 2 |  | DE143 working in their boundary
Sun (24/07) | 24 Jul 2022 | Zone 2 |  | No activity by other contractor
Sun (24/07) | 24 Jul 2022 | Zone 1 |  | No activity by other contractor
Mon (25/07) | 25 Jul 2022 | Zone 1 |  | Hi-tech working at side table towards CV
Mon (25/07) | 25 Jul 2022 | Zone 1 |  | DE143 working just outside our boundary
Mon (25/07) | 25 Jul 2022 | Zone 2 |  | Dongah TMA for their 2nd rig shifting to site office
Mon (25/07) | 25 Jul 2022 | Zone 2 | to TPE | No activity by other contractor
Mon (25/07) | 25 Jul 2022 | BH-199 |  | Hand auger ongoing
Mon (25/07) | 25 Jul 2022 | Zone 2 |  | DE143 working in their boundary
Mon (25/07) | 25 Jul 2022 | ULT1 |  | 3rd cylce holding for 300% loading 13/24 hrs. Current jack expansion at 190mm. Still holding
Mon (25/07) | 25 Jul 2022 | Zone 1 |  | Manual excavation for trial trench. Found M1 cable at 600mm depth
Mon (25/07) | 25 Jul 2022 | Entrance 3 BH187 |  | Hand augering in progress
Mon (25/07) | 25 Jul 2022 | Zone 3 |  | No activity by other contractor
Mon (25/07) | 25 Jul 2022 | Zone 4 | to CV | No activity by other contractor
Mon (25/07) | 25 Jul 2022 | Zone 4 | to TPE | Singtel working here
Mon (25/07) | 25 Jul 2022 | Entrance 3 |  | 2 rigs are here now. Works continue for hand augering at BH197 (balance 1m) and BH199 (balance 500mm). Tomorrow to start SI here
Tue (26/07) | 26 Jul 2022 | Zone 3 |  | No activity by other contractor
Tue (26/07) | 26 Jul 2022 | Zone 4 | to CV | No activity by other contractor
Tue (26/07) | 26 Jul 2022 | Zone 4 | to TPE | Singtel working along fast lane
Tue (26/07) | 26 Jul 2022 | BH 199 |  | Pump repairing
Tue (26/07) | 26 Jul 2022 | BH197 |  | Drilling/SPT started
Tue (26/07) | 26 Jul 2022 | Zone 2 |  | No activity by other contractor
Tue (26/07) | 26 Jul 2022 | Zone 2 |  | DE143 within their boundary
Tue (26/07) | 26 Jul 2022 | BH197 |  | Drilling/SPT in progress. Current depth at 8m
Tue (26/07) | 26 Jul 2022 | Zone 4 |  | Singtel works towards TPE
Tue (26/07) | 26 Jul 2022 | BH-199 |  | Preparing to start coring work
Tue (26/07) | 26 Jul 2022 | BH-198 |  | Hand augering ongoing
Tue (26/07) | 26 Jul 2022 | BH-197 |  | Pending to start
Wed (27/07) | 27 Jul 2022 | Zone 1 |  | No activity of other contractor
Wed (27/07) | 27 Jul 2022 | Zone 2 |  | No activity of other contractor
Wed (27/07) | 27 Jul 2022 | ULT1 |  | HSL materials demob
Wed (27/07) | 27 Jul 2022 | ULT11 area |  | Surveyor's team here to set out excavation area
Thu (28/07) | 28 Jul 2022 | Zone 3 |  | BH 200 hand augering
Thu (28/07) | 28 Jul 2022 | BH200 |  | Hand augering continue. Balance 800mm
Thu (28/07) | 28 Jul 2022 | BH 199 |  | Drilling/SPT continue. Current depth at 28m
Thu (28/07) | 28 Jul 2022 | BH197 |  | Packer test completed
Thu (28/07) | 28 Jul 2022 | Zone 3 |  | No activity of other contractor
Thu (28/07) | 28 Jul 2022 | Zone 4 |  | No activity towards CV. DE143 working inside their boundary
Thu (28/07) | 28 Jul 2022 | Zone 4 |  | Singtel lane closure at fast lane towards TPE
Thu (28/07) | 28 Jul 2022 | BH198 |  | Drilling started
Sun (31/07) | 31 Jul 2022 | Zone 2 |  | Observed DE143 doing soil levelling at the area taken over
Sun (31/07) | 31 Jul 2022 | BH200 |  | Drilling in progress. Current depth 27m
Sun (31/07) | 31 Jul 2022 | BH198 |  | Drilling terminated at 37.4m. Preparation for packer test
Sun (31/07) | 31 Jul 2022 | Zone 2 |  | DE143 dismantling hoarding and clearing materials at the handed over area
Mon (01/08) | 01 Aug 2022 | Zone 1 |  | No activity of other contractor
Tue (02/08) | 02 Aug 2022 | DE143 take over area |  | WH installing temporary hoarding
Tue (02/08) | 02 Aug 2022 | DE143 |  | Installing hoarding at their boundary
Wed (03/08) | 03 Aug 2022 | BH02 |  | Hand augering resumed
Wed (03/08) | 03 Aug 2022 | BH198 |  | Packer test resumed
Wed (03/08) | 03 Aug 2022 | BH198 |  | Packer test completed
Thu (04/08) | 04 Aug 2022 | Zone 4 |  | SingTel contractor working at the area
Thu (04/08) | 04 Aug 2022 | Zone 3 |  | No activity of other contractor. CCECC working at Loyang way
Thu (04/08) | 04 Aug 2022 | BH-02 |  | SPT 1 at 4.0m
Thu (04/08) | 04 Aug 2022 | BH-02 |  | Hand angering in progress, 1m depth currently
Thu (04/08) | 04 Aug 2022 | BH-200 |  | Coring in progress, current depth 32m
Fri (05/08) | 05 Aug 2022 | Zone 3 |  | No activity of other contractor
Fri (05/08) | 05 Aug 2022 | Zone 4 |  | Singtel works towards TPE
Fri (05/08) | 05 Aug 2022 | Zone 4 |  | No activity towards CV
Fri (05/08) | 05 Aug 2022 | BH02 |  | SPT in progress
Fri (05/08) | 05 Aug 2022 | BH200 |  | Preparation for Packer test
Fri (05/08) | 05 Aug 2022 | BH01 |  | Hand augering continue
Fri (05/08) | 05 Aug 2022 | BH01 |  | SPT at 8m
Fri (05/08) | 05 Aug 2022 | Zone 3 |  | Steel plate laying for crane platform
Fri (05/08) | 05 Aug 2022 | BH200 |  | Drilling 36-39m depth
Fri (05/08) | 05 Aug 2022 | Zone 3 |  | Area preparation for crane platform
Fri (05/08) | 05 Aug 2022 | BH01 |  | Hand augering started
Sat (06/08) | 06 Aug 2022 | BH02 |  | Drilling continue. 25-30m
Sat (06/08) | 06 Aug 2022 | BH186 |  | Hand augering in progress
Sat (06/08) | 06 Aug 2022 | ULT11 |  | Cable detection done. Telco cables were detected
Sat (06/08) | 06 Aug 2022 | BH02 |  | Drilling continue. Depth 28m
Sat (06/08) | 06 Aug 2022 | BH186 |  | Hand augering continue. Balance 1.2m
Sat (06/08) | 06 Aug 2022 | Zone 2 |  | No activity of other contractor
Sat (06/08) | 06 Aug 2022 | Zone 1 |  | No activity of other contractor on both bounds
Sat (06/08) | 06 Aug 2022 | Zone 3 |  | No activity of other contractor
Sat (06/08) | 06 Aug 2022 | Zone 4 |  | Singtel works towards TPE
Sat (06/08) | 06 Aug 2022 | Zone 4 |  | No activity towards CV. DE143 working inside their boundary
Sat (06/08) | 06 Aug 2022 | BH02 |  | Drilling continue to 34m. DG SI team will work until 6pm today. Tomorrow they will off
Sat (06/08) | 06 Aug 2022 | Zone 3 |  | Steel plate laid for crane platform. COS yet to issue by PE
Sat (06/08) | 06 Aug 2022 | BH200 |  | Grouting in progress
Sat (06/08) | 06 Aug 2022 | Zone 2 desander and filter press area |  | No activity. Workers occupied at crane platform area preparation works
Sun (07/08) | 07 Aug 2022 | Zone 3 |  | No activity by other contractors
Sun (07/08) | 07 Aug 2022 | Zone 4 |  | CR1070 working at Loyang Way junction. Hacking works ongoing
Mon (08/08) | 08 Aug 2022 | Zone 3 side table |  | BH186 hand augering in progress. Balance 800mm
Mon (08/08) | 08 Aug 2022 | Zone 2 |  | ECB laying
Mon (08/08) | 08 Aug 2022 | BH196 |  | Drilling/SPT in progress
Mon (08/08) | 08 Aug 2022 | BH02 |  | Pending WH QP confirmation if need to terminate at 37m
Mon (08/08) | 08 Aug 2022 | BH196 |  | Access preparation to shift rig and start SI work
Mon (08/08) | 08 Aug 2022 | BH-2 |  | Alr reached termination depth at 37m, waiting for confirmation
Mon (08/08) | 08 Aug 2022 | BH-196 |  | Rig setting up/ access preparing ongoing
Tue (09/08) | 09 Aug 2022 | Zone 3 |  | No activity of other contractor
Tue (09/08) | 09 Aug 2022 | Zone 4 |  | No activity of other contractor
Tue (09/08) | 09 Aug 2022 | Zone 1 |  | No activity of other contractor
Tue (09/08) | 09 Aug 2022 | ULT-1/11 |  | No activity
Tue (09/08) | 09 Aug 2022 | Exit 3 access footpath |  | Painting works ongoing
Tue (09/08) | 09 Aug 2022 | Exit 3/Silo area |  | No activity
Tue (09/08) | 09 Aug 2022 | DE143 Handover area |  | No activity
Tue (09/08) | 09 Aug 2022 | Zone 2 |  | No activity of other contractor
Wed (10/08) | 10 Aug 2022 | Zone 4 | to CV | No activity by other contractor
Wed (10/08) | 10 Aug 2022 | Zone 4 | to TPE | Hi tech working here
Wed (10/08) | 10 Aug 2022 | Exit 3 | dwall | Filter press arrived at site
Wed (10/08) | 10 Aug 2022 | 3rd load casting |  | 25.5/90 m3
Wed (10/08) | 10 Aug 2022 | BH196 |  | Drilling terminated at 36.8m. Packer test required
Wed (10/08) | 10 Aug 2022 | BH01 |  | SPT at 14m
Wed (10/08) | 10 Aug 2022 | Silo area | 2nd part | Casting in progress
Wed (10/08) | 10 Aug 2022 | BH01 |  | Drilling started / SPT 1 ongoing
Wed (10/08) | 10 Aug 2022 | BH-196 |  | Drilling ongoing, @ 23m depth
Thu (11/08) | 11 Aug 2022 | DE143 road interface |  | Site discussion of WH and Singtec for earthworks to construct temporary access. This week they are preparing all documents and start to mob machineries monday next week
Thu (11/08) | 11 Aug 2022 | BH01 |  | Coring ongoing, 30.20m depth
Thu (11/08) | 11 Aug 2022 | Zone 1 |  | No activity on both bounds
Thu (11/08) | 11 Aug 2022 | BH01 |  | Grouting completed
Fri (12/08) | 12 Aug 2022 | Zone 3 |  | BH186 drilling started
Fri (12/08) | 12 Aug 2022 | Zone 3 |  | BH188 drilling in progress. Depth 16-18m
Fri (12/08) | 12 Aug 2022 | Zone 3 |  | BH183 trial trench in progress
Fri (12/08) | 12 Aug 2022 | Exit 3 |  | Hydraulic hose drum & water stop on site, lifting work ongoing, balance mud drum & cutter machine base delivery
Mon (15/08) | 15 Aug 2022 | BH188 |  | Coring ongoing, 33m depth
Mon (15/08) | 15 Aug 2022 | BH-183 |  | TT ongoing
Mon (15/08) | 15 Aug 2022 | Zone 1 |  | No activity by other contractor
Mon (15/08) | 15 Aug 2022 | Zone 1 |  | No activity of other contractor
Mon (15/08) | 15 Aug 2022 | Zone 2 |  | Lane closure towards CV for tree felling
Mon (15/08) | 15 Aug 2022 | ULT-11 |  | Utilities found as of now: 1 - unknown, 2,4&5 - SPPG, 3 - telco
Mon (15/08) | 15 Aug 2022 | BH188 |  | Packer test no.1 in progress at depth of 30.8m to 35.80m
Mon (15/08) | 15 Aug 2022 | BH-186 |  | Coring works ongoing, current depth 29m
Mon (15/08) | 15 Aug 2022 | BH-183 |  | Manual trial trench works
Tue (16/08) | 16 Aug 2022 | BH183 |  | Trial trench continue. Balance 200mm
Tue (16/08) | 16 Aug 2022 | ULT11 |  | Manual excavation along perimeter & removal of hardcore only
Tue (16/08) | 16 Aug 2022 | Zone 3 |  | ABH 39-1 trial trench commence
Tue (16/08) | 16 Aug 2022 | ULT 11 |  | Trial trench continue
Tue (16/08) | 16 Aug 2022 | ULT-11 |  | Trial trench around the perimeter of ult completed. Housekeeping and Leveling works in progress
Tue (16/08) | 16 Aug 2022 | DE143 |  | Setting out for temporary access construction
Wed (17/08) | 17 Aug 2022 | Zone 4 |  | Trial trenching works ongoing for ATT28-06
Wed (17/08) | 17 Aug 2022 | Zone 3 |  | Monthly maintenance of the TP camera
Wed (17/08) | 17 Aug 2022 | Zone 4 |  | CCECC works at Loyang Way junction
Wed (17/08) | 17 Aug 2022 | ULT11 |  | Access / barricade erection in progress
Wed (17/08) | 17 Aug 2022 | BH188 |  | Packer test no.2 in progress at depth of 38.8m to 43.80m
Wed (17/08) | 17 Aug 2022 | BH-186 |  | Coring in progress. Current depth - 40m
Wed (17/08) | 17 Aug 2022 | BH-188 |  | 2nd Packer Test completed. Pending WH design team concurrence on the termination depth
Wed (17/08) | 17 Aug 2022 | BH183 |  | Hand augering continue
Wed (17/08) | 17 Aug 2022 | BH186 |  | Depth reach at 43m
Wed (17/08) | 17 Aug 2022 | Exit 3 |  | Guide wall marking by surveyor. Plan to start excavation by tomorrow
Fri (19/08) | 19 Aug 2022 | BH188 |  | Trench backfilling
Fri (19/08) | 19 Aug 2022 | BH186 |  | Packer test on going at 44.8m
Fri (19/08) | 19 Aug 2022 | DE143 interface area |  | No activity
Fri (19/08) | 19 Aug 2022 | ULT11 |  | No activity
Fri (19/08) | 19 Aug 2022 | Zone 1 |  | Works @ the POB
Fri (19/08) | 19 Aug 2022 | DE143 road interface |  | Temporary access compaction on going. Today plan to continue backfilling. Target 20 loads today
Sat (20/08) | 20 Aug 2022 | ABH39-1 |  | Currently hand auger ongoing, 300mm depth. shifting rig to standby
Sat (20/08) | 20 Aug 2022 | BH-183 |  | Coring ongoing
Sat (20/08) | 20 Aug 2022 | Zone 2 tree felling |  | No activity today
Sat (20/08) | 20 Aug 2022 | Zone 1 |  | Works at POB
Sat (20/08) | 20 Aug 2022 | Zone 2 temp site access |  | Current status
Sun (21/08) | 21 Aug 2022 | Zone 2 |  | No activity of other contractor
Sun (21/08) | 21 Aug 2022 | Zone 1 |  | POB status, DE143 working
Sun (21/08) | 21 Aug 2022 | Zone 3 |  | CR1070 works at junction
Sun (21/08) | 21 Aug 2022 | Zone 3 |  | No activity towards CV
Sun (21/08) | 21 Aug 2022 | Zone 4 |  | No activity of other contractor on both bounds
Sun (21/08) | 21 Aug 2022 | Temporary access to DE143 status |  | About 25 loads backfilled ~ 180-200 m3. Breaker on site for retaining wall hacking to start from tomorrow
Mon (22/08) | 22 Aug 2022 | Zone 2 |  | Preparation for slurry tank assembly
Mon (22/08) | 22 Aug 2022 | Zone 2 |  | Internal shifting and housekeeping at material storage area inside 106 boundary
Mon (22/08) | 22 Aug 2022 | ATT28-03 |  | Services status for trial trench done
Mon (22/08) | 22 Aug 2022 | Zone 2 |  | Temporary access soil backfilling continue
Tue (23/08) | 23 Aug 2022 | Zone 4 |  | No activity of other contractor
Tue (23/08) | 23 Aug 2022 | Zone 2 |  | Tree feeling of small trees at vacant land near junction. RFI submitted
Tue (23/08) | 23 Aug 2022 | Zone 1 |  | POB demolition works by DE143
Tue (23/08) | 23 Aug 2022 | ULT11 |  | Further excavation and area preparation for cable spiking in progress
Tue (23/08) | 23 Aug 2022 | Zone 2 |  | Slurry tank assembly in progress
Tue (23/08) | 23 Aug 2022 | ABH 39-1 |  | Drilling in progress, depth 24m
Wed (24/08) | 24 Aug 2022 | ULT11 |  | No activity
Wed (24/08) | 24 Aug 2022 | ATT33-06 |  | Found telstra, 500mm dia water pipe and HT cables at 1.4m depth
Wed (24/08) | 24 Aug 2022 | zone 2 |  | New 10T roller safety inspection for slip road construction
Thu (25/08) | 25 Aug 2022 | ULT11 |  | No activity, pending SPPG
Thu (25/08) | 25 Aug 2022 | Exit 3 guidewall area |  | Finally going to start excavation
Thu (25/08) | 25 Aug 2022 | Exit 3 |  | Fabrication of movable barricade
Fri (26/08) | 26 Aug 2022 | Zone 2 |  | Stock pile shifting for ECM excavation works
Sat (27/08) | 27 Aug 2022 | Zone 2 |  | Soil trimming for preparation of PCN footpath diversion
Sat (27/08) | 27 Aug 2022 | Zone 2 |  | No activity of other contractor
Sat (27/08) | 27 Aug 2022 | Zone 1 |  | No activity of other contractor
Sat (27/08) | 27 Aug 2022 | Zone 2 |  | Footpath hacking for pipe installation for hoarding lighting after PCN diversion
Sat (27/08) | 27 Aug 2022 | Ult-1/11 |  | No activity
Sat (27/08) | 27 Aug 2022 | ATT28-03 | Loyang Way | Trial trench in progress, TMO provided
Sat (27/08) | 27 Aug 2022 | Zone 4 |  | No activity of other contractor
Sat (27/08) | 27 Aug 2022 | Zone 3 |  | No activity of other contractor
Sat (27/08) | 27 Aug 2022 | Zone 2 |  | Continue of Soil trimming. Target to complete by tmr
Sat (27/08) | 27 Aug 2022 | ATT28-03 |  | Services status
Sat (27/08) | 27 Aug 2022 | Zone 2 |  | No activity at ecm pond area. SingTec only have 1 excavator operator and currently doing the pcn footpath
Mon (29/08) | 29 Aug 2022 | Zone 2 PCN Diversion |  | Removal of unsuitable soil / compaction work. covering exposed soil with ecb ongoing
Mon (29/08) | 29 Aug 2022 | Exit 3 |  | Removal of hardcore for guidewall construction
Mon (29/08) | 29 Aug 2022 | Zone 2 |  | Excavation of new ECM on going. Rubbish and tree branches found below
Tue (30/08) | 30 Aug 2022 | Exit 3 | dwall guidewall | Trial trench ongoing
Wed (31/08) | 31 Aug 2022 | ULT-1/11 |  | No activity at the area
Wed (31/08) | 31 Aug 2022 | Zone 2 |  | No activity of other contractors
Wed (31/08) | 31 Aug 2022 | Exit 3 |  | Guidewall excavation in progress for panel no.8
Wed (31/08) | 31 Aug 2022 | Zone 2 PCN |  | Soil bag removal in progress
Fri (02/09) | 02 Sep 2022 | Exit 3 |  | Guidewall construction still no activity. Plan to shift filter press, desander and mud tank by tomorrow
Sat (03/09) | 03 Sep 2022 | Zone 2 |  | Footpath soil trimming
Sat (03/09) | 03 Sep 2022 | Zone 1 |  | POB works by other contractor
Sat (03/09) | 03 Sep 2022 | Zone 2 |  | Trial trench on going to find water pipe for utility settlement marker installation
Sat (03/09) | 03 Sep 2022 | Zone 2 footpath diversion works |  | Laying of balance BRC and formworks. Monday to cast
Sat (03/09) | 03 Sep 2022 | Zone 2 |  | No activity of other contractor
Sun (04/09) | 04 Sep 2022 | Exit 3 |  | No activity
Mon (05/09) | 05 Sep 2022 | PCN diversion | footpath part 2 | Casting started / levelling ongoing, current vol: 7/21m3
Mon (05/09) | 05 Sep 2022 | Zone 1 |  | POB works by DE143
Mon (05/09) | 05 Sep 2022 | PCN diversion | part 1 | Column post installation status, hoarding sheets otw
Mon (05/09) | 05 Sep 2022 | PCN diversion | footpath part 2 | Casting ongoing
Tue (06/09) | 06 Sep 2022 | ULT 11 |  | Housekeeping work only
Tue (06/09) | 06 Sep 2022 | Exit 3 guidewall |  | Rebar installation on going for panel 08
Tue (06/09) | 06 Sep 2022 | Exit 3 |  | Guidewall first casting started
Wed (07/09) | 07 Sep 2022 | Zone 1 |  | POB works by DE143
Wed (07/09) | 07 Sep 2022 | Exit 3 |  | Unloading of steel plates
Wed (07/09) | 07 Sep 2022 | Exit 3 |  | Guide wall excavation in progress for panels 8-7
Thu (08/09) | 08 Sep 2022 | ULT 11 |  | Survey marking ongoing
Thu (08/09) | 08 Sep 2022 | ULT 11 |  | Excavation resume
Thu (08/09) | 08 Sep 2022 | Exit 3 guidewall panel 7 and 8 |  | Formworks inspection. Concrete ordered 15 m3
Thu (08/09) | 08 Sep 2022 | Exit 3 guidewall |  | Hi-rib dismantling and preparation for rebar installation. Progressively installing toe board
Thu (08/09) | 08 Sep 2022 | Sump 1 | Holding tank near silo | Removal of access and barricades to prepare for backfilling works. They will partly backfill this area to facilitate USD construction. WH to submit revise ECM plan as the latest plan used this area for holding tank
Fri (09/09) | 09 Sep 2022 | Exit 3 |  | Area preparation for guidewall excavation
Fri (09/09) | 09 Sep 2022 | Zone 2 |  | Soil levelling
Mon (12/09) | 12 Sep 2022 | Exit 3 | GWV31001 | Trial trench in progress for piezometer
Mon (12/09) | 12 Sep 2022 | Exit 3 | DW05 | Current excavation status
Mon (12/09) | 12 Sep 2022 | trimming ongoing, target to cast at 4 |  | 30pm
Fri (16/09) | 16 Sep 2022 | DW01&02 | 9.8m length | Casting ongoing, total vol: 16m3
Fri (16/09) | 16 Sep 2022 | Exit 3 Silo Area |  | Resume slurry tank erection
Fri (16/09) | 16 Sep 2022 | Zone 1 |  | DE143 works at POB
Fri (16/09) | 16 Sep 2022 | PRD3 LP4 |  | DE143 taken over area previously occupied by PUB
Fri (16/09) | 16 Sep 2022 | ULT 11 |  | Setting up of reference beam ongoing
Sat (17/09) | 17 Sep 2022 | Zone 2 |  | No activity of other contractor
Sat (17/09) | 17 Sep 2022 | Zone 1 |  | DE143 works at POB
Sat (17/09) | 17 Sep 2022 | ULT-11 |  | Dewatering and Test setup in progress
Sat (17/09) | 17 Sep 2022 | Zone 3 |  | No activity of other contractor
Sat (17/09) | 17 Sep 2022 | Zone 4 |  | No activity of other contractor
Sat (17/09) | 17 Sep 2022 | GWV 31002 |  | Drilling rig shifted to the location. Hand augering in progress
Sat (17/09) | 17 Sep 2022 | ULT-11 |  | Welding of I-beam to reaction pile
Sat (17/09) | 17 Sep 2022 | GWV-31002 |  | Piezometer drilling commenced
Sat (17/09) | 17 Sep 2022 | Exit 3 |  | GWV 31002 manual trial trench in progress
Sat (17/09) | 17 Sep 2022 | DW01&02 | 9.8m length | Curing in progress
Sun (18/09) | 18 Sep 2022 | Exit 3 |  | Both sumps working fine, site is ok
Mon (19/09) | 19 Sep 2022 | Exit 3 |  | Guidewall works for panel 02,03 and 04. Today to cast
Mon (19/09) | 19 Sep 2022 | Exit 3 silo area |  | Slurry tank assembly
Mon (19/09) | 19 Sep 2022 | Exit 3 |  | GWV31002 drilling on going. Current depth 9m, required 22.7m
Mon (19/09) | 19 Sep 2022 | Zone 2 |  | Trial trench area pavement rectification on going
Mon (19/09) | 19 Sep 2022 | ULT 11 |  | Jack set up completed. Required documents verified by QPS. Now taking initial reading for inclinometer before bidirectional test
Mon (19/09) | 19 Sep 2022 | Exit 3 |  | Guidewall for panel 02,03 and 04 casting started
Tue (20/09) | 20 Sep 2022 | Zone 2 |  | No activity of other contractor
Tue (20/09) | 20 Sep 2022 | ULT11 status |  | No activity
Tue (20/09) | 20 Sep 2022 | Zone 2 |  | Soil delivery for USD backfilling
Tue (20/09) | 20 Sep 2022 | Zone 2 |  | BRC laying for slab of temporary desander
Tue (20/09) | 20 Sep 2022 | Gate 5 |  | Pavement hacking for trial trench (GWV31003)
Wed (21/09) | 21 Sep 2022 | ULT-11 |  | No activity
Wed (21/09) | 21 Sep 2022 | Zone 2 north ramp |  | Tree transplant started
Wed (21/09) | 21 Sep 2022 | Zone 2 diverted PCN |  | Cable termination for temporary lightings
Wed (21/09) | 21 Sep 2022 | Zone 2 |  | Access for north ramp casting
Wed (21/09) | 21 Sep 2022 | Zone 2 |  | No activity by other contractor
Wed (21/09) | 21 Sep 2022 | Exit 3 |  | Continue of slurry tank set up
Wed (21/09) | 21 Sep 2022 | Zone 3 |  | No activity of other contractor
Wed (21/09) | 21 Sep 2022 | Zone 4 |  | No activity of other contractor
Wed (21/09) | 21 Sep 2022 | 21/09/22 |  | Today's summary of work done, *Transplant*, 1. T483, 2. T485, 3. T478, 4. T475, 5. T555, 6. T547, 7. T550, *Fell*, 1. T236, 2. T238, 3. T239
Thu (22/09) | 22 Sep 2022 | ATT-JTC-04 | next to substation | Hitech will commence TT work here to locate the retaining wall depth
Thu (22/09) | 22 Sep 2022 | ULT11 |  | Bi-directional test status
Fri (23/09) | 23 Sep 2022 | ATT-JTC-05 |  | Found water pipe at 600mm as of now. The purpose of trial trench is to confirm the fencing and retaining restructure detail
Fri (23/09) | 23 Sep 2022 | ULT11 bidirectional test |  | Loading to 100% ~950KN
Fri (23/09) | 23 Sep 2022 | ULT11 |  | Loading to 187.5%, 1781KN
Fri (23/09) | 23 Sep 2022 | ULT1 | reaction pile | Can clearly see the gap as deflection
Fri (23/09) | 23 Sep 2022 | ULT 11 | test pile | The deflection also is noticeable
Mon (26/09) | 26 Sep 2022 | Zone 1 LP192 | Sidetable | DE143 drain works ongoing
Mon (26/09) | 26 Sep 2022 | Zone 1 |  | POB works by DE143
Mon (26/09) | 26 Sep 2022 | Exit 3 |  | GWV31003 drilling in progress
Tue (27/09) | 27 Sep 2022 | Zone 2 |  | No activity of other contractor
Wed (28/09) | 28 Sep 2022 | Zone 2 |  | USD (20m) formworks closing. Plan to cast today. Estimated volume 9m3
Wed (28/09) | 28 Sep 2022 | Zone 2 USD |  | Formworks closing continue
Thu (29/09) | 29 Sep 2022 | ULT 11 |  | 6th load backfilled (total 10 loads ordered)
Fri (30/09) | 30 Sep 2022 | Zone 2 North ramp access |  | Hacking for slab over drain installation
Fri (30/09) | 30 Sep 2022 | Zone 2 city bound |  | Street light contractor working in front of shell
Fri (30/09) | 30 Sep 2022 | ULT1 and 11 |  | Backfilling completed. Slope concrete lining arranged and cast this afternoon
Sat (01/10) | 01 Oct 2022 | Exit 3 |  | BRC laying for 1st slurry tank base in progress
Sat (01/10) | 01 Oct 2022 | Exit 3 |  | Crawler Crane boom down for monthly inspection
Sat (01/10) | 01 Oct 2022 | Zone 2 |  | No activity of other contractor
Sat (01/10) | 01 Oct 2022 | Zone 1 |  | No activity of other contractor
Sat (01/10) | 01 Oct 2022 | ULT-11 |  | No activity. Backfilling and slope casting completed
Sat (01/10) | 01 Oct 2022 | Zone 4 |  | No activity of other contractor
Sat (01/10) | 01 Oct 2022 | Zone 3 |  | No activity of other contractor
Sat (01/10) | 01 Oct 2022 | Zone 2 PCN |  | Cable termination works for 8th lamp post in progress
Mon (03/10) | 03 Oct 2022 | Slurry tank 01 |  | Rebar inspection done with minor comment. Plug in bolts to place in between 1st and 2nd layer of BRC. Rectification on going
Mon (03/10) | 03 Oct 2022 | Zone 2 |  | No activity of other contractor
Mon (03/10) | 03 Oct 2022 | Zone 3 junction |  | CR1070 works, road kerb installation
Wed (05/10) | 05 Oct 2022 | Zone 1 PCN Sidetable |  | DE143 footpath diversion / drain construction ongoing
Thu (06/10) | 06 Oct 2022 | ULT11/1 |  | No activity
Thu (06/10) | 06 Oct 2022 | Zone 1 PCN Sidetable |  | Drain work / footpath diversion ongoing
Thu (06/10) | 06 Oct 2022 | PRD3 |  | DE143 / Powergrid working along here
Thu (06/10) | 06 Oct 2022 | Zone 1 |  | POB shelter column removal ongoing by DE143
Fri (07/10) | 07 Oct 2022 | Zone 3 |  | No activity by other contractor
Fri (07/10) | 07 Oct 2022 | Slurry tank 01 |  | Preparation for mixer installation. Today to complete mixer installation. Plan to continue slurry tank 02 3rd layer panel installation
Fri (07/10) | 07 Oct 2022 | Zone 3 Exit 1 |  | ECS on site, preparation ongoing for hoarding works & mini mob-in
Fri (07/10) | 07 Oct 2022 | Zone 2 |  | DE143 diverted the footpath for their works
Fri (07/10) | 07 Oct 2022 | Slurry tank 01 |  | Mixer installation on going
Fri (07/10) | 07 Oct 2022 | Slurry Tank 01 |  | Mixer installation in progress
Mon (10/10) | 10 Oct 2022 | Slurry Tank No.2 |  | 3rd layer panel installation in progress
Mon (10/10) | 10 Oct 2022 | Slurry tank 2 |  | Assembly for 3rd layer continue
Tue (11/10) | 11 Oct 2022 | Zone 1 | Blk 272A | ABH-10 TT started
Tue (11/10) | 11 Oct 2022 | Zone 1 ABH-07 | Blk 273 | No activity for now
Tue (11/10) | 11 Oct 2022 | ULT 1/11 |  | No activity
Tue (11/10) | 11 Oct 2022 | Plan for the Power USD Mockup 1 on Friday |  | SPPG Ops team will come in the morning to confirm the cable arrangement/cutting and SPPG planning team will come in the afternn to inspect the cables laid
Tue (11/10) | 11 Oct 2022 | Slurry tank 02 |  | 3rd layer panel installation continue
Tue (11/10) | 11 Oct 2022 | Zone 2 Site Access |  | Removal of existing kerb ongoing
Wed (12/10) | 12 Oct 2022 | Zone 1 ABH-10 |  | TT completed, backfilling ongoing
Wed (12/10) | 12 Oct 2022 | Zone 1 ABH-07 |  | No activity
Wed (12/10) | 12 Oct 2022 | PRD3 |  | Road works by DE143
Wed (12/10) | 12 Oct 2022 | Exit 3 |  | Cutter body modification to reduce to 1m width
Wed (12/10) | 12 Oct 2022 | ULT 1/11 |  | Pending to cast
Wed (12/10) | 12 Oct 2022 | Exit 3 |  | Slurry tank assembly for 3rd panel continue. Balance 4 panels
Thu (13/10) | 13 Oct 2022 | ULT1/11 |  | Lean concrete casting for the previous excavated area
Thu (13/10) | 13 Oct 2022 | Zone 1 PCN Sidetable |  | Reinstatement works by DE143
Thu (13/10) | 13 Oct 2022 | Zone 1 ABH-7 | Blk 273 | TT ongoing. 1 team working today only
Thu (13/10) | 13 Oct 2022 | CR103 accident reporting |  | On 13 Oct 2022 at about 1130hrs, IP (lifting supervisor) was tasked to shift steel plates (1m x 1m) to another location for setting up the concrete pump outriggers. The IP instructed an excavator operator to slightly lift up one side of the steel plate to pull out the lifting lug (refer to the red arrow in the picture below). While he was trying to pull out the lifting lug, the steel plate slipped from the excavator bucket, and IP’s middle finger tip was caught underneath the steel plate (IP was wearing cut resistance gloves during the accident). The IP was immediately sent to clinic for treatment. Doctor gave 4 stitches and 3 days light duty
Thu (13/10) | 13 Oct 2022 | Zone 1 |  | No works at ABH-10
Fri (14/10) | 14 Oct 2022 | Zone 1 | ABH-07 | TT in progress
Fri (14/10) | 14 Oct 2022 | Slurry Tank No.2 |  | Base slab casting started
Fri (14/10) | 14 Oct 2022 | Slurry Tank No.2 |  | Base slab casting completed
Fri (14/10) | 14 Oct 2022 | Power USD Mock Up 1 |  | Pulling and laying of all 6 cables completed
Fri (14/10) | 14 Oct 2022 | Time taken to pull and cut 14m length per cable |  | ~20mins
Sat (15/10) | 15 Oct 2022 | USD casting completed, 20m. Total vol | power | 24m3, G20
Sun (16/10) | 16 Oct 2022 | Zone 3 LP144 |  | Lane closure done for lane rectification work, TMA provided, preparing to commence
Sun (16/10) | 16 Oct 2022 | Zone 1 LP201 |  | Lane closure done & TMA provided
Mon (17/10) | 17 Oct 2022 | Exit 3 |  | End plate cutting and welding works
Mon (17/10) | 17 Oct 2022 | Zone 1 |  | POB status
Mon (17/10) | 17 Oct 2022 | Zone 1 PCN Sidetable |  | Current status
Mon (17/10) | 17 Oct 2022 | Zone 1 ABH05 | next to Blk 269A | TT ongoing, HDB doing their upgrading works oso
Mon (17/10) | 17 Oct 2022 | ULT 1/11 |  | Current status
Mon (17/10) | 17 Oct 2022 | Zone 2 |  | No activity by other contractor
Tue (18/10) | 18 Oct 2022 | Zone 1 ABH-05 | Blk 269A | TT ongoing
Tue (18/10) | 18 Oct 2022 | Exit 3 |  | End plate welding works in progress
Tue (18/10) | 18 Oct 2022 | Exit 3 slurry tank 02 |  | Pipe installation in progress
Tue (18/10) | 18 Oct 2022 | Zone 3 VS area |  | Soil levelling on going for movable barricade installation. Concrete counterweights on the way
Tue (18/10) | 18 Oct 2022 | Zone 1 |  | Tree feeling works by EngLam
Tue (18/10) | 18 Oct 2022 | Zone 3 |  | Unloading of counterweights for movable barricades on going
Wed (19/10) | 19 Oct 2022 | Zone 2 |  | EL works at center island
Wed (19/10) | 19 Oct 2022 | ABH 05 |  | Hand augering continue. Balance 1m
Wed (19/10) | 19 Oct 2022 | Exit 3 |  | End plate welding works continue
Wed (19/10) | 19 Oct 2022 | Slurry tank 2 |  | Access panel installation on going
Wed (19/10) | 19 Oct 2022 | Slurry tank 1 |  | Pipe inlet/outlet installation on going
Wed (19/10) | 19 Oct 2022 | Zone 2 slip road |  | USD still no work. Chasing Ambi to arrange power duct formwork dismantling and arrange Telco Duct lean concrete
Thu (20/10) | 20 Oct 2022 | Exit 3 |  | End plate for dwall welding continue. 1 plate around 20m
Thu (20/10) | 20 Oct 2022 | Slurry tank 1 |  | Water tightness test. Can see water gushing at the joint. 🤭
Thu (20/10) | 20 Oct 2022 | Zone 1 | ABH-05 | Setting up work only, water top up in progress
Thu (20/10) | 20 Oct 2022 | Zone 1 |  | POB status
Thu (20/10) | 20 Oct 2022 | Zone 1 LP2 |  | PCN side table status
Thu (20/10) | 20 Oct 2022 | Zone 2 |  | No activity by other contractor
Fri (21/10) | 21 Oct 2022 | MC 96 |  | Cutter body alignment plate welding works
Fri (21/10) | 21 Oct 2022 | Zone 2 |  | Machinery and equipment shifting to north ramp for micropile works
Fri (21/10) | 21 Oct 2022 | Zone 1 |  | POB status
Fri (21/10) | 21 Oct 2022 | Zone 1 |  | PCN Sidetable, reinstatement work ongoing
Fri (21/10) | 21 Oct 2022 | Zone 2 |  | No activity by other contractor
Sat (22/10) | 22 Oct 2022 | Gate 5 |  | Preparation work for construction of inspection tower for soil dispo
Sat (22/10) | 22 Oct 2022 | Zone 1 |  | POB works by other contractor
Sat (22/10) | 22 Oct 2022 | Zone 1 |  | ABH5 no activity observed
Sat (22/10) | 22 Oct 2022 | Zone 2 |  | No activity of other contractor
Sat (22/10) | 22 Oct 2022 | Zone 3 |  | Hoarding panel installation continue
Sat (22/10) | 22 Oct 2022 | Zone 3 |  | ECS completed work for the day
Sat (22/10) | 22 Oct 2022 | Exit 3 |  | End plate cutting and welding works continue
Sat (22/10) | 22 Oct 2022 | Slurry tank 2 |  | Cable termination for pump and agitator
Sat (22/10) | 22 Oct 2022 | Slurry tank 2 |  | Water test continue. Still got leak
Tue (25/10) | 25 Oct 2022 | Zone 1 PCN Sidetable |  | Current status
Tue (25/10) | 25 Oct 2022 | Exit 3 |  | End plate cutting and welding continue. One more set to weld
Tue (25/10) | 25 Oct 2022 | Zone 2 |  | No activity by other contractor
Wed (26/10) | 26 Oct 2022 | Gate 5 |  | Inspection tower for soil disposal erection continue
Thu (27/10) | 27 Oct 2022 | Exit 3 |  | End plate welding continue
Thu (27/10) | 27 Oct 2022 | Zone 2 north ramp |  | Location of micropiles along manhole is very close to the fencing with less than 500mm. Singtec feedback their Rig cannot work with this kind of set up. WH to check with their design team
Thu (27/10) | 27 Oct 2022 | ABH-05 |  | No activity
Thu (27/10) | 27 Oct 2022 | MC96 |  | Cutterbody maintenance works ongoing
Fri (28/10) | 28 Oct 2022 | Exit 3 |  | End plate for water stop welding work continue
Fri (28/10) | 28 Oct 2022 | Exit 3 |  | Levelling in progress for storage area
Fri (28/10) | 28 Oct 2022 | Slurry tank 2 |  | Bolt tightening on going
Fri (28/10) | 28 Oct 2022 | Zone 2 North ramp |  | Hardcore and steel plate laying for micropile rig platform
Fri (28/10) | 28 Oct 2022 | Zone 2 |  | DE143 works at junction area
Fri (28/10) | 28 Oct 2022 | Zone 1 |  | POB demolition work status by other contractor
Fri (28/10) | 28 Oct 2022 | Zone 2 |  | No activity of other contractor
Fri (28/10) | 28 Oct 2022 | Dw002 |  | Bottom rebar cage on site
Fri (28/10) | 28 Oct 2022 | Zone 3 exit 1 |  | Hoarding installation continue
Fri (28/10) | 28 Oct 2022 | Zone 3 |  | No activity of other contractor
Fri (28/10) | 28 Oct 2022 | Zone 4 |  | No activity of other contractor
Fri (28/10) | 28 Oct 2022 | Zone 3 Mapletree |  | No activity as Exit 1 hoarding is still in progress. Hoarding materials are barricaded up
Fri (28/10) | 28 Oct 2022 | Zone 3 |  | Replacement of dented panels for moveable hoarding. TMA scheduled for tmr for moveable hoarding installation
Fri (28/10) | 28 Oct 2022 | Zone 4 |  | DE143 working within hoarding. No activity by other contractors
Sat (29/10) | 29 Oct 2022 | Zone 2 |  | No activity by other contractors
Sat (29/10) | 29 Oct 2022 | Exit 3 |  | Levelling and Steel plate laying ongoing. To shift materials there later
Sat (29/10) | 29 Oct 2022 | Zone 3 Mapletree Block 4 |  | B&T contractor for loading bay construction is onsite
Sat (29/10) | 29 Oct 2022 | DW002 |  | 2/8nos. Of rebar cage delivered
Sat (29/10) | 29 Oct 2022 | Zone 2 |  | Washbay no activity. WHDA requested 1 more week for rectification
Sat (29/10) | 29 Oct 2022 | Gate 5 |  | Painting of soil inspection tower ongoing
Sat (29/10) | 29 Oct 2022 | Exit 1 |  | Moveable hoarding works in progress. To complete by today
Sat (29/10) | 29 Oct 2022 | Exit 3 |  | Levelling ongoing. Stopends shifted to that area
Sat (29/10) | 29 Oct 2022 | Zone 3 Mapletree Blk 4 |  | B&T continuing to remove cobblestones. B&T to cover exposed area with canvas once completed
Sat (29/10) | 29 Oct 2022 | Exit 1 |  | Moveable hoarding completed. Housekeeping ongoing
Sat (29/10) | 29 Oct 2022 | Zone 3 |  | No activity by other contractors
Sat (29/10) | 29 Oct 2022 | Zone 4 |  | No activity by other contractors
Sat (29/10) | 29 Oct 2022 | Zone 1 |  | DE143 working within hoarding area
Sat (29/10) | 29 Oct 2022 | Zone 2 |  | DE143 working at Pasir Ris Dr 3 junction
Mon (31/10) | 31 Oct 2022 | Zone 1 PCN Sidetable |  | Current status
Mon (31/10) | 31 Oct 2022 | ABH-05 |  | No activity
Mon (31/10) | 31 Oct 2022 | ULT1/11 |  | No activity
Mon (31/10) | 31 Oct 2022 | Exit 3 |  | Slurry guidewall formworks assembly. Today plan LSS casting
Mon (31/10) | 31 Oct 2022 | Gate 5 |  | CCTV installation at inspection tower
Mon (31/10) | 31 Oct 2022 | Exit 3 |  | Slurry guidewall for casting. LSS ordered. Highlighted to clear the water
Tue (01/11) | 01 Nov 2022 | Zone 3 Mapletree |  | Manual excavation ongoing for hoarding footing. 13 nos. Completed. To cast footing today
Tue (01/11) | 01 Nov 2022 | Zone 2 |  | No activity by other contractor
Tue (01/11) | 01 Nov 2022 | Exit 3 |  | Hardcore levelling in progress
Tue (01/11) | 01 Nov 2022 | Exit 3 |  | Flood lights stand fabrication
Wed (02/11) | 02 Nov 2022 | Zone 2 |  | No activity by other contractor
Wed (02/11) | 02 Nov 2022 | Gate 5 |  | Diversion of drain pipe to facilitate guidewall and dwall construction
Wed (02/11) | 02 Nov 2022 | Zone 1 Blk 269A |  | TT to locate sewer line along ABH-6 alignment, PTD signed
Thu (03/11) | 03 Nov 2022 | Zone 1 | Blk 269A/ ABH-06 | TT started
Thu (03/11) | 03 Nov 2022 | Zone 1 | Blk 269A | ATT-HDB-4: backfilling ongoing
Fri (04/11) | 04 Nov 2022 | Exit 3 |  | Balance platform area need to re-arrange steel plates
Fri (04/11) | 04 Nov 2022 | Exit 3 |  | Ramp access steel plate welding
Fri (04/11) | 04 Nov 2022 | Mapple tree blk 2 |  | Manual excavation for hoarding footing in progress. Today target to cast around 28 nos
Fri (04/11) | 04 Nov 2022 | Zone 3 |  | No activity of other contractor
Fri (04/11) | 04 Nov 2022 | Zone 4 |  | No activity of other contractor
Fri (04/11) | 04 Nov 2022 | Zone 3 junction |  | EL works for drain works
Fri (04/11) | 04 Nov 2022 | Exit 1 |  | Gate entrance plate welding
Fri (04/11) | 04 Nov 2022 | Zone 3 exit 1 |  | Silt fence shifting
Fri (04/11) | 04 Nov 2022 | BH3 |  | Trial trench started
Fri (04/11) | 04 Nov 2022 | Zone 2 North ramp |  | Rebar installation for wall and beam in progress
Fri (04/11) | 04 Nov 2022 | Zone 2 |  | No activity of other contractor
Fri (04/11) | 04 Nov 2022 | Zone 1 blk 269A |  | ATT HDB 06 excavation on going
Fri (04/11) | 04 Nov 2022 | Zone 2 mapple tree blk 2 |  | Total hoarding footing casting done today is 30 nos
Sat (05/11) | 05 Nov 2022 | Zone 2 North ramp |  | Rebar and Formwork installation for wall and beam in progress. Target to cast in the afternoon
Sat (05/11) | 05 Nov 2022 | Exit 3 |  | BH03 manual trial trench works in progress
Sat (05/11) | 05 Nov 2022 | Zone 2 |  | No activity of other contractor
Sat (05/11) | 05 Nov 2022 | Zone 1 |  | DE143 POB works
Sat (05/11) | 05 Nov 2022 | Zone 1 Blk 269A |  | ATT HDB 01 excavation ongoing
Sat (05/11) | 05 Nov 2022 | Zone 3, Exit 1 |  | DE143 box culvert works at Loyang way
Sat (05/11) | 05 Nov 2022 | Zone 3, Exit 1 |  | Currently, no activity
Sat (05/11) | 05 Nov 2022 | Zone 4 |  | No activity of other contractor
Sat (05/11) | 05 Nov 2022 | Zone 3 |  | No activity of other contractor
Sat (05/11) | 05 Nov 2022 | Exit 3 |  | BC cutter temporary shifted for balance levelling works and steel plate laying
Sat (05/11) | 05 Nov 2022 | Zone 2 North ramp |  | Formwork installation in progress for washing bay. Target to cast 5pm
Sat (05/11) | 05 Nov 2022 | Exit 3 |  | Partial backfilling completed for old ecm pond area
Sat (05/11) | 05 Nov 2022 | Zone 2 |  | Washing bay casting completed
Mon (07/11) | 07 Nov 2022 | Trenching commence at 22 |  | 20 hrs
Mon (07/11) | 07 Nov 2022 | 2101 hrs |  | Started recording for excavation works
Tue (08/11) | 08 Nov 2022 | Zone 2 |  | MP4 Pre-drilling started for casing installation
Tue (08/11) | 08 Nov 2022 | Gate 6 |  | North ramp washing bay status. Access backfilling with hardcore on going
Tue (08/11) | 08 Nov 2022 | Zone 2 |  | No activity of other contractor
Tue (08/11) | 08 Nov 2022 | Zone 3 Exit 1 |  | DE143 culvert works ongoing
Tue (08/11) | 08 Nov 2022 | Blk 222 noise meter hit alert level until 8 |  | 20PM. Now better
Wed (09/11) | 09 Nov 2022 | Exit 3 |  | SI rig for BH03 mobilized on site
Wed (09/11) | 09 Nov 2022 | Zone 1 |  | POB status, beam removal 12 Nov @ 1-5am
Wed (09/11) | 09 Nov 2022 | Zone 2 PCN Sidetable |  | Backfilling ongoing
Wed (09/11) | 09 Nov 2022 | TT-0107 | near LP165 | TT for NCE for Singtel & Netlink ongoing
Wed (09/11) | 09 Nov 2022 | Zone 2 |  | No activity by other contractor
Wed (09/11) | 09 Nov 2022 | Old ECM at gate 5 |  | Backfilling done, steel plate laying on going . Will be use as storage area
Wed (09/11) | 09 Nov 2022 | Zone 2 slip road |  | Telco duct 1st stage hardcore material rejected by QPS. To replace material and lean concrete by tomorrow
Wed (09/11) | 09 Nov 2022 | Exit 3 |  | Material shifting
Wed (09/11) | 09 Nov 2022 | Update on Zone 2 Dwall |  | Hi Bernard, we have been stressing to Eric and team that the current rectification made to identified leakage points is unacceptable and that all pipes (flexi and rigid pipes inclusive) shd be replaced immediately, Hence at 6 ish just now Eric came by to inform that preparation is underway for the following:, 1) for rigid pipes joints - All joints to be exposed and shall be replaced with new collar joints and gaskets, 2) for flexi rubber hoses (ttl 11 nos): new ones are coming in by Tues 15 Nov and all will be replaced with new ones, From now till Tues, they will replace all rigid pipes collar and gaskets and will test them progressively. Tues, when the flexi rubber hoses get delivered on-site, they will be installed on same day and testing of whole network to be done on Tues/Wed to the satisfaction of PJT and QPS, As supplies for the new hoses can only come in by next Tuesday, WHDA will backfill back the trench w LSS tomorrow, Mr Woo will come back to us tmr morning on when they shd restart dwall (after pass flow test) as they need to time themselves to make sure they reach G3 [~28m depth] for monitoring at 10pm. Ideally may take them a 24hr timeframe to reach G3, Hope the above is agreeable to you, Meanwhile at current, trench stability is being checked at every 6 hr interval. And trench is being barricaded all around sufficiently with no one allowed to go near. Current trench level is at 9m from top of guide wall. QPS has checked today and informed that depth to bottom of trench has been consistent with no sediment build up
Wed (09/11) | 09 Nov 2022 | Blk 222 |  | Noise reading below allowable level after 8:15PM
Wed (09/11) | 09 Nov 2022 | Exit 3 dwall area |  | Joint inspection for pipe/hose connections for bentonite supply
Thu (10/11) | 10 Nov 2022 | Zone 1 |  | No SI work observed
Thu (10/11) | 10 Nov 2022 | Zone 1 |  | Preparation works for ATT HDB-10
Thu (10/11) | 10 Nov 2022 | Exit 3 |  | BH-03 inspection of SI rig ongoing. Will start after inspection complete
Thu (10/11) | 10 Nov 2022 | Exit 3 |  | Removal of mud hoses in progress
Thu (10/11) | 10 Nov 2022 | Zone 2 |  | No activities towards TPE
Thu (10/11) | 10 Nov 2022 | Zone 2 near junction |  | Road contractor works
Thu (10/11) | 10 Nov 2022 | Micropile | U5b-No.7 | Drilling in progress
Thu (10/11) | 10 Nov 2022 | DW02 |  | Bentonite property checked ✅
Thu (10/11) | 10 Nov 2022 | Gate 5 BH3 |  | Rig inspection completed. Drilling to commence now
Thu (10/11) | 10 Nov 2022 | Exit 3 dwall |  | Bentonite properties check for Dw002
Thu (10/11) | 10 Nov 2022 | Gate 5 |  | BH3 drilling/SPT temporary stop due to rain. current level 6m
Thu (10/11) | 10 Nov 2022 | BH3 |  | Drilling/SPT continue. Current depth at 10m
Thu (10/11) | 10 Nov 2022 | MP7 |  | Grouting in progress
Thu (10/11) | 10 Nov 2022 | Zone 2 |  | Rebar fabrication for micropile in progress. Area lean concreted
Thu (10/11) | 10 Nov 2022 | Exit 3 |  | Tremie pipes installation for LSS backfilling tomorrow at 10 am
Fri (11/11) | 11 Nov 2022 | Dwall-002 |  | Backfilling with LSS started. Total 27m^3
Fri (11/11) | 11 Nov 2022 | Zone 2 |  | Permanent soil pit enclosure PE inspection. He has no adverse comment on the design done on site
Fri (11/11) | 11 Nov 2022 | BH3 |  | SPT at 26m done. Taking out sample. Expected to terminate at 31m with no packer test required
Fri (11/11) | 11 Nov 2022 | Zone 2 |  | Telco duct 1st stage pipe laying in progress. Layers 5-7 on going. Formwork closing to start today and cast by tomorrow
Fri (11/11) | 11 Nov 2022 | MP05 |  | Rebar cage installed. Now preparing to flush sludge
Fri (11/11) | 11 Nov 2022 | MP05 |  | Sludge flushing on going
Fri (11/11) | 11 Nov 2022 | DW02 |  | Bentonite & depth checked, all ok
Fri (11/11) | 11 Nov 2022 | All noise reading at LVC with in range except around 19 |  | 45 hrs. Suspect a noisy motorcycle pass by
Fri (11/11) | 11 Nov 2022 | Noise readings between 8-9 |  | 40 with in limit
Fri (11/11) | 11 Nov 2022 | Exit 3 |  | Dw002 1st bite. Preparation for LSS backfilling. Estimated volume 27 m3
Mon (14/11) | 14 Nov 2022 | zone 2 |  | USD telco formwork rectification as per RTO comment. Concrete cover from PVC to formwork should be 100mm. On site only 60mm
Mon (14/11) | 14 Nov 2022 | Zone 1 | ABH-05 | Preparing to commence work
Mon (14/11) | 14 Nov 2022 | Exit 3 |  | Realignment of rigid pipe and replacement of coupler. Target to complete today until 10pm and fo testing tomorrow
Mon (14/11) | 14 Nov 2022 | Exit 3 |  | Rigid pipe laying in progress
Mon (14/11) | 14 Nov 2022 | Zone 3 exit 1 |  | Tree feeling done for the day. 8 nos
Mon (14/11) | 14 Nov 2022 | MP01 |  | Rebar cage lowered down and installed
Mon (14/11) | 14 Nov 2022 | Mapple tree blk 4 |  | Hoarding footing casting, 11 nos
Mon (14/11) | 14 Nov 2022 | Mapple tree blk 2 |  | Manual excavation for hoarding footing. 6 nos. currently completed to cast also
Mon (14/11) | 14 Nov 2022 | Zone 1 ABH05 |  | Drilling/SPT in progress. Current depth at 14m
Mon (14/11) | 14 Nov 2022 | Exit 3 |  | Rigid pipe connection done at this area. Bentonite circulated and observed no leakage. Informed Mr. Woo to arrange final inspection tomorrow with QPS and LTA before they backfill
Mon (14/11) | 14 Nov 2022 | Zone 2 slip road area |  | Telco duct stage 2 (12m) lean concrete completed
Mon (14/11) | 14 Nov 2022 | MP1 |  | Grouting in progress
Mon (14/11) | 14 Nov 2022 | Exit 3 |  | Mud hose connection to rigid pipe installation in progress
Mon (14/11) | 14 Nov 2022 | BH3 |  | Terminated at 35.60m. Pending confirmation from WH design team before grouting
Tue (15/11) | 15 Nov 2022 | Zone 1 | ABH-05 | Drilling / SPT work ongoing, currently 20m depth
Tue (15/11) | 15 Nov 2022 | Zone 2 |  | Micropile rebar cage fabrication
Tue (15/11) | 15 Nov 2022 | Zone 2 |  | Shelter installation for micropile cube storage
Tue (15/11) | 15 Nov 2022 | Zone 2 |  | No activity by other contractor
Tue (15/11) | 15 Nov 2022 | Zone 2 |  | Working platform preparation for MP9
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Perimeter drain replace with 3 nos 6 inches hose to channel water approved by QECP. This area to backfill hardcore and lay steel plate to install noise barrier
Tue (15/11) | 15 Nov 2022 | Exit 1 |  | Tree felling ongoing for small trees
Tue (15/11) | 15 Nov 2022 | Telco duct stage 2, 12m |  | Pipe laying done. Preparation for formworks closing
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Preparation works in progress to cast and level the vehicular access. Casting will be around 5.30pm. 10m will be cast today
Tue (15/11) | 15 Nov 2022 | Zone 2 MP9 |  | Grouting in progress
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Steel plate laying and backfilling for noise barrier realignment
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Ramp area backfilling continue
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Noise barrier re-installation status. They will work until 10pm
Tue (15/11) | 15 Nov 2022 | Slip road area telco duct stage 2 |  | Formworks closing in progress
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Additional supports to be installed at below the long pipe span
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Additional supports to be installed to reduce the force induced by change of direction of flow
Tue (15/11) | 15 Nov 2022 | Exit 3 |  | Dongah stlop work for the day. Housekeeping
Wed (16/11) | 16 Nov 2022 | Zone 1 |  | ABH 05 resume drilling and SPT works. Current depth 34m
Wed (16/11) | 16 Nov 2022 | Zone 1 | LA/PRD3 | DE143 work status
Wed (16/11) | 16 Nov 2022 | Zone 1 PRD3 |  | Work status by DE143
Wed (16/11) | 16 Nov 2022 | Zone 2 |  | MP10 halt at the moment to verify alignment. WH and QPS now checking with the design team
Wed (16/11) | 16 Nov 2022 | Exit 3 |  | DW002 rebar cage grouting pipe installation
Thu (17/11) | 17 Nov 2022 | Exit 3 |  | Ramp area steel plate welding
Thu (17/11) | 17 Nov 2022 | Exit 3 |  | Hardcore backfilling for noise barrier installation
Thu (17/11) | 17 Nov 2022 | Zone 1 |  | ABH-05 depth termination at 46.45m, preparing to shift to ABH-07
Thu (17/11) | 17 Nov 2022 | Zone 1 PCN Sidetable |  | Current status DE143 works
Thu (17/11) | 17 Nov 2022 | Zone 2 LP170 |  | Railing removal ongoing
Thu (17/11) | 17 Nov 2022 | Zone 2 |  | Bentonite mixing
Thu (17/11) | 17 Nov 2022 | Exit 1 |  | ABH69C SI at 4m depth. Next SI to commence at ABH69D
Thu (17/11) | 17 Nov 2022 | Exit 1 |  | 27 nos of trees felled. Next stage of tree felling to tbc by WHDA
Fri (18/11) | 18 Nov 2022 | Zone 1 ABH 07 |  | Drilling in progress to 6m depth. Termination at 48m
Fri (18/11) | 18 Nov 2022 | Exit-1 |  | Continue removal of tree branches and logs
Fri (18/11) | 18 Nov 2022 | Exit 1 |  | ECB laying on exposed soil area
Fri (18/11) | 18 Nov 2022 | Zone 1 |  | POB demobilition by other contractor status
Fri (18/11) | 18 Nov 2022 | Zone 2 |  | No activity of other contractor
Fri (18/11) | 18 Nov 2022 | Zone 2 |  | Storage area clearing continue. Balance concrete barriers, water pipes and construction bin. Today to clear then tomorrow to start excavation for ECM pond
Sat (19/11) | 19 Nov 2022 | Exit 3 ECM extension |  | Excavation ongoing, PTD signed
Sat (19/11) | 19 Nov 2022 | Exit 3 | perm desander | Noise barrier setting up
Sat (19/11) | 19 Nov 2022 | Zone 2 | MP11 | Final toe confirmed 10.950m from TOC, preparing to lower rebar cage / grouting
Sat (19/11) | 19 Nov 2022 | Zone 3 | Exit 1 | Current status
Sat (19/11) | 19 Nov 2022 | Zone 4 |  | No activity by other contractor
Sat (19/11) | 19 Nov 2022 | Zone 3 |  | No activity by other contractor
Sat (19/11) | 19 Nov 2022 | Zone 3 | JTC / Mapletree | No activity
Sat (19/11) | 19 Nov 2022 | Zone 2 | LP168 -170 | Current status
Sat (19/11) | 19 Nov 2022 | Zone 2 | north ramp | Old washing bay backfilling status
Sat (19/11) | 19 Nov 2022 | Zone 2 | north ramp | MP16 drilling in progress
Sat (19/11) | 19 Nov 2022 | Zone 2 |  | No activity by other contractor
Sat (19/11) | 19 Nov 2022 | Zone 1 | New Loyang Link LP8 | Relocation of bulk meter in progress
Sat (19/11) | 19 Nov 2022 | Zone 1 |  | POB removal status by DE143
Sat (19/11) | 19 Nov 2022 | Zone 2 PCN Sidetable |  | Current status by DE143
Sat (19/11) | 19 Nov 2022 | Zone 1 | Blk 273 | ABH-07 drilling work ongoing, current depth 36/48m. Works till 5pm
Sat (19/11) | 19 Nov 2022 | Exit 1 |  | ABH-69C
Sat (19/11) | 19 Nov 2022 | Gate 5 Access |  | Preparation for casting, excavation for perimeter drain in progress
Tue (22/11) | 22 Nov 2022 | Exit 3 Silo plant area |  | Bentonite pipe laying from old ecm pond to filter press in progress. About 9m. This for pumping of bentonite if there is any leakage to ecm pond
Tue (22/11) | 22 Nov 2022 | Exit 3 |  | Perimeter drain no work observed
Wed (23/11) | 23 Nov 2022 | Zone 1 (TTSN0102) | Blk 269A | IM trial trench for NCE ongoing
Wed (23/11) | 23 Nov 2022 | Zone 2 | PCN Sidetable | DE143 shifted the footpath, removal of existing footpath ongoing
Wed (23/11) | 23 Nov 2022 | Zone 1 | POB removal | Current status by DE143
Wed (23/11) | 23 Nov 2022 | Zone 1 ABH-07 |  | Pending turfing reinstatement
Wed (23/11) | 23 Nov 2022 | ABH-05 |  | Turfing reinstatement complete, balance some materials to be shifted out
Wed (23/11) | 23 Nov 2022 | Zone 1 | ABH-10 | Hand auger ongoing
Wed (23/11) | 23 Nov 2022 | Zone 1 | New Loyang Link | M&P works ongoing by DE143
Wed (23/11) | 23 Nov 2022 | Zone 2 |  | No activity by other contractor
Wed (23/11) | 23 Nov 2022 | Exit 3 |  | Construction of perimeter drain to new ECM pond in progress
Thu (24/11) | 24 Nov 2022 | Zone 2 |  | No activity of other contractor
Thu (24/11) | 24 Nov 2022 | Exit 3 |  | Perimeter drain excavation along slope are commence
Thu (24/11) | 24 Nov 2022 | Exit 3 |  | Cutting of steel plate welding joints to adjust gradient to newly cast vehicular access
Thu (24/11) | 24 Nov 2022 | Exit 3 |  | Regrading works in progress. Backfilling and steel plate laying to the access road level
Thu (24/11) | 24 Nov 2022 | Exit 3 |  | Excavation for perimeter drain ongoing. Target to cast tomorrow
Thu (24/11) | 24 Nov 2022 | Zone 1 POB |  | Column / staircase removal ongoing
Thu (24/11) | 24 Nov 2022 | Zone 2 | PCN Sidetable | Current status
Thu (24/11) | 24 Nov 2022 | Zone 1 PRD3 |  | Pgas TT ongoing, with TMO deployed
Thu (24/11) | 24 Nov 2022 | Zone 1 | ABH-10 | Drilling work ongoing
Thu (24/11) | 24 Nov 2022 | Gate 5 Access |  | Casting / levelling ongoing
Thu (24/11) | 24 Nov 2022 | Zone 2 | North Ramp | MP10 to MP15 lean con completed, levelling done, setting up barricade / housekeeping ongoing
Fri (25/11) | 25 Nov 2022 | Zone 1 POB |  | Staircase / column removal ongoing, DE143 working on both bounds
Fri (25/11) | 25 Nov 2022 | Zone 2 PCN Sidetable |  | Current status
Fri (25/11) | 25 Nov 2022 | Zone 1 | ABH-10 | Drilling ongoing 42m depth
Fri (25/11) | 25 Nov 2022 | Zone 2 north ramp |  | MP32 drilling in progress
Fri (25/11) | 25 Nov 2022 | Zone 1 (TTSN0102) | Blk 269A | IM trial trench for NCE in progress, trying to locate singtel cables
Fri (25/11) | 25 Nov 2022 | Zone 3 |  | No activity by other contractors. Truck broke done at side of Loyang Ave
Fri (25/11) | 25 Nov 2022 | Zone 3 |  | DE143 continuing drain works
Fri (25/11) | 25 Nov 2022 | Exit 3 |  | Continue excavation of perimeter drain along noise barrier alignment. Plan to cast today at 2pm
Sat (26/11) | 26 Nov 2022 | CR106 site office |  | Sign board installation on going
Sat (26/11) | 26 Nov 2022 | Zone 3 |  | No activity of other contractor
Sat (26/11) | 26 Nov 2022 | Zone 4 |  | No activity of other contractor
Sat (26/11) | 26 Nov 2022 | Exit 1 access |  | BRC laying done. Next monday to cast
Sat (26/11) | 26 Nov 2022 | Exit 1 |  | Steel plate laying for vehicle access to expedite tree feeling
Sat (26/11) | 26 Nov 2022 | Zone 3 exit 1 |  | ABH69A- Drilling/SPT in progress
Sat (26/11) | 26 Nov 2022 | Mapple tree blk 2 |  | ATT-JTC-18 trial trench services found
Sat (26/11) | 26 Nov 2022 | Zone 2 |  | No activity of other contractor
Sat (26/11) | 26 Nov 2022 | Zone 1 |  | POB demolition status
Sat (26/11) | 26 Nov 2022 | Zone 1 |  | ABH 06-3 manual excavation on going
Sat (26/11) | 26 Nov 2022 | Zone 2 exit 5 |  | Balance scupper drain (18m) hacking in progress
Sat (26/11) | 26 Nov 2022 | Exit 3 |  | Noise barrier installation started
Sat (26/11) | 26 Nov 2022 | Perimeter drain section C2 |  | Today to cast
Sat (26/11) | 26 Nov 2022 | Exit 3 |  | Noise barrier installation continue
Sat (26/11) | 26 Nov 2022 | Perimeter drain section C2 |  | Casting in progress
Sat (26/11) | 26 Nov 2022 | PMH11 |  | Plate bearing test continue
Sat (26/11) | 26 Nov 2022 | Exit 3 |  | WH plan today to reduce crane boom length from 36.5 to 30.5m
Sat (26/11) | 26 Nov 2022 | Exit 3 |  | Perimeter drain status along the trenching area for d-wall. Noise barrier installation plan to start today
Sat (26/11) | 26 Nov 2022 | Zone 2 |  | Pegging for PMH11 invert level and location
Sun (27/11) | 27 Nov 2022 | Zone 4 |  | DE143 working within hoarding
Sun (27/11) | 27 Nov 2022 | Exit 1 |  | Unloading of material from Exit 3. Casting of site access to be done tmr
Sun (27/11) | 27 Nov 2022 | Exit 3 |  | Removal of concrete barriers beside scupper drain
Sun (27/11) | 27 Nov 2022 | Zone 1 |  | No activity at POB
Mon (28/11) | 28 Nov 2022 | Zone 2 |  | No activity by other contractor
Mon (28/11) | 28 Nov 2022 | Zone 3 | Mapletree | TT ongoing to find corridor for power cables, 2 nos done. 3rd ongoing
Mon (28/11) | 28 Nov 2022 | Zone 3 |  | No activity by other contractor
Mon (28/11) | 28 Nov 2022 | Zone 4 |  | No activity by other contractor
Mon (28/11) | 28 Nov 2022 | Zone 3 | ABH-69A | Currently 32m drilling depth
Mon (28/11) | 28 Nov 2022 | Zone 3 | Loyang Way LP19 | DE143 status, pipe sleeve laying
Mon (28/11) | 28 Nov 2022 | PMH11 |  | Area preparation for lean concreting
Mon (28/11) | 28 Nov 2022 | Zone 2 | PCN Sidetable PRD3 LP2 | DE143 work status for road diversion
Mon (28/11) | 28 Nov 2022 | Zone 1 POB removal |  | DE143 working along Loy Ave to TPE bound
Mon (28/11) | 28 Nov 2022 | Zone 1 | New Loyang Link | Pgas / DE143 working along here
Mon (28/11) | 28 Nov 2022 | Zone 1 ABH6-3 | Blk269A | Manual excavation for TT ongoing
Mon (28/11) | 28 Nov 2022 | Exit 3 |  | D-wall panel 002 1st bite trenching started
Mon (28/11) | 28 Nov 2022 | MP36 |  | Grouting ongoing
Mon (28/11) | 28 Nov 2022 | PMH11 area |  | Lean concrete on going
Mon (28/11) | 28 Nov 2022 | Zone 2 |  | Capping beam rebar works installation continue
Tue (29/11) | 29 Nov 2022 | Exit 3 |  | Material clearing to continue drain (section D)
Tue (29/11) | 29 Nov 2022 | Zone 1 | ABH6-3 | TT completed, workers having break, will resume later
Tue (29/11) | 29 Nov 2022 | Zone 1 | POB removal | DE143 working at slow lane along Loyang Ave towards TPE
Tue (29/11) | 29 Nov 2022 | Zone 1 | New Loyang Link | Pgas TT ongoing
Tue (29/11) | 29 Nov 2022 | Zone 2 | North Ramp | Concrete for capping beam arrived on site, slump / cube test ongoing
Tue (29/11) | 29 Nov 2022 | Zone 2 | North Ramp | Capping beam casting started, vol: 7m3 C40
Tue (29/11) | 29 Nov 2022 | Zone 2 |  | Capping beam rebar tying on going and preparation for formworks closing. Today plan to cast after lunch
Wed (30/11) | 30 Nov 2022 | Zone 1 (TTSN0103) | Loy Ave LP201 | TT ongoing for NCE
Wed (30/11) | 30 Nov 2022 | Zone 1 |  | Rig shifting to ABH6-3
Wed (30/11) | 30 Nov 2022 | Zone 1 LP 202 | Loy Ave slow lane to TPE | POB removal ongoing by DE143
Wed (30/11) | 30 Nov 2022 | Zone 2 | PCN Sidetable | Current status work by DE143
Wed (30/11) | 30 Nov 2022 | Exit 1 |  | Levelling ongoing for access casting
Wed (30/11) | 30 Nov 2022 | Exit 1 |  | DE143 working on RCU under our gate access area
Wed (30/11) | 30 Nov 2022 | Zone 3 |  | BH118 trial trench ongoing
Wed (30/11) | 30 Nov 2022 | Exit 3 |  | End plate ans water stop inspection just completed. Now preparing for installation
Wed (30/11) | 30 Nov 2022 | Zone 3 |  | Trench near Mapletree water tank done to check waterpipe alignment. 30m of 22kV pipe laying done as of yesterday
Wed (30/11) | 30 Nov 2022 | Zone 3 |  | Both rigs shifted to Dwall BH location
Wed (30/11) | 30 Nov 2022 | Exit 3 |  | DW002 desanding continue
Thu (01/12) | 01 Dec 2022 | Zone 1 | Blk 275 Loy Ave | *works by DE143* Tan Huan tree cutting work
Thu (01/12) | 01 Dec 2022 | Zone 1 (TTSN0103) | Loy Ave LP201 | No activity
Thu (01/12) | 01 Dec 2022 | Zone 1 | New Loyang Link | Current status, pgas no work today only DE143 working here
Thu (01/12) | 01 Dec 2022 | Zone 1 | Loy Ave to TPE | POB removal ongoing by DE143
Thu (01/12) | 01 Dec 2022 | Zone 3 |  | BH113 manual excavation completed. Preparation to start hand augering
Thu (01/12) | 01 Dec 2022 | Zone 3 exit 1 |  | Bundwall construction along fencing. Concrete lining today
Thu (01/12) | 01 Dec 2022 | Zone 3 |  | Tree feeling on going. 2 nos
Thu (01/12) | 01 Dec 2022 | Zone 4 |  | No activity of other contractor
Thu (01/12) | 01 Dec 2022 | Zone 3 |  | No activity of other contractor
Thu (01/12) | 01 Dec 2022 | Zone 3 | substation | ECS setting up hoarding
Thu (01/12) | 01 Dec 2022 | Zone 3 | exit 1 access | De143 work status
Thu (01/12) | 01 Dec 2022 | Lapping length between 3rd & 4th cage |  | 2.24m. Now installation of u-clips, 16nos at each face
Thu (01/12) | 01 Dec 2022 | MC96 |  | Preparation to dismantle cutter blade to replaced with 800mm width for slurry wall
Thu (01/12) | 01 Dec 2022 | Noise reading for Blk222 is within allowable level after 8 |  | 15PM
Thu (01/12) | 01 Dec 2022 | Zone 2 | LP170 centre median for LVC bus stop relocation | Manual excavation 200mm only ongoing
Fri (02/12) | 02 Dec 2022 | Zone 1 ABH6-2 |  | TT ongoing
Fri (02/12) | 02 Dec 2022 | Loy Ave Blk 275 |  | DE143 working here
Fri (02/12) | 02 Dec 2022 | Exit 3 |  | Panel DW002, waiting for last 2 trucks, 18m3
Fri (02/12) | 02 Dec 2022 | Zone 3 |  | No activity of other contractor
Fri (02/12) | 02 Dec 2022 | Zone 4 |  | No activity of other contractor
Fri (02/12) | 02 Dec 2022 | Zone 3 exit 1 |  | Bundwall construction along fencing line continue
Fri (02/12) | 02 Dec 2022 | Exit 1 |  | Washing boot construction
Fri (02/12) | 02 Dec 2022 | Exit 1 |  | No silty discharge to public drain observed
Fri (02/12) | 02 Dec 2022 | Exit 3 |  | Perimeter section D casting on going
Fri (02/12) | 02 Dec 2022 | Noise reading between 7-7 |  | 10pm, crane in operation and excavator for casting of perimeter drain
Fri (02/12) | 02 Dec 2022 | Exit 3 |  | DW002 preparation for base grouting 1st stage. Tentative 12-1 am ( 12 hrs) after casting
Sat (03/12) | 03 Dec 2022 | MC96 |  | Continue changing of cutters for geofoam trenching work
Sat (03/12) | 03 Dec 2022 | Zone 2 | Exit 3 | Setting up of clayshock plant ongoing
Sat (03/12) | 03 Dec 2022 | Zone 3 | Mapletree Blk 4 | 22kV cable protection pipe laying, excavation continue
Sat (03/12) | 03 Dec 2022 | Zone 3 |  | No activity by other contractor
Sat (03/12) | 03 Dec 2022 | Zone 4 |  | No activity by other contractor
Sat (03/12) | 03 Dec 2022 | Zone 3 Exit 1 | Loyang Way LP18 | DE143 drain work
Sat (03/12) | 03 Dec 2022 | Zone 3 Exit 1 |  | Survey marking for ECM pond excavation
Sat (03/12) | 03 Dec 2022 | Zone 3 BH-113 |  | Rock coring ongoing, 19.3m depth
Sat (03/12) | 03 Dec 2022 | BH-116 |  | TT ongoing
Sat (03/12) | 03 Dec 2022 | Zone 2 |  | No activity by other contractor
Sat (03/12) | 03 Dec 2022 | Zone 2 PCN Sidetable |  | Current status
Sat (03/12) | 03 Dec 2022 | Zone 1 PRD3 |  | DE143 working middle lane
Sat (03/12) | 03 Dec 2022 | Zone 1 Loy Ave centre median |  | (POB removal) DE143 hacking works ongoing
Sat (03/12) | 03 Dec 2022 | ABH6-1 |  | TT ongoing
Sat (03/12) | 03 Dec 2022 | Zone 2 | North Ramp | MP18 rebar cage installation ongoing
Sat (03/12) | 03 Dec 2022 | Zone 2 | slip rd/pmh construction | Vibro platform pending rectification
Sat (03/12) | 03 Dec 2022 | Zone 2 Capping Beam |  | 6nos of 6m length steel plates installed, Monday will continue
Sat (03/12) | 03 Dec 2022 | Zone 2 | North Ramp | MP20 coring work ongoing
Sun (04/12) | 04 Dec 2022 | Zone 3 Exit 1 |  | Scaffold inspection tower erection by KTC in progress
Sun (04/12) | 04 Dec 2022 | Zone 4 |  | No activity of other contractor on both bounds
Sun (04/12) | 04 Dec 2022 | Zone 3 |  | No activity of other contractor
Sun (04/12) | 04 Dec 2022 | Zone 2 |  | No activity of other contractor
Sun (04/12) | 04 Dec 2022 | DW002 |  | 2nd stage grouting in progress
Sun (04/12) | 04 Dec 2022 | Exit 3 |  | Geofoam counterweight fabrication continue. Framing for geofoam still not done. Chasing Dongah to expedite to start trenching by Tuesday as per target
Mon (05/12) | 05 Dec 2022 | Zone 2 LP194 |  | 6nos of trees under Phase E3 is being felled by DE143
Mon (05/12) | 05 Dec 2022 | Zone 1 | POB removal | Current work status by DE143
Mon (05/12) | 05 Dec 2022 | Zone 1 ABH6-2 |  | Preparing to start drilling work
Mon (05/12) | 05 Dec 2022 | Zone 1 | PRD3 | DE143 working these two locations. Centre median removal & premix laying / compaction
Mon (05/12) | 05 Dec 2022 | Exit 3 |  | Geofoam counterweight welding works continue. Today plan to complete and start geofoam frame
Tue (06/12) | 06 Dec 2022 | MPH11 |  | Base slab bottom bar laying in progress. Target to cast tomorrow
Tue (06/12) | 06 Dec 2022 | Exit 3 |  | Geofoam frame fabrication status. Tonight WH plan to complete fabrication
Tue (06/12) | 06 Dec 2022 | Exit - 1 |  | Casting of generator storage area and partial of ECM pond on going
Tue (06/12) | 06 Dec 2022 | Zone 1 |  | DE143 working along Loy Ave slip rd to PRD3
Tue (06/12) | 06 Dec 2022 | Zone 1 POB removal |  | DE143 working slow lane along Loyang Avenue to TPE
Wed (07/12) | 07 Dec 2022 | Exit 3 |  | Area preparation for pre-excavation for slurry wall
Thu (08/12) | 08 Dec 2022 | Zone 1 LP198 |  | Gridlocked along Loy Ave to CV as DE143 working along slow lane
Thu (08/12) | 08 Dec 2022 | Zone 1 LP201 | towards TPE | DE143 working along slow lane, continue POB removal
Thu (08/12) | 08 Dec 2022 | Zone 1 | New Loyang Link | Only DE143 working here
Thu (08/12) | 08 Dec 2022 | PMH11 |  | Slope casting in progress at near the perimeter drain
Thu (08/12) | 08 Dec 2022 | Exit 3 |  | Trenching completed for 1st panel slurry wall. Afternoon will continue with the lowering of geofoam cage and clayshock injection
Thu (08/12) | 08 Dec 2022 | Exit 3 |  | Counterweight spliced plate preparation for welding. So far they are not fabricating new counterweight. FYI
Fri (09/12) | 09 Dec 2022 | Exit 1 |  | Inspection tower erection completed. Balance CCTV installation
Fri (09/12) | 09 Dec 2022 | Exit 3 |  | The counterweight has been safely shifted to Geoframe area. (Crane radius: 15.4m, SWL: 31ton, Lifting load: 22.7ton - 73% of SWL) Within acceptable range
Fri (09/12) | 09 Dec 2022 | Exit 3 |  | Geofoam counterweight installation of additional stiffener
Fri (09/12) | 09 Dec 2022 | Mapletree Blk 2 |  | Trial trench for BH14 ongoing. BH15 to be done next
Fri (09/12) | 09 Dec 2022 | Zone 1 | to CV | DE143 working along slow lane, for traffic light cable & pipe laying
Fri (09/12) | 09 Dec 2022 | Exit 1 |  | Shifting of steel plates ongoing for lorry crane to access the area and deliver genset at 11am
Sat (10/12) | 10 Dec 2022 | Noise Reading at LVC between 12-12 |  | 50 when there's no work on site, maybe due to noisy passing vehicles
Sun (11/12) | 11 Dec 2022 | Exit 3 |  | Bentonite checks completed. All data taken within range
Sun (11/12) | 11 Dec 2022 | Exit 3 |  | No activity
Sun (11/12) | 11 Dec 2022 | PMH-11 |  | Formwork assembly in progress
Sun (11/12) | 11 Dec 2022 | Zone 3 |  | No activity of other contractor
Sun (11/12) | 11 Dec 2022 | Zone 4 |  | DE143 working toward changi village rd
Sun (11/12) | 11 Dec 2022 | Exit 1 |  | ECM Netting installation and painting works in progress
Sun (11/12) | 11 Dec 2022 | Exit 1 | Hoarding area | Caution Signages pasting ongoing around the hoarding perimeter
Sun (11/12) | 11 Dec 2022 | Zone 1 |  | No activity of other contractor
Sun (11/12) | 11 Dec 2022 | Zone 2 |  | No activity of other contractor
Sun (11/12) | 11 Dec 2022 | Exit 3 |  | Bentonite check done. All within acceptable range
Sun (11/12) | 11 Dec 2022 | Mapletree | Blk2 | Preparation works for 1 no. of tree felling
Mon (12/12) | 12 Dec 2022 | PMH-11 |  | Wall rebar fixing and fabricating of formworks in progress
Mon (12/12) | 12 Dec 2022 | ABH6-2 |  | 39.46m depth, 3rd permeability test ongoing & will resume drilling work once the test is completed, target to complete tmr & start ABH6-1
Mon (12/12) | 12 Dec 2022 | Zone 1 | to CV | DE143 street light / traffic light team working along middle lane
Mon (12/12) | 12 Dec 2022 | Zone 1 | to TPE | Pgas working along middle lane with 3 TMOs, now they having their break
Mon (12/12) | 12 Dec 2022 | Zone 1 | POB Removal | Turfing works completed (this is to TPE)
Mon (12/12) | 12 Dec 2022 | Zone 1 | New Loyang Link | DE143 working here
Mon (12/12) | 12 Dec 2022 | Zone 2 | USD Power Duct | 12m length casting ongoing
Mon (12/12) | 12 Dec 2022 | Zone 2 | North Ramp | Manual excavation ongoing from MP16 onwards
Tue (13/12) | 13 Dec 2022 | Zone 2 |  | USD construction telco stage 3 phase 2, pipe laying on going. Target to cast late afternoon today
Tue (13/12) | 13 Dec 2022 | Zone 2 | aft Loy Ave/PRD3 junction | DE143 working middle lane to CV
Tue (13/12) | 13 Dec 2022 | Zone 1 | Loy Ave to TPE | Works alr completed, lane opened
Tue (13/12) | 13 Dec 2022 | Zone 2 north ramp |  | USD telco stage 3 phase 2 formworks closing. Still target to cast today, waiting for rain to subside
Tue (13/12) | 13 Dec 2022 | PMH11 |  | Formworks closing status. Wall and slab to cast as monolithic
Tue (13/12) | 13 Dec 2022 | Exit 3 |  | Preparation for clayshock grouting
Tue (13/12) | 13 Dec 2022 | SW002 |  | Clayshock injection stopped for the day, total 4538L injected. They will resume tmr am instead
Tue (13/12) | 13 Dec 2022 | PMH11 |  | Shoring erection for topslab formwork assembly. Side formwork inner face completed
Wed (14/12) | 14 Dec 2022 | Clayshock grouting stopped at 9 |  | 55PM. Will continue grouting tomorrow
Wed (14/12) | 14 Dec 2022 | Zone 1 |  | DE143 working on the middle lane before Pasir Ris Dr3 junction
Thu (15/12) | 15 Dec 2022 | PMH11 |  | Top slab formwork assembly and shoring jack adjusting. Work slow due to wet weather
Thu (15/12) | 15 Dec 2022 | Zone 2 Changi bound temp bus stop location |  | PCN diversion cast yesterday. Now they are preparing the area to open for public. Foothpath and PCN shared width is 2.6m
Thu (15/12) | 15 Dec 2022 | Zone 2 towards TPE |  | Starhub working for pipe laying
Thu (15/12) | 15 Dec 2022 | Zone 3 |  | Tree feeling towards CV, banksmen provided on both sides
Thu (15/12) | 15 Dec 2022 | Zone 3 maple tree blk 2 |  | BH13 hand augering temporarily stopped due to tree feeling
Thu (15/12) | 15 Dec 2022 | Zone 3 Mapletree blk 4 |  | 22kV pipe laying no activity observed
Thu (15/12) | 15 Dec 2022 | Zone 3 exit 1 |  | ECM maintenance. Washing bay plan to start rebar works on monday. Waiting for subcon as per San
Thu (15/12) | 15 Dec 2022 | Exit 1 |  | Top soil cutting. Soil disposal to start from tomorrow. Dispose to C821A
Thu (15/12) | 15 Dec 2022 | Zone 4 |  | No activity of other contractor
Thu (15/12) | 15 Dec 2022 | Zone 2 |  | DE143 works at center median
Thu (15/12) | 15 Dec 2022 | Zone 2 towards CV |  | Lamp post dismantling in progress, LP166
Thu (15/12) | 15 Dec 2022 | Mapple tree blk 2 |  | Loading bay excavation and removal of existing kerb
Thu (15/12) | 15 Dec 2022 | PMH-11 |  | Formwork closing in progress
Thu (15/12) | 15 Dec 2022 | BLK 2 Mapletree Loading Bay |  | Excavation ongoing. BRC to be laid today and tmr cast
Thu (15/12) | 15 Dec 2022 | Exit 1 |  | ECM pond excavation ongoing
Thu (15/12) | 15 Dec 2022 | SW01 |  | Pre-excavation started
Fri (16/12) | 16 Dec 2022 | Slip road CH 1+180-200 |  | Sub grade trimming on going. Today they will start laying sub base using RCA
Fri (16/12) | 16 Dec 2022 | Zone 2 |  | Hoarding shifting behind new temp bus stop location
Fri (16/12) | 16 Dec 2022 | Zone 2 |  | Temp bus stop at side table excavation to 400mm for base slab and 600mm for bollard continue. Plan to cast slab tomorrow
Fri (16/12) | 16 Dec 2022 | Zone 3 towards CV |  | 6/6 tree feeling on going
Fri (16/12) | 16 Dec 2022 | Zone 3 |  | Maple tree blk 2 new loading bay casting in progress
Fri (16/12) | 16 Dec 2022 | Zone 3 exit 1 |  | BRC mesh bending for washing way reinforcement
Fri (16/12) | 16 Dec 2022 | Zone 3 |  | No activity of other contractor
Fri (16/12) | 16 Dec 2022 | Zone 2 LP 194 | to TPE | DE143 working along centre median for streetlight pipe laying
Fri (16/12) | 16 Dec 2022 | Zone 1 | to CV | No activity by other contractor
Fri (16/12) | 16 Dec 2022 | ABH6-1 |  | 2nd permeability test ongoing, from 34.99m to 35.99m
Fri (16/12) | 16 Dec 2022 | Loy Ave LP185 | to TPE | StarHub term contractor pipe laying 2x3 ongoing
Fri (16/12) | 16 Dec 2022 | Exit 1 |  | ECM pond excavation ongoing
Fri (16/12) | 16 Dec 2022 | Exit 1 |  | Observed workers attempting to place BRC into the ECM pond from the top of the slope. Safety reminded the workers to use the proper access to enter the ECM pond
Fri (16/12) | 16 Dec 2022 | Zone 3 |  | TMA provided for SI materials shifting to Mapletree
Fri (16/12) | 16 Dec 2022 | SW01 |  | Clayshock grouting started
Fri (16/12) | 16 Dec 2022 | Zone 2 |  | Yellow fencing and netting installation. Tomorrow to installation white fence
Sat (17/12) | 17 Dec 2022 | ABH6-1 |  | 3rd permeability test ongoing, from 38.94m to 39.94m
Sat (17/12) | 17 Dec 2022 | Zone 1 |  | DE143 working within the boundary
Sat (17/12) | 17 Dec 2022 | Mapletree | Blk4 | Ecm pond excavation
Sat (17/12) | 17 Dec 2022 | BH-24 |  | Manual trial trench works
Sat (17/12) | 17 Dec 2022 | Exit 1 |  | Soil disposal ongoing
Sat (17/12) | 17 Dec 2022 | Exit 1 |  | BRC laying for washing bay
Sat (17/12) | 17 Dec 2022 | Near Exit 1 |  | DE143 & CR1070 working
Sat (17/12) | 17 Dec 2022 | Zone 4 |  | No activity of other contractor
Sat (17/12) | 17 Dec 2022 | Zone 3 |  | No activity of other contractor
Sat (17/12) | 17 Dec 2022 | Exit1 |  | Housekeeping ongoing. Today soil disposal - 22 loads out. Tomorrow to continue soil disposal for balance
Sat (17/12) | 17 Dec 2022 | Mapletree | Blk 4 | Trial trench works completed. Backfilling ongoing
Sun (18/12) | 18 Dec 2022 | Gate 6 |  | Hoarding installation ongoing
Sun (18/12) | 18 Dec 2022 | Exit 3 |  | Storage area extension in progress
Sun (18/12) | 18 Dec 2022 | Zone 2 |  | No activity by other contractors
Sun (18/12) | 18 Dec 2022 | Zone 1 |  | No activity by other contractors
Sun (18/12) | 18 Dec 2022 | Mapletree Blk2 |  | Excavation ongoing by B&T
Sun (18/12) | 18 Dec 2022 | Exit 3 |  | Shelter completed
Sun (18/12) | 18 Dec 2022 | Mapletree blk 2 |  | Excavation done. Clearing of debris ongoing. 6m of pipes to be laid today
Sun (18/12) | 18 Dec 2022 | Zone 3 |  | No activity at Blk4 ECM pond area. Side gate was provided on Friday and is locked
Sun (18/12) | 18 Dec 2022 | Zone 2 |  | No Activity
Sun (18/12) | 18 Dec 2022 | Exit 1 |  | Housekeeping ongoing
Sun (18/12) | 18 Dec 2022 | Exit 1 |  | Status of washbay. No activity
Sun (18/12) | 18 Dec 2022 | Mapletree Blk2 |  | Backfilled after pipes laid
Sun (18/12) | 18 Dec 2022 | Exit 3 |  | BC cutter modification ongoing
Sun (18/12) | 18 Dec 2022 | Exit 3 |  | Hydraulic oil topping up for machine
Sun (18/12) | 18 Dec 2022 | Zone 3 |  | No activity by other contractors. Grass cutting ongoing
Sun (18/12) | 18 Dec 2022 | Exit 1 |  | Soil disposal in progress. 5 loads
Sun (18/12) | 18 Dec 2022 | Exit 1 |  | DE143 roadworks ongoing
Sun (18/12) | 18 Dec 2022 | Exit 1 |  | Clear water discharging from ECM
Sun (18/12) | 18 Dec 2022 | Zone 4 |  | DE143 working within their hoarding
Sun (18/12) | 18 Dec 2022 | Exit 1 |  | Shelter construction for genset in progress
Mon (19/12) | 19 Dec 2022 | Exit 2 | substation | Tree felling in progress. TMA on site
Mon (19/12) | 19 Dec 2022 | Monitoring until 23 |  | 30 hrs. 2nd VMS monitoring estimated around 3:30 am once reach GIII rock
Mon (19/12) | 19 Dec 2022 | BH-13 at Blk 2 Mapletree |  | Current depth at 33m. Coring in progress
Mon (19/12) | 19 Dec 2022 | Slip road CH 1+120-160 |  | Road kerb and formwork installation till 10pm. Target to cast tomorrow
Tue (20/12) | 20 Dec 2022 | ABH6-1 |  | 9m drilling ongoing
Tue (20/12) | 20 Dec 2022 | Zone 1 | previously POB area | Grano works by DE143
Tue (20/12) | 20 Dec 2022 | 10 |  | 15hrs: DW-004 excavation resume from 28.3m from TOGW
Tue (20/12) | 20 Dec 2022 | Zone 2 LP187 | to TPE | Mo Guan working at Lane 3
Tue (20/12) | 20 Dec 2022 | DW004 |  | Bentonite properties checking in progress
Tue (20/12) | 20 Dec 2022 | Zone 2 Loy Ave Centre Median LP170 |  | Utility briefing held prior to tree root removal
Tue (20/12) | 20 Dec 2022 | PDR3 |  | Tonight PGas will only work at this location (around 3m) for gas pipe laying. Tomorrow they will work at the other side of the road
Tue (20/12) | 20 Dec 2022 | Zone 1 Loy Ave Junction | to TPE | DE143 traffic / street light team working middle lane
Wed (21/12) | 21 Dec 2022 | DW-004 |  | End plate + waterstop installation
Wed (21/12) | 21 Dec 2022 | Z2 LP170 Centre Median |  | Rebar work for bus stop ongoing
Wed (21/12) | 21 Dec 2022 | Z2 LP199 | to TPE | Lane 3 Mo Guan working
Wed (21/12) | 21 Dec 2022 | Zone 1 PRD3 Junction |  | DE143 traffic / street light team working mid junction
Thu (22/12) | 22 Dec 2022 | Exit 1 |  | ECM pond wall trimming, target to cast afternoon
Thu (22/12) | 22 Dec 2022 | Zone 3 Loyang Way LP19/1 |  | DE143 working
Thu (22/12) | 22 Dec 2022 | Zone 2 LP170 bus stop slab / bollard footing |  | Lorry here
Thu (22/12) | 22 Dec 2022 | Zone 1 |  | DE143 working Loy Ave / PRD3 junction
Thu (22/12) | 22 Dec 2022 | Zone 2 Lane 3 | Loy Ave to TPE | StarHub working at LP 191
Thu (22/12) | 22 Dec 2022 | 1st lapping |  | Lapping length and required nos of u-clip inspection in progress
Thu (22/12) | 22 Dec 2022 | Dwall 004 |  | Casting in progress. 2nd truck now. Total volume: 119m^3
Thu (22/12) | 22 Dec 2022 | Zone 2 |  | Backfilling for access to PMH11 done. Slope to lean concrete
Thu (22/12) | 22 Dec 2022 | 2nd lapping |  | U-clip installation and grouting pipe welding works continue
Thu (22/12) | 22 Dec 2022 | 2nd lapping |  | Inspection in progress
Thu (22/12) | 22 Dec 2022 | Zone 2 Cluster Installation | IS21013 | Preparation work ongoing
Thu (22/12) | 22 Dec 2022 | 2nd lapping |  | Cage lowering and progressive installation of grouting tube and spacer block
Thu (22/12) | 22 Dec 2022 | 2nd lapping |  | Cage D&C + B safely lowered
Thu (22/12) | 22 Dec 2022 | Zone 1 |  | Powergas premix laying and compaction in progress. Target to finish by 6pm
Thu (22/12) | 22 Dec 2022 | DW001 |  | Exposing guidewall ongoing
Thu (22/12) | 22 Dec 2022 | Sorry supposed to be 1 |  | 2 slope
Thu (22/12) | 22 Dec 2022 | Exit 3 |  | Guide wall 10-14 plan to start today
Fri (23/12) | 23 Dec 2022 | Zone 3 in front of maple tree blk 2 |  | Preparation for uprooting works. Highlighted to install utility signage before proceeding
Fri (23/12) | 23 Dec 2022 | zone 3 JTC area |  | Trial trench in progress to verify alignment of water pipe
Fri (23/12) | 23 Dec 2022 | Slip rd CH200-130 |  | Continue base course laying and compaction
Fri (23/12) | 23 Dec 2022 | Zone 3 JTc area |  | B&T today target to lay HV and LV pipe, 20m L
Fri (23/12) | 23 Dec 2022 | Slip rd CH200-160 |  | Scupper connection installed last night
Fri (23/12) | 23 Dec 2022 | Slip rd CH130-118 |  | Drain wall rebar works in progress
Fri (23/12) | 23 Dec 2022 | CH153-143 drain |  | Concrete ordered for benching
Fri (23/12) | 23 Dec 2022 | Zone 3 JTC area |  | BH24 permeability test 1st stage in progress
Fri (23/12) | 23 Dec 2022 | Zone 3 JTC area |  | Excavation in progress for perimeter drain
Fri (23/12) | 23 Dec 2022 | Zone 2 | to TPE | LP193 StarHub working lane 3
Fri (23/12) | 23 Dec 2022 | Zone 1 Loy Ave Lane 3 LP198 | to CV | Pgas working here
Fri (23/12) | 23 Dec 2022 | Zone 3 |  | TT in progress by Ryobi-G for NCE
Fri (23/12) | 23 Dec 2022 | Zone 3 junction towards loyang lane |  | DE143 lane closure for stop light cable laying
Fri (23/12) | 23 Dec 2022 | Zone 4 towards CV |  | Lane closure for singtel works
Fri (23/12) | 23 Dec 2022 | Zone 4 center median |  | Tree cutting by DE143
Fri (23/12) | 23 Dec 2022 | Zone 3 exit 1 |  | Washing bay wall formworks closing on going
Fri (23/12) | 23 Dec 2022 | Zone 3 exit 1 |  | Soil disposal in progress, 5 loads already out
Fri (23/12) | 23 Dec 2022 | Zone 1 | ABH6-3 | Preparing for backfilling & housekeeping work
Fri (23/12) | 23 Dec 2022 | Zone 3 |  | Lane closure by other contractor towards TPE to replace speed camera
Fri (23/12) | 23 Dec 2022 | Zone 3 Mapletree |  | Clearing of debris ongoing by B&T. 2×6 laid. 2×4 pipes to be laid in the circled area
Fri (23/12) | 23 Dec 2022 | Zone 3 Blk 4 Mapletree |  | Plan to cast Perimeter drain at 5pm
Fri (23/12) | 23 Dec 2022 | Zone 3 Mapletree Blk 2 |  | Trial trench done shows that the 150mm waterpipe is capped. Selvam will share the asbuilt of the waterpipe once ready
Sat (24/12) | 24 Dec 2022 | Exit 1 |  | ECM pond toeboard installation ongoing
Sat (24/12) | 24 Dec 2022 | Zone 3 |  | No activity by other contractors
Sat (24/12) | 24 Dec 2022 | Dwall 001 |  | Koden Test result
Sat (24/12) | 24 Dec 2022 | Zone 2 North ramp |  | Steel plate shifting and excavation of capping beam area ongoing
Sat (24/12) | 24 Dec 2022 | Dwall 001 |  | Installation of Waterstop at Dwall 035 side
Sat (24/12) | 24 Dec 2022 | Dwall 001 |  | Bentonite test checks done. All within acceptable range
Sat (24/12) | 24 Dec 2022 | Exit 3 |  | Excavator used to loosen around endplate
Sat (24/12) | 24 Dec 2022 | Exit 1 Spoil disposal |  | 9 loads out today. 2 loads shifted to Exit 1 from Mapletree area
Sat (24/12) | 24 Dec 2022 | Gate 6 |  | Vibro mobbed in for steel plate lagging installation
Sat (24/12) | 24 Dec 2022 | Pasir Ris Dr 3 Jn |  | DE143 working on Loyang Ave Lane 2 towards TPE
Sat (24/12) | 24 Dec 2022 | Zone 2 |  | LP193 Starhub works ongoing at Lane 3 towards TPE
Sat (24/12) | 24 Dec 2022 | Zone 1 |  | No activity by other contractors
Sat (24/12) | 24 Dec 2022 | Dwall 001 |  | Desanding in progress
Sat (24/12) | 24 Dec 2022 | Exit 1 |  | Levelling ongoing with 2 excavators
Sat (24/12) | 24 Dec 2022 | Exit 1 |  | Concrete patching at site access in progress
Sat (24/12) | 24 Dec 2022 | Zone 4 towards CV |  | Singtel works ongoing
Sun (25/12) | 25 Dec 2022 | Exit 1 / Gate 7a |  | No activity, gate closed
Sun (25/12) | 25 Dec 2022 | Zone 1 |  | No works by other contractor
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Waterstop welding works in progress
Sun (25/12) | 25 Dec 2022 | Zone 1 | PRD3 | Powergas pipe laying works in progress
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Waterstop installation completed. Total length of water stop is 24.535m from GWTL
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Preparation to lower 1st rebar cage
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Lowering of rebar cage 1a
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Rebar Cage 1b lowered. (2/8 nos.)
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Lowering of rebar cage 2b. Lapping in progress for 1b & 2b
Sun (25/12) | 25 Dec 2022 | Dwall 0001 |  | Lapping completed for rebar cage 1B+2B. Lowering of rebar cage 2B ongoing
Sun (25/12) | 25 Dec 2022 | Dwall 001 |  | Rebar Cage 2a lowering and lapping ongoing for (1a & 2a)
Sun (25/12) | 25 Dec 2022 | Dwall 0001 |  | Lapping completed for rebar cage 1A+2A. Lowering of rebar cage 3B ongoing and lapping in progress (2B+3B)
Sun (25/12) | 25 Dec 2022 | DW001 |  | 2a + 3a lapping ongoing
Sun (25/12) | 25 Dec 2022 | Zone 3 LP116 | to TPE | DE143 working at Lane 1
Mon (26/12) | 26 Dec 2022 | Zone 1 |  | No activity of other contractor
Mon (26/12) | 26 Dec 2022 | Zone 2, LP193 - LP199 | to TPE | Starhub Mo Guan working ongoing
Mon (26/12) | 26 Dec 2022 | Zone 2 |  | No activity of other contractor
Mon (26/12) | 26 Dec 2022 | Zone 3 |  | No activity of other contractor
Mon (26/12) | 26 Dec 2022 | Zone 4 |  | DE143 working along Loyang way
Mon (26/12) | 26 Dec 2022 | Truck 15 & 16. Running vol |  | 136/165m3
Tue (27/12) | 27 Dec 2022 | Zone 2 LP170 centre median |  | Type A bus stop arrived. Lane closure ok, TMA provided. Now waiting for supporting documents to arrive
Tue (27/12) | 27 Dec 2022 | Zone 2 Loy Ave Jxn Lane 1 | to TPE | DE143 street light team working here
Tue (27/12) | 27 Dec 2022 | Zone 1 LP198 | to CV | Lane 3 Pgas working. TMA provided
Tue (27/12) | 27 Dec 2022 | Zone 2 LP192 | to CV | DE143 roadwork team working along Lane 3
Tue (27/12) | 27 Dec 2022 | Zone 2 | CM-Bus stop | Bollard installation in progress. Target to cast 4pm
Tue (27/12) | 27 Dec 2022 | Mapletree Blk 2 |  | Trial trench ongoing to identify 700mm water pipe location across Mapletree driveway
Tue (27/12) | 27 Dec 2022 | Dwall 009 |  | Pre-excavation for dwall panel started
Tue (27/12) | 27 Dec 2022 | Slip Road | Ch 190-200 | Base course laying ongoing
Wed (28/12) | 28 Dec 2022 | Zone 2 LP170 Bus Stop |  | Casting ongoing. lightning protection & lighting will install progressively for both bus stops
Fri (30/12) | 30 Dec 2022 | DW-009 |  | Lowering of cage 2
Fri (30/12) | 30 Dec 2022 | DW009 |  | First cage lowering ongoing
Fri (30/12) | 30 Dec 2022 | Zone 1 Loy Ave | TPE bound | Pgas doing their M&P works for 3 locations. to address the feedback received by the public
Fri (30/12) | 30 Dec 2022 | Zone 2 drain |  | Today plan to cast top slab from ~CH140-120
Sat (31/12) | 31 Dec 2022 | As of 31 Dec 22, Exit 3 D-wall |  | 4/14nos completed
Tue (03/01) | 03 Jan 2023 | Exit 3 |  | Pre-excavation for DW003 started
Tue (03/01) | 03 Jan 2023 | PMH-11 |  | Rebar tying ongoing
Tue (03/01) | 03 Jan 2023 | Zone 2 Slip Rd |  | Box culvert drain fwk removal ongoing from Ch 140 onwards
Tue (03/01) | 03 Jan 2023 | Zone 2 |  | MP no activity
Tue (03/01) | 03 Jan 2023 | Zone 2 | Slip Rd Access | Current status
Tue (03/01) | 03 Jan 2023 | Zone 1 | both bounds | No activity of other contractor, DE143 lane closure from LP206-207A
Tue (03/01) | 03 Jan 2023 | Zone 1 | Loy Ave Junction | No work here today, DE143 street light team working at PRD3/Loy Ave island LP8
Wed (04/01) | 04 Jan 2023 | Zone 2 LP8 PRD3/Loy Ave Island |  | DE143 working here
Wed (04/01) | 04 Jan 2023 | Zone 1 Loy Ave | to TPE | Mo Guan working at LP199/1
Wed (04/01) | 04 Jan 2023 | Lane 3 LP199/1 |  | Mo Guan removal of rigid pavement in progress
Wed (04/01) | 04 Jan 2023 | Zone 1 | next to AWWA | DE143 opened their hoarding, current status of their work
Wed (04/01) | 04 Jan 2023 | Loy Ave from LP206/A to LP203/A | to CV | PUB & DE143 working here
Wed (04/01) | 04 Jan 2023 | Zone 1 Loy Ave LP200 | to TPE | Powergas preparation work ongoing
Wed (04/01) | 04 Jan 2023 | Dwall 003 |  | 2nd bite continue trenching - about 4m depth now
Wed (04/01) | 04 Jan 2023 | TT-SN- 0108 |  | Trial trench on going by Ryobi-G for Net-Link NCE
Wed (04/01) | 04 Jan 2023 | Z2 North ramp |  | Excavator mobilized onsite. Will start to prepare the platform for MP
Wed (04/01) | 04 Jan 2023 | Zone 2 |  | Temp PCN painting works in progress
Wed (04/01) | 04 Jan 2023 | Zone-4 |  | PowerGrid contractor (Dosk) doing trial trench at LP111 (TPE bound)
Wed (04/01) | 04 Jan 2023 | Zone 2 North Ramp |  | Platform preparing ongoing for MPs
Wed (04/01) | 04 Jan 2023 | Gate 5 |  | First load out from site. Target 10 loads today
Thu (05/01) | 05 Jan 2023 | Zone 1 middle lane | to TPE | Powergas TMA
Thu (05/01) | 05 Jan 2023 | Blk 208 ABH1-3 | C107 boundary | Setting up / preparation work ongoing
Thu (05/01) | 05 Jan 2023 | Exit 1 | silo | Hardcore backfilling / levelling work ongoing
Thu (05/01) | 05 Jan 2023 | Zone 2 |  | PCN Re-inspection completed. PCN has opened for public use
Thu (05/01) | 05 Jan 2023 | Zone 4 |  | No activity by other contractor
Thu (05/01) | 05 Jan 2023 | Loy Ave LP199/1 | to TPE | Mo Guan working at rigid pavement
Fri (06/01) | 06 Jan 2023 | New Loyang Link LP7 |  | Mo Guan working here
Fri (06/01) | 06 Jan 2023 | Zone 2 Loy Ave Lane 2 LP199/1 | to TPE | Mo Guan continue rigid pavement removal
Fri (06/01) | 06 Jan 2023 | Zone 1 LP202/A | to TPE | Powergas continue with pipe laying work
Fri (06/01) | 06 Jan 2023 | Zone 3 PCN |  | Moveable hoarding installation
Fri (06/01) | 06 Jan 2023 | zone 2 PMH11 |  | Concrete pump truck on site, pending concrete
Fri (06/01) | 06 Jan 2023 | Dwall 10 |  | Area preparation for BC cutter parking in progress
Fri (06/01) | 06 Jan 2023 | Exit 3 | Dwall 03 | Desanding completed. Koden test checking ongoing
Fri (06/01) | 06 Jan 2023 | Zone 2 slip rd |  | Hacking works continue till 630pm
Sat (07/01) | 07 Jan 2023 | Zone 2 | Slip Road | Continue of excavation works
Sat (07/01) | 07 Jan 2023 | Dwall 03 |  | Lowering of Cage 3B and lapping works in progress for Cage 2B/3B
Sat (07/01) | 07 Jan 2023 | Zone 1 | Changi bound, LP198 | Powergas works (Team 1) ongoing at 3rd lane
Sat (07/01) | 07 Jan 2023 | Zone 1 LP202/A | to TPE | Powergas (Team 2) continue with pipe laying work at middle lane
Sat (07/01) | 07 Jan 2023 | Zone 1 |  | DE143 works at traffic island
Sat (07/01) | 07 Jan 2023 | Zone 1 | TPE Bound | Mo Guan pipe laying works at lane 3
Sat (07/01) | 07 Jan 2023 | Zone 2 |  | No activity of other contractor
Sat (07/01) | 07 Jan 2023 | Exit 2 |  | Noise barriers counterweight Formwork installation. Casting will be done in the afternoon
Sat (07/01) | 07 Jan 2023 | Exit 1 |  | Hardcores laying in progress. Tomorrow will do base casting
Sat (07/01) | 07 Jan 2023 | Exit 1 |  | C7 drain patching works
Sat (07/01) | 07 Jan 2023 | Exit 1 |  | Entrance access works
Sat (07/01) | 07 Jan 2023 | Zone 4 |  | No activity of other contractor
Sat (07/01) | 07 Jan 2023 | Zone 3 |  | No activity of other contractor
Sat (07/01) | 07 Jan 2023 | Dwall 03 |  | Cage 3B lowered down. Balance 2nos. of rebar cages
Sat (07/01) | 07 Jan 2023 | Dwall 03 |  | Lowering of Cage 4B and lapping works in progress for Cage 3B/4B
Sat (07/01) | 07 Jan 2023 | Dwall 10 |  | Excavation ongoing at depth 26m. GIII confirmed at 26m depth
Sat (07/01) | 07 Jan 2023 | Dwall 03 |  | Cage 4B lowered. Balance: 1no. of rebar cage. 7/8 nos of cages lowered
Sat (07/01) | 07 Jan 2023 | Exit 2 |  | Casting works ongoing for noise barrier counterweight. 7nos
Sat (07/01) | 07 Jan 2023 | Exit 1 |  | Construction of ECM holding pond for treated water from ECM treatment plant
Sat (07/01) | 07 Jan 2023 | Exit 3 |  | SI rig shifting to JTC area. BH15
Sat (07/01) | 07 Jan 2023 | Dwall 10 |  | 1/6 nos of rebar cages arrived onsite
Sat (07/01) | 07 Jan 2023 | DW12 to 14 |  | Continue excavation for guide wall
Sat (07/01) | 07 Jan 2023 | Dwall 10 |  | As of now, excavation depth 10m
Sat (07/01) | 07 Jan 2023 | Dwall 03 |  | Cage 2A and 3A lapping completed and lowered
Sun (08/01) | 08 Jan 2023 | Zone 2 |  | Replacing utility signage with laminated paper and yellow tape
Sun (08/01) | 08 Jan 2023 | Gate 6 |  | Ramp painting in progress
Sun (08/01) | 08 Jan 2023 | Zone 2 |  | Continuation of excavation at slip road and PMH10
Sun (08/01) | 08 Jan 2023 | Zone 2 |  | No activity by other contractors
Sun (08/01) | 08 Jan 2023 | Zone 1 | next to AWWA | DE143 works ongoing. Portion of road subbase has been laid
Sun (08/01) | 08 Jan 2023 | Zone 1 | next to Shell | DE143 working at sidetable
Sun (08/01) | 08 Jan 2023 | Zone 1 |  | No activity by other contractors
Sun (08/01) | 08 Jan 2023 | Gate 5 |  | Barrier Painting ongoing
Sun (08/01) | 08 Jan 2023 | DW012 |  | Commenced guidewall rebar work
Sun (08/01) | 08 Jan 2023 | Exit 1 Base slab cast |  | 51m³/150m³
Sun (08/01) | 08 Jan 2023 | Exit 1 |  | 7th concrete truck arrived
Sun (08/01) | 08 Jan 2023 | Gate 5 |  | Repainting of ramp ongoing
Sun (08/01) | 08 Jan 2023 | DW10 |  | Trimming work completed, preparing for an internal koden test. if all okay, they’ll proceed with water stop installation
Sun (08/01) | 08 Jan 2023 | Zone 3 |  | No activity by other contractors
Sun (08/01) | 08 Jan 2023 | Zone 4 |  | No activity by other contractors
Sun (08/01) | 08 Jan 2023 | Exit 1 |  | Rebar works ongoing for silo base slab. Plan to cast at 9pm
Sun (08/01) | 08 Jan 2023 | Exit 1 |  | Shifting of steel plates for access ongoing
Sun (08/01) | 08 Jan 2023 | Exit 1 |  | Genset shelter dismantling ongoing. To shift genset and ECM plant behind the Ecm pond on Monday
Mon (09/01) | 09 Jan 2023 | Dwall 10 |  | Last rebar cage delivered on site. 6/6 nos
Mon (09/01) | 09 Jan 2023 | Dwall 10 |  | Water stop removal in progress
Mon (09/01) | 09 Jan 2023 | BH-16 |  | Hand augering in progress. WH discussing with Dongah to do SI at other available location first for BT to work at this area
Mon (09/01) | 09 Jan 2023 | BH 34 |  | Trial trench started
Mon (09/01) | 09 Jan 2023 | BH16 |  | Hand augering on going
Mon (09/01) | 09 Jan 2023 | Zone 1 middle lane TPE bound |  | Powergas works ongoing — pipe laying 24m
Mon (09/01) | 09 Jan 2023 | Exit 3 DW10 |  | Desanding on going
Mon (09/01) | 09 Jan 2023 | DW10 |  | Trimming work ongoing, current trimming depth at 25.5m. they’re slowly trimming their way down to ensure that the water stop removal can be done smoothly
Mon (09/01) | 09 Jan 2023 | DW10 |  | Preparation work ongoing for water stop installation
Tue (10/01) | 10 Jan 2023 | GL P7-N6 at zone 2 |  | Cable detection carried out to continue micropile works
Tue (10/01) | 10 Jan 2023 | Zone 4 |  | No activity of other contractor. DE143 working at Loyang way nead T junction
Tue (10/01) | 10 Jan 2023 | Zone 2 |  | Lagging plate installation on going. Target to complete 30m today
Tue (10/01) | 10 Jan 2023 | Zone 2 |  | Existing drain hacking in progress in preparation for drain work connection
Tue (10/01) | 10 Jan 2023 | Zone 2 Slip road balance drain CH 1+120 - CH 1+ 90 | 30m | Level a bit high. Lean concrete to hack and redo. Target to re-cast after lunch
Tue (10/01) | 10 Jan 2023 | PMH11 |  | Area preparation for rebar works. Surveyor marking done
Tue (10/01) | 10 Jan 2023 | DW10 |  | Water stop installation ongoing
Tue (10/01) | 10 Jan 2023 | DW10 |  | Cage 1B lowering ongoing & installation of spacers
Tue (10/01) | 10 Jan 2023 | Dwall 5 |  | Pre-excavation in progress
Tue (10/01) | 10 Jan 2023 | BH16 |  | Boring reached 13m depth
Tue (10/01) | 10 Jan 2023 | Zone 2 North ramp |  | Lagging plate installation continue. 20/30m installed
Tue (10/01) | 10 Jan 2023 | PMH10 |  | Sump pit location excavated and lean concreted. Rebar preparation for sump pit area
Tue (10/01) | 10 Jan 2023 | Zone 2 north ramp |  | Hardcore backfilling and steel plate laying for micropile rig working platform
Tue (10/01) | 10 Jan 2023 | DW05 |  | Pre-excavation in progress. Tonight start trenching
Tue (10/01) | 10 Jan 2023 | DW03 |  | Stage 3 grouting on going
Tue (10/01) | 10 Jan 2023 | DW10 |  | Lowering of cage 2A
Tue (10/01) | 10 Jan 2023 | DW10 |  | Cage 2A + 1A lapping ongoing
Tue (10/01) | 10 Jan 2023 | DW10 |  | Cage A last lapping on going
Tue (10/01) | 10 Jan 2023 | DW-10 |  | Once cage A lowered, they will proceed with platform access for casting & shifting of materials. Target to start casting at ard 3am
Tue (10/01) | 10 Jan 2023 | Exit 3 |  | Soil disposal on going
Tue (10/01) | 10 Jan 2023 | BH34 |  | Trial trench on going
Wed (11/01) | 11 Jan 2023 | BH16 |  | Arranging water supply to continue boring
Wed (11/01) | 11 Jan 2023 | Exit 1 |  | Hard barrier installation at new ECM plant location
Wed (11/01) | 11 Jan 2023 | Exit 1 site access |  | BRC laying for casting above RC pipe. Today to cast
Wed (11/01) | 11 Jan 2023 | DW-10 |  | Tremie pipe installation ongoing
Wed (11/01) | 11 Jan 2023 | DW-05 |  | BC cutter parked, green line is where the slurry wall is
Wed (11/01) | 11 Jan 2023 | Exit 3 |  | Marking on the location of slurry wall and MC cutter parking location for 2nd bite will be done at 1700 hrs. Clayshock condition and level will also be checked later
Wed (11/01) | 11 Jan 2023 | Exit 3 |  | Bentonite pipe laying and connection for permanent desander. Informed Mr. Woo to invite LTA and QPS for pipe inspection before using permanent desander
Wed (11/01) | 11 Jan 2023 | BH16 |  | Boring reached 28.8m. Now confirmation of G3 rock
Wed (11/01) | 11 Jan 2023 | Zone 2 |  | Manual excavation to lower down LV cable to facilitate slip road construction towards Loyang avenue
Wed (11/01) | 11 Jan 2023 | DW-10 |  | Casting ongoing
Wed (11/01) | 11 Jan 2023 | Exit 3 |  | Slurry wall visual inspection. Clayshock level remains intact at top of guidewall. QPS no further comment
Wed (11/01) | 11 Jan 2023 | DW-10 |  | Casting ongoing, 102/150m3
Wed (11/01) | 11 Jan 2023 | DW10 |  | Casting status, vol: 136/161.5m3. Last 2 loads otw
Wed (11/01) | 11 Jan 2023 | PMH-10 |  | Rebar status
Wed (11/01) | 11 Jan 2023 | Zone 2 Slip Rd |  | Compaction work ongoing
Wed (11/01) | 11 Jan 2023 | Zone 2 Slip Rd |  | Soil backfilling along retaining wall
Wed (11/01) | 11 Jan 2023 | DW05 |  | Cutter teeth replacement ongoing
Thu (12/01) | 12 Jan 2023 | BH16 |  | Boring reached 37m depth. Packer test on going
Thu (12/01) | 12 Jan 2023 | Zone 1 |  | TT location at PDR3 tonight. Target 1 location (3m x 1m x 1.5m)
Fri (13/01) | 13 Jan 2023 | Zone 1 LP204 | to CV | No activity by other contractor
Fri (13/01) | 13 Jan 2023 | DW05 |  | Trench is stable. No leak of clayshock observed
Fri (13/01) | 13 Jan 2023 | Loyang Ave Lane 1 | to TPE | Pgas pipe laying continue, TMA/TMO provided
Fri (13/01) | 13 Jan 2023 | New Loyang Link LP3 |  | StarHub continue pipe laying work
Fri (13/01) | 13 Jan 2023 | PRD3 along Bus Depot |  | No activity
Fri (13/01) | 13 Jan 2023 | Zone 2 |  | Slip road progress status
Fri (13/01) | 13 Jan 2023 | C107 boundary |  | ABH1-2 SPT ongoing
Fri (13/01) | 13 Jan 2023 | DW05 |  | Balance trenching for 2nd bite(socketing 1m) in progress
Fri (13/01) | 13 Jan 2023 | BH33 |  | Boring reached 25m. Now preparing for packet test and access rectification on going
Fri (13/01) | 13 Jan 2023 | Zone 2 LP190 (PCN Sidetable) | to CV | ECS unloading footing for hoarding work, TMA provided
Fri (13/01) | 13 Jan 2023 | Zone 2 LP192 |  | No activity by DE143
Sat (14/01) | 14 Jan 2023 | Exit 1 |  | Current status of silo slab, access preparation ongoing
Sat (14/01) | 14 Jan 2023 | Loyang Way LP19 |  | No activity by other contractor
Sat (14/01) | 14 Jan 2023 | Zone 4 |  | No activity by other contractor
Sat (14/01) | 14 Jan 2023 | DW05 |  | Cleaning completed. Setting up for Koden test
Sat (14/01) | 14 Jan 2023 | Zone 2 LP184 |  | ECS continue movable hoarding installation & material delivery
Sat (14/01) | 14 Jan 2023 | Zone 2 MP |  | Working platform & access preparation work ongoing, replacing of existing turfing with hardcore & good earth
Sat (14/01) | 14 Jan 2023 | Zone 2 Slip Rd box drain |  | Benching casting / patching up ongoing till Ch105
Sat (14/01) | 14 Jan 2023 | Ch105 to 103 |  | Drain base casting completed
Sat (14/01) | 14 Jan 2023 | Exit 3 |  | DW11 pre excavation completed today at around 3pm. Tonight they plan to start trenching here
Sat (14/01) | 14 Jan 2023 | PDR3 east bound | towards loyang avenue | Lane 3 closure for trial trench work
Sat (14/01) | 14 Jan 2023 | PDR3 west bound |  | Lane 1 close for trial trench and pipe laying
Sat (14/01) | 14 Jan 2023 | BH33 |  | Preparing for packer test
Sun (15/01) | 15 Jan 2023 | Pasir Ris Dr 3 | toward Loyang Avenue bound | Turning lane (trial trench done), Lane 1 ( plan for TT tomorrow), Lane 2 ( TT in progress), Lane 3 ( completed on 14.01.2023), DE143 road widening area ( Yet to complete)
Sun (15/01) | 15 Jan 2023 | Zone 1 |  | DE143 working near AWWA
Sun (15/01) | 15 Jan 2023 | Zone 2 workers rest area |  | Roofing extension ongoing
Sun (15/01) | 15 Jan 2023 | DW-05 |  | Preparing to install cage 2B
Sun (15/01) | 15 Jan 2023 | PDR3 west bound |  | 8 pcs x 2 layer pipes installed. Total 6m laid up to date
Sun (15/01) | 15 Jan 2023 | PDR3 east bound | towards Loyang avenue | Found 22KV at 1.5m depth and gas pipe at 1.3m depth
Sun (15/01) | 15 Jan 2023 | DW05 |  | End plate installation continue
Mon (16/01) | 16 Jan 2023 | Mapple tree blk 2 |  | BH15 drilling/SPT at 4m depth
Mon (16/01) | 16 Jan 2023 | Mapple tree blk 4 |  | BH34 hand augering, balance 300mm
Mon (16/01) | 16 Jan 2023 | Zone 3 |  | New PCN painting works in preparation for diversion
Mon (16/01) | 16 Jan 2023 | Zone 3 Exit 1 |  | Material delivery and steel plate laying
Mon (16/01) | 16 Jan 2023 | Zone 4 |  | Lane closure at slow lane by road contractor for road kerb grating maintenance
Mon (16/01) | 16 Jan 2023 | Zone 3 |  | DE143 working along loyang way
Mon (16/01) | 16 Jan 2023 | 1st bite |  | Excavation reached 28.8m as of now
Mon (16/01) | 16 Jan 2023 | DW005 |  | Rebar lapping done and lowered down. Now housekeepind preparation for tremie pipe installation for casting
Mon (16/01) | 16 Jan 2023 | Mapletree Blk2 |  | Excavation for Perimeter drain ongoing
Mon (16/01) | 16 Jan 2023 | Zone 3 |  | DE143 still occupying one lane of Loyang Way
Mon (16/01) | 16 Jan 2023 | Exit 1 |  | Excavation ongoing to lower RC pipe
Mon (16/01) | 16 Jan 2023 | DW10 |  | Tremie pipe installation for casting
Mon (16/01) | 16 Jan 2023 | PMH10 status |  | Wall (stage 1) formworks closing. Plan to cast tomorrow morning
Mon (16/01) | 16 Jan 2023 | PMH10 |  | Wall formwork support installation. Tomorrow to cast
Mon (16/01) | 16 Jan 2023 | Zone 2 to Zone 3 |  | All lamp post no power along Loyang Avenue toward Changi Bound. So far, we did not have any activity along the road now to impact the lamp post power supply. FYI
Tue (17/01) | 17 Jan 2023 | Zone 3 |  | Lane closure towards CV to clear rubbish from new PCN. Inform WH to expedite and try to install hoarding at this area before CNY
Tue (17/01) | 17 Jan 2023 | Zone 4 |  | Lane closure at slow lane towards TPE for TNT metak engineering works
Tue (17/01) | 17 Jan 2023 | Zone 4 |  | No activity towards CV
Tue (17/01) | 17 Jan 2023 | Zone 3 |  | 100T mobile crane mobilisation for unloading of desander and undertank this afternoon
Tue (17/01) | 17 Jan 2023 | Zone 3, TRVR31 |  | Trial trench for NCE near LP137
Tue (17/01) | 17 Jan 2023 | Zone 4 |  | VMS installation towards CV near LP89
Tue (17/01) | 17 Jan 2023 | Zone 4 |  | 2nd VMS installation towards TPE between LP113-LP115
Tue (17/01) | 17 Jan 2023 | Powergas premix lorry broke down ard 4 |  | 15pm. Now waiting for premix
Tue (17/01) | 17 Jan 2023 | Premix arrived at 5 |  | 45pm. Reinstatement works in progress
Tue (17/01) | 17 Jan 2023 | Zone 3 |  | Maple tree blk 2 perimeter drain excavation in progress
Tue (17/01) | 17 Jan 2023 | BH15 |  | Topping up water to continue drilling. Current depth 10m
Tue (17/01) | 17 Jan 2023 | Mapple tree blk 4 |  | BH34 drilling/SPT at 22m depth
Wed (18/01) | 18 Jan 2023 | zone 3 |  | Nee PCN marking in progress
Wed (18/01) | 18 Jan 2023 | Zone 3 |  | No activity of other contractor
Wed (18/01) | 18 Jan 2023 | Zone 4 |  | No activity of other contractor
Wed (18/01) | 18 Jan 2023 | Zone 3 Exit 1 |  | Assembly of Crawler Crane in progress
Wed (18/01) | 18 Jan 2023 | Zone 1 | LP202A | Pgas continue with pipe laying work
Wed (18/01) | 18 Jan 2023 | Exit 1 |  | Crawler crane boom assembly
Wed (18/01) | 18 Jan 2023 | DW-11 |  | Current status
Wed (18/01) | 18 Jan 2023 | Zone 2 | north ramp | Telco duct lean con ongoing
Wed (18/01) | 18 Jan 2023 | DW011 |  | Cage B (1/3 lowered down). Cage A (0/3 lowered down)
Wed (18/01) | 18 Jan 2023 | DW006 | 1st bite | Excavation reached 29.5m
Wed (18/01) | 18 Jan 2023 | Pasir Ris Dr 3 | toward Loyang Avenue, lane 1 | Lane closure done and noise barrier installed for road premix cutting and excavation. Tonight plan to lay 3.5m length of cable duct
Wed (18/01) | 18 Jan 2023 | BH15 |  | Drilling/SPT at 15m depth
Wed (18/01) | 18 Jan 2023 | BH34 |  | SI completed and grouted
Wed (18/01) | 18 Jan 2023 | Zone 2 LP194 | to CV | Current status of work by DE143
Thu (19/01) | 19 Jan 2023 | Zone 2 LA after PRD3 slip road | LP192 to 186 | Slow lane closure for tree felling works. Now preparing to start. 7nos to be felled today
Thu (19/01) | 19 Jan 2023 | Zone 1 Loyang Ave TPE bound |  | Powergas continue rectification works (~10m) middle lane
Thu (19/01) | 19 Jan 2023 | DW06 |  | Preparing to remove water stop
Thu (19/01) | 19 Jan 2023 | TTSP-07 |  | Found 22kV pipe crossing at 0.85m depth
Thu (19/01) | 19 Jan 2023 | Zone 2 sidetable LP177 | TPE bound | Hi-Tech trial trench works ongoing for HSL NCE application
Thu (19/01) | 19 Jan 2023 | DW006 |  | 2nd bite internal koden test in progress. Current depth at 28.33m. Balance about 1.76m to toe level
Thu (19/01) | 19 Jan 2023 | Exit 3 |  | Area preparation for guidewall panel 13 and 14
Thu (19/01) | 19 Jan 2023 | Zone 3 |  | Movable hoarding installation started. Target today 25m to complete
Thu (19/01) | 19 Jan 2023 | BH15 |  | Boring done and confirmed termimation depth at 36.98m. Now preparing for packer test
Thu (19/01) | 19 Jan 2023 | PRD3 LP3 |  | TT work started, premix cutting ongoing
Fri (20/01) | 20 Jan 2023 | Zone 3/4 junction area |  | DE143 tree felling work
Fri (20/01) | 20 Jan 2023 | DW06 |  | Cage 2A lapping ongoing
Fri (20/01) | 20 Jan 2023 | Zone 1 traffic junction |  | Traffic light works by contractor Eng Hup
Fri (20/01) | 20 Jan 2023 | Zone 1 middle lane TPE bound |  | Powergas rectification works ongoing
Fri (20/01) | 20 Jan 2023 | Exit 3 |  | Shifting of crawler crane in progress for water stop installation
Fri (20/01) | 20 Jan 2023 | Exit 3, Guidewall | Panel 13 & 14 | Rebar installation in progress. Target to cast today
Fri (20/01) | 20 Jan 2023 | Exit 3 | Dwall 6 | Lowering of 1st rebar cage (Cage b)
Sat (21/01) | 21 Jan 2023 | Zone 1 PDR3 |  | No activity of DE143
Sat (21/01) | 21 Jan 2023 | DW006 |  | Casting in progress. Running volume 68 m3. Total ordered 187 m3
Sat (21/01) | 21 Jan 2023 | BH30 |  | Drilling/SPT in progress. Current dept at 23m
Sat (21/01) | 21 Jan 2023 | BH17 |  | Hand augering in progress. Balance 1.2m
Sat (21/01) | 21 Jan 2023 | Zone 3 |  | No activity of other contractor
Sat (21/01) | 21 Jan 2023 | Zone 4 |  | No activity of other contractor
Sat (21/01) | 21 Jan 2023 | Exit 1 |  | Access steel plate laying to VS
Sat (21/01) | 21 Jan 2023 | Exit 1 |  | Slurry tank marking done. Plan to start assembly today
Sat (21/01) | 21 Jan 2023 | DW006 |  | Casting continue. Running volume 127/187 m3
Sat (21/01) | 21 Jan 2023 | DW006 |  | Casting continue. Running volume 178.5 m3
Sat (21/01) | 21 Jan 2023 | DW006 |  | Casting now at 195.5 m3. (May still need to order 1 more truck)
Sat (21/01) | 21 Jan 2023 | DW06 |  | 2A/3A lapping started
Sat (21/01) | 21 Jan 2023 | Zone 1 PRD3 LP3 |  | SPPG pipe laying work completed, 4x2 12m length. quarry dust backfilling ongoing
Sat (21/01) | 21 Jan 2023 | Zone 3 |  | Dongah SI team stopped work for the day
Sat (21/01) | 21 Jan 2023 | Exit 1 |  | Laying steel plate for crane parking to boom down
Sat (21/01) | 21 Jan 2023 | DW-06 |  | Cage 3B lapping ongoing
Sat (21/01) | 21 Jan 2023 | Exit 3 |  | Crane now boom down and housekeeping
Sat (21/01) | 21 Jan 2023 | Zone 1 LP3 PRD3 | next to AWWA | Lane closure for SPPG pipe laying works, tonight 2 teams
Sat (21/01) | 21 Jan 2023 | PMH10 |  | Wall stage 1 formwork dismantling
Sat (21/01) | 21 Jan 2023 | Zone 2 |  | No activity of other contractor
Wed (25/01) | 25 Jan 2023 | BH30 |  | Coring in progress
Wed (25/01) | 25 Jan 2023 | New Loyang Link LP3 |  | Lane closed, pgas setting up ongoing
Wed (25/01) | 25 Jan 2023 | Zone 1 Loy Ave | both bounds | No activity by other contractors
Wed (25/01) | 25 Jan 2023 | Zone 2 near bus stop 98041 |  | WH plans to extend the hoarding and start hacking works at this area (along blue marker). Bus pole needs to be shifted slightly
Wed (25/01) | 25 Jan 2023 | Zone 2 |  | No activity by other contractor
Wed (25/01) | 25 Jan 2023 | Zone 2 PCN side |  | No silty discharge
Wed (25/01) | 25 Jan 2023 | PDR3 |  | Wee Guan is here to continue 22KV pipe laying. Now still raining, they are waiting for the rain to subside a bit then will close the lane
Thu (26/01) | 26 Jan 2023 | New Loyang Link LP 3 |  | Lane closed by Pgas
Thu (26/01) | 26 Jan 2023 | Zone 2 LP192 | next to bus depot | No activity
Thu (26/01) | 26 Jan 2023 | Zone 2 Sidetable | bus depot | No activity
Thu (26/01) | 26 Jan 2023 | Zone 2 LP199/1 | Sidetable to Shell Stn | SPTel NCE manual excavation ongoing
Thu (26/01) | 26 Jan 2023 | Zone 1 | CV bound | No activity by other contractor
Thu (26/01) | 26 Jan 2023 | Zone 1 | TPE bound | No activity by other contractor
Thu (26/01) | 26 Jan 2023 | Zone 2 |  | No activity by other contractor
Thu (26/01) | 26 Jan 2023 | Zone 2 Slip Rd |  | Balance footpath casting ongoing
Fri (27/01) | 27 Jan 2023 | Zone 3 |  | No activity by other contractor
Fri (27/01) | 27 Jan 2023 | PDR3 lane 3 |  | Excavation in progress
Fri (27/01) | 27 Jan 2023 | Exit 1 |  | Shifting of hoarding line ongoing, existing road signage is in the way of their hoarding
Fri (27/01) | 27 Jan 2023 | Exit 1 |  | Excavation for sewer line ongoing, they’ll excavate before & after the existing drain as the pipe needs to go underneath to connect to MH
Fri (27/01) | 27 Jan 2023 | Zone 2 |  | Current status of existing drain hacking
Fri (27/01) | 27 Jan 2023 | Exit 1 |  | They’ll plan to lift up the silos today in the afternoon
Fri (27/01) | 27 Jan 2023 | Loyang Way | facing Gate 7A | No activity by other contractor
Fri (27/01) | 27 Jan 2023 | Loyang Way LP23 |  | DE143 working here
Fri (27/01) | 27 Jan 2023 | Zone 4 LA LP110 |  | TT for SPTel NCE extension
Fri (27/01) | 27 Jan 2023 | Z4 |  | DE143 working within their hoarding area
Fri (27/01) | 27 Jan 2023 | Zone 2 |  | No activity near bus depot side
Fri (27/01) | 27 Jan 2023 | Z3 LA LP118 | to CV | TT work for NCE extension
Fri (27/01) | 27 Jan 2023 | Exit 2 | BH-134 | Coring ongoing, 6m depth
Fri (27/01) | 27 Jan 2023 | DW007 |  | Pre-excavation completed
Fri (27/01) | 27 Jan 2023 | Exit 1 |  | Continue balance C7 panel installation
Fri (27/01) | 27 Jan 2023 | DW-12 |  | 4/6nos cages lowered
Fri (27/01) | 27 Jan 2023 | PMH10 |  | 2nd stage wall and top slab rebar works continue
Fri (27/01) | 27 Jan 2023 | PDR3 |  | Wee Guan start cutting premix
Sat (28/01) | 28 Jan 2023 | DW012 |  | Last truck arrived. 203m³ cast
Sat (28/01) | 28 Jan 2023 | Zone 3 |  | No activity by other contractors
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | 5nos. Of silo anchored. 4nos done yesterday
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | Hoarding removal and shifting ongoing
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | C7 drain installation ongoing
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | Steel plate laying to prepare access for Tan Huan's tree felling
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | Excavation for sewer still in progress
Sat (28/01) | 28 Jan 2023 | PDR3 lane 3 |  | Excavation continue. FYI this location have 22KV and new gas pipe installed. They will undercross these 2 utilities for pipe laying
Sat (28/01) | 28 Jan 2023 | Exit 2 |  | BH134 pending confirmation of termination depth
Sat (28/01) | 28 Jan 2023 | Exit 2 |  | BH135 trial trench completed. Hand augering to continue
Sat (28/01) | 28 Jan 2023 | Exit 2 |  | Chain link fence removal in progress
Sat (28/01) | 28 Jan 2023 | Zone 2 |  | No activity by other contractors
Sat (28/01) | 28 Jan 2023 | Zone 1 |  | DE143 works within hoarding
Sat (28/01) | 28 Jan 2023 | Zone 1 |  | DE143 occupying the slow lane and slip lane to excavate the sidetable
Sat (28/01) | 28 Jan 2023 | DW07 |  | 5 / 6nos of rebar cages delivered
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | Sewer team plans to work until 10pm (or later if it continues to rain)
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | Scissor lift mobbed in today. Slurry tank installation ongoing
Sat (28/01) | 28 Jan 2023 | Exit 1 |  | Lowbed trailer damaged one water barrier when turning. Informed WHDA to remove the water barrier to create more space
Sat (28/01) | 28 Jan 2023 | DW12 casting |  | Running volume 85/187 m3
Sat (28/01) | 28 Jan 2023 | PDR3 |  | Excavation in progress for 22KV pipe laying. If no obstruction they will lay pipes tonight
Sun (29/01) | 29 Jan 2023 | PMH-10 |  | Rebar works and Formwork closing ongoing
Sun (29/01) | 29 Jan 2023 | Zone 1 | Loyang Ave - Changi Bound | DE143 works ongoing
Sun (29/01) | 29 Jan 2023 | Zone 1 |  | DE143 working within their hoarded area
Sun (29/01) | 29 Jan 2023 | Loyang Ave - PRD3 junction |  | No activity of other contractor
Sun (29/01) | 29 Jan 2023 | Zone 2 |  | No activity of other contractor
Sun (29/01) | 29 Jan 2023 | Exit 1 |  | Silo slurry tank assembly in progress for 1st layer
Sun (29/01) | 29 Jan 2023 | Zone 3 |  | No activity of other contractor
Sun (29/01) | 29 Jan 2023 | Zone 4 |  | No activity of other contractor
Sun (29/01) | 29 Jan 2023 | Zone 3 | Jtc/Mapletree | No activity
Sun (29/01) | 29 Jan 2023 | Exit 3 |  | Gate 5 washing bay cleaning in progress
Sun (29/01) | 29 Jan 2023 | Exit 1 |  | Safety briefing conducted for non-routine lift. Desander assembly works
Sun (29/01) | 29 Jan 2023 | Exit 1 |  | Desander assembly/lowering completed
Sun (29/01) | 29 Jan 2023 | PMH10 |  | Current status of wall formwork closing. Target to cast tmr
Mon (30/01) | 30 Jan 2023 | Zone 2 LP170 | centre median | Excavation for barrier free access ongoing
Mon (30/01) | 30 Jan 2023 | Slip road stage 2 | inside hoarding | RCA backfilling continue. Plan to do NDT today, but due to wet weather postponed to tomorrow or Wednesday. Singtec need to re-compact the area. Balance kerb 24m to cast today. Plan B1 layer this week if weather condition allows. 🙏
Mon (30/01) | 30 Jan 2023 | Zone 2 | North Ramp | Coring for MP27 started
Mon (30/01) | 30 Jan 2023 | PMH10 |  | Wall stage 2 and top slab to cast today AM
Mon (30/01) | 30 Jan 2023 | Zone 3 JTC |  | BH28 drilling/SPT in progress depth 34.4m
Mon (30/01) | 30 Jan 2023 | Zone 2 | Sidetable next to Bus depot | No activity by other contractor
Mon (30/01) | 30 Jan 2023 | Zone 3 |  | No activity of other contractor
Mon (30/01) | 30 Jan 2023 | Zone 2 LP190 onwards |  | Tree roots removal ongoing via grabber
Mon (30/01) | 30 Jan 2023 | Zone 4 |  | Tree feeling works by other contractor. Subcon is teck Heng
Mon (30/01) | 30 Jan 2023 | Exit 1 |  | Balance sewer pipe connection (3m) in progress
Mon (30/01) | 30 Jan 2023 | Exit 1 |  | Hoarding shifted preparing to cast and and install silt fence
Mon (30/01) | 30 Jan 2023 | Exit 1 |  | Silo tank pull out tets
Mon (30/01) | 30 Jan 2023 | Exit 1 |  | Slurry tank layer 1 assembly in progress
Mon (30/01) | 30 Jan 2023 | Zone 3 exit 1 |  | Area preparation for tree feeling. Steel plate laying in progress
Mon (30/01) | 30 Jan 2023 | Zone 3 exit 2 |  | BH135 drilling/SPT, depth at 14m
Mon (30/01) | 30 Jan 2023 | Zone 3 exit 2 |  | Hoarding footing casting on going. Tomorrow they will excavate ECM pond here
Mon (30/01) | 30 Jan 2023 | PMH-10 |  | Casting completed
Mon (30/01) | 30 Jan 2023 | Exit 3 |  | Guidewall Panel 14 rebar works in progress
Mon (30/01) | 30 Jan 2023 | Exit 1 |  | Silo slurry tank assembly in progress for 2nd layer
Mon (30/01) | 30 Jan 2023 | DW07 |  | Waterstop installation in progress. Will continue with rebar cage lowering down after this
Mon (30/01) | 30 Jan 2023 | DW07 |  | 2nd bite trimming in progress
Tue (31/01) | 31 Jan 2023 | Zone 2 MP24 |  | Casing installation & continue coring
Tue (31/01) | 31 Jan 2023 | Zone 2 |  | Preparation for next section of MPs
Tue (31/01) | 31 Jan 2023 | Zone 3 |  | JTC area BH26 hand augering started
Tue (31/01) | 31 Jan 2023 | LA/PRD3 | next to AWWA | DE143 current work status
Tue (31/01) | 31 Jan 2023 | Zone 4 |  | Lane closure at fast lane by signmechanic for signboard installation
Tue (31/01) | 31 Jan 2023 | Zone 3 exit 1 |  | Hardcore laying for tree feeling working platform
Tue (31/01) | 31 Jan 2023 | Zone 1 LA LP198 | to CV | HT preparing area for TT work to locate 300mm dia water pipe
Tue (31/01) | 31 Jan 2023 | DW-07 casting in progress. Running vol |  | 42.5/187m3
Tue (31/01) | 31 Jan 2023 | New Loyang Link | lane 1 | M&P done by other contractor
Tue (31/01) | 31 Jan 2023 | Exit 1 |  | Silo base slab slope protection casting in progress
Tue (31/01) | 31 Jan 2023 | DW07 |  | Cage A (2/3 cage lowered down). Cage B (2/3 cage lowered down)
Tue (31/01) | 31 Jan 2023 | DW-07 casting ongoing. Truck 19 just arrived. Running vol |  | 153/187m3
Tue (31/01) | 31 Jan 2023 | PMH09 |  | Lean concrete done. Cover up expose soil area with canvas and installation of hard barrier
Wed (01/02) | 01 Feb 2023 | Zone 3 mapple tree blk 2 |  | TT to find water pipe along boundary wall and to confirm if live or not
Wed (01/02) | 01 Feb 2023 | Zone 3 BH26 |  | Drilling/SPT in progress. Depth at 8m
Wed (01/02) | 01 Feb 2023 | Zone 2 |  | Current status of lighting cable pipes laying. Will continue laying from CH100 onwards
Wed (01/02) | 01 Feb 2023 | Zone 4 |  | No activity of other contractor towards TPe
Wed (01/02) | 01 Feb 2023 | PMH09 |  | Preparation for base slab rebar and sump pit rebar
Wed (01/02) | 01 Feb 2023 | Exit 1 |  | Slurry tank assembly continue
Wed (01/02) | 01 Feb 2023 | Exit 1 |  | Hardcore laying for tree feeling working platform in progress
Wed (01/02) | 01 Feb 2023 | Zone 2 near bus depot |  | No activity
Wed (01/02) | 01 Feb 2023 | Zone 1 | near AWWA | Current status DE143 works
Wed (01/02) | 01 Feb 2023 | Zone 1 LP200 | TPE bound | Hi-Tech slow lane closure and preparing for trial trench works to locate water pipe alignment
Wed (01/02) | 01 Feb 2023 | Zone 1 | CV bound | DE143 middle lane closure
Wed (01/02) | 01 Feb 2023 | Zone 2 LP191-195 | TPE bound | Tree felling ongoing. Plan to fell 3nos today
Wed (01/02) | 01 Feb 2023 | Zone 3 exit 2 |  | Levelling on going for ECM plant. Today lean concrete
Wed (01/02) | 01 Feb 2023 | DW14 |  | Guide wall casting in progress
Wed (01/02) | 01 Feb 2023 | Exit 1 |  | Lifting of desander starting soon
Wed (01/02) | 01 Feb 2023 | Zone 3 |  | VMS-26 at loyang way installed
Wed (01/02) | 01 Feb 2023 | BH26 |  | Depth now at 18m
Wed (01/02) | 01 Feb 2023 | Slip road stage 2 | inside hoarding | Pre-mix laying in progress
Thu (02/02) | 02 Feb 2023 | DW013 |  | Cage B (3/3) lapping ongoing
Thu (02/02) | 02 Feb 2023 | DW08 |  | Preparing for trimming work at DW09 waterstop side
Thu (02/02) | 02 Feb 2023 | LA LP202A | to TPE | Lane markings ongoing
Thu (02/02) | 02 Feb 2023 | LA LP204A | to TPE | Premix laying / compaction work ongoing
Thu (02/02) | 02 Feb 2023 | Zone 2 Loyang Ave | TPE bound | Slow lane closure for tree felling works (LP177 onwards). As of now, 3 trees felled. Now felling temporarily stopped cos heavy rain
Thu (02/02) | 02 Feb 2023 | Zone 2 near PD office |  | 4nos trees felled yesterday
Thu (02/02) | 02 Feb 2023 | BH26 |  | Drilling/SPT at 26m
Thu (02/02) | 02 Feb 2023 | BH29 |  | Drilling/SPT at 6m
Thu (02/02) | 02 Feb 2023 | Zone 1 Loyang Ave |  | No activity at both bounds
Thu (02/02) | 02 Feb 2023 | PRD3 | loyang point bound | Slow lane closure by DE143 at LP3
Thu (02/02) | 02 Feb 2023 | Zone 3 |  | No activity of other contractor
Thu (02/02) | 02 Feb 2023 | Zone 4 |  | DE143 working at slow lane and side table towards CV
Thu (02/02) | 02 Feb 2023 | Zone 2 Changi bound |  | Area excavated for barrier free access to temporary bus stop
Thu (02/02) | 02 Feb 2023 | Zone 2 Centre Median |  | Current status of barrier free access. Already cast, pending tactile installation
Thu (02/02) | 02 Feb 2023 | Exit 1 |  | Slurry tank assembly continue
Thu (02/02) | 02 Feb 2023 | Exit 2 |  | ECM plant delivery and set up
Thu (02/02) | 02 Feb 2023 | Zone 3 exit 2 |  | TT in progress to check cable alignment from substation
Thu (02/02) | 02 Feb 2023 | LP177-189 |  | 4nos trees felled
Thu (02/02) | 02 Feb 2023 | Zone 2 LP189 |  | Now preparing to cut only tree branches for 1 tree before lane openimg
Thu (02/02) | 02 Feb 2023 | DW008 |  | Excavation reached 15m depth
Thu (02/02) | 02 Feb 2023 | DW013 |  | Continue welding of water stop end plate joint
Thu (02/02) | 02 Feb 2023 | PRD3 Sidetable LP2 | next to AWWA | DE143 working here
Thu (02/02) | 02 Feb 2023 | PRD3 LP3 | next to bus depot | WG hacking to remove footpath in progress, noise barriers set up. WG will have to do this hacking carefully due to proximity with box drain
Thu (02/02) | 02 Feb 2023 | LA LP200 onwards (to TPE) | middle lane | M&P works started by Pgas
Fri (03/02) | 03 Feb 2023 | Zone 2 TPE bound |  | No activity
Fri (03/02) | 03 Feb 2023 | Zone 2 near bus depot |  | No activity
Fri (03/02) | 03 Feb 2023 | Zone 2 Changi bound |  | No activity
Fri (03/02) | 03 Feb 2023 | Zone 1 PRD3 & next to AWWA |  | DE143 works ongoing
Fri (03/02) | 03 Feb 2023 | Exit 1 |  | Maintenance and hose connection for desander
Fri (03/02) | 03 Feb 2023 | Exit 1 |  | Sump pit installation between RC pipe and C7 drain
Fri (03/02) | 03 Feb 2023 | Zone 3 & 4 junction |  | DE143 lane closure for their traffic signal pipe laying
Fri (03/02) | 03 Feb 2023 | Zone 1 PRD3 LP2 | next to bus depot | WG continue excavation to expose the pipes they previously laid at red line & will undercross existing box drain (marked in green)
Fri (03/02) | 03 Feb 2023 | DW08 |  | Removal of water stopper from DW07 side
Fri (03/02) | 03 Feb 2023 | LA to TPE | LP 204A | Premix removal ongoing at lane 1
Fri (03/02) | 03 Feb 2023 | Exit 2 |  | Plan to cast temporary ECM pond today
Fri (03/02) | 03 Feb 2023 | PM09 |  | Wall starter bar installation
Fri (03/02) | 03 Feb 2023 | Exit 3 |  | Bentonite properties checked. Within the range
Fri (03/02) | 03 Feb 2023 | DW13 |  | Cages lowered, tremie pipe installation ongoing
Fri (03/02) | 03 Feb 2023 | BH27 |  | TT done. To continue hand augering
Fri (03/02) | 03 Feb 2023 | BH29 |  | Coring reached, 26m
Fri (03/02) | 03 Feb 2023 | PMH 10 |  | Backfilling and levelling
Fri (03/02) | 03 Feb 2023 | BH-27 |  | Trial trench in progress
Sat (04/02) | 04 Feb 2023 | Slip road foot path stage 2 diversion |  | Adjusting level to cast today. Tomorrow plan to install barricade/hoarding. Monday to complete and Tuesday to divert (est)
Sat (04/02) | 04 Feb 2023 | DW-08 |  | Cage 2A/3A lapping ongoing
Sat (04/02) | 04 Feb 2023 | Zone 3 JTC |  | BH29 drilling/SPT in progress. Depth 29.6m
Sat (04/02) | 04 Feb 2023 | Zone 3 |  | No activity of other contractor at City bound
Sat (04/02) | 04 Feb 2023 | Zone 3 near junction |  | DE143 close fast lane for stop light cable laying
Sat (04/02) | 04 Feb 2023 | Exit 1 perimeter drain |  | C7 drain installation on going
Sat (04/02) | 04 Feb 2023 | Exit 1 hoarding area |  | Backfilling and levelling
Sat (04/02) | 04 Feb 2023 | Exit 1 |  | Desander piping works on going
Sat (04/02) | 04 Feb 2023 | Exit 2 |  | Perimeter drain excavation on going
Sat (04/02) | 04 Feb 2023 | Zone 3 towards CV |  | TT in progress to find water pipe alignment
Sat (04/02) | 04 Feb 2023 | Zone 2 towards TPE |  | Lane closure by DE143 at slow lane. Tan Huan also working at slow lane for tree feeling
Sat (04/02) | 04 Feb 2023 | Zone 2 towards TPE |  | Tree feeling works between LP181-185
Sat (04/02) | 04 Feb 2023 | Zone 2 |  | DE143 working towards CV at side table
Sat (04/02) | 04 Feb 2023 | Zone 1 |  | DE143 working near AWWA homes
Sat (04/02) | 04 Feb 2023 | Zone 1 |  | DE143 working at junction near shell
Sat (04/02) | 04 Feb 2023 | DW08 |  | Continue removal of water stop at DW09 side
Sat (04/02) | 04 Feb 2023 | DW08 |  | 1st bite trimming ongoing
Sat (04/02) | 04 Feb 2023 | DW08 |  | Cage 2A preparation for lapping
Sat (04/02) | 04 Feb 2023 | SW02 |  | Pre-excavation completed. Re-arranging steel plate for BC cutter parking
Sat (04/02) | 04 Feb 2023 | Exit 2 |  | Now levelling for genset area to be lean con today
Sat (04/02) | 04 Feb 2023 | Zone 3 near exit 1 |  | DE143 working at junction for telcom cable pipe laying
Sat (04/02) | 04 Feb 2023 | BH29 |  | Drilling/SPT at 8m
Sat (04/02) | 04 Feb 2023 | BH29 |  | Rock coring at 35m
Sat (04/02) | 04 Feb 2023 | Dw08 |  | Cage 2A lapping in progress
Sat (04/02) | 04 Feb 2023 | Zone 1 PRD3 LP2 | next to bus depot | Shoring removal & proceed with backfilling work
Sun (05/02) | 05 Feb 2023 | Zone 3 & Zone 4 junction |  | DE143 laying of traffic light pipes
Sun (05/02) | 05 Feb 2023 | DW014 |  | Pre- excavation for excavation work
Sun (05/02) | 05 Feb 2023 | DW-08 |  | Tremie pipe installation ongoing
Sun (05/02) | 05 Feb 2023 | Zone 1 PRD3 near LP2 |  | Wee Guan prep works. Tonight plan to lay 3m
Mon (06/02) | 06 Feb 2023 | SW01 |  | LSS casting commenced at 10:50am, currently waiting for LSS lorries
Mon (06/02) | 06 Feb 2023 | North ramp MP1-20 |  | Area preparation for vibro machine paltform to remove lagging plate
Mon (06/02) | 06 Feb 2023 | BH29 |  | Coring reached 38m depth and still have fracture rock/ highly weathered rock. So, need to continue until 43m depth to check on rock condition. This is the only location whether encountered this type of rock condition
Mon (06/02) | 06 Feb 2023 | Zone 2 LP170 |  | Footpath cast / levelling work ongoing
Mon (06/02) | 06 Feb 2023 | Zone 2 LP197 | to TPE | Tree felling works ongoing
Mon (06/02) | 06 Feb 2023 | PMH-09 |  | Wall rebar works ongoing
Mon (06/02) | 06 Feb 2023 | TMH-05 |  | Preparation works for plate load test
Mon (06/02) | 06 Feb 2023 | Exit 1 |  | Silo maintenance and hose connection
Tue (07/02) | 07 Feb 2023 | PMH11 |  | Barricade installation at top slab in preparation for Cable pulling mock up
Tue (07/02) | 07 Feb 2023 | Exit 2 | substation | Drain removal and backfilling work started
Tue (07/02) | 07 Feb 2023 | Zone 1 (LP200 onwards) | to TPE | No activity by other contractor
Tue (07/02) | 07 Feb 2023 | Zone 1 | next to AWWA | DE143 road work status
Tue (07/02) | 07 Feb 2023 | Zone 1 LP198 | to CV | DE143 working along the sidetable
Tue (07/02) | 07 Feb 2023 | Zone 2 LP163 onwards |  | Tree felling work ongoing
Tue (07/02) | 07 Feb 2023 | Exit 1 |  | Earthing installation for silo
Tue (07/02) | 07 Feb 2023 | Exit 1 |  | Continue shifting of soil toward Exit 2
Tue (07/02) | 07 Feb 2023 | Exit 1 |  | DB and electrical work for desander
Tue (07/02) | 07 Feb 2023 | Zone 3 & 4 junction |  | DE143 working for traffic cable pipe laying
Tue (07/02) | 07 Feb 2023 | DW014 |  | Final koden test in progress. Tonight to continue with rebar cage lowering down
Tue (07/02) | 07 Feb 2023 | Exit 2 | substation | Lighting installation and cable pulling for the site work
Tue (07/02) | 07 Feb 2023 | DW14 |  | Preparation to remove end plate at DW13 side
Wed (08/02) | 08 Feb 2023 | DW-14 running vol |  | 76.5m3
Wed (08/02) | 08 Feb 2023 | Exit 1 |  | Banner installation on silo
Wed (08/02) | 08 Feb 2023 | Zone 2 |  | Temporary hard standing area for buses turfing and top soil removal. Target to lean con today
Wed (08/02) | 08 Feb 2023 | Zone 1 LP200-202A | to TPE | DE143 preparing for tree/shrub removal
Wed (08/02) | 08 Feb 2023 | Zone 2 NLL | next to Shell | DE143 continue with drain widening works
Wed (08/02) | 08 Feb 2023 | Zone 2 Slip road area |  | PCN diversion will not happening today as the area is not ready. Railing to be replaced with movable hoarding to prevent security breach on our working area. Chasing Rupert to expedite and divert by this week
Wed (08/02) | 08 Feb 2023 | Zone 1 | next to AWWA | DE143 crushing existing drain
Wed (08/02) | 08 Feb 2023 | Zone 2 |  | No activity of other contractor
Wed (08/02) | 08 Feb 2023 | PMH-11 |  | Cable pulling from PMH-10
Wed (08/02) | 08 Feb 2023 | Started pulling at about 14 |  | 50hrs
Wed (08/02) | 08 Feb 2023 | DW-14 casting started. Est vol |  | 156m3. 4 trucks currently on site
Thu (09/02) | 09 Feb 2023 | PMH10 |  | Dismantling of barricade
Thu (09/02) | 09 Feb 2023 | Exit 3 |  | Materials shifting works ongoing
Thu (09/02) | 09 Feb 2023 | Exit 2 |  | Current status of backfilling
Thu (09/02) | 09 Feb 2023 | Zone 1 (near to C107 boundary) | PRD1 LP1F | TT for ABH-03 will start afternoon, currently shifting their materials out from C107
Thu (09/02) | 09 Feb 2023 | Zone 2 (LP177 - LP185) | to TPE | Derooting work ongoing
Thu (09/02) | 09 Feb 2023 | Zone 2 |  | Tan Huan @ TPE bound, Singtec @ CV bound
Thu (09/02) | 09 Feb 2023 | Exit 3 |  | Dismantling of BC cutter ongoing
Thu (09/02) | 09 Feb 2023 | Exit 1 |  | Current status of mud pit excavation
Thu (09/02) | 09 Feb 2023 | Exit 1 |  | Continue clearing of soil stockpile
Thu (09/02) | 09 Feb 2023 | THM05 |  | Wall stage 1 formworks closing
Thu (09/02) | 09 Feb 2023 | Zone 1 | next to AWWA | DE143 removal of existing drain box
Thu (09/02) | 09 Feb 2023 | Zone 1 LP200 to LP204A | both bounds | DE143 working here
Thu (09/02) | 09 Feb 2023 | PDR3 |  | Wee guan will continue excavation tonight. Tomorrow night plan to lay pipe around 10m
Fri (10/02) | 10 Feb 2023 | Zone 1 (LP 200 till LP206/A) | both bounds | DE143 continue with centre median excavation
Fri (10/02) | 10 Feb 2023 | Zone 1 | next to AWWA | Current status of road work
Fri (10/02) | 10 Feb 2023 | Zone 2 | side table TPE bound | Continue turfing removal for footpath/covered linkway works
Fri (10/02) | 10 Feb 2023 | ABH-03 |  | TT completed, found utilities
Fri (10/02) | 10 Feb 2023 | PDR3 |  | Cable pipe laying in progress
Sat (11/02) | 11 Feb 2023 | Zone 2 |  | No activity of other contractor
Sat (11/02) | 11 Feb 2023 | Zone 2 | side table TPE bound | Preparation for casting for footpath/covered linkway works. Concrete ordered (7m^3)
Sat (11/02) | 11 Feb 2023 | Zone 1 |  | DE143 working at both TPE and Changi bound
Sat (11/02) | 11 Feb 2023 | Zone 1 |  | DE143 working within their hoarded area
Sat (11/02) | 11 Feb 2023 | Zone 1 |  | DE143 closing at center of PRD3-LA junction
Sat (11/02) | 11 Feb 2023 | Zone 1 | NLL | Powergas unloading of materials. Preparation works ongoing
Sat (11/02) | 11 Feb 2023 | Zone 1 |  | De143 working at side table. Beside traffic light
Sat (11/02) | 11 Feb 2023 | Zone 2 | side table TPE bound | Casting ongoing for footpath/covered linkway works
Sat (11/02) | 11 Feb 2023 | Exit 2 |  | 20 pcs of steel plates delivered
Sat (11/02) | 11 Feb 2023 | Zone 3 |  | No activity of other contractor
Sat (11/02) | 11 Feb 2023 | Exit 1 |  | Mud pit wall Formwork installation
Sat (11/02) | 11 Feb 2023 | Exit 1 |  | Filter press maintenance works
Sat (11/02) | 11 Feb 2023 | Zone 4 |  | Loyang way - DE143 works ongoing
Sat (11/02) | 11 Feb 2023 | Zone 4 | LP115-Center median | SingTel Contractor Skk doing trial trench works
Sat (11/02) | 11 Feb 2023 | Exit 3 |  | BC cutter dismantling works ongoing
Sat (11/02) | 11 Feb 2023 | PMH-09 |  | Formwork installation for balance wall and top slab
Sat (11/02) | 11 Feb 2023 | Zone 2 | Slip road | Removing of previous diverted PCN in progress
Sat (11/02) | 11 Feb 2023 | Mapletree | BH-22 | Drilling works ongoing at 18m depth
Sat (11/02) | 11 Feb 2023 | BH-18 |  | Hand angering works
Sat (11/02) | 11 Feb 2023 | Exit 1 |  | Continue of wall Formwork installation for mud pit
Sat (11/02) | 11 Feb 2023 | Exit 2 |  | ECM holding pond widening
Sat (11/02) | 11 Feb 2023 | Exit 2 |  | Steel plate laying status
Sat (11/02) | 11 Feb 2023 | Zone 2 | side table TPE bound | Footpath/covered linkway casting completed
Sat (11/02) | 11 Feb 2023 | Zone 1 | NLL | Powergas hacking works to undercross existing drain completed. Shoring ongoing
Sat (11/02) | 11 Feb 2023 | Zone 2 |  | Temporary PCN opened. Reinspection completed with QPS and WHDA
Sun (12/02) | 12 Feb 2023 | Zone 1 TPE bound |  | DE143 lane closure at first lane
Sun (12/02) | 12 Feb 2023 | Zone 2 sidetable | TPE bound | Housekeeping at footpath area
Mon (13/02) | 13 Feb 2023 | PTD signed for Trial trench & BH works at exit 2 |  | BH-134/136
Mon (13/02) | 13 Feb 2023 | Zone 1 Loyang Ave |  | DE143 working at centre median. Lane closures at first lane at both bounds respectively
Mon (13/02) | 13 Feb 2023 | PRD3 |  | HSB DE160 installing VMS near their site office. Abit of traffic jam from slip rd going into PRD3
Mon (13/02) | 13 Feb 2023 | Zone 4 | ATT-Z4-006 | Trial trench done. Found 700mm & 300mm dia water pipe and LV cable
Mon (13/02) | 13 Feb 2023 | Zone 2 slip road |  | Installation of DIC and formwork closing for kerb casting
Mon (13/02) | 13 Feb 2023 | Mapletree | Blk 4 | Found two layers of HT cables (3×2). WH will continue exposing along fencing to check the HT cable turning area
Mon (13/02) | 13 Feb 2023 | Exit -2 |  | New BC cutter machine safely mobilized
Mon (13/02) | 13 Feb 2023 | Mapletree for boundary wall demolition | Blk 4 | WH continue checking of HT cable bend area. 3nos of LV cables found crossing above HT cables
Mon (13/02) | 13 Feb 2023 | Zone 2 Loy Ave | next to bus depot | WG hacking to remove of existing footpath
Mon (13/02) | 13 Feb 2023 | Zone 1 | both bounds | DE143 working along centre median
Tue (14/02) | 14 Feb 2023 | Exit 2 |  | Platform preparation to start SI work
Tue (14/02) | 14 Feb 2023 | Zone 2 segment 1 |  | Excavation in progress to adjust level and backfill with RCA today
Tue (14/02) | 14 Feb 2023 | Exit 1 |  | Adjusting of steel plate for worker & machinery access
Tue (14/02) | 14 Feb 2023 | Exit 1 |  | Crane servicing and inspection by mechanic
Tue (14/02) | 14 Feb 2023 | Zone 3& Zone 4 junction |  | DE143 cable pulling for traffic light
Tue (14/02) | 14 Feb 2023 | Exit 2 |  | Continue hardcore backfilling and levelling
Tue (14/02) | 14 Feb 2023 | Exit 2 |  | Prepare materials for access installation to ECM plant
Tue (14/02) | 14 Feb 2023 | Zone 2 PRD3/Loy Ave PCN Sidetable | next to bus depot | Excavation started for pipe laying works by WG
Wed (15/02) | 15 Feb 2023 | Zone 1 Loyang Ave Changi bound |  | DE143 lane closure at slow lane
Wed (15/02) | 15 Feb 2023 | Exit 1 |  | 1st layer wall formwork dismantling
Wed (15/02) | 15 Feb 2023 | Zone 3& 4 junction |  | DE143 removal of center median
Wed (15/02) | 15 Feb 2023 | Exit 3 |  | Material shifting and housekeeping
Thu (16/02) | 16 Feb 2023 | Zone 1 | next to AWWA | DE143 continue with their road works
Thu (16/02) | 16 Feb 2023 | Mapple tree blk 4 |  | Tong contracts preparing safety documents and PTW board before starting work for boundary wall demolition
Thu (16/02) | 16 Feb 2023 | Zone 3 |  | DE143 working at loyang way
Thu (16/02) | 16 Feb 2023 | Zone 4 |  | Pavement cutting for trial trench of water pipe, ATT Z4-08
Thu (16/02) | 16 Feb 2023 | Zone 4 |  | Lane closed towards TPE for singtel works
Thu (16/02) | 16 Feb 2023 | Zone 2 |  | No activity by other contractor
Thu (16/02) | 16 Feb 2023 | Zone 2 |  | 106 works only
Thu (16/02) | 16 Feb 2023 | Exit 1 |  | Man access to cast today
Thu (16/02) | 16 Feb 2023 | Exit 1 |  | Mud pit wall formwork closing continue
Thu (16/02) | 16 Feb 2023 | Exit 2 |  | BH 138 drilling/SPT. Depth now at 29m
Thu (16/02) | 16 Feb 2023 | Zone 2 sidetable | changi bound | M1 works ongoing
Thu (16/02) | 16 Feb 2023 | Zone 2 slip road |  | Scupper pipes installation
Thu (16/02) | 16 Feb 2023 | Mapletree blk 2 |  | Pavement bricks removal and levelling
Thu (16/02) | 16 Feb 2023 | Zone 2 PCN Sidetable |  | Ytd night footpath repair still curing
Fri (17/02) | 17 Feb 2023 | Exit 2 |  | BH-137 Drilling in progress at 12.45m
Fri (17/02) | 17 Feb 2023 | Zone 2 North ramp |  | Constructing of perimeter drain for completed micropile area
Fri (17/02) | 17 Feb 2023 | Mapletree Blk4 |  | 10m of retaining wall demolished yesterday
Fri (17/02) | 17 Feb 2023 | Mapletree Blk4 |  | Backfilling of trial trench area ongoing
Fri (17/02) | 17 Feb 2023 | Zone 2 Loyang Ave |  | Lane 3 reopened. B1 layer done for the day. Now will only do housekeeping
Fri (17/02) | 17 Feb 2023 | Zone 2 PMH11 |  | Yesterday comments rectification still in progress
Fri (17/02) | 17 Feb 2023 | Exit 1 |  | Washing of access ongoing. Also going to install 2 banners on slurry tank for phototaking later
Sat (18/02) | 18 Feb 2023 | Zone 2 |  | DE143 lane 2 closed for their works
Sat (18/02) | 18 Feb 2023 | Zone 1 |  | DE143 close middle lane towards CV for their works
Sat (18/02) | 18 Feb 2023 | Zone 1 next to AWWA |  | DE143 working here
Sat (18/02) | 18 Feb 2023 | Zone 2 LVC side |  | Unloading of materials for linkway shelter. Today they plan to start
Sat (18/02) | 18 Feb 2023 | Exit 2 |  | BH137 drilling/SPT, 24m
Sat (18/02) | 18 Feb 2023 | Zone 2 substation |  | This location to do trial trench to confirm cable alignment serving LVC
Sat (18/02) | 18 Feb 2023 | Zone 3 |  | No activity of other contractor
Sat (18/02) | 18 Feb 2023 | Exit 1 |  | Installation of agitator
Sat (18/02) | 18 Feb 2023 | Zone 3 junction |  | DE143 works
Sat (18/02) | 18 Feb 2023 | Zone 4 |  | Sptel trial trench at side table towards CV
Sat (18/02) | 18 Feb 2023 | Zone 3 JTC |  | Shifting of SI rig and accessories to exit 3
Sat (18/02) | 18 Feb 2023 | Zone 3 JTC Area |  | Boundary wall demolition 16m as of now
Sat (18/02) | 18 Feb 2023 | Zone 2 towards CV in front of exit 3 |  | Safety briefing for tree feeling works
Sat (18/02) | 18 Feb 2023 | Zone 2 LVC side |  | Linkway shelter erection in progress
Sat (18/02) | 18 Feb 2023 | Exit 1 |  | Gate entrance removal of steel plate and excavation works. They plan to cast it
Sat (18/02) | 18 Feb 2023 | Exit 1 |  | Assembly of cat ladder for slurry tank
Sat (18/02) | 18 Feb 2023 | zone 3 towards CV between LP145-147 |  | Trial trench work for Netlink
Sat (18/02) | 18 Feb 2023 | Exit 2 |  | BH137 coring in progress. Depth at 31m
Sat (18/02) | 18 Feb 2023 | Exit 3 DW2-4 |  | Excavation to expose guidewall for hacking
Sun (19/02) | 19 Feb 2023 | Zone 4 | both bounds | No activity by other contractor
Sun (19/02) | 19 Feb 2023 | Zone 3/4 Loyang Way |  | DE143 road works current status
Sun (19/02) | 19 Feb 2023 | Zone 1 | next to AWWA | DE143 current work status
Sun (19/02) | 19 Feb 2023 | Exit 3 |  | No work by Dongah
Sun (19/02) | 19 Feb 2023 | LP206/A |  | DE143 drain works
Sun (19/02) | 19 Feb 2023 | Exit 2 |  | No activity
Sun (19/02) | 19 Feb 2023 | Zone 2/3 |  | No activity by other contractor
Sun (19/02) | 19 Feb 2023 | Exit 1 |  | Access excavation ongoing
Sun (19/02) | 19 Feb 2023 | exit 1 |  | No activity by Dongah
Sun (19/02) | 19 Feb 2023 | Zone 3 Loyang Way |  | No activity by other contractor
Mon (20/02) | 20 Feb 2023 | Zone 2 sidetable | Changi bound | Yellow painting for concrete barriers ongoing
Mon (20/02) | 20 Feb 2023 | Zone 1 |  | DE143 premix laying and compaction in progress
Mon (20/02) | 20 Feb 2023 | Zone 2 Loyang Ave | TPE bound | Slow lane closure for barrier free access works at sidetable
Mon (20/02) | 20 Feb 2023 | Zone 2 sidetable | Changi bound | Hacking access for gradient adjustment at temp bus stop area
Mon (20/02) | 20 Feb 2023 | PBH 11 |  | Top up water to start boring work tomrrrow
Tue (21/02) | 21 Feb 2023 | Zone 2 |  | Concrete barrier painting works ongoing
Tue (21/02) | 21 Feb 2023 | PMH10 |  | Balance neck formwork closing
Tue (21/02) | 21 Feb 2023 | Zone 1 | next to AWWA | Roadworks by DE143
Tue (21/02) | 21 Feb 2023 | Zone 1 | to TPE | SK working here for LP works
Tue (21/02) | 21 Feb 2023 | PMH09 |  | Wall rebar tying and tie rod installation for formwork closing
Tue (21/02) | 21 Feb 2023 | Zone 2 | NLL, next to shell | De143 working here
Tue (21/02) | 21 Feb 2023 | PRD3 |  | M&P works by DE143
Tue (21/02) | 21 Feb 2023 | Zone 2 LVC |  | Hoarding line
Tue (21/02) | 21 Feb 2023 | Zone 3&4 junction |  | DE143 M&P at Loyang Way
Tue (21/02) | 21 Feb 2023 | Zone 2 |  | No activity by other contractor
Tue (21/02) | 21 Feb 2023 | Exit 3 |  | Continue concrete hacking and rebar cutting for guidewall
Tue (21/02) | 21 Feb 2023 | Exit 2 |  | Excavation for hoarding footing ongoing
Tue (21/02) | 21 Feb 2023 | BH11 |  | Drilling in progress, depth 10m
Tue (21/02) | 21 Feb 2023 | Exit 2 |  | Hebei setting out the noise barrier alignment
Tue (21/02) | 21 Feb 2023 | Zone 2 sidetable | Changi bound | Access casting next to temp bus stop
Tue (21/02) | 21 Feb 2023 | Exit 2 |  | Guidewall for DW-51 to 53 preparation for rebar installation
Tue (21/02) | 21 Feb 2023 | Exit 2 |  | Noise barrier footing rebar works done for the day
Tue (21/02) | 21 Feb 2023 | Exit 1 |  | Slurry tank bolt tightening ongoing
Tue (21/02) | 21 Feb 2023 | Exit 1 |  | Continue pipe connection works for silo
Tue (21/02) | 21 Feb 2023 | Zone 2 ECM area |  | Soil sieving in progress
Wed (22/02) | 22 Feb 2023 | Zone 2, Bus stop at center median |  | Tactile installation in progress (1/3 locations completed.)
Wed (22/02) | 22 Feb 2023 | Zone 1 LA | both bounds | No activity by other contractor. LPs replaced with new ones
Wed (22/02) | 22 Feb 2023 | PRD3 | LP5-9 | M&P works about to start
Wed (22/02) | 22 Feb 2023 | Exit 3, SI work | PBH-11 | Driling works in progress, current at 22m depth
Wed (22/02) | 22 Feb 2023 | Exit 3 |  | Guidewall hardcores removal ongoing
Wed (22/02) | 22 Feb 2023 | PHB-11 |  | SI completed, reached termination depth 33.5m. Pending design team confirmation
Wed (22/02) | 22 Feb 2023 | Exit 3, SI work | PBH-08 | Driling works started
Wed (22/02) | 22 Feb 2023 | Exit 2 |  | Current status of footing rebar works and formwork installation
Wed (22/02) | 22 Feb 2023 | Exit 1 |  | Silo tank pipe connection works ongoing
Wed (22/02) | 22 Feb 2023 | Exit 2 |  | Hoarding footing cast, 5nos
Thu (23/02) | 23 Feb 2023 | Zone 1 | both bounds Lane 3 | Lane closure by DE143, to CV bound: M&P works ongoing
Thu (23/02) | 23 Feb 2023 | Exit 1 |  | Crane dismantling for demob
Thu (23/02) | 23 Feb 2023 | Zone 2 center median |  | Preparing to erect shelter next to temp bus stop
Thu (23/02) | 23 Feb 2023 | Exit 2 |  | Excavation done. Setting out for guide wall rebar work. Preparation on going to install barrier along trench
Thu (23/02) | 23 Feb 2023 | Exit 1 silo area |  | Pipe painting works
Thu (23/02) | 23 Feb 2023 | Exit 1 |  | Dongah housekeeping
Thu (23/02) | 23 Feb 2023 | Exit 2 |  | Guidewall rebar installation in progress
Thu (23/02) | 23 Feb 2023 | Zone 2 | LA to TPE | DE143 closing Lane 2 from LP171 onwards
Thu (23/02) | 23 Feb 2023 | Zone 2 LP192 |  | M&P status by DE143
Fri (24/02) | 24 Feb 2023 | PMH11 |  | Scaffold dismantled
Fri (24/02) | 24 Feb 2023 | PRD3 |  | DE143 painting is D1 kerbs & fwk erection / casting for roadside kerb
Fri (24/02) | 24 Feb 2023 | Exit 2 |  | Exacation for Hoarding footing ongoing. To complete shifting of Hoarding by today
Fri (24/02) | 24 Feb 2023 | Zone 2 (LP188 onwards) | to CV | Tree pruning by NParks ongoing
Fri (24/02) | 24 Feb 2023 | PBH-8 |  | Drilling in progress @ 30m depth
Fri (24/02) | 24 Feb 2023 | PBH-10 |  | Started drilling works
Sat (25/02) | 25 Feb 2023 | Exit 1 |  | Continue hoarding panels installation. To complete by today
Sat (25/02) | 25 Feb 2023 | Zone 2 |  | 2 lorries temporarily stopped at side of road to secure their load properly
Sat (25/02) | 25 Feb 2023 | Zone 1 |  | Busy hours for DE143
Sat (25/02) | 25 Feb 2023 | De143 |  | Current M&P status. Completed Loyang Ave (changi bound.)
Sun (26/02) | 26 Feb 2023 | LA/PRD3 |  | Signage team installing road signage ongoing
Mon (27/02) | 27 Feb 2023 | Zone 3 loyang way |  | Installation of concrete barrier in progress
Mon (27/02) | 27 Feb 2023 | Zone 2 | telco USD | Fwk closing ongoing, target 4pm inspection
Mon (27/02) | 27 Feb 2023 | TMH05 |  | Fwk inspected, concrete otw. Target to cast 4pm
Mon (27/02) | 27 Feb 2023 | Zone 2 | North Ramp | Capping beam rebar tying ongoing
Mon (27/02) | 27 Feb 2023 | Exit 1 |  | C7 drain patch up works
Mon (27/02) | 27 Feb 2023 | PBH04 |  | Drilling at 4m depth
Mon (27/02) | 27 Feb 2023 | PMH09 |  | Drilling at 23m depth
Mon (27/02) | 27 Feb 2023 | PBH04 |  | Drilling at 19m depth
Mon (27/02) | 27 Feb 2023 | PBH09 |  | Drilling at 25m depth
Mon (27/02) | 27 Feb 2023 | Exit 3 |  | Removal of bentonite pipes that will not be use anymore
Mon (27/02) | 27 Feb 2023 | Zone 2 | LVC old guardhouse | Yellow barriers with netting installation in progress
Mon (27/02) | 27 Feb 2023 | Exit 2 |  | Housekeeping works
Mon (27/02) | 27 Feb 2023 | Exit 1 |  | Works stopped for the day
Mon (27/02) | 27 Feb 2023 | Zone 2 | Telco USD | Casting completed - 12m
Mon (27/02) | 27 Feb 2023 | Exit 3 to Exit 2 bentonite pipe laying |  | Today will start materials shifting and start premix cutting. Tomorrow will mobilize mini excavator for excavation
Tue (28/02) | 28 Feb 2023 | Zone 2 |  | Concrete barrier painting ongoing
Tue (28/02) | 28 Feb 2023 | USD construction status between PMH08-PMH07 |  | Telco 24m, power 18m
Wed (01/03) | 01 Mar 2023 | Exit 1 |  | Checking of hardcore levelling for vehicle access
Wed (01/03) | 01 Mar 2023 | Zone 1 |  | Replacing with half height concrete barrier
Wed (01/03) | 01 Mar 2023 | Zone 1 | inside 106 boundary | PGas is here, preparing to commence work. WHDA safety had briefed them
Wed (01/03) | 01 Mar 2023 | Zone 3 |  | Loyang Ave Premix cutting for bentonite pipe laying ongoing
Wed (01/03) | 01 Mar 2023 | Zone 2 POB |  | Delivery of scaffolding materials
Wed (01/03) | 01 Mar 2023 | Zone 2 LVC |  | Installation of hoarding panel at the previous condo access
Wed (01/03) | 01 Mar 2023 | Exit 2 |  | Green fencing dismantling status
Wed (01/03) | 01 Mar 2023 | Exit 1 |  | Cleaning and tidy up the barricade by WH
Wed (01/03) | 01 Mar 2023 | Exit 1 |  | Dongah continue fill in water for slurry tank leakage test
Thu (02/03) | 02 Mar 2023 | Zone 2 |  | NDT done at north ramp between PMH10-8. 3 locations selected by RTO. All compaction achieved more than 95%
Thu (02/03) | 02 Mar 2023 | Exit 3 |  | Demobilising BC cutter hose drum and other parts
Thu (02/03) | 02 Mar 2023 | DW13 |  | 2nd stage base grouting on going
Thu (02/03) | 02 Mar 2023 | Zone 2 LP169 | centre median | Railing removal ongoing
Thu (02/03) | 02 Mar 2023 | Zone 2 | NLL, in front of shell | No activity
Sat (04/03) | 04 Mar 2023 | Exit 2 |  | Bundwall installation for ecm
Sat (04/03) | 04 Mar 2023 | Exit 2 |  | BC cutter maintenance works
Sat (04/03) | 04 Mar 2023 | Bet. LP156 & LP154 |  | Trees disposal ongoing
Sat (04/03) | 04 Mar 2023 | Gate 6 |  | Hoarding extension in progress
Sat (04/03) | 04 Mar 2023 | TMH-05 |  | Formwork dismantling
Sat (04/03) | 04 Mar 2023 | Exit 3 |  | Continue waterstop fabrication
Sat (04/03) | 04 Mar 2023 | Exit 3 SI |  | PBH-01 drilling works in progress, 32m depth
Sat (04/03) | 04 Mar 2023 | Exit 2 |  | Barricading works installation prior to erect steel columns for noise barriers
Sat (04/03) | 04 Mar 2023 | ABH53 |  | Coring & grouting completed. Removal of SI pipes ongoing
Sat (04/03) | 04 Mar 2023 | Exit 1 |  | Tree felling works. As of now 8nos. felled, target to fell 11nos. today
Sat (04/03) | 04 Mar 2023 | Exit 3 to Exit 2 |  | Continue of bentonite pipe laying. Will cast the crossing today
Sat (04/03) | 04 Mar 2023 | Gate 6 |  | Continue of hoarding installation
Sat (04/03) | 04 Mar 2023 | Exit 2 |  | Steel columns installation for Noise barrier ongoing
Sat (04/03) | 04 Mar 2023 | Exit 3 SI |  | PBH-01 drilling works in progress, 18.8m depth
Sat (04/03) | 04 Mar 2023 | Exit 3 |  | Water stop fabrication ongoing
Sat (04/03) | 04 Mar 2023 | Exit 3 to Exit 2 |  | Bentonite pipe laying in progress. Pipe near the side of the road will be lay above the existing road using rubber hose and barricaded afterwards
Sun (05/03) | 05 Mar 2023 | Loyang Avenue/ Pasir Ris Dr 3 junction |  | Current status of concrete barrer/ hard hoarding with transparent board installation. Tomorrow to continue the balance work
Sun (05/03) | 05 Mar 2023 | Exit 2 |  | Current status of C7 panel installation
Sun (05/03) | 05 Mar 2023 | Loyang Avenue/ Pasir Ris Dr 3 junction |  | 3 APOs controlling unauthorised entry through bus lane
Sun (05/03) | 05 Mar 2023 | Exit 2 |  | C7 panel installation done around 21m today. To continue tomorrow
Sun (05/03) | 05 Mar 2023 | Exit 3 to Exit 2 bentonite pipe laying |  | Highlighted in green ( completed)
Sun (05/03) | 05 Mar 2023 | Exit 2 |  | WH installation of C7 drain panel along the hoarding
Mon (06/03) | 06 Mar 2023 | Exit 3 |  | PBH-02 SI working driling in progress, current depth 29m
Mon (06/03) | 06 Mar 2023 | Dwall-004 |  | Permeability test ongoing. 3rd test @ (-4.76 to -5.76mSHD, 17.049m-18.049m)
Mon (06/03) | 06 Mar 2023 | Zone 2 | next to slip rd | WH continue hoarding line behind the water barriers (2.5m gap) until the centre median
Mon (06/03) | 06 Mar 2023 | Zone 3 LP148 |  | Lucky Joint trial trench works on road and sidetable. On road, services found: 66kv, 22kv
Mon (06/03) | 06 Mar 2023 | LP148 sidetable |  | Services found — M1, lamp post, LV and 22kV
Mon (06/03) | 06 Mar 2023 | Zone 2 near LP181 |  | Ryobi-G TT for netlink
Mon (06/03) | 06 Mar 2023 | Exit 3 |  | Concrete barrier with acrylic panel dismantling. This will be shift to zone 1
Mon (06/03) | 06 Mar 2023 | Zone 2 next to slip road |  | Moveable hoarding installed
Tue (07/03) | 07 Mar 2023 | Zone 2 LVC Linkway |  | Continue excavation & housekeeping
Tue (07/03) | 07 Mar 2023 | Zone 2 centre median |  | Preparing to remove green railings
Tue (07/03) | 07 Mar 2023 | Exit 2 |  | Continue excavation for C7 panels installation
Tue (07/03) | 07 Mar 2023 | Exit 2 |  | Continue assembly of BC cutter machine
Tue (07/03) | 07 Mar 2023 | Zone 1 LP200 | to TPE | Pgas removing premix layer for pipe laying
Tue (07/03) | 07 Mar 2023 | Exit 1 |  | Shelter frame preparation for filter press
Tue (07/03) | 07 Mar 2023 | Exit 1 |  | Leakage point identify for slurry tank. To remove water and rectify the leakage point
Tue (07/03) | 07 Mar 2023 | Exit 3 |  | Noise barrier removal started
Tue (07/03) | 07 Mar 2023 | Exit 3 |  | Material shifting to exit 1
Tue (07/03) | 07 Mar 2023 | BH197 | Dw004 | 5th stage permeability test in progress
Wed (08/03) | 08 Mar 2023 | NLL LP3-4 |  | Pgas close the lane & premix cutting ongoing
Wed (08/03) | 08 Mar 2023 | Zone 1 LP194 | to TPE | Concrete barriers are on site, gonna start painting work
Wed (08/03) | 08 Mar 2023 | Near Exit 1 |  | Dongah shifting of materials from Exit 3
Wed (08/03) | 08 Mar 2023 | Zone 2 North Ramp |  | Current status of the access
Wed (08/03) | 08 Mar 2023 | Zone 2 | Along LVC | Soil trimming for noise barrier footing base ongoing
Wed (08/03) | 08 Mar 2023 | Exit 2 |  | BRC laying for slope protection casting
Wed (08/03) | 08 Mar 2023 | Zone 2 LVC side |  | 15m lean concreted for noise barrier installation
Wed (08/03) | 08 Mar 2023 | Zone 2 LVC side |  | Lean concrete casting. Total: 40m cast
Wed (08/03) | 08 Mar 2023 | Exit 2 |  | Slope protection casting in progress
Wed (08/03) | 08 Mar 2023 | Exit 2 |  | Continue assembly of BC cutter
Wed (08/03) | 08 Mar 2023 | Zone 1 barrier current status |  | 8nos concrete barriers with acrylic panels, 5nos concrete barriers, 10nos concrete barriers with half hoarding, Total: 23nos currently on site
Thu (09/03) | 09 Mar 2023 | Zone 2 TT |  | ABH47 for ULT4 in progress
Thu (09/03) | 09 Mar 2023 | BH134A |  | Continue SI boring
Thu (09/03) | 09 Mar 2023 | Zone 1 NLL LP 3 | opp shell | PGas continue with excavation work, today will lay pipe
Thu (09/03) | 09 Mar 2023 | Exit 3 |  | Continue bentonite pipe joining and area preparation ongoing. KTC machineries will mobilize by 12pm
Thu (09/03) | 09 Mar 2023 | Zone 2 changi bound |  | Preparing to close up the hoarding
Thu (09/03) | 09 Mar 2023 | Exit 1 |  | Current status of roofing installation for filter press
Thu (09/03) | 09 Mar 2023 | Exit 3 |  | KTC Excavator mobilized on site
Thu (09/03) | 09 Mar 2023 | Substation | BH140 | Boring work in progress at 5 to 6m depth. Plastic bit is used for safe working near utility risk area
Thu (09/03) | 09 Mar 2023 | Zone 2 |  | Preparing to install hoarding behind temp bus stop
Thu (09/03) | 09 Mar 2023 | Exit 3 m |  | Backfilling and compaction works ongoing. 1st load from SingTec
Thu (09/03) | 09 Mar 2023 | Exit 3 |  | As of now 3rd load arrived on site for backfilling works
Thu (09/03) | 09 Mar 2023 | Exit 1 |  | Cleaning inside slurry tank in progress
Thu (09/03) | 09 Mar 2023 | Exit 3 |  | Shifting of crane to give way for backfilling
Thu (09/03) | 09 Mar 2023 | Exit 3 |  | Bentonite pipe bracket installation
Thu (09/03) | 09 Mar 2023 | Exit 2 |  | BC cutter machine assembly, hydraulic hose preparation
Fri (10/03) | 10 Mar 2023 | Zone 2 along LVC |  | Continue soil trimming (20m) for noise barrier base footing
Fri (10/03) | 10 Mar 2023 | Zone 2 changi bound |  | Continue closing up hoarding
Fri (10/03) | 10 Mar 2023 | Zone 2 NLL | in front of Shell | Mo Guan here exposing their manhole
Fri (10/03) | 10 Mar 2023 | Zone 1 |  | Concrete barrier replacement status quo
Fri (10/03) | 10 Mar 2023 | Zone 2 north ramp bus stop |  | Dismantling bus seats
Fri (10/03) | 10 Mar 2023 | 02 |  | 00PM, PUB maintenance officer (Alan Tan) is on site with his contractor. PUB informing the effected stakeholder before shut off the water supply for rectification of the pipe. He suspect the Newater pipe branch out to air valve was damaged. He can confirm the damages only after shut off the Newater supply
Fri (10/03) | 10 Mar 2023 | Exit 3 |  | Continue of backfilling and compaction works
Fri (10/03) | 10 Mar 2023 | Exit 3 |  | RG Drilling rig mobilized on site
Fri (10/03) | 10 Mar 2023 | Exit 3 |  | Current backfilling status
Fri (10/03) | 10 Mar 2023 | Loyang Avenue/ Pasir Ris Dr 3 |  | DE143 D1 kerbs are damaged
Sat (11/03) | 11 Mar 2023 | BH134A |  | Continue boring work
Sat (11/03) | 11 Mar 2023 | BH140 |  | Continue boring
Sat (11/03) | 11 Mar 2023 | Exit 1 |  | Filter press roof and access installation done
Sat (11/03) | 11 Mar 2023 | Exit 1 |  | Platform access making for bentonite pipe cross over area
Sun (12/03) | 12 Mar 2023 | North ramp section U4 |  | Backfilling in progress at the excavated area
Sun (12/03) | 12 Mar 2023 | Exit 2 |  | Fabrication of end plate for water stop continue
Sun (12/03) | 12 Mar 2023 | North ramp section U4 |  | Backfilling done
Mon (13/03) | 13 Mar 2023 | Zone 1 | LA | WH will prepare to remove the centre median
Mon (13/03) | 13 Mar 2023 | Zone 2 | previous temporary desander area | Hoarding installation ongoing. To install 52m
Mon (13/03) | 13 Mar 2023 | Exit 2 BC cutter |  | Changing of hydraulic hose
Tue (14/03) | 14 Mar 2023 | BH136 |  | TT in progress
Tue (14/03) | 14 Mar 2023 | ULT7 |  | Workers shifting of materials to resume boring work, 12m as of now
Tue (14/03) | 14 Mar 2023 | ULT 5 |  | HSL mobilized excavator yesterday. Today will mobilized crawler crane. Tomorrow night plan to mobilize BG machine, escort arranged
Tue (14/03) | 14 Mar 2023 | Exit 2 |  | Today to continue hard barrier and staircase access
Tue (14/03) | 14 Mar 2023 | Exit 1 Slurry tank |  | PU grouting for the leakage point
Tue (14/03) | 14 Mar 2023 | Exit 1 |  | Soil levelling for installed C7 panels
Tue (14/03) | 14 Mar 2023 | DW04 |  | Drilling for TAM grouting done. Preparing pipe for installation
Tue (14/03) | 14 Mar 2023 | Gate 5 loyang lane |  | Column installation for hoarding
Tue (14/03) | 14 Mar 2023 | DW04 |  | 1/2 location for tam grouting pipe installed. Preparing to drill for 2nd location
Tue (14/03) | 14 Mar 2023 | Zone 2 |  | Noise barrier footing works at LVC. Formwork installation (18m)
Tue (14/03) | 14 Mar 2023 | Section U4 |  | Excavation for telco duct 12m in progress. Today lean concrete
Tue (14/03) | 14 Mar 2023 | Exit 1 to slurry wall road crossing area |  | Rigid pavement hacking and removal
Tue (14/03) | 14 Mar 2023 | ULT4 | ABH43 | Coring ongoing, 35.2m depth
Tue (14/03) | 14 Mar 2023 | Zone 1 |  | Removal of road kerb in progress. They will do casting in the evening
Tue (14/03) | 14 Mar 2023 | Zone 1 |  | Shifting of concrete barrier with hoarding sheet ongoing
Tue (14/03) | 14 Mar 2023 | Exit 1 |  | Hardcore laying in preparation for tree felling
Tue (14/03) | 14 Mar 2023 | DW04 |  | 2nd point drilling for TAM grouting
Tue (14/03) | 14 Mar 2023 | Exit 3 |  | KTC now covering soil before ending work
Tue (14/03) | 14 Mar 2023 | Exit 2 |  | Dongah dwall team to work until 8pm only today
Tue (14/03) | 14 Mar 2023 | Zone 2 LVC |  | Noise barrier counterweight to cast tomorrow. Est volume 49 m3
Tue (14/03) | 14 Mar 2023 | zone 1 |  | Location of center island remove and casting in progress
Tue (14/03) | 14 Mar 2023 | 1. Excavation works and lagging plate installation |  | Operators: 3, Banksmen: 3, 2. RC works, A. PMH9 plinth formwork installation, Workers: 5, Supervisor: 1, B. Capping formwork dismantling, Workers: 2, Supervisor: 1, Welder: 1, Rigger/signal: 2, Housekeeping: 3, Supervisor: 1, Safety: 1, Total: 24
Tue (14/03) | 14 Mar 2023 | PMH09 |  | Plinth formwork closing & drilling for gravity concrete block. 5+1 pax
Fri (17/03) | 17 Mar 2023 | Exit 2 |  | Crane boom down inspection
Fri (17/03) | 17 Mar 2023 | Exit 1 |  | Continue hardcore laying and access preparation for tree felling access
Fri (17/03) | 17 Mar 2023 | Exit 1 |  | PU grouting work continue for slurry tank leakage area
Fri (17/03) | 17 Mar 2023 | Exit 1 |  | Worker rest area erection in progress
Fri (17/03) | 17 Mar 2023 | Exit 2 |  | BC cutter hydraulic hoses connection in progress. Tomorrow plan to install cutter body and hoses
Fri (17/03) | 17 Mar 2023 | Exit 1 to slurry wall |  | Preparation for quarry dust backfilling
Fri (17/03) | 17 Mar 2023 | CR107 Utility Damage incident |  | Date: 17 March 2023 (Friday), Time: 1615hrs, Area: Area 1A, Subcontractor: Sinohydro Foundation, Description:, 1-W SingTel cable at approximately 1m depth was damaged during excavation works for guide wall construction, The cable was indicated as proposed 1W pipe in Singtel SIP in a dotted line. SSJV assumed it’s abandoned and didn't capture in Combined Utility Plan. Upon checking with SingTel, SingTel informed at 7.30pm that the cable is live, serving the Junction eye at Pasir Ris drive 1/2, PJT called ITSC, confirmed the provision affected. SingTel team arrived at site at 8.40pm for investigation and repair, Further update will be provided
Sat (18/03) | 18 Mar 2023 | Exit 2 |  | End plate fabrication on going
Sat (18/03) | 18 Mar 2023 | Exit 2 |  | BH136 coring, drill depth at 24m
Sat (18/03) | 18 Mar 2023 | Exit 2 |  | Mud hose connection on going
Sat (18/03) | 18 Mar 2023 | Exit 1 |  | Laying of slurry pipe done. BRC mesh laying in progress to cast today
Sat (18/03) | 18 Mar 2023 | Zpne 3 loyang way |  | Shingda is here for water pressure testing
Sat (18/03) | 18 Mar 2023 | Zone 3 loyang way |  | Today Hitech will do trial here for exit 1 water pipe connection
Sat (18/03) | 18 Mar 2023 | BH61 for ULT7 |  | Drilling in progress, 21m depth
Sat (18/03) | 18 Mar 2023 | DW004 |  | 3/3 points for TAM grouting drilling completed. Grouting hose installation in progress
Sat (18/03) | 18 Mar 2023 | Exit 3 backfilling works |  | Compaction in progress
Sat (18/03) | 18 Mar 2023 | Zone 3 ULT 9 |  | Trial trench in progress
Sat (18/03) | 18 Mar 2023 | Zone 1 NLL |  | Gas pipe laid today 18m
Sat (18/03) | 18 Mar 2023 | Zone 1 |  | Gate installed and hoarding closure done along live road
Sat (18/03) | 18 Mar 2023 | DW07 |  | Base grouting 3rd stage in progress. 10/14 panels completed base grouting for stage 1 dwall at exit 3. Plan to complete all by Monday
Sat (18/03) | 18 Mar 2023 | Exit 3 backfilling works |  | Today no soil delivery, only final levelling and prepare for NDT
Sat (18/03) | 18 Mar 2023 | DW04 |  | Drilling for tam grouting 3/3 in progress. Target to complete tam grouting today and vacate the area to giveway for backfilling works
Sun (19/03) | 19 Mar 2023 | Exit 2 |  | Welding works ongoing for stop end pipe
Sun (19/03) | 19 Mar 2023 | Exit 2 |  | BC cutter maintenance works
Sun (19/03) | 19 Mar 2023 | Zone 3 | In front of lincstech | RG manual trial trench works for instrumentation installation
Sun (19/03) | 19 Mar 2023 | Exit 1 |  | No activity
Sun (19/03) | 19 Mar 2023 | Zone 3 | Mapletree | Electrical cable installation works
Sun (19/03) | 19 Mar 2023 | Zone 2 |  | Geotextile installation along the perimeter drain
Sun (19/03) | 19 Mar 2023 | Zone 1 |  | No activity
Sun (19/03) | 19 Mar 2023 | Exit 2 |  | Welding works for stop end pipe
Sun (19/03) | 19 Mar 2023 | Exit 2 |  | Continue of BC cutter maintenance works
Sun (19/03) | 19 Mar 2023 | Exit 3 |  | No activity for KTC
Mon (20/03) | 20 Mar 2023 | BH136 |  | Boring completed, 34.5. Casing removal in progress
Mon (20/03) | 20 Mar 2023 | DW05 |  | Stage 2 base grouting
Mon (20/03) | 20 Mar 2023 | Exit 2 |  | BC cutter (cutter head) repairing of electrical issue in progress
Mon (20/03) | 20 Mar 2023 | Exit 2 |  | Continue welding of waterstop frame
Mon (20/03) | 20 Mar 2023 | ABH61 | ULT7 | Excavation reached 32m
Mon (20/03) | 20 Mar 2023 | DW04 |  | Tam grouting preparation in progress
Mon (20/03) | 20 Mar 2023 | ABH61 | ULT-7 | Boring in progress
Mon (20/03) | 20 Mar 2023 | Exit 2 |  | Water stop end plate welding work continue
Mon (20/03) | 20 Mar 2023 | Zone 1 NLL LP7 |  | Powergas pipe laying completed, 17m. Now preparing to backfill
Mon (20/03) | 20 Mar 2023 | Exit 1 |  | Access preparation for tree felling
Mon (20/03) | 20 Mar 2023 | Zone 2 north ramp |  | Preparing to shift and extend the moveable hoarding to the side table
Mon (20/03) | 20 Mar 2023 | Exit 1 |  | Rest area erection by WH
Mon (20/03) | 20 Mar 2023 | Exit 2 |  | Waterstop welding work
Mon (20/03) | 20 Mar 2023 | Exit 2 |  | BC cutter wheel installation ongoing
Tue (21/03) | 21 Mar 2023 | Exit 1 |  | Continue hardcore levelling and access preparation
Tue (21/03) | 21 Mar 2023 | Zone 2 |  | Noise barrier footing formwork dismantling. Highlighted to continue i beam and noise panel installation, they have different team for this
Tue (21/03) | 21 Mar 2023 | Zone 4 TPE bound |  | Singtel works ongoing
Tue (21/03) | 21 Mar 2023 | North ramp along PDR3 |  | WH continue install hoarding here
Tue (21/03) | 21 Mar 2023 | Zone 1 |  | Tree feeling works
Tue (21/03) | 21 Mar 2023 | Zone 2 noise barrier footing |  | Continue to dismantle formwork and erect next section for casting (18m)
Tue (21/03) | 21 Mar 2023 | Exit 2 |  | End plate fabrication
Tue (21/03) | 21 Mar 2023 | Zone 1 NLL |  | Powergas fitting and pipe installation ongoing
Tue (21/03) | 21 Mar 2023 | Exit 3 |  | Backfilling works at washing bay. Preparation for crane shifting at around 3.30pm
Tue (21/03) | 21 Mar 2023 | Zone 1 Loyang Rise |  | 7/7nos trees felled. Uprooting and clearing works ongoing
Tue (21/03) | 21 Mar 2023 | Exit 3 |  | Backfilling works. 2 loads completed
Tue (21/03) | 21 Mar 2023 | Zone 3 |  | Ryobi-G TT for NCE
Tue (21/03) | 21 Mar 2023 | Exit 2 |  | Preparation works ongoing, tremie pipes all lifted down from the rack
Tue (21/03) | 21 Mar 2023 | Exit 3 |  | Safety / RA briefing conducted for shifting of crane to exit 1
Tue (21/03) | 21 Mar 2023 | Exit 2 |  | Water stop welding work ongoing
Tue (21/03) | 21 Mar 2023 | Exit 2 |  | Bc cutter teeth installation work ongoing
Tue (21/03) | 21 Mar 2023 | Zone 1 |  | WG preparing to commence work
Tue (21/03) | 21 Mar 2023 | Zone 2 |  | MPs grouting work ongoing
Tue (21/03) | 21 Mar 2023 | Exit 2 |  | BC cutter wheel works ongoing
Tue (21/03) | 21 Mar 2023 | CH1418-CH1406 | Telco duct | Lean concrete completed, housekeeping ongoing
Tue (21/03) | 21 Mar 2023 | Exit 1 |  | Rest area erection in progress
Tue (21/03) | 21 Mar 2023 | Zone 3 Loyang Way |  | Pressure test ongoing by Shingda
Wed (22/03) | 22 Mar 2023 | ABH74 |  | Preparing to start boring
Wed (22/03) | 22 Mar 2023 | ABH67 |  | Boring on going
Wed (22/03) | 22 Mar 2023 | ABH61 |  | Confirming termination depth
Wed (22/03) | 22 Mar 2023 | Exit 2 |  | Mechanic from Hong Kong will reach Singapore by 3PM. Probably 4PM will reach site for repairing. Mr Yoon will fetch him from air port
Wed (22/03) | 22 Mar 2023 | Zone 1 NLL |  | Powergas continue pipe laying at portion highlighted in red. Pipe to be laid ard 1.7m
Wed (22/03) | 22 Mar 2023 | Zone 1 Loyang Rise |  | Balance 3nos to uproot. Yesterday completed 4nos
Wed (22/03) | 22 Mar 2023 | Exit 1 |  | Access making to rest area
Wed (22/03) | 22 Mar 2023 | Zone 1 Changi bound |  | EL lane closure
Wed (22/03) | 22 Mar 2023 | Section U4 |  | Telco duct laying 12m
Wed (22/03) | 22 Mar 2023 | Exit 1 |  | Status of access for tree felling works
Wed (22/03) | 22 Mar 2023 | North Ramp | P13 onwards to PMH06 | Lean con for power duct completed
Wed (22/03) | 22 Mar 2023 | Zone 1 | night work | WG preparing to commence excavation work, they’ll start ~3m away from PMH03. Excavation will commence after last bus & they will under cross the live drain
Wed (22/03) | 22 Mar 2023 | Exit 2 |  | Bc cutter maintenance work ongoing
Wed (22/03) | 22 Mar 2023 | Exit 3 |  | Soil levelling and compaction. Today 2pm NDT
Thu (23/03) | 23 Mar 2023 | Zone 2 NLL |  | Pgas working here
Thu (23/03) | 23 Mar 2023 | Exit 2 |  | Slope concrete lining next to ECM pond casting
Thu (23/03) | 23 Mar 2023 | Zone 1 | night work | Excavation for 1st layer strut done, shoring / strutting installation ongoing
Thu (23/03) | 23 Mar 2023 | Exit 2 |  | Levelling of slope and improve on slope protection
Thu (23/03) | 23 Mar 2023 | Exit 2 |  | Testing of BC cutter (cutter body) on going. Surveryor marking to start preexcavation for DW52
Thu (23/03) | 23 Mar 2023 | Zone 3 |  | 7nos of tree fell toward changi bound. (All Khaya)
Thu (23/03) | 23 Mar 2023 | Exit 1 |  | Extension of hardcore laying for tree felling
Thu (23/03) | 23 Mar 2023 | PMH-7 |  | Continue of wall formwork closing
Thu (23/03) | 23 Mar 2023 | Exit 2 |  | Pre excavation done for DW52
Thu (23/03) | 23 Mar 2023 | Exit 2 |  | Mechanic and electrician continue testing of machine. Tonight target to start excavation
Thu (23/03) | 23 Mar 2023 | Zone 2 |  | ABH-18 hand augering work ongoing
Thu (23/03) | 23 Mar 2023 | Exit 2 |  | Steel plates arranging for platform
Thu (23/03) | 23 Mar 2023 | Near MH8 |  | 1 span of telecom duct cast
Thu (23/03) | 23 Mar 2023 | Zone 2 |  | Wee guan continue excavation for power duct
Thu (23/03) | 23 Mar 2023 | Zone 2 noise barrier footing |  | Preparing working platform. Plan for casting today, 30m
Thu (23/03) | 23 Mar 2023 | Zone 1 |  | Pending replacement of EL water barriers & Gate 1 installation
Thu (23/03) | 23 Mar 2023 | Zone 1 |  | No activity
Thu (23/03) | 23 Mar 2023 | Zone 1 | to CV | DE143 working middle lane
Thu (23/03) | 23 Mar 2023 | Zone 1 |  | Area marked in red still open to public, EL water barriers haven’t replaced
Thu (23/03) | 23 Mar 2023 | Exit 1 |  | WH continue excavation for C7 drain work
Thu (23/03) | 23 Mar 2023 | Exit 1 |  | Painting of hard barrier for new rest area
Thu (23/03) | 23 Mar 2023 | Exit 1 |  | Manual excavation for hoarding footing
Fri (24/03) | 24 Mar 2023 | Zone 2 | SI | ABH-18 drilling works started
Fri (24/03) | 24 Mar 2023 | Exit 1 |  | Steel plate shift to prepare proper working platform for tree felling work
Fri (24/03) | 24 Mar 2023 | Zone 1 | NLL | Powergas preparation for pipe testing works
Fri (24/03) | 24 Mar 2023 | PMH-7 |  | Wall stage 1 cast yesterday. Curing in progress
Fri (24/03) | 24 Mar 2023 | Telco duct | near PMH8 | 12m cast yesterday. Curing in progress
Fri (24/03) | 24 Mar 2023 | Zone 2 |  | VIG removal ongoing
Fri (24/03) | 24 Mar 2023 | Zone 2 POB staircase 1 |  | Preparing area before start crushing works. Noise balloon will be set up near LVC area
Fri (24/03) | 24 Mar 2023 | Zone 1 | in front of Blk 275 | Noise barrier columns status by de143
Fri (24/03) | 24 Mar 2023 | Zone 1 | to CV | Pgas oso working here, TMA provided
Fri (24/03) | 24 Mar 2023 | Zone 2 ABH-19 |  | Trial trench in progress
Fri (24/03) | 24 Mar 2023 | Zone 1 |  | No activity
Fri (24/03) | 24 Mar 2023 | DW052 |  | Excavation reached 16m depth (1st bite)
Fri (24/03) | 24 Mar 2023 | Zone 2 near PDR3/LA junction |  | Tonight's wee guan work to continue excavation
Fri (24/03) | 24 Mar 2023 | Exit 2 |  | Slope protection casting was done. Now hard barrier installation
Fri (24/03) | 24 Mar 2023 | Exit 1 to slurry wall |  | WH started hoarding dismantling of access
Fri (24/03) | 24 Mar 2023 | Zone 3 near junction |  | Ryobi G doing TT for their NCE approval
Sat (25/03) | 25 Mar 2023 | Zone 2 |  | VIG removal in progress
Sat (25/03) | 25 Mar 2023 | Zone 2 |  | Excavation after PMH6 ongoing
Sat (25/03) | 25 Mar 2023 | Zone 2 |  | Plan to cast 18m of Power USD today
Sat (25/03) | 25 Mar 2023 | Zone 2 |  | Rebar works for Noise barrier footing in progress
Sat (25/03) | 25 Mar 2023 | Loyang Way/Exit 1 |  | Hoarding door to be installed
Sat (25/03) | 25 Mar 2023 | Exit 1 |  | WF manual excavation at 1.1m depth as near to utilities
Sat (25/03) | 25 Mar 2023 | Exit 3 |  | Levelling of hardcore ongoing. Reminded WHDA to remove rebar from the hardcore
Sat (25/03) | 25 Mar 2023 | Zone 2 |  | Tree logs loaded to be shifted to Nparks designated area
Sat (25/03) | 25 Mar 2023 | Zone 1 |  | Gas pipe works yet to start
Sat (25/03) | 25 Mar 2023 | Exit 2 |  | Fabrication of end plate
Sat (25/03) | 25 Mar 2023 | Exit 1 |  | Shingda working along Loyang Way
Sun (26/03) | 26 Mar 2023 | Exit 3 |  | SI no activity. Hardcore levelling ongoing
Sun (26/03) | 26 Mar 2023 | Zone 2 noise barrier |  | No activity
Sun (26/03) | 26 Mar 2023 | Zone 1 |  | No activity
Sun (26/03) | 26 Mar 2023 | Zone 1 PRD3 |  | Works at sewer manhole by PUB
Sun (26/03) | 26 Mar 2023 | Blk222 |  | Noise reading within allowable level as of now
Sun (26/03) | 26 Mar 2023 | Exit 1 |  | Water pipeline works ongoing. Have informed sup to look out for pedestrians and safely guide them
Sun (26/03) | 26 Mar 2023 | JTC blk 2 |  | Excavation (1m depth) for water pipe laying. Plan to lay around 18m
Sun (26/03) | 26 Mar 2023 | Exit 3 |  | Continue hardcore laying
Sun (26/03) | 26 Mar 2023 | Zone 2 |  | Excavation and shoring works to undercross drain in progress
Sun (26/03) | 26 Mar 2023 | JTC blk 2 |  | Water pipe laying completed 16m. WF working until 4pm today
Sun (26/03) | 26 Mar 2023 | Exit 2 |  | Making of new access and clearing grass
Sun (26/03) | 26 Mar 2023 | Zone 3 near Lincstech |  | No activity
Sun (26/03) | 26 Mar 2023 | Zone 3 Loyang Way |  | DE143 works at centre median
Sun (26/03) | 26 Mar 2023 | Exit 1 |  | Chemical storage area erection ongoing
Sun (26/03) | 26 Mar 2023 | Exit 1 |  | WF preparing for pipe connection
Mon (27/03) | 27 Mar 2023 | Lane 2 |  | Premix hacking done for TT. Will continue with excavation
Mon (27/03) | 27 Mar 2023 | Zone 2 ABH18 |  | In progress. Currently at 38m
Mon (27/03) | 27 Mar 2023 | Exit 1 |  | Gate valve installation status by WF
Mon (27/03) | 27 Mar 2023 | Exit 3 | BH-195 | Drilling works ongoing, current depth 26m
Mon (27/03) | 27 Mar 2023 | Zone 2 Noise Barrier footing |  | Preparing to dismantle formwork
Mon (27/03) | 27 Mar 2023 | Along Zone 2 |  | Soil at the side table, removal ongoing
Mon (27/03) | 27 Mar 2023 | PMH-7 |  | Wall formworks installation
Mon (27/03) | 27 Mar 2023 | PMH6-5 |  | Pipe laying and rebar works ongoing. 12m
Mon (27/03) | 27 Mar 2023 | Zone 1 |  | Excavation works to lean concrete for base of noise barrier footing. Will continue in afternoon
Mon (27/03) | 27 Mar 2023 | Zone 1 ABH-18 |  | Coring work ongoing, 46m depth
Mon (27/03) | 27 Mar 2023 | DW049 first bite |  | Trenching at 26.5m
Mon (27/03) | 27 Mar 2023 | Zone 3 |  | HSL crane counterweight assembly
Mon (27/03) | 27 Mar 2023 | Zone 3 insinde Linsctech boundary |  | Trial trench to identify utilities just started
Mon (27/03) | 27 Mar 2023 | Zone 3 |  | Rig set up for drilling works for IS 36003
Mon (27/03) | 27 Mar 2023 | Zone 1 LP 1 to 200 |  | WHDA continue with fwk / excavation for noise barrier footing base. They plan to cast today afternoon, while avoiding utility manholes & signgage that are in the way while WHDA get these sorted out
Mon (27/03) | 27 Mar 2023 | Zone 3 VS |  | Tree feeling 8 nos completed
Mon (27/03) | 27 Mar 2023 | Exit 1 |  | Brickwall construction for water pipe valve
Mon (27/03) | 27 Mar 2023 | Zone 3 |  | Silt fence installation and perimeter drain excavation
Mon (27/03) | 27 Mar 2023 | Exit 1 |  | Shifting rebar cages
Mon (27/03) | 27 Mar 2023 | DW49 |  | Steel plate adjusting for 2nd bite excavation
Mon (27/03) | 27 Mar 2023 | CH1260 to 1240 |  | Lean concrete was done for Power duct
Mon (27/03) | 27 Mar 2023 | Slip road near PMH3 |  | Wee Guan continue excavation to install ERSS for power duct
Mon (27/03) | 27 Mar 2023 | Zone 3 VS |  | Tree feeling temporary stop due to rain
Tue (28/03) | 28 Mar 2023 | BH 47 |  | Drilling/SPT at 4m depth
Tue (28/03) | 28 Mar 2023 | Zone 1 NLL |  | No activity
Tue (28/03) | 28 Mar 2023 | Zone 1 Loyang Rise |  | Base lean concrete cast yesterday for noise barrier footing, 50m
Tue (28/03) | 28 Mar 2023 | Zone 3 |  | Drilling of IS 36003 continue. 6m depth now
Tue (28/03) | 28 Mar 2023 | Zone 3 |  | ECM pond excavation found concrete slab at 1.1m. Cable detection done yesterday and no signal found. No utility here also as per drawing. Manual hacking in progress
Tue (28/03) | 28 Mar 2023 | Zone 2 ABH18 |  | In progress, 56m. Termination depth ard 58m
Tue (28/03) | 28 Mar 2023 | Zone 2 |  | ABH 18 Terminated at 58.5m depth
Tue (28/03) | 28 Mar 2023 | Zone 1 loyang rise |  | 20m lean concrete done
Tue (28/03) | 28 Mar 2023 | Zone 3 ABH46 |  | Preparing to start
Tue (28/03) | 28 Mar 2023 | 2nd bite |  | Excavation reached 15m depth. Now checking of mud hoses
Tue (28/03) | 28 Mar 2023 | PMH6 |  | Base slab continue casting
Tue (28/03) | 28 Mar 2023 | Exit-1 |  | Water valve chamber brickwork and cover completed today. Balance to install meter by PUB for water turn on
Tue (28/03) | 28 Mar 2023 | Exit 3 |  | BH195 termination depth at 33.18m. Now packer test ongoing
Tue (28/03) | 28 Mar 2023 | Along zone 2 |  | Making of barricade for designated access
Tue (28/03) | 28 Mar 2023 | Zone 2 noise barrier footing |  | Continue formwork closing, 18m
Wed (29/03) | 29 Mar 2023 | Zone 3 |  | Cable pulling for power supply to exit 1
Wed (29/03) | 29 Mar 2023 | Zone 1 |  | Noise barrier footing base excavation ongoing
Wed (29/03) | 29 Mar 2023 | Zone 3 VS area |  | Tree trunks clearing and uprooting works
Wed (29/03) | 29 Mar 2023 | BH47 |  | Drilling/SPT at 24m
Wed (29/03) | 29 Mar 2023 | BH46 |  | Drilling and SPT at 20m
Wed (29/03) | 29 Mar 2023 | Zone 2 LVC shelter |  | Pending staircase & EL painting work ongoing
Wed (29/03) | 29 Mar 2023 | Zone 2 SI |  | ABH18 completed. Rig has been shifted to ABH19
Wed (29/03) | 29 Mar 2023 | Zone 3 |  | ECM pond for slurry wall works concrete lining completed yesterday. Volume capacity 25m3
Wed (29/03) | 29 Mar 2023 | Zone 3 |  | DE143 working at loyang way
Wed (29/03) | 29 Mar 2023 | Zone 2 |  | Center median soil removal ongoing
Wed (29/03) | 29 Mar 2023 | Zone 2 | Noise barrier footing | 18m cast completed. Materials shifting to zone 1 ongoing
Wed (29/03) | 29 Mar 2023 | Zone 2 Power duct |  | 18m pipe laying completed. Casting today. Concrete ordered
Wed (29/03) | 29 Mar 2023 | PMH7 |  | Continue wall rebar and formwork closing. Target to cast tomorrow
Wed (29/03) | 29 Mar 2023 | Zone 2 |  | Access barricades set up ongoing
Wed (29/03) | 29 Mar 2023 | POB staircase 2 |  | Railing joints cutting for crushing tomorrow
Wed (29/03) | 29 Mar 2023 | Near PMH6 |  | Casting of Power duct (1 span) in progress
Wed (29/03) | 29 Mar 2023 | PMH7 |  | Roof slab rebar work in progress
Wed (29/03) | 29 Mar 2023 | Zone 2 noise barrier footing |  | Today will cast 18m. Continue rebar fixing for next section and shifting of materials
Wed (29/03) | 29 Mar 2023 | Zone 3 mapple tree |  | Green completed water pipe laying last night. Today plan to lay along the slope (red)
Thu (30/03) | 30 Mar 2023 | PMH07 |  | Top rebar tying work ongoing & wall fwk closure in progress
Thu (30/03) | 30 Mar 2023 | PMH-06 |  | Current status, slab fwk removal ongoing
Thu (30/03) | 30 Mar 2023 | GL P12 |  | Power duct status
Thu (30/03) | 30 Mar 2023 | Zone 2 North Ramp | GL 09-P10 | Current status of capping beam
Thu (30/03) | 30 Mar 2023 | GL P9 |  | 8 nos to manually hack micropile to COL
Thu (30/03) | 30 Mar 2023 | Zone 1 LP200 |  | Fwk closure for noise barrier footing ongoing
Thu (30/03) | 30 Mar 2023 | Zone 2 MP works |  | Pending last 4 nos, VSK carrying out housekeeping work
Thu (30/03) | 30 Mar 2023 | Zone 1 |  | Noise barrier footing base cast until existing bus stop. WHDA have yet to replace EL water barriers with theirs
Thu (30/03) | 30 Mar 2023 | Zone 3 |  | Soil disposal from ECM pond ongoing
Thu (30/03) | 30 Mar 2023 | Zone 3 |  | Excavation ongoing to expose root ball for transplanting trees
Thu (30/03) | 30 Mar 2023 | Zone 3 |  | Tree pruning for the 7 nos transplanting trees completed
Thu (30/03) | 30 Mar 2023 | Exit 3 |  | Hardcore laying in progress
Thu (30/03) | 30 Mar 2023 | Zone 2 |  | Noise barrier footing - formworks dismantling
Thu (30/03) | 30 Mar 2023 | Zone 2 | ABH-20 | Drilling works in progress, current depth 14m
Thu (30/03) | 30 Mar 2023 | Zone 2 | ABH-19 | Drilling works in progress, current depth 27m
Thu (30/03) | 30 Mar 2023 | Zone 3 |  | Delivery of steel plates for piling rig platform
Thu (30/03) | 30 Mar 2023 | Zone 1 | Noise barrier footing | 18m Formwork closing ongoing. Target to cast tmr
Thu (30/03) | 30 Mar 2023 | Zone 1 |  | Height limit bar for gate installation ongoing
Thu (30/03) | 30 Mar 2023 | Exit 3 |  | Clearing of hardcore for setting out of guidewall for panel 33,34 and 35
Thu (30/03) | 30 Mar 2023 | Exit 3 |  | Guidewall setting out for panel 33-35
Thu (30/03) | 30 Mar 2023 | DW053 |  | Resume excavation after changing of cutter teeth
Thu (30/03) | 30 Mar 2023 | JTC blk 2 |  | Preparation for water pipe pressure test tmr. Access ladder installation in progress
Thu (30/03) | 30 Mar 2023 | Zone 1 |  | Wee Guan preparing for TT works. Hacking to be completed before 10pm
Thu (30/03) | 30 Mar 2023 | Zone 2 POB Demolition |  | Installation of protection screen started
Thu (30/03) | 30 Mar 2023 | Zone 2 POB Demolition |  | Status of soil clearing for crane parking location
Fri (31/03) | 31 Mar 2023 | Zone 2 LVC |  | Trial trench for sewer 2 launching shaft in progress by LCH
Fri (31/03) | 31 Mar 2023 | 2nd bite |  | Excavation reached 21m as of now
Fri (31/03) | 31 Mar 2023 | Zone 1 | noise barrier footing | Working platform erection prior to bolt installation
Fri (31/03) | 31 Mar 2023 | Zone 1 | Gate 1 | Height gantry status
Fri (31/03) | 31 Mar 2023 | Zone 1 | NLL | SK here for LP installation
Fri (31/03) | 31 Mar 2023 | Zone 3 toward Changi bound |  | Felling of big trees in progress. Total 10nos of big trees to fell here
Fri (31/03) | 31 Mar 2023 | Exit 1 |  | WH removal of generator and cables. Permanent power supply is used for ECM plants
Fri (31/03) | 31 Mar 2023 | Exit 3 |  | Excavation for guidewall started
Fri (31/03) | 31 Mar 2023 | Zone 1 TT |  | Found water pipe
Fri (31/03) | 31 Mar 2023 | Zone 1 |  | Backfilling of trial trench ongoing
Fri (31/03) | 31 Mar 2023 | Exit 3 |  | Guidewall excavation status
Fri (31/03) | 31 Mar 2023 | Zone 2 |  | Green railing dismantling
Fri (31/03) | 31 Mar 2023 | Zone 2 |  | Plate load test for mobile crane outrigger location
Fri (31/03) | 31 Mar 2023 | DW053 |  | 3rd bite excavation started
Fri (31/03) | 31 Mar 2023 | Exit 2 | DW048 | Pre-excavation ongoing
Fri (31/03) | 31 Mar 2023 | Zone 1 |  | WG lane closure. 4/4nos TT completed. Tonight plan for steel decking
Sun (02/04) | 02 Apr 2023 | Zone 3 |  | RG working outside Lincstech
Sun (02/04) | 02 Apr 2023 | Zone 2 |  | No activity
Sun (02/04) | 02 Apr 2023 | Exit 1 |  | Welding works for bentonite piping connection ongoing
Sun (02/04) | 02 Apr 2023 | Exit 1 |  | Release of water after water testing. Some very minor leakage at the base
Sun (02/04) | 02 Apr 2023 | Exit 1 |  | Barrier painting in progress
Sun (02/04) | 02 Apr 2023 | Exit 1 |  | WHDA is planning to connect flexible hose at the slope area (green) and rigid pipes for the other areas (blue)
Sun (02/04) | 02 Apr 2023 | Zone 1 |  | No activity
Sun (02/04) | 02 Apr 2023 | Exit 2 |  | Shifting of steel plates for DW048 excavation ongoing
Sun (02/04) | 02 Apr 2023 | Exit 2 |  | Extraction of DW053 endplate still ongoing
Sun (02/04) | 02 Apr 2023 | DW048 |  | Pre excavation done. Tonight plan to start excavation of this Dwall panel
Mon (03/04) | 03 Apr 2023 | Lane 1 |  | Continue pumping out rain water before continue with excavation
Mon (03/04) | 03 Apr 2023 | DW053 |  | Cage A (3/3 cages lowering down). Cage B (2/3 cages lowered down, preparing to lower down last cage)
Mon (03/04) | 03 Apr 2023 | DW048 |  | Excavation reached 26.5m as of now
Mon (03/04) | 03 Apr 2023 | Zone 2 |  | Noise barrier footing formworks dismantling
Mon (03/04) | 03 Apr 2023 | PMH-7 |  | Formwork dismantling
Mon (03/04) | 03 Apr 2023 | PMH6 |  | Formwork dismantling & pipe laying to connect to pmh 6 from pmh 7
Mon (03/04) | 03 Apr 2023 | Zone 1 |  | Rest area and cube house making in progress
Mon (03/04) | 03 Apr 2023 | Zone 2 within LVC |  | Trial trench for sewer 2
Mon (03/04) | 03 Apr 2023 | Zone 3 |  | Hardcore laying for ULT5 plant platform ongoing. To shift in bentonite plant tmr once hardcore laying is completed
Mon (03/04) | 03 Apr 2023 | Zone 3 |  | Inclinometer installation completed
Mon (03/04) | 03 Apr 2023 | DW048 |  | BC cutter machine set up to start excavation
Mon (03/04) | 03 Apr 2023 | DW053 |  | Cage A ( 2/3 cage lowered down). Cage B (2/3 cage lowered down in progress)
Mon (03/04) | 03 Apr 2023 | PMH5 |  | Concrete on site for lean concrete
Tue (04/04) | 04 Apr 2023 | Zone 2 SI | ABH22-2 and ABH22-3 | Drilling work ongoing. Current depth 16m
Tue (04/04) | 04 Apr 2023 | Zone 4 Hi-Tech |  | TT completed. Found 700mm dia water pipe & singtel haunching
Tue (04/04) | 04 Apr 2023 | DW053 |  | Casting in progress. 76.5/ 136m3
Tue (04/04) | 04 Apr 2023 | Zone 2 North Ramp | PMH6 | Fwk support erection for top slab ongoing & continue backfilling for the power duct
Tue (04/04) | 04 Apr 2023 | Zone 2 North Ramp) |  | Excavation towards PMH04
Tue (04/04) | 04 Apr 2023 | Zone 2 | GL P09 | Rebar work for capping beam ongoing
Tue (04/04) | 04 Apr 2023 | Zone 2 Micropile |  | Balance 4 nos (198, 200, 202 and 204) currently clearing slurry choke from their pump. Target to resume after lunch
Tue (04/04) | 04 Apr 2023 | Loyang Way | near exit 1 | DE143 works at centre median
Tue (04/04) | 04 Apr 2023 | PMH-07 |  | Current status
Tue (04/04) | 04 Apr 2023 | Zone 2 SI | ABH22-2 and ABH22-3 | Drilling work ongoing
Tue (04/04) | 04 Apr 2023 | Zone 4 LP100 Hi-Tech |  | Trial trench to identify water pipe. Yesterday completed 1 section, no water pipe found
Wed (05/04) | 05 Apr 2023 | Zone 3 |  | Preparing for ABH-64 TT work
Wed (05/04) | 05 Apr 2023 | Zone 3 Hoarding | along Selarang Camp | Manual excavation for hoarding post ongoing
Wed (05/04) | 05 Apr 2023 | Zone 3 |  | Clearing of trees felled ytd
Wed (05/04) | 05 Apr 2023 | Zone 3 |  | Perimeter drain casting ongoing
Wed (05/04) | 05 Apr 2023 | Power duct at P11 |  | Preparing to cut the pipes due to the change in the power USD for P11 and P10
Wed (05/04) | 05 Apr 2023 | DW048 |  | Waiting for last lorry
Wed (05/04) | 05 Apr 2023 | Zone 3 Lincstecth |  | B&T continue excavation work for noise barrier footing base
Wed (05/04) | 05 Apr 2023 | Zone 2 LVC |  | Manual excavation for staircase construction
Wed (05/04) | 05 Apr 2023 | Zone 1 noise barrier footing |  | 18m already cast. Another 12m pending casting
Wed (05/04) | 05 Apr 2023 | Zone 2 |  | 750T crane just demobilised from site
Wed (05/04) | 05 Apr 2023 | Zone 2 |  | Tree felling in progress
Wed (05/04) | 05 Apr 2023 | Exit 3 |  | Materials were shifted to zone 3 yesterday. Now tidying up the area
Wed (05/04) | 05 Apr 2023 | casting completed at 11 |  | 15am
Wed (05/04) | 05 Apr 2023 | Zone 3 yesterday |  | Trees felled (TPE bound): 22nos, Uprooted (changi bound): 17nos
Wed (05/04) | 05 Apr 2023 | Zone 2 | changi bound | 12 trees felled
Wed (05/04) | 05 Apr 2023 | Zone 3 Exit 2 |  | Crawler crane servicing today and tmr ongoing
Wed (05/04) | 05 Apr 2023 | Zone 3 |  | ~7 loads of hardcore here
Wed (05/04) | 05 Apr 2023 | Zone 3 | along Selarang Camp | 28nos of hoarding post casting ongoing
Wed (05/04) | 05 Apr 2023 | DW-051 |  | Excavation ongoing
Wed (05/04) | 05 Apr 2023 | PMH-05 |  | Pending to cast
Wed (05/04) | 05 Apr 2023 | Zone 2 noise barrier |  | Today plan to start i-beam installation
Wed (05/04) | 05 Apr 2023 | ULT-5 |  | HSL continue with site preparation work
Wed (05/04) | 05 Apr 2023 | Zone 3 |  | VIG removal ongoing
Wed (05/04) | 05 Apr 2023 | BH-63 |  | Drilling ongoing, 13m depth
Wed (05/04) | 05 Apr 2023 | PMH7 neck |  | Cast yesterday
Thu (06/04) | 06 Apr 2023 | Zone 2 |  | Trees trunks removal ongoing. Later will continue with uprooting
Thu (06/04) | 06 Apr 2023 | Zone 2-Noise barrier |  | Access making ongoing for panel installation
Thu (06/04) | 06 Apr 2023 | Zone 2 | near to PMH3 after drain | They’ll cast this portion tonight, target vol: 14m3. Concrete batch ETA 11pm
Thu (06/04) | 06 Apr 2023 | Zone 1 | Lane 1 LA to PRD3 | Excavation for S2 strut ongoing
Thu (06/04) | 06 Apr 2023 | Zone 4 |  | Hi-Tech preparing to start trial trench. TT to find water pipe
Thu (06/04) | 06 Apr 2023 | PMH-9 to PMH-8 |  | Area preparation ongoing for base lean concrete (20m)
Thu (06/04) | 06 Apr 2023 | PMH-6 |  | Stage 2 wall rebar works ongoing
Thu (06/04) | 06 Apr 2023 | PMH-5 to PMH-4 |  | Power Pipe laying ongoing (24m)
Thu (06/04) | 06 Apr 2023 | Zone 2 noise barrier footing |  | Continue formwork installation for next section, 18m
Thu (06/04) | 06 Apr 2023 | Zone 1 |  | No activity
Thu (06/04) | 06 Apr 2023 | Zone 2 LVC |  | Continue manual excavation for staircase
Thu (06/04) | 06 Apr 2023 | Zone 2 |  | ABH22-3 & ABH22-2 current depth at 43m. Permeability tests ongoing
Thu (06/04) | 06 Apr 2023 | Zone 4 TT |  | Found starhub, LV, PVC pipe, drain & HV slab
Thu (06/04) | 06 Apr 2023 | Zone 2 |  | Uprooting works ongoing. Today will uproot 11nos
Thu (06/04) | 06 Apr 2023 | Zone 2 near Shell LP199/1 |  | Trial trench in progress for receiving shaft
Thu (06/04) | 06 Apr 2023 | Sewer 5 |  | Manhole trial trench completed. Pending Utility Engr for confirmation
Thu (06/04) | 06 Apr 2023 | PMH-9 to 8 |  | Base Lean concrete completed
Thu (06/04) | 06 Apr 2023 | PMH-6 |  | Continue of stage 2 wall rebar works
Thu (06/04) | 06 Apr 2023 | PMH-5 to PMH-4 |  | Power Pipe laying 24m target to cast today. Concrete ordered
Thu (06/04) | 06 Apr 2023 | Zone 3 | near Selarang Camp | Continue hoarding posts installation. Today plan to complete hoarding (~60m)
Thu (06/04) | 06 Apr 2023 | Exit 3 |  | Guidewall Formwork dismantling
Thu (06/04) | 06 Apr 2023 | Exit 3 |  | Shifting of hardcore to exit 1
Thu (06/04) | 06 Apr 2023 | DW-051 |  | 28.2m depth
Thu (06/04) | 06 Apr 2023 | Zone 3 |  | Guidewall excavation for slurry wall started
Fri (07/04) | 07 Apr 2023 | Zone 3 |  | Uprooting works ongoing. Today will uproot 14nos
Fri (07/04) | 07 Apr 2023 | Exit 1 |  | New access excavation and levelling works
Fri (07/04) | 07 Apr 2023 | Zone 3 Slurry Wall area |  | Steel plates unloading works
Fri (07/04) | 07 Apr 2023 | Zone 3 Slurry Wall |  | Rebar works for guidewall. Target to cast 10m today
Fri (07/04) | 07 Apr 2023 | Zone 3 Slurry Wall |  | BC cutter assembly and inspection woeks
Fri (07/04) | 07 Apr 2023 | Exit 1 slurry tank |  | PU grouting for leakage area. Total 4 locations
Fri (07/04) | 07 Apr 2023 | Exit 3 |  | Materials clearing and shifting in progress
Fri (07/04) | 07 Apr 2023 | North ramp | PMH5 to 4 | 24m power duct cast yesterday
Fri (07/04) | 07 Apr 2023 | Exit 2 |  | Dwall-47 pre-excavation works started
Fri (07/04) | 07 Apr 2023 | Zone 3 |  | Trees uprooting works completed. Total 14nos
Fri (07/04) | 07 Apr 2023 | Exit 1 |  | Continue levelling works for new access
Fri (07/04) | 07 Apr 2023 | Zone 3 Slurry Wall |  | Formwork installation for guidewall. Target to cast 10m around 6pm
Fri (07/04) | 07 Apr 2023 | DW-051 |  | Desanding completed, preparing for koden test
Sat (08/04) | 08 Apr 2023 | Zone 2 | bus depot | Preparing to continue pipe laying work
Sat (08/04) | 08 Apr 2023 | DW47 |  | 1st bite - excavation in progress, 28m
Sat (08/04) | 08 Apr 2023 | DW51 |  | Cage A (2/3 done). Cage B (1/3 done, 2nd cage lapping in progress)
Sat (08/04) | 08 Apr 2023 | ATTZ3-21 |  | Road premix removal for TT by Hi-tech to identify 200mm dia water pipe
Sat (08/04) | 08 Apr 2023 | DW51 |  | Cage A (3/3 cage installation in progress). Cage B (2/3 cage installed)
Sat (08/04) | 08 Apr 2023 | DW47- 1st bite |  | Excavation reached toe level, 28m depth
Sat (08/04) | 08 Apr 2023 | DW-051 |  | Lowering of cages 3B&2B
Sat (08/04) | 08 Apr 2023 | DW-047 |  | Cutter teeth changing ongoing
Sat (08/04) | 08 Apr 2023 | Zone 2 |  | Hardcore and soil clearing at center median. BRC laying for cast back in progress
Sat (08/04) | 08 Apr 2023 | PMH06 |  | Balance rebar work in progress for wall and top slab. Plan to cast today
Sat (08/04) | 08 Apr 2023 | PMH05 |  | Wall rebar work in progress
Sat (08/04) | 08 Apr 2023 | Zone 1 | next to AWWA | Continue excavation to S2 strut
Sat (08/04) | 08 Apr 2023 | PMH05 to PMH04 |  | Steel plate installation work
Sun (09/04) | 09 Apr 2023 | Exit 2 |  | Rebar cages delivery for Dwall 47
Sun (09/04) | 09 Apr 2023 | Exit 1 |  | Access making in progress
Sun (09/04) | 09 Apr 2023 | Exit 1 |  | Extension of muck pit for future additional desander
Sun (09/04) | 09 Apr 2023 | Zone 2 |  | 18m noise barrier cast yesterday
Sun (09/04) | 09 Apr 2023 | PMH-6 |  | Wall and top slab cast yesterday
Sun (09/04) | 09 Apr 2023 | Zone 1 |  | 12m of noise barrier footing cast yesterday. Total 30m cast at zone 1
Sun (09/04) | 09 Apr 2023 | DW-051 |  | Casting started at 1:25am & in progress
Sun (09/04) | 09 Apr 2023 | Exit 2 | Dwall 47 | 2nd bite excavation completed. Preparing for koden test
Sun (09/04) | 09 Apr 2023 | Exit 2 |  | All rebar cages already delivered on site for dwall 47
Sun (09/04) | 09 Apr 2023 | Exit 1 |  | Current status for the new access
Sun (09/04) | 09 Apr 2023 | Exit 1 |  | BRC laying for the extended muck pit. Target to cast today
Sun (09/04) | 09 Apr 2023 | Exit 1 |  | Silo shifting in progress
Sun (09/04) | 09 Apr 2023 | Exit 2 | Dwall 47 | Koden test in progress
Sun (09/04) | 09 Apr 2023 | Zone 1 |  | WG 2nd team continue premix cutting for steel decking installation
Mon (10/04) | 10 Apr 2023 | PRD3 LP4 |  | WG team 1 lane closure for trial trench works
Mon (10/04) | 10 Apr 2023 | Zone 1 WG |  | Steel decking installation in progress
Mon (10/04) | 10 Apr 2023 | Zone 2 LP171 NB |  | Base plate fwk erection, followed by grouting & they’ll continue GI pipe installation
Mon (10/04) | 10 Apr 2023 | ATTZ3-22 |  | Identify 200mm dia water pipe at 1m and 300mm dia water pipe at 1.4m depth. Location : Loyang lane
Mon (10/04) | 10 Apr 2023 | Zone 2 Northramp Capping Beam |  | L-bar welding ongoing
Mon (10/04) | 10 Apr 2023 | Zone 2 PMH-08 |  | RW rebar work started
Mon (10/04) | 10 Apr 2023 | Zone 2 | Sewer Receiving Shaft | TT ongoing
Mon (10/04) | 10 Apr 2023 | Zone 2 LP187 |  | 13nos hoarding post casting ongoing
Mon (10/04) | 10 Apr 2023 | PMH-05 |  | 1st lift wall fwk closure ongoing, target to cast later
Mon (10/04) | 10 Apr 2023 | Btwn PMH05/4 | power duct | Levelling ongoing, target to lean con later
Mon (10/04) | 10 Apr 2023 | Exit 1 |  | Bentonite pipe laying and connection
Tue (11/04) | 11 Apr 2023 | Zone 2 in front of LVC |  | Noise barrier panel installation today to commence
Tue (11/04) | 11 Apr 2023 | Zone 2 |  | Noise barrier footing formwork dismantling. 18m
Tue (11/04) | 11 Apr 2023 | North ramp section U4 between PMH9-8 |  | Rebar installation for retaining wall base slab in progress. Target to cast tomorrow
Tue (11/04) | 11 Apr 2023 | PMH06 |  | Plinth formwork closing
Tue (11/04) | 11 Apr 2023 | PMH05 |  | Wall 1st lift curing
Tue (11/04) | 11 Apr 2023 | USD laying between PMH5-PMH4 |  | Today plan to cast 18m
Tue (11/04) | 11 Apr 2023 | Zone 1 | PMH01 | Current status; preparation work only
Tue (11/04) | 11 Apr 2023 | PRD3 LP4 |  | TT ongoing
Tue (11/04) | 11 Apr 2023 | Zone 1 |  | Shoring installation ongoing
Tue (11/04) | 11 Apr 2023 | Zone 2 | PMH-12 | Soil for backfilling work is here
Tue (11/04) | 11 Apr 2023 | Zone 3 |  | Boring rig assembly completed. Waiting for AE to inspect
Tue (11/04) | 11 Apr 2023 | Zone 2 | MH5-2 RS | Backfilling work ongoing
Tue (11/04) | 11 Apr 2023 | Zone 2 | MH5-1 | No activity
Tue (11/04) | 11 Apr 2023 | Zone 2 LP187 | to PDO | 13 nos hoarding post casting ongoing
Tue (11/04) | 11 Apr 2023 | Zone 1 PMH01 |  | Marking for the new location completed. Tomorrow plan to do plate load test at 1.5m and 3m depth respectively. Then will do TT progressively
Tue (11/04) | 11 Apr 2023 | Zone 1 NB |  | Protruding partition board removal (1 +1). No work for noise barrier footing today, the team here shifted to zone 3 Lincstech area
Tue (11/04) | 11 Apr 2023 | Exit 1 |  | Access casting in progress
Tue (11/04) | 11 Apr 2023 | DW47 |  | Koden test for last point in progress. 4/5 points done
Tue (11/04) | 11 Apr 2023 | DW047 |  | Platform for casting ongoing. Crane to shift nearer to dwall panel for concrete truck access. Truck to arrive tentatively 6pm
Tue (11/04) | 11 Apr 2023 | Exit 1 access |  | Casting in progress
Tue (11/04) | 11 Apr 2023 | DW047 rebar cage installation |  | 5/6nos installed as of now
Tue (11/04) | 11 Apr 2023 | DW047 LSS backfilling ongoing, current vol |  | 48m3. Est total vol: 120m3
Tue (11/04) | 11 Apr 2023 | Zone 2 |  | Access preparation for backfilling works behind silo area to continue USD construction and PMH12
Wed (12/04) | 12 Apr 2023 | Zone 2 |  | Noise barrier panel installation status. Boom lift operator MC for 2 days. Now work is idling. Highlighted to WX to arrange
Wed (12/04) | 12 Apr 2023 | Zone 2 |  | Continuation of noise barrier footing along LVC sheltered linkway no activity
Wed (12/04) | 12 Apr 2023 | Zone 2 ABH24 |  | Depth at 6m
Wed (12/04) | 12 Apr 2023 | ULT5 |  | Continue preparation work for ULT
Wed (12/04) | 12 Apr 2023 | Zone 2 ABH 32-1 |  | Depth at 8m
Wed (12/04) | 12 Apr 2023 | Zone 2 |  | Sewer 5-1 TT in progress
Wed (12/04) | 12 Apr 2023 | Zone 1 |  | WG to continue pipe laying tonight, 15m (36-way)
Wed (12/04) | 12 Apr 2023 | Zone 2 | ABH 23-1 | Drilling works ongoing, depth 24m
Wed (12/04) | 12 Apr 2023 | ABH 24 |  | Now at 18m depth
Wed (12/04) | 12 Apr 2023 | Zone 1 |  | No activity
Wed (12/04) | 12 Apr 2023 | USD connection to PMH5 |  | Rebar and Formwork closing works. Target to cast today 3m
Wed (12/04) | 12 Apr 2023 | RW base slab between PMH9-8 |  | Casting works in progress
Wed (12/04) | 12 Apr 2023 | ULT5 |  | Instrument installation on rebar cage
Wed (12/04) | 12 Apr 2023 | ULT5 |  | Premix removal for trial trench at pile location
Wed (12/04) | 12 Apr 2023 | DW047 LSS backfilling completed last night, total vol |  | 104m3
Wed (12/04) | 12 Apr 2023 | DW50 |  | Trenching in progress at 4m depth for 1st bite
Wed (12/04) | 12 Apr 2023 | Zone 3 |  | Bunkwall casting to contain silty water inside the ULT area incase of spillage
Wed (12/04) | 12 Apr 2023 | Zone 3 Lincstech area |  | No more activity observed
Wed (12/04) | 12 Apr 2023 | Zone 3 |  | Slurry guidewall rebar works in progress, 15m. To cast tomorrow
Wed (12/04) | 12 Apr 2023 | Zone 2 |  | Backfilling works for uSd and PMH12, now 4 loads delivered
Thu (13/04) | 13 Apr 2023 | PMH4 |  | Preparing to start PLT
Thu (13/04) | 13 Apr 2023 | Zone 2 noise barrier |  | Safety check prior to starting works. Boom lift operator on site
Thu (13/04) | 13 Apr 2023 | Exit 1 |  | Formwork removal for mud pit and will continue with hardcore backfilling
Thu (13/04) | 13 Apr 2023 | Exit 1 |  | Continue excavation for access balance casting
Thu (13/04) | 13 Apr 2023 | PMH12/USD area |  | NDT done earlier this morning. Today will continue backfilling. Noted that soil will be internally shifted from exit 1 today
Thu (13/04) | 13 Apr 2023 | DW50 |  | C-clamp welding before trimming works
Thu (13/04) | 13 Apr 2023 | North ramp | PMH10 | Gravity block wall formwork closing (21m). Today plan to cast
Thu (13/04) | 13 Apr 2023 | PMH5-4 |  | Power duct 12m rebar works and formwork closing. Target to cast today
Thu (13/04) | 13 Apr 2023 | North ramp | PMH4-3 | Excavation works ongoing and hardcore laying for PMH4. Lean concrete for pmh4 today
Thu (13/04) | 13 Apr 2023 | Zone 2 |  | Noise barrier panel installation
Thu (13/04) | 13 Apr 2023 | Zone 2 |  | Current status of noise barrier panel installation
Thu (13/04) | 13 Apr 2023 | PMH04 |  | Levelling done. Will lean concrete today
Thu (13/04) | 13 Apr 2023 | DW50 |  | Cutter teeth changing and preparation for trimming
Thu (13/04) | 13 Apr 2023 | Zone 3 |  | SW guidewall casting completed. 25m3
Thu (13/04) | 13 Apr 2023 | Zone 3 |  | BC cutter teeth welding works. Dayshift until 9pm
Thu (13/04) | 13 Apr 2023 | Zone 2 |  | Noise panel installation until 930 pm
Thu (13/04) | 13 Apr 2023 | North ramp section U4 |  | Pipe laying for power duct, 12m
Thu (13/04) | 13 Apr 2023 | Zone 1 near AWWA homes |  | Tonight casting of 22KV pipe, 36 way 15m lenght. Highlighted to install noise barrier here for AWWA homes
Thu (13/04) | 13 Apr 2023 | MH6-1 |  | Shaft location marking was done
Thu (13/04) | 13 Apr 2023 | Zone 2 LP195 |  | MH5-1 plan to start trial trench today
Thu (13/04) | 13 Apr 2023 | 2nd bite |  | Excavation in progress. 16m as of now
Fri (14/04) | 14 Apr 2023 | Zone 2 MH5-1 |  | Trial trench utility confirmation by UE
Fri (14/04) | 14 Apr 2023 | Zone 1 |  | No activity
Fri (14/04) | 14 Apr 2023 | North ramp U4 |  | Continue power duct pipe laying. Today plan to cast 18m
Fri (14/04) | 14 Apr 2023 | PMH-01 |  | Cutting road premix for TT to locate 700mm dia water pipe
Fri (14/04) | 14 Apr 2023 | PMH4 |  | Today plan for base slab works. Continue excavation towards PMH3 area
Fri (14/04) | 14 Apr 2023 | Zone 3 center median |  | Continue pruning of trees for transplanting
Fri (14/04) | 14 Apr 2023 | Zone 2 Loyang Ave |  | Hi-Tech trial trench ongoing
Fri (14/04) | 14 Apr 2023 | Exit 1 |  | Most of the Dongah workers are at Exit 1 for bentonite hose connection to SW. Target this week to complete
Fri (14/04) | 14 Apr 2023 | Zone 1 |  | USD power duct casting continue. Now pouring last load, 21m3
Fri (14/04) | 14 Apr 2023 | Zone 2 |  | Unloading of concrete blocks for PMH-12 area
Fri (14/04) | 14 Apr 2023 | DW50 |  | Trimming in progress
Fri (14/04) | 14 Apr 2023 | Zone 2 MH5-1 |  | Another trial trench done. This point awaiting for UE’s confirmation
Fri (14/04) | 14 Apr 2023 | North ramp U4 |  | Formwork closing in progress. Today plan to cast 18m
Fri (14/04) | 14 Apr 2023 | Zone 2 ABH26 |  | Trial trench completed. Hand auger in progress
Fri (14/04) | 14 Apr 2023 | PMH4 |  | Rebar works for base slab ongoing
Fri (14/04) | 14 Apr 2023 | PMH5 |  | Working platform erection in progress
Fri (14/04) | 14 Apr 2023 | DW050 |  | C lock welding ongoing
Fri (14/04) | 14 Apr 2023 | Zone 3 |  | Mandrel test unable to proceed due to wrong Mandrel equipment used. Not based on SPPG design. WHDA to rearrange the inspection
Fri (14/04) | 14 Apr 2023 | DW50 |  | End plate extraction at DW51 side
Fri (14/04) | 14 Apr 2023 | MH5-1 |  | Highlighted in green (completed TT). Red ( TT in progress)
Fri (14/04) | 14 Apr 2023 | MH8 to MH9 |  | 18m length of Power duct casting in progress
Fri (14/04) | 14 Apr 2023 | MH6-1 |  | TT done for 3m length × 1.6m depth. No services found as of now
Fri (14/04) | 14 Apr 2023 | DW50 |  | Welding of C-lock for trimming at DW49 side
Fri (14/04) | 14 Apr 2023 | DW50 |  | End plate extraction at DW49 side
Fri (14/04) | 14 Apr 2023 | Zone 3 |  | SW area, slope protection casting
Fri (14/04) | 14 Apr 2023 | Zone 1 near AWWA homes |  | Traffic decking removal. Tonight plan to remove shoring, backfill and premix
Fri (14/04) | 14 Apr 2023 | PMH12/USD area |  | Continue backfilling
Fri (14/04) | 14 Apr 2023 | Zone 2 noise barrier |  | Continue panel installation
Fri (14/04) | 14 Apr 2023 | Zone 2 ABH25 |  | Trial trench ongoing
Fri (14/04) | 14 Apr 2023 | MH6-1 |  | TT in progress for MH
Fri (14/04) | 14 Apr 2023 | ABH23-1 |  | Preparing for SPT. Current depth, 54m
Sat (15/04) | 15 Apr 2023 | DW50 |  | Shifting of BC cutter for DW50 rebar lowering down. DW47 : boring will start after working platform adjusting
Sat (15/04) | 15 Apr 2023 | ULT5 |  | Welding for instrument and instrument installation
Sat (15/04) | 15 Apr 2023 | ULT5 |  | HSL plan to install noise barrier panels around rig
Sat (15/04) | 15 Apr 2023 | ULT4 |  | Hi tech doing TT for feasible location
Sat (15/04) | 15 Apr 2023 | DW50 |  | Preparation for tremie pipes installation
Sat (15/04) | 15 Apr 2023 | PMH5 |  | Wall rebar work in progress
Sat (15/04) | 15 Apr 2023 | Zone 3 |  | Wee Guan mobilized water barrier and mini excavator
Sat (15/04) | 15 Apr 2023 | Zone 3 |  | 5/15 tree transplant. 5/6 tree felled at center median
Sat (15/04) | 15 Apr 2023 | DW50 |  | Cleaning in progress
Sat (15/04) | 15 Apr 2023 | DW47 |  | Pre-excavation completed
Sat (15/04) | 15 Apr 2023 | Zone 1 USD work |  | Backfilling status
Sat (15/04) | 15 Apr 2023 | MH6-1 |  | TT continue by LCH
Sat (15/04) | 15 Apr 2023 | ULT4 |  | Hitech has done TT. LV cable found
Sat (15/04) | 15 Apr 2023 | PMH05 |  | Wall rebar and top slab rebar work in progress. Plan to cast tomorrow
Sat (15/04) | 15 Apr 2023 | PMH4 |  | Formwork closing for base slab
Sat (15/04) | 15 Apr 2023 | DW50 |  | 2nd bite cleaning in progress
Sat (15/04) | 15 Apr 2023 | ULT5 |  | Continue instrument installation
Sat (15/04) | 15 Apr 2023 | Exit 1 |  | Bentonite hose laying to SW in progress. Target to complete by tomorrow
Sat (15/04) | 15 Apr 2023 | Zone 3 center median |  | 6nos of big trees and 6nos of small trees felled today. 5/16nos of big tree transplant
Sat (15/04) | 15 Apr 2023 | DW50 |  | Cleaning completed. desanding on going
Sat (15/04) | 15 Apr 2023 | DW50 |  | Actual depth check prior to Koden test
Sat (15/04) | 15 Apr 2023 | DW50 |  | All cage lowered. Hanging bar installation. Target to cast by 11pm
Sat (15/04) | 15 Apr 2023 | Zone 1 |  | Lane closing for wee guan works
Sun (16/04) | 16 Apr 2023 | Zone 1 Loyang Rise |  | No activity
Sun (16/04) | 16 Apr 2023 | Zone 1 PMH1 |  | Yesterday did the plate load test. Now preparing to backfill the area
Sun (16/04) | 16 Apr 2023 | Zone 2 sewer |  | No activity today
Sun (16/04) | 16 Apr 2023 | PMH5 |  | 2nd stage wall and top slab formwork completed. Pending inspection. Plan fo casting today
Sun (16/04) | 16 Apr 2023 | DW047 |  | 2nd bite resume
Sun (16/04) | 16 Apr 2023 | Exit 1 |  | Continue bentonite pipe connection
Sun (16/04) | 16 Apr 2023 | Zone 3 Wee Guan |  | No activity at the moment. The team is currently at zone 1
Sun (16/04) | 16 Apr 2023 | DW50 |  | Casting in progress for 1st and 2nd truck
Sun (16/04) | 16 Apr 2023 | DW50 |  | Casting completed. Total volume 149 m3
Sun (16/04) | 16 Apr 2023 | DW047 |  | End plate extraction ongoing
Mon (17/04) | 17 Apr 2023 | DW-047 |  | Guide wall top level checked, preparing to continue with 1st bite cleaning
Mon (17/04) | 17 Apr 2023 | Exit 3 |  | Hardcore and steel plate laying as preparation works for stage 2 dwall construction
Mon (17/04) | 17 Apr 2023 | ULT6 |  | Hi-tech doing TT to explore feasible location
Mon (17/04) | 17 Apr 2023 | ULT5 |  | Noise barrier installed for the rig
Mon (17/04) | 17 Apr 2023 | ULT5 |  | Instrument installed for the rebar cage
Mon (17/04) | 17 Apr 2023 | Zone 1 Loyang Rise |  | No activity
Mon (17/04) | 17 Apr 2023 | Zone 1 PRD3 |  | DE143 working at centre median
Mon (17/04) | 17 Apr 2023 | Zone 1 PMH1 |  | No activity
Mon (17/04) | 17 Apr 2023 | North ramp PMH8 |  | Soldier pile & steel plate installation
Mon (17/04) | 17 Apr 2023 | PMH5 |  | Formwork dismantling
Mon (17/04) | 17 Apr 2023 | PMH4 |  | First stage wall formwork installation. Plan for casting today
Mon (17/04) | 17 Apr 2023 | USD/PMH12 |  | Backfilling in progress
Mon (17/04) | 17 Apr 2023 | Sewer MH6-1 |  | TT completed. Found water pipe (abandoned), LCH to confirm it is abandoned by screw tapping
Mon (17/04) | 17 Apr 2023 | MH2-7 |  | This location is utility free area. TT and physical work can be done without impact anything
Mon (17/04) | 17 Apr 2023 | MH2-8 |  | Located at the center of gate 5 access. LCH to plan in away to have minimum impact to the access
Mon (17/04) | 17 Apr 2023 | Zone 2 near PD office |  | Bus stop dismantling on going
Mon (17/04) | 17 Apr 2023 | Exit 1 |  | Continue excavation for 2nd half of access
Mon (17/04) | 17 Apr 2023 | DW-047 |  | Excavation depth at 21m
Mon (17/04) | 17 Apr 2023 | DW-047 |  | Excavation completed, 28.2m depth from GWTL. raising cutter in progress
Mon (17/04) | 17 Apr 2023 | Exit 3 |  | Permeability in progress. 8:30PM to complete
Mon (17/04) | 17 Apr 2023 | PMH4 |  | Wall formwork closing done. Concrete ordered, 6m3
Mon (17/04) | 17 Apr 2023 | Zone 1 | LA to PRD3 | WG lane closure done
Mon (17/04) | 17 Apr 2023 | Zone 1 LA LP196 |  | Premix cutting ongoing, to continue 1st layer excavation & strut work
Tue (18/04) | 18 Apr 2023 | Zone 2 noise barrier footing |  | RC team (1 worker + 1 sup) here for next section of footing works. Rebar installation started
Tue (18/04) | 18 Apr 2023 | PMH12/USD |  | Backfilling in progress. Today will complete final layer and NDT will be done
Tue (18/04) | 18 Apr 2023 | Zone 3 |  | Casting back of SI locations along loyang avenue
Tue (18/04) | 18 Apr 2023 | Zone 3 |  | No activity observed by wee guan here
Tue (18/04) | 18 Apr 2023 | Zone 1 Loyang Ave LP198 |  | Premix cutting ongoing, tonight 2 teams both working at LA
Tue (18/04) | 18 Apr 2023 | Zone 2 LP187 |  | Existing bus shelter was dismantled. The location now will be used to erect the rest area
Tue (18/04) | 18 Apr 2023 | Zone 2 ABH26 |  | Drilling ongoing, depth at 40m
Tue (18/04) | 18 Apr 2023 | ABH25 |  | Drilling ongoing, depth at 48m
Tue (18/04) | 18 Apr 2023 | Zone 2 ABH27 |  | Trial trench in progress
Tue (18/04) | 18 Apr 2023 | ABH 66 |  | Grouting completed. Removal of NC casing in progress
Tue (18/04) | 18 Apr 2023 | BH45 |  | Just now terminated at 37.2m
Tue (18/04) | 18 Apr 2023 | Zone 2 sewer |  | No other activity. Only backfilling and levelling at MH5-1
Tue (18/04) | 18 Apr 2023 | Zone 1 Loyang Rise |  | No activity
Tue (18/04) | 18 Apr 2023 | Zone 1 PMH1 |  | Preparing for plate load test. PLT has been arranged for this afternoon
Tue (18/04) | 18 Apr 2023 | PRD3 |  | DE143 working at centre median
Tue (18/04) | 18 Apr 2023 | Zone 2 ABH31 |  | Trial trench started
Tue (18/04) | 18 Apr 2023 | North ramp PMH5 |  | Removing steel plates
Tue (18/04) | 18 Apr 2023 | PMH4 |  | First stage wall formwork dismantling. Pipe laying ongoing, 6m. Plan for casting today
Tue (18/04) | 18 Apr 2023 | PMH8 |  | Today plan for PLT
Tue (18/04) | 18 Apr 2023 | Exit 3 |  | Hardcore delivery for machinery access
Tue (18/04) | 18 Apr 2023 | Zone 2 |  | No noise panel installation, this team go to Lincstech today
Tue (18/04) | 18 Apr 2023 | Zone 2 along LVC after LP177 |  | NB footing formwork closing. 2+1 here
Tue (18/04) | 18 Apr 2023 | PMH8 |  | Plate load test started
Tue (18/04) | 18 Apr 2023 | PMH3 |  | Soldier pile installation started
Tue (18/04) | 18 Apr 2023 | ABH45 |  | Depth at 37.7m. Pending termination depth confirmation
Tue (18/04) | 18 Apr 2023 | Exit 1 |  | Continue excavation
Tue (18/04) | 18 Apr 2023 | DW047 |  | 1st bite cleaning temporarily stopped at ~27.5m due to mud hose choked with lss. finding out choke point ongoing
Tue (18/04) | 18 Apr 2023 | Zoneb2 near PD office |  | Bollard removal from previous bus stop
Tue (18/04) | 18 Apr 2023 | BH 26 |  | Drilling depth now at 50m
Tue (18/04) | 18 Apr 2023 | ABh25 |  | Terminated at 56.44m
Tue (18/04) | 18 Apr 2023 | Zone 2 |  | TT for sewer 5-1 backfilling works
Tue (18/04) | 18 Apr 2023 | Zone 1 | PMH-1 | Plate load test in progress
Tue (18/04) | 18 Apr 2023 | Zone 3 |  | WG mobilising their materials at trial hole location. To start tmr
Tue (18/04) | 18 Apr 2023 | DW047 |  | 2nd bite cleaning in progress
Tue (18/04) | 18 Apr 2023 | DW04 permeability test |  | Preparing to start 4th test. 3/5nos completed
Tue (18/04) | 18 Apr 2023 | PMH12/USD |  | Compaction in progress
Tue (18/04) | 18 Apr 2023 | Zone 2 NB footing |  | Formwork closing in progress, 9m done
Tue (18/04) | 18 Apr 2023 | LP183 |  | Base lean con for NB footing
Tue (18/04) | 18 Apr 2023 | PMH3 |  | Soldier pile works stopped
Tue (18/04) | 18 Apr 2023 | Zone 2 NB |  | Unloading materials. Today HBJB until 10pm here
Tue (18/04) | 18 Apr 2023 | ULT5 |  | Rectification ongoing. Lean concrete at bund wall
Tue (18/04) | 18 Apr 2023 | JTC area MH6-1 |  | Trial hole for pipe jacking location
Tue (18/04) | 18 Apr 2023 | Dw47 |  | Mud hose repaired. Now preparing to do cleaning
Wed (19/04) | 19 Apr 2023 | Zone 1 |  | Lane closure by WG and TMA provided. DE143 working at blk 275
Wed (19/04) | 19 Apr 2023 | Zone 1 PMH1 |  | WG preparation works. Today plan excavation & shoring works
Wed (19/04) | 19 Apr 2023 | PRD3 |  | DE143 working at centre median
Wed (19/04) | 19 Apr 2023 | North ramp PMH8 location |  | Retaining wall base slab rebar works in progress
Wed (19/04) | 19 Apr 2023 | DW47 |  | 1A & 1B rebar cages lowered
Wed (19/04) | 19 Apr 2023 | PMH12 |  | PLT ongoimg
Wed (19/04) | 19 Apr 2023 | Zone 2 noise barrier footing |  | Formwork closing & platform erection. Tmr plan for casting, 18m
Wed (19/04) | 19 Apr 2023 | MH6-1 |  | Excavation for metal caisson installation
Wed (19/04) | 19 Apr 2023 | Zone 2 Hi-Tech LP199 |  | Trial trench completed. Found SPTel, starhub, HT
Wed (19/04) | 19 Apr 2023 | PMH8 |  | RW base slab rebar works ongoing
Wed (19/04) | 19 Apr 2023 | PMH4 |  | 2nd stage wall rebar and formwork
Wed (19/04) | 19 Apr 2023 | MH 6-1 |  | 1st layer metal caisson installed. Perimeter lean con in progress
Wed (19/04) | 19 Apr 2023 | ULT 5 |  | Boring depth at 32m now
Wed (19/04) | 19 Apr 2023 | DW47 |  | Casting now at 51m3
Wed (19/04) | 19 Apr 2023 | ULT 5 |  | Boring stop for the day. 33m. Est 2.6m to toe level
Wed (19/04) | 19 Apr 2023 | DW047 |  | 12th truck casting ongoing
Wed (19/04) | 19 Apr 2023 | MH6-1 |  | TT completed. Excavator mobilized for sewer shaft. Steel caisson will be delivered today
Wed (19/04) | 19 Apr 2023 | Zone 1 Loyang Ave LP198 |  | Lane closure done, TMA provided
Wed (19/04) | 19 Apr 2023 | 2nd team at LA Traffic Island |  | Commence excavation work
Wed (19/04) | 19 Apr 2023 | PM12/USD |  | Final level reached and NDT done yesterday
Thu (20/04) | 20 Apr 2023 | ULT 6 |  | Preparation for Jack installation
Thu (20/04) | 20 Apr 2023 | PMH8 |  | RW base slab rebar works in progress
Thu (20/04) | 20 Apr 2023 | Zone 1 PMH-01 |  | Preparation works only, no lane closure due to the 1070 PUB inspection ahead
Thu (20/04) | 20 Apr 2023 | PMH4 |  | Platform erection ongoing
Thu (20/04) | 20 Apr 2023 | PMH3 |  | Pre-drilling started. First 3m in progress
Thu (20/04) | 20 Apr 2023 | Zone 3 towards CV |  | TT for possible corridor or 22KV pipe laying
Thu (20/04) | 20 Apr 2023 | Zone 3 Lincstech area |  | B&T soil trimming and excavation works. Total 5 pax
Thu (20/04) | 20 Apr 2023 | Zone 2 noise barrier footing |  | Today to cast 18m. Already inspected earlier this morning
Thu (20/04) | 20 Apr 2023 | ULT4 |  | Hi-Tech trial trench for feasible location
Thu (20/04) | 20 Apr 2023 | DW04 |  | Permeability test completed. Rig is shifted to zone 3
Thu (20/04) | 20 Apr 2023 | PMH12 |  | Preparation for hardcore laying. Today plan for lean concrete
Thu (20/04) | 20 Apr 2023 | Exit 2 |  | Area preparation for DW46 working platform
Thu (20/04) | 20 Apr 2023 | Zone 2 |  | Noise Barrier roofing panels installation ongoing
Thu (20/04) | 20 Apr 2023 | Zone 2 noise barrier footing |  | Casting works ongoing (18m)
Thu (20/04) | 20 Apr 2023 | Zone 3 |  | ABH 58 hand augering balance 200mm
Thu (20/04) | 20 Apr 2023 | ABH59 |  | Drilling and SPT just started. 4m depth
Thu (20/04) | 20 Apr 2023 | Zone 2 ABH29 |  | Continue TT. Depth at abt 1.5m
Thu (20/04) | 20 Apr 2023 | Zone 2 |  | ABH31-2 hand augering ongoing
Thu (20/04) | 20 Apr 2023 | PMH8 |  | RW base slab rebar and formworks closing ongoing. Target to cast today
Thu (20/04) | 20 Apr 2023 | Zone 2 | ABH-27 | Preparation to start SI work
Thu (20/04) | 20 Apr 2023 | PMH4 |  | Continue 2nd stage wall rebar works installation
Thu (20/04) | 20 Apr 2023 | PMH3 |  | Soldier pile installation works. 1 no. installed
Thu (20/04) | 20 Apr 2023 | Zone 1 | PMH1 - WG | Shoring works ongoing
Thu (20/04) | 20 Apr 2023 | Zone 3 VS area |  | Movable hoarding dismantling
Thu (20/04) | 20 Apr 2023 | Zone 2 |  | Rebar unloading for caisson works
Thu (20/04) | 20 Apr 2023 | Zone 2 |  | Rest area construction ongoing
Thu (20/04) | 20 Apr 2023 | Zone 2 | ABH-27 | Drilling works in progress. Current depth 6m
Thu (20/04) | 20 Apr 2023 | PMH3 |  | Drilling for S03 in progress. 1/9 soldier pile so far completed
Thu (20/04) | 20 Apr 2023 | 1. Toolbox meeting to change to 7 |  | 50am instead coming Mon onwards, 2. Lifting work to follow standard lifting plan / SUP
Thu (20/04) | 20 Apr 2023 | ULT5 |  | Lowering of rebar cage started, total 4 cages (3 lapping)
Thu (20/04) | 20 Apr 2023 | Noise barrier panel installation work until 9 |  | 30PM
Thu (20/04) | 20 Apr 2023 | Power duct joint to PMH4 |  | Casting done
Thu (20/04) | 20 Apr 2023 | PD3 road crossing |  | 15m duct laid and cast previously. 8m length excavation done. Tonight to continue with the next 8m length excavation
Thu (20/04) | 20 Apr 2023 | Zone 2 noise barrier |  | Panel installation no activity at the moment. Yesterday installed 22nos columns
Thu (20/04) | 20 Apr 2023 | Zone 3 |  | MH6-1 hard barricade installation at the opening
Thu (20/04) | 20 Apr 2023 | Zone 2 ABH27 |  | TT completed. Now preparing for hand auger
Thu (20/04) | 20 Apr 2023 | Zone 2 NLL |  | No activity by other contractor
Thu (20/04) | 20 Apr 2023 | ULT5 |  | Boring depth now at 34m
Thu (20/04) | 20 Apr 2023 | ABH27 |  | Hand auger started
Thu (20/04) | 20 Apr 2023 | Zone 2 ABH31 |  | Continue TT. Depth at abt 1.2m now
Thu (20/04) | 20 Apr 2023 | Zone 1 |  | No activity
Fri (21/04) | 21 Apr 2023 | Zone 2 noise barrier |  | Continue horizontal pipes installation
Fri (21/04) | 21 Apr 2023 | Zone 2 noise barrier footing |  | Continue rebar works. Yesterday cast 18m
Fri (21/04) | 21 Apr 2023 | Zone 2 ABH27 |  | Drilling in progress, current depth at 18m
Fri (21/04) | 21 Apr 2023 | MH5-1 location |  | Soil levelling works ongoing
Fri (21/04) | 21 Apr 2023 | Zone 2 | near Shell station | Tree felling in progress. Balance 2 nos to fell here
Fri (21/04) | 21 Apr 2023 | Zone 1 PMH-01 |  | No activity
Fri (21/04) | 21 Apr 2023 | PRD3 |  | EL working here
Fri (21/04) | 21 Apr 2023 | Exit 2 |  | ATT Z3 -31: preparation for Trial trench work to find HV Cable alignment
Fri (21/04) | 21 Apr 2023 | ABH 59 |  | Depth 17m
Fri (21/04) | 21 Apr 2023 | ABH 58 |  | Depth at 6m
Fri (21/04) | 21 Apr 2023 | ABH 60 |  | Depth at 34.6m
Fri (21/04) | 21 Apr 2023 | PMH3 |  | Preboring for next soldier pile installation
Fri (21/04) | 21 Apr 2023 | Zone 1 |  | No activity
Fri (21/04) | 21 Apr 2023 | PMH4 |  | 2nd stage wall rebar inspected. Preparing for formwork closing
Fri (21/04) | 21 Apr 2023 | MH2-4 |  | Trial trench ongoing
Fri (21/04) | 21 Apr 2023 | Exit 2 |  | Housekeeping and i beam removal
Fri (21/04) | 21 Apr 2023 | PMH12 |  | Preparation for lean concrete
Fri (21/04) | 21 Apr 2023 | ULT5 |  | Casting in progress. 15/30m3
Fri (21/04) | 21 Apr 2023 | PMH3 |  | Pre boring for soldier pile installation 3/9 completed, 5th SP boring in progress and going to complete. After this they will bore location for inclinometer and install. Tomorrow will do grouting
Fri (21/04) | 21 Apr 2023 | MH2-4 |  | Found cut and abandoned cables of lamppost . Lamppost removal done Previously by SK contractors
Fri (21/04) | 21 Apr 2023 | Zone 2 center median between |  | 15 nos tree feeling here
Fri (21/04) | 21 Apr 2023 | ULT5 |  | LSS backfilling from COL to ground level. Total volume 35m3
Fri (21/04) | 21 Apr 2023 | DW033 |  | Further trial trench carried out. Unknown cable is LV as per Selvam
Fri (21/04) | 21 Apr 2023 | ABH59 |  | Depth at 24m now
Fri (21/04) | 21 Apr 2023 | Zone 3 |  | Crawler crane assembly completed
Fri (21/04) | 21 Apr 2023 | Exit 2 |  | Dongah housekeeping and adjusting of steel plates
Fri (21/04) | 21 Apr 2023 | PMH12 and USD area |  | Backfilling extension for PMH12 working platform
Sat (22/04) | 22 Apr 2023 | Zone 3 |  | JTC/outside Lincstech hoarding works ongoing
Sat (22/04) | 22 Apr 2023 | Exit 1 |  | Survey taking of drain ongoing
Sat (22/04) | 22 Apr 2023 | Zone 2 |  | ECM pond barricade in progress
Sat (22/04) | 22 Apr 2023 | Exit 3 |  | Vector control oiling done. No activity
Sat (22/04) | 22 Apr 2023 | Zone 2 Noise barrier |  | No activity
Sat (22/04) | 22 Apr 2023 | Zone 2 |  | PMH08 wall rebar works still in progress
Sat (22/04) | 22 Apr 2023 | Zone 2 |  | No activity for rest of PMHs
Sat (22/04) | 22 Apr 2023 | Zone 1 |  | No activity
Sat (22/04) | 22 Apr 2023 | Zone 1 |  | DE143 working at Pasir Ris Dr 3 Centre median
Sat (22/04) | 22 Apr 2023 | Exit 2 |  | No activity
Sat (22/04) | 22 Apr 2023 | Zone 3 |  | No activity
Sat (22/04) | 22 Apr 2023 | Zone 3 |  | Half of the hoarding completed. Tmr to continue the rest
Sat (22/04) | 22 Apr 2023 | Exit 1 |  | No activity
Sat (22/04) | 22 Apr 2023 | Zone 2 |  | PMH08 Wall rebar works ongoing
Sat (22/04) | 22 Apr 2023 | Zone 2 |  | Starhub just arrived onsite near LP 175 manhole for cable diversion
Sun (23/04) | 23 Apr 2023 | Zone 3 |  | HSL no activity
Sun (23/04) | 23 Apr 2023 | Exit 2 | DW-46 | Preparation works ongoing for shifting of BC cutter
Sun (23/04) | 23 Apr 2023 | Exit 2 |  | Pre-excavation works completed for DW-46
Sun (23/04) | 23 Apr 2023 | DW46 |  | 1st bite excavation depth now at 23m
Sun (23/04) | 23 Apr 2023 | Zone 3 |  | Trial trench works by Wee Guan. In progress
Sun (23/04) | 23 Apr 2023 | Exit 1 |  | No activity
Sun (23/04) | 23 Apr 2023 | Zone 3 Slurry Wall area |  | No activity
Sun (23/04) | 23 Apr 2023 | Zone 4 |  | No activity. DE143 working in their hoarded area
Sun (23/04) | 23 Apr 2023 | Zone 3 | Lincstech | No activity
Sun (23/04) | 23 Apr 2023 | Exit 2 |  | BC cutter parked at DW46 location. Hose connection to BC cutter ongoing
Sun (23/04) | 23 Apr 2023 | Exit 3 |  | No activity
Sun (23/04) | 23 Apr 2023 | Zone 2 |  | Noise barrier No activity
Sun (23/04) | 23 Apr 2023 | Zone 1 | PMH-1 | Material shifting works
Sun (23/04) | 23 Apr 2023 | Zone 1 |  | DE143 working at Pasir Ris Dr 3 Centre median & Loyang Ave (behind pmh-1)
Sun (23/04) | 23 Apr 2023 | Zone 3 |  | 1 no. of Trial trench completed. Shifting of excavator & materials to infront of JTC Blk 4 and housekeeping in progress. For tmr trial trenches works
Sun (23/04) | 23 Apr 2023 | Zone 1 | PMH-01 | Preparation for shoring and housekeeping done. WG dayshift work stopped for the day
Sun (23/04) | 23 Apr 2023 | Zone 1 |  | Excavation work for SPPG pipe laying
Mon (24/04) | 24 Apr 2023 | Zone 3 |  | Slope casting at slurry wall area. Levelling in progress
Mon (24/04) | 24 Apr 2023 | Blk 2 behind |  | B&T internal mandrel in progress
Mon (24/04) | 24 Apr 2023 | ULT6 |  | Instrument installation on rebar cage
Mon (24/04) | 24 Apr 2023 | DW046 |  | Locking plate installation for trimming
Mon (24/04) | 24 Apr 2023 | ULT5 |  | Ramp and steel plate removal
Mon (24/04) | 24 Apr 2023 | Zone 3 |  | TT done by Wee Guan. Servinces found are LV, 66KV & starhub
Mon (24/04) | 24 Apr 2023 | Exit 1 |  | Steel plate laying for acces in progress
Mon (24/04) | 24 Apr 2023 | Zone 1 |  | Steel deck reinstated and lane opened
Mon (24/04) | 24 Apr 2023 | MH2-4 | Dia 4.5m | TT was done. Highlighted in green is Starhub alignment. Highlighted in red (Singtel) alignment
Mon (24/04) | 24 Apr 2023 | MH1-1 |  | TT in progress. LV cable found as of now
Mon (24/04) | 24 Apr 2023 | Exit 3 |  | Steel plates laying & arranging ongoing
Mon (24/04) | 24 Apr 2023 | PMH-12 |  | Base slab rebar & Formwork works ongoing. Target to cast today
Mon (24/04) | 24 Apr 2023 | PMH-11 to PMH-12 |  | Hardcores laying in progress. Target to lean concrete today
Mon (24/04) | 24 Apr 2023 | Zone 2 |  | Noise barrier panels installation ongoing
Mon (24/04) | 24 Apr 2023 | PMH-8 |  | Formwork closing ongoing for 1st stage wall. Target to cast today
Mon (24/04) | 24 Apr 2023 | PMH3 |  | Pre boring for soldier pile installation ongoing
Mon (24/04) | 24 Apr 2023 | PMH-4 |  | Formwork dismantling
Mon (24/04) | 24 Apr 2023 | PMH12 |  | Wall rebar installation in progress
Mon (24/04) | 24 Apr 2023 | MH1-1 | 4.5m dia | TT in progress. Red (LV). Yellow ( Singtel). Pink ( Starhub)
Mon (24/04) | 24 Apr 2023 | Continue noise barrier panel installation until 9 |  | 30PM
Mon (24/04) | 24 Apr 2023 | DW46 |  | 2nd bite Trenching continue at 9m from GWTL
Mon (24/04) | 24 Apr 2023 | DW46 |  | Continue trimming, 20m as of now
Mon (24/04) | 24 Apr 2023 | DW46 |  | 2nd bite trimming continues
Mon (24/04) | 24 Apr 2023 | Zone 1 slow lane Loyang avenue to PDR3 |  | Excavation continue for 4m tonight
Mon (24/04) | 24 Apr 2023 | 1st team |  | Excavation and soil disposal
Mon (24/04) | 24 Apr 2023 | 2nd team |  | Excavation and premix/soil disposal
Tue (25/04) | 25 Apr 2023 | ULT6 |  | Installation of instrument on rebar cage
Tue (25/04) | 25 Apr 2023 | DW46 |  | First cage lowered down. Preparing to lap 2nd cage
Tue (25/04) | 25 Apr 2023 | Mapletree | behind blk 2 | WH adjusting of hoarding panels
Tue (25/04) | 25 Apr 2023 | Zone 1 PMH1 |  | WG team 1 to continue excavation and shoring works
Tue (25/04) | 25 Apr 2023 | Zone 1 USD |  | WG team 2 day shift to start hacking works to facilitate the steel decking installation & pipe laying (36-way) continuation (night shift)
Tue (25/04) | 25 Apr 2023 | PRD3 centre median |  | DE143 works
Tue (25/04) | 25 Apr 2023 | Zone 1 Loyang Rise |  | WG team 3 trial trench in progress for Singtel works
Tue (25/04) | 25 Apr 2023 | Zone 1 Loyang Rise |  | Continue formwork installation & rebar works for NB footing. Plan for casting tmr, 24m
Tue (25/04) | 25 Apr 2023 | Zone 1 traffic island |  | PUB contractor doing maintenance
Tue (25/04) | 25 Apr 2023 | PMH3 |  | Pre-boring in progress, 6/10nos completed
Tue (25/04) | 25 Apr 2023 | PMH12 |  | Base slab cast
Tue (25/04) | 25 Apr 2023 | Zone 2 NB footing |  | 3nos (9m) formwork installed & inspected. Pending to cast
Tue (25/04) | 25 Apr 2023 | Zone 1 USD |  | Kerb hacked earlier today. Now continue to cut part of the PCN to facilitate the works
Tue (25/04) | 25 Apr 2023 | ULT6 |  | Preparing to start boring
Tue (25/04) | 25 Apr 2023 | PMH3 |  | Pre-boring in progress
Tue (25/04) | 25 Apr 2023 | DW46 |  | Confirming toe level using sound tape
Tue (25/04) | 25 Apr 2023 | Exit 3 |  | Noise barriers installation for BG25 ongoing
Tue (25/04) | 25 Apr 2023 | Exit 3 |  | 2 nos of pre-coring locations marked on site
Tue (25/04) | 25 Apr 2023 | Exit 3 |  | VM-1 & VM-2 sensors installation for pre-coring in progress
Tue (25/04) | 25 Apr 2023 | PMH11 to PMH-12 |  | Lean concrete ongoing for duct construction
Tue (25/04) | 25 Apr 2023 | Zone 3 |  | Excavation for ECM pond
Tue (25/04) | 25 Apr 2023 | PMH8 |  | First stage wall dismantling
Tue (25/04) | 25 Apr 2023 | PMH3 |  | Pre-boring ongoing till 8pm. 8/10nos completed
Tue (25/04) | 25 Apr 2023 | DW46 |  | End plate + water stop installation at DW45 side
Tue (25/04) | 25 Apr 2023 | JTC area blk 2 |  | Mandrel test and backfilling done. Now B&T housekeeping
Tue (25/04) | 25 Apr 2023 | Zone 3 |  | SW guidewall rebar works to continue until 10pm. Workers on dinner break
Tue (25/04) | 25 Apr 2023 | PMH3 ERSS |  | 9/10 pre-boring done for soldier pile installation. Balance 1 no to complete tomorrow
Tue (25/04) | 25 Apr 2023 | Zone 1 |  | Delivery of pvc pipe for laying tonight
Tue (25/04) | 25 Apr 2023 | PMH12 |  | Base slab & wall rebar works. Target to cast base slab today
Tue (25/04) | 25 Apr 2023 | Zone 2 noise barrier panels |  | Continue installation
Tue (25/04) | 25 Apr 2023 | Zone 2 noise barrier footing |  | Continue formwork installation for next section
Wed (26/04) | 26 Apr 2023 | Zone 1 NB |  | Housekeeping & preparing for casting
Wed (26/04) | 26 Apr 2023 | ULT6 |  | Instrument installed on rebar cage. Plan for inspection afternoon
Wed (26/04) | 26 Apr 2023 | ULT6 |  | Boring in progress, 10/32.2m boring done
Wed (26/04) | 26 Apr 2023 | Exit 2 |  | BC cutter teeth replacement and changing flange for 1000mm size D wall
Wed (26/04) | 26 Apr 2023 | Exit 2 |  | Dismantling of container and shift out materials to exit 1
Wed (26/04) | 26 Apr 2023 | MH6-1 |  | TT on going by Ryobi G
Wed (26/04) | 26 Apr 2023 | PMH-12 |  | 1st stage wall - rebar installation ongoing
Wed (26/04) | 26 Apr 2023 | PMH-11 to PMH-12 |  | Barricades installation works
Wed (26/04) | 26 Apr 2023 | Near PMH8 |  | Soldier pile installation in progress
Wed (26/04) | 26 Apr 2023 | PMH3 |  | Last pre-boring point in progress. As of yesterday, 9/10nos
Wed (26/04) | 26 Apr 2023 | Zone 2 | ABH31-2 | Drilling works, current depth 16m
Wed (26/04) | 26 Apr 2023 | PMH-01 |  | Current status of erss
Wed (26/04) | 26 Apr 2023 | Exit 3 |  | Bentonite pipes laying for pre-coring works
Wed (26/04) | 26 Apr 2023 | Exit 2 |  | Clearing materials for trial trenches for 6nos of D wall panels
Wed (26/04) | 26 Apr 2023 | Zone 3 |  | Excavation for ECM pond
Wed (26/04) | 26 Apr 2023 | Exit 2 |  | Mud hose dismantling. Today to shift and set up at exit 3
Wed (26/04) | 26 Apr 2023 | DW-035-1 |  | Preboring started at 4.20pm, current 4m depth. Target to install 8m casing today. Works until 7pm only
Wed (26/04) | 26 Apr 2023 | PMH-12 |  | Current status
Wed (26/04) | 26 Apr 2023 | PMH-03 |  | Pre-boring completed, rig demob
Wed (26/04) | 26 Apr 2023 | PMH-08 |  | Levelling & compaction work ongoing
Wed (26/04) | 26 Apr 2023 | Zone 3 |  | SW guidewall formwork closing. Tomorrow to cast
Wed (26/04) | 26 Apr 2023 | Zone 2 NB panels |  | Continue horizontal GI pipes installation
Wed (26/04) | 26 Apr 2023 | Zone 2 NB footing |  | Continue rebar works
Thu (27/04) | 27 Apr 2023 | Zone 2 NB |  | Formwork dismantling
Thu (27/04) | 27 Apr 2023 | ABH 29 |  | Drilling and SPT started. 4m
Thu (27/04) | 27 Apr 2023 | ABH31-2 |  | Drilling at 32m
Thu (27/04) | 27 Apr 2023 | Zone 1 NB |  | Preparation to commence work, HBJB just arrived
Thu (27/04) | 27 Apr 2023 | PRD3 |  | EL removing centre median
Thu (27/04) | 27 Apr 2023 | PMH-8 to PMH-7 |  | Solider pile & steel plates installation
Thu (27/04) | 27 Apr 2023 | Zone 2 |  | Singtel TT along loyang avenue
Thu (27/04) | 27 Apr 2023 | Zone 2 |  | Rebar cutting for caison rebars
Thu (27/04) | 27 Apr 2023 | Zone 1 | towards PMH-01 | WG preparing to remove kerb & DIC for the continuation of 36-way pipe laying. Material shifting ongoing
Thu (27/04) | 27 Apr 2023 | Exit 1 |  | 10/12 silo installed. Balance two number to complete by today too
Thu (27/04) | 27 Apr 2023 | PMH-12 |  | 1st stage wall Formwork closing. Today will cast
Thu (27/04) | 27 Apr 2023 | PMH-11 to PMH-12 |  | Formwork closing. Today will cast 12m duct
Thu (27/04) | 27 Apr 2023 | ABH31-2 |  | Drilling at 36m
Thu (27/04) | 27 Apr 2023 | ABH 29 |  | Drilling ongoing, current depth 11m
Thu (27/04) | 27 Apr 2023 | Zone 2 | Noise barrier footing | Formwork closing for next section of noise barrier footing
Thu (27/04) | 27 Apr 2023 | 01 |  | 55hrs, Dongah SI team conducted trial trench to identify services for ABH54 boring work. Excavator was used due to existing rigid concrete with debris was encountered. Rigid concrete and debris was found until 1.3m. During removal of concrete and debris at 1.3m depth excavator bucket accidentally damaged the cable protection conduit including the cable inside the protection pipe. After investigation of manhole at surrounding area and the cable, suspect the cable probably under Singtel. Detail investigation is still on going by WH Dongah JV, Location : Zone 3 (Near Bus Stop of Blk 2 toward Changi bound), Contractor involved : Dongah SI team, Purpose of activity: Trial trench for ABH54, Operator : Jabed, Banksman : Soliman, RES : Rashel
Thu (27/04) | 27 Apr 2023 | ULT6 |  | Continue boring until toe level in progress
Thu (27/04) | 27 Apr 2023 | Exit 1 |  | Continue clearing materials and tidy up the storage area
Thu (27/04) | 27 Apr 2023 | Zone 1 |  | Noise barrier footing rebar and Formwork installation. Next section will cast 24m
Thu (27/04) | 27 Apr 2023 | MH1-1 |  | TT done. Found 300mm dia water pipe at 1m depth. Running along road kerb
Thu (27/04) | 27 Apr 2023 | MH08 |  | Wall fromwork closing in progress
Thu (27/04) | 27 Apr 2023 | PMH8 |  | 2nd stage wall formwork installation & access erection ongoing
Thu (27/04) | 27 Apr 2023 | PMH12 |  | 1st stage wall cast
Thu (27/04) | 27 Apr 2023 | Exit 2 |  | No activity
Thu (27/04) | 27 Apr 2023 | DW35 |  | 1/1 pre-coring works in progress. Current depth 7m from top of casing
Thu (27/04) | 27 Apr 2023 | ULT6 |  | Boring reached 30.5m
Thu (27/04) | 27 Apr 2023 | Zone 1 |  | WG backfilling works ongoing
Fri (28/04) | 28 Apr 2023 | Zone 1 |  | Final layer backfilling & levelling
Fri (28/04) | 28 Apr 2023 | PMH12 |  | Scaffold erection for 2nd stage wall and top slab works
Fri (28/04) | 28 Apr 2023 | Zone 1 NB |  | 24m formwork done. Installation or railings in progress. To cast tomorrow
Fri (28/04) | 28 Apr 2023 | PMH3 |  | Soldier pile installation in progress. 3/10
Fri (28/04) | 28 Apr 2023 | Exit 1 |  | Pipes connection ongoing for silo
Fri (28/04) | 28 Apr 2023 | ULT6 |  | Started lowering of rebar cage
Fri (28/04) | 28 Apr 2023 | Exit 3 |  | Preparing for BC cutter teeth welding works
Fri (28/04) | 28 Apr 2023 | Zone 1 Wee Guan |  | Shifting of materials. Tonight plan for excavation for steel deck installation
Sat (29/04) | 29 Apr 2023 | Exit 1 |  | Pipe connection for new silos in progress
Sat (29/04) | 29 Apr 2023 | Zone 4 |  | DE143 working within their hoarding
Sat (29/04) | 29 Apr 2023 | Zone 1 Wee Guan |  | Tonight continue excavation & shoring installation. Excavation about 1.5m depth, 4.5m length
Sat (29/04) | 29 Apr 2023 | Zone 3 near Selarang Camp |  | HT cables (green) and unknown cables (red) found. Selvam will come down to check
Sat (29/04) | 29 Apr 2023 | Zone 2 LVC |  | Concrete casting for 6 nos of NB footing ongoing
Sat (29/04) | 29 Apr 2023 | Zone 2 |  | ABH31-2 at 38m depth
Sat (29/04) | 29 Apr 2023 | Zone 2 |  | ABH29 at 22m depth
Sat (29/04) | 29 Apr 2023 | PMH08 area |  | Lean concreting of slope ongoing
Sat (29/04) | 29 Apr 2023 | Zone 1 |  | Casting of 8 nos. Of NB footing ongoing
Sat (29/04) | 29 Apr 2023 | PMH03 |  | Soldier pile installation in progress
Sat (29/04) | 29 Apr 2023 | ULT6 |  | Preparing for casting
Sat (29/04) | 29 Apr 2023 | Zone 2 |  | Trial trench at Loyang ave sidetable for abandoned 66kV ongoing
Sat (29/04) | 29 Apr 2023 | Zone 2 |  | Weng guan mobilized excavator in. Weng Guan is planning to do trial trench on the road
Sat (29/04) | 29 Apr 2023 | Exit 3 |  | Pipe laying from PMH11 to PMH12 ongoing. Scaffold installation at PMH12 also in progress
Sat (29/04) | 29 Apr 2023 | Exit 3 |  | DW035 precoring internal koden test ongoing
Sat (29/04) | 29 Apr 2023 | Zone 3 JTC |  | Footpath hacking still ongoing
Sat (29/04) | 29 Apr 2023 | Zone 3 near JTC |  | 2 nos. Trial trench ongoing by WG
Sat (29/04) | 29 Apr 2023 | Zone 3 Blk 2 Sidetable |  | Services found: 66KV, LV and SH found (0.9m depth)
Sat (29/04) | 29 Apr 2023 | Zone 3 Blk 4 sidetable |  | Services found: LV and SH
Sat (29/04) | 29 Apr 2023 | Exit 3 |  | DW35 preparing for excavation
Sat (29/04) | 29 Apr 2023 | PMH8 to PMH7 area |  | Lean concrete casting ongoing
Sat (29/04) | 29 Apr 2023 | PMH8 |  | Continue top slab works & 2nd stage wall formwork installation. Plan for casting tmr
Sat (29/04) | 29 Apr 2023 | Near Exit 1 |  | Container roofing works ongoing
Sat (29/04) | 29 Apr 2023 | Zone 3 |  | Barricade installation ongoing
Sat (29/04) | 29 Apr 2023 | Zone 3 Slurry wall |  | Soil disposal ongoing
Sun (30/04) | 30 Apr 2023 | Zone 2&1 NBs |  | No activity
Sun (30/04) | 30 Apr 2023 | PMH-01 |  | No activity
Sun (30/04) | 30 Apr 2023 | PMH-08 |  | Casting started
Sun (30/04) | 30 Apr 2023 | Zone 1 |  | No wee guan works tonight for 22KV pipe laying
Sun (30/04) | 30 Apr 2023 | Near to PMH-12 |  | Power duct casting ongoing
Sun (30/04) | 30 Apr 2023 | Near to PMH-11 |  | Power duct fwk done, hardcore backfill & compaction done for telco duct
Sun (30/04) | 30 Apr 2023 | Near to PMH-11 |  | Pipe laying for power duct ongoing
Sun (30/04) | 30 Apr 2023 | PMH-12 |  | Current status
Mon (01/05) | 01 May 2023 | PMH3 |  | 8/10nos soldier piles installed. Abt 800-900mm excavated. Now preparing for waler bracket installation
Mon (01/05) | 01 May 2023 | Zone 1 Loyang Rise |  | No activity
Mon (01/05) | 01 May 2023 | Zone 1 LA |  | No other activity
Mon (01/05) | 01 May 2023 | Exit 2 |  | No activity
Mon (01/05) | 01 May 2023 | Exit 1 |  | No activity
Mon (01/05) | 01 May 2023 | DW35 |  | Depth now at 5.6m from TGWL
Mon (01/05) | 01 May 2023 | PMH3 |  | Waler bracket installation ongoing
Mon (01/05) | 01 May 2023 | DW35 |  | 2nd bite trenching continue. Current depth 23.9m from GWTL
Mon (01/05) | 01 May 2023 | Zone 2 noise barrier |  | No activity
Mon (01/05) | 01 May 2023 | PMH8 |  | No activity. 2nd stage wall & top slab cast yesterday
Tue (02/05) | 02 May 2023 | Exit 1 |  | Center median casting
Tue (02/05) | 02 May 2023 | ULT6 |  | Removal of bund wall and housekeeping
Tue (02/05) | 02 May 2023 | Exit 2 |  | Briefing before start TT to check on existing services
Tue (02/05) | 02 May 2023 | Zone 3 |  | Wee Guan reinstate the area after trial trench. Today they plan for 2 numbers off TT
Tue (02/05) | 02 May 2023 | Zone 1 |  | DE143 working next to blk 275
Tue (02/05) | 02 May 2023 | Zone 1 Loyang Rise |  | No activity
Tue (02/05) | 02 May 2023 | PRD3 |  | No activity
Tue (02/05) | 02 May 2023 | Zone 1 Wee Guan |  | PMH1 - Today plan to continue excavation. Current excavation depth ard 1.5m
Tue (02/05) | 02 May 2023 | Zone 1 Wee Guan |  | Team 2 to continue premix removal & excavation to facilitate the decking installation
Tue (02/05) | 02 May 2023 | PMH8 |  | Readjusting the barricade
Tue (02/05) | 02 May 2023 | Exit 1 |  | Hoses connection from silo to desander & filter press
Tue (02/05) | 02 May 2023 | PMH3 |  | Balance soldier pile installation (2nos)
Tue (02/05) | 02 May 2023 | Zone 2 |  | Trial trench works ongoing for MH2-5
Tue (02/05) | 02 May 2023 | Zone 2 | WG | Trial trenches ongoing near noise barriers
Tue (02/05) | 02 May 2023 | Zone 2 ABH29 |  | Current depth 52m. Pending termination depth confirmation
Tue (02/05) | 02 May 2023 | ABH31-2 |  | Driling works ongoing, Current depth 50m
Tue (02/05) | 02 May 2023 | Zone 2 NB footing |  | Rebar and Formwork installation
Tue (02/05) | 02 May 2023 | Zone 1 Wee Guan |  | PMH1 - housekeeping ongoing to open back the road
Tue (02/05) | 02 May 2023 | PMH-3 |  | 10nos. of soldier piles installation completed
Tue (02/05) | 02 May 2023 | Zone 2 |  | Lean concrete completed for telco duct
Tue (02/05) | 02 May 2023 | DW45 |  | Dongah doing TT to check on services
Tue (02/05) | 02 May 2023 | ZONE 3 ECM pond |  | Brick wall installation around ECM pond
Tue (02/05) | 02 May 2023 | MH2-5 |  | No services for current TT. Tomorrow to continue TT highlighted in blue
Tue (02/05) | 02 May 2023 | ULT4 |  | Shifting of noise barrier
Tue (02/05) | 02 May 2023 | Exit 1 |  | Hoses connection and power supply cable pulling
Tue (02/05) | 02 May 2023 | MH8 to 7 |  | Rebar work in progress
Tue (02/05) | 02 May 2023 | Zone 2 |  | USD power connecting to PMH12 pipe laying. 3m
Tue (02/05) | 02 May 2023 | Exit 3 |  | Dismantling of machine cutter body for the pulley repair works
Tue (02/05) | 02 May 2023 | PMH12-11 |  | Hardcore levelling ongoing
Tue (02/05) | 02 May 2023 | Zone 2 NB panels |  | Safety checks before start work
Tue (02/05) | 02 May 2023 | Zone 2 NB footing |  | Formwork dismantling
Tue (02/05) | 02 May 2023 | Zone 2 ABH29 |  | Current depth 42m
Tue (02/05) | 02 May 2023 | ABH31-2 |  | Current depth 42m
Wed (03/05) | 03 May 2023 | Zone 2 Power USD |  | Rebar installation for pipe connection at PMH12. Today plan for casting 3m
Wed (03/05) | 03 May 2023 | MH2-5 |  | Preparing to continue trial trench
Wed (03/05) | 03 May 2023 | Zone 2 Weng Guan |  | Trial trench, TT13 for Singtel in progress. Now clearing of premix debris
Wed (03/05) | 03 May 2023 | Zone 2 noise barrier |  | Continue panel installation. This team will move to Lincstech area in the afternoon
Wed (03/05) | 03 May 2023 | Zone 2 ABH33 |  | SI team is marking out the alignment & counter check with UE on the service prior to proceeding with the SI works
Wed (03/05) | 03 May 2023 | Zone 2 NB footing |  | Formwork installation in progress. Plan for casting today, 6nos
Wed (03/05) | 03 May 2023 | Zone 1 Loyang Rise |  | No activity
Wed (03/05) | 03 May 2023 | Zone 1 LA |  | DE143 working next to blk 275
Wed (03/05) | 03 May 2023 | Zone 1 USD |  | Today Wee Guan no lane closure. The team will continue excavation at PMH1
Wed (03/05) | 03 May 2023 | PMH1 |  | WG to continue excavation here
Wed (03/05) | 03 May 2023 | Zone 2 near Shell station |  | Weng Guan preparing for trial trench (TT14)
Wed (03/05) | 03 May 2023 | Retaining wall between PMH7-8 |  | Base slab rebar & formwork ongoing. Plan for casting today
Wed (03/05) | 03 May 2023 | Exit 3 |  | Repair works & crane checking ongoing
Wed (03/05) | 03 May 2023 | Zone 2 Wee Guan |  | Trial trench (ATT14) for Singtel completed. Found LP cable and water pipe
Wed (03/05) | 03 May 2023 | Zone 2 |  | Proposed MH (1) location marking for SingTel cables
Wed (03/05) | 03 May 2023 | Zone 1 | PMH-1 | Current status of PMH-1. Work stopped for the day. Housekeeping ongoing
Wed (03/05) | 03 May 2023 | PMH12 |  | 2nd stage formwork assembly
Wed (03/05) | 03 May 2023 | Zone 1 loyang avenue lane 1 |  | Excavation work for 22KV pipe laying
Wed (03/05) | 03 May 2023 | 2nd team TT |  | Premix cutting on going
Wed (03/05) | 03 May 2023 | Zone 3 Selarang camp side |  | Barricade installation ongoing
Thu (04/05) | 04 May 2023 | Zone 2 ABH32 |  | Hand auger in progress
Thu (04/05) | 04 May 2023 | ABH33 |  | Trial trench ongoing
Thu (04/05) | 04 May 2023 | ABH34 |  | Trial trench ongoing
Thu (04/05) | 04 May 2023 | ABH35 |  | Trial trench in progress
Thu (04/05) | 04 May 2023 | Zone 1 Loyang Rise |  | No activity
Thu (04/05) | 04 May 2023 | PRD3 |  | No activity
Thu (04/05) | 04 May 2023 | Zone 2 NB footing |  | Continue rebar works for next section
Thu (04/05) | 04 May 2023 | Exit 3 |  | Crane track rectification ongoing
Thu (04/05) | 04 May 2023 | Zone 3 |  | Floodlights installation (facing Lincstech) ongoing
Thu (04/05) | 04 May 2023 | Exit 1 |  | Muck pit wall formwork closing ongoing. Plan for casting today
Thu (04/05) | 04 May 2023 | Zone 3 ECM pond |  | Bund wall installation ongoing
Thu (04/05) | 04 May 2023 | PMH12 |  | 2nd stage wall formwork ongoing
Thu (04/05) | 04 May 2023 | ABH42 |  | Trial trench ongoing
Thu (04/05) | 04 May 2023 | ULT4 |  | Instrument installation ongoing
Thu (04/05) | 04 May 2023 | ABH33 |  | TT completed. No obstruction
Thu (04/05) | 04 May 2023 | ABH34 |  | TT ongoing
Thu (04/05) | 04 May 2023 | ABH35 |  | TT ongoing
Thu (04/05) | 04 May 2023 | PMH3 |  | 3nos struts already installed. Will continue welding works. Now workers on dinner break
Thu (04/05) | 04 May 2023 | Zone 3 near exit 2 |  | Trial trench by Wee Guan for the 22kv. Found starhub (green) & LV (black) at ard 800mm depth
Thu (04/05) | 04 May 2023 | PMH3 |  | Singtec continue waler installation and welding. Tonight they working until 10PM. 2 workers + 1 safety
Thu (04/05) | 04 May 2023 | PD3 |  | Lane closure for tonight work
Fri (05/05) | 05 May 2023 | ULT4 |  | Boring completed at 28.4m depth. To confirm toe level and proceed with desanding
Fri (05/05) | 05 May 2023 | Zone 3 Loyang Way |  | No activity
Fri (05/05) | 05 May 2023 | Zone 3 |  | PUB cctv installation ongoing
Fri (05/05) | 05 May 2023 | Zone 4 |  | No activity
Fri (05/05) | 05 May 2023 | Near exit 1 |  | Access steel plate laying ongoing
Fri (05/05) | 05 May 2023 | Exit 2 |  | Water breaking before 1st base grouting
Fri (05/05) | 05 May 2023 | ULT4 |  | Koden test preparation
Fri (05/05) | 05 May 2023 | Zone 2 LVC side |  | NB casting 9m until LP183
Fri (05/05) | 05 May 2023 | Zone 3 |  | TT for posible corridor of 22KV pipe laying. To date 16 TT completed
Fri (05/05) | 05 May 2023 | Exit 2 DW41 TT |  | 2/2 TT completed. 2nd TT location no utility found
Fri (05/05) | 05 May 2023 | Zone 3 ST32 |  | TT to find LV cable
Fri (05/05) | 05 May 2023 | PMH3 |  | Packing concrete casting. Tomorrow to start excavation
Fri (05/05) | 05 May 2023 | DW035 |  | Bentonite noses connection before resume excavation
Fri (05/05) | 05 May 2023 | ULT4 |  | Last cage of rebar cage already lowered down. Going to start instrument testing before continue with casting
Fri (05/05) | 05 May 2023 | PD3 |  | Lane closure done for tonight work
Fri (05/05) | 05 May 2023 | PHM3 |  | Singtec already end work and go back
Fri (05/05) | 05 May 2023 | PD3 |  | Noise curtin installation around work area. Tonight plan to lay 9m length of duct
Sat (06/05) | 06 May 2023 | DW35 |  | Internal Koden test ongoing
Sat (06/05) | 06 May 2023 | DW35 |  | Cutter teeth changing in progress
Sat (06/05) | 06 May 2023 | ABH-42 | SI | Manual trial trenching ongoing
Sat (06/05) | 06 May 2023 | Zone 2 | ABH-33 | Setting up SI rig ongoing
Sat (06/05) | 06 May 2023 | Zone 2 | ABH-32 | Driling ongoing. Current depth 6m
Sat (06/05) | 06 May 2023 | Zone 2 | Bet LP199/1 to LP199 | SingTel pipe laying works. Hacking of premix ongoing. 6x3 (18way)
Sat (06/05) | 06 May 2023 | Zone 1 | Bet LP200 | SingTel pipe laying works. Today target to lay another 12m, yesterday laid 6m. (6 by 3, 18way)
Sat (06/05) | 06 May 2023 | Zone 1 |  | Shoring works ongoing for tonight pipe laying towards PMH-1
Sat (06/05) | 06 May 2023 | Zone 1 | PMH-1 | Continue excavation & shoring works installation for PMH-1
Sat (06/05) | 06 May 2023 | Zone 1 |  | DE143 & DE160 works near Blk 275
Sat (06/05) | 06 May 2023 | Zone 2 | North ramp | Pipe laying works ongoing from PMH-7 to 8. Target to cast 18m today
Sat (06/05) | 06 May 2023 | Zone 2 | North ramp | Current status for PMH-3. Target to start excavation in the afternoon
Sat (06/05) | 06 May 2023 | Zone 1 | Gate 1 | Trial trench at Side table by Hi-tech
Sat (06/05) | 06 May 2023 | Exit 2 |  | Wee Guan trial trench works for SPPG ongoing (ATT-WG022 & ATT-WG023)
Sat (06/05) | 06 May 2023 | ULT4 |  | Casting was done
Sat (06/05) | 06 May 2023 | Exit 2 | DW41 | Trial trench completed for Point 3. No services
Sat (06/05) | 06 May 2023 | Exit 2 |  | Continue of manual trial trench works for ATT-WG023
Sat (06/05) | 06 May 2023 | Exit 2 |  | Wee Guan trial trench works for ATT-WG022 completed. Found starhub cables & LV cable
Sat (06/05) | 06 May 2023 | Zone 3 | ABH-53 | SI started, drilling in progress. Current depth 4m
Sat (06/05) | 06 May 2023 | Exit 2 | RG-GWS 33004 | Drilling for water standpipe completed, depth 15m. Cleaning in progress. Monday will do the installation
Sat (06/05) | 06 May 2023 | Zone 3 |  | ECM Pond blocks laying works
Sat (06/05) | 06 May 2023 | Zone 4 |  | DE143 working within their boundary
Sat (06/05) | 06 May 2023 | Zone 3 | ABH-51 | SI drilling in progress. Current depth 10m
Sat (06/05) | 06 May 2023 | MH2-5 |  | Trial trench completed. Found LT cable at 2.3m depth
Sat (06/05) | 06 May 2023 | Zone 2 |  | Bored pile rig and crawler crane shifting to opposite gate 6 for parking
Sat (06/05) | 06 May 2023 | Zone 2 | ABH-33 | Drilling in progress, current depth 16m
Sat (06/05) | 06 May 2023 | Zone 2 | ABH-32 | Driling ongoing. Current depth 18m
Sat (06/05) | 06 May 2023 | Zone 2 |  | Steel plates laying for bored pile rig and crawler crane parking
Sat (06/05) | 06 May 2023 | Zone 2 |  | Noise barrier barricades works installation ongoing. Monday to continue with columns installation
Sat (06/05) | 06 May 2023 | Zone 2 PMH-3 |  | Current excavation status
Sat (06/05) | 06 May 2023 | Zone 2 | PMH-7 to PMH-8 | 18m duct casting ongoing
Sat (06/05) | 06 May 2023 | Zone 2 | ABH 31-1 | Premix removal completed. Monday will continue with manual trial trench works
Sat (06/05) | 06 May 2023 | Zone 2 | Bet LP199/1 to LP199 | SingTel pipe laying works - 6m laid. Pending premix laying
Sat (06/05) | 06 May 2023 | Zone 1 | Bet LP200 | SingTel pipe laying works. 12m laid, pending premix laying. (As of now, 16m SingTel pipe laid at zone 1)
Sat (06/05) | 06 May 2023 | PMH12 |  | Top slab casting completed
Sat (06/05) | 06 May 2023 | Exit 3 |  | PMH12 rebar and Formwork installation works for 2nd stage of wall. Target to cast in today afternoon
Sun (07/05) | 07 May 2023 | PMH3 |  | Excavation in progress
Sun (07/05) | 07 May 2023 | Zone 2 NB footings |  | No activity. Footings completed till LP183
Sun (07/05) | 07 May 2023 | Zone 1 Loyang Rise |  | No activity
Sun (07/05) | 07 May 2023 | PRD3 |  | No activity
Sun (07/05) | 07 May 2023 | Exit 3 |  | DW35 trimming in progress
Sun (07/05) | 07 May 2023 | Exit 2 |  | No activity
Sun (07/05) | 07 May 2023 | Zone 3 |  | HSL & SI teams no activity
Sun (07/05) | 07 May 2023 | Zone 3 |  | Painting of access crossing from new ECM pond in progress
Sun (07/05) | 07 May 2023 | Exit 1 |  | No activity
Sun (07/05) | 07 May 2023 | Loyang Way near Exit 1 |  | Shingda works ongoing
Sun (07/05) | 07 May 2023 | DW35 |  | Trimming in progress for waterstop end plate removal
Sun (07/05) | 07 May 2023 | DW53 |  | Base grouting 3rd stages completed. Cleaning and housekeeping
Sun (07/05) | 07 May 2023 | DW35 |  | 3rd bite excavation in progress
Sun (07/05) | 07 May 2023 | ABH38-2 |  | TT in progress
Sun (07/05) | 07 May 2023 | ABH41 |  | TT in progress
Sun (07/05) | 07 May 2023 | ABH44 |  | TT in progress
Sun (07/05) | 07 May 2023 | DW-035 |  | Site rearrangement ongoing
Mon (08/05) | 08 May 2023 | DW-035 |  | 3A&2A cage lapping ongoing
Mon (08/05) | 08 May 2023 | Zone 3 |  | No activity
Mon (08/05) | 08 May 2023 | DW35 |  | 2/8nos rebar cages lowered
Mon (08/05) | 08 May 2023 | ABH44 |  | TT in progress
Mon (08/05) | 08 May 2023 | ATT-WG-22 |  | Found 300mm dia water pipe. Corridor enough for laying
Mon (08/05) | 08 May 2023 | Zone 2 near LP199 |  | Singtel pipe laying, 12m
Mon (08/05) | 08 May 2023 | Zone 1 near Loyang Rise |  | Singtel pipe laid and haunching, 12m completed
Mon (08/05) | 08 May 2023 | Zone 1 NB footing |  | No activity
Mon (08/05) | 08 May 2023 | Zone 1 LA towards TPE |  | First lane closure by HSB and zone 1 next to blk 275: DE143 piling works ongoing
Mon (08/05) | 08 May 2023 | Zone 2 |  | POB pile cap hacking in progress
Mon (08/05) | 08 May 2023 | Zone 3 near Loyang Avenue junction |  | Hitech started TT for ECM pond
Mon (08/05) | 08 May 2023 | Zone 3 |  | Current status of ECM pond bund wall installation
Mon (08/05) | 08 May 2023 | PMH1 |  | Shoring installation in progress. To open back the lane by 5pm
Mon (08/05) | 08 May 2023 | PRD3 |  | No activity
Mon (08/05) | 08 May 2023 | Zone 2 ABH32 |  | Drilling ongoing, 38m
Mon (08/05) | 08 May 2023 | ABH33 |  | SPT in progress, current depth at 32m
Mon (08/05) | 08 May 2023 | DW-035 |  | Cage 1A lowered at 4am
Mon (08/05) | 08 May 2023 | DW-035 |  | 3B&2B lowered
Mon (08/05) | 08 May 2023 | Zone 1 |  | 2 teams provided. 1st team at usd, erss & decking removal. proceed with backfill & premix
Mon (08/05) | 08 May 2023 | PMH-01 |  | 2nd team proceed with excavation. TMA provided
Tue (09/05) | 09 May 2023 | Team 1 |  | Excavation for 36W started
Tue (09/05) | 09 May 2023 | Team 2 |  | PMH 01 remaining portion excavation and soil disposal ongoing
Tue (09/05) | 09 May 2023 | ABH33 |  | SPT ongoing. Current depth 44m
Tue (09/05) | 09 May 2023 | Zone 2 POB |  | Pile cap hacking completed. Now clearing debris
Tue (09/05) | 09 May 2023 | Zone 2 noise barrier |  | 20nos columns install yesterday
Tue (09/05) | 09 May 2023 | Substation | DW41 to DW45 | TT on going by Dongah
Tue (09/05) | 09 May 2023 | Zone 2 |  | Wee Guan to continue Singtel pipe laying today, 12m. As of yesterday, 18m completed
Tue (09/05) | 09 May 2023 | Zone 2 |  | Starhub here to retrieve cables
Tue (09/05) | 09 May 2023 | Zone 1 LA towards TPE |  | HSB first lane closure
Tue (09/05) | 09 May 2023 | Zone 1 Loyang Rise |  | Continue NB footing rebar & formwork installation
Tue (09/05) | 09 May 2023 | Zone 1 |  | Wee Guan to continue laying Singtel pipe today
Tue (09/05) | 09 May 2023 | Zone 1 blk 275 |  | DE143 piling works ongoing
Tue (09/05) | 09 May 2023 | Zone 1 PMH1 |  | Preparing to make access to PMH
Tue (09/05) | 09 May 2023 | PRD3 |  | No activity
Tue (09/05) | 09 May 2023 | Zone 2 USD |  | Continue power duct pipe laying, 12m. Target for casting today
Tue (09/05) | 09 May 2023 | ABH32 |  | Drilling in progress, 48m
Tue (09/05) | 09 May 2023 | DW-035 |  | 4A & 3A rebar cage lapping on going
Tue (09/05) | 09 May 2023 | Zone 2 |  | BRC laying for 12m Singtel pipe laying ongoing
Tue (09/05) | 09 May 2023 | ABH42 |  | Drilling and SPT continue
Tue (09/05) | 09 May 2023 | PMH3 |  | Lean concrete on going
Tue (09/05) | 09 May 2023 | Zone 2 noise barrier |  | Continue horizontal pipes installation
Tue (09/05) | 09 May 2023 | Zone 1 PMH1 |  | Access making to PMH in progress
Tue (09/05) | 09 May 2023 | Zone 2 |  | Singtel pipe laid, 12m
Tue (09/05) | 09 May 2023 | ABH35 |  | Hand auger ongoing
Tue (09/05) | 09 May 2023 | Zone 3 ECM pond |  | Slope protection casting with BRC
Tue (09/05) | 09 May 2023 | Zone 2 |  | Premix reinstatement done for Singtel duct laid
Wed (10/05) | 10 May 2023 | MH2-3 |  | Silt fence installation
Wed (10/05) | 10 May 2023 | Zone 1 LA towards TPE |  | No activity by other contractor
Wed (10/05) | 10 May 2023 | Zone 1 NB footing |  | Plan for casting today, 3nos
Wed (10/05) | 10 May 2023 | Zone 1 Wee Guan |  | Preparing for premix laying at yesterday’s location. Today plan to continue another 12m
Wed (10/05) | 10 May 2023 | Zone 2 |  | USD backfilling between PMH7-8
Wed (10/05) | 10 May 2023 | PMH1 |  | To continue access preparation to PMH
Wed (10/05) | 10 May 2023 | PMH3 |  | Sump pit rebar works started
Wed (10/05) | 10 May 2023 | PMH3 |  | Area preparation for PLT
Wed (10/05) | 10 May 2023 | Exit 1 |  | Today KTC will start trial trench to prepare for excavation
Wed (10/05) | 10 May 2023 | Zone 4 junction |  | No activity of other contractor
Wed (10/05) | 10 May 2023 | PMH03 |  | Base slab rebar works in progress
Wed (10/05) | 10 May 2023 | Zone 3 near junction |  | Construction of ECM pond in progress
Wed (10/05) | 10 May 2023 | Zone 2 |  | Singtel pipe laid. Casting in progress. 12m
Wed (10/05) | 10 May 2023 | DW15 TT |  | No cable found. Dongah will straightway do guidewall here
Wed (10/05) | 10 May 2023 | JTC behind blk 2 |  | TT done by Hitech. Found 22KV and LV
Wed (10/05) | 10 May 2023 | ABH42 |  | Drilling in progress, 27m
Wed (10/05) | 10 May 2023 | ABH41 |  | Hand auger in progress
Wed (10/05) | 10 May 2023 | Zone 1 |  | Singtel pipe laying ongoing, 14m. Bend pipes undercrossing the M1 pipe
Wed (10/05) | 10 May 2023 | PMH3 |  | Will resume after dinner
Wed (10/05) | 10 May 2023 | Towards PMH8 |  | Power duct pipe laid (14m), formwork installation ongoing
Wed (10/05) | 10 May 2023 | DW15 |  | Guidewall excavation in progress
Wed (10/05) | 10 May 2023 | DW-035 |  | They’ll remove the platform & hanging bar and shifting of materials here
Wed (10/05) | 10 May 2023 | PMH-01 |  | Team 2 preparing for lean con
Wed (10/05) | 10 May 2023 | Team 1 |  | To resume excavation till 2.4m depth & erss installation. current at 1.7m depth
Wed (10/05) | 10 May 2023 | ABH42 |  | Continue drilling, 14m
Wed (10/05) | 10 May 2023 | Zone 2 noise barrier |  | Continue horizontal pipes installation
Thu (11/05) | 11 May 2023 | Zone 1 LP201/2 |  | NB footing casting ongoing. Lane closure by HSB along Loy Ave to TPE Lane 1
Thu (11/05) | 11 May 2023 | MH2-3 |  | Gren mesh fencing dismantling and preparation work for TT
Thu (11/05) | 11 May 2023 | Zone 2 LP197 | Singtel Pipe Laying | WG premix cutting & removal ongoing
Thu (11/05) | 11 May 2023 | Zone 2 LP183 |  | Noise Barrier panels installation ongoing
Thu (11/05) | 11 May 2023 | DW34 |  | First bite excavation in progress
Thu (11/05) | 11 May 2023 | ABH35 |  | Preparation for drilling and SPT
Thu (11/05) | 11 May 2023 | USD towards PMH3 |  | Hardcore laying to leab concrete today
Thu (11/05) | 11 May 2023 | Zone 1 |  | Starhub closing third lane for cable pulling works
Thu (11/05) | 11 May 2023 | Zone 2 LVC side |  | B&T here with WX to check soye condition for NB lean concrete
Thu (11/05) | 11 May 2023 | Zone 2 LVC side |  | Yellow fencing installation to for NB footing
Thu (11/05) | 11 May 2023 | ABH35 |  | Drilling/SPT in progress
Thu (11/05) | 11 May 2023 | Zone 2 |  | MH2-3 trial trench works ongoing
Thu (11/05) | 11 May 2023 | ABH34 |  | Drilling/SPT resume
Thu (11/05) | 11 May 2023 | PMH3 |  | Base slab casting in progress
Thu (11/05) | 11 May 2023 | Zone 2 LP197 | Singtel Pipe Laying | 15m pipe laid today, pending haunching casting
Thu (11/05) | 11 May 2023 | JTC- DW | JTC-002 | Trial trench to check on existing services for Dwall work
Thu (11/05) | 11 May 2023 | Zone 3 |  | Brick wall installation for ECM pond
Thu (11/05) | 11 May 2023 | ZONE 3 |  | Road crossing TT by Wee Guan. Found Sptel and LV cable
Thu (11/05) | 11 May 2023 | Zone 1 |  | DE160 close fast for their work
Thu (11/05) | 11 May 2023 | Zone 2 |  | Continue of noise barrier panels installation
Thu (11/05) | 11 May 2023 | Zone 2 north ramp |  | Gantry installation in progress
Thu (11/05) | 11 May 2023 | DW34 |  | Trenching depth now at 8.7m
Thu (11/05) | 11 May 2023 | Zone 2 |  | Telco duct formwork closing. 12m, tomorrow to cast
Thu (11/05) | 11 May 2023 | Zone 2 |  | Continue NB panels installation
Thu (11/05) | 11 May 2023 | Between PMH7-8 |  | Area backfilled. Compaction ongoing
Thu (11/05) | 11 May 2023 | PMH3 |  | Activity stopped for the day
Thu (11/05) | 11 May 2023 | Team 1 |  | Marking out TT location and cable detection
Thu (11/05) | 11 May 2023 | Team 2 |  | Excavation in progress
Thu (11/05) | 11 May 2023 | PMH1 |  | Base lean concrete was cast last night
Thu (11/05) | 11 May 2023 | DW15 |  | Formwork closed. To cast before lunch
Thu (11/05) | 11 May 2023 | AbH42 |  | 32m depth now
Fri (12/05) | 12 May 2023 | DW34 |  | 2nd bite excavation in progress
Fri (12/05) | 12 May 2023 | Zone 1 |  | Trial trench done. Found 66kV and water pipe at 1.5m depth
Fri (12/05) | 12 May 2023 | DW34 |  | Cutter teeth replacing
Fri (12/05) | 12 May 2023 | Zone 2 |  | TT work in progress for drain hacking works
Fri (12/05) | 12 May 2023 | ABH35 |  | Drilling/SPT, depth at 22m
Fri (12/05) | 12 May 2023 | ABH34 |  | Drilling and SPT , depth now at 24m
Fri (12/05) | 12 May 2023 | Zone 1 |  | NB footing fwk closure ongoing
Fri (12/05) | 12 May 2023 | Zone 1 | Singtel by Dipcie | TT done, only found M1 pipe crossing. Proceed with backfilling & reinstatement
Fri (12/05) | 12 May 2023 | Mapletree | Blk 2 | TT on going by Dongah. 22KV running along Dwall alignment (10×2)
Fri (12/05) | 12 May 2023 | Mapletree behind Blk 2 |  | TT on going
Fri (12/05) | 12 May 2023 | Zone 3 side table near ULT5 |  | Wee Guan doing TT for their duct laying
Fri (12/05) | 12 May 2023 | Zone 1 to PMH01 |  | WG prepare to lay 36W pipes. On site 72 pieces, 12m length delivered. Tonight plan to cast
Fri (12/05) | 12 May 2023 | Zone 1 |  | Trial trench team completed
Fri (12/05) | 12 May 2023 | Exit 3 |  | First bite excavation was done and teetch changing for BC cutter
Fri (12/05) | 12 May 2023 | MH2-3 |  | TT done for the day. No service found as of now
Fri (12/05) | 12 May 2023 | Zone 2 |  | Continue NB panel installation
Fri (12/05) | 12 May 2023 | Towards PMH3 |  | Power duct pipe laying in progress
Fri (12/05) | 12 May 2023 | PMH3 |  | 1st stage wall casting
Fri (12/05) | 12 May 2023 | Zone 1 WG |  | Team 1 continue to do TT to find EHV
Fri (12/05) | 12 May 2023 | WG Team 2 |  | To continue pipe laying, 6m. Day shift team completed laying, 6m. Plan for casting tonight. Now area preparation
Sat (13/05) | 13 May 2023 | Zone 2 |  | Premix removal for ABH37 ongoing
Sat (13/05) | 13 May 2023 | Zone 3 |  | Premix removal for 22kV trial trench ongoing
Sat (13/05) | 13 May 2023 | Zone 2 |  | Singtel pipe laying by WG. Target to lay 18m today
Sat (13/05) | 13 May 2023 | Zone 2 |  | Rigid pavement removal by WG ongoing. Planned 2nos. trial trench at the same location today
Sat (13/05) | 13 May 2023 | WG team 1 |  | TT completed. Found 66kV slab at 850mm depth & EHV slab at 1.2m depth
Sat (13/05) | 13 May 2023 | Exit 3 |  | Drain demolition by KTC ongoing
Sat (13/05) | 13 May 2023 | Zone 3 |  | 12m 22kv pipes laid
Sat (13/05) | 13 May 2023 | Zone 2 |  | Singtel pipes 18m laid and cast
Sat (13/05) | 13 May 2023 | Zone 1 |  | NB footing access installation ongoing
Sat (13/05) | 13 May 2023 | Zone 2 |  | NB no. 27 cast
Sat (13/05) | 13 May 2023 | Zone 1 |  | Target to lay 8m for singtel pipes. Found traffic light cables and water pipe
Sat (13/05) | 13 May 2023 | Exit 3 |  | Manual excavation near LP cables ongoing. To be shifted away. Also highlighted to KTC to be careful of the LU installed
Sat (13/05) | 13 May 2023 | Exit 3 |  | BC cutter C lock welding still ongoing
Sat (13/05) | 13 May 2023 | Exit 3 |  | Access and barricade mostly completed
Sat (13/05) | 13 May 2023 | Towards PMH3 |  | Power duct formwork installation in progress. Plan for casting tmr, 24m
Sat (13/05) | 13 May 2023 | PMH3 |  | 1st stage wall formwork dismantled
Sat (13/05) | 13 May 2023 | Zone 2 |  | Noise barrier works done for the day
Sat (13/05) | 13 May 2023 | Zone 1 Wee Guan |  | Team 1 to do trial trench to find the existing 22kv
Sat (13/05) | 13 May 2023 | Zone 1 WG |  | Team 2 excavation for 36way pipe laying
Sun (14/05) | 14 May 2023 | MH6-1 |  | TT on going for water standpipe
Sun (14/05) | 14 May 2023 | DW34 |  | Water stop inspection
Sun (14/05) | 14 May 2023 | MH6-1 |  | Boring in progress for inclinometer, already reached 29m. Preparing for pipe installation
Mon (15/05) | 15 May 2023 | DW34 |  | Casting in progress, 51/170 m3
Mon (15/05) | 15 May 2023 | DW35 |  | Cage 4B/3B lapping in progress
Mon (15/05) | 15 May 2023 | Exit 3 |  | Current status of drain/pavement demolition by KTC
Mon (15/05) | 15 May 2023 | Zone 3 MH6-1 |  | Hand auger ongoing for water standpipe by RG
Mon (15/05) | 15 May 2023 | ABH41 |  | Drilling in progress, 23.5m
Mon (15/05) | 15 May 2023 | ABH39-3 |  | Hand auger in progress
Mon (15/05) | 15 May 2023 | ABH38-2 |  | Drilling/SPT in progress, 32m
Mon (15/05) | 15 May 2023 | MH2-3 |  | Manual trial trench ongoing
Mon (15/05) | 15 May 2023 | ABH37 |  | Hand auger in progress
Mon (15/05) | 15 May 2023 | Zone 2 |  | WG continue premix clearing for Singtel pipe laying. Plan to lay 6m today
Mon (15/05) | 15 May 2023 | Zone 2 |  | Continue NB panel installation
Mon (15/05) | 15 May 2023 | Zone 2 near LP191 |  | Singtel pipe laying, 18m
Mon (15/05) | 15 May 2023 | Zone 2 near LP193 |  | WG manual trial trench for proposed Singtel MH 02 (MX04)
Mon (15/05) | 15 May 2023 | Zone 3 |  | Excavation for 22kV pipe laying. 6m to be laid
Mon (15/05) | 15 May 2023 | Zone 3 |  | 22kV 9m pipe laying ongoing
Mon (15/05) | 15 May 2023 | Zone 1 LA towards TPE |  | DE160 fast lane closure
Mon (15/05) | 15 May 2023 | PRD3 sidetable | near bus depot | Lane closure by PUB contractor Kingview
Mon (15/05) | 15 May 2023 | Zone 1 USD |  | Reinstatement works ongoing for previous 36way (12m) pipe laying
Mon (15/05) | 15 May 2023 | PMH1 |  | Currently no activity
Mon (15/05) | 15 May 2023 | Next to blk 275 |  | DE143 works ongoing
Mon (15/05) | 15 May 2023 | Zone 1 Loyang Rise |  | Term contractor M1 trial trench for their pipe swinging to the new alignment. Current pipe depth at 1.1m
Mon (15/05) | 15 May 2023 | Zone 3 |  | Ley choon backfilling ongoing. Completed 1 no. Trial pit for singtel NCE
Mon (15/05) | 15 May 2023 | Zone 2 |  | Premix completed for the 6m pipes location done today
Mon (15/05) | 15 May 2023 | Near LP191 |  | Premix laid for the 18m pipes location
Mon (15/05) | 15 May 2023 | LP193 |  | TT completed. ATT-WG-21 and 22 — Found Starhub at 1.1m depth, LV at 0.9m depth, Singtel at 0.6m depth
Mon (15/05) | 15 May 2023 | DW34 |  | Rebar cage installation completed. Now preparation works for casting
Mon (15/05) | 15 May 2023 | PMH03 |  | Strut and waler dismantled. Now singtec housekeeping
Mon (15/05) | 15 May 2023 | PMH1 |  | Barricade installation on going
Mon (15/05) | 15 May 2023 | Zone 1 |  | Tonight excavation work for 22KV pipe alignment. This area here don't have enough space to install noise ballon. I asked Wee guan/WH to enclose the area and closely monitor noise reading for AWWA homes and loyang rise
Tue (16/05) | 16 May 2023 | PMH3 |  | 1st stage wall formwork dismantling and 2nd stage wall rebar works ongoing
Tue (16/05) | 16 May 2023 | After | GL P38 | Commenced TT work
Tue (16/05) | 16 May 2023 | Zone 2 near LP189 |  | WG premix hacking for Singtel pipe laying. Today plan 24m here
Tue (16/05) | 16 May 2023 | SW-023 |  | Pre excavation started
Tue (16/05) | 16 May 2023 | Zone 3 |  | ECM pond hollow block wall cement patching ongoing
Tue (16/05) | 16 May 2023 | Zone 2 near LP199/1 |  | WG trial trench for Singtel pipe laying
Tue (16/05) | 16 May 2023 | Zone 1 LA towards TPE |  | DE160 fast lane closure
Tue (16/05) | 16 May 2023 | Zone 1 Loyang Rise |  | Term contractor, Lucky Joint, premix hacking for the M1 pipe swinging
Tue (16/05) | 16 May 2023 | DW32 |  | Guidewall rebar installation in
Tue (16/05) | 16 May 2023 | Zone 3 |  | WG started excavation to continue 22kV pipe laying
Tue (16/05) | 16 May 2023 | PRD3 |  | No other activity. PUB contractor at side table
Tue (16/05) | 16 May 2023 | Zone 1 WG |  | Reinstatement at USD area
Tue (16/05) | 16 May 2023 | PMH1 |  | No activity
Tue (16/05) | 16 May 2023 | Zone 2 WG |  | Pipe laying team 2 near LVC continue premix removal for Singtel pipe. Today plan 18m here
Tue (16/05) | 16 May 2023 | Zone 3 |  | WG target to lay 6m for 22kV
Tue (16/05) | 16 May 2023 | Zone 3 |  | Hydraulic oil topping up for BC cutter ongoing
Tue (16/05) | 16 May 2023 | Zone 3 Drain |  | Manual TT ongoing. No services found yet
Tue (16/05) | 16 May 2023 | Exit 2 |  | Pavement hacking for DW039 TT ongoing
Tue (16/05) | 16 May 2023 | Exit 3 | DW-032 | Removal of drain ongoing
Tue (16/05) | 16 May 2023 | Opp Blk 224 LVC |  | B&T continue with excavation for noise barrier footing
Tue (16/05) | 16 May 2023 | Zone 3 near Selarang Camp |  | Continue ECM pond excavation
Tue (16/05) | 16 May 2023 | Zone 3 Loyang Way |  | Wee Guan (not under CR106) trial trench for Xenith manhole works
Tue (16/05) | 16 May 2023 | Exit 1 |  | KTC area preparation for machinery access
Tue (16/05) | 16 May 2023 | DW44 |  | Continue manual TT
Tue (16/05) | 16 May 2023 | DW39 |  | Continue manual TT
Tue (16/05) | 16 May 2023 | WG near Exit 2 |  | Backfilling & compaction ongoing
Tue (16/05) | 16 May 2023 | Zone 2 WG |  | Singtel pipe laying in progress, 18m
Tue (16/05) | 16 May 2023 | Near LP189 |  | Singtel pipe laying, 24m in progress
Tue (16/05) | 16 May 2023 | PMH-11 |  | Plinth fwk inspected, concrete otw
Tue (16/05) | 16 May 2023 | North ramp inspection for N6 done. Minor comments |  | To ensure proper access to storage area, steel plates gap, general housekeeping. HSL plans to install casing today
Tue (16/05) | 16 May 2023 | Zone 3 lincstech area |  | HBJB still here dismantling railings at the completed NB
Tue (16/05) | 16 May 2023 | Zone 2 north ramp |  | Casing for 1st bored pile installed, total 6m. Tomorrow to construct bundwall before start Boring. Rebar cages to deliver tomorrow afternoon
Wed (17/05) | 17 May 2023 | 2nd team |  | Maunual TT on going. No service found as of now
Wed (17/05) | 17 May 2023 | Zone 3 |  | Noise balloon setup for areas where 12m NB not completed
Wed (17/05) | 17 May 2023 | Zone 3 |  | Sealing of gaps for ECM pond still ongoing
Wed (17/05) | 17 May 2023 | PMH-3 |  | Fwk support for 2nd lift ongoing
Wed (17/05) | 17 May 2023 | Zone 2 Singtel | LP 185 | Started premix cutting work
Wed (17/05) | 17 May 2023 | Zone 2 North Ramp BP |  | Rebar cages on site
Wed (17/05) | 17 May 2023 | Zone 1 | 36W to PMH1 | WG continue excavation towards PMH1
Wed (17/05) | 17 May 2023 | PMH1 |  | No activity pending rebar delivery
Wed (17/05) | 17 May 2023 | Zone 2 North Ramp Piling | N6-2 | Status quo; site setting up ongoing
Wed (17/05) | 17 May 2023 | Exit 1 |  | Continue top soil removal in progress
Wed (17/05) | 17 May 2023 | Zone 2 Singtel | Before LVC linkway | Premix remocal done, proceed with excavation. Target 12m oso
Wed (17/05) | 17 May 2023 | SW23 |  | Clayshock grouting in progress. Estimated volume 45m3
Wed (17/05) | 17 May 2023 | Team 2 |  | Singtel pipe laying done for today is 26m
Wed (17/05) | 17 May 2023 | Team 1 |  | Casting done is 18m. Total 44m laid today
Wed (17/05) | 17 May 2023 | North ramp 1500D | N6-02 | Boring in progress, 17m/33.55m
Wed (17/05) | 17 May 2023 | PMH3 |  | Top slab plywood laying to continue rebar work
Wed (17/05) | 17 May 2023 | Zone 1 |  | 22KV pipe laying tonight estimate 12m for team 1
Wed (17/05) | 17 May 2023 | 2nd team |  | TT to find water pipe 700mm diamter alignment
Wed (17/05) | 17 May 2023 | MH6-1 |  | Rebar work for extension of working platform casting
Wed (17/05) | 17 May 2023 | Zone 3 Box Drain |  | 3 nos. 25mm dia pipes found within pavement area. Selvam coming onsite to identify
Wed (17/05) | 17 May 2023 | Loyang Avenue crossing near ULT5 |  | Wee Guan road cutting and continue excavation, today target to lay 6m length
Thu (18/05) | 18 May 2023 | Exit 1 | SW019 | 2nd bite excavation ongoing
Thu (18/05) | 18 May 2023 | Zone 2 |  | B&T preparation for cut&fill to lean con for NB
Thu (18/05) | 18 May 2023 | Zone 2 |  | Wee guan here 2 teams to continue pipe laying for singtel. Today target only 12m. 2x6m to connect to existing manhole
Thu (18/05) | 18 May 2023 | Zone 2 |  | Balance NB footing adjacent to linkway, formwork closing
Thu (18/05) | 18 May 2023 | Behind blk 2 |  | Selvam briefing his team to continue work
Thu (18/05) | 18 May 2023 | Zone 2 near LP185 |  | WG preparing to start works for Singtel pipe laying. Today plan 18m here
Thu (18/05) | 18 May 2023 | ABH44 |  | Hand auger ongoing
Thu (18/05) | 18 May 2023 | ABH39-3 |  | Drilling/SPT in progress
Thu (18/05) | 18 May 2023 | Zone 2 WG team 1 |  | Preparing to lay BRC and pipes, 12m here
Thu (18/05) | 18 May 2023 | RG near MH2-3 |  | Hand auger ongoing for inclinometer/water standpipe installation
Thu (18/05) | 18 May 2023 | Zone 2 NB footing |  | Formwork installation & HBJB preparing working platform
Thu (18/05) | 18 May 2023 | Near LP185 |  | WG team 2 preparing BRC for 18m pipe laying
Thu (18/05) | 18 May 2023 | ULT5 |  | HSL & Argus preparing for testing. Target monday start
Thu (18/05) | 18 May 2023 | Zone 1 LA | TPE bound | DE160 lane closure at first lane
Thu (18/05) | 18 May 2023 | Zone 1 Loyang Rise |  | No activity
Thu (18/05) | 18 May 2023 | LA/PRD3 junction |  | Lowering of manhole works by M1 contractor, Lucky Joint
Thu (18/05) | 18 May 2023 | Zone 1 USD near PMH1 |  | Excavation & shoring installation
Thu (18/05) | 18 May 2023 | PMH1 |  | No activity. Have informed WG to continuously pump the water out from the PMH
Thu (18/05) | 18 May 2023 | PRD3 |  | No other activity. PUB contractor at sidetable
Thu (18/05) | 18 May 2023 | SW21 |  | Preparation for clayshock grouting
Thu (18/05) | 18 May 2023 | SW21 |  | Clayshock grouting started
Thu (18/05) | 18 May 2023 | PMH3 |  | Propping in progress. Concrete (G50) ordered
Thu (18/05) | 18 May 2023 | Blk 222, reached 67db between 3 |  | 50-4 am due to casting of guidewall for ST11. Informed WH to stop trenching temporarily
Thu (18/05) | 18 May 2023 | DW-33 |  | Trenching completed at 16:00hrs , current depth - 34.5m. Preparation for Koden test ongoing
Thu (18/05) | 18 May 2023 | Exit 2 |  | DW44 manual trial trench in progress
Thu (18/05) | 18 May 2023 | Exit 2 |  | DW40 manual trial trench in progress
Thu (18/05) | 18 May 2023 | 22kV |  | 9m laid. Now backfilling
Thu (18/05) | 18 May 2023 | SW19 |  | Excavation temporarily stopped due to mud pump hydraulic oil leaking. Waiting for repair
Thu (18/05) | 18 May 2023 | Zone 2 WG team 1 |  | Singtel 12m pipe laid. Backfilling ongoing
Thu (18/05) | 18 May 2023 | DW33 |  | Trenching continue at 25.3m from GWTL
Thu (18/05) | 18 May 2023 | PMH3 |  | Casting completed. Singtec till 7pm today
Thu (18/05) | 18 May 2023 | N6-2 |  | Casting started
Thu (18/05) | 18 May 2023 | Team 1 |  | To do TT to locate 700mm dia water pipe
Thu (18/05) | 18 May 2023 | Team 2 | LA Island | Prepare for casting work for 36W
Thu (18/05) | 18 May 2023 | DW033 |  | Trimming work ongoing
Fri (19/05) | 19 May 2023 | DW-033 |  | Trimming at water stopper side ongoing
Fri (19/05) | 19 May 2023 | Zone 2 Loyang Lane |  | TT work ongoing by Dipcie
Fri (19/05) | 19 May 2023 | DW33 |  | BC Cutter wheel spoiled. Now changing to new wheel. Trenching reached at toe level but pending cleaning. Target to start by 1pm
Fri (19/05) | 19 May 2023 | MH6-1 |  | LCH tidy up materials before continue with next layer excavation
Fri (19/05) | 19 May 2023 | AbH44 |  | Drilling and SPT started
Fri (19/05) | 19 May 2023 | ABH39-3 |  | Current depth 32m
Fri (19/05) | 19 May 2023 | RG near MH2-3 |  | Boring ongoing for inclinometer installation
Fri (19/05) | 19 May 2023 | ABH39-3 |  | Depth 32m
Fri (19/05) | 19 May 2023 | BH176 |  | TT in progress
Fri (19/05) | 19 May 2023 | Zone 2 near LP181 |  | WG to continue Singtel pipe laying, 12m here today
Fri (19/05) | 19 May 2023 | MH2-3 |  | Ryobi-G drilling for water stand pipe and iclinometer installation
Fri (19/05) | 19 May 2023 | Exit 2 DW40 & DW41 |  | Preparing to continue excavation for guide wall
Fri (19/05) | 19 May 2023 | Zone 2 |  | Singtel pipe laying 12m target Today for team 2
Fri (19/05) | 19 May 2023 | Exit 1 | SW019 | 3rd bite excavation work completed, 9.30m depth
Fri (19/05) | 19 May 2023 | Zone 3 |  | Team 2 to lay 24m for 22kV today
Fri (19/05) | 19 May 2023 | Zone 3 |  | WG Team 3 exposing 66kV for SPPG to check again on Monday
Fri (19/05) | 19 May 2023 | Zone 2 |  | Singtel pipe laying team 2 excavation done
Fri (19/05) | 19 May 2023 | Zone 2 |  | Team 2 for pipe laying. Today also 12m. Total 24m
Fri (19/05) | 19 May 2023 | Zone 1 NLL |  | Pgas here doing M&P
Fri (19/05) | 19 May 2023 | Exit 1 |  | Cutter slope excavation ongoing
Fri (19/05) | 19 May 2023 | Zone 1 |  | PMH01 waiting for rebar delivery. Est to arrive at 4pm
Fri (19/05) | 19 May 2023 | Zone 3 ECM pond |  | Access construction by WH
Fri (19/05) | 19 May 2023 | Zone 1 |  | DE143 rest area to shift tomorrow morning. Then Wee guan will shift 2 signages +1 VMS in the afternoon and start excavation for USD
Fri (19/05) | 19 May 2023 | PMH-3 |  | Housekeeping works ongoing. WH-DA need to submit fresh Annex C and D to QPS team before work can resume
Fri (19/05) | 19 May 2023 | DW33 |  | Trimming works in progress
Fri (19/05) | 19 May 2023 | P37 |  | TT on going by Hitech at Lane 1
Fri (19/05) | 19 May 2023 | Exit 1 | SW019 | Clayshock injection ongoing & will continue till day shift
Fri (19/05) | 19 May 2023 | N5-2 |  | Tremie pipe lowering for casting. Concrete ordered-25.5m3
Fri (19/05) | 19 May 2023 | Zone 2 North Ramp BP | N5-2 | Casting ongoing
Fri (19/05) | 19 May 2023 | Zone 3 SW-017 |  | Cleaning / desanding completed. Depth at 9.3m
Sat (20/05) | 20 May 2023 | ABH-49 | Zone 3 | Drilling in progress, depth 28.5m
Sat (20/05) | 20 May 2023 | Dipcie team at Loyang Lane near to Gate 5 |  | Excavation ongoing
Sat (20/05) | 20 May 2023 | Zone 3 |  | Tong contractor removal of capping beam ongoing
Sat (20/05) | 20 May 2023 | Exit 1 |  | Slope cutting works in progress
Sat (20/05) | 20 May 2023 | Zone 3 | SW-15 | Pre excavation work in progess
Sat (20/05) | 20 May 2023 | Exit 1 |  | Manual excavation in progress for temp power supply OG box
Sat (20/05) | 20 May 2023 | Zone 4 |  | De143 working within their hoarded area
Sat (20/05) | 20 May 2023 | Zone 3 |  | Excavation for pipe laying ongoing. Target to lay 18m today
Sat (20/05) | 20 May 2023 | Exit 2 |  | Levelling works ongoing for upcoming SI works
Sat (20/05) | 20 May 2023 | ABH39-3 |  | Current depth 39m
Sat (20/05) | 20 May 2023 | ABH31-3 |  | Drilling in progress. Current depth 14m
Sat (20/05) | 20 May 2023 | Zone 3 | MH2-3 | PVC pipe for water stand pipe installation in progress
Sat (20/05) | 20 May 2023 | Zone 2 |  | Premix removal in progress for SingTel pipe laying. Today target to lay 37m
Sat (20/05) | 20 May 2023 | Zone 2 |  | Manual trial trench for SingTel manhole location
Sat (20/05) | 20 May 2023 | Zone 1 |  | Ibeam delivery for noise barriers (36nos). Target to start installation on Monday
Sat (20/05) | 20 May 2023 | Zone 1 |  | DE143 have already shifted out their rest area. Now lamppost shifting works ongoing and balance signages and VMS will shift in the afternoon to DE143 previous rest area location
Sat (20/05) | 20 May 2023 | PMH-1 |  | Rebars for base slab delivered. Installation of rebar for base slab in progress
Sat (20/05) | 20 May 2023 | Zone 1 |  | DE160 & DE143 works ongoing
Sat (20/05) | 20 May 2023 | DW-033 |  | C lock welding ongoing
Sat (20/05) | 20 May 2023 | SW-017 |  | Clayshock injection ongoing
Sat (20/05) | 20 May 2023 | ABH-44 | Zone 3 | Drilling in progress, depth 27m
Sat (20/05) | 20 May 2023 | Dwall 33 |  | Preparation for Waterstop installation at Dwall 32 side
Sat (20/05) | 20 May 2023 | MH6-1 |  | Current status for 2nd layer caisson installation. Today target to complete 2nd layer installation
Sat (20/05) | 20 May 2023 | ABH-49 | Zone 3 | Drilling in progress, depth 40m
Sat (20/05) | 20 May 2023 | Zone 3 |  | Continue Excavation for pipe laying ongoing
Sat (20/05) | 20 May 2023 | Zone 3 |  | Tong contractor removal of capping beam in progress
Sat (20/05) | 20 May 2023 | Exit 1 |  | Slope cutting works in progress
Sat (20/05) | 20 May 2023 | Exit 1 |  | Current status for temp power supply OG box
Sat (20/05) | 20 May 2023 | Zone 3 | SW-15 | 3rd bite trenching completed. Now cleaning and Desanding in progress
Sat (20/05) | 20 May 2023 | Zone 3 |  | Drain hacking works ongoing
Sat (20/05) | 20 May 2023 | Dwall 33 |  | Waterstop joint welding at Dwall 32 side
Sat (20/05) | 20 May 2023 | ABH39-3 |  | SI completed, depth 40m
Sat (20/05) | 20 May 2023 | ABH39-2 |  | SI rig setting up
Sat (20/05) | 20 May 2023 | MH2-3 |  | Instrumentation installation completed
Sat (20/05) | 20 May 2023 | Zone 2 |  | SingTel pipe laying in progress. Total length 37m
Sat (20/05) | 20 May 2023 | Zone 1 |  | Premix removal for 250mm depth cut off drain
Sat (20/05) | 20 May 2023 | Zone 1 |  | 2 nos. of signages shifted to new location. Now shifting VMS
Sat (20/05) | 20 May 2023 | PMH-1 |  | Continue Installation of rebar for base slab
Sat (20/05) | 20 May 2023 | DW-033 |  | C lock welding ongoing
Sat (20/05) | 20 May 2023 | PMH-3 |  | Wall & top slab casting completed. Now casting 3.5m usd duct connection
Sat (20/05) | 20 May 2023 | PMH7-PMH8 |  | C7 drain installation works
Sat (20/05) | 20 May 2023 | North ramp | BP N6-6 | Toe confirmed at 33.80m from TOC. Actual toe: 10.722mSHD. Rebar cage lapping & lowering in progress
Sat (20/05) | 20 May 2023 | PMH12 |  | Scaffold platform dismantling completed
Sat (20/05) | 20 May 2023 | TMH5 - TMH6 |  | Telco duct laying works in progress
Sat (20/05) | 20 May 2023 | MH6-1 |  | Current status for 2nd layer caisson installation
Sat (20/05) | 20 May 2023 | DW-033 |  | Trimming resumed
Sat (20/05) | 20 May 2023 | Exit 1 | SW-017 | Clayshock injection completed at 6:35am, Theoretical volume - 45360 L, Actual Volume - 47391 L, Overbreak - 4.477 %
Sat (20/05) | 20 May 2023 | DW-033 |  | Cage inspected & lowering ongoing
Sat (20/05) | 20 May 2023 | SW-015 |  | Clayshock injection ongoing
Sat (20/05) | 20 May 2023 | Zone 3 JTC side |  | Works stopped for the night
Sat (20/05) | 20 May 2023 | North ramp | BP N6-6 | Casting ongoing
Sat (20/05) | 20 May 2023 | Dwall 33 |  | Waterstop endplate extraction in progress
Sat (20/05) | 20 May 2023 | ABH-44 | Zone 3 | Drilling in progress, depth 20m
Sun (21/05) | 21 May 2023 | Zone 3 near P32 |  | Excavation works in progress to prepare for 66KV spiking
Sun (21/05) | 21 May 2023 | Zone 3 |  | 3rd team of wee guan work for SPPG pipe laying. Top soil removal and preparation for manual excavation. Today plan to lay 6m
Sun (21/05) | 21 May 2023 | Exit 1 |  | Slope cut down and soil disposal
Sun (21/05) | 21 May 2023 | Zone 1 |  | Cut off drain no activity
Sun (21/05) | 21 May 2023 | Zone 1 NB |  | Railing installation in progress for I-beam installation tomorrow
Sun (21/05) | 21 May 2023 | Zone 1 Junction |  | DE143 working here for kerb replacement
Sun (21/05) | 21 May 2023 | Exit 1 SW-015 |  | Clayshock injection completed, Theoretical volume - 45360 L, Actual Volume - 47695 L, Overbreak - 5.147 %
Sun (21/05) | 21 May 2023 | DW-033 |  | Preparing for casting
Sun (21/05) | 21 May 2023 | Exit 1 |  | Clayshock mixing
Sun (21/05) | 21 May 2023 | DW033 - vol |  | 51m³/102m³
Sun (21/05) | 21 May 2023 | Zone 3 |  | No activity
Sun (21/05) | 21 May 2023 | Zone 3 |  | Across loyang avenue in front of jTC, manual excavation on going for 22KV pipe laying. 6m
Sun (21/05) | 21 May 2023 | BH 154 |  | TT in progress, BH142: TT in progress, BH153: TT in progress
Sun (21/05) | 21 May 2023 | Exit 2 |  | Guidewall rebar works for DW41 and DW42
Mon (22/05) | 22 May 2023 | SW013 |  | 3rd bite cleaning in progress, Completed Slurry Wall - 5 Panels ( SW23, SW21, SW19, SW17, SW15)
Mon (22/05) | 22 May 2023 | Zone 3 |  | WG 1st Team target to lay 12m for 22kV. 2nd Team excavating the corridor beside
Mon (22/05) | 22 May 2023 | Zone 3 |  | SW013 to start after shifting of steel plates for working platform
Mon (22/05) | 22 May 2023 | Exit 3 |  | Area preparation for DW32 trenching
Mon (22/05) | 22 May 2023 | ABH44 |  | Drilling in progress. Depth at 37m
Mon (22/05) | 22 May 2023 | Zone 2 NLL LP 7 -34) | ATT-WG(D | TT work by SPTel. Found LV, StarHub & Water pipe
Mon (22/05) | 22 May 2023 | Zone 1 Noise Barrier |  | 12nos I beam installed as of now. Worker on break. Will resume after
Mon (22/05) | 22 May 2023 | North ramp | N5-1 | Boring in progress, current depth 17m
Mon (22/05) | 22 May 2023 | Singtel pipe cable laying team 1 |  | 12m pipe laid
Mon (22/05) | 22 May 2023 | PMH01 |  | Base slab rebar tying & first lift wall rebar ongoing
Mon (22/05) | 22 May 2023 | LA LP201 |  | Preparation for night time pipe laying
Mon (22/05) | 22 May 2023 | ABH39-1 |  | Depth now at 30m
Mon (22/05) | 22 May 2023 | Zone 2 |  | Singtel team 2 pipe laying, 6m
Mon (22/05) | 22 May 2023 | PMH-3 |  | Backfilling & levelling works
Mon (22/05) | 22 May 2023 | Zone 2 |  | Previous entrance of LVC, NB footing formwork closing, 9m
Mon (22/05) | 22 May 2023 | Zone 3 |  | 3rd team manual excavating for 22kV. May take a few days to manual excavate around the utilities
Mon (22/05) | 22 May 2023 | MH6-1 |  | Excavation for 3rd layer caison. To continue tomorrow
Mon (22/05) | 22 May 2023 | Exit 2 |  | Manual excavation to find alignment of LV for DW43
Mon (22/05) | 22 May 2023 | Zone 3 |  | Wee guan stop work for the day
Mon (22/05) | 22 May 2023 | Zone 3 drain hacking works |  | KTC stopped for the day
Mon (22/05) | 22 May 2023 | Zone 3 |  | Tong contracts stopped work for the day
Mon (22/05) | 22 May 2023 | DW032 |  | 1st bite excavation in progress. 11.5m depth as of now
Mon (22/05) | 22 May 2023 | Gate 5 |  | WH installation of shelter for biometric machine
Tue (23/05) | 23 May 2023 | Zone 3 across L.A |  | To continue manual excavation for SPPG pipe laying
Tue (23/05) | 23 May 2023 | North ramp, N5-1 |  | Toe level confirmed at 23.35m
Tue (23/05) | 23 May 2023 | Exit 2 |  | Continue manual excavation to expose LV cable
Tue (23/05) | 23 May 2023 | Zone 2 NLL |  | WG preparation work ongoing
Tue (23/05) | 23 May 2023 | Zone 3 near JTC blk 4 |  | SPPG here for 66KV spiking
Tue (23/05) | 23 May 2023 | Zone 3 |  | Wee Guan 2nd team for SPPG pipe laying to continue excavate here
Tue (23/05) | 23 May 2023 | Zone 1 |  | Continue excavation for 36w pipes
Tue (23/05) | 23 May 2023 | PMH1 |  | Continue base slab rebar tying & fwk closure
Tue (23/05) | 23 May 2023 | Zone 2 Exit 3 ECM pond |  | Excavation started
Tue (23/05) | 23 May 2023 | Exit 1 |  | System foundation here for subsoil drain installation. They plan to start after lunch
Tue (23/05) | 23 May 2023 | Zone 3 |  | WG casting 7m of 6W Singtel
Tue (23/05) | 23 May 2023 | Between TMH5-6 |  | Telco duct pipes laid 12m & formwork closed. Pending inspection
Tue (23/05) | 23 May 2023 | PMH3 |  | Backfilling ongoing
Tue (23/05) | 23 May 2023 | Zone 2 North Ramp |  | Hardcore delivered to site
Tue (23/05) | 23 May 2023 | Zone 2 |  | TT work at N2 location by WH
Tue (23/05) | 23 May 2023 | Zone 2 near LVC |  | Hi-Tech TT for NCE extension. Found Singtel at 1.2m depth
Tue (23/05) | 23 May 2023 | Exit 1 |  | Subsoil drain drilling ongoing
Tue (23/05) | 23 May 2023 | Zone 3 |  | WG One team backfilling trench area occupied by utilities and the other team laying 6m 22kV pipes
Tue (23/05) | 23 May 2023 | Exit 3 Drain |  | KTC preparing for drain removal. Now material shifting only. Will stop work at 6.30pm
Tue (23/05) | 23 May 2023 | MH6-1 |  | No activity. Rebar installation and inspection was done
Tue (23/05) | 23 May 2023 | DW032 |  | 2nd bite excavation in progress, reached 30m/34.47m
Tue (23/05) | 23 May 2023 | ULT5 | Cycle 3 | Applied 275% of working load. Jack opening is around 6.04mm
Tue (23/05) | 23 May 2023 | Zone 1 |  | Decking removal to continue excavation at center island
Tue (23/05) | 23 May 2023 | PMH1 |  | Base slab casting was done
Tue (23/05) | 23 May 2023 | Between TMH5-6 |  | Telco duct pipe lahing in progress. Between PMH11-12: Toe board installation
Tue (23/05) | 23 May 2023 | MH6-1 |  | Manual excavation for 3rd layer caison
Tue (23/05) | 23 May 2023 | Zone 2 Noise barrier footing | LVC after boundary wall | Rebar work started
Tue (23/05) | 23 May 2023 | Zone 2 Noise barrier footing | LVC old access | 3 nos plan to cast today, pending fwk inspection
Tue (23/05) | 23 May 2023 | Zone 2 POB pile cap area |  | 66kV spiking has been arranged for today. Have informed WH to pump out the water from the trench
Tue (23/05) | 23 May 2023 | RG near MH2-5 |  | Manual trial trench ongoing for inclinometer/water standpipe installation
Wed (24/05) | 24 May 2023 | LP199/1 near Shell station |  | Singtel pipe laid 7m yesterday. Now pending reinstatement
Wed (24/05) | 24 May 2023 | ATT-WG-37 | D | Found LV and Starhub
Wed (24/05) | 24 May 2023 | ATT-WG-34 | D | Found water pipe, Starhub & LV
Wed (24/05) | 24 May 2023 | Zone 1 LA towards TPE |  | No lane closure by other contractor
Wed (24/05) | 24 May 2023 | PMH1 |  | Base slab cast yesterday. Wall rebar works in progress
Wed (24/05) | 24 May 2023 | Zone 1 USD |  | Today will continue pipe laying, 6m. Plan for casting tonight
Wed (24/05) | 24 May 2023 | North ramp N6-5 |  | Toe level reached, ard 33.8m. Pending confirmation depth
Wed (24/05) | 24 May 2023 | N2 and N3 area |  | Hardcore laying & area preparation
Wed (24/05) | 24 May 2023 | PMH3 |  | Steel plate/soldier pile removal. RFI, annex C & D submitted
Wed (24/05) | 24 May 2023 | Zone 1 |  | Lane open back to public
Wed (24/05) | 24 May 2023 | Zone 3 |  | 8m pipe laying ongoing for singtel by WG
Wed (24/05) | 24 May 2023 | Zone 3 |  | Supporting of starhub cables ongoing for 22kv pipe laying by WG
Wed (24/05) | 24 May 2023 | Zone 3 |  | Target to lay 9m 22kV pipes today. Utilities support and manual excavation ongoing
Wed (24/05) | 24 May 2023 | Zone 3 ULT8 |  | Hardcore removal for trial trench works
Wed (24/05) | 24 May 2023 | Exit 2 |  | Guidewall rebar installation for DW43-44
Wed (24/05) | 24 May 2023 | North ramp N5-3 | 1.3D | Preboring & casing installed
Wed (24/05) | 24 May 2023 | N6-5 |  | Depth confirmed at 33.83m. Rebar cage installed. Now preparation for casting works
Wed (24/05) | 24 May 2023 | N2-N3 area |  | Steel plate laying ongoing
Wed (24/05) | 24 May 2023 | MH6-1 |  | 3rd layer caisson wall casting in progress
Wed (24/05) | 24 May 2023 | MH6-1 |  | 3rd layer caisson casting done. Levelling on going
Wed (24/05) | 24 May 2023 | N6-5 |  | Casting in progress, 27/53m3
Thu (25/05) | 25 May 2023 | Zone 2 IS20501 |  | Drilling work ongoing for GWS. Ytd installed inclinometer. For sewer MH2-5
Thu (25/05) | 25 May 2023 | ULT5 |  | Cycle 4 in progress. Current load at 275%
Thu (25/05) | 25 May 2023 | Zone 2 Noise Barrier | fronting LVC Blk 204A | HBJB clearing area / preparing to continue rebar work
Thu (25/05) | 25 May 2023 | Zone 2 |  | TT ongoing for utility crossing. By WG
Thu (25/05) | 25 May 2023 | Zone 2 NLL |  | WG commence TT work
Thu (25/05) | 25 May 2023 | Zone 1 Noise Barriers |  | Preparing to commence horizontal pipe installation
Thu (25/05) | 25 May 2023 | PMH1 |  | Removing fwk support ongoing
Thu (25/05) | 25 May 2023 | 36W |  | Ytd cast, preparing for backfilling work
Thu (25/05) | 25 May 2023 | Zone 2 North Ramp Piling |  | N5-3(1.3D) toe confirmed at 23.35m(+0.186mshd) from TOC, rebar cages have been checked
Thu (25/05) | 25 May 2023 | PMH-3 |  | Pending plinth work
Thu (25/05) | 25 May 2023 | DW 32 |  | Lapping and lowering of last Cage B in progress. Current status: Cage A (3/4 cages lowered down). Cage B (3/4 cages lowered down)
Thu (25/05) | 25 May 2023 | BH-9 |  | TT status
Thu (25/05) | 25 May 2023 | Zone 2 |  | NB Formwork closing in progress. Target to cast tmr
Thu (25/05) | 25 May 2023 | TMH-6 |  | Lean concrete completed
Thu (25/05) | 25 May 2023 | Zone 3 JTC |  | Capping beam hacking ongoing
Thu (25/05) | 25 May 2023 | N6-1 | 1.5D | Pre boring completed. Now installing casing
Thu (25/05) | 25 May 2023 | Zone 3 SW |  | Box drain removal / excavation
Thu (25/05) | 25 May 2023 | PMH 3 |  | Formwork closing for neck casting tmr
Thu (25/05) | 25 May 2023 | Zone 1 |  | Noise barrier horizontal pipe installation ongoing
Thu (25/05) | 25 May 2023 | PMH1 |  | Formwork support removal completed
Thu (25/05) | 25 May 2023 | Zone 1 near AWWA |  | Continue backfilling. Thereafter will shift back the signage
Thu (25/05) | 25 May 2023 | Zone 1 traffic island |  | Tonight plan for 36way casting, 17.3m
Thu (25/05) | 25 May 2023 | Zone 3 |  | WH continue 22kV pipe laying
Thu (25/05) | 25 May 2023 | Noted. MH6-1 |  | LCH provided 7 workers for formwork dismantling and cage ladder installation. MH5-2 : LCH provided 3 workers for rebar bending
Fri (26/05) | 26 May 2023 | Zone 2 Gate 6 |  | Vibro demob by Singtec
Fri (26/05) | 26 May 2023 | Zone 2 North Ramp |  | Steel plate removal by Singtec & clearing up the work area
Fri (26/05) | 26 May 2023 | Exit 2 |  | Formwork closing for DW43 & 44. Today plan to cast
Fri (26/05) | 26 May 2023 | Zone 1 |  | Backfilling in progress
Fri (26/05) | 26 May 2023 | Zone 2 Bored Pile Dia | N6-1 | ∅1500mm: boring ongoing
Fri (26/05) | 26 May 2023 | Zone 2 NLL | next to Shell | EL working here
Fri (26/05) | 26 May 2023 | Zone 1 Noise Barrier |  | Panel installation ongoing
Fri (26/05) | 26 May 2023 | P23 |  | Wee Guan plan to continue excavation for Power duct laying
Fri (26/05) | 26 May 2023 | PMH1 |  | Current status
Fri (26/05) | 26 May 2023 | TMH6 + telco duct |  | Fwk removal & slab rebar work ongoing
Fri (26/05) | 26 May 2023 | MH2-4 |  | TT work prior to cluster installation by Ryobi G
Fri (26/05) | 26 May 2023 | Zone 2 | opp old LVC guardhouse | TT work by WG, setting up barricade
Fri (26/05) | 26 May 2023 | Zone 2 North Ramp Piling |  | N6-1(1.5D) toe level confirmed at 33.75m (+10.763mSHD). Installing 1st rebar cage
Fri (26/05) | 26 May 2023 | Zone 2 North Ramp |  | PMH3 plinth casting completed, ECM platform casting completed & ECM pond access & barricade setting up ongoing
Fri (26/05) | 26 May 2023 | DW32 casting progressive vol |  | 69.5/195.5m3
Fri (26/05) | 26 May 2023 | ULT8 |  | Trial trench ongoing to find water pipe alignment and possible ULT8 location
Fri (26/05) | 26 May 2023 | Zone 2 North Ramp |  | Continue excavation & steel plate laying for piling working platform
Fri (26/05) | 26 May 2023 | MH2-3 |  | Levelling work only. Tmr they will mob-in their materials. 2+1
Fri (26/05) | 26 May 2023 | Zone 2 NB footing |  | Casting ongoing
Fri (26/05) | 26 May 2023 | Zone 3 WG |  | Backfilling completed
Fri (26/05) | 26 May 2023 | Zone 1 near AWWA |  | Works completed. Signages shifted
Fri (26/05) | 26 May 2023 | Exit 3 SC40 |  | Welding work ongoing
Fri (26/05) | 26 May 2023 | Exit 1 |  | Soil Trimming to the 2nd level (+5mSHD) ongoing. To install 2 layers of subsoil drain between +10mSHD and +5mSHD
Fri (26/05) | 26 May 2023 | Exit 1 |  | SW18 clayshock injection ongoing
Fri (26/05) | 26 May 2023 | N4-3 |  | Preparing machine for tomorrow work
Fri (26/05) | 26 May 2023 | N6-1 |  | Tremie pipe lowering down for casting, estimated volume- 53m3
Fri (26/05) | 26 May 2023 | DW32 progressive vol |  | 190m3
Fri (26/05) | 26 May 2023 | Tele MH6 |  | Base slab rebar work in progress. Tomorrow casting
Fri (26/05) | 26 May 2023 | PMH1 |  | Rebar work for 2nd lift wall casting
Fri (26/05) | 26 May 2023 | North ramp N6-1 |  | Casting ongoing
Fri (26/05) | 26 May 2023 | PMH1 |  | 2nd lift wall rebar inspected. Formwork closing in progress. Plan for casting tonight
Fri (26/05) | 26 May 2023 | Zone 1 USD |  | Continue excavation for 36way
Fri (26/05) | 26 May 2023 | Zone 1 LA traffic island |  | To continue backfilling & reinstatement. Preparation works in progress
Fri (26/05) | 26 May 2023 | Exit 2 |  | DW43-44 guidewall casting in progress
Fri (26/05) | 26 May 2023 | Zone 3 WG |  | Power duct pipe laying in progress
Sat (27/05) | 27 May 2023 | Zone 3 |  | 2nd WG team plans to excavate this 12m stretch today
Sat (27/05) | 27 May 2023 | Zone 3 |  | Preparation works ongoing for 3rd WG team
Sat (27/05) | 27 May 2023 | Zone 3 P27-29 |  | WG continue excavation for 22kV pipe laying
Sat (27/05) | 27 May 2023 | DW15 |  | 2nd bite excavation in progress
Sat (27/05) | 27 May 2023 | Exit 1 |  | Barricade installation and excavation to +5mSHD ongoing
Sat (27/05) | 27 May 2023 | Zone 3 |  | Kerb hacking ongoing
Sat (27/05) | 27 May 2023 | Exit 2 |  | Manual excavation for SPPG cables again to cast concrete for utility protection
Sat (27/05) | 27 May 2023 | Zone 2 |  | Yellow fence dismantling ongoing to facilitate NB footing works
Sat (27/05) | 27 May 2023 | Zone 2 |  | I beam installation ongoing. 3nos. Left to install at this location
Sat (27/05) | 27 May 2023 | Zone 2 |  | 2nd WG (Dipcie) team excavation across Loyang Ave ongoing
Sat (27/05) | 27 May 2023 | PMH1 |  | 2nd lift wall inspected. Concrete on the way
Sat (27/05) | 27 May 2023 | Zone 3 WG |  | 18m pipes laid (SPPG)
Sat (27/05) | 27 May 2023 | Zone 1 Loyang Rise |  | Protruding edges have been wrapped but not entirely for some areas. Have informed WHDA to follow up
Sat (27/05) | 27 May 2023 | Zone 1 |  | DE143 working at the centre median of Loyang Ave
Sat (27/05) | 27 May 2023 | Zone 1 NLL |  | DE143 occupied 1 lane for their works
Sat (27/05) | 27 May 2023 | Zone 1 Loyang Rise |  | Bund wall construction next to roadside drain ongoing
Sat (27/05) | 27 May 2023 | Zone 1 USD |  | To cast 9m tonight. Pipe laying ongoing
Sat (27/05) | 27 May 2023 | Zone 1 |  | Panel installation ongoing
Sat (27/05) | 27 May 2023 | Zone 1 |  | 3rd WG (Dipcie) team excavation ongoing near the junction. To continue along NLL on Mon
Sat (27/05) | 27 May 2023 | Zone 2 |  | Preparation to lift materials to N4-3
Sat (27/05) | 27 May 2023 | Exit 3 |  | Backfilling of ground till USD level
Sat (27/05) | 27 May 2023 | Exit 3 |  | Remaining concrete used to lean concrete USD slope
Sat (27/05) | 27 May 2023 | PMH1 |  | 2nd lift wall cast
Sat (27/05) | 27 May 2023 | Zone 4 |  | No activity
Sat (27/05) | 27 May 2023 | Zone 3 |  | Changing from crusher to another accessory to grab the retaining wall pieces
Sat (27/05) | 27 May 2023 | Zone 3 |  | Hacking works for retaining wall and footing connection stopped temporarily due to VM trigger
Sat (27/05) | 27 May 2023 | Exit 2 |  | Excavation to expose cables completed. To cast around 6.30pm
Sat (27/05) | 27 May 2023 | Zone 3 |  | Status of hacked centre median
Sat (27/05) | 27 May 2023 | DW15 |  | Trenchint ongoing. Depth at 17m
Sat (27/05) | 27 May 2023 | SW16 |  | 2nd bite excavation completed
Sat (27/05) | 27 May 2023 | DW15 |  | First bite excavation in progress
Sat (27/05) | 27 May 2023 | Zone 1 USD |  | 9m pipe laid. Casting in progress
Sat (27/05) | 27 May 2023 | PMH1 |  | Wall formwork dismantling
Sat (27/05) | 27 May 2023 | Zone 1 traffic island |  | To continue backfilling & premix laying, 7m
Sat (27/05) | 27 May 2023 | Zone 1 |  | 12m pipes laid (4way). Now backfilling
Sat (27/05) | 27 May 2023 | Zone 3 |  | WG excavating for 22kV pipe laying. If no utilities to undercross, target to lay 18m today
Sat (27/05) | 27 May 2023 | Zone 2 |  | 6m pipes laid. Casting ongoing
Sun (28/05) | 28 May 2023 | Zone 1 |  | Banner installation on noise barrier and bund wall installation along scupper drain
Sun (28/05) | 28 May 2023 | Exit 2 |  | Hardcore backfilling and levelling for parking platform
Sun (28/05) | 28 May 2023 | DW015 |  | Continue water stopper side (DW014) trimming @ 19.3m depth
Sun (28/05) | 28 May 2023 | Zone 1 USD |  | Casting completed
Sun (28/05) | 28 May 2023 | Zone 3 |  | 12m pipes laid
Sun (28/05) | 28 May 2023 | MH6-1 |  | 4th layer casting done
Sun (28/05) | 28 May 2023 | DW15 |  | Trimming for waterstop end plate removal
Sun (28/05) | 28 May 2023 | MH2-4 |  | Inclinometer pipe installed. Boring on going for waterstand pipe ( 14m/15m boring done)
Sun (28/05) | 28 May 2023 | Zone 1 traffic island |  | Works completed. Lane reopened
Sun (28/05) | 28 May 2023 | Zone 3 |  | No activity for the night
Sun (28/05) | 28 May 2023 | Zone 2 |  | No activity
Mon (29/05) | 29 May 2023 | Zone 3 P28-29 |  | Continue excavation for pipe laying
Mon (29/05) | 29 May 2023 | Zone 3 P31 |  | Backfilling ongoing
Mon (29/05) | 29 May 2023 | SW012 |  | Clayshock injection ongoing
Mon (29/05) | 29 May 2023 | DW015 |  | 2B & 3B lapping ongoing
Mon (29/05) | 29 May 2023 | Exit 3 | DW15 | Water stop installation at dw16 side
Mon (29/05) | 29 May 2023 | Zone 2 | NB footing-Phase 2 | 21m of noise barrier footing (To be cast today)
Mon (29/05) | 29 May 2023 | Zone 3 across road |  | WH laying pipe and rebar for haunch
Mon (29/05) | 29 May 2023 | BH-176 |  | Drilling works in progress, depth 40m
Mon (29/05) | 29 May 2023 | BH174 |  | Hand augering ongoing
Mon (29/05) | 29 May 2023 | ABH39-2 |  | Drilling ongoing, depth 37m
Mon (29/05) | 29 May 2023 | TMH-06 |  | Rebar installation ongoing for 1st lift wall
Mon (29/05) | 29 May 2023 | ABH38-1 |  | Manual trial trench
Mon (29/05) | 29 May 2023 | P32 to P33 |  | Duct laying for singtel pipe in progress. Target 18m laying today
Mon (29/05) | 29 May 2023 | Zone 2 | WG-SingTel | Excavation across Loyang Ave ongoing for 21way pipe laying
Mon (29/05) | 29 May 2023 | Zone 2 | Noise barrier | Horizontal pipe installation ongoing
Mon (29/05) | 29 May 2023 | PMH-1 |  | Formwork dismantling
Mon (29/05) | 29 May 2023 | Zone 1 |  | Excavation & shoring ongoing for pipe laying works
Mon (29/05) | 29 May 2023 | Zone 1 |  | DE160 & DE143 works
Mon (29/05) | 29 May 2023 | Zone 1 |  | WG - LV cable pipe laying works
Mon (29/05) | 29 May 2023 | Exit 3 |  | Prop installation ongoing for mockup for temp control. To cast soon
Mon (29/05) | 29 May 2023 | MH6-1 |  | Continue excavation to 5th layer
Mon (29/05) | 29 May 2023 | DW015 |  | Continue rebar lapping, preparing for next cage
Mon (29/05) | 29 May 2023 | 1st team |  | Premix removal & proceed with excavation, erss & steel deck installation. For power cables identification
Mon (29/05) | 29 May 2023 | 2nd team |  | Continue with 36w pipe excavation. First they’ll support the LP here
Tue (30/05) | 30 May 2023 | ULT6 |  | Cycle 2 loading at 100%
Tue (30/05) | 30 May 2023 | Exit 2 |  | DW053 ~ DW046 area soil backfill on going
Tue (30/05) | 30 May 2023 | SW010 |  | Clayshock injection completed
Tue (30/05) | 30 May 2023 | MH6-1 |  | LCH continue manual excavation and improve housekeeping around work area. Manpower -11
Tue (30/05) | 30 May 2023 | Loyang Way | opp 64+4 | Xenith team working here
Tue (30/05) | 30 May 2023 | ULT5 |  | Testing started this morning. Now applying load for 50% (1st cycle)
Tue (30/05) | 30 May 2023 | SW10 |  | Continue excavation
Tue (30/05) | 30 May 2023 | Zone 2 MH2-3 |  | LCH team is here to prepare work area
Tue (30/05) | 30 May 2023 | Zone 2 LVC |  | Continue noise barrier panel installation
Tue (30/05) | 30 May 2023 | DW-015 |  | All cages installed
Tue (30/05) | 30 May 2023 | Blk 275 |  | DE143 works ongoing
Tue (30/05) | 30 May 2023 | Zone 1 Loyang Rise |  | Bund wall installation and housekeeping
Tue (30/05) | 30 May 2023 | MH6-1 |  | Manual excavation to 5th layer
Tue (30/05) | 30 May 2023 | TMH-6 |  | First lift wall formwork closing in progress
Tue (30/05) | 30 May 2023 | Exit 1 |  | Status of excavation. Lean concrete for 2nd slope partially done
Tue (30/05) | 30 May 2023 | North ramp | N3-3 | Rebar cage lowered, pending concrete truck to arrive for casting
Tue (30/05) | 30 May 2023 | DW015 |  | Casting ongoing
Tue (30/05) | 30 May 2023 | Exit 1 |  | SW010, 02:40: Pre excavation started, 03:50: Pre excavation completed, 06:00: 1st bite excavation started
Tue (30/05) | 30 May 2023 | Zone 3 Gate 5 Loyang Lane |  | Dipcie team here for TT work
Tue (30/05) | 30 May 2023 | pipe laying ongoing, will cast tonight. Target cast 9 |  | 30pm. They’ll erect one noise balloon facing LVC
Tue (30/05) | 30 May 2023 | Casting completed at 7 |  | 30pm. Gate 6 alr closed
Tue (30/05) | 30 May 2023 | Zone 2 LA | bus only lane | Dipcie team will commence singtel pipe laying at lane 2 after last bus
Wed (31/05) | 31 May 2023 | MH6-1 |  | Pumping out water to continue excavation
Wed (31/05) | 31 May 2023 | BH178 |  | Hand auger in progress
Wed (31/05) | 31 May 2023 | BH176 |  | Drilling in progress, 52m, BH174: Drilling in progress, 33m, BH173: Drilling started, current depth at 9m, ABH38-1: Drilling started, current depth at 8m
Wed (31/05) | 31 May 2023 | Zone 2 near LVC linkway |  | Continue closing up the balance portion of NB panels
Wed (31/05) | 31 May 2023 | Zone 1 USD |  | Road cutting for next pipe laying section
Wed (31/05) | 31 May 2023 | Zone 1 Loyang Rise |  | Resume NB column installation. 1 TMA on site
Wed (31/05) | 31 May 2023 | North ramp N4-1 | 1.3D | Toe confirmed at 25.95m
Wed (31/05) | 31 May 2023 | Zone 2 LP193 |  | WG (D) trial trench for Singtel
Wed (31/05) | 31 May 2023 | MH6-1 |  | Excavation almost completed. To continue rebar and formwork today
Wed (31/05) | 31 May 2023 | MH6-1 |  | Rebar installation in progress
Wed (31/05) | 31 May 2023 | NB footing | phase 2 | 6nos cast today
Wed (31/05) | 31 May 2023 | North ramp, N2-1 |  | Preboring ongoing
Wed (31/05) | 31 May 2023 | TMH-6 |  | First lift wall cast
Wed (31/05) | 31 May 2023 | Gate 5 Loyang Lane |  | WG commence TT work, continuation from ytd night
Wed (31/05) | 31 May 2023 | Exit 2 | DW-040 | Continue fwk closing
Wed (31/05) | 31 May 2023 | ULT-6 |  | Loaded till 300% at cycle 3. Holding time 24hrs from 7pm
Wed (31/05) | 31 May 2023 | ULT-8 |  | Guide wall rebar & fwk inspected, pending concrete
Wed (31/05) | 31 May 2023 | casting completed at 8.50pm. Vol |  | 27.5m3
Thu (01/06) | 01 Jun 2023 | Zone 3 P33-34 |  | TT ongoing to locate JTC streetlight cables
Thu (01/06) | 01 Jun 2023 | P30 |  | Backfilling ongoing
Thu (01/06) | 01 Jun 2023 | P29 |  | Excavation ongoing
Thu (01/06) | 01 Jun 2023 | PMH1 |  | Top slab rebar in progress
Thu (01/06) | 01 Jun 2023 | North ramp P17 |  | RG inclinometer installation, IS21012
Thu (01/06) | 01 Jun 2023 | New Loyang Link LP4 |  | WG (D) to continue trial trench for Singtel
Thu (01/06) | 01 Jun 2023 | Zone 2 | near LVC linkway | Continue to close up the balance top NB panels
Thu (01/06) | 01 Jun 2023 | Exit 2 |  | Sppg onsite to check sptel alignment. Waiting for SPTel
Thu (01/06) | 01 Jun 2023 | ABH38-1 |  | Drilling/SPT ongoing, 26m, BH173: Drilling ongoing, 28m, BH174: Drilling ongoing, 33m, BH176: Depth at 57.6m. Pending confirmation depth
Thu (01/06) | 01 Jun 2023 | MH2-3 |  | No activity. Today only plan material delivery
Thu (01/06) | 01 Jun 2023 | P29 |  | Excavation in progress for power duct pipe laying. Plan to lay 12m
Thu (01/06) | 01 Jun 2023 | P30-31 |  | Singtel pipe laying. Plan to lay 18m
Thu (01/06) | 01 Jun 2023 | Loyang Ave LP119 |  | Rectification ongoing. Now waiting for premix
Thu (01/06) | 01 Jun 2023 | Zone 3 |  | Removal of centre median
Thu (01/06) | 01 Jun 2023 | LVC NB | phase 2 | Formwork closing for next section of NB footings
Thu (01/06) | 01 Jun 2023 | Zone 2 near Shell Station |  | WG (D) trial trench for NCE
Thu (01/06) | 01 Jun 2023 | PRD3 near bus depot |  | PUB contractor (Kingview) demobilising their materials
Thu (01/06) | 01 Jun 2023 | North ramp | N2-1 | Boring completed, depth 19.93m from TOC. Preparation for lowering of rebar cage ongoing
Thu (01/06) | 01 Jun 2023 | PMH1 |  | 2nd stage wall rebar in progress
Thu (01/06) | 01 Jun 2023 | Zone 1 USD |  | Excavation for 16way pipe laying
Thu (01/06) | 01 Jun 2023 | LP119 |  | Rectification completed. Lane reopened
Thu (01/06) | 01 Jun 2023 | P29-P31 |  | Works completed. Today power duct laid 12m, Singtel 18m
Thu (01/06) | 01 Jun 2023 | ULT7 |  | Premix hacking and clearing harcore for trial trench works
Thu (01/06) | 01 Jun 2023 | N2-1 |  | Rebar cage installation completed. Setting up works for casting completed. Concrete on the way
Thu (01/06) | 01 Jun 2023 | TMH-6 |  | First lift wall cast yesterday. Outer formwork dismantled
Thu (01/06) | 01 Jun 2023 | Zone 3 P34 |  | RW crushing ongoing
Fri (02/06) | 02 Jun 2023 | PMH1 |  | Continue top slab rebar tying
Fri (02/06) | 02 Jun 2023 | MH6-1 |  | 5th layer formwork dismantling
Fri (02/06) | 02 Jun 2023 | Zone 3 WG |  | No activity
Fri (02/06) | 02 Jun 2023 | ULT7 |  | Trial trench in progress
Fri (02/06) | 02 Jun 2023 | ULT8 |  | Guidewall formwork removal
Fri (02/06) | 02 Jun 2023 | Exit 1 |  | BH74: Manual trial trench, BH75: Manual TT, BH76: Manual TT, BH84: Manual TT
Fri (02/06) | 02 Jun 2023 | Exit 1 |  | KTC soil disposal to Changi
Fri (02/06) | 02 Jun 2023 | ULT6 |  | Currently loading at 350%
Fri (02/06) | 02 Jun 2023 | DW43 |  | First bite excavation in progress
Fri (02/06) | 02 Jun 2023 | DW43 |  | Trenching stopped. Koden test to be done. Mr Woo is currently looking into this issue
Sat (03/06) | 03 Jun 2023 | P30 |  | Excavation for sppg pipe laying
Sat (03/06) | 03 Jun 2023 | P29 |  | Excavation for singtel pipe laying
Sat (03/06) | 03 Jun 2023 | Zone 2 LVC |  | Fwk / access removal ongoing
Sat (03/06) | 03 Jun 2023 | Zone 2 North Ramp Piling | N3-2 | Boring started
Sat (03/06) | 03 Jun 2023 | Zone 2 PMH3 |  | Preparing to commence cement patch-up
Sat (03/06) | 03 Jun 2023 | Z1 Loy Ave LP204/A |  | PGas has started work along fast lane
Sat (03/06) | 03 Jun 2023 | Zone 1 USD |  | No work for 36W
Sat (03/06) | 03 Jun 2023 | PMH1 |  | 2nd lift wall & top slab rebar work ongoing
Sat (03/06) | 03 Jun 2023 | Zone 1 |  | Noise barrier panels installation ongoing
Sat (03/06) | 03 Jun 2023 | Zone 2 NLL after Loyang Rise |  | TT work for singtel ongoing
Sat (03/06) | 03 Jun 2023 | ATT-Z3-50 |  | TT for dwall, found LV cables, singtel haunch
Sat (03/06) | 03 Jun 2023 | ULT-4 |  | Preparation work ongoing
Sat (03/06) | 03 Jun 2023 | North Ramp Bored Pile | N3-2 | Toe Level confirmed 22.2m from TOC, preparing for casting
Sat (03/06) | 03 Jun 2023 | Zone 2 |  | Noise barrier footing casting ongoing
Sat (03/06) | 03 Jun 2023 | MH2-3 and MH2-4 |  | No activity
Sat (03/06) | 03 Jun 2023 | DW45 |  | Hardcore levelling and platform preparation work in progress
Sat (03/06) | 03 Jun 2023 | DW043 |  | 16m depth excavation ongoing
Sat (03/06) | 03 Jun 2023 | ULT-7 |  | Rebar work for guidewall ongoing
Sat (03/06) | 03 Jun 2023 | P34 |  | Removal of centre median ongoing
Sat (03/06) | 03 Jun 2023 | Exit 1 |  | Slope excavation status
Sun (04/06) | 04 Jun 2023 | Zone 3 | Exit 1 | Slope face making ongoing. Target to lean concrete around 2pm
Sun (04/06) | 04 Jun 2023 | Zone 4 |  | DE143 working within their boundary
Sun (04/06) | 04 Jun 2023 | Zone 3 |  | LC doing LV cable retrival
Sun (04/06) | 04 Jun 2023 | Exit 2 | DW-43 | Continue lowering and installation of stopend plate in progress at DW-44 side
Sun (04/06) | 04 Jun 2023 | Zone 1 |  | No activity for noise barrier
Sun (04/06) | 04 Jun 2023 | Zone 1 |  | DE143 working within their boundary
Sun (04/06) | 04 Jun 2023 | Zone 1 | PMH-1 | 2nd lift wall rebar installation in progress. Target to inspect and cast tmr
Sun (04/06) | 04 Jun 2023 | Zone 1 | PMH-1 | 2nd lift wall continue rebar and Formwork installation
Sun (04/06) | 04 Jun 2023 | Zone 3 |  | Setting up of service crane completed
Sun (04/06) | 04 Jun 2023 | Zone 3 | Exit 1 | Lean concrete postpone to Monday due to rain
Sun (04/06) | 04 Jun 2023 | Exit 2 | DW-43 | Rebar cage 1a & 1b lowered. Lowering and lapping of rebar cage 2a ongoing
Sun (04/06) | 04 Jun 2023 | DW43 |  | Cage 3A/2A lapping completed
Sun (04/06) | 04 Jun 2023 | Exit 2 | DW-43 | Lowering of stop end plate in progress at DW-42 side
Sun (04/06) | 04 Jun 2023 | Exit 2 |  | Backfilling and levelling works for completed trial trench
Sun (04/06) | 04 Jun 2023 | Zone 3 |  | Setting up of service crane ongoing
Mon (05/06) | 05 Jun 2023 | Loyang Lane | outside Gate 5 | WG plan for SPPG pipe laying tonight
Mon (05/06) | 05 Jun 2023 | Zone 1 WG |  | Manually exposing the existing 66kV
Mon (05/06) | 05 Jun 2023 | DW16 |  | Manual TT on going for guide wall. Checking on Singtel cable
Mon (05/06) | 05 Jun 2023 | MH6-1 |  | Excavation continue for 6th layer
Mon (05/06) | 05 Jun 2023 | DW43 |  | Casting ongoing. Progressive vol: 85m3
Mon (05/06) | 05 Jun 2023 | Zone 2 TMH6 |  | Top slab & 2nd lift wall rebar tying & fwk making ongoing
Mon (05/06) | 05 Jun 2023 | MH2-3 |  | Status quo
Mon (05/06) | 05 Jun 2023 | MH2-4 |  | Status quo
Mon (05/06) | 05 Jun 2023 | MH2-5 |  | Materials on site
Mon (05/06) | 05 Jun 2023 | Zone 2 | Opp Old LVC Guardhouse | Erss & excavation for pipe laying works by Dipcie
Mon (05/06) | 05 Jun 2023 | Zone 2 | corner of NLL | Dipcie TT completed, shifting to second location after their break
Mon (05/06) | 05 Jun 2023 | Zone 2 North Ramp BP | N4-2 | Boring ongoing & soil disposal. Current depth 26.05m
Mon (05/06) | 05 Jun 2023 | PMH01 |  | Fwk closure ongoing, target to cast tonight
Mon (05/06) | 05 Jun 2023 | Zone 2 Noise barrier footing |  | Formwork closing ongoing
Mon (05/06) | 05 Jun 2023 | ULT8 |  | First bite excavation completed. BC cutter washing ongoing prior proceeding to 2nd bite
Mon (05/06) | 05 Jun 2023 | DW41 |  | First bite excavation in progress. Current depth 15m
Mon (05/06) | 05 Jun 2023 | Zone 2 |  | Dipcie (dayshift team) continue Singtel pipe laying, 6m. Thereafter proceed to haunching & backfilling. Target to complete ard 10pm
Mon (05/06) | 05 Jun 2023 | North ramp, N4-2 |  | Last load casting completed
Mon (05/06) | 05 Jun 2023 | PMH1 |  | Top slab plan for casting tonight
Mon (05/06) | 05 Jun 2023 | Zone 1 WG |  | Team 2 to expose the existing 66kV. Once fully exposed, SPPG will come down to inspect (date TBA)
Tue (06/06) | 06 Jun 2023 | MH2-3 |  | Hoarding shifting
Tue (06/06) | 06 Jun 2023 | MH2-4 |  | Status quo
Tue (06/06) | 06 Jun 2023 | MH2-5 |  | Status quo
Tue (06/06) | 06 Jun 2023 | Zone 2 North Ramp BP |  | HSL preparing for next pile, N3-1. Soil disposal & shifting of materials
Tue (06/06) | 06 Jun 2023 | Zone 1 |  | 66kV exposed
Tue (06/06) | 06 Jun 2023 | Zone 2 North Ramp BP | N3-1 | Boring commenced
Tue (06/06) | 06 Jun 2023 | Zone 1 |  | PMH-1 area no activity
Tue (06/06) | 06 Jun 2023 | MH6-1 |  | Excavation for 6th layer in progress
Tue (06/06) | 06 Jun 2023 | Zone 1 |  | Levelling in progress for lean concrete works (ecm holding tank). Concrete truck otw to site
Tue (06/06) | 06 Jun 2023 | 4 |  | 50PM
Tue (06/06) | 06 Jun 2023 | Zone 2 North Ramp BP | N3-1 | Boring works ongoing, current depth 13m. Casting works will be carried out tmr
Tue (06/06) | 06 Jun 2023 | DW41 |  | 2nd bite excavation in progress
Tue (06/06) | 06 Jun 2023 | ULT-8 |  | Final koden test in progress
Wed (07/06) | 07 Jun 2023 | Hi-tech-Trial Trench | ATT-Z3-52 | Premix hacking ongoing
Wed (07/06) | 07 Jun 2023 | Zone 1 USD |  | SPPG officer (Victor) came down to inspect the previous exposed 66kV & confirmed not in service. Spiking might be arranged for this week
Wed (07/06) | 07 Jun 2023 | Zone 1 Noise Barrier |  | Pending ibeam & panel installation
Wed (07/06) | 07 Jun 2023 | Zone 3 |  | Bentonite piping connection from Exit 2 to ULT7 ongoing. Slope to be done at hump area for BC cutter to move over hump
Wed (07/06) | 07 Jun 2023 | North ramp | N3-1 | Toe Level confirmed at 22.15m from Toc. Lowering of rebar cages in progress
Wed (07/06) | 07 Jun 2023 | Exit 1 |  | Plan to lean concrete today. Tmr do 2nd layer of subsoil drain
Wed (07/06) | 07 Jun 2023 | DW41 |  | Rebar cage installation in progress
Wed (07/06) | 07 Jun 2023 | MH2-3 |  | Status quo
Wed (07/06) | 07 Jun 2023 | MH2-4 |  | Status quo
Wed (07/06) | 07 Jun 2023 | MH2-5 |  | Status quo
Wed (07/06) | 07 Jun 2023 | BH173 |  | Started on 30.05.2023 and reached 54m
Wed (07/06) | 07 Jun 2023 | BH174 |  | Started on 29.05.2023 and reached 61.5m depth
Wed (07/06) | 07 Jun 2023 | BH178 |  | Packer test ongoing
Wed (07/06) | 07 Jun 2023 | Zone 3 |  | WG housekeeping ongoing
Wed (07/06) | 07 Jun 2023 | TMH6 area |  | Housekeeping in progress
Wed (07/06) | 07 Jun 2023 | MH6-1 |  | Continue excavation for 6th layer. Almost completed
Wed (07/06) | 07 Jun 2023 | DW41 |  | Continue lowering down water stop end plate and lapping
Wed (07/06) | 07 Jun 2023 | DW41 |  | Desanding ongoing
Wed (07/06) | 07 Jun 2023 | ULT8 casting completed. Total vol |  | 75m3
Wed (07/06) | 07 Jun 2023 | MH2-3 |  | Today LCH provided 3 subcon workers for material mobilization and preparation for shaft work. Tomorrow to start
Wed (07/06) | 07 Jun 2023 | N2-3 |  | Casing installed. Boring to continue tomorrow
Wed (07/06) | 07 Jun 2023 | MH6-1 |  | Started BRC installation. Tonight to cast
Wed (07/06) | 07 Jun 2023 | DW41 |  | Water stop installation in progress
Thu (08/06) | 08 Jun 2023 | Zone 2 BP | N2-3 | Boring ongoing, 19m depth. This is last pile
Thu (08/06) | 08 Jun 2023 | Zone 2 | next to PD office | Shifting of materials ongoing by WH for South Ramp works
Thu (08/06) | 08 Jun 2023 | Noise barrier footing | Phase 2 | Formwork dismantling in progress and will cast 4nos of footings today
Thu (08/06) | 08 Jun 2023 | PMH1 |  | Preparation for confined space access, documentation submission to WH ongoing
Thu (08/06) | 08 Jun 2023 | ABH38-3 |  | Preparation to start SI work
Thu (08/06) | 08 Jun 2023 | ATT-Z3-53 | PTD691 | Manual TT ongoing to locate EHV cables
Thu (08/06) | 08 Jun 2023 | TMH-6 |  | Rebar & Formwork installation for MH neck cast and Pipe laying for telco duct in progress
Thu (08/06) | 08 Jun 2023 | MH6-1 |  | Re-inspection was done. Casting ongoing
Thu (08/06) | 08 Jun 2023 | DW41 |  | Rebar cage lapping in progress
Thu (08/06) | 08 Jun 2023 | Zone 2 | facing Old LVC Guardhouse | Premix compaction work ongoing by WG
Thu (08/06) | 08 Jun 2023 | ULT-7 |  | Boring ongoing, 10.5m depth
Thu (08/06) | 08 Jun 2023 | Zone 3 P30 |  | Premix laying / compaction ongoing
Thu (08/06) | 08 Jun 2023 | Zone 1 WG |  | 2 teams tonight at PMH1 area. 1 team will continue pipe laying (36way) to connect to PMH1, 1 team will continue excavation for pipe laying (36way). Now setting up ongoing, TMA on site
Thu (08/06) | 08 Jun 2023 | Exit 2 DW041 |  | Casting ongoing
Thu (08/06) | 08 Jun 2023 | Zone 3 | LVC Bin Centre | WH preparation to continue noise barrier footing work
Thu (08/06) | 08 Jun 2023 | TMH6 |  | Fwk removal ongoing
Thu (08/06) | 08 Jun 2023 | next to TMH6 |  | KTC backfilling / levelling work ongoing
Fri (09/06) | 09 Jun 2023 | Near exit 3 |  | Hi-Tech clearing debris prior to trial trench works
Fri (09/06) | 09 Jun 2023 | PDR3 junction near bus lane side table |  | Depcie team 1 preparation for excavation for singtel pipe laying
Fri (09/06) | 09 Jun 2023 | MT4 |  | Open pit manual excavation for mandrel test continue
Fri (09/06) | 09 Jun 2023 | ULT-7 |  | Set up platform for rebar cage lowering down
Fri (09/06) | 09 Jun 2023 | Zone 1 team 1 |  | 9m USD to cast tonight
Fri (09/06) | 09 Jun 2023 | Zone 1 Team 2 |  | To continue excavation here tonight for 22kV pipe laying. Water pumping in progress
Fri (09/06) | 09 Jun 2023 | PMH1 |  | Erss removal ongoing
Fri (09/06) | 09 Jun 2023 | ULT7 |  | Noise ballon set up for casting
Fri (09/06) | 09 Jun 2023 | DW45 |  | 1st bite excavation in progress. Current depth 4.8m
Fri (09/06) | 09 Jun 2023 | PRD3 sidetable |  | Cable pull pit, MT4 manual excavation in progress. Slight revision in the sequence as MT7 location is currently occupied with the Singtel pipe laying works (bus-only lane sidetable)
Fri (09/06) | 09 Jun 2023 | Dwall 16 |  | Guidewall rebar installation works in progress. Target to cast tonight
Fri (09/06) | 09 Jun 2023 | Zone 1 WG |  | Team 1 pipe laying in progress (6m)
Fri (09/06) | 09 Jun 2023 | WG Team 2 |  | Excavation & shoring installation ongoing
Fri (09/06) | 09 Jun 2023 | BH178 |  | Current depth at 56m. Drilling ongoing
Fri (09/06) | 09 Jun 2023 | TMH6 |  | Formwork installation for the MH neck. Target to cast today
Fri (09/06) | 09 Jun 2023 | Zone 1 |  | PMH1 Formwork removal & Shoring installation for connection pipe laying works
Fri (09/06) | 09 Jun 2023 | Zone 1 |  | 9m of pipe laying target to cast today
Fri (09/06) | 09 Jun 2023 | DW16 |  | Balance end formwork to close. Will cast tonight
Fri (09/06) | 09 Jun 2023 | ULT7 |  | All.cage installed. Preparation to install Tremie pipes
Fri (09/06) | 09 Jun 2023 | Exit 1 |  | Fabrication of end plates. No other activity
Fri (09/06) | 09 Jun 2023 | BH178 |  | Current depth at 52.7m. Pending confirmation
Fri (09/06) | 09 Jun 2023 | ABH38-3 |  | In progress, 8m
Sat (10/06) | 10 Jun 2023 | Zone 1 Loyang Rise |  | Guardrail installation for NB works
Sat (10/06) | 10 Jun 2023 | Zone 1 LA | to TPE | No other activity. LA (to CV): DE143 works and WG’s TMA on site
Sat (10/06) | 10 Jun 2023 | Zone 1 USD |  | Last night cast 9m. Now shoring removal ongoing
Sat (10/06) | 10 Jun 2023 | Zone 2 | opp old LVC guardhouse | WG(D) excavation for Singtel pipe laying
Sat (10/06) | 10 Jun 2023 | Zone 2 |  | MT7 open pit excavation on going
Sat (10/06) | 10 Jun 2023 | ULT9 |  | Trial trench in progress
Sat (10/06) | 10 Jun 2023 | BH74 |  | Drilling in progress
Sat (10/06) | 10 Jun 2023 | BH76 |  | Drilling in progress
Sat (10/06) | 10 Jun 2023 | Zone 3 |  | Centre median soil removal
Sat (10/06) | 10 Jun 2023 | ULT7 casting in progress |  | 27/72 m3
Sat (10/06) | 10 Jun 2023 | Zone 1 |  | USD casting on going, 2md truck
Sat (10/06) | 10 Jun 2023 | Zone 1 |  | USD 9m casting completed
Sat (10/06) | 10 Jun 2023 | Zone 1 Team 2 |  | Shoring works on going
Sat (10/06) | 10 Jun 2023 | Near Exit 3 |  | Hi-Tech completed trial trench. No services found
Sat (10/06) | 10 Jun 2023 | Zone 3 |  | Centre median hacking ongoing
Sat (10/06) | 10 Jun 2023 | Zone 3 |  | Hardcore disposal
Sat (10/06) | 10 Jun 2023 | Exit 1 |  | DW93-98 guidewall preparation ongoing
Sat (10/06) | 10 Jun 2023 | ULT 7 |  | Additional 5 m3 ordered. Total volume 77 m3
Sat (10/06) | 10 Jun 2023 | BH179 |  | Manual TT started
Sat (10/06) | 10 Jun 2023 | TMH6 |  | MH neck cast yesterday
Sat (10/06) | 10 Jun 2023 | ULT7 |  | Casting for last load, Total volume 77 m3
Sat (10/06) | 10 Jun 2023 | ULT7 |  | Casting completed
Sat (10/06) | 10 Jun 2023 | ULT9 |  | Manual TT in progress
Sat (10/06) | 10 Jun 2023 | Setting up noise ballon at exit 2 for night shift work |  | DW45 Guidewall BRC installation
Sat (10/06) | 10 Jun 2023 | Zone 1 |  | Team 1 TT to find 700mm dia water pipe. Premix cuting done
Sat (10/06) | 10 Jun 2023 | Zone 1 |  | 2nd team preparation to continue excavation work for USD
Sat (10/06) | 10 Jun 2023 | DW16 |  | Guidewall plan for casting today
Sat (10/06) | 10 Jun 2023 | BH180 |  | Manual TT in progress
Sat (10/06) | 10 Jun 2023 | BH172 |  | In progress, 8m
Sun (11/06) | 11 Jun 2023 | Exit 2 |  | DW45 guidewall formwork ongoing
Sun (11/06) | 11 Jun 2023 | Exit 1 |  | Clearing of muck pit
Sun (11/06) | 11 Jun 2023 | Exit 1 |  | BRC installation for DW94-98 in progress
Sun (11/06) | 11 Jun 2023 | Zone 2 |  | No activity
Sun (11/06) | 11 Jun 2023 | Exit 1 |  | Status of cut slope. No activity by KTC
Sun (11/06) | 11 Jun 2023 | Exit 1 |  | WHDA shifting soil to make space
Sun (11/06) | 11 Jun 2023 | Zone 1 |  | PMH1 Housekeeping ongoing
Sun (11/06) | 11 Jun 2023 | MH6-1 |  | Status of excavation
Sun (11/06) | 11 Jun 2023 | Zone 3 |  | Clearing of demolished centre median debris
Sun (11/06) | 11 Jun 2023 | Zone 3 |  | Leychoon cable recovery of OG box LV ongoing
Sun (11/06) | 11 Jun 2023 | Exit 2 |  | DW45 guidewall rebar installation status
Sun (11/06) | 11 Jun 2023 | ULT9 |  | Guidewall rebar installation in progress
Sun (11/06) | 11 Jun 2023 | Exit 1 |  | DW94-96 guidewall rebar installation in progress
Sun (11/06) | 11 Jun 2023 | Exit 3 |  | Access preparation still ongoing
Sun (11/06) | 11 Jun 2023 | Zone 3 |  | Endplate welding in progress
Sun (11/06) | 11 Jun 2023 | Zone 2 |  | No Activity
Sun (11/06) | 11 Jun 2023 | Zone 1 New Loyang Link |  | No activity
Sun (11/06) | 11 Jun 2023 | Zone 1 |  | ECM pond block laying ongoing
Sun (11/06) | 11 Jun 2023 | MT7 |  | Work stopped for the night. Area barricaded
Sun (11/06) | 11 Jun 2023 | MH6-1 |  | Confined space assessor checking the gas levels. Plan to excavate abt 600mm today
Mon (12/06) | 12 Jun 2023 | Exit 2 | DW094 to DW096 | Guide wall rebar works ongoing
Mon (12/06) | 12 Jun 2023 | Zone 2 Loy Ave Sidetable | next to bus depot | One team here at MT7, continue manual excavation for mandrel test
Mon (12/06) | 12 Jun 2023 | PMH1 to 36W |  | Continue pipe laying
Mon (12/06) | 12 Jun 2023 | BH175 |  | Hand augering
Mon (12/06) | 12 Jun 2023 | Bh172 |  | Depth at 32.5m
Mon (12/06) | 12 Jun 2023 | MH2-3 |  | Excavator inspection, tomorrow plan to start excavation here
Mon (12/06) | 12 Jun 2023 | Zone 2 |  | Depcie team 1 excavation for singtel pipe laying, 6m
Mon (12/06) | 12 Jun 2023 | N1 |  | Trial trench on going
Mon (12/06) | 12 Jun 2023 | Exit 3 |  | BH4 preparation works
Mon (12/06) | 12 Jun 2023 | Zone 1 |  | Water pumping and preparation for pipe laying
Mon (12/06) | 12 Jun 2023 | BH4 |  | Drilling/SPT at 14m
Mon (12/06) | 12 Jun 2023 | MH6-1 |  | 7th ring 1st lift preparation for casting. Concrete ordered, estimated to arrive on site around 730pm
Mon (12/06) | 12 Jun 2023 | DW45 |  | Guidewall formwork dismantling
Mon (12/06) | 12 Jun 2023 | Exit 2 |  | Slope protection casting
Mon (12/06) | 12 Jun 2023 | Zone 3 |  | Weng guan pipe laying for SPPG between P37-P38
Mon (12/06) | 12 Jun 2023 | DW94-96 |  | Some soil and hardcore cave in at the trench and need to remove before casting
Mon (12/06) | 12 Jun 2023 | Exit 2 | DW45 | Guidewall support / backfilling. They will also do some housekeeping & BC cutter maintenance
Tue (13/06) | 13 Jun 2023 | Zone 1 |  | LA (TPE bound) no activity. LA to CV bound: WG lane closure. TMA on site.m
Tue (13/06) | 13 Jun 2023 | MH6-1 |  | Excavation for 7th layer 2nd stages casting in progress. 7 layer casting will be in 4 stages. Manpower today- MH6-1 (9 workers) + MH2-3 ( 5 workers)
Tue (13/06) | 13 Jun 2023 | BH4 |  | Drilling and SPT at 20m depth
Tue (13/06) | 13 Jun 2023 | Zone 3 along loyang lane |  | TT to find water pipe and singtel cable alignment
Tue (13/06) | 13 Jun 2023 | Zone 3 along LVC |  | 18m NB footing approved for casting
Tue (13/06) | 13 Jun 2023 | Zone 1 |  | Current status of ECM holding pond
Tue (13/06) | 13 Jun 2023 | Near PMH1 |  | Today plan for 12m casting (pipe connection)
Tue (13/06) | 13 Jun 2023 | PMH1 |  | Housekeeping ongoing
Tue (13/06) | 13 Jun 2023 | Zone 1 |  | SPPG is here for the cable testing of decomm 66kV
Tue (13/06) | 13 Jun 2023 | MH2-3 |  | Excavation to start today and install 1st layer caison
Tue (13/06) | 13 Jun 2023 | BH172 |  | Depth 38m
Tue (13/06) | 13 Jun 2023 | ABH38-3 |  | Depth at 36.8m
Tue (13/06) | 13 Jun 2023 | Zone 1 | PMH1 to 36W | Fwk removal ongoing
Tue (13/06) | 13 Jun 2023 | MT3 |  | Removal of top premix layer ongoing
Tue (13/06) | 13 Jun 2023 | Exit 1 DW97-98 |  | Rebar tying for guidewall ongoing
Tue (13/06) | 13 Jun 2023 | TTSP-29 |  | TT located, found 700mm dia water pipe at 1.5m depth. will start to reinstate after dinner
Tue (13/06) | 13 Jun 2023 | ATT-WG-073 | D | TT completed, found HT cables & water pipe
Tue (13/06) | 13 Jun 2023 | ATT-WG-074 | D | TT completed, no utilities found & pipes laid
Tue (13/06) | 13 Jun 2023 | BH4 |  | Drilling and SPT continue
Tue (13/06) | 13 Jun 2023 | BH179 |  | TT ongoing
Tue (13/06) | 13 Jun 2023 | MH6-1 |  | 7th layer 2nd stage rebar work on going. Tonight to cast
Tue (13/06) | 13 Jun 2023 | BH4 |  | Depth at 37.5m. Pending confirmation depth
Tue (13/06) | 13 Jun 2023 | P38 |  | Power duct pipe laid, 16m. Backfilling in progress
Tue (13/06) | 13 Jun 2023 | MH2-3 |  | 1st caisson ring installed
Tue (13/06) | 13 Jun 2023 | Loyang Lane | LP4 | Continue singtel pipe laying work
Wed (14/06) | 14 Jun 2023 | BH04 |  | Drilling ongoing, current depth 39m
Wed (14/06) | 14 Jun 2023 | Loyang Way LP81 |  | Dipcie team continue with excavation & pipe laying
Wed (14/06) | 14 Jun 2023 | Loyang Lane LP5 |  | Dipcie team continue with excavation & pipe laying. Highlighted of the close proximity to gas during their TBM & on site
Wed (14/06) | 14 Jun 2023 | Near PMH1 |  | Backfilling in progress
Wed (14/06) | 14 Jun 2023 | Zone 1 LA - To TPE bound |  | No activity. To CV bound, WG TMA on site. DE143 works next to blk 275
Wed (14/06) | 14 Jun 2023 | MH1-2 |  | Today to start the hacking works prior to starting the trial trench
Wed (14/06) | 14 Jun 2023 | BH179 |  | Slab for 66Kv found at 1.5m depth. The hard soil hatch in red they will do manual excavation instead of using hand held tools
Wed (14/06) | 14 Jun 2023 | Exit 3 |  | USD power 6m laid today. Tomorrow to cast
Wed (14/06) | 14 Jun 2023 | MH2-3 |  | Lean concrete on the surface of shaft completed. Barricaded to install tomorrow once concrete hardened
Wed (14/06) | 14 Jun 2023 | Next to PMH12 |  | Continue power duct pipe laying by Wee Guan
Wed (14/06) | 14 Jun 2023 | MH6-1 |  | Pumping out water for formwork removal. Today to continue 7th layer 3rd stage excavation
Wed (14/06) | 14 Jun 2023 | LP202 |  | Lane cutting completed, proceed with excavation & pipe laying. Last 12m
Thu (15/06) | 15 Jun 2023 | Zone 1 |  | MT3 manual excavation on going
Thu (15/06) | 15 Jun 2023 | Zone 1 |  | MT3-A, preparation for premix removal using reaper hook
Thu (15/06) | 15 Jun 2023 | Zone 1 |  | MT1 premix cutting on going for excavation
Thu (15/06) | 15 Jun 2023 | MT3 |  | Manual excavation continue
Thu (15/06) | 15 Jun 2023 | Zone 3 |  | Excavation ongoing for horizontal steel plate laying for utility protection
Thu (15/06) | 15 Jun 2023 | Dw045 |  | End plate removal ongoing
Thu (15/06) | 15 Jun 2023 | MH2-3 |  | Current status. Preparation for access ladder installation
Thu (15/06) | 15 Jun 2023 | BH171 |  | Preparation to start SI work
Thu (15/06) | 15 Jun 2023 | BH178 |  | Current depth 48m, Packer test ongoing
Thu (15/06) | 15 Jun 2023 | BH180 |  | Manual TT ongoing
Thu (15/06) | 15 Jun 2023 | Zone 2 |  | Trenching and shoring ongoing for SingTel pipe laying
Thu (15/06) | 15 Jun 2023 | Zone 1 |  | HSL unloading works in progress
Thu (15/06) | 15 Jun 2023 | PMH1 |  | Excavation and shoring for mandrel test area ongoing
Thu (15/06) | 15 Jun 2023 | MH2-3 |  | Barricade installation around shaft. Tomorrow to continue excavation
Thu (15/06) | 15 Jun 2023 | DW45 |  | Desanding completed. Preparation to install waterstop
Thu (15/06) | 15 Jun 2023 | Exit 1 |  | DW99 casting completed. Excess concrete removal in progress
Thu (15/06) | 15 Jun 2023 | Exit 1 |  | Guidewall for DW 108-109 rebar installation in progress
Fri (16/06) | 16 Jun 2023 | MH2-3 |  | Preparation to excavate for 3rd layer
Fri (16/06) | 16 Jun 2023 | Zone 1 |  | Lane closing to continue open pit excavation, MH3-A and MH3-B
Fri (16/06) | 16 Jun 2023 | Team 2 |  | Excavation for MT3-A
Fri (16/06) | 16 Jun 2023 | JTC Blk 2 |  | Tack welding for steel plates ongoing. Plan to backfill today
Fri (16/06) | 16 Jun 2023 | Zone 3 |  | HSL demobbing materials
Fri (16/06) | 16 Jun 2023 | Zone 3 |  | End plate welding ongoing
Fri (16/06) | 16 Jun 2023 | Zone 3 |  | Clearing of centre median debris in progress
Fri (16/06) | 16 Jun 2023 | Zone 2 P20-P21 |  | Manual excavation for singtel pipe laying
Fri (16/06) | 16 Jun 2023 | PMH-1 |  | Sump pit making ongoing
Fri (16/06) | 16 Jun 2023 | Zone 1 |  | HSL unloading works ongoing
Fri (16/06) | 16 Jun 2023 | Zone 1 | NLL | Excavation works ongoing for 8m pipe laying for SingTel and SPTel
Fri (16/06) | 16 Jun 2023 | DW45 |  | Casting continue, 119 m3/144.5 m3
Fri (16/06) | 16 Jun 2023 | DW45 |  | Waterstop installation in progress
Fri (16/06) | 16 Jun 2023 | Noise barrier | Phase 2 | Ongoing horizontal pipes installation
Fri (16/06) | 16 Jun 2023 | MH2-3 |  | Side Trimming in progress for 3rd layer
Fri (16/06) | 16 Jun 2023 | JTC BLK 2 |  | KTC backfilling in progress. Utility markers have also been placed
Fri (16/06) | 16 Jun 2023 | North ramp | N3 Area | Instrumentations installation completed
Fri (16/06) | 16 Jun 2023 | DW45 |  | Cage 1A and 1B installed. Now preparing to install cage 2B
Fri (16/06) | 16 Jun 2023 | Zone 1 | NLL | 8m pipe laying for SingTel and SPTel completed. Reinstatement ongoing
Fri (16/06) | 16 Jun 2023 | Zone 1 | MH1-2 | Manual trial trench in progress
Fri (16/06) | 16 Jun 2023 | Zone 1 |  | HSL continue unloading materials
Fri (16/06) | 16 Jun 2023 | PMH-1 |  | Current status of sump pit
Fri (16/06) | 16 Jun 2023 | Zone 1 | PMH area | Housekeeping ongoing
Fri (16/06) | 16 Jun 2023 | MT1 |  | Excavation completed. Steel deck reinstate
Fri (16/06) | 16 Jun 2023 | MT3-A |  | Excavation 75% completed. Area covered with steel deck (at the island)
Fri (16/06) | 16 Jun 2023 | MT3 |  | Excavation completed. Covered with steel deck
Fri (16/06) | 16 Jun 2023 | DW45 |  | 4/6 rebar cages installed
Fri (16/06) | 16 Jun 2023 | DW45 |  | Casting in started
Fri (16/06) | 16 Jun 2023 | ULT9 |  | BC cutter maintenance on going
Fri (16/06) | 16 Jun 2023 | Exit 1 |  | DW104 and DW105 guidewall rebar works on going
Fri (16/06) | 16 Jun 2023 | Exit 3 | Power USD | 6m duct cast yesterday. Formwork dismantling and 6m pipe laying ongoing
Fri (16/06) | 16 Jun 2023 | Noise barrier | Phase 2 | As of now, 24nos of columns installed. Preparation works to start horizontal pipe installation for panel
Fri (16/06) | 16 Jun 2023 | JTC BLK4 near Pier34 |  | 3nos. Unknown LV cables found. Excavation for new ecm pond ongoing
Fri (16/06) | 16 Jun 2023 | BH 163 |  | Hand augering in progress
Sat (17/06) | 17 Jun 2023 | Zone 3 |  | Casting of centre median just started
Sat (17/06) | 17 Jun 2023 | Zone 1 MT1 |  | Preparing rope installation for madrel test
Sat (17/06) | 17 Jun 2023 | Zone 1 |  | MT3-B manual excavation continue
Sat (17/06) | 17 Jun 2023 | Zone 3 CCE |  | BH41 TT started
Sat (17/06) | 17 Jun 2023 | Zone 3 |  | WG using handheld breaker to remove concrete spilled from the guidewall. Pipe laying corridor 600mm away from Dwall
Sat (17/06) | 17 Jun 2023 | Exit 1 |  | DW104 guidewall to cast today
Sat (17/06) | 17 Jun 2023 | Exit 1 |  | DW108-109 cast yesterday. To continue with DW110 after KTC removes the soil stockpile
Sat (17/06) | 17 Jun 2023 | Exit 1 |  | KTC soil removal ongoing
Sat (17/06) | 17 Jun 2023 | Zone 3 |  | BH52 debris removal ongoing. Utilities such as gas pipe and HV slab has been marked out onsite
Sat (17/06) | 17 Jun 2023 | JTC BLK2 |  | KTC backfilling the area for guidewall works
Sat (17/06) | 17 Jun 2023 | Zone 1 |  | MT1 to MT2, rope set up for mandrel test completed. Now closing back steel deck
Sat (17/06) | 17 Jun 2023 | DW45 |  | Casting completed. Total volume 144.5m3
Sat (17/06) | 17 Jun 2023 | ULT10 |  | 1st bite trenching on going, depth at 35.4m
Sat (17/06) | 17 Jun 2023 | Exit 1 |  | DW04 guidewall rebar completed. Installation of spacer bar for formwork closing
Sat (17/06) | 17 Jun 2023 | Team 2 |  | Found HT cable at 1.1m depth. Not feasible to put manhole here
Sat (17/06) | 17 Jun 2023 | Exit 3 |  | JTC tree removal ongoing
Sat (17/06) | 17 Jun 2023 | Zone 1 |  | MT3-B manual excavation on going
Sat (17/06) | 17 Jun 2023 | Loyang avenue Zone 2 P20-P21 |  | Manual excavation for singtel pipe laying continue
Sat (17/06) | 17 Jun 2023 | Zone 1 |  | PMH1 neck just cast
Sat (17/06) | 17 Jun 2023 | Zone 1 |  | Mandrel test pulling pit trial trench ongoing. PTD 736 not onsite. WG is checking now
Sat (17/06) | 17 Jun 2023 | Zone 1 NLL junction |  | WG backfilling trial trench
Sat (17/06) | 17 Jun 2023 | Zone 1 |  | Housekeeping ongoing. To reopen lane
Sat (17/06) | 17 Jun 2023 | JTC BLK2 |  | Status of backfilling
Sat (17/06) | 17 Jun 2023 | DW16 |  | To Pre-excavation done during dayshift, backfilling will be done tonight
Sat (17/06) | 17 Jun 2023 | ULT9 |  | 1st bite trenching resume, 39.3m depth now
Sat (17/06) | 17 Jun 2023 | Exit 1 |  | DW110 guidewall rebar works on going
Sun (18/06) | 18 Jun 2023 | LVC | Phase 2 | Noise barrier panel installation in progress
Sun (18/06) | 18 Jun 2023 | Exit 2 |  | Manual trial trench ongoing to locate SPTel
Sun (18/06) | 18 Jun 2023 | ULT-9 |  | Excavation ongoing for 1st bite, current depth 46m
Sun (18/06) | 18 Jun 2023 | Exit 1 |  | Guidewall for dw110 cast completed by nightshift team
Sun (18/06) | 18 Jun 2023 | Zone 4 |  | DE143 working within their hoarded boundary
Sun (18/06) | 18 Jun 2023 | Zone 1 |  | No activity
Sun (18/06) | 18 Jun 2023 | Zone 1 |  | No activity by WG
Sun (18/06) | 18 Jun 2023 | ULT9 |  | Excavation continue. Depth at 40.8m
Sun (18/06) | 18 Jun 2023 | Zone 1 |  | MT2 to PMH01, rope setting up for mandrel test
Sun (18/06) | 18 Jun 2023 | Zone 2 |  | P20-P21 manual excavation for singtel pipe laying
Sun (18/06) | 18 Jun 2023 | ULT9 |  | BC cutter teeth maintenance
Sun (18/06) | 18 Jun 2023 | Exit 1 |  | DW110 rebar completed. Formwork closing in progress
Sun (18/06) | 18 Jun 2023 | LVC | Phase 2 | Continue of Noise barrier panel installation
Sun (18/06) | 18 Jun 2023 | MH6-1 |  | Work stopped for the day, housekeeping ongoing. Tmr to continue with 7th ring wall phase 2, bottom part manual excavation
Sun (18/06) | 18 Jun 2023 | ABH-50 |  | Manual TT work
Sun (18/06) | 18 Jun 2023 | ABH-52 |  | Manual TT work
Sun (18/06) | 18 Jun 2023 | ULT-9 |  | Excavation ongoing for 1st bite, current depth 48.5m
Sun (18/06) | 18 Jun 2023 | ULT9 |  | Excavation continue, current depth at 44m
Mon (19/06) | 19 Jun 2023 | Zone 2 near exit 3 |  | Selvam discussing to wee guan regarding installation of PVC at bend area
Mon (19/06) | 19 Jun 2023 | Zone 3 |  | WG using handheld breaker for pipe laying corridor near guidewall. Pipe laying at 600mm depth
Mon (19/06) | 19 Jun 2023 | Zone 3 CCE |  | BH41 TT completed yesterday. BH40 TT ongoing
Mon (19/06) | 19 Jun 2023 | Zone 2 |  | USD Power madrel test on going. PMH3-4 completed. PMH4-5 on going
Mon (19/06) | 19 Jun 2023 | Zone 1 |  | PMH1 housekeeping only
Mon (19/06) | 19 Jun 2023 | Exit 3 |  | Dwall 16 1st bite trenching started
Mon (19/06) | 19 Jun 2023 | DW16 |  | Depth now at 19.5m
Mon (19/06) | 19 Jun 2023 | Mh6-1 |  | 7th layer rebar installed. Still plan to cast today. RFI raised before closing formwork
Mon (19/06) | 19 Jun 2023 | ULT9 |  | Desanding completed. Now final koden test
Mon (19/06) | 19 Jun 2023 | MH6-1 |  | 7th layer 4th casting in progress, almost completed. Nexg stage will be base slab casting
Mon (19/06) | 19 Jun 2023 | Loyang Avenue/Pasir Ris Dr 3 | Team1 | Preparation for Rope set up from PMH01 to MT3(A) for Mandrel test
Tue (20/06) | 20 Jun 2023 | ABH50 |  | Preparation to start drilling
Tue (20/06) | 20 Jun 2023 | Zone 2 NR |  | Preparing for mandrel test from PMH5 to PMH6
Tue (20/06) | 20 Jun 2023 | ULT9 |  | Rebar cage installed. Now fixing cables for bidirectional test
Tue (20/06) | 20 Jun 2023 | Zone 2 South Ramp |  | No activity
Tue (20/06) | 20 Jun 2023 | MH1-2 |  | Manual TT ongoing, PTD #725 on site
Tue (20/06) | 20 Jun 2023 | NLL LP3 |  | TT for LV mandrel test preparation ongoing, setting up camera #17. PTD 736 on site
Tue (20/06) | 20 Jun 2023 | Exit 1 |  | Excavation for Guidewall of panel DW101
Tue (20/06) | 20 Jun 2023 | PMH1 |  | Housekeeping & reinstatement work
Tue (20/06) | 20 Jun 2023 | DW16 |  | Flange welding. 2nd bite completed
Tue (20/06) | 20 Jun 2023 | MH6-1 |  | Access ladder installation to final level. Excavation for base slab yet to commence. PTD yet to apply
Tue (20/06) | 20 Jun 2023 | Zone 3 JTC area |  | Backfilling for Dwall working platform levelling. 5pm plan for NDT
Tue (20/06) | 20 Jun 2023 | BH-179 |  | 1st packer test ongoing for depth 41.36m ~ 46.36m
Tue (20/06) | 20 Jun 2023 | BH180 |  | Hand augering ongoing
Tue (20/06) | 20 Jun 2023 | Noise barrier | Phase 2 | Panels installation in progress
Tue (20/06) | 20 Jun 2023 | MH2-3 |  | 4th layer trimming completed. Preparation to lower BRC
Tue (20/06) | 20 Jun 2023 | BH-171 |  | Drilling ongoing, 57m
Tue (20/06) | 20 Jun 2023 | PMH1 |  | Patching works completed. Housekeeping ongoing
Tue (20/06) | 20 Jun 2023 | Zone 2 | North ramp | Preparation for mandrel test for PMH-7 to PMH-8
Tue (20/06) | 20 Jun 2023 | Exit 3 | WG | Power duct pipe laying works in progress
Tue (20/06) | 20 Jun 2023 | ULT9 |  | 6/11 truck on going
Tue (20/06) | 20 Jun 2023 | DW16 |  | End plate removal prior to desanding
Tue (20/06) | 20 Jun 2023 | Exit 3 |  | USD power pipe laying by wee guan, 16m. To cast tomorrow
Tue (20/06) | 20 Jun 2023 | MH 2-3 |  | Rebar works for 4th layer caison. Work till 7pm
Tue (20/06) | 20 Jun 2023 | Exit 2 |  | Working platform for BC cutter parking done. Plan tk start tomorrow afternoon
Tue (20/06) | 20 Jun 2023 | DW16 |  | 2nd bite at 29m
Tue (20/06) | 20 Jun 2023 | Zone 2 NBs | along Blk 224 LVC | Current status of panel installation
Tue (20/06) | 20 Jun 2023 | MH6-1 |  | 7th layer formwork dismantling
Tue (20/06) | 20 Jun 2023 | MH2-3 |  | Preparing to start 4th layer excavation, bringing the mini from MH6-1
Tue (20/06) | 20 Jun 2023 | Exit 2 |  | TT to find sptel, EHV and HV cable for DW40
Wed (21/06) | 21 Jun 2023 | BH177 |  | To continue manual TT
Wed (21/06) | 21 Jun 2023 | Zone 3 P33 |  | WH continue TT for dwall works. PTD 713, Camera B
Wed (21/06) | 21 Jun 2023 | BH179 |  | In progress, 47m
Wed (21/06) | 21 Jun 2023 | LVC side phase 2 |  | Preparation to install i-beam using mobile crane
Wed (21/06) | 21 Jun 2023 | BH41 |  | Going to start drilling work
Wed (21/06) | 21 Jun 2023 | Exit 1 |  | Guidewall backfilling ongoing & reinstate access
Wed (21/06) | 21 Jun 2023 | Exit 1 |  | Guidewall construction ongoing
Wed (21/06) | 21 Jun 2023 | ULT-10 |  | Excavation resume
Wed (21/06) | 21 Jun 2023 | Exit 3 - DWall 16 |  | Waterstop end plate installation ongoing
Wed (21/06) | 21 Jun 2023 | ZONE 3 CCE |  | BH41 at 3m depth
Wed (21/06) | 21 Jun 2023 | MH2-3 |  | 4th layer rebar installation in progress. Target to cast in afternoon
Wed (21/06) | 21 Jun 2023 | Zone 1 near PMH1 |  | Preparing to reinstate kerb
Wed (21/06) | 21 Jun 2023 | MH1-2 |  | No activity. RES is on course & will be back tmr. Noted from WX that a stand-in RES was requested but no stand-in
Wed (21/06) | 21 Jun 2023 | Exit 3 DW16 |  | Rebar cage lapping ongoing
Wed (21/06) | 21 Jun 2023 | Zone 2 LVC |  | Ibeam installed
Wed (21/06) | 21 Jun 2023 | Zone 2 USD Power |  | Casting ongoing
Wed (21/06) | 21 Jun 2023 | Zone 1 MT2 to PMH1 |  | Mandrel test in progress. Tonight plan to complete PMH1 to MT3A mandrel test also
Wed (21/06) | 21 Jun 2023 | Zone 3 P27-P28 |  | Backfilling / compaction ongoing
Wed (21/06) | 21 Jun 2023 | Exit 2 |  | Laying of steel plates for BC movement from Exit 3
Thu (22/06) | 22 Jun 2023 | Exit 3 |  | Today will start excavation work for USD pipe laying along slope
Thu (22/06) | 22 Jun 2023 | LVC phase 2 NB |  | Horizontal pipe installation
Thu (22/06) | 22 Jun 2023 | Zone 3 Loyang Way LP25 -94) | ATT-WG(D | TT ongoing
Thu (22/06) | 22 Jun 2023 | TT-NW-Z4-001 |  | To locate NEWater pipe
Thu (22/06) | 22 Jun 2023 | MH2-3 |  | 4th layer cast yesterday, curing ongoing
Thu (22/06) | 22 Jun 2023 | Zone 1 near PMH1 |  | Preparing for kerb reinstatement works
Thu (22/06) | 22 Jun 2023 | MH1-2 |  | Manual TT in progress
Thu (22/06) | 22 Jun 2023 | Zone 3 |  | Backfilled slope where there are no concrete blocks looks sufficiently gentle. WHDA to provide ECB after compaction
Thu (22/06) | 22 Jun 2023 | Zone 3 BLK4 JTC |  | Trial trench every 6m ongoing. Thereafter to level down the whole area to match the pavement
Thu (22/06) | 22 Jun 2023 | Zone 3 JTC Blk 4 |  | Trial trench at this area done. KTC shifting the soil to be disposed
Thu (22/06) | 22 Jun 2023 | ULT10 |  | Platform already prepared. Preparing to lower down rebar cage
Thu (22/06) | 22 Jun 2023 | BH180 |  | Continue hand auger
Thu (22/06) | 22 Jun 2023 | Exit 3 |  | 6m excavated for SPPG pipe laying
Thu (22/06) | 22 Jun 2023 | Zone 2 LVC |  | NB footing hacking yet to start
Thu (22/06) | 22 Jun 2023 | MH2-5 |  | Just started hacking the footpath
Thu (22/06) | 22 Jun 2023 | Exit 2 |  | DW40 trenching in progress. Depth at 5m
Thu (22/06) | 22 Jun 2023 | Exit 1 |  | Excavation for DW91-DW93 completed. Tonight to install rebar and formwork
Thu (22/06) | 22 Jun 2023 | Loyang Lane LP3 |  | Commence work for SPPG 6way (3x3), target to lay 4m length
Thu (22/06) | 22 Jun 2023 | Loyang Lane LP5 |  | Setting up work to continue singtel 18way pipe laying
Thu (22/06) | 22 Jun 2023 | Exit 2 DW40 |  | Boring ongoing, currently 16m depth
Thu (22/06) | 22 Jun 2023 | Zone 2 |  | Excavation started for MX8 installation
Thu (22/06) | 22 Jun 2023 | PRD3 LP5 |  | Setting up for MT5
Thu (22/06) | 22 Jun 2023 | Exit 3 |  | Ryobi-G drilling for inclinometer and water stand pipe0
Fri (23/06) | 23 Jun 2023 | BH171 |  | Hand auger in progress
Fri (23/06) | 23 Jun 2023 | Zone 2 LVC |  | Continue NB panel installation
Fri (23/06) | 23 Jun 2023 | Exit 3 |  | LCH to continue pipe laying here for SPPG after the staircase (tomorrow to shift). Plan to lay across DW33 today if there's no overcast concrete at the panel. Target 15m
Fri (23/06) | 23 Jun 2023 | Zone 2 near PD office |  | Hardcore removal & excavation for South Ramp ECM construction
Fri (23/06) | 23 Jun 2023 | MH2-5 |  | No activity observed
Fri (23/06) | 23 Jun 2023 | Inside PMH1 |  | Housekeeping ongoing
Fri (23/06) | 23 Jun 2023 | Near PMH1 |  | Preparing to remove kerb formwork
Fri (23/06) | 23 Jun 2023 | Zone 2 PD Office |  | Lean concrete removal prior to excavation of ECM pond
Fri (23/06) | 23 Jun 2023 | MH1-2 |  | To continue trial trench. Now preparing to cut the existing pavement
Fri (23/06) | 23 Jun 2023 | Zone 3 JTC |  | Water valve has been barricaded from KTC backfilling area
Fri (23/06) | 23 Jun 2023 | Exit 3 |  | Backfilled and levelled for pipe laying
Fri (23/06) | 23 Jun 2023 | BH180 |  | Started drilling. Depth at 6m
Fri (23/06) | 23 Jun 2023 | BH171 |  | Continue hand auger
Fri (23/06) | 23 Jun 2023 | Zone 2 |  | NB panel panel installation continue
Fri (23/06) | 23 Jun 2023 | DW40 |  | Current depth 30.2m
Fri (23/06) | 23 Jun 2023 | PRD3 |  | Lane reopened
Fri (23/06) | 23 Jun 2023 | Zone 3 |  | Power duct pipe laying completed, 18m. Backfilling ongoing
Fri (23/06) | 23 Jun 2023 | DW40 |  | 3rd bite excavation reached 30.3m. Now c-lock welding in progress
Fri (23/06) | 23 Jun 2023 | DW040 |  | Trimming work ongoing on DW041 side
Fri (23/06) | 23 Jun 2023 | Loyang Lane LP5 |  | Pgas preparing to commence excavation for cap-off
Fri (23/06) | 23 Jun 2023 | MX8 |  | Tonight will start rebar tying & fwk closing to connect the two MH parts tgt & target to cast at 5am
Fri (23/06) | 23 Jun 2023 | MH6-1 |  | Continue manual excavation and provide support to sewer pipe. LCH total manpower -17
Fri (23/06) | 23 Jun 2023 | Near Exit 3 |  | RG inclinometer installation
Fri (23/06) | 23 Jun 2023 | ATT-WG-97 | D | Removing premix ongoing
Fri (23/06) | 23 Jun 2023 | MH2-1 |  | Location marked. Site preparation work to arrange by LCH
Sat (24/06) | 24 Jun 2023 | Zone 4 Loyang Way | corner of Hitachi Chemicals | Singtel is here
Sat (24/06) | 24 Jun 2023 | Zone 3 |  | ABH54 TT on going
Sat (24/06) | 24 Jun 2023 | Z4 Loy Way LP23 |  | Lane closure by Dipcie, to commence TT work. ATT-WG(D)-101
Sat (24/06) | 24 Jun 2023 | ABH41 |  | Drilling on going. Depth at 41m
Sat (24/06) | 24 Jun 2023 | Loy Way LP19 |  | Dipcie team commenced TT work. ATT-WG(D)-102
Sat (24/06) | 24 Jun 2023 | Exit 1 |  | Guidewall for DW92-DW93 guidewall to cast, concrete ordered
Sat (24/06) | 24 Jun 2023 | Zone 3 Loy Way | krislite bldg | Dosk (Powergrid) working here
Sat (24/06) | 24 Jun 2023 | Exit 3 |  | COL for dwall confirmed. Excavation on going for SPPG pipe laying
Sat (24/06) | 24 Jun 2023 | BH177 |  | Preparation for drilling and SPT
Sat (24/06) | 24 Jun 2023 | BH180 |  | Depth at 24m
Sat (24/06) | 24 Jun 2023 | LVC phase 2 |  | NB panel installation status. Plan to complete today
Sat (24/06) | 24 Jun 2023 | Zone 2 LVC side |  | Scaffold erection for installation of 6m temporary noise barrier
Sat (24/06) | 24 Jun 2023 | Zone 1 Loy Ave | to CV | Lane closure by WG
Sat (24/06) | 24 Jun 2023 | Zone 2 MH5-1 |  | Ryobi-G mobilising their materials for inclinometer and water stand pipe installation
Sat (24/06) | 24 Jun 2023 | Zone 2 PD office |  | ECM pond excavation on going
Sat (24/06) | 24 Jun 2023 | Zone 1 NLL |  | Excavation works for singtel pipe laying
Sat (24/06) | 24 Jun 2023 | Zone 2 MT5-MT3 | B | WG reported that pipe 6-7 experience some blockage while doing mandrel test & they’re going to attempt to solve this blockage. Will update further
Sat (24/06) | 24 Jun 2023 | Zone 2 Loy Ave Sidetable | Bus Depot | TT by dipcie for singtel
Sat (24/06) | 24 Jun 2023 | Zone 1 |  | MH1-2 no activity
Sat (24/06) | 24 Jun 2023 | Zone 1 |  | Side table backfilling works for reinstatement
Sat (24/06) | 24 Jun 2023 | ATT-WG-98 | D | No services found as of now
Sat (24/06) | 24 Jun 2023 | ATT-WG-100 | D | To commence TT
Sat (24/06) | 24 Jun 2023 | M6-1 |  | Excavation for base slab continue
Sat (24/06) | 24 Jun 2023 | Exit 3 |  | Excavation for SPPG pipe laying continue. Today plan to lay 15m
Sat (24/06) | 24 Jun 2023 | BH180 |  | Depth now at 28m
Sat (24/06) | 24 Jun 2023 | DW40 |  | 1st to 3rd bite cleaning completed as well as desanding
Sat (24/06) | 24 Jun 2023 | MH2-5 |  | Rebar cutting works from previous PCN
Sat (24/06) | 24 Jun 2023 | Zone 2 LVC side |  | Scaffold erection for temporary noise barrier status
Sat (24/06) | 24 Jun 2023 | DW40 |  | Rebar cages 2/6 installed. 3rd cage installation on going
Sat (24/06) | 24 Jun 2023 | JTC area blk 2 |  | Slope protection casting on going
Sat (24/06) | 24 Jun 2023 | completed at 06 |  | 20am
Sat (24/06) | 24 Jun 2023 | exit 3 |  | Shifting of scaffold tower for non-ppe access
Sat (24/06) | 24 Jun 2023 | Exit 2 | DW40 | Rebar cages fully installed, preparing for casting
Sat (24/06) | 24 Jun 2023 | MH6-1 |  | To continue excavate for base slab today
Sat (24/06) | 24 Jun 2023 | DW40 |  | Waterstop installed. Preparation for rebar cage installation
Sun (25/06) | 25 Jun 2023 | Exit 3, Gate 5 |  | Shifting of soil inspection tower and access
Sun (25/06) | 25 Jun 2023 | MH6-1 |  | Manual excavation for base slab
Sun (25/06) | 25 Jun 2023 | Near Exit 2 |  | Concrete barriers grinding ongoing for painting work
Sun (25/06) | 25 Jun 2023 | Zone 3 |  | No activity for DA team
Sun (25/06) | 25 Jun 2023 | Zone 4 | Lane 1 - Changi bound, near LP110 | WG lane closed for trial trench work
Sun (25/06) | 25 Jun 2023 | Zone 4 |  | DE143 working within their boundary
Sun (25/06) | 25 Jun 2023 | Zone 1 |  | No activity
Sun (25/06) | 25 Jun 2023 | Zone 2 LVC side |  | Scaffold erection for installation of 6m temporary noise barrier ongoing
Sun (25/06) | 25 Jun 2023 | Zone 2 Loy Ave Bus Only Lane | to CV | M&P ongoing
Sun (25/06) | 25 Jun 2023 | Zone 2 Bus Only Lane | to TPE | M&P started
Sun (25/06) | 25 Jun 2023 | Exit 3, Gate 5 |  | Shelter installation and signages works for entrance access area
Sun (25/06) | 25 Jun 2023 | MH6-1 |  | Continue manual excavation for base slab
Sun (25/06) | 25 Jun 2023 | Zone 2 LVC side |  | Current status for Scaffold erection. Monday will continue with the diagonal GI pipes installation
Sun (25/06) | 25 Jun 2023 | Zone 4 |  | Lane opened back
Mon (26/06) | 26 Jun 2023 | PRD3 |  | Premix removal & excavation for pipe rectification for Mandrel test
Mon (26/06) | 26 Jun 2023 | MH6-1 |  | Base slab lean concrete done. Tomorrow plan to cast base slab
Mon (26/06) | 26 Jun 2023 | Exit 3 |  | SPPG pipe laying 9m. Backfilling on going
Mon (26/06) | 26 Jun 2023 | MH2-6 |  | TT for instrumentation found slab at 800mm depth. Utility teams were informed
Mon (26/06) | 26 Jun 2023 | JTC/Mapletree- BH11 &12 |  | Machine set up for SI work
Mon (26/06) | 26 Jun 2023 | Bh177 |  | Depth now 26m
Mon (26/06) | 26 Jun 2023 | BH180 |  | Depth 39m
Mon (26/06) | 26 Jun 2023 | Zone 2 LVC side |  | 6m NB panel installation
Mon (26/06) | 26 Jun 2023 | MH2-5 |  | Excavation for 1st layer caison completed. Now preparing to install steel caison
Mon (26/06) | 26 Jun 2023 | MH5-1 |  | Hand augering for Inclinometer installation
Mon (26/06) | 26 Jun 2023 | Zone 2 |  | MX8 hacking to road level
Mon (26/06) | 26 Jun 2023 | MH2-6 |  | Ryobi G TT for inclinometer and water stand pipe
Mon (26/06) | 26 Jun 2023 | Zone 2 |  | Scaffold erection completed. Housekeeping ongoing
Mon (26/06) | 26 Jun 2023 | Zone 2 |  | NB panels installation done for the day
Mon (26/06) | 26 Jun 2023 | DW98 |  | First bite excavation around 19.9m now. BC cutter teeth rectification. Preparation for koden test
Mon (26/06) | 26 Jun 2023 | Loyang Way LP20S1 |  | WG plan for trial trench for 22kV tonight
Mon (26/06) | 26 Jun 2023 | Loyang Way near LP23 |  | Plan for TT for Singtel tonight
Mon (26/06) | 26 Jun 2023 | Loyang Way near LP118S1 |  | Demobilisation of excavator
Tue (27/06) | 27 Jun 2023 | PRD3 |  | Pipe rectification ongoing
Tue (27/06) | 27 Jun 2023 | MT5-MT3 | B | Completed
Tue (27/06) | 27 Jun 2023 | ST032 |  | Guidewall plan for casting during day shift
Tue (27/06) | 27 Jun 2023 | Exit 3 |  | Guidewall for DW33 hacking for SPPG pipe laying. Today DG will hack dwall until C.O.L
Tue (27/06) | 27 Jun 2023 | Exit 1 DW98 |  | 2nd bite excavation in progress. Currently at 11.9m
Tue (27/06) | 27 Jun 2023 | ATT-WG-105 | D | Completed. No other services found, only drain top at 0.3m
Tue (27/06) | 27 Jun 2023 | Another TT was done at zone 4 |  | ATT-WG(D)-106
Tue (27/06) | 27 Jun 2023 | MH2-3 |  | Mini excavator mobilise to expedite excavation works for 5th layer
Tue (27/06) | 27 Jun 2023 | LP20S1 |  | TT completed. Found 22kV and water pipe. Now pending backfilling & reinstatement works
Tue (27/06) | 27 Jun 2023 | Zone 2 |  | Singtep pipe laying connecting MX8 to complete today. Balance 5m
Tue (27/06) | 27 Jun 2023 | BH177 |  | Drilling ongoing, 37m
Tue (27/06) | 27 Jun 2023 | Zone 1 loyang avenue |  | PCN reinstatement by Wee guan
Tue (27/06) | 27 Jun 2023 | Zone 2 | South ramp | Drilling works ongoing for inclinometer installation
Tue (27/06) | 27 Jun 2023 | Jtc blk 2 |  | Guidewall for ST32 ready for inspection. Qps was called
Tue (27/06) | 27 Jun 2023 | Zone 2 LP193 |  | Excavation ongoing for MX4 installation tonight
Tue (27/06) | 27 Jun 2023 | PRD3 |  | No activity
Tue (27/06) | 27 Jun 2023 | Zone 1 USD |  | Preparation for backfilling
Wed (28/06) | 28 Jun 2023 | Zone 1 |  | Tonight to cast pavement, 3m3. Concrete already ordered. Highlighted to Wee guan team to install atleast noise curtain along the casting area since noise ballon is not feasible
Wed (28/06) | 28 Jun 2023 | Zone 4 |  | TT done. Found traffic light & water pipe
Wed (28/06) | 28 Jun 2023 | Exit 1 DW98 |  | Water stop endplate welding connection in progress
Wed (28/06) | 28 Jun 2023 | MH6-1 |  | Preparation of rebar for base slab
Wed (28/06) | 28 Jun 2023 | MH2-3 |  | Excavation on going to 5th layer
Wed (28/06) | 28 Jun 2023 | DW98 |  | Waiting for 1st truck. Total volume 88m3
Wed (28/06) | 28 Jun 2023 | Zone 3 loyang way |  | Lane closed for Trial trench
Wed (28/06) | 28 Jun 2023 | Zone 4 |  | Lane close towarda CV to do TT for singtel corridor
Wed (28/06) | 28 Jun 2023 | Zone 4 |  | EL working inside their boundary
Wed (28/06) | 28 Jun 2023 | Zone 3 loyang way near junction |  | Lane closed for sptel pipe laying
Wed (28/06) | 28 Jun 2023 | Zone 2 LVC |  | Today plan to install the temporary NB panels
Wed (28/06) | 28 Jun 2023 | Near MH5-1 |  | Drilling ongoing for inclinometer installation by RG
Wed (28/06) | 28 Jun 2023 | Zone 3 loyang lane at junction |  | Singtel pipe laying 4m crossing tonight
Wed (28/06) | 28 Jun 2023 | MX8 |  | Setting up work area for 18-way pipe laying today towards MH
Wed (28/06) | 28 Jun 2023 | BH177 |  | In progress. Current depth at 44.5m
Thu (29/06) | 29 Jun 2023 | Zone 3 loyang way |  | Lucky joint sptel pipe laying, 24m
Thu (29/06) | 29 Jun 2023 | Zone 4 |  | 2nd Trial trench location on going
Thu (29/06) | 29 Jun 2023 | DW98 |  | Casting completed. 85m3
Thu (29/06) | 29 Jun 2023 | Zone 4 |  | Lane opened
Thu (29/06) | 29 Jun 2023 | Exit 1 |  | DW091 guidewall casting in progress
Fri (30/06) | 30 Jun 2023 | BH50 |  | Drilling on going at 50m depth
Fri (30/06) | 30 Jun 2023 | Zone 3 JTC |  | Clearing of debris from perimeter drain ongoing
Fri (30/06) | 30 Jun 2023 | PRD3 |  | Reinstatement works at MT5 area by Wee Guan. TMA on site
Fri (30/06) | 30 Jun 2023 | PMH1 area |  | No activity. Pending turfing reinstatement
Fri (30/06) | 30 Jun 2023 | MH1-2 |  | Continue manual trial trench
Fri (30/06) | 30 Jun 2023 | Zone 1 |  | Monthly drone activity
Fri (30/06) | 30 Jun 2023 | Exit 1 |  | Weephole construction ongoing
Fri (30/06) | 30 Jun 2023 | Zone 2 LVC |  | After lunch planned for footing hacking. Have informed the team to barricade the area before start works
Fri (30/06) | 30 Jun 2023 | MH2-5 |  | No activity
Fri (30/06) | 30 Jun 2023 | Zone 3 |  | Manual excavation for SPTel pipe laying works in progress
Fri (30/06) | 30 Jun 2023 | Exit 3 |  | Drain hacking for SPPG pipe laying
Fri (30/06) | 30 Jun 2023 | Zone 3 BH40 |  | In progress, 31m
Fri (30/06) | 30 Jun 2023 | Exit 3 |  | SPPG Pipe laying crossing dwall on going. Dwall hacked to C.O.L. plan today 12m
Fri (30/06) | 30 Jun 2023 | BH177 |  | Drilling on going at 52.5m depth
Fri (30/06) | 30 Jun 2023 | DW108 |  | First bite started
Fri (30/06) | 30 Jun 2023 | MH2-6 |  | Drilling in progress for inclinometer and water stand pipe installation
Fri (30/06) | 30 Jun 2023 | Zone 4 |  | Eng Lam works ongoing
Fri (30/06) | 30 Jun 2023 | Zone 2 loyang avenue |  | Hacking works for singtel pipe laying , 6m
Fri (30/06) | 30 Jun 2023 | Zone 2 north ramp |  | SPPG on site to retrieve abandoned 66 cable
Fri (30/06) | 30 Jun 2023 | Zone 4 |  | Trial trench by Hi-Tech for water pipe
Fri (30/06) | 30 Jun 2023 | Zone 1 NLL |  | Singtel pipe laying to existing manhole. Today plan to complete
Fri (30/06) | 30 Jun 2023 | Zone 1 MH1-2 |  | Manual trial trench on going
Fri (30/06) | 30 Jun 2023 | Zone 1 |  | NB panel installation on going. 9m
Fri (30/06) | 30 Jun 2023 | PDR3 |  | MT4 backfilling and premix completed
Fri (30/06) | 30 Jun 2023 | Zone 3 |  | Manual excavation for sptel continue. Work till 8pm
Fri (30/06) | 30 Jun 2023 | Exit 3 |  | SPPG pipe laying done for the day, 12m
Fri (30/06) | 30 Jun 2023 | Zone 3 |  | JTC area hardcore backfilling for BC cutter platform
Fri (30/06) | 30 Jun 2023 | Zone 3 JTC area |  | Excavation for guidewall ST30 and 31 on going. Tonight rebar works
Fri (30/06) | 30 Jun 2023 | Exit 1 |  | DW108 trenching continue at 20m depth
Fri (30/06) | 30 Jun 2023 | DW30 & DW31 |  | Preparing for guidewall rebar work. Shifting of rebar in progress. DW29 & DW32 casting done previously
Fri (30/06) | 30 Jun 2023 | MH6-1 |  | Currently no activity
Fri (30/06) | 30 Jun 2023 | BH11 |  | Depth at 40m. Preparation for permeability test
Fri (30/06) | 30 Jun 2023 | MH2-3 |  | Excavation now at 5th layer. Plan for BRC installation today
Sat (01/07) | 01 Jul 2023 | MH6-1 |  | Base slab BRC works ongoing
Sat (01/07) | 01 Jul 2023 | BH11 |  | Drilling ongoing, 42.5m depth
Sat (01/07) | 01 Jul 2023 | Zone 3 |  | JTC area hardcore backfilling for BC cutter platform
Sat (01/07) | 01 Jul 2023 | Zone 3 JTC area |  | Formwork closing for guidewall ST30 and 31
Sat (01/07) | 01 Jul 2023 | ABH50 |  | Drilling ongoing, 48m depth
Sat (01/07) | 01 Jul 2023 | Zone 3 JTC Area |  | Soil levelling & kerb removal works
Sat (01/07) | 01 Jul 2023 | DW108 |  | 2nd bite excavation done. Flap welding ongoing
Sat (01/07) | 01 Jul 2023 | Zone 3 |  | Stop end plate welding works
Sat (01/07) | 01 Jul 2023 | BH-78A |  | Drilling ongoing, 14m
Sat (01/07) | 01 Jul 2023 | Zone 4 | TT-NW-Z4-004 | HiTech trial trench works to locate water pipe crossings
Sat (01/07) | 01 Jul 2023 | Zone 4 |  | DE143 working within their boundary
Sat (01/07) | 01 Jul 2023 | Zone 1 | PMH1 area | WG reinstatement works
Sat (01/07) | 01 Jul 2023 | Zone 1 | NLL | SingTel pipe laying works. Target to lay 8m
Sat (01/07) | 01 Jul 2023 | MH1-2 |  | LCH manual trial trench works ongoing
Sat (01/07) | 01 Jul 2023 | Zone 1 |  | Noise barrier panels installation
Sat (01/07) | 01 Jul 2023 | Zone 3 |  | SPTel pipe laying works in progress
Sat (01/07) | 01 Jul 2023 | Exit 3 |  | Excavation ongoing for SPPG pipe laying
Sat (01/07) | 01 Jul 2023 | MH2-3 |  | No activity. 5th Layer cast yesterday
Sat (01/07) | 01 Jul 2023 | Zone 2 |  | Premix removal ongoing for SingTel pipe laying (7.5m)
Sat (01/07) | 01 Jul 2023 | Exit 3 |  | SPPG pipe laying in progress (12m)
Sat (01/07) | 01 Jul 2023 | Zone 3 | infront bin center | WG trial trench works for SingTel pipe laying
Sat (01/07) | 01 Jul 2023 | BH-163 |  | Drilling works ongoing, depth 4m
Sat (01/07) | 01 Jul 2023 | BH-162 |  | Hand augering works
Sat (01/07) | 01 Jul 2023 | Zone 2 RG |  | Inclinometer installed, now ongoing drilling for water stand pipe installation
Sat (01/07) | 01 Jul 2023 | Zone 2 |  | Excavation works ongoing for SingTel pipe laying (7.5m)
Sat (01/07) | 01 Jul 2023 | Zone 1 | NLL | SingTel pipe laying works completed. 6m laid. Pending concrete to arrive
Sat (01/07) | 01 Jul 2023 | Zone 1 |  | Continue noise barrier panels installation
Sat (01/07) | 01 Jul 2023 | MH1-2 |  | LCH manual trial trench work
Sat (01/07) | 01 Jul 2023 | Zone 1 |  | Kingview contractor works ongoing beside shell station
Sat (01/07) | 01 Jul 2023 | MH6-1 |  | Base slab BRC works
Sat (01/07) | 01 Jul 2023 | Zone 3 |  | SPTel reinstatement works in progress
Sat (01/07) | 01 Jul 2023 | Zone 3 JTC area |  | Formwork closing for guidewall ST30 and 31
Sat (01/07) | 01 Jul 2023 | Exit 2 |  | BC cutter maintenance works
Sat (01/07) | 01 Jul 2023 | DW108 |  | Excavation completed & final konden test done. Now preparation for stop end plates installation
Sat (01/07) | 01 Jul 2023 | Exit 1 | DW90 | Guidewall inspected. Concrete ordered
Sat (01/07) | 01 Jul 2023 | DW108 |  | Waterstop end plate welding on going
Sat (01/07) | 01 Jul 2023 | Zone 4 Loyang avenue center median |  | Excavation on going for Singtel duct laying. Target to lay around 24m length
Sun (02/07) | 02 Jul 2023 | DW108 |  | Casting completed, total vol: 60m3. No activity now
Sun (02/07) | 02 Jul 2023 | Zone 2 Southramp |  | No activity
Sun (02/07) | 02 Jul 2023 | Zone 1 Loy Ave Sidetable LP200 |  | Turfing reinstatement by WG ongoing
Sun (02/07) | 02 Jul 2023 | MT4 |  | Target to turf this today
Sun (02/07) | 02 Jul 2023 | MT7 |  | Target to turf this too
Sun (02/07) | 02 Jul 2023 | Zone 4 Loyang Way LP107 |  | Dipcie started premix cutting work / proceed with pipe laying work (singtel)
Sun (02/07) | 02 Jul 2023 | Zone 3 Loyang Way | krislite | No activity by other contractor
Sun (02/07) | 02 Jul 2023 | Zone 4 loyang avenue |  | Excavation for pipe laying works in progress
Sun (02/07) | 02 Jul 2023 | ST28 |  | Rebar for guidewall ongoing
Sun (02/07) | 02 Jul 2023 | Zone 1 |  | Open back lane to public
Sun (02/07) | 02 Jul 2023 | DW108 |  | Casting in progress
Sun (02/07) | 02 Jul 2023 | Loyang way LP 76 |  | Sptel working here
Sun (02/07) | 02 Jul 2023 | Zone 3 loyang way LP76-74 |  | Tonight singtel pipe laying here at the side table, target 24m
Sun (02/07) | 02 Jul 2023 | Zone 4 |  | Lane closure towards TPE for singtel pipe laying 12-way. Target tonight 18m
Sun (02/07) | 02 Jul 2023 | Exit 2 |  | BC cutter maintenance
Sun (02/07) | 02 Jul 2023 | JTC ST30&31 |  | Fwk closure ongoing, target to cast today
Mon (03/07) | 03 Jul 2023 | Zone 1 |  | MT3-A backfilling in progress
Mon (03/07) | 03 Jul 2023 | Zpne 4 loyang avenue |  | Excavation done. Preparation for pipe laying
Mon (03/07) | 03 Jul 2023 | Zone 3 Loyang way |  | Excavation done. Preparation for pipe installation
Mon (03/07) | 03 Jul 2023 | MH6-1 |  | Just preparation work for base slab
Mon (03/07) | 03 Jul 2023 | BH163 |  | In progress, 22m
Mon (03/07) | 03 Jul 2023 | Zone 3 |  | BH39 hand augering started
Mon (03/07) | 03 Jul 2023 | DW32 |  | Preparing rebar for guidewall extension
Mon (03/07) | 03 Jul 2023 | Zone 3 |  | Trial trench ongoing before retaining wall demolition
Mon (03/07) | 03 Jul 2023 | Zone 4 loyang avenue |  | Pipe laying done 18m. Casting in progress
Mon (03/07) | 03 Jul 2023 | MH2-5 |  | No activity
Mon (03/07) | 03 Jul 2023 | Exit 1 |  | Excavation for guidewall DW89 and DW88 (Half) ongoing
Mon (03/07) | 03 Jul 2023 | Zone 2 near LP193 |  | Singtel pipe laying ongoing
Mon (03/07) | 03 Jul 2023 | Zone 2 NLL |  | Pipe laying done 3.5m length, pending premix laying / compaction
Mon (03/07) | 03 Jul 2023 | Near MH5-1 |  | Continue drilling for inclinometer installation by RG
Mon (03/07) | 03 Jul 2023 | PMH1 |  | Reinstatement in progress
Mon (03/07) | 03 Jul 2023 | Zone 3 loyang way |  | Casting on going
Mon (03/07) | 03 Jul 2023 | MH2-3 |  | Excavation works ongoing for 6th layer
Mon (03/07) | 03 Jul 2023 | Near Exit 3 |  | WG manually removing soil to locate existing Starhub
Mon (03/07) | 03 Jul 2023 | Zone 3 |  | ST28 guidewall casting completed
Mon (03/07) | 03 Jul 2023 | Zone 4 loyang avenue |  | Work completed. Lane opened
Mon (03/07) | 03 Jul 2023 | MH6-1 |  | Lowering down rebar and continue with base slab rebar work
Mon (03/07) | 03 Jul 2023 | MH2-3 |  | Excavation on going to 6th layer
Mon (03/07) | 03 Jul 2023 | Zone 3 |  | Access diversion for dwall works
Mon (03/07) | 03 Jul 2023 | DW99 |  | 1st bite trenching at 19m depth
Mon (03/07) | 03 Jul 2023 | Zone 3 loyang way |  | Lane closed for SPPG TT
Mon (03/07) | 03 Jul 2023 | Zone 4 loyang avenue |  | Lane closure for singtel pipe laying
Tue (04/07) | 04 Jul 2023 | MH2-1 |  | TT on going by Ryobi G
Tue (04/07) | 04 Jul 2023 | Zone 1 Noise Barrier |  | Horizontal pipe installation ongoing & will proceed with panel installation
Tue (04/07) | 04 Jul 2023 | SEW 1 |  | Preparing to commence TT here, to locate LV, ST & existing SEW
Tue (04/07) | 04 Jul 2023 | DW99 |  | Desanding completed
Tue (04/07) | 04 Jul 2023 | Zone 2 Southramp |  | No activity
Tue (04/07) | 04 Jul 2023 | Zone 4 loyang avenue |  | Excavation for singtel pipe laying. 24m
Tue (04/07) | 04 Jul 2023 | Zone 3 loyang way |  | Manual excavation continue
Tue (04/07) | 04 Jul 2023 | Zone 4 |  | Singtel pipe laying in progress
Tue (04/07) | 04 Jul 2023 | DW99 |  | 2nd bite trenching on going. Depth at 10m
Tue (04/07) | 04 Jul 2023 | Zone 2 Noise Barrier Footing Removal |  | Footing no.15 completed, pending no.16. Workers went to have their break
Tue (04/07) | 04 Jul 2023 | MH2-3 |  | Excavation works ongoing for 6th layer
Tue (04/07) | 04 Jul 2023 | Zone 1 |  | MT3-A backfilling done and premix reinstated
Tue (04/07) | 04 Jul 2023 | MT4 |  | Turfing ongoing
Tue (04/07) | 04 Jul 2023 | Zone 1 | PMH 1 Area | Balance footpath to match with current one
Tue (04/07) | 04 Jul 2023 | Zone 2 | South ramp area | SingTel pipe laying works ongoing towards SingTel MH. Target to lay 12m today
Tue (04/07) | 04 Jul 2023 | Near MH5-1 |  | Drilling for inclinometer installation by RG, depth 19.5m
Tue (04/07) | 04 Jul 2023 | DW99 |  | Trenching continue for 2nd bite, depth at 15.60m
Tue (04/07) | 04 Jul 2023 | DW099 |  | Continue water stop trimming
Tue (04/07) | 04 Jul 2023 | ST29 |  | Temporarily stop trenching due to bentonite spillage to JTC drain. Current depth at 6.6m. Dongah now investigating the cause of bentonite spillage
Tue (04/07) | 04 Jul 2023 | MH2-3 |  | Excavation for 6th layer ongoing
Tue (04/07) | 04 Jul 2023 | MH2-5 |  | Status quo
Tue (04/07) | 04 Jul 2023 | MH6-1 |  | Base slab rebar work in progress
Wed (05/07) | 05 Jul 2023 | Zone 4 loyang avenue |  | Excavation on going for singtel pipe laying. 20m target tonight
Wed (05/07) | 05 Jul 2023 | Zone 3 loyang way |  | TT on going for SPPG
Wed (05/07) | 05 Jul 2023 | Zone 2 Noise Barrier Footing Removal |  | Current status
Wed (05/07) | 05 Jul 2023 | Zone 2 ULT area |  | Clearing of debris
Wed (05/07) | 05 Jul 2023 | Zone 1 Receiving Shaft |  | Manual TT ongoing by LCH
Wed (05/07) | 05 Jul 2023 | Zone 2 old LVC entrance |  | Removal of 6m NB panels to facilitate the 12m NB works
Wed (05/07) | 05 Jul 2023 | MT7 |  | Reinstated
Wed (05/07) | 05 Jul 2023 | PMH1 reinstatement |  | Balance premix top up for PCN, housekeeping & remove their materials. OKP starting to excavate their new box drain
Wed (05/07) | 05 Jul 2023 | MH6-1 |  | Base slab rebar work in progress
Wed (05/07) | 05 Jul 2023 | Zone 4 Loyang avenue |  | Pipe laying completed
Wed (05/07) | 05 Jul 2023 | Zone 1 loyang avenue |  | MT1 backfilling done. Lane opened
Wed (05/07) | 05 Jul 2023 | ST29 |  | Backfilled until 1m below guidewall. So far no more bentonite spillage at JTC area
Wed (05/07) | 05 Jul 2023 | DW99 |  | Waterstop installation in progress
Wed (05/07) | 05 Jul 2023 | Zone 4 loyang avenue |  | Premix done. Lane opened
Wed (05/07) | 05 Jul 2023 | Zone 2 LP193 |  | Manually clearing soil for the Singtel pipe laying
Wed (05/07) | 05 Jul 2023 | MH2-3 |  | 6th layer casting just completed
Wed (05/07) | 05 Jul 2023 | DW99 |  | 3/4 cages installation in progress
Wed (05/07) | 05 Jul 2023 | MH6-1 |  | Base rebar works ongoing
Wed (05/07) | 05 Jul 2023 | Zone 3 loyang avenue |  | Tonight wee guan to continue TT here for singtel
Wed (05/07) | 05 Jul 2023 | Zone 3 |  | End plate fabrication
Wed (05/07) | 05 Jul 2023 | Exit 1 |  | Formwork closing for DW88 guidewall
Thu (06/07) | 06 Jul 2023 | Zone 2 |  | Singtel pipe laying completed, 15m. Concrete haunching completed. Tmr to continue backfilling & reinstatement works
Thu (06/07) | 06 Jul 2023 | Exit 1 |  | DW88 formwork closing continue
Thu (06/07) | 06 Jul 2023 | Zone 3 loyang way |  | Trial trench done. Found drain at 0.7m depth
Thu (06/07) | 06 Jul 2023 | MH6-1 |  | Inspection of base slab rebar on going by RE
Thu (06/07) | 06 Jul 2023 | Zone 4 loyang avenue |  | Singtel pipe laying completed
Thu (06/07) | 06 Jul 2023 | Exit 3 |  | Due to existing utility (SH) nearby the drain, WHDA will need to install steel plate and pipe protection before continue with drain hacking and removal works
Thu (06/07) | 06 Jul 2023 | BH-163 |  | Packer test ongoing, current depth 45m. BH-164: Drilling ongoing, depth 26m. BH-162: Manual Trial trench
Thu (06/07) | 06 Jul 2023 | MH2-5 |  | Mini excavator lowered for 2nd layer excavation
Thu (06/07) | 06 Jul 2023 | MH2-3 |  | 6th layer cast yesterday
Thu (06/07) | 06 Jul 2023 | Zone 2 |  | NB footings hacking completed. Now clearing the hardcores
Thu (06/07) | 06 Jul 2023 | Gate 6 |  | Permanent gate installation ongoing
Thu (06/07) | 06 Jul 2023 | Zone 2 |  | SingTel Pipe laying works, to lay 13m today
Thu (06/07) | 06 Jul 2023 | MH5-1 |  | (RG) inclinometer installed, depth 20.7m
Thu (06/07) | 06 Jul 2023 | Zone 1 |  | LCH manual trial trench works
Thu (06/07) | 06 Jul 2023 | Zone 1 |  | DE143 working within their boundary
Thu (06/07) | 06 Jul 2023 | Zone 2 |  | Singtel pipe laying in progress
Thu (06/07) | 06 Jul 2023 | ULT8 |  | First cycle load at 100% in progress. Another 1hr to hold at current load
Thu (06/07) | 06 Jul 2023 | Loyang Way | near Exit 1 | Premix hacking for TT for SPPG
Thu (06/07) | 06 Jul 2023 | Zone 4 LP111 |  | Plan for Singtel pipe laying tonight
Fri (07/07) | 07 Jul 2023 | Loyang Way LP26 |  | Sidetable excavation for Singtel pipe laying
Fri (07/07) | 07 Jul 2023 | PMH1 |  | Current status
Fri (07/07) | 07 Jul 2023 | Zone 1 | next to MH1-2 | LCH preparing to commence TT to locate LV cables
Fri (07/07) | 07 Jul 2023 | Zone 2 LP193 |  | Laying singtel slab & continue backfilling
Fri (07/07) | 07 Jul 2023 | MH2-3 |  | 6th layer formwork removal in progress
Fri (07/07) | 07 Jul 2023 | LVC blk 222 |  | From 10pm onwards, noise level breach. Between 11-1110pm, temporarily stopped. Will continue to closely monitor
Fri (07/07) | 07 Jul 2023 | Zone 4 |  | Singtel pipe laid, 20m
Fri (07/07) | 07 Jul 2023 | Exit 3 |  | Area preparation for drain hacking. TT for 1 side completed. Other side beside PCN will do TT again before drain hacking
Fri (07/07) | 07 Jul 2023 | Loyang Way | near Exit 1 | TT completed. Found 22kV & PUB (LV)
Fri (07/07) | 07 Jul 2023 | BH163 |  | Depth at 53m, BH164: depth at 38m
Fri (07/07) | 07 Jul 2023 | Zone 2 LVC side |  | Hardcore disposal from NB footing
Fri (07/07) | 07 Jul 2023 | Zone 2 |  | Pavement hacking in progress to do TT for new MX4 location
Fri (07/07) | 07 Jul 2023 | Loyang Way | near Exit 1 | Reinstatement completed. Lane reopened
Fri (07/07) | 07 Jul 2023 | ST27 |  | Guidewall formwork closing in progress
Fri (07/07) | 07 Jul 2023 | ST29 |  | 1st bite trenching in progress. Depth at 20m
Fri (07/07) | 07 Jul 2023 | ULT8 |  | 2nd cycle load 100% in progress
Fri (07/07) | 07 Jul 2023 | ULT8 |  | 3rd cyle at 175%, maximum elongation at 1.329mm
Fri (07/07) | 07 Jul 2023 | Zone 3 |  | Area preparation for SI rig platform to get clayshock sampling
Fri (07/07) | 07 Jul 2023 | Exit 1 Desander # 2 |  | Balance return pipe installation and connection from BC cutter
Fri (07/07) | 07 Jul 2023 | Exit 1 |  | DW97 Preparation for flap guide welding for 2nd bite
Fri (07/07) | 07 Jul 2023 | ST29 |  | First bite excavation in progress, current depth 27m. Noise balloons installed
Fri (07/07) | 07 Jul 2023 | LVC blk 222 |  | So far noise level maintained
Fri (07/07) | 07 Jul 2023 | ULT8 |  | 3rd cycle at 250% in progress. Holding time 1hr
Fri (07/07) | 07 Jul 2023 | Exit 1 DW107 |  | 2nd bite excavation in progress
Fri (07/07) | 07 Jul 2023 | Zone 4 | in front of SIA bldg | Plan for TT works for Singtel tonight. Area preparation ongoing
Sat (08/07) | 08 Jul 2023 | ST29 |  | LSS backfilling in progress
Sat (08/07) | 08 Jul 2023 | MH2-3 |  | Preparing access for next layer, 7th layer, excavation
Sat (08/07) | 08 Jul 2023 | MH1-2 |  | TT for manhole was done
Sat (08/07) | 08 Jul 2023 | Zone 4 |  | Manual trial trench in progress
Sat (08/07) | 08 Jul 2023 | Zone 4 |  | Another TT for Singtel
Sat (08/07) | 08 Jul 2023 | MH2-7 |  | 1st ring rebar and proper access installation on going
Sat (08/07) | 08 Jul 2023 | DW107 |  | 2nd bite excavation completed. Now cleaning before start trimming works
Sat (08/07) | 08 Jul 2023 | ULT8 |  | Now loading at 350% for 24hrs
Sat (08/07) | 08 Jul 2023 | ST29 |  | 1st bite excavation ongoing. Current depth 37.3m
Sat (08/07) | 08 Jul 2023 | DW114 |  | Manual TT on going
Sat (08/07) | 08 Jul 2023 | Zone 4 |  | Second TT completed. No services observed
Sat (08/07) | 08 Jul 2023 | MH2-3 |  | Continue excavation to 7th layer
Sat (08/07) | 08 Jul 2023 | ULT8 |  | 350% load in progress (20hrs). Another 4hrs to hold at current load
Sat (08/07) | 08 Jul 2023 | Exit 1 DW107 |  | Preparing for hanging bar installation
Sat (08/07) | 08 Jul 2023 | Exit 1 DW100 |  | BC cutter teeth works ongoing prior to 2nd bite excavation
Sat (08/07) | 08 Jul 2023 | Zone 4 LP99 | near SIA bldg | Tonight plan for 2nos TT at sidetable
Sat (08/07) | 08 Jul 2023 | MH2-7 |  | Excavation for 1st ring started. Today target to cast first ring of caisson
Sun (09/07) | 09 Jul 2023 | Exit 1 |  | DW114 trial trench in progress
Sun (09/07) | 09 Jul 2023 | Exit 1 |  | DW100 cleaning for 1st bite completed
Sun (09/07) | 09 Jul 2023 | DW100 |  | Cage 1A&2A lowered
Sun (09/07) | 09 Jul 2023 | Zone 4 Loy Way |  | No activity by WG tonight
Sun (09/07) | 09 Jul 2023 | Zone 1 |  | BH 15 Trial trench on going
Sun (09/07) | 09 Jul 2023 | Zone 1 |  | BH14 Trial trench on going
Sun (09/07) | 09 Jul 2023 | Zone 4 ATT-WG-113 | D | Found LP cable, LV, HT and concrete
Sun (09/07) | 09 Jul 2023 | Zone 4 |  | Now preparing to start 2nd TT
Sun (09/07) | 09 Jul 2023 | MT2-7 |  | Barricade installation in progress
Sun (09/07) | 09 Jul 2023 | ST29 |  | Additional LSS until guidewall top level
Sun (09/07) | 09 Jul 2023 | DW100 |  | Cleaning and Koden test completed . Now preparing for water stop installation
Sun (09/07) | 09 Jul 2023 | Zone 3 near selerang camp |  | ECM level ok
Sun (09/07) | 09 Jul 2023 | Zone 4 |  | Second TT completed. No services found
Sun (09/07) | 09 Jul 2023 | Zone 3 LA | within site | TT completed. Services: EHT, 66kV, gas and water pipe
Sun (09/07) | 09 Jul 2023 | ST29 |  | LSS backfilling completed earlier. Total vol: 190m3
Sun (09/07) | 09 Jul 2023 | DW107 |  | Casting in progress
Sun (09/07) | 09 Jul 2023 | DW100 |  | 2nd bite excavation depth at 22.3m. Internal koden test ongoing
Sun (09/07) | 09 Jul 2023 | LVC blk 222 |  | Noise level so far maintained
Sun (09/07) | 09 Jul 2023 | BH15 |  | TT continue
Sun (09/07) | 09 Jul 2023 | BH14 |  | TT continue. Dongah SI team will work until 5pm only
Sun (09/07) | 09 Jul 2023 | DW107 completed. Total vol |  | 62m3
Mon (10/07) | 10 Jul 2023 | LP69 Loyang Way |  | Dipcie team here, prepare for premix removal / pipe laying for singtel 18-way
Mon (10/07) | 10 Jul 2023 | LP121 Loyang Way | ATT-WG-51 | TT for Singtel, TMA & TMO provided
Mon (10/07) | 10 Jul 2023 | Zone 2 LVC |  | NB footing formwork & guardrail installation ongoing. Plan for casting tmr morning
Mon (10/07) | 10 Jul 2023 | Exit 3 |  | Excavation work in progress for SPPG pipe laying. Today 6m
Mon (10/07) | 10 Jul 2023 | Zone 1 LA |  | No lane closures
Mon (10/07) | 10 Jul 2023 | Zone 1 near AWWA |  | DE143 drain works ongoing
Mon (10/07) | 10 Jul 2023 | Zone 1 Gate 2 |  | TT by LCH to locate the alignment of the traffic light (near MH1-2)
Mon (10/07) | 10 Jul 2023 | Zone 1 within hoarding |  | No activity
Mon (10/07) | 10 Jul 2023 | Zone 2 |  | Hacking works in progress for singtel pipe laying. Target 12m
Mon (10/07) | 10 Jul 2023 | DW100 |  | A side tremie pipe fully installed, B side tremie pipe installation on going
Mon (10/07) | 10 Jul 2023 | MH2-7 |  | Excavation on going for 2nd layer caisson. Plan to cast tomorrow
Mon (10/07) | 10 Jul 2023 | Loyang Lane LP3 |  | WG started excavation till 2.1m for 10-way pipe laying
Mon (10/07) | 10 Jul 2023 | LP77 Loyang Way |  | Dipcie commence premix removal / pipe laying, singtel 18-way
Tue (11/07) | 11 Jul 2023 | Zone 2 |  | Demobilisation of 80 tonne crane from HSL
Tue (11/07) | 11 Jul 2023 | Zone 4 area |  | Sptel just started pipe laying work today. Loyang way near Salarang camp toward prison. So, consider 0% pipe laying. Trial trench completed for this part pipe laying
Tue (11/07) | 11 Jul 2023 | Zone 3 |  | Pavement hacking for BC cutter platform
Tue (11/07) | 11 Jul 2023 | Zone 2 LVC Side |  | NB footing casting. 15m
Tue (11/07) | 11 Jul 2023 | Zone 3 |  | BH39 in progress, 49.7m
Tue (11/07) | 11 Jul 2023 | Zone 3 |  | Continue TT & premix hacking to locate the retaining wall base slab
Tue (11/07) | 11 Jul 2023 | Loyang way near Exit 1 toward Prison |  | Road premix removal for TT. Highlighted to the team here to be more careful of existing services especially gas pipe. Today PowerGas has 4 cases of gas pipe damages (two cases at Loyang area)
Tue (11/07) | 11 Jul 2023 | Exit 1 |  | Preparation to start trial trench for DW112, 1113 and 114
Tue (11/07) | 11 Jul 2023 | Zone 2 |  | Singtel pipe laying, 12m today
Tue (11/07) | 11 Jul 2023 | ULT7 |  | Setting up for test ongoing
Tue (11/07) | 11 Jul 2023 | ST32 |  | Area preparation for preboring
Tue (11/07) | 11 Jul 2023 | MH6-1 |  | No activity
Tue (11/07) | 11 Jul 2023 | Zone 2 |  | Ryobi-G hand augering for Inclinometer and water stand pipe installation at MH5-2
Tue (11/07) | 11 Jul 2023 | MH2-7 |  | To continue excavation for 2nd layer
Tue (11/07) | 11 Jul 2023 | Zone 1 |  | LCH to pacth back TT location here
Tue (11/07) | 11 Jul 2023 | MH2-7 |  | Excavation for 2nd layer
Tue (11/07) | 11 Jul 2023 | Loyang Way LP99 | ATT-WG-115 | TT completed, HT & drain found
Tue (11/07) | 11 Jul 2023 | Loyang Way LP99 | ATT-WD-116 | TT commence
Tue (11/07) | 11 Jul 2023 | MH2-7 |  | 2nd layer excavation in progress
Tue (11/07) | 11 Jul 2023 | Zone 3 |  | Manual excavation continue for singtel pipe laying
Tue (11/07) | 11 Jul 2023 | BH142 |  | Drilling at 18m depth
Tue (11/07) | 11 Jul 2023 | ST30 |  | Trial trenching on going till 9m. To be backfilled with LSS
Tue (11/07) | 11 Jul 2023 | ST32 |  | Pre-coring till 9m
Tue (11/07) | 11 Jul 2023 | ULt7 |  | Set up on going for bi directional test
Tue (11/07) | 11 Jul 2023 | Zone 2 |  | Singtel pipe laying in progress
Tue (11/07) | 11 Jul 2023 | MH2-5 |  | 3rd layer excavation ongoing
Tue (11/07) | 11 Jul 2023 | MH2-3 |  | No activity
Tue (11/07) | 11 Jul 2023 | Zone 3 |  | Trial trench to find Retaining wall base slab
Tue (11/07) | 11 Jul 2023 | MH2-7 |  | Continue 2nd layer excavation
Tue (11/07) | 11 Jul 2023 | Zone 2 |  | Singtel pipes laid for the day, 12m
Tue (11/07) | 11 Jul 2023 | ST28 |  | First bite excavation in progress
Tue (11/07) | 11 Jul 2023 | ST30 |  | LSS backfilling in progress
Tue (11/07) | 11 Jul 2023 | BH 163 |  | Drilling and SPT
Tue (11/07) | 11 Jul 2023 | Bh164 |  | Drilling on going
Tue (11/07) | 11 Jul 2023 | BH165 |  | TT on going
Tue (11/07) | 11 Jul 2023 | Zone 3 WG team 1 |  | Shoring installation for the Singtel pipe laying. 4m already laid yesterday
Tue (11/07) | 11 Jul 2023 | Zone 3 WG team 2 |  | Today to continue excavation and shoring installation for Singtel pipe laying
Wed (12/07) | 12 Jul 2023 | Exit 1 DW106 |  | Trimming (DW107 side) completed
Wed (12/07) | 12 Jul 2023 | BH162 |  | Preparing for drilling
Wed (12/07) | 12 Jul 2023 | Bh164 |  | Drilling at 51m
Wed (12/07) | 12 Jul 2023 | BH168 |  | TT in progress
Wed (12/07) | 12 Jul 2023 | Zone 3 |  | Premix cutting to facilitate TT works for ST142-140
Wed (12/07) | 12 Jul 2023 | Zone 3 RW |  | Cable detection
Wed (12/07) | 12 Jul 2023 | Exit 2 |  | BH142 in progress, 23.2m
Wed (12/07) | 12 Jul 2023 | MH2-3 |  | No activity
Wed (12/07) | 12 Jul 2023 | Zone 2 |  | Singtel pipe laid 15m
Wed (12/07) | 12 Jul 2023 | MH6-1 |  | Dewatering ongoing. Was informed on site the flexi hoses will come this afternoon
Wed (12/07) | 12 Jul 2023 | Exit 3 |  | Current status at drain area
Wed (12/07) | 12 Jul 2023 | Zone 1/2 junction |  | Premix cutting to expose pipe for cable pulling towards zone 1, for power supply
Wed (12/07) | 12 Jul 2023 | Outside CR106 main gate |  | (Works under CCECC) Preparing for installation of live valve (water pipe connection)
Wed (12/07) | 12 Jul 2023 | MH2-7 |  | 2nd layer formwork closing done. Ready for casting
Wed (12/07) | 12 Jul 2023 | Zone 3 |  | Singtel pipe laid, 6m. Now removing shoring
Wed (12/07) | 12 Jul 2023 | MH2-5 |  | 3rd layer rebar installation. Target to cast today
Wed (12/07) | 12 Jul 2023 | ST29 |  | Excavation temporarily stopped. BC cutter rectification ongoing
Wed (12/07) | 12 Jul 2023 | MH6-1 |  | Hacking of the existing sewer haunching
Wed (12/07) | 12 Jul 2023 | Zone 3 |  | TT for ST 143, 144 and 144A
Wed (12/07) | 12 Jul 2023 | MH2-7 |  | 2nd layer caisson casting almost completed
Wed (12/07) | 12 Jul 2023 | Zone 3 WG |  | Team 1 to continue excavation for Singtel pipe laying
Wed (12/07) | 12 Jul 2023 | Zone 3 WG |  | Team 2 to continue excavation & pipe laying for Singtel, 6m
Wed (12/07) | 12 Jul 2023 | Exit 3 |  | Preparation for Utility protection, later today will do drain removal. Selvam will be full time here
Wed (12/07) | 12 Jul 2023 | Zone 3 |  | BH39 completed, 54.3m. Today to start BH38
Thu (13/07) | 13 Jul 2023 | Exit 3 |  | Steel plate & GI pipes already installed to protect the Starhub cable. Today to hack the drain
Thu (13/07) | 13 Jul 2023 | Zone 4 |  | Pavement hacking in progress
Thu (13/07) | 13 Jul 2023 | Exit 1 |  | DW101 preparation works for rebar cage lowering
Thu (13/07) | 13 Jul 2023 | MH2-3 |  | No activity
Thu (13/07) | 13 Jul 2023 | BH168 |  | Hand auger in progress
Thu (13/07) | 13 Jul 2023 | Zone 2 LVC |  | NB footing formwork dismantling in progress
Thu (13/07) | 13 Jul 2023 | Zone 2 LP181 |  | Excavation ongoing for Singtel pipe laying to existing MH.Today plan to lay, 8m
Thu (13/07) | 13 Jul 2023 | MH5-1 |  | No activity. Inclinometer & waterstandpipe already installed
Thu (13/07) | 13 Jul 2023 | MH6-1 |  | Pipe both ends were cut into half for hose installation. LCH will work until hose connection completed. Estimated 1230 am
Thu (13/07) | 13 Jul 2023 | ST29 |  | 1st bite trimming completed
Thu (13/07) | 13 Jul 2023 | DW101 |  | Excavation done, 22.50m. Installation of C lock for waterstop end plate trimming
Thu (13/07) | 13 Jul 2023 | DW106 |  | Cage B (1/2 lowered down). Preparing for Cage A first cage lowering down
Thu (13/07) | 13 Jul 2023 | Exit 3 |  | Drain hacking completed
Thu (13/07) | 13 Jul 2023 | MH2-3 |  | Excavation for 8th layer in progress
Thu (13/07) | 13 Jul 2023 | MH2-5 |  | Currently only curing for 4th layer which was cast yesterday
Thu (13/07) | 13 Jul 2023 | Zone 2 |  | Singtel pipe laying ongoing
Thu (13/07) | 13 Jul 2023 | Gate 2 |  | Temp water pipe laying in progress
Thu (13/07) | 13 Jul 2023 | MH1-2 |  | Instrument installation by RG started
Thu (13/07) | 13 Jul 2023 | Zone 1 P4 |  | BH15 manual trial trench in progress
Thu (13/07) | 13 Jul 2023 | Zone 1 P3 |  | BH14 manual TT in progress
Thu (13/07) | 13 Jul 2023 | MH2-6 |  | No activity. Instruments already in place
Thu (13/07) | 13 Jul 2023 | MH6-1 |  | Preparing to install bracket thereafter install the flexible hose. Works for today will end ard 10pm
Thu (13/07) | 13 Jul 2023 | DW106 |  | 10th truck casting ongoing
Thu (13/07) | 13 Jul 2023 | DW113/114 area |  | Barricade installation before continuing trial trench
Thu (13/07) | 13 Jul 2023 | Gate 5 |  | Biometrics shelter dismantling. Tomorrow to shift
Thu (13/07) | 13 Jul 2023 | MH6-1 |  | Setting up flexible hose for diversion
Thu (13/07) | 13 Jul 2023 | ST29 |  | 1st bite trenching, 27.5m depth
Thu (13/07) | 13 Jul 2023 | Zone 3 Loyang way Junction |  | Depcie team 2 for singtel pipe laying. Target here tonight is 10m
Thu (13/07) | 13 Jul 2023 | Zone 4 loyang avenue |  | Wee guan team 2 for SPPG trial trench
Thu (13/07) | 13 Jul 2023 | Zone 3 loyang way in front of exit 1 |  | Trial trench for singtel pipe corridor
Thu (13/07) | 13 Jul 2023 | Exit 1 |  | DW101 setting up for final koden test
Fri (14/07) | 14 Jul 2023 | Zone 3 loyang way LP 17 |  | TT for singtel corridor
Fri (14/07) | 14 Jul 2023 | MH2-3 |  | Preparing to continue excavation for 8th layer
Fri (14/07) | 14 Jul 2023 | MH2-5 |  | No activity. Same team is doing for MH2-3
Fri (14/07) | 14 Jul 2023 | MH2-7 |  | No activity. Heard on site this team is doing for MH2-6 as well
Fri (14/07) | 14 Jul 2023 | MH2-6 |  | No activity. Noted on site that today plan to start trial trench
Fri (14/07) | 14 Jul 2023 | Zone 2 Singtel |  | Yesterday completed 8m. Now pending reinstatement. Once completed, target to continue near workers’ rest area
Fri (14/07) | 14 Jul 2023 | MH5-1 |  | No activity
Fri (14/07) | 14 Jul 2023 | MH5-2 |  | RG drilling ongoing for waterstandpipe installation. Now ongoing 9/15m. Yesterday installed inclinometer
Fri (14/07) | 14 Jul 2023 | ULT7 |  | Holding 24 hrs for 300% loading. To complete by 7pm tomorrow
Fri (14/07) | 14 Jul 2023 | MH1-2 |  | RG drilling ongoing for inclinometer installation
Fri (14/07) | 14 Jul 2023 | Zone 1 P3 |  | Continue BH14 manual TT
Fri (14/07) | 14 Jul 2023 | ST29 |  | LSS casting on going. 81/300 m3 on site
Fri (14/07) | 14 Jul 2023 | BH164 |  | Current depth 60m. Packer test in progress
Fri (14/07) | 14 Jul 2023 | BH162 |  | Drilling ongoing, 32m
Fri (14/07) | 14 Jul 2023 | Zone 3 |  | Trial trench for DR2 ongoing
Fri (14/07) | 14 Jul 2023 | Near DW114 |  | Manual excavation to be done under drain to check for more services. LT cables found at DW114
Fri (14/07) | 14 Jul 2023 | ST29 |  | 3rd bite trenching in progress. Depth 18.9m
Fri (14/07) | 14 Jul 2023 | ULT7 |  | Holding at 200% for 3rd cycle. Elongation at 2.494mm
Fri (14/07) | 14 Jul 2023 | DW101 |  | 2/2 rebar cages installed. Balance hanging bar
Fri (14/07) | 14 Jul 2023 | Zone 3 Loyang way |  | Trial trench for manhole location done. No services found
Fri (14/07) | 14 Jul 2023 | Zone 4 loyang avenue TT |  | Found 22KV, LT cables and old road kerb
Fri (14/07) | 14 Jul 2023 | Zone 3 loyang way junction |  | Area backfilled. Not feasible to lay pipe because of existing utilities. Tomorrow they will do TT at 2md lane and 1st lane for possible corridor
Fri (14/07) | 14 Jul 2023 | BH54 |  | In progress, 18m
Fri (14/07) | 14 Jul 2023 | Zone 3 Singtel |  | Continue manual clearing soil below services thereafter pipe laying (to lay today)
Fri (14/07) | 14 Jul 2023 | Exit 3 SPPG |  | Excavation in progress
Fri (14/07) | 14 Jul 2023 | MH2-3 |  | Excavation in progress
Fri (14/07) | 14 Jul 2023 | DW101 |  | Tremie pipe installation in progress
Fri (14/07) | 14 Jul 2023 | Zone 3 loyang way in front of exit 1 |  | Lane opened
Fri (14/07) | 14 Jul 2023 | Zone 2 LVC |  | Tmr mobile crane mobilisation for the NB column installation
Fri (14/07) | 14 Jul 2023 | Zone 2 Singtel |  | Previous work area near existing MH reinstated
Fri (14/07) | 14 Jul 2023 | Blk 222 |  | Noise reading has been breaching since 12 midnight because of our Dwall works at JTC area. Average at 67 dB
Fri (14/07) | 14 Jul 2023 | ST29 |  | 3rd bite trenching at 44m depth
Fri (14/07) | 14 Jul 2023 | DW101 |  | Casting in progress. 32/48 m3
Fri (14/07) | 14 Jul 2023 | DW101 |  | Additional 2 m3 ordered. Total 50 m3
Fri (14/07) | 14 Jul 2023 | ULT7 |  | Still holding at 200%
Fri (14/07) | 14 Jul 2023 | ST29 trenching done |  | Cleaning in progress
Fri (14/07) | 14 Jul 2023 | Zone 3 loyang way in front of JTC blk |  | Excavation for singtel pipe laying. 15m target tonight
Fri (14/07) | 14 Jul 2023 | Zone 3 Loyang way LP 23 |  | TT for SPPG corridor
Fri (14/07) | 14 Jul 2023 | Zone 4 Loyang Avenue |  | TT for SPPG corridor
Fri (14/07) | 14 Jul 2023 | Zone 3 Singtel |  | Today plan to lay 6m
Fri (14/07) | 14 Jul 2023 | Exit 3 SPPG |  | Today WG to continue works and plan to lay 6m. Now dewatering and work area preparation ongoing
Sat (15/07) | 15 Jul 2023 | Zone 3 Singtel |  | Continue excavation works. Yesterday didn’t lay, today plan to lay 5m
Sat (15/07) | 15 Jul 2023 | ST32 |  | BP No.2 Koden testing in progress, depth 39.6m from TOC
Sat (15/07) | 15 Jul 2023 | ABH54 |  | Drilling ongoing, depth 30m
Sat (15/07) | 15 Jul 2023 | ULT 7 |  | Loading at 300%, 16hrs ongoing. Need hold for 24hrs
Sat (15/07) | 15 Jul 2023 | BH38 |  | Drilling ongoing at 42m depth
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | Excavation in progress for slope protection casting
Sat (15/07) | 15 Jul 2023 | Exit 1 | DW ST113/ST114 | Interface trial trench ongoing
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang avenue |  | Manual excavation for singtel pipe laying continues
Sat (15/07) | 15 Jul 2023 | Zone 4 |  | Powergas pit excavation for connection works ongoing
Sat (15/07) | 15 Jul 2023 | Zone 4 |  | DE143 working within their boundary
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | Trial trench works ongoing for ST143-ST140
Sat (15/07) | 15 Jul 2023 | BH-162 |  | Packer test ongoing for depth 39.10-44.10m
Sat (15/07) | 15 Jul 2023 | Zone 2 |  | 6 nos. of columns installed for noise barrier panels installation. Afternoon, the team will continue columns installation near LVC bin center area
Sat (15/07) | 15 Jul 2023 | MH2-3 |  | Rebar installation for 8th layer. Target to cast today
Sat (15/07) | 15 Jul 2023 | Zone 1 | MH1-2 | RG inclinometer installation works
Sat (15/07) | 15 Jul 2023 | Zone 2 |  | Premix removal ongoing for singtel pipe laying. Target to lay 18m
Sat (15/07) | 15 Jul 2023 | ST29 |  | LSS casting continue. 149/300 m3
Sat (15/07) | 15 Jul 2023 | ULT7 |  | Continue holding for 300%, 7/24 hours. Recorded elongation so far at 3.7mm
Sat (15/07) | 15 Jul 2023 | Zone 4 loyang avenue |  | TT record. No utility found
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang way LP23 |  | Trial trench record. No utility found
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang way in front of lincstech |  | Singtel pipe laying completed. 12m
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang way in front of JTC blk 4 |  | Singtel pipe laying done, 12.5m. Reinstating empty street light pipes
Sat (15/07) | 15 Jul 2023 | MH2-7 |  | Excavation ongoing for 3rd layer
Sat (15/07) | 15 Jul 2023 | MH6-1 |  | Mobilisation of pipe jacking materials in progress
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | SingTel pipe laying - Laid 4m. Reinstatement ongoing
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | Trial trench and shoring works ongoing. Tonight to continue with SingTel pipe laying
Sat (15/07) | 15 Jul 2023 | BH-162 |  | Continue drilling works, current depth 44.1m
Sat (15/07) | 15 Jul 2023 | BH-166 |  | Current depth 66m
Sat (15/07) | 15 Jul 2023 | MH2-6 |  | KTC backfilling & compaction works in progress
Sat (15/07) | 15 Jul 2023 | ST29 |  | LSS backfilling continue
Sat (15/07) | 15 Jul 2023 | MH2-3 |  | Preparation to close Formwork for casting works at 8th layer
Sat (15/07) | 15 Jul 2023 | Zone 2 North Ramp N6 pile cap |  | Manual Trial trench ongoing for ERSS works
Sat (15/07) | 15 Jul 2023 | Zone 1 |  | RG inclinometer drilling works ongoing. Depth 16m
Sat (15/07) | 15 Jul 2023 | MH5-2 |  | Inclinometer & Water standpipe instrumentation installation completed
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | PUB came to shut the small valves due to de143 water pipe leakage at zone 4
Sat (15/07) | 15 Jul 2023 | Zone 4 |  | Powergas current pit excavation status
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | Slope trimming done. Concrete ordered for slope protection casting
Sat (15/07) | 15 Jul 2023 | Zone 3 |  | BC cutter noise barrier panel installation & maintenance works
Sat (15/07) | 15 Jul 2023 | MH6-1 |  | Current status for pipe jacking mobilisation
Sat (15/07) | 15 Jul 2023 | ST29 LSS backfilling continue |  | 279/316 m3
Sat (15/07) | 15 Jul 2023 | ULT7 |  | Continue holding at 300%, 12/24 hrs
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang avenue |  | Team 1 singtel pipe laying tonight. 8m
Sat (15/07) | 15 Jul 2023 | Zone 2 MH03 | MX4 | Excavation works for manhole installation
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang way |  | Team 1 for singtel pipe laying. Excavtion on going
Sat (15/07) | 15 Jul 2023 | Zone 3 loyang way |  | Team 2 for singtel pipe laying. Excavation on going
Sat (15/07) | 15 Jul 2023 | MH2-7 |  | Preparing to remove formworks and start excavation for 3rd layer
Sun (16/07) | 16 Jul 2023 | Exit 1 | DW87 | Excavation for GW ongoing & they will also start TT near to drain (circled in green)
Sun (16/07) | 16 Jul 2023 | Exit 1 | ST141 | TT ongoing, found 300mm dia WP
Sun (16/07) | 16 Jul 2023 | Exit 1 |  | Hot works for end plates ongoing
Sun (16/07) | 16 Jul 2023 | BH 12 | ST028 | Setting up ongoing
Sun (16/07) | 16 Jul 2023 | Zone 2 |  | MH3 (MX4) safely unloaded/installed
Sun (16/07) | 16 Jul 2023 | Team 2 at loyang way |  | Works completed. Lane opened
Sun (16/07) | 16 Jul 2023 | MH2-6 |  | Backfilling ongoing
Sun (16/07) | 16 Jul 2023 | MH2-5 |  | No activity
Mon (17/07) | 17 Jul 2023 | LVC blk 222 |  | Slight noise breach from 10pm onwards
Mon (17/07) | 17 Jul 2023 | MH2-3 |  | Area leveling for 8m NB installation
Mon (17/07) | 17 Jul 2023 | Zone 2 P11 |  | Excavation work for singtel pipe laying
Mon (17/07) | 17 Jul 2023 | Zone 2 |  | Horizontal bracings and noise barriers panel installation ongoing
Mon (17/07) | 17 Jul 2023 | Zone 2 |  | SingTel removing unused cables
Mon (17/07) | 17 Jul 2023 | Zone 2 MH5-1 |  | Pavement hacking in progress
Mon (17/07) | 17 Jul 2023 | North Ramp | N6 | Manual trial trench works for pile cap ERSS
Mon (17/07) | 17 Jul 2023 | MH2-5 |  | Hacking for 4th layer ongoing
Mon (17/07) | 17 Jul 2023 | MH6-1 |  | Installing jack & frame ongoing
Mon (17/07) | 17 Jul 2023 | ST-032 |  | Boring ongoing
Mon (17/07) | 17 Jul 2023 | MH6-1 |  | Continue setting up jack & frame. Works continue till ard 10pm
Mon (17/07) | 17 Jul 2023 | Exit 1 |  | Setting up frame for noise barrier panel installation for BC cutter
Mon (17/07) | 17 Jul 2023 | Loyang Way | near exit 1 | Plan for trial trench for Singtel. Preparation works ongoing
Mon (17/07) | 17 Jul 2023 | Zone 4 Loyang Ave |  | Preparation works ongoing for trial trench for SPPG
Mon (17/07) | 17 Jul 2023 | Loyang Way LP23 |  | Tonight to expedite trial trench for SPPG
Mon (17/07) | 17 Jul 2023 | Loyang Way opp LP71 |  | Tonight plan for Singtel pipe laying, 18m
Mon (17/07) | 17 Jul 2023 | Zone 2 |  | Singtel pipe laid, 18m. Works done for the day. Tmr to reinstate location
Mon (17/07) | 17 Jul 2023 | MH2-5 |  | Works done for the day. Tmr to continue works for 4th layer
Tue (18/07) | 18 Jul 2023 | BH162 |  | Drilling at 61m depth
Tue (18/07) | 18 Jul 2023 | MH2-5 |  | Excavation for 4th layer
Tue (18/07) | 18 Jul 2023 | Zone 2 LVC side |  | NB panel installation
Tue (18/07) | 18 Jul 2023 | MH6-1 |  | Jacking frame lowered down. Today target thrust block casting. Plan to complete cables and hose connection by Thursday or Friday, by then will be ready for jacking
Tue (18/07) | 18 Jul 2023 | ST140 to ST143 |  | Dongah preparing to install protection to existing services for guidewall work
Tue (18/07) | 18 Jul 2023 | Loyang Way | near exit 1 | TT done. No utilities found
Tue (18/07) | 18 Jul 2023 | Loyang Way LP23 |  | TT completed. Found Starhub
Tue (18/07) | 18 Jul 2023 | Zone 4 |  | TT completed. No services found
Tue (18/07) | 18 Jul 2023 | MH6-1 |  | Formwork closing for thrust block. Today to cast
Tue (18/07) | 18 Jul 2023 | MH2-3 |  | Rebar installation for 3rd layer
Tue (18/07) | 18 Jul 2023 | Opp LP71 |  | Singtel pipe laying in progress
Tue (18/07) | 18 Jul 2023 | Zone 4 |  | Reinstatement in progress
Tue (18/07) | 18 Jul 2023 | Opp LP71 |  | Singtel pipe laying completed, 18m
Tue (18/07) | 18 Jul 2023 | MH2-5 |  | Trimming and preparation for rebar installation
Tue (18/07) | 18 Jul 2023 | MH5-1 |  | Utilities exposed. Found Starhub, and singtel. Waiting Selvam to confirm starhub is terminated
Tue (18/07) | 18 Jul 2023 | Loyang Way | near exit 1 | Lane reopened
Tue (18/07) | 18 Jul 2023 | Loyang Way LP23 |  | Lane reopened
Tue (18/07) | 18 Jul 2023 | Opp LP71 |  | Works completed. Lane reopened
Tue (18/07) | 18 Jul 2023 | Exit 1 |  | BC cutter noise barrier panel installation in progress
Tue (18/07) | 18 Jul 2023 | MH6-1 |  | Thrust block casting in progress
Tue (18/07) | 18 Jul 2023 | ST32 |  | 2nd bite excavation in progress
Tue (18/07) | 18 Jul 2023 | Exit 1 |  | To continue installing the top part of the noise barrier
Tue (18/07) | 18 Jul 2023 | Zone 4 LP99 | near SIA bldg | Tonight plan to lay Singtel, 18m. TMA on site, preparation works in progress
Tue (18/07) | 18 Jul 2023 | Loyang Ave LP112 |  | Tonight to continue trial trench for SPPG
Tue (18/07) | 18 Jul 2023 | Loyang Way LP23 |  | Tonight to continue trial trench for SPPG
Tue (18/07) | 18 Jul 2023 | Loyang Way opp LP72 |  | 2 teams working here tonight & plan to lay Singtel pipe, 30m
Tue (18/07) | 18 Jul 2023 | Loyang Way LP77 |  | SPTel works ongoing
Tue (18/07) | 18 Jul 2023 | MH6-1 |  | Works completed
Tue (18/07) | 18 Jul 2023 | Zone 2 LP199/1 |  | Manual TT for tree root removal
Wed (19/07) | 19 Jul 2023 | Loyang Way LP78 |  | SPTel works
Wed (19/07) | 19 Jul 2023 | Loyang Way | opp LP73 | Tonight plan Singtel pipe laying, 24m. Preparation works ongoing
Wed (19/07) | 19 Jul 2023 | BH162 |  | Drilling at 62m depth
Wed (19/07) | 19 Jul 2023 | BH2-3 |  | Today to remove formwork for 8th layer and start excavation for 9th layer
Wed (19/07) | 19 Jul 2023 | Loyang Way LP23 |  | Tonight plan to lay SPPG pipes, 3m. Now manually clearing soil prior installation
Wed (19/07) | 19 Jul 2023 | BH2-5 status |  | Today formwork closing for 4th layer and casting
Wed (19/07) | 19 Jul 2023 | Loyang Way LP19 |  | Tonight plan to lay SPPG pipes, 4m. Now waiting for tipper truck
Wed (19/07) | 19 Jul 2023 | Zone 4 |  | Safety briefing by utility engr for Singtel MX3 manhole installation at centre median (near LP113)
Wed (19/07) | 19 Jul 2023 | MH5-1 |  | To start excavation today. Starhub cable haven't retrieve so they still need to protect
Wed (19/07) | 19 Jul 2023 | LP23 |  | Continue manual clearing & shoring installation
Wed (19/07) | 19 Jul 2023 | Opp LP73 |  | Premix hacking & excavation works ongoing
Wed (19/07) | 19 Jul 2023 | LP23 |  | TT done. Found LV and 22kV
Wed (19/07) | 19 Jul 2023 | LP112 |  | TT done. Found Singtel, 300mm dia water pipe and metal pipe
Wed (19/07) | 19 Jul 2023 | Zone 4 |  | Singtel pipes laid, 18m
Wed (19/07) | 19 Jul 2023 | Opp LP72 |  | Singtel pipes laid, 38m
Wed (19/07) | 19 Jul 2023 | Zone 3 |  | Singtel pipe laying today, 9m
Wed (19/07) | 19 Jul 2023 | MH2-6 |  | Today plan to start excavation for 1st layer
Wed (19/07) | 19 Jul 2023 | MH2-5 |  | 4th layer casting done
Wed (19/07) | 19 Jul 2023 | Zone 2 |  | Singtel pipe laying, 12m
Wed (19/07) | 19 Jul 2023 | LP23 |  | Area reinstated. Housekeeping ongoing
Wed (19/07) | 19 Jul 2023 | LP112 |  | Area reinstated. Lane reopened
Wed (19/07) | 19 Jul 2023 | MH6-1 |  | Soft eye hacking and set up jacking machine
Wed (19/07) | 19 Jul 2023 | Opp LP72 |  | Works completed. Lane reopened
Wed (19/07) | 19 Jul 2023 | MH2-6 |  | First layer rebar installation
Wed (19/07) | 19 Jul 2023 | Exit 1 |  | No activity
Thu (20/07) | 20 Jul 2023 | Zone 3 P39 | retaining wall base hacking | Temporarily paused
Thu (20/07) | 20 Jul 2023 | BH37 |  | Boring ongoing, 29m
Thu (20/07) | 20 Jul 2023 | ST30-01 |  | Preboring by HSL & ST32: trimming work by Dongah
Thu (20/07) | 20 Jul 2023 | ST030-01 | 600mm | Preboring depth 20m, soil disposal ongoing
Thu (20/07) | 20 Jul 2023 | Zone 4 |  | Continue excavation for Singtel pipe laying. Plan to lay 5m
Thu (20/07) | 20 Jul 2023 | LP23 |  | SPPG pipes laid, 3m
Thu (20/07) | 20 Jul 2023 | Opp LP73 |  | Singtel pipe laying in progress
Thu (20/07) | 20 Jul 2023 | LP23 |  | Backfilling ongoing
Thu (20/07) | 20 Jul 2023 | Zone 4 Singtel |  | Connection to newly installed MX3. Laid 5m tonight
Thu (20/07) | 20 Jul 2023 | LP19 |  | SPPG pipes laid, 4m at 2.3m depth. Pipes laid below existing 22kV
Thu (20/07) | 20 Jul 2023 | Opp LP73 |  | Singtel pipes laid, 24m. Concrete haunching in progress
Thu (20/07) | 20 Jul 2023 | MH2-3 |  | Scaffold erection for 8m NB started
Thu (20/07) | 20 Jul 2023 | Bh165 |  | Drilling at 12m depth
Thu (20/07) | 20 Jul 2023 | ST30 |  | 2nd bite pre-coring on going
Thu (20/07) | 20 Jul 2023 | MH6-1 |  | Slurry pump installation on going
Thu (20/07) | 20 Jul 2023 | Loyang Way | Zone 3/4 | Middle lane closing for Power duct, target 3m laying today
Fri (21/07) | 21 Jul 2023 | MH2-7 |  | Excavation for 4th layer on going
Fri (21/07) | 21 Jul 2023 | Access diversion at gate 5 |  | Hardcore laying
Fri (21/07) | 21 Jul 2023 | Zone 2 exit 3 |  | TT for drain hacking along L.A done. To start hacking today
Fri (21/07) | 21 Jul 2023 | Zone 2 |  | Excavation for singtel pipe laying, to connect to existing manhole
Fri (21/07) | 21 Jul 2023 | Next to Gate 5 | fronting JTC | SPPG commenced excavation/ manual TT for pipe laying. PTD 893
Fri (21/07) | 21 Jul 2023 | MH6-1 |  | Preparing to insert frame at soft eye
Fri (21/07) | 21 Jul 2023 | ST30-1 |  | Preparing for LSS casting, ST32: trimming ongoing & internal koden ongoing
Fri (21/07) | 21 Jul 2023 | P39 | retaining wall | No activity
Fri (21/07) | 21 Jul 2023 | Near Gate 5 |  | Shoring by WG ongoing for SPPG pipe laying. Pipe arrangement may have to change due to limited space
Fri (21/07) | 21 Jul 2023 | MH6-1 |  | Jacking machine already set up. Hydraulic hose connection to hydraulic jack in progress. Today to complete and ready for jacking
Fri (21/07) | 21 Jul 2023 | ST32 |  | Trimming in progress, current depth is 35m
Sat (22/07) | 22 Jul 2023 | Zone 3 |  | Retaining wall base slab hacking
Sat (22/07) | 22 Jul 2023 | ULT9 |  | Set up for bidirectional test status..plan to start on Monday
Sat (22/07) | 22 Jul 2023 | Exit 1 |  | Excavation works for DW87 guidewall
Sat (22/07) | 22 Jul 2023 | Exit 1 |  | DW97 depth and bentonite check
Sat (22/07) | 22 Jul 2023 | Exit 1 |  | 2nd desander NB installation
Sat (22/07) | 22 Jul 2023 | Zone 2 |  | Scaffold erection for 8m NB status
Sat (22/07) | 22 Jul 2023 | MH2-3 |  | Trimming for 9th layer. Today to cast
Sat (22/07) | 22 Jul 2023 | Zone 2 |  | Excavation for singtel pipe laying. Target 8m today
Sat (22/07) | 22 Jul 2023 | Zone 2 South ramp |  | Sewer pipe at PD office dismantled last night. This afternoon to connect new pipe (2m below formation level)
Sat (22/07) | 22 Jul 2023 | MH5-1 |  | Excavation on going for 1st layer. Target to cast today
Sat (22/07) | 22 Jul 2023 | Zone 1 |  | MH1-2 drilling for waterstand pipe
Sat (22/07) | 22 Jul 2023 | Zone 1 |  | ABH14 drilling at 48m
Sat (22/07) | 22 Jul 2023 | Zone 1 Junction |  | Preparing to shift AE camera footing
Sat (22/07) | 22 Jul 2023 | ST29 |  | Trenching started
Sat (22/07) | 22 Jul 2023 | ST32 |  | End plate + waterstop installation
Sat (22/07) | 22 Jul 2023 | MH2-3 |  | Rebar installation in progress
Sat (22/07) | 22 Jul 2023 | MH5-1 |  | 1st ring (800mm depth) rebar installation on going. Lampost cable at 900mm depth and singtel at 1.1m depth
Sat (22/07) | 22 Jul 2023 | Zone 1 |  | AE camera footing and post shifted. LTA on the way to fix back the camera
Sat (22/07) | 22 Jul 2023 | Zone 1 |  | ABH14 drilling continue
Sat (22/07) | 22 Jul 2023 | MH6-1 |  | Final inspection prior tk jacking. RTO verifying the actual invert level of sewer pipe
Sat (22/07) | 22 Jul 2023 | MH6-1 |  | Inspection done. Approved for pipe jacking
Sat (22/07) | 22 Jul 2023 | DW97 |  | Circulation of bentonite
Sat (22/07) | 22 Jul 2023 | MH6-1 |  | Still settling technical issue for jacking machine. Today they work until 10PM. Tomorrow to continue repair
Sat (22/07) | 22 Jul 2023 | Gate 5 |  | Steel plate laying for access diversion
Sat (22/07) | 22 Jul 2023 | MH2-7 |  | Today to continue hacking and soil excavation for 4th layer
Sat (22/07) | 22 Jul 2023 | MH6-1 |  | Jacking frame tilted a bit and need to re-align. Mechanic on site. Once done alignment they will start jacking
Sat (22/07) | 22 Jul 2023 | ST32 |  | Final Koden test on going
Sun (23/07) | 23 Jul 2023 | ST029 |  | Internal koden test ongoing, 2nd bite completed earlier
Sun (23/07) | 23 Jul 2023 | Zone 3 JTC |  | ST32 rebar cage installation ongoing
Sun (23/07) | 23 Jul 2023 | Zone 3 |  | Railing painting works ongoing
Sun (23/07) | 23 Jul 2023 | Zone 4 |  | PUB contractor fixed the water pipe leakage, to backfill now. TMA provided
Sun (23/07) | 23 Jul 2023 | Zone 4 Loyang Way jn |  | DE143 shifting steel plates near the pavement
Sun (23/07) | 23 Jul 2023 | Zone 4 |  | The other 2 shingda teams also working at Loyang Way
Sun (23/07) | 23 Jul 2023 | Zone 2 |  | No activity
Sun (23/07) | 23 Jul 2023 | Zone 1 |  | No activity by other contractors
Sun (23/07) | 23 Jul 2023 | Exit 3 |  | New access lined with concrete barriers done. Soil leveling still ongoing
Sun (23/07) | 23 Jul 2023 | Zone 3 |  | WHDA plans to cast ST32 at 5pm. Preparation for casting ongoing
Sun (23/07) | 23 Jul 2023 | Near Exit 1 |  | Existing water pipe has been cut by Shingda. Waiting for new water pipe connection to be delivered
Sun (23/07) | 23 Jul 2023 | Zone 4 |  | 3rd Shingda team welding also ongoing
Sun (23/07) | 23 Jul 2023 | Near Exit 1 |  | Water pipe connection delivered
Sun (23/07) | 23 Jul 2023 | Zone 3 |  | Backfilling of demolished retaining wall area ongoing
Sun (23/07) | 23 Jul 2023 | Zone 4 |  | Backfilling for fixed PUB waterpipe has yet to start
Sun (23/07) | 23 Jul 2023 | Zone 3 |  | Railing painting works in progress
Sun (23/07) | 23 Jul 2023 | Zone 2 |  | Shifting of steel mould to MH2-7
Sun (23/07) | 23 Jul 2023 | Zone 3 |  | Backfilling done for the day. Canvas sheets laid of backfilled area
Sun (23/07) | 23 Jul 2023 | Near Exit 1 |  | Shingda welding in progress
Sun (23/07) | 23 Jul 2023 | ST032 |  | Casting ongoing (187m³/250m³)
Sun (23/07) | 23 Jul 2023 | DW097 |  | No boring work, just monitoring depth & continue bentonite circulation
Sun (23/07) | 23 Jul 2023 | Update for CR1070 Pt 2,3,4 Linkup at Loyang Way/Loyang Ave |  | All 3 pits link up & cap off completed, handed over for charging tmr morning, lanes at Loy Ave opened up to public
Mon (24/07) | 24 Jul 2023 | Loyang Way LP79 |  | Excavation ongoing for 18-way singtel pipe laying
Mon (24/07) | 24 Jul 2023 | Loyang Way LP19 | towards Loy Ave/CV | Preparing to commence work
Mon (24/07) | 24 Jul 2023 | Loyang Way LP27 | along Nidec | SPTel working along footpath
Mon (24/07) | 24 Jul 2023 | MH2-7 |  | Waiting for concrete lorry to cast 4th layer
Mon (24/07) | 24 Jul 2023 | Zone 2 exit 3 |  | Drain hacking in progress
Mon (24/07) | 24 Jul 2023 | BH166 |  | Drilling at 37m
Mon (24/07) | 24 Jul 2023 | MH2-3 NB |  | 12m today to complete scaffolding
Mon (24/07) | 24 Jul 2023 | MH6-1 |  | Jacking machine was send back to factory for repair
Mon (24/07) | 24 Jul 2023 | Zone 2 |  | Excavation for singtel pipe laying. 9m
Mon (24/07) | 24 Jul 2023 | MH5-1 |  | Access making in progress
Mon (24/07) | 24 Jul 2023 | MH1-2 |  | Instrumentation installation completed
Mon (24/07) | 24 Jul 2023 | Zone 1 ABH15 |  | Drilling started
Mon (24/07) | 24 Jul 2023 | ST29 |  | Koden test ongoing
Mon (24/07) | 24 Jul 2023 | Aft Loyang Ave slip Rd | LP19/1 | Lane closure by WG
Tue (25/07) | 25 Jul 2023 | Loyang Way LP75 |  | Dipcie team here to continue with singtel pipe laying
Tue (25/07) | 25 Jul 2023 | Zone 2 |  | Singtel to lay 9m today
Tue (25/07) | 25 Jul 2023 | Exit 1 desander |  | Noise barrier panels installation ongoing
Tue (25/07) | 25 Jul 2023 | BH165 |  | Packer test, BH166: drilling at 47m
Tue (25/07) | 25 Jul 2023 | ST29 |  | Water stop installation at ST30 side ongoing
Tue (25/07) | 25 Jul 2023 | North ramp N6 |  | TT on going
Tue (25/07) | 25 Jul 2023 | MH6-1 |  | Set up pump and hose connection work
Tue (25/07) | 25 Jul 2023 | Zone 3 JTC |  | ST25 TT ongoing. Sppg pipes will be laid at ST25 utility crossing
Tue (25/07) | 25 Jul 2023 | MH5-1 |  | Adjusting rebar to avoid singtel hunching. Revised drawing yet to submit for 1st layer
Tue (25/07) | 25 Jul 2023 | ST29 |  | Cage 3B&4B lapping status
Tue (25/07) | 25 Jul 2023 | MH6-1 |  | Shelter installation for materials storage area. Plan to bring back jacking machine by this afternoon or tomorrow morning
Tue (25/07) | 25 Jul 2023 | Loyang Way LP19 | opp Exit 1 gate | Dipcie team continue with their singtel pipe laying
Tue (25/07) | 25 Jul 2023 | Loyang Way LP19/1 |  | SPPG team continue with their TT here
Tue (25/07) | 25 Jul 2023 | BH165 |  | Depth at 44.5m
Tue (25/07) | 25 Jul 2023 | Loyang Way LP24 |  | Premix removal started, proceed with excavation & singtel pipe laying towards existing MH
Tue (25/07) | 25 Jul 2023 | MH2-5 |  | Rebar installation for 5th layer. To cast today
Wed (26/07) | 26 Jul 2023 | Loyang Ave LP112 |  | Lane closure by WG SPPG to continue with their pipe laying work
Wed (26/07) | 26 Jul 2023 | Zone 2 |  | TT for drain removal continue
Wed (26/07) | 26 Jul 2023 | BH165 |  | Drilling at 46.5m, BH166: drilling at 52m
Wed (26/07) | 26 Jul 2023 | MH2-3 |  | Today to lean concrete this part to continue 8m NB installation
Wed (26/07) | 26 Jul 2023 | MH2-3 |  | 9th layer formwork removal. Today to start 10th layer excavation
Wed (26/07) | 26 Jul 2023 | Loyang Way LP78 |  | Excavation for MX4 ongoing, plan for installation tonight
Wed (26/07) | 26 Jul 2023 | Loyang Lane LP3 |  | Lane closure by Dipcie
Wed (26/07) | 26 Jul 2023 | P18 |  | Excavation work for singtel pipe laying to connect at existing manhole. 7m
Wed (26/07) | 26 Jul 2023 | DW97 |  | First cage lowered
Wed (26/07) | 26 Jul 2023 | MH6-1 |  | Testing of jacking machine before lower down
Wed (26/07) | 26 Jul 2023 | MH2-3 |  | Formwork closing for lean concrete for 8m NB
Wed (26/07) | 26 Jul 2023 | MH2-6 |  | 2nd layer rebar works
Wed (26/07) | 26 Jul 2023 | Zone 2 |  | 7m singtel pipe laying
Wed (26/07) | 26 Jul 2023 | ST029 |  | Casting ongoing, vol: 51m³/325m³
Wed (26/07) | 26 Jul 2023 | DW097 |  | Casting started 9:35pm, total vol: 80m3, ~51m3 on site
Wed (26/07) | 26 Jul 2023 | DW-105 |  | 2nd bite excavation completed, now cutter welding work ongoing. will resume with cleaning & desanding work
Wed (26/07) | 26 Jul 2023 | Loyang Way LP17/18 |  | Premix cutting started for singtel pipe laying
Wed (26/07) | 26 Jul 2023 | MH2-7 |  | 4th layer to remove moulding and start 5th layer excavation
Wed (26/07) | 26 Jul 2023 | Loyang Way LP19/1 |  | Lane closure by WG to continue TT
Thu (27/07) | 27 Jul 2023 | Loyang avenue zone 3 |  | Continue excavation for singtel pipe laying. Expected services here LV. At 1.1m depth
Thu (27/07) | 27 Jul 2023 | MH2-3 |  | Excavation for 10th layer ongoing
Thu (27/07) | 27 Jul 2023 | ST25 |  | TT on going. So far no utility found
Thu (27/07) | 27 Jul 2023 | BH153 |  | Drilling at 38m depth
Thu (27/07) | 27 Jul 2023 | MH2-5 | 5th layer | No activity
Thu (27/07) | 27 Jul 2023 | PRD3 |  | Powergrid works ongoing
Thu (27/07) | 27 Jul 2023 | Zone 1 P4 |  | BH15 grouting in progress. Depth at 56.42m
Thu (27/07) | 27 Jul 2023 | Zone 1 LA |  | No lane closures. DE143 works near AWWA
Thu (27/07) | 27 Jul 2023 | MH1-2 |  | No activity. Instruments installed
Thu (27/07) | 27 Jul 2023 | Zone 3 DR2 |  | Today slope cutting in preparation for sheet pile installation. Vibro to mob in today. Tomorrow sheet pile delivery
Thu (27/07) | 27 Jul 2023 | MH5-2 |  | No activity
Thu (27/07) | 27 Jul 2023 | DW105 |  | Koden test on going
Thu (27/07) | 27 Jul 2023 | MH5-1 |  | Ladder installation ongoing
Thu (27/07) | 27 Jul 2023 | MH2-7 |  | Hacking ongoing for 5th layer construction
Thu (27/07) | 27 Jul 2023 | Zone 3 |  | Singtel pipe laying ongoing, 4m. Yesterday laid 3m
Thu (27/07) | 27 Jul 2023 | MH6-1 |  | Boring machine spoiled again. Was hoist up and checking in progress. 🙊🙈
Thu (27/07) | 27 Jul 2023 | ST24A |  | Trial trench on going
Thu (27/07) | 27 Jul 2023 | Zone 3 |  | Singtel pipe laid 4m today. Backfilling on going
Thu (27/07) | 27 Jul 2023 | MH6-1 |  | Jacking pipe extension on going. Boring machine already in about 2m
Thu (27/07) | 27 Jul 2023 | P24 | along the previous PCN / drain | Levelling work ongoing
Fri (28/07) | 28 Jul 2023 | MH5-1 |  | No activity
Fri (28/07) | 28 Jul 2023 | Zone 1 ABH-16 |  | Removal of rigid pavement prior to TT
Fri (28/07) | 28 Jul 2023 | Zone 2 South Ramp |  | Excavation & soil disposal ongoing
Fri (28/07) | 28 Jul 2023 | North Ramp N5 |  | TT ongoing by LE
Fri (28/07) | 28 Jul 2023 | N2 |  | Previous PCN / footpath removal completed, balance hardcore removal & rebar cutting
Fri (28/07) | 28 Jul 2023 | N3 |  | Target to commence removal after lunch
Fri (28/07) | 28 Jul 2023 | Zone 3 |  | WG (2 teams) excavation for Singtel pipe laying
Fri (28/07) | 28 Jul 2023 | MH2-3 |  | Scaffold erection for NB 8m ongoing
Fri (28/07) | 28 Jul 2023 | MH2-3 |  | 10th layer curing
Fri (28/07) | 28 Jul 2023 | Zone 2 P20 |  | TT ongoing by dipcie team, locating 200mm dia water pipe
Fri (28/07) | 28 Jul 2023 | Zone 3 |  | 40nos of props available to cover 20m of the canal. Sheetpiles for DR2 to be delivered by tmr. Silent piler to arrive next wk
Fri (28/07) | 28 Jul 2023 | MH2-7 |  | 5th layer hacking cont
Fri (28/07) | 28 Jul 2023 | MH2-5 |  | Excavation for 6th layer
Fri (28/07) | 28 Jul 2023 | Zone 2 P20 |  | Excavation for singtel pipe laying. 11m
Fri (28/07) | 28 Jul 2023 | N5 |  | TT on going. 3 sides completed. Last side TT on going
Fri (28/07) | 28 Jul 2023 | N2 |  | Previous PCN+retaining wall hacking completed. Tomorrow LE can start here
Fri (28/07) | 28 Jul 2023 | MH6-1 |  | 2nd pipe jacking done. Placing 3rd pipe for jacking
Fri (28/07) | 28 Jul 2023 | MH2-5 |  | Excavation to 6th layer in progress. Tonight they work until 10PM
Sat (29/07) | 29 Jul 2023 | Zone 3 |  | EL here waiting for the delivery of sheet piles. Vibro here
Sat (29/07) | 29 Jul 2023 | BH36 |  | Drilling at 32m
Sat (29/07) | 29 Jul 2023 | DW109 |  | Waiting for rebar cage delivery. Expected today 1pm
Sat (29/07) | 29 Jul 2023 | Zone 3 |  | Premix removal for sppg pipe laying. Today target 6m
Sat (29/07) | 29 Jul 2023 | Zone 2 |  | TT for drain removal at singtel manhole
Sat (29/07) | 29 Jul 2023 | zone 2 |  | Excavation for singtel pipe laying. Today target 6m
Sat (29/07) | 29 Jul 2023 | PMH3 |  | Shifting access ladder as per SPPG comment
Sat (29/07) | 29 Jul 2023 | MH6-1 |  | Penetration depth now at 14.8m. Est 1m more to go before can reach to next existing manhole
Sat (29/07) | 29 Jul 2023 | Zone 3 |  | WH doing setting out for the new ECM pond
Sat (29/07) | 29 Jul 2023 | BH36 |  | Packer test on going at 36m
Sat (29/07) | 29 Jul 2023 | ULT10 |  | Instrument setting up for testing
Sat (29/07) | 29 Jul 2023 | DW109 |  | Onlyb2 rebar cages can be deliver today at 4pm. Balance 2 cages have comments from QPS during inspection at the fabrication yard. Target to deliver by Monday
Sat (29/07) | 29 Jul 2023 | Zone 3 junction |  | SPPG pipe laying on going
Sat (29/07) | 29 Jul 2023 | Zone 4 |  | DE143 working inside their boundary
Sat (29/07) | 29 Jul 2023 | N2 |  | TT for pile cap ERSS on going
Sat (29/07) | 29 Jul 2023 | MH2-7 |  | 5th layer trimming. Today plan to cast
Sat (29/07) | 29 Jul 2023 | MH6-1 |  | Pipe installation to continue jacking. Current penetration depth at 8.8m
Sat (29/07) | 29 Jul 2023 | Zone 2 drain hacking status |  | Balance 50-75m
Sat (29/07) | 29 Jul 2023 | ST25 |  | Formwork closing
Sat (29/07) | 29 Jul 2023 | ST30 |  | Preparing to remove end plate at St29 side
Sun (30/07) | 30 Jul 2023 | Zone 1 NLL |  | Kingview working within their barricaded area
Sun (30/07) | 30 Jul 2023 | Zone 1 |  | No other activity
Sun (30/07) | 30 Jul 2023 | Exit 3 |  | 4 nos. Banners installation ongoing
Sun (30/07) | 30 Jul 2023 | Zone 3 |  | IC hacking ongoing for MH6-1. To complete hacking and retrieve pipe jacking equipment today
Sun (30/07) | 30 Jul 2023 | Zone 3 |  | JTC hoarding installation ongoing
Sun (30/07) | 30 Jul 2023 | Zone 3 |  | Status of backfilled area at retaining wall. Some backfilling was done this morning
Sun (30/07) | 30 Jul 2023 | Exit 1 |  | No activity
Sun (30/07) | 30 Jul 2023 | Zone 3 |  | Premix cutting for new ECM pond
Sun (30/07) | 30 Jul 2023 | Exit 3 |  | BH192 and BH08 TT in progress. No services found thus far
Sun (30/07) | 30 Jul 2023 | MH6-1 |  | Existing IC hacking still ongoing
Sun (30/07) | 30 Jul 2023 | Zone 3 |  | JTC new hoarding installation more than halfway done
Sun (30/07) | 30 Jul 2023 | Exit 1 |  | Ground levelling ongoing
Sun (30/07) | 30 Jul 2023 | Zone 2 |  | ABH93 TT in progress
Sun (30/07) | 30 Jul 2023 | Zone 2 |  | ABH92 TT ongoing
Sun (30/07) | 30 Jul 2023 | JTC ST30 |  | Rebar cage 2A & 3A lapping in progress
Sun (30/07) | 30 Jul 2023 | Exit 1 |  | No activity
Sun (30/07) | 30 Jul 2023 | Zone 3 & 4 |  | Tonight no activity by Wee Guan/Dipcie
Sun (30/07) | 30 Jul 2023 | Zone 3 |  | ST25, 24A guidewall formwork in progress. Plan to cast today
Mon (31/07) | 31 Jul 2023 | LP17 |  | Excavation ongoing
Mon (31/07) | 31 Jul 2023 | MH2-6 |  | 3rd layer excavation
Mon (31/07) | 31 Jul 2023 | ST 30 |  | Casting completed at 1:30pm. Total vol: 289.0cm3
Mon (31/07) | 31 Jul 2023 | MH2-6 |  | Excavation continue
Mon (31/07) | 31 Jul 2023 | ST24A & ST25 |  | Guidewall fwk removal ongoing
Mon (31/07) | 31 Jul 2023 | Zone 2 |  | Excavation for singtel pipe laying. 6m
Mon (31/07) | 31 Jul 2023 | Loyang Way/ Ave Junction | LP116 | WG working here for sppg pipe laying
Mon (31/07) | 31 Jul 2023 | Loyang Way LP20 |  | Singtel working here
Mon (31/07) | 31 Jul 2023 | Exit 3 |  | Premix cutting for ST20 trial trench ongoing
Mon (31/07) | 31 Jul 2023 | DW109 |  | Cleaning ongoing
Mon (31/07) | 31 Jul 2023 | Zone 1 |  | ABH16 TT in.progress
Mon (31/07) | 31 Jul 2023 | Zone 1 |  | Singtel contractor here doing cable pulling. Not under our WO
Mon (31/07) | 31 Jul 2023 | LV blk 222 |  | Noise level captured so far ok
Mon (31/07) | 31 Jul 2023 | ST30 |  | Hanging bar installed & casting platform setup done. Now tremie pipe installation. Concrete ordered. Est total vol: 255m3
Mon (31/07) | 31 Jul 2023 | ST30 |  | Casting started
Mon (31/07) | 31 Jul 2023 | Zone 2 NB |  | Housekeeping
Mon (31/07) | 31 Jul 2023 | ULT10 |  | 1st cycle in progress, 100% load (6hrs holding time)
Mon (31/07) | 31 Jul 2023 | Exit 1 DW109 |  | Cage 1B and 2B lapping ongoing
Mon (31/07) | 31 Jul 2023 | Loyang Way LP17 | near Selarang Camp | Tonight plan to lay Singtel 6m. Road cutting in progress
Mon (31/07) | 31 Jul 2023 | Loyang Way LP19/1 |  | Excavation in progress for SPPG. This area has Starhub, 22kV & LV. Likely tonight only plan for excavation and shoring installation
Mon (31/07) | 31 Jul 2023 | Loyang Way near LP118S1 |  | Road cutting in progress for SPPG trial trench
Tue (01/08) | 01 Aug 2023 | MH2-5 |  | No activity
Tue (01/08) | 01 Aug 2023 | MH2-1 |  | Drilling for waterstand pipe installation
Tue (01/08) | 01 Aug 2023 | Loyang Ave LP105 |  | Excavation commenced for MX3 installation, TMA provided. Target to install ard 11:45pm~12am
Tue (01/08) | 01 Aug 2023 | MH2-3 |  | Today to continue 11th layer
Tue (01/08) | 01 Aug 2023 | Zone 3 Loyang Way LP 73 |  | Premix removal completed
Tue (01/08) | 01 Aug 2023 | ULT10- 2nd cycle |  | Applied load 150%. Jack opening is around 10mm
Tue (01/08) | 01 Aug 2023 | Zone 2 LVC side |  | 6m NB to be replaced with 8m hoarding for the construction of MH2-4
Tue (01/08) | 01 Aug 2023 | Zone 3 Loyang Way | Krislite Bldg | SPTel working here
Tue (01/08) | 01 Aug 2023 | MH5-1 |  | Barricade installation ongoing
Tue (01/08) | 01 Aug 2023 | Exit 3 |  | Depcie levelling for singtel pipe laying
Tue (01/08) | 01 Aug 2023 | DW109 |  | First truck on site
Tue (01/08) | 01 Aug 2023 | 2nd truck arrived. Casting started. Est total vol |  | 90m3
Tue (01/08) | 01 Aug 2023 | LP17 |  | Manual excavation in progress. Location is packed with utilities — 22kV, starhub, Xenith
Tue (01/08) | 01 Aug 2023 | LP19/1 |  | Continue manual clearing of soil beneath the services
Tue (01/08) | 01 Aug 2023 | LP118S1 |  | Trial trench completed. Found drain slab at 300mm. Pending premix reinstatement
Tue (01/08) | 01 Aug 2023 | LP19/1 |  | SPPG pipe laid, 3m
Tue (01/08) | 01 Aug 2023 | LP17 |  | Unable to lay pipes tonight due to area packed with services
Tue (01/08) | 01 Aug 2023 | LP17 |  | Lane reopened
Tue (01/08) | 01 Aug 2023 | DW109 completed at 0515am. Total vol |  | 98m3
Tue (01/08) | 01 Aug 2023 | MH5-1 |  | Support installation for Lamp post cable
Tue (01/08) | 01 Aug 2023 | MH2-3 |  | Excavation to 11th layer in progress
Tue (01/08) | 01 Aug 2023 | MH2-3 |  | 11th layer excavation ongoing
Tue (01/08) | 01 Aug 2023 | DW104 |  | 2nd bite excavation ongoing, 15.5m depth
Tue (01/08) | 01 Aug 2023 | Loyang Way LP 23 | ATT-WG-117 | Dipcie team started rigid pavement removal
Tue (01/08) | 01 Aug 2023 | Loyang Lane near exit 3 |  | ST20 trial trench ongoing
Tue (01/08) | 01 Aug 2023 | Loyang Way LP19/1 |  | Lane closure by WG, 2 TMO on site
Tue (01/08) | 01 Aug 2023 | BH165 |  | Drilling ongoing, 53.5m
Tue (01/08) | 01 Aug 2023 | BH168 |  | In progress, 32.5m
Wed (02/08) | 02 Aug 2023 | Exit 1- DW104 |  | Cage A (2/2 lapping in progress). Cage B (1/2 cage lowered down)
Wed (02/08) | 02 Aug 2023 | Loyang Way LP 83 | 18-way Singtel | Dipcie team commence excavation for pipe laying work. Opp SPTel working
Wed (02/08) | 02 Aug 2023 | Zone 3 |  | Taiyo plans to complete trial trenches for first 2 piles then mobilise their machinery in
Wed (02/08) | 02 Aug 2023 | Loyang Way LP23 | ATT-WG-117 | Completed TT, backfilling / compaction ongoing. Trying to locate drain top slab
Wed (02/08) | 02 Aug 2023 | Zone 4 Loyang Ave LP 105 | 12way Singtel | Excavation ongoing for pipe laying
Wed (02/08) | 02 Aug 2023 | Zone 3 Loyang Way LP19/1 |  | Waiting for last bus to close the slip rd, continue pipe laying work. 2 TMO on site. As of now, no activity
Wed (02/08) | 02 Aug 2023 | DW104 |  | Casting completed. Total volume: 99cum
Wed (02/08) | 02 Aug 2023 | Zone 3 Loyang Way LP 70 -135) | ATT-WG(D | 2 nos TT ongoing prior to manhole installation
Wed (02/08) | 02 Aug 2023 | DW104 | MC96 | 2nd & 3rd bite excavation work completed
Wed (02/08) | 02 Aug 2023 | Exit 3 |  | 6m pipe laid. To excavate location of MH
Wed (02/08) | 02 Aug 2023 | Zone 2 singtel MH |  | Trial trench on going
Wed (02/08) | 02 Aug 2023 | Zone 2 |  | Erection of scaffold for 8m NB behind MH2-4, to replace 6m NB
Wed (02/08) | 02 Aug 2023 | Zone 2 LP199/2 |  | Dipcie to lay Singtel pipe today, 8m
Wed (02/08) | 02 Aug 2023 | Zone 1 ABH16 |  | Drilling and SPT ongoing, 10m
Wed (02/08) | 02 Aug 2023 | Zone 1 LA |  | DE143 works near AWWA. No other activity
Wed (02/08) | 02 Aug 2023 | MH1-2 |  | No activity
Wed (02/08) | 02 Aug 2023 | MH2-3 |  | Pending to cast 11th layer
Wed (02/08) | 02 Aug 2023 | DW104 | MC96 | 3rd bite cleaning started
Wed (02/08) | 02 Aug 2023 | Zone 3 |  | WG completed excavation for MX2 singtel manhole to be installed tonight
Wed (02/08) | 02 Aug 2023 | Exit 2 | ST028 | 1st bite excavation work resumed at 3am & current depth at 27.50m from the GWTL
Wed (02/08) | 02 Aug 2023 | ST28 |  | Trenching continue at 34.8m depth
Wed (02/08) | 02 Aug 2023 | ST31 |  | 1st pre boring reached 34m. Tomorrow to start 2nd point
Wed (02/08) | 02 Aug 2023 | Exit 3 |  | Singtel manhole for tonight's installation
Wed (02/08) | 02 Aug 2023 | MH2-6 |  | Hacking ongoing for 3rd layer works
Wed (02/08) | 02 Aug 2023 | ST028 |  | First bite excavation ongoing, now hoisting up cutter due to mud drum problem
Wed (02/08) | 02 Aug 2023 | BH165 |  | In progress, 52.5m
Wed (02/08) | 02 Aug 2023 | BH168 |  | In progress, 34m
Wed (02/08) | 02 Aug 2023 | Zone 2 |  | Briefing for MX4 installation done
Wed (02/08) | 02 Aug 2023 | ST029 |  | LSS completed at 19:50, vol: 18m3
Wed (02/08) | 02 Aug 2023 | MH2-5 |  | No activity
Thu (03/08) | 03 Aug 2023 | Zone 3 loyang way |  | Excavation for singtel pipe laying
Thu (03/08) | 03 Aug 2023 | Zone 3 loyang way junction |  | Excavation for SPPG pipe laying
Thu (03/08) | 03 Aug 2023 | Zone 4 loyang avenue |  | Excavation for singtel pipe laying
Thu (03/08) | 03 Aug 2023 | MH2-5 |  | Excavation to 7th layer in progress
Thu (03/08) | 03 Aug 2023 | MH2-7 |  | Preparing for 5th layer formwork removal and continue excavation
Thu (03/08) | 03 Aug 2023 | ST | 20 | Manual trial trench works to check for utilities
Thu (03/08) | 03 Aug 2023 | MH2-5 |  | Continual excavation work for 7th layer
Thu (03/08) | 03 Aug 2023 | MH2-3 |  | No activity. 11th layer cast yesterday
Thu (03/08) | 03 Aug 2023 | Z2 |  | Singtel Pipe laying - 6m laid. Preparing for reinstatement works now
Thu (03/08) | 03 Aug 2023 | Zone 1 | ABH16 | Drilling in progress, current depth 26m
Thu (03/08) | 03 Aug 2023 | MH5-1 |  | Manual excavation in progress for 2nd layer
Thu (03/08) | 03 Aug 2023 | ST20 |  | Singtel, 22kV and water pipe found
Thu (03/08) | 03 Aug 2023 | MH2-7 |  | Excavation ongoing for 6th layer
Thu (03/08) | 03 Aug 2023 | Exit 2 - ST028 | SC40 | 1st bite excavation work completed at 5am, depth 39.40m from GWTL
Thu (03/08) | 03 Aug 2023 | ST28 |  | 2nd bite trenching at 33.3m
Thu (03/08) | 03 Aug 2023 | Zone 3 loyang way junction |  | Excavation for SPPG pipe laying. Target here tonight 6m
Thu (03/08) | 03 Aug 2023 | Zone 3 loyang way |  | Waiting for the last bus to close slip road for sppg pipe laying. Target here tonight is 4m
Thu (03/08) | 03 Aug 2023 | Loyang way in frong of 64+4 |  | Depcie team 2 for singtel pipe laying
Fri (04/08) | 04 Aug 2023 | ST214 |  | TT done. Found Starhub and HT
Fri (04/08) | 04 Aug 2023 | Zone 3 loyang way junction |  | Excavation for SPPG pipe laying
Fri (04/08) | 04 Aug 2023 | P6 |  | Dipcie prepare area to continue pipe laying
Fri (04/08) | 04 Aug 2023 | Zone 4 |  | Excavation work for singtel manhole installation. (Mx3)
Fri (04/08) | 04 Aug 2023 | ABH-16 |  | Current 28m depth, team at ABH-92 for grouting work, they’ll resume work once completed
Fri (04/08) | 04 Aug 2023 | Exit 1 |  | DW103 trenching on going
Fri (04/08) | 04 Aug 2023 | Zone 2 |  | Dipcie to lay 6m at drain demolition area
Fri (04/08) | 04 Aug 2023 | MH5-1 |  | Today plan to cast 2nd layer
Fri (04/08) | 04 Aug 2023 | Gate 5 |  | WG manual excavation ongoing. To lay 3m of SPPG pipes
Fri (04/08) | 04 Aug 2023 | MH2-7 |  | Layer 6 in progress. Now temporarily stopped due to mini excavator hydraulic issue. Mechanic otw
Fri (04/08) | 04 Aug 2023 | ST140&ST141 |  | Guidewall formwork closing in progress. Today to cast
Fri (04/08) | 04 Aug 2023 | Zone 4 Slip road closed |  | Premix removal on going
Fri (04/08) | 04 Aug 2023 | ST28 |  | 2nd bite trenching continue at 35.6m
Fri (04/08) | 04 Aug 2023 | Zone 3 loyang way |  | May not able to lay pipes tonight due to existing services
Fri (04/08) | 04 Aug 2023 | Zone 3 loyang way junction |  | Unable to lay pipes due to existing services
Fri (04/08) | 04 Aug 2023 | MH2-6 |  | 3rd layer formwork dismantling ongoing
Fri (04/08) | 04 Aug 2023 | BH165 |  | Current depth 55.5m. Packer test in progress
Fri (04/08) | 04 Aug 2023 | BH168 |  | In progress, 41m
Fri (04/08) | 04 Aug 2023 | MH5-1 |  | 2nd layer rebar works in progress
Fri (04/08) | 04 Aug 2023 | Zone 2 P6 |  | Found starhub & 300mm dia water pipe at 800mm depth. Unable to lay pipe today. Plan to continue extending the trench prior to pipe laying
Fri (04/08) | 04 Aug 2023 | Zone 4 |  | Singtel pipe laying works completed. Premix on going
Fri (04/08) | 04 Aug 2023 | ST28 |  | 2nd bite cleaning in progress
Fri (04/08) | 04 Aug 2023 | ST28 |  | Positioning BC cutter for lock plate welding. Afterwhich they will trim 3rd bite
Fri (04/08) | 04 Aug 2023 | Zone 2 |  | 8m NB scafgold erection till 9pm
Fri (04/08) | 04 Aug 2023 | MH5-1 |  | 2nd layer casting on going
Fri (04/08) | 04 Aug 2023 | Zone 2 P6 |  | Depcie Dayshift team working till 10 pm for singtel pipe laying
Fri (04/08) | 04 Aug 2023 | BH165 |  | In progress, 53m
Fri (04/08) | 04 Aug 2023 | BH168 |  | In progress, 40m
Fri (04/08) | 04 Aug 2023 | MH2-3 |  | No activity
Fri (04/08) | 04 Aug 2023 | Zone 3 loyang way LP 74 |  | Lane closure for TT for singtel MH installation
Sat (05/08) | 05 Aug 2023 | Zone 3 loyang way LP70 |  | Excavation work for manhole installation
Sat (05/08) | 05 Aug 2023 | MH5-1 |  | Ventilation fan installation for sewer shaft work
Sat (05/08) | 05 Aug 2023 | ST28 |  | Water stop installed
Sat (05/08) | 05 Aug 2023 | Zone 4 loyang way |  | Singtel manhole MX3 safely installed
Sat (05/08) | 05 Aug 2023 | Zone 3 Loyang way junction |  | Pipe laying on going
Sat (05/08) | 05 Aug 2023 | Zone 3 loyang way LP74 |  | TT completed. No services found
Sat (05/08) | 05 Aug 2023 | MH2-7 |  | Excavation for 7th layer ring casting in progress
Sat (05/08) | 05 Aug 2023 | ST28 |  | Trimming completed. Now extracting cutter body then remove end plate
Sat (05/08) | 05 Aug 2023 | Zone 4 slip road |  | Work completed. Road marking on going
Sat (05/08) | 05 Aug 2023 | Zone 3 Loyang way LP74 |  | Work completed. Premix reinstated and lane opened
Sat (05/08) | 05 Aug 2023 | Zone 4 loyang way |  | TT for SPPG pipe corrridor
Sat (05/08) | 05 Aug 2023 | Zone 4 loyang way junction |  | Area enclose for sppg pipe laying tonight
Sat (05/08) | 05 Aug 2023 | Exit 1 DW103 |  | 4/4 cages installation on going. Balance hanging bar. Target to cast by 11pm
Sat (05/08) | 05 Aug 2023 | Zone 3 loyang way LP17 |  | Excavation work for singtel pipe laying
Sat (05/08) | 05 Aug 2023 | MH2-6 |  | Ventilation fan installation
Sat (05/08) | 05 Aug 2023 | MH2-5 |  | Yesterday cast the 7th layer ring
Sun (06/08) | 06 Aug 2023 | P06 |  | No activity by dipcie team
Sun (06/08) | 06 Aug 2023 | MH5-1 |  | No activity
Sun (06/08) | 06 Aug 2023 | Zone 3 | ST021 | TT ongoing
Sun (06/08) | 06 Aug 2023 | Exit 2 | ST 028 | 4A & 3A lapping in progress
Sun (06/08) | 06 Aug 2023 | P36 |  | WH commence with manual excavation for 4 nos hoarding footing
Sun (06/08) | 06 Aug 2023 | Exit 1 |  | KTC hardcore levelling ongoing
Sun (06/08) | 06 Aug 2023 | Loyang Way LP18 |  | Singtel cable pulling ongoing (not under our WO)
Sun (06/08) | 06 Aug 2023 | Loyang Way LP 25 |  | Shingda working here
Sun (06/08) | 06 Aug 2023 | Loyang Way LP80 |  | No activity by other contractor
Sun (06/08) | 06 Aug 2023 | Zone 3 loyang way |  | MH cover installation. Lane to be open by 630 am
Sun (06/08) | 06 Aug 2023 | ST28 |  | Casting in progress. Est total vol, 270m3
Sun (06/08) | 06 Aug 2023 | Exit 1 |  | No activity
Sun (06/08) | 06 Aug 2023 | ST28 |  | Progressive vol, 71.5m3
Sun (06/08) | 06 Aug 2023 | MH2-7 |  | 6th layer hacking ongoing
Sun (06/08) | 06 Aug 2023 | MH2-3 | 12th layer | No activity
Sun (06/08) | 06 Aug 2023 | MH2-5 | 7th layer | Curing only
Sun (06/08) | 06 Aug 2023 | P21 | 8m noise barrier scaffold | No activity
Mon (07/08) | 07 Aug 2023 | MH2-7 |  | 6th layer casting ongoing
Mon (07/08) | 07 Aug 2023 | Loyang Lane LP5 |  | SPTel has 2 teams working tonight for pipe laying. Plan 24m
Mon (07/08) | 07 Aug 2023 | Zone 2 |  | Setting up 6m NB for POB pile crashing
Mon (07/08) | 07 Aug 2023 | N3 |  | Pre boring for casing installation started this morning. Apparently rig breakdown
Mon (07/08) | 07 Aug 2023 | Zone 2 |  | ABH94 drilling started
Mon (07/08) | 07 Aug 2023 | Zone 1 | ABH-16 | ~56m depth, now worker go rest
Mon (07/08) | 07 Aug 2023 | DW110 |  | 1st bite excavation started
Mon (07/08) | 07 Aug 2023 | Casting completed at 0215hrs. Total vol |  | 285m3
Mon (07/08) | 07 Aug 2023 | Zone 1 WP diversion | by krishco | 2 nos TT completed as of today
Mon (07/08) | 07 Aug 2023 | ST31 1st bite |  | Current excavation depth, 10m
Mon (07/08) | 07 Aug 2023 | MH2-7 |  | 6th layer inspection. Plan for casting tonight
Mon (07/08) | 07 Aug 2023 | Zone 2 P21 |  | Continue scaffold installation & housekeeping
Mon (07/08) | 07 Aug 2023 | JTC ST31 |  | First bite excavation in progress
Mon (07/08) | 07 Aug 2023 | Zone 3 ST42-43 |  | Guidewall cast earlier today. Levelling ongoing
Mon (07/08) | 07 Aug 2023 | Exit 1 DW110 |  | 2nd bite excavation in progress, 7m
Mon (07/08) | 07 Aug 2023 | Loyang Way LP17 |  | Today plan for Singtel pipe laying, 10m
Mon (07/08) | 07 Aug 2023 | Loyang Way/Ave slip rd LP121 |  | Today plan for SPPG pipe laying, 3m. Slip road will be closed for machinery movement. APOs on standby
Mon (07/08) | 07 Aug 2023 | Loyang Way LP23 |  | Road hacking ongoing for SPPG trial trench
Tue (08/08) | 08 Aug 2023 | 8m hoarding behind MH2-4 |  | Preparation for NB panel installation
Tue (08/08) | 08 Aug 2023 | Zone 4 |  | Excavation for pipe laying in progress
Tue (08/08) | 08 Aug 2023 | Zone 4 |  | Trial trench ongoing
Tue (08/08) | 08 Aug 2023 | LP23 |  | Trial trench ongoing
Tue (08/08) | 08 Aug 2023 | LP17 |  | To continue manual trial trench here. Workers currently on break
Tue (08/08) | 08 Aug 2023 | Loyang Lane LP5 and LP4 |  | Excavation and pipe laying works ongoing
Tue (08/08) | 08 Aug 2023 | Zone 3 along sidetable of loyang lane |  | Manual excavation by Wee guan for Power duct laying. Target to lay 3m today
Tue (08/08) | 08 Aug 2023 | MH2-6 |  | Preparation for 4th layer excavation
Tue (08/08) | 08 Aug 2023 | MH2-5 |  | Water pumping to continue excavation works
Tue (08/08) | 08 Aug 2023 | LP23 |  | Trial trench for SPPG completed (ATT-WG-073). Drain top & BRC. Premix reinstatement ongoing
Tue (08/08) | 08 Aug 2023 | LP17 |  | Managed to lay Singtel 7m tonight
Tue (08/08) | 08 Aug 2023 | LP17 |  | Concrete haunching done. Backfilling ongoing
Tue (08/08) | 08 Aug 2023 | MH5-1 |  | 3rd layer excavation. Plan to cast today
Tue (08/08) | 08 Aug 2023 | ST31 |  | First bite excavation completed. Depth at 38.2m. BC cutter cleaning ongoing
Tue (08/08) | 08 Aug 2023 | DW110 |  | 2nd bite completed earlier tonight. Currently no activity
Tue (08/08) | 08 Aug 2023 | ST31 |  | 2nd bite trenching on going. Depth 9m
Tue (08/08) | 08 Aug 2023 | Loyang Way LP17 |  | Lane reopened. Footpath casting ongoing. Alternate footpath at sidetable to be opened to divert pedestrian access
Tue (08/08) | 08 Aug 2023 | Zone 3 lincstech area |  | 2.4m hoarding installation
Tue (08/08) | 08 Aug 2023 | Zone 3 loyang avenue |  | Premix cutting for the construction of ECM pond
Tue (08/08) | 08 Aug 2023 | Zone 2 P21 |  | Noise barrier panel installation ongoing
Tue (08/08) | 08 Aug 2023 | JTC ST31 |  | 2nd bite excavation in progress, 26.6m
Tue (08/08) | 08 Aug 2023 | Loyang Lane LP5-4 |  | SPTel preparation works ongoing. Today plan to continue pipe laying, 24m (2 teams)
Tue (08/08) | 08 Aug 2023 | Loyang Way LP74-69 |  | M&P by other contractor
Tue (08/08) | 08 Aug 2023 | Loyang Way/Ave junction LP121 |  | Tonight plan to continue SPPG pipe laying here. Now removing premix
Tue (08/08) | 08 Aug 2023 | Zone 4 LP99 | near SIA bldg | Tonight 2 teams here for Singtel — 1 for pipe laying, 1 for trial trench. Preparation works ongoing, TMA on site
Tue (08/08) | 08 Aug 2023 | Loyang Way LP23 |  | DE143 casting works nearby
Tue (08/08) | 08 Aug 2023 | Loyang Way LP23 |  | DE143 casting completed. WG to proceed works here. Tonight plan for SPPG pipe laying, 6m
Wed (09/08) | 09 Aug 2023 | DW110 |  | 4/4nos rebar cages completed. Hanging bar installation ongoing
Wed (09/08) | 09 Aug 2023 | LP23 |  | SPPG pipe laying in progress
Wed (09/08) | 09 Aug 2023 | Zone 4 |  | Manually clearing area before lay pipe
Wed (09/08) | 09 Aug 2023 | Zone 4 |  | TT completed. Found HV & LV
Wed (09/08) | 09 Aug 2023 | LP23 |  | SPPG pipes laid, 6m
Wed (09/08) | 09 Aug 2023 | Zone 4 LP99 |  | Singtel pipes laid, 8m
Wed (09/08) | 09 Aug 2023 | JTC ST31 |  | 2nd bite trimming ongoing
Wed (09/08) | 09 Aug 2023 | ST31 |  | Trimming completed
Wed (09/08) | 09 Aug 2023 | Exit 1 DW110 |  | 3/4nos rebar cage lowered
Thu (10/08) | 10 Aug 2023 | MH2-5 |  | 8th layer excavation ongoing
Thu (10/08) | 10 Aug 2023 | P21 |  | Continue NB panel installation
Thu (10/08) | 10 Aug 2023 | North ramp ST422 |  | Affected pile is N1 and P10. Rebar cage on site is N1 and P11. Now HSL is shifting their materials at P11 and working platform preparation for boring
Thu (10/08) | 10 Aug 2023 | ABH94 |  | SPT at 20m
Thu (10/08) | 10 Aug 2023 | Loyang Way | next to 64+4 | SPTel working here also
Thu (10/08) | 10 Aug 2023 | Loyang Way LP79 onwards |  | No activity by other contractor
Thu (10/08) | 10 Aug 2023 | Zone 2 P6 |  | Hacking for singtel pipe laying. Target 8m today
Thu (10/08) | 10 Aug 2023 | Gate 5 |  | WG to lay 3m sppg pipes today
Thu (10/08) | 10 Aug 2023 | Zone 3 near junction |  | Manual excavation for power duct laying
Thu (10/08) | 10 Aug 2023 | ZONE 3 |  | Rebar works for 1.5m high RC wall for ECM pond ongoing
Thu (10/08) | 10 Aug 2023 | MH5-1 |  | Rebar works ongoing for 3rd layer. Today target to cast
Thu (10/08) | 10 Aug 2023 | Exit 2 ST31 |  | 3rd bite ongoing
Thu (10/08) | 10 Aug 2023 | Exit 1 | DW89 | 2nd bite ongoing
Thu (10/08) | 10 Aug 2023 | MH2-3 |  | No activity
Thu (10/08) | 10 Aug 2023 | Loyang Way LP20S1 | to LW | Rigid pavement removal ongoing
Thu (10/08) | 10 Aug 2023 | Loyang Way LP18 |  | SPTel working here
Thu (10/08) | 10 Aug 2023 | Loyang Ave LP121F |  | Road cutting ongoing for SPPG, TMA & TMO provided
Thu (10/08) | 10 Aug 2023 | Loyang Ave LP99 | to LW | Premix removal ongoing, proceed with excavation & singtel pipe laying
Thu (10/08) | 10 Aug 2023 | Exit 3 area |  | Continuation of singtel pipe laying, today 12m target
Thu (10/08) | 10 Aug 2023 | MH2-6 |  | Hacking at 4th layer
Fri (11/08) | 11 Aug 2023 | Loyang Way LP74 |  | Lane closure by Dipcie
Fri (11/08) | 11 Aug 2023 | Zone 2 P6 |  | Current status of Singtel pipe laying. Today plan to lay ard 5m
Fri (11/08) | 11 Aug 2023 | Zone 1 Loyang Rise |  | No activity
Fri (11/08) | 11 Aug 2023 | North ramp P11 |  | Preparation for pre-boring and casing installation. This week target to cast 1 pile
Fri (11/08) | 11 Aug 2023 | Zone 2 |  | NB panel installation status for MH2-3 and MH2-4
Fri (11/08) | 11 Aug 2023 | Zone 2 POB pile removal |  | P7 LSS backfilling done. Now pre-boring for P5
Fri (11/08) | 11 Aug 2023 | MH2-9 |  | RG drilling ongoing for inclinometer installation
Fri (11/08) | 11 Aug 2023 | Zone 2 |  | Singtel pipe laid, 4m
Fri (11/08) | 11 Aug 2023 | MH5-1 |  | No activity. 3rd ring was cast yesterday
Fri (11/08) | 11 Aug 2023 | MH2-6 |  | Hacking to continue till 8pm
Fri (11/08) | 11 Aug 2023 | MH2-3 |  | 13th layer excavation on going
Fri (11/08) | 11 Aug 2023 | Zone 2 |  | P21-P22 backfilling works
Fri (11/08) | 11 Aug 2023 | ST31 |  | Koden test on going
Fri (11/08) | 11 Aug 2023 | Zone 3 VS |  | Slope cutting and soil internal shifting continue. Work till 7pm
Fri (11/08) | 11 Aug 2023 | Zone 2 LP20 |  | Dipcie continue excavation for singtel pipe laying, target to lay 9m tonight
Fri (11/08) | 11 Aug 2023 | Loyang Way LP20S1 | to LW | Continue removal of rigid pavement
Fri (11/08) | 11 Aug 2023 | Loyang Ave LP121F | to LW | SPPG lane closure, TMA & TMO provided
Fri (11/08) | 11 Aug 2023 | Loyang Way / Selarang Rd LP 18 |  | SPTel working here
Sat (12/08) | 12 Aug 2023 | MH2-7 |  | No activity
Sat (12/08) | 12 Aug 2023 | MH2-6 |  | Excavation works ongoing for 4th layer. Target to cast today
Sat (12/08) | 12 Aug 2023 | Loyang Way LP74 |  | Lane closure by Dipcie
Sat (12/08) | 12 Aug 2023 | BH-193 |  | Drilling works, current depth 39m
Sat (12/08) | 12 Aug 2023 | Loyang Way LP83 |  | Dipcie working middle lane towards PRD3, Powergrid (dosk) working opp
Sat (12/08) | 12 Aug 2023 | BH-192 |  | Drilling works, current depth 32m
Sat (12/08) | 12 Aug 2023 | BH168 |  | Drilling completed, termination depth 58.6m. Now preparation for grouting works
Sat (12/08) | 12 Aug 2023 | MH2-3 |  | Base slab excavation works. Target to lean concrete base slab afternoon
Sat (12/08) | 12 Aug 2023 | Zone 2 POB pile removal |  | 2/3 nos. completed. Now preparing to start the 3rd pile crushing
Sat (12/08) | 12 Aug 2023 | North Ramp | P11-2-2 | Boring works ongoing. Today will complete 1 no
Sat (12/08) | 12 Aug 2023 | PRD3 Bus only lane slip road |  | Lane closed. SPTel lucky joint preparation for premix cutting for pipe laying works (6-ways)
Sat (12/08) | 12 Aug 2023 | Zone 1 | Bet. P3-P4 | Krishco doing manual trial trench for water pipe laying works
Sat (12/08) | 12 Aug 2023 | Zone 2 South ramp |  | Preparation for recasting of base lean concrete as previous level was too high
Sat (12/08) | 12 Aug 2023 | MH5-1 |  | No activity
Sat (12/08) | 12 Aug 2023 | Exit 2 - JTC | ST031 | 2B & 1B Rebar cage lapping completed. Now preparing to lower cage 2A
Sat (12/08) | 12 Aug 2023 | DW89 |  | No activity. Waiting for rebar cage to arrive
Sat (12/08) | 12 Aug 2023 | Zone 4 |  | Excavation for SPPG pipe laying works. Target to lay 12m
Sat (12/08) | 12 Aug 2023 | Exit 2 | ST31 | 1st bite cleaning completed
Sat (12/08) | 12 Aug 2023 | Exit 1 | DW089 | Depth monitoring and bentonite circulation ongoing
Sat (12/08) | 12 Aug 2023 | Zone 3 near junction |  | Manual excavation for SPPG laying
Sat (12/08) | 12 Aug 2023 | Exit 3 |  | Jacking pipes delivered on site for MH2-7, 2-8, 2-6
Sat (12/08) | 12 Aug 2023 | Exit 3 |  | Hacking of the previous vechicle access ramp
Sat (12/08) | 12 Aug 2023 | MH2-6 |  | Rebar works ongoing. Target to cast today
Sat (12/08) | 12 Aug 2023 | MH2-9 |  | RG drilling works ongoing for inclionmeter installation. Current depth 3m
Sat (12/08) | 12 Aug 2023 | Zone 2 |  | KTC backfilling and compaction works
Sat (12/08) | 12 Aug 2023 | North Ramp | P11-2-2 | Boring completed, lowering of rebar cage onging
Sat (12/08) | 12 Aug 2023 | Zone 1 | Bet. P3-P4 | Trial trench for water pipe laying works completed. Now reinstatement ongoing
Sat (12/08) | 12 Aug 2023 | Zone 2 South Ramp |  | Base lean concrete in progress. Today to cast 48m of lean concrete
Sat (12/08) | 12 Aug 2023 | MH2-3 |  | Base lean concrete cast
Sat (12/08) | 12 Aug 2023 | BH192 |  | Drilling ongoing at depth 41m. BH193: Drilling completed at depth 41.2m, pending termination depth confirmation
Sat (12/08) | 12 Aug 2023 | Zone 3 | ST-027 | 1st bite excavation started
Sat (12/08) | 12 Aug 2023 | Exit 2 - JTC | ST031 | 3B & 2B Rebar cage lapping in progress. Balance 3nos. of rebar cages, 5/8 nos. lowered down
Sat (12/08) | 12 Aug 2023 | Exit 2 |  | New access making ongoing
Sat (12/08) | 12 Aug 2023 | Zone 3 | BH73 | Drilling ongoing, depth 22m
Sat (12/08) | 12 Aug 2023 | BH92 |  | Current depth 10m
Sat (12/08) | 12 Aug 2023 | DW89 |  | Koden test in progress, preparing to lower water stop
Sat (12/08) | 12 Aug 2023 | Exit 1 |  | Slope cutting works in progress
Sat (12/08) | 12 Aug 2023 | Exit 2 ST-031 |  | Cage A hanging bar completed, lowering in progress
Sat (12/08) | 12 Aug 2023 | Exit 2 ST027 |  | Checking cutter due to suction pipe line leakage, prior to resume 1st bite excavation
Sat (12/08) | 12 Aug 2023 | Loyang Way LP116 |  | Lane closure by sppg
Sat (12/08) | 12 Aug 2023 | Loyang Ave LP121F |  | Removal of rigid pavement ongoing & proceed with 12-way pipe laying. TMA & TMO provided
Sun (13/08) | 13 Aug 2023 | ST31 Casting in progress. Vol. |  | 296.5m³
Sun (13/08) | 13 Aug 2023 | Exit 2 |  | Access installation ongoing
Sun (13/08) | 13 Aug 2023 | Zone 3 Lincstech |  | Palm tree cutting into smaller pieces for removal
Sun (13/08) | 13 Aug 2023 | Zone 3 |  | New hoarding installation to make traffic light DB box accessible
Sun (13/08) | 13 Aug 2023 | Zone 4 |  | Singtel HDD works ongoing
Sun (13/08) | 13 Aug 2023 | Zone 4 Loyang Way Junction |  | DE143 premix cutting and hacking works
Sun (13/08) | 13 Aug 2023 | Zone 4 |  | DE143 continuing hoarding/fence installation
Sun (13/08) | 13 Aug 2023 | Zone 4 |  | DE143 works ongoing within barricaded/hoarded area
Sun (13/08) | 13 Aug 2023 | Zone 3 |  | VM trigger likely not due to our site works. Only palm tree cutting and removal near lincstech
Sun (13/08) | 13 Aug 2023 | Exit 1 DW089 |  | Rebar cage 1B(1/6) lowered
Sun (13/08) | 13 Aug 2023 | Exit 2 ST031 |  | Casting ongoing
Sun (13/08) | 13 Aug 2023 | MH2-7 |  | Telescopic excavator to be shifted from MH2-6
Sun (13/08) | 13 Aug 2023 | Zone 3 |  | Formwork for 1 side of ECM pond RC wall in progress
Sun (13/08) | 13 Aug 2023 | Zone 3 |  | Endplate welding ongoing
Sun (13/08) | 13 Aug 2023 | Zone 4 |  | DE143 compacting premix at Loyang Way junction
Sun (13/08) | 13 Aug 2023 | Zone 3 Lincstech |  | Silt fence gap concreting in progress
Sun (13/08) | 13 Aug 2023 | Exit 3 |  | Formwork installation for concrete block (for hoarding) ongoing
Mon (14/08) | 14 Aug 2023 | Exit 3 |  | 3m sppg pipe laying to be done today
Mon (14/08) | 14 Aug 2023 | Zone 2 |  | POB pile removal TT on going. Found unknown cable affecting 1 pile
Mon (14/08) | 14 Aug 2023 | Zone 2 North Ramp | P11-2-01 | Boring in progress. Target to cast today
Mon (14/08) | 14 Aug 2023 | Zone 2 P6 |  | Excavation work for singtel pipe laying
Mon (14/08) | 14 Aug 2023 | PDR3 |  | Sptel manhole cover installation
Mon (14/08) | 14 Aug 2023 | Zone 3 |  | ECM pond wall formwork ongoing
Mon (14/08) | 14 Aug 2023 | Exit 3 |  | Hacking ongoing
Mon (14/08) | 14 Aug 2023 | Near MH6-1 |  | SPPG pipe laid, 3m. Backfilling ongoing
Mon (14/08) | 14 Aug 2023 | Zone 2 POB pile |  | P1 casing installation
Mon (14/08) | 14 Aug 2023 | MH2-8 |  | Rebar cutting and removal for sewer work
Tue (15/08) | 15 Aug 2023 | Hi PD, DDs. Team CR103 would like to report the following |  | *CR103: Wire Rope of Hydraulic Grab Snapped during D-Wall Trenching Works*, Date: 15/08/2023, Time: Approximately 1815HRS, Initial findings:, Machine Details: XCMG Grab 04, Panel No: NS 16, Excavation Depth: 26m, BRK reported that during the removal of excavated soil from DWall trench (at depth 26m) to the soil tank using the clamshell grab, a snapping sound of wire rope was heard. The clamshell grab which was at the time positioned over the soil tank was found to have 1 wire rope damaged, Operator immediately stopped the machine, lowered the clamshell into the soil tank. BRK had also immediately arranged for 2 crawler cranes to lower down the clamshell grab. Clamshell was lowered flat to the ground at 1940HRS, No one was injured. BRK management and XCMG engineer is en route to site for further investigation now
Tue (15/08) | 15 Aug 2023 | MH2-9 |  | IM drilling ongoing for inclinometer. Current depth at 15m/31m
Tue (15/08) | 15 Aug 2023 | Near Gate 5 |  | Continue access hacking for MH2-8
Tue (15/08) | 15 Aug 2023 | MH6-1 |  | Rebar tying for base slab
Tue (15/08) | 15 Aug 2023 | MH2-7 |  | Excavation for 7th layer on going
Tue (15/08) | 15 Aug 2023 | MH2-6 |  | No activity
Tue (15/08) | 15 Aug 2023 | Zone 2 |  | POB 4th pile (P1) crushing ongoing
Tue (15/08) | 15 Aug 2023 | MH2-5 |  | Excavation works for 9th layer
Tue (15/08) | 15 Aug 2023 | Zone 3 |  | Sheetpile installation in progress
Tue (15/08) | 15 Aug 2023 | Zone 3 Vent Shaft |  | KTC excavation ongoing. Internal shifting to exit 3 area
Tue (15/08) | 15 Aug 2023 | Zone 3 BH93 |  | In progress, 8m
Tue (15/08) | 15 Aug 2023 | Zone 3 BH92 |  | 1st packer test ongoing at 36m
Tue (15/08) | 15 Aug 2023 | Zone 3 BH85 |  | In progress, 4m
Tue (15/08) | 15 Aug 2023 | Exit 1 DW102 |  | First bite excavation in progress
Tue (15/08) | 15 Aug 2023 | Zone 2 North Ramp (Bored Pile) | P11-2-01 | Casting in progress
Tue (15/08) | 15 Aug 2023 | Loyang Way LP20S1 |  | DE143 works
Tue (15/08) | 15 Aug 2023 | Zone 4 |  | DE143 works ongoing
Tue (15/08) | 15 Aug 2023 | Loyang Way | near Exit 1/ Selarang Camp | Lane closure for Singtel by SKK
Tue (15/08) | 15 Aug 2023 | Loyang Way near LP118S1 |  | SPPG pipe laid, 4m (12 way). Backfilling ongoing
Tue (15/08) | 15 Aug 2023 | P44 |  | Continue manual trial trench for Singtel. Found existing M1, Starhub, 22kV and PUB manhole
Tue (15/08) | 15 Aug 2023 | Zone 3 |  | ST94-95 guidewall inspected. To cast today
Tue (15/08) | 15 Aug 2023 | Zone 3 |  | Hacking ongoing for retaining wall base slab
Tue (15/08) | 15 Aug 2023 | BH-8 |  | Hand auger in progress
Tue (15/08) | 15 Aug 2023 | Zone 2 P21-P22 |  | Compaction on going. Tomorrow NDT
Tue (15/08) | 15 Aug 2023 | ST27 |  | 2nd bite trimming on going
Tue (15/08) | 15 Aug 2023 | MH6-1 |  | Base slab rebar and starter bar completed. Pending RTO inspection. Tonight to cast
Tue (15/08) | 15 Aug 2023 | MH2-8 |  | Rebar cutting and removal
Tue (15/08) | 15 Aug 2023 | ST27 |  | Cleaning in progress. Tonight to continue 3rd bite
Tue (15/08) | 15 Aug 2023 | MH2-5 |  | Excavation to 9th layer in progress. Tomorrow to cast
Tue (15/08) | 15 Aug 2023 | MH5-1 |  | Now no activity
Wed (16/08) | 16 Aug 2023 | Zone 3 ECM pond |  | Continue rebar and formwork closing. Plan for casting tmr
Wed (16/08) | 16 Aug 2023 | Zone 3 |  | Continue excavation and internal shifting by KTC
Wed (16/08) | 16 Aug 2023 | Zone 3 BH93 |  | Rig breakdown. Now rectifying. Depth as of yesterday, 8m
Wed (16/08) | 16 Aug 2023 | Zone 3 BH92 |  | Completed. This rig will move over to BH94
Wed (16/08) | 16 Aug 2023 | Zone 2 in front of shell |  | Unable to lay singtel pipes due to existing utilities. Corridor to shift again today and finalise the alignment undercrossing the drain at NLL
Wed (16/08) | 16 Aug 2023 | BH85 |  | In progress, 12m
Wed (16/08) | 16 Aug 2023 | Exit 1 DW102 |  | Completed
Wed (16/08) | 16 Aug 2023 | Loyang Way near Exit 1 |  | DE143 works ongoing
Wed (16/08) | 16 Aug 2023 | Zone 4 |  | DE143 works ongoing
Wed (16/08) | 16 Aug 2023 | Zone 3 ST94-95 |  | Guidewall cast yesterday
Wed (16/08) | 16 Aug 2023 | Zone 3 |  | Augering ongoing prior sheetpile installation
Wed (16/08) | 16 Aug 2023 | MH6-1 |  | Base slab rebars inspected. Formwork installation ongoing
Wed (16/08) | 16 Aug 2023 | BH-08 |  | Drilling started
Wed (16/08) | 16 Aug 2023 | MH5-1 |  | Formwork closing in progress. Concrete ordered. Waiting for concrete for casting
Wed (16/08) | 16 Aug 2023 | MH2-7 |  | 7th layer Formwork closing in progress. To cast today
Wed (16/08) | 16 Aug 2023 | MH2-6 |  | No activity
Wed (16/08) | 16 Aug 2023 | MH2-5 |  | Rebar installation for 9th layer in progress. Target to cast today
Wed (16/08) | 16 Aug 2023 | Zone 2 P21-P22 |  | Backfilling works ongoing
Wed (16/08) | 16 Aug 2023 | Zone 2 |  | KTC drain hacking works
Wed (16/08) | 16 Aug 2023 | Zone 2 | POB | 5th Pile crushing in progress
Wed (16/08) | 16 Aug 2023 | Zone 2 in front of shell |  | SingTel pipe laying in progress, target to lay 8m today
Wed (16/08) | 16 Aug 2023 | Zone 3 |  | Resume sheetpile installation
Wed (16/08) | 16 Aug 2023 | Exit 1 DW95 |  | LSS backfilling ongoing
Wed (16/08) | 16 Aug 2023 | Zone 3 BH94 |  | Manual trial trench started
Wed (16/08) | 16 Aug 2023 | JTC ST27 |  | Water stop welding ongoing
Wed (16/08) | 16 Aug 2023 | BH167 |  | Drilling ongoing, depth 35.5m
Wed (16/08) | 16 Aug 2023 | Dear PD and DDs, CR101PT would like to report the following |  | *CR101 LV Cable Damage Report*, Company involved : Ang Tong Seng (ATS), Date: 16 Aug 2023, Time : 1035hrs, Personnel involved : Ramesh (Registered Earthwork Supervisor), Oliver (Project Manager) and Peh Chin Hock (Excavator Vibro Operator), Location: Vehicular Bridge East Bank (Changi Exhibition Centre (CEC) side, Work: Subcontractor ATS was shifting the extracted kingposts using excavator vibro which were previously used to support the LV and 22KV cables for drain construction below the cables, At about 1035hrs, while excavator vibro operator was adjusting 1 of the kingposts near the locality of the LV and 22KV cables which was already backfilled, During the lowering, the tip of the kingpost hit the ground where LV and 22KV cables are buried 200mm below the ground, The team sensed a burnt smell and decided to expose the cables manually. They discovered that the LV cable was damaged, SPPG was alerted and confirmed that the LV cable was damaged. Despite the damage, the LV cable is still live and functioning. Nearby stakeholder CEC confirmed that they did not experience any service disruption. According to SPPG, there is no power failure report by any stakeholder. SPPG will come down again tomorrow to carry out the repair, The 22KV and LV cables are supported during drain work and are shown on the utility plan. There are labels on site indicating the cables location after area was backfilled. ATS RES is also supervising the kingpost extraction works, Will update again pending further investigation and SPPG repair
Wed (16/08) | 16 Aug 2023 | MH5-1 |  | Rectification ongoing. LCH on site informed plan for casting ard 10pm
Wed (16/08) | 16 Aug 2023 | Zone 2 |  | Singtel pipe laying, 8m
Wed (16/08) | 16 Aug 2023 | North ramp P8-2-4 |  | Pending concrete. Casting ramp platform ready
Wed (16/08) | 16 Aug 2023 | MH2-5 |  | 9th layer casting ongoing
Wed (16/08) | 16 Aug 2023 | ST27 |  | First rebar cage installed. Balance rebar cages otw
Wed (16/08) | 16 Aug 2023 | MH6-1 |  | Base slab rebar cast. Levelling ongoing
Wed (16/08) | 16 Aug 2023 | MH2-8 |  | Noise curtain installation for access slab and beam hacking work
Wed (16/08) | 16 Aug 2023 | P8-2-04 | 1300mm dia | Casting completed. 11m3. (Depth-14.25m)
Wed (16/08) | 16 Aug 2023 | MH5-1 |  | Rebar installation done. Concrete spacer installation on going. LCH arranging RTO inspection
Wed (16/08) | 16 Aug 2023 | MH2-7 |  | 7th layer excavation completed. Preparation for rebar installation
Wed (16/08) | 16 Aug 2023 | Zone 2 P21-P22 |  | Backfilling works preparation for NDT
Wed (16/08) | 16 Aug 2023 | Zone 2 |  | POB pile crashing, 5/7 on going
Wed (16/08) | 16 Aug 2023 | MH2-5 |  | Excavation for 9th layer
Thu (17/08) | 17 Aug 2023 | Gate 5 MH2-8 area |  | To continue access hacking
Thu (17/08) | 17 Aug 2023 | BH-08 |  | Rock coring ongoing, depth at 27.5m
Thu (17/08) | 17 Aug 2023 | ST21 |  | Today plan for guidewall installation (3m)
Thu (17/08) | 17 Aug 2023 | Behind exit 2 NB |  | Krishco to continue trial trench for water pipe. Now preparing for hacking works
Thu (17/08) | 17 Aug 2023 | Zone 3 loyang way in front of Krislite building |  | Power grid working
Thu (17/08) | 17 Aug 2023 | Loyang Way near Exit 1 |  | No activity. DE143 works at opp side
Thu (17/08) | 17 Aug 2023 | Zone 4 Loyang Way/Ave |  | WG plan to continue SPPG trial trench and pipe laying here at sidetable
Thu (17/08) | 17 Aug 2023 | Zone 2 | POB | 5th Pile crushing in progress
Thu (17/08) | 17 Aug 2023 | North Ramp | P11-2-3 | Platform preparation works ongoing for boring work
Thu (17/08) | 17 Aug 2023 | Zone 2 | Near shell station | Pipe laying for SPTel & SPPG ongoing. Target to lay 8m today
Thu (17/08) | 17 Aug 2023 | ST27 |  | Casting in progress
Thu (17/08) | 17 Aug 2023 | Zone 3 |  | Continue rebar works for 2nd ECM pond
Thu (17/08) | 17 Aug 2023 | Zone 3 |  | Concrete just arrived for ECM pond 1
Thu (17/08) | 17 Aug 2023 | MH2-6 |  | 5th layer excavation works
Thu (17/08) | 17 Aug 2023 | MH2-3 |  | BRC lowering for base slab
Thu (17/08) | 17 Aug 2023 | MH2-4 |  | Marking and surveying works in progress
Thu (17/08) | 17 Aug 2023 | Zone 2 | POB | Crushing of 5th pile temporary stopped due to some parts changing. Will continue after fixing work done. Target to complete 5th pile crushing today
Thu (17/08) | 17 Aug 2023 | MH2-7 |  | No activity. 7th layer was cast yesterday
Thu (17/08) | 17 Aug 2023 | Zone 2 | Near shell station | Pipe laying for SPTel & SPPG
Thu (17/08) | 17 Aug 2023 | ST21 |  | Guidewall rebar installation ongoing
Thu (17/08) | 17 Aug 2023 | ST27 |  | Casting ongoing. Progressive vol: 231.5/269m3
Thu (17/08) | 17 Aug 2023 | MH2-3 |  | Base slab rebar installation in progress
Thu (17/08) | 17 Aug 2023 | MH5-1 |  | No activity. Only housekeeping now till 7pm
Thu (17/08) | 17 Aug 2023 | Zone 2 P6 |  | SPTel (8m) & SPPG (8m) pipes laid. Reinstatement works ongoing
Thu (17/08) | 17 Aug 2023 | MH2-3 |  | Base slab rebar works 3rd layer (last layer of D3 mesh installation till 10pm. Balance links and starter bars. Target to complete installation and inspection tomorrow before lunch
Thu (17/08) | 17 Aug 2023 | MH6-1 |  | Preparation works to reinstate existing sewer pipe
Thu (17/08) | 17 Aug 2023 | Zone 3/4 loyang way junction |  | TT for SPPG corridor
Thu (17/08) | 17 Aug 2023 | Zone 4 LP97 |  | Premix removal on going for singtel pipe laying. Target tonight 9m, pick up at installed pipe to connect at new manhole
Fri (18/08) | 18 Aug 2023 | Zone 3 loyang way |  | Lane closed for singtel pipe laying. Connection of pipe from pick up points to new MH
Fri (18/08) | 18 Aug 2023 | Zone 4 Loyang avenue towards TPE |  | Unable to lay pipes due to many utilities. Arra backfilled and premix reinstated
Fri (18/08) | 18 Aug 2023 | Zone 4 loyang avenue towards CV |  | Started TT to find corridor for singtel pipe laying
Fri (18/08) | 18 Aug 2023 | Zome 3 |  | KTC continuing to excavate the area
Fri (18/08) | 18 Aug 2023 | Zone 3 loyang way in front of lincstech |  | Hacking of uneven premix to repair tonight
Fri (18/08) | 18 Aug 2023 | Zone 3 |  | Marking of Survey points for SPPG cable pulling pit ongoing. 2 areas already excavated
Fri (18/08) | 18 Aug 2023 | Zone 3 |  | ECM pond BRC installation in progress
Fri (18/08) | 18 Aug 2023 | Zone 3 |  | DR2 augering ongoing before sheetpile installation continues
Fri (18/08) | 18 Aug 2023 | Zone 3 |  | Rubber mat laying near Lincstech
Fri (18/08) | 18 Aug 2023 | Zone 4 |  | DE143 works ongoing
Fri (18/08) | 18 Aug 2023 | Zone 4 LA towards CV |  | WG continue manual trial trench for SPPG pipe laying. Found water pipes & LV
Fri (18/08) | 18 Aug 2023 | Exit 1 DW94 |  | 1st bite excavation in progress
Fri (18/08) | 18 Aug 2023 | Zone 3 P43 |  | WG excavation for SPPG pipe laying
Fri (18/08) | 18 Aug 2023 | Zone 3 BH93 |  | In progress, 39m
Fri (18/08) | 18 Aug 2023 | Zone 3 DR2 |  | Continue augering
Fri (18/08) | 18 Aug 2023 | Zone 3 |  | ECM pond 2 base slab casting & levelling in progress
Fri (18/08) | 18 Aug 2023 | Zone 3 BH152 |  | In progress, 32.5m
Fri (18/08) | 18 Aug 2023 | Zone 3/4 loyang way junction |  | TT done and area reinstated. Lane opened
Fri (18/08) | 18 Aug 2023 | Zone 4 loyang avenue towards CV |  | Works completed, area reinstated and lane opened
Fri (18/08) | 18 Aug 2023 | ST21 |  | Guidewall inspection
Fri (18/08) | 18 Aug 2023 | BH-08 |  | In progress, 37.2m
Fri (18/08) | 18 Aug 2023 | Zone 3 loyang way |  | Singtel pipe installation done. Area reinstated and lane opened
Fri (18/08) | 18 Aug 2023 | MH5-1 |  | 5th layer excavation in progress
Fri (18/08) | 18 Aug 2023 | MH5-2 |  | Clearing hardcore
Fri (18/08) | 18 Aug 2023 | ST21 |  | Guidewall casting in progress
Fri (18/08) | 18 Aug 2023 | North ramp P8-2-2 |  | Casting completed,17 m3
Fri (18/08) | 18 Aug 2023 | MH5-1 |  | Excavation will continue till 10pm. Current depth at 1m. Tonight to complete excavation works. Tomorrow am to continue trimming. Target to install rebar cage and moulding after lunch and final inspection by 5pm
Fri (18/08) | 18 Aug 2023 | MH6-1 |  | Tonight again plan to connect existing sewer and new pipe alignment
Fri (18/08) | 18 Aug 2023 | Exit 1 DW94 |  | 1st bite excavation completed. BC cutter teeth changing for 2nd bite
Fri (18/08) | 18 Aug 2023 | zone 4 slip road towards loyang way |  | DE143 working here for road kerb installation
Fri (18/08) | 18 Aug 2023 | Zone 4 loyang avenue towards CV |  | Lane closed for TT, singtel pipe corridor
Sat (19/08) | 19 Aug 2023 | Zone 3/4 junction |  | Premix top up along drain for sppg pipe laying
Sat (19/08) | 19 Aug 2023 | Zone 3 Slurry guide wall |  | Overcast concrete hacking for SPPG pipe laying. @⁨Dwayne⁩ FYI in case got VM alert
Sat (19/08) | 19 Aug 2023 | Zone 3 loyang way towards zone 4 loyang avenue |  | Slip road premix top up also here, 300-400mm
Sat (19/08) | 19 Aug 2023 | Zone 3 loyang way side table |  | Preparation for singtel pipe laying. 6m to connect at new MH
Sat (19/08) | 19 Aug 2023 | MH2-3 base slab |  | Casting completed. Levelling in progress
Sat (19/08) | 19 Aug 2023 | Zone 4 loyang avenue |  | TT done, found both 22KV at 2 TT location. Waiting quary dust for backfilling works
Sat (19/08) | 19 Aug 2023 | Exit 1 DW94 |  | 2nd bite trenching done, koden test also done
Sat (19/08) | 19 Aug 2023 | Zone 4 loyang avenue |  | Work completed and area reinstated. Lane opened
Sat (19/08) | 19 Aug 2023 | Zone 3 loyang way |  | Work completed and are reinstated. Lane opened
Sat (19/08) | 19 Aug 2023 | MH5-1 |  | Rebar works outer layer installation on going. Target to complete rebar works by 1030 pm and request for inspection, Close formwork and complete by 1130pm. Target to cast by 12mn to 1230am
Sat (19/08) | 19 Aug 2023 | MH2-4 |  | Rebar cage installation done. Balance formwork closing. They target to cast by 11pm-12mn
Sat (19/08) | 19 Aug 2023 | Zone 3 DR2 |  | High strength jack installation on going. Works till 10pm
Sat (19/08) | 19 Aug 2023 | DW94 |  | Rebar cage installation on going. Target to cast by 12mn
Sun (20/08) | 20 Aug 2023 | Zone 3 ECM ponds |  | Today ICE no activity
Sun (20/08) | 20 Aug 2023 | Zone 3 |  | ECM water pipe connection ongoing by WH
Sun (20/08) | 20 Aug 2023 | Zone 3 DR2 |  | Continue sheetpile installation
Sun (20/08) | 20 Aug 2023 | Zone 3 |  | Today KTC no activity
Sun (20/08) | 20 Aug 2023 | Zone 3 Retaining Wall area |  | Clearing soil before continue hacking works. Have informed WH to continue install the hard barricades
Sun (20/08) | 20 Aug 2023 | Exit 1 DW94 |  | Casting was completed earlier this morning. No activity today
Sun (20/08) | 20 Aug 2023 | Zone 4 |  | DE143 works ongoing
Sun (20/08) | 20 Aug 2023 | Exit 2 DW49 |  | Drilling for toe grouting in progress
Sun (20/08) | 20 Aug 2023 | North ramp N2 |  | Preparing to resume pre-boring & soldier pile installation. As of yesterday, 5/20nos soldier pile installed
Sun (20/08) | 20 Aug 2023 | MH5-1 |  | No activity
Sun (20/08) | 20 Aug 2023 | MH5-2 |  | No activity
Sun (20/08) | 20 Aug 2023 | MH2-5 |  | No activity
Sun (20/08) | 20 Aug 2023 | MH2-4 |  | No activity
Sun (20/08) | 20 Aug 2023 | MH2-3 |  | No activity
Sun (20/08) | 20 Aug 2023 | MH2-6 |  | 5th layer rebar works ongoing
Sun (20/08) | 20 Aug 2023 | MH2-7 |  | 8th layer rebar works ongoing
Sun (20/08) | 20 Aug 2023 | MH2-4 |  | 1st layer casting in progress
Sun (20/08) | 20 Aug 2023 | MH5-1 |  | 5th layer casting in progress
Sun (20/08) | 20 Aug 2023 | DW94 |  | Casting in progress. Running volume 17/65m3
Sun (20/08) | 20 Aug 2023 | Zone 3 DR2 |  | Now installing the last sheetpile for the day. As of today, 88/172pcs installed. Tmr morning to bring in another 32pcs
Sun (20/08) | 20 Aug 2023 | Zone 3 P38 |  | Continue RW base slab hacking
Sun (20/08) | 20 Aug 2023 | North ramp N2 |  | Pre-boring in progress, 5th one for the day. Thereafter will install the soldier pile. The team will be working till 5pm today. Additional noise mitigation measure to be installed tmr at the rotary area (boxed in yellow)
Sun (20/08) | 20 Aug 2023 | DW94 |  | Casting completed. Tremie pipe removal
Sun (20/08) | 20 Aug 2023 | Zone 4 |  | Singtel pipe laid. Waiting for concrete lorry for casting
Sun (20/08) | 20 Aug 2023 | Zone 4 |  | Singtel pipe laying completed. Area reinstated and lane opened
Sun (20/08) | 20 Aug 2023 | Zone 3 loyang way junction |  | Premix top up (350mm ) and road marking completed
Sun (20/08) | 20 Aug 2023 | MH6-1 |  | Wall rebar works for manhole RC in progress. Plan for casting tmr
Mon (21/08) | 21 Aug 2023 | ST25 |  | Part replacement arrived. Rectification ongoing
Mon (21/08) | 21 Aug 2023 | Zone 3 P43 |  | Excavation for power duct pipe laying
Mon (21/08) | 21 Aug 2023 | MH2-7 |  | 8th layer casting completed
Mon (21/08) | 21 Aug 2023 | MH2-6 |  | 5th layer casting
Mon (21/08) | 21 Aug 2023 | P21 |  | Krishco doing trial trench works to find existing water pipe for live valve installation location
Mon (21/08) | 21 Aug 2023 | ECM pond 2 |  | Shifting of ECM plant. Tomorrow can complete
Mon (21/08) | 21 Aug 2023 | DW111 |  | Excavation in progress, 6m depth as of now
Mon (21/08) | 21 Aug 2023 | MH5-1 |  | Excavation for 5th layer on going
Mon (21/08) | 21 Aug 2023 | BH167 |  | Drilling in progress, current depth 48m
Mon (21/08) | 21 Aug 2023 | MH2-5 |  | Excavation for 10th layer caisson
Mon (21/08) | 21 Aug 2023 | MH2-4 |  | Preparing to install support for Singtel haunch. Today they will work until 10PM
Mon (21/08) | 21 Aug 2023 | MH5-1 |  | Excavation to 6th layer in progress
Mon (21/08) | 21 Aug 2023 | MH6-1 |  | Formwork closing in progress
Mon (21/08) | 21 Aug 2023 | MH2-4 |  | Continue to clear soil manually
Mon (21/08) | 21 Aug 2023 | MH2-5 |  | Continue 10th layer hacking and excavation works. The team will work till 10pm
Mon (21/08) | 21 Aug 2023 | MH5-1 |  | Continue excavation for 6th layer. Works till 10pm
Mon (21/08) | 21 Aug 2023 | Zone 3 DR2 |  | Works done for the day
Mon (21/08) | 21 Aug 2023 | Exit 1 DW111 |  | 2nd bite excavation in progress
Mon (21/08) | 21 Aug 2023 | Loyang Way opp exit 1 |  | Singtel pipeline works by other contractor
Mon (21/08) | 21 Aug 2023 | Zone 4 LP95 |  | Today plan for Singtel pipe laying (18way)
Mon (21/08) | 21 Aug 2023 | Loyang Way opp LP24 |  | Tonight plan for excavation & shoring installation for Singtel pipe laying
Tue (22/08) | 22 Aug 2023 | Loyang Way LP24 |  | Premix hacking and excavation for Singtel pipe laying
Tue (22/08) | 22 Aug 2023 | Zone 2 pumping main |  | Stamp installed 50m length (2 way). Pipe will only be deliver today at 2pm
Tue (22/08) | 22 Aug 2023 | DW111 |  | Hanging bar installation ongoing
Tue (22/08) | 22 Aug 2023 | MH5-1 |  | 5th layer excavation on going at 0.6m depth. Hard soil, target to complete excavation today
Tue (22/08) | 22 Aug 2023 | N2 ERSS for pile cap |  | 15/20 SP installed. Now pre-boring for lagging plate installation
Tue (22/08) | 22 Aug 2023 | Zone 4 |  | Excavation in progress
Tue (22/08) | 22 Aug 2023 | Zone 4 |  | Singtel pipe laying, 9m
Tue (22/08) | 22 Aug 2023 | Exit 3 |  | Removal of guidewall left over to start excavation work
Tue (22/08) | 22 Aug 2023 | P21 |  | Trial trench works ongoing for singtel manhole installation MX4
Tue (22/08) | 22 Aug 2023 | MH6-1 |  | Starter bar installation on going
Tue (22/08) | 22 Aug 2023 | N2 ERSS work |  | Pre-boring to continue for lagging plate
Tue (22/08) | 22 Aug 2023 | DW111 |  | Excavation completed, 22.5m. Internal koden checked
Tue (22/08) | 22 Aug 2023 | Zone 3 P43 |  | Works done for the night
Tue (22/08) | 22 Aug 2023 | Zone 2 shell area |  | Found few internal cables from shell. Surveyor team to mark the alignment of drain then see if cables are need to be shift locally
Tue (22/08) | 22 Aug 2023 | Zone 4 LP95 |  | Premix reinstatement in progress
Tue (22/08) | 22 Aug 2023 | MH5-1 |  | Excavation in progress for 6th layer
Tue (22/08) | 22 Aug 2023 | ST25 |  | 1st bite excavation in progress
Tue (22/08) | 22 Aug 2023 | MH2-5 |  | Formwork closing for 10th layer. Concrete ordered
Tue (22/08) | 22 Aug 2023 | MH2-4 |  | Singtel haunch support installation done
Tue (22/08) | 22 Aug 2023 | MH5-2 |  | Rebar work in progress. Tomorrow to cast
Tue (22/08) | 22 Aug 2023 | MH5-1 |  | Excavation to 6th layer. To cast tomorrow
Tue (22/08) | 22 Aug 2023 | MH6-1 |  | Casting done. Levelling in progress
Tue (22/08) | 22 Aug 2023 | DW111 |  | Cage A (2/2 lowered down). Cage B ( 1/2 cage lowered down). Tonight to cast
Tue (22/08) | 22 Aug 2023 | MH2-5 |  | Casting ongoing for 10th layer
Tue (22/08) | 22 Aug 2023 | MH2-4 |  | No activity. The team is supporting the casting works at MH2-5
Tue (22/08) | 22 Aug 2023 | MH5-2 |  | Works done for the day. Current status: First layer rebar installation
Tue (22/08) | 22 Aug 2023 | MH5-1 |  | Works done for the day
Tue (22/08) | 22 Aug 2023 | ST25 |  | 2nd bite trimming in progress
Tue (22/08) | 22 Aug 2023 | MH2-7 |  | 8th layer curing
Tue (22/08) | 22 Aug 2023 | Zone 3 DR2 |  | Works done for the day
Tue (22/08) | 22 Aug 2023 | Exit 1 DW111 |  | Rebar cage lowering
Tue (22/08) | 22 Aug 2023 | Zone 2 P21 |  | Krishco here for TT work to find 300mm water pipe. This area will be the pick up point. Yesterday they have done TT near P22 to install live valve
Tue (22/08) | 22 Aug 2023 | MH6-1 |  | Formwork still closing in progress
Tue (22/08) | 22 Aug 2023 | BH167 |  | Drilling at 48m depth
Tue (22/08) | 22 Aug 2023 | Zone 4 Loyang Ave LP95 |  | Tonight plan for Singtel pipe laying
Tue (22/08) | 22 Aug 2023 | MH2-4 |  | Yesterday night exposed singtel haunching. Today they plan to proceed with the support installation
Tue (22/08) | 22 Aug 2023 | Zone 4 LA towards CV | LP112 | Continue manual clearing of soil for SPPG pipe laying works
Wed (23/08) | 23 Aug 2023 | MH2-7 |  | No activity
Wed (23/08) | 23 Aug 2023 | Loyang Way opp exit 1 |  | Lucky Joint works
Wed (23/08) | 23 Aug 2023 | Loyang Way LP24 |  | Continue trench excavation for Singtel pipe corridor
Wed (23/08) | 23 Aug 2023 | Zone 4 LP112 |  | Continue premix removal and excavation for SPPG pipe corridor
Wed (23/08) | 23 Aug 2023 | Zone 4 LP92 |  | Tonight plan for Singtel pipe laying (18way)
Wed (23/08) | 23 Aug 2023 | ST25 |  | Tremie pipe lowering in progress
Wed (23/08) | 23 Aug 2023 | MH5-1 |  | Excavation in progress for 6th layer
Wed (23/08) | 23 Aug 2023 | MH5-2 |  | 1st layer rebar works installation. Target to cast today
Wed (23/08) | 23 Aug 2023 | Zone 2 in fron of shell |  | Depcie team 1 here for pipe joining at new manhole
Wed (23/08) | 23 Aug 2023 | North ramp | P9-2-3 | Preparation to start boring works. Alignment checking ongoing
Wed (23/08) | 23 Aug 2023 | North Ramp | N2 - Pile Cap ERSS | Preboring ongoing for solider pile installation. As of now, 15/20 soldier pile and 10/20 lagging plate installed
Wed (23/08) | 23 Aug 2023 | North ramp | N6 area | RG continue manual trial trench works. Tmr will shift in the rig
Wed (23/08) | 23 Aug 2023 | DW111 |  | Casting in progress
Wed (23/08) | 23 Aug 2023 | LP112 |  | Continue manual clearing of soil
Wed (23/08) | 23 Aug 2023 | Zone 4 |  | Singtel pipe laying in progress
Wed (23/08) | 23 Aug 2023 | LP112 |  | Services found — HT, LT, Starhub & water pipe. No pipe laying tonight (SPPG)
Wed (23/08) | 23 Aug 2023 | LP112 |  | Lane reopened
Wed (23/08) | 23 Aug 2023 | Casting completed at 0450hrs. Total vol |  | 95m3
Wed (23/08) | 23 Aug 2023 | MH6-1 |  | Formwork removal
Wed (23/08) | 23 Aug 2023 | MH2-3& MH2-5 |  | No activity as of now
Wed (23/08) | 23 Aug 2023 | MH2-4 |  | Formwork closing done for utility support footing/ stump. Concrete ordered
Wed (23/08) | 23 Aug 2023 | ST25 |  | Water stop installation ongoing
Wed (23/08) | 23 Aug 2023 | MH5-2 |  | Formwork closing. Casting planned at 7:30PM
Wed (23/08) | 23 Aug 2023 | MH5-1 |  | Excavation for 6th layer caisson
Wed (23/08) | 23 Aug 2023 | P9-2-3 |  | 1st lorry on site for casting
Wed (23/08) | 23 Aug 2023 | South ramp & MH5-1 |  | Housekeeping ongoing. MH5-2: Casting ongoing
Wed (23/08) | 23 Aug 2023 | North ramp P9-2-3 |  | Casting completed. Now HSL removing casting ramp, etc then housekeeping
Wed (23/08) | 23 Aug 2023 | Near MH6-1 |  | Wee Guan preparing to remove their duct for Dwall work
Wed (23/08) | 23 Aug 2023 | Zone 3 DR2 |  | No more activity
Wed (23/08) | 23 Aug 2023 | Exit 1 DW111 |  | LSS backfilling completed
Thu (24/08) | 24 Aug 2023 | MH6-1 |  | Formwork closing done. Adjusting of formwork. Concrete on site
Thu (24/08) | 24 Aug 2023 | Zone 4 |  | Singtel pipes laid, 7m
Thu (24/08) | 24 Aug 2023 | ST25 |  | Casting completed at 0122hrs. Total vol: 70m3
Thu (24/08) | 24 Aug 2023 | LP24 |  | TT completed. Found NLT, Singtel, LP cable, EHT, M1 and Xenith
Thu (24/08) | 24 Aug 2023 | LP112 |  | SPPG pipe laying in progress. Plan to lay 6m tonight
Thu (24/08) | 24 Aug 2023 | Exit 1 DW93 |  | Trimming completed. Desanding ongoing
Thu (24/08) | 24 Aug 2023 | MH2-5 |  | Cage ladder installation
Thu (24/08) | 24 Aug 2023 | Zone 2 sewer twin pipe installation |  | 47.7m+53m. Total laid 100.7m. Now RTO inspection prior to casting
Thu (24/08) | 24 Aug 2023 | MH5-1 |  | 6th layer rebar works on going. Target to cast by 6pm
Thu (24/08) | 24 Aug 2023 | MH2-5 |  | No activity. Only stock pile clearing
Thu (24/08) | 24 Aug 2023 | MH2-7 |  | Excavation for base slab. Tomorrow to lean concrete
Thu (24/08) | 24 Aug 2023 | MH6-1 |  | Current status of 1st ring work. Tonight to cast
Thu (24/08) | 24 Aug 2023 | MH2-6 |  | Excavation for 6th layer caisson. This team will work late. Will work until MH6-1 complete casting
Thu (24/08) | 24 Aug 2023 | MH5-1 |  | 6th layer caisson casting done
Fri (25/08) | 25 Aug 2023 | Zone 4 |  | DE143 works. No other activity
Fri (25/08) | 25 Aug 2023 | Zone 2 pumping main |  | Area clearing of overcast concrete in preparation for formwork dismantling. Today expected to deliver more concrete stump formwork
Fri (25/08) | 25 Aug 2023 | MH5-1 |  | 6th layer curing
Fri (25/08) | 25 Aug 2023 | Zone 3 |  | Access erection uphill
Fri (25/08) | 25 Aug 2023 | Zone 3 DR2 |  | To continue excavation & hacking before continuing sheetpile installation. As to date, 141/172nos installed
Fri (25/08) | 25 Aug 2023 | MH5-2 |  | Toe board installation, moulding for removal
Fri (25/08) | 25 Aug 2023 | Zone 3 BH151 |  | In progress, 31m
Fri (25/08) | 25 Aug 2023 | BH191 |  | In progress, 26m
Fri (25/08) | 25 Aug 2023 | Zone 4-Loyang Avenue after SIA toward TPE |  | Excavation for Singtel duct laying. 12m target to lay
Fri (25/08) | 25 Aug 2023 | MH6-1 |  | Casting was done
Fri (25/08) | 25 Aug 2023 | MH2-7 |  | Base slab lean concrete done. Levelling in progress
Fri (25/08) | 25 Aug 2023 | MH2-5 |  | Excavation for 11th layer ring. Tomorrow casting. Today they will work until 10PM
Fri (25/08) | 25 Aug 2023 | Zone 3 ECM |  | Second pond wall formwork installation. Plan for casting today
Fri (25/08) | 25 Aug 2023 | Zone 3 BH50 |  | Drilling started
Fri (25/08) | 25 Aug 2023 | Zone 3 DW115 |  | Trial trench in progress
Fri (25/08) | 25 Aug 2023 | Outside exit 1 hoarding |  | DE143 works ongoing
Fri (25/08) | 25 Aug 2023 | MH2-6 |  | 6th layer to continue excavation today
Fri (25/08) | 25 Aug 2023 | Zone 2 PMH11-pMH12 |  | Backfilling works on going, 17 mSHD
Fri (25/08) | 25 Aug 2023 | MH2-5 |  | Today to start 11th layer excavation
Sat (26/08) | 26 Aug 2023 | DR2 |  | Hacking in progress for sheetpile works
Sat (26/08) | 26 Aug 2023 | BH50 |  | In progress, 26m
Sat (26/08) | 26 Aug 2023 | Zone 4 |  | No activity
Sat (26/08) | 26 Aug 2023 | Loyang Way | near exit 1/ Selarang camp | No activity
Sat (26/08) | 26 Aug 2023 | Exit 1 |  | BC cutter maintenance ongoing
Sat (26/08) | 26 Aug 2023 | Zone 3 ST93 |  | Continue trenching for guidewall works
Sat (26/08) | 26 Aug 2023 | MH2-3 |  | No activity
Sat (26/08) | 26 Aug 2023 | MH2-4 |  | No activity. 2nos of prisms was installed
Sat (26/08) | 26 Aug 2023 | MH2-5 |  | Excavation for 11th layer ongoing
Sat (26/08) | 26 Aug 2023 | MH5-2 |  | Preparing to resume 2nd layer excavation. Excavator was shifted from MH2-7
Sat (26/08) | 26 Aug 2023 | Loyang Avenue sidetable- ATT-WG-080 |  | TT on going to identify water pipe (700mm dia)
Sat (26/08) | 26 Aug 2023 | MH5-1 |  | Rectifying the water pump
Sat (26/08) | 26 Aug 2023 | DW15/16 area |  | No activity as of this morning
Sat (26/08) | 26 Aug 2023 | MH2-7 |  | No activity. Base lean concrete was cast last evening
Sat (26/08) | 26 Aug 2023 | Zone 3 BP |  | Site briefing before start work is arranged at 3:30pm
Sat (26/08) | 26 Aug 2023 | MH6-1 |  | Backfilling ongoing
Sat (26/08) | 26 Aug 2023 | ST24A |  | Trimming in progress
Sat (26/08) | 26 Aug 2023 | MH2-6 |  | Hacking and excavation for 6th layer
Sat (26/08) | 26 Aug 2023 | MH2-5 |  | 11th layer BRC installed. Now formwork closing
Sat (26/08) | 26 Aug 2023 | North ramp N2 |  | Excavation temporarily on hold. Toe board installation ongoing
Sat (26/08) | 26 Aug 2023 | MH5-1 |  | Excavation in progress for 7th layer
Sat (26/08) | 26 Aug 2023 | MH5-2 |  | 2nd layer works in progress
Sat (26/08) | 26 Aug 2023 | Z3 BP |  | 2nd casing installation ongoing for first pile
Sat (26/08) | 26 Aug 2023 | Exit 2 |  | Pending lean con casting for pumping main sump pit. Concrete otw
Sat (26/08) | 26 Aug 2023 | MH2-7 |  | Base slab rebar lowering in progress. Tomorrow to cast
Sat (26/08) | 26 Aug 2023 | MH6-1 |  | Rebar work for 2nd ring casting. Tonight to cast. This team will work late
Sat (26/08) | 26 Aug 2023 | ST24A |  | Removal of waterstop end plate
Sat (26/08) | 26 Aug 2023 | MH2-6 |  | Rebar work. Tonight to cast the 6th layer
Sat (26/08) | 26 Aug 2023 | Zone 2 |  | MX4 (Manhole 4)- preparing to lower down tonight
Sat (26/08) | 26 Aug 2023 | Exit 2 |  | Continue excavating for pumping main sump pit
Sat (26/08) | 26 Aug 2023 | MH5-1& MH5-2 |  | End work for today
Sat (26/08) | 26 Aug 2023 | Zone 3 BP retrieval |  | Continue setting up works. Plan to start ard 3pm
Sat (26/08) | 26 Aug 2023 | Zone 3 ECM |  | Pond 2 wall was cast yesterday. Now no activity
Sat (26/08) | 26 Aug 2023 | 9 |  | 45PM left the work area already
Sun (27/08) | 27 Aug 2023 | Zone 3 |  | Formwork installation for ST92, 93 Guidewall ongoing
Sun (27/08) | 27 Aug 2023 | Zone 4 |  | Singtel works at Loyang Way junction
Sun (27/08) | 27 Aug 2023 | Exit 1 |  | Crawler crane maintenance
Sun (27/08) | 27 Aug 2023 | Exit 1 |  | Waterstop welding works ongoing
Sun (27/08) | 27 Aug 2023 | Zone 3 |  | KTC casting the slope
Sun (27/08) | 27 Aug 2023 | Zone 4 |  | DE143 occupying 1 left turn lane at Loyang Way junction for their traffic light pipe laying works
Sun (27/08) | 27 Aug 2023 | MH2-6 |  | Formwork closing almost completed
Sun (27/08) | 27 Aug 2023 | Zone 3 |  | Removal of all 6 cages (including the 2 bottommost cages) ongoing
Sun (27/08) | 27 Aug 2023 | Zone 3 |  | Slope casting completed earlier. Continued ecavation by KTC
Sun (27/08) | 27 Aug 2023 | Zone 3 |  | Levelling of slope by KTC next to access is ongoing
Sun (27/08) | 27 Aug 2023 | Zone 2 |  | Part 1 drain formwork dismantled
Sun (27/08) | 27 Aug 2023 | Zone 2 |  | Part 2 drain formwork installation ongoing
Sun (27/08) | 27 Aug 2023 | ST24A |  | Koden test in progress
Sun (27/08) | 27 Aug 2023 | ST24A |  | Cleaning completed. Now extracting cutter body and prepare for Koden test
Sun (27/08) | 27 Aug 2023 | ST24A |  | Manual depth inspection, depth at 37.43m
Mon (28/08) | 28 Aug 2023 | MH2-7 |  | Base slab casting done
Mon (28/08) | 28 Aug 2023 | ST24A |  | Casting completed. 119 m3. Tremie dismantling on going
Mon (28/08) | 28 Aug 2023 | ST24A |  | Cages 1A and 1B lowered
Mon (28/08) | 28 Aug 2023 | ST24A |  | 3/4 cages installed
Mon (28/08) | 28 Aug 2023 | Exit 2 |  | Continue NB panel installation
Mon (28/08) | 28 Aug 2023 | Exit 2 |  | Continue excavation for pumping main sump pit. Plan for lean con casting today
Mon (28/08) | 28 Aug 2023 | Zone 3 ECM |  | Pond 2 formwork dismantling ongoing
Mon (28/08) | 28 Aug 2023 | DR2 |  | Silt fence installed. Sheetpile installation in progress
Mon (28/08) | 28 Aug 2023 | MH2-7 |  | Base slab rebar inspection done. Concrete ordered
Mon (28/08) | 28 Aug 2023 | MH6-1 |  | Backfilling balance 2.4m to complete
Mon (28/08) | 28 Aug 2023 | MH2-6 |  | Current status of 7th layer. Today they work until 7PM only
Mon (28/08) | 28 Aug 2023 | MH2-3 |  | Now no activity
Mon (28/08) | 28 Aug 2023 | MH5-1 |  | Excavation for 7th layer ring. Tonight working until 10PM
Mon (28/08) | 28 Aug 2023 | N2 |  | 4nos of waler installed. Welding 3 corner done. Balance one, today can complete. Tomorrow 2PM MPI test
Mon (28/08) | 28 Aug 2023 | MH 2-7 |  | Base slab casting on going, 6.5/13 m3
Mon (28/08) | 28 Aug 2023 | MH2-4 |  | Segment of 2nd layer rebar works on going
Mon (28/08) | 28 Aug 2023 | N2 |  | Waler (W1) welding works till 9 pm. Packing concrete also to cast tomorrow after MPI
Mon (28/08) | 28 Aug 2023 | MH5-1 |  | 7th layer excavation continue. Estimated depth at 1m
Mon (28/08) | 28 Aug 2023 | Zone 2 pumping main pipe installation |  | 20 nos concrete stump casting on going
Mon (28/08) | 28 Aug 2023 | Zone 2 P20-21 |  | Depcie team 1 here tonight for singtel pipe laying
Mon (28/08) | 28 Aug 2023 | ST24A |  | Casting status, 102/110 m3. Last 2 trucks on site
Mon (28/08) | 28 Aug 2023 | Zone 3 DR2 sheet pile installation |  | LE stopped work for the day. 100% completed, 167/167
Mon (28/08) | 28 Aug 2023 | Zone 4 loyang way to CV |  | SpTel working here for pipe laying. Target tonight 20m
Mon (28/08) | 28 Aug 2023 | Zone 3 junction |  | Powergas working here to raised up 7 nos valves
Mon (28/08) | 28 Aug 2023 | Zone 3 loyang way to loyang avenue |  | Lane Closure by weng guan for SPPG TT, to find 500mm water pipe alignment
Tue (29/08) | 29 Aug 2023 | ST25A |  | 1st bite trenching continue at 33.3m. Design Depth 35.27m
Tue (29/08) | 29 Aug 2023 | ST24A |  | LSS backfilling done
Tue (29/08) | 29 Aug 2023 | Exit 1 |  | Housekeeping
Tue (29/08) | 29 Aug 2023 | Zone 3 loyang way junction |  | Pgas work continue
Tue (29/08) | 29 Aug 2023 | Exit 1 |  | Preparation for DW88
Tue (29/08) | 29 Aug 2023 | BH167 |  | Drilling works ongoing, current depth 56.7m
Tue (29/08) | 29 Aug 2023 | BH170 |  | Preparation to start SI work
Tue (29/08) | 29 Aug 2023 | BH169 |  | Manual trial trench works for SI work
Tue (29/08) | 29 Aug 2023 | MH2-6 |  | Continue excavation for 7th layer
Tue (29/08) | 29 Aug 2023 | MH2-5 |  | Excavation for 12th layer in progress
Tue (29/08) | 29 Aug 2023 | North ramp | N6 area | Instrumentation installation completed
Tue (29/08) | 29 Aug 2023 | DW15/16 |  | No activity due to no banksman. Called Ye Kyaw to come down to continue and monitor excavation
Tue (29/08) | 29 Aug 2023 | North Ramp | N3 | Preboring works ongoing for pile cap ERSS. Current 9/20nos preboring & 5/20nos. soldier pile completed
Tue (29/08) | 29 Aug 2023 | DW15/16 |  | Excavation and soil loosening ongoing. Ye kyaw will be the substitute banksman
Tue (29/08) | 29 Aug 2023 | North Ramp | N2 | MPI test completed. Concrete packing to be carry out today. Concrete ordered
Tue (29/08) | 29 Aug 2023 | MH5-1 |  | Excavation works ongoing for 7th layer. Target to cast today
Tue (29/08) | 29 Aug 2023 | MH5-2 |  | Excavation ongoing for 3rd layer
Tue (29/08) | 29 Aug 2023 | Zone 3 |  | 2 nos. webbing slings already inserted for Taiyo grab recovery
Tue (29/08) | 29 Aug 2023 | MH5-2 |  | 2nd layer formwork removal ongoing. Thereafter to continue excavation for 3rd layer
Tue (29/08) | 29 Aug 2023 | MH5-1 |  | Continue excavation for 7th layer
Tue (29/08) | 29 Aug 2023 | MH2-5 |  | Continue 12th layer excavation
Tue (29/08) | 29 Aug 2023 | ST25A |  | First bite excavation in progress, 20m
Tue (29/08) | 29 Aug 2023 | MH2-6 |  | Hacking for 7th layer. Estimated depth 1m. Work until 10pm
Tue (29/08) | 29 Aug 2023 | MH2-5 |  | Excavation for 12th layer continue till 10pm. Estimated depth 1m
Tue (29/08) | 29 Aug 2023 | Zone 2 P20-P21 |  | Depcie team 1 for singtel pipe laying. Road kerb was hacked during dayshift. Tonight should be able to lay atleast 8m length of pipe
Tue (29/08) | 29 Aug 2023 | MH5-2 |  | Excavation for 3rd layer completed. LCH already stopped work. Tomorrow to clear soil and trimming works. Tomorrow afternoon to cast
Tue (29/08) | 29 Aug 2023 | Zone 2 pumping main twin pipe laying |  | 42.4m + 37.1 m laid here in between P23-P24. Total nos of footing done 30 pcs
Tue (29/08) | 29 Aug 2023 | Zone 3 P38-P39 |  | Tonight guidewall rebar works for ST89 and ST91 half
Tue (29/08) | 29 Aug 2023 | Exit 1 DW88 |  | 1st bite done. Unfortunately the operator for nightshift on sick leave. Dayshift to continue trenching. Dongah to continue bentonite property check tonight
Tue (29/08) | 29 Aug 2023 | Zone 4 loyang way LP191 |  | Lucky joint here for sptel pipe paying. Tonight target 15m
Tue (29/08) | 29 Aug 2023 | Zone 3/4 juntion |  | Lane closure for pgas work to connect air release valve
Wed (30/08) | 30 Aug 2023 | BH-167 |  | Drilling in progress, current depth 60m, BH-169: SI Rig shifting in progress, to start today, BH-170: Drilling in progress, depth 4m
Wed (30/08) | 30 Aug 2023 | Zone 3 ST91, 90 and 89A | half | Guidewall formwork installation in progress. Plan for casting today
Wed (30/08) | 30 Aug 2023 | Exit 1 |  | Now exposing the trench for 66kV spiking
Wed (30/08) | 30 Aug 2023 | Zone 3 loyang way |  | Pgas working here for gas pipe link up
Wed (30/08) | 30 Aug 2023 | Exit 2 |  | Pumping main sump pit base rebar works ongoing
Wed (30/08) | 30 Aug 2023 | North Ramp | N2 | Concrete packing cast yesterday. Now pending concrete to gain strength before excavation to FEL
Wed (30/08) | 30 Aug 2023 | Exit 1 DW88 |  | 2nd bite excavation in progress
Wed (30/08) | 30 Aug 2023 | Zone 3 |  | PUB maintenance works
Wed (30/08) | 30 Aug 2023 | Zone 3 P30 |  | SPPG contractor working for draw pit. Currently removing existing pipes
Wed (30/08) | 30 Aug 2023 | ST25A |  | BC cutter teeth replacement ongoing
Wed (30/08) | 30 Aug 2023 | MH5-2 |  | Casting completed. 10 m3
Wed (30/08) | 30 Aug 2023 | Zone 2 |  | Singtel pipe laying on going
Wed (30/08) | 30 Aug 2023 | MH5-1 |  | Casting in progress
Wed (30/08) | 30 Aug 2023 | MH5-1 |  | 7th layer casting completed
Wed (30/08) | 30 Aug 2023 | Zone 4 |  | TT completed. Found 500mm water pipe
Wed (30/08) | 30 Aug 2023 | MH2-7 |  | LCH shifting their jacking control container and generator for jacking work
Wed (30/08) | 30 Aug 2023 | MH2-6 |  | Rebar work for 7th layer. Tonight to cast
Wed (30/08) | 30 Aug 2023 | MH2-5 |  | 12th layer casting in progress
Wed (30/08) | 30 Aug 2023 | MH5-2 |  | 3rd layer tonight casting too. Rebar work on going
Wed (30/08) | 30 Aug 2023 | North ramp N3 |  | 3nos of preboring done for soldier piles and 3nos done for steel plates. Today also install 5nos of solder piles
Wed (30/08) | 30 Aug 2023 | ST25A |  | 1st bite excavation done
Wed (30/08) | 30 Aug 2023 | ST25A |  | 1st bite at 34m depth. Balance about 1.2m. Now extracting cutter body for teeth checking and replacement
Wed (30/08) | 30 Aug 2023 | MH2-6 7th layer |  | Last segment of moulding installation in progress. Target to cast at 9pm
Wed (30/08) | 30 Aug 2023 | Zone 2 P15-P16 |  | Depcie team 1 here for singtel pipe laying. Target tonight 6m. FYI no hacking to be done, they will use reaper hook to remove premix
Wed (30/08) | 30 Aug 2023 | MH5-2 |  | 3rd layer moulding installation. Target to cast at 10pm. Concrete ordered
Wed (30/08) | 30 Aug 2023 | MH2-6 |  | 7th layer casting in progress
Wed (30/08) | 30 Aug 2023 | ST25A |  | Flange welding prior to 2nd bite trenching
Wed (30/08) | 30 Aug 2023 | Zone 3 |  | Weng guan team 1 here at P43 for SPPG pipe laying
Wed (30/08) | 30 Aug 2023 | DW88 |  | Waterstop installation on going
Wed (30/08) | 30 Aug 2023 | Zone 4 loyang way junction |  | Lucky joint working here for sptel pipe laying. Tonight target 17m
Wed (30/08) | 30 Aug 2023 | Zone 3 DR2 area |  | LE shifting out their materials
Wed (30/08) | 30 Aug 2023 | Zone 3 near P36 |  | Backfilling ongoing for platform making for ST313 instruments installation
Thu (31/08) | 31 Aug 2023 | Ongoing SI works by 3 rigs |  | *BH167* current depth 61m;, *BH169* current depth 14m;, *BH170* current depth 6m
Thu (31/08) | 31 Aug 2023 | Zone 2 in front of shel |  | Singtel contractor here for pipe jamming works at new MH. Target to complete today
Thu (31/08) | 31 Aug 2023 | Zone 2 singtel pipe laying works |  | Excavation status
Thu (31/08) | 31 Aug 2023 | ST25A |  | 2nd bite trenching on going at 21m depth
Thu (31/08) | 31 Aug 2023 | Zone 3 P43 |  | Drain hacked for SPPG pipe laying. Continue excavation
Thu (31/08) | 31 Aug 2023 | Exit 1 |  | DW88 rebar cages installation in progress. 3/6 completed. 4th cage in progress
Thu (31/08) | 31 Aug 2023 | Zone 3 |  | Manual TT ongoing for BH51
Thu (31/08) | 31 Aug 2023 | Exit 1 DW88 |  | Casting completed
Thu (31/08) | 31 Aug 2023 | DR2 |  | No activity
Thu (31/08) | 31 Aug 2023 | Zone 3 ST91 -89A | half | Guidewall casting done
Thu (31/08) | 31 Aug 2023 | Exit 2 |  | Pumping main sump pit rebar works in progress
Thu (31/08) | 31 Aug 2023 | BH-167 |  | Drilling in progress, current depth 62m, BH-169: Drilling in progress, depth 26m, BH-170: Drilling in progress, depth 14m
Thu (31/08) | 31 Aug 2023 | MH2-4 |  | Pending QPS inspection on the brc for 2nd layer part 2 casting. Today will cast
Thu (31/08) | 31 Aug 2023 | MH2-7 |  | Shifting materials
Thu (31/08) | 31 Aug 2023 | Zone 3 |  | Road cutting and hacking for ECM pond
Thu (31/08) | 31 Aug 2023 | Zone 3 |  | ECM backfilling
Thu (31/08) | 31 Aug 2023 | Exit 2 |  | Pumping main sump pit base casting
Thu (31/08) | 31 Aug 2023 | ST25A |  | 2nd bite trenching completed. Now flange welding to do trimming for end plate removal
Thu (31/08) | 31 Aug 2023 | Exit 1 DW88 |  | 6/6 cages and 2/2 hanging bars installed. Now preparing to install Tremie pipes. Target to cast around 930am
Thu (31/08) | 31 Aug 2023 | MH5-1 |  | Excavation ongoing
Thu (31/08) | 31 Aug 2023 | ST25A |  | Trimming ongoing
Thu (31/08) | 31 Aug 2023 | North ramp N3 |  | LMRA briefing before start work
Thu (31/08) | 31 Aug 2023 | N3 ERSS pile cap |  | Today target to complete 20 nos pre coring for lagging plate and install 10 nos plate
Thu (31/08) | 31 Aug 2023 | MH5-1 |  | Excavation to 8th layer in progress. Until 10PM
Thu (31/08) | 31 Aug 2023 | MH5-2 |  | LCH tidy up around work area
Fri (01/09) | 01 Sep 2023 | MH2-6 |  | Working platfrom preparation work for telecopic. Yesterday drain was hacked. Today to remove 7th layer moulding and proceed with 8th layer excavation
Fri (01/09) | 01 Sep 2023 | MH2-4 |  | Segment of 2nd layer near singtel haunching to cast. 1.5m3
Fri (01/09) | 01 Sep 2023 | MH5-1 |  | 8th layer excavation on going. Estimated depth 1m. Today plan to complete excavation and trimming. Tomorrow am plan to cast
Fri (01/09) | 01 Sep 2023 | MH5-2 |  | Today to remove moulding for 3rd layer and continue excavation. They will try to complete excavation until 1m
Fri (01/09) | 01 Sep 2023 | ST25A |  | End plate extraction on going
Fri (01/09) | 01 Sep 2023 | Zone 3 |  | 3rd ECM pond debris clearing
Fri (01/09) | 01 Sep 2023 | ZONE 3 |  | Today formwork dismantling of guidewall for ST8A-ST91 half
Fri (01/09) | 01 Sep 2023 | MH2-7 |  | Setting up of genset and control room on going
Fri (01/09) | 01 Sep 2023 | MH5-1 |  | Excavation til 1.2m completed. Now wall trimming at 200mm. Target to complete trimming by 5pm. Today LCH will work till 5pm only
Fri (01/09) | 01 Sep 2023 | MH5-2 |  | Excavation status. Now mini excavator still occupied at MH5-1. Therefore unable to continue excavation here
Fri (01/09) | 01 Sep 2023 | Zone 3 |  | Cable pulling for pumping main power supply
Fri (01/09) | 01 Sep 2023 | DW87 |  | Pre excavation completed. Now preparation to start trenching
Fri (01/09) | 01 Sep 2023 | ST25A |  | 2nd bite cleaning still not done. Bc cutter coolant pipe got leakage. Repair works in progress
Fri (01/09) | 01 Sep 2023 | MH2-7 |  | Area levelling for slurry tank set up
Fri (01/09) | 01 Sep 2023 | Exit 3 |  | DW15/16 excavation for Utility crossing no activity
Sat (02/09) | 02 Sep 2023 | Loyang Way near LP23 |  | Tonight plan for power duct pipe laying
Sat (02/09) | 02 Sep 2023 | BH-167 |  | Drilling in progress, current depth 64.7m, BH-169: Drilling in progress, depth 33m, BH-170: Drilling in progress, depth 24m
Sat (02/09) | 02 Sep 2023 | MH2-3 |  | No activity
Sat (02/09) | 02 Sep 2023 | MH2-4 |  | Today plan to do drain support works
Sat (02/09) | 02 Sep 2023 | MH2-5 |  | Preparation for 13th layer excavation
Sat (02/09) | 02 Sep 2023 | Zone 3 P35 |  | Premix removal for Singtel pipe laying works
Sat (02/09) | 02 Sep 2023 | N3 ERSS |  | Preboring for 16th soldier pile in progress
Sat (02/09) | 02 Sep 2023 | N2 |  | Excavation works by KTC in progress to FEL
Sat (02/09) | 02 Sep 2023 | ST21 |  | First bite excavation temporarily on hold for cutter teeth replacement. Current depth ard 31m
Sat (02/09) | 02 Sep 2023 | MH2-6 |  | Tonight 1 night shift team to continue for the 8th layer works. Manpower: 4
Sat (02/09) | 02 Sep 2023 | MH5-2 |  | Excavation works for 4th layer. Target to cast tmr
Sat (02/09) | 02 Sep 2023 | MH5-1 |  | Rebar installation for 8th layer. Target to cast today
Sat (02/09) | 02 Sep 2023 | Sewer Pumping Main pipes | P24-25 | Pipes bolt tightening in progress. Target to cast 30nos. stump formwork today
Sat (02/09) | 02 Sep 2023 | ST21 |  | BC cutter shifting ongoing. Target to start in the afternoon
Sat (02/09) | 02 Sep 2023 | Zone 3 |  | Crane inspection works
Sat (02/09) | 02 Sep 2023 | Zone 3 | Beside JTC | Cable pulling works for SPPG
Sat (02/09) | 02 Sep 2023 | Zone 3 |  | LE unloading of walers materials
Sat (02/09) | 02 Sep 2023 | Exit 1 | DW87 | Cleaning in progress
Sat (02/09) | 02 Sep 2023 | Zone3 |  | Manual excavation in progress for SPPG pipe laying works
Sat (02/09) | 02 Sep 2023 | BH49 |  | SI Drilling works
Sat (02/09) | 02 Sep 2023 | Zone 4 |  | SingTel contractor & DE143 working along Loyang way
Sat (02/09) | 02 Sep 2023 | MH2-7 |  | Setting up & wiring works for pipe jacking
Sat (02/09) | 02 Sep 2023 | Exit 3 |  | DW15/16 continue excavation and shoring works
Sat (02/09) | 02 Sep 2023 | Opp. Exit 2, JTC | ST21-SC40 | 1st bite trenching work ongoing
Sat (02/09) | 02 Sep 2023 | MH2-6 |  | Excavation works ongoing for 8th layer
Sat (02/09) | 02 Sep 2023 | BH-167 |  | Drilling completed, current depth 66m. Pending termination depth confirmation, BH-169: Drilling in progress, depth 37m, BH-170: Drilling in progress, depth 32m
Sat (02/09) | 02 Sep 2023 | Bet. P21-P22 |  | Premix removal for trial trench work for 1.5m dia BP
Sat (02/09) | 02 Sep 2023 | MH2-5 |  | Excavation for 13th layer in progress
Sat (02/09) | 02 Sep 2023 | MH5-1 |  | 8th layer Formwork completed. Pending for concrete truck to arrive for cast
Sat (02/09) | 02 Sep 2023 | MH5-2 |  | Continue excavation for 4th layer
Sat (02/09) | 02 Sep 2023 | PRD3 side table |  | SPTel lucky joint pipe laying works (16m) ongoing
Sat (02/09) | 02 Sep 2023 | N2 |  | KTC Continue excavation works to FEL
Sat (02/09) | 02 Sep 2023 | MH1-3 |  | RC sump wall rebar works
Sat (02/09) | 02 Sep 2023 | Zone 3 |  | Excavation work for ECM construction
Sat (02/09) | 02 Sep 2023 | Exit 1 |  | Slope casting works in progress
Sat (02/09) | 02 Sep 2023 | Exit 1 | DW87 | Preparation for rebar cage lowering
Sat (02/09) | 02 Sep 2023 | BH49 |  | SI Drilling works, current depth 34m
Sat (02/09) | 02 Sep 2023 | Bet. P24-25 |  | Twin pipe stumps 30nos. casting in progress
Sat (02/09) | 02 Sep 2023 | MH2-6 |  | Current status at 8th layer
Sat (02/09) | 02 Sep 2023 | MH2-5 |  | Excavation ongoing for 13th layer
Sat (02/09) | 02 Sep 2023 | MH5-2 |  | BRC installation ongoing for 4th layer. Target to cast tmr
Sat (02/09) | 02 Sep 2023 | MH5-1 |  | No more activity. 8th ring was cast just now
Sat (02/09) | 02 Sep 2023 | DW15/16 |  | Continue excavation and shoring till 10pm
Sat (02/09) | 02 Sep 2023 | Exit 1 |  | DW87 rebar cage 2A/1A lapping ongoing
Sat (02/09) | 02 Sep 2023 | Exit 3 |  | DW15/16 excavation and shoring works in progress
Sat (02/09) | 02 Sep 2023 | MH2-6 |  | Excavation works for 8th layer
Sat (02/09) | 02 Sep 2023 | MH2-7 |  | Preparation for pipe jacking setting up works
Sun (03/09) | 03 Sep 2023 | Zone 2 |  | Gate 6 installation of gate for man access
Sun (03/09) | 03 Sep 2023 | Zone 1 |  | No activity
Sun (03/09) | 03 Sep 2023 | Zone 3 |  | DR2 No activity
Sun (03/09) | 03 Sep 2023 | Exit 1 |  | Endplate welding in progress
Sun (03/09) | 03 Sep 2023 | Exit 1 |  | DW113/114 guidewall formwork ongoing. To cast in the afternoon
Sun (03/09) | 03 Sep 2023 | Zone 3 CCE |  | Steel plate shifting
Sun (03/09) | 03 Sep 2023 | Exit 1 |  | DW87 cast this morning. To start excavation at DW90 next
Sun (03/09) | 03 Sep 2023 | Zone 3 Loyang Way near bus depot entrance |  | M&P works by DE143
Sun (03/09) | 03 Sep 2023 | MH2-6 |  | Hacking and excavation ongoing for 8th layer
Sun (03/09) | 03 Sep 2023 | N3 Pilecap |  | 2 nos. steel plates left to drive in
Sun (03/09) | 03 Sep 2023 | P35/34 |  | Singtel pipe laying in progress. Target 18m
Sun (03/09) | 03 Sep 2023 | DW87 |  | Rebar cage & hanging bar installation completed. Now preparing for tremie pipe installation
Sun (03/09) | 03 Sep 2023 | Gate 6 |  | Man access completed
Sun (03/09) | 03 Sep 2023 | Zone 2 South Ramp |  | Formwork dismantling progress
Sun (03/09) | 03 Sep 2023 | Zone 3 P44 |  | Shoring installation in progress for SPPG pipe laying
Sun (03/09) | 03 Sep 2023 | Zone 2 South Ramp |  | Status of Drain Formwork installation
Sun (03/09) | 03 Sep 2023 | Loyang Way opp LP68 |  | Backfilling completed. Now pending premix reinstatement. Singtel pipes unable to lay tonight at corridor location due to congested services
Sun (03/09) | 03 Sep 2023 | Loyang Way LP67 | T-junction | Works ongoing by Lucky Joint
Sun (03/09) | 03 Sep 2023 | DW87 |  | Tremie pipe installation in progress
Sun (03/09) | 03 Sep 2023 | P34/35 |  | Singtel pipes laid, 18m. Concrete haunching in progress
Sun (03/09) | 03 Sep 2023 | ST21 |  | First bite excavation about 34.4m
Sun (03/09) | 03 Sep 2023 | P44 |  | Tonight only excavation & shoring installation. No pipe laying
Sun (03/09) | 03 Sep 2023 | Zone 3 |  | KTC done for the day. Canvas sheets laid over slope
Sun (03/09) | 03 Sep 2023 | Exit 1 |  | DW113/114 guidewall cast
Sun (03/09) | 03 Sep 2023 | DW87 |  | Casting ongoing. Progressive vol: 85m3/110.5m3
Sun (03/09) | 03 Sep 2023 | DW15/16 |  | Soil loosening until 10pm
Sun (03/09) | 03 Sep 2023 | ST21 |  | 2nd bite trenching at 22m
Mon (04/09) | 04 Sep 2023 | Zone 3 LP68 |  | Excavation work for singtel pipe laying. Target 8m
Mon (04/09) | 04 Sep 2023 | Zone 3 loyang way |  | No activity observed for M1 pipe laying
Mon (04/09) | 04 Sep 2023 | ST21 |  | 2/2 cages installed. Hanging bar also installed. Fissure grouting pipe installation and welding works in progress
Mon (04/09) | 04 Sep 2023 | ST21 |  | Trimming on going
Mon (04/09) | 04 Sep 2023 | MH2-6 |  | No activity. 8th ring was cast yesterday
Mon (04/09) | 04 Sep 2023 | MH2-5 |  | 13th ring casting ongoing
Mon (04/09) | 04 Sep 2023 | North ramp N2 |  | Access installation in progress. Workers currently on tea break
Mon (04/09) | 04 Sep 2023 | ST21 |  | Cleaning in progress
Mon (04/09) | 04 Sep 2023 | MH5-2 |  | Currently no activity. 4th ring was cast yesterday
Mon (04/09) | 04 Sep 2023 | Zone 2 P6 |  | Singtel pipe jamming works by term contractor
Mon (04/09) | 04 Sep 2023 | MH5-1 |  | Hacking & excavation ongoing for 9th layer
Mon (04/09) | 04 Sep 2023 | BH169, BH170 |  | Coring in progress
Mon (04/09) | 04 Sep 2023 | MH2-7 |  | WH checking the invert level for LCH. Tomorrow plan to cast thrust block
Mon (04/09) | 04 Sep 2023 | MH2-6 |  | 8th layer formwork removal
Mon (04/09) | 04 Sep 2023 | 04/08/2023 |  | 15.9m + 10.6m = 26.5m (5 pipes)
Mon (04/09) | 04 Sep 2023 | 04/08/2023 |  | 15.9m + 15.9m = 31.8m (6 pipes)
Mon (04/09) | 04 Sep 2023 | MH2-4 |  | Current status of excavation for 2nd layer 2nd part. Tomorrow plan to cast. Today this team working until 7PM only
Mon (04/09) | 04 Sep 2023 | MH5-2 |  | Current status of 5th layer excavation
Mon (04/09) | 04 Sep 2023 | DW15/16 |  | Access and barricade installation continue
Mon (04/09) | 04 Sep 2023 | ST21 |  | 2/2 rebar cages installation in progress
Mon (04/09) | 04 Sep 2023 | MH5-2 |  | LCH provided 1 team tonight for excavation work at 5th layer
Mon (04/09) | 04 Sep 2023 | Zone 3 P35-P36 |  | 1 team for singtel pipe laying here. Plan to undercross drain. Estimated length 8m
Mon (04/09) | 04 Sep 2023 | Exit 1 |  | DW90 trenching on going. Current depth at 16m
Mon (04/09) | 04 Sep 2023 | Zpne 3 P44-P45 |  | Sppg pipe laying 12way on going. Target 25m
Tue (05/09) | 05 Sep 2023 | P36 |  | Drilling ongoing for inclinometer installation by RG
Tue (05/09) | 05 Sep 2023 | MH2-7 |  | Preparation, wiring and setting up works in progress. Target to cast Thrust block today
Tue (05/09) | 05 Sep 2023 | MH2-6 |  | Excavation for 9th layer
Tue (05/09) | 05 Sep 2023 | BH169 |  | Drilling ongoing, current depth 48m, BH170: Drilling ongoing, current depth 45m
Tue (05/09) | 05 Sep 2023 | Zone 3 BH48 |  | SI started
Tue (05/09) | 05 Sep 2023 | Exit 1 DW90 |  | Water stop end plate preparation
Tue (05/09) | 05 Sep 2023 | MH2-4 |  | Manual excavation for 2nd ring 2nd part 600mm
Tue (05/09) | 05 Sep 2023 | Exit 1 |  | SPPG on site for the cable spiking
Tue (05/09) | 05 Sep 2023 | Loyang Way near Exit 1 |  | Lane closure by other contractor
Tue (05/09) | 05 Sep 2023 | Zone 4 |  | DE143 works at LA junction
Tue (05/09) | 05 Sep 2023 | Loyang way LP 86 |  | Lane closed for singtel pipe laying
Tue (05/09) | 05 Sep 2023 | Zone 3 |  | ECM pond 3 currently no activity
Tue (05/09) | 05 Sep 2023 | Exit 2 BH149 |  | In progress, 32m
Tue (05/09) | 05 Sep 2023 | MH5-1 |  | Excavation ongoing for 9th layer
Tue (05/09) | 05 Sep 2023 | MH5-2 |  | Excavation ongoing for 5th layer
Tue (05/09) | 05 Sep 2023 | North Ramp | N6 ERSS | LE area preparation and surveying & marking of ERSS location in progress
Tue (05/09) | 05 Sep 2023 | North ramp | N2 | KTC - excavation works to FEL
Tue (05/09) | 05 Sep 2023 | MH2-7 |  | Thrust block casting completed
Tue (05/09) | 05 Sep 2023 | MH2-6 |  | Wall trimming prior to rebar installation
Tue (05/09) | 05 Sep 2023 | ST21 |  | Tremie pipe installed. Waiting for concrete lorry
Tue (05/09) | 05 Sep 2023 | MH5-2 |  | Excavation on going. Tonight target to complete excavation till 1.2m. Dayshift to do wall trimming and cast
Tue (05/09) | 05 Sep 2023 | Zone 3 |  | SPPG pipe laying completed. 34m
Tue (05/09) | 05 Sep 2023 | Zone 3 loyang way LP68 |  | Singtel pipe laying in progress. 9m
Tue (05/09) | 05 Sep 2023 | ST21 |  | Casting completed. 73m3
Tue (05/09) | 05 Sep 2023 | MH2-6 |  | Hacking works continue. *9th layer*
Tue (05/09) | 05 Sep 2023 | MH5-2 |  | Excavation reached 1.2m depth. Dayshift to continue do trimming, rebar installation and casting
Tue (05/09) | 05 Sep 2023 | DW90 |  | Trimming done. End plate extraction in progress
Tue (05/09) | 05 Sep 2023 | Zone 3 |  | SPPG pipe laid, backfilling works
Tue (05/09) | 05 Sep 2023 | Zone 3 loyang avenue |  | Singtel pipe laid. 7.5m
Tue (05/09) | 05 Sep 2023 | MH5-1 |  | Hacking & excavation in progress for 9th layer
Tue (05/09) | 05 Sep 2023 | MH5-2 |  | 5th ring rebar installation ongoing. Plan for casting later today
Tue (05/09) | 05 Sep 2023 | North ramp N6 |  | Works to resume tmr
Tue (05/09) | 05 Sep 2023 | North ramp N3 |  | Excavation in progress
Tue (05/09) | 05 Sep 2023 | North ramp N2 |  | No activity
Tue (05/09) | 05 Sep 2023 | MH2-4 |  | 2nd layer formwork installation. Pending to cast
Tue (05/09) | 05 Sep 2023 | DW15/16 |  | Current shoring status. Now ongoing barricade installation
Tue (05/09) | 05 Sep 2023 | DW15/16 |  | Barricade installation continue
Tue (05/09) | 05 Sep 2023 | Exit 3 |  | Excavation on going to lower down SPPG pipes laid previously. Pipe current depth at 1.7m. They need to go until 2.3m
Tue (05/09) | 05 Sep 2023 | Depcie team 2 |  | Area preparation for sspg pipe laying along loyang lane (MH6-1 location)
Tue (05/09) | 05 Sep 2023 | Zone 3 P25-P26 |  | Pumping main twin pipe stump casting completed. Housekeeping on going. 24 stumps cast, 12 pipes installed (63.6m)
Tue (05/09) | 05 Sep 2023 | MH2-6 |  | Dayshift ended their work. Nightshift to take over. Plan to cast tonight around 3am
Tue (05/09) | 05 Sep 2023 | MH2-7 |  | Preparation for thrust block casting
Tue (05/09) | 05 Sep 2023 | Zone 2 Depcie team 1 |  | Tonight to lay singtel pipe here. Estimate 18m
Tue (05/09) | 05 Sep 2023 | MH5-1 9th layer |  | Rebar installation on going. Target to cast by 11pm
Tue (05/09) | 05 Sep 2023 | MH5-2 |  | Concrete just arrived for 5th layer casting
Tue (05/09) | 05 Sep 2023 | Zone 3 |  | BC cutter maintenance works
Tue (05/09) | 05 Sep 2023 | Exit 1 |  | DW90 casting on going. 42.5/59 m3. 2 more trucks to go
Wed (06/09) | 06 Sep 2023 | Exit 1 |  | Plan to start pre-excavation and trenching tonight
Wed (06/09) | 06 Sep 2023 | P36 |  | Drilling in progress for inclinometer installation by RG, 22/43m
Wed (06/09) | 06 Sep 2023 | Exit 1 DW114 |  | Guidewall rebar installation in progress
Wed (06/09) | 06 Sep 2023 | Zone 3 loyang way |  | Lane closed for singtel pipe laying
Wed (06/09) | 06 Sep 2023 | Loyang way opp 64+4 coffe shop |  | M1 lane closed for pipe laying
Wed (06/09) | 06 Sep 2023 | MH5-1 |  | 9th layer casting completed. No more activity here
Wed (06/09) | 06 Sep 2023 | MH5-2 |  | 5th layer casting completed. No more activity here
Wed (06/09) | 06 Sep 2023 | Zone 2 |  | Singtel pipe laying on going. 12m only
Wed (06/09) | 06 Sep 2023 | Exit 1 |  | DW90 casting completed
Wed (06/09) | 06 Sep 2023 | Loyang way LP 86 |  | Singtel pipe laid 6m
Wed (06/09) | 06 Sep 2023 | Zone 3 loyang way |  | Work completed and area reinstated. Lane opened
Wed (06/09) | 06 Sep 2023 | Zone 2 |  | Singtel pipe laying work completed. Area backfilled
Wed (06/09) | 06 Sep 2023 | MH2-7 |  | Cabling and piping work for jacking work in progress
Wed (06/09) | 06 Sep 2023 | MH2-6 |  | 9th layer rebar installation in progress. Casting will take over by dayshift team
Wed (06/09) | 06 Sep 2023 | Exit 3 Dwall coring |  | Clearing stagnant before continue with coring work
Wed (06/09) | 06 Sep 2023 | MH6-1 |  | LCH clearing their materials to handover to Wee Guan
Wed (06/09) | 06 Sep 2023 | 06/09/2023 |  | Pumping pipe 4 pipes 4×5.3=21.2m installed and footing stump 8nos installed
Wed (06/09) | 06 Sep 2023 | N3 |  | Excavation done for waler installation. Now pumping out water
Wed (06/09) | 06 Sep 2023 | N2 |  | Preparing to dewater
Wed (06/09) | 06 Sep 2023 | MH5-2 |  | LCH bending BRC for caisson shaft rebar work
Wed (06/09) | 06 Sep 2023 | Pile No-1 |  | Casing installation from ground level is done around 4.7m/ planned to install is 9.5m (4.7/9.5m done). Tonight Taiyo working until 10PM (until complete PE inspection)
Wed (06/09) | 06 Sep 2023 | Exit 3 |  | Weng guan team 1 here to continue remove sppg pipes previously laid. Level need to change
Wed (06/09) | 06 Sep 2023 | Zone 2 |  | Depcie team 1 here for singtel pipe laying
Wed (06/09) | 06 Sep 2023 | North ramp N3 |  | Access installation to W1 layer on going
Thu (07/09) | 07 Sep 2023 | MH5-2 |  | To continue hacking & excavation for layer 6
Thu (07/09) | 07 Sep 2023 | North ramp N6 |  | Boring ongoing for soldier pie installation
Thu (07/09) | 07 Sep 2023 | North ramp N3 |  | Lean con casting
Thu (07/09) | 07 Sep 2023 | Zone 3 ECM pond 3 |  | Rebar works in progress
Thu (07/09) | 07 Sep 2023 | P36 |  | Drilling ongoing for inclinometer installation by RG, 23.5m/43m
Thu (07/09) | 07 Sep 2023 | Zone 3 BH110 |  | In progress, 22m
Thu (07/09) | 07 Sep 2023 | DW91 |  | 1st bite excavation done. Now prepare platform for 2nd bite
Thu (07/09) | 07 Sep 2023 | MH5-2 |  | Excavation on going
Thu (07/09) | 07 Sep 2023 | BH169 |  | Termination depth - 60.8m, BH170: Drilling ongoing, current depth 57m
Thu (07/09) | 07 Sep 2023 | MH2-7 |  | Preparation for jacking works
Thu (07/09) | 07 Sep 2023 | Zone 3 ST142 |  | Pre-excavation completed
Thu (07/09) | 07 Sep 2023 | MH5-2 |  | Excavation in progress for 6th layer
Thu (07/09) | 07 Sep 2023 | ST142 |  | Preparing to start trenching
Thu (07/09) | 07 Sep 2023 | Exit 1 DW91 |  | C-lock welding
Thu (07/09) | 07 Sep 2023 | Exit 1 |  | Guidewall excavation for DW83-84
Thu (07/09) | 07 Sep 2023 | N2 |  | Continue excavation to FEL
Thu (07/09) | 07 Sep 2023 | Near MH6-1 |  | To continue excavation for SPPG pipe laying
Thu (07/09) | 07 Sep 2023 | Zone 2 loyang avenue |  | Singtel pipe laying done. Area backfilled
Thu (07/09) | 07 Sep 2023 | Exit 1 |  | DW91 trenching started
Thu (07/09) | 07 Sep 2023 | MH5-1 |  | Continue hacking and excavation for 10th layer
Thu (07/09) | 07 Sep 2023 | MH5-2 |  | Continue excavation for 6th layer
Thu (07/09) | 07 Sep 2023 | North ramp N6 |  | Preboring for ERSS completed for the day — 3nos for solider pile, 4nos for steel plates. Tmr to resume
Thu (07/09) | 07 Sep 2023 | N3 |  | Continue waler bracket welding. Works till ard 9pm today
Thu (07/09) | 07 Sep 2023 | MH2-4 |  | 3rd layer formwork installation
Thu (07/09) | 07 Sep 2023 | CCE ST142 |  | First bite excavation in progress, 21m
Thu (07/09) | 07 Sep 2023 | Near MH6-1 |  | Wee Guan working for Power duct laying
Fri (08/09) | 08 Sep 2023 | 3rd ECM pond |  | Plan to cast base today
Fri (08/09) | 08 Sep 2023 | MH2-5 |  | Excavation works in progress for base slab. Today to lean concrete
Fri (08/09) | 08 Sep 2023 | MH2-4 |  | No activity
Fri (08/09) | 08 Sep 2023 | Zone 1 |  | Krishco excavator mobilized in. Inspection of excavator ongoing
Fri (08/09) | 08 Sep 2023 | MH5-1 & MH5-2 |  | No activity. Curing works
Fri (08/09) | 08 Sep 2023 | MH2-7 |  | Soft eye hacking. Tomorrow to start trial jacking
Fri (08/09) | 08 Sep 2023 | MH6-1 |  | HDPE work was done. Safety net installation on going
Fri (08/09) | 08 Sep 2023 | ST142 |  | Dongah laid 3 layers of rubber mats and prepare to resume excavation. If vibration alert come again then they will discontinue first bite excavation and continue with 2nd bite excavation tonight
Fri (08/09) | 08 Sep 2023 | MH2-5 |  | Excavation done to base slab. Going to remove mini and lean concrete today
Fri (08/09) | 08 Sep 2023 | MH5-1& MH5-2 |  | Now no work
Sun (10/09) | 10 Sep 2023 | DR2 |  | Continue boring for inclinometer, 32/43m done
Sun (10/09) | 10 Sep 2023 | MH2-7 |  | Jacking machine already lowered down and push in. Preparing for 2nd part of machine push in
Sun (10/09) | 10 Sep 2023 | MH5-2 |  | Continue excavation at center. Balance around side to complete
Sun (10/09) | 10 Sep 2023 | ST142 |  | Cutter teeth wheel replacement
Sun (10/09) | 10 Sep 2023 | ST142 |  | First bite current depth at 29m from GWTL
Sun (10/09) | 10 Sep 2023 | MH2-3, MH2-4, MH2-5, MH2-6 |  | No activity
Sun (10/09) | 10 Sep 2023 | MH5-2 |  | Excavation in progress
Sun (10/09) | 10 Sep 2023 | MH5-1 |  | No activity
Mon (11/09) | 11 Sep 2023 | MH5-2 |  | A little bit more trimming to be completed. Thereafter to lay BRC. Manpower: 4
Mon (11/09) | 11 Sep 2023 | Zone 3 in front of JTC blk 2 |  | 6m excavation and shoring by WG(Hynergy). To lay at night
Mon (11/09) | 11 Sep 2023 | Zone 3 |  | 3rd ECM pond formwork installation ongoing
Mon (11/09) | 11 Sep 2023 | Zone 1 |  | Krishco Live valve installation in progress for existing 300mm pipe
Mon (11/09) | 11 Sep 2023 | Zone 3 DR2 |  | Drilling for Inclinometer at 36.5/43m. To install inclinometer by Wed and start drilling for WSP
Mon (11/09) | 11 Sep 2023 | Exit 3 |  | BH05 at 27m/37.2m depth
Mon (11/09) | 11 Sep 2023 | MH5-2 |  | 7th layer cast
Mon (11/09) | 11 Sep 2023 | N3 |  | No activity. Concrete packing was cast on sat. Tmr will carry out cube test
Mon (11/09) | 11 Sep 2023 | N2 |  | HSL continue pile hacking works
Mon (11/09) | 11 Sep 2023 | MH5-2 |  | 7th layer abt 80% rebar tying completed. Night team working from 8pm-5am. Day shift will take over
Mon (11/09) | 11 Sep 2023 | N5 |  | Backfilling in progress for SPPG works
Mon (11/09) | 11 Sep 2023 | MH2-5 |  | Base slab rebar works in progress
Mon (11/09) | 11 Sep 2023 | MH2-6 |  | Excavation for 11th layer
Mon (11/09) | 11 Sep 2023 | MH2-7 |  | Pipe jacking for 2nd pipe
Mon (11/09) | 11 Sep 2023 | ST142 |  | Trimming completed
Mon (11/09) | 11 Sep 2023 | MH2-7 to MH2-6 |  | 3rd pipe jacking in progress. 3/15 pipes in progress. (15 pipes is center to center of manhole, around 13 pipes will reach MH2-6 caisson already)
Mon (11/09) | 11 Sep 2023 | MH2-5 |  | Base slab rebar work in progress. Tonight plan to cast. Will be late night
Mon (11/09) | 11 Sep 2023 | MH5-1 & MH5-2 |  | Rebar bending for shaft work
Mon (11/09) | 11 Sep 2023 | MH2-7 |  | 5th pipe in progress. The team working till 10pm today
Mon (11/09) | 11 Sep 2023 | Zone 1 |  | No more activity. Gate locked
Mon (11/09) | 11 Sep 2023 | MH5-2 & MH5-1 |  | No activity
Mon (11/09) | 11 Sep 2023 | MH2-5 |  | No activity
Mon (11/09) | 11 Sep 2023 | MH2-4 |  | No activity
Mon (11/09) | 11 Sep 2023 | MH2-6 |  | Preparing to continue 11th layer excavation. Tonight manpower: 6
Mon (11/09) | 11 Sep 2023 | Zone 3 P27 |  | Continue excavation & shoring installation for Singtel pipe laying
Mon (11/09) | 11 Sep 2023 | Zone 3 BP Retrieval P7 |  | Casing installed 8m
Mon (11/09) | 11 Sep 2023 | Zone 3 BP Retrieval P1 |  | 7.6/9.5m. Taiyo works done for the day. Now housekeeping
Mon (11/09) | 11 Sep 2023 | ST142 |  | Cutter wheel replacement ongoing
Mon (11/09) | 11 Sep 2023 | DW92 |  | 2nd bite excavation in progress, 11m
Mon (11/09) | 11 Sep 2023 | DW92 |  | Rebar cage delivery
Mon (11/09) | 11 Sep 2023 | Loyang Ave LP110 |  | Plan for Singtel pipe laying tonight, 24m
Tue (12/09) | 12 Sep 2023 | Zone 4 LP110 |  | Singtel pipe laying in progress
Tue (12/09) | 12 Sep 2023 | MH2-6 |  | 11th layer trimming ongoing
Tue (12/09) | 12 Sep 2023 | Exit 3 |  | Singtel pipe jamming ongoing
Tue (12/09) | 12 Sep 2023 | P27 |  | Singtel pipe laying in progress
Tue (12/09) | 12 Sep 2023 | ST142 |  | Trimming in progress
Tue (12/09) | 12 Sep 2023 | DW92 |  | 2nd bite excavation completed, 22.5m. Now preparing for waterstop end plate loosening at DW93 side
Tue (12/09) | 12 Sep 2023 | Zone 4 LP110 |  | Singtel pipes laid, 24m tonight. Now preparing for reinstatement
Tue (12/09) | 12 Sep 2023 | BH160 |  | SI drilling in progress, current depth 4m
Tue (12/09) | 12 Sep 2023 | MH2-6 |  | 11th layer rebar installation started
Tue (12/09) | 12 Sep 2023 | Bet. P22-P21 |  | HSL unloading materials for trial bore works
Tue (12/09) | 12 Sep 2023 | N3 |  | KTC Excavation to FEL in progress
Tue (12/09) | 12 Sep 2023 | N2 |  | Manual hacking/trimming works for piles
Tue (12/09) | 12 Sep 2023 | Zone 1 |  | WHDA continue manual trial trench works to identify existing utilities location
Tue (12/09) | 12 Sep 2023 | Zone 1 |  | Krishco doing trial trench for water pipe laying works
Tue (12/09) | 12 Sep 2023 | P27 |  | Singtel pipe laying completed, 24m
Tue (12/09) | 12 Sep 2023 | MH5-1 |  | No activity
Tue (12/09) | 12 Sep 2023 | MH2-6 |  | BRC installation in progress. Works continue till 7am
Tue (12/09) | 12 Sep 2023 | MH2-4 |  | Formwork closing for 5th layer caisson
Tue (12/09) | 12 Sep 2023 | MH2-5 |  | Base slab casting
Tue (12/09) | 12 Sep 2023 | MH2-6 |  | Dayshift to continue rebar tying onwards
Tue (12/09) | 12 Sep 2023 | MH2-4 |  | 5th ring casting ongoing
Tue (12/09) | 12 Sep 2023 | MH5-2 |  | No activity at the moment. Tonight’s manpower will be working at this location (6pax)
Tue (12/09) | 12 Sep 2023 | MH5-1 |  | No activity
Tue (12/09) | 12 Sep 2023 | Zone 3 P28 |  | Tonight plan for Singtel pipe laying ard 10m
Tue (12/09) | 12 Sep 2023 | MH2-7 |  | 5nos of pipe jacking done yesterday. Preparing to continue No-6 jacking
Tue (12/09) | 12 Sep 2023 | CCE ST 92 |  | Temporarily on halt earlier to check on mud pump
Tue (12/09) | 12 Sep 2023 | Exit 1 DW92 |  | Rebar cage installation in progress
Tue (12/09) | 12 Sep 2023 | ST92 |  | First bite resume
Tue (12/09) | 12 Sep 2023 | P27-P28 |  | 24m length of Singtel duct laid. Manhole location confirmed
Tue (12/09) | 12 Sep 2023 | Zone 4 LP112 |  | Tonight plan for Singtel pipe laying
Tue (12/09) | 12 Sep 2023 | Near MH2-6 |  | Tonight plan for Singtel pipe laying
Wed (13/09) | 13 Sep 2023 | BH111 |  | Reached 20m
Wed (13/09) | 13 Sep 2023 | Zone 3 |  | Excavation for DW28 guidewall started
Wed (13/09) | 13 Sep 2023 | MH5-1 |  | Dayshift team continue rebar tying. Plan to call for inspection ard midnight
Wed (13/09) | 13 Sep 2023 | P28 |  | Shoring done. Now preparing to lay pipes
Wed (13/09) | 13 Sep 2023 | Zone 2 |  | Pipe laying in progress
Wed (13/09) | 13 Sep 2023 | MH5-2 |  | Continue hacking and excavation for 8th layer
Wed (13/09) | 13 Sep 2023 | P28 |  | Singtel pipes laid, 10.7m
Wed (13/09) | 13 Sep 2023 | Zone 2 |  | Singtel pipes laid, 13m
Wed (13/09) | 13 Sep 2023 | Zone 4 |  | Singtel pipes laid, 24m
Wed (13/09) | 13 Sep 2023 | MH5-2 |  | Continue hacking & excavation
Wed (13/09) | 13 Sep 2023 | Zone 3 |  | ST142 LSS last 2 trucks
Wed (13/09) | 13 Sep 2023 | DR2 |  | Drilling reached 43m. Inclinometer installation ongoing. Tomorrow morning to continue wsp
Wed (13/09) | 13 Sep 2023 | DW92 |  | Rebar cage installation completed at 0405hrs
Wed (13/09) | 13 Sep 2023 | ST92 |  | First bite excavation in progress, 28.4m
Wed (13/09) | 13 Sep 2023 | Exit 1 DW113 |  | First bite excavation started, DW92: Tremie pipe installation in progress
Wed (13/09) | 13 Sep 2023 | MH5-2 |  | Continue excavation 8th layer. Current depth abt 600mm. Works till 730am
Wed (13/09) | 13 Sep 2023 | Zone 2 |  | Tonight plan for Singtel pipe laying
Wed (13/09) | 13 Sep 2023 | MH5-1 |  | 12th layer excavation in progress
Wed (13/09) | 13 Sep 2023 | MH5-2 |  | Continue hacking & excavation for 8th layer
Wed (13/09) | 13 Sep 2023 | Zone 3 P26 |  | WG trial trench ongoing
Wed (13/09) | 13 Sep 2023 | CCE ST92 |  | First bite trimming in progress, 21m
Wed (13/09) | 13 Sep 2023 | Zone 4 LP112 |  | Tonight trial trench for Singtel manhole installation
Wed (13/09) | 13 Sep 2023 | MH2-6 |  | Continue excavation. About 800mm more to excavate
Thu (14/09) | 14 Sep 2023 | Exit 2 |  | Excavation ongoing
Thu (14/09) | 14 Sep 2023 | N2 |  | Hardcore removal in progress. Today target to lean concrete
Thu (14/09) | 14 Sep 2023 | N3 |  | Afternoon to continue excavation to FEL with mini excavator
Thu (14/09) | 14 Sep 2023 | Zone 3 P7 |  | Casing installation in progress
Thu (14/09) | 14 Sep 2023 | P26 |  | Trial trench ongoing for Starhub pipe laying
Thu (14/09) | 14 Sep 2023 | MH5-1 |  | Inspection done. Now preparing for casting
Thu (14/09) | 14 Sep 2023 | P26 |  | TT completed
Thu (14/09) | 14 Sep 2023 | MH5-1 |  | 12th layer casting started
Thu (14/09) | 14 Sep 2023 | Zone 2 |  | Singtel pipe laid, 9m
Thu (14/09) | 14 Sep 2023 | P26 |  | Trench covered and barricaded back
Thu (14/09) | 14 Sep 2023 | Zone 4 |  | TT done — cables at 1.1 and 1.6m depths
Thu (14/09) | 14 Sep 2023 | Bet. P21 - P22 |  | Preboring for trial bore started. Preparing to install casing
Thu (14/09) | 14 Sep 2023 | Beside MH2-5 |  | KTC drain removal in progress. Once done, will proceed with backfilling works
Thu (14/09) | 14 Sep 2023 | N2 |  | Levelling works in progress, to cast lean concrete later
Thu (14/09) | 14 Sep 2023 | Zone 1 |  | Krishco excavation works for water pipe laying in progress
Thu (14/09) | 14 Sep 2023 | MH5-1 |  | 12th layer casting completed
Thu (14/09) | 14 Sep 2023 | DW113 |  | Casting ongoing
Thu (14/09) | 14 Sep 2023 | MH2-6 |  | Continue hacking and trimming
Thu (14/09) | 14 Sep 2023 | P20-21 |  | Singtel duct laying to Manhole number MH321956. Plan to lay 10m
Thu (14/09) | 14 Sep 2023 | MH2-4 |  | Continue excavation for 6th layer caisson. Tomorrow to cast
Thu (14/09) | 14 Sep 2023 | North ramp | N2 | Lean concrete for the base. Now preparing for pressure washing of pile head
Thu (14/09) | 14 Sep 2023 | MH5-2 |  | Trimming below caisson wall in progress. Tonight to cast
Thu (14/09) | 14 Sep 2023 | Zone 3 P26 |  | Plan to continue exposing Starhub cable, abt 4m excavation
Thu (14/09) | 14 Sep 2023 | DR2 |  | RG drilling ongoing for water standpipe installation. Inclinometer already installed
Thu (14/09) | 14 Sep 2023 | Zone 3 ECM pond 4 |  | Rebar installation
Thu (14/09) | 14 Sep 2023 | Exit 1 BH86 |  | Packer test in progress
Thu (14/09) | 14 Sep 2023 | DW113 |  | Casting already completed earlier this morning. Total vol: 72m3
Thu (14/09) | 14 Sep 2023 | Bet. P21 - P22 |  | Preparation works to start trial bore today
Thu (14/09) | 14 Sep 2023 | ST92 |  | 2nd bite excavation in progress, 32m
Fri (15/09) | 15 Sep 2023 | Exit 2 |  | Excavation ongoing near existing pond. Pumping main sump no activity
Fri (15/09) | 15 Sep 2023 | DW28 |  | Guidewall formwork installation. Plan for casting today
Fri (15/09) | 15 Sep 2023 | Near Gate 5 |  | Excavation for cable pulling ongoing
Fri (15/09) | 15 Sep 2023 | MH2-9 |  | TT in progress
Fri (15/09) | 15 Sep 2023 | MH2-4 |  | Excavation ongoing for 6th layer. Target to cast today
Fri (15/09) | 15 Sep 2023 | P19 |  | Manual trial trench to check for utilities ongoing
Fri (15/09) | 15 Sep 2023 | North ramp | N6 | Pre boring in progress
Fri (15/09) | 15 Sep 2023 | Zone 1 |  | Krishco installing 2x 45deg short bend pipe to undercross existing utilities for water pipe laying
Fri (15/09) | 15 Sep 2023 | DR2 |  | No activity
Fri (15/09) | 15 Sep 2023 | ST92 |  | Stop endplate installation in progress
Fri (15/09) | 15 Sep 2023 | Exit 1 DW114 |  | First bite excavation in progress
Fri (15/09) | 15 Sep 2023 | Zone 3 BH67 |  | In progress
Fri (15/09) | 15 Sep 2023 | Exit 1 DW114 |  | First bite completed. Now ongoing 2nd bite
Fri (15/09) | 15 Sep 2023 | ST92 |  | Water stop installation
Fri (15/09) | 15 Sep 2023 | MH5-2 |  | 1st layer BRC installed. Now continue with 2nd layer
Fri (15/09) | 15 Sep 2023 | Zone 3 P7 |  | Current status 8.3/9.5m
Fri (15/09) | 15 Sep 2023 | MH5-1 |  | Excavation ongoing for 13th layer
Fri (15/09) | 15 Sep 2023 | North ramp N2 |  | Base lean con for balance portion
Fri (15/09) | 15 Sep 2023 | North ramp N6 |  | Activity done for the day
Fri (15/09) | 15 Sep 2023 | MH2-4 |  | 6th ring rebars inspected. Now formwork closing
Fri (15/09) | 15 Sep 2023 | MH2-6 |  | TBM already reached to MH2-6 outer caisson. Now hacking for TBM retrieval. This team working until 10PM tonight
Fri (15/09) | 15 Sep 2023 | Near MH2-5 |  | Excavation for Singtel duct laying. Plan to lay 7m tonight
Fri (15/09) | 15 Sep 2023 | MH2-4 |  | 6th layer casting done. Now housekeeping
Fri (15/09) | 15 Sep 2023 | MH5-1 |  | Continue excavation for 13th layer casting. Casting will be late night already
Fri (15/09) | 15 Sep 2023 | Zone 3 P7 |  | Preparing to install casing. Current status: 8.2/9.5m
Fri (15/09) | 15 Sep 2023 | Zone 3 BH111 |  | In progress, 43m
Fri (15/09) | 15 Sep 2023 | Zone 3 |  | ECM pond 4 rebar works ongoing
Fri (15/09) | 15 Sep 2023 | ST221 |  | Current status of slope cutting
Fri (15/09) | 15 Sep 2023 | Zone 3 BH67 |  | SPT ongoing. Current depth, 8m
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | N3 pilecap excavation by KTC started
Sat (16/09) | 16 Sep 2023 | Zone 3 |  | DW28 guidewall casting started
Sat (16/09) | 16 Sep 2023 | Gate 5 |  | Levelling works ongoing
Sat (16/09) | 16 Sep 2023 | Loyang Way junction at Exit 1 side |  | CR1070 preparing to start coring at the 300mm dia pipe
Sat (16/09) | 16 Sep 2023 | Zone 4 |  | DE143 working within their hoarding. No other activity
Sat (16/09) | 16 Sep 2023 | ST92 |  | Cage A (1/4) & Cage B (2/4) cages lowered down
Sat (16/09) | 16 Sep 2023 | Exit 3 |  | Trial trench by RG still ongoin
Sat (16/09) | 16 Sep 2023 | 1st stage |  | 3/6nos. Done
Sat (16/09) | 16 Sep 2023 | Zone 3 JTC |  | WG excavated the area for WHDA to hack the guidewall. To continue SPPG pipe laying after guidewall hacking is done
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | Singtel works still ongoing
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | Rebar shifting to North Ramp
Sat (16/09) | 16 Sep 2023 | Zone 1 |  | Krischo excavation for water pipes ongoing. To lay 14m today
Sat (16/09) | 16 Sep 2023 | DW114 |  | Trimming for waterstop end plate removal
Sat (16/09) | 16 Sep 2023 | ST92 |  | Continue lower down rebar cages
Sat (16/09) | 16 Sep 2023 | MH2-9 |  | TT on going for shaft construction
Sat (16/09) | 16 Sep 2023 | DW15/16 1st stage |  | 4th vertical cut ongoing. To reposition machine thereafter to cut remaining 2 horizontal cuts
Sat (16/09) | 16 Sep 2023 | Zone 3 |  | ST92 to cast around 6pm
Sat (16/09) | 16 Sep 2023 | Zone 3 |  | DR1 area levelling works
Sat (16/09) | 16 Sep 2023 | Zone 3 |  | BH112 at 12m depth
Sat (16/09) | 16 Sep 2023 | Zone 3 |  | BH67 drilling ongoing. 35.5m/39m
Sat (16/09) | 16 Sep 2023 | MH2-9 |  | TT was done until 1.2m. No services found as of now
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | Hacking of drain debris
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | Singtel pipe jamming works ongoing
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | Trial trench for P19-5 in progress
Sat (16/09) | 16 Sep 2023 | Zone 2 |  | ICE top slab rebar works for drain ongoing. To cast top slab in the afternoon
Sun (17/09) | 17 Sep 2023 | Dipcie pipe jamming work until 5 |  | 30AM. Today they have done internal koden test from T junction to Lamp post 25 (Loyang Way) MH322152 to MH322152/ 18 Ways
Sun (17/09) | 17 Sep 2023 | MH5-2 |  | Excavation in progress to 1m depth
Sun (17/09) | 17 Sep 2023 | ST142 |  | First bite excavation in progress, 33m
Sun (17/09) | 17 Sep 2023 | Exit 1 DW85 |  | Rebar cage lapping in progress
Sun (17/09) | 17 Sep 2023 | MH5-2 |  | Tonight to continue 9th layer excavation. Manpower: 4
Mon (18/09) | 18 Sep 2023 | MH5-1 |  | Casting completed for 14th layer
Mon (18/09) | 18 Sep 2023 | ST142 |  | Cutter wheel teeth replaced. First bite excavation resumes. Current depth 34.1m
Mon (18/09) | 18 Sep 2023 | DW85 |  | Casting ongoing. Progressive vol: 22.5m3. Est vol: 45m3
Mon (18/09) | 18 Sep 2023 | MH5-2 |  | Hacking and excavation in progress for 9th layer. Works for the night till 5am
Mon (18/09) | 18 Sep 2023 | Zone 2 Trial bore pile |  | Found rock (GIII) at 34.95m from TOC. Socketing 6m to commence
Mon (18/09) | 18 Sep 2023 | DW85 |  | Casting completed at 0200hrs. Total vol: 45m3
Mon (18/09) | 18 Sep 2023 | Near MH6-1 |  | Ley Choon doing cable pulling from MH6-1 area to Gate 5
Mon (18/09) | 18 Sep 2023 | Bet. P21-P22 |  | Trial boring works ongoing. Current Depth 38m
Mon (18/09) | 18 Sep 2023 | MH2-4 |  | Excavation in progress for 7th layer
Mon (18/09) | 18 Sep 2023 | Zone 3 |  | Drain hacked for SPPG pipe laying. Now preparing to hack guidewall for ST25. Balance 8m length of pipe here to be laid
Mon (18/09) | 18 Sep 2023 | Zone 3 P26-P27 |  | Starhub term contractor shifting cables, work to complete by today
Mon (18/09) | 18 Sep 2023 | N2 |  | CGW rebar installation for pile cap works
Mon (18/09) | 18 Sep 2023 | Zone 1 |  | Krishco reinstatement ongoing. They unable to locate the existing water pipe at the trial trench location due to existing eHV and 66kV utilities. Tmr they will do another trial trench at another location
Mon (18/09) | 18 Sep 2023 | MH5-2 |  | Rebar installation for 9th layer. Today will cast
Mon (18/09) | 18 Sep 2023 | MH5-2 |  | Trimming
Mon (18/09) | 18 Sep 2023 | ST142 |  | 2nd bite excavation in progress, 18.6m
Mon (18/09) | 18 Sep 2023 | BP7 |  | Outer casing installation in progress, 5.4m
Mon (18/09) | 18 Sep 2023 | Zone 3 P27 |  | Excavation for SPPG pipe laying
Mon (18/09) | 18 Sep 2023 | MH2-4 |  | Hacking and excavation ongoing for 7th layer until 10pm
Mon (18/09) | 18 Sep 2023 | Zone 2 |  | Hump installation
Mon (18/09) | 18 Sep 2023 | MH5-1 |  | Awaiting to cast 14th layer
Mon (18/09) | 18 Sep 2023 | MH5-2 |  | No activity
Mon (18/09) | 18 Sep 2023 | Loyang Way LP23/1F |  | TT for Singtel corridor
Mon (18/09) | 18 Sep 2023 | Loyang Way LP24F |  | Singtel pipe jamming
Mon (18/09) | 18 Sep 2023 | Zone 4 LP114 |  | Excavation for Singtel manhole installation. Plan installation ard midnight. TMOs on standby
Tue (19/09) | 19 Sep 2023 | Zone 3 LVC side |  | Starhub localised shifting done, today to backfill. Area now available for ST224, 223 and 222
Tue (19/09) | 19 Sep 2023 | Zone 4 LP114 |  | Tonight plan to lay Singtel pipes connecting to the newly installed MX3
Tue (19/09) | 19 Sep 2023 | MH2-5 |  | Area preparation for setting up of control room and slurry tank for Jacking to 2-6 and 2-4
Tue (19/09) | 19 Sep 2023 | MH2-7 to MH2-6 jacking |  | Today water tightness test
Tue (19/09) | 19 Sep 2023 | Exit 1/ Vent shaft |  | Subsoil pipe installation
Tue (19/09) | 19 Sep 2023 | Zone 1 |  | Area preparation for lean con for new ECM pond
Tue (19/09) | 19 Sep 2023 | PMH7-9 |  | Rebar scanning and marking for civil brackets
Tue (19/09) | 19 Sep 2023 | Zone 4 |  | MX3 safely installed
Tue (19/09) | 19 Sep 2023 | LP23/1F |  | Manual TT ongoing
Tue (19/09) | 19 Sep 2023 | ST142 |  | 2nd bite excavation in progress, 27m
Tue (19/09) | 19 Sep 2023 | MH2-9 |  | Manual TT in progress
Tue (19/09) | 19 Sep 2023 | DW15/DW16 wire saw cutting |  | Balance 2 vertical lines to cut
Tue (19/09) | 19 Sep 2023 | Zone 2 |  | Trial bore for LSS backfilling, waiting for truck
Tue (19/09) | 19 Sep 2023 | N6 |  | Installation of solider pile and lagging plate in progress due to insufficient embedment depth previously
Tue (19/09) | 19 Sep 2023 | Zone 4 |  | Area backfilled and compacted at newly installed MX3 location
Tue (19/09) | 19 Sep 2023 | Zone 1 |  | Krishco trial trench completed. Able to find the existing water pipe. Tmr will continue trial trench and water pipe laying at other lane
Tue (19/09) | 19 Sep 2023 | Zone 1 |  | Cable exposed for OG box shifting
Tue (19/09) | 19 Sep 2023 | P27 |  | Excavation & shoring installation only
Tue (19/09) | 19 Sep 2023 | Exit 1 DW84 |  | First bite excavation started
Tue (19/09) | 19 Sep 2023 | MH2-4 |  | 7th ring casting completed
Tue (19/09) | 19 Sep 2023 | North ramp N2 pile cap revar works |  | B2 and B1 installation completed. Bar chair installation in progress. Works until 7pm only
Tue (19/09) | 19 Sep 2023 | N101 Incident Report |  | Date: 18 Sep 2023, Time of Incident: 17:45pm, Location: Section 6-1 Span-G, IP details: PITCHAI SURESH, Fin: XXXX8975X, Nationality: Indian, Subcon: JKG Construction Pte. Ltd. (GS Supply Worker), Type of incident: Finger Injury (Right hand – ring finger), Description:, On 18th Sep 2023 about 17:45hrs, IP, and 3nos of his co-workers were adjusting the concrete block which was used to support the water pipe (size-650X650X700mm). The concrete block was lifted and supported using crane. In the process of setting up, IP assisted to guide the concrete blocks and IP finger was caught in between concrete block & support bracket (C-channel) – Pls refer the photo. Immediately rendered first-aid treatment and sent to Farrer Park Medical Centre for treatment, Further investigation is ongoing and will further update
Tue (19/09) | 19 Sep 2023 | MH5-2 |  | Currently no activity. Tonight plan to continue excavation for 10th layer
Tue (19/09) | 19 Sep 2023 | ST142 |  | Trimming completed. Internal koden checked done
Tue (19/09) | 19 Sep 2023 | Exit 1 DW86 |  | First bite excavation in progress. DW84: To continue rebar cage installation tonight
Tue (19/09) | 19 Sep 2023 | ST142 |  | Preparing for 3rd bite
Tue (19/09) | 19 Sep 2023 | BP7 |  | Taiyo to continue inner casing removal tmr. Now housekeeping
Tue (19/09) | 19 Sep 2023 | Zone 3 P27 |  | ST25 guidewall hacking done yesterday. Shoring and excavation on going. Today to lay 5m pipe 14 ways here for SPPG
Tue (19/09) | 19 Sep 2023 | Loyang Way LP23/1F |  | Tonight plan for shoring & steel decking installation (Singtel)
Wed (20/09) | 20 Sep 2023 | Zone 3 P32-P33 |  | Starhub term contractor here for pipe laying, 6 way. Today target to lay 12m
Wed (20/09) | 20 Sep 2023 | N6 |  | Excavation to W1 layer started. Target to complete today. Est loose volume 100 m3 ~ 30 loads
Wed (20/09) | 20 Sep 2023 | N2 |  | Top bar T2 installation on going. Today plan to complete T1 and T2 and start side bar
Wed (20/09) | 20 Sep 2023 | MH5-2 |  | Hacking ongoing for 10th layer
Wed (20/09) | 20 Sep 2023 | MH5-2 |  | Hacking & excavation ongoing
Wed (20/09) | 20 Sep 2023 | ST142 |  | 3rd bite internal koden check
Wed (20/09) | 20 Sep 2023 | Exit 1 DW86 |  | First bite excavation completed. Depth at 21.3m. // DW84: Rebar cage & hanging bar installed. Now preparing tremie pipe installation
Wed (20/09) | 20 Sep 2023 | Zone 4 |  | Singtel pipes laid, 11m
Wed (20/09) | 20 Sep 2023 | DW84 |  | Casting ongoing. Progressive vol: 26.5m3. Est total vol: 54m3
Wed (20/09) | 20 Sep 2023 | Zone 2 LP192 |  | TT done for SPPG
Wed (20/09) | 20 Sep 2023 | LP23/1F |  | Shoring completed
Wed (20/09) | 20 Sep 2023 | Zone 2 near PMH3 |  | Shoring installation (SPPG)
Wed (20/09) | 20 Sep 2023 | DW84 |  | Casting completed at 0520hrs. Total vol: 54m3
Wed (20/09) | 20 Sep 2023 | Loyang Way LP23/1F |  | Steel decking installed. Lane opened
Wed (20/09) | 20 Sep 2023 | MH5-2 |  | 10th layer hacking & excavation depth about 600mm. Night team until 7am
Wed (20/09) | 20 Sep 2023 | 3rd block |  | Excavating around 200-300mm to expose lifting point
Wed (20/09) | 20 Sep 2023 | MH5-2 |  | Excavation for 10th layer. Plan for casting later tonight
Wed (20/09) | 20 Sep 2023 | MH5-1 |  | No activity
Wed (20/09) | 20 Sep 2023 | BP7 |  | Setup ongoing for pile extraction
Wed (20/09) | 20 Sep 2023 | ST142 |  | Waterstop installation in progress
Wed (20/09) | 20 Sep 2023 | Exit 1 DW86 |  | Preparing to resume 2nd bote
Wed (20/09) | 20 Sep 2023 | DW15/16 |  | Backfill current status
Wed (20/09) | 20 Sep 2023 | DW15/16 |  | Wire saw cutting completed yesterday. Now removing cutting machine and area preparing for lifting works. Crane will be on site after lunch. Lifting from 4pm-7pm
Wed (20/09) | 20 Sep 2023 | Loyang Way LP23/1F |  | Plan to continue excavation tonight
Wed (20/09) | 20 Sep 2023 | Zone 4 LA |  | Works by other contractor
Wed (20/09) | 20 Sep 2023 | Zone 3 P27 |  | Yesterday SPPG pipe 5m length laid here until pulling pit area. Now Wee guan helping DG to remove the adjacent guidewall for ST24A so not to damage their pipe
Thu (21/09) | 21 Sep 2023 | MH2-4 |  | 7th layer mould to open and start exacavation today
Thu (21/09) | 21 Sep 2023 | MH2-5 |  | Control room setting up for pipe jacking works
Thu (21/09) | 21 Sep 2023 | N2 |  | Side bars installation on going. Today plan also to install starter bars for column
Thu (21/09) | 21 Sep 2023 | Zone 1 |  | Krishco trial trench work in progress for 300mm water pipe work @ Loyang Avenue (3rd lane). They will lay pipe if the area is free from services
Thu (21/09) | 21 Sep 2023 | Zone 1 |  | Trial trench works ongoing for SPPG cable diversion for OG box
Thu (21/09) | 21 Sep 2023 | MH5-2 |  | 10th layer curing
Thu (21/09) | 21 Sep 2023 | MH5-1 |  | Manual Excavation for 15th layer due to existing sewer pip
Thu (21/09) | 21 Sep 2023 | Zone 3 |  | Starhub (Mo Guan) excavation for pipe laying ongoing. Target to lay 12-18m today
Thu (21/09) | 21 Sep 2023 | DW15/16 |  | WG backfilled 1 side and to continue backfilling the other side. Today to lay singtel and sppg. Tmr to lay M1 and starhub
Thu (21/09) | 21 Sep 2023 | MH5-2 |  | BRC installation for 10th layer in progress
Thu (21/09) | 21 Sep 2023 | LP23/1F |  | Continue manual excavation
Thu (21/09) | 21 Sep 2023 | DW15/16 |  | Shoring works in progress. Current depth 2.5m. Pipe level is 3.5m below current ground level
Thu (21/09) | 21 Sep 2023 | Loyang Way near Exit 1 |  | Singtel pipe laying in progress
Thu (21/09) | 21 Sep 2023 | MH2-4 |  | 8th layer excavation on going
Thu (21/09) | 21 Sep 2023 | Zone 1 |  | Krishco trial trench completed. Now suverying and preparing to backfill
Thu (21/09) | 21 Sep 2023 | MH5-2 |  | BRC installation in progress. Target to call for inspection ard 4am
Thu (21/09) | 21 Sep 2023 | MH5-1 |  | Manual excavation continue around existing pipe. Now around 500mm
Thu (21/09) | 21 Sep 2023 | CCE ST93 |  | First bite excavation in progress
Thu (21/09) | 21 Sep 2023 | ST142 |  | Rebar cage installation in progress
Thu (21/09) | 21 Sep 2023 | N6 |  | Excavation till W1 layer completed
Thu (21/09) | 21 Sep 2023 | N2 |  | Column starter bar installation on going
Thu (21/09) | 21 Sep 2023 | DW15/16 area | P25 | Excavation & shoring for SPPG pipe laying
Thu (21/09) | 21 Sep 2023 | Zone 3 |  | 4th ecm pond formwork closing. 1 side only fully closed
Thu (21/09) | 21 Sep 2023 | DW15/16 |  | Propping and manual excavation ongoing. Night team to lay singtel and sppg pipes
Thu (21/09) | 21 Sep 2023 | Loyang Way LP23/1F |  | Lane reopened
Thu (21/09) | 21 Sep 2023 | DR2 |  | Rebar planting for 5 diagonal struts completed. Now waiting for Lifting machine for waler installation
Thu (21/09) | 21 Sep 2023 | Loyang Way near Exit 1 |  | Lane reopened
Thu (21/09) | 21 Sep 2023 | MH5-2 |  | 10th ring rebar inspected. Formwork installation ongoing
Thu (21/09) | 21 Sep 2023 | MH5-2 |  | Casting ongoing
Thu (21/09) | 21 Sep 2023 | DW15/16 |  | Wee guan excavation for SPPG pipe laying
Thu (21/09) | 21 Sep 2023 | ST142 |  | Cage 3B/4B lapping ongoing
Thu (21/09) | 21 Sep 2023 | Zone 3 BH68 |  | Drilling in progress, 30.5m
Fri (22/09) | 22 Sep 2023 | BH161 |  | Drilling works ongoing, depth 48m
Fri (22/09) | 22 Sep 2023 | MH2-4 |  | Excavation for 8th layer
Fri (22/09) | 22 Sep 2023 | N6 |  | Access on going for bracket and waler installation
Fri (22/09) | 22 Sep 2023 | N3 |  | Super mini excavator on site. Excavation resume
Fri (22/09) | 22 Sep 2023 | N2 pile cap |  | Rebar works in progress
Fri (22/09) | 22 Sep 2023 | MH5-1 |  | 15th layer manual excavation to expose existing sewer pipe
Fri (22/09) | 22 Sep 2023 | MH5-2 |  | Moulding dismantling for 10th layer. Afterwhich will start excavation
Fri (22/09) | 22 Sep 2023 | Zone 1 |  | Krishco doing trial trench works at 2 locations to locate existing services
Fri (22/09) | 22 Sep 2023 | MH2-1 |  | Current status of excavation. To continue hacking of footpath and divert the internal CCTV cables
Fri (22/09) | 22 Sep 2023 | Zone 1 |  | 2nos TT by Krishco. Found HT cable slab at slow lane & 300mm dia water pipe within site
Fri (22/09) | 22 Sep 2023 | MH5-2 |  | 11th layer excavation in progress
Fri (22/09) | 22 Sep 2023 | North ramp N2 |  | Continue pile cap rebar works
Fri (22/09) | 22 Sep 2023 | North ramp N3 |  | No activity
Fri (22/09) | 22 Sep 2023 | MH2-4 |  | Continue excavation for layer 8
Fri (22/09) | 22 Sep 2023 | P25 |  | Starhub pipe laying in progress. M1 completed
Fri (22/09) | 22 Sep 2023 | MH2-4 |  | 8th layer excavation in progress. Tonight to cast. Will be late night
Fri (22/09) | 22 Sep 2023 | MH2-5 |  | Clearing rain water and set up for jacking frame
Fri (22/09) | 22 Sep 2023 | MH2-5 |  | Hoses and cables connection for jacking work
Fri (22/09) | 22 Sep 2023 | MH5-1 |  | Excavation for 15th layer caisson until 7PM
Fri (22/09) | 22 Sep 2023 | MH5-2 |  | Excavation to 11th layer in progress
Fri (22/09) | 22 Sep 2023 | MH2-9 |  | Tonight LCH will start manual excavation for hoarding footing
Sat (23/09) | 23 Sep 2023 | ST093 |  | Rebar cages inspection completed with RTO, QAQC and WHDA. Total 8 cages inspected
Sat (23/09) | 23 Sep 2023 | DW15/16 area |  | Current backfill status
Sat (23/09) | 23 Sep 2023 | BH68 |  | Drilling completed. Grouting works in progress. Will shift the rig next to BH69
Sat (23/09) | 23 Sep 2023 | BH70 |  | Hand augering works in progress
Sat (23/09) | 23 Sep 2023 | ECM pond 4 |  | Formwork closing ongoing
Sat (23/09) | 23 Sep 2023 | MC96 |  | Maintenance works in progress
Sat (23/09) | 23 Sep 2023 | Zone 4 |  | Slope casting works in progress
Sat (23/09) | 23 Sep 2023 | Zone 1 |  | Krishco excavation works in progress. Today to check if the existing water pipe found is live or not. (not shown in the pub plan). They will use ferrule tapping method to check
Sat (23/09) | 23 Sep 2023 | MH5-2 |  | Unloading of material in progress
Sat (23/09) | 23 Sep 2023 | N5 |  | Preboring for Soldier pile started
Sat (23/09) | 23 Sep 2023 | N3 |  | No activity
Sat (23/09) | 23 Sep 2023 | N2 pile cap |  | Rebar works (shear links) installation in progress. Target to cast on Monday
Sat (23/09) | 23 Sep 2023 | MH5-1 |  | Manual excavation works for 15th layer
Sat (23/09) | 23 Sep 2023 | Near MH2-8 |  | WG continue excavation and shoring works for utilities pipe laying
Sat (23/09) | 23 Sep 2023 | MH2-1 |  | Rebar installation for 1st layer. Target to cast today
Sat (23/09) | 23 Sep 2023 | Exit 2 |  | Unloading of dwall materials to storage area
Sat (23/09) | 23 Sep 2023 | Exit 2 |  | BH133A SI work has commenced. Drilling in progress
Sat (23/09) | 23 Sep 2023 | ST093 |  | Desanding / Cleaning in progress for 3rd bite
Sat (23/09) | 23 Sep 2023 | Zone 1 |  | Krishco reinstatement works in progress. The existing water pipe found previously was not live after ferrule tapping check
Sat (23/09) | 23 Sep 2023 | MH5-2 |  | Excavation ongoing for 11th layer
Sat (23/09) | 23 Sep 2023 | N6 |  | Waler bracket installation in progress
Sat (23/09) | 23 Sep 2023 | N5 |  | Continue of preboring works
Sat (23/09) | 23 Sep 2023 | N2 Pile cap |  | Continue of rebar installation
Sat (23/09) | 23 Sep 2023 | Near PMH3 |  | Excavation & shoring works ongoing for SPPG pipe laying works
Sat (23/09) | 23 Sep 2023 | BH159 |  | Rig shifted from BH161, Monday will start
Sun (24/09) | 24 Sep 2023 | MH2-5 |  | Platform preparation for jacking work
Sun (24/09) | 24 Sep 2023 | MH5-2 |  | LCH one team working for excavation. Current excavation depth is around 800mm for 11th layer
Sun (24/09) | 24 Sep 2023 | Loyang way from Changi Village | LP11-LP12 | Lane closed for TT for singtel pipe corridor
Sun (24/09) | 24 Sep 2023 | P33-34 |  | Starhub excavation for duct laying
Sun (24/09) | 24 Sep 2023 | MH5-2 |  | 11 layer excavation on going. Reached 1.2m. Now trimming on going
Sun (24/09) | 24 Sep 2023 | MH5-2 |  | Excavation for 11th layer caisson. To cast in night shift
Sun (24/09) | 24 Sep 2023 | MH2-5 |  | Formwork closing for Thrust block. To cast tomorrow
Sun (24/09) | 24 Sep 2023 | N2 |  | Formwork completed. No more activity
Sun (24/09) | 24 Sep 2023 | ST93 |  | Replacing some Tremie pipes before casting. 5 concrete trucks now on site
Mon (25/09) | 25 Sep 2023 | ST141 |  | 1st bite trenching at 36.2m depth
Mon (25/09) | 25 Sep 2023 | Zone 4 loyang way opp selerang camp, LP12-13 |  | Lane closed for singtel TT work
Mon (25/09) | 25 Sep 2023 | Loyang way in front of exit 1 |  | Lane closed for singtel pipe laying towards junction. Target tonight 15m
Mon (25/09) | 25 Sep 2023 | Loyang way opp lincstech LP32/1F |  | Lane closed for singtel pipe laying
Mon (25/09) | 25 Sep 2023 | MH2-9 |  | Hoarding works on going
Mon (25/09) | 25 Sep 2023 | ST93 |  | Casting continue. Running volume 217/245 m3
Mon (25/09) | 25 Sep 2023 | Zone 4 loyang way |  | 2nd TT for the night. Found HT, starhub and singtel cables
Mon (25/09) | 25 Sep 2023 | P34 |  | Starhub pipe laying
Mon (25/09) | 25 Sep 2023 | Zone 4 loyang way |  | Work completed and area reinstated, 1st TT
Mon (25/09) | 25 Sep 2023 | Zone 4 loyang way |  | Work completed and area reinstated, 2nd TT
Mon (25/09) | 25 Sep 2023 | BP7 |  | 2nd casing removal in progress
Mon (25/09) | 25 Sep 2023 | MH5-2 |  | 11th layer BRC installation on going
Mon (25/09) | 25 Sep 2023 | ST93 |  | Casting completed
Mon (25/09) | 25 Sep 2023 | ST141 |  | Bentonite hose connection to BC cutter prior to trenching
Mon (25/09) | 25 Sep 2023 | MH2-1 |  | No activity
Mon (25/09) | 25 Sep 2023 | Zone 3 ST223 |  | Manual trial trench in progress
Mon (25/09) | 25 Sep 2023 | P25 |  | SPPG and Singtel pipe laying (4m each)
Mon (25/09) | 25 Sep 2023 | MH5-2 |  | 11th layer BRC installation completed. LCH stop work for the night. Dayshift to install moulding and do casting
Mon (25/09) | 25 Sep 2023 | MH2-4 |  | Continue 9th layer excavation
Mon (25/09) | 25 Sep 2023 | MH5-2 |  | 11th ring casting in progress
Mon (25/09) | 25 Sep 2023 | North ramp N6 |  | Waler beam welding in progress. Works till 7pm
Mon (25/09) | 25 Sep 2023 | North ramp N5 |  | Preboring done for the day
Mon (25/09) | 25 Sep 2023 | North ramp N2 |  | Rectification ongoing as per QPS team comments. Works till 8:30pm
Mon (25/09) | 25 Sep 2023 | ST141 |  | 1st bite trenching on going
Mon (25/09) | 25 Sep 2023 | MH2-5 |  | Hacking ongoing for the entry point. Works till 8pm
Mon (25/09) | 25 Sep 2023 | Zone 3 P7 |  | 2m dia casing installation in progress
Mon (25/09) | 25 Sep 2023 | ST141 |  | First bite excavation in progress, 33.8m
Mon (25/09) | 25 Sep 2023 | Zone 3 MH2-8 location |  | Singtel and SPPG pipe laid, 4m. Tonighg singtel haunching to cast
Mon (25/09) | 25 Sep 2023 | MH2-4 |  | Excavation for 9th layer. Reached 1.2m. Trimming on going. Tonight to complete excavation till 10pm. Tomorrow to install rebar, mould and casting
Mon (25/09) | 25 Sep 2023 | MH5-1 |  | 15thnlayer half rebar installation on going. Rebar Inspection around 930-10pm prior to formwork installation. Tonight to cast est 12mn
Tue (26/09) | 26 Sep 2023 | Zone 3 loyang way opp lincstech |  | Excavation for singtel pipe laying. Tonight target 18m
Tue (26/09) | 26 Sep 2023 | Zone 3 loyang way opp sapphire windows building |  | M1 pipe laying here. Target tonight 25m
Tue (26/09) | 26 Sep 2023 | Zone 3 loyang way opp krislite building |  | Lucky joint here for sptel pipe laying, 25m target tonight
Tue (26/09) | 26 Sep 2023 | Zone 1 LA | towards TPE | Lane closure by Krishco. Plan for cctv inspection this afternoon
Tue (26/09) | 26 Sep 2023 | LA towards PRD3 |  | DE143 works
Tue (26/09) | 26 Sep 2023 | Exit 2 |  | Slope area lean concrete casting
Tue (26/09) | 26 Sep 2023 | Zone 1 junction |  | Traffic shutdown. APOs deployed at respective locations
Tue (26/09) | 26 Sep 2023 | MH5-1 |  | Half 15th layer casting completed
Tue (26/09) | 26 Sep 2023 | ST224 |  | Manual TT in progress
Tue (26/09) | 26 Sep 2023 | MH2-1 |  | 2nd layer excavation for caisson
Tue (26/09) | 26 Sep 2023 | MH2-4 |  | Steel mould lowering and installation works ongoing for 9th layer
Tue (26/09) | 26 Sep 2023 | N6 |  | Stiffening plate welding works for waler beam in progress
Tue (26/09) | 26 Sep 2023 | BP7 |  | Continue 2m dia casing installation and balance soil removal by grabber
Tue (26/09) | 26 Sep 2023 | P34 |  | Starhub pipe laying, 18m
Tue (26/09) | 26 Sep 2023 | Zone 3 BH69 |  | In progress, 28.5m
Tue (26/09) | 26 Sep 2023 | N5 |  | Continue pre boring works for soldier piles and lagging plate
Tue (26/09) | 26 Sep 2023 | PMH8 |  | Lean concrete for SPPG upcoming works
Tue (26/09) | 26 Sep 2023 | ST141 |  | Trenching continue at 37.8m
Tue (26/09) | 26 Sep 2023 | N2 Pile cap |  | Rebar and formwork still in progress
Tue (26/09) | 26 Sep 2023 | N3 |  | KTC excavation to FEL in progress
Tue (26/09) | 26 Sep 2023 | Zone 3 BH114 |  | In progress, 21m
Tue (26/09) | 26 Sep 2023 | Zone 4 loyang way |  | 1st TT for the night completed
Tue (26/09) | 26 Sep 2023 | Zone 4 loyang way |  | 2nd TT for the night completed
Tue (26/09) | 26 Sep 2023 | Zone 3 |  | Pumping main pipes installation in progress. At current, 16nos installed and progressively installing the footing formwork
Tue (26/09) | 26 Sep 2023 | Zone 1 |  | Krishco reinstatement works ongoing. CCTV inspection rejected. Krishco to rectify all problems highlighted by PUB RTO and arrange for CCTV inspection again
Tue (26/09) | 26 Sep 2023 | MH5-2 |  | Yst cast 11th layer, curing ongoing. Later the team will remove the Formwork
Tue (26/09) | 26 Sep 2023 | MH5-1 |  | No activity, curing works. Casting was done last night
Tue (26/09) | 26 Sep 2023 | ST92/93 |  | Current status of guidewall hacking. Now stopped
Tue (26/09) | 26 Sep 2023 | Loyang way team 2 pipe laying |  | 7.5m pipe laid here. Backfilling on going
Tue (26/09) | 26 Sep 2023 | BH159 |  | SI drilling in progress, depth 34m
Tue (26/09) | 26 Sep 2023 | Zone 2 |  | Access making by KTC to PMH11&12 for SPPG lorry crane
Tue (26/09) | 26 Sep 2023 | Near Dw15/16 |  | Shoring for next 4m pipe laying ongoing. To complete pipe laying by tonight
Tue (26/09) | 26 Sep 2023 | Zone 3 |  | BP7 casing still onsite. To send out around 5.30pm
Tue (26/09) | 26 Sep 2023 | ST141 |  | 1st bite completed. Internal Koden test by DG
Tue (26/09) | 26 Sep 2023 | MH2-5 |  | Jacking machine setting up till 10pm. Hopefully to start jacking to 2-6 tomorrow
Tue (26/09) | 26 Sep 2023 | MH5-2 |  | Tonight 11th layer moulding removal and excavation for 12th layer
Tue (26/09) | 26 Sep 2023 | Zone 3 Taiyo Asia pile removal |  | BP 7 boring and grabbing on going, 7.1m/9m. They will work until 10pm
Tue (26/09) | 26 Sep 2023 | ST141 |  | 2nd bite excavation on going. Depth bow at 22m
Tue (26/09) | 26 Sep 2023 | MH2-1 |  | 1st layer formwork removal
Tue (26/09) | 26 Sep 2023 | Zone 1 |  | Now preparing to relocate SPPG OG box. Existing cable to be cut and new cable to be connected to relocated box. Cisco otw
Tue (26/09) | 26 Sep 2023 | Zone 3/4 junction |  | Cap off for gas pipe continue
Tue (26/09) | 26 Sep 2023 | Zone 1 |  | 4 APOs on site
Wed (27/09) | 27 Sep 2023 | Zone 3/4 |  | Depcie working at junction for singtel pipe laying
Wed (27/09) | 27 Sep 2023 | Next to Gate 5 access |  | SPPG & Singtel pipes laid, 4m respectively. Dayshift preparing to cast concrete haunching & backfilling
Wed (27/09) | 27 Sep 2023 | P25 |  | BH159 in progress, 42m
Wed (27/09) | 27 Sep 2023 | Zone 3 loyang way |  | M1 pipe laying on going. Tonight to connect to existing manhole,10m
Wed (27/09) | 27 Sep 2023 | MH5-2 |  | Excavation on going
Wed (27/09) | 27 Sep 2023 | Zone 3 loyang way |  | Singtel pipe laying on going
Wed (27/09) | 27 Sep 2023 | Zone 3/4 junction |  | Power gas cap off completed. Area backfilled, waiting for premix
Wed (27/09) | 27 Sep 2023 | PMH12 |  | KTC access making for SPPG works
Wed (27/09) | 27 Sep 2023 | MH2-5 |  | Preparation to lower pipe for pipe jacking works
Wed (27/09) | 27 Sep 2023 | N5 |  | Continue preboring works for soldier pile & lagging plate
Wed (27/09) | 27 Sep 2023 | ST141 |  | BC cutter teeth maintenance
Wed (27/09) | 27 Sep 2023 | N2 |  | Pile cap casting in progress
Wed (27/09) | 27 Sep 2023 | N3 |  | Excavation works to FEL in progress
Wed (27/09) | 27 Sep 2023 | BP7 |  | Taiyo continue casing installation & soil removal. New grabber already on site & PE will be coming down this evening ard 6pm for inspection
Wed (27/09) | 27 Sep 2023 | ST92/93 area |  | WG setting out alignment for SPPG pipe laying
Wed (27/09) | 27 Sep 2023 | ST141 |  | 2nd bite excavation in progress, 35.8m
Wed (27/09) | 27 Sep 2023 | BH69 |  | Depth terminated at 39.5m
Wed (27/09) | 27 Sep 2023 | Zone 3/4 junction |  | Pgas work completed
Wed (27/09) | 27 Sep 2023 | Zone 1 |  | Krishco doing backfilling and reinstatement works
Wed (27/09) | 27 Sep 2023 | Near PMH3 |  | 12m of SPPG pipe laid
Wed (27/09) | 27 Sep 2023 | BH159 |  | SI drilling in progress, depth 45m
Wed (27/09) | 27 Sep 2023 | MH5-2 |  | 12th layer excavation work continue, eat depth 400-500mm depth
Wed (27/09) | 27 Sep 2023 | ST141 |  | 2nd bite trenching continue
Wed (27/09) | 27 Sep 2023 | MH2-7 |  | Jacking to 2-6, 2nd pipe on going. This team to work until 10pm
Wed (27/09) | 27 Sep 2023 | N2 pile cap |  | Casting and levelling completed. CGW left the site
Wed (27/09) | 27 Sep 2023 | MH5-2 |  | Night shift team here, to continue excavation for 12th layer
Wed (27/09) | 27 Sep 2023 | Exit 2 |  | DW55 status. Pipe joing is still in progress, est to resume trenching in 1 hr time
Wed (27/09) | 27 Sep 2023 | ST141 |  | 2nd bite continue trenching, depth at 37.2m
Wed (27/09) | 27 Sep 2023 | BH06 |  | Current depth at 33.4m. Packer test in progress
Thu (28/09) | 28 Sep 2023 | DW55 |  | Excavation reached 24m. Replacing of mud pump
Thu (28/09) | 28 Sep 2023 | JTC area blk 2 |  | Exposing 22KV for cable spiking
Thu (28/09) | 28 Sep 2023 | Zone 3 |  | Chisel inspection by RTO done. Below are the following comments
Thu (28/09) | 28 Sep 2023 | MH2-1 |  | Another valve found out during excavation of 3rd layer, now they are exposing the valve to check the alignment
Thu (28/09) | 28 Sep 2023 | ST141 |  | 2nd bite trenching continue
Thu (28/09) | 28 Sep 2023 | Zone 3/4 junction |  | Singtel pipe laid 9m. Casting on going
Thu (28/09) | 28 Sep 2023 | MH2-8 |  | RG drilling works ongoing for inclinometer
Thu (28/09) | 28 Sep 2023 | MH2-8 |  | LCH unloading of materials
Thu (28/09) | 28 Sep 2023 | DW55 |  | Trenching on going
Thu (28/09) | 28 Sep 2023 | BH159 |  | SI work completed, termination depth 49.5m. The rig will shift to BH150 next
Thu (28/09) | 28 Sep 2023 | Zone 4 Loyang Ave |  | No activity
Thu (28/09) | 28 Sep 2023 | Zone 3 P39 |  | 7m SPPG laid yesterday, and starhub laid today
Thu (28/09) | 28 Sep 2023 | N6 |  | Current status for ERSS waler and strut works
Thu (28/09) | 28 Sep 2023 | N5 |  | Continue pre boring and installation works for soldier pile and lagging plate
Thu (28/09) | 28 Sep 2023 | N3 |  | KTC Continue excavation to FEL. Target to complete by today
Thu (28/09) | 28 Sep 2023 | N2 |  | No activity. Curing works for pile cap
Thu (28/09) | 28 Sep 2023 | DR2 |  | MPI test for sheetpile
Thu (28/09) | 28 Sep 2023 | Taiyo BP7 |  | Continue casing installation (7.6m ongoing) and clearing soil. Pending PE cert for the new grabber
Thu (28/09) | 28 Sep 2023 | Zone 1 |  | Krishco split tee pipe installation ongoing
Thu (28/09) | 28 Sep 2023 | LVC blk 222 |  | Noise reading reached during trenching of DW55
Thu (28/09) | 28 Sep 2023 | BH06 |  | Depth terminated at 42m
Thu (28/09) | 28 Sep 2023 | Zone 1 |  | Krishco preparing to connect the water pipe
Thu (28/09) | 28 Sep 2023 | Zone 3/4 junction |  | Work completed
Thu (28/09) | 28 Sep 2023 | ST141 |  | Trenching continue at 39m depth
Thu (28/09) | 28 Sep 2023 | MH5-2 |  | 12th layer excavation continue. Estimated depth 1-1.1m
Thu (28/09) | 28 Sep 2023 | Hi sir,Tomorrow 11 |  | 30-1200 CCTV zone1
Thu (28/09) | 28 Sep 2023 | MH2-4 |  | Continue hacking & excavation for 10th layer
Thu (28/09) | 28 Sep 2023 | MH5-2 |  | 12th ring trimming in progress. To continue casting tonight
Thu (28/09) | 28 Sep 2023 | MH5-1 |  | Pumping out water
Thu (28/09) | 28 Sep 2023 | North ramp N5 |  | Activity done for the day
Thu (28/09) | 28 Sep 2023 | North ramp N6 |  | Strut welding ongoing. Team working till 7pm
Thu (28/09) | 28 Sep 2023 | N3 |  | Continue excavation. Team working till ard 8pm
Thu (28/09) | 28 Sep 2023 | MH2-5 |  | Pipe jacking in progress, 7/26nos
Thu (28/09) | 28 Sep 2023 | Exit 2 DW55 |  | Mud pump replacement. First bite current depth at 24m
Thu (28/09) | 28 Sep 2023 | 100mm dia water pipe link up work |  | Excavation done. Will start link up work at 10PM
Thu (28/09) | 28 Sep 2023 | MH2-5 to MH2-6 |  | Pipe no 9 jacking in progress
Thu (28/09) | 28 Sep 2023 | MH2-4 |  | Excavation for 10th layer caisson in progress. Tomorrow to cast. This team working until 10PM
Thu (28/09) | 28 Sep 2023 | MH5-2 |  | Rebar work in progress. Outer done, inner in progress. Casting of 12th layer will be after mid night
Thu (28/09) | 28 Sep 2023 | DE143/ CR106 Zone 4 |  | Lane markings done except for the 2 ends
Thu (28/09) | 28 Sep 2023 | MH2-8 |  | Preparation for drilling for inclinometer amd waterstand pipe
Fri (29/09) | 29 Sep 2023 | DR2 |  | Waler welding in progress
Fri (29/09) | 29 Sep 2023 | CCE ST143 |  | Pre-excavation
Fri (29/09) | 29 Sep 2023 | ST141 |  | Final koden check ongoing
Fri (29/09) | 29 Sep 2023 | P22-P23 |  | Mo guan here for starhub pipe laying. Today target 18m
Fri (29/09) | 29 Sep 2023 | Zone 3 BH70 |  | Drilling & SPT in progress
Fri (29/09) | 29 Sep 2023 | Zone 3 BH63 |  | Today plan to start drilling. BH64: Preparing to start hand auger
Fri (29/09) | 29 Sep 2023 | N5 |  | Pre boring works for SP. Today target 3 nos 12m pre boring for SP
Fri (29/09) | 29 Sep 2023 | N6 |  | All strut installed. Welding works on going
Fri (29/09) | 29 Sep 2023 | Loyang Way near Exit 1 |  | No activity
Fri (29/09) | 29 Sep 2023 | BH64 |  | Hand auger ongoing
Fri (29/09) | 29 Sep 2023 | Zone 1 |  | Krishco fixing of pipe fittings in progress
Fri (29/09) | 29 Sep 2023 | Zone 3 BH09 |  | Hand auger ongoing
Fri (29/09) | 29 Sep 2023 | MH5-1 |  | Manual excavation to expose existing sewer pipe. Today protection installation to start
Fri (29/09) | 29 Sep 2023 | Zone 1 |  | Krishco flushing works in progress before CCTV inspection
Fri (29/09) | 29 Sep 2023 | MH2-9 |  | Footpath removal for sewer shaft work
Fri (29/09) | 29 Sep 2023 | Zone 1 |  | SPPG pipe laying ongoing, to lay 12m today. (1-way)
Fri (29/09) | 29 Sep 2023 | MH5-2 |  | Formwork closing in progress
Fri (29/09) | 29 Sep 2023 | N5 |  | Pre boring for SP and llaging plate continue. 2 nos 12m and 3 nos 6m completed as of the moment
Fri (29/09) | 29 Sep 2023 | N3 |  | Pile head cutting for hacking works to COL
Fri (29/09) | 29 Sep 2023 | MH2-1 |  | No activity
Fri (29/09) | 29 Sep 2023 | MH1-3 |  | Top slab rebar works ongoing
Fri (29/09) | 29 Sep 2023 | MH5-1 |  | Exposing existing sewer using handheld breaker continue
Fri (29/09) | 29 Sep 2023 | ST141 |  | Rebar cage installation in progress
Fri (29/09) | 29 Sep 2023 | Zone 3 BH115 |  | Hand auger just completed. To start drilling now
Fri (29/09) | 29 Sep 2023 | BH09 |  | Drilling & SPT in progress
Fri (29/09) | 29 Sep 2023 | MH2-4 |  | 10th ring casting completed
Fri (29/09) | 29 Sep 2023 | MH5-1 |  | Continue exposing existing sewer
Fri (29/09) | 29 Sep 2023 | MH5-2 |  | No activity
Fri (29/09) | 29 Sep 2023 | North ramp N6 |  | Continue welding for diagonal struts
Fri (29/09) | 29 Sep 2023 | N5 |  | Preboring done for the day
Fri (29/09) | 29 Sep 2023 | N3 |  | Pile head cutting done for the day. WH rectifying the access location
Fri (29/09) | 29 Sep 2023 | N2 |  | No activity
Fri (29/09) | 29 Sep 2023 | MH2-5 |  | Preparing to hoist down pipe no.15
Fri (29/09) | 29 Sep 2023 | Taiyo BP7 |  | No more activity for the day
Fri (29/09) | 29 Sep 2023 | Exit 2 DW55 |  | LSS backfilling completed. Total vol: 98m3
Fri (29/09) | 29 Sep 2023 | ST141 |  | Cage 2B and 3B lapping
Fri (29/09) | 29 Sep 2023 | MH5-1 |  | Manual excavation for caisson shaft casting. This team working until 10PM
Fri (29/09) | 29 Sep 2023 | MH5-2 |  | Still curing
Sat (30/09) | 30 Sep 2023 | MH5-1 |  | Manual excavation for 15th ring 2nd layer
Sat (30/09) | 30 Sep 2023 | MH5-2 |  | Moulding dismantling for 12th layer
Sat (30/09) | 30 Sep 2023 | Zone 1 |  | WH to do TT to find traffic lights cables
Sat (30/09) | 30 Sep 2023 | Zone 4 |  | DE143 M&P and road markings for the upcoming road diversion tonight
Sat (30/09) | 30 Sep 2023 | Zone 3/4 junction |  | Shifting traffic light
Sat (30/09) | 30 Sep 2023 | ST143 |  | 1st bite excavation at 24m depth
Sat (30/09) | 30 Sep 2023 | DR2 |  | Joint plate welding on going 18/21 completed. Today to complete
Sat (30/09) | 30 Sep 2023 | DR2 |  | Today also to install brackets for waler at the sheetpile area (inclined part), 4 nos
Sat (30/09) | 30 Sep 2023 | Zone 3 |  | BH115, drilling started
Sat (30/09) | 30 Sep 2023 | Zone 3 P33-34 |  | Lean concrete on going for pumping main twin pipe installation, 40m
Sat (30/09) | 30 Sep 2023 | Zone 3 blk 2 |  | SPPG contractor here retrieving abandoned cables
Sat (30/09) | 30 Sep 2023 | Zone 3 |  | Taiyo Asia, today to replace crane wire rope and continue boring and grabbing for BP7, balance 2m
Sat (30/09) | 30 Sep 2023 | Zone 3 |  | Pump sump access hatch frame welding on going. Today 130pm final inspection and cast by 2 or 3 pm
Sat (30/09) | 30 Sep 2023 | MH2-1 |  | Water pipe confirmed to be live
Sat (30/09) | 30 Sep 2023 | N6 |  | Strut welding continue
Sat (30/09) | 30 Sep 2023 | Zone 2 |  | Starhub pipe laying, 12m
Sat (30/09) | 30 Sep 2023 | Zone 3 sump pump |  | Inspection done. Minor comment from RTO, formwork inspection checklist to be signed by formwork supervisor. Good to go for casting
Sat (30/09) | 30 Sep 2023 | DR2 |  | Now raining, work temporary stopped
Sat (30/09) | 30 Sep 2023 | BH115 |  | Drilling now at 18m depth
Sat (30/09) | 30 Sep 2023 | ST143 |  | 1st bite excavation and internal koden test completed. Now cutter wheel teeth changing and start 2nd bite
Sat (30/09) | 30 Sep 2023 | BH54 |  | Hand augering
Sat (30/09) | 30 Sep 2023 | Zone 4 |  | Busy junction now due to upcoming diversion
Sat (30/09) | 30 Sep 2023 | MH2-8 |  | 1st layer steel caisson installed
Sat (30/09) | 30 Sep 2023 | MH5-1 |  | Formwork closing on going for 15th layer (600mm). Target to cast around 10PM
Sat (30/09) | 30 Sep 2023 | MH5-1 |  | Excavation in progress for 13th layer caisson
Sat (30/09) | 30 Sep 2023 | MH2-5 |  | 17/26 jacking to 2-6. Yesterday completed 16 pipes
Sat (30/09) | 30 Sep 2023 | MH2-4 |  | 11th layer curing
Sat (30/09) | 30 Sep 2023 | N5 pre boring works |  | Today target to complete all SP and LP pre boring, complete also SP installation. Tomorrow to complete lagging plate (LP) driving
Sat (30/09) | 30 Sep 2023 | N6 |  | Strut welding and stiffiner continue. Plan to complete all strut joints welding today. Balance will be stiffiners
Sat (30/09) | 30 Sep 2023 | N3 |  | Pile head hacking. Target to complete tomorrow
Sun (01/10) | 01 Oct 2023 | MH2-3 |  | Pipe jacking setting up works
Sun (01/10) | 01 Oct 2023 | N6 |  | Welding of stiffening plate in progress. MPI test to arrange on Monday
Sun (01/10) | 01 Oct 2023 | N5 |  | Installation of soldier pile & lagging plate in progress
Sun (01/10) | 01 Oct 2023 | N3 |  | Access installation ongoing
Sun (01/10) | 01 Oct 2023 | N2 |  | No activity
Sun (01/10) | 01 Oct 2023 | Zone 1 |  | No activity
Sun (01/10) | 01 Oct 2023 | MH5-2 |  | Excavation for 13th layer in progress
Sun (01/10) | 01 Oct 2023 | MH5-1 |  | No activity
Sun (01/10) | 01 Oct 2023 | Exit 2 |  | No activity
Sun (01/10) | 01 Oct 2023 | Exit 1 |  | KTC slope trimming and leveling in progress
Sun (01/10) | 01 Oct 2023 | ST-143 |  | Cutter Gear box seal damaged, now preparing for gear box changing
Sun (01/10) | 01 Oct 2023 | Zone 4 |  | DE143 working within the closed road area and Eng hup finishing up their balance traffic lane works
Sun (01/10) | 01 Oct 2023 | MH5-2 |  | Continue excavation for cassion shaft work
Sun (01/10) | 01 Oct 2023 | Beside MH2-6 |  | Starhub pipe laying completed 12m. Backfilling works in progress
Sun (01/10) | 01 Oct 2023 | MH5-2 |  | Continue Excavation for 13th layer
Sun (01/10) | 01 Oct 2023 | N3 |  | No activity. Tmr to continue with manual pile hacking
Sun (01/10) | 01 Oct 2023 | N5 |  | Installation of solider pile & lagging plate completed. Leveling works in progress now
Sun (01/10) | 01 Oct 2023 | N6 |  | Continue of stiffening plate welding works. Target to MPI test and concrete packing tmr
Sun (01/10) | 01 Oct 2023 | SC40 |  | New gear box installation to cutter wheel in progress. Currently, no activity for ST143
Sun (01/10) | 01 Oct 2023 | Zone 4 |  | Current traffic status
Sun (01/10) | 01 Oct 2023 | Beside MH2-6 |  | Starhub contractor excavation in progress for pipe laying works. Target to lay 12m
Mon (02/10) | 02 Oct 2023 | Zone 2 P23-P24 |  | Starhub pipe laid, 12m. Backfilling on going
Mon (02/10) | 02 Oct 2023 | Zone 2 P22-P23 |  | M1 pipe laying, 12m
Mon (02/10) | 02 Oct 2023 | MH2-7 |  | Pipe jacking reached MH2-6. Now hacking to retrieve machine
Mon (02/10) | 02 Oct 2023 | MH2-4 |  | Excavation for 11th layer
Mon (02/10) | 02 Oct 2023 | MH2-3 |  | Unloading of pipe jacking materials
Mon (02/10) | 02 Oct 2023 | N3 |  | Continue pile hacking works
Mon (02/10) | 02 Oct 2023 | N6 |  | Welding completed. Waiting for MPI. Today also to cast packing concrete
Mon (02/10) | 02 Oct 2023 | MH5-1 |  | Manual excavation for 16th layer
Mon (02/10) | 02 Oct 2023 | MH2-4 |  | Excavation for caisson to 11th layer. This team working until 10PM tonight
Mon (02/10) | 02 Oct 2023 | MH5-1 |  | Manual excavation and soil clearing for 16th layer caisson
Mon (02/10) | 02 Oct 2023 | MH5-2 |  | Excavation for 13th layer caisson
Mon (02/10) | 02 Oct 2023 | MH2-4 |  | Continue hacking & excavation 11th layer. Tmr plan for casting
Mon (02/10) | 02 Oct 2023 | MH5-2 |  | Night shift team to take over excavation for 13th layer. Dayshift team ended already
Mon (02/10) | 02 Oct 2023 | MH5-1 |  | Hacking for 16th layer
Mon (02/10) | 02 Oct 2023 | Zone 3 P27/28 area |  | Tonight plan for Singtel pipe laying
Mon (02/10) | 02 Oct 2023 | Exit 2 DW55 |  | First bite current depth at 20.4m. Now temporarily stopped due to high temp of hydraulic oil
Mon (02/10) | 02 Oct 2023 | ST143 |  | First bite excavation in progress. Current depth ard 26.2m
Mon (02/10) | 02 Oct 2023 | Loyang Way towards CV, LP72 |  | M1 works
Tue (03/10) | 03 Oct 2023 | MH5-1 |  | Excavation for 16th layer continue, est depth 600mm
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | 13th laywr casting
Tue (03/10) | 03 Oct 2023 | Zone 1 |  | Depcie team here for singtel pipe laying for J-eye camera. From existing manhole to new traffic light box at NLL
Tue (03/10) | 03 Oct 2023 | P27/28 area |  | Singtel pipes laid, 1.7m
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | 13th layer excavation in progress
Tue (03/10) | 03 Oct 2023 | P27/28 area |  | Another manual excavation for Singtel pipe laying
Tue (03/10) | 03 Oct 2023 | DW55 |  | Internal koden check. BC cutter machine still ongoing rectification
Tue (03/10) | 03 Oct 2023 | Zone 3 |  | P39-40 subsoil drain drilling in progress
Tue (03/10) | 03 Oct 2023 | Zone 3 |  | ST143 at 26.7m depth. Cutter teeth changing ongoing
Tue (03/10) | 03 Oct 2023 | Along MH2-5 & MH2-6 |  | Lucky joint & Mo guan contractors laying starhub and m1 pipes
Tue (03/10) | 03 Oct 2023 | N3 |  | KTC leveling works in progress. The mini excavator will be shift to N6 today
Tue (03/10) | 03 Oct 2023 | Zone 1 |  | 1-way Singtel Pipe laying in progress, today to lay 40m
Tue (03/10) | 03 Oct 2023 | MH5-1 |  | Manual excavation for 16th layer
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | 13th layer casting completed in the afternoon
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | 13th ring rebar installation completed. Pending inspection
Tue (03/10) | 03 Oct 2023 | DW55 |  | Cutter wheel teeth changing on going
Tue (03/10) | 03 Oct 2023 | Zone 3 DR2 |  | L-angle at inclined waler 2/2 welding completed. Now LE housekeeping, work till 7pm
Tue (03/10) | 03 Oct 2023 | ST143 |  | Cutter wheel teeth changing on going
Tue (03/10) | 03 Oct 2023 | Zone 2 P22-23 |  | M1 pipe laying 29m completed today. Backfilling works on gking
Tue (03/10) | 03 Oct 2023 | MH2-4 |  | 11th ring casting completed
Tue (03/10) | 03 Oct 2023 | N6 |  | Excavator shifted for excavation to FEL
Tue (03/10) | 03 Oct 2023 | N3 |  | Lean concrete just started
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | No activity, 13th layer curing
Tue (03/10) | 03 Oct 2023 | MH5-1 |  | 16th layer trimming. Work till 9pm
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | 13th ring formwork completed. Dayshift will take over for casting
Tue (03/10) | 03 Oct 2023 | MH5-2 |  | No activity
Tue (03/10) | 03 Oct 2023 | MH5-1 |  | Works done for the day. Housekeeping now. Tonight there’s no night team for LCH
Tue (03/10) | 03 Oct 2023 | N3 |  | Lean con completed. Levelling ongoing
Tue (03/10) | 03 Oct 2023 | P28 |  | Tonight to raise up Singtel MX2
Tue (03/10) | 03 Oct 2023 | DR2 |  | Works done for the day
Tue (03/10) | 03 Oct 2023 | ST143 |  | First bite excavation in progress, depth ard 26.75m
Tue (03/10) | 03 Oct 2023 | MH2-6 |  | Sewer pipe break trough, boring machine retrieved
Tue (03/10) | 03 Oct 2023 | MH2-5 |  | Today plan to take out slurry pipes and cables, tomorrow plan for water tightness test
Tue (03/10) | 03 Oct 2023 | MH2-4 |  | 11th layer trimming, today to cast around 5pm
Tue (03/10) | 03 Oct 2023 | Exit 2 DW55 |  | First bite completed, 25.2m. Now ongoing 2nd bite. Temporarily stopped to check for the hydraulic hose
Tue (03/10) | 03 Oct 2023 | N6 |  | Concrete packing cast yesterday. Curin
Tue (03/10) | 03 Oct 2023 | N3 |  | Pile head manual hacking to COL. Today plan to lean con
Wed (04/10) | 04 Oct 2023 | BP1 |  | Casing installation in progress, 7.8/9m
Wed (04/10) | 04 Oct 2023 | MH5-2 |  | Continue hacking and excavation for 14th layer
Wed (04/10) | 04 Oct 2023 | MH5-1 |  | 16th ring BRC inspected. Steel mould installation in progress
Wed (04/10) | 04 Oct 2023 | DW55 |  | Hanging bar u-clip inspection done with RTO
Wed (04/10) | 04 Oct 2023 | P22-24 |  | Starhub and M1 completed pipe laying works here, now they shifting materials and continue pipe laying at zone 3
Wed (04/10) | 04 Oct 2023 | N6 |  | Tonight to get result of packing concrete cube test result. If reach 10mpa csn proceed with the excavation
Wed (04/10) | 04 Oct 2023 | P28 |  | Works completed
Wed (04/10) | 04 Oct 2023 | N3 |  | Cutting of excess spiral links at pile head. Surveyor marking for pile cap setting out done
Wed (04/10) | 04 Oct 2023 | P26 area |  | Open pit for mandrel test preparation (SPPG)
Wed (04/10) | 04 Oct 2023 | DW55 |  | 2nd bite current depth at 25.2m. Internal koden check ongoing
Wed (04/10) | 04 Oct 2023 | ST143 |  | Replacing damaged bolts for flange
Wed (04/10) | 04 Oct 2023 | Zone 1 NLL |  | EL working here to hacking pedestrian access lamp post
Wed (04/10) | 04 Oct 2023 | DW55 |  | Torque test done for rebar cage u-clips. Bottom cages are ok to proceed. Rechecking to be done for the middle & top cages
Wed (04/10) | 04 Oct 2023 | P26 |  | Shoring works completed for SPPG open pit mandrel test
Wed (04/10) | 04 Oct 2023 | Zone 1 |  | Excavation for traffic light cable shifting to new Control box
Wed (04/10) | 04 Oct 2023 | P23 |  | Water pipe 300mm diameter delivery, 15 nos on site. Tonight to start Installation of pipe bracket. Laying to start tomorrow
Wed (04/10) | 04 Oct 2023 | MH2-5 |  | Jacking frame support dismantling on going. Plan to complete tonight and reorient jacking frame to 2-4 tomorrow
Wed (04/10) | 04 Oct 2023 | MH5-1 |  | Final trimming on going
Wed (04/10) | 04 Oct 2023 | MH5-2 |  | Night shift team to dismantle mould for 13th layer and proceed excavation for 14th layer
Wed (04/10) | 04 Oct 2023 | DW55 |  | Hanging bar torque test inspection for u-clip
Wed (04/10) | 04 Oct 2023 | DW55 |  | Rebar cage 2B installation
Wed (04/10) | 04 Oct 2023 | Zone 3 |  | Rebar installation for ECM cable pipe haunching crossing machinery access. Tonight to cast
Wed (04/10) | 04 Oct 2023 | ST143 |  | 1st bite current depth at 27m
Wed (04/10) | 04 Oct 2023 | MH5-1 |  | 16th ring BRC ongoing. To cast tonight
Wed (04/10) | 04 Oct 2023 | MH5-2 |  | Night shift team to continue excavation for 14th layer
Wed (04/10) | 04 Oct 2023 | BP1 |  | Night shift team already here. 1.2m dia casing installation in progress
Wed (04/10) | 04 Oct 2023 | DW55 |  | Rebar cage 2A & 3A lapping and inspection
Wed (04/10) | 04 Oct 2023 | ST143 |  | Continue first bite excavation. Current depth at 27.15m
Wed (04/10) | 04 Oct 2023 | P27 |  | Excavation for mandrel test pit (SPPG)
Thu (05/10) | 05 Oct 2023 | ST143 |  | Cutter wheel teeth replacement. Current depth 27.7m
Thu (05/10) | 05 Oct 2023 | Zone 3 loyang way opp SiTa building |  | Singtel term contractor here for pipe jamming works
Thu (05/10) | 05 Oct 2023 | Zone 3 loyang way LP 67 |  | Lucky joint here for M1 pipe laying. Tonighg target 28m
Thu (05/10) | 05 Oct 2023 | MH5-1 |  | 16th ring casting in progress
Thu (05/10) | 05 Oct 2023 | MH5-1 |  | Casting completed
Thu (05/10) | 05 Oct 2023 | BP1 |  | Continue casing installation
Thu (05/10) | 05 Oct 2023 | DW55 |  | Casting in progress
Thu (05/10) | 05 Oct 2023 | MH2-3 |  | Set up jacking frame. Tomorrow plan for thrust block casting
Thu (05/10) | 05 Oct 2023 | MH2-5 |  | Concrete on the way for thrust block casting
Thu (05/10) | 05 Oct 2023 | MH2-4 |  | Excavation in progress. Today this team working until 10PM. Tomorrow to cast
Thu (05/10) | 05 Oct 2023 | MH5-2 |  | Continue excavation for caisson shaft, around 400mm as of now
Thu (05/10) | 05 Oct 2023 | MH2-4 |  | Hacking for 12th layer till 10pm, est depth 1-1.1m
Thu (05/10) | 05 Oct 2023 | Z4 |  | Mob in of barricades for SI works. Tmrw to start trial trench
Thu (05/10) | 05 Oct 2023 | MH5-2 |  | Tonight to continue excavation work for 14th layer. Current depth at 300mm. Target tonight to excavate till 800-1000mm
Fri (06/10) | 06 Oct 2023 | Zone 3 BH64 |  | Preparing to start SI
Fri (06/10) | 06 Oct 2023 | Fyi at zone 3 |  | Bund wall surrounding the perimeter hoarding has been constructed
Fri (06/10) | 06 Oct 2023 | DW56 |  | Trenching on going, current depth 13m
Fri (06/10) | 06 Oct 2023 | ST143 |  | Cutter wheel teeth replacement and nose clamp welding
Fri (06/10) | 06 Oct 2023 | ST143 |  | Continue excavation
Fri (06/10) | 06 Oct 2023 | DR2 |  | Plan for strut installation. Mobile crane on site
Fri (06/10) | 06 Oct 2023 | MH2-1 |  | No activity
Fri (06/10) | 06 Oct 2023 | ST143 |  | 1st bite excavation continue
Fri (06/10) | 06 Oct 2023 | Zone 3 P38-39 |  | Excavation for SPPG pipe laying, 12m
Fri (06/10) | 06 Oct 2023 | P24-25 |  | Singtel & Starhub pipes laid (6m respectively). Now continue excavation for Starhub
Fri (06/10) | 06 Oct 2023 | BP1 |  | Outer casing installation in progress, 3m length. Already installed 3+3.7m
Fri (06/10) | 06 Oct 2023 | ST143 |  | First bite excavation in progress, 27.9m
Fri (06/10) | 06 Oct 2023 | ABH110 |  | Continue manual TT
Fri (06/10) | 06 Oct 2023 | Zone 4 ABH111 |  | Manual trial trench in progress
Fri (06/10) | 06 Oct 2023 | Zone 4 |  | Unloading of concrete barriers
Fri (06/10) | 06 Oct 2023 | DR2 |  | 1nos strut installed. Today plan 3nos
Fri (06/10) | 06 Oct 2023 | Zone 3 loyang way |  | M1 pipe laying completed. Lane opened
Fri (06/10) | 06 Oct 2023 | ST143 |  | Cutter wheel teeth changing again
Fri (06/10) | 06 Oct 2023 | MH5-2 |  | Excavation for 14th layer to continue till 630 am
Fri (06/10) | 06 Oct 2023 | DR2 |  | 3nos struts installed
Fri (06/10) | 06 Oct 2023 | ST143 |  | BC cutter hoist up for cutter teeth wheel replacement
Fri (06/10) | 06 Oct 2023 | Exit 2 DW56 |  | First bite excavation started
Fri (06/10) | 06 Oct 2023 | MH5-1 |  | Hacking & excavation for base slab works
Fri (06/10) | 06 Oct 2023 | N3 |  | No activity
Fri (06/10) | 06 Oct 2023 | N2 |  | No activity
Fri (06/10) | 06 Oct 2023 | N6 |  | Works done for the day
Fri (06/10) | 06 Oct 2023 | MH2-5 |  | To continue entry point hacking towards MH2-4. Now workers on dinner break. Team will be working till 10pm
Fri (06/10) | 06 Oct 2023 | MH2-3 |  | Preparing to cast thrust block
Fri (06/10) | 06 Oct 2023 | Gate 5 |  | Tonigh to do excavation for SPPG, singtel and M1 pipe laying. Current access will be closed till sunday
Fri (06/10) | 06 Oct 2023 | MH2-5 |  | Entry ring installation prior to jacking to 2-4, tomorrow plan to start jacking
Fri (06/10) | 06 Oct 2023 | N6 |  | WH working till 10pm for scaffold access and pump installation
Fri (06/10) | 06 Oct 2023 | MH5-2 |  | Excavation will continue tonight, current depth 700mm
Fri (06/10) | 06 Oct 2023 | MH5-1 |  | Dayshift team left the site, base slab current depth of excavation is 200-300mm. Tomorrow they will continue
Fri (06/10) | 06 Oct 2023 | Zone 4 ABH109 |  | Trial trench ongoing. Found water pipe at 900mm depth
Fri (06/10) | 06 Oct 2023 | Zone 4 ABH110 |  | Trial trench in progress
Fri (06/10) | 06 Oct 2023 | Zone 4 |  | To continue hoarding frame installation
Sat (07/10) | 07 Oct 2023 | Loyang way LP65 |  | M1 pipe laying here to installed MH, 4m only. Pipe laying completed and backfilling in progress
Sat (07/10) | 07 Oct 2023 | Zone 4 status |  | No activity
Sat (07/10) | 07 Oct 2023 | ST143 |  | Trenching on going, depth 28.1m
Sat (07/10) | 07 Oct 2023 | DW56 |  | 1st bite excavation continue
Sat (07/10) | 07 Oct 2023 | MH5-2 |  | Excavation continue for 14th layer. Depth 800mm
Sat (07/10) | 07 Oct 2023 | BP1 |  | Inner casing aligned and boring works. Now no activity
Sat (07/10) | 07 Oct 2023 | DW56 |  | 1st bite done
Sat (07/10) | 07 Oct 2023 | MH5-2 |  | Excavation depth already 1m. Dayshift to complete and cast 14th layer
Sat (07/10) | 07 Oct 2023 | DW56 |  | 2nd bite started
Sat (07/10) | 07 Oct 2023 | ST143 |  | Cutter wheel teeth changing again. Curewnt depth 28.55m
Sat (07/10) | 07 Oct 2023 | Gate 5 |  | Tonight to continue excavation for SPPG, singtel and M1 pipe laying
Sat (07/10) | 07 Oct 2023 | MH5-2 |  | 14th layer rebar installation. Target to cast before 12mn
Sat (07/10) | 07 Oct 2023 | BP1 |  | Lenght of pile from COL: 8m, Outercasing: 6.7 m (2 layers), Inner casing: 9.2m (3 layers), Tonight to continue boring
Sat (07/10) | 07 Oct 2023 | DW56 |  | Cutter wheel teeth replacement, current depth 24.7m for 2nd bite
Sat (07/10) | 07 Oct 2023 | ST143 |  | 1st bite trenching continue at depth 28.35m from TOGW
Sun (08/10) | 08 Oct 2023 | MH2-1 |  | No activity
Sun (08/10) | 08 Oct 2023 | Near Gate 5 |  | Backfilling ongoing by SPPG contractor
Sun (08/10) | 08 Oct 2023 | P23 |  | M1 preparing for their MH installation
Sun (08/10) | 08 Oct 2023 | P20 |  | Starhub plan for pipe laying today, ard 18m
Sun (08/10) | 08 Oct 2023 | North ramp N2, N3, N6 |  | No activity today
Sun (08/10) | 08 Oct 2023 | MH5-2, MH5-1 |  | No activity
Sun (08/10) | 08 Oct 2023 | Zone 1 |  | No activity
Sun (08/10) | 08 Oct 2023 | P23 |  | Krishco rectifying the water pipe support
Sun (08/10) | 08 Oct 2023 | MH2-4, 2-5, 2-3 |  | No activity
Sun (08/10) | 08 Oct 2023 | P25 |  | Wee Guan continue excavation for SPPG and Singtel pipe laying
Sun (08/10) | 08 Oct 2023 | BP1 |  | Boring works continue. They plan to lift up the BP by monday
Sun (08/10) | 08 Oct 2023 | DW56 |  | Trimming on going
Sun (08/10) | 08 Oct 2023 | DW36 |  | Guidewall rebar installation
Sun (08/10) | 08 Oct 2023 | DW56 |  | Preparing for 2nd final koden check
Sun (08/10) | 08 Oct 2023 | ST143 |  | Resume excavation
Sun (08/10) | 08 Oct 2023 | MH5-2 |  | 14th layer casting on going
Sun (08/10) | 08 Oct 2023 | DW56 |  | Final koden check done
Sun (08/10) | 08 Oct 2023 | Gate 5 |  | Excavation work for SPPG, M1 and singtel pipe laying status, tonight wee guan will continue work here
Sun (08/10) | 08 Oct 2023 | MH5-2 |  | 14th layer casting continue
Sun (08/10) | 08 Oct 2023 | DW56 |  | Cleaning on going
Sun (08/10) | 08 Oct 2023 | ST143 |  | Cutter wheel teeth changing, current depth 28.9m
Sun (08/10) | 08 Oct 2023 | DR2 |  | No activity today
Sun (08/10) | 08 Oct 2023 | ST143 |  | Cutter teeth changing in progress. Current trench depth 28.95m
Sun (08/10) | 08 Oct 2023 | Taiyo BP6 and BP1 |  | No activity today
Sun (08/10) | 08 Oct 2023 | Exit 2 DW56 |  | Cleaning & desanding completed. Now final koden check
Mon (09/10) | 09 Oct 2023 | Gate 5 |  | Backfilling on going for the pipe laid for sppg, singtel, M1 and starhub. Length 8m
Mon (09/10) | 09 Oct 2023 | Zone 3 P23 |  | M1 term contractor pipe jamming works
Mon (09/10) | 09 Oct 2023 | Zone 2 P19-P20 |  | Starhub pipe laying here, 12m
Mon (09/10) | 09 Oct 2023 | N6 |  | Balance 300mm to FEL. Tomorrow to complete
Mon (09/10) | 09 Oct 2023 | N4 |  | Area leveling for previous PCN hacking and TT. Tomorrow start TT
Mon (09/10) | 09 Oct 2023 | Gate 5 |  | WG to remove shoring and reinstate access at this area
Mon (09/10) | 09 Oct 2023 | ST143 |  | First bite excavation in progress, 38m
Mon (09/10) | 09 Oct 2023 | Zone 4 ABH107 |  | Manual TT in progress
Mon (09/10) | 09 Oct 2023 | Zone 4 |  | Concrete barriers installation in progress. First lane of LA closed for works
Mon (09/10) | 09 Oct 2023 | Zone 4 |  | Today ECS only installed 9nos hoarding frames (CV bound). Tmr plan to start panel installation. Panels are already on site
Mon (09/10) | 09 Oct 2023 | Zone 4 ABH111 |  | Hand auger in progress
Mon (09/10) | 09 Oct 2023 | Loyang Way near exit 1 |  | DE143 kerb works ongoing at centre median & slip road
Mon (09/10) | 09 Oct 2023 | MH5-1 |  | Support installation on going at the existing sewer, afterwhich still need to excavate below it. Tomorrow to lean con, Wed then plan to cast base slab
Mon (09/10) | 09 Oct 2023 | Zone 3 BH64 |  | In progress, 36m
Mon (09/10) | 09 Oct 2023 | Zone 3 BH88 |  | In progress, 18m
Mon (09/10) | 09 Oct 2023 | Zone 1 |  | Krishco shoring works in progress for tmr cctv inspection
Mon (09/10) | 09 Oct 2023 | MH5-1 |  | Continue support installation
Mon (09/10) | 09 Oct 2023 | MH5-2 |  | Continue 15th layer excavation
Mon (09/10) | 09 Oct 2023 | N6 |  | Tmr to complete. KTC soil disposal in progress. Netting installation ongoing
Mon (09/10) | 09 Oct 2023 | N4 |  | Hacking in progress
Mon (09/10) | 09 Oct 2023 | N3 |  | No activity
Mon (09/10) | 09 Oct 2023 | N2 |  | Concrete plug casting in progress
Mon (09/10) | 09 Oct 2023 | MH2-4 |  | 13th ring excavation. Team working till 7pm today
Mon (09/10) | 09 Oct 2023 | MH2-5 to MH2-4 |  | Pipe jacking in progress, 3/18nos. Team working till 10pm today
Mon (09/10) | 09 Oct 2023 | Taiyo BP1 |  | LSS backfilling in progress
Mon (09/10) | 09 Oct 2023 | BP6 |  | No activity
Mon (09/10) | 09 Oct 2023 | DR2 |  | No activity
Mon (09/10) | 09 Oct 2023 | ST143 |  | Trimming ongoing
Mon (09/10) | 09 Oct 2023 | Exit 2 DW54 |  | First bite excavation in progress
Mon (09/10) | 09 Oct 2023 | Gate 5 |  | Access area reinstated
Mon (09/10) | 09 Oct 2023 | MH2-1 |  | 2nd layer formwork fully remove. This team working until 10PM
Tue (10/10) | 10 Oct 2023 | Zone 4 LA towards CV |  | Lane closure for hoarding panel installation
Tue (10/10) | 10 Oct 2023 | P20-P21 |  | Starhub pipe laying to continue here. Target 12m
Tue (10/10) | 10 Oct 2023 | Zone 3 BH64 |  | In progress, 40m
Tue (10/10) | 10 Oct 2023 | BH88 |  | In progress, 28m
Tue (10/10) | 10 Oct 2023 | ST143 |  | Trimming ongoing
Tue (10/10) | 10 Oct 2023 | DR2 |  | Stifferner plate welding ongoing
Tue (10/10) | 10 Oct 2023 | Zone 3 BH107A |  | In progress, 6m
Tue (10/10) | 10 Oct 2023 | BH117 |  | Current depth at 37m
Tue (10/10) | 10 Oct 2023 | N2 |  | Concrete plug curing
Tue (10/10) | 10 Oct 2023 | N3 |  | Installation of bar chair done. Horizontal and diagonal bracing installation in progress
Tue (10/10) | 10 Oct 2023 | BP6 |  | First inner casing installation in progress
Tue (10/10) | 10 Oct 2023 | N4 |  | Hacking of previous pcn in progress
Tue (10/10) | 10 Oct 2023 | MH5-2 |  | Continue excavation for 15th layer caisson
Tue (10/10) | 10 Oct 2023 | MH5-2 |  | Excavation for 15th layer caisson
Tue (10/10) | 10 Oct 2023 | MH2-5 |  | 6/18 pipe jacked to 2-4, preparation for 17th pipe
Tue (10/10) | 10 Oct 2023 | DW22 & 23 |  | Continue trial trench works
Tue (10/10) | 10 Oct 2023 | N6 |  | Excavation to FEL completed. Pending marking of pile COL for cutting works
Tue (10/10) | 10 Oct 2023 | N4 |  | Old pcn hacking continue
Tue (10/10) | 10 Oct 2023 | N3 |  | Top bar installation on going. Plan to complete top bars today and start side bars
Tue (10/10) | 10 Oct 2023 | Zone 4 |  | Manual trial trench work for ABH-108
Tue (10/10) | 10 Oct 2023 | Zone 4 |  | DE143 works at traffic island
Tue (10/10) | 10 Oct 2023 | Zone 4 Loyang Ave towards Loyang Way |  | 1st lane closure for concrete barrier installation. Will open back the lane by 4.30pm
Tue (10/10) | 10 Oct 2023 | Zone 4 Loyang Ave toward changi |  | ECS hoarding sheet/mesh installation at CV bound lane
Tue (10/10) | 10 Oct 2023 | MH5-1 |  | Base slab trimming, lean concrete by 5pm
Tue (10/10) | 10 Oct 2023 | MH5-2 |  | 15th layer hacking, est 800mm depth
Tue (10/10) | 10 Oct 2023 | Zone 1 |  | Krishco reinstating water pipe. Today to backfill, tomorrow to do premix
Tue (10/10) | 10 Oct 2023 | ST143 |  | 2nd bite excavation reached 24m depth. Koden test and replacing of cutter teeth in progress
Tue (10/10) | 10 Oct 2023 | MH2-1 |  | 3rd layer excavation. Balance trimming, they are trying to cast today before 10pm
Tue (10/10) | 10 Oct 2023 | DR2 |  | Balamce concrete packing at diagonal waler to cast, waiting for concrete lorry
Tue (10/10) | 10 Oct 2023 | ST91 |  | 1st bite trenching using grab bucket. Current depth 8m
Tue (10/10) | 10 Oct 2023 | St143 |  | Cutter wheel teeth changing
Tue (10/10) | 10 Oct 2023 | MH2-5 |  | Work ended for the day. 7/18 pipes jacked to 2-4
Tue (10/10) | 10 Oct 2023 | MH2-4 |  | 13th layer casting completed. LCH housekeeping
Tue (10/10) | 10 Oct 2023 | N4 |  | Old pcn hacking completed. Debirs clearing. Tomorrow to do TT
Tue (10/10) | 10 Oct 2023 | N3 |  | T2 layer completed. Now T1 hoingnto start
Tue (10/10) | 10 Oct 2023 | MH5-1 |  | Concrete just arrive for slab lean concrete
Tue (10/10) | 10 Oct 2023 | MH5-2 |  | Dayshift team stopped work for the day, night shift team to continue excavation
Tue (10/10) | 10 Oct 2023 | MH2-5 to MH2-4 |  | Now no activity of jacking work
Tue (10/10) | 10 Oct 2023 | Gate 5 |  | Continuation of sppg, singtel, m1 and starhub pipe laying. Today target 4m
Tue (10/10) | 10 Oct 2023 | Exit 3 |  | TT for DW22 and DW23
Tue (10/10) | 10 Oct 2023 | Exit 2 |  | DW36 guidewall formwork dismantling
Tue (10/10) | 10 Oct 2023 | Zone 4 Loyang Ave towards Loyang Way |  | First lane closure for concrete barrier installation
Tue (10/10) | 10 Oct 2023 | MH2-1 |  | 3rd layer excavation on going. Today plan to complete excavation, balance will be trimming. Tomorrow am plan to cast
Tue (10/10) | 10 Oct 2023 | Zone 4 |  | DE143 works at traffic island
Wed (11/10) | 11 Oct 2023 | P19-20 |  | Starhub to continue pipe laying here
Wed (11/10) | 11 Oct 2023 | N6 |  | No activity. pile hacking to start today
Wed (11/10) | 11 Oct 2023 | N3 |  | Rebar installation for pile cap
Wed (11/10) | 11 Oct 2023 | N2 |  | Addressing QPS comment on patching works before arranging another reinspection in the afternoon
Wed (11/10) | 11 Oct 2023 | Loyang Ave/PRD3 junction |  | No silty water observed
Wed (11/10) | 11 Oct 2023 | MH5-2 |  | Continue excavation for caisson shaft
Wed (11/10) | 11 Oct 2023 | Zone 4 |  | ABH108 TT on going
Wed (11/10) | 11 Oct 2023 | Zone 3/4 Junction |  | De143 working here installing road kerbs
Wed (11/10) | 11 Oct 2023 | Zone 3 |  | Delivery of 3rd dwall rig, upper mast on site
Wed (11/10) | 11 Oct 2023 | ST143 |  | Chisel c-lug welding for trimming
Wed (11/10) | 11 Oct 2023 | DR2 |  | No activity observed
Wed (11/10) | 11 Oct 2023 | BP6 setting up on going |  | Tonight to start coring
Wed (11/10) | 11 Oct 2023 | DW54 |  | Now end plate removal at DW53 side
Wed (11/10) | 11 Oct 2023 | MH2-1 |  | 3rd layer moulding installation. Casting at 6pm
Wed (11/10) | 11 Oct 2023 | MH2-8 |  | Manual excavation on going
Wed (11/10) | 11 Oct 2023 | N3 |  | Shearlinks installation on going
Wed (11/10) | 11 Oct 2023 | P10-2-1 |  | Casing installed. Tomorrow plan to start boring
Wed (11/10) | 11 Oct 2023 | MH5-1 |  | Base slab rebar installation, target to cast around 3 am
Wed (11/10) | 11 Oct 2023 | MH5-2 |  | 15th layer excavation completed, night shift team to install rebar and cast
Wed (11/10) | 11 Oct 2023 | MH2-5 to 2-4 |  | No activity
Wed (11/10) | 11 Oct 2023 | MH2-8 |  | Today to continue excavation for 2nd layer. Plan to cast today
Wed (11/10) | 11 Oct 2023 | MH5-1 |  | BRC laying for base slab casting
Wed (11/10) | 11 Oct 2023 | MH2-1 |  | Trimming completed last night
Wed (11/10) | 11 Oct 2023 | MH5-2 |  | Caisson BRC installation. Tonight to cast
Wed (11/10) | 11 Oct 2023 | N4 |  | Levelling & suverying works in progress. LE to start trial trench today
Thu (12/10) | 12 Oct 2023 | MH5-1 |  | Continue base slab rebar work in progress. Left one more layer to complete
Thu (12/10) | 12 Oct 2023 | MH5-2 |  | Formwork closing in progress. Estimate around 2:30AM concrete will be on site
Thu (12/10) | 12 Oct 2023 | P10-2-1 |  | Boring in progress, started before lunch
Thu (12/10) | 12 Oct 2023 | Zone 3/4 Junction |  | DE143 working here for kerb installation
Thu (12/10) | 12 Oct 2023 | MH2-9 |  | New access gate making in progress
Thu (12/10) | 12 Oct 2023 | Zone 1 |  | Patching works for new ecm
Thu (12/10) | 12 Oct 2023 | Zone 4 |  | Premix cutting for Bored pile TT work. Tomorrow excavator will deliver
Thu (12/10) | 12 Oct 2023 | Zone 1 |  | De143 works beside shell station
Thu (12/10) | 12 Oct 2023 | DR2 |  | 2 excavators onsite to start excavation soon
Thu (12/10) | 12 Oct 2023 | Zone 4 |  | Hoarding panel installation on going
Thu (12/10) | 12 Oct 2023 | MH5-1 |  | Base slab cast
Thu (12/10) | 12 Oct 2023 | DR2 |  | Pavement hacking ongoing
Thu (12/10) | 12 Oct 2023 | Exit 1 |  | Silo base slab extension rebar works in progress. Tomorrow plan to cast
Thu (12/10) | 12 Oct 2023 | BH88 |  | Drilling at 40m depth
Thu (12/10) | 12 Oct 2023 | N3 |  | Continue rebar installation for pile cap
Thu (12/10) | 12 Oct 2023 | P10-2-1 |  | Boring completed. Now rto inspection on rebar cage before lowering
Thu (12/10) | 12 Oct 2023 | N2 |  | To start backfill works for pilecap today
Thu (12/10) | 12 Oct 2023 | N6 |  | Pile hacking in progress
Thu (12/10) | 12 Oct 2023 | DR2 |  | Excavation to W1 layer started. Site plan to complete by tomorrow
Thu (12/10) | 12 Oct 2023 | P10-2-1 |  | Rebar cage lapping and u-clip torque test inspection. Total 2 cages, 1.5T tonnes
Thu (12/10) | 12 Oct 2023 | MH2-4 |  | Base slab excavation in progress. Plan for lean con ard 10pm
Thu (12/10) | 12 Oct 2023 | MH5-2, MH5-1 |  | No activity
Thu (12/10) | 12 Oct 2023 | P10-2-1 |  | Casting completed. Total vol: 26.5m3
Thu (12/10) | 12 Oct 2023 | N4 |  | Barricade installation
Thu (12/10) | 12 Oct 2023 | Loyang Lane LP2 |  | Plan for Singtel pipe laying tonight ard 6m
Thu (12/10) | 12 Oct 2023 | BP6 |  | Tonight continue installation of 2m dia casing. Inner casing installed ard 6.5m
Thu (12/10) | 12 Oct 2023 | DW54 |  | Progressive vol: 84m3. Another 2 more trucks otw
Thu (12/10) | 12 Oct 2023 | DR2 |  | Works done for the day. Housekeeping ongoing
Thu (12/10) | 12 Oct 2023 | ST143 |  | Trimming ongoing ard 35m
Fri (13/10) | 13 Oct 2023 | MH5-2 |  | Today to remove moulding for 15th layer and start excavation for base slab
Fri (13/10) | 13 Oct 2023 | N1-1 |  | Casting in progress
Fri (13/10) | 13 Oct 2023 | N6 |  | Pile head hacking in progress, 1/4 completed. 1 pile per day. 😩
Fri (13/10) | 13 Oct 2023 | N4 no activity observed |  | Highlighted to WH to arrange
Fri (13/10) | 13 Oct 2023 | N3 |  | Today to complete formwork closing. Tomorrow plan to install shearlinks,, Sunday to complete formwork supports and tie back,, Monday to cast
Fri (13/10) | 13 Oct 2023 | N2 |  | Soil backfilling for 1st layer (300mm), after lunch to do NDT
Fri (13/10) | 13 Oct 2023 | N1-1 |  | Casing installation in progress
Fri (13/10) | 13 Oct 2023 | MH2-4 |  | Base slab rebar works in progress, bottom layer completed
Fri (13/10) | 13 Oct 2023 | Zone 2 P22 |  | Mo guan working here for starhub pipe laying. Today target 12m
Fri (13/10) | 13 Oct 2023 | Zone 2 |  | TT for POB pile cap at center median
Fri (13/10) | 13 Oct 2023 | MH2-6 |  | RC bedding rebar works kn going. Today plan to cast base slab
Fri (13/10) | 13 Oct 2023 | MH2-9 |  | Drain hacking in progress
Fri (13/10) | 13 Oct 2023 | Gate 5 |  | Excavation and shoring works for SPPG, singtel, m1 and starhub pipe laying
Fri (13/10) | 13 Oct 2023 | Loyang lane DW23 |  | Mamual hacking to expose 66Kv cable for spiking
Fri (13/10) | 13 Oct 2023 | exit 2 |  | Area leveling for BC cutter working platform
Fri (13/10) | 13 Oct 2023 | MH2-1 |  | 4th layer excavation on going
Fri (13/10) | 13 Oct 2023 | Exit 2 |  | Backfilled soil shifting to prepare the area for dwall works
Fri (13/10) | 13 Oct 2023 | BP6 |  | Outer casing drilling continue at 5.7m/6m
Fri (13/10) | 13 Oct 2023 | P31 |  | WH TT to find LV cable alignment
Fri (13/10) | 13 Oct 2023 | Zone 2 |  | Continue TT and exposing for POB pile cap
Fri (13/10) | 13 Oct 2023 | ST143 |  | Desanding in progress
Fri (13/10) | 13 Oct 2023 | MH2-3 |  | Preparing to lower 3rd jacking pipe
Fri (13/10) | 13 Oct 2023 | MH2-4 |  | Rebar works for base slab. To cast today
Fri (13/10) | 13 Oct 2023 | BP6 |  | Continue outer casing installation, 5.3m
Fri (13/10) | 13 Oct 2023 | Exit 2 DW54 |  | Casting was completed. Total vol: 99m3
Fri (13/10) | 13 Oct 2023 | ST143 |  | Chiselling completed. Now preparing for water stopper extraction
Fri (13/10) | 13 Oct 2023 | N6 |  | 3rd pile head hacking in progress, 2/4 completed
Fri (13/10) | 13 Oct 2023 | N3 |  | Formwork closing and rebar installation for pile cap
Fri (13/10) | 13 Oct 2023 | N1-1 |  | Boring completed. Cleaning in progress
Fri (13/10) | 13 Oct 2023 | N2 |  | NDT done. To continue backfill for next layer
Fri (13/10) | 13 Oct 2023 | Exit 1 |  | Extension of silo base slab, formwork closing. Today to cast
Fri (13/10) | 13 Oct 2023 | Zone 3/4 junction |  | DE143 works for kerb installation
Fri (13/10) | 13 Oct 2023 | Zone 4 |  | CV bound hoarding panel installation stopped for the day, completed until the frame installed. ECS will go TPE bound to install frames
Fri (13/10) | 13 Oct 2023 | Zone 4 TPE bound |  | Concrete barrier installation on going
Fri (13/10) | 13 Oct 2023 | Zone 4 |  | ABH110 drilling at 4m depth
Fri (13/10) | 13 Oct 2023 | MH2-6 |  | Base slab casting in progress
Fri (13/10) | 13 Oct 2023 | MH2-4 |  | Base slab cast
Fri (13/10) | 13 Oct 2023 | North ramp N1-1 |  | Rebar cage and hanging bar installation completed. Preparing for casting
Fri (13/10) | 13 Oct 2023 | Exit 2 |  | Excavation for bentonite pipe laying
Fri (13/10) | 13 Oct 2023 | BP6 |  | Outer casing installation completed 6m. Now installing additional inner casing. Night team to continue drive in inner casing
Fri (13/10) | 13 Oct 2023 | ST143 |  | Waterstop end plate joint welding ongoing
Fri (13/10) | 13 Oct 2023 | ST91 |  | First bite excavation in progress
Fri (13/10) | 13 Oct 2023 | MH2-9 |  | Gate shifted yesterday as per PGI comment
Fri (13/10) | 13 Oct 2023 | MH2-9 |  | Today to continue drain hacking
Fri (13/10) | 13 Oct 2023 | Near MH2-8 |  | Starhub plan to continue pipe laying tonight
Sat (14/10) | 14 Oct 2023 | Zone 3 |  | BH143 drilling works ongoing, current depth 29m
Sat (14/10) | 14 Oct 2023 | MH2-1 |  | Excavation works for 4th layer
Sat (14/10) | 14 Oct 2023 | DR2 Canal Drain Diversion ERSS |  | Excavation and waler bracket installation
Sat (14/10) | 14 Oct 2023 | DR2 |  | Welding of stiffener plate for waler beam
Sat (14/10) | 14 Oct 2023 | ST91 |  | 2nd bite excavation in progress
Sat (14/10) | 14 Oct 2023 | ST143 |  | Rebar cage installation and lapping ongoing. 5/8 lowered. 6th rebar cage lapping and lowering in progress
Sat (14/10) | 14 Oct 2023 | Exit 1 |  | Extension of silo base slab, inspection has been done. Pending concrete truck to arrive for casting
Sat (14/10) | 14 Oct 2023 | Zone 3/4 junction |  | DE143 works for kerb installation
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | ABH-107 drilling in progress, current depth 10m
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | ABH-110 drilling in progress, current depth 15.3m
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | Concrete barriers installation works
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | ECS hoarding installation works
Sat (14/10) | 14 Oct 2023 | N3 |  | Continue rebar and Formwork supports installation for pile cap
Sat (14/10) | 14 Oct 2023 | N6 |  | 3rd Pile head hacking in progress. 2/4 nos completed
Sat (14/10) | 14 Oct 2023 | N2 |  | Continue backfilling and levelling works
Sat (14/10) | 14 Oct 2023 | P10-2-4 |  | Rebar cage shifting in progress prior to start of boring works
Sat (14/10) | 14 Oct 2023 | Zone 1 |  | Krishco doing trial trench for live valve installation works which schedule on Monday
Sat (14/10) | 14 Oct 2023 | MH5-2 |  | Base slab excavation works
Sat (14/10) | 14 Oct 2023 | MH5-1 |  | No activity
Sat (14/10) | 14 Oct 2023 | MH2-4 |  | No activity
Sat (14/10) | 14 Oct 2023 | MH2-3 to MH2-4 |  | 5th pipe jacking completed. Preparing to lower 6th pipe
Sat (14/10) | 14 Oct 2023 | N1-1 |  | Casting completed
Sat (14/10) | 14 Oct 2023 | Near Exit 3 |  | Excavation works to divert bentonite pipe for DW23 trial trench and guidewall construction
Sat (14/10) | 14 Oct 2023 | Near Exit 3 |  | Wee Guan Continue excavation and Shoring works for pipe laying
Sat (14/10) | 14 Oct 2023 | ST91 |  | 2nd bite excavation in progress, current depth 10m
Sat (14/10) | 14 Oct 2023 | ST143 |  | Rebar cage lowering and lapping ongoing. 7/8 lowered. 8th rebar cage lapping and lowering in progress. Inspection done for hanging bar u-clip
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | ABH-104 Manual trial trench in progress for SI work
Sat (14/10) | 14 Oct 2023 | ST143 |  | U-clip torque test inspection done. OK to proceed installation
Sat (14/10) | 14 Oct 2023 | ST91 |  | Continue first bite excavation, 22.8m
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | Continue Concrete barriers installation works
Sat (14/10) | 14 Oct 2023 | Zone 4 |  | ECS hoarding installation current status. Workers now on break, to resume after that
Sat (14/10) | 14 Oct 2023 | Exit 1 |  | Extension of silo base slab casting and levelling ongoing
Sat (14/10) | 14 Oct 2023 | ST143 |  | Rebar cage installation started
Sat (14/10) | 14 Oct 2023 | P34 |  | Singtel pipe jamming
Sat (14/10) | 14 Oct 2023 | BP6 |  | Continue driving in inner casing, current depth ard 6.5m
Sat (14/10) | 14 Oct 2023 | DR2 |  | Continue of waler beams & waler brackets installation and welding works
Sat (14/10) | 14 Oct 2023 | DR2 |  | Continue of excavation works
Sat (14/10) | 14 Oct 2023 | MH2-1 |  | Continue Excavation works for 4th layer
Sat (14/10) | 14 Oct 2023 | Zone 3 |  | BH143 drilling works ongoing, current depth 35m
Sat (14/10) | 14 Oct 2023 | MH2-3 |  | Pipe jacking for 6th pipe in progress
Sat (14/10) | 14 Oct 2023 | MH2-6 |  | No activity
Sat (14/10) | 14 Oct 2023 | N6 |  | Continue 3rd Pile head hacking works. 2/4 nos completed
Sat (14/10) | 14 Oct 2023 | N2 |  | Continue compaction and levelling works
Sat (14/10) | 14 Oct 2023 | P10-2-4 |  | Boring completed. Now preparation to lower rebar cages
Sat (14/10) | 14 Oct 2023 | MH5-2 |  | Continue excavation works for base slab
Sat (14/10) | 14 Oct 2023 | N3 |  | Rebar and Formwork installation works for pile cap
Sat (14/10) | 14 Oct 2023 | Zone 1 |  | Krishco trial trench completed. Reinstatement in progress
Sat (14/10) | 14 Oct 2023 | MH2-9 |  | 1st layer steel mould installation. To cast today
Sat (14/10) | 14 Oct 2023 | ST143 |  | Rebar cage installation in progress. 4/8nos lowered
Sat (14/10) | 14 Oct 2023 | P10-2-4 |  | Casting completed. Tremie pipes removal ongoing
Sat (14/10) | 14 Oct 2023 | MH5-2 |  | No activity
Sat (14/10) | 14 Oct 2023 | BP2 |  | First inner casing installation in progress, current depth ard 5.2m
Sat (14/10) | 14 Oct 2023 | DR2 |  | Barricade installation ongoing. No other activity
Sat (14/10) | 14 Oct 2023 | ST143 |  | Casting ongoing. Progressive vol: 18/280m3
Sat (14/10) | 14 Oct 2023 | Loyang Lane LP2 |  | Starhub plan to continue pipe laying tonight
Sat (14/10) | 14 Oct 2023 | Near Exit 3 |  | Shoring & levelling works for pipe laying at P25-P26 by Wee Guan
Sat (14/10) | 14 Oct 2023 | Zone 3 |  | BH157 grouting works ongoing. Termination depth 46.5m
Sun (15/10) | 15 Oct 2023 | BP2 |  | Continue inner casing installation, 5.7m
Sun (15/10) | 15 Oct 2023 | ST91 |  | 2nd bite excavation in progress
Sun (15/10) | 15 Oct 2023 | ST143 |  | Casting in progress, 285m3
Sun (15/10) | 15 Oct 2023 | ST143 |  | Casting completed. Total vol: 285/285m3
Sun (15/10) | 15 Oct 2023 | Zone 2 |  | No more activity at MH area
Sun (15/10) | 15 Oct 2023 | ST91 |  | 2nd bite internal koden test on going
Mon (16/10) | 16 Oct 2023 | ST94 |  | 1st bite trenching, depth at 19m depth
Mon (16/10) | 16 Oct 2023 | ST91 |  | Cage 3B, 4A&B u-clip torque test
Mon (16/10) | 16 Oct 2023 | MH2-3 |  | 10th pipe lowered. Preparation to start jacking in progress
Mon (16/10) | 16 Oct 2023 | N6 |  | Manual hacking of pile head to COL
Mon (16/10) | 16 Oct 2023 | N3 |  | Preparation works for thermocouple installation
Mon (16/10) | 16 Oct 2023 | N2 |  | Backfill & NDT works
Mon (16/10) | 16 Oct 2023 | P10-2-2 |  | Preboring completed. Now casing installation
Mon (16/10) | 16 Oct 2023 | Zone 1 |  | Krishco water live valve installation in progress
Mon (16/10) | 16 Oct 2023 | Zone 1 |  | NLL M&P works
Mon (16/10) | 16 Oct 2023 | MH5-2 |  | Base slab excavation works. Today will lean concrete base slab
Mon (16/10) | 16 Oct 2023 | N4 |  | LE Boring rig shifted to N4, to start preboring in the afternoon
Mon (16/10) | 16 Oct 2023 | Gate 5 |  | Excavation to FEL completed, levelling in progress
Mon (16/10) | 16 Oct 2023 | MH2-4 |  | Hacking of wall for pipe jacking to continue
Mon (16/10) | 16 Oct 2023 | MH2-3 |  | Pending MH2-4 to finish wall hacking before continue of pipe jacking
Mon (16/10) | 16 Oct 2023 | N6 |  | HSL Manual pile head hacking in progress
Mon (16/10) | 16 Oct 2023 | N3 |  | Themocouple installed. Now survey works in progress
Mon (16/10) | 16 Oct 2023 | N2 |  | NDT done for 4th layer, KTC will proceed with 5th layer backfilling to pile cap level
Mon (16/10) | 16 Oct 2023 | P10-2-2 |  | Boring completed. Cleaning in progress
Mon (16/10) | 16 Oct 2023 | Zone 1 |  | Krishco live valve installation done, reinstatement ongoing
Mon (16/10) | 16 Oct 2023 | Zone 1 |  | M&P works
Mon (16/10) | 16 Oct 2023 | MH5-2 |  | Continue base slab excavation. To cast lean concrete around 6-7pm
Mon (16/10) | 16 Oct 2023 | Gate 5 |  | Shoring done, today to lay pipes for sppg, singtel, starhub and M1
Mon (16/10) | 16 Oct 2023 | MH2-4 |  | Caisson hacking for jacking machine retrieval
Mon (16/10) | 16 Oct 2023 | ST91 |  | Cleaning completed for 1st bite and 2nd bite, next to clean 3rd bite and do desanding
Mon (16/10) | 16 Oct 2023 | N1-3 |  | Casing installed for the pile
Mon (16/10) | 16 Oct 2023 | P2-2 |  | Concrete will be on site around 6:30PM for casting
Mon (16/10) | 16 Oct 2023 | MH5-2 |  | Concrete ordered. Plan for lean concrete around 7PM
Mon (16/10) | 16 Oct 2023 | P21 |  | POB pile cap continue excavation till 9pm
Mon (16/10) | 16 Oct 2023 | N4 |  | Work stopped for the day, 1 no pre-boring completed
Mon (16/10) | 16 Oct 2023 | P10-2-2 |  | Casting in progress. 18/27 m3. Waiting for the last truck
Mon (16/10) | 16 Oct 2023 | BP6 |  | Installing outer casing to fish the balance 2.8m BP, target to lift tomorrow
Mon (16/10) | 16 Oct 2023 | ST91 |  | Rebar cages installation
Tue (17/10) | 17 Oct 2023 | MH5-2 |  | Preparation for base slab works. Today to proceed BRC laying & target for casting
Tue (17/10) | 17 Oct 2023 | MH5-1 & South Ramp |  | No activity
Tue (17/10) | 17 Oct 2023 | PMH8 |  | WG preparation for winch bracket installation. Currently nobody is inside the PMH
Tue (17/10) | 17 Oct 2023 | N4 |  | Preboring in progress
Tue (17/10) | 17 Oct 2023 | N3 |  | Inspection ongoing prior to casting. Concrete pump on site
Tue (17/10) | 17 Oct 2023 | N1-3 |  | Boring in progress
Tue (17/10) | 17 Oct 2023 | Zone 2 |  | Small tree cutting & big tree pruning ongoing
Tue (17/10) | 17 Oct 2023 | MH2-4 |  | Continue caisson hacking for jacking machine retrieval
Tue (17/10) | 17 Oct 2023 | BH158 |  | In progress, 28m
Tue (17/10) | 17 Oct 2023 | Exit 3 |  | Excavation in progress for SPPG/Singtel pipe laying
Tue (17/10) | 17 Oct 2023 | Zone 3 near DR1 |  | Trial trench to check for existing utilities
Tue (17/10) | 17 Oct 2023 | P32 |  | Starhub pipe laying, 12m (6way)
Tue (17/10) | 17 Oct 2023 | ST91 |  | 7/8 rebar cage installation in progress
Tue (17/10) | 17 Oct 2023 | ST94 |  | Cutter wheel teeth changing, current depth 30m
Tue (17/10) | 17 Oct 2023 | P22 |  | Krishco water pipe laying in progress
Tue (17/10) | 17 Oct 2023 | MH2-4 |  | Continue hacking of wall to expose jacking machine
Tue (17/10) | 17 Oct 2023 | Zone 2 |  | Continue Small tree cutting & big tree pruning
Tue (17/10) | 17 Oct 2023 | DR2 |  | Continue drain cleaning & waler joint welding
Tue (17/10) | 17 Oct 2023 | ST91 |  | Casting ongoing, progressive vol: 228/250m3
Tue (17/10) | 17 Oct 2023 | Zone 3 ABH103 |  | In progress, 8m
Tue (17/10) | 17 Oct 2023 | N4 |  | Preboring works in progress. 3/20 nos. completed
Tue (17/10) | 17 Oct 2023 | N6 |  | Manual pile head hacking in progress. 1/4 nos completed
Tue (17/10) | 17 Oct 2023 | Zone 3 ABH104 |  | First permeability test (10.96-11.96m)
Tue (17/10) | 17 Oct 2023 | N3 |  | Pile cap casting in progress
Tue (17/10) | 17 Oct 2023 | N1-3 |  | Boring works completed. Now preparing to lower the rebar cages
Tue (17/10) | 17 Oct 2023 | MH2-6 |  | Wall casting, 1.3m height
Tue (17/10) | 17 Oct 2023 | Gate 5 |  | Area backfilling completed
Tue (17/10) | 17 Oct 2023 | MH2-3 |  | Pushing of jacking pipe for machine retrieval at MH2-4
Tue (17/10) | 17 Oct 2023 | N1-3 |  | Casting in progress
Tue (17/10) | 17 Oct 2023 | ST94 |  | Trenching temp on hold due to pipe leaking at desanding machine, rectification on going
Tue (17/10) | 17 Oct 2023 | MH5-2 |  | Current status of base slab. This team working until 9PM
Tue (17/10) | 17 Oct 2023 | ST91 |  | All rebar cages installed. Now installing tremie pipes for casting
Tue (17/10) | 17 Oct 2023 | Gate 5 |  | Tonight pipe laying here for sppg, singtel, m1 and starhub. 3m
Tue (17/10) | 17 Oct 2023 | N1-3 |  | Casting continue, last load
Tue (17/10) | 17 Oct 2023 | Exit 2 |  | BC cutter body flange welding tonight to 1.2m width
Tue (17/10) | 17 Oct 2023 | BP06 |  | Work stopped for the day
Tue (17/10) | 17 Oct 2023 | ST94 |  | 2nd bite trenching on going
Tue (17/10) | 17 Oct 2023 | Zone 2 |  | Preparation for tree felling/pruning
Tue (17/10) | 17 Oct 2023 | Zone 1 |  | M1 cable diversion
Wed (18/10) | 18 Oct 2023 | Zone 4 |  | Depcie working here for sptel pipe laying
Wed (18/10) | 18 Oct 2023 | Zone 3 ABH104 |  | In progress, 17m
Wed (18/10) | 18 Oct 2023 | Exit 3 |  | Dongaha here connecting bentonite pipe supply and return
Wed (18/10) | 18 Oct 2023 | Gate 5 exit 3 |  | Singtel pipe installation on going
Wed (18/10) | 18 Oct 2023 | Gate 5 |  | SPPG pipe laid, 3m
Wed (18/10) | 18 Oct 2023 | Exit 2 |  | BC cutter body flange welding continue
Wed (18/10) | 18 Oct 2023 | ST94 |  | 2md bite trenching at 18m depth
Wed (18/10) | 18 Oct 2023 | Zone 4 inside the hoarded area |  | Depcie here for sptel pipe laying
Wed (18/10) | 18 Oct 2023 | DR2 |  | Current status. Observed no silty discharge
Wed (18/10) | 18 Oct 2023 | ST94 |  | BC cutter wheel repair works ongoing
Wed (18/10) | 18 Oct 2023 | ST94 |  | Chiselling works ongoing
Wed (18/10) | 18 Oct 2023 | DR2 |  | Continue waler beam installation. As to date, 48m/60m installed
Wed (18/10) | 18 Oct 2023 | Exit 2 |  | Excavation for dwall guidewall works
Wed (18/10) | 18 Oct 2023 | BP6 |  | Continue to drive in casing. Current depth ard 8.5m, balance about 500mm. Tmr morning plan to extract remaining pile
Wed (18/10) | 18 Oct 2023 | P23 |  | Krishco water pipe laying works
Wed (18/10) | 18 Oct 2023 | MH2-3 |  | 10th pipe jacking works
Wed (18/10) | 18 Oct 2023 | MH2-4 |  | Preparation to pipe remove jacking machine
Wed (18/10) | 18 Oct 2023 | Zone 2 Trees Transplanting |  | 11/24 nos. done
Wed (18/10) | 18 Oct 2023 | N6 |  | No activity for Pile head hacking. 2/4 nos completed
Wed (18/10) | 18 Oct 2023 | N4 |  | 15 nos. of soldier piles delivered onsite
Wed (18/10) | 18 Oct 2023 | Exit 3 |  | Continue excavation for power duct laying
Wed (18/10) | 18 Oct 2023 | P10-2-3 |  | Rebar cage lowering in progress
Wed (18/10) | 18 Oct 2023 | MH5-2 |  | Rebar installation for base slab ongoing, to cast today
Wed (18/10) | 18 Oct 2023 | Gate 5 |  | Backfilling status, balance 1m till ground level, dayshift team to continue
Wed (18/10) | 18 Oct 2023 | Zone 2 |  | Tree transplanting done for the day. Balance 6nos to be continued tmr
Wed (18/10) | 18 Oct 2023 | MH5-2 |  | Base slab rebar pending inspection prior to casting
Wed (18/10) | 18 Oct 2023 | ST94 |  | 2nd bite trenching resume after repair of hydraulic hose. Current depth at 22m
Wed (18/10) | 18 Oct 2023 | North ramp P10-2-3 |  | Casting in progress. Progressive vol: 18/27m3
Wed (18/10) | 18 Oct 2023 | P23 |  | Krishco water pipe laying ongoing. Team working till 7pm
Wed (18/10) | 18 Oct 2023 | BP6 |  | Casing installation completed. Tmr morning to extract remaining pile
Wed (18/10) | 18 Oct 2023 | DR2 |  | Waler and strut installation done for the day
Wed (18/10) | 18 Oct 2023 | DW22 |  | Guidewall casting completed
Wed (18/10) | 18 Oct 2023 | P25 loyang lane/ave junction |  | Tonight Depcie will work here for singtel pipe installation
Wed (18/10) | 18 Oct 2023 | BP06 |  | Taiyo asia no more activity
Wed (18/10) | 18 Oct 2023 | Exit 2 |  | End plate preparation and welding works tonight
Wed (18/10) | 18 Oct 2023 | DR2 no more activity |  | Railing installation by WH till 10pm
Wed (18/10) | 18 Oct 2023 | ST94 |  | Trenching tem stopped for teeth replacement
Wed (18/10) | 18 Oct 2023 | Zone 3/4 loyang way junction |  | Lane closed for sppg pipe laying
Thu (19/10) | 19 Oct 2023 | BP6 |  | Ard 1.5m managed to be extracted. Balance 1.5m to remove
Thu (19/10) | 19 Oct 2023 | P31 |  | Starhub plan for pipe laying today, 12m (6way)
Thu (19/10) | 19 Oct 2023 | DR2 |  | Strain gauge installation ongoing by RG
Thu (19/10) | 19 Oct 2023 | DR2 |  | Continue waler joint welding. Balance 2 nos diagonal struts and 1 nos waler beam to be installed
Thu (19/10) | 19 Oct 2023 | DW23 |  | Trench to be further excavated as there’s a 66kV alignment running here. Once cable exposed, SPPG will come down for spiking. Tentatively target next week for spiking
Thu (19/10) | 19 Oct 2023 | P25 |  | WG continue excavation for power duct cable laying
Thu (19/10) | 19 Oct 2023 | Mh5-2 casting completed at 23 |  | 30 hrs
Thu (19/10) | 19 Oct 2023 | ST94 |  | 3rd bite trenching in progress
Thu (19/10) | 19 Oct 2023 | Zone 3/4 loyang way junction |  | Sppg pipe laid 7m
Thu (19/10) | 19 Oct 2023 | ST94 |  | U-clip torque test inspection for all 6 cages
Thu (19/10) | 19 Oct 2023 | Zone 3 ABH104 |  | In progress, 24m
Thu (19/10) | 19 Oct 2023 | Zone 4 |  | ABH107 in progress, 36m
Thu (19/10) | 19 Oct 2023 | P23 |  | Krishco continue water pipe laying works. Roughly 25m completed as of now
Thu (19/10) | 19 Oct 2023 | Zone 4 |  | ABH110 in progress, 29m
Thu (19/10) | 19 Oct 2023 | MH2-3 |  | Removal of slurry pipes in progress
Thu (19/10) | 19 Oct 2023 | P19 |  | Premix hacking in progress for bored piling trial trench works
Thu (19/10) | 19 Oct 2023 | Zone 4 |  | ECS continue hoarding frame installation
Thu (19/10) | 19 Oct 2023 | Zone 4 |  | 2nos TT in progress
Thu (19/10) | 19 Oct 2023 | Zone 3 |  | Continue sewer twin pipe laying
Thu (19/10) | 19 Oct 2023 | DR2 |  | Strain gauge & 1nos waler beam installed. Pending 2nos diagonal struts installation. Today also plan for concrete packing
Thu (19/10) | 19 Oct 2023 | MH2-1 |  | Removing shoring for 5th layer excavation
Thu (19/10) | 19 Oct 2023 | ST222A |  | First bite excavation in progress
Thu (19/10) | 19 Oct 2023 | N1-2 |  | Boring completed. Now preparing for rebar cage lowering
Thu (19/10) | 19 Oct 2023 | N6 |  | HSL continue hacking works for 3rd pile head
Thu (19/10) | 19 Oct 2023 | N4 |  | Preboring works for ERSS installation
Thu (19/10) | 19 Oct 2023 | BP6 |  | Continue soil removal using grabber
Thu (19/10) | 19 Oct 2023 | Zone 3/4 loyang way junction |  | Work completed
Thu (19/10) | 19 Oct 2023 | P25 |  | Shoring installation and manual clearing of soil prior to power duct laying
Thu (19/10) | 19 Oct 2023 | N6 |  | Current status of pile hacking. Tmr to continue
Thu (19/10) | 19 Oct 2023 | N1-2 |  | Preparing for casting
Thu (19/10) | 19 Oct 2023 | DR2 |  | Continue waler joint welding works
Thu (19/10) | 19 Oct 2023 | North ramp N1-2 |  | Casting completed, 38m3
Thu (19/10) | 19 Oct 2023 | Exit 2 |  | To continue TT for next section of dwall panels. TT done for DW57-60
Thu (19/10) | 19 Oct 2023 | BP6 |  | Inner casing removal ongoing prior to extracting remaining BP
Fri (20/10) | 20 Oct 2023 | BP02 |  | Today to shift rotary here from BP06
Fri (20/10) | 20 Oct 2023 | DR2 |  | Installation of balance waler at the bent side. Welding works to continue
Fri (20/10) | 20 Oct 2023 | DR2 inclined area |  | Dismantling of railing to start excavation to FEL
Fri (20/10) | 20 Oct 2023 | ST90 |  | 1st bite excavation at 19.92m
Fri (20/10) | 20 Oct 2023 | ST94 |  | Casting in progress. Running volume 105.5/230 m3
Fri (20/10) | 20 Oct 2023 | ABH103 |  | Drilling at 26m
Fri (20/10) | 20 Oct 2023 | BH104 |  | Drilling at 30m depth
Fri (20/10) | 20 Oct 2023 | Zone 4 P46-1 |  | TT on going, found HV and sptel cable
Fri (20/10) | 20 Oct 2023 | Zone 4 |  | Hoarding frame installation towards TPE
Fri (20/10) | 20 Oct 2023 | N6 |  | Last pile hacking. Balance trimming
Fri (20/10) | 20 Oct 2023 | MH2-5 |  | Pulling of sewer pipe continue for 4th pipe. 3/9 completed
Fri (20/10) | 20 Oct 2023 | Zone 4 |  | WHDA replacing EL water barrier with WHDA water barrier at PC crossing
Fri (20/10) | 20 Oct 2023 | Zone 4 |  | ABH110 current level ard 36m
Fri (20/10) | 20 Oct 2023 | Zone 4 |  | Utility signage in progress
Fri (20/10) | 20 Oct 2023 | Zone 4 |  | ABH-107 at 36m. ABH-109 & ABH-106 trial trench in progress
Sun (22/10) | 22 Oct 2023 | Exit 2 |  | BC cutter maintenance, changing from 1.2m to 0.80m
Sun (22/10) | 22 Oct 2023 | ST90 |  | Tremie pipes lowering. Est to cast at 11pm
Sun (22/10) | 22 Oct 2023 | Zone 3/4 loyang way Junction |  | Lucky joint here for Sptel pipe laying
Mon (23/10) | 23 Oct 2023 | ST90 |  | Casting continue, running volume 105.5/230 m3
Mon (23/10) | 23 Oct 2023 | ST90 |  | Casting status, 156.5/230 m3
Mon (23/10) | 23 Oct 2023 | ST90 |  | Casting of the last 2 loads, total 258.5 m3
Mon (23/10) | 23 Oct 2023 | N4 |  | Preboring completed. To start installation for solider pile now
Mon (23/10) | 23 Oct 2023 | N6 |  | Lean concrete for base slab in progress
Mon (23/10) | 23 Oct 2023 | N3 |  | Formwork dismantling for pilecap
Mon (23/10) | 23 Oct 2023 | N2 |  | Debris cleaning from pile cap prior to backfilling works till pile cap level
Mon (23/10) | 23 Oct 2023 | MH5-2 |  | Setting up works for pipe jacking in progress
Mon (23/10) | 23 Oct 2023 | MH2-8 |  | 2nd layer half casting
Mon (23/10) | 23 Oct 2023 | Gate 5 |  | Excavation on going for SPPG open pit for mandrel test
Mon (23/10) | 23 Oct 2023 | MH2-1 |  | 5th layer half casting in progress
Mon (23/10) | 23 Oct 2023 | Zone 2 P24 |  | Laying of bentonite pipe from substation to exit 3 silo tank area, temporary desander to set up
Mon (23/10) | 23 Oct 2023 | BP02 |  | Dismantling of attachments at the rotary. Tomorrow to set up at BP04
Mon (23/10) | 23 Oct 2023 | Zone 3/4 loyang way junction |  | Lane closed by lucky joint for sptel pipe laying
Tue (24/10) | 24 Oct 2023 | ABH102 |  | In progress, 10m
Tue (24/10) | 24 Oct 2023 | Zone 3 Vent Shaft area |  | Continue sewer pipe laying
Tue (24/10) | 24 Oct 2023 | BP2 |  | LSS backfilling in progress
Tue (24/10) | 24 Oct 2023 | P27-28 |  | Starhub pipe laying works
Tue (24/10) | 24 Oct 2023 | Near MH2-8 |  | Excavation ongoing for SPPG pulling pit
Tue (24/10) | 24 Oct 2023 | MH2-8 |  | 2nd layer partially cast. Now preparing vent fan and works area. Today plan to continue balance 2nd layer portion
Tue (24/10) | 24 Oct 2023 | DW36 |  | BC cutter extracted at trench area
Tue (24/10) | 24 Oct 2023 | Gate 5 loyang lane |  | SPPG mandrel test done, 1 pipe choked, rectification on going
Tue (24/10) | 24 Oct 2023 | P20-22 |  | Bentonite pipe laying in progress
Tue (24/10) | 24 Oct 2023 | DW36 |  | Pre-excavation in progress
Tue (24/10) | 24 Oct 2023 | BP2 |  | LSS backfilling completed. Casing removal ongoing. Thereafter rotary machine will be shifted to BP4
Tue (24/10) | 24 Oct 2023 | MH5-2 |  | Installation of formwork in progress for gantry crane base
Tue (24/10) | 24 Oct 2023 | DR2 |  | Manually clearing soil along P37 area and pending concrete packing at P36 area
Tue (24/10) | 24 Oct 2023 | BH65 |  | In progress, 30m
Tue (24/10) | 24 Oct 2023 | ABH102 |  | First permeability test in progress
Tue (24/10) | 24 Oct 2023 | ABH100 |  | Manual TT ongoing
Tue (24/10) | 24 Oct 2023 | N6 |  | Continue trimming works for BP
Tue (24/10) | 24 Oct 2023 | N4 |  | Continue soldier pile installation works
Tue (24/10) | 24 Oct 2023 | N3 |  | Removing of tie rod in progress
Tue (24/10) | 24 Oct 2023 | Gate 5 |  | SPPG madrel test completed. Backfilling of pit in progress
Tue (24/10) | 24 Oct 2023 | Zone 3/4 loyang way junction |  | Sptel work completed. Laid 8m
Tue (24/10) | 24 Oct 2023 | N4 |  | Continue ERSS installation till 6:30pm
Tue (24/10) | 24 Oct 2023 | DW36 |  | First bite excavation in progress, 10m
Tue (24/10) | 24 Oct 2023 | DR2 |  | Concrete packing completed. Housekeeping ongoing
Tue (24/10) | 24 Oct 2023 | ST95 |  | First bite excavation in progress
Tue (24/10) | 24 Oct 2023 | Taiyo BP4 |  | Inner casing installation in progress
Tue (24/10) | 24 Oct 2023 | Gate 5 |  | Tonight to do mandrell test from loyang lane to loyang Ave junction
Tue (24/10) | 24 Oct 2023 | MH2-6 |  | Perm MH structure rebar works and dewatering. LCH will work till 10pm
Tue (24/10) | 24 Oct 2023 | BP02 |  | Backfilling and soil levelling, BP04:, Inner casing installation: 5.4m/8.2m
Tue (24/10) | 24 Oct 2023 | BP2 |  | Casing installation in progress. Plan for LSS backfilled today
Tue (24/10) | 24 Oct 2023 | ST95 |  | 1st bite trenching in progress
Tue (24/10) | 24 Oct 2023 | DR2 |  | Continue waler/strut joint welding. Today plan for concrete packing
Tue (24/10) | 24 Oct 2023 | Zone 3/4 loyang way junction |  | Lane close for singtel pipe laying preparation works
Tue (24/10) | 24 Oct 2023 | Near exit 1 |  | BC cutter SC40 rig assembly in progress
Tue (24/10) | 24 Oct 2023 | Zone 3 BH65 |  | In progress, 26m
Wed (25/10) | 25 Oct 2023 | MH2-8 |  | 2md layer half casting completed
Wed (25/10) | 25 Oct 2023 | DW36 |  | 1st bite completed. Now preparing to do internal koden test
Wed (25/10) | 25 Oct 2023 | Noise reading at LVC blk 222 |  | No breached alert after 10pm
Wed (25/10) | 25 Oct 2023 | DW36 |  | Internal koden test
Wed (25/10) | 25 Oct 2023 | ST95 |  | 1st bite trenching continue at 22.3m depth
Wed (25/10) | 25 Oct 2023 | Zone 3 |  | WG pumping out water before continuing excavation & shoring installation for power duct pipe laying
Wed (25/10) | 25 Oct 2023 | Zone 3 |  | Starhub continue excavation for pipe laying
Wed (25/10) | 25 Oct 2023 | BP4 |  | Area preparation for rotary machine set-up
Wed (25/10) | 25 Oct 2023 | BH65 |  | In progress, 36m
Wed (25/10) | 25 Oct 2023 | ABH102 |  | In progress, 20m
Wed (25/10) | 25 Oct 2023 | Zone 3 BH90 |  | Manual trial trench in progress
Wed (25/10) | 25 Oct 2023 | Zone 3 |  | Continue sewer pipe laying
Wed (25/10) | 25 Oct 2023 | ST95 |  | Excavation temporarily stopped for cutter teeth wheel change. Current first bite depth at 26.8m
Wed (25/10) | 25 Oct 2023 | DW36 |  | Trenching temporarily stopped for mud hose rectification works
Wed (25/10) | 25 Oct 2023 | Zone 3 |  | WG excavation for power duct pulling pit
Wed (25/10) | 25 Oct 2023 | Zone 2 | P19 area | HSL materials mobilisation and setting up works
Wed (25/10) | 25 Oct 2023 | N6 |  | Pilecap rebar works in progress
Wed (25/10) | 25 Oct 2023 | N4 |  | Installation of lagging plates ongoing
Wed (25/10) | 25 Oct 2023 | N3 |  | No activity
Wed (25/10) | 25 Oct 2023 | N2 column |  | Current status for rebar works for 1st stage
Wed (25/10) | 25 Oct 2023 | N1 |  | Area preparation for LE to start TT works
Wed (25/10) | 25 Oct 2023 | MH5-2 |  | Pipe jacking setting up works in progress
Wed (25/10) | 25 Oct 2023 | P23 |  | Bentonite pipes laying to exit 3 in progress
Wed (25/10) | 25 Oct 2023 | MH2-6 |  | Base backfilling ongoing
Wed (25/10) | 25 Oct 2023 | N4 |  | Continue lagging plate installation
Wed (25/10) | 25 Oct 2023 | N6 |  | Pilecap rebar works in progress
Wed (25/10) | 25 Oct 2023 | ST95 |  | Cutter wheel teeth replacement. Current depth 26.6m
Wed (25/10) | 25 Oct 2023 | P23 |  | Bentonite pipe installation in progress
Wed (25/10) | 25 Oct 2023 | BP4 |  | Outer casing installation in progress
Wed (25/10) | 25 Oct 2023 | DR2 |  | No activity
Wed (25/10) | 25 Oct 2023 | ST95 |  | Excavation resume
Wed (25/10) | 25 Oct 2023 | DW36 |  | Excavation resume
Wed (25/10) | 25 Oct 2023 | MH2-8 |  | 2nd layer half formwork closing. Concrete order for casting
Wed (25/10) | 25 Oct 2023 | DW36 |  | 1st bite trenching in progress, depth 30m. Balance 1.5m
Wed (25/10) | 25 Oct 2023 | N6 status |  | No more activity, B1 and B2 50% completed
Wed (25/10) | 25 Oct 2023 | MH5-2 |  | No more activity
Wed (25/10) | 25 Oct 2023 | BP04 |  | Inner casing installation: 5.5m/8.2m, Outer casing: 5.8m/6.9m, Inner casing attachment installation in progress. Night shift team to continue boring of inner casing
Wed (25/10) | 25 Oct 2023 | Zone 3/4 loyang way junction |  | Lane closed for singtel pipe laying
Thu (26/10) | 26 Oct 2023 | MH2-6 |  | MH structure casting in progress
Thu (26/10) | 26 Oct 2023 | ST95 |  | BC cutter teeth replacement. Current depth 27.5m
Thu (26/10) | 26 Oct 2023 | MH2-8 |  | Excavation for 2nd layer caisson
Thu (26/10) | 26 Oct 2023 | Zone 4 loyang way |  | Singtel pipe laid and casting done, total 12m
Thu (26/10) | 26 Oct 2023 | MH2-1 |  | Excavation for 5th layer 2nd part casting. Tonight plan to cast 600mm
Thu (26/10) | 26 Oct 2023 | DW36 |  | Installation of ibeam on going
Thu (26/10) | 26 Oct 2023 | ST95 |  | Main plate welding in progress
Thu (26/10) | 26 Oct 2023 | Zone 4 loyang way junction |  | Singtel pipe laying completed. Area reinstated
Thu (26/10) | 26 Oct 2023 | MH2-6 |  | MH structure rebar works in progress. Plan for inspection later
Thu (26/10) | 26 Oct 2023 | N6 |  | Works done for the day. To resume tmr
Thu (26/10) | 26 Oct 2023 | DW36 |  | 2nd bite cleaning in progress
Thu (26/10) | 26 Oct 2023 | BP4 |  | Continue inner casing installation, 8m. Dayshift team will complete the works tonight. Tmr plan for pile extraction
Thu (26/10) | 26 Oct 2023 | ST95 |  | Flab welding ongoing. First bite current depth at 30m
Thu (26/10) | 26 Oct 2023 | P26 |  | WG continue excavation for SPPG pipe laying
Fri (27/10) | 27 Oct 2023 | Zone 1 |  | Enghup contractor here to do cable pulling from existing controller box to the new controller box at NLL. 16 Nov to shift controller box
Fri (27/10) | 27 Oct 2023 | MH2-9 |  | 2nd ring casting in progress
Fri (27/10) | 27 Oct 2023 | N1 |  | Today to start TT
Fri (27/10) | 27 Oct 2023 | N4 |  | Excavation to W1 layer in progress, today to complete
Fri (27/10) | 27 Oct 2023 | PMH8 |  | Installation of cable brackets. PMh9-12 completed
Fri (27/10) | 27 Oct 2023 | N6 |  | T2 installation on going
Fri (27/10) | 27 Oct 2023 | DW36 |  | Hanging bar u-clip inspection done
Fri (27/10) | 27 Oct 2023 | DW36 |  | Rebar installation ongoing, 5/6nos
Fri (27/10) | 27 Oct 2023 | MH2-9 |  | Manual excavation in progress for rebar installation
Fri (27/10) | 27 Oct 2023 | MH2-8 |  | Preparing to resume excavation
Fri (27/10) | 27 Oct 2023 | Zone 2 |  | HSL continue POB pile no.10 crushing work
Fri (27/10) | 27 Oct 2023 | N6 |  | Pilecap rebars works in progress
Fri (27/10) | 27 Oct 2023 | P26 |  | Shoring installation in progress
Fri (27/10) | 27 Oct 2023 | N4 |  | Excavation to S1 level completed. Now access making before LE continue with waler installation
Fri (27/10) | 27 Oct 2023 | N3 |  | No activity
Fri (27/10) | 27 Oct 2023 | N2 |  | No activity
Fri (27/10) | 27 Oct 2023 | N1 |  | LE trial trench works ongoing
Fri (27/10) | 27 Oct 2023 | ST95 |  | Trimming in progress
Fri (27/10) | 27 Oct 2023 | Zone 1 |  | Enghup contractor cable pulling from existing controller box to the new controller box at NLL
Fri (27/10) | 27 Oct 2023 | MH2-6 |  | Casting completed 0024hrs
Fri (27/10) | 27 Oct 2023 | DW36 |  | Re-cleaning ongoing prior to final koden test
Fri (27/10) | 27 Oct 2023 | MH2-1 |  | 5th layer (2nd part) casting in progress
Fri (27/10) | 27 Oct 2023 | MH2-1 |  | Casting completed 0616hrs
Fri (27/10) | 27 Oct 2023 | N3 |  | Concrete plug casting in progress
Fri (27/10) | 27 Oct 2023 | N6 |  | Access installation ongoing by WH. Rebar works done for the day
Fri (27/10) | 27 Oct 2023 | DW36 |  | Rebar cage installation ongoing — 4/6nos
Fri (27/10) | 27 Oct 2023 | DR2 |  | Rebar works ongoing at P37 area. Team working till 10pm. Tmr plan for slab casting
Fri (27/10) | 27 Oct 2023 | ST95 |  | Continue first bite trimming, 32m
Fri (27/10) | 27 Oct 2023 | Zone 4 |  | Tonight plan for Singtel pipe laying. Target 12m
Fri (27/10) | 27 Oct 2023 | MH2-8 |  | Formwork dismantling
Fri (27/10) | 27 Oct 2023 | Taiyo BP4 |  | Tmr plan to mob out the extracted pile from this afternoon and continue removing the balance pile (2m)
Fri (27/10) | 27 Oct 2023 | Loyang Lane | outside Gate 5 | WG manually clearing area for SPPG mandrel test
Sat (28/10) | 28 Oct 2023 | DW23 |  | Preparation for guidewall works
Sat (28/10) | 28 Oct 2023 | Zone 4 |  | Singtel pipes laid, 12m
Sat (28/10) | 28 Oct 2023 | DW36 |  | 6/6nos rebar cage lowered. Hanging bar installation in progress
Sat (28/10) | 28 Oct 2023 | DW36 |  | Casting started
Sat (28/10) | 28 Oct 2023 | MH2-6 |  | Backfilling and levelling ongoing
Sat (28/10) | 28 Oct 2023 | North ramp N6 |  | Works done for the day
Sat (28/10) | 28 Oct 2023 | MH5-2 |  | Thrust block casting completed. Team has left the site
Sat (28/10) | 28 Oct 2023 | P25 |  | Continue manual clearing of soil for Singtel pipe laying
Sat (28/10) | 28 Oct 2023 | MH2-1 |  | Preparation for first part for 6th layer rebar works thereafter plan for casting
Sat (28/10) | 28 Oct 2023 | BP4 |  | LSS backfiiling in progress
Sat (28/10) | 28 Oct 2023 | DR2 |  | Base was cast (P37 area)
Sat (28/10) | 28 Oct 2023 | ST95 |  | 2nd bite excavation in progress, 33m
Sun (29/10) | 29 Oct 2023 | MH2-6 |  | Soil backfilling works
Sun (29/10) | 29 Oct 2023 | Bet. MH2-5 & MH2-6 |  | MoGuan excavation works in progress for stabhub pipe laying
Sun (29/10) | 29 Oct 2023 | MH2-3 |  | Debris clearing ongoing
Sun (29/10) | 29 Oct 2023 | N6 pilecap |  | Rebar & formworks installation
Sun (29/10) | 29 Oct 2023 | N4 |  | No activity
Sun (29/10) | 29 Oct 2023 | N3 |  | No activity
Sun (29/10) | 29 Oct 2023 | N2 |  | No activity
Sun (29/10) | 29 Oct 2023 | North Ramp bet. P8 & P7 |  | Excavation for ECM extension ongoing
Sun (29/10) | 29 Oct 2023 | Zone 1 |  | No activity
Sun (29/10) | 29 Oct 2023 | MH5-2 |  | Pipe jacking setting up works
Sun (29/10) | 29 Oct 2023 | DW23 |  | Guidewall formwork installation in progress. Casting to be done today
Sun (29/10) | 29 Oct 2023 | Zone 3 |  | Preparation of working platform for preboring works at JTC area
Sun (29/10) | 29 Oct 2023 | ST-095 |  | Chiseling work completed. Now preparation for Desanding and cleaning works
Sun (29/10) | 29 Oct 2023 | Zone 4 |  | Materials shifting works
Sun (29/10) | 29 Oct 2023 | MH2-1 |  | First part casting completed
Sun (29/10) | 29 Oct 2023 | P25 |  | Singtel pipe laying in progress, 12m
Sun (29/10) | 29 Oct 2023 | DW23 |  | Guidewall rebar works ongoing
Sun (29/10) | 29 Oct 2023 | DW23 |  | Guidewall formwork completed. Now pending concrete to arrive for casting
Sun (29/10) | 29 Oct 2023 | ST-52 |  | Trial trench works
Sun (29/10) | 29 Oct 2023 | DW61 |  | Guidewall Formwork & BRC installation
Sun (29/10) | 29 Oct 2023 | ST95 |  | 2nd bite cleaning in progress
Sun (29/10) | 29 Oct 2023 | ST95 |  | Rebar cage U clip checking ongoing
Sun (29/10) | 29 Oct 2023 | Zone 4 |  | Singtel pipe laid — 9m (18way) + 7.5m(12way)
Sun (29/10) | 29 Oct 2023 | Zone 4 |  | Materials shifting and surveying works
Sun (29/10) | 29 Oct 2023 | DR2 |  | 2nd bay slab cast completed
Sun (29/10) | 29 Oct 2023 | DW23 |  | Guidewall casting ongoing
Sun (29/10) | 29 Oct 2023 | MH2-6 |  | Materials clearing in progress. Tmr to continue brc works
Sun (29/10) | 29 Oct 2023 | N6 pilecap |  | Continue Rebar & formworks installation
Sun (29/10) | 29 Oct 2023 | North Ramp bet. P8 & P7 |  | Excavation for ECM extension
Sun (29/10) | 29 Oct 2023 | MH5-2 |  | Ring wall hacking works
Mon (30/10) | 30 Oct 2023 | DR2 |  | Preparing to continue excavation (P36 area)
Mon (30/10) | 30 Oct 2023 | Zone 4 ABH108 |  | Coring in progress, 29m
Mon (30/10) | 30 Oct 2023 | P39-P40 |  | Wee Guan excavation for Power duct laying. Tonight plan around 9 to 12m
Mon (30/10) | 30 Oct 2023 | Zone 4 ABH111 |  | In progress, 42.6m
Mon (30/10) | 30 Oct 2023 | Loyang ave P25 |  | Backfilling works for singtel pipe laid. 8.5m
Mon (30/10) | 30 Oct 2023 | P20-P21 |  | Excavation work for starhub pipe laying
Mon (30/10) | 30 Oct 2023 | P48 |  | Preparation to continue trial trench at this location
Mon (30/10) | 30 Oct 2023 | Zone 4 ABH116 |  | Trial trench started
Mon (30/10) | 30 Oct 2023 | Zone 4 |  | No lane closures today
Mon (30/10) | 30 Oct 2023 | ST89A |  | First bite excavation in progress
Mon (30/10) | 30 Oct 2023 | ST95 |  | Cage A fully lowered. Now ongoing hanging bar installation for Cage B
Mon (30/10) | 30 Oct 2023 | N6 |  | Shearlinks installation in progress. Plan to complete today
Mon (30/10) | 30 Oct 2023 | N4 |  | Waler beam installation started. Today to complete fitting
Mon (30/10) | 30 Oct 2023 | PMH5 |  | Civil bracket installation on going. 6-12 completed
Mon (30/10) | 30 Oct 2023 | Zone 3 |  | Continue sewer pipe installation
Mon (30/10) | 30 Oct 2023 | Taiyo BP3 |  | Continue machine setting up
Mon (30/10) | 30 Oct 2023 | MH2-8 |  | Continue excavation for 3rd layer second part
Mon (30/10) | 30 Oct 2023 | MH5-2 |  | No activity
Mon (30/10) | 30 Oct 2023 | Zone 1 |  | 300mm water pipe pressure test. Hold at 12 bar
Mon (30/10) | 30 Oct 2023 | Zone 1 |  | Eng hup here replacing traffic light pole
Mon (30/10) | 30 Oct 2023 | ABH108 |  | Drilling in progress
Mon (30/10) | 30 Oct 2023 | Zone 4 ABH112 |  | Manual trial trench started
Mon (30/10) | 30 Oct 2023 | MH5-2 |  | Entry pipe opening hacking in progress
Mon (30/10) | 30 Oct 2023 | P48 |  | Trial trench and shoring installation ongoing
Mon (30/10) | 30 Oct 2023 | ST95 |  | Casting in progress, 87/245m3
Mon (30/10) | 30 Oct 2023 | ST89A |  | First bite trenching in progress, 29.5m
Mon (30/10) | 30 Oct 2023 | DR2 |  | Excavation in progress
Mon (30/10) | 30 Oct 2023 | MH2-8 |  | Continue excavation for 3rd layer
Mon (30/10) | 30 Oct 2023 | P20 |  | 1 cage on site. Tomorrow they can start boring
Mon (30/10) | 30 Oct 2023 | BP3 |  | Inner casing installation in progress
Mon (30/10) | 30 Oct 2023 | MH2-8 |  | Started BRC installation. Tonight to cast
Mon (30/10) | 30 Oct 2023 | P26 |  | Continue excavation for power duct laying
Mon (30/10) | 30 Oct 2023 | ST140 |  | Guidewall formwork dismantling ongoing
Mon (30/10) | 30 Oct 2023 | ST95 |  | Hanging bar installation in progress
Tue (31/10) | 31 Oct 2023 | Zone 3 |  | Continue sewer pipe installation
Tue (31/10) | 31 Oct 2023 | ABH100 |  | In progress, 12m
Tue (31/10) | 31 Oct 2023 | Zone 3 BC Cutter SC40 |  | Frame installation for noise barrier panels
Tue (31/10) | 31 Oct 2023 | N6 |  | Installing level peg for casting
Tue (31/10) | 31 Oct 2023 | N4 |  | Waler welding works. Tomorrow MPI and packing concrete casting
Tue (31/10) | 31 Oct 2023 | N1 |  | Setting out for ERSS alignment, LE will start here first
Tue (31/10) | 31 Oct 2023 | ST89A |  | Continue trimming
Tue (31/10) | 31 Oct 2023 | Zone 4 P48 |  | Trial trench completed. Found water pipe at 2m depth
Tue (31/10) | 31 Oct 2023 | DW22 |  | Pre-excavation
Tue (31/10) | 31 Oct 2023 | DW22 |  | First bite excavation in progress
Tue (31/10) | 31 Oct 2023 | DR2 |  | Continue base rebar installation (P36 area)
Tue (31/10) | 31 Oct 2023 | ABH108 |  | Current depth 47m
Tue (31/10) | 31 Oct 2023 | Zone 4 P48 |  | Continue trial trench
Tue (31/10) | 31 Oct 2023 | Zone 4 |  | Pipe testing by Singtel
Tue (31/10) | 31 Oct 2023 | ABH113 |  | In progress, 4m
Tue (31/10) | 31 Oct 2023 | MH2-3 |  | Setting up works in progress for pipe jacking towards MH2-1
Tue (31/10) | 31 Oct 2023 | ABH114 |  | Rig setting up ongoing
Tue (31/10) | 31 Oct 2023 | MH2-4 |  | Cleaning works in progress prior to rebar lowering
Tue (31/10) | 31 Oct 2023 | Zone 4 |  | WH is replacing concrete barriers with water barriers for Singtel works
Tue (31/10) | 31 Oct 2023 | Zone 4 |  | Hoarding panels near sewer works to be replaced with green fencing, approx 50m for PUB pumping main CCTV
Tue (31/10) | 31 Oct 2023 | Zone 2 |  | HSL boring rig for zone 3 mobilization works
Tue (31/10) | 31 Oct 2023 | Zone 3 |  | Water pipes fixing ongoing
Tue (31/10) | 31 Oct 2023 | N6 |  | Pilecap inspection completed. Pending concrete truck to arrive for casting
Tue (31/10) | 31 Oct 2023 | MH5-2 |  | Pipe jacking setting up works. Target to complete tmr
Tue (31/10) | 31 Oct 2023 | North ramp, N6 |  | Casting in progress, 156/178m3
Tue (31/10) | 31 Oct 2023 | Loyang ave P25-P24 |  | SPPG mandrel test
Tue (31/10) | 31 Oct 2023 | MH2-1 |  | Preparation for 6th layer second part
Tue (31/10) | 31 Oct 2023 | P32 |  | Trial trench for ST51-54 completed. Today plan for guidewall excavation & continue trial trench for ST55 onwards
Wed (01/11) | 01 Nov 2023 | Zone 4 ABH116 |  | Preparing to start hand auger
Wed (01/11) | 01 Nov 2023 | P48 |  | Continue trial trench for P48-BP-TT-04-1
Wed (01/11) | 01 Nov 2023 | P48 |  | Continue trial trench and shoring installation for P48-BP-TT-04A
Wed (01/11) | 01 Nov 2023 | Zone 4 |  | Singtel works ongoing within the site
Wed (01/11) | 01 Nov 2023 | Zone 4 |  | Green fencing installation near sewer works. Lane closure at first lane Loyang Ave by WH
Wed (01/11) | 01 Nov 2023 | MH5-2 |  | Slurry pipe connection on going. TBM not yet delivered. Target to deliver and set up tomorrow. @⁨Devi⁩
Wed (01/11) | 01 Nov 2023 | BP3 |  | Continue to clear soil for balance pile removal. Yesterday managed to remove ard 5.5m
Wed (01/11) | 01 Nov 2023 | P32 |  | Guidewall formwork installation for ST53-54 in progress, plan for casting today. HSL also started mobilising their materials here
Wed (01/11) | 01 Nov 2023 | DR2 |  | Continue base rebar works
Wed (01/11) | 01 Nov 2023 | BC cutter SC40 |  | Noise barrier panel installation
Wed (01/11) | 01 Nov 2023 | Zone 3 |  | Continue pumping main pipe installation
Wed (01/11) | 01 Nov 2023 | ST89A |  | Casting ongoing. Progressive vol: 21/110m3
Wed (01/11) | 01 Nov 2023 | DR2 |  | In blue - Base slab cast, In red - Base rebar ongoing
Wed (01/11) | 01 Nov 2023 | P48-BP-TT-04A |  | Found water pipe at 2m depth
Wed (01/11) | 01 Nov 2023 | DW22 |  | Mud pump replacement on going prior to cleaning
Wed (01/11) | 01 Nov 2023 | Zone 3 pumping main today balance 2 nos pump installed |  | 4/4 pumps installed
Wed (01/11) | 01 Nov 2023 | DR2 |  | Base slab 4th panel rebar works completed. Waiting for concrete lorry
Wed (01/11) | 01 Nov 2023 | MH2-1 |  | Manual excavation in progress
Thu (02/11) | 02 Nov 2023 | DR2 |  | Night shift team here for excavation work
Thu (02/11) | 02 Nov 2023 | DR2 |  | Blue: Base slab cast, Red: Base slab casting completed today, Orange: Excavation work tonight
Thu (02/11) | 02 Nov 2023 | Loyang way junction zone 4 |  | Lane closed for SPPG pipe laying
Thu (02/11) | 02 Nov 2023 | Zone 4 |  | 2nd team here to do excavation for open pit
Thu (02/11) | 02 Nov 2023 | DR2 |  | Yesterday cast about 12m length base. Today plan to continue for next portion base rebar and cast, and excavation
Thu (02/11) | 02 Nov 2023 | DW22 |  | All cages safely lowered
Thu (02/11) | 02 Nov 2023 | Zone 3 |  | Pumping main pipes installed up till near exit 1
Thu (02/11) | 02 Nov 2023 | Zone 4 |  | Lane closure by other contractor along Loyang Ave towards CV
Thu (02/11) | 02 Nov 2023 | Zone 4 ABH116 |  | Preparing to start Si
Thu (02/11) | 02 Nov 2023 | ABH117 |  | Manual trial trench ongoing
Thu (02/11) | 02 Nov 2023 | P48-04a-1 |  | TT in progress. Found water pipe, PFO and one unknown pipe
Thu (02/11) | 02 Nov 2023 | ABH113 |  | In progress, 15m
Thu (02/11) | 02 Nov 2023 | ABH114 |  | In progress, 14m
Thu (02/11) | 02 Nov 2023 | Zone 4 |  | Singtel pipe works. Yesterday laid 36m. Lane closure along LA towards LW under direct Singtel
Thu (02/11) | 02 Nov 2023 | P20-5 |  | Casting completed
Thu (02/11) | 02 Nov 2023 | DR2 |  | Blue: Base slab cast, Red: Base rebar ongoing
Thu (02/11) | 02 Nov 2023 | Zone 2 |  | 2/4nos silo installed
Thu (02/11) | 02 Nov 2023 | DW22 |  | Rebar cage installation in progress, 4/6nos
Thu (02/11) | 02 Nov 2023 | Zone 3 |  | SPPG mandrel test ongoing
Thu (02/11) | 02 Nov 2023 | MH2-1 |  | No activity
Thu (02/11) | 02 Nov 2023 | JTC blk 4 |  | HSL mobilising materials
Thu (02/11) | 02 Nov 2023 | DR2 |  | Continue base rebar works
Thu (02/11) | 02 Nov 2023 | ABH100 |  | In progress, 33m
Thu (02/11) | 02 Nov 2023 | P49 |  | Preparation ongoing to start trial trench here
Thu (02/11) | 02 Nov 2023 | ABH114 |  | In progress, 19m
Thu (02/11) | 02 Nov 2023 | Zone 4 |  | Gate frame installation in progress
Thu (02/11) | 02 Nov 2023 | ABH113 |  | In progress, 19.5m
Thu (02/11) | 02 Nov 2023 | N6 |  | No activity
Thu (02/11) | 02 Nov 2023 | P20-5 |  | Rebar cage installation completed. Concrete coming ard 7:30pm
Thu (02/11) | 02 Nov 2023 | MH2-4 |  | Wall rebar installation in progress. Team working till 7pm
Thu (02/11) | 02 Nov 2023 | BP3 |  | Continue grabbing works
Thu (02/11) | 02 Nov 2023 | JTC blk 4 |  | ST58 trial trench
Thu (02/11) | 02 Nov 2023 | DW22 |  | Rebar cage installation in progress, 5/6nos
Thu (02/11) | 02 Nov 2023 | MH2-7 |  | Setting up of slurry tank for pipe jacking works towards MH2-8
Thu (02/11) | 02 Nov 2023 | DW22 |  | Lapping for the last cage. 6/6
Thu (02/11) | 02 Nov 2023 | P20-5 |  | Casting started
Thu (02/11) | 02 Nov 2023 | P20-P21 |  | Lucky joint here tonight for M1 pipe laying
Thu (02/11) | 02 Nov 2023 | MH2-1 |  | Water clearing on going. Night shift team here to continue excavation for 6th layer half
Thu (02/11) | 02 Nov 2023 | Zone 3 Taiyo Asia |  | Work stopped for the day. Now cleaning and housekeeping
Thu (02/11) | 02 Nov 2023 | ST96 |  | Guidewall formwork closing. To cast tonight
Thu (02/11) | 02 Nov 2023 | ST140 |  | Tonight to start trenching, now laying mud hose
Fri (03/11) | 03 Nov 2023 | BP3 |  | Outer casing installation ongoing before continuing grabbing works
Fri (03/11) | 03 Nov 2023 | JTC blk 4 |  | Guidewall formwork removal for ST53-54
Fri (03/11) | 03 Nov 2023 | JTC blk 4 |  | Trial trench ongoing for ST57. Today plan to construct guidewall for ST58
Fri (03/11) | 03 Nov 2023 | DR2 |  | Preparation ongoing for next section of base rebar
Fri (03/11) | 03 Nov 2023 | ST140 |  | First bite excavation in progress, 18m
Fri (03/11) | 03 Nov 2023 | P21 | Mo Guan starhub | Premix hacking and pipe laying works
Fri (03/11) | 03 Nov 2023 | Zone 3 Rig 3 |  | Continue noise barrier panel installation
Fri (03/11) | 03 Nov 2023 | ABH100 |  | Current depth at 36m. To continue till ard 45m. Now waiting for water topup
Fri (03/11) | 03 Nov 2023 | MH2-4 |  | Manhole Base rebar tying in progress
Fri (03/11) | 03 Nov 2023 | DR2 |  | Night shift to continue rebar works for slab
Fri (03/11) | 03 Nov 2023 | ST140 |  | 1st bite excavation at 33m. Cutter wheel teeth changing
Fri (03/11) | 03 Nov 2023 | P19-5 |  | HSL boring works for pile in progress
Fri (03/11) | 03 Nov 2023 | Zone 4 loyang way |  | 2 teams here for mandrel test
Fri (03/11) | 03 Nov 2023 | N6 |  | No activity
Fri (03/11) | 03 Nov 2023 | N4 |  | Acess & barricades works
Fri (03/11) | 03 Nov 2023 | N3 |  | Formwork installation for column stage 1 casting in the afternoon
Fri (03/11) | 03 Nov 2023 | N2 |  | Supports installation in progress, column stage 1 casting in afternoon
Fri (03/11) | 03 Nov 2023 | N1 |  | LE preboring works in progress
Fri (03/11) | 03 Nov 2023 | Exit 2 BH131 |  | In progress, 22m
Fri (03/11) | 03 Nov 2023 | Bet. P8-P9 north ramp |  | Trial trench works for drain demolition in progress
Fri (03/11) | 03 Nov 2023 | MH1-3 |  | Pumping main pipe installation ongoing
Fri (03/11) | 03 Nov 2023 | P25 |  | Singtel pipes laid. Pending backfilling
Fri (03/11) | 03 Nov 2023 | DW22 |  | Casting completed. Total vol: 168m3
Fri (03/11) | 03 Nov 2023 | Zone 1 |  | Preparation for lamppost shifting
Fri (03/11) | 03 Nov 2023 | Near P6 |  | Earthing installation for EA camera OG box
Fri (03/11) | 03 Nov 2023 | MH5-2 |  | Current status
Fri (03/11) | 03 Nov 2023 | DR2 |  | Blue: Base slab completed, Red: Base rebar ongoing, Yellow: Excavation ongoing
Fri (03/11) | 03 Nov 2023 | PMH-1 |  | WG Brackets installation works
Fri (03/11) | 03 Nov 2023 | P23 |  | Excavation works for bentonite pipe laying
Fri (03/11) | 03 Nov 2023 | MH2-1 |  | Rebar installation on going for 6th layer half
Fri (03/11) | 03 Nov 2023 | DR2 |  | Excavation for the night completed. No more activity observed
Fri (03/11) | 03 Nov 2023 | ST140 |  | 1st bite trenching in progress
Fri (03/11) | 03 Nov 2023 | Zone 4 loyang way |  | Open pit excavation completed
Fri (03/11) | 03 Nov 2023 | Zone 4 loyang way |  | Sppg pipe laying 14m completed
Fri (03/11) | 03 Nov 2023 | ST96 |  | Guidewall casting in progress
Fri (03/11) | 03 Nov 2023 | DW22 |  | Casting started
Fri (03/11) | 03 Nov 2023 | P21 | Mo Guan starhub | Excavation completed, now continue pipe laying works
Fri (03/11) | 03 Nov 2023 | MH2-4 |  | Manhole Base rebar tying works in progress
Fri (03/11) | 03 Nov 2023 | MH 2-3 towards MH2-1 |  | Jacking pipe entry hole hacking work ongoing
Fri (03/11) | 03 Nov 2023 | P25 |  | This pit to remain open for SPPG mandrel test. To complete all mandrel test by 8 Nov
Fri (03/11) | 03 Nov 2023 | MH2-1 |  | Dewatering ongoing. Thereafter plan for base slab works
Fri (03/11) | 03 Nov 2023 | P19-5 |  | Rebar cage installation in progress
Fri (03/11) | 03 Nov 2023 | BP3 |  | Continue installing casing prior to grabbing
Fri (03/11) | 03 Nov 2023 | Zone 3 Selarang hoarding |  | Continue next section of water pipe installation
Fri (03/11) | 03 Nov 2023 | DR2 |  | Continue excavation
Fri (03/11) | 03 Nov 2023 | ABH100 |  | Depth reached 45m. Pending termination confirmation
Fri (03/11) | 03 Nov 2023 | N4 |  | Barricades works along the waler beam
Fri (03/11) | 03 Nov 2023 | N3 |  | Propping installation ongoing for column stage 1 casting
Fri (03/11) | 03 Nov 2023 | n2 |  | Working platform installation for column stage 1 casting
Fri (03/11) | 03 Nov 2023 | Near P6 |  | Continue earthing installation for EA camera OG box
Fri (03/11) | 03 Nov 2023 | Zone 1 |  | Lamp post shifting completed
Fri (03/11) | 03 Nov 2023 | MH2-1 |  | 6th layer half casting completed
Fri (03/11) | 03 Nov 2023 | MH5-2 |  | Pipe jacking setting up works
Fri (03/11) | 03 Nov 2023 | Zone 4 loyang way |  | Work completed. Lane opened
Fri (03/11) | 03 Nov 2023 | BP3 |  | Inner casing installation in progress, 6.5m3
Fri (03/11) | 03 Nov 2023 | MH2-6 |  | Backfilling and compaction around shaft
Fri (03/11) | 03 Nov 2023 | P19-5 |  | Tremie pipe lowering down for casting
Fri (03/11) | 03 Nov 2023 | MH5-2 |  | Jacking machine set up in progress
Fri (03/11) | 03 Nov 2023 | MH2-8 |  | Resume 4th layer excavation
Fri (03/11) | 03 Nov 2023 | MH2-3 |  | Soft eyes hacking for jacking work
Fri (03/11) | 03 Nov 2023 | DW22 |  | Volume cast 136/161.5 m3. Reducing Tremie pipe length to continue casting
Fri (03/11) | 03 Nov 2023 | DW22 |  | Casting resume. Running volume 153/161.5m3
Fri (03/11) | 03 Nov 2023 | MH2-4 |  | Base slab casting completed
Fri (03/11) | 03 Nov 2023 | P19-5 |  | Just now casting completed
Fri (03/11) | 03 Nov 2023 | N4 |  | Scaffold access installation till 10pm
Fri (03/11) | 03 Nov 2023 | N3 |  | No more activity
Fri (03/11) | 03 Nov 2023 | N2 |  | Casting platform erection till 10pm. Tomorrow to cast
Fri (03/11) | 03 Nov 2023 | N1 |  | LE stopped work for the day
Fri (03/11) | 03 Nov 2023 | MH2-1 |  | Excavation for base slab till 10pm
Fri (03/11) | 03 Nov 2023 | BP03 |  | Preparation for grabbing balance pile at 2.6m
Fri (03/11) | 03 Nov 2023 | BP03 |  | Balance pile safely extracted and unloaded
Fri (03/11) | 03 Nov 2023 | MH2-6 |  | Formwork dismantling and removal works
Fri (03/11) | 03 Nov 2023 | ST58 |  | Guidewall formwork closing
Sat (04/11) | 04 Nov 2023 | MH2-1 |  | Preparation for base casting
Sat (04/11) | 04 Nov 2023 | BH-131 |  | 2nd Packer test in progress for depth at 23.98m to 28.98m
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Laying of sppg pipe above drain. 10m
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Excavation for mandrel test
Sat (04/11) | 04 Nov 2023 | Zone 3 |  | Krishco water pipe laying works
Sat (04/11) | 04 Nov 2023 | DR2 Bay 6 |  | Rebar inspection, preparation for casting
Sat (04/11) | 04 Nov 2023 | ST-140 |  | Excavation stop due to bentonite leakage repairing work, Current depth: 36.0m
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | WG to start excavation & lay 12ways for SPPG pipe laying. Target to lay 10m today
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-116 |  | SI drilling works in progress, current depth 33m
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-109 |  | Manual trial trench works in progress
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-117 |  | Manual trial trench works in progress
Sat (04/11) | 04 Nov 2023 | Zone 4 | P49-BP-TT-05-1 | Manual trial trench in progress
Sat (04/11) | 04 Nov 2023 | Zone 4 | P48-TT | Trial trench completed. Backfilling ongoing
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-113 |  | SI drilling works in progress, current depth 36m
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-114 |  | SI drilling works in progress, current depth 40m
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | SKK contractor mobilization works for SingTel submarine HDD pipe laying
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Fiber Reach contractor SingTel submarine pipe laying works
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Washing bay excavation in progress by WH team
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Dipcie Singtel 4-ways pipe laying inside SIA engineering
Sat (04/11) | 04 Nov 2023 | DR2 |  | Last panel starter bar planting
Sat (04/11) | 04 Nov 2023 | N6 |  | No activity
Sat (04/11) | 04 Nov 2023 | N4 |  | KTC started excavation to FEL
Sat (04/11) | 04 Nov 2023 | N3 |  | Pending concrete truck to arrive to cast stage 1 column
Sat (04/11) | 04 Nov 2023 | N2 |  | Working platform installation works, today to cast
Sat (04/11) | 04 Nov 2023 | N1 |  | Preboring works ongoing
Sat (04/11) | 04 Nov 2023 | Zone 1 |  | No activity
Sat (04/11) | 04 Nov 2023 | MH5-2 |  | Afternoon will start pipe jacking works
Sat (04/11) | 04 Nov 2023 | P20-4 |  | HSL boring work ongoing
Sat (04/11) | 04 Nov 2023 | P23 |  | Excavation works for bentonite pipe laying
Sat (04/11) | 04 Nov 2023 | MH 2-4 |  | Permanent manhole base curing works
Sat (04/11) | 04 Nov 2023 | MH 2-3 |  | Current status for entry hole hacking towards MH2-1
Sat (04/11) | 04 Nov 2023 | MH2-6 |  | Backfilling works for manhole
Sat (04/11) | 04 Nov 2023 | Exit 2 temporary desander |  | Bracket installation for NB installation
Sat (04/11) | 04 Nov 2023 | ST58 guidewall |  | Hi-rib installation on going, dayshift to cast
Sat (04/11) | 04 Nov 2023 | DR2 |  | 6th Bay slab status, bottom bar planting completed
Sat (04/11) | 04 Nov 2023 | ST140 |  | 1st bite trenching at 34.4m depth
Sat (04/11) | 04 Nov 2023 | Zone 4 loyang way |  | SPPG madrel test on going
Sat (04/11) | 04 Nov 2023 | DR2 |  | Slab rebar laying in progress
Sat (04/11) | 04 Nov 2023 | MH2-8 |  | 4th layer excavation in progress
Sat (04/11) | 04 Nov 2023 | MH2-1 |  | Excavation works for base slab ongoing
Sat (04/11) | 04 Nov 2023 | Exit 2 |  | Slope and platform lean concrete casting for upcoming pumping main laying works
Sat (04/11) | 04 Nov 2023 | BH-131 |  | SI drilling in progress, current depth 32m
Sat (04/11) | 04 Nov 2023 | Dw-62 |  | Rebar inspection for guidewall in progress, to cast today
Sat (04/11) | 04 Nov 2023 | ST-58 |  | Guidewall cast
Sat (04/11) | 04 Nov 2023 | ST-54 |  | HSL no activity
Sat (04/11) | 04 Nov 2023 | Zone 3 |  | Krishco continue water pipe laying works. As of now, about 7.5m of pipes laid
Sat (04/11) | 04 Nov 2023 | DR2 Bay 6 |  | Casting completed
Sat (04/11) | 04 Nov 2023 | P27 to P39 |  | WG Rope pulling in progress
Sat (04/11) | 04 Nov 2023 | ST140 | SC40 | Excavation work temporary stop due to change of wheel teeth, current depth 37.90m from GWTL
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | WG continue excavation works for SPPG pipe laying
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-116 |  | SI drilling works in progress, current depth 36m
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-113 |  | SI drilling works in progress, current depth 41m
Sat (04/11) | 04 Nov 2023 | Zone 4 ABH-114 |  | Water top up for SI works in progress, current depth 45m
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Dipcie Singtel 4-ways pipe laying inside SIA engineering
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | SKK contractor mobilization works
Sat (04/11) | 04 Nov 2023 | Zone 4 |  | Fiber Reach contractor SingTel submarine pipe laying works
Sat (04/11) | 04 Nov 2023 | N4 |  | KTC continue excavation works to FEL
Sat (04/11) | 04 Nov 2023 | N3 |  | Column stump cast
Sat (04/11) | 04 Nov 2023 | N2 |  | Column stump casting in progress
Sat (04/11) | 04 Nov 2023 | North ramp Bet. P12 & P11 |  | Excavation works to install drainage pipes to divert water from existing drain to ecm pond
Sat (04/11) | 04 Nov 2023 | Zone 4 loyang way |  | Mandrel test completed. Area reinstated
Sat (04/11) | 04 Nov 2023 | MH5-2 |  | Pipe jacking commenced, towards existing sewer mh
Sat (04/11) | 04 Nov 2023 | P20-4 |  | HSL boring work completed. Rebar cages lowering in progress
Sat (04/11) | 04 Nov 2023 | P23 |  | Continue bentonite pipe laying works
Sat (04/11) | 04 Nov 2023 | Zone 4 loyang way |  | 2nd location area reinstated
Sat (04/11) | 04 Nov 2023 | ST140 |  | 1st bite trenching continue. 34+ m
Sat (04/11) | 04 Nov 2023 | DR2 |  | 6th panel slab rebar installation status. Target to cast today around 10 am
Sat (04/11) | 04 Nov 2023 | Exit 2 |  | Temporary desander Noise barrier frame installation status
Sat (04/11) | 04 Nov 2023 | MH2-8 |  | 4th layer hacking works till 10pm
Sat (04/11) | 04 Nov 2023 | P20-4 |  | Casting on going. Total vol. 45.5 m3
Sat (04/11) | 04 Nov 2023 | N2 |  | Column casting completed
Sat (04/11) | 04 Nov 2023 | N4 |  | Excavation work stopped for the day. WH installing barricades
Sat (04/11) | 04 Nov 2023 | MH2-1 |  | Lean con for base slab
Sat (04/11) | 04 Nov 2023 | Exit 2 |  | Temp desander NB frame installation
Sat (04/11) | 04 Nov 2023 | Zone 3 |  | ST55-57 guidewall rebar works
Sat (04/11) | 04 Nov 2023 | DR2 |  | Dayshift end work for the day, night shift take over. To lay rebars tonight for last slab
Sat (04/11) | 04 Nov 2023 | ST140 |  | 2nd bite trenching started
Sat (04/11) | 04 Nov 2023 | MH2-8 |  | 5th layer excavation works ongoing
Sat (04/11) | 04 Nov 2023 | MH2-9 |  | To cast the balance small portion of 2nd layer which affected by the utility today
Sat (04/11) | 04 Nov 2023 | Bet. P27-P28 |  | KTC backfilling works in progress
Sun (05/11) | 05 Nov 2023 | Exit 2 |  | Temp desander NB framing installation continue
Sun (05/11) | 05 Nov 2023 | ST55-57 |  | Rebar installation completed. Formwork closing on going
Sun (05/11) | 05 Nov 2023 | ST140 |  | 2nd bite now at 14m depth
Sun (05/11) | 05 Nov 2023 | Zone 4 |  | SPPG mandrel test in progress
Sun (05/11) | 05 Nov 2023 | Loyang way LP70-71 |  | Lucky joint here for M1 pipe laying
Sun (05/11) | 05 Nov 2023 | Zone 4 |  | SPPG mandrel test completed. Area reinstated
Sun (05/11) | 05 Nov 2023 | ST55-57 |  | Formwork closing done. Dayshift to cast
Sun (05/11) | 05 Nov 2023 | ST140 |  | 2nd bite trenching continue at 20m depth
Sun (05/11) | 05 Nov 2023 | DR2 |  | Last bay slab rebar works. Dayshift to cast
Sun (05/11) | 05 Nov 2023 | DW23 |  | First bite excavation in progress, 28.7m
Sun (05/11) | 05 Nov 2023 | JTC blk 4 |  | Guidewall ST55, 56 57 were cast earlier today
Sun (05/11) | 05 Nov 2023 | ST140 |  | Cutter body up for cutter wheel replacement. 2nd bite excavation current depth at 33.5m
Mon (06/11) | 06 Nov 2023 | DW23 |  | Toe cleaning ongoing
Mon (06/11) | 06 Nov 2023 | MH2-9 |  | Preparing for BRC installation. Plan to cast today
Mon (06/11) | 06 Nov 2023 | MH2-6 |  | No activity
Mon (06/11) | 06 Nov 2023 | MH2-3 |  | Pipe jacking towards MH2-1 set up works in progress. To start pipe jacking tmr
Mon (06/11) | 06 Nov 2023 | P21 |  | Pipe jamming works by starhub contractor
Mon (06/11) | 06 Nov 2023 | MH2-4 |  | Pipe installation until ring beam..tomorrow plan to cast ring beam
Mon (06/11) | 06 Nov 2023 | P19-4 |  | Boring works on going
Mon (06/11) | 06 Nov 2023 | Zone 4 |  | HDD pit by Singtel Submarine SKK in progress
Mon (06/11) | 06 Nov 2023 | N6 |  | No activity
Mon (06/11) | 06 Nov 2023 | N4 |  | KTC excavation to FEL
Mon (06/11) | 06 Nov 2023 | N3 |  | No activity
Mon (06/11) | 06 Nov 2023 | N2 |  | No activity
Mon (06/11) | 06 Nov 2023 | P11 |  | WH Trial trench for drain hacking in progress
Mon (06/11) | 06 Nov 2023 | MH5-2 |  | Jacking to existing MH, 2/5 completed
Mon (06/11) | 06 Nov 2023 | DW23 |  | 2nd bite excavation in progress, 8.5m
Mon (06/11) | 06 Nov 2023 | ST140 |  | 2nd bite excavation, 35.7m
Mon (06/11) | 06 Nov 2023 | MH2-1 |  | BRC laying in progress for base slab. Today to cast
Mon (06/11) | 06 Nov 2023 | MH2-4 |  | Shaft wall rebar work in progress
Mon (06/11) | 06 Nov 2023 | MH5-2 |  | 3 pipes completed. Lowered pipe 4. Pipe jacking to continue tmr
Mon (06/11) | 06 Nov 2023 | BP5 |  | Inner casing installed, 7m. Tmr plan for pile extraction
Mon (06/11) | 06 Nov 2023 | Blk 4 |  | No activity
Mon (06/11) | 06 Nov 2023 | DR2 |  | No activity
Mon (06/11) | 06 Nov 2023 | ST140 |  | BC cutter rectification ongoing — cutter teeth, gear box and hydraulic hoses
Mon (06/11) | 06 Nov 2023 | Zone 4 LA LP105 |  | Tonight plan for Singtel pipe laying
Mon (06/11) | 06 Nov 2023 | Zone 4 LA/LW junction & Loyang Way LP23 |  | Tonight plan for SPPG mandrel test. 2 TMOs on site
Tue (07/11) | 07 Nov 2023 | P21 |  | Working platform preparation works for piling works. Today to start preboring here
Tue (07/11) | 07 Nov 2023 | N6 |  | Pile cap formwork dismantling
Tue (07/11) | 07 Nov 2023 | N4 |  | Excavation to FEL today to complete. HSL to start hacking of pile head from tomorrow
Tue (07/11) | 07 Nov 2023 | MH2-6 |  | Preparation for backfilling works
Tue (07/11) | 07 Nov 2023 | N6 |  | Pilecap Formwork dismantling
Tue (07/11) | 07 Nov 2023 | P21 |  | Pre boring prior to installation of casing
Tue (07/11) | 07 Nov 2023 | P19-4 |  | Rebar cage installation
Tue (07/11) | 07 Nov 2023 | ST140 |  | BC cutter rectification ongoing
Tue (07/11) | 07 Nov 2023 | Loyang Way/Ave junction & Loyang Way LP23 |  | Works completed. Lanes reopened. Housekeeping ongoing
Tue (07/11) | 07 Nov 2023 | N4 |  | Excavation to FEL completed. Now lowering of HSL excavator for hacking
Tue (07/11) | 07 Nov 2023 | N3 |  | No activity
Tue (07/11) | 07 Nov 2023 | Zone 4 |  | Singtel pipe laid, 6m
Tue (07/11) | 07 Nov 2023 | Exit 2 |  | LCH adjusting the hoarding to shift the pipe alignment towards the bin centre so as to avoid Dwall alignment
Tue (07/11) | 07 Nov 2023 | Ko Saw, jtc last pile will be extracted at 4 |  | 00 pm
Tue (07/11) | 07 Nov 2023 | North ramp | P8 to P11 | KTC Drain hacking works
Tue (07/11) | 07 Nov 2023 | DW23 |  | Waterstop end plate installation ongoing at DW24 side
Tue (07/11) | 07 Nov 2023 | Exit 2 |  | Pumping mains to shift to 800mm from DW37 guidewall outer edge
Tue (07/11) | 07 Nov 2023 | MH2-5 |  | Clearing out materials inside shaft
Tue (07/11) | 07 Nov 2023 | P19-4 |  | Casting in progress, last lorry already on site
Tue (07/11) | 07 Nov 2023 | Blk 4 |  | No more activity
Tue (07/11) | 07 Nov 2023 | ST59-60 |  | Guidewall cast
Tue (07/11) | 07 Nov 2023 | ST140 |  | 3rd bite excavation in progress
Tue (07/11) | 07 Nov 2023 | Zone 4 LA LP105 | towards LW | Plan for Singtel pipe laying tonight
Tue (07/11) | 07 Nov 2023 | ST223 |  | Guidewall formwork closing
Tue (07/11) | 07 Nov 2023 | DW23 |  | Casting ongoing, progressive vol: 34/116m3
Tue (07/11) | 07 Nov 2023 | Outside Gate 5 |  | Open pit for SPPG mandrel test
Tue (07/11) | 07 Nov 2023 | P21-P25 |  | Krishco preparation for pressure test
Wed (08/11) | 08 Nov 2023 | N6 |  | Housekeeping and preparation for patching works
Wed (08/11) | 08 Nov 2023 | N4 |  | Pile head cutting in progress
Wed (08/11) | 08 Nov 2023 | N3 |  | KTC backfilling works to start today
Wed (08/11) | 08 Nov 2023 | N2 |  | Working platform dismantling
Wed (08/11) | 08 Nov 2023 | Zone 1 |  | No activity
Wed (08/11) | 08 Nov 2023 | MH5-2 |  | No activity. The current team is shifting the telescopic to MH2-3, afternoon to resume hacking of wall to retrieve the tbm
Wed (08/11) | 08 Nov 2023 | MH6-1 |  | Manhole touch up for inspection
Wed (08/11) | 08 Nov 2023 | P21-3 |  | Casing installation completed, now to continue boring work. Target to cast tmr
Wed (08/11) | 08 Nov 2023 | N6 |  | Continue pile cap patching works
Wed (08/11) | 08 Nov 2023 | N4 |  | Pile head cutting completed, 3/3. Hacking to start after tea break
Wed (08/11) | 08 Nov 2023 | N3 |  | KTC backfilling works in progress. Tmr to do NDT
Wed (08/11) | 08 Nov 2023 | N1 |  | LE preboring completed, going to start soldier pile & lagging plate installation now
Wed (08/11) | 08 Nov 2023 | P8-P10 |  | KTC drain hacking works in progress
Wed (08/11) | 08 Nov 2023 | Casting completed at 0100hrs. Total vol |  | 130m3
Wed (08/11) | 08 Nov 2023 | Zone 4 |  | Works completed. Lane reopened
Wed (08/11) | 08 Nov 2023 | ST140 |  | C-lug welding in progress
Wed (08/11) | 08 Nov 2023 | Near blk 2 |  | Bentonite pipes fixing ongoing
Wed (08/11) | 08 Nov 2023 | BP05 |  | Boring for balance 2.2m completed. Now preparing to extract pile
Wed (08/11) | 08 Nov 2023 | ST53 |  | 1st bite pre-boring on going, current depth at 25/26.8m. To complete by 8pm. Noise ballon now setting up
Wed (08/11) | 08 Nov 2023 | ST54 |  | LSS backfilling completed, 14m3
Wed (08/11) | 08 Nov 2023 | DR2 |  | Rebar cutting on going, dayshift team to work until 10pm to place concrete blocks
Wed (08/11) | 08 Nov 2023 | ST140 |  | End plate extraction
Wed (08/11) | 08 Nov 2023 | ST61 |  | Guidewall rebar installation. Nightshift team to continue formwork closing
Wed (08/11) | 08 Nov 2023 | P21-3 |  | Boring works at 11m depth. Work will stop at 7pm
Wed (08/11) | 08 Nov 2023 | MH2-3 |  | TBM successfully drilled. Tomorrow to install extension and start pipe jacking
Wed (08/11) | 08 Nov 2023 | MH2-4 |  | Ring beam rebar completed. Tomorrow to close formwork. Work stopped for the day
Wed (08/11) | 08 Nov 2023 | ST140 |  | Trimming ongoing
Wed (08/11) | 08 Nov 2023 | MH2-6 |  | Precast ring installation in progress
Wed (08/11) | 08 Nov 2023 | BP5 |  | LSS backfilling in progress
Wed (08/11) | 08 Nov 2023 | ST53 |  | Pre-boring in progress, current depth 26m
Wed (08/11) | 08 Nov 2023 | P34 |  | SPPG manual cleaning ongoing for mandrel test. Tonight 2 teams
Wed (08/11) | 08 Nov 2023 | DR2 |  | Continue cleaning of rebars and debris at the other end
Wed (08/11) | 08 Nov 2023 | Zone 4 |  | Tonight no activity here
Wed (08/11) | 08 Nov 2023 | P27 |  | SPPG mandrel test
Wed (08/11) | 08 Nov 2023 | MH2-9 |  | Excavation for 4th layer in progress
Wed (08/11) | 08 Nov 2023 | ST53 |  | PB1 boring completed. Reached 27.2m
Wed (08/11) | 08 Nov 2023 | MH2-4 |  | Rebar installation for manhole
Wed (08/11) | 08 Nov 2023 | ST223 |  | Guidewall formwork dismantling
Thu (09/11) | 09 Nov 2023 | MH2-8 |  | 4th ring formwork dismantling. Thereafter to continue excavation for 5th layer
Thu (09/11) | 09 Nov 2023 | MH2-6 |  | Current status of precast ring installation
Thu (09/11) | 09 Nov 2023 | Zone 1 |  | DE143 working at NLL for drain works
Thu (09/11) | 09 Nov 2023 | Zone 1 |  | No activity
Thu (09/11) | 09 Nov 2023 | MH5-2 |  | No activity
Thu (09/11) | 09 Nov 2023 | ST96 |  | 1st bite trenching
Thu (09/11) | 09 Nov 2023 | ST140 |  | 1st bite cleaning in progress
Thu (09/11) | 09 Nov 2023 | Exit 2 |  | Noise barrier setup for desander ongoing
Thu (09/11) | 09 Nov 2023 | P21-3 |  | HSL Boring works in progress
Thu (09/11) | 09 Nov 2023 | MH2-3 |  | 1st pipe lowered down, jacking ongoing
Thu (09/11) | 09 Nov 2023 | N6 |  | Preparation for concrete plug casting
Thu (09/11) | 09 Nov 2023 | MH2-8 |  | Continue excavation
Thu (09/11) | 09 Nov 2023 | MH2-9 |  | Excavation almost completed
Thu (09/11) | 09 Nov 2023 | N4 |  | No activity
Thu (09/11) | 09 Nov 2023 | N3 |  | KTC continue backfill works
Thu (09/11) | 09 Nov 2023 | N2 |  | No activity
Thu (09/11) | 09 Nov 2023 | N1 |  | Soldier pile & lagging plate installation
Thu (09/11) | 09 Nov 2023 | North ramp P8-P11 |  | KTC Hacking of drain in progress
Thu (09/11) | 09 Nov 2023 | Rig 3 |  | BC cutter wheel setting up in progress
Thu (09/11) | 09 Nov 2023 | ST140 |  | 3rd bite cleaning ongoing
Thu (09/11) | 09 Nov 2023 | MH2-8 |  | Continue excavation for 5th layer
Thu (09/11) | 09 Nov 2023 | MH2-3 to MH2-1 |  | 2nd pipe jacking done. Preparing for 3rd pipe lowering
Thu (09/11) | 09 Nov 2023 | P19-6 |  | Casing installation in progress
Thu (09/11) | 09 Nov 2023 | MH 2-9 |  | Rebar installed. Preparing formwork closing for casting
Thu (09/11) | 09 Nov 2023 | MH2-9 |  | 4th layer for casting
Thu (09/11) | 09 Nov 2023 | Dear all, today 10 |  | 30am meeting with wh-da and LCH on the safety concern to hack existing manhole for shell station before reach 5-2 jacking. Please do join if you are available. Thanks
Thu (09/11) | 09 Nov 2023 | MH2-8 |  | 5th laywr hacking works on going
Thu (09/11) | 09 Nov 2023 | MH2-6 |  | No more activity
Thu (09/11) | 09 Nov 2023 | MH2-3 and MH2-4 |  | No more activity
Thu (09/11) | 09 Nov 2023 | P19-3 |  | Internal koden test. Tomorrow to cast
Thu (09/11) | 09 Nov 2023 | P14-P18 |  | Shifting of bentonite pipes to be laid tomorrow. Supply to South ramp for piling works
Thu (09/11) | 09 Nov 2023 | Zone 2 PDR3/loyang avenue junction |  | 1 team here tonight for SPPG open pit excavation and mandrel test
Thu (09/11) | 09 Nov 2023 | Zone 3 JTC |  | WG to re-lay 15m length SPPG pipes today due to pipe damage and unable to pull mandrel through
Thu (09/11) | 09 Nov 2023 | MH2-9 |  | Excavation in progress. Today plan to cast 4th layer caisson
Thu (09/11) | 09 Nov 2023 | MH2-3 |  | Preparation to lower 1st pipe down for jacking towards MH2-1
Thu (09/11) | 09 Nov 2023 | Zone 3 P27-P29 |  | Excavation works to replace SPPG pipe. Unfortunately madrel failed here. 😔
Thu (09/11) | 09 Nov 2023 | ST61 |  | To install guidewall formwork and cast today
Thu (09/11) | 09 Nov 2023 | MH2-4 |  | Current status for MH wall rebar works
Thu (09/11) | 09 Nov 2023 | Zone 2 LCH |  | Preparation works for excavation at discharge manhole area
Thu (09/11) | 09 Nov 2023 | ST140 |  | Final koden check in progress
Thu (09/11) | 09 Nov 2023 | Zone 3 JTC area |  | HSL pre-boring stopped for the day, now housekeeping
Thu (09/11) | 09 Nov 2023 | ST58 |  | Bentonite pipe leak, repairing on going. Later to continue trenching
Thu (09/11) | 09 Nov 2023 | DR2 |  | Installation of concrete blocks
Thu (09/11) | 09 Nov 2023 | N6 |  | Preparation for concrete plug casting
Thu (09/11) | 09 Nov 2023 | P21-3 |  | To continue boring works. Now pending soil truck to empty the soil bin
Thu (09/11) | 09 Nov 2023 | N3 |  | KTC continue backfilling and compaction works. Evening will carry out ndt
Thu (09/11) | 09 Nov 2023 | N2 |  | No activity
Thu (09/11) | 09 Nov 2023 | N1 |  | LE soldier pile & lagging plate installation
Fri (10/11) | 10 Nov 2023 | P19-6 |  | Preboring and casing installation completed. To resume with boring works
Fri (10/11) | 10 Nov 2023 | N6 |  | No activity. Concrete plug was cast yesterday
Fri (10/11) | 10 Nov 2023 | N4 |  | HSL Mechanic addressing all the safety comments before start of pile hacking works
Fri (10/11) | 10 Nov 2023 | N3 |  | KTC backfilling works
Fri (10/11) | 10 Nov 2023 | N2 |  | KTC backfilling works ongoing. Today to do NDT
Fri (10/11) | 10 Nov 2023 | N1 |  | Installation of solider pile and lagging plate completed yesterday. Now adjusting the solider pile and lagging plate plate to the required embedment depth
Fri (10/11) | 10 Nov 2023 | North ramp P8-P10 |  | KTC drain hacking completed. Now clearing hardcores
Fri (10/11) | 10 Nov 2023 | ST96 |  | First bite excavation in progress
Fri (10/11) | 10 Nov 2023 | DR2 |  | Hacking ongoing
Fri (10/11) | 10 Nov 2023 | ST140 |  | Hanging bar u-clip inspection done
Fri (10/11) | 10 Nov 2023 | Zone 3 P27 |  | Excavation to expose SPPG pipe continue
Fri (10/11) | 10 Nov 2023 | ST96 |  | 1st bite trenching continue
Fri (10/11) | 10 Nov 2023 | ST140 |  | 3/8 cages installation on going
Fri (10/11) | 10 Nov 2023 | Zone 2 loyang avenue/PDR3 junction |  | 1st pit to 2nd pit madrel done. Backfilling works
Fri (10/11) | 10 Nov 2023 | Zone 2 P6 |  | SPPG madrel and open pit excavation completed
Fri (10/11) | 10 Nov 2023 | Exit 2 |  | Desander NB panel installation
Fri (10/11) | 10 Nov 2023 | Zone 3 |  | Excavation to expose sppg pipe completed for the night, 52m. Dayshift to replace pipe
Fri (10/11) | 10 Nov 2023 | ST140 |  | 6/8 cage rebar lapping inspection
Fri (10/11) | 10 Nov 2023 | ST96 |  | 1st bite trenching at 27m depth. Cutter body extraction to replace cutter wheel teeth
Fri (10/11) | 10 Nov 2023 | Blk 4 |  | Preboring ongoing for ST55
Fri (10/11) | 10 Nov 2023 | DR2 |  | Continue marking of wall alignment
Fri (10/11) | 10 Nov 2023 | P21-3 |  | Koden Test check ongoing
Fri (10/11) | 10 Nov 2023 | ST140 |  | Rebar cage lapping in progress
Fri (10/11) | 10 Nov 2023 | ABH101 |  | In progress, 39m
Sat (11/11) | 11 Nov 2023 | MH2-1 |  | No activity
Sat (11/11) | 11 Nov 2023 | Zone 2 JTC |  | WG excavation and shoring installation prior to pipe replacement of damage SPPG 12way pipe
Sat (11/11) | 11 Nov 2023 | Near MH2-1 |  | LCH pumping main pipe laying works
Sat (11/11) | 11 Nov 2023 | BH147 |  | SI works drilling ongoing, depth 55m
Sat (11/11) | 11 Nov 2023 | DW061 | MC96 | 1st bite excavation in progress. Current depth 20.5m
Sat (11/11) | 11 Nov 2023 | ST51 |  | Excacation for guidewall ongoing
Sat (11/11) | 11 Nov 2023 | ST55 |  | HSL preboring works in progress for PB2, current depth 25m
Sat (11/11) | 11 Nov 2023 | BLK 4 - ST058 | SC40#02 | 1st bite excavation in process, current depth 34m
Sat (11/11) | 11 Nov 2023 | MH2-4 |  | Concrete on site for 1st stage raised wall casting
Sat (11/11) | 11 Nov 2023 | P36 |  | MoGuan starhub 6ways pipe laying in progress
Sat (11/11) | 11 Nov 2023 | ST096 CCE area | SC40 #01 | Electrical box checking ongoing, current depth for 1st bite is 28.6m
Sat (11/11) | 11 Nov 2023 | Zone 4 |  | SKK contractor Singtel works along Loyang way
Sat (11/11) | 11 Nov 2023 | Zone 4 | ABH117 | SI work in progress, current depth 45m
Sat (11/11) | 11 Nov 2023 | Zone 4 | ABH109 | SI works in progress, current depth 14.36m
Sat (11/11) | 11 Nov 2023 | Zone 4 |  | ABH115 hand augering ongoing
Sat (11/11) | 11 Nov 2023 | Zone 4 | P51-BP-TT-07 | Manual trial trench in progress
Sat (11/11) | 11 Nov 2023 | Zone 4 | P51-BP-TT-07A | Manual trial trench in progress
Sat (11/11) | 11 Nov 2023 | Zone 4 |  | Washing bay ramp to cast in the afternoon
Sat (11/11) | 11 Nov 2023 | Zone 4 |  | Fiber Reach contractor working along Loyang ave
Sat (11/11) | 11 Nov 2023 | N5 |  | KTC excavation work to S1 waler level ongoing
Sat (11/11) | 11 Nov 2023 | N6 |  | No activity
Sat (11/11) | 11 Nov 2023 | N4 |  | HSL pile head hacking works
Sat (11/11) | 11 Nov 2023 | N3 |  | Backfilling competed, balance compaction works. NDT to be carried out at 3pm
Sat (11/11) | 11 Nov 2023 | N2 |  | Backfilling competed, balance compaction works. NDT to be carried out at 3pm
Sat (11/11) | 11 Nov 2023 | N1 |  | LE housekeeping and preparation works to shift the materials to P8
Sat (11/11) | 11 Nov 2023 | North Ramp | P8 to P10 | KTC Backfilling & levelling works and hardcore removal ongoing
Sat (11/11) | 11 Nov 2023 | Zone 1 | Lucky Joint | Preparation works to carry out localised shifting of M1 cable at MH1-2
Sat (11/11) | 11 Nov 2023 | Zone 1 |  | DE143 works along NLL
Sat (11/11) | 11 Nov 2023 | MH2-3 |  | Jacking toward MH2-1 in progress, 6th pipe
Sat (11/11) | 11 Nov 2023 | MH2-6 |  | No activity
Sat (11/11) | 11 Nov 2023 | P19-6 |  | BP to cast today
Sat (11/11) | 11 Nov 2023 | MH5-2 to existing sewer |  | Afternoon to start work
Sat (11/11) | 11 Nov 2023 | MH2-4 |  | 1pm arranged for QPS inspection
Sat (11/11) | 11 Nov 2023 | MH2-8 |  | Excavation for 5th layer completed, now BRC installation ongoing
Sat (11/11) | 11 Nov 2023 | MH2-9 |  | 5th layer excavation in progress
Sat (11/11) | 11 Nov 2023 | ST26 |  | Formwork installation for guidewall work. Target to cast around 5pm
Sat (11/11) | 11 Nov 2023 | P26 - P27 |  | Pumping main pipe stump footing 20 nos cast
Sat (11/11) | 11 Nov 2023 | DW061 | MC96 | 1st bite excavation completed. Current depth 25m. Preparation for internal koden test
Sat (11/11) | 11 Nov 2023 | Zone 2 JTC |  | WG excavation and shoring installation prior to pipe replacement of damage SPPG 12way pipe
Sat (11/11) | 11 Nov 2023 | BH147 |  | SI grouting works completed
Sat (11/11) | 11 Nov 2023 | ST55 |  | HSL preboring works completed, now preparing to backfill with LSS
Sat (11/11) | 11 Nov 2023 | ST51 |  | Excacation for guidewall completed
Sat (11/11) | 11 Nov 2023 | BLK 4 - ST058 | SC40#02 | 1st bite excavation completed, current depth 39.5m. Preparing for internal koden test
Sat (11/11) | 11 Nov 2023 | DR2 |  | Housekeeping works ongoing
Sat (11/11) | 11 Nov 2023 | ST096 CCE area | SC40 #01 | Changing of cutter teeth in progress, current depth for 1st bite is 28.8m
Sat (11/11) | 11 Nov 2023 | Zone 4 | ABH117 | SI work grouting work completed, termination depth 47m
Sat (11/11) | 11 Nov 2023 | Zone 4 | ABH109 | SI works in progress, current depth 16m
Sat (11/11) | 11 Nov 2023 | Zone 4 |  | SI rig shifter to ABH115
Sat (11/11) | 11 Nov 2023 | Zone 4 |  | Washing bay ramp finished casting
Sat (11/11) | 11 Nov 2023 | Zone 4 | P51-BP-TT-07 | Manual trial trench completed, found 300mm new water pipe
Sat (11/11) | 11 Nov 2023 | Zone 4 | P51-BP-TT-07A | Manual trial trench completed. Found 300mm new water pipe
Sat (11/11) | 11 Nov 2023 | N5 |  | KTC excavation work to S1 waler level completed
Sat (11/11) | 11 Nov 2023 | N4 |  | HSL continue pile head hacking works
Sat (11/11) | 11 Nov 2023 | N3 |  | NDT completed. Next LE need to remove the waler beams for next layer backfilling works
Sat (11/11) | 11 Nov 2023 | N2 |  | NDT completed. KTC will continue next layer backfilling next week. Housekeeping ongoing
Sat (11/11) | 11 Nov 2023 | North Ramp | P8 to P10 | KTC levelling works and hardcore removal ongoing
Sat (11/11) | 11 Nov 2023 | North Ramp | P8 | LE area preparation ongoing for machineries and materials shifting
Sat (11/11) | 11 Nov 2023 | Zone 1 | Lucky Joint | Current status for localised shifting of M1 cables at MH1-2
Sat (11/11) | 11 Nov 2023 | MH5-2 | existing sewer | Preparation works in progress for wall hacking to retrieve TBM
Sat (11/11) | 11 Nov 2023 | P19-6 |  | Rebar cages lowered. Preparation for casting
Sat (11/11) | 11 Nov 2023 | MH2-4 |  | Formwork closing in progress
Sat (11/11) | 11 Nov 2023 | MH2-3 |  | Jacking toward MH2-1 in progress, 7th pipe
Sat (11/11) | 11 Nov 2023 | MH2-6 |  | Wall BRC rebar works installation in progress
Sat (11/11) | 11 Nov 2023 | MH2-7 |  | Thrust wall hacking works
Sat (11/11) | 11 Nov 2023 | MH2-4 |  | Ring beam formwork closing. To cast tonight
Sat (11/11) | 11 Nov 2023 | P19-6 |  | Casting completed
Sat (11/11) | 11 Nov 2023 | St26 |  | Guidewall casting
Sat (11/11) | 11 Nov 2023 | Exit 2 |  | DW61 2nd bite trenching at 6m
Sat (11/11) | 11 Nov 2023 | ST58 |  | 2nd bite trenching, BC cutter body extract for cutter wheel maintenance
Sat (11/11) | 11 Nov 2023 | MH2-7 |  | Thrust block hacking works
Sat (11/11) | 11 Nov 2023 | MH2-8 |  | Excavation for 5th layer. Target to cast today
Sat (11/11) | 11 Nov 2023 | ST26 |  | Formwork installation for guidewall work
Sun (12/11) | 12 Nov 2023 | Exit 2 |  | DW61 just now 2nd bite reached 25m
Sun (12/11) | 12 Nov 2023 | ST96 |  | 1st bite trenching at 29.2m depth
Sun (12/11) | 12 Nov 2023 | ST58 |  | Cutter wheel teeth replacement. Current depth 14m
Sun (12/11) | 12 Nov 2023 | DW61 |  | Excavation and internal Koden test completed. Now flange extension need to weld for trimming
Sun (12/11) | 12 Nov 2023 | ST96 |  | 1st bite completed. 2nd bite trenching started
Sun (12/11) | 12 Nov 2023 | ST58 |  | Trenching continue at 22m depth
Mon (13/11) | 13 Nov 2023 | DW61 |  | 93m³/111m³ cast
Mon (13/11) | 13 Nov 2023 | ST58 |  | 3rd bite depth reached 39.6m. Cleaning resumes
Mon (13/11) | 13 Nov 2023 | ST96 |  | Preparing to resume trimming at water stop side. Currently waiting for excavator to shift some materials
Mon (13/11) | 13 Nov 2023 | ST96 |  | Trimming started
Mon (13/11) | 13 Nov 2023 | DR2 |  | Drilling of base slab by CGS for rebar planting
Tue (14/11) | 14 Nov 2023 | MH2-3 |  | Setting up pipe no.10 to jack towards MH2-1. 9/75 pipes completed
Tue (14/11) | 14 Nov 2023 | MH2-4 |  | Today mould dismantling and backfilling works. Now pumping water
Tue (14/11) | 14 Nov 2023 | P20-4 |  | Pre boring for casing installation. Today to cast
Tue (14/11) | 14 Nov 2023 | MH5-2 |  | Existing sewer shaft Benching hacking for pipe connection
Tue (14/11) | 14 Nov 2023 | MH1-2 |  | No activity. M1 shifted
Tue (14/11) | 14 Nov 2023 | Zone 1 P4 |  | Plan to start TT here today for BP
Tue (14/11) | 14 Nov 2023 | PMH3 area |  | No SPPG team here yet. FYI
Tue (14/11) | 14 Nov 2023 | P8 |  | Site access and platform preparation works. Plan to start pre boring tomorrow once COS issued
Tue (14/11) | 14 Nov 2023 | N3 |  | Scaffold dismantling, later todat to start removing waler
Tue (14/11) | 14 Nov 2023 | N4 |  | Pile head trimming at COL. Today to complete, tomorrow to lean con
Tue (14/11) | 14 Nov 2023 | N5 |  | Excavation till W1 completed. Now no activity. Asked WH to arrange waler installation
Tue (14/11) | 14 Nov 2023 | ST58 |  | Final koden test in progress
Tue (14/11) | 14 Nov 2023 | ST96 |  | Chiselling temporarily on hold for repair. Current depth at 26m
Tue (14/11) | 14 Nov 2023 | ST58 |  | Final koden test completed
Tue (14/11) | 14 Nov 2023 | MH2-7 |  | Hardcore clear from hacked trust block. To continue hacking tomorrow
Tue (14/11) | 14 Nov 2023 | MH2-6 |  | Continue backfilling in progress. This team working until 7PM
Tue (14/11) | 14 Nov 2023 | MH2-3 to MH2-1 |  | Pipe nos 12 jacking done. To continue jacking of pipe nos 13
Tue (14/11) | 14 Nov 2023 | MH2-4 |  | Preparation for wall rebar work
Tue (14/11) | 14 Nov 2023 | P20-6 |  | Excavation reached 29.5m/32.2m. Tomorrow to continue
Tue (14/11) | 14 Nov 2023 | MH2-8 |  | Excavation to 6th layer already stopped. Tomorrow to resume
Tue (14/11) | 14 Nov 2023 | N5 |  | Continue access installation
Tue (14/11) | 14 Nov 2023 | South ramp area/MH5 |  | No activity
Tue (14/11) | 14 Nov 2023 | P29 |  | WG to expose SPPG pipes and install shoring
Tue (14/11) | 14 Nov 2023 | Exit 2 DW60 |  | Preparation for excavation
Tue (14/11) | 14 Nov 2023 | ST54 |  | First bite excavation in progress
Tue (14/11) | 14 Nov 2023 | DR2 |  | No activity
Tue (14/11) | 14 Nov 2023 | Zone 4 |  | No activity tonight
Tue (14/11) | 14 Nov 2023 | ST96 |  | Preparation for waterstop end plate extraction
Tue (14/11) | 14 Nov 2023 | MH2-9 |  | Excavation in progress for 5th layer. Today plan to cast. Excavator need to repair
Tue (14/11) | 14 Nov 2023 | BH-10 |  | Preparing for hand augering
Tue (14/11) | 14 Nov 2023 | MH2-6 |  | Today plan to dismantle perm structure formwork and do backfilling
Wed (15/11) | 15 Nov 2023 | N5 |  | Access installation to W1 layer
Wed (15/11) | 15 Nov 2023 | N4 |  | Today final levelling and lean con
Wed (15/11) | 15 Nov 2023 | N3 |  | Access installation for waler bracket dismantling
Wed (15/11) | 15 Nov 2023 | N2 |  | SP and LP to extract today
Wed (15/11) | 15 Nov 2023 | P8 |  | ERSS setting out. Today to start pre-boring once COS issued
Wed (15/11) | 15 Nov 2023 | PMH3 |  | No SPPG work also today
Wed (15/11) | 15 Nov 2023 | Zone 4 | P45-BP-TT-01 | Manual trial trench work ongoing
Wed (15/11) | 15 Nov 2023 | Zone 4 | P45-BP-TT-01A | Manual trial trench in progress
Wed (15/11) | 15 Nov 2023 | ABH109 |  | SI work in progress, current depth 28m
Wed (15/11) | 15 Nov 2023 | ABH115 |  | SI works drilling in progress, current depth 27.5m
Wed (15/11) | 15 Nov 2023 | Zone 4 |  | Fiber reach contractor working in zone 4 working boundary
Wed (15/11) | 15 Nov 2023 | Zone 4 |  | SKK contractor working in zone 4 working boundary
Wed (15/11) | 15 Nov 2023 | Zone 1 P4-5 |  | TT on going
Wed (15/11) | 15 Nov 2023 | P4-6 |  | TT completed yesterday, found LV cable. Suspect to be abandoned, utility team to check
Wed (15/11) | 15 Nov 2023 | ST096 |  | Final koden test checking in progress
Wed (15/11) | 15 Nov 2023 | P37 |  | MoGuan starhub 6ways excavation for pipe laying in progress
Wed (15/11) | 15 Nov 2023 | Blk 4 ST061 - PB2 | HSL | PreBoring in progress, current depth is 15m from the TOC
Wed (15/11) | 15 Nov 2023 | Blk 4 | ST058 | Rebar cage 3A & 4A lapping ongoing
Wed (15/11) | 15 Nov 2023 | Blk 4 | ST054 | 2nd bite excavation ongoing, current depth 11m
Wed (15/11) | 15 Nov 2023 | MH5-2 |  | Existing sewer MH benching hacking continue
Wed (15/11) | 15 Nov 2023 | DW060 |  | Internal koden test done
Wed (15/11) | 15 Nov 2023 | ST54 |  | First bite excavation in progress, 23.6m
Wed (15/11) | 15 Nov 2023 | ST58 |  | Rebar cage installation in progress, 3/10nos
Wed (15/11) | 15 Nov 2023 | MH2-9 |  | 5th layer rebar works
Wed (15/11) | 15 Nov 2023 | Z4 ABH 114 |  | Drilling just started
Wed (15/11) | 15 Nov 2023 | P21-4 |  | Preparation for casing installation
Wed (15/11) | 15 Nov 2023 | MH2-3 |  | Pipe no.16 jacking in progress toward MH2-1
Wed (15/11) | 15 Nov 2023 | P20-6 |  | Rebar cages lowered. Now preparing casting platform for casting
Wed (15/11) | 15 Nov 2023 | MH2-4 |  | Benching work
Wed (15/11) | 15 Nov 2023 | N5 |  | Wiring installation for lightings
Wed (15/11) | 15 Nov 2023 | N4 |  | Final levelling completed. Now waiting for removal of excavator and lean concrete works
Wed (15/11) | 15 Nov 2023 | N3 |  | Waler bracket dismantling completed
Wed (15/11) | 15 Nov 2023 | N2 |  | SP and LP extraction in progress
Wed (15/11) | 15 Nov 2023 | P8-P10 |  | KTC compaction & levelling works
Wed (15/11) | 15 Nov 2023 | P8-2 |  | Preboring works has commenced
Wed (15/11) | 15 Nov 2023 | ST58 |  | Rebar cage installation ongoing, 5/10nos
Wed (15/11) | 15 Nov 2023 | Zone 1 P4-5 |  | TT completed, backfilling in progress. WH will proceed to TT for P4-4 next
Wed (15/11) | 15 Nov 2023 | MH5-2 |  | Existing manhole (receiving area) hacking in progress
Wed (15/11) | 15 Nov 2023 | DW60 |  | Excavation in progress
Wed (15/11) | 15 Nov 2023 | ST58 |  | Rebar cage installation ongoing
Wed (15/11) | 15 Nov 2023 | ST96 |  | Rebar cages u-clip inspection done with RTO
Wed (15/11) | 15 Nov 2023 | ST96 |  | First bite cleaning in progress
Wed (15/11) | 15 Nov 2023 | P29 |  | Shoring installation completed
Wed (15/11) | 15 Nov 2023 | P20-6 |  | Casting in progress
Wed (15/11) | 15 Nov 2023 | MH2-6 |  | Backfilling works ongoing
Wed (15/11) | 15 Nov 2023 | Zone 4 |  | ABH 115 drilling at 39.5m
Wed (15/11) | 15 Nov 2023 | Zone 4 |  | Singtel contractor pipe jacking for singtel cable
Wed (15/11) | 15 Nov 2023 | ABH109 |  | Drilling continue at 33m depth
Wed (15/11) | 15 Nov 2023 | P45 |  | 2 teams TT on going
Wed (15/11) | 15 Nov 2023 | DW96 |  | Finally water stop fully lowered. Now preparing to install rebar cages
Wed (15/11) | 15 Nov 2023 | DR2 |  | Starter bar planting on going
Wed (15/11) | 15 Nov 2023 | ST61 |  | 2nd point preboring on going. Depth 27m
Wed (15/11) | 15 Nov 2023 | DW60 |  | Trimming completed, next to remove end plate
Wed (15/11) | 15 Nov 2023 | Hi PD/DDs, CR103PJT would like to report the following |  | *CR103: Mechanical Grab Wire Rope Snapped during Crosswall Trenching Works*, Date: 15/11/2023, Time: Approximately 0155H, Initial Findings:, Machine Details: LIEBHERR HS855 (Mechanical Grab), Panel No: CW15A, Excavation Depth: 23m, BRK reported that at approximately 0155H during the crosswall trench excavation (~depth 23m) using the mechanical grab, the banksman had seen the outer core of the wire rope snapping. He immediately notified the operator to stop operating the grab and site team was subsequently notified of the occurrence. The grab clamshell which was positioned inside the trench at that time, was carefully lifted by using the remaining 2nd wire rope of the mechanical grab and laid flat on the ground by around 0500H. The wire rope has been replaced as of 0750H and no injuries were sustained in the incident
Wed (15/11) | 15 Nov 2023 | MH2-3 |  | Pipe no.18 completed. Tmr to resume
Wed (15/11) | 15 Nov 2023 | N4 |  | Lean con completed
Wed (15/11) | 15 Nov 2023 | South ramp/MH5 |  | No more activity for the day
Wed (15/11) | 15 Nov 2023 | P29 |  | Preparation to continue exposing SPPG pipes & shoring installation by WG
Wed (15/11) | 15 Nov 2023 | ST58 |  | First bite cleaning completed. Cutter body washing ongoing
Wed (15/11) | 15 Nov 2023 | DR2 |  | Current status of starter bar planting. No more activity
Wed (15/11) | 15 Nov 2023 | P36 |  | Preparation to expose SPPG pipes and shoring installation by WG also. Tonight 2 teams
Wed (15/11) | 15 Nov 2023 | ST96 |  | Cage 1B and 2B lapping checked — 3/6nos ongoing
Wed (15/11) | 15 Nov 2023 | Zone 4 |  | No activity tonight
Wed (15/11) | 15 Nov 2023 | MH2-8 |  | Excavation for 6th layer
Wed (15/11) | 15 Nov 2023 | Zone 3 BH10 |  | Drilling at 20m depth
Wed (15/11) | 15 Nov 2023 | MH2-6 |  | Backfilling works
Wed (15/11) | 15 Nov 2023 | MH2-4 |  | Today plan inner formwork dismantling and continue wall rebar installation
Wed (15/11) | 15 Nov 2023 | MH2-9 |  | Excavation in progress for 5th layer. Target to cast today
Wed (15/11) | 15 Nov 2023 | P21 |  | Pumping main twin pipe to connect at this area today
Wed (15/11) | 15 Nov 2023 | MH2-3 |  | Pipe jacking to MH2-1, 14/75 pipes completed
Wed (15/11) | 15 Nov 2023 | P20-6 |  | Final toe level inspection prior to cage lowering
Thu (16/11) | 16 Nov 2023 | Zone 1 |  | Shingda preparation works for Friday 700mm water main cap off
Thu (16/11) | 16 Nov 2023 | PMH3 |  | SPPG here for cable drum delivery and excavator
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | 2 Trial trench ongoing
Thu (16/11) | 16 Nov 2023 | P45-BP-TT01A-1 |  | EHV, traffic light cables and lamppost cables found
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | ABH109 at 37m depth
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | BH115 at 40m depth. G3 encountered at 15m depth
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | Singtel SKK work ongoing within our hoarding area
Thu (16/11) | 16 Nov 2023 | DW60 |  | U-clip inspection done with RTO for rebar cage and hanging bar
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | PUB (Kingview) caisson work ongoing
Thu (16/11) | 16 Nov 2023 | Zone 4 P45 |  | Trial trenches in green done. 2 Trial trenches in red ongoing. Target to complete by tmr
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | Washing bay completed on Sat. Water will be provided today
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | NETLINK (Vistek) cable pulling to SIA in progress
Thu (16/11) | 16 Nov 2023 | DR2 drain diversion area new drain wall construction |  | Part 1:, Drilling and planting: 100%, Rebar installation works in progress: 15%, Part 2:, Drilling works ongoing
Thu (16/11) | 16 Nov 2023 | MH2-6 & MH2-8 |  | Both casting done
Thu (16/11) | 16 Nov 2023 | BH19 |  | Drilling started
Thu (16/11) | 16 Nov 2023 | Zone 3 P30 |  | Excavation to replace SPPPG pipe continue
Thu (16/11) | 16 Nov 2023 | Exit 2 |  | DW30 cleaning in progress
Thu (16/11) | 16 Nov 2023 | P29 |  | Shoring installation completed
Thu (16/11) | 16 Nov 2023 | ST52 |  | PB1 and PB2 casing installed. Now starting pre-boring
Thu (16/11) | 16 Nov 2023 | ST54 |  | 2nd bote excavation current depth at 23m
Thu (16/11) | 16 Nov 2023 | ST58 |  | Rebar cage lowering started
Thu (16/11) | 16 Nov 2023 | P34-P35 |  | Starhub pipe laying, 6m
Thu (16/11) | 16 Nov 2023 | Zone 3 VS area |  | Wayer pipe stumps casting in progress, 23 nos
Thu (16/11) | 16 Nov 2023 | ST96 |  | Hanging bar inspection done with RTO
Thu (16/11) | 16 Nov 2023 | ST96 |  | Cage 2A and 3A lapping ongoing — 6/6nos rebar cage installation
Thu (16/11) | 16 Nov 2023 | ST58 |  | 3rd bite cleaning in progress
Thu (16/11) | 16 Nov 2023 | DR2 base slab Construction status |  | Drilling: 50% completed, Dowel bar planting: 36.5% completed, Rebar works: 23m on going
Thu (16/11) | 16 Nov 2023 | P21-4 |  | Boring works ongoing, 34.5m/37.2m
Thu (16/11) | 16 Nov 2023 | N5 |  | All the waler beams lowered. Now to carry out welding works
Thu (16/11) | 16 Nov 2023 | N4 |  | Pile head final trimming to COL
Thu (16/11) | 16 Nov 2023 | N3 |  | KTC Backfilling in progress till column stump level. NDT arranged tmr
Thu (16/11) | 16 Nov 2023 | N2 |  | ERSS extraction completed
Thu (16/11) | 16 Nov 2023 | PMH3 to PMH5 |  | SPPG cable pulling works ongoing
Thu (16/11) | 16 Nov 2023 | Zone 4 |  | Netlink cable pulling to SIA continue. As of now they haven't found out the location of cable damage
Thu (16/11) | 16 Nov 2023 | Zone 2 |  | HSL pipe connection works till south ramp for next bored piling location
Thu (16/11) | 16 Nov 2023 | Zone 2 |  | SPPG cable pulling stopped for the day
Thu (16/11) | 16 Nov 2023 | Zone 1/2 junction |  | Traffic normal
Thu (16/11) | 16 Nov 2023 | N3 |  | Backfilling works stopped for the day
Thu (16/11) | 16 Nov 2023 | N4 |  | Lifting ring cutting in progress. Tomorrow CGW will start rebar for pile cap
Thu (16/11) | 16 Nov 2023 | N5 |  | Waler welding works till 9pm. Tomorrow mpi and concrete packing casting
Thu (16/11) | 16 Nov 2023 | P21-4 |  | Boring works 36m/37.2m. Balance 1m. Now internal koden test. Tomorrow to cast
Thu (16/11) | 16 Nov 2023 | MH2-8 |  | Concrete on site for 6th layer casting
Thu (16/11) | 16 Nov 2023 | MH2-7 |  | Thrust blocking hacking in progress
Thu (16/11) | 16 Nov 2023 | MH2-6 |  | Formwork closing in progress for shaft wall. Tonight to cast
Thu (16/11) | 16 Nov 2023 | Zone 1 |  | Tonight PowerGrid will come for cable pulling at Loyang Avenue/ Pasir Ris Dr 3 for EA camera power. They are yet on site. Just for info
Thu (16/11) | 16 Nov 2023 | ST58 |  | Internal koden check in progress
Thu (16/11) | 16 Nov 2023 | DR2 |  | Continue starter bar planting
Thu (16/11) | 16 Nov 2023 | MH2-6 |  | Today to continue precast ring installation and rebar installation
Thu (16/11) | 16 Nov 2023 | P21-4 |  | Boring works on going, 15.5/37.2m. Plan to cast today
Thu (16/11) | 16 Nov 2023 | MH2-3 |  | 19th pipe lowered for jacking towards MH2-1
Thu (16/11) | 16 Nov 2023 | MH2-4 |  | Benching works
Thu (16/11) | 16 Nov 2023 | N5 |  | Waler brackets installation ongoing
Thu (16/11) | 16 Nov 2023 | N3 |  | Backfilling in progress till column stump level
Thu (16/11) | 16 Nov 2023 | N2 |  | ERSS extraction
Thu (16/11) | 16 Nov 2023 | ST96 |  | Preparation for casting
Thu (16/11) | 16 Nov 2023 | Zone 3 |  | Formwork closing for haunching works at sewer pipes area
Thu (16/11) | 16 Nov 2023 | P25 |  | WG dismantling shoring to facilitate backfilling works
Thu (16/11) | 16 Nov 2023 | MH2-8 |  | Excavation ongoing for 6th layer
Fri (17/11) | 17 Nov 2023 | Zone 3 |  | WG rectification of damaged SPPG pipes will be completed by next Wed. WHDA has informed them to haunch the area till P39. WHDA design team will design the utility support to carry the haunched pipes
Fri (17/11) | 17 Nov 2023 | DR2 |  | Continue rebar installation. Target to cast base today, pull-out test & continue wall rebar. Dewatering ongoing prior to continuing installing the starter bars for the next sections
Fri (17/11) | 17 Nov 2023 | P21-4 |  | Boring work completed. Preparation for final koden test
Fri (17/11) | 17 Nov 2023 | N5 |  | Welding joints cleaning final touch up. MPI arranged at 3pm
Fri (17/11) | 17 Nov 2023 | N4 |  | Guide bar installation started
Fri (17/11) | 17 Nov 2023 | ST58 |  | Casting ongoing
Fri (17/11) | 17 Nov 2023 | N3 |  | NDT. Passed
Fri (17/11) | 17 Nov 2023 | ST52 |  | PB2 boring in progress
Fri (17/11) | 17 Nov 2023 | Zone 2 |  | SPPG to continue cable pulling today. Target 2 sets (1 power cable + 2 pilot cable)
Fri (17/11) | 17 Nov 2023 | P30 |  | BH18 hand auger in progress
Fri (17/11) | 17 Nov 2023 | BH19 |  | In progress, 18m
Fri (17/11) | 17 Nov 2023 | DW60 |  | Last truck casting, 83/83m3
Fri (17/11) | 17 Nov 2023 | MH2-7 |  | Clearing hacking debris. Thereafter to continue thrust block hacking
Fri (17/11) | 17 Nov 2023 | P21-4 |  | Final koden test in progress
Fri (17/11) | 17 Nov 2023 | Zone 1 |  | P3 TT on going
Fri (17/11) | 17 Nov 2023 | Zone 1 |  | Lucky joint here doning ratan test on the previous shifted pipe of M1
Fri (17/11) | 17 Nov 2023 | Opp exit 1 |  | Singtel works ongoing
Fri (17/11) | 17 Nov 2023 | Zone 4 ABH109 |  | In progress, 47.5m
Fri (17/11) | 17 Nov 2023 | Zone 2 P21 |  | Access preparation for backfilling works along slip road. Monday to start backfilling
Fri (17/11) | 17 Nov 2023 | Zone 4 |  | HDD works by term contractor SKK
Fri (17/11) | 17 Nov 2023 | Zone 4 ABH118 |  | In progress
Fri (17/11) | 17 Nov 2023 | N5 |  | Waler MPI on going
Fri (17/11) | 17 Nov 2023 | DR2 |  | Continue rebar works for first section, drilling and making formwork
Fri (17/11) | 17 Nov 2023 | ST58 |  | Casting ongoing. Progressive vol: 148/270m3
Fri (17/11) | 17 Nov 2023 | BH19 |  | In progress, 28m
Fri (17/11) | 17 Nov 2023 | N4 |  | Bottom rebar works on going. Today plan to complete bottom bars and bar chair
Fri (17/11) | 17 Nov 2023 | P8 |  | Pre-boring just started
Fri (17/11) | 17 Nov 2023 | Zone 3 |  | SPPG pipe laying in progress
Fri (17/11) | 17 Nov 2023 | Zone 1 |  | LCH mobilization of excavator for MH1-2
Sun (19/11) | 19 Nov 2023 | ST38 |  | Excavation for Guidewall ongoing
Sun (19/11) | 19 Nov 2023 | St054 |  | Tremie pipe preparation for casting
Sun (19/11) | 19 Nov 2023 | DR2 |  | Wall formwork installation in progress
Sun (19/11) | 19 Nov 2023 | DR2 |  | Continue dowel bar planting
Sun (19/11) | 19 Nov 2023 | Zone 3 |  | Perimeter hoarding installation ongoing
Sun (19/11) | 19 Nov 2023 | P38 to P37 |  | Slope reinstatement works
Sun (19/11) | 19 Nov 2023 | Zone 3 |  | Krishco continue water pipe laying along the slope hoarding
Sun (19/11) | 19 Nov 2023 | Zone 4 ABH-109 |  | SI drilling ongoing, depth 54.5m
Sun (19/11) | 19 Nov 2023 | N5 |  | KTC excavation to FEL
Sun (19/11) | 19 Nov 2023 | N6 |  | No activity
Sun (19/11) | 19 Nov 2023 | N4 |  | CGW Pile cap rebars (side/top) installation works in progress
Sun (19/11) | 19 Nov 2023 | N3 |  | No activity
Sun (19/11) | 19 Nov 2023 | N2 |  | No activity
Sun (19/11) | 19 Nov 2023 | Zone 1 |  | No activity
Sun (19/11) | 19 Nov 2023 | Zone 1 | NLL | DE143 drain works ongoing
Sun (19/11) | 19 Nov 2023 | Zone 2 |  | LCH Existing MH wall (near shell station) hacking work ongoing
Sun (19/11) | 19 Nov 2023 | Near PMH-11 |  | KTC backfilling and compaction works
Sun (19/11) | 19 Nov 2023 | MH2-4 |  | No activity
Sun (19/11) | 19 Nov 2023 | MH2-3 |  | No activity. Current jacking status is at pipe no. 20 towards MH2-1
Sun (19/11) | 19 Nov 2023 | MH2-7 |  | Pipe jacking setting up
Sun (19/11) | 19 Nov 2023 | MH2-6 |  | No activity
Sun (19/11) | 19 Nov 2023 | MH2-5 |  | Hacking works
Sun (19/11) | 19 Nov 2023 | ST223 |  | Working platform preparation
Sun (19/11) | 19 Nov 2023 | DW62 |  | All rebar cages U clip torque wrench inspection checked
Sun (19/11) | 19 Nov 2023 | DW62 |  | 2nd bite cleaning started
Sun (19/11) | 19 Nov 2023 | ST057 |  | 1st bite excavation has commenced
Sun (19/11) | 19 Nov 2023 | ST054 |  | Dwall casting in progress, 14th truck
Sun (19/11) | 19 Nov 2023 | DR2 |  | Wall formwork installation in progress, target to cast 3pm
Sun (19/11) | 19 Nov 2023 | P38 to P37 |  | Continue Slope reinstatement works
Sun (19/11) | 19 Nov 2023 | Zone 3 |  | Perimeter hoarding installation ongoing
Sun (19/11) | 19 Nov 2023 | Zone 3 |  | Krishco continue water pipe laying along the slope
Sun (19/11) | 19 Nov 2023 | ST223 |  | Pre excavation in progress
Sun (19/11) | 19 Nov 2023 | MH2-5 |  | Thrust wall hacking
Sun (19/11) | 19 Nov 2023 | N5 |  | KTC work stopped for the day. Tmr continue excavation
Sun (19/11) | 19 Nov 2023 | N4 |  | CGW continue pilecap rebar installation
Sun (19/11) | 19 Nov 2023 | N2 |  | WH backfilling works around the side of N2
Sun (19/11) | 19 Nov 2023 | Zone 2 |  | LCH Existing MH wall (near shell station) continue hacking work
Sun (19/11) | 19 Nov 2023 | ST54 |  | Hanging bar Uclip torque test inspection was done
Sun (19/11) | 19 Nov 2023 | MH2-7 |  | Hacking works on caisson ring for the entry point of pipe jacking towards MH2-8
Sun (19/11) | 19 Nov 2023 | ST223 |  | Localised inflatable noise panel installation prior to boring. Will monitor noise level once they start trenching
Sun (19/11) | 19 Nov 2023 | DW62 |  | Final koden test
Sun (19/11) | 19 Nov 2023 | DR2 |  | Retaining wall casting completed. 23/63m. 14m3
Sun (19/11) | 19 Nov 2023 | DR2 |  | Night shift team to continue rebar works for part 2 base slab casting,~25m. Tomorrow to cast 20m span
Sun (19/11) | 19 Nov 2023 | Zone 3 |  | No other activity
Sun (19/11) | 19 Nov 2023 | ST223 |  | Trenching started at 9pm
Mon (20/11) | 20 Nov 2023 | ST57 |  | 1st bite trenching at 36.3m
Mon (20/11) | 20 Nov 2023 | ST223 |  | Trenching at lower RPM
Mon (20/11) | 20 Nov 2023 | ST223 |  | 1st bite trenching at 17.9m. Trenching temporarily stopped to clean cutter wheel
Mon (20/11) | 20 Nov 2023 | DW62 |  | Water stop installed. Cage lowering on going
Mon (20/11) | 20 Nov 2023 | ST57 |  | 1st bite trenching at 28m depth
Mon (20/11) | 20 Nov 2023 | MH2-9 |  | 6th layer excavation started
Mon (20/11) | 20 Nov 2023 | ABH-118 |  | Coring in progress, 40.5m
Mon (20/11) | 20 Nov 2023 | Zone 2 | Bet P18-P19 | HSL Premix hacking for bentonite pipe laying across road towards south ramp
Mon (20/11) | 20 Nov 2023 | Zone 2 | P15 | WH kerb hacking for trial trench works P15-bottom piles
Mon (20/11) | 20 Nov 2023 | N5 |  | Installation of barricade and access before continue excavation to FEL
Mon (20/11) | 20 Nov 2023 | N6 |  | No activity
Mon (20/11) | 20 Nov 2023 | N4 |  | CGW rebar installation for pilecap
Mon (20/11) | 20 Nov 2023 | N3 |  | No activity
Mon (20/11) | 20 Nov 2023 | N2 |  | No activity
Mon (20/11) | 20 Nov 2023 | P11-2 |  | LE trial trench works ongoing
Mon (20/11) | 20 Nov 2023 | P8-2 |  | LE preboring works for ERSS installation
Mon (20/11) | 20 Nov 2023 | PMH3 |  | SPPG doing cable protection works
Mon (20/11) | 20 Nov 2023 | ST223 |  | Excavation resume
Mon (20/11) | 20 Nov 2023 | DW62 |  | 5/6 rebar cages lowering
Mon (20/11) | 20 Nov 2023 | ST57 |  | 1st bite depth now at 31m depth
Mon (20/11) | 20 Nov 2023 | DR2 |  | Retaining wall part 2 rebar work status. Balance coupler bars
Mon (20/11) | 20 Nov 2023 | DW62 |  | Hanging bar installation
Mon (20/11) | 20 Nov 2023 | ST223 |  | 1st bite current excavation depth at 24m
Mon (20/11) | 20 Nov 2023 | MH2-5 |  | Thrust block hacking till 930pm
Mon (20/11) | 20 Nov 2023 | MH5-2 |  | Existing MH wall hacking till 930 pm. 900/1.1m
Mon (20/11) | 20 Nov 2023 | MH1-2 |  | Manual excavation for 1st layer, work till 930pm
Mon (20/11) | 20 Nov 2023 | ST223 |  | 1st bite trenching at 31m depth
Mon (20/11) | 20 Nov 2023 | P29-30 |  | Team 1 backfilling works for the re-laid sppg pipe
Mon (20/11) | 20 Nov 2023 | DW62 |  | Casting continue. 136/148 m3, balance 2 loads
Mon (20/11) | 20 Nov 2023 | DR2 |  | WH arranging to pump water. CGS here
Tue (21/11) | 21 Nov 2023 | DR2 |  | Continue rebar installation for Bay 2 and 3. Today target to cast Bay 2 base
Tue (21/11) | 21 Nov 2023 | Blk 4 |  | ST57 second bite excavation started
Tue (21/11) | 21 Nov 2023 | Zone 3 BH21 |  | In progress, 35m
Tue (21/11) | 21 Nov 2023 | BH20 |  | Started and in progress
Tue (21/11) | 21 Nov 2023 | Zone 3 |  | SPPG preparing for backfilling and continue pipe laying (2 teams)
Tue (21/11) | 21 Nov 2023 | P28 |  | Excavation ongoing for ST33 guidewall
Tue (21/11) | 21 Nov 2023 | ST223 |  | 2nd bite excavation in progress
Tue (21/11) | 21 Nov 2023 | MH2-8 |  | Dewatering ongoing prior starting 7th layer ring
Tue (21/11) | 21 Nov 2023 | ST223 2nd bite started at 11 |  | 55 pm. Wee guan works stopped for dinner break, noise level reduced from 65.x-63.x
Tue (21/11) | 21 Nov 2023 | ST223 |  | 2nd bite trenching at 8m depth
Tue (21/11) | 21 Nov 2023 | DR2 |  | Water pumping status. Pumping continue. Coupler bar installation completed for 20m span
Tue (21/11) | 21 Nov 2023 | ST57 |  | Trenching continue. 37.7m
Tue (21/11) | 21 Nov 2023 | MH2-9 |  | 6th layer excavation in progress. Plan to cast tonight if no heavy rain
Tue (21/11) | 21 Nov 2023 | ST223 |  | Cutter wheel replacement in progress
Tue (21/11) | 21 Nov 2023 | Exit 2 DW59 |  | 1st bite excavation in progress
Tue (21/11) | 21 Nov 2023 | DR2 |  | Works on hold due to downpour. Bay 2 base formwork installation in pogress & bay 3 rebar works ongoing. Target to cast base tonight if no heavy rain
Tue (21/11) | 21 Nov 2023 | DR2 |  | 3rd part hole cleaning for drill depth inspection
Tue (21/11) | 21 Nov 2023 | Zone 2 |  | HSL continue bentonite pipe laying
Tue (21/11) | 21 Nov 2023 | N5 |  | KTC excavation to FEL
Tue (21/11) | 21 Nov 2023 | N4 |  | Water pumping in progress before continue rebar installation for pile cap
Tue (21/11) | 21 Nov 2023 | N3 |  | ERSS removal in progress
Tue (21/11) | 21 Nov 2023 | N2 |  | No activity
Tue (21/11) | 21 Nov 2023 | P8-2 |  | LE preboring works for ERSS installation
Tue (21/11) | 21 Nov 2023 | ST223 |  | 2nd bite trenching at 18m depth
Tue (21/11) | 21 Nov 2023 | MH2-7 |  | Slurry pipe installation in progress. Tomorrow to be ready for jacking work
Tue (21/11) | 21 Nov 2023 | ST57 |  | Cutter wheel teeth replacement
Tue (21/11) | 21 Nov 2023 | MH2-5 |  | Thrust block hacking and removal
Tue (21/11) | 21 Nov 2023 | ST57 |  | 1st bite completed. Internal Koden test
Tue (21/11) | 21 Nov 2023 | DR2 |  | Part 3 dowel bar installation on going
Tue (21/11) | 21 Nov 2023 | MH2-8 |  | 7th layer formwork closing
Tue (21/11) | 21 Nov 2023 | N5 |  | Excavation to final level continue till 930pm
Tue (21/11) | 21 Nov 2023 | N4 |  | Tie rod welding till 10pm only. No workers arranged for night shift. Tomorrow to continue shearlinks installation
Tue (21/11) | 21 Nov 2023 | N2 |  | Slope protection casting
Tue (21/11) | 21 Nov 2023 | MH1-2 |  | No more activity
Tue (21/11) | 21 Nov 2023 | P29-P30 |  | Tonight wee guan to continue excavation to replace sppg pipe here
Tue (21/11) | 21 Nov 2023 | DW59 |  | 2nd bite trenching on going
Tue (21/11) | 21 Nov 2023 | ST57 |  | 2nd bite internal koden test
Tue (21/11) | 21 Nov 2023 | MH2-9 |  | Excavation in progress for caisson shaft. Plan to cast today
Tue (21/11) | 21 Nov 2023 | DR2 |  | 3rd bay balance 10m to complete drilling tonight
Wed (22/11) | 22 Nov 2023 | DR2 |  | Today to continue bay 2 wall formwork installation and bay 3 rebar works. Bay 2 base was cast yesterday
Wed (22/11) | 22 Nov 2023 | MH1-2 |  | 1st layer casting started. Noise level will be monitored at Loyang rise
Wed (22/11) | 22 Nov 2023 | ST223 |  | Trimming done. Still need to do chiselling
Wed (22/11) | 22 Nov 2023 | DW59 |  | Trenching temporarily stopped due to desanding machine pump spoil. Repair works on going
Wed (22/11) | 22 Nov 2023 | ST57 |  | Cleaning in progress
Wed (22/11) | 22 Nov 2023 | DR2 |  | Bay 2 wall rebar tying continue
Wed (22/11) | 22 Nov 2023 | DR2 |  | 3rd bay drilling continue. 2 pax
Wed (22/11) | 22 Nov 2023 | ST223 |  | Chiselling on going. All readings ok
Wed (22/11) | 22 Nov 2023 | ST57 |  | Rebar cages U-clip torque test
Wed (22/11) | 22 Nov 2023 | ST57 |  | 8 rebar cages including hanging bar torque test done
Wed (22/11) | 22 Nov 2023 | DR2 |  | 3rd bay drilling continue. Est balance 25 holes
Wed (22/11) | 22 Nov 2023 | ST57 |  | Desanding in progress
Wed (22/11) | 22 Nov 2023 | DW59 |  | Rebar Cages torque test
Wed (22/11) | 22 Nov 2023 | DW59 |  | 3 rebar cages torque test done including hanging bars
Wed (22/11) | 22 Nov 2023 | ST223 |  | Chiselling in progress to remove end plate
Wed (22/11) | 22 Nov 2023 | ST223 |  | Continue chiselling
Wed (22/11) | 22 Nov 2023 | P30 |  | Tonight wee guan will continue to replace sppg pipe here. Target 12m
Wed (22/11) | 22 Nov 2023 | ST53 |  | 1st bite excavation started
Wed (22/11) | 22 Nov 2023 | ST57 |  | Rebar cages installation, 5/8 cages
Wed (22/11) | 22 Nov 2023 | DR2 |  | Dayshift work ended. Night shift team still on the way
Wed (22/11) | 22 Nov 2023 | Zone 3 P37 |  | Lucky joint here to remove existing M1 manhole
Wed (22/11) | 22 Nov 2023 | MH2-4 |  | Chamber ring for casting, concrete on site
Wed (22/11) | 22 Nov 2023 | N4 |  | Casting completed earlier
Wed (22/11) | 22 Nov 2023 | Zome 1 MH1-2 |  | 1st layer formwork closing. Target to cast by 1030 pm. Advised LCH to put up noise ballon
Thu (23/11) | 23 Nov 2023 | MH2-8 |  | Preparing to start next layer excavation
Thu (23/11) | 23 Nov 2023 | MH6-1 |  | Touch up work to sewer line
Thu (23/11) | 23 Nov 2023 | P30-P31 |  | Power duct rectification
Thu (23/11) | 23 Nov 2023 | Zone 2 |  | Site surveying with SCDF for the upcoming drill exercise which will be on 2nd week of Jan 2024
Thu (23/11) | 23 Nov 2023 | N6 |  | Water pumping works in progress, KTC to continue backfilling works in afternoon
Thu (23/11) | 23 Nov 2023 | N5 |  | Excavation to FEL completed. HSL to start pile head hacking in afternoon
Thu (23/11) | 23 Nov 2023 | ST223 |  | Chisel c-lug welding
Thu (23/11) | 23 Nov 2023 | P30 |  | SPPG pipe laying, 12m
Thu (23/11) | 23 Nov 2023 | ST57 |  | No.8 rebar cages lapping on going
Thu (23/11) | 23 Nov 2023 | ST53 |  | 1st bite excavation at 21.5m
Thu (23/11) | 23 Nov 2023 | MH2-8 |  | Cage ladder installed. Preparing to continue excavation for 8th layer
Thu (23/11) | 23 Nov 2023 | ST223 |  | C-lug welding broken again, welding in progress
Thu (23/11) | 23 Nov 2023 | ST57 |  | All rebar cages lowered. Tremie pipe installation in progress
Thu (23/11) | 23 Nov 2023 | DR2 |  | Wall rebar works completed for 3rd bay
Thu (23/11) | 23 Nov 2023 | MH2-7 to MH2-8 |  | 7th nos pipe jacking in progress 7/35nos. (Around pipe nos 33 will reach MH2-8 caisson shaft wall)
Thu (23/11) | 23 Nov 2023 | MH2-5 |  | Thrust block hacking done
Thu (23/11) | 23 Nov 2023 | MH1-2 |  | Hard barricade installation done
Thu (23/11) | 23 Nov 2023 | S4-5 |  | Boring done, 18m. Cleaning and preparation for casting
Thu (23/11) | 23 Nov 2023 | ST60 |  | Koden test for preboring. ST62: preboring reached 14m. LCH working until 10PM
Thu (23/11) | 23 Nov 2023 | ST223 |  | 2nd bite cleaning in progress
Thu (23/11) | 23 Nov 2023 | P30-31 |  | Continue SPPG pipe laying rectification
Thu (23/11) | 23 Nov 2023 | ST53 |  | 2nd bite excavation in progress
Thu (23/11) | 23 Nov 2023 | DR2 |  | 3rd bay slab casting in progress
Thu (23/11) | 23 Nov 2023 | Zone 4 |  | No activity
Thu (23/11) | 23 Nov 2023 | Exit 1 and CCE |  | No other activity. End plate welding works ongoing
Thu (23/11) | 23 Nov 2023 | S4-5 |  | Casting in progress
Fri (24/11) | 24 Nov 2023 | ST223 |  | Last lapping ongoing (8/8nos cage)
Fri (24/11) | 24 Nov 2023 | ST223 |  | Hanging bar u-clip inspection done
Fri (24/11) | 24 Nov 2023 | S4-5 |  | Casting completed at 22:36hrs
Fri (24/11) | 24 Nov 2023 | P30-31 |  | Concrete haunching done for 12m length. Backfilling ongoing. The team also continue excavation for next pipe laying section plan ard 6m tonight
Fri (24/11) | 24 Nov 2023 | ST53 |  | 2nd bite excavation in progress
Fri (24/11) | 24 Nov 2023 | DR2 |  | 3rd bay slab cast. Casting completed at 21:40hrs last night
Fri (24/11) | 24 Nov 2023 | DR2 |  | Localised hacking of existing drain slab in progress (Part 1A)
Fri (24/11) | 24 Nov 2023 | Exit 2 DW59 |  | 3/3nos rebar cages installed. Hanging bar installation ongoing
Fri (24/11) | 24 Nov 2023 | ST223 |  | Cleaning & desanding completed. Final koden check in progress
Fri (24/11) | 24 Nov 2023 | P25 |  | M1 pipe laying by term contractor. Plan to lay ard 5m tonight
Fri (24/11) | 24 Nov 2023 | P30-31 |  | Only 3m SPPG laid tonight laid tonight
Fri (24/11) | 24 Nov 2023 | DR2 |  | Works continue for part 1A
Fri (24/11) | 24 Nov 2023 | DW59 |  | Preparing for casting
Fri (24/11) | 24 Nov 2023 | ST223 |  | Waterstop end plate installation in progress
Fri (24/11) | 24 Nov 2023 | MH1-2 |  | Affected junction eye OG box shifting done by woh hup
Fri (24/11) | 24 Nov 2023 | MH2-5 |  | Base rebar works in progress. Works till 10pm
Fri (24/11) | 24 Nov 2023 | S3-1 |  | Casting completed. Housekeeping ongoing
Fri (24/11) | 24 Nov 2023 | N6 |  | KTC continue backfilling works till 930pm
Fri (24/11) | 24 Nov 2023 | N5 |  | BP rebar cutting till 930pm
Fri (24/11) | 24 Nov 2023 | N3 |  | Barricades and toe boards installation
Fri (24/11) | 24 Nov 2023 | N2 |  | No activity
Fri (24/11) | 24 Nov 2023 | ST223 |  | Cage 3A and 4A lapping in progress (7/8nos)
Fri (24/11) | 24 Nov 2023 | P31 |  | Tonight WG plan for SPPG pipe laying rectification and continue subsequent excavation & support installation
Fri (24/11) | 24 Nov 2023 | ST62 |  | Preboring PB2 ongoing
Fri (24/11) | 24 Nov 2023 | ST59 |  | First bite excavation in progress
Fri (24/11) | 24 Nov 2023 | P36 |  | WG to remove power duct pipes for rectification
Fri (24/11) | 24 Nov 2023 | DR2 |  | Tonight plan for debris removal for benching slab and continue wall formwork for Bay 3
Fri (24/11) | 24 Nov 2023 | Exit 1 and CCE |  | Only endplate welding works. No other activity
Fri (24/11) | 24 Nov 2023 | MH2-9 |  | Started excavation for 7th layer. Formwork removal done
Sat (25/11) | 25 Nov 2023 | DR2 |  | Continue 3rd bay wall formwork installation (6pax)
Sat (25/11) | 25 Nov 2023 | ST59 |  | Continue first bite excavation, 29.6m
Sat (25/11) | 25 Nov 2023 | P31 |  | SPPG pipes laid 3m tonight. Concrete haunching ongoing
Sat (25/11) | 25 Nov 2023 | ST223 |  | All rebar cages lowered. Preparation for casting ongoing
Sat (25/11) | 25 Nov 2023 | Near MH2-8 |  | M1 pipes laid tonight, 8m. Reinstatement in progress
Sat (25/11) | 25 Nov 2023 | ST223 |  | Casting in progress
Sat (25/11) | 25 Nov 2023 | MH2-7 |  | Preparing for pipe 17 jacking — 16/35nos done. Team working till 10pm
Sat (25/11) | 25 Nov 2023 | South ramp S4-2 |  | Casting was completed this afternoon. No more activity now
Sat (25/11) | 25 Nov 2023 | North ramp N5 |  | Only ECO workers doing the water pipe works. No other activity
Sat (25/11) | 25 Nov 2023 | P30-31 |  | Tonight plan to continue power duct pipe laying
Sat (25/11) | 25 Nov 2023 | ST53 |  | 2nd bite excavation in progress
Sat (25/11) | 25 Nov 2023 | DR2 |  | 3rd bay wall was cast this afternoon
Sat (25/11) | 25 Nov 2023 | P34 |  | WG to continue remove power duct pipes for rectification
Sat (25/11) | 25 Nov 2023 | ST26 |  | First bite excavation in progress
Sat (25/11) | 25 Nov 2023 | DW28 |  | Internal koden check ongoing
Sun (26/11) | 26 Nov 2023 | DW28 |  | Final koden check has also been done
Sun (26/11) | 26 Nov 2023 | DW28 |  | Rebar cages and hanging bar u-clip inspection done
Sun (26/11) | 26 Nov 2023 | P30-31 |  | Shoring removal ongoing
Sun (26/11) | 26 Nov 2023 | DR2 |  | Continue hacking of existing drain base slab, Part 1A
Sun (26/11) | 26 Nov 2023 | ST53 |  | Cutter body up and washing ongoing. 2nd bite current depth ard 26m
Sun (26/11) | 26 Nov 2023 | P34 |  | Shoring installation ongoing
Sun (26/11) | 26 Nov 2023 | ST53 |  | Rebar cages and hanging bar u-clip inspection done
Sun (26/11) | 26 Nov 2023 | ST53 |  | 3rd bite excavation in progress
Sun (26/11) | 26 Nov 2023 | P34 |  | Shoring installation completed
Sun (26/11) | 26 Nov 2023 | P31 |  | Works completed for the night
Sun (26/11) | 26 Nov 2023 | MH2-7 to MH2-8 |  | Pipe No-21 jacking done. Pipe No-22 lower down. Total 21/35 done. (Estimate around 33 pipes to reach MH2-8 caisson shaft)
Sun (26/11) | 26 Nov 2023 | MH2-3 to MH2-1 |  | Pipe jacking machine push in and all the cable/ hoses connection done. To continue jacking tomorrow
Mon (27/11) | 27 Nov 2023 | MH2-3 |  | 1st pipe lowered down for jacking towards MH2-1
Mon (27/11) | 27 Nov 2023 | MH2-4 |  | No activity
Mon (27/11) | 27 Nov 2023 | Zone 4 P48 |  | Trial trench in progress
Mon (27/11) | 27 Nov 2023 | Zone 4 |  | HDD works by term contractor
Mon (27/11) | 27 Nov 2023 | Zone 4 P49 |  | Trial trench in progress
Mon (27/11) | 27 Nov 2023 | Zone 4 P50 |  | Preparation to hack for trial trench works
Mon (27/11) | 27 Nov 2023 | Zone 4 |  | Singtel works by Fiber Reach for pipe laying towards new MH. Lane closure at first lane LA not under CR106
Mon (27/11) | 27 Nov 2023 | N5 |  | Pile head final trimming to COL
Mon (27/11) | 27 Nov 2023 | N6 |  | KTC soil compaction works then NDT
Mon (27/11) | 27 Nov 2023 | N4 |  | CGW patching works
Mon (27/11) | 27 Nov 2023 | N3 |  | No activity
Mon (27/11) | 27 Nov 2023 | N2 |  | No activity
Mon (27/11) | 27 Nov 2023 | P8-2 |  | Continue preboring works for soldier piles & steel plate installation
Mon (27/11) | 27 Nov 2023 | ST53 |  | Cleaning ongoing
Mon (27/11) | 27 Nov 2023 | P31 |  | WG continue excavation for pipe laying rectification works
Mon (27/11) | 27 Nov 2023 | ST26 |  | Waterstop side trimming ongoing
Mon (27/11) | 27 Nov 2023 | MH1-2 |  | Housekeeping & removal of excavated soil in progress
Mon (27/11) | 27 Nov 2023 | Zone 1 NLL |  | DE143 works
Mon (27/11) | 27 Nov 2023 | Zone 2 | Near P6 | WG excavation works to expose previous laid SPTel pipe. To check on the location of failed mandrel test
Mon (27/11) | 27 Nov 2023 | Zone 2, South ramp BP S3-2 |  | Pre boring & casing installation completed. Now preparation for continual of boring works
Mon (27/11) | 27 Nov 2023 | MH5-2 |  | Benching works ongoing
Mon (27/11) | 27 Nov 2023 | BH190 |  | In progress, 28m
Mon (27/11) | 27 Nov 2023 | DR2 |  | Continue hacking of existing drain wall
Mon (27/11) | 27 Nov 2023 | Zone 3 BH91 |  | Preparing to start, BH90: In progress, 24m
Mon (27/11) | 27 Nov 2023 | MH2-3 |  | Pipe jacking towards 2-1, 3rd pipe on going
Mon (27/11) | 27 Nov 2023 | MH2-5 |  | Base slab rebar works on going
Mon (27/11) | 27 Nov 2023 | P34 |  | WG plan to lay power duct pipes today, ard 6m. Manual clearing of soil ongoing
Mon (27/11) | 27 Nov 2023 | N5 |  | Final trimming of pile head to COL
Mon (27/11) | 27 Nov 2023 | N4 |  | Housekeeping and access erection for concrete plug casting
Mon (27/11) | 27 Nov 2023 | S3-2 |  | Boring completed. Preparation for rebar cage installation
Mon (27/11) | 27 Nov 2023 | S4-6 |  | Setting out, today to start pre-boring and casing installation
Mon (27/11) | 27 Nov 2023 | MH5-2 |  | Hacking of existing sewer shaft today to complete
Mon (27/11) | 27 Nov 2023 | MH1-2 |  | 2nd layer half formwork closing. To cast today
Mon (27/11) | 27 Nov 2023 | S3-2 |  | Rebar cages and hanging bar installed. Now preparation for casting
Mon (27/11) | 27 Nov 2023 | N5 |  | Cleaning ongoing
Mon (27/11) | 27 Nov 2023 | MH2-5 |  | Base slab rebar has been inspected. Now preparing for formwork installation
Mon (27/11) | 27 Nov 2023 | ST39-40 |  | Guidewall was cast earlier today
Mon (27/11) | 27 Nov 2023 | ST37-35 |  | Guidewall casting completed too
Mon (27/11) | 27 Nov 2023 | ST53 |  | Rebar cage installation in progress
Mon (27/11) | 27 Nov 2023 | ST59 |  | 2nd bite excavation in progress
Mon (27/11) | 27 Nov 2023 | DR2 |  | Currently dayshift team has ended for the day. Night team will come ard 8pm
Mon (27/11) | 27 Nov 2023 | MH2-7 to MH2-8 |  | Pipe No-27 jacking in progress
Mon (27/11) | 27 Nov 2023 | MH2-3 to MH2-1 |  | Pipe No 6 jacking done. To continue pipe No 7
Mon (27/11) | 27 Nov 2023 | MH1-2 |  | Concrete on site for 2nd layer 1st part casting
Mon (27/11) | 27 Nov 2023 | P29 |  | ST37-35 guidewall wall formwork installation ongoing. Plan for casting after lunch
Mon (27/11) | 27 Nov 2023 | ST39-40 |  | Preparation for guidewall casting
Mon (27/11) | 27 Nov 2023 | BH119 |  | In progress, 10m
Mon (27/11) | 27 Nov 2023 | DR2 |  | Existing drain wall hacking in progress
Mon (27/11) | 27 Nov 2023 | DR2 |  | Bay 3 wall formwork dismantling ongoing
Mon (27/11) | 27 Nov 2023 | BH91 |  | Hand auger in progress
Mon (27/11) | 27 Nov 2023 | BH90 |  | In progress, 20m
Tue (28/11) | 28 Nov 2023 | Zone 3 |  | BH91 and BH90 in progress
Tue (28/11) | 28 Nov 2023 | MH2-5 |  | Base slab curing
Tue (28/11) | 28 Nov 2023 | MH2-4 |  | Today plan for backfilling works. Water pumping
Tue (28/11) | 28 Nov 2023 | MH2-3 |  | Access construction, no other activity
Tue (28/11) | 28 Nov 2023 | DR2 |  | Continue hacking of existing drain wall
Tue (28/11) | 28 Nov 2023 | N5 |  | Rebar works on going. Plan to complete until top bars today
Tue (28/11) | 28 Nov 2023 | N4 |  | Concrete plug casting this afternoon
Tue (28/11) | 28 Nov 2023 | P10 |  | Platform preparation for pre-boring
Tue (28/11) | 28 Nov 2023 | P8 |  | SP and LP installation
Tue (28/11) | 28 Nov 2023 | Zone 1 |  | SPPG here doing Trial hole to find installed pipe for their cable pulling. Pick up point near AWWA homes TT completed yesterday
Tue (28/11) | 28 Nov 2023 | Zone 4 P48 |  | Continue trial trench
Tue (28/11) | 28 Nov 2023 | P49 |  | Continue trial trench
Tue (28/11) | 28 Nov 2023 | P50 |  | Dewatering ongoing before continuing trial trench
Tue (28/11) | 28 Nov 2023 | Zone 4 |  | Fiber reach continue works for pipe laying along Loyang Ave. Lane closure not under CR106
Tue (28/11) | 28 Nov 2023 | BH190 |  | In progress, 37m
Tue (28/11) | 28 Nov 2023 | MH1-2 |  | No activity. 2nd layer half cast yesterday
Tue (28/11) | 28 Nov 2023 | Zone 2 in front of shell |  | Lucky joint here excavating for sptel mandrel test
Tue (28/11) | 28 Nov 2023 | S4-6 |  | Boring works on going
Tue (28/11) | 28 Nov 2023 | JTC blk 2 |  | Continue levelling and steel plates laying
Tue (28/11) | 28 Nov 2023 | ST26 |  | Waterstop extraction in progress
Tue (28/11) | 28 Nov 2023 | ST53 |  | Casting completed. Total vol: 210m3
Tue (28/11) | 28 Nov 2023 | MH2-7 |  | Pipe jacking towards MH2-8, 29/35 pipes
Tue (28/11) | 28 Nov 2023 | MH2-4 |  | Preparation for backfilling works
Tue (28/11) | 28 Nov 2023 | Zone 2 P18 |  | LCH working here to check existing sewer for discharge pipe connection
Tue (28/11) | 28 Nov 2023 | S4-6 |  | Boring works completed
Tue (28/11) | 28 Nov 2023 | S3-3 |  | Area preparation for pre-boring and casing installation
Tue (28/11) | 28 Nov 2023 | N6 |  | No activity
Tue (28/11) | 28 Nov 2023 | N5 |  | Continue rebar installation for pile cap
Tue (28/11) | 28 Nov 2023 | N4 |  | Concrete plug casting arranged at 5pm
Tue (28/11) | 28 Nov 2023 | P31 |  | WG preparing to lay power duct pipes. Plan ard 9m
Tue (28/11) | 28 Nov 2023 | BH119 |  | Preparing for packer test. Current depth at 34.5m
Tue (28/11) | 28 Nov 2023 | DR2 |  | Continue hacking of existing drain base slab
Tue (28/11) | 28 Nov 2023 | MH1-2 |  | No activity. 2nd layer half cast yesterday. LCH doing housekeeping works
Tue (28/11) | 28 Nov 2023 | Zone 2 P20 |  | M1 cable pulling started here towards loyang lane. Plan to complete this week until loyang to new manhole near TPk
Tue (28/11) | 28 Nov 2023 | MH2-7 |  | Jacking status still at no. 29 pipe. Hard soil
Tue (28/11) | 28 Nov 2023 | ST26 |  | C-lug welding to trim end plate
Tue (28/11) | 28 Nov 2023 | JTC blk 2 |  | Platform preparation for dwall continue
Tue (28/11) | 28 Nov 2023 | ST42 and 43 |  | Old pavement hacking and preparation for TT
Tue (28/11) | 28 Nov 2023 | Zone 3 P31-32 |  | Today sppg re-laid pipe 9m length
Tue (28/11) | 28 Nov 2023 | DR2 |  | Drain slab concrete plug casting
Tue (28/11) | 28 Nov 2023 | MH2-7 to MH2-8 |  | Pipe No-30 jacking in progress
Tue (28/11) | 28 Nov 2023 | MH2-3 to MH2-1 |  | Day shift team already go back. Night shift team yet to come
Tue (28/11) | 28 Nov 2023 | JTC blk 2 |  | Ground levelling and arranging steel plates ongoing
Tue (28/11) | 28 Nov 2023 | ST53 |  | Casting in progress
Tue (28/11) | 28 Nov 2023 | BH119 |  | In progress, 28m
Tue (28/11) | 28 Nov 2023 | MH2-7 |  | Pipe jacking towards MH2-8, 28/35 pipes
Wed (29/11) | 29 Nov 2023 | JTC blk 2 |  | HSL mobilising materials
Wed (29/11) | 29 Nov 2023 | P31 |  | Backfilling ongoing by WG
Wed (29/11) | 29 Nov 2023 | JTC blk 4 |  | ST59 3rd bite in progress, 12m
Wed (29/11) | 29 Nov 2023 | BH119 |  | In progress, 38m
Wed (29/11) | 29 Nov 2023 | DR2 |  | Existing drain wall demolition completed, Concrete plug construction for part 1A and 1B was cast yesterday, Ongoing hacking for part 2A and 2B
Wed (29/11) | 29 Nov 2023 | P39 |  | Power duct pipes removal by WG for rectification works
Wed (29/11) | 29 Nov 2023 | P40 |  | Starhub pipes laid, 18m
Wed (29/11) | 29 Nov 2023 | P21 |  | Backfilling for stage 1 diversion along slip road started
Wed (29/11) | 29 Nov 2023 | P48 |  | Continue trial trench
Wed (29/11) | 29 Nov 2023 | P50 |  | Trial trench in progress. Currently dewatering ongoing
Wed (29/11) | 29 Nov 2023 | P51 |  | Clearing debris prior starting trial trench
Wed (29/11) | 29 Nov 2023 | Zone 4 |  | Preparation for Gate 8 works. Plan for casting base tmr
Wed (29/11) | 29 Nov 2023 | N5 |  | Formwork closing. Tomorrow to cast
Wed (29/11) | 29 Nov 2023 | P10-P11 |  | Drain hacking on going
Wed (29/11) | 29 Nov 2023 | ST59 |  | U-clip inspection for hanging bar and rebar cage done (6/8nos rebar cage). Balance 2nos (cage 2A and 3A) to inspect once crane is available to unload from the stack
Wed (29/11) | 29 Nov 2023 | Zone 1 |  | HSL delivery of mud tank and water tank for piling works
Wed (29/11) | 29 Nov 2023 | Zone 1 |  | Sptel pipe jamming works near new MH
Wed (29/11) | 29 Nov 2023 | N5 |  | Continue formwork installation
Wed (29/11) | 29 Nov 2023 | MH2-5 |  | Works ongoing till 10pm
Wed (29/11) | 29 Nov 2023 | MH2-4 |  | Preparation to backfill
Wed (29/11) | 29 Nov 2023 | DR2 concrete plug construction |  | To cast part 2A and 2B
Wed (29/11) | 29 Nov 2023 | ST59 |  | 3rd bite excavation was completed, 39.5m. Now endplate removal and cutter body washing ongoing
Wed (29/11) | 29 Nov 2023 | P39 |  | WG power duct shoring installation & backfilling next to shoring. Have reminded the team to barricade once done
Wed (29/11) | 29 Nov 2023 | MH2-8 |  | Jacking machine already break through. Now erection of platform for machine retrival
Wed (29/11) | 29 Nov 2023 | MH2-3 to MH2-1 |  | Preparing for Pipe No-21 jacking work
Wed (29/11) | 29 Nov 2023 | MH2-4 |  | Continue backfilling until 10PM
Wed (29/11) | 29 Nov 2023 | MH1-2 |  | Tonight LCH provide night shift team for 2nd layer 2nd part excavation and support installation to existing services
Thu (30/11) | 30 Nov 2023 | ST26 |  | Rebar cage u-clip inspection completed
Thu (30/11) | 30 Nov 2023 | JTC blk 2 |  | Preboring started for ST33
Thu (30/11) | 30 Nov 2023 | Blk 2 |  | ST38 first bite excavation in progress
Thu (30/11) | 30 Nov 2023 | Zone 4 |  | Top soil removal on going to do TT for SPPG duct corridor. Team 1
Thu (30/11) | 30 Nov 2023 | P39 |  | WG target to lay power duct pipes today, 12m
Thu (30/11) | 30 Nov 2023 | P40 |  | Starhub continue excavation for pipe laying. Target ard 24m
Thu (30/11) | 30 Nov 2023 | BH119 |  | In progress, 40.5m
Thu (30/11) | 30 Nov 2023 | DR2 |  | Clearing debris ongoing
Thu (30/11) | 30 Nov 2023 | P50 & P51 |  | TT on going for bored pile. Total 3 teams for TT
Thu (30/11) | 30 Nov 2023 | ST59 |  | Balance 2nos rebar cage u-clip inspection completed
Thu (30/11) | 30 Nov 2023 | ST41 & ST42 | half | Guidewall construction ongoing. Plan for casting today
Thu (30/11) | 30 Nov 2023 | MH2-3 to MH2-1 |  | Pipe No 22 jacking done. Preparing for Pipe No-23 jacking
Thu (30/11) | 30 Nov 2023 | MH2-7 |  | Jacking towards MH2-8 completed as of yesterday. Total 33nos. pipes
Thu (30/11) | 30 Nov 2023 | MH2-5 |  | Pipe connection in progress for benching works
Thu (30/11) | 30 Nov 2023 | N5 pilecap |  | Rebars & formworks checked. Now pending concrete trucks to arrive for casting
Thu (30/11) | 30 Nov 2023 | P8-2 |  | KTC continue excavation to S1 layer for waler installation. Today to complete
Thu (30/11) | 30 Nov 2023 | P9-2 |  | Drain hacking and removal works for ERSS preboring works
Thu (30/11) | 30 Nov 2023 | MH2-3 to MH2-1 |  | Current status of jacking is Pipe No-25
Thu (30/11) | 30 Nov 2023 | MH2-3 |  | Jacking to 2-1 to continue. 24/75 pipes completed
Thu (30/11) | 30 Nov 2023 | N5 |  | Pile cap casting completed earlier
Thu (30/11) | 30 Nov 2023 | DW29 |  | 2nd bite trenching at 18m depth
Thu (30/11) | 30 Nov 2023 | ST26 |  | 4/6 cage lowering
Thu (30/11) | 30 Nov 2023 | ST55 |  | 1st bite excavation at 22m depth
Thu (30/11) | 30 Nov 2023 | ST59 |  | 6/8 rebar lapping on going
Thu (30/11) | 30 Nov 2023 | DR2 |  | Tonight no activity
Fri (01/12) | 01 Dec 2023 | Zone 4 |  | 1 team here for TT
Fri (01/12) | 01 Dec 2023 | P47 |  | Wee guan provide one team for TT for power duct laying
Fri (01/12) | 01 Dec 2023 | MH2-3 |  | Pipe jacking also stopped due to continuous rain
Fri (01/12) | 01 Dec 2023 | Gate 5 access |  | Still under control
Fri (01/12) | 01 Dec 2023 | DR2 |  | Condition getting better
Fri (01/12) | 01 Dec 2023 | DW29 |  | Internal Koden test
Fri (01/12) | 01 Dec 2023 | ST26 |  | 5/6 rebar cage lapping
Fri (01/12) | 01 Dec 2023 | ST55 |  | 1st bite trenching continue
Fri (01/12) | 01 Dec 2023 | ST59 |  | 6th rebar cage lapping inspected with minor comments. Workers advised to take a break and continue after the rain subside
Fri (01/12) | 01 Dec 2023 | DW29 |  | Cutter wheel teeth changing
Fri (01/12) | 01 Dec 2023 | N4 |  | Preparation for backfilling works to s1 level for waler removal
Fri (01/12) | 01 Dec 2023 | N1 |  | KTC excavation works to S1 layer
Fri (01/12) | 01 Dec 2023 | P9-2 |  | Preboring for solider piles in progress
Fri (01/12) | 01 Dec 2023 | P8-2 |  | Waler brackets installation in progress
Fri (01/12) | 01 Dec 2023 | MH2-5 |  | Wall rebar work in progress
Fri (01/12) | 01 Dec 2023 | MH2-4 |  | Backfilling around shaft
Fri (01/12) | 01 Dec 2023 | ST26 |  | Hanging bar u-clip torque test
Fri (01/12) | 01 Dec 2023 | N4 |  | KTC preparing to resume backfilling
Fri (01/12) | 01 Dec 2023 | DW29 |  | Trimming started at waterstop side
Fri (01/12) | 01 Dec 2023 | MH2-3 |  | Pipe jacking 26/75 pipes completed. 27th pipe in progress
Fri (01/12) | 01 Dec 2023 | ST26 |  | Last cage lapping (6/6)
Fri (01/12) | 01 Dec 2023 | ST38 |  | Excavation temporarily stopped due to desander sunction pump elbow leaking. Rectification on going
Fri (01/12) | 01 Dec 2023 | ST55 |  | 1st bite at 24.8m
Fri (01/12) | 01 Dec 2023 | ST59 |  | 7/8 rebar cages installed
Fri (01/12) | 01 Dec 2023 | MH1-2 |  | 2nd layer 2nd part excavation for caisson
Fri (01/12) | 01 Dec 2023 | ST26 |  | Casting continue
Fri (01/12) | 01 Dec 2023 | P23 |  | Soil bundwall construction to contain silty water from Loyang avenue
Fri (01/12) | 01 Dec 2023 | MH2-3 |  | Pipe jacking to continue for night shift. 26/75 pipes completed
Fri (01/12) | 01 Dec 2023 | MH5-2 |  | Pipe pull back to complete tonight. 3/6. Completed
Fri (01/12) | 01 Dec 2023 | MH1-2 |  | 2nd layer 2nd part rebar installation. Plan to cast after 12mn
Fri (01/12) | 01 Dec 2023 | ST38 |  | 3rd bite trenching on going at 8m depth
Fri (01/12) | 01 Dec 2023 | MH2-8 |  | Workers arranging pumps to clear rain water inside shaft
Fri (01/12) | 01 Dec 2023 | ST55 |  | 1st bite completed. Preparation for internal koden then will proceed to 2nd bite
Fri (01/12) | 01 Dec 2023 | Zone 3 P36 |  | Tonight SPPG pipe replacement will continue here. Target 9m
Sat (02/12) | 02 Dec 2023 | DW29 |  | Final koden test completed
Sat (02/12) | 02 Dec 2023 | ST38 |  | Water stop lowering
Sat (02/12) | 02 Dec 2023 | ST42-44 |  | Guidewall casting completed. Levelling
Sat (02/12) | 02 Dec 2023 | P34-P35 |  | Sppg pipe laid 12m. Casting done. Backfilling in progress
Sat (02/12) | 02 Dec 2023 | P36-P37 |  | To continue sppg pipe replacement here tonight, target 12m
Sat (02/12) | 02 Dec 2023 | Zone 4 |  | No activity for nightshift
Sat (02/12) | 02 Dec 2023 | MH1-2 |  | 2nd layer 2nd part rebar installation continue. Target to cast around 2am
Sat (02/12) | 02 Dec 2023 | ST26 |  | Casting continue, 239/257 m3 in progress
Sat (02/12) | 02 Dec 2023 | MH2-3 |  | Pipe jacking 27/75 pipe completed. 28th pipe joining
Sat (02/12) | 02 Dec 2023 | MH5-2 |  | 6 pipes pulled back. Now TBM pulling back
Sat (02/12) | 02 Dec 2023 | ST38 |  | Cleaning in progress
Sat (02/12) | 02 Dec 2023 | ST55 |  | 2nd bite trenching at 21.2m depth
Sat (02/12) | 02 Dec 2023 | P36 |  | SPPG pipe laid 12m, backfilling on going
Sat (02/12) | 02 Dec 2023 | Zone 4 |  | TT completed for the night
Sat (02/12) | 02 Dec 2023 | MH2-3 |  | Pipe jacking towards 2-1: 28 pipes completed, 29th pipe in progress
Sat (02/12) | 02 Dec 2023 | MH2-3 |  | Jacking continue, 29/75 completed. 30th pipe in progress
Sat (02/12) | 02 Dec 2023 | N1 no more activity |  | Waler bracket installed
Sat (02/12) | 02 Dec 2023 | P8 |  | Waler beam and stiffiner fitting completed. Balance full welding
Sat (02/12) | 02 Dec 2023 | Zone 1 |  | Gate locked. No activity for tonight
Sun (03/12) | 03 Dec 2023 | Zone 1 MH1-2 |  | Preparing for formwork removal
Sun (03/12) | 03 Dec 2023 | MH2-3 |  | Pipe jacking 31/75 completed
Sun (03/12) | 03 Dec 2023 | P36-P37 |  | SPPG pipe laid, 12m. Waiting for concrete lorry to cast
Sun (03/12) | 03 Dec 2023 | P34 |  | SPPG backfilling status
Sun (03/12) | 03 Dec 2023 | ST38 |  | Lower cage lowering, 3/8 cages
Sun (03/12) | 03 Dec 2023 | DW29 |  | End plate and water stop fully installed
Sun (03/12) | 03 Dec 2023 | MH1-2 |  | Now no activity
Sun (03/12) | 03 Dec 2023 | P36-P37 |  | SPPG pipe laying completed, area backfilled
Sun (03/12) | 03 Dec 2023 | ST55 |  | Desander repair works still in progress. Trenching yet to resume
Sun (03/12) | 03 Dec 2023 | ST38 |  | 5/8 cages installed
Sun (03/12) | 03 Dec 2023 | MH2-3 |  | Pipe jacking 33/75 completed. No. 34 pipe joining in progress
Sun (03/12) | 03 Dec 2023 | DW29 |  | 4/6 rebar cages lowered
Sun (03/12) | 03 Dec 2023 | MH2-6 |  | Removal of ventilation fan and clearing materials
Sun (03/12) | 03 Dec 2023 | MH2-5 |  | Clearing water and preparing to lower down shaft base and wall casting
Mon (04/12) | 04 Dec 2023 | Zone 4 |  | Tonight Singtel cable pulling from MH322153 (2nos)
Mon (04/12) | 04 Dec 2023 | P18-P19 |  | Sewer discharge manhole, bracket installation in progress. 50/60 completed. Today to complete
Mon (04/12) | 04 Dec 2023 | MH2-4 |  | Backfilling works in progress (H= 1m)
Mon (04/12) | 04 Dec 2023 | N6 |  | Backfilling works to S1 layer
Mon (04/12) | 04 Dec 2023 | N5 |  | Formwork dismantling
Mon (04/12) | 04 Dec 2023 | N4 |  | Backfilling & compaction works to S1 layer
Mon (04/12) | 04 Dec 2023 | N3 |  | No activity
Mon (04/12) | 04 Dec 2023 | N2 |  | No activity
Mon (04/12) | 04 Dec 2023 | N1 |  | LE waler brackets welding & installation works
Mon (04/12) | 04 Dec 2023 | MH5-2 |  | Pipe pushing to existing sewer. 6/7 completed. Last pipe setting
Mon (04/12) | 04 Dec 2023 | P9-2 |  | Preboring works for soldier piles & lagging plates
Mon (04/12) | 04 Dec 2023 | P8-2 |  | MPI test for waler & brackets. Today to cast concrete packing
Mon (04/12) | 04 Dec 2023 | MH2-3 to MH2-1 |  | Pipe No-38 jacking done. Preparing pipe No-39 for jacking
Tue (05/12) | 05 Dec 2023 | N6 |  | Backfilling to pile cap head level. Last layer
Tue (05/12) | 05 Dec 2023 | N1 |  | Waler beam welding works completed. MpI today am, afternoon to do packing concrete
Tue (05/12) | 05 Dec 2023 | P9 |  | One side of the ERSS is 300mm-500mm away from 22KV cable. Today they will expose the cable do steel plate protection. Utility team aware
Tue (05/12) | 05 Dec 2023 | N1 |  | Packing concrete curing. Later today to start excavation to FEL
Tue (05/12) | 05 Dec 2023 | Zone 1 |  | SPPG here to do excavation works for pulling pit. Tentative this week to start cable pulling
Tue (05/12) | 05 Dec 2023 | MH1-2 |  | 4th layer excavation on going
Tue (05/12) | 05 Dec 2023 | Zone 1 |  | Area preparation for piling works
Tue (05/12) | 05 Dec 2023 | MH5-2 |  | Today water tightness test
Tue (05/12) | 05 Dec 2023 | P51 |  | TT work on going for ECM pond
Tue (05/12) | 05 Dec 2023 | Zone 4 P49 |  | TT results for SPPG duct corridor
Tue (05/12) | 05 Dec 2023 | Zone 2 |  | Krishco continue water pipe laying works at MH2-3 location
Tue (05/12) | 05 Dec 2023 | P18-P19 |  | Sewer discharge manhole, pipe installation in progress. As of now, 3 pipes lowered down
Tue (05/12) | 05 Dec 2023 | P44 |  | 2 teams TT for piling works
Tue (05/12) | 05 Dec 2023 | MH2-4 |  | Wall rebar installation works
Tue (05/12) | 05 Dec 2023 | N5 |  | Pier 1st stage (H=1.24m) formwork closing
Tue (05/12) | 05 Dec 2023 | N6 |  | Continue backfilling & compaction works to S1 layer
Tue (05/12) | 05 Dec 2023 | N4 |  | Backfilling & ndt completed
Tue (05/12) | 05 Dec 2023 | N3 |  | No activity
Tue (05/12) | 05 Dec 2023 | N2 |  | No activity
Tue (05/12) | 05 Dec 2023 | N1 |  | MPI tests completed, today to cast concrete packing
Tue (05/12) | 05 Dec 2023 | P9-2 |  | Preboring works for solider pile and lagging plate installation
Tue (05/12) | 05 Dec 2023 | P8-2 |  | Barricades installation works
Tue (05/12) | 05 Dec 2023 | BH71 |  | TT completed. Preparation for hand augering
Tue (05/12) | 05 Dec 2023 | PBH20 |  | Drilling at 51.6m, completed
Tue (05/12) | 05 Dec 2023 | P37 |  | Starhub pipe laying here by Mo guan, 18m
Tue (05/12) | 05 Dec 2023 | P36-P37 |  | Shoring works for SPPG pipe laying, 12m target Today. To complete all by Thursday (target)
Tue (05/12) | 05 Dec 2023 | PBH16 |  | Current depth 45.5m
Tue (05/12) | 05 Dec 2023 | DR2 |  | Backfilling works until panel 3B
Tue (05/12) | 05 Dec 2023 | MH1-2 |  | 4th layer excavation ongoing
Tue (05/12) | 05 Dec 2023 | DR2 |  | Backfilling works until panel 3B
Tue (05/12) | 05 Dec 2023 | DR2 |  | Today panel 5 concrete plug rebar works and casting
Tue (05/12) | 05 Dec 2023 | JTC area Blk 4 |  | Excavation works to expose LT cables to shift locally
Tue (05/12) | 05 Dec 2023 | ST60 |  | Trenching on going at 18m depth
Tue (05/12) | 05 Dec 2023 | ST55 |  | 4/6 cages installed
Tue (05/12) | 05 Dec 2023 | BH120 |  | Current depth at 20.5m
Tue (05/12) | 05 Dec 2023 | MH5-2 |  | Preparation for water tightness test in progress (5-2 to Existing MH)
Tue (05/12) | 05 Dec 2023 | ST33 |  | Trimming works
Tue (05/12) | 05 Dec 2023 | DW31 |  | Rebar cage lapping 3/4
Tue (05/12) | 05 Dec 2023 | MH2-8 |  | 9th ring casting
Tue (05/12) | 05 Dec 2023 | MH1-2 |  | Excavation for next layer caisson shaft work
Tue (05/12) | 05 Dec 2023 | MH2-8 |  | Concrete on site for casting of 9th layer caisson
Tue (05/12) | 05 Dec 2023 | MH2-8 |  | 9th layer excavation, plan to cast today
Tue (05/12) | 05 Dec 2023 | MH2-4 |  | Backfilling works
Tue (05/12) | 05 Dec 2023 | P18-P19 |  | Sewer discharge manhole, brackets (60 pcs) completed yesterday. Today to start pipe installation
Tue (05/12) | 05 Dec 2023 | N5 |  | Access construction to pile cap area for column stamp rebar works
Wed (06/12) | 06 Dec 2023 | MH2-6 |  | Tonight LCH provide one team manhole brick and cover installation work
Wed (06/12) | 06 Dec 2023 | Zone 4 P45 |  | Trial trench in progress by WH
Wed (06/12) | 06 Dec 2023 | Zone 4 P50 |  | SPPG trial trench in progress by WG
Wed (06/12) | 06 Dec 2023 | N6 |  | Backfilling to pile cap head level
Wed (06/12) | 06 Dec 2023 | ST55 |  | Bite 2 cleaning ongoing
Wed (06/12) | 06 Dec 2023 | MH2-8 |  | No activity. Layer 9 was cast yesterday
Wed (06/12) | 06 Dec 2023 | Gate 5 |  | M1 cable pulling ongoing
Wed (06/12) | 06 Dec 2023 | ST60 |  | 2nd bite excavation in progress
Wed (06/12) | 06 Dec 2023 | BH120 |  | In progress, 31m
Wed (06/12) | 06 Dec 2023 | Zone 3 |  | Installation of data logger inside PUB manhole — works under PUB contractor
Wed (06/12) | 06 Dec 2023 | DR2 |  | Inspection done for panel 5 concrete plug
Wed (06/12) | 06 Dec 2023 | P35 |  | Starhub manhole installation
Wed (06/12) | 06 Dec 2023 | P38 |  | WG continue to install shoring for SPPG pipe laying. Pipes length for this area ard 18m
Wed (06/12) | 06 Dec 2023 | PBH14 |  | Trial trench in progress
Wed (06/12) | 06 Dec 2023 | PBH18 |  | In progress, 24m
Wed (06/12) | 06 Dec 2023 | PBH16 |  | Current depth at 52.5m. Pending confirmation prior to grouting
Wed (06/12) | 06 Dec 2023 | P20 from PDr3 |  | M1 cable pulling completed
Wed (06/12) | 06 Dec 2023 | N5 |  | Today concrete plug casting
Wed (06/12) | 06 Dec 2023 | N4 |  | Access dismantling
Wed (06/12) | 06 Dec 2023 | P9 |  | Pre-boring completed
Wed (06/12) | 06 Dec 2023 | Zone 1 |  | SPPG cable pulling pit excavation continue
Wed (06/12) | 06 Dec 2023 | Zone 3 BH71 |  | Hand auger ongoing
Wed (06/12) | 06 Dec 2023 | ST33 |  | Flap hydraulic repair works on going. Current at 2nd bite
Wed (06/12) | 06 Dec 2023 | ST37 PB2 |  | Boring depth current at 25m
Wed (06/12) | 06 Dec 2023 | Exit 2 |  | Casting of guidewall for DW63 and 64
Wed (06/12) | 06 Dec 2023 | ST55 |  | Cleaning completed. Now Tremie pipe installed, Dongah to cast 13m height from Toe level with G20. Estimated volume 120m3
Wed (06/12) | 06 Dec 2023 | ST60 |  | 3rd bite trenching now at 14m depth
Wed (06/12) | 06 Dec 2023 | ST33 |  | 2nd bite trenching resumed
Wed (06/12) | 06 Dec 2023 | Zone 4 |  | No activity tonight. Wee Guan team will be working near MH2-8
Wed (06/12) | 06 Dec 2023 | MH2-3 to MH2-1 |  | Lowered down Pipe No-48. 47/75m as of now. Tonight no activity. LCH found out the pump need to repair. Tomorrow only then they arrange mechanic to come
Wed (06/12) | 06 Dec 2023 | ST37 |  | Preboring in progress
Wed (06/12) | 06 Dec 2023 | DR2 |  | Part 5 concrete plug construction plan for casting today
Wed (06/12) | 06 Dec 2023 | DR2 |  | 2nd layer backfilling & compaction in progress
Wed (06/12) | 06 Dec 2023 | PBH16 |  | Depth at 50m
Wed (06/12) | 06 Dec 2023 | P18-P19 |  | Sewer discharge pipe installation inside existing MH to complete today
Wed (06/12) | 06 Dec 2023 | PBH18 |  | To start boring today
Thu (07/12) | 07 Dec 2023 | DR2 |  | Panel 5 concrete plug was cast yesterday. Today plan to continue backfilling
Thu (07/12) | 07 Dec 2023 | PBH18 |  | In progress, 29.5m
Thu (07/12) | 07 Dec 2023 | Zone 3 BH87 |  | Trial trench ongoing
Thu (07/12) | 07 Dec 2023 | ST33 |  | Bite 2 excavation in progress
Thu (07/12) | 07 Dec 2023 | MH2-8 |  | Excavation for 10th ring ongoing
Thu (07/12) | 07 Dec 2023 | DW30 |  | 2md bite trenching started
Thu (07/12) | 07 Dec 2023 | ST33 |  | Trimming continue
Thu (07/12) | 07 Dec 2023 | ST60 |  | Rebar cage u-clip inspection done — 4/8nos. Balance 4nos to be done after lunch
Thu (07/12) | 07 Dec 2023 | Near MH2-8 |  | Excavation and ERSS installation for power duct rectification
Thu (07/12) | 07 Dec 2023 | Zone 3 | P38 | Concrete haunch casting done
Thu (07/12) | 07 Dec 2023 | ST60 |  | Rebar cage (6/6nos) & hanging bar u-clip inspection completed
Thu (07/12) | 07 Dec 2023 | Zone 2 | P18-P19 | Excavation in progress for laying twin ductile pipe connection to existing discharge manhole
Thu (07/12) | 07 Dec 2023 | ST60 |  | Rebar cage installation in progress, 3/6nos
Thu (07/12) | 07 Dec 2023 | BH122 |  | Trial trench in progress
Thu (07/12) | 07 Dec 2023 | N6 |  | No activity
Thu (07/12) | 07 Dec 2023 | N5 |  | Concrete plug casting in progress
Thu (07/12) | 07 Dec 2023 | DR2 |  | Backfilling ongoing
Thu (07/12) | 07 Dec 2023 | PBH16 |  | Completed. SI rig will move to PBH14
Thu (07/12) | 07 Dec 2023 | N4 |  | Waler beams removal in progress
Thu (07/12) | 07 Dec 2023 | PBH18 |  | In progress, 38m
Thu (07/12) | 07 Dec 2023 | Zone 3 near exit 1 |  | Crane mobilisation and unloading of machinery parts
Thu (07/12) | 07 Dec 2023 | N3 |  | No activity
Thu (07/12) | 07 Dec 2023 | N2 |  | No activity
Thu (07/12) | 07 Dec 2023 | N1 |  | No activity
Thu (07/12) | 07 Dec 2023 | P9-2 |  | Preboring works for ERSS installation
Thu (07/12) | 07 Dec 2023 | P8-2 |  | KTC excavation to FEL. Target to finish today
Thu (07/12) | 07 Dec 2023 | Zone 4 P49 |  | Singtel pipe laying works by SKK
Thu (07/12) | 07 Dec 2023 | Zone 4 |  | Excavation for ECM pond in progress
Thu (07/12) | 07 Dec 2023 | Zone 4 |  | WG completed TT. Found water pipe (300mm dia)
Thu (07/12) | 07 Dec 2023 | Zone 1 |  | Boring rig assembly in progress
Thu (07/12) | 07 Dec 2023 | Zone 1 | MH1-2 | Utility support works in progress. Yst cast 4th layer
Thu (07/12) | 07 Dec 2023 | P46 |  | 1 team here continue trial trench for bored pile ERSS
Thu (07/12) | 07 Dec 2023 | P45 |  | 2 teams here continue trial trench
Thu (07/12) | 07 Dec 2023 | Zone 1 |  | DE143 works at NLL
Thu (07/12) | 07 Dec 2023 | Zone 1 |  | SPPG Leychoon works
Thu (07/12) | 07 Dec 2023 | Zone 1 |  | Singtel cable pulling works for EA camera
Thu (07/12) | 07 Dec 2023 | MH5-2 |  | Internal water tightness test in progress (5-2 to Existing MH)
Thu (07/12) | 07 Dec 2023 | DW30 |  | First bite excavation in progress
Thu (07/12) | 07 Dec 2023 | MH2-4 |  | Wall casting in progress
Thu (07/12) | 07 Dec 2023 | P18-19 |  | Continue excavation for twin ductile pipe connection
Thu (07/12) | 07 Dec 2023 | N5 |  | Concrete plug casting completed. Levelling ongoing
Thu (07/12) | 07 Dec 2023 | DW30 |  | First bite excavation in progress, 31.6m
Thu (07/12) | 07 Dec 2023 | MH2-8 |  | 10th layer excavation continue till 10pm
Thu (07/12) | 07 Dec 2023 | MH2-3 |  | Pipe jacking until 10pm, 50/75 completed
Thu (07/12) | 07 Dec 2023 | North ramp P8 |  | Excavation to FEL till 10pm. Tomorrow afternoon to complete
Thu (07/12) | 07 Dec 2023 | MH1-2 |  | Night shift team to continue excavation for 4th layer
Thu (07/12) | 07 Dec 2023 | DW30 |  | 1st bite internal koden test
Thu (07/12) | 07 Dec 2023 | ST33 |  | Trimming for end plate removal
Thu (07/12) | 07 Dec 2023 | ST55 |  | BC cutter maintenance, to start trenching at 1am
Thu (07/12) | 07 Dec 2023 | ST60 |  | Hanging bar installation
Thu (07/12) | 07 Dec 2023 | Zone 4 |  | Previous pavement cutting to do TT for SPPG corridor
Fri (08/12) | 08 Dec 2023 | N5 |  | Curing works. Concrete plug cast yst
Fri (08/12) | 08 Dec 2023 | N6 |  | Dewatering in progress
Fri (08/12) | 08 Dec 2023 | N3 |  | No activity
Fri (08/12) | 08 Dec 2023 | N2 |  | No activity
Fri (08/12) | 08 Dec 2023 | N1 |  | Today to start excavation to FEL
Fri (08/12) | 08 Dec 2023 | P9-2 |  | Preboring works in progress. Today to complete
Fri (08/12) | 08 Dec 2023 | P8-2 |  | Excavation to FEL. Today to complete
Fri (08/12) | 08 Dec 2023 | DW30 |  | B2 cleaning continue
Fri (08/12) | 08 Dec 2023 | ST33 |  | Waterstop installation
Fri (08/12) | 08 Dec 2023 | ST55 |  | Trenching in progress
Fri (08/12) | 08 Dec 2023 | ST60 |  | Casting in progress, total volume 180 m3
Fri (08/12) | 08 Dec 2023 | Zone 4 |  | ATT-WG 12 trial trench result
Fri (08/12) | 08 Dec 2023 | MH1-2 |  | 4th layer excavation continue
Fri (08/12) | 08 Dec 2023 | MH2-4 |  | No activity. Curing ongoing
Fri (08/12) | 08 Dec 2023 | MH2-5 |  | Benching works in progress
Fri (08/12) | 08 Dec 2023 | Z2 P18-19 |  | Hacking of existing sewer manhole wall prior to laying/connection of sewer main pumping twin ductile pipe
Fri (08/12) | 08 Dec 2023 | N6 |  | Dewatering works
Fri (08/12) | 08 Dec 2023 | N5 |  | Curing in progress for concrete plug
Fri (08/12) | 08 Dec 2023 | N4 |  | Preparation for backfilling
Fri (08/12) | 08 Dec 2023 | Near N4 |  | M1 cable pulling works
Fri (08/12) | 08 Dec 2023 | N3 |  | No activity
Fri (08/12) | 08 Dec 2023 | N2 |  | No activity
Fri (08/12) | 08 Dec 2023 | N1 |  | Excavation to FEL
Fri (08/12) | 08 Dec 2023 | P9-2 |  | Preboring completed, SP & LP installation works ongoing
Fri (08/12) | 08 Dec 2023 | P8-2 |  | Access relocation completed. Now continue excavation to FEL
Fri (08/12) | 08 Dec 2023 | MH1-2 |  | 5th layer Formwork installation. To cast around 5pm
Fri (08/12) | 08 Dec 2023 | Zone 1 |  | HSL Setting up & bentonite mixing works in progress
Fri (08/12) | 08 Dec 2023 | ST60 |  | Casting continue, 150/180 m3
Fri (08/12) | 08 Dec 2023 | MH5-2 |  | Dismantling of jacking equipment
Fri (08/12) | 08 Dec 2023 | Zone 2 |  | RG Hand augering works
Fri (08/12) | 08 Dec 2023 | DW30 |  | 2nd bite trenching completed. 32.5m. BC cutter body extraction
Fri (08/12) | 08 Dec 2023 | ST33 |  | Chiselling continue
Fri (08/12) | 08 Dec 2023 | ST55 |  | 1st bite trenching at 27m depth
Fri (08/12) | 08 Dec 2023 | ST60 |  | Last load casting. 180 m3
Fri (08/12) | 08 Dec 2023 | ST55 |  | 1st bite trenching completed. Design depth 26.8m
Fri (08/12) | 08 Dec 2023 | ST33 |  | Chiselling completed, end plate loosen. Bigger crane to mobilise to extract end plate
Fri (08/12) | 08 Dec 2023 | MH2-3 |  | Pipe jacking status, 53/75 pipes completed
Fri (08/12) | 08 Dec 2023 | N1 |  | Excavation to FEL status, KTC stopped work for the day
Fri (08/12) | 08 Dec 2023 | P8-2 |  | KTC to work until 10pm to complete excavation till FEL
Fri (08/12) | 08 Dec 2023 | Zone 1 HSL |  | Mixing bentonite and desander NB frame installation. Work till 10pm
Fri (08/12) | 08 Dec 2023 | MH1-2 |  | Tonight to do singtel haunch support full welding. No other activity
Fri (08/12) | 08 Dec 2023 | DW30 |  | Cleaning
Fri (08/12) | 08 Dec 2023 | ST55 |  | Cutter wheel teeth changing. 2nd bite completed
Fri (08/12) | 08 Dec 2023 | Zone 4 |  | Team 1 TT for SPPG duct corridor
Fri (08/12) | 08 Dec 2023 | Zone 4 |  | Team 2 for TT work
Sat (09/12) | 09 Dec 2023 | Zone 4 |  | Wee guan TT for SPPG duct corridor
Sat (09/12) | 09 Dec 2023 | ST33 |  | Casting continue, 248.5/257. Last load on site
Sat (09/12) | 09 Dec 2023 | ST55 |  | Casting in progress
Sat (09/12) | 09 Dec 2023 | DW30 |  | Torque test for u-clips
Sat (09/12) | 09 Dec 2023 | Zone 4 |  | Team 1 TT result
Sat (09/12) | 09 Dec 2023 | Zone 4 Team 2 |  | TT result
Sat (09/12) | 09 Dec 2023 | ST55 |  | 1st bite cleaning in progress
Sat (09/12) | 09 Dec 2023 | ST33 |  | Preparation for rebar cage lowering
Sat (09/12) | 09 Dec 2023 | ST33 |  | Rebar cage lifting
Sat (09/12) | 09 Dec 2023 | DW30 |  | Cleaning completed. Preparation for rebar cage lowering
Sat (09/12) | 09 Dec 2023 | ST39 |  | 1st bite trenching at 29m depth
Sat (09/12) | 09 Dec 2023 | ST55 |  | Cleaning completed
Sat (09/12) | 09 Dec 2023 | ST33 |  | 5/8 cages installed
Sat (09/12) | 09 Dec 2023 | DW30 |  | 3/6 cages installed. 4th cage lapping in progress
Sat (09/12) | 09 Dec 2023 | MH2-5 |  | 2nd raised wall casting completed
Sat (09/12) | 09 Dec 2023 | MH2-3 |  | Jakcking done for the day. 58/75 pipes completed
Sat (09/12) | 09 Dec 2023 | N1 |  | Excavation to FEL stopped for the day
Sat (09/12) | 09 Dec 2023 | P8-2 |  | Pile head cutting completed today. Monday to start hacking. HSL off tomorrow
Sat (09/12) | 09 Dec 2023 | MH1-2 |  | Night shift to continue excavation work for 6th layer
Sat (09/12) | 09 Dec 2023 | DW30 |  | Casting completed. 118 m3
Sat (09/12) | 09 Dec 2023 | ST33 |  | Casting on going, 150/230 m3
Sat (09/12) | 09 Dec 2023 | ST39 |  | 3rd bite trenching at 23.5m depth
Sat (09/12) | 09 Dec 2023 | ST52 |  | 1st bite trenching at 14m3
Sat (09/12) | 09 Dec 2023 | ST55 |  | To cast also tonight, concrete ordered, total volume 190 m3
Sun (10/12) | 10 Dec 2023 | North ramp N6 and N5 |  | No activity
Sun (10/12) | 10 Dec 2023 | N4 |  | No activity
Sun (10/12) | 10 Dec 2023 | N3 and N2 |  | No activity
Sun (10/12) | 10 Dec 2023 | N1 |  | Access installation and excavation
Sun (10/12) | 10 Dec 2023 | N1 |  | KTC soil disposal & internal shifting
Sun (10/12) | 10 Dec 2023 | P10 |  | Levelling ongoing
Sun (10/12) | 10 Dec 2023 | ST39 |  | Waterstop extraction in progress
Sun (10/12) | 10 Dec 2023 | ST52 |  | First bite in progress. Currently cutter body wash. Depth ard 25m/27.46m
Sun (10/12) | 10 Dec 2023 | JTC blk 4 |  | ST62-64 guidewall formwork installation
Sun (10/12) | 10 Dec 2023 | DR2 |  | No activity. Backfilling was completed till layer 4. Balance 2 more layers
Sun (10/12) | 10 Dec 2023 | Zone 3 |  | SI rig maintenance
Sun (10/12) | 10 Dec 2023 | Exit 1 |  | Levelling and steel plate laying rectification ongoing
Sun (10/12) | 10 Dec 2023 | Zone 4 |  | ECM pond current status
Sun (10/12) | 10 Dec 2023 | Zone 4 |  | Loyang Ave centre median works by other contractor
Sun (10/12) | 10 Dec 2023 | Zone 4 |  | Moveable hoarding sheets removal
Sun (10/12) | 10 Dec 2023 | Zone 4 |  | No other activity
Sun (10/12) | 10 Dec 2023 | Zone 4 junction |  | No activity
Sun (10/12) | 10 Dec 2023 | Zone 3 P30 |  | Starhub manhole cover installation
Sun (10/12) | 10 Dec 2023 | ST39 |  | Waterstop extracted. Cleaning ongoing
Sun (10/12) | 10 Dec 2023 | Zone 4 |  | Trial trench status, shoring done at 1.4m
Sun (10/12) | 10 Dec 2023 | Gate 5 loyang lane to JTC area |  | Singtel contractor here for cable pulling. Total 9 cables pulled here
Sun (10/12) | 10 Dec 2023 | ST39 |  | 3rd bite completed. Now chiselling on going to remove end plate. (Trenching for this panel is less than 24 hrs 👏👏👏)
Sun (10/12) | 10 Dec 2023 | ST52 |  | 1st bite trenching at 22m depth
Sun (10/12) | 10 Dec 2023 | ST55 |  | Casting in progress, 177/195 m3
Sun (10/12) | 10 Dec 2023 | MH2-3 |  | Pipe jacking no.59/75 in progress
Sun (10/12) | 10 Dec 2023 | MH1-2 |  | Layer 6 rebars inspected. Formwork closing ongoing
Sun (10/12) | 10 Dec 2023 | N1 |  | Current status
Sun (10/12) | 10 Dec 2023 | North ramp P8-2 |  | Pile head hacking ongoing
Sun (10/12) | 10 Dec 2023 | MH1-2 |  | 6th layer excavation continue, reached 600mm depth, wall trimming on going
Sun (10/12) | 10 Dec 2023 | ST52 |  | BC cutter teeth replacement done. First bite trenching resumes
Sun (10/12) | 10 Dec 2023 | ST62-64 |  | Guidewall casting ongoing
Sun (10/12) | 10 Dec 2023 | Zone 4 TT |  | Work completed for the night. Area reinstated
Sun (10/12) | 10 Dec 2023 | ST39 |  | U-clips inspection for rebar cages and hanging bars done
Sun (10/12) | 10 Dec 2023 | ST55 |  | Casting completed
Sun (10/12) | 10 Dec 2023 | ST52 |  | BC cutter teeth changing
Sun (10/12) | 10 Dec 2023 | ST39 |  | Trimming using BC cutter
Sun (10/12) | 10 Dec 2023 | MH1-2 |  | 6th layer excavation completed. Now preparing rebars for installation & plan for casting today
Sun (10/12) | 10 Dec 2023 | Zone 1 |  | HSL no activity
Sun (10/12) | 10 Dec 2023 | Zone 1 |  | No other activity
Sun (10/12) | 10 Dec 2023 | Zone 2 near Shell station |  | Benching works ongoing at existing MH
Sun (10/12) | 10 Dec 2023 | Zone 2 P18-P19 |  | No activity
Mon (11/12) | 11 Dec 2023 | Zone 4 |  | Shoring installation done for both trial trenches. Continue manual clearing of soil
Mon (11/12) | 11 Dec 2023 | MH2-8 |  | Excavation for 11th layer + base slab. Tomorrow to cast
Mon (11/12) | 11 Dec 2023 | N6 |  | Today NDT for final layer backfilling (til pile cap head level)
Mon (11/12) | 11 Dec 2023 | N1 |  | Pile head cutting of COL prior to hacking
Mon (11/12) | 11 Dec 2023 | P10-2 |  | Pre-boring started
Mon (11/12) | 11 Dec 2023 | P8-2 |  | Pile head hacking surprisingly fast. Today to complete hacking, Trimming and final levelling tomorrow
Mon (11/12) | 11 Dec 2023 | DR2 |  | Current status of backfilling. Target tomorrow to complete
Mon (11/12) | 11 Dec 2023 | MH2-3 to MH2-1 |  | Pipe No-64 jacking in progress
Mon (11/12) | 11 Dec 2023 | MH2-4 |  | Continue backfilling until 7PM
Mon (11/12) | 11 Dec 2023 | MH1-2 |  | Continue excavation for the next layer cassion casting
Mon (11/12) | 11 Dec 2023 | MH2-3 |  | Pipe jacking no.65 in progress
Mon (11/12) | 11 Dec 2023 | MH1-2 |  | Tonight LCH will continue excavation for 7th layer
Mon (11/12) | 11 Dec 2023 | ST39 |  | Casting completed. Total volume: 226m3
Mon (11/12) | 11 Dec 2023 | ST52 |  | Cutter teeth checking & replacement ongoing
Mon (11/12) | 11 Dec 2023 | DR2 |  | No activity. Backfilling & compaction completed till 5th layer. Balance 1 more layer
Mon (11/12) | 11 Dec 2023 | Zone 4 |  | 2 teams for SPPG trial trench tonight
Tue (12/12) | 12 Dec 2023 | MH2-8 |  | Preparing to cast
Tue (12/12) | 12 Dec 2023 | ST41 |  | Pre boring works in progress
Tue (12/12) | 12 Dec 2023 | ST52 |  | C-lug welding for end plate trimming
Tue (12/12) | 12 Dec 2023 | BH71 |  | Packer yestat 25-26m depth
Tue (12/12) | 12 Dec 2023 | Zone 3 near exit 1 |  | Exposing water pipe for cap off works in progress
Tue (12/12) | 12 Dec 2023 | P45 |  | Transfer beam TT in progress
Tue (12/12) | 12 Dec 2023 | P46 |  | Team 2, marking for transfer beam TT
Tue (12/12) | 12 Dec 2023 | P44 |  | Team 3, TT record. Found new water pipe, singtel slab and traffic light cable
Tue (12/12) | 12 Dec 2023 | MH1-2 |  | Continue excavation for 7th layer
Tue (12/12) | 12 Dec 2023 | Zone 4 |  | Perimeter drain excavation work
Tue (12/12) | 12 Dec 2023 | Zone 4 |  | ECM pond excavation work
Tue (12/12) | 12 Dec 2023 | Zone 4 |  | ATT21 and 22 trial trench work for SPPG duct corridor
Tue (12/12) | 12 Dec 2023 | Zone 3 near exit 1 |  | CR1070 excavation for the cap-off works
Tue (12/12) | 12 Dec 2023 | ST52 |  | WS trimming done. Cutter body wash before internal koden check
Tue (12/12) | 12 Dec 2023 | MH2-5 |  | 2nd lift wall backfilling for last layer
Tue (12/12) | 12 Dec 2023 | MH2-4 |  | 3rd lift wall backfilling status, balance 1.5m
Tue (12/12) | 12 Dec 2023 | MH2-3 |  | Jacking to 2-1 status, 67/75 pipes
Tue (12/12) | 12 Dec 2023 | P16 |  | Road kerb hacking to do TT for Bored pile
Tue (12/12) | 12 Dec 2023 | N6 |  | Today plan to cast concrete plug at pile cap head level
Tue (12/12) | 12 Dec 2023 | N5 |  | Column stump formwork dismantling
Tue (12/12) | 12 Dec 2023 | P8-2 |  | Final levelling, today lean con
Tue (12/12) | 12 Dec 2023 | MH1-2 |  | Continue excavation for 7th ring
Tue (12/12) | 12 Dec 2023 | PDR3 |  | SPPG excavating pulling pit. Balance 3 nos. Target to start cable pulling earliest Saturday, latest monday
Tue (12/12) | 12 Dec 2023 | Zone 4 |  | Trial trench completed — ATT-WG(Z4)-19
Tue (12/12) | 12 Dec 2023 | Zone 4 |  | Trial trench completed — ATT-WG(Z4)-20
Tue (12/12) | 12 Dec 2023 | MH1-2 |  | Manual excavation for 7th layer
Tue (12/12) | 12 Dec 2023 | P3-7 |  | Casing installation in progress
Tue (12/12) | 12 Dec 2023 | DW57 |  | Trimming ongoing (DW56 side)
Tue (12/12) | 12 Dec 2023 | ST52 |  | Continue trimming
Tue (12/12) | 12 Dec 2023 | Average noise level from LVC blk 222 |  | 63dB
Tue (12/12) | 12 Dec 2023 | Average noise level at zone 1 Loyang Rise |  | 50dB
Tue (12/12) | 12 Dec 2023 | DW57 |  | U-clip inspection done for rebar cages and hanging bars
Tue (12/12) | 12 Dec 2023 | MH2-8 |  | Base slab rebar works. Target to cast today at 8pm
Tue (12/12) | 12 Dec 2023 | ST41 |  | Pre- boring to continue until 8pm
Tue (12/12) | 12 Dec 2023 | DW57 |  | 1st bite cleaning completed. Now verifying depth then proceed to 2nd bite cleaning
Tue (12/12) | 12 Dec 2023 | ST52 |  | Trimming completed
Tue (12/12) | 12 Dec 2023 | DR2 |  | Backfilling status
Tue (12/12) | 12 Dec 2023 | MH2-5 |  | 2nd lift wall backfilling completed
Tue (12/12) | 12 Dec 2023 | MH2-4 |  | Backfilling balance 500mm
Tue (12/12) | 12 Dec 2023 | MH2-3 |  | Pipe jacking 69th pipe in progress. To complete 70/75 pipes by 9pm
Tue (12/12) | 12 Dec 2023 | MH2-3 |  | Pipe 70 lowered. Works till 9pm only
Tue (12/12) | 12 Dec 2023 | P19 |  | Sewer pipes area backfilled
Tue (12/12) | 12 Dec 2023 | N5 |  | First layer backfilling and levelling
Tue (12/12) | 12 Dec 2023 | P8-2 |  | Lean concrete casting ongoing
Tue (12/12) | 12 Dec 2023 | ST37 |  | First bite excavation in progress, 32m
Tue (12/12) | 12 Dec 2023 | ST52 |  | 2nd bite excavation in progress
Tue (12/12) | 12 Dec 2023 | DR2 |  | Backfilling completed
Tue (12/12) | 12 Dec 2023 | Zone 4 |  | Tonight 2 teams for SPPG trial trench works — ATT-WG(z4)-24 and 25
Wed (13/12) | 13 Dec 2023 | N6 |  | Pile head level concrete plug to cast at 10am
Wed (13/12) | 13 Dec 2023 | ST37 |  | Trimming completed. Now BC cutter teeth check & preparation for internal koden test
Wed (13/12) | 13 Dec 2023 | N5 |  | 2nd layer backfilling to pile head level
Wed (13/12) | 13 Dec 2023 | N4 |  | SP and LP extraction
Wed (13/12) | 13 Dec 2023 | N1 |  | Pile head hacking. 1 pile completed yesterday for 1.5hrs. 2nd pile a bit hard
Wed (13/12) | 13 Dec 2023 | P10-2 |  | Pre boring. 8/22 completed
Wed (13/12) | 13 Dec 2023 | P8-2 |  | Pile head final trimming to COL, today to complete
Wed (13/12) | 13 Dec 2023 | Zone 4 |  | 1 team here for SPPG trial trench — ATT-WG(z4)-28
Wed (13/12) | 13 Dec 2023 | ST52 |  | 2nd bite excavation in progress, 26m
Wed (13/12) | 13 Dec 2023 | ST37 |  | Internal koden check ongoing
Wed (13/12) | 13 Dec 2023 | Next to MH2-8 |  | WG 1 team here for open pit SPPG pipe rectification
Wed (13/12) | 13 Dec 2023 | MH1-2 |  | Continue 7th layer excavation
Wed (13/12) | 13 Dec 2023 | ATT-24 |  | Manual excavation ongoing
Wed (13/12) | 13 Dec 2023 | ST52 |  | Cutter teeth replaced. 2nd bite resumes. Ongoing 20m
Wed (13/12) | 13 Dec 2023 | DW57 |  | Hourly depth check will be done. Next check will be around 430am. So far, no change in depth
Wed (13/12) | 13 Dec 2023 | ST37 |  | First bite completed. Currently flab rectification ongoing before starting bite 2
Wed (13/12) | 13 Dec 2023 | N6 |  | Concrete plug casting completed
Wed (13/12) | 13 Dec 2023 | N4 |  | Balance 2 SP to be extracted
Wed (13/12) | 13 Dec 2023 | N1 |  | Last pile head hacking. Tomorrow to do final levelling and lean con
Wed (13/12) | 13 Dec 2023 | P10 |  | Excavation down to 22+ msHD
Wed (13/12) | 13 Dec 2023 | P8-2 |  | Pile head trimming 2 completed. Tonight to complete. Rebar works to start tomorrow
Wed (13/12) | 13 Dec 2023 | MH1-2 |  | 7th layer rebar works
Wed (13/12) | 13 Dec 2023 | ST168& ST167 |  | Removal of 66KV for Dwall work
Wed (13/12) | 13 Dec 2023 | Zone 1 |  | P3-7 boring, current depth 32/28m
Wed (13/12) | 13 Dec 2023 | MH5-2 |  | Jacking frame setting
Wed (13/12) | 13 Dec 2023 | MH2-3 |  | Woh hup installation of platform for water pipe laying
Wed (13/12) | 13 Dec 2023 | MH2-4 |  | Prepare the area for next stage of manhole shaft work
Wed (13/12) | 13 Dec 2023 | N1 |  | Hacking done by HSL
Wed (13/12) | 13 Dec 2023 | MH5-2 |  | Formwork closing for gantry crane track
Wed (13/12) | 13 Dec 2023 | MH5-2 |  | Jacking frame set up and thrust block work in progress
Wed (13/12) | 13 Dec 2023 | MH1-2 |  | 7th layer rebar installation ongoing. Plan for inspection ard 1030pm
Thu (14/12) | 14 Dec 2023 | Zone 3 |  | Dipcie continue excavation for Singtel pipe laying (from Selarang camp side). Target ard 15m today
Thu (14/12) | 14 Dec 2023 | ST37 |  | Water stop endplate removal ongoing
Thu (14/12) | 14 Dec 2023 | ST37 |  | Endplate and water stop installation. 1st part lowered
Thu (14/12) | 14 Dec 2023 | DW57 |  | 1st bite trenching at depth of 22.9m. Now cutter body up for teeth changing
Thu (14/12) | 14 Dec 2023 | ST61 |  | Mud hose preparing to connect at BC cutter, later to start trenching
Thu (14/12) | 14 Dec 2023 | Zone 4 after SIA |  | 2 teams here doing TT for SPPG duct corridor
Thu (14/12) | 14 Dec 2023 | MH2-5 |  | 3rd raise wall (2.55m height) Formwork casting. To cast today
Thu (14/12) | 14 Dec 2023 | MH2-4 |  | No activity
Thu (14/12) | 14 Dec 2023 | Near MH2-3 |  | To cast concrete haunching for laid pumping main pipes
Thu (14/12) | 14 Dec 2023 | MH2-3 |  | No activity. The team is now doing preparation works for hacking of wall at MH2-1
Thu (14/12) | 14 Dec 2023 | N6 |  | No activity. Concrete plug cast yesterday
Thu (14/12) | 14 Dec 2023 | N5 |  | No activity
Thu (14/12) | 14 Dec 2023 | N4 |  | ERSS extraction completed. Now adjusting the barricades
Thu (14/12) | 14 Dec 2023 | N3 |  | No activity
Thu (14/12) | 14 Dec 2023 | N2 |  | No activity
Thu (14/12) | 14 Dec 2023 | N1 |  | Removal of debris and final leveling in progress. Target to lean concrete today
Thu (14/12) | 14 Dec 2023 | P10-2 |  | Preboring works for SP & LP
Thu (14/12) | 14 Dec 2023 | P9-2 |  | Excavation works to S1 layer in progress
Thu (14/12) | 14 Dec 2023 | P8-2 |  | CGW lowering rebar for pile cap rebar installation works
Thu (14/12) | 14 Dec 2023 | MH1-2 |  | 7th layer cast yesterday night. Curing in progress
Thu (14/12) | 14 Dec 2023 | P3-7 |  | Rebar cages lowered. Now pending for casting
Thu (14/12) | 14 Dec 2023 | P4-5 |  | Preboring works in progress
Thu (14/12) | 14 Dec 2023 | MH1-2 |  | 7th layer cast
Thu (14/12) | 14 Dec 2023 | MH5-2 |  | Jacking setting up works in progress
Thu (14/12) | 14 Dec 2023 | ST40 |  | First bite excavation in progress
Thu (14/12) | 14 Dec 2023 | MH2-3 |  | Water pipe platform casting in progress. Total 11 box
Thu (14/12) | 14 Dec 2023 | MH2-4 |  | Prepare rebar for manhole shaft work
Thu (14/12) | 14 Dec 2023 | MH2-5 |  | Formwork closing done manhole shaft. Tomorrow to cast
Thu (14/12) | 14 Dec 2023 | Zone 2 P20-21.5 |  | Concrete stump raise up for water pipe alignment casting completed
Thu (14/12) | 14 Dec 2023 | N1 |  | Final levelling till 10pm. Tomorrow only can lean con
Thu (14/12) | 14 Dec 2023 | P9-2 |  | Excavation to lower current level to 22+ msHD. Work till 10pm
Thu (14/12) | 14 Dec 2023 | P30 |  | Guidewall for ST45, 45A and 46 cast yesterday
Thu (14/12) | 14 Dec 2023 | ST40 |  | First bite excavation in progress, 28m
Thu (14/12) | 14 Dec 2023 | MH1-2 |  | Water pumping, night shift team to dismantle 7th layer moulding and proceed to expose existing sewer
Thu (14/12) | 14 Dec 2023 | ST52 |  | 3rd bite excavation started
Thu (14/12) | 14 Dec 2023 | Zone 1 |  | BP P3-7 casting completed..housekeeping now
Thu (14/12) | 14 Dec 2023 | DR2 |  | Cutting of joint between waler and strut at retaining wall side
Thu (14/12) | 14 Dec 2023 | BH87 |  | In progress, 20m
Fri (15/12) | 15 Dec 2023 | MH2-3 |  | No activity
Fri (15/12) | 15 Dec 2023 | MH2-5 |  | 3rd raise wall (2.55m height) to cast in the afternoon
Fri (15/12) | 15 Dec 2023 | N6 |  | Dewatering in progress
Fri (15/12) | 15 Dec 2023 | N5 |  | No activity
Fri (15/12) | 15 Dec 2023 | N4 |  | Dewatering in progress
Fri (15/12) | 15 Dec 2023 | N1 |  | Levelling in progress. To cast lean concrete in the afternoon
Fri (15/12) | 15 Dec 2023 | P10-2 |  | Preboring works for SP & LP
Fri (15/12) | 15 Dec 2023 | P9-2 |  | Excavation & Levelling works to s1 layer
Fri (15/12) | 15 Dec 2023 | P8-2 |  | Rebar installation for pile cap
Fri (15/12) | 15 Dec 2023 | MH1-2 |  | 8th layer manual excavation in progress and expose existing sewer pipe
Fri (15/12) | 15 Dec 2023 | P4-5 |  | Pile Boring in progress. Current depth 5m
Fri (15/12) | 15 Dec 2023 | MH5-2 |  | Pipe jacking setting up works
Fri (15/12) | 15 Dec 2023 | Zone 4 |  | Wee guan 1 team doing TT for SPPG duct corridor
Fri (15/12) | 15 Dec 2023 | ST37 |  | Waterstop fully lowered
Fri (15/12) | 15 Dec 2023 | ST37 |  | Rebar cages u-clip torque test
Fri (15/12) | 15 Dec 2023 | DW57 |  | 1st bite current depth at 23.3m. Teeth changing
Fri (15/12) | 15 Dec 2023 | ST61 |  | Trenching started
Fri (15/12) | 15 Dec 2023 | ST52 |  | Preparation for rebar cage lowering
Fri (15/12) | 15 Dec 2023 | ST52 |  | Hanging bar u-clip torque test
Fri (15/12) | 15 Dec 2023 | MH2-5 |  | 3rd raise wall (2.55m height) - casting completed
Fri (15/12) | 15 Dec 2023 | Zone 4 |  | TT completed for the night. Backfilling in progress
Fri (15/12) | 15 Dec 2023 | N5 |  | Dewatering in progress
Fri (15/12) | 15 Dec 2023 | N1 |  | Pile head trimming in progress. To lean concrete today
Fri (15/12) | 15 Dec 2023 | P10-2 |  | Preboring for SP & LP
Fri (15/12) | 15 Dec 2023 | P9-2 |  | Excavation to S1 layer in progress
Fri (15/12) | 15 Dec 2023 | P8-2 |  | Continue rebar installation for pile cap
Fri (15/12) | 15 Dec 2023 | MH1-2 |  | 8th layer Manual excavation & expose of sewer pipe in progress
Fri (15/12) | 15 Dec 2023 | P4-5 |  | Boring ongoing, current depth 23m
Fri (15/12) | 15 Dec 2023 | MH5-2 |  | Hacking of wall for upcoming pipe jacking works
Fri (15/12) | 15 Dec 2023 | MH1-2 |  | Continue exposing existing sewer
Fri (15/12) | 15 Dec 2023 | ST37 |  | Rebar cage lowering (3/4 cages)
Fri (15/12) | 15 Dec 2023 | ST52 |  | Rebar cages 3/6 lowered
Fri (15/12) | 15 Dec 2023 | ST61 |  | 1st bite trenching at 18m depth
Fri (15/12) | 15 Dec 2023 | Zone 3 |  | Re-laying of SpTel pipe crossing Dwall. Total 15m
Fri (15/12) | 15 Dec 2023 | P9-2 |  | Excavation to W1 to complete tonight. Balance 5 loads
Fri (15/12) | 15 Dec 2023 | P8-2 |  | Bottom and top bars completed. Tomorrow to complete horizontal bars, column starter bar and shearlinks. Still target to cast on Sunday
Fri (15/12) | 15 Dec 2023 | MH1-2 |  | Continue manual excavation to expose existing sewer pipe. Water pumping in progress
Fri (15/12) | 15 Dec 2023 | P4-2 |  | Boring stopped for the day. Tomorrow to complete and cast
Fri (15/12) | 15 Dec 2023 | Zone 1 |  | Lucky joint team here for singtel cable pulling. 4 cables pulled here
Fri (15/12) | 15 Dec 2023 | DW57 |  | 1st and 2nd bite completed. Preparation for internal koden test prior to cleaning and desanding
Fri (15/12) | 15 Dec 2023 | ST40 |  | 2nd bite excavation in progress
Fri (15/12) | 15 Dec 2023 | ST52 |  | Casting, last truck. 201/201 m3
Fri (15/12) | 15 Dec 2023 | ST61 |  | 1st bite trenching
Sat (16/12) | 16 Dec 2023 | Loyang lane near MH2-8 |  | Excavation to replace sppg pipe
Sat (16/12) | 16 Dec 2023 | MH1-2 |  | Excavation continue
Sat (16/12) | 16 Dec 2023 | DW57 |  | 2nd bite cleaning completed. Now shifting BC cutter for 1st bite cleaning. Observed ground condition ok
Sat (16/12) | 16 Dec 2023 | ST61 |  | Continue trenching for 1st bite
Sat (16/12) | 16 Dec 2023 | Zone 4 |  | Shoring works in progress
Sat (16/12) | 16 Dec 2023 | DW57 |  | Desanding in progress. Bentonite stable, ground stable
Sat (16/12) | 16 Dec 2023 | ST40 |  | 3rd bite trenching in progress
Sat (16/12) | 16 Dec 2023 | ST61 |  | 2nd bite trenching
Sat (16/12) | 16 Dec 2023 | Zone 4 |  | TT completed. Area reinstated
Sat (16/12) | 16 Dec 2023 | Zone 3 |  | P25-P26, Krishco completed work for the day, laid 20m 200mm dia pipe
Sat (16/12) | 16 Dec 2023 | N1 |  | Lean con and pile head trimming done
Sat (16/12) | 16 Dec 2023 | P8-2 status |  | CGW stopped work at 8pm
Sat (16/12) | 16 Dec 2023 | MH1-2 |  | Tonight to continue manual excavation to expose existing pipe. Water pumping in progress
Sat (16/12) | 16 Dec 2023 | Zone 1 |  | HSL stopped work for the day. P4-2 cast
Sat (16/12) | 16 Dec 2023 | ST40 |  | BC cutter 2 hydraulic hose burst, need to replace. 1st bite cleaning completed
Sat (16/12) | 16 Dec 2023 | DW57 |  | All rebar cages installed. Hanging bar installation on going
Sat (16/12) | 16 Dec 2023 | ST61 |  | 2nd bite trenching, BC cutter up for teeth replacement
Sun (17/12) | 17 Dec 2023 | N4, N5, N6 |  | Cement apply to the starter bars
Sun (17/12) | 17 Dec 2023 | P9-2 |  | Hard barricadr installation by woh hup
Sun (17/12) | 17 Dec 2023 | P8-2 |  | Formwork closing for pile cap
Sun (17/12) | 17 Dec 2023 | MH5-2 |  | Preparation and testing of TBM machine
Sun (17/12) | 17 Dec 2023 | MH1-2 |  | Manual excavation in progress
Sun (17/12) | 17 Dec 2023 | ST40 |  | Excavation done. Need to do cleaning and desanding. This machine need to replace gear box
Sun (17/12) | 17 Dec 2023 | ST56 |  | Pre excavation in progress
Sun (17/12) | 17 Dec 2023 | ST61 |  | 3rd bite excavation in progress
Sun (17/12) | 17 Dec 2023 | ST40 |  | Cleaning continue
Sun (17/12) | 17 Dec 2023 | DW57 |  | Tremie pipe installation for casting. Concrete ordered
Sun (17/12) | 17 Dec 2023 | MH5-2 |  | Jacking machine lowered down. Hoses connection and set up work
Sun (17/12) | 17 Dec 2023 | MH1-2 |  | Existing sewer pipe got two joints. Jacking pipe
Sun (17/12) | 17 Dec 2023 | MH1-2 |  | Continue manual excavation
Sun (17/12) | 17 Dec 2023 | MH1-2 |  | 8th layer excavation continue
Sun (17/12) | 17 Dec 2023 | Loyang lane near MH2-8 |  | Excavation to replace sppg pipe stopped for the night
Sun (17/12) | 17 Dec 2023 | Zone 3 |  | SPPG pipe laying completed for the night. Area backfilled
Sun (17/12) | 17 Dec 2023 | DW57 |  | Casting in progress. 36/99m3
Sun (17/12) | 17 Dec 2023 | ST40 |  | 1st bite cleaning completed. But BC cutter can not hoist up due to mechanical issue. Dongah BC cutter mechanic will come during dayshift to check and repair
Sun (17/12) | 17 Dec 2023 | MH2-3 to MH2-4 |  | Krishco laying water pipe in progress. Today target 20m
Sun (17/12) | 17 Dec 2023 | MH2-3 |  | Dismantling of jacking frame and removal of slurry pipes
Mon (18/12) | 18 Dec 2023 | Zone 2 |  | Starhub contractor cable pulling towards loyang lane/ave junction
Mon (18/12) | 18 Dec 2023 | MH2-5 |  | Permanent Manhole wall 3rd lift formwork dismantling
Mon (18/12) | 18 Dec 2023 | N6 |  | Waler and strut to cut today
Mon (18/12) | 18 Dec 2023 | MH2-4 |  | Permanent Manhole wall 2nd lift formwork dismantling
Mon (18/12) | 18 Dec 2023 | N5 |  | Soil backfilling and compaction to S1 layer in progress
Mon (18/12) | 18 Dec 2023 | N1 |  | Rebar installation for pile cap
Mon (18/12) | 18 Dec 2023 | P9-2 |  | Waler brackets & Waler welding & installation
Mon (18/12) | 18 Dec 2023 | P8-2 |  | Shearlinks installation. Tomorrow only WH plan to cast
Mon (18/12) | 18 Dec 2023 | Zone 1 |  | M1 T&C
Mon (18/12) | 18 Dec 2023 | P10-2 |  | Installation of lagging plate in progress. Today to complete
Mon (18/12) | 18 Dec 2023 | MH1-2 |  | Excavation for 8th layer (0.6m) in progress
Mon (18/12) | 18 Dec 2023 | P3-8 |  | Boring in progress. Final toe level tatget to confirm by 1pm. To cast today
Mon (18/12) | 18 Dec 2023 | MH5-2 |  | TBM lowered down. Setting up in progress
Mon (18/12) | 18 Dec 2023 | MH2-9 |  | Excavation for 9th layer in progress
Mon (18/12) | 18 Dec 2023 | Zone 4 |  | Hacking for perimeter drain
Mon (18/12) | 18 Dec 2023 | MH2-7 |  | Slurry cleaning / Houskeeping for MH base construction next
Mon (18/12) | 18 Dec 2023 | Zone 4 |  | P46 transfer beam TT on going
Mon (18/12) | 18 Dec 2023 | MH2-4 |  | Permanent Manhole wall 2nd lift formwork dismantled. Preparing for backfilling works
Mon (18/12) | 18 Dec 2023 | Zone 3 |  | Starhub cable pulling towards loyang way junction
Mon (18/12) | 18 Dec 2023 | PBH28 |  | TT on going
Mon (18/12) | 18 Dec 2023 | PBH26 |  | Drilling at 30m depth
Mon (18/12) | 18 Dec 2023 | PBH22 |  | Hand augering
Mon (18/12) | 18 Dec 2023 | Zone 4 LW junction |  | Starhub cable pulling
Mon (18/12) | 18 Dec 2023 | ST67, 67A and 68 |  | Guidewall excavation work
Mon (18/12) | 18 Dec 2023 | N6 |  | Removal of waler & strut in progress
Mon (18/12) | 18 Dec 2023 | ST61 |  | Hanging bar installation. To cast around 5pm
Mon (18/12) | 18 Dec 2023 | ST56 |  | 1st bite trenching at 39m depth
Mon (18/12) | 18 Dec 2023 | ST43 |  | Casing installation for pre-boring works
Mon (18/12) | 18 Dec 2023 | P10-2 |  | ERSS installation completed. Now LE shifting materials to south ramp. They plan to do south ramp ERSS next
Mon (18/12) | 18 Dec 2023 | P10-2 |  | Trial trench in progress for vehicular access making
Mon (18/12) | 18 Dec 2023 | ST40 |  | Tremie pipe installation. Target to cast around 5pm
Mon (18/12) | 18 Dec 2023 | ST36 |  | Trenching temporarily stopped due to hydraulic oil leak
Mon (18/12) | 18 Dec 2023 | P9-2 |  | Welding of waler beams in progress. Today to cast concrete packing too
Mon (18/12) | 18 Dec 2023 | P8-2 |  | Continue shearlinks installation
Mon (18/12) | 18 Dec 2023 | MH1-2 |  | Excavation for 8th layer (0.6m) in progress. Mini excavator lowered
Mon (18/12) | 18 Dec 2023 | P3-8 |  | Boring completed. Now preparing for casting
Mon (18/12) | 18 Dec 2023 | Near MH2-8 |  | Wee Guan preparing for excavation and shoring for rectification of duct
Mon (18/12) | 18 Dec 2023 | ST36 |  | 1st bite in progress, 19m
Mon (18/12) | 18 Dec 2023 | North ramp P10-2 |  | Excavation in progress by KTC. Tonight workinh until 10PM
Mon (18/12) | 18 Dec 2023 | P8-2 |  | Working platform preparation for pump car for tomorrow casting
Mon (18/12) | 18 Dec 2023 | MH1-2 |  | Manual excavation in progress for 8th layer
Mon (18/12) | 18 Dec 2023 | MH5-2 |  | Cable connection for jacking machine
Tue (19/12) | 19 Dec 2023 | MH2-4 |  | Backfilling works at 4th lift permanent wall
Tue (19/12) | 19 Dec 2023 | MH2-5 |  | Backfilling for 3rd lift permanent wall
Tue (19/12) | 19 Dec 2023 | Zone 2 |  | Starhub cable pulling works continue
Tue (19/12) | 19 Dec 2023 | Zone 2 |  | CGS here Doing TT for the relocation of bus stop for Stage 1 diversion
Tue (19/12) | 19 Dec 2023 | N6 |  | Waler beam and strut dismantling
Tue (19/12) | 19 Dec 2023 | P10-2 |  | Excavation to W1 completed
Tue (19/12) | 19 Dec 2023 | P9-2 |  | Waler beam welding works continue. MPI today
Tue (19/12) | 19 Dec 2023 | P8-2 |  | Shearlinks tying, cast today around 3pm
Tue (19/12) | 19 Dec 2023 | Zone 1 |  | BP works temporarily stopped for water pipe link up
Tue (19/12) | 19 Dec 2023 | MH2-9 |  | Excavation works for 9th layer
Tue (19/12) | 19 Dec 2023 | MH2-5 |  | Continue backfilling works
Tue (19/12) | 19 Dec 2023 | MH2-7 |  | Rebar installation for MH construction
Tue (19/12) | 19 Dec 2023 | Zone 2 |  | CGS manual excavation - TT for the relocation of bus stop for Stage 1 diversion
Tue (19/12) | 19 Dec 2023 | P10-2 |  | Preparation works for waler brackets installation
Tue (19/12) | 19 Dec 2023 | P9-2 |  | MPI completed. KTC will continue with FEL excavation next
Tue (19/12) | 19 Dec 2023 | N5 |  | 1st & 2nd layer soil backfilling & NDT test done
Tue (19/12) | 19 Dec 2023 | N1 |  | Rebar installation in progress
Tue (19/12) | 19 Dec 2023 | P8-2 |  | Casting ongoing for pilecap
Tue (19/12) | 19 Dec 2023 | Zone 4 |  | Hacking of perimeter drain status
Tue (19/12) | 19 Dec 2023 | P47 |  | Transfer beam TT
Tue (19/12) | 19 Dec 2023 | P48 |  | Transfer beam TT
Tue (19/12) | 19 Dec 2023 | Zone 3 loyang way |  | Krishco here doing TT to find existing pipe as pick up point for the diversion work
Tue (19/12) | 19 Dec 2023 | Starhub cable pulling at zone 3 |  | Last 2 cables to be able to compete by tomorrow
Tue (19/12) | 19 Dec 2023 | MH1-2 |  | Trimming completed for half of 8th layer ring. BRC installation in progress. Target to cast tonight
Tue (19/12) | 19 Dec 2023 | ST168 and 169 |  | Guidewall for casting. Concrete ordered
Tue (19/12) | 19 Dec 2023 | ST56 |  | 1st bite trenching continue
Tue (19/12) | 19 Dec 2023 | MH5-2 |  | TBM jacking in progress. Going to lower pipe no. 1 next
Tue (19/12) | 19 Dec 2023 | ST43 |  | Pre boring works on going. Current depth 30/38.3m
Tue (19/12) | 19 Dec 2023 | ST36 |  | Cleaning still on hold due to BC cutter maintenence
Tue (19/12) | 19 Dec 2023 | Exit 2 |  | DW63 pre-excavation, tomorrow to start trenching
Tue (19/12) | 19 Dec 2023 | Zone 3 |  | Balance sptel pipe connection to complete today
Tue (19/12) | 19 Dec 2023 | Zone 2 |  | Bus stop location for stage 1 so far no utility found from TT
Tue (19/12) | 19 Dec 2023 | N1 |  | Column starter bar installation. Tomorrow to cloae formwork and start shearlinks installation
Tue (19/12) | 19 Dec 2023 | P10-2 |  | Waler bracket installation in progress
Tue (19/12) | 19 Dec 2023 | P9-2 |  | Access and barricade installation. Tonight KTC will work late to start excavation to FEL
Tue (19/12) | 19 Dec 2023 | P8-2 |  | Casting continue. Balance 2 loads, 72m3
Tue (19/12) | 19 Dec 2023 | MH1-2 |  | 8th layer rebar works in progress. To cast around 9pm
Tue (19/12) | 19 Dec 2023 | MH5-2 |  | Jacking to MH1-2 started
Tue (19/12) | 19 Dec 2023 | MH1-2 |  | Excavation done. Left trimming for BRC installation
Tue (19/12) | 19 Dec 2023 | MH1-2 |  | BRC installation in progress, tonight to cast
Tue (19/12) | 19 Dec 2023 | Near MH2-8 |  | Wee Guan excavation and ERSS installation for Power duct rectification
Wed (20/12) | 20 Dec 2023 | ST168-169 |  | Guidewall cast yesterday
Wed (20/12) | 20 Dec 2023 | N1 |  | Shearlinks installation, Tomorrow to cast
Wed (20/12) | 20 Dec 2023 | P10-2 |  | Waler beam installation. Today to cast packing concrete, tomorrow mpi
Wed (20/12) | 20 Dec 2023 | P9-2 |  | Excavation to FEL
Wed (20/12) | 20 Dec 2023 | P8-2 |  | Curing
Wed (20/12) | 20 Dec 2023 | Zone 1 |  | SPPG here preparing area for cable pulling
Wed (20/12) | 20 Dec 2023 | MH1-2 |  | 8th layer half curing
Wed (20/12) | 20 Dec 2023 | Zone 1 |  | Krishco excavation of open pit for link up
Wed (20/12) | 20 Dec 2023 | DR2 |  | No activity
Wed (20/12) | 20 Dec 2023 | ST67, 67A, 68 |  | Guidewall formwork installation ongoing. Plan for casting today
Wed (20/12) | 20 Dec 2023 | PBH24 |  | In progress, 29m
Wed (20/12) | 20 Dec 2023 | Zone 4 P47 & P48 |  | Continue trial trench for transfer beam (2 teams)
Wed (20/12) | 20 Dec 2023 | Zone 4 |  | Current status of perimeter drain. Plan to continue lean con casting
Wed (20/12) | 20 Dec 2023 | MH5-2 |  | Jacking to 1-2 for 2nd pipe
Wed (20/12) | 20 Dec 2023 | Zone 3 PBH33 |  | Trial trench ongoing
Wed (20/12) | 20 Dec 2023 | ST56 |  | Continue first bite excavation
Wed (20/12) | 20 Dec 2023 | ST43 |  | Preboring in progress
Wed (20/12) | 20 Dec 2023 | P25 |  | WG preparation for power duct mandrel test
Wed (20/12) | 20 Dec 2023 | MH1-2 |  | Formwork closing in progress. Concrete ordered
Wed (20/12) | 20 Dec 2023 | ST56 |  | U-clip inspection for rebar cages (8nos) & hanging bars (8nos) done
Wed (20/12) | 20 Dec 2023 | MH2-3 |  | Jacking frame dismantled
Wed (20/12) | 20 Dec 2023 | MH2-4 |  | 4th lift wall backfilling
Wed (20/12) | 20 Dec 2023 | ST36 |  | U-clip inspection for rebar cages done (8nos)
Wed (20/12) | 20 Dec 2023 | ST36 |  | Cleaning ongoing
Wed (20/12) | 20 Dec 2023 | ST167-166A |  | Preparation for guidewall works
Wed (20/12) | 20 Dec 2023 | ST43 |  | Preboring in progress, 36m/38.24m
Wed (20/12) | 20 Dec 2023 | ST67-68 |  | Guidewall cast before lunch today
Wed (20/12) | 20 Dec 2023 | Zone 3 PBH28, PBH30 |  | Just started
Wed (20/12) | 20 Dec 2023 | DW63 |  | Excavation temporarily stopped for cutter teeth replacement
Wed (20/12) | 20 Dec 2023 | Next to MH2-8 |  | Power duct pipes rectification & mandrel test
Wed (20/12) | 20 Dec 2023 | MH2-7 |  | Base slab & wall rebar works ongoing
Wed (20/12) | 20 Dec 2023 | Zone 1 |  | Krishco preparation work for excavation of open pit for tmr link up
Wed (20/12) | 20 Dec 2023 | Zone 2 |  | TT for bus stop relocation, found starhub slab
Wed (20/12) | 20 Dec 2023 | P16 |  | Premix cutting for TT work
Wed (20/12) | 20 Dec 2023 | N6 |  | Surface roughening and column stump shearlinks installation
Wed (20/12) | 20 Dec 2023 | N1 |  | Formworks closing
Wed (20/12) | 20 Dec 2023 | P10-2 |  | Waler beam welding continue. Today to cast packing concrete
Wed (20/12) | 20 Dec 2023 | P9-2 |  | Excavation to FEL
Wed (20/12) | 20 Dec 2023 | MH2-9 |  | 9th layer excavation. Tonight LCH night shift team will be working here
Wed (20/12) | 20 Dec 2023 | P10-2 |  | Hard barricade installation
Wed (20/12) | 20 Dec 2023 | P9-2 |  | Excavation in progress. KTC will try to complete excavation tonight
Thu (21/12) | 21 Dec 2023 | N1 |  | Formwork closing. Balance shearlinks, to cast tomorrow
Thu (21/12) | 21 Dec 2023 | P10 |  | Waler beam welding, 11 am to do MPI
Thu (21/12) | 21 Dec 2023 | P9 |  | Preparation for pile head cutting and hacking
Thu (21/12) | 21 Dec 2023 | MH3-5 |  | TT completed. No services found until 2m depth
Thu (21/12) | 21 Dec 2023 | MH3-6 |  | TT also completed. Found Singtel duct laid by Wee Guan
Thu (21/12) | 21 Dec 2023 | MH1-2 |  | Continue excavation
Thu (21/12) | 21 Dec 2023 | Zone 1 LA towards PRD3 |  | First lane closure by Ley Choon for the cable pulling works
Thu (21/12) | 21 Dec 2023 | MH2-9 |  | Continue excavation for caisson shaft
Thu (21/12) | 21 Dec 2023 | MH2-5 |  | Precast chamber 3rd lift installed
Thu (21/12) | 21 Dec 2023 | N1 |  | Shearlinks installation in progress
Thu (21/12) | 21 Dec 2023 | P10 |  | MPI completed. Excavation to FEL in progress
Thu (21/12) | 21 Dec 2023 | P9 |  | Cutting of pile head to COL continue, last pile
Thu (21/12) | 21 Dec 2023 | MH1-2 |  | Water pumping before continuing excavation
Thu (21/12) | 21 Dec 2023 | Zone 1 |  | Water pipe link up. Est to complete by 530pm
Thu (21/12) | 21 Dec 2023 | MH2-7 |  | Base slab casting (last truck). Total volume: 9m3
Thu (21/12) | 21 Dec 2023 | N6 and N5 |  | No activity
Thu (21/12) | 21 Dec 2023 | P10 |  | KTC excavation and internal soil shifting. Works till 10pm
Thu (21/12) | 21 Dec 2023 | MH5-2 |  | Pipe jacking ongoing, 7/45nos. Works till 10pm
Thu (21/12) | 21 Dec 2023 | MH1-2 |  | Night shift team on site. Now dewatering prior to continuing excavation for layer 8 (second part)
Thu (21/12) | 21 Dec 2023 | ST56 |  | BC cutter teeth replacement ongoing. First bite current depth 36.82m
Thu (21/12) | 21 Dec 2023 | DW63 |  | Casting completed. Total vol: 60m3
Thu (21/12) | 21 Dec 2023 | MH2-9 |  | BRC installation in progress. Today to cast
Thu (21/12) | 21 Dec 2023 | DR2 |  | No activity
Thu (21/12) | 21 Dec 2023 | Zone 4 |  | No activity tonight
Thu (21/12) | 21 Dec 2023 | MH2-7 |  | Base slab rebar works. To cast tonight
Thu (21/12) | 21 Dec 2023 | MH2-5 |  | 3rd lift precast wall to install today
Thu (21/12) | 21 Dec 2023 | ST41 |  | 2nd bite in progress
Thu (21/12) | 21 Dec 2023 | Next to MH2-8 |  | WG backfilling ongoing for the power duct trench
Thu (21/12) | 21 Dec 2023 | Zone 2 |  | Stage 1 temp bus stop location TT towards south bound
Thu (21/12) | 21 Dec 2023 | Zone 2 |  | Stage 1 temp bus stop location premix cutting at north bound
Fri (22/12) | 22 Dec 2023 | MH2-9 |  | Caisson still curing. Housekeeping and maintenance work
Fri (22/12) | 22 Dec 2023 | MH2-8 |  | Continue set up for jacking work. Thrust block casting will be tomorrow
Fri (22/12) | 22 Dec 2023 | Zone 4 |  | First lane closed for trial trench works
Fri (22/12) | 22 Dec 2023 | ST41 |  | Excavation temporarily stopped for cutter teeth replacement
Fri (22/12) | 22 Dec 2023 | Zone 1 LA towards PRD3 |  | First lane closed for SPPG cable pulling
Fri (22/12) | 22 Dec 2023 | Zone 3 |  | SPTel pipe laying works towards Exit 2
Fri (22/12) | 22 Dec 2023 | Zone 2 |  | Activ mobilised today to pull 3 cables from Zone 2 towards Zone 3
Fri (22/12) | 22 Dec 2023 | Zone 2 MH5-2 |  | 8/45nos pipe jacking in progress
Fri (22/12) | 22 Dec 2023 | ST41 |  | In progress, 28.2m
Fri (22/12) | 22 Dec 2023 | ST56 |  | First bite current depth at 37.17m. Now cutter teeth replacement ongoing
Fri (22/12) | 22 Dec 2023 | MH1-2 |  | Continue excavation
Fri (22/12) | 22 Dec 2023 | MH2-7 |  | Pipe joining in progress. Works till 10pm
Fri (22/12) | 22 Dec 2023 | P9 |  | Pile rebar cutting ongoing til 10pm
Fri (22/12) | 22 Dec 2023 | N1 |  | Pilecap was cast this afternoon
Fri (22/12) | 22 Dec 2023 | MH5-2 |  | No activity
Fri (22/12) | 22 Dec 2023 | MH1-2 |  | Tonight to continue excavation for layer 8 (part 2)
Fri (22/12) | 22 Dec 2023 | ST56 |  | 2nd bite excavation in progress, 26.3m
Fri (22/12) | 22 Dec 2023 | P37 |  | Drain hacking done for the hacking of retaining wall works
Fri (22/12) | 22 Dec 2023 | Zone 4 |  | Tonight 1 team (WG) plan for TT on road at Loyang Ave. Now material preparation ongoing
Sat (23/12) | 23 Dec 2023 | Zone 3 |  | PBH22 SI at 29m depth. To terminate at ~34m depth
Sat (23/12) | 23 Dec 2023 | Zone 4 |  | Premix hacking for Trial GI started. To finish trial trench for trial GI points on Tues and start trial GI on Wed
Sat (23/12) | 23 Dec 2023 | Zone 4 LA towards Loyang Way |  | Lane closure for SPPG trial trench
Sat (23/12) | 23 Dec 2023 | Zone 4 |  | GCE rig mobilised in yesterday. Repair of the machine and connection of the hoses to be done today
Sat (23/12) | 23 Dec 2023 | Zone 4 |  | GCE equipment, water tank etc were all shifted in yesterday. Setting up in progress
Sat (23/12) | 23 Dec 2023 | ST41 |  | To continue chiselling at waterstop side
Sat (23/12) | 23 Dec 2023 | Zone 4 |  | 2 teams for P48 Trial trench
Sat (23/12) | 23 Dec 2023 | Zone 3 substation |  | Leychoon under sppg will be doing 2 trial trenches to find the sppg pipes today
Sat (23/12) | 23 Dec 2023 | Zone 3 substation |  | Leychoon mobilised in and shifted in quarry dust
Sat (23/12) | 23 Dec 2023 | Zone 3 near substation |  | Sptel pipe laying works
Sat (23/12) | 23 Dec 2023 | MH1-2 |  | Continue excavation
Sat (23/12) | 23 Dec 2023 | Zone 4 |  | Trial trench completed
Sat (23/12) | 23 Dec 2023 | Zone 2 |  | S3 pilecap ERSS preboring to start on Tuesday
Sat (23/12) | 23 Dec 2023 | Zone 1 |  | P4-4 casting started. 1st concrete truck. Total volume 56m³
Sat (23/12) | 23 Dec 2023 | Zone 2 |  | CGS excavation for the other temp bus stop
Sat (23/12) | 23 Dec 2023 | Zone 1 TPE bound |  | Singtel works ongoing
Sat (23/12) | 23 Dec 2023 | DW58 |  | Trimming ongoing at DW59 waterstop side
Sat (23/12) | 23 Dec 2023 | ST41 |  | Flap welding ongoing
Sat (23/12) | 23 Dec 2023 | ST56 |  | Trenching temporarily stopped for cutter teeth replacement. Second bite current depth at 33.4m
Sat (23/12) | 23 Dec 2023 | ST41 |  | U-clip inspection done for rebar cages and hanging bars
Sat (23/12) | 23 Dec 2023 | DW58 |  | U-clip inspection done for rebar cages and hanging bars
Sat (23/12) | 23 Dec 2023 | Zone 1 |  | No activity by other contractors
Sat (23/12) | 23 Dec 2023 | MH2-7 |  | Wall casting
Sat (23/12) | 23 Dec 2023 | MH2-4 |  | 2nd wall formwork installation ongoing
Sat (23/12) | 23 Dec 2023 | N6 |  | Water pump installation
Sat (23/12) | 23 Dec 2023 | P9 |  | Base lean con casting complex
Sat (23/12) | 23 Dec 2023 | MH5-2 |  | Pipe jacking 11/45nos. Works till 10pm
Sat (23/12) | 23 Dec 2023 | MH1-2 |  | Night shift team preparing to continue layer 8 (part 2). Tonight plan for BRC installation
Sat (23/12) | 23 Dec 2023 | ST56 |  | 2nd bite excavation in progress, 35.5m
Sat (23/12) | 23 Dec 2023 | Zone 3 Vent shaft area |  | Soil leveling by KTC. To conduct NDT on Tues
Sun (24/12) | 24 Dec 2023 | Zone 4 |  | Trial trench done. No services found
Sun (24/12) | 24 Dec 2023 | MH1-2 |  | Continue trimming and lowering of BRC
Sun (24/12) | 24 Dec 2023 | ST41 |  | First bite cleaning in progress
Sun (24/12) | 24 Dec 2023 | ST56 |  | 2nd bite excavation in progress
Sun (24/12) | 24 Dec 2023 | MH1-2 |  | BRC installation ongoing
Mon (25/12) | 25 Dec 2023 | Zone 2 |  | Krishco preparation works for upcoming cctv inspection for water pipe
Mon (25/12) | 25 Dec 2023 | JTC - ST35A (2.8m X 1.2m) | SC40#02 | 1st bite Excavation in progress, Current depth 19m/35.62m
Mon (25/12) | 25 Dec 2023 | JTC - ST41 |  | Tremie pipe lowered. Now waiting for concrete truck to arrive for casting works
Mon (25/12) | 25 Dec 2023 | DW-64 |  | Pre excavation completed. Today will start trenching works
Mon (25/12) | 25 Dec 2023 | Zone 3 |  | Guidewall excavation works for ST49 to ST51
Mon (25/12) | 25 Dec 2023 | BLK 4 - ST56 (5.791m X 1.2m) | SC40#01 | 2nd bite cleaning in progress
Mon (25/12) | 25 Dec 2023 | ST165 |  | Formwork installation for guidewall. Today to cast
Mon (25/12) | 25 Dec 2023 | Zone 3 |  | KTC soil clearing and levelling for upcoming ST163 & ST164 guidewall works
Mon (25/12) | 25 Dec 2023 | Zone 4 |  | No activity
Mon (25/12) | 25 Dec 2023 | N6 |  | No activity
Mon (25/12) | 25 Dec 2023 | N5 |  | No activity
Mon (25/12) | 25 Dec 2023 | N4 |  | No activity
Mon (25/12) | 25 Dec 2023 | N3 |  | No activity
Mon (25/12) | 25 Dec 2023 | N2 |  | No activity
Mon (25/12) | 25 Dec 2023 | N1 |  | No activity. Cast last Friday
Mon (25/12) | 25 Dec 2023 | P10-2 |  | Debris clearing and levelling works for lean concrete today
Mon (25/12) | 25 Dec 2023 | P9-2 |  | Rebar installation for pilecap
Mon (25/12) | 25 Dec 2023 | P8-2 |  | No activity
Mon (25/12) | 25 Dec 2023 | Zone 1 |  | No activity
Mon (25/12) | 25 Dec 2023 | MH5-2 |  | Pipe jacking in progress. 13th pipe lowered. 13/45nos
Mon (25/12) | 25 Dec 2023 | Exit 3 |  | Washing bay removal of soil in progress
Mon (25/12) | 25 Dec 2023 | MH2-8 |  | Entrance hacking for pipe jacking works in progress
Tue (26/12) | 26 Dec 2023 | DW64 |  | Rebar cage installation in progress, 6/6nos
Tue (26/12) | 26 Dec 2023 | ST42 |  | First bite trenching in progress
Tue (26/12) | 26 Dec 2023 | ST35A |  | Water stop endplate joining ongoing
Tue (26/12) | 26 Dec 2023 | MH2-7 |  | Chamber ring rebar inspected and formwork installation in progress. Casting will be done today
Tue (26/12) | 26 Dec 2023 | MH2-5 |  | 2nd lift precast chamber ring installation in progress
Tue (26/12) | 26 Dec 2023 | MH2-3 |  | Cleaning works in progress for MH construction work
Tue (26/12) | 26 Dec 2023 | Exit 3 |  | KTC bus lane backfilling & leveling works
Tue (26/12) | 26 Dec 2023 | Zone 2 |  | CGS BRC installation for temp bus stop base slab. Target to cast today
Tue (26/12) | 26 Dec 2023 | P10-2 |  | Lean concrete cast yesterday
Tue (26/12) | 26 Dec 2023 | P9-2 |  | Shear links installation in progress for pile cap
Tue (26/12) | 26 Dec 2023 | P8-2 |  | Dewatering in progress
Tue (26/12) | 26 Dec 2023 | P4-6 |  | Preboring for BP casing installation
Tue (26/12) | 26 Dec 2023 | Zone 2 |  | CGS still constructing the base slab. Plan for casting tmr
Tue (26/12) | 26 Dec 2023 | MH1-2 |  | Excavation ongoing
Tue (26/12) | 26 Dec 2023 | P3-9 |  | Casting completed
Tue (26/12) | 26 Dec 2023 | Zone 1 |  | Rebar cage delivery for next bored pile
Tue (26/12) | 26 Dec 2023 | P9-2 |  | Formwork installation ongoing
Tue (26/12) | 26 Dec 2023 | Zone 4 LA LP105 | towards Loyang Way | PUB works ongoing
Tue (26/12) | 26 Dec 2023 | Zone 4 LA towards Loyang Way |  | WG plan for SPPG pipe laying tonight (roadside). Preparation works ongoing
Wed (27/12) | 27 Dec 2023 | Zone 2-3 |  | Krishco preparing for CCTV inspection for 300mm water pipe
Wed (27/12) | 27 Dec 2023 | MH2-5 |  | Rebar installation for 2nd lift chamber ring
Wed (27/12) | 27 Dec 2023 | Zone 2 P16 |  | Preparation for bus stop base slab rebar works
Wed (27/12) | 27 Dec 2023 | ST56 |  | Bite 1 cleaning completed. Bite 2 cleaning start
Wed (27/12) | 27 Dec 2023 | ST42 |  | First bite excavation temporarily stopped due to cutter mud pump choked. Rectification ongoing. Current depth 33.4m
Wed (27/12) | 27 Dec 2023 | P10-2 |  | Rebar installation for pile cap in progress
Wed (27/12) | 27 Dec 2023 | P9-2 |  | Shear links installation ongoing, to cast pilecap today
Wed (27/12) | 27 Dec 2023 | MH1-2 |  | Excavation for 9th layer in progress
Wed (27/12) | 27 Dec 2023 | MH3-5 |  | TT for inclinometer
Wed (27/12) | 27 Dec 2023 | MH1-2 |  | Continue soil hacking and excavation for layer 9 (part 1)
Wed (27/12) | 27 Dec 2023 | MH2-8 |  | TBM pipe jacking in progress
Wed (27/12) | 27 Dec 2023 | MH2-5 |  | 3m height BRC inspected. Formwork closing in progress. Will cast today
Wed (27/12) | 27 Dec 2023 | Zone 2 |  | Temp bus stop BRC laying in progress, to cast the base today
Wed (27/12) | 27 Dec 2023 | Between P8-2 & P9-2 |  | Trial trench works in progress for ABH22-1
Wed (27/12) | 27 Dec 2023 | N1 |  | Formwork dismantling in progress
Wed (27/12) | 27 Dec 2023 | P10-2 |  | Rebar installation for pile cap
Wed (27/12) | 27 Dec 2023 | P9-2 |  | Rebar installation for pile cap completed, now QPS inspection. Today will cast pile cap
Wed (27/12) | 27 Dec 2023 | ST35A |  | Rebar cage installation in progress
Wed (27/12) | 27 Dec 2023 | ST42 |  | Continue first bite excavation
Wed (27/12) | 27 Dec 2023 | DW64 |  | Casting ongoing. Progressive vol: 45/95m3
Wed (27/12) | 27 Dec 2023 | ST56 |  | Chiselling in progress
Wed (27/12) | 27 Dec 2023 | Zone 4 |  | SPPG pipes laid, 4m
Wed (27/12) | 27 Dec 2023 | MH2-8 to MH2-9 |  | 1st pipe start jacking in progress. Around 25 pipes to reach to the outer caisson of MH2-9. Total will be around 27 pipes
Wed (27/12) | 27 Dec 2023 | MH2-5 |  | Shaft casting done
Wed (27/12) | 27 Dec 2023 | MH1-2 |  | Excavation for 9th layer
Wed (27/12) | 27 Dec 2023 | P4-6 |  | Preparation done for casting. Concrete on the way
Wed (27/12) | 27 Dec 2023 | MH2-5 |  | Pipe no-16 jacking in progress
Wed (27/12) | 27 Dec 2023 | P9-2 |  | Casting in progress
Wed (27/12) | 27 Dec 2023 | MH5-2 |  | Pipe jacking no.16 ongoing. Pipe 17 lowered. Works till 10pm
Wed (27/12) | 27 Dec 2023 | P4-6 |  | Casting completed. Tremie pipes removal ongoing
Wed (27/12) | 27 Dec 2023 | MH1-2 |  | Continue excavation for layer 9 (part 1)
Wed (27/12) | 27 Dec 2023 | MH2-7 |  | Permanent MH wall casting in progress
Wed (27/12) | 27 Dec 2023 | MH2-8 |  | No activitu
Wed (27/12) | 27 Dec 2023 | Zone 4 LP105 | LA towards LW | WG to continue trial trench for SPPG pipe laying
Thu (28/12) | 28 Dec 2023 | Zone 4 |  | Utility safety briefing for JGP team
Thu (28/12) | 28 Dec 2023 | MH2-4 |  | Preparation for outer wall rebar work
Thu (28/12) | 28 Dec 2023 | PBH27 |  | In progress, 6m
Thu (28/12) | 28 Dec 2023 | Zone 2 | P16 | Temp bus stop base slab rebar installation completed. Concrete ordered for casting
Thu (28/12) | 28 Dec 2023 | P10-2 |  | Hard barricades installation & marking for formwork installation ongoing
Thu (28/12) | 28 Dec 2023 | P9-2 |  | Pilecap cast yesterday, curing in progress
Thu (28/12) | 28 Dec 2023 | ABH22-1 |  | Manual trial trench in progress
Thu (28/12) | 28 Dec 2023 | Zone 1 |  | MH1-2 excavation for 9th layer (0.6m)
Thu (28/12) | 28 Dec 2023 | Zone 1 |  | P3-6 boring in progress for casing installation
Thu (28/12) | 28 Dec 2023 | MH5-2 |  | Pipe no.17 pipe jacking towards existing manhole at Z1 ongoing
Thu (28/12) | 28 Dec 2023 | ST42 |  | First bite excavation ongoing, 33.6m. Now cutter body up for some rectification
Thu (28/12) | 28 Dec 2023 | ST56 |  | Desanding in progress
Thu (28/12) | 28 Dec 2023 | MH2-8 |  | Jacking machine already retrieved and send back to factory
Thu (28/12) | 28 Dec 2023 | P10-2 |  | Preparing for footing formwork closing
Thu (28/12) | 28 Dec 2023 | MH1-2 |  | Preparing to shift mini to continue excavation
Thu (28/12) | 28 Dec 2023 | MH2-7 |  | Casting completed last night
Thu (28/12) | 28 Dec 2023 | MH2-8 |  | Continue pipe jacking works
Thu (28/12) | 28 Dec 2023 | ST48 | PB2 | Preboring temporarily stopped for gear box motor repair
Thu (28/12) | 28 Dec 2023 | ST49-50 |  | Guidewall formwork dismantling ongoing
Thu (28/12) | 28 Dec 2023 | ST56 |  | Rebar cage installation in progress, 2/8nos
Thu (28/12) | 28 Dec 2023 | Zone 4 slow lane |  | Wee Guan road cutting for power duct laying
Fri (29/12) | 29 Dec 2023 | Zone 4 |  | Marking of utility alignment prior to JGP works
Fri (29/12) | 29 Dec 2023 | P51 |  | WH continue trial trench for transfer beam
Fri (29/12) | 29 Dec 2023 | Zone 4 |  | WH preparing to install hoarding panel near Gate 8
Fri (29/12) | 29 Dec 2023 | Zone 4 |  | WG open trench for power duct pipe laying
Fri (29/12) | 29 Dec 2023 | ST56 |  | Casting in progress, 297/297m3
Fri (29/12) | 29 Dec 2023 | Exit 2 |  | Noise barrier panels for desander dismantled
Fri (29/12) | 29 Dec 2023 | Zone 4 junction |  | No activity
Fri (29/12) | 29 Dec 2023 | MH2-8 |  | No activity
Fri (29/12) | 29 Dec 2023 | ST42 |  | Flap support welding ongoing
Fri (29/12) | 29 Dec 2023 | MH2-7 |  | MH wall formwork dismantling in progress
Fri (29/12) | 29 Dec 2023 | 1. joel |  | Travel adapter
Fri (29/12) | 29 Dec 2023 | MH2-3 |  | Thrust block hacking ongoing
Fri (29/12) | 29 Dec 2023 | MH2-4 |  | MH wall (last lift) rebars inspected. Now preparation for formwork installation
Fri (29/12) | 29 Dec 2023 | P10-2 |  | Shear links and formwork installation in progress
Fri (29/12) | 29 Dec 2023 | MH1-2 |  | Continue manual trimming for layer 9 (part 1)
Fri (29/12) | 29 Dec 2023 | Zone 1 P3-6 |  | Casting in progress
Fri (29/12) | 29 Dec 2023 | Zone 4 |  | GCE plans to start JGP at TB7 once all 7 pipes are installed at the drilling points
Fri (29/12) | 29 Dec 2023 | MH5-2 |  | Pipe jacking 19 ongoing
Fri (29/12) | 29 Dec 2023 | Zone 4 |  | Uknown slab found at TB2X trial trench. GCE has already informed WHDA utility team
Fri (29/12) | 29 Dec 2023 | Zone 2 |  | Excavation and levelling works ongoing for second bus stop
Fri (29/12) | 29 Dec 2023 | Zone 2 near MH2-5 |  | Singtel cable pulling ongoing
Fri (29/12) | 29 Dec 2023 | Gate 8 |  | Hoarding installation in progress
Fri (29/12) | 29 Dec 2023 | MH2-9 |  | Excavation ongoing for 10th layer
Fri (29/12) | 29 Dec 2023 | MH2-8 |  | Jacking machine will deliver tomorrow. One worker was provided during night shift to pump out water during heavy rain
Fri (29/12) | 29 Dec 2023 | MH2-5 |  | Formwork dismantling
Fri (29/12) | 29 Dec 2023 | MH1-2 |  | BRC installation. Tonight to cast
Fri (29/12) | 29 Dec 2023 | PBH27 |  | In progress, 26m
Sat (30/12) | 30 Dec 2023 | MH2-8 |  | Preparation to lower the TBM and resume with pipe jacking
Sat (30/12) | 30 Dec 2023 | Along zone 2 - 3 |  | Krishco rectifying the comments given during 1st cctv inspection. Changing the pipe in progress
Sat (30/12) | 30 Dec 2023 | Blk 4 - ST062 |  | Endplate removal completed (ST061 side). Now preparing for cleaning
Sat (30/12) | 30 Dec 2023 | ST062 |  | Rebar cage & Hanging bar U clip torque wrench inspection completed
Sat (30/12) | 30 Dec 2023 | JTC - ST042 | SC40#02 | Internal koden test in progress. Current 2nd bite excavation depth 26.5m
Sat (30/12) | 30 Dec 2023 | Zone 3 |  | Formwork installation for ST163 & ST164 guidewall works
Sat (30/12) | 30 Dec 2023 | Zone 3 PBH-29 |  | Drilling in progress, current depth 15m
Sat (30/12) | 30 Dec 2023 | Zone 3 PBH-32 |  | Drilling in progress, current depth 34m
Sat (30/12) | 30 Dec 2023 | Zone 4 MH3-5 |  | RyobiG Drilling for Inclinometer in progress
Sat (30/12) | 30 Dec 2023 | Zone 4 JGP |  | Excavation for monitoring rod
Sat (30/12) | 30 Dec 2023 | Zone 3 SW-10 |  | Driling to check for existing sewer line
Sat (30/12) | 30 Dec 2023 | MH2-3 |  | Thrust block hacking in progress
Sat (30/12) | 30 Dec 2023 | MH2-4 |  | Chamber ring outer wall 3rd raise formwork closing
Sat (30/12) | 30 Dec 2023 | Zone 2 P17 |  | Hardcore laying for temporary bus stop shelter base slab
Sat (30/12) | 30 Dec 2023 | N5 |  | LE walers beams & brackets dismantle works
Sat (30/12) | 30 Dec 2023 | P10-2 |  | Pilecap casting in progress
Sat (30/12) | 30 Dec 2023 | South ramp, S3 |  | Preboring in progress
Sat (30/12) | 30 Dec 2023 | MH5-2 |  | Pipe no.21 jacking in progress
Sat (30/12) | 30 Dec 2023 | Zone 1 MH1-2 |  | 9th ring, 1st part concrete curing
Sat (30/12) | 30 Dec 2023 | Zone 1 |  | HSL housekeeping and shifting of materials to zone 4
Sat (30/12) | 30 Dec 2023 | MH2-9 |  | BRC installation for 10th layer in progress. Target to cast today
Sat (30/12) | 30 Dec 2023 | MH2-8 |  | 1st pipe lowered down, pipe jacking in progress
Sat (30/12) | 30 Dec 2023 | JTC - ST042 | SC40#02 | 2nd bite excavation in progress. Current depth 30.5m/36m
Sat (30/12) | 30 Dec 2023 | Blk 4 - ST062 |  | Cleaning completed, Desanding ongoing
Sat (30/12) | 30 Dec 2023 | Zone 3 SW-02 |  | Driling to check for existing sewer line
Sat (30/12) | 30 Dec 2023 | Zone 3 |  | Formwork installation completed for ST163 & ST164 guidewall works. Concrete ordered for casting
Sat (30/12) | 30 Dec 2023 | Zone 3 |  | Formwork installation completed for ST69 & ST69A guidewall works. Concrete ordered for casting
Sat (30/12) | 30 Dec 2023 | Zone 3 PBH-29 |  | Housekeeping ongoing, current depth 19m
Sat (30/12) | 30 Dec 2023 | Zone 3 PBH-32 |  | Housekeeping ongoing, current depth 34m
Sat (30/12) | 30 Dec 2023 | Zone 3 |  | BC cutter maintenance works
Sat (30/12) | 30 Dec 2023 | Zone 4 | JGP TB3X | Drilling works completed, grouting in progress 3m/6m
Sat (30/12) | 30 Dec 2023 | Zone 4 |  | Perimeter drain casting ongoing
Sat (30/12) | 30 Dec 2023 | Zone 2 P17 |  | Compaction ongoing for temporary bus stop shelter base slab
Sat (30/12) | 30 Dec 2023 | N5 |  | Current status for waler beams & brackets removal
Sat (30/12) | 30 Dec 2023 | P10-2 |  | Casting for pilecap completed
Sat (30/12) | 30 Dec 2023 | Zone 1 |  | HSL housekeeping works in progress
Sat (30/12) | 30 Dec 2023 | MH5-2 |  | Pipe no. 21 jacking in progress, (21/45) pipes jacking completed
Sat (30/12) | 30 Dec 2023 | MH2-9 |  | Caisson casting in progress
Sat (30/12) | 30 Dec 2023 | MH2-8 |  | Pipe no-3 jacking in progress
Sat (30/12) | 30 Dec 2023 | MH2-4 |  | Wall casting done. Levelling
Sat (30/12) | 30 Dec 2023 | MH2-7 |  | LSS backfilling in progress
Sat (30/12) | 30 Dec 2023 | MH2-9 |  | Excavation for 10th layer completed. Now preparing for BRC installation
Mon (01/01) | 01 Jan 2024 | MH2-8 |  | Pipe no-11 jacking in progress, 10/27nos done
Mon (01/01) | 01 Jan 2024 | MH1-2 |  | Drilling for starter bar planting for sewer diversion
Mon (01/01) | 01 Jan 2024 | MH2-5 |  | Last layer shaft formwork closing in progress. Today to cast
Tue (02/01) | 02 Jan 2024 | Zone 4 LP99 | towards LW | WG continue trial trench for power duct
Tue (02/01) | 02 Jan 2024 | ST42 |  | Lapping inspection
Tue (02/01) | 02 Jan 2024 | Zone 4 junction |  | No activity
Tue (02/01) | 02 Jan 2024 | MH2-8 |  | Pipe jacking continue night shift, 19/27nos completed
Tue (02/01) | 02 Jan 2024 | MH3-5 |  | Inclinometer pipe installed. Boring in progress for water stand pipe
Tue (02/01) | 02 Jan 2024 | Zone 3 |  | Leychoon is planning to do a trial trench at this location for the cable pulling pit
Tue (02/01) | 02 Jan 2024 | MH2-7 |  | Formwork closing for shaft casting. Remind lifting sup and rigger to use tag line when lifting and avoid holding of formwork near joint area to prevent fingers trap in between when adjusting the formwork
Tue (02/01) | 02 Jan 2024 | MH2-8 |  | Pipe no 17 jacking done. Removal of hoses to lower down pipe no 18
Tue (02/01) | 02 Jan 2024 | MH2-1 |  | Rebar installation for shaft base slab
Tue (02/01) | 02 Jan 2024 | Zone 2 Temp bus stop |  | Levelling ongoing
Tue (02/01) | 02 Jan 2024 | MH5-2 |  | Pipe jacking 25 ongoing. Works till 10pm
Tue (02/01) | 02 Jan 2024 | MH1-2 |  | Tonight to continue rebar installation for drainage pipe support. Night shift team just came
Tue (02/01) | 02 Jan 2024 | ST35 |  | First bite excavation in progress, 21m
Tue (02/01) | 02 Jan 2024 | ST42 |  | Rebar cage installation, 5/8nos. Now ongoing lapping for cage 2A and 3A
Tue (02/01) | 02 Jan 2024 | ST51 |  | First bite excavation in progress, 19.4m
Tue (02/01) | 02 Jan 2024 | MH2-9 |  | Continue pumping out water. Today plan to remove formwork
Wed (03/01) | 03 Jan 2024 | ST168 |  | First bite excavation in progress, 11m
Wed (03/01) | 03 Jan 2024 | P17 |  | Temp bus stop slab cast. Curing works in progress
Wed (03/01) | 03 Jan 2024 | P16 |  | BP Trial trench works for bottom piles
Wed (03/01) | 03 Jan 2024 | N5 |  | KTC Backfilling works in progress
Wed (03/01) | 03 Jan 2024 | Zone 4 LP99 | towards Loyang Way | WG continue manual trial trench for power duct
Wed (03/01) | 03 Jan 2024 | P10-2 |  | Rebar inspection for 1st lift column done. Preparing for Formwork closing
Wed (03/01) | 03 Jan 2024 | P50& P51 |  | TT in progress for transfer beam
Wed (03/01) | 03 Jan 2024 | ABH22-1 |  | Drilling in progress, depth 16m
Wed (03/01) | 03 Jan 2024 | N1 |  | Preparation for 1st lift column rebar installation works
Wed (03/01) | 03 Jan 2024 | P8-2 |  | Rebar inspection for 1st lift column done. Preparing for Formwork closing
Wed (03/01) | 03 Jan 2024 | MH1-2 |  | Continue rebar installation for existing sewer pipe diversion
Wed (03/01) | 03 Jan 2024 | Zone 1 |  | HSL Material Demobilisation in progress. They will shift the materials to zone 2
Wed (03/01) | 03 Jan 2024 | Zone 2, Shell |  | Excavation for new lamp post footing
Wed (03/01) | 03 Jan 2024 | MH5-2 |  | Pipe jacking to existing MH at Zone 1 in progress, Pipe done 26/45
Wed (03/01) | 03 Jan 2024 | Zone 2 south ramp | S3 | LE Preboring works in progress for ERSS installation
Wed (03/01) | 03 Jan 2024 | MH3-5 |  | Inclinometer and water standpipe installed. Rig will shift to MH3-6
Wed (03/01) | 03 Jan 2024 | MH3-5 |  | Preparing for footpath diversion and hoarding work
Wed (03/01) | 03 Jan 2024 | MH1-2 |  | Continue drilling and rebar installation
Wed (03/01) | 03 Jan 2024 | ST51 |  | Continue first bite excavation, 25.3m
Wed (03/01) | 03 Jan 2024 | Zone 4 |  | Continue manual soil clearing
Wed (03/01) | 03 Jan 2024 | ST42 |  | Rebar cage installation in progress, 8/8nos. Now pipe joining before lowering rebar cage
Wed (03/01) | 03 Jan 2024 | ST35 |  | In progress, 30m
Wed (03/01) | 03 Jan 2024 | MH2-8 |  | 21/27nos pipe jacking in progress. Pipe 22 lowered
Wed (03/01) | 03 Jan 2024 | ABH22-1 |  | Boring in progress, 34m
Wed (03/01) | 03 Jan 2024 | MH2-8 |  | 22/27nos jacking completed. Pipe 23 lowered
Wed (03/01) | 03 Jan 2024 | MH1-2 |  | Starter bar planting done for sewer diversion. Need to continue BRC laying
Wed (03/01) | 03 Jan 2024 | MH5-2 |  | Jacking in progress for Pipe No-27
Wed (03/01) | 03 Jan 2024 | MH2-7 |  | Formwork closing done for the shaft. Concrete ordered
Wed (03/01) | 03 Jan 2024 | MH2-5 |  | LSS backfilling in progress
Wed (03/01) | 03 Jan 2024 | MH2-7 |  | Casting ongoing
Wed (03/01) | 03 Jan 2024 | MH1-2 |  | Tonight to continue rebar works
Wed (03/01) | 03 Jan 2024 | Zone 1 HSL |  | No more activity
Wed (03/01) | 03 Jan 2024 | MH5-2 |  | Current status till pipe 27 for the day. Tmr to continue. Now housekeeping
Wed (03/01) | 03 Jan 2024 | MH2-7 |  | Preparation for BRC installation for permanent chamber ring. Target to cast afternoon
Wed (03/01) | 03 Jan 2024 | MH2-9 |  | Formwork removal
Wed (03/01) | 03 Jan 2024 | MH2-5 |  | Preparation for 3rd raise chamber ring mould removal and backfilling works
Wed (03/01) | 03 Jan 2024 | ST35 |  | Excavation completed, 35.7m
Wed (03/01) | 03 Jan 2024 | ST51 |  | 2nd bite excavation in progress, 22m
Thu (04/01) | 04 Jan 2024 | ST51 |  | Endplate extraction ongoing
Thu (04/01) | 04 Jan 2024 | ST168 |  | Cutter teeth changing ongoing
Thu (04/01) | 04 Jan 2024 | Zone 1 |  | HSL dismantle of boring rig and shift to zone 2
Thu (04/01) | 04 Jan 2024 | MH5-2 |  | Pipe no.27 Pipe jacking ongoing
Thu (04/01) | 04 Jan 2024 | ST65A |  | Pre excavation done. Platform arranging to start excavation
Thu (04/01) | 04 Jan 2024 | ST51 |  | Desanding done
Thu (04/01) | 04 Jan 2024 | MH1-2 |  | Continue rebar installation
Thu (04/01) | 04 Jan 2024 | MH2-8 towards MH2-9 |  | 1m short length pipe no.25 (last) lowered down. Pipe jacking in progress
Thu (04/01) | 04 Jan 2024 | Exit 3 |  | SPPG LC doing ERSS installation for open pit
Thu (04/01) | 04 Jan 2024 | MH2-8 to MH2-9 |  | Jacking machine retrival was done. One worker provided tonight to monitor and pump out water
Thu (04/01) | 04 Jan 2024 | MH5-2 |  | Now no activity already
Fri (05/01) | 05 Jan 2024 | PBH23 |  | In progress, 18m
Fri (05/01) | 05 Jan 2024 | MH2-7 |  | Preparation for next backfilling works
Fri (05/01) | 05 Jan 2024 | P19 |  | HSL setting up boring rig for bp works
Fri (05/01) | 05 Jan 2024 | P18-6 |  | Manual trial trench in progress for BP
Fri (05/01) | 05 Jan 2024 | P44 |  | Trial trench to locate any underground services by WH
Fri (05/01) | 05 Jan 2024 | Zone 4 |  | Continue trial trench for transfer beams by WH (2 teams)
Fri (05/01) | 05 Jan 2024 | Zone 4 |  | WG continue manual soil clearing under services for power duct pipe laying works
Fri (05/01) | 05 Jan 2024 | Zone 4 |  | Preparation ongoing to resume JGP drilling works. As of now, 2/7nos completed
Fri (05/01) | 05 Jan 2024 | N6 |  | Housekeeping & debris removal ongoing
Fri (05/01) | 05 Jan 2024 | N5 |  | ERSS removal & shifting to south ramp
Fri (05/01) | 05 Jan 2024 | N1 |  | Formwork closing for 1st stage column wall
Fri (05/01) | 05 Jan 2024 | P10-2 |  | 1st column cast yst. Curing ongoing
Fri (05/01) | 05 Jan 2024 | P9-2 |  | Rebar installation in progress for 1st stage column wall
Fri (05/01) | 05 Jan 2024 | P8-2 |  | 1st column cast yst. Curing ongoing
Fri (05/01) | 05 Jan 2024 | Zone 1 along PRD3 |  | Leychoon doing trial trench works to locate existing 22kV & 6.6kV
Fri (05/01) | 05 Jan 2024 | MH1-2 |  | Continue rebar installation for diversion of existing sewer
Fri (05/01) | 05 Jan 2024 | Zone 1 |  | HSL dismantle of crane in progress and shifting to Zone 2
Fri (05/01) | 05 Jan 2024 | Near MH3-5 |  | RG has demobilise IM rig
Fri (05/01) | 05 Jan 2024 | ST168 |  | Excavation temporarily on hold due to suction hose drum issue. Waiting for rectification
Fri (05/01) | 05 Jan 2024 | ST65A |  | Excavation temporarily on hold. Rectification ongoing for flap hydraulic oil leakage
Fri (05/01) | 05 Jan 2024 | ST51 |  | Rebar cage installation, 5/6nos
Fri (05/01) | 05 Jan 2024 | MH5-2 |  | Pipe no.27 jacking completed. LCH informed that they may need to pull back the pipes to change the TBM cutter teeth due to hard soil
Fri (05/01) | 05 Jan 2024 | MH1-2 |  | Rebar work in progress for sewer diversion
Fri (05/01) | 05 Jan 2024 | MH2-1 |  | Rebar installation ongoing for permanent MH wall
Fri (05/01) | 05 Jan 2024 | ST35 |  | Casting completed. Total volume: 130m3
Fri (05/01) | 05 Jan 2024 | ST51 |  | Hanging bar installation ongoing
Fri (05/01) | 05 Jan 2024 | ST48A |  | Trimming ongoing. First bite excavation completed, 28.6m
Fri (05/01) | 05 Jan 2024 | Zone 4 JGP |  | 3/7nos completed. Now area preparation and marking of utility services before starting next point
Fri (05/01) | 05 Jan 2024 | ST168 |  | Rectification ongoing
Fri (05/01) | 05 Jan 2024 | ST65A |  | Rectification ongoing
Fri (05/01) | 05 Jan 2024 | MH2-7 |  | Backfilling done & continue plastering works inside MH
Fri (05/01) | 05 Jan 2024 | P23 |  | Ley Choon has opened trench for power cable pulling
Fri (05/01) | 05 Jan 2024 | Zone 2 |  | Krishco has installed live valve here. Premix laying ongoing
Fri (05/01) | 05 Jan 2024 | Zone 2 |  | HSL unloading machinery equipment
Fri (05/01) | 05 Jan 2024 | MH5-2 |  | Preparation to pull back the pipes
Fri (05/01) | 05 Jan 2024 | N5 |  | Slope protection was done. Soil levelling works ongoing
Fri (05/01) | 05 Jan 2024 | N1 |  | Formwork closing
Fri (05/01) | 05 Jan 2024 | P9-2 |  | Formwork closing and toe board installation ongoing
Fri (05/01) | 05 Jan 2024 | MH1-2 |  | Tonight activity will be rebar work for sewer diversion
Fri (05/01) | 05 Jan 2024 | ST35 |  | Casting in progress, 94/110m3
Fri (05/01) | 05 Jan 2024 | ST51 |  | Rebar cage installation in progress, 4/6nos
Fri (05/01) | 05 Jan 2024 | ST48A |  | First bite excavation in progress, 28.4m
Sat (06/01) | 06 Jan 2024 | Zone 1 PD3 |  | Ley choon preparing for trial hole
Sat (06/01) | 06 Jan 2024 | CR106 Worker's Quarters |  | Hoarding footing installation ongoing
Sat (06/01) | 06 Jan 2024 | Zone 1 Loyang Rise |  | Singtel cable pulling works
Sat (06/01) | 06 Jan 2024 | Zone 3 |  | 300mm slab cast over water valves with 750mmx750mm openings made to widen vehicle access area. Steel plates will be laid over. Reminded WHDA to mark the locations of the water valves on the steel plates once done
Sat (06/01) | 06 Jan 2024 | Outside Exit 1 |  | Trial trench to identify army cable ongoing
Sat (06/01) | 06 Jan 2024 | Zone 4 |  | JGP TB6 drilling to 14.29m depth done. Grouting to start now
Sat (06/01) | 06 Jan 2024 | Zone 4 |  | Drain has been partially blocked off with some water flowing out. WHDA to fully seal off before drain hacking for ULT trial trenches
Sat (06/01) | 06 Jan 2024 | Zone 4 |  | Hoarding installation near lincstech
Sat (06/01) | 06 Jan 2024 | Zone 3 |  | Excavation for ST175-177 guidewall in progress
Sat (06/01) | 06 Jan 2024 | ST-48A |  | Cleaning completed. Preparation for desanding
Sat (06/01) | 06 Jan 2024 | Zone 2 |  | HSL preparing to set up boring rig and crawler crane. AE inspection on Monday
Sat (06/01) | 06 Jan 2024 | Zone 2 |  | P17-6 trial trench ongoing. Nearest utility is the gas pipe at the green railing
Sun (07/01) | 07 Jan 2024 | ST048A |  | Top cage and hanging bar lapping in progress
Sun (07/01) | 07 Jan 2024 | ST065A |  | 1st bite excavation in progress, Current depth 27.6m/30.43m
Sun (07/01) | 07 Jan 2024 | Zone 4 |  | No activity
Sun (07/01) | 07 Jan 2024 | MH2-8 |  | Demob of pipe jacking materials
Sun (07/01) | 07 Jan 2024 | N6 |  | Dewatering in progress
Sun (07/01) | 07 Jan 2024 | P10-2 |  | Dewatering in progress
Sun (07/01) | 07 Jan 2024 | MH1-2 |  | Temporary Sewer pipe diversion slab casting in progress
Sun (07/01) | 07 Jan 2024 | MH1-2 |  | Formwork closing done for the base slab casting for drain diversion
Sun (07/01) | 07 Jan 2024 | Zone 1 |  | Lucky joint Singtel cable pulling works from PRD1
Sun (07/01) | 07 Jan 2024 | Zone 2 |  | CGW material storage room making in progress
Sun (07/01) | 07 Jan 2024 | ST048A |  | Dwall panel casting in progress
Sun (07/01) | 07 Jan 2024 | ST065A |  | 1st bite excavation & internal koden test completed. Now starting 2nd bite excavation
Mon (08/01) | 08 Jan 2024 | MH1-2 |  | Casting ongoing
Mon (08/01) | 08 Jan 2024 | Zone 4 |  | WG continue manual clearing under the services
Mon (08/01) | 08 Jan 2024 | ST168 |  | Cutter body washing prior to replacing cutter teeth. Current depth at 18.6m (first bite)
Mon (08/01) | 08 Jan 2024 | ST49 |  | First bite in progress, 17m
Mon (08/01) | 08 Jan 2024 | MH3-6 side table |  | TT done by Krishco subcon. Found Starhub, EHV & LV
Mon (08/01) | 08 Jan 2024 | TB1 |  | Boring and grouting done. Now preparing to start TB7 boring
Mon (08/01) | 08 Jan 2024 | P50& P49 |  | TT on going for Transfer beam
Mon (08/01) | 08 Jan 2024 | Zone 4 |  | WG lane closure for power duct trial trench works
Mon (08/01) | 08 Jan 2024 | Zone 4 junction |  | CR1070 cap off works
Mon (08/01) | 08 Jan 2024 | ST168 |  | Resume first bite excavation
Mon (08/01) | 08 Jan 2024 | ST49 |  | First bite excavation in progress, 12m
Mon (08/01) | 08 Jan 2024 | P36 |  | ST73, 74 guidewall casting completed
Mon (08/01) | 08 Jan 2024 | Zone 2 |  | Hoarding panel installation at centre median by WH ongoing
Mon (08/01) | 08 Jan 2024 | South ramp & MH5-2 |  | No more activity
Mon (08/01) | 08 Jan 2024 | MH1-2 |  | Tonight continue formwork installation for sewer diversion drain wall and plan for casting
Tue (09/01) | 09 Jan 2024 | Zone 2 |  | Bentonite pipe connection for P14-P18 bottom part BP works
Tue (09/01) | 09 Jan 2024 | Zone 4 |  | Wee Guan preparing to continue the area for excavation and ERSS for Power duct
Tue (09/01) | 09 Jan 2024 | N6 |  | Column stump formwork closing
Tue (09/01) | 09 Jan 2024 | N1 |  | Column stump formwork dismantling
Tue (09/01) | 09 Jan 2024 | P11 |  | TT on going for drain removal
Tue (09/01) | 09 Jan 2024 | P9-2 |  | Column stump formwork dismantling
Tue (09/01) | 09 Jan 2024 | Zone 1 NLL |  | SPPG here doing TT to find existing 6.6Kv for diversion works
Tue (09/01) | 09 Jan 2024 | ST168 |  | Resume excavation
Tue (09/01) | 09 Jan 2024 | ST65A |  | Desanding in progress
Tue (09/01) | 09 Jan 2024 | ST49 |  | BC cutter teeth rectification ongoing. Current first bite depth at 19m
Tue (09/01) | 09 Jan 2024 | Zone 3 |  | ST178-ST182 drain hacking & removal in progress
Tue (09/01) | 09 Jan 2024 | MH2-3 |  | Rebar work in progress for permanent manhole
Tue (09/01) | 09 Jan 2024 | MH1-2 |  | Formwork removal for base for sewer diversion
Tue (09/01) | 09 Jan 2024 | South ramp & MH5-2 |  | No activity
Tue (09/01) | 09 Jan 2024 | MH1-2 |  | Tonight plan for pipe cutting
Tue (09/01) | 09 Jan 2024 | ST49 |  | Cutter teeth replacement ongoing
Tue (09/01) | 09 Jan 2024 | ST168 |  | Cutter teeth replacement ongoing
Tue (09/01) | 09 Jan 2024 | Zone 4 P46 |  | Tonight WG to continue trial trench for power duct
Tue (09/01) | 09 Jan 2024 | ST65A |  | Preparation for rebar cage lowering
Wed (10/01) | 10 Jan 2024 | ABH31-3 |  | Drilling/SPT on going at 8m depth
Wed (10/01) | 10 Jan 2024 | BC 1 |  | Repairing gear box in progress
Wed (10/01) | 10 Jan 2024 | P11 |  | Drain hacking for ERSS works
Wed (10/01) | 10 Jan 2024 | S3 |  | Waiting for contractor to arrange water pumping to continue excavation works
Wed (10/01) | 10 Jan 2024 | MH3-5 |  | Painting of hoarding and TT for MH3-6 at Lane 2
Wed (10/01) | 10 Jan 2024 | ULT3 & 12 |  | Drain demolish. Backfilling in progress
Wed (10/01) | 10 Jan 2024 | MH1-2 |  | Preparation to cut existing sewer pipe. Line diverted last night
Wed (10/01) | 10 Jan 2024 | Zone 2 near PMH3 |  | SPPG here doing trial hole to find pipe for 6.6kV diversion
Wed (10/01) | 10 Jan 2024 | MH1-2 |  | Cutting and removing pipe collar
Wed (10/01) | 10 Jan 2024 | MH1-2 |  | Pipe cutting ongoing
Wed (10/01) | 10 Jan 2024 | Zone 4 P45 |  | Shoring installation in progress
Wed (10/01) | 10 Jan 2024 | ST65A |  | Rebar cage installation in progress, 4/6nos
Wed (10/01) | 10 Jan 2024 | P18-5 |  | Preparation for pre boring
Wed (10/01) | 10 Jan 2024 | MH2-8 |  | Water pumping prior to lowering of base slab rebar
Wed (10/01) | 10 Jan 2024 | Loyang lane gate 5 |  | Singtel contractor here putting cables inside their manhole to give access for sppg open pit excavation
Wed (10/01) | 10 Jan 2024 | ST49 |  | 2nd bite trenching at 28.1m depth
Wed (10/01) | 10 Jan 2024 | ST65A |  | Ready for casting, waiting for concrete lorry. Total volume 195 m3
Wed (10/01) | 10 Jan 2024 | ST67 |  | Mud pump spoil, preparation for repair
Wed (10/01) | 10 Jan 2024 | ST176-177, 180-181 |  | TT completed
Wed (10/01) | 10 Jan 2024 | ST168 |  | BC cutter gear box repair works continue
Wed (10/01) | 10 Jan 2024 | MH2-3 |  | RC wall casting in progress
Wed (10/01) | 10 Jan 2024 | N6 |  | Working platform erection ongoing
Wed (10/01) | 10 Jan 2024 | MH5-2 |  | Tonight plan to pull back the pipes
Wed (10/01) | 10 Jan 2024 | ST65A |  | 2 trucks already on site for casting
Wed (10/01) | 10 Jan 2024 | Zone 4 junction |  | PUB repair works by their contractor
Wed (10/01) | 10 Jan 2024 | P46 |  | WG continue excavating for power duct trial trench
Wed (10/01) | 10 Jan 2024 | ST67A |  | Pending for additional flap welding works before starting bite 2
Wed (10/01) | 10 Jan 2024 | ST168 |  | Current depth at 19.8m. Now cutter teeth wheel and welding works ongoing
Wed (10/01) | 10 Jan 2024 | P18-5 |  | Pre boring to start today
Wed (10/01) | 10 Jan 2024 | N6 |  | Column stump formwork closing. Water pumping in progress. Target to cast tomorrow
Thu (11/01) | 11 Jan 2024 | Loyang Way near exit 1 | Gate 7 | Singtel cable pulling works
Thu (11/01) | 11 Jan 2024 | P46 |  | Dewatering ongoing before continuing excavation for power duct
Thu (11/01) | 11 Jan 2024 | Zone 4 |  | Designated man access erection ongoing
Thu (11/01) | 11 Jan 2024 | P49 |  | Continue trial trench for transfer beams
Thu (11/01) | 11 Jan 2024 | Zone 4 |  | Open trench for usd duct backfilling works only tonight
Thu (11/01) | 11 Jan 2024 | Zone 4 |  | Platform for biometrics location cast
Thu (11/01) | 11 Jan 2024 | Zone 4 |  | GCE continue clearing materials
Thu (11/01) | 11 Jan 2024 | P48 |  | Area preparation for ULT3 and ULT12 trial trench
Thu (11/01) | 11 Jan 2024 | Zone 3 loyang way |  | Singtel contractor here joining optic fiber cables
Thu (11/01) | 11 Jan 2024 | Zone 2 N6 |  | Formwork propping installation in progress. Casting will be done tmr
Thu (11/01) | 11 Jan 2024 | Near MH2-7 |  | Backfilling ongoing
Thu (11/01) | 11 Jan 2024 | ABH31-3 |  | Water permeability test in progress
Thu (11/01) | 11 Jan 2024 | P8-2 |  | Concrete plug casting in progress
Thu (11/01) | 11 Jan 2024 | PMH3 |  | SPPG LC open pit excavation
Thu (11/01) | 11 Jan 2024 | MH1-2 |  | Hacking of existing sewer pipe which already diverted
Thu (11/01) | 11 Jan 2024 | MH2-8 |  | Base slab casting in progress
Thu (11/01) | 11 Jan 2024 | Zone 4 |  | Shoring installation in progress
Thu (11/01) | 11 Jan 2024 | ST65A casting completed at 0200hrs. Total volume |  | 194.5m3
Thu (11/01) | 11 Jan 2024 | MH2-8 |  | Rebar installation in progress for base slab
Thu (11/01) | 11 Jan 2024 | MH2-3 |  | Perm MH wall rebar works installation ongoing
Thu (11/01) | 11 Jan 2024 | Zone 2 |  | HSL housekeeping works. Boring works will resume tmr
Thu (11/01) | 11 Jan 2024 | MH5-2 |  | Continue pull back tbm machine
Thu (11/01) | 11 Jan 2024 | MH5-2 |  | Pull back pipes in progress, current status: 5/27 nos. completed
Thu (11/01) | 11 Jan 2024 | P46 |  | Shoring works done for the night
Thu (11/01) | 11 Jan 2024 | ST49 |  | Chiselling completed. Waterstop removal ongoing (ST48A side)
Thu (11/01) | 11 Jan 2024 | ST168 |  | Resume first bite excavation, 20m
Thu (11/01) | 11 Jan 2024 | ST67A |  | 2nd bite excavation in progress
Thu (11/01) | 11 Jan 2024 | ABH31-3 |  | Driling in progress, current depth 36m
Thu (11/01) | 11 Jan 2024 | N6 |  | Continue Formwork propping installation
Thu (11/01) | 11 Jan 2024 | MH2-8 |  | Base slab rebar installation
Thu (11/01) | 11 Jan 2024 | MH2-3 |  | No more activity
Thu (11/01) | 11 Jan 2024 | Zone 2 |  | To lean concrete this area for access diversion
Thu (11/01) | 11 Jan 2024 | N6 |  | Formwork bracing installation till 10pm. Tomorrow to cast
Thu (11/01) | 11 Jan 2024 | ST49 |  | Final koden test
Thu (11/01) | 11 Jan 2024 | Zone 3 |  | Krishco area preparation for crane working platform. Tomorrow plan to replace rejected water pipe
Thu (11/01) | 11 Jan 2024 | ST67A |  | Final Koden test in progress
Thu (11/01) | 11 Jan 2024 | ST168 |  | BC cutter maintenance. To continue trenching tonight using BC cutter
Thu (11/01) | 11 Jan 2024 | ST168 |  | BC cutter teeth changing ongoing
Thu (11/01) | 11 Jan 2024 | ST67A |  | Bite 2 completed, 30.9m
Thu (11/01) | 11 Jan 2024 | P37 |  | Retaining wall base hacking ongoing
Thu (11/01) | 11 Jan 2024 | P38 |  | Area preparation for PBH17 and PBH19 SI works
Thu (11/01) | 11 Jan 2024 | P44 |  | GCE continue trial trench for JGP works
Fri (12/01) | 12 Jan 2024 | Zone 2 P18 |  | Lean con casting ongoing for access
Fri (12/01) | 12 Jan 2024 | Zone 4 |  | SPPG pipe laying, target tonight 18m
Fri (12/01) | 12 Jan 2024 | Zone 2 P18-5 |  | Boring in progress
Fri (12/01) | 12 Jan 2024 | Zone 2 |  | Apron slab rebar works ongoing. Plan for casting today
Fri (12/01) | 12 Jan 2024 | Zone 1 |  | LE machinery mobilisation
Fri (12/01) | 12 Jan 2024 | MH1-2 |  | To continue excavation for 10th layer. Now waiting for new operator to complete SIC
Fri (12/01) | 12 Jan 2024 | PMH3 |  | Ley Choon continue excavation for SPPG pit
Fri (12/01) | 12 Jan 2024 | ST49 |  | All cages lowered
Fri (12/01) | 12 Jan 2024 | MH2-8 |  | 1st lift wall rebar works
Fri (12/01) | 12 Jan 2024 | P8 |  | No activity
Fri (12/01) | 12 Jan 2024 | P9 |  | No activity
Fri (12/01) | 12 Jan 2024 | P10 |  | No activity
Fri (12/01) | 12 Jan 2024 | ST49 |  | Waterstop & end plate fully lowered
Fri (12/01) | 12 Jan 2024 | ST49 |  | U-clip torque test
Fri (12/01) | 12 Jan 2024 | ST168 |  | BC cutter teeth replacement. Current depth 20.5m
Fri (12/01) | 12 Jan 2024 | MH2-3 |  | Currently no activity as machine breakdown. Pending mould installation. Machine repair ongoing
Fri (12/01) | 12 Jan 2024 | Zone 2 P17-5 |  | Boring ongoing & P18-5 rebar cage installation in progress
Fri (12/01) | 12 Jan 2024 | MH5-2 |  | Continue pipe pulling, 14/27nos done
Fri (12/01) | 12 Jan 2024 | MH1-2 |  | Continue soil disposal and excavation for 10th layer
Fri (12/01) | 12 Jan 2024 | ABH31-3 |  | In progress, 41m
Fri (12/01) | 12 Jan 2024 | MH2-8 |  | Continue MH wall rebar works
Fri (12/01) | 12 Jan 2024 | MH5-2 |  | Pipe pull back continue. 11/27 completed
Fri (12/01) | 12 Jan 2024 | MH1-2 |  | 10th layer excavation and soil disposal continue
Fri (12/01) | 12 Jan 2024 | Zone 4 |  | Backfilling stopped for the night
Fri (12/01) | 12 Jan 2024 | P18-5 |  | Tremie pipe lowered. Concrete on the way
Fri (12/01) | 12 Jan 2024 | P17-5 |  | Boring in progress, 6m
Fri (12/01) | 12 Jan 2024 | MH1-2 |  | Excavation in progress for 10th layer
Fri (12/01) | 12 Jan 2024 | ST49 |  | Rebar cage installation, 3/6
Fri (12/01) | 12 Jan 2024 | ST168 |  | Trenching continue
Fri (12/01) | 12 Jan 2024 | ST67A |  | Waterstop lowering
Fri (12/01) | 12 Jan 2024 | MH5-2 |  | Jacking pipe retrieval in progress
Fri (12/01) | 12 Jan 2024 | P18-5 |  | Casting in progress. Balance 1 load
Fri (12/01) | 12 Jan 2024 | P17-5 |  | Pre-boring completed. Tomorrow to bore and cast
Fri (12/01) | 12 Jan 2024 | N6 |  | Column stump casting
Fri (12/01) | 12 Jan 2024 | MH5-2 |  | Sewer pipe retrieval 14/27 completed
Fri (12/01) | 12 Jan 2024 | MH1-2 |  | Hacking for 10th layer continue for night shift
Fri (12/01) | 12 Jan 2024 | ST46 |  | 1st bite excavation on going
Fri (12/01) | 12 Jan 2024 | ST49 |  | Last hanging bar installation in progress. Target to cast at 12mn. Estimated vol 200 m3
Fri (12/01) | 12 Jan 2024 | ST65 |  | 1st bite excavation in progress
Fri (12/01) | 12 Jan 2024 | ST67A |  | Rebar cage lowering
Fri (12/01) | 12 Jan 2024 | ST168 |  | Trenching continue, current depth at 21m
Fri (12/01) | 12 Jan 2024 | ST164 |  | Pre-boring till 10pm
Sat (13/01) | 13 Jan 2024 | P17-5 |  | Casing installed. No boring today. Rebar cage yet to deliver
Sat (13/01) | 13 Jan 2024 | ST168 |  | Mud pump reducer leaking. Repair in progress
Sat (13/01) | 13 Jan 2024 | ABH31-3 |  | Boring reached 42.3m. 3rd permeability test in progress
Sat (13/01) | 13 Jan 2024 | Zone 4 |  | SPPG pipe laying on going. Target 12m tonight
Sat (13/01) | 13 Jan 2024 | MH1-2 |  | Excavation for the next layer caisson work
Sat (13/01) | 13 Jan 2024 | MH5-2 |  | Preparing to retrieve pipe No-6. Now balance only 6nos to complete retrieval
Sat (13/01) | 13 Jan 2024 | MH2-8 |  | Perm wall casting in progress
Sat (13/01) | 13 Jan 2024 | Zone 4 |  | SPPG pipe laying status. 6m laid, 27 ways
Sat (13/01) | 13 Jan 2024 | ST46 |  | 1st bite trenching continue. 24m depth
Sat (13/01) | 13 Jan 2024 | ST49 |  | Casting started
Sat (13/01) | 13 Jan 2024 | ST65 |  | 1st bite excavation continue at 20m depth
Sat (13/01) | 13 Jan 2024 | ST168 |  | Trenching continue at 21.2m depth
Sat (13/01) | 13 Jan 2024 | ST67A |  | Tremie pipe installation in progress
Sat (13/01) | 13 Jan 2024 | MH5-2 |  | Sewer pipe pull back 18/27
Sat (13/01) | 13 Jan 2024 | MH1-2 |  | 9th layer 2nd part continue excavation
Sat (13/01) | 13 Jan 2024 | Zone 4 |  | Pipe laying completed for the night. Total 12m
Sat (13/01) | 13 Jan 2024 | MH2-4 |  | Preparing to install Bricks and manhole cover
Sat (13/01) | 13 Jan 2024 | MH1-2 |  | Excavation for the next layer caisson
Sat (13/01) | 13 Jan 2024 | ST46 |  | 1st bite trenching continue at 27.5m depth
Sat (13/01) | 13 Jan 2024 | ST49 |  | Casting continue, 195/204 m3. Last lorry on site
Sat (13/01) | 13 Jan 2024 | ST168 |  | Cutter wheel teeth changing. Depth at 21.4m
Sat (13/01) | 13 Jan 2024 | ST67A |  | Casting started. Est vol 100 m3
Sat (13/01) | 13 Jan 2024 | ST49 |  | Last load casting
Sat (13/01) | 13 Jan 2024 | MH2-8 |  | LCH stopped work for the night
Sat (13/01) | 13 Jan 2024 | MH2-8 |  | Rebar works for Benching to continue tonight
Sat (13/01) | 13 Jan 2024 | Zone 2 |  | Access lean con till 10pm
Sat (13/01) | 13 Jan 2024 | P9 |  | Concrete plug casting completed. No more activity
Sat (13/01) | 13 Jan 2024 | MH1-2 |  | 10th layer excavation to continue tonight. Est depth 1m
Sat (13/01) | 13 Jan 2024 | Zone 1 |  | M1 here tonight for cable joining
Sat (13/01) | 13 Jan 2024 | MH5-2 |  | Pipe pulling back to complete tonight. Balance 3 pipes
Sat (13/01) | 13 Jan 2024 | South ramp S3 |  | Packing concrete cast today
Sat (13/01) | 13 Jan 2024 | ST46 |  | Cutter wheel teeth replacement
Sat (13/01) | 13 Jan 2024 | ST65 |  | 1st bite continue, Current depth at 28.2m
Sat (13/01) | 13 Jan 2024 | MH2-3 |  | Replacing pump to clear stagnant water
Sun (14/01) | 14 Jan 2024 | Zone 2 |  | CGS preparing to install the bollards for the temp bus shelters
Sun (14/01) | 14 Jan 2024 | Zone 2 |  | CGS hacking the existing drain
Sun (14/01) | 14 Jan 2024 | Zone 1 |  | No activity by other contractors
Sun (14/01) | 14 Jan 2024 | Zone 1 |  | Singtel cable pulling works by Lucky Joint
Sun (14/01) | 14 Jan 2024 | Zone 2 |  | Removal of grass/debris before lean concreting for new walkway
Sun (14/01) | 14 Jan 2024 | Zone 4 |  | Pipe laying continue
Sun (14/01) | 14 Jan 2024 | MH2-8 |  | Casting completed
Sun (14/01) | 14 Jan 2024 | MH1-2 |  | Excavation continue
Sun (14/01) | 14 Jan 2024 | Zone 3 |  | Formwork for ST177 and ST178 guidewall still in progress. Plan to cast today
Sun (14/01) | 14 Jan 2024 | Zone 4 |  | Pipe laying completed for the night. 18m. Area backfilled
Sun (14/01) | 14 Jan 2024 | ST46 |  | 2nd bite excavation at 26m depth
Sun (14/01) | 14 Jan 2024 | ST65 |  | 2nd bite excavation continue at 14.7m depth
Sun (14/01) | 14 Jan 2024 | ST168 |  | 1st bite internal koden. 22.1m depth
Mon (15/01) | 15 Jan 2024 | MH2-8 |  | Continue formwork closing for permanent manhole. Tonight to cast. Now continue raining
Mon (15/01) | 15 Jan 2024 | MH2-8 |  | MH wall rebar works in progress
Mon (15/01) | 15 Jan 2024 | ST178 to ST180 | half | Guidewall excavation in progress
Mon (15/01) | 15 Jan 2024 | ST177-ST180 | half | Guidewall was cast yesterday
Mon (15/01) | 15 Jan 2024 | ST171 |  | Preboring in progress
Mon (15/01) | 15 Jan 2024 | MH2-24 |  | MH cover installation
Mon (15/01) | 15 Jan 2024 | Zone 3, 1.8m dia trial JGP |  | T-A7 drilling in progress (first point)
Mon (15/01) | 15 Jan 2024 | Zone 4 |  | WH continue trial trench for transfer beams (2 teams)
Mon (15/01) | 15 Jan 2024 | Zone 4 |  | WG no activity
Mon (15/01) | 15 Jan 2024 | Zone 4 junction |  | No activity
Mon (15/01) | 15 Jan 2024 | ST78-79 |  | Guidewall casting
Mon (15/01) | 15 Jan 2024 | ST68 |  | First bite excavation in progress
Mon (15/01) | 15 Jan 2024 | Zone 2 |  | Lucky joint here for singtel cable pulling
Mon (15/01) | 15 Jan 2024 | P17-5 |  | Rebar cage installation
Mon (15/01) | 15 Jan 2024 | P16-5 |  | Area preparation for boring works
Mon (15/01) | 15 Jan 2024 | ST46 |  | Rebar cage installation in progress, 2/6nos
Mon (15/01) | 15 Jan 2024 | Zone 2 |  | Temp bus stop bollard installation ongoing
Mon (15/01) | 15 Jan 2024 | P8 |  | Backfilling works
Mon (15/01) | 15 Jan 2024 | Zone 1 |  | Pulling pit excavation ny sppg
Mon (15/01) | 15 Jan 2024 | MH5-2 |  | TBM fixing works in progress
Mon (15/01) | 15 Jan 2024 | South ramp | S3 | Trimming of excess packing concrete
Mon (15/01) | 15 Jan 2024 | MH2-3 |  | LSS backfilling ongoing
Mon (15/01) | 15 Jan 2024 | P16-5 |  | Casing installed
Mon (15/01) | 15 Jan 2024 | Zone 2 |  | Singtel cable pulling works
Mon (15/01) | 15 Jan 2024 | MH1-2 |  | Layer 10 hacking works ongoing
Mon (15/01) | 15 Jan 2024 | Zone 1 |  | LE had started trial trench. Optic fibre cable found at ard 1.1m depth. Tmr to continue TT works
Mon (15/01) | 15 Jan 2024 | MH5-2 |  | Pipe fixing ongoing before lowering the TBM
Mon (15/01) | 15 Jan 2024 | P17-5 |  | Pending to cast
Mon (15/01) | 15 Jan 2024 | MH2-5 |  | MH cover works
Mon (15/01) | 15 Jan 2024 | ST46 |  | Rebar cage installation in progress, 4/6nos
Mon (15/01) | 15 Jan 2024 | ST49A |  | First bite excavation in progress, 26.7m
Mon (15/01) | 15 Jan 2024 | ST164 |  | First bite excavation in progress, 32.5m
Mon (15/01) | 15 Jan 2024 | ST78-79 |  | Guidewall cast
Mon (15/01) | 15 Jan 2024 | ST68 |  | First bite excavation ongoing, 28.4m
Mon (15/01) | 15 Jan 2024 | ST171 |  | Preboring continue. Works planned till 10pm
Mon (15/01) | 15 Jan 2024 | ST178 -ST180 | half | Guidewall rebar works. Plan for casting tmr
Mon (15/01) | 15 Jan 2024 | P17-5 |  | Casting in progress. Last truck on site
Mon (15/01) | 15 Jan 2024 | MH5-2 |  | Set up jacking machine to push in. Night shift arranged for tonight to push in jacking pipes
Mon (15/01) | 15 Jan 2024 | MH1-2 |  | Continue excavation. Left around 200mm to trim
Tue (16/01) | 16 Jan 2024 | ST46 |  | Casting in progress, 81m3
Tue (16/01) | 16 Jan 2024 | P16-5 |  | Boring work started
Tue (16/01) | 16 Jan 2024 | DR2 |  | Canal status so far no silty discharge observed
Tue (16/01) | 16 Jan 2024 | Zone 1 |  | M1 is here. Migration to complete by today. Tomorrow to recover old cables
Tue (16/01) | 16 Jan 2024 | Exit 1 |  | ECM status
Tue (16/01) | 16 Jan 2024 | Zone 4 |  | WG material shifting
Tue (16/01) | 16 Jan 2024 | Zone 4 |  | WH continue trial trench for transfer beams and backfilling works
Tue (16/01) | 16 Jan 2024 | Zone 4 |  | ECM pond status
Tue (16/01) | 16 Jan 2024 | MH1-2 |  | Today to continue rebar installation for 10th layer
Tue (16/01) | 16 Jan 2024 | MH5-2 |  | Sewer pipe jacking status. 2nd pipe done
Tue (16/01) | 16 Jan 2024 | Trial JGP T-A7 |  | Precutting in progress
Tue (16/01) | 16 Jan 2024 | ST46 |  | Casting progressive vol: 135/160m3
Tue (16/01) | 16 Jan 2024 | MH2-8 |  | Casting started
Tue (16/01) | 16 Jan 2024 | ST46 |  | Casting completed. Total volume: 156m3
Tue (16/01) | 16 Jan 2024 | ST164 |  | Continue first bite excavation
Tue (16/01) | 16 Jan 2024 | ST78-79 |  | Pending to dismantle guidewall formwork
Tue (16/01) | 16 Jan 2024 | Zone 3 |  | TA7 grouting completed. 1/7nos. Trial JGP done. To continue drilling next point tmr. Target to do 2 points per day
Tue (16/01) | 16 Jan 2024 | ST68 |  | 2nd bite excavation in progress, 25m
Tue (16/01) | 16 Jan 2024 | S3 |  | Excavation to FEL
Tue (16/01) | 16 Jan 2024 | MH5-2 |  | 3/45 pipe jacking completed
Tue (16/01) | 16 Jan 2024 | Zone 1 |  | SPTel here pulling cables
Tue (16/01) | 16 Jan 2024 | Zone 4 P45 |  | Premix hacking by WH to continue trial trench for transfer beams
Tue (16/01) | 16 Jan 2024 | P46 |  | Debris removal for trial trench works by WH
Tue (16/01) | 16 Jan 2024 | ST171 |  | Continue preboring
Tue (16/01) | 16 Jan 2024 | ST168 |  | Continue LSS backfilling. Yesterday backfilled 99m3. Today plan 30m3
Tue (16/01) | 16 Jan 2024 | Exit 2 BH146 |  | In progress, 14m
Tue (16/01) | 16 Jan 2024 | BH148 |  | Preparing to start SI
Tue (16/01) | 16 Jan 2024 | MH1-2 |  | Continue trimming of soil and removal
Tue (16/01) | 16 Jan 2024 | Zone 2-3 |  | Singtel here for cable joining
Tue (16/01) | 16 Jan 2024 | Zone 2 |  | Rebar cage delivery for P18
Tue (16/01) | 16 Jan 2024 | P16-5 |  | Setting up for casting ramp
Tue (16/01) | 16 Jan 2024 | ST49A |  | 1st part end plate extracted
Tue (16/01) | 16 Jan 2024 | Zone 3 |  | Guidewall formwork closing for ST178 half and ST180
Tue (16/01) | 16 Jan 2024 | ST171 |  | Pre-boring temporarily stopped due to hydraulic hose leaking. Repair works in progress
Tue (16/01) | 16 Jan 2024 | ST164 |  | 1st bite completed. 2nd bite now in progress at 12m depth
Tue (16/01) | 16 Jan 2024 | ST68 |  | BC cutter teeth replacement
Tue (16/01) | 16 Jan 2024 | MH2-3 |  | Inner formwork closed. Left outer formwork for tonight casting
Tue (16/01) | 16 Jan 2024 | P16-5 |  | Casting done. Now start to tidy up the area
Tue (16/01) | 16 Jan 2024 | MH5-2 |  | Lowering down pipe no 7. Preparing to push in
Tue (16/01) | 16 Jan 2024 | MH1-2 |  | Casting in progress
Wed (17/01) | 17 Jan 2024 | Zone 4 |  | WH continue trial trench for transfer beams at P45 and P46 (2 teams)
Wed (17/01) | 17 Jan 2024 | Zone 4 |  | WG shifting materials
Wed (17/01) | 17 Jan 2024 | Zone 4 |  | Erection of traffic controller shelter
Wed (17/01) | 17 Jan 2024 | P15-4 |  | Preparation for boring, noise ballon to be set up
Wed (17/01) | 17 Jan 2024 | Zone 3 P44 |  | Preparing to start second point trial JGP, 1/7nos completed. Now waiting for soil disposal
Wed (17/01) | 17 Jan 2024 | P37 |  | RW hacking ongoing
Wed (17/01) | 17 Jan 2024 | ST164 |  | 2nd bite excavation in progress
Wed (17/01) | 17 Jan 2024 | ST171 | PB2 | Continue preboring
Wed (17/01) | 17 Jan 2024 | ST178 - ST180 | half | Guidewall plan for casting today
Wed (17/01) | 17 Jan 2024 | Exit 3 |  | KTC excavation works till exisiting ground level ongoing
Wed (17/01) | 17 Jan 2024 | MH5-2 |  | Pipe No-7 push in done. Lower down pipe No-8. Prepare for push in
Wed (17/01) | 17 Jan 2024 | P15-6 BP |  | Boring works in progress
Wed (17/01) | 17 Jan 2024 | MH2-3 |  | Continue formwork closing of manhole formwork. Continue drizzling
Wed (17/01) | 17 Jan 2024 | South ramp s3 |  | Excavation to FEL
Wed (17/01) | 17 Jan 2024 | MH5-2 |  | Pipe jacking in progress. Preparing to lower pipe no. 13
Wed (17/01) | 17 Jan 2024 | MH1-2 |  | Preparation for Formwork dismantle
Wed (17/01) | 17 Jan 2024 | BH146 |  | In progress, 27m
Wed (17/01) | 17 Jan 2024 | BH148 |  | In progress, 14m
Wed (17/01) | 17 Jan 2024 | MH2-1 |  | MH wall formwork dismantling
Wed (17/01) | 17 Jan 2024 | ST49A |  | Waterstop joint welding ongoing
Wed (17/01) | 17 Jan 2024 | Zone 3 |  | Rearranging steel plates along vehicular access
Wed (17/01) | 17 Jan 2024 | ST45A |  | First bite excavation in progress
Wed (17/01) | 17 Jan 2024 | ST178 -ST180 | half | Guidewall casting in progress
Wed (17/01) | 17 Jan 2024 | ST171 |  | Continue preboring
Wed (17/01) | 17 Jan 2024 | P17 |  | Bollard installation ongoing at temp bus stop
Wed (17/01) | 17 Jan 2024 | P15-6 |  | Rebar cage installation
Wed (17/01) | 17 Jan 2024 | P15-6 |  | Casting started
Wed (17/01) | 17 Jan 2024 | MH5-2 |  | Pipe No-15 lowered down. Preparing for push in
Thu (18/01) | 18 Jan 2024 | BH148 |  | In progress, 22m
Thu (18/01) | 18 Jan 2024 | ST49A |  | Casting ongoing. Progressive vol: 67/100m3
Thu (18/01) | 18 Jan 2024 | MH2-8 |  | Dewatering ongoing before continuing rebar tying for MH wall
Thu (18/01) | 18 Jan 2024 | MH5-2 |  | Pipe No-17 push in done. Now lowering down pipe No-18
Thu (18/01) | 18 Jan 2024 | ST49A |  | Casting was completed ard 1217pm. Total volume: 105m3
Thu (18/01) | 18 Jan 2024 | ST64 |  | First bite excavation in progress, 14m
Thu (18/01) | 18 Jan 2024 | MH1-2 |  | Continue excavation for the next layer caisson
Thu (18/01) | 18 Jan 2024 | P18-6 |  | Boring completed. Working platform preparation for rebar cage installation
Thu (18/01) | 18 Jan 2024 | P38 |  | Excavation for guidewall ST88-ST89
Thu (18/01) | 18 Jan 2024 | Zone 3 BH52 |  | Hand auger in progress
Thu (18/01) | 18 Jan 2024 | Zone 2 |  | Singtel cable pulling
Thu (18/01) | 18 Jan 2024 | P44 |  | Trial JGP 3rd point grouting in progress (T-A5). As to date, 2/7nos completed
Thu (18/01) | 18 Jan 2024 | ST68 |  | Rebar cages (6nos) u-clip inspection done
Thu (18/01) | 18 Jan 2024 | Zone 1 NLL |  | Open pit excavation for 6.6KV. Last pit prior to cable pulling
Thu (18/01) | 18 Jan 2024 | Zone 4 P45 |  | WH continue trial trench for transfer beam. Currently team is on tea break. Only 1 team today
Thu (18/01) | 18 Jan 2024 | Loyang Way near exit 1 |  | Krishco lane closure
Thu (18/01) | 18 Jan 2024 | P18-6 |  | Rebar cage installation
Thu (18/01) | 18 Jan 2024 | P17-6 |  | Marking prior to casing installation
Thu (18/01) | 18 Jan 2024 | ST49A |  | Casting in progress
Thu (18/01) | 18 Jan 2024 | ST178 -ST180 | half | Guidewall cast yesterday
Thu (18/01) | 18 Jan 2024 | ST164 |  | Second bite cleaning ongoing
Thu (18/01) | 18 Jan 2024 | BH146 |  | In progress, 33m
Thu (18/01) | 18 Jan 2024 | N6 |  | Formworks dismantling
Fri (19/01) | 19 Jan 2024 | Loyang Way near exit 1 |  | Lane closure by Krishco. Singtel is also doing cable pulling here
Fri (19/01) | 19 Jan 2024 | MH1-2 |  | 11th layer excavation continue. Current depth 400mm/1.2m
Fri (19/01) | 19 Jan 2024 | Zone 1 |  | Area preparation for boring rig mobilisation. Today to shift kelly bar and upper mast. Tomorrow main body will shift and do assembly
Fri (19/01) | 19 Jan 2024 | MH5-2 |  | 25/45 pipe jacking
Fri (19/01) | 19 Jan 2024 | Zone 1 |  | SPPG completed pulling pit excavation for 6.6KV along NLL. Balance one pit along PDR3
Fri (19/01) | 19 Jan 2024 | P38 |  | ST89-ST88 guidewall rebar works ongoing
Fri (19/01) | 19 Jan 2024 | S3 |  | Excavation to FEL to complete by today. Then HSL will bring down excavator to start hacking of pile head
Fri (19/01) | 19 Jan 2024 | ST68 |  | Preparing for casting
Fri (19/01) | 19 Jan 2024 | ST164 |  | Waterstop endplate joint welding in progress
Fri (19/01) | 19 Jan 2024 | Zone 3 P44 |  | Trial JGP point 4 precutting in progress (T-A1). As to date, 3/7nos completed
Sat (20/01) | 20 Jan 2024 | P38 |  | ST89-88 continue guidewall rebar tying. Plan for casting today
Sat (20/01) | 20 Jan 2024 | ST64 |  | Trenching in progress
Sat (20/01) | 20 Jan 2024 | Zone 4 |  | WH to lean con the previous trial trench areas across zone 4 vehicular access
Sat (20/01) | 20 Jan 2024 | P46 |  | WH to continue trial trench for transfer beam. Dewatering and shoring preparation ongoing. Only 1 team today
Sat (20/01) | 20 Jan 2024 | Zone 4 |  | WG on site to continue SPPG pipe laying
Sat (20/01) | 20 Jan 2024 | P44 |  | Trial JGP grout density checked. Now ongoing point 5. As to date, 4/7nos completed
Sat (20/01) | 20 Jan 2024 | ST64 |  | 2nd bite excavation temporarily stopped. BC cutter gear box repair ongoing
Sat (20/01) | 20 Jan 2024 | BH148 |  | In progress, 39m
Sat (20/01) | 20 Jan 2024 | MH2-3 |  | Dewatering ongoing
Sat (20/01) | 20 Jan 2024 | N6 |  | Clearing materials
Sat (20/01) | 20 Jan 2024 | MH1-2 |  | Continue 10th layer excavation
Sat (20/01) | 20 Jan 2024 | Zone 1 |  | Kelly bar was mobbed in yesterday. Today plan to mob in main body from zone 2
Sat (20/01) | 20 Jan 2024 | MH5-2 |  | Pipe jacking in progress, 29/45nos
Sat (20/01) | 20 Jan 2024 | P17-6 |  | Rebar cage installation in progress
Sat (20/01) | 20 Jan 2024 | ST45A |  | Waterstop endplate joint welding in progress
Sat (20/01) | 20 Jan 2024 | ST50 |  | First bite excavation ongoing, 15m
Sat (20/01) | 20 Jan 2024 | Exit 2 BH145 |  | Hand auger ongoing
Sat (20/01) | 20 Jan 2024 | Exit 2 BH129 |  | Manual trial trench in progress
Sat (20/01) | 20 Jan 2024 | ST45A |  | Rebar cages (3nos) and hanging bars u-clip inspection done
Sat (20/01) | 20 Jan 2024 | ST88-89 |  | Guidewall inspection done. Can proceed for casting
Sat (20/01) | 20 Jan 2024 | Zone 1 |  | LE boring rig mobilised
Sat (20/01) | 20 Jan 2024 | MH1-2 |  | Continue hacking 10th layer
Sat (20/01) | 20 Jan 2024 | P17-6 |  | Casting ongoing
Sat (20/01) | 20 Jan 2024 | P18-4 |  | Boring ongoing
Sat (20/01) | 20 Jan 2024 | MH2-7 |  | MH outer wall casting ongoing
Sat (20/01) | 20 Jan 2024 | Zone 2 |  | HSL completed work for the day
Sat (20/01) | 20 Jan 2024 | MH5-2 |  | No activity for night shift. FYI
Sat (20/01) | 20 Jan 2024 | Zone 1 |  | MH1-2 hacking and soil removal to continue tonight
Sat (20/01) | 20 Jan 2024 | ST45A |  | Top cage installation in progress
Sat (20/01) | 20 Jan 2024 | ST50 |  | 1st bite current depth at 21m. Trenching temporarily stopped due to desander repair works
Sat (20/01) | 20 Jan 2024 | ST164 |  | Casting in progress. 141/195 m3
Sat (20/01) | 20 Jan 2024 | ST168 |  | Preboring in progress
Sat (20/01) | 20 Jan 2024 | ST164 |  | Rebar cage installation in progress, 10/10nos
Sun (21/01) | 21 Jan 2024 | ST164 |  | Waiting for the last 2 loads. 177/195 m3
Sun (21/01) | 21 Jan 2024 | Zone 2 |  | Singtel here for cable pulling works
Sun (21/01) | 21 Jan 2024 | MH1-2 |  | Hacking continue. Average depth 700-800mm
Sun (21/01) | 21 Jan 2024 | ST45A |  | Tremie pipe installation in progress
Sun (21/01) | 21 Jan 2024 | ST50 |  | 1st bite excavation current depth at 24.5m
Sun (21/01) | 21 Jan 2024 | ST64 |  | 1st bite trenching at 24.5m depth
Sun (21/01) | 21 Jan 2024 | ST164 |  | Casting completed
Sun (21/01) | 21 Jan 2024 | ST45A |  | Casting in progress
Mon (22/01) | 22 Jan 2024 | Near exit 1 |  | Barricade painting for sewer pipes area
Mon (22/01) | 22 Jan 2024 | ST171 |  | Guidewall formwork dismantling
Mon (22/01) | 22 Jan 2024 | Exit 2 BH145 |  | Pending permit before start works
Mon (22/01) | 22 Jan 2024 | BH148 |  | In progress, 43m
Mon (22/01) | 22 Jan 2024 | ST168 |  | Preboring ongoing
Mon (22/01) | 22 Jan 2024 | P18-4 |  | Boring works in progress
Mon (22/01) | 22 Jan 2024 | MH5-2 |  | Pipe jacking for 30th pipe
Mon (22/01) | 22 Jan 2024 | Zone 1 |  | TT for P3 ERSS
Mon (22/01) | 22 Jan 2024 | ST163 |  | Target to start today. Now area preparation ongoing
Mon (22/01) | 22 Jan 2024 | MH2-3 |  | Pre-cast chamber 1st raised installation
Mon (22/01) | 22 Jan 2024 | S3 |  | Pile head hacking, 2/3 piles completed
Mon (22/01) | 22 Jan 2024 | P15-5 |  | TT to expose abandoned LV cable
Mon (22/01) | 22 Jan 2024 | Zone 2 |  | Temp bus stop bollard MPI
Mon (22/01) | 22 Jan 2024 | Zone 3 BH52 |  | In progress, 20m
Mon (22/01) | 22 Jan 2024 | Loyang lane gate 5 |  | Singtel cable joining
Mon (22/01) | 22 Jan 2024 | P25 |  | Manual trial trench in progress for NCE application for recharge well works
Mon (22/01) | 22 Jan 2024 | BH148 |  | In progress, 45m
Mon (22/01) | 22 Jan 2024 | BH145 |  | SI works started
Mon (22/01) | 22 Jan 2024 | MH2-3 |  | Precast chamber ring outer wall 1st raise formwork closing, today will cast
Mon (22/01) | 22 Jan 2024 | ST171 |  | Continue guidewall formwork removal
Mon (22/01) | 22 Jan 2024 | ST168 |  | Continue preboring
Mon (22/01) | 22 Jan 2024 | ST163 |  | First bite excavation in progress, 15m
Mon (22/01) | 22 Jan 2024 | P18-4 |  | Boring works completed, now preparing to lower rebar cages
Mon (22/01) | 22 Jan 2024 | P18-4 |  | Bottom cage lowered
Mon (22/01) | 22 Jan 2024 | P17-4 |  | Area preparation for pre-boring
Mon (22/01) | 22 Jan 2024 | P8-2 |  | KTC backfilling works in progress for ERSS removal
Mon (22/01) | 22 Jan 2024 | MH1-2 |  | Continue excavation for 11th layer, target to cast tonight
Mon (22/01) | 22 Jan 2024 | S3 |  | Pile head hacking 3/3 completed
Mon (22/01) | 22 Jan 2024 | Zone 1 |  | LE boring rig setting up works
Mon (22/01) | 22 Jan 2024 | MH5-2 |  | Lowering and connecting of Pipe no. 31 in progress
Mon (22/01) | 22 Jan 2024 | P18-4 |  | Ready for casting, waiting for concrete lorry
Mon (22/01) | 22 Jan 2024 | MH2-3 |  | Wall first lift formwork closed. Waiting for concrete lorry to cast
Mon (22/01) | 22 Jan 2024 | ST45 |  | B1 trenching in progress, current depth 18m
Mon (22/01) | 22 Jan 2024 | ST50 |  | End plate extraction
Mon (22/01) | 22 Jan 2024 | ST64 |  | Trimming continue
Mon (22/01) | 22 Jan 2024 | ST164 |  | BC cutter teeth replacement
Mon (22/01) | 22 Jan 2024 | ST168 |  | Boring works to continue until 10pm
Mon (22/01) | 22 Jan 2024 | Loyang lane gate 5 |  | TT to exposed water pipe alignment for diversion
Mon (22/01) | 22 Jan 2024 | MH2-7 |  | Last layer raised wall casting in progress
Mon (22/01) | 22 Jan 2024 | MH2-3 |  | Manhole casting was done. Housekeeping before end work
Mon (22/01) | 22 Jan 2024 | MH1-2 |  | Trimming below caisson wall. Preparing for wall formwork in progress. Target tonight casting
Mon (22/01) | 22 Jan 2024 | ST50 |  | Preparing for chiselling works
Mon (22/01) | 22 Jan 2024 | P38 |  | ST88-89 guidewall was cast last Sat. To continue formwork dismantling. Have asked Dongah to clear water
Mon (22/01) | 22 Jan 2024 | P44 |  | Trial JGP as to date completed, 6/7nos. Now housekeeping ongoing before starting last point, T-A3
Mon (22/01) | 22 Jan 2024 | P46 |  | Marking of utilities done. TT for pilecap to start soon
Tue (23/01) | 23 Jan 2024 | P22 |  | Krishco here rectifying pipe joint from CCTV inspection comments
Tue (23/01) | 23 Jan 2024 | P17-4 |  | Boring works on going
Tue (23/01) | 23 Jan 2024 | P44 |  | Trial JGP completed yesterday, 7/7nos. Soil clearing ongoing
Tue (23/01) | 23 Jan 2024 | P46 |  | WH continue trial trench
Tue (23/01) | 23 Jan 2024 | Zone 4 |  | Trench backfilling ongoing by Wee Guan
Tue (23/01) | 23 Jan 2024 | P15-4 |  | Abandoned LV recovered
Tue (23/01) | 23 Jan 2024 | ST181 |  | Guidewall excavation in progress
Tue (23/01) | 23 Jan 2024 | S3 |  | Final levelling today by KTC, then WH to lean con
Tue (23/01) | 23 Jan 2024 | MH5-2 |  | Currently 29/45 completed. Discharge pump yet to replace, waiting for the delivery by today
Tue (23/01) | 23 Jan 2024 | MH1-2 |  | 11th layer formwork closing. Afternoon to cast
Tue (23/01) | 23 Jan 2024 | P3 |  | TT for ERSS in progress
Tue (23/01) | 23 Jan 2024 | ST50 |  | Rebar cage (6nos) and hanging bar u-clip inspection done
Tue (23/01) | 23 Jan 2024 | ST45 |  | Gearbox repair ongoing. First bite excavation ard 22m
Tue (23/01) | 23 Jan 2024 | P25 |  | Geomotion trial trench for NCE application
Tue (23/01) | 23 Jan 2024 | Zone 3 |  | SPTel excavation ongoing for pipe laying towards new MH
Tue (23/01) | 23 Jan 2024 | P17-4 |  | Boring works completed, preparation for rebar cage lowering
Tue (23/01) | 23 Jan 2024 | ST50 |  | Rebar cage installation ongoing, 3/6nos
Tue (23/01) | 23 Jan 2024 | ST181 |  | Preparation for guidewall works
Tue (23/01) | 23 Jan 2024 | ST168 |  | Continue preboring
Tue (23/01) | 23 Jan 2024 | ST64 |  | 2nd bite excavation completed, 26.4m. BC cutter body washing ongoing
Tue (23/01) | 23 Jan 2024 | Zone 1 |  | Boring rig waiting for cable replacement
Tue (23/01) | 23 Jan 2024 | Zone 1 |  | P3 ERSS TT continue
Tue (23/01) | 23 Jan 2024 | Zone 4 TT |  | Found Singtel pipes
Tue (23/01) | 23 Jan 2024 | Zone 1 |  | Old ECM hacking works in progress
Tue (23/01) | 23 Jan 2024 | S3 |  | Final levelling completed. Pending final inspection for lean con
Tue (23/01) | 23 Jan 2024 | MH1-2 |  | Casting works ongoing for 11th layer
Tue (23/01) | 23 Jan 2024 | MH2-1 |  | MH grinding works ongoing
Tue (23/01) | 23 Jan 2024 | S3 |  | Inspection prior to lean con
Tue (23/01) | 23 Jan 2024 | Zone 2 |  | Lean con ongoing near designated access
Tue (23/01) | 23 Jan 2024 | Zone 3 |  | SPTel pipe laying today plan 7m
Tue (23/01) | 23 Jan 2024 | ST45 |  | First bite excavation ongoing, 26.3m
Tue (23/01) | 23 Jan 2024 | ST50 |  | Rebar cage installation in progress, 4/6nos
Tue (23/01) | 23 Jan 2024 | ST181 |  | Guidewall rebar works ongoing
Tue (23/01) | 23 Jan 2024 | ST168 |  | Preboring depth check
Tue (23/01) | 23 Jan 2024 | ST163 |  | First bite completed, 41.5m
Tue (23/01) | 23 Jan 2024 | MH2-8 |  | LCH night shift team will be working here tonight
Tue (23/01) | 23 Jan 2024 | P17-4 |  | Casting done
Tue (23/01) | 23 Jan 2024 | MH1-2 |  | Caisson casting was done
Tue (23/01) | 23 Jan 2024 | BH148 |  | In progress, 49m
Tue (23/01) | 23 Jan 2024 | BH145 |  | In progress, 20m
Tue (23/01) | 23 Jan 2024 | ST181 |  | Preparing to start guidewall excavation
Tue (23/01) | 23 Jan 2024 | Zone 3 |  | WH to rectify temp water pipes
Tue (23/01) | 23 Jan 2024 | ST168 |  | Preboring in progress, 22.5m
Tue (23/01) | 23 Jan 2024 | ST163 |  | First bite excavation in progress, 33m
Tue (23/01) | 23 Jan 2024 | P37 |  | Continue retaining wall hacking works and rebar cutting
Tue (23/01) | 23 Jan 2024 | BH52 |  | In progress, 22m
Tue (23/01) | 23 Jan 2024 | P24 |  | TT for NCE by geomotion
Tue (23/01) | 23 Jan 2024 | MH2-3 |  | Rebar cage fabrication for 2nd lift wall
Wed (24/01) | 24 Jan 2024 | BH181 |  | Guidewall rebar works ongoing. Target to cast today
Wed (24/01) | 24 Jan 2024 | ST64 |  | C-lug welding ongoing for waterstop trimming side
Wed (24/01) | 24 Jan 2024 | ST163 |  | 2nd bite excavation in progress, 17m
Wed (24/01) | 24 Jan 2024 | P37 |  | Retaining wall excavation in progress. Target to complete today and then handover to Dongah for guidewall works
Wed (24/01) | 24 Jan 2024 | BH52 |  | Packer test in progress
Wed (24/01) | 24 Jan 2024 | Zone 3 |  | GCE continue soil disposal and area cleanup
Wed (24/01) | 24 Jan 2024 | Zone 4 P46-47 |  | Today Wee Guan to lean con the power duct pipe area
Wed (24/01) | 24 Jan 2024 | P46 |  | WH to continue trial trench for DR3
Wed (24/01) | 24 Jan 2024 | ST64 |  | Preparing for waterstop end plate extraction
Wed (24/01) | 24 Jan 2024 | MH2-3 |  | LSS backfilling
Wed (24/01) | 24 Jan 2024 | P16-6 |  | Boring works on going
Wed (24/01) | 24 Jan 2024 | Zone 3 in front of substation |  | SPTel laid 7m yesterday. Pipe laying ongoing. Remaining ~30m towards substation
Wed (24/01) | 24 Jan 2024 | MH2-8 |  | Hacking of caisson shaft for sewer pipe connection
Wed (24/01) | 24 Jan 2024 | S3 |  | Pile head manual hacking to COL completed. Cleaning in progress
Wed (24/01) | 24 Jan 2024 | P16-6 |  | Boring completed, rebar cage installation in progress
Wed (24/01) | 24 Jan 2024 | MH1-2 |  | Excavation for 12th layer
Wed (24/01) | 24 Jan 2024 | MH2-8 |  | Sewer pipe T-joint installation. Highlighted to improve housekeeping
Wed (24/01) | 24 Jan 2024 | ST50 |  | Casting continue, balance 2 loads. Total volume 200 m3
Wed (24/01) | 24 Jan 2024 | St181 half |  | Guidewall cast
Wed (24/01) | 24 Jan 2024 | ST66 |  | Trimming completed, end plate will try to extract
Wed (24/01) | 24 Jan 2024 | ST163 |  | 2nd bite trenching at 29.5m depth
Wed (24/01) | 24 Jan 2024 | ST168 |  | Pre-boring at 14.5m depth
Wed (24/01) | 24 Jan 2024 | P25 |  | Krishco here continue replacement of bolt and nuts
Wed (24/01) | 24 Jan 2024 | P16-6 |  | Casting in progress
Wed (24/01) | 24 Jan 2024 | MH2-8 |  | Permanent manhole chamber installed. Tomorrow to continue casting of the base
Wed (24/01) | 24 Jan 2024 | P16-6 |  | Casting done. Now tidy up the area
Wed (24/01) | 24 Jan 2024 | MH1-2 |  | Continue hacking/ excavation for next layer cassion casting
Wed (24/01) | 24 Jan 2024 | BH145 |  | In progress, 32m. BH148 terminated at 57m
Thu (25/01) | 25 Jan 2024 | ST45 |  | Trimming end plate trimming
Thu (25/01) | 25 Jan 2024 | ST64 |  | Rebar cage installation 4/8 installed
Thu (25/01) | 25 Jan 2024 | ST66 |  | 1st bite trenching on going
Thu (25/01) | 25 Jan 2024 | St163 |  | End plate extraction
Thu (25/01) | 25 Jan 2024 | Zone 1 |  | LECE Manual Trial trenching works for P3 (No.5) in progress
Thu (25/01) | 25 Jan 2024 | Zone 4 opp SIA building |  | Lane closed for SPPG works
Thu (25/01) | 25 Jan 2024 | Zone 2 North ramp | bet n2 & n3 | Manual trial trench works to locate existing fire hydrant connection joint
Thu (25/01) | 25 Jan 2024 | N6 |  | KTC backfilling works
Thu (25/01) | 25 Jan 2024 | MH1-2 |  | Continue excavation
Thu (25/01) | 25 Jan 2024 | Loyang lane gate 5 |  | WF here to lay pipe tonight for sewer over pumping
Thu (25/01) | 25 Jan 2024 | Zone 2 |  | P15-6 casting completed. Balance 2 piles to complete this week. HSL ended work for today
Thu (25/01) | 25 Jan 2024 | Zone 2 |  | Lucky joint here for singtel cable pulling
Thu (25/01) | 25 Jan 2024 | MH1-2 |  | Continue excavation for 12th layer. Current depth 750mm
Thu (25/01) | 25 Jan 2024 | MH2-3 |  | 2nd layer raised wall casting
Thu (25/01) | 25 Jan 2024 | P15-5 |  | Boring works in progress
Fri (26/01) | 26 Jan 2024 | Zone 4 opp SIA building |  | Manual excavation for SPPG pipe laying
Fri (26/01) | 26 Jan 2024 | ST45 |  | Waterstop endplate removal in progress
Fri (26/01) | 26 Jan 2024 | ST190 |  | Guidewall excavation ongoing
Fri (26/01) | 26 Jan 2024 | BH144 |  | Trial trench in progress
Fri (26/01) | 26 Jan 2024 | Zone 3 |  | SPTel to install manhole and continue pipe joining
Fri (26/01) | 26 Jan 2024 | MH2-8 |  | Dewatering ongoing before continuing works
Fri (26/01) | 26 Jan 2024 | Zone 4 loyang avenue LP105 |  | Manual excavation for SPPG pipe laying continue
Fri (26/01) | 26 Jan 2024 | ST163 |  | End plate extracted. Preparation for cleaning
Fri (26/01) | 26 Jan 2024 | ST66 |  | 1st bite trenching continue
Fri (26/01) | 26 Jan 2024 | ST64 |  | 6/8 rebar cages installed
Fri (26/01) | 26 Jan 2024 | MH1-2 |  | 12th layer excavation continue. Current depth 900mm
Fri (26/01) | 26 Jan 2024 | Zone 3 BH53 |  | In progress, 14m
Fri (26/01) | 26 Jan 2024 | P37 area |  | Backfilling and slope levelling. Lean con casting progressively done
Fri (26/01) | 26 Jan 2024 | ST163 |  | Waterstop endplate joint welding in progress
Fri (26/01) | 26 Jan 2024 | ST64 |  | Casting ongoing, 148.5/180m3
Fri (26/01) | 26 Jan 2024 | ST181 |  | Second part guidewall construction ongoing. Pending inspection before casting
Fri (26/01) | 26 Jan 2024 | ST66 |  | First bite excavation in progress, 29m
Fri (26/01) | 26 Jan 2024 | ST45 |  | Bite 2 cleaning ongoing
Fri (26/01) | 26 Jan 2024 | Near MH2-8/Gate 5 |  | Ley Choon open pit for SPPG cable pulling
Fri (26/01) | 26 Jan 2024 | Zone 4 |  | Excavation stopped for the night
Fri (26/01) | 26 Jan 2024 | Loyang lane gate 5 |  | Sewer pipe laying completed. Area reinstated
Fri (26/01) | 26 Jan 2024 | ST45 |  | WS trimming continue
Fri (26/01) | 26 Jan 2024 | ST66 |  | 1st bite current depth at 25.4m. Now BC cutter hoist up for maintenance
Fri (26/01) | 26 Jan 2024 | ST163 |  | Cleaning completed. Desanding in progress
Fri (26/01) | 26 Jan 2024 | ST64 |  | All rebar cages installed , preparation for Tremie pipe installation
Fri (26/01) | 26 Jan 2024 | Zone 1 |  | Hacking ongoing for TT P3 deck post
Fri (26/01) | 26 Jan 2024 | Zone 1 |  | LE no more activity
Fri (26/01) | 26 Jan 2024 | MH1-2 |  | Continue excavation for 12th layer
Fri (26/01) | 26 Jan 2024 | P16-4 |  | Pending to cast
Fri (26/01) | 26 Jan 2024 | ST64 |  | Completed. Total volume: 187.5m3
Fri (26/01) | 26 Jan 2024 | ST168 |  | Continue preboring
Fri (26/01) | 26 Jan 2024 | ST163 |  | Waterstop end plate joint welding ongoing
Fri (26/01) | 26 Jan 2024 | ST171 |  | Started today. Currently excavation temporarily stopped due to flap cylinder damaged. Current depth 8m
Fri (26/01) | 26 Jan 2024 | ST190 |  | Guidewall rebar works ongoing
Fri (26/01) | 26 Jan 2024 | MH2-8 |  | 2nd raise wall formwork closing. Tonight to cast
Fri (26/01) | 26 Jan 2024 | Zone 2 |  | Backfilling at slip road for stage 1 diversion will continue until 10pm
Fri (26/01) | 26 Jan 2024 | P16-4 |  | Casting completed. Now housekeeping
Fri (26/01) | 26 Jan 2024 | South ramp S3 |  | Column starter bar installed, tying on going. Work till 10pm
Fri (26/01) | 26 Jan 2024 | Zone 1 |  | Traffic light pipe 6m laid. Now backfilling, tomorrow to lay premix
Fri (26/01) | 26 Jan 2024 | MH1-2 |  | Final levelling. Tonight install rebar and plan for casting before ending shift
Fri (26/01) | 26 Jan 2024 | ST45 |  | Koden completed, ST47: preparation for trenching
Fri (26/01) | 26 Jan 2024 | ST66 |  | BC cutter teeth replacement
Sat (27/01) | 27 Jan 2024 | MH5-2 |  | Pipe No-27 removal in progress
Sat (27/01) | 27 Jan 2024 | ST45 |  | Rebar cage lowering, 8/8 completed
Sat (27/01) | 27 Jan 2024 | ST47 |  | Trenching at 17.5m depth
Sat (27/01) | 27 Jan 2024 | St171 |  | Gear box replacement
Sat (27/01) | 27 Jan 2024 | St163 |  | 10/10 cage installed
Sat (27/01) | 27 Jan 2024 | MH1-2 |  | Curing
Sat (27/01) | 27 Jan 2024 | Zone 1 |  | LE removal of abandoned slab
Sat (27/01) | 27 Jan 2024 | Zone 1 |  | LE welder cutting and preparing for waler beam
Sat (27/01) | 27 Jan 2024 | MH1-2 |  | Rebar installation on going for 12th layer
Sat (27/01) | 27 Jan 2024 | Zone 1 PRD3 |  | Sptel here for cable pulling works
Sat (27/01) | 27 Jan 2024 | ST45 |  | End plate and water stop installation
Sat (27/01) | 27 Jan 2024 | ST47 |  | BC cutter gear box repair works prior to trenching
Sat (27/01) | 27 Jan 2024 | ST66 |  | BC cutter teeth maintenance continue
Sat (27/01) | 27 Jan 2024 | MH2-8 |  | Benching work
Sat (27/01) | 27 Jan 2024 | MH2-6 |  | Hacking of cassion for removal
Sat (27/01) | 27 Jan 2024 | MH2-5 |  | Access making for HDPE welding
Sat (27/01) | 27 Jan 2024 | MH5-2 |  | Jacking pipe No-23 retrieval in progress
Sat (27/01) | 27 Jan 2024 | Zone 4 |  | Work completed for the night. Lane opened
Sat (27/01) | 27 Jan 2024 | ST45 |  | Rebar cage installation in progress
Sat (27/01) | 27 Jan 2024 | ST171 |  | 1st bite trenching at 20.4m
Sat (27/01) | 27 Jan 2024 | ST163 |  | Rebar cage installation, 5/10 installed
Sat (27/01) | 27 Jan 2024 | Zone 2 stage 1 Diversion slip road |  | Backfilling until 10pm . Target to complete tomorrow, monday NDT
Sat (27/01) | 27 Jan 2024 | P15-4 |  | Last pile completed. HSL now housekeeping
Sat (27/01) | 27 Jan 2024 | MH5-2 |  | Pipe pull back 11/30 completed
Sat (27/01) | 27 Jan 2024 | MH2-8 |  | Preparing for benching work
Sat (27/01) | 27 Jan 2024 | MH2-5 |  | Preparing for HDPE welding
Sat (27/01) | 27 Jan 2024 | P15-4 |  | Preparing to start boring. Today to cast
Sun (28/01) | 28 Jan 2024 | MH5-2 |  | Preparation ongoing to continue pulling back pipes
Sun (28/01) | 28 Jan 2024 | S3 |  | No activity
Sun (28/01) | 28 Jan 2024 | Zone 2 |  | HSL no activity
Sun (28/01) | 28 Jan 2024 | Zone 2 |  | M1 works ongoing
Sun (28/01) | 28 Jan 2024 | ST45 |  | Casting in progress, 114/200m3
Sun (28/01) | 28 Jan 2024 | ST163 |  | In progress. Est total volume: 303m3
Sun (28/01) | 28 Jan 2024 | ST190 |  | Guidewall cast yesterday
Sun (28/01) | 28 Jan 2024 | ST171 |  | BC cutter wheel replacement ongoing
Sun (28/01) | 28 Jan 2024 | MH2-8 |  | LSS backfilling completed. Housekeeping
Sun (28/01) | 28 Jan 2024 | MH1-2 |  | Excavation continue
Sun (28/01) | 28 Jan 2024 | MH5-2 |  | 11/30 pipes pulled out
Sun (28/01) | 28 Jan 2024 | ST45 |  | All cage fully lowered with hanging bar
Sun (28/01) | 28 Jan 2024 | ST47 |  | Cutter wheel teeth replacement
Sun (28/01) | 28 Jan 2024 | ST171 |  | New gear box installation on going
Sun (28/01) | 28 Jan 2024 | ST163 |  | Tremie pipe installation in progress
Sun (28/01) | 28 Jan 2024 | Zone 4 |  | Manual excavation for SPPG pipe laying continue
Sun (28/01) | 28 Jan 2024 | MH5-2 |  | Continue pipe retrieval
Sun (28/01) | 28 Jan 2024 | Zone 2 centre median |  | Trial trench ongoing for BP works
Sun (28/01) | 28 Jan 2024 | P25 |  | Krishco rectifying water pipe bolts and painting works
Sun (28/01) | 28 Jan 2024 | Exit 2 |  | Preparing area for desander plant. Today to cast base lean con
Sun (28/01) | 28 Jan 2024 | ST45 |  | Last truck casting ongoing
Sun (28/01) | 28 Jan 2024 | ST184 |  | Excavation in progress for guidewall works
Sun (28/01) | 28 Jan 2024 | Next to exit 3 vehicular access |  | Lean con cast
Sun (28/01) | 28 Jan 2024 | Zone 3 |  | Ramp casting for vehicular movement/bentonite pipe protection between the designated walkway access
Sun (28/01) | 28 Jan 2024 | ST163 |  | Casting completed. Total volume: 312m3
Sun (28/01) | 28 Jan 2024 | Zone 3 |  | Ground levelling and arranging steel plates
Sun (28/01) | 28 Jan 2024 | ST66 |  | 2nd bite excavation in progress
Sun (28/01) | 28 Jan 2024 | ST45 casting completed. Total volume |  | 215m3
Sun (28/01) | 28 Jan 2024 | Zone 4 |  | Work completed, area reinstated. Lane opened
Sun (28/01) | 28 Jan 2024 | ST45 |  | Tremie pipes installed
Sun (28/01) | 28 Jan 2024 | ST163 |  | Casting in progress
Sun (28/01) | 28 Jan 2024 | ST47 |  | 1st bite trenching in progress
Sun (28/01) | 28 Jan 2024 | MH1-2 |  | Continue hacking and excavation for 13th layer
Sun (28/01) | 28 Jan 2024 | Zone 1 |  | No other activities
Mon (29/01) | 29 Jan 2024 | ST168 |  | No more activity
Mon (29/01) | 29 Jan 2024 | ST47 |  | Pressure hydraulic main pump installation ongoing
Mon (29/01) | 29 Jan 2024 | Exit 3 |  | KTC works done for the day
Mon (29/01) | 29 Jan 2024 | MH2-8 |  | Casting completed
Mon (29/01) | 29 Jan 2024 | MH2-3 |  | Precast chamber ring final raise installation work
Mon (29/01) | 29 Jan 2024 | MH2-5 |  | Preparation for HDPE lining welding
Mon (29/01) | 29 Jan 2024 | P25 |  | Krishco doing painting works
Mon (29/01) | 29 Jan 2024 | P13-6 |  | TT completed, no utility found
Mon (29/01) | 29 Jan 2024 | Zone 2 |  | HSL preparation works to shift all the materials that affecting upcoming bus-only lane alignment
Mon (29/01) | 29 Jan 2024 | P13-5 |  | Trial trench in progress
Mon (29/01) | 29 Jan 2024 | Zone 2 |  | Temporary desander and mud tank to shift
Mon (29/01) | 29 Jan 2024 | S3 |  | Shear links installation works for pile cap
Mon (29/01) | 29 Jan 2024 | PMH8-12 |  | SPPG cable pulling in progress. 2/6 main cables pulled. @⁨Hannah Lim LTA⁩ FYI
Mon (29/01) | 29 Jan 2024 | Zone 4 |  | GCE 1st coring point to start soon
Mon (29/01) | 29 Jan 2024 | Zone 4 |  | Casing installation for core point (BCR1) for TB3X trial JGP started. 2 workers, 1 supervisor, 1 operator
Mon (29/01) | 29 Jan 2024 | MH2-3 |  | Mould close for raised wall casting. Concrete ordered. Manpower 3+1
Mon (29/01) | 29 Jan 2024 | P14 |  | Movable hoarding installation in progress
Mon (29/01) | 29 Jan 2024 | MH2-8 |  | 3rd lift raised wall formwork closing. Tonight to cast
Mon (29/01) | 29 Jan 2024 | Exit 3 |  | Backfilled soil removal for fissure grouting in progress
Mon (29/01) | 29 Jan 2024 | MH2-3 |  | Raised wall casting in progress
Mon (29/01) | 29 Jan 2024 | Zone 3 opp selerang camp |  | Old drain hacking
Mon (29/01) | 29 Jan 2024 | ST171 |  | Internal Koden test for 1st bite
Mon (29/01) | 29 Jan 2024 | ST168 |  | Pre boring works till 10pm
Mon (29/01) | 29 Jan 2024 | ST66 |  | Cleaning completed
Mon (29/01) | 29 Jan 2024 | MH2-8 |  | Casting of 3rd raised wall
Mon (29/01) | 29 Jan 2024 | Exit 3 |  | KTC works ongoing
Mon (29/01) | 29 Jan 2024 | Zone 2 |  | Singtel cable pulling ongoing
Mon (29/01) | 29 Jan 2024 | South ramp S3 |  | No activity. Plan for casting tmr
Mon (29/01) | 29 Jan 2024 | MH5-2 |  | LSS backfilling
Mon (29/01) | 29 Jan 2024 | MH1-2 |  | Trimming ongoing for 13th layer. Target to cast tonight
Mon (29/01) | 29 Jan 2024 | Zone 1 |  | No other activity
Mon (29/01) | 29 Jan 2024 | ST171 |  | First bite excavation completed, 41.4m. Cutter teeth changing ongoing
Mon (29/01) | 29 Jan 2024 | Zone 4 |  | GCE Preparing for trial trench before coring JGP areas
Mon (29/01) | 29 Jan 2024 | Zone 4 LP105 | towards LW | WG to continue manual excavation for power duct pipe laying. Barricade installation & dewatering works ongoing currently
Tue (30/01) | 30 Jan 2024 | N6 |  | Just now NDT at abutment level completed. This team of KTC will shift to P8-2 to continue backfilling
Tue (30/01) | 30 Jan 2024 | Zone 4 |  | Manual excavation ongoing
Tue (30/01) | 30 Jan 2024 | MH2-6 |  | Top 2 layer of wall hacking completed. Now pending soil truck to arrive for backfilling works
Tue (30/01) | 30 Jan 2024 | MH2-5 |  | Preparation for HDPE lining welding
Tue (30/01) | 30 Jan 2024 | Zone 2 | Temp Bus Stops | Pull out tests completed for 4nos of mechanical bolts
Tue (30/01) | 30 Jan 2024 | S3 |  | Pending to cast, addressing QPS comment
Tue (30/01) | 30 Jan 2024 | P8-2 |  | Backfilling until pile cap level completed. NDT tomorrow
Tue (30/01) | 30 Jan 2024 | N1 |  | Backfilling in progress
Tue (30/01) | 30 Jan 2024 | Zone 4 |  | BCR1 core point grouted. To continue for next core point tmr after trial trench and GI pipe installation. BCR1 core meets the >85% TCR. To send to the lab after all cores are done next week. 3 workers, 1 supervisor, 1 operator
Tue (30/01) | 30 Jan 2024 | ST63 |  | First bite excavation in progress, 18.3m
Tue (30/01) | 30 Jan 2024 | ST66 |  | Rebar cage installation in progress, 2/3nos
Tue (30/01) | 30 Jan 2024 | ST171 |  | 2nd bite excavation resume
Tue (30/01) | 30 Jan 2024 | ST47 |  | Now mud hose choked. Rectification ongoing. Machine seems to be down since last night
Tue (30/01) | 30 Jan 2024 | MH2-8 |  | MH wall formwork removal. Tonight plan for LSS backfilling
Tue (30/01) | 30 Jan 2024 | Exit 3 |  | KTC works ongoing
Tue (30/01) | 30 Jan 2024 | ST47 |  | Waterstop side trimming in progress
Tue (30/01) | 30 Jan 2024 | ST171 |  | 2nd bite excavation temporarily on hold. Cutter teeth replacement ongoing. Current depth at 18.5m
Tue (30/01) | 30 Jan 2024 | ST183 |  | Guidewall was cast just now
Tue (30/01) | 30 Jan 2024 | ST168 |  | Preboring completed
Tue (30/01) | 30 Jan 2024 | Zone 4 LP105 | towards LW | Dewatering ongoing before continuing manual excavation for power duct
Wed (31/01) | 31 Jan 2024 | MH2-8 |  | LSS backfilling
Wed (31/01) | 31 Jan 2024 | MH2-8 |  | 4th truck LSS backfilling ongoing
Wed (31/01) | 31 Jan 2024 | MH2-8 |  | LSS backfilling completed
Wed (31/01) | 31 Jan 2024 | S3 |  | No activity. Pile cap cast last night, curing in progress
Wed (31/01) | 31 Jan 2024 | PMH8-12 |  | Pilot cables pulling, today to complete
Wed (31/01) | 31 Jan 2024 | N6 |  | LECE ERSS removal completed
Wed (31/01) | 31 Jan 2024 | Zone 2 |  | Shifting of desander and bentonite plant by HSL
Wed (31/01) | 31 Jan 2024 | Zone 4 |  | WG continue manual excavation and shoring installation
Wed (31/01) | 31 Jan 2024 | ST47 |  | Endplate extraction
Wed (31/01) | 31 Jan 2024 | Near ST47 |  | Singtel cable recovery by term contractor
Wed (31/01) | 31 Jan 2024 | ST171 |  | 2nd bite current depth at 19.2m. Cutter teeth rectification ongoing
Wed (31/01) | 31 Jan 2024 | ST63 |  | First bite excavation in progress
Wed (31/01) | 31 Jan 2024 | MH2-3 |  | LSS backfilling in progress
Wed (31/01) | 31 Jan 2024 | MH2-8 |  | Last raised wall formwork closing. To cast today
Wed (31/01) | 31 Jan 2024 | Exit 3 |  | Backfilled soil disposal continue
Wed (31/01) | 31 Jan 2024 | ST44 |  | 1st bite trenching at 21.7m
Wed (31/01) | 31 Jan 2024 | ST182 |  | Guidewall rebar works. Tomorrow to cast
Wed (31/01) | 31 Jan 2024 | ST171 |  | 2nd bite trenching in progress
Wed (31/01) | 31 Jan 2024 | ST169 |  | Pre boring works
Wed (31/01) | 31 Jan 2024 | ST168 |  | To be backfilled, waiting for LSS
Wed (31/01) | 31 Jan 2024 | ST47 |  | Bottom cage installation in progress
Wed (31/01) | 31 Jan 2024 | MH2-8 |  | Wall casting
Wed (31/01) | 31 Jan 2024 | Exit 3 |  | KTC works ongoing
Wed (31/01) | 31 Jan 2024 | Zone 1 |  | Casing installed for DP3-2
Wed (31/01) | 31 Jan 2024 | MH1-2 |  | Tonight continue soil hacking and excavation for 14th layer
Wed (31/01) | 31 Jan 2024 | MH5-2 |  | No activity
Wed (31/01) | 31 Jan 2024 | ST47 |  | Rebar cage installation in progress, 2/3nos
Wed (31/01) | 31 Jan 2024 | ST171 |  | Bite 2 current depth 22.7m. Internal koden check ongoing
Wed (31/01) | 31 Jan 2024 | Zone 4 LP105 | towards LW | WG continue manual soil clearing for power duct pipe laying
Wed (31/01) | 31 Jan 2024 | ST63 |  | BC cutter gearbox rectification ongoing
Wed (31/01) | 31 Jan 2024 | MH2-8 |  | Works completed
Thu (01/02) | 01 Feb 2024 | Zone 3 |  | Continue old drain hacking for ST188-ST184 guidewall works
Thu (01/02) | 01 Feb 2024 | P12 |  | Road kerb hacking works in progress. Manpower - 3 (2 Sup & 1 Operator)
Thu (01/02) | 01 Feb 2024 | Zone 3 | P23-P24 | Preparation to start Trial trench for Bored Pile BP-6-4 and BP-6-2
Thu (01/02) | 01 Feb 2024 | Zone 4 |  | WG continue manual soil clearing below services
Thu (01/02) | 01 Feb 2024 | Exit 3 |  | KTC excavation & levelling works. Seongha arranging steel plates for working platform
Thu (01/02) | 01 Feb 2024 | Zone 2 |  | HSL plants/materials shifting and setting up works in progress
Thu (01/02) | 01 Feb 2024 | Zone 1 |  | DP3-2 installed, now waiting for LSS to arrive at 5pm
Thu (01/02) | 01 Feb 2024 | MH1-2 |  | Continue soil disposal for 14th layer
Thu (01/02) | 01 Feb 2024 | P12 |  | Road kerb affecting bp, hacking completed. Now housekeeping & levelling
Thu (01/02) | 01 Feb 2024 | ST47 |  | Casting ongoing. Progressive vol: 45/99m3
Thu (01/02) | 01 Feb 2024 | ST44 |  | First bite excavation ongoing
Thu (01/02) | 01 Feb 2024 | ST171 |  | Bite 2 waterstop side trimming ongoing
Thu (01/02) | 01 Feb 2024 | ST44 |  | First bite excavation temporarily stopped for cutter teeth replacement. Current depth 27.9m
Thu (01/02) | 01 Feb 2024 | MH2-8 |  | Clearing materials from inside manhole
Thu (01/02) | 01 Feb 2024 | Exit 3 |  | Soil levelling until 10pm
Thu (01/02) | 01 Feb 2024 | North ramp P10 |  | Soil delivery for backfilling
Thu (01/02) | 01 Feb 2024 | P9 |  | Backfilling to pile cap level, KTC will work until 10pm
Thu (01/02) | 01 Feb 2024 | MH1-2 |  | 14th layer excavation current depth at 1.1m. Tonight to complete excavation and trimming and start BRC installation
Thu (01/02) | 01 Feb 2024 | ST44 |  | Mud pump repair works
Thu (01/02) | 01 Feb 2024 | ST171 |  | Hydraulic hose replacement, 2nd bite, depth at 22.7
Thu (01/02) | 01 Feb 2024 | ST63 |  | 1st bite trenching at 25m
Thu (01/02) | 01 Feb 2024 | MH2-5 |  | HDPE lining welding works. Manpower - 5
Thu (01/02) | 01 Feb 2024 | Zone 4 |  | Slow lane closed for decking installation. Premix removal in progress
Thu (01/02) | 01 Feb 2024 | ST182 |  | Guidewall plan for casting today
Thu (01/02) | 01 Feb 2024 | ST171 |  | Mud pump change ongoing
Thu (01/02) | 01 Feb 2024 | Zone 3 |  | Sewer team preparation for connection works
Thu (01/02) | 01 Feb 2024 | P9-2 |  | KTC backfilling works ongoing. Manpower -3
Fri (02/02) | 02 Feb 2024 | MH2-5 |  | HDPE lining welding works. Manpower - 4
Fri (02/02) | 02 Feb 2024 | MH2-4 |  | LCH informed that hacking works for top 2 layers of wall will be postponed as sewer is live at the moment
Fri (02/02) | 02 Feb 2024 | MH2-3 |  | Caisson mould dismantling & preparation for soil backfilling works
Fri (02/02) | 02 Feb 2024 | Zone 2 N6 |  | LECE extracting ERSS @ north ramp. Manpower 2+1, 1 Vibro
Fri (02/02) | 02 Feb 2024 | P9-2 |  | KTC continue backfilling works for pile cap. Manpower - 4
Fri (02/02) | 02 Feb 2024 | Zone 3 |  | Loyang way junction singtel here for cable pulling
Fri (02/02) | 02 Feb 2024 | Zone 1, CGS |  | Temporary diverting pedestrian access for next pipe laying works. Manpower 4+2, 1 mini excavator
Fri (02/02) | 02 Feb 2024 | Zone 1, MH1-2 LCH |  | 14th layer excavation & trimming in progress. Target to install BRC in the afternoon and cast at night. 1 telescopic excavator & 1 mini excavator. Manpower 4+1
Fri (02/02) | 02 Feb 2024 | Zone 1, LECE |  | Steel plate laying for next preboring location, DP1-2. 1 boring rig, 1 vibro & 1 excavator. Manpower 10+1
Fri (02/02) | 02 Feb 2024 | Zone 1 |  | Singtel contractor trial trench works for their 6W pipe laying
Fri (02/02) | 02 Feb 2024 | MH1-2 |  | 14th layer casting completed
Fri (02/02) | 02 Feb 2024 | ST44 |  | Trenching in progress
Fri (02/02) | 02 Feb 2024 | P23 |  | Trial trench work completed for PB-6B-4. Found HT slab
Fri (02/02) | 02 Feb 2024 | ST171 |  | Trenching resume for 2nd bite
Fri (02/02) | 02 Feb 2024 | MH2-3 |  | Final piece of Caisson mould dismantling in progress. Backfilling will start after removal done
Fri (02/02) | 02 Feb 2024 | Zone 2 |  | HSL continue setting up works
Fri (02/02) | 02 Feb 2024 | ST63 |  | Mud pump pressure low, Dongah resolving the issue
Fri (02/02) | 02 Feb 2024 | P11 |  | Partial trial trenches work till road kerb in progress for P11 BP. Manpower - 3, 1 mini excavator
Fri (02/02) | 02 Feb 2024 | Zone 1 |  | Singtel term contractor doing excavation for cable pipe laying 6W along noise barrier
Fri (02/02) | 02 Feb 2024 | MH1-2 |  | Wall trimming in progress. Excavator hydraulic spoiled, excavation yet to complete. Dayshift mechanic will come down to repair
Fri (02/02) | 02 Feb 2024 | Zone 1 |  | Deck post (DP3-1) boring completed and reached 16.4m from GL. LECE will install the deck post next
Fri (02/02) | 02 Feb 2024 | Zone 1, MH1-2 |  | LCH excavation for 14th layer completed. Now BRC installation
Fri (02/02) | 02 Feb 2024 | Zone 1, CGS |  | Traffic Cable pipe laying works in progress, 5m length
Fri (02/02) | 02 Feb 2024 | P9-2 |  | Backfilling till pile cap level completed, now KTC shifting to N1 for backfilling works till pile cap level
Fri (02/02) | 02 Feb 2024 | N6 |  | ERSS extraction for pile cap fully completed
Fri (02/02) | 02 Feb 2024 | ST44 |  | Cutter wheel teeth replacement
Fri (02/02) | 02 Feb 2024 | ST171 |  | 2nd trenching continue
Fri (02/02) | 02 Feb 2024 | BP6B-4 |  | Found 22kV
Fri (02/02) | 02 Feb 2024 | BP6B-3 |  | Road premix removal in progress
Fri (02/02) | 02 Feb 2024 | MH2-3 |  | Houskeeping by LCH
Fri (02/02) | 02 Feb 2024 | MH1-2 |  | BRC installation in progress
Fri (02/02) | 02 Feb 2024 | MH2-5 |  | LCH ending work for the day. Housekeeping
Fri (02/02) | 02 Feb 2024 | N1 |  | Backfilling to pile cap level. Tomorrow NDT
Fri (02/02) | 02 Feb 2024 | P8 |  | Concrete plug cast at pile cap level
Fri (02/02) | 02 Feb 2024 | DP3-1 |  | Deck post installed and LSS backfilling completed
Fri (02/02) | 02 Feb 2024 | MH1-2 |  | Formwork closed. Waiting for concrete lorry
Fri (02/02) | 02 Feb 2024 | ST44 |  | Waterstop trimming
Fri (02/02) | 02 Feb 2024 | ST171 |  | 2nd bite trenching
Fri (02/02) | 02 Feb 2024 | Exit 3 Seongha |  | Preparation works, materials & office container delivery. Manpower - 6
Fri (02/02) | 02 Feb 2024 | Zone 4 opp SIA building |  | Slow lane closed for excavation of SPPG pipe corridor
Fri (02/02) | 02 Feb 2024 | Exit 3 |  | KTC continue excavation & levelling works
Fri (02/02) | 02 Feb 2024 | P23 |  | Trial trench work in progress for PB-6B-4. Manpower 4+1, 1 excavator
Sat (03/02) | 03 Feb 2024 | Zone 4 |  | Tonight to continue excavation for SPPG pipe laying
Sat (03/02) | 03 Feb 2024 | BH128 |  | SI completed, grouting in progress
Sat (03/02) | 03 Feb 2024 | ST-188 & ST-189 half |  | BRC laying for Guidewall construction
Sat (03/02) | 03 Feb 2024 | ST-171 |  | 2nd bite trenching completed. Now internal koden test for 2nd bite
Sat (03/02) | 03 Feb 2024 | ST-169 |  | Continue preboring works (PB1)
Sat (03/02) | 03 Feb 2024 | ST-63 |  | Preparation to resume 1st bite trenching
Sat (03/02) | 03 Feb 2024 | Zone 3 |  | Krishco doing flushing works for upcoming cctv inspection
Sat (03/02) | 03 Feb 2024 | Zone 3, vent shaft |  | Working Platform backfilling and compaction
Sat (03/02) | 03 Feb 2024 | Zone 3, P37 |  | Hardcores hacking works in progress
Sat (03/02) | 03 Feb 2024 | Zone 4, P46-P47 |  | MoGuan starhub 6W pipe laying works in progress, target to lay 24m today
Sat (03/02) | 03 Feb 2024 | Zone 4, T-B2 JGP |  | Drilling rod retrieval in progress
Sat (03/02) | 03 Feb 2024 | N6 |  | WH Compaction works in progress. Manpower - 2, 1 excavator
Sat (03/02) | 03 Feb 2024 | N1 |  | KTC backfilling to pile cap completed, NDT in the afternoon. They will continue backfill at P10-2 next. Manpower - 3, 1 excavator
Sat (03/02) | 03 Feb 2024 | Zone 1 |  | Singtel contractor continue 6W pipe laying works along noise barrier
Sat (03/02) | 03 Feb 2024 | Zone 1 |  | LECE housekeeping works in progress. Today they only working half day due to company event
Sat (03/02) | 03 Feb 2024 | Zone 1, MH1-2 |  | 14th layer cast last night. Excavation at the center area in progress, afternoon will remove the mould formwork. 1 telescopic excavator & 1 mini excavator. Manpower 4+1
Sat (03/02) | 03 Feb 2024 | Zone 1 |  | CGS preparation works in progress for traffic pipe laying works at near Shell station. Manpower - 5, 1 mini excavator
Sat (03/02) | 03 Feb 2024 | MH5-2 |  | TBM delivered, now testing works ongoing
Sat (03/02) | 03 Feb 2024 | ST44 |  | End plate extracted
Sat (03/02) | 03 Feb 2024 | ST171 |  | 2nd bite trenching continue. 35m
Sat (03/02) | 03 Feb 2024 | ST044 |  | 1st & 2nd rebar cage lapping and lowering in progress
Sat (03/02) | 03 Feb 2024 | ST-188 & ST-189 | 1/2 | Formwork installation for Guidewall construction
Sat (03/02) | 03 Feb 2024 | ST63 | SC40#02 | Excavation work temporary stop due to wheel teeth change, current depth is 25.60m/26.20m
Sat (03/02) | 03 Feb 2024 | ST-171 |  | 2nd bite trimming works in progress
Sat (03/02) | 03 Feb 2024 | ST-169 |  | HSL Preboring works and koden test for (PB1) completed. Now preparing for LSS backfill
Sat (03/02) | 03 Feb 2024 | Zone 3, Vent Shaft |  | Continue Working Platform backfilling and compaction
Sat (03/02) | 03 Feb 2024 | Zone 3, P36-P37 |  | Hardcores hacking works
Sat (03/02) | 03 Feb 2024 | Zone 4, P46-P47 |  | MoGuan starhub 6W pipe laying works completed 24m. Reinstatement ongoing
Sat (03/02) | 03 Feb 2024 | Zone 4 |  | HSL preparation works in progress for bentonite pipes
Sat (03/02) | 03 Feb 2024 | MH5-2 |  | TBM lowered down, setting up in progress. Today will start jacking. Manpower - 8
Sat (03/02) | 03 Feb 2024 | Zone 1 |  | CGS hacking of rigid pavement ongoing for pipe laying works
Sat (03/02) | 03 Feb 2024 | Zone 1 |  | Singtel contractor continue 6W pipe laying works outside the gate area. Pipe laying inside zone 1 boundary (along noise barriers) have all been completed
Sat (03/02) | 03 Feb 2024 | P8-2 |  | KTC continue backfill works
Sat (03/02) | 03 Feb 2024 | N1 |  | Concrete plug casting at pile cap level
Sat (03/02) | 03 Feb 2024 | P10 |  | Partial bottom piles till road kerb trial trenches completed for BP. No utility
Sat (03/02) | 03 Feb 2024 | MH2-3 |  | Backfilling completed. Now compaction in progress
Sat (03/02) | 03 Feb 2024 | P24 |  | Trial trench for PB-6b-3 completed. Now hacking premix for PB-6b-1
Sat (03/02) | 03 Feb 2024 | ST44 |  | Desanding
Sat (03/02) | 03 Feb 2024 | ST171 |  | BC cutter up for teeth replacement
Sat (03/02) | 03 Feb 2024 | MH5-2 |  | Night shift team here for HDPE welding
Sat (03/02) | 03 Feb 2024 | N1 |  | Last layer of concrete plug cast
Sat (03/02) | 03 Feb 2024 | P8 and P9 |  | Backfilling to column stump level
Sat (03/02) | 03 Feb 2024 | MH1-2 |  | Excavation of 15th layer in progress. Current depth at 250mm
Sat (03/02) | 03 Feb 2024 | ST44 |  | 4/4 rebar cage installation
Sat (03/02) | 03 Feb 2024 | ST171 |  | Gear box oil top up, later will do desanding
Sat (03/02) | 03 Feb 2024 | ST63 |  | 1st bite trenching, current depth at 25.7m
Sat (03/02) | 03 Feb 2024 | MH2-8 |  | Preparation for LSS backfill. Manpower - 6
Sat (03/02) | 03 Feb 2024 | Exit 3 |  | KTC excavation & levelling works. Manpower - 3
Sat (03/02) | 03 Feb 2024 | Exit 3 |  | Seongha materials mobilisation and setting up works. Manpower - 9
Sun (04/02) | 04 Feb 2024 | MH1-2 |  | Hacking continue for 15th layer
Sun (04/02) | 04 Feb 2024 | JTC blk 2 |  | WF here installing pipe at existing MH for over pumping
Sun (04/02) | 04 Feb 2024 | MH2-5 |  | HDPE welding continue
Sun (04/02) | 04 Feb 2024 | ST44 |  | Rebar cages and tremie pipe installed. Wating for concrete lorry
Sun (04/02) | 04 Feb 2024 | ST63 |  | 1st bite trenching continue, current depth at 25.5m
Sun (04/02) | 04 Feb 2024 | ST171 |  | Waterstop trimming on going
Sun (04/02) | 04 Feb 2024 | ST168-169 |  | Guidewall casting completes
Sun (04/02) | 04 Feb 2024 | Zone 4 |  | Shoring works in progress
Sun (04/02) | 04 Feb 2024 | ST44 |  | Casting completed, 110 m3. Tremie pipe dismantling
Sun (04/02) | 04 Feb 2024 | ST63 |  | 1st bite trenching completed
Sun (04/02) | 04 Feb 2024 | ST171 |  | 3rd bite excavation started
Mon (05/02) | 05 Feb 2024 | ST171 |  | Lowering down last cage. Left tremie pipe lowering for casting. Tonight to cast
Mon (05/02) | 05 Feb 2024 | Zone 3 BH128 and BH127 |  | SI completed. Today continue hand auger for BH126 and BH125
Mon (05/02) | 05 Feb 2024 | Zone 3 |  | Guidewall excavation for ST186 & backfilling for ST184, ST185
Mon (05/02) | 05 Feb 2024 | ST171 |  | Rebar cage installation in progress, 6/8nos
Mon (05/02) | 05 Feb 2024 | ST169 |  | Preboring ongoing
Mon (05/02) | 05 Feb 2024 | Zone 4 |  | Coring point B-CR3 stage 3
Mon (05/02) | 05 Feb 2024 | Zone 4 |  | HSL has mobilised their machineries on site (1 crane, 1 excavator, 1 rig)
Mon (05/02) | 05 Feb 2024 | Zone 4 |  | Starhub excavation for pipe laying. Today plan 24m
Mon (05/02) | 05 Feb 2024 | Zone 4 |  | Singtel Activ cable pulling
Mon (05/02) | 05 Feb 2024 | ST165 |  | Gear box repair in progress. First bite excavation current depth at 17m
Mon (05/02) | 05 Feb 2024 | ST69 |  | To replace suction hose. First bite excavation depth at 23.55m
Mon (05/02) | 05 Feb 2024 | N1 |  | KTC backfilling works in progress, manpower 4 + 1
Mon (05/02) | 05 Feb 2024 | MH5-2 |  | Pipe jacking in progress for 6th pipe
Mon (05/02) | 05 Feb 2024 | MH2-8 |  | Backfilling works
Mon (05/02) | 05 Feb 2024 | Next to MH2-8/Gate 5 |  | Ley Choon open pit and shoring installation for SPPG cable pulling pit
Mon (05/02) | 05 Feb 2024 | Exit 3 |  | KTC continue excavation and levelling works
Mon (05/02) | 05 Feb 2024 | Exit 3 |  | Seongha equipment roofing frame setup ongoing
Mon (05/02) | 05 Feb 2024 | Zone 4 |  | 3/4 nos. BCR3 coring and grouting completed today. BCR4 to do tmr
Mon (05/02) | 05 Feb 2024 | Zone 4 |  | Mobile crane unloaded some boring rig accessories. To unload boring rig counterweight tmr. Crawler crane to mob in tmr as well to set up boring rig
Mon (05/02) | 05 Feb 2024 | Zone 2 |  | Lean con casting at slope area
Mon (05/02) | 05 Feb 2024 | ST171 |  | Rebar cage installation ongoing, 8/8nos
Mon (05/02) | 05 Feb 2024 | ST69 |  | First bite excavation temporarily stopped for cutter teeth replacement. Current depth 24m
Mon (05/02) | 05 Feb 2024 | BC cutter 1 for ST165 |  | Gear box repair works still ongoing
Mon (05/02) | 05 Feb 2024 | MH2-6 |  | LCH one team doing HDPE welding. 2 workers + 1sup
Mon (05/02) | 05 Feb 2024 | MH1-2 |  | Continue trimming for BRC installation. Tonight to cast
Mon (05/02) | 05 Feb 2024 | ST69 |  | 1st bite in progress, reached 24.3m
Tue (06/02) | 06 Feb 2024 | ST165 |  | First bite current depth, 29.20m/41.30m
Tue (06/02) | 06 Feb 2024 | Zone 4 |  | Retrieval of drilling rod. Thereafter start coring for point BCR4
Tue (06/02) | 06 Feb 2024 | Zone 4 |  | Starhub to continue pipe laying. Today plan 18m
Tue (06/02) | 06 Feb 2024 | Zone 4 |  | HSL to mob in crawler crane today. Currently some general housekeeping ongoing
Tue (06/02) | 06 Feb 2024 | P8-2 |  | Waler beam dismantling
Tue (06/02) | 06 Feb 2024 | ST171 |  | Casting almost completed, 291m3
Tue (06/02) | 06 Feb 2024 | ST69 |  | Cutter teeth wheel replacement ongoing
Tue (06/02) | 06 Feb 2024 | Zone 3 |  | Dongah 135T crane demobilisation
Tue (06/02) | 06 Feb 2024 | Zone 3 BH126 |  | SI in progress
Tue (06/02) | 06 Feb 2024 | P28 area |  | Lean con casting ongoing
Tue (06/02) | 06 Feb 2024 | Near Gate 5 |  | Ley Choon open pit for SPPG works
Tue (06/02) | 06 Feb 2024 | MH2-8 |  | HDPE lining installation inside manhole
Tue (06/02) | 06 Feb 2024 | BH126 |  | In progress, 14m
Tue (06/02) | 06 Feb 2024 | ST176, ST176A |  | Guidewall excavation in progress
Tue (06/02) | 06 Feb 2024 | ST165 |  | First bite excavation in progress, 31.7m
Tue (06/02) | 06 Feb 2024 | ST169 |  | Preboring temporarily stopped. Machine broke down and rectification in progress
Tue (06/02) | 06 Feb 2024 | S3 |  | Concrete plug casting in progress
Tue (06/02) | 06 Feb 2024 | Zone 4 |  | BCR4 trial trench ongoing
Tue (06/02) | 06 Feb 2024 | Zone 4 |  | Starhub pipes laid 12m today. Backfilling ongoing
Tue (06/02) | 06 Feb 2024 | Zone 4 |  | HSL continue equipment mobilisation & machinery diesel topup. Pending mobilisation of crawler crane
Tue (06/02) | 06 Feb 2024 | Loyang Way near exit 1 |  | Singtel cable pulling works
Tue (06/02) | 06 Feb 2024 | MH5-2 |  | No. 12th pipe on going
Tue (06/02) | 06 Feb 2024 | P10 |  | Compaction done. NDT scheduled at 430pm
Tue (06/02) | 06 Feb 2024 | Zone 3 |  | Sewer pipe preparation works for the linkup on Thursday
Tue (06/02) | 06 Feb 2024 | BH123 |  | In progress, 23.5m
Tue (06/02) | 06 Feb 2024 | ST186-ST187 | half | Formwork installation in progress
Tue (06/02) | 06 Feb 2024 | P30 |  | Arranging of steel plates
Tue (06/02) | 06 Feb 2024 | MH2-4 |  | LCH preparing for backfilling
Tue (06/02) | 06 Feb 2024 | ST186-ST187 | half | Guidewall rebar installed. Today to continue formwork installation and casting
Tue (06/02) | 06 Feb 2024 | Zone 3 BH123 |  | Started yesterday. In progress, 10m
Tue (06/02) | 06 Feb 2024 | Zone 3 BH54 |  | Completed. Pending confirmation of termination depth, 39.3m
Tue (06/02) | 06 Feb 2024 | ST165 |  | Continue first bite excavation
Wed (07/02) | 07 Feb 2024 | MH1-2 |  | Excavation for 16th layer in progress. Manpower 5+1
Wed (07/02) | 07 Feb 2024 | MH5-2 |  | Pipe jacking in progress for 13th pipe. Manpower - 7
Wed (07/02) | 07 Feb 2024 | Zone 3 |  | Sewer pipe connection prep works
Wed (07/02) | 07 Feb 2024 | ST169 |  | Preboring ongoing
Wed (07/02) | 07 Feb 2024 | ST165 |  | Bite 2 excavation in progress
Wed (07/02) | 07 Feb 2024 | Zone 4 |  | BCR4 coring to commence soon. Yesterday, GCE was able to thread the rod catcher in but could not pull the rod out
Wed (07/02) | 07 Feb 2024 | MH2-6 |  | LCH continue HDPE welding. 2 workers+ 1 watchman + 1 sup
Wed (07/02) | 07 Feb 2024 | Zone 3 BH126 |  | In progress, 28m
Wed (07/02) | 07 Feb 2024 | ST186-ST187 | half | Guidewall formwork removal ongoing
Wed (07/02) | 07 Feb 2024 | BH123 |  | Packer test ongoing
Wed (07/02) | 07 Feb 2024 | ST69 |  | First bite trenching temporarily on hold. BC cutter wheel repair works ongoing
Wed (07/02) | 07 Feb 2024 | ST169 |  | Preboring soil removal
Wed (07/02) | 07 Feb 2024 | ST165 |  | 2nd bite excavation in progress, 22m
Wed (07/02) | 07 Feb 2024 | Zone 4 |  | BCR4 coring for 4th sample in progress. 3 samples taken
Wed (07/02) | 07 Feb 2024 | Zone 4 |  | Starhub excavation for pipe laying ongoing. Today plan 12m. Already completed 6m for the day
Wed (07/02) | 07 Feb 2024 | Zone 4 |  | HSL crane assembly in progress
Wed (07/02) | 07 Feb 2024 | MH5-2 |  | 14/45 pipes completed. 15th pipe connection on going
Wed (07/02) | 07 Feb 2024 | Zone 4 junction/Loyang Way |  | No activity
Wed (07/02) | 07 Feb 2024 | ST176, ST176A |  | Guidewall formwork installation in progress
Wed (07/02) | 07 Feb 2024 | Zone 1 |  | Pipe laying for traffic light, today target 7.7m
Wed (07/02) | 07 Feb 2024 | MH1-2 |  | 16th layer excavation in progress. Estimated depth 200mm
Wed (07/02) | 07 Feb 2024 | MH2-9 area |  | Concrete levelling for pedestrian footpath
Wed (07/02) | 07 Feb 2024 | MH1-2 |  | Soil disposal
Wed (07/02) | 07 Feb 2024 | Zone 1 |  | LEW cable detection. Found singtel slab and NLT, all live. Singtel affecting 2 deck post
Wed (07/02) | 07 Feb 2024 | North ramp P10 |  | Continue backfilling works to pile cap.level
Wed (07/02) | 07 Feb 2024 | P11 |  | TT for P11 ERSS. Verifying power duct alignment
Wed (07/02) | 07 Feb 2024 | Loyang lane gate 5 | inside our hoarding | Sppg open pi excavation. Pipe already found, shoring in progress
Wed (07/02) | 07 Feb 2024 | MH1-2 |  | Formwork dismantling done
Wed (07/02) | 07 Feb 2024 | ST186 and 187 half |  | Area backfilling. Guidewall completed
Wed (07/02) | 07 Feb 2024 | ST69 |  | 1st bite trenching at 27m
Wed (07/02) | 07 Feb 2024 | Mud pump hydraulic hose leakage. Start leakage at 6 |  | 00AM. This machine is BC cutter 03 (SAMBO CMC machine). SAMBO machine break down more frequent now adays. Either Gear Box , mud pump or hydraulic hose issue
Thu (08/02) | 08 Feb 2024 | MH2-3 |  | HDPE lining works. Manpower 3+1
Thu (08/02) | 08 Feb 2024 | P38 area |  | Hardcore levelling ongoing
Thu (08/02) | 08 Feb 2024 | ST165 |  | Bite 2 excavation reached 41.5m
Thu (08/02) | 08 Feb 2024 | Zone 3 Sewer |  | Prep works ongoing for the connection works
Thu (08/02) | 08 Feb 2024 | Zone 4 |  | Rest area erection ongoing
Thu (08/02) | 08 Feb 2024 | Zone 4 |  | HSL prep for rig assembly, Starhub continue excavation for pipe laying
Thu (08/02) | 08 Feb 2024 | Zone 4 |  | GCE to continue trial trench for SPT works. Starhub is currently working at the area where they need to retrieve rod. Works will be done thereafter
Thu (08/02) | 08 Feb 2024 | Exit 2 |  | PBH40 trial trench ongoing
Thu (08/02) | 08 Feb 2024 | PBH41 |  | In progress
Thu (08/02) | 08 Feb 2024 | BH126 |  | Depth at 35.8m. Packer test ongoing
Thu (08/02) | 08 Feb 2024 | Zone 4 |  | Biometric on site
Thu (08/02) | 08 Feb 2024 | Zone 4 |  | GCE preparing to retrieve rod
Thu (08/02) | 08 Feb 2024 | Zone 4 |  | HSL boring rig assembly & ULT3 rebar cage delivery
Thu (08/02) | 08 Feb 2024 | P3 |  | Backfilling in progress
Thu (08/02) | 08 Feb 2024 | MH5-2 |  | Pipe jacking 16/45 completed
Thu (08/02) | 08 Feb 2024 | ST165 |  | 3rd bite already completed. Now trimming ongoing
Thu (08/02) | 08 Feb 2024 | Zone 1 |  | 2 lane biometrics on site
Thu (08/02) | 08 Feb 2024 | MH1-2 |  | Delivery of mini excavator . Current depth 600mm
Thu (08/02) | 08 Feb 2024 | P38 |  | Steel plate laying ongoing
Thu (08/02) | 08 Feb 2024 | Exit 3 |  | Seongha genset area setting up works ongoing
Thu (08/02) | 08 Feb 2024 | Zone 1/2 |  | Traffic light pipe laying at Loyang lane completed 6m ( one lane). Now plan to lay 4m (side table). Today will complete 10m
Thu (08/02) | 08 Feb 2024 | MH1-2 |  | Excavation in progress for next layer caisson work
Thu (08/02) | 08 Feb 2024 | Zone 3 BH126 |  | In progress, 31.8m
Thu (08/02) | 08 Feb 2024 | BH123 |  | In progress, 35.5m
Thu (08/02) | 08 Feb 2024 | ST176, ST176A |  | Guidewall cast yesterday
Fri (09/02) | 09 Feb 2024 | Zone 2 |  | HSL crane boom down since yesterday
Fri (09/02) | 09 Feb 2024 | Zone 4 |  | GCE to continue rod retrieval
Fri (09/02) | 09 Feb 2024 | Zone 4 |  | HSL no activity
Fri (09/02) | 09 Feb 2024 | Zone 4 |  | Today Starhub plan to continue excavation and pipe laying (12m)
Fri (09/02) | 09 Feb 2024 | ST165 |  | Maintenance works ongoing
Fri (09/02) | 09 Feb 2024 | ST69 |  | Trench backfilling with G15
Fri (09/02) | 09 Feb 2024 | Zone 2 |  | HSL boring rig parked and barricaded
Fri (09/02) | 09 Feb 2024 | BH126 |  | In progress, 40m
Fri (09/02) | 09 Feb 2024 | PBH40 |  | Hand auger in progress
Fri (09/02) | 09 Feb 2024 | PBH41 |  | In progress, 38.5m
Fri (09/02) | 09 Feb 2024 | P11 |  | Area exposed for USD hacking to backfill today for CNY holiday
Fri (09/02) | 09 Feb 2024 | MH5-2 |  | LCH not here yet to continue pipe jacking
Fri (09/02) | 09 Feb 2024 | MH2-8 |  | HDPE lining works
Fri (09/02) | 09 Feb 2024 | Exit 3 |  | Seongha continue setting up works. The team working till 5pm today. Tuesday plan to start trial trench
Fri (09/02) | 09 Feb 2024 | Zone 1 |  | Site inspection with RTO and WH safety area IC for CNY holiday
Fri (09/02) | 09 Feb 2024 | MH1-2 |  | Excavation reached 1.2m. Balance trimming of wall. They will install rebar and close formwork tomorrow then cast on Tuesday
Fri (09/02) | 09 Feb 2024 | MH2-3 |  | HDPE welding in progress. Completed for MH2-5 & MH2-6
Fri (09/02) | 09 Feb 2024 | MH1-2 |  | Continue excavation for next span caisson work
Fri (09/02) | 09 Feb 2024 | MH5-2 |  | 20/45 pipe jacking completed. LCH will continue to here tomorrow
Fri (09/02) | 09 Feb 2024 | ST165 |  | Backfilling on going
Fri (09/02) | 09 Feb 2024 | Zone 4 |  | CGE ending work for the day. Housekeeping
Sun (11/02) | 11 Feb 2024 | MH2-6 |  | Plan for railing installation today. Gas check done
Sun (11/02) | 11 Feb 2024 | MH5-2 |  | No activity
Sun (11/02) | 11 Feb 2024 | MH1-2 |  | 16th ring rebar installation
Sun (11/02) | 11 Feb 2024 | Zone 1 |  | No other activity
Sun (11/02) | 11 Feb 2024 | Zone 2 |  | No other activities
Sun (11/02) | 11 Feb 2024 | Zone 3 |  | Dongah (SI) no activities
Sun (11/02) | 11 Feb 2024 | Zone 3 |  | Chisel rectification ongoing
Sun (11/02) | 11 Feb 2024 | JTC blk 4 |  | No activity
Sun (11/02) | 11 Feb 2024 | Zone 4 |  | No activity
Sun (11/02) | 11 Feb 2024 | P38/DR2 area |  | No activity
Sun (11/02) | 11 Feb 2024 | ST168 | MC96 | Ground preparations ongoing prior to ST168 works. Once BC cutter parked and hose connections done etc, trenching works will start. Target to start during day shift
Sun (11/02) | 11 Feb 2024 | BC cutter 2 | SC40 | No activity
Sun (11/02) | 11 Feb 2024 | BC cutter 3 | SC40 | Maintenance works ongoing
Sun (11/02) | 11 Feb 2024 | Exit 3 |  | KTC & Seongha no activity
Sun (11/02) | 11 Feb 2024 | MH2-8 |  | No activity
Mon (12/02) | 12 Feb 2024 | Zone 1 |  | No activity
Mon (12/02) | 12 Feb 2024 | ST48 |  | No activity
Mon (12/02) | 12 Feb 2024 | ST168 |  | To resume trenching after lunch, one Operator assisting mechanic at BC cutter 3 for maintenance work
Mon (12/02) | 12 Feb 2024 | Exit 1 |  | Ryobi-G here installing inclinometer at D-wall
Mon (12/02) | 12 Feb 2024 | MH5-2 |  | No activity
Tue (13/02) | 13 Feb 2024 | MH5-2 |  | No activity. Current pipe jacking status - Pipe no. 25
Tue (13/02) | 13 Feb 2024 | MH1-2 |  | No activity. 16th layer Formwork installation completed
Tue (13/02) | 13 Feb 2024 | MH1-2 |  | Continue casting
Tue (13/02) | 13 Feb 2024 | Zone 4 |  | Hacking/clearing of debris near the centre median for Starhub pipe laying
Tue (13/02) | 13 Feb 2024 | BC cutter 2 | SC40 | Maintenance works ongoing
Tue (13/02) | 13 Feb 2024 | BC cutter 3 | SC40 | Maintenance ongoing
Tue (13/02) | 13 Feb 2024 | P28/JTC blk 2 |  | SPPG on site with WH for ground survey for their machinery parking for works towards the transformer room at JTC
Tue (13/02) | 13 Feb 2024 | Exit 2 |  | PBH40 in progress
Tue (13/02) | 13 Feb 2024 | Outside Gate 5 |  | Ley Choon works for 22kV here
Tue (13/02) | 13 Feb 2024 | Loyang Way | near exit 1 | Singtel lane closure
Tue (13/02) | 13 Feb 2024 | Zone 4 |  | Starhub excavation for pipe laying ongoing. Plan 12m
Tue (13/02) | 13 Feb 2024 | Zone 4 HSL |  | Jacking instrument installation ongoing
Tue (13/02) | 13 Feb 2024 | ST166A |  | Preboring in progress
Tue (13/02) | 13 Feb 2024 | ST168 |  | BC cutter flap rectification ongoing
Tue (13/02) | 13 Feb 2024 | ST69 | BC cutter 3, SC40 | Excavation in progress
Tue (13/02) | 13 Feb 2024 | BH124 |  | In progress, 18m
Tue (13/02) | 13 Feb 2024 | BH125 |  | In progress, 12m
Tue (13/02) | 13 Feb 2024 | P26 area |  | Ley Choon continue open pit and shoring installation
Tue (13/02) | 13 Feb 2024 | Exit 3 |  | Trial trench for fissure grouting completed earlier today
Tue (13/02) | 13 Feb 2024 | South ramp S3 |  | Backfilling ongoing
Tue (13/02) | 13 Feb 2024 | ST168 |  | Resume excavation
Tue (13/02) | 13 Feb 2024 | ST166A |  | Preboring in progress. Works till 8pm
Tue (13/02) | 13 Feb 2024 | MH1-2 |  | Caisson shaft casting started
Tue (13/02) | 13 Feb 2024 | Exit 3 |  | Today TT at DW006 for trial fissure grouting
Tue (13/02) | 13 Feb 2024 | BH124 & BH125 |  | In progress
Tue (13/02) | 13 Feb 2024 | ST168 |  | First bite temporarily stopped. Cutter teeth replacement in progress. Current depth at 16.5m
Tue (13/02) | 13 Feb 2024 | Exit 1 |  | IM installation for IW36012 (DW97) in progress
Wed (14/02) | 14 Feb 2024 | Zone 4 |  | GCE demobilising rig from zone 4 & shift to zone 3
Wed (14/02) | 14 Feb 2024 | MH1-2 |  | Formwork removal for 16th layer. Manpower - 7+1
Wed (14/02) | 14 Feb 2024 | Zone 4 |  | Starhub continue excavation for pipe joining and manhole works
Wed (14/02) | 14 Feb 2024 | Zone 1 |  | Temporary drain pipe installation (preparation works for working platform for dp1-1 & dp1-2)
Wed (14/02) | 14 Feb 2024 | P48 |  | Trial trench for ULT12 was done yesterday. Today plan for casing installation
Wed (14/02) | 14 Feb 2024 | Zone 4 HSL |  | Rebar cage (with jacking instrument) fabrication
Wed (14/02) | 14 Feb 2024 | MH5-2 |  | Pipe jacking in progress for pipe no.25
Wed (14/02) | 14 Feb 2024 | ST168 |  | Trenching temporarily stopped for cutter teeth change. Current depth at 17.6m
Wed (14/02) | 14 Feb 2024 | ST69 |  | Cutter body washing
Wed (14/02) | 14 Feb 2024 | BH124, BH125 |  | In progress
Wed (14/02) | 14 Feb 2024 | BC cutter 2 | SC40 | Noise barrier panel rectification. No other activity at the moment
Wed (14/02) | 14 Feb 2024 | JTC blk 2 |  | SPPG lorry crane on site for their works at JTC now
Wed (14/02) | 14 Feb 2024 | ST191-194 |  | Clearing debris prior to guidewall TT works & checking of nearby services with utility team
Wed (14/02) | 14 Feb 2024 | Exit 3 |  | Soil disposal
Wed (14/02) | 14 Feb 2024 | Zone 2 |  | Singtel cable recovery
Wed (14/02) | 14 Feb 2024 | Zone 4 |  | Bund wall works along earth drain
Wed (14/02) | 14 Feb 2024 | Zone 4 |  | Starhub manhole installed
Wed (14/02) | 14 Feb 2024 | Zone 4 ULT12 |  | Strain gauge installation for rebar cage
Wed (14/02) | 14 Feb 2024 | Zone 3 |  | BC cutter flap rectification for ST168
Wed (14/02) | 14 Feb 2024 | ST168 |  | BC cutter teeth changing ongoing
Wed (14/02) | 14 Feb 2024 | ST69 |  | First bite excavation ongoing, 30m
Wed (14/02) | 14 Feb 2024 | MH5-2 |  | Pipe jacking status, 26/45 completed. 27th pipe in progress
Wed (14/02) | 14 Feb 2024 | BH124 |  | Packer test in progress. Depth at 34.5m
Wed (14/02) | 14 Feb 2024 | BH125 |  | In progress, 27m
Wed (14/02) | 14 Feb 2024 | SC40-2 |  | Rectification ongoing
Wed (14/02) | 14 Feb 2024 | PBH40 |  | In progress, 38m
Wed (14/02) | 14 Feb 2024 | Exit 3 |  | Soil disposal completed
Wed (14/02) | 14 Feb 2024 | P24-P25 |  | Platform preparation for Temporary desander. Tomorrow to lean con
Wed (14/02) | 14 Feb 2024 | BC cutter 2 |  | Engine repair works continue. Plan to complete tonight and resume operation by tomorrow
Wed (14/02) | 14 Feb 2024 | ST69 |  | BC cutter teeth replacement and gear box maintenance
Wed (14/02) | 14 Feb 2024 | ST168 |  | Trenching resume
Wed (14/02) | 14 Feb 2024 | ST166A pre boring |  | Hydraulic hose burst, repair works in progress
Wed (14/02) | 14 Feb 2024 | Zone 4 |  | ULT12, pre boring completed and casing installed
Wed (14/02) | 14 Feb 2024 | BC cutter-2 |  | Continue repairing. Prepare to install rubber hose for cooling system. Tomorrow plan to do trial run. Still have some parts to replace
Wed (14/02) | 14 Feb 2024 | Exit 3 |  | Preparation works ongoing for fissure grouting works. To start today
Wed (14/02) | 14 Feb 2024 | MH1-2 |  | Continue excavation for the next layer caisson
Wed (14/02) | 14 Feb 2024 | Near exit 2 |  | Marking of guidewall alignment for ST191-194 before trial trench works
Wed (14/02) | 14 Feb 2024 | JTC blk 2 |  | Crane rectification ongoing
Wed (14/02) | 14 Feb 2024 | ST166A |  | Continue preboring
Wed (14/02) | 14 Feb 2024 | ST168 |  | First bite excavation in progress, 17.5m
Thu (15/02) | 15 Feb 2024 | Zone 4 |  | Lane close for sppg work
Thu (15/02) | 15 Feb 2024 | Zone 4 ULT12 |  | Prep works ongoing prior preboring
Thu (15/02) | 15 Feb 2024 | Zone 4 |  | GCE demobilising excavator to shift to zone 3
Thu (15/02) | 15 Feb 2024 | Zone 4 |  | WH and Starhub currently discussing on the pipe alignment
Thu (15/02) | 15 Feb 2024 | ST69 |  | Endplate removal ongoing
Thu (15/02) | 15 Feb 2024 | ST168 |  | Cutter teeth changing in progress. First bite current depth at 18.1m
Thu (15/02) | 15 Feb 2024 | ST191-192 |  | Guidewall excavation
Thu (15/02) | 15 Feb 2024 | Exit 3 |  | Drilling ongoing for fissure grouting
Thu (15/02) | 15 Feb 2024 | MH5-2 |  | No more activity
Thu (15/02) | 15 Feb 2024 | MH1-2 |  | 17th layer to continue excavation for night shift. Current depth 800mm
Thu (15/02) | 15 Feb 2024 | Zone 1 |  | Biometrics secondary roof installation
Thu (15/02) | 15 Feb 2024 | ST48 |  | 1st bite excavation in progress
Thu (15/02) | 15 Feb 2024 | ST168 |  | Cutter wheel teeth replacement. Current depth 18.1m
Thu (15/02) | 15 Feb 2024 | ST69 |  | Desanding completed. Preparation for final Koden test
Thu (15/02) | 15 Feb 2024 | ST191-192 |  | Guidewall excavation in progress
Thu (15/02) | 15 Feb 2024 | BH125 |  | In progress, 32m
Thu (15/02) | 15 Feb 2024 | ST168 |  | Centre holder welding and rectification ongoing. First bite current depth at 17.9m
Thu (15/02) | 15 Feb 2024 | ST166A |  | Continue preboring
Fri (16/02) | 16 Feb 2024 | ST166A |  | Continue preboring
Fri (16/02) | 16 Feb 2024 | P44 |  | GCE continue coring for ACR1
Fri (16/02) | 16 Feb 2024 | Exit 3 |  | Pre-lugeon test for point O-24 in progress
Fri (16/02) | 16 Feb 2024 | Exit 3 |  | Trial Fissure Grout works, Started 15 Feb, *In progress*:, Soil side (O)- 1/5nos, *Completed*:, Soil side (O)- 0/5, D-wall side (I)- 0/5, Total- 0/10
Fri (16/02) | 16 Feb 2024 | Zone 2 |  | WH trial trench for Singtel NCE application. Manpower 1+3, 1 excavator
Fri (16/02) | 16 Feb 2024 | Zone 4 |  | Slow lane closed for SPPG pipe laying
Fri (16/02) | 16 Feb 2024 | O-24 |  | Bottom pre-lugeon test done. Now preparing for middle section
Fri (16/02) | 16 Feb 2024 | P26 area |  | Ley Choon open pit for SPPG cable works
Fri (16/02) | 16 Feb 2024 | MH5-2 |  | Pipe jacking works in progress, pipe no. 31
Fri (16/02) | 16 Feb 2024 | ST67 |  | Trenching temporarily stopped due to slope side of the adjacent ECM pond collapsed. Current first bite is 7m depth
Fri (16/02) | 16 Feb 2024 | ST69 |  | Water stop installation
Fri (16/02) | 16 Feb 2024 | MH2-4 |  | HDPE lining works in progress
Fri (16/02) | 16 Feb 2024 | Exit 3 | Seongha | Fissure grout area O-24 pre lugeon test completed. Now preparing to install PVC pipes
Fri (16/02) | 16 Feb 2024 | St168 |  | 1st bite trenching continue, 27m depth
Fri (16/02) | 16 Feb 2024 | ST69 |  | Top cage lapping in progress
Fri (16/02) | 16 Feb 2024 | ST48 |  | BC cutter teeth maintenance
Fri (16/02) | 16 Feb 2024 | P14-5 |  | Rebar lowered down. Concrete ordered
Fri (16/02) | 16 Feb 2024 | P13-5 |  | Preparing for casing installatio
Fri (16/02) | 16 Feb 2024 | MH5-2 |  | Pipe No-34 jacking in progress
Fri (16/02) | 16 Feb 2024 | MH1-2 |  | Excavation in progress for next layer
Fri (16/02) | 16 Feb 2024 | MH2-8 |  | Brick work for manhole cover
Fri (16/02) | 16 Feb 2024 | Zone 3 CCW |  | TT for king post BP done for the day. Backfilling in progress
Fri (16/02) | 16 Feb 2024 | Zone 2 P17-20 |  | Premix hacking for DIC and drop inlet pipe installation status. CGS plan to mob in 1 more excavator to facilitate hacking
Fri (16/02) | 16 Feb 2024 | P13-5 |  | Setting rig for boring works tomorrow
Fri (16/02) | 16 Feb 2024 | P14-5 |  | Casting started. Est vol 39m3
Fri (16/02) | 16 Feb 2024 | MH5-2 |  | No activity observed for night shift
Fri (16/02) | 16 Feb 2024 | Zone 1 |  | Singtel here for cable pulling
Fri (16/02) | 16 Feb 2024 | MH1-2 |  | Tonight plan to complete excavation for 17th layer and start rebar installation
Fri (16/02) | 16 Feb 2024 | ST67 |  | Pre-excavation on going
Fri (16/02) | 16 Feb 2024 | ST168 |  | 1st bite trenching continue
Fri (16/02) | 16 Feb 2024 | ST48 |  | 2nd bite temporarily stopped. Bolt rectification ongoing
Fri (16/02) | 16 Feb 2024 | Exit 2 |  | Preparation for guidewall works for ST191-192 (half)
Fri (16/02) | 16 Feb 2024 | ST168 |  | Continue first bite trenching, 18.6m
Fri (16/02) | 16 Feb 2024 | MH2-3 |  | Handrail/netting installation CCTV monitoring
Fri (16/02) | 16 Feb 2024 | MH2-4 |  | HDPE lining works
Sat (17/02) | 17 Feb 2024 | PBH-38 |  | SI drilling in progress, depth 24m
Sat (17/02) | 17 Feb 2024 | ST34 |  | Excavation for guide wall construction ongoing. Manpower 4+1
Sat (17/02) | 17 Feb 2024 | Blk 2 - ST048 | SC40#01 | Trimming in progress (ST048A side) for endplate removal
Sat (17/02) | 17 Feb 2024 | Blk 4 - ST067 | SC40#02 | 1st bite excavation in progress, current depth 4m/30.86m
Sat (17/02) | 17 Feb 2024 | Selarang Camp - ST168 | MC96 | Cutter teeth changing in progress. 1st bite excavation current depth - 19.9m
Sat (17/02) | 17 Feb 2024 | Zone 4 |  | Lane closed for SPPG pipe laying
Sat (17/02) | 17 Feb 2024 | Zone 3, JGP Area |  | Casing installation in progress for JGP coring point (A-CR2)
Sat (17/02) | 17 Feb 2024 | Zone 4 |  | ULT12 rebar cage installation. HSL will extend work tonight until ULT cast. Target to cast by 12mn
Sat (17/02) | 17 Feb 2024 | Zone 4, ULT-12, P48 |  | Boring works completed. Now preparing for Desanding works. Today will cast
Sat (17/02) | 17 Feb 2024 | Zone 4, P50-P51 |  | Excavation in progress for StarHub pipe laying works
Sat (17/02) | 17 Feb 2024 | MH1-2 |  | Dewatering & BRC laying in progress for 17th layer, manpower 6+1
Sat (17/02) | 17 Feb 2024 | MH5-2 |  | Pipe jacking no. 35 in progress
Sat (17/02) | 17 Feb 2024 | ST43 |  | Trenching in progress
Sat (17/02) | 17 Feb 2024 | ST48 |  | Chiselling on going
Sat (17/02) | 17 Feb 2024 | ST67 |  | Pre-excavation completed. BC cutter operator now at ST48 for chiselling. Will start ST67 once ST48 completed
Sat (17/02) | 17 Feb 2024 | MH1-2 |  | Excavation completed. Soil disposal in progress
Sat (17/02) | 17 Feb 2024 | Exit 3 | FG O-28 | Drilling completed, Pre-lugeon test in progress
Sat (17/02) | 17 Feb 2024 | MH2-7 |  | HDPE lining work in progress
Sat (17/02) | 17 Feb 2024 | PBH-38 |  | SI drilling in progress, depth 30m
Sat (17/02) | 17 Feb 2024 | ST34 |  | Continue Excavation for guide wall construction ongoing
Sat (17/02) | 17 Feb 2024 | Blk 2 - ST048 | SC40#01 | Trimming in progress (ST047 side) for endplate removal. Work temporarily stopped due to hydraulic hose leak. Repairing in progress
Sat (17/02) | 17 Feb 2024 | Blk 4 - ST067 | SC40#02 | 1st bite excavation in progress, current depth 16m
Sat (17/02) | 17 Feb 2024 | Selarang Camp - ST168 | MC96 | 1st bite excavation ongoing, current depth - 20.4m
Sat (17/02) | 17 Feb 2024 | Zone 3, JGP Area |  | Coring in progress for JGP point (A-CR2). Current depth 11m
Sat (17/02) | 17 Feb 2024 | Zone 4 ULT-12 |  | 1st rebar cage lowering in progress
Sat (17/02) | 17 Feb 2024 | P8-2 |  | KTC compaction works completed, NDT arranged at 5.30pm
Sat (17/02) | 17 Feb 2024 | MH1-2 |  | 17th layer brc installation completed, now installing formworks
Sat (17/02) | 17 Feb 2024 | Zone 1 |  | LECE preboring for steel plates in progress
Sat (17/02) | 17 Feb 2024 | Zone 1 | NLL | 8ways traffic light pipe laying completed. Reinstatement ongoing
Sat (17/02) | 17 Feb 2024 | P13-5 |  | HSL rebar cage lowering for BP
Sat (17/02) | 17 Feb 2024 | Guidewall ST01& ST02 half |  | Preparing for backfill works
Sat (17/02) | 17 Feb 2024 | Zone 3 |  | Lean con on going for temporary desander platform
Sat (17/02) | 17 Feb 2024 | P13-5 |  | Casting in progress
Sat (17/02) | 17 Feb 2024 | Zone 2 |  | CGS hacking works for DIC and DIP done for the day
Sat (17/02) | 17 Feb 2024 | Zone 1 NLL |  | Cast Concrete along fast lane still curing. Plan to open around 11pm
Sat (17/02) | 17 Feb 2024 | MH1-2 |  | Existing sewer pipe support installation. 17th layer moulding closed, waiting for concrete lorry
Sat (17/02) | 17 Feb 2024 | ST48 |  | End plate extraction
Sat (17/02) | 17 Feb 2024 | ST168 |  | 1st bite trenching continue
Sat (17/02) | 17 Feb 2024 | Seongha - Exit 3 |  | FG #O-26, Lugeon test at bottom layer & FG #O-28 drilling works in progress
Sun (18/02) | 18 Feb 2024 | MH2-5 |  | Pipe No-35 jacking done. Lowering pipe No-36
Sun (18/02) | 18 Feb 2024 | Zone-1 |  | Soldier piles joint welding
Sun (18/02) | 18 Feb 2024 | MH2-8 to MH2-7 |  | Preparing for CCTV inspection
Sun (18/02) | 18 Feb 2024 | MH1-2 |  | 17th layer casting completed
Sun (18/02) | 18 Feb 2024 | ST48 |  | Cleaning in progress
Sun (18/02) | 18 Feb 2024 | ST67 |  | 1st bite trenching continue
Sun (18/02) | 18 Feb 2024 | ST168 |  | 1st bite trenching continue, very hard rock
Sun (18/02) | 18 Feb 2024 | ULT12 |  | Cage lowering still in progress
Sun (18/02) | 18 Feb 2024 | MH2-6 to MH2-7 - CCTV done. MH2-7 to MH2-8 |  | To continue tomorrow
Sun (18/02) | 18 Feb 2024 | MH1-2 |  | Continue excavation in progress
Sun (18/02) | 18 Feb 2024 | Zone 1 |  | LE welding of soldier piles joints
Sun (18/02) | 18 Feb 2024 | MH5-2 |  | Pipe Jacking in progress. *Note- completed jacking number is Pipe No-37. Now lowering down pipe No-38. Number on pipe is old one. Need to rewrite. FYI*
Sun (18/02) | 18 Feb 2024 | MH2-8 |  | LCH already end work
Sun (18/02) | 18 Feb 2024 | Zone 4 ULT12 |  | Tremie pipes installation for casting. Concrete ordered
Mon (19/02) | 19 Feb 2024 | ST67 |  | First bite excavation temporarily on hold. Cutter teeth wheel & centre holder rectification ongoing
Mon (19/02) | 19 Feb 2024 | ST67 |  | First bite depth ard 30.5m
Mon (19/02) | 19 Feb 2024 | ST168 |  | Cutter teeth wheel changing ongoing
Mon (19/02) | 19 Feb 2024 | Zone 4 LP105 | towards LW | Tonight Wee Guan to continue backfilling and premix reinstatement works. Shoring removal ongoing
Mon (19/02) | 19 Feb 2024 | ST168 |  | Resume first bite excavation
Mon (19/02) | 19 Feb 2024 | ST43 |  | First bite temporarily on hold. Cutter teeth changing ongoing. Current depth 33.4m
Mon (19/02) | 19 Feb 2024 | Zone 1 |  | Excavation to exposed LT cables for localised shifting. Today LE plan to settle this
Mon (19/02) | 19 Feb 2024 | MH1-2 |  | 18th layer excavation in progress, current depth 0.4m. Target to cast tmr
Mon (19/02) | 19 Feb 2024 | Loyang Ave-PRD3 |  | Pipe laying for traffic light completed, 4.7m. Team 2. Reinstatement in progress
Mon (19/02) | 19 Feb 2024 | Zone 2 |  | Road kerb raised up casting in progress. 24m
Mon (19/02) | 19 Feb 2024 | Exit 3 |  | FG #O-27, Pre Lugeon test at top layer has started. Started at 2 Bars, 5Bars, 8bars,10bars at 5mins holding time each sequence
Mon (19/02) | 19 Feb 2024 | Zone 3 |  | Lucky joint here grouting old M1 pipes
Mon (19/02) | 19 Feb 2024 | Exit 3 |  | TT continue for Fissure grouting. DW6-10 completed
Mon (19/02) | 19 Feb 2024 | Zone 2 |  | Hardcore removal for DIC installation. Tomorrow CGS will start to install DIC
Mon (19/02) | 19 Feb 2024 | P12-5 |  | Rebar cage installation on going
Mon (19/02) | 19 Feb 2024 | ST34 |  | Guidewall completed yesterday. Backfilling done. Plan to start here this week
Mon (19/02) | 19 Feb 2024 | ST43 |  | BC cutter replacement still in progress
Mon (19/02) | 19 Feb 2024 | ST181 |  | Pre-boring to continue till 10pm
Mon (19/02) | 19 Feb 2024 | Zone 2 |  | CGS manual hacking & hardcore clearing. Works till 10pm
Mon (19/02) | 19 Feb 2024 | Zone 2 |  | Lean con casting at centre median by WH
Mon (19/02) | 19 Feb 2024 | P12-5 |  | Casting in progress
Mon (19/02) | 19 Feb 2024 | MH5-2 |  | No activity. Tonight LCH working at MH1-2
Mon (19/02) | 19 Feb 2024 | MH1-2 |  | Tonight continue 18th layer excavation
Tue (20/02) | 20 Feb 2024 | P14-4 |  | Casting completed
Tue (20/02) | 20 Feb 2024 | ST43 |  | Cutter teeth changing ongoing. Current first bite depth at 36.8m
Tue (20/02) | 20 Feb 2024 | ST168 |  | 2nd bite completed, 23m. Now cutter teeth changing
Tue (20/02) | 20 Feb 2024 | MH5-2 |  | Existing MH wall came in contact at 41st pipe. Now LCH preparing to do wall hacking at existing sewer shaft
Tue (20/02) | 20 Feb 2024 | Zone 4 HSL |  | ULT3 boring ongoing
Tue (20/02) | 20 Feb 2024 | ST67 |  | Cutter wheel changing ongoing
Tue (20/02) | 20 Feb 2024 | ST168 |  | 3rd bite excavation started
Tue (20/02) | 20 Feb 2024 | Zone 1 |  | CGS team 1 for traffic light pipe laying
Tue (20/02) | 20 Feb 2024 | Zone 1 |  | CGS team 2 for traffic light pipe laying. Plan to lay 3m here today
Tue (20/02) | 20 Feb 2024 | P8-2 |  | Backfilling to column stump level completed
Tue (20/02) | 20 Feb 2024 | P9-10 |  | Backfilling to column stump level completed
Tue (20/02) | 20 Feb 2024 | P10-2 |  | Waler beam dismantling. Manpower, 3+1
Tue (20/02) | 20 Feb 2024 | Zone 1 along PDR3 |  | Lucky joint here for Sptel cable recovery
Tue (20/02) | 20 Feb 2024 | ST93-94 |  | Drain removal for TT
Tue (20/02) | 20 Feb 2024 | Exit 2 |  | Ley choon to excavate trench all the way to just before the substation/pumping mains and excavate another pulling pit
Tue (20/02) | 20 Feb 2024 | Exit 2 |  | Another Sppg pulling pit at this area where all the slack will be coiled
Tue (20/02) | 20 Feb 2024 | Zone 4 |  | Premix reinstatement in progress
Tue (20/02) | 20 Feb 2024 | Gate 5 |  | Ley choon has exposed the existing 22kV (red) and 6.6kV (green) cables. Pending SPPG to come for cable ID
Tue (20/02) | 20 Feb 2024 | Gate 5 |  | M1 grouting old pipes
Tue (20/02) | 20 Feb 2024 | Exit 3 I25 fissure grout |  | Drilling completed. Now checking the depth
Tue (20/02) | 20 Feb 2024 | P10-2v |  | Waler beam dismantling continue
Tue (20/02) | 20 Feb 2024 | ST168 |  | Cutter teeth replacement ongoing
Tue (20/02) | 20 Feb 2024 | ST67 |  | First bite excavation in progress
Tue (20/02) | 20 Feb 2024 | ST43 |  | First bite excavation in progress
Tue (20/02) | 20 Feb 2024 | P14-4 |  | Boring completed. Now preparation for rebar cage installation
Tue (20/02) | 20 Feb 2024 | Zone 2 |  | Hacking for DIC and drop inlet pipe continue
Tue (20/02) | 20 Feb 2024 | MH1-2 |  | Continue 18th layer soil disposal and manual trimming
Tue (20/02) | 20 Feb 2024 | P14-4 |  | Preparing tremie pipe for casting
Tue (20/02) | 20 Feb 2024 | MH1-2 |  | Excavation for the next layer caisson. Tonight target to cast
Tue (20/02) | 20 Feb 2024 | Exit 3 |  | Netting installation for newly diverted access
Tue (20/02) | 20 Feb 2024 | Zone 2 |  | Hardcore removal for DIC works. Works till 10pm
Tue (20/02) | 20 Feb 2024 | P14-4 |  | Casting ongoing
Tue (20/02) | 20 Feb 2024 | Zone 1 LA | towards PRD3 | Lane closure by CGS for traffic light pipe laying. Plan ard 4m to lay tonight
Tue (20/02) | 20 Feb 2024 | PRD3 | towards NLL | Lane closure by CGS for pipe laying. Plan ard 4m to lay tonight. Premix removal ongoing
Tue (20/02) | 20 Feb 2024 | MH1-2 |  | Formwork installation ongoing for 18th layer
Wed (21/02) | 21 Feb 2024 | ST67 |  | 2nd bite excavation in progress
Wed (21/02) | 21 Feb 2024 | Zone 3 |  | M1 grouting of old pipes
Wed (21/02) | 21 Feb 2024 | Zone 2 P18-19 |  | Raised road kerb formwork closing
Wed (21/02) | 21 Feb 2024 | ST-178- PB2 |  | Coring reached 22.67m/25.1m
Wed (21/02) | 21 Feb 2024 | LA towards PRD3 |  | Premix reinstatement ongoing
Wed (21/02) | 21 Feb 2024 | MH1-2 |  | Casting in progress
Wed (21/02) | 21 Feb 2024 | Zone 3 near JTC |  | Leychoon cable pulling pit (CPP19) shoring ongoing
Wed (21/02) | 21 Feb 2024 | Zone 3 |  | Trenching by Leychoon from CPP20 towards substation still in progress
Wed (21/02) | 21 Feb 2024 | Zone 2 |  | Pumping mains or ecm pipe leaking near Mh2-4. Have informed Mr Lee
Wed (21/02) | 21 Feb 2024 | Zone 1 |  | LCH doing site survey and preparing for wall hacking at existing sewer shaft
Wed (21/02) | 21 Feb 2024 | P13-4 |  | Boring works completed. Preparation for rebar cage installation
Wed (21/02) | 21 Feb 2024 | P12-4 |  | Working platform preparation for boring works tomorrow
Wed (21/02) | 21 Feb 2024 | Zone 1 |  | 3 locations for traffic light pipe now premix laying. 2 lane opened
Wed (21/02) | 21 Feb 2024 | Zone 1 |  | LT cable localise shifting adjusting to accommodate steel plate protection. This area to start pre-boring tomorrow
Wed (21/02) | 21 Feb 2024 | ST168 |  | 3rd bite excavation in progress
Wed (21/02) | 21 Feb 2024 | ST181 |  | LSS backfilling for preboring. ST178- boring reached 24.78m
Wed (21/02) | 21 Feb 2024 | Zone 4 |  | HSL works done for the night. Housekeeping ongoing
Wed (21/02) | 21 Feb 2024 | ST43 |  | First bite excavation completed, 37.2m. Cutter teeth changing ongoing
Wed (21/02) | 21 Feb 2024 | ST67 |  | Cutter wheel replacement ongoing
Wed (21/02) | 21 Feb 2024 | P9-2 |  | ERSS extraction on going
Wed (21/02) | 21 Feb 2024 | MH1-2 |  | Continue excavation for the base
Wed (21/02) | 21 Feb 2024 | MH5-2 |  | Shifting of materials for hacking at Zone 1 side
Wed (21/02) | 21 Feb 2024 | P13-4 |  | Concrete on the way
Wed (21/02) | 21 Feb 2024 | P12-4 |  | Casing installation in progress
Wed (21/02) | 21 Feb 2024 | P24 |  | Trial trench for BP done for the day. Housekeeping ongoing
Wed (21/02) | 21 Feb 2024 | P13-4 |  | Casting completed
Wed (21/02) | 21 Feb 2024 | S3 |  | Column stump formwork closing ongoing
Wed (21/02) | 21 Feb 2024 | Zone 1 |  | WH continue backfilling works
Wed (21/02) | 21 Feb 2024 | MH1-2 |  | Tonight continue base slab excavation
Wed (21/02) | 21 Feb 2024 | Zone 1 junction |  | No activity tonight
Wed (21/02) | 21 Feb 2024 | ST43 |  | Bite 2 excavation temporarily stopped for gear box changing & oil pumping. Current depth at 6.2m
Wed (21/02) | 21 Feb 2024 | ULT3 |  | Boring continue. Last depth check was 21.9m
Thu (22/02) | 22 Feb 2024 | Seongha - Exit 3 |  | FG #I-24, Casing installed & Pre Lugeon test completed. Now preparing to lower grouting pipe. Manpower - 13
Thu (22/02) | 22 Feb 2024 | MH1-2 |  | Continue excavation and prepare BRC for slab
Thu (22/02) | 22 Feb 2024 | MH1-2 |  | 1nos cage ladder was installed
Thu (22/02) | 22 Feb 2024 | ST43 |  | Resume 2nd bite excavation
Thu (22/02) | 22 Feb 2024 | ST168 |  | Pump installed at the toe level of the trenching. Circulation in progress
Thu (22/02) | 22 Feb 2024 | Exit 3 FG I22 |  | Grouting pipe installation completed, now removing the casing. Tmr they will start the grouting works for the trial FG
Thu (22/02) | 22 Feb 2024 | ST67 |  | Trimming in progress
Thu (22/02) | 22 Feb 2024 | ST34 |  | Platform preparation
Thu (22/02) | 22 Feb 2024 | P12-4 |  | Rebar cages fully lowered. Preparation works in progress for casting
Thu (22/02) | 22 Feb 2024 | ULT3 |  | Current depth at 29.7m
Thu (22/02) | 22 Feb 2024 | MH1-2 |  | Continue base hacking and excavation
Thu (22/02) | 22 Feb 2024 | ST43 |  | Bite 2 excavation temporarily stopped. Current depth at 17.4m. Hydraulic issue for the cutter body flap
Fri (23/02) | 23 Feb 2024 | PBH15 |  | Completed. Pending confirmation of termination depth
Fri (23/02) | 23 Feb 2024 | P44 |  | GCE preparing for A-SPT1 stage 2 SPT works
Fri (23/02) | 23 Feb 2024 | Zone 4 Gate 9 |  | Today Starhub plan for pipe laying, 18m
Fri (23/02) | 23 Feb 2024 | ULT3 |  | Tremie pipe installation ongoing
Fri (23/02) | 23 Feb 2024 | ST168 |  | Cutter teeth replacement ongoing
Fri (23/02) | 23 Feb 2024 | ST43 |  | Cutter wheel changing ongoing
Fri (23/02) | 23 Feb 2024 | Exit 3 |  | Trial fissure grouting points pending grouting works
Fri (23/02) | 23 Feb 2024 | PBH36 |  | Trial trench in progress
Fri (23/02) | 23 Feb 2024 | ST43 |  | 2nd bite excavation in progress
Fri (23/02) | 23 Feb 2024 | ST168 |  | Cutter teeth changing ongoing. 3rd bite current depth at 21.4m
Fri (23/02) | 23 Feb 2024 | ULT3 |  | Casting
Fri (23/02) | 23 Feb 2024 | Zone 2 slip road |  | Re-levelling works in progress. Plan to start base course here next Monday
Fri (23/02) | 23 Feb 2024 | Zone 1 |  | 1 no. Solider pile installed. Now reinstatement works to reopen the lane
Fri (23/02) | 23 Feb 2024 | MH1-2 |  | Continue base slab excavation works. Target to cast tonight
Fri (23/02) | 23 Feb 2024 | Zone 2 |  | Raised slab formwork closing and rebar installation for linkway
Fri (23/02) | 23 Feb 2024 | P9-2 |  | ERSS extraction completed
Fri (23/02) | 23 Feb 2024 | ST43 |  | 2nd bite excavation completed. Preparation for trimming at end plate side
Fri (23/02) | 23 Feb 2024 | ST67 |  | 2nd bite cleaning in progress
Fri (23/02) | 23 Feb 2024 | ST168 |  | Cutter wheel teeth replacement
Fri (23/02) | 23 Feb 2024 | Zone 3 P44 |  | TT completed for SPT2. No utility found. Backfilling in progress
Fri (23/02) | 23 Feb 2024 | Exit 2 |  | WH excavation and pipe laying of 150 dia. from existing sump pump to sewer manhole
Fri (23/02) | 23 Feb 2024 | PBH39 |  | In progress
Fri (23/02) | 23 Feb 2024 | ST192 -ST193 | half | Guidewall cast yesterday
Sat (24/02) | 24 Feb 2024 | MH1-2 |  | Base slab rebar work in progress
Sat (24/02) | 24 Feb 2024 | Substation at CR107 |  | Wee Guan laying power duct in progress. Today to complete duct laying
Sat (24/02) | 24 Feb 2024 | Zone 4 |  | No activity of other contractor
Sun (25/02) | 25 Feb 2024 | Zone 2 P16 |  | Formwork installation for road kerb
Sun (25/02) | 25 Feb 2024 | Zone 2 |  | WH excavation for temp water pipe diversion
Sun (25/02) | 25 Feb 2024 | ST192-193 |  | Guidewall backfilling
Sun (25/02) | 25 Feb 2024 | Zone 4 |  | Starhub plan for 9m pipe laying today
Sun (25/02) | 25 Feb 2024 | Zone 4 |  | HSL no activity
Sun (25/02) | 25 Feb 2024 | ST168 |  | Cutter wheel rectification ongoing
Sun (25/02) | 25 Feb 2024 | ST69A |  | Cutter teeth changing ongoing
Sun (25/02) | 25 Feb 2024 | ST43 |  | Trimming completed
Sun (25/02) | 25 Feb 2024 | ST182-ST183 |  | Guidewall rebar works ongoing
Sun (25/02) | 25 Feb 2024 | ST168 |  | Hanging bar u-clip inspection done
Sun (25/02) | 25 Feb 2024 | ST168 |  | Bite 2 cleaning ongoing
Sun (25/02) | 25 Feb 2024 | ST69A |  | First bite in progress
Sun (25/02) | 25 Feb 2024 | ST43 |  | Continue trimming at WS ST42 side
Sun (25/02) | 25 Feb 2024 | MH1-2 |  | Base slab rebar work in progress
Sun (25/02) | 25 Feb 2024 | Gate 5 |  | Preparing for washing bay cleaning
Sun (25/02) | 25 Feb 2024 | Zone 2 |  | CGS plan for scupper pipe installation
Sun (25/02) | 25 Feb 2024 | Zone 2 |  | HSL no activity
Sun (25/02) | 25 Feb 2024 | MH1-2 |  | Permanent MH base slab rebar works in progress. Plan for casting this afternoon
Sun (25/02) | 25 Feb 2024 | Zone 1 |  | LCH hacking of existing sewer manhole in progress
Sun (25/02) | 25 Feb 2024 | Zone 1 |  | No other activity
Mon (26/02) | 26 Feb 2024 | P12-6 |  | Boring works completed..preparation for rebar cage installation
Mon (26/02) | 26 Feb 2024 | Zone 2 P16-15 |  | Raised kerb formwork closing, plus 20 length
Mon (26/02) | 26 Feb 2024 | Zone 2, CGS team 2 |  | Drop inlet pipe installation in progress
Mon (26/02) | 26 Feb 2024 | Zone 3 between MH2-1 to MH2-3 |  | Water pipe flange rectification by Krishco
Mon (26/02) | 26 Feb 2024 | P12-6 |  | Preparing for casting
Mon (26/02) | 26 Feb 2024 | MH1-2 |  | Current status of scaffold work by woh hup
Mon (26/02) | 26 Feb 2024 | Zone 2 |  | Road kerb formwork installation ongoing
Mon (26/02) | 26 Feb 2024 | P12-6 |  | Casting in progress
Mon (26/02) | 26 Feb 2024 | Zone 1 |  | CGS clearing materials. No night work for the night
Mon (26/02) | 26 Feb 2024 | MH1-2 |  | WH continue scaffold erection till 10pm. Thereafter LCH night team to continue rebar works
Mon (26/02) | 26 Feb 2024 | Zone 1 |  | No other activities
Mon (26/02) | 26 Feb 2024 | ST43 |  | Continue trimming at WS side (ST42)
Mon (26/02) | 26 Feb 2024 | ST69A |  | First bite excavation temporarily stopped. Gear box and motor installation ongoing
Mon (26/02) | 26 Feb 2024 | Zone 4 |  | WG to rectify the traffic island tactile area tonight
Mon (26/02) | 26 Feb 2024 | Zone 4 LA | towards LW | Lane closure by WG
Mon (26/02) | 26 Feb 2024 | Zone 4 |  | No other activity tonight
Tue (27/02) | 27 Feb 2024 | ST165 |  | Resume 2nd bite excavation
Tue (27/02) | 27 Feb 2024 | Zone 2 South bound side |  | Extension of footh path rebar and formwork closing
Tue (27/02) | 27 Feb 2024 | Zone 2 North bound side |  | Area preparation for foothpath construction
Tue (27/02) | 27 Feb 2024 | Zone 2 South bound side |  | Formwork close for road kerb casting
Tue (27/02) | 27 Feb 2024 | P13-6 |  | Casting completed
Tue (27/02) | 27 Feb 2024 | P13-6 |  | Boring completed. Now preparing to lower rebar cages
Tue (27/02) | 27 Feb 2024 | ST43 |  | Continue trimming
Tue (27/02) | 27 Feb 2024 | ST168 |  | Rebar cages were extracted. Bite 2 cleaning ongoing
Tue (27/02) | 27 Feb 2024 | Zone 4 |  | Tactiles rectified. Lane reopened
Tue (27/02) | 27 Feb 2024 | ST69A |  | First bite excavation in progress
Tue (27/02) | 27 Feb 2024 | P13-6 |  | Rebar cage lowering in progress
Tue (27/02) | 27 Feb 2024 | MH1-2 |  | Outer ring rebar installation in progress
Tue (27/02) | 27 Feb 2024 | Exit 3 |  | Platform preparation for the next drilling for fissure grouting works
Tue (27/02) | 27 Feb 2024 | P25-P26 |  | Krishco here for flange replacement
Tue (27/02) | 27 Feb 2024 | ST43 |  | Rebar cage lowering in progress, 3/8 completed
Tue (27/02) | 27 Feb 2024 | ST194 half |  | Guidewall formwork closed. Waiting for concrete lorry to cast
Tue (27/02) | 27 Feb 2024 | ST182 and 183 |  | Final inspection done. Waiting for concrete lorry to cast
Tue (27/02) | 27 Feb 2024 | ST180 |  | Pre-boring works until 10pm
Tue (27/02) | 27 Feb 2024 | ST66 |  | Chiselling at water stop side on going
Tue (27/02) | 27 Feb 2024 | ST165 |  | 1st bite excavation continue
Tue (27/02) | 27 Feb 2024 | ST168 |  | All Tremie pipes lowered for casting
Tue (27/02) | 27 Feb 2024 | ST34 |  | BC cutter maintenance prior to start trenching
Tue (27/02) | 27 Feb 2024 | MH2-8 |  | LCH completed work for the day. Housekeeping
Tue (27/02) | 27 Feb 2024 | Zone 2 new slip rd |  | Current status of soil levelling works
Tue (27/02) | 27 Feb 2024 | Zone 2 |  | Footpath rebar and formwork installation in progress
Tue (27/02) | 27 Feb 2024 | P13-6 |  | Pending to cast
Tue (27/02) | 27 Feb 2024 | MH1-2 |  | WH continue to erect scaffold access till 10pm. Thereafter LCH to continue wall rebar installation
Tue (27/02) | 27 Feb 2024 | Zone 1 |  | No other activity
Tue (27/02) | 27 Feb 2024 | ST43 |  | Rebar cage lapping in progress, 4/8nos
Tue (27/02) | 27 Feb 2024 | ST168 |  | Casting in progress, 17.5/150m3
Tue (27/02) | 27 Feb 2024 | Loyang Way LP23/1F |  | WG reinstatement works for road kerb at centre median
Wed (28/02) | 28 Feb 2024 | Zone 2 slip road |  | Subgrade backfilling started. 3 loads backfilled so far
Wed (28/02) | 28 Feb 2024 | ST168 |  | Casting completed at 0205hrs. Total vol: 197m3
Wed (28/02) | 28 Feb 2024 | ST43 |  | Rebar cage installation in progress, 7/8nos
Wed (28/02) | 28 Feb 2024 | ST69A |  | First bite excavation in progress
Wed (28/02) | 28 Feb 2024 | Zone 2 CGS |  | Continue excavation & trial trench for DIC installation
Wed (28/02) | 28 Feb 2024 | ST182 & ST183 |  | Guidewall was cast last evening
Wed (28/02) | 28 Feb 2024 | ST194 | half | Guidewall was cast last evening
Wed (28/02) | 28 Feb 2024 | Zone 1 |  | Continue hacking of existing sewer MH. Works till 10pm
Wed (28/02) | 28 Feb 2024 | MH1-2 |  | Night team continue centre wall rebar installation
Wed (28/02) | 28 Feb 2024 | Zone 1 |  | No other activity
Wed (28/02) | 28 Feb 2024 | ST165 |  | 3rd bite excavation in progress
Wed (28/02) | 28 Feb 2024 | Loyang Way LP23/1F |  | WG to cast road kerb. Waiting for concrete lorry
Wed (28/02) | 28 Feb 2024 | ST69A |  | First bite excavation in progress
Thu (29/02) | 29 Feb 2024 | ST69A |  | Continue first bite excavation
Thu (29/02) | 29 Feb 2024 | Exit 2 |  | PBH52 completed. Depth terminated at 42.5m. The team will continue hand auger for PBH50
Thu (29/02) | 29 Feb 2024 | PBH45 |  | Trial trench in progress
Thu (29/02) | 29 Feb 2024 | ST69A |  | 1st bite trenching continue
Thu (29/02) | 29 Feb 2024 | ST34 |  | Rectification works ongoing
Thu (29/02) | 29 Feb 2024 | PBH34 |  | SPT in progress
Thu (29/02) | 29 Feb 2024 | ST165 |  | Desanding on going
Thu (29/02) | 29 Feb 2024 | P9-2 |  | WH Slope protection concrete casting & levelling in progress. Manpower 3+1
Thu (29/02) | 29 Feb 2024 | Exit 3 |  | Fissure grout point O-32 drilling in progress
Thu (29/02) | 29 Feb 2024 | Zone 2 |  | HSL materials shifting to CCW
Thu (29/02) | 29 Feb 2024 | Zone 4 |  | Wee guan housekeeping only
Thu (29/02) | 29 Feb 2024 | PRD3 |  | Lane closure by CGS for premix rectification. Rectification works done by Road Builders
Thu (29/02) | 29 Feb 2024 | MH1-2 |  | Centre wall horizontal Rebar installation work in progress
Thu (29/02) | 29 Feb 2024 | ST165 |  | Trimming ongoing at waterstop side
Thu (29/02) | 29 Feb 2024 | ST69A |  | First bite in progress, 27.4m
Thu (29/02) | 29 Feb 2024 | MH1-2 |  | Formwork closing in progress
Thu (29/02) | 29 Feb 2024 | ST165 |  | Trimming ongoing at waterstop side (ST164)
Thu (29/02) | 29 Feb 2024 | Zone 2 | P19 | CGS excavation of existing center median for RCA backfilling works in progress. Manpower 2+1
Fri (01/03) | 01 Mar 2024 | Exit 3 |  | Fissure grout point O-18 drilling in progress. Today plan 3nos
Fri (01/03) | 01 Mar 2024 | PBH45 |  | Hand auger in progress
Fri (01/03) | 01 Mar 2024 | PBH50 |  | Preparing to start
Fri (01/03) | 01 Mar 2024 | ST69A |  | First bite excavation in progress
Fri (01/03) | 01 Mar 2024 | ST165 |  | Rebar cage installation ongoing, 6/10nos
Fri (01/03) | 01 Mar 2024 | ST89 |  | BC Cutter wire rope works ongoing
Fri (01/03) | 01 Mar 2024 | P43 |  | Trial trench for bored pile in progress
Fri (01/03) | 01 Mar 2024 | Zone 3 |  | Starhub plan for pipe laying (0.6m depth) on top of ST171
Fri (01/03) | 01 Mar 2024 | ST34 |  | 2nd bite excavation in progress
Fri (01/03) | 01 Mar 2024 | P25 near desander area |  | WH continue trial trench for bored pile
Fri (01/03) | 01 Mar 2024 | ST08 |  | Guidewall trial trench in progress
Fri (01/03) | 01 Mar 2024 | Zone 3/4 loyang way |  | Kerb painting works by wee Guan
Fri (01/03) | 01 Mar 2024 | ST69A |  | Cutter teeth wheel change ongoing
Fri (01/03) | 01 Mar 2024 | ST179 |  | LSS backfilling
Fri (01/03) | 01 Mar 2024 | ST165 |  | Rebar cage installation in progress, 8/10nos
Fri (01/03) | 01 Mar 2024 | Zone 2 |  | CGS Bus lane RCA backfilling & levelling in progress. As of now, 13 loads of RCA arrived. (Completed 25 loads/38 loads)
Fri (01/03) | 01 Mar 2024 | Zone 2 |  | CGS Formwork installation for footpath in progress, 24m. Target to cast 40m tmr
Fri (01/03) | 01 Mar 2024 | ST34 |  | BC cutter teeth replacement
Fri (01/03) | 01 Mar 2024 | Zone 2 |  | CGS continue hacking for DIC installation. Balance 2 nos for current available space
Fri (01/03) | 01 Mar 2024 | Zone 2 |  | CGS continue Formwork installation for road kerb casting
Fri (01/03) | 01 Mar 2024 | S3 |  | CGW Formwork dismantle completed for pile column stage 1
Fri (01/03) | 01 Mar 2024 | ST69A |  | BC cutter teeth replacement
Fri (01/03) | 01 Mar 2024 | ST165 |  | Desanding and final koden completed. Preparation for water stop lowering
Fri (01/03) | 01 Mar 2024 | PBH50, PBH44 and PBH45 |  | SI in progress
Fri (01/03) | 01 Mar 2024 | MH1-2 |  | Wall formwork closing. Target tonight casting
Fri (01/03) | 01 Mar 2024 | ST69A |  | 1st bite excavation resume
Fri (01/03) | 01 Mar 2024 | ST165 |  | 3rd rebar cage installation in progress
Fri (01/03) | 01 Mar 2024 | ST89 |  | 1st bite excavation started. Today, this BC cutter wire rope will be replaced
Fri (01/03) | 01 Mar 2024 | ST34 |  | Desander pump spoiled. Repair works in progress
Fri (01/03) | 01 Mar 2024 | ST69A |  | 1st bite trenching continue, current depth 28.7m. Revised toe level is 29.4m
Fri (01/03) | 01 Mar 2024 | ST165 |  | Hanging bar installation on going
Fri (01/03) | 01 Mar 2024 | ST89 |  | Hydraulic oil top up, once done they will resume trenching for 1st bite. Current depth 10m
Fri (01/03) | 01 Mar 2024 | Zone 1 | NLL side | Extension of junction at center islands subbase backfilling completed. CGS ending work. Housekeeping
Sat (02/03) | 02 Mar 2024 | Zone 4 B-SPT3 |  | GCE to drill till 2nd SPT today. Monday to start permeability test
Sat (02/03) | 02 Mar 2024 | ST33 |  | Cutter wheel drum maintenance
Sat (02/03) | 02 Mar 2024 | ST69A |  | 2nd bite trimming at WS side
Sat (02/03) | 02 Mar 2024 | ST89 |  | Cutter wheel teeth replacement. Current depth 30m
Sat (02/03) | 02 Mar 2024 | Zone 1 P3 |  | 2 nos. soldier piles to vibro down further. To also excavate the top layer of soil and after installation of instruments for excavation, to excavate till W1
Sat (02/03) | 02 Mar 2024 | Zone 1 Slip road |  | Hacking works for DIC installation
Sat (02/03) | 02 Mar 2024 | MH1-2 |  | HDPE and formwork installation continue. Looks like casting will be this afternoon due to the installation of water proofing membrane
Sat (02/03) | 02 Mar 2024 | ST69A |  | 1st bite trenching continue
Sat (02/03) | 02 Mar 2024 | ST165 |  | Tremie pipe installation
Sat (02/03) | 02 Mar 2024 | ST89 |  | Trenching resume for first bite
Sat (02/03) | 02 Mar 2024 | ST34 |  | Trenching resume
Sat (02/03) | 02 Mar 2024 | Zone 4 |  | Krishco backfilled the trial trench. They found the 300mm water pipe and starhub
Sat (02/03) | 02 Mar 2024 | ST89 |  | Gearbox motor replaced. B1 excavation resumed
Sat (02/03) | 02 Mar 2024 | Zone 4 |  | Breaking of hardcore into smaller pieces
Sat (02/03) | 02 Mar 2024 | Zone 4 |  | Starhub completed laying at this area
Sat (02/03) | 02 Mar 2024 | Zone 1 |  | Drilling for Inclinometer near P3 at 3m depth. Using plastic bit until 6m depth. Target to install by tmr afternnon. Followed by WSP by Mon
Sat (02/03) | 02 Mar 2024 | Zone 1 P3 |  | Soldier piles all pushed to the final level. M1 and gas pipe to be supported during excavation. To resume excavation after instrumentation installed by Mon
Sat (02/03) | 02 Mar 2024 | Zone 1 Slip road |  | DIC backfilling in progress
Sat (02/03) | 02 Mar 2024 | Zone 2 |  | Footh path casting completed..levelling in progress. 25m
Sat (02/03) | 02 Mar 2024 | MH1-2 |  | Formwork additional support in progress. Target to cast around 12mn
Sat (02/03) | 02 Mar 2024 | Zone 1 |  | Vistek here for singtel cable pulling
Sun (03/03) | 03 Mar 2024 | Zone 1 LA | lane 3 towards PRD3 | Lane closure by CGS for the side table excavation for DIC. TMA provided
Sun (03/03) | 03 Mar 2024 | PRD3 |  | No activity
Sun (03/03) | 03 Mar 2024 | Zone 1 |  | IM drilling ongoing for inclinometer, 9/18m
Sun (03/03) | 03 Mar 2024 | Zone 1 |  | KTC soil disposal
Sun (03/03) | 03 Mar 2024 | MH1-2 |  | Casting in progress, 18/76m3
Sun (03/03) | 03 Mar 2024 | ST05 |  | Guidewall trial trench in progress
Sun (03/03) | 03 Mar 2024 | ST69A |  | Trimming ongoing
Sun (03/03) | 03 Mar 2024 | ST89 |  | First bite excavation in progress
Sun (03/03) | 03 Mar 2024 | LA/LW junction LP21 |  | Starhub excavation for pipe laying. Today plan 15m
Sun (03/03) | 03 Mar 2024 | Zone 4 |  | B-SPT3 permeability test in progress
Sun (03/03) | 03 Mar 2024 | ST74 |  | Pre-excavation
Sun (03/03) | 03 Mar 2024 | ST34 |  | Trimming temporarily stopped for rectification. C-lug broken
Sun (03/03) | 03 Mar 2024 | ST34 |  | WS trimming in progress
Sun (03/03) | 03 Mar 2024 | ST69A |  | BC cutter teeth replacement
Sun (03/03) | 03 Mar 2024 | ST89 |  | Trenching continue for 1st bite
Sun (03/03) | 03 Mar 2024 | Exit 3 |  | Seongha works done for the day
Sun (03/03) | 03 Mar 2024 | Zone 1 |  | IM inclinometer drilling completed. Pipe installation in progress
Sun (03/03) | 03 Mar 2024 | MH1-2 |  | Continue casting 1st lift. Progressive vol: 47/76m3
Sun (03/03) | 03 Mar 2024 | ST89 |  | 2nd bite excavation in progress, 19m
Sun (03/03) | 03 Mar 2024 | Zone 4 LP21 |  | Starhub completed pipe laying for the day, 15m. Lane reopened
Sun (03/03) | 03 Mar 2024 | ST69A |  | Trimming ongoing
Sun (03/03) | 03 Mar 2024 | ST34 |  | Resume trimming works
Sun (03/03) | 03 Mar 2024 | Exit 3 |  | Fissure grout point PL-01 post lugeon test in progress. Today plan 1 point only
Sun (03/03) | 03 Mar 2024 | Zone 2 |  | Krishco preparing formwork for water pipe stump. Tmr plan for casting
Sun (03/03) | 03 Mar 2024 | Zone 2 |  | Slip rd footpath was cast yesterday, 20m
Sun (03/03) | 03 Mar 2024 | Zone 2 |  | CGS continue debris removal and plan for DIC installation
Mon (04/03) | 04 Mar 2024 | Zone 2 |  | Concrete barrier delivery
Mon (04/03) | 04 Mar 2024 | ST89 |  | Bite 3 completed
Mon (04/03) | 04 Mar 2024 | ST69A |  | Cleaning ongoing
Mon (04/03) | 04 Mar 2024 | ST34 |  | Desanding completed. Final koden check
Mon (04/03) | 04 Mar 2024 | Zone 4 |  | No activity
Mon (04/03) | 04 Mar 2024 | Zone 2 slip road |  | Foot path formwork dismantling
Mon (04/03) | 04 Mar 2024 | Zone 2 |  | 6m hoarding dismantling. HBJB here for 12m NB
Mon (04/03) | 04 Mar 2024 | PMH12 open pit |  | SPPG here exposing the pipes. Plan this week to start cable pulling
Mon (04/03) | 04 Mar 2024 | Zone 2 |  | Foot path rebar works and formwork closing
Mon (04/03) | 04 Mar 2024 | Zone 3 CCW |  | HSL crane wire rope replacement
Mon (04/03) | 04 Mar 2024 | P21-P22 |  | Scaffold dismantling status
Mon (04/03) | 04 Mar 2024 | ST34 |  | Cleaning in progress
Mon (04/03) | 04 Mar 2024 | ST69A |  | Mud hose connection prior to desanding and cleaning
Mon (04/03) | 04 Mar 2024 | P21-22 |  | WH continue NB scaffold dismantling
Mon (04/03) | 04 Mar 2024 | Zone 2 |  | Footpath formwork fabrication ongoing
Mon (04/03) | 04 Mar 2024 | Zone 2 |  | Backfilling ongoing at DIC area
Mon (04/03) | 04 Mar 2024 | Zone 1 LA sidetable towards PRD |  | CGS works done for the day
Mon (04/03) | 04 Mar 2024 | P3 |  | KTC continue excavation till 10pm
Mon (04/03) | 04 Mar 2024 | Zone 1 |  | LCH continue hacking of sewer MH till 930pm
Mon (04/03) | 04 Mar 2024 | MH1-2 |  | WH scaffold erection ongoing. LCH night team continue 2nd lift wall rebar works
Mon (04/03) | 04 Mar 2024 | Zone 1 junction |  | No activity
Mon (04/03) | 04 Mar 2024 | Loyang Lane outside Gate 5 |  | Ley Choon plan for powergrid pipe laying tonight
Tue (05/03) | 05 Mar 2024 | Zone 2 |  | Foot path formwork closing, today to cast 16m. Manpower 4+2
Tue (05/03) | 05 Mar 2024 | Zone 2 P14-P15 |  | Dismantling of 6m hoarding. Today and tomorrow to complete dismantling including scaffold
Tue (05/03) | 05 Mar 2024 | ST34 |  | Hanging bar installation in progress
Tue (05/03) | 05 Mar 2024 | Loyang Lane LP3 |  | Ley Choon to continue pipe laying works
Tue (05/03) | 05 Mar 2024 | S3 |  | Backfilling works to column stump level
Tue (05/03) | 05 Mar 2024 | Zone 2 P13-P7 |  | Machineries for M&P will start to mobilise tomorrow
Tue (05/03) | 05 Mar 2024 | Zone 3 P22-P23 |  | Addition concrete stump for water pipe casting in progress
Tue (05/03) | 05 Mar 2024 | Zone 2 | Slip road | RCA Compaction and levelling works in progress
Tue (05/03) | 05 Mar 2024 | Zone 4 P45 to P46 |  | Road premix hacking and prepare for actual GI work
Tue (05/03) | 05 Mar 2024 | ST34 |  | Rebar cage installation in progress, 2/8nos
Tue (05/03) | 05 Mar 2024 | ST89 |  | Trimming ongoing
Tue (05/03) | 05 Mar 2024 | ST69A |  | Bottom endplate installation in progress
Tue (05/03) | 05 Mar 2024 | ST181 |  | First bite excavation started
Tue (05/03) | 05 Mar 2024 | BC cutter 3 |  | Cutter teeth replacement ongoing
Tue (05/03) | 05 Mar 2024 | Zone 2 north bound |  | Footpath formwork installation (~20m). Plan for casting tmr
Tue (05/03) | 05 Mar 2024 | NLL LP4 |  | Tonight CGS to continue pipe laying (4m)
Tue (05/03) | 05 Mar 2024 | P3 |  | Barricade and access installation by WH
Tue (05/03) | 05 Mar 2024 | MH1-2 |  | WH continue scaffold erection. LCH night team to continue wall rebar works
Tue (05/03) | 05 Mar 2024 | NLL LP4 |  | To continue pipe joining
Tue (05/03) | 05 Mar 2024 | Exit 3 |  | Continue fissure grouting, pts O-48-O49
Tue (05/03) | 05 Mar 2024 | ST181 |  | First bite excavation in progress, 19m
Tue (05/03) | 05 Mar 2024 | ST69A |  | Casting in progress, 45/108m3
Tue (05/03) | 05 Mar 2024 | ST89 |  | Desanding completed. Final koden checking ongoing
Tue (05/03) | 05 Mar 2024 | Zone 4 |  | No activity
Wed (06/03) | 06 Mar 2024 | MH1-2 |  | Continue wall rebar works
Wed (06/03) | 06 Mar 2024 | PRD3 |  | Singtel lane closure for cable pulling
Wed (06/03) | 06 Mar 2024 | ST69A |  | Casting completed at 0007hrs. Total vol: 113m3
Wed (06/03) | 06 Mar 2024 | ST34 |  | Casting in progress, 54/225m3
Wed (06/03) | 06 Mar 2024 | ST181 |  | Trimming ongoing at waterstop side
Wed (06/03) | 06 Mar 2024 | ST178 |  | First bite started at 0325hrs. Now temporarily on hold due to jam at suction line. Rectification ongoing
Wed (06/03) | 06 Mar 2024 | MH1-2 |  | Formwork closing on going for the shaft
Wed (06/03) | 06 Mar 2024 | Zone 1 P3 |  | Activities done for the day
Wed (06/03) | 06 Mar 2024 | MH1-2 |  | HDPE lining sheet preparation and 2nd lift formwork installation ongoing
Wed (06/03) | 06 Mar 2024 | Zone 1 junction |  | No activity
Wed (06/03) | 06 Mar 2024 | South ramp S3 |  | Activity done for the day
Wed (06/03) | 06 Mar 2024 | ST89 |  | Rebar cage installation in progress, 5/6nos
Wed (06/03) | 06 Mar 2024 | Zone 4 |  | No activity
Wed (06/03) | 06 Mar 2024 | ST178 |  | First bite excavation in progress, 8.5m
Wed (06/03) | 06 Mar 2024 | Exit 3 |  | FG - O-47 drilling ongoing
Wed (06/03) | 06 Mar 2024 | ST181 |  | First bite cleaning completed
Wed (06/03) | 06 Mar 2024 | Zone 2 P14-P15 |  | Dismantling of scaffold in progress
Wed (06/03) | 06 Mar 2024 | Zone 2 |  | Footpath formwork closing, today to cast 20m. Manpower 2+1
Thu (07/03) | 07 Mar 2024 | Zone 2 slip road status |  | Balance asphaltic base course and wearing course
Thu (07/03) | 07 Mar 2024 | P44 |  | WH trial trench ongoing for bored pile
Thu (07/03) | 07 Mar 2024 | ST169 |  | First bite excavation in progress
Thu (07/03) | 07 Mar 2024 | S3 |  | KTC backfilling works till s1 layer in progress. Manpower 2+1
Thu (07/03) | 07 Mar 2024 | ST181 |  | Waterstop end plate joint welding ongoing
Thu (07/03) | 07 Mar 2024 | Zone 2 P15 |  | HBJB here for NB footing construction. Today to lean con the area, Tomorrow to start footing construction
Thu (07/03) | 07 Mar 2024 | MH1-2 |  | Continue Formwork installation for manhole chamber 2nd lift
Thu (07/03) | 07 Mar 2024 | Zone 1 NLL to L.A |  | Draw pit excavation in progress. NLL to PDR3 completed
Thu (07/03) | 07 Mar 2024 | Zone 1 P3 ERSS |  | Lagging plate + channel installed below M1, 2 sides completed. Bracket for waler 4/10 installed
Thu (07/03) | 07 Mar 2024 | ST74 |  | First bite excavation in progress
Thu (07/03) | 07 Mar 2024 | ST169 |  | First bite excavation started
Thu (07/03) | 07 Mar 2024 | ST178 |  | Continue first bite excavation
Thu (07/03) | 07 Mar 2024 | ST181 |  | Final koden check was done
Thu (07/03) | 07 Mar 2024 | Zone 1 |  | Relocation of existing DIC and connection of drainage pipe
Thu (07/03) | 07 Mar 2024 | ST181 |  | Rebar cage installation. 3/4 nos
Thu (07/03) | 07 Mar 2024 | ST178 |  | BC cutter teeth replacement, current B1 excavation
Thu (07/03) | 07 Mar 2024 | ST169 |  | B1 trenching continue
Thu (07/03) | 07 Mar 2024 | ST167 |  | Pre-boring till 10pm
Thu (07/03) | 07 Mar 2024 | BC cutter 1 |  | Cuttern wheel replacement
Thu (07/03) | 07 Mar 2024 | MH1-2 |  | Formwork closing on going
Thu (07/03) | 07 Mar 2024 | PBH36, 35 |  | Lean con cast at the area
Thu (07/03) | 07 Mar 2024 | PBH51 |  | In progress, 34.5m. PBH53: pending grouting. Termination depth already confirmed 40m
Thu (07/03) | 07 Mar 2024 | ST181 |  | Cage A (2/2) and Cage B (2/2 cages in progress). Tonight to cast
Thu (07/03) | 07 Mar 2024 | P29 |  | Hacking ongoing for PBH trial trench and SI works (PBH46, 47)
Thu (07/03) | 07 Mar 2024 | ST178 |  | First bite in progress, 19.2m
Thu (07/03) | 07 Mar 2024 | ST80 |  | Guidewall excavation in progress
Thu (07/03) | 07 Mar 2024 | ST74 |  | First bite ongoing, 27.5m
Thu (07/03) | 07 Mar 2024 | Exit 3 |  | Fissure grouting drilling in progress
Thu (07/03) | 07 Mar 2024 | ST89 |  | Casting in progress, 132/240m3
Fri (08/03) | 08 Mar 2024 | ST169 |  | 1st bite excavation in progress, 21.7m / 41.3m
Fri (08/03) | 08 Mar 2024 | Zone 2 |  | Balance foothpath and kerb cast yesterday. Formwork dismantling
Fri (08/03) | 08 Mar 2024 | ST74 |  | 1st bite excavation completed. Now doing internal koden test
Fri (08/03) | 08 Mar 2024 | P44 |  | Trial Trench for BP 7 & 8 in progress
Fri (08/03) | 08 Mar 2024 | Zone 4 | Bet. P46-P47 | GCE Materials shifting and preparation works for next JGP location
Fri (08/03) | 08 Mar 2024 | MH1-2 |  | Loosening of stuck formwork and continue formwok closing
Fri (08/03) | 08 Mar 2024 | Zone 2 |  | 12m NB footing rebar completed. Tomorrow formwork closing and casting
Fri (08/03) | 08 Mar 2024 | ST178 |  | 1st bite trenching, current 22.8m
Fri (08/03) | 08 Mar 2024 | ST69 |  | 1st bite trenching, current depth 21.2m
Fri (08/03) | 08 Mar 2024 | ST74 |  | 2nd bite trenching, 18m
Fri (08/03) | 08 Mar 2024 | MH1-2 |  | Day shift handover to night shift
Fri (08/03) | 08 Mar 2024 | Exit 3 |  | Drilling for fissure grouting, pt O-19
Fri (08/03) | 08 Mar 2024 | Zone 3 |  | PBH-46 Manual trial trench in progress for SI works
Sat (09/03) | 09 Mar 2024 | Exit 3 |  | Drilling for fissure grouting on going, pt O-17
Sat (09/03) | 09 Mar 2024 | PMH12-loyang lane |  | SPPG cable continue. 2 nos main cables pulled
Sat (09/03) | 09 Mar 2024 | ST178 |  | 2nd bite in progress, reached 21.5m
Sat (09/03) | 09 Mar 2024 | LVC side along MH2-3 |  | WH and HBJB here discussing to start NB footing. Surveyor setting out in progress
Sat (09/03) | 09 Mar 2024 | Zone 2 |  | TT in progress for lampost footing
Sat (09/03) | 09 Mar 2024 | P14-15 |  | NB footing formwork closing. Plan to cast Tomorrow
Sat (09/03) | 09 Mar 2024 | MH1-2 |  | Perm wall 2nd lift casting in progress. 3rd load
Sat (09/03) | 09 Mar 2024 | Zone 1 P3 ERSS |  | Waler beam installation in progress
Sat (09/03) | 09 Mar 2024 | PDR3 |  | Loop detector pipe installation in progress
Sat (09/03) | 09 Mar 2024 | Zone 1 L.A road widening for stage 1 |  | D1 ker installation
Sat (09/03) | 09 Mar 2024 | Zone 3 CCW |  | TT for KP bored pile
Sat (09/03) | 09 Mar 2024 | Zone 3 |  | TT for SI works , PBH46 and 47
Sat (09/03) | 09 Mar 2024 | ST178 |  | 2nd bite trenching continue, current depth at 34.0m/39m
Sat (09/03) | 09 Mar 2024 | ST69 |  | 2nd bite trenching at 20.90m/22.80m depth
Sat (09/03) | 09 Mar 2024 | ST74 |  | 2nd bite trenching at 13.0m/23.30m depth
Sat (09/03) | 09 Mar 2024 | MH2-1 |  | LSS backfilling
Sat (09/03) | 09 Mar 2024 | ST182 |  | Pre-excavation in progress
Sat (09/03) | 09 Mar 2024 | ST178 |  | 2nd bite trenching continue. Current depth 19.5/23.30m
Sat (09/03) | 09 Mar 2024 | ST169 |  | 2nd bite trenching temporary stopped, desander cyclone repair works in progress. Current depth 18/22.8m
Sat (09/03) | 09 Mar 2024 | ST167 PB2 |  | Pre-boring completed. Preparation for LSS casting
Sat (09/03) | 09 Mar 2024 | CBP-32 |  | Boring completed, today to cast
Sat (09/03) | 09 Mar 2024 | ST74 |  | Mud pump replaced. Now topping up hydraulic oil then cam resume 2nd bite
Sat (09/03) | 09 Mar 2024 | PMH12-loyang lane |  | SPPG cable pulling, 4/6 main cables completed
Sat (09/03) | 09 Mar 2024 | MH1-2 |  | Continue casting. 66m3/78m3
Sun (10/03) | 10 Mar 2024 | ST-178 |  | 3rd bite excavation completed
Sun (10/03) | 10 Mar 2024 | ST169 |  | Water stop installation ongoing
Sun (10/03) | 10 Mar 2024 | Zone 3 | Vent shaft | No activity
Sun (10/03) | 10 Mar 2024 | ST-74 |  | Desanding completed. Now preparing for koden test
Sun (10/03) | 10 Mar 2024 | Zone 4 |  | Starhub MoGuan 6-ways pipe laying in progress
Sun (10/03) | 10 Mar 2024 | Zone 4 | Bet P45-P46 | Hacking of road premix in progress for JGP work
Sun (10/03) | 10 Mar 2024 | Zone 1 Slip road |  | CGS excavation works and soil disposal ongoing
Sun (10/03) | 10 Mar 2024 | Zone 1 | P3 | S1 diagonal strut, waler beam end plate welding works in progress
Sun (10/03) | 10 Mar 2024 | MH1-2 |  | Scaffold erection in progress for 3rd lift chamber wall
Sun (10/03) | 10 Mar 2024 | Zone 1 Existing Sewer Manhole |  | TBM retrieval works in progress
Sun (10/03) | 10 Mar 2024 | Zone 2 | Bet. P15-P16 | Preparation for casting for 3 nos. of noise barrier footings
Sun (10/03) | 10 Mar 2024 | Exit 3 |  | Post lugeon tests completed for PL-1, PL-2 & PL-3, now casings removal in progress
Sun (10/03) | 10 Mar 2024 | ST-182 |  | 1st bite excavation in progress, current depth 4m
Sun (10/03) | 10 Mar 2024 | ST-178 |  | Due to limited access area, rebar lowering and casting for this panel will wait till ST-169 and ST-74 complete casting first
Sun (10/03) | 10 Mar 2024 | ST-169 |  | Cleaning in progress for 2nd bite
Sun (10/03) | 10 Mar 2024 | ST-74 |  | Water stop installation in progress
Sun (10/03) | 10 Mar 2024 | Zone 4 |  | MoGuan starhub pipe laying completed. Now reinstatement works ongoing
Sun (10/03) | 10 Mar 2024 | Zone 4 | Bet P45-P46 | Continue Hacking of road premix in progress for JGP work
Sun (10/03) | 10 Mar 2024 | Zone 1 Slip road |  | CGS soil disposal works ongoing
Sun (10/03) | 10 Mar 2024 | Zone 1 | P3 | LE work stopped for the day. To continue S1 diagonal strut, waler beam end plate welding works next day
Sun (10/03) | 10 Mar 2024 | MH1-2 |  | Rebar installation for 3rd lift chamber wall
Sun (10/03) | 10 Mar 2024 | Zone 1 Existing Sewer Manhole |  | Continue pushing of TBM & retrieval works in progress
Sun (10/03) | 10 Mar 2024 | Zone 2 | Bet. P15-P16 | Casting completed for 3 nos. of noise barrier footings
Sun (10/03) | 10 Mar 2024 | Exit 3 |  | Post lugeon test (bottom) for O-27 & O-28 in progress
Sun (10/03) | 10 Mar 2024 | Exit 3 |  | O-37 & O-39 grouting works in progress
Mon (11/03) | 11 Mar 2024 | ST167 |  | Preparation to backfill 1st bite due to soil collapse from dayshift. G20 concrete ordered. Est vol 60m3
Mon (11/03) | 11 Mar 2024 | ST74 |  | 5/8 rebar cage installation in progress
Mon (11/03) | 11 Mar 2024 | ST88 |  | 2nd bite trenching continue at 14m depth
Mon (11/03) | 11 Mar 2024 | P11-2 |  | Preboring for ERSS installation in progress
Mon (11/03) | 11 Mar 2024 | Zone 2 |  | CGS hacking works for DIC drainage pipe installation
Mon (11/03) | 11 Mar 2024 | Zone 2 | Bus lane | Road premix laying works in progress
Mon (11/03) | 11 Mar 2024 | Zone 2 | Bet. P14 to P16 | Continue Road premix laying works in progress
Mon (11/03) | 11 Mar 2024 | MH1-2 |  | Scaffold erection by Woh Hup
Mon (11/03) | 11 Mar 2024 | MH1-2 |  | Formwork dismantling in progress. Tonight plan to dismantle formwork and start hacking existing pipe to reconnect pipe
Mon (11/03) | 11 Mar 2024 | P8 |  | Slope levelling to lean con tomorrow
Mon (11/03) | 11 Mar 2024 | Exit 3 |  | Fissure grout point O-29 drilling in progress
Mon (11/03) | 11 Mar 2024 | ST182 |  | 1st bite completed. Now teeth replacement to start 2nd bite
Mon (11/03) | 11 Mar 2024 | ST178 |  | Water stop fully lowered. Preparation to lower rebar cages, 4 nos
Tue (12/03) | 12 Mar 2024 | P44 |  | WH continue hacking works for bored pile trial trench
Tue (12/03) | 12 Mar 2024 | ST188 |  | Pre excavation done. To start 1st bite
Tue (12/03) | 12 Mar 2024 | ST174 |  | Cleaning done. Preparation for desanding then final Koden
Tue (12/03) | 12 Mar 2024 | ST88 |  | 3rd bite trenching, 8/34.7m
Tue (12/03) | 12 Mar 2024 | ST74 |  | Casting completed, tremie pipe dismantling
Tue (12/03) | 12 Mar 2024 | ST74 |  | Preparing for casting
Tue (12/03) | 12 Mar 2024 | Exit 3 |  | Drilling ongoing for fissure grout point O-31
Tue (12/03) | 12 Mar 2024 | ST178 |  | Rebar cages extracted for trench cleaning with high density
Tue (12/03) | 12 Mar 2024 | PBH35 |  | Preparing for trial trench works
Tue (12/03) | 12 Mar 2024 | Zone 3 |  | Repainting of access ongoing
Tue (12/03) | 12 Mar 2024 | Zone 2 |  | Setting up noise ballon, tonight to continue extension od drop inlet pipe at bus only lane
Tue (12/03) | 12 Mar 2024 | Gate 5 |  | SPPG 6/6 nos. 22kV cable pulling completed. 6/12nos. Pilot cables completed. To complete by today
Tue (12/03) | 12 Mar 2024 | ST178 |  | Rebar cage installation in Progress, 3/4 cages
Tue (12/03) | 12 Mar 2024 | ST167 |  | G20 concrete backfilling in progress
Tue (12/03) | 12 Mar 2024 | ST74 |  | 6/8 rebar cages installed
Tue (12/03) | 12 Mar 2024 | Z4 Loyang way |  | Singtel cable recovery works
Tue (12/03) | 12 Mar 2024 | DW20-21 |  | Guidewall casting
Tue (12/03) | 12 Mar 2024 | ST182 |  | 2nd bite excavation on going. 9m depth
Tue (12/03) | 12 Mar 2024 | ST178 |  | Hanging bar installation in progress
Tue (12/03) | 12 Mar 2024 | ST167 |  | Backfilling with G20 completed
Tue (12/03) | 12 Mar 2024 | ST74 |  | 8/8 cages installed
Tue (12/03) | 12 Mar 2024 | Zone 2 |  | WH marking for concrete barrier alignment at southbound
Tue (12/03) | 12 Mar 2024 | Zone 2 P8-9 |  | Center median and kerb hacking for stage 0A. Debris clearing, work till 10pm
Tue (12/03) | 12 Mar 2024 | MH1-2 |  | To continue hacking tonight of the diverted sewer pipe
Tue (12/03) | 12 Mar 2024 | BH4A |  | In progress, 32m
Tue (12/03) | 12 Mar 2024 | DW20-DW21 |  | Guidewall formwork installation in progress. Plan for casting today
Tue (12/03) | 12 Mar 2024 | P26 |  | Premix hacking for bored pile trial trench
Tue (12/03) | 12 Mar 2024 | PBH46, PBH47 |  | SI in progress
Tue (12/03) | 12 Mar 2024 | ST182 |  | 2nd bite excavation temporarily stopped. Desander cyclone leakage. Current depth at 22.6m
Tue (12/03) | 12 Mar 2024 | ST88 |  | Cutter wheel teeth replacement ongoing
Wed (13/03) | 13 Mar 2024 | Gate 5 |  | Activ preparing to pull Singtel cables (4nos)
Wed (13/03) | 13 Mar 2024 | ST188 |  | Currently at 1st bite. Gear box replacement in progress
Wed (13/03) | 13 Mar 2024 | ST182 |  | Water stop side trimming
Wed (13/03) | 13 Mar 2024 | ST178 |  | Casting in progress, 111/160 m3
Wed (13/03) | 13 Mar 2024 | Zone 3 |  | LCS under Starhub is preparing to pull 1 cable from Selarang camp to this manhole
Wed (13/03) | 13 Mar 2024 | ST167 |  | Teeth changing and internal koden for 1st bite
Wed (13/03) | 13 Mar 2024 | ST88 |  | Water stop lowering
Wed (13/03) | 13 Mar 2024 | ST178 |  | Rebar cage installation in progress, 3/4nos
Wed (13/03) | 13 Mar 2024 | ST182 |  | 2nd bite in progress, 23.6m
Wed (13/03) | 13 Mar 2024 | MH2-1 |  | Hacking works ongoing prior to backfilling
Wed (13/03) | 13 Mar 2024 | P25 |  | WH continue trial trench for bored pile works
Wed (13/03) | 13 Mar 2024 | MH1-2 |  | Hacking continue and debris clearing
Wed (13/03) | 13 Mar 2024 | P18 |  | Excavation for pvc pipes for lamp posts
Wed (13/03) | 13 Mar 2024 | P11-2 |  | Preboring ongoing for soldier pile installation
Wed (13/03) | 13 Mar 2024 | Zone 1 LA | towards PRD3 | CGS continue excavation for DIC extension and road widening works
Wed (13/03) | 13 Mar 2024 | Zone 1 |  | Trial trench for DIC extension
Wed (13/03) | 13 Mar 2024 | Zone 1 LCH |  | Works ongoing for cutter head retrieval at existing manhole
Wed (13/03) | 13 Mar 2024 | MH1-2 |  | Hacking ongoing for existing channel
Wed (13/03) | 13 Mar 2024 | P3 |  | MPI test done for S1 waler/strut joints
Wed (13/03) | 13 Mar 2024 | ST188 |  | First bite excavation in progress, 14m
Wed (13/03) | 13 Mar 2024 | ST188 |  | 1st bite trenching in progress, current depth 11.5m
Wed (13/03) | 13 Mar 2024 | ST178 |  | Cleaning and desanding done. Koden test ok. Now lowering rebar cages
Wed (13/03) | 13 Mar 2024 | ST178 |  | Preparing for casting
Wed (13/03) | 13 Mar 2024 | ST88 |  | Water stop endplate installation ongoing
Wed (13/03) | 13 Mar 2024 | ST88 |  | 2nd bite trenching completed. Trimming at water stop side on going
Wed (13/03) | 13 Mar 2024 | Zone 2 slip road |  | Slope protection casting
Wed (13/03) | 13 Mar 2024 | Zone 2 |  | Lamp post pipe laying done for the day. Backfilling in progress, est 30m
Wed (13/03) | 13 Mar 2024 | Zone 2 |  | Drop inlet pipe connection to existing drain. Work till 10 pm, tonight to backfill and tomorrow am casting
Wed (13/03) | 13 Mar 2024 | Zone 2 |  | Half height hoarding today installation started. ECS stopped work at 7pm
Wed (13/03) | 13 Mar 2024 | Zone 2 P8-P9 new slip road for stage 0A |  | Backfilling at previous center median and levelling. Work till 10pm
Wed (13/03) | 13 Mar 2024 | MH1-2 |  | To continue hacking of temporary drain
Thu (14/03) | 14 Mar 2024 | Loyang Way | near exit 1 gate | Singtel cable pulling works
Thu (14/03) | 14 Mar 2024 | Zone 4 |  | Today plan for shifting of jgp machine to zone 4
Thu (14/03) | 14 Mar 2024 | Zone 4 |  | Bund wall construction
Thu (14/03) | 14 Mar 2024 | Zone 4 LA |  | Lane closure for Stahub pipe laying works. Today plan 6m
Thu (14/03) | 14 Mar 2024 | Gate 5 |  | Dismantling of soil disposal tower and to be shifted to exit 1 area
Thu (14/03) | 14 Mar 2024 | ST188 |  | Gear box repair works continue
Thu (14/03) | 14 Mar 2024 | ST182 |  | Trenching temporarily stopped due to mud pump leaking, repair works in progress
Thu (14/03) | 14 Mar 2024 | ST167 |  | Water stop side trimming on going
Thu (14/03) | 14 Mar 2024 | ST88 |  | Rebar cages installation started
Thu (14/03) | 14 Mar 2024 | PBH35 |  | SI started
Thu (14/03) | 14 Mar 2024 | PBH43 |  | SI started
Thu (14/03) | 14 Mar 2024 | Zone 2 bus only lane |  | Continue premix laying and compaction works
Thu (14/03) | 14 Mar 2024 | Bet P23-P22 |  | 3 nos. of noise barrier footings casting in progress
Thu (14/03) | 14 Mar 2024 | Bet. P18 to P19 |  | Center Median kerb Formwork closing in progress. Today to cast
Thu (14/03) | 14 Mar 2024 | Zone 2 |  | Covered Linkway erection in progress
Thu (14/03) | 14 Mar 2024 | ST188 |  | Cutter teeth replacement ongoing. First bite depth at 23.8m
Thu (14/03) | 14 Mar 2024 | ST182 |  | Cleaning ongoing
Thu (14/03) | 14 Mar 2024 | JTC blk 4 |  | Starhub here for fibre joining works
Thu (14/03) | 14 Mar 2024 | CBP15 |  | Last truck casting in progress
Thu (14/03) | 14 Mar 2024 | Zone 2 |  | ECS Hoarding installation on concrete barriers ongoing
Thu (14/03) | 14 Mar 2024 | MH1-2 |  | Continue hacking of temporary drain
Thu (14/03) | 14 Mar 2024 | Zone 1 | P3 | KTC excavation works completed for decking installation. Soil disposal in progress
Thu (14/03) | 14 Mar 2024 | MH1-2 |  | Hacking of temporary drain continue
Thu (14/03) | 14 Mar 2024 | Zone 1 slip road |  | CGS levelling works in progress
Thu (14/03) | 14 Mar 2024 | ST88 |  | Preparing to install tremie pipes
Thu (14/03) | 14 Mar 2024 | DW24 |  | Guidewall excavation
Thu (14/03) | 14 Mar 2024 | Exit 3 |  | Fissure grout point I-29 drilling in progress
Thu (14/03) | 14 Mar 2024 | Zone 2 centre median |  | Hacking ongoing for drain works
Thu (14/03) | 14 Mar 2024 | ST182 |  | Preparation to extract water stop
Thu (14/03) | 14 Mar 2024 | ST167 |  | Trimming done, to loosen end plate
Thu (14/03) | 14 Mar 2024 | ST88 |  | 5th cage rebar lapping. Total 6 cages
Thu (14/03) | 14 Mar 2024 | MH1-2 |  | Wall rebar work in progress
Thu (14/03) | 14 Mar 2024 | ST188 |  | 1st bite in progress, reached 24.4m/ 26.49m
Thu (14/03) | 14 Mar 2024 | MH2-1 |  | Levelling
Thu (14/03) | 14 Mar 2024 | PBH37 |  | Trial trench in progress. PBH35: Hand auger in progress
Thu (14/03) | 14 Mar 2024 | ST188 |  | First bite excavation in progress, 20.1m
Thu (14/03) | 14 Mar 2024 | ST167 |  | Trimming temporarily stopped for rectification works
Thu (14/03) | 14 Mar 2024 | ST88 |  | Rebar cage installation in progress
Thu (14/03) | 14 Mar 2024 | PBH43 |  | Hand auger in progress
Fri (15/03) | 15 Mar 2024 | PBH37 |  | In progress, 18m
Fri (15/03) | 15 Mar 2024 | PBH43 |  | In progress, 27m
Fri (15/03) | 15 Mar 2024 | ST188 |  | 2nd bite excavation in progress, 5m
Fri (15/03) | 15 Mar 2024 | CBP11 |  | Rebar cage installation, CBP23: Boring ongoing
Fri (15/03) | 15 Mar 2024 | ST78 |  | Temporarily stopped for rectification for suction hose leakage. Current 1st bite depth at 23.5m
Fri (15/03) | 15 Mar 2024 | DW24 |  | Continue guidewall excavation
Fri (15/03) | 15 Mar 2024 | MH1-2 |  | Rebar work in progress
Fri (15/03) | 15 Mar 2024 | ST182 |  | Cage A ( 1/2 cage) and Cage B (2/2 cages lowering in progress)
Fri (15/03) | 15 Mar 2024 | Zone 2 slip road |  | RCA backfilled at the footpath location. Tonight CGS will backfill 1st layer of premix at the existing road
Fri (15/03) | 15 Mar 2024 | P8-P11 |  | M&P in progress
Fri (15/03) | 15 Mar 2024 | P11-2 |  | SP and LP installation completed. Now lowering to required level for ERSS
Fri (15/03) | 15 Mar 2024 | Zone 1 stage 1 |  | L.A to PDR3 slip road, RCA backfilling completed before DE160 area
Fri (15/03) | 15 Mar 2024 | MH1-2 |  | Perm structure wall 3rd lift rebar works in progress
Fri (15/03) | 15 Mar 2024 | ST182 |  | Hanging bar installation and fully lowered down in progress
Fri (15/03) | 15 Mar 2024 | Zone 1 |  | Gantry on site for TBM retrieval at existing sewer
Fri (15/03) | 15 Mar 2024 | MH1-2 |  | Wall rebar work in progress
Sat (16/03) | 16 Mar 2024 | P11-2 |  | Today to complete driving SP and LP 1m lower from GL
Sat (16/03) | 16 Mar 2024 | Zone 2 |  | ECS half height hoarding frame installation
Sat (16/03) | 16 Mar 2024 | Zone 1 | SB side | Road widening for stage 1 diversion
Sat (16/03) | 16 Mar 2024 | P3 |  | Plate fitting inspection for main beam installation
Sat (16/03) | 16 Mar 2024 | Zone 1 |  | Existing sewer area preparation for gantry setting up
Sat (16/03) | 16 Mar 2024 | P3 decking |  | 2/4 Main beams and 8/20 secodary beams delivery
Sat (16/03) | 16 Mar 2024 | MH1-2 |  | 3rd lift perm wall rebar completed. Preparation for formwork closing
Sat (16/03) | 16 Mar 2024 | MH1-2 |  | Formwork closing. Tomorrow night target to cast
Sat (16/03) | 16 Mar 2024 | Zone 1 |  | DE143 started their reinstatement work
Sat (16/03) | 16 Mar 2024 | Zone 4 |  | JGP machine testing
Sat (16/03) | 16 Mar 2024 | Zone 4 P46 |  | Hacking of existing pavement for CGE works
Sat (16/03) | 16 Mar 2024 | ST78 |  | Trimming at end plate side in progress
Sat (16/03) | 16 Mar 2024 | ST81-87 |  | Area preparation for guidewall construction
Sat (16/03) | 16 Mar 2024 | ST188 |  | 2nd bite excavation, 24m depth
Sat (16/03) | 16 Mar 2024 | Exit 3 |  | DW24 and 25, guidewall rebar installation
Sat (16/03) | 16 Mar 2024 | Zone 4 |  | CGE Trial trench in progress
Sat (16/03) | 16 Mar 2024 | Zone 1 opp AWWA homes |  | Tonight to do premix here
Sat (16/03) | 16 Mar 2024 | MH1-2 |  | Continue formwork closing
Sat (16/03) | 16 Mar 2024 | P3 decking |  | Top plate welding in progress
Sat (16/03) | 16 Mar 2024 | ST188 |  | 1st bote trenching continue
Sat (16/03) | 16 Mar 2024 | ST81-87 |  | Railing installation fot guidewall construction
Sat (16/03) | 16 Mar 2024 | PBH37, PBH35, PBH43 |  | SI works for Barrete piles
Sat (16/03) | 16 Mar 2024 | Exit 3 |  | Drilling for fissure grouting. Pt I-18
Sat (16/03) | 16 Mar 2024 | Zone 2 |  | Backfilling in progress along with the new slip road
Sun (17/03) | 17 Mar 2024 | MH2-1 |  | LCH Benching works
Sun (17/03) | 17 Mar 2024 | ST188 |  | Waterstop installation in progress
Sun (17/03) | 17 Mar 2024 | ST177 |  | 1st bite excavation in progress ,current depth 4.9m
Sun (17/03) | 17 Mar 2024 | ST167 |  | Wheel bolt replacing in progress. Current depth - 1st bite 26.95m
Sun (17/03) | 17 Mar 2024 | ST078 |  | 1st bite excavation in progress, current depth 29m
Sun (17/03) | 17 Mar 2024 | ST087 |  | Excavation for Guidewall in progress
Sun (17/03) | 17 Mar 2024 | Zone 4 | Bet P46-P47 | GCE trial trench and pipe sleeve installation works ongoing
Sun (17/03) | 17 Mar 2024 | P23 |  | Trial Trench to locate SPTel in progress
Sun (17/03) | 17 Mar 2024 | Zone 2 |  | Linkway erection works
Sun (17/03) | 17 Mar 2024 | Zone 2 | Bet. P15-P16 | Horizontal bracings installation for noise barriers in progress
Sun (17/03) | 17 Mar 2024 | MH1-2 |  | 3rd layer wall Formwork installation in progress
Sun (17/03) | 17 Mar 2024 | MH5-2 to existing sewer |  | TBM retrieval completed. Next will remove the slurry pipes and benching works
Sun (17/03) | 17 Mar 2024 | P3 |  | Installation of secondary beams in progress for decking works
Sun (17/03) | 17 Mar 2024 | Zone 1 |  | CGS Formwork installation for road kerb casting
Sun (17/03) | 17 Mar 2024 | P11-2 |  | KTC excavation to S1 layer & soil disposal works
Sun (17/03) | 17 Mar 2024 | DW24 & 25 |  | Guide Wall continue formwork closing, target to cast ard 5pm
Sun (17/03) | 17 Mar 2024 | ST188 |  | Continue Waterstop installation in progress at ST189 side
Sun (17/03) | 17 Mar 2024 | MH1-2 |  | Wall formwork closing in progress
Sun (17/03) | 17 Mar 2024 | ST177 |  | 1st bite excavation in progress, current depth 16.9m
Sun (17/03) | 17 Mar 2024 | ST167 |  | Resumed 1st bite excavation & trimming works
Sun (17/03) | 17 Mar 2024 | ST078 |  | 1st bite excavation temporarily stopped, cutter teeth replacement in progress
Sun (17/03) | 17 Mar 2024 | ST087 |  | Excavation for Guidewall completed. Now preparation for rebar installation works
Sun (17/03) | 17 Mar 2024 | Zone 4 |  | MoGuan starhub 6ways pipe laying along loyang way. Reinstatement in progress
Sun (17/03) | 17 Mar 2024 | Zone 4 | Bet P46-P47 | GCE continue trial trench and pipe sleeve installation works. As of now 2 points completed
Sun (17/03) | 17 Mar 2024 | Zone 1 |  | CGS road kerb casting completed. Work stopped for the day
Sun (17/03) | 17 Mar 2024 | P3 |  | 6 nos. of secondary beams installed. Now welding works for main beam platform making in progress
Sun (17/03) | 17 Mar 2024 | MH5-2 |  | Removal of slurry pipes and cables ongoing
Sun (17/03) | 17 Mar 2024 | P11-2 |  | Current status for excavation works. Housekeeping ongoing
Sun (17/03) | 17 Mar 2024 | Zone 2 | Bet. P15-P16 | Noise barrier Panels installation ongoing
Sun (17/03) | 17 Mar 2024 | MH1-2 |  | Continue closing formwork for shaft wall
Sun (17/03) | 17 Mar 2024 | Exit 3 |  | No activity
Sun (17/03) | 17 Mar 2024 | DW24 & 25 |  | Guide Wall formwork closing in progress, today to cast
Mon (18/03) | 18 Mar 2024 | Zone 4 |  | No activity
Mon (18/03) | 18 Mar 2024 | CBP27 |  | Casting in progress
Mon (18/03) | 18 Mar 2024 | ST86 |  | Guidewall rebar works ongoing. ST87 guidewall was cast during day shift
Mon (18/03) | 18 Mar 2024 | ST78 |  | Cutter wheel plate welding completed. Preparing to resume excavation
Mon (18/03) | 18 Mar 2024 | Zone 2 slip road |  | TT to find lamp post cable for connection, tomorrow ATS will shift the lamp post
Mon (18/03) | 18 Mar 2024 | BP6A-7 |  | Preparation for casting. Tremie pipe installation ongoing
Mon (18/03) | 18 Mar 2024 | Zone 1 P3 |  | Manual excavation in progress for pgas support footing
Mon (18/03) | 18 Mar 2024 | MH1-2 |  | 3rd layer formwork closing continue. Hdpe completed, balance tie back. To cast tonight at 9pm
Mon (18/03) | 18 Mar 2024 | P11-2 |  | Excavation to S1 layer completed. Now access making in progress
Mon (18/03) | 18 Mar 2024 | MH5-2 |  | Slurry pipe retrieval, balance 13 pipes
Mon (18/03) | 18 Mar 2024 | Zone 2 |  | Roofing sheet installation for covered linkway
Mon (18/03) | 18 Mar 2024 | Zone 2 slip road from PDR3 to L.A |  | Hacking of pavement in progress
Mon (18/03) | 18 Mar 2024 | S4 |  | TT on going for ERSS, expected services are singtel and PD office temp sewer pipe
Mon (18/03) | 18 Mar 2024 | Zone 2 stage 01 |  | Concrete barrier reflective strips painting started
Mon (18/03) | 18 Mar 2024 | Exit 3 |  | Drilling for fissure grouting continue, pt I-8
Mon (18/03) | 18 Mar 2024 | BP6A-7 |  | Toe level confirmed. Preparation for rebar cage installation. Tonight to cast
Mon (18/03) | 18 Mar 2024 | P23-24 |  | NB footing formwork closing, balance 3 panel
Mon (18/03) | 18 Mar 2024 | Gate 5 |  | Active cable pulling for singtel
Mon (18/03) | 18 Mar 2024 | ST185 |  | Pre-boring to continue till 10pm
Mon (18/03) | 18 Mar 2024 | ST177 |  | 2nd bite trenching at 17.3m depth
Mon (18/03) | 18 Mar 2024 | ST167 |  | 1st bite completed. Cutter teeth replacement to start 2nd bite
Mon (18/03) | 18 Mar 2024 | CBP 27 |  | Boring completed at 17.8m depth
Mon (18/03) | 18 Mar 2024 | BP6A-7 |  | Rebar cages fully installed. Now preparing to install hanging bar and then cast
Mon (18/03) | 18 Mar 2024 | Zone 2 |  | Continue roofing sheet installation
Mon (18/03) | 18 Mar 2024 | P3 |  | No activity
Mon (18/03) | 18 Mar 2024 | MH1-2 |  | 3rd layer formwork in progress. To cast tonight
Mon (18/03) | 18 Mar 2024 | Zone 1 |  | No other activity
Mon (18/03) | 18 Mar 2024 | ST177 |  | 2nd bite excavation in progress, 19m
Mon (18/03) | 18 Mar 2024 | ST167 |  | 2nd bite ongoing
Tue (19/03) | 19 Mar 2024 | ST78 |  | Trimming ongoing
Tue (19/03) | 19 Mar 2024 | ST167 |  | Waterstop end plate joint welding in progress
Tue (19/03) | 19 Mar 2024 | ST183 |  | First bite temporarily stopped. Gear box changing ongoing. Current depth at 12.2m
Tue (19/03) | 19 Mar 2024 | ST177 |  | Cutter body washing ongoing
Tue (19/03) | 19 Mar 2024 | P11-2 |  | Bracket installed. Today to install waler beam and cast Concrete packing
Tue (19/03) | 19 Mar 2024 | MH1-2 |  | Casting almost done. Last load
Tue (19/03) | 19 Mar 2024 | Zone 1 P3 |  | Manual excavation for gas pipe support footing
Tue (19/03) | 19 Mar 2024 | BP6A-7 |  | Casting completed at 2255hrs. Total vol: 9m3
Tue (19/03) | 19 Mar 2024 | CGS night team 1 |  | TBM done for scupper pipe installation at bus lane
Tue (19/03) | 19 Mar 2024 | CGS night team 2 |  | TBM conducted for lane painting at bus lane
Tue (19/03) | 19 Mar 2024 | MH1-2 |  | Casting started
Tue (19/03) | 19 Mar 2024 | CGS team 1 |  | Works done for the night. Premix compaction ongoing
Tue (19/03) | 19 Mar 2024 | CGS team 2 |  | Painting at bus-only lane completed. Lane reopened
Tue (19/03) | 19 Mar 2024 | CGS team 1 |  | Works comoleted. Lane reopened
Tue (19/03) | 19 Mar 2024 | ST78 |  | 1st bite current excavation depth 37.8m/39m
Tue (19/03) | 19 Mar 2024 | Bet P14-P15 |  | NB panels installation completed
Tue (19/03) | 19 Mar 2024 | Zone 2 |  | Hoarding installation on concrete barrier in progress
Tue (19/03) | 19 Mar 2024 | P11-2 |  | Waler beams welding works in progress
Tue (19/03) | 19 Mar 2024 | Zone 2 |  | W3B laying towards slip road
Tue (19/03) | 19 Mar 2024 | P11-2 |  | Waler welding continue
Tue (19/03) | 19 Mar 2024 | ST167 |  | 3rd bite excavation in progress
Tue (19/03) | 19 Mar 2024 | ST177 |  | 2nd bite excavation in progress
Tue (19/03) | 19 Mar 2024 | P11-2 |  | Prepare for packing concrete casting
Tue (19/03) | 19 Mar 2024 | BP6A -7 |  | Preparing for LSS backfilling
Tue (19/03) | 19 Mar 2024 | BP6C-3 |  | Coring in progress. Preparing to confirm depth
Tue (19/03) | 19 Mar 2024 | MH5-2 area |  | No activity
Tue (19/03) | 19 Mar 2024 | Zone 1 P3 |  | No activity
Tue (19/03) | 19 Mar 2024 | MH1-2 |  | No activity currently
Tue (19/03) | 19 Mar 2024 | MH1-2 |  | LCH night team TBM done. Tonight plan to open formwork
Tue (19/03) | 19 Mar 2024 | Exit 3 |  | Pt I-10 installation of PVC pipe for grouting
Wed (20/03) | 20 Mar 2024 | ST78 |  | Cutter teeth wheel changed and internal koden checked. Now preparing to resume trenching
Wed (20/03) | 20 Mar 2024 | PRD3 |  | Ley Choon works
Wed (20/03) | 20 Mar 2024 | MH1-2 |  | Support removal prior to dismantling formwork
Wed (20/03) | 20 Mar 2024 | MH1-2 |  | 3rd layer formwork dismantling
Wed (20/03) | 20 Mar 2024 | Bet. P21 to P22 |  | Noise barrier footings works in progress
Wed (20/03) | 20 Mar 2024 | P11-2 |  | Welding completed. Waiting tester for MPI
Wed (20/03) | 20 Mar 2024 | ST167 |  | Rebar cage installation in progress, 5/6nos
Wed (20/03) | 20 Mar 2024 | ST78 |  | 2nd bite excavation in progress
Wed (20/03) | 20 Mar 2024 | ST183 |  | Rectification for gear box still ongoing
Wed (20/03) | 20 Mar 2024 | PRD3 |  | Ley Choon works completed
Wed (20/03) | 20 Mar 2024 | BP6C-3 |  | Boring continue. Current depth at 30m/38.85m. Boring works to stop at 7pm
Wed (20/03) | 20 Mar 2024 | P21-22 |  | NB footing along MH2-4 formwork closing
Wed (20/03) | 20 Mar 2024 | Zone 4 |  | JGP # B449 grouting in progress
Wed (20/03) | 20 Mar 2024 | Zone 1 P3 |  | No activity
Wed (20/03) | 20 Mar 2024 | MH1-2 |  | Continue formwork dismantling
Wed (20/03) | 20 Mar 2024 | Zone 1 |  | No other activity
Wed (20/03) | 20 Mar 2024 | BC cutter 3 | Sambo | Currently pending mud hose rectification
Wed (20/03) | 20 Mar 2024 | ST183 |  | Internal koden check ongoing
Wed (20/03) | 20 Mar 2024 | ST177 |  | Waterstop end plate installation in progress
Wed (20/03) | 20 Mar 2024 | ST167 |  | Casting completed. Total vol: 184m3
Wed (20/03) | 20 Mar 2024 | Zone 4 |  | JGP in progress
Thu (21/03) | 21 Mar 2024 | MH1-2 |  | 3rd layer wall Formwork removal in progress
Thu (21/03) | 21 Mar 2024 | P3 |  | Stiffiner welding in progress for top plate
Thu (21/03) | 21 Mar 2024 | P11-2 |  | Excavation to FEL
Thu (21/03) | 21 Mar 2024 | P22 |  | NB footing rebar works
Thu (21/03) | 21 Mar 2024 | MH1-2 |  | Continue formwork dismantling
Thu (21/03) | 21 Mar 2024 | Zone 2 |  | ATS lamp post installation works in progress
Thu (21/03) | 21 Mar 2024 | Zone 2 |  | Covered linkway Hoarding installation ongoing
Thu (21/03) | 21 Mar 2024 | Zone 4 |  | Starhub pipe laying by MoGuan
Thu (21/03) | 21 Mar 2024 | Zone 2 |  | Concrete barriers painting works
Thu (21/03) | 21 Mar 2024 | Zone 2 |  | Continue road premix laying works
Thu (21/03) | 21 Mar 2024 | S4 |  | Trial trench in progress for ERSS installation. Tmr to start preboring
Thu (21/03) | 21 Mar 2024 | MH5-2 |  | Jacking pipes unloading for MH5-2 to MH5-1
Thu (21/03) | 21 Mar 2024 | MH1-2 |  | Continue 3rd layer Formwork dismantle & removal
Thu (21/03) | 21 Mar 2024 | Zone 2 near shell station |  | Excavation works for site access making
Thu (21/03) | 21 Mar 2024 | P11-2 |  | Excavation to FEL ongoing
Thu (21/03) | 21 Mar 2024 | Zone 4 ULT12 |  | 1st cycle testing at 50% loading. Expansion less than 1mm
Thu (21/03) | 21 Mar 2024 | Zone 4 |  | JGP Point no B-447 grouting in progress. 3/32
Thu (21/03) | 21 Mar 2024 | ST78 |  | 2nd bite excavation in progress
Thu (21/03) | 21 Mar 2024 | ST177 |  | Rebar cage installation, 4/4nos
Thu (21/03) | 21 Mar 2024 | MH1-2 |  | Scaffold erection by Woh hup
Fri (22/03) | 22 Mar 2024 | P43/44 |  | Singtel cable recovery ongoing
Fri (22/03) | 22 Mar 2024 | Zone 4 |  | WH exposing trench for Starhub and army cable for localised shifting
Fri (22/03) | 22 Mar 2024 | ULT12 |  | 2nd cycle in progress, 150% load. Holding time 6hrs
Fri (22/03) | 22 Mar 2024 | Zone 1 existing sewer |  | Benching completed. Reinstating cover
Fri (22/03) | 22 Mar 2024 | Zone 4 LA | towards LW | Starhub lane closure for pipe laying works
Fri (22/03) | 22 Mar 2024 | Zone 4 GCE |  | Area preparation for next grouting point, B-448
Fri (22/03) | 22 Mar 2024 | S4 |  | TT completed, preparation for pre-boring
Fri (22/03) | 22 Mar 2024 | P11-2 |  | Excavation to FEL, balance 500mm
Fri (22/03) | 22 Mar 2024 | ST73A |  | Excavation started at 1005hrs
Fri (22/03) | 22 Mar 2024 | PBH55 |  | Hand auger ongoing
Fri (22/03) | 22 Mar 2024 | Zone 3 Seongha |  | Bund wall making ongoing around the site container
Fri (22/03) | 22 Mar 2024 | Near exit 2 |  | BH155 trial trench in progress
Fri (22/03) | 22 Mar 2024 | Zone 3 |  | Sump pit extension hacking ongoing by WH
Fri (22/03) | 22 Mar 2024 | Zone 3 PBH59 |  | SI started
Fri (22/03) | 22 Mar 2024 | Zone 2 |  | Hacking for tactile installation
Fri (22/03) | 22 Mar 2024 | Zone 2 |  | Tactile installation works
Fri (22/03) | 22 Mar 2024 | ST84 | half | Guidewall rebar works in progress
Fri (22/03) | 22 Mar 2024 | CBP31 |  | Rebar cage installation in progress, CB21: Preboring ongoing
Fri (22/03) | 22 Mar 2024 | P11-2 |  | Preparation works to start pile head hacking
Fri (22/03) | 22 Mar 2024 | Zone 2 |  | Concrete barriers painting in progress
Fri (22/03) | 22 Mar 2024 | Zone 2 |  | Signages installation ongoing
Fri (22/03) | 22 Mar 2024 | ST78 |  | Water stop endplate installation ongoing
Fri (22/03) | 22 Mar 2024 | ST73A |  | First bite excavation in progress
Fri (22/03) | 22 Mar 2024 | ST183 |  | 2nd bite excavation temporarily stopped. Mud pump change ongoing
Fri (22/03) | 22 Mar 2024 | P28 |  | Seongha demobilising materials that were shifted from exit 3
Fri (22/03) | 22 Mar 2024 | Exit 3 |  | Levelling works ongoing. Seongha materials shifted to P28 area
Fri (22/03) | 22 Mar 2024 | MH1-2 |  | Current status for singtel haunching manual hacking works
Fri (22/03) | 22 Mar 2024 | Zone 1 existing sewer |  | Reinstating cover ongoing
Fri (22/03) | 22 Mar 2024 | Zone 4 P46 |  | TT to find starhub and army cable for localised shifting
Fri (22/03) | 22 Mar 2024 | Zone 4 |  | Spoil disposal
Fri (22/03) | 22 Mar 2024 | Zone 4 ULT12 |  | 3rd cycle in progress at 150% loading. Average expansion at 17-18mm
Fri (22/03) | 22 Mar 2024 | Zone 4 |  | JGP, 2 nos completed today. 5/608 completed
Fri (22/03) | 22 Mar 2024 | Zone 3 P22 |  | Last 3 NB footing casting in progress. Tomorrow plan to install i-beams, 14 pcs
Fri (22/03) | 22 Mar 2024 | S4 |  | Preboring for SP&LP done for the day. 2/33 completed
Fri (22/03) | 22 Mar 2024 | P11-2 |  | BP hacking 2/3 completed. Work till 7pm
Fri (22/03) | 22 Mar 2024 | ST78 |  | Cleaning and desanding done. Prepare for final koden test
Fri (22/03) | 22 Mar 2024 | ST189 |  | First bite excavation in progress
Fri (22/03) | 22 Mar 2024 | ST185 |  | Preboring in progress
Sun (24/03) | 24 Mar 2024 | MH2-10 |  | Trial trench in progress
Mon (25/03) | 25 Mar 2024 | Zone 4 |  | No activity
Mon (25/03) | 25 Mar 2024 | N5 |  | Scaffold erection status for pier construction. 2/4 sides completed
Mon (25/03) | 25 Mar 2024 | P11-2 |  | Pile head hacking continue for the last pile
Mon (25/03) | 25 Mar 2024 | Zone 2 |  | Preparation for setting up boring rig
Mon (25/03) | 25 Mar 2024 | Zone 2 |  | Preparation for hacking of kerb and premix for BP TT works
Mon (25/03) | 25 Mar 2024 | S4 |  | Preboring for soldier pile ongoing
Mon (25/03) | 25 Mar 2024 | P11-2 |  | Pending for casting. Checks done by RTO earlier
Mon (25/03) | 25 Mar 2024 | Zone 1 P3 |  | No activity
Mon (25/03) | 25 Mar 2024 | Zone 1 |  | Cable works ongoing by Vistek
Mon (25/03) | 25 Mar 2024 | Zone 1 |  | Existing sewer MH water test was done earlier today. Benching works ongoing
Mon (25/03) | 25 Mar 2024 | MH1-2 |  | Continue wall rebar works
Mon (25/03) | 25 Mar 2024 | ST179 |  | First bite excavation in progress, 13.8m
Mon (25/03) | 25 Mar 2024 | ST166A |  | First bite ongoing, 21m
Mon (25/03) | 25 Mar 2024 | ST73A |  | Preparation for water stop endplate extraction
Tue (26/03) | 26 Mar 2024 | MH1-2 |  | Casting start
Tue (26/03) | 26 Mar 2024 | BP6D-2 |  | Casting completed at 2217hrs
Tue (26/03) | 26 Mar 2024 | P11-2 |  | KTC final levelling
Tue (26/03) | 26 Mar 2024 | Zone 2 |  | Premix hacking for BP Trial trench
Tue (26/03) | 26 Mar 2024 | S4 |  | Pre-boring for ERSS continue
Tue (26/03) | 26 Mar 2024 | MH1-2 |  | Rebar tying on going. Target to cast today evening
Tue (26/03) | 26 Mar 2024 | MH1-2 |  | Continue wall rebar installation for 4th layer
Tue (26/03) | 26 Mar 2024 | ST179 |  | Continue first bite excavation
Tue (26/03) | 26 Mar 2024 | N5 |  | Scaffold erection in progress
Tue (26/03) | 26 Mar 2024 | P11-2 |  | Lean con casting done
Tue (26/03) | 26 Mar 2024 | MH1-2 |  | Preparing for casting
Tue (26/03) | 26 Mar 2024 | Zone 1 |  | No other activity
Tue (26/03) | 26 Mar 2024 | ST179 |  | Cutter teeth wheel changing in progress
Tue (26/03) | 26 Mar 2024 | ST166A |  | First bite in progress, 27.4m
Tue (26/03) | 26 Mar 2024 | ST73A |  | Rebar cage installation in progress, 4/4nos
Tue (26/03) | 26 Mar 2024 | ST77 |  | Excavation temporarily stopped. Rectification ongoing for desander cyclone part. Current depth at 10.2m
Tue (26/03) | 26 Mar 2024 | Zone 4 |  | No activity
Wed (27/03) | 27 Mar 2024 | ST185 |  | First bite excavation in progress, 15.1m
Wed (27/03) | 27 Mar 2024 | N5 |  | Scaffold installation in progress, today to complete
Wed (27/03) | 27 Mar 2024 | P11-2 |  | Guidebar installation started for pile cap
Wed (27/03) | 27 Mar 2024 | Zone 1 P3 |  | LECE drilling works for gas pipe protection ongoing
Wed (27/03) | 27 Mar 2024 | MH1-2 |  | 4th layer cast. This afternoon to dismantle formwork and prepare roof slab construction
Wed (27/03) | 27 Mar 2024 | Zone 1 | SB side | Road widening for stage 1 diversion
Wed (27/03) | 27 Mar 2024 | MH1-2 |  | Casting completed
Wed (27/03) | 27 Mar 2024 | Bet. P22 & P21 |  | Noise barriers bracings and panels installation in progress
Wed (27/03) | 27 Mar 2024 | P11-2 |  | Rebar installation for pile cap
Wed (27/03) | 27 Mar 2024 | Zone 2 | P9 & P10 | Trial trenches work for BP
Wed (27/03) | 27 Mar 2024 | MH1-2 |  | 4th layer Formwork dismantle & removal ongoing
Wed (27/03) | 27 Mar 2024 | Zone 1 | SB side | Road widening for stage 1 diversion
Wed (27/03) | 27 Mar 2024 | ST166A |  | 2nd bite excavation in progress
Wed (27/03) | 27 Mar 2024 | Zone 1 |  | CGS pipe laying for lamp post
Wed (27/03) | 27 Mar 2024 | Zone 2 |  | CGS Formwork installation for footpath works
Wed (27/03) | 27 Mar 2024 | ST73A |  | Preparing for casting
Wed (27/03) | 27 Mar 2024 | MH5-2 |  | Soil clearing & houskeeping works ongoing. Tmr to start on the jacking frame works
Wed (27/03) | 27 Mar 2024 | Zone 1 P3 |  | No activity
Wed (27/03) | 27 Mar 2024 | Zone 3 |  | Bentonite hoses removal and levelling ongoing
Wed (27/03) | 27 Mar 2024 | BP6A-6 |  | Pre-boring, BP6D-2: LSS backfilling
Wed (27/03) | 27 Mar 2024 | P22 |  | Noise barriers bracings installation in progress
Wed (27/03) | 27 Mar 2024 | Zone 2 |  | CGS hacking of premix for DIC extension ongoing
Wed (27/03) | 27 Mar 2024 | ST77 |  | First bite excavation in progress
Thu (28/03) | 28 Mar 2024 | Bet P22-P21 |  | Noise barrier panels installation works
Thu (28/03) | 28 Mar 2024 | Zone 2 Bus-only lane |  | Footpath casting works. Today to cast finish the balance footpath
Thu (28/03) | 28 Mar 2024 | N5 |  | Rebar installation for column works ongoing
Thu (28/03) | 28 Mar 2024 | N3 |  | Scaffold installation works
Thu (28/03) | 28 Mar 2024 | P11-2 |  | Top rebar installation for pile cap
Thu (28/03) | 28 Mar 2024 | P10 |  | Trial trenches completed. Now reinstatement works
Thu (28/03) | 28 Mar 2024 | P9 |  | Premix hacking and removal for BP trial trench works
Thu (28/03) | 28 Mar 2024 | MH5-2 |  | Soil clearing works ongoing
Thu (28/03) | 28 Mar 2024 | P3 |  | Gas pipe protection works - 2 nos. I beams installed. Now preparing to install balance 2 main beams for traffic decking
Thu (28/03) | 28 Mar 2024 | S4 |  | Preboring for ERSS installation ongoing
Thu (28/03) | 28 Mar 2024 | ST166A |  | Preparation for casting
Thu (28/03) | 28 Mar 2024 | ST77 |  | Continue first bite excavation
Thu (28/03) | 28 Mar 2024 | ST97 |  | Guidewall rebar works ongoing. Plan for casting today
Fri (29/03) | 29 Mar 2024 | Zone 2 | Near exit 3 | Levelling works for vehicular access
Fri (29/03) | 29 Mar 2024 | Zone 2 |  | CGS footpath Formwork dismantle ongoing
Fri (29/03) | 29 Mar 2024 | Zone 2 |  | CGS DIC extension works
Fri (29/03) | 29 Mar 2024 | N5 |  | Current status for rebar installation for column works
Fri (29/03) | 29 Mar 2024 | P11-2 |  | Shear links installation for pile cap ongoing
Fri (29/03) | 29 Mar 2024 | P9 |  | Premix removal for trial trench works
Fri (29/03) | 29 Mar 2024 | S4 |  | Preboring ongoing for ERSS installation
Fri (29/03) | 29 Mar 2024 | P3 |  | Traffic decking secondary beams installation
Fri (29/03) | 29 Mar 2024 | MH1-2 |  | Scaffold works ongoing
Fri (29/03) | 29 Mar 2024 | Zone 4 |  | No activity
Fri (29/03) | 29 Mar 2024 | Zone 4 | Outside working boundary | Englam doing drain works
Fri (29/03) | 29 Mar 2024 | Zone 3 | ST-98 | Guidewall excavation works
Fri (29/03) | 29 Mar 2024 | ST-77 |  | Resumed 2nd bite excavation works
Fri (29/03) | 29 Mar 2024 | ST-179 |  | 2nd bite excavation currently stopped due to desander issue. Depth: 23m
Fri (29/03) | 29 Mar 2024 | ST-185 |  | 1st bite excavation ongoing, current depth 27.2m/28m
Fri (29/03) | 29 Mar 2024 | ST-185 |  | Excavation work temporary stop due to cutter teeth change. Current depth 1st bite: 27.9m/28m
Fri (29/03) | 29 Mar 2024 | ST-179 |  | Continue 2nd bite excavation. Current depth 23.5m/24.1m
Fri (29/03) | 29 Mar 2024 | ST-77 |  | 2nd bite excavation temporary stopped due to desander issue and cutter teeth change, current depth 28m
Fri (29/03) | 29 Mar 2024 | P11-2 |  | Continue Shear links & Formwork installation for pile cap
Fri (29/03) | 29 Mar 2024 | P3 |  | Current status for traffic decking secondary beams installation. Balance 3 nos. SB. Tmr to continue
Sat (30/03) | 30 Mar 2024 | P11-2 |  | Casting completed
Sat (30/03) | 30 Mar 2024 | Zone 2 |  | Access casting ongoing
Sat (30/03) | 30 Mar 2024 | P11-2 |  | First truck arrived. Preparing to start casting
Sat (30/03) | 30 Mar 2024 | P11-2 |  | Casting started
Sat (30/03) | 30 Mar 2024 | ST77 |  | Trimming ongoing
Sat (30/03) | 30 Mar 2024 | ST179 |  | Bite 3 in progress
Sat (30/03) | 30 Mar 2024 | ST185 |  | Bite 3 started at 2126hrs
Sun (31/03) | 31 Mar 2024 | ST185 |  | Bite 3 cleaning ongoing
Sun (31/03) | 31 Mar 2024 | ST179 |  | 3rd bite cleaning in progress
Mon (01/04) | 01 Apr 2024 | Exit 3 |  | Compaction works for new vehicular access
Mon (01/04) | 01 Apr 2024 | Bet. P22-P21 |  | Noise barrier panels installation. Today to complete
Mon (01/04) | 01 Apr 2024 | P45-P46 |  | Status of premix and rigid pavement hacking
Mon (01/04) | 01 Apr 2024 | P46-P47 |  | Continue drilling and grouting for JGP
Mon (01/04) | 01 Apr 2024 | Zone 2 |  | CGS DIC extension works
Mon (01/04) | 01 Apr 2024 | N5 |  | Column rebar installation works in progress. Manpower - 3
Mon (01/04) | 01 Apr 2024 | Zone 2 |  | New foopath opened for public access
Mon (01/04) | 01 Apr 2024 | N3 |  | Scaffold platform installation in progress. Manpower - 2
Mon (01/04) | 01 Apr 2024 | P11-2 |  | Shear links installation for column stage 1 works
Mon (01/04) | 01 Apr 2024 | Zone 2 |  | HSL crane assembly works
Mon (01/04) | 01 Apr 2024 | MH5-2 |  | Thrust block hacking completed
Mon (01/04) | 01 Apr 2024 | Zone 1 |  | ECM removal works in progress
Mon (01/04) | 01 Apr 2024 | P3 |  | Bolts tightening for traffic decking beams ongoing
Mon (01/04) | 01 Apr 2024 | MH1-2 |  | Debris clearing for pipe installation works
Mon (01/04) | 01 Apr 2024 | Bet LP200/1 & LP200 |  | CGS lamp post pipe laying works
Mon (01/04) | 01 Apr 2024 | BP6A-6 |  | Tremie pipe preparation for casting
Mon (01/04) | 01 Apr 2024 | MH5-2 |  | Jacking frame shifted to correct position. To continue with thrust block work
Mon (01/04) | 01 Apr 2024 | P11-2 |  | Shear link installation for column
Mon (01/04) | 01 Apr 2024 | MH1-2 |  | Clearing unused materials inside shaft
Mon (01/04) | 01 Apr 2024 | Near Gate 5 |  | Hardcore clearing ongoing
Mon (01/04) | 01 Apr 2024 | Zone 2 |  | Clearing hardcore
Mon (01/04) | 01 Apr 2024 | MH5-2 |  | No activity
Mon (01/04) | 01 Apr 2024 | MH1-2/P3 |  | No activity
Mon (01/04) | 01 Apr 2024 | ST73 |  | First bite excavation ongoing
Mon (01/04) | 01 Apr 2024 | ST77 |  | Rebar cage installation in progress, 7/8nos
Mon (01/04) | 01 Apr 2024 | ST190 |  | Rectification ongoing due to leakage
Mon (01/04) | 01 Apr 2024 | ST187 |  | First bite excavation ongoing, 16.4m
Tue (02/04) | 02 Apr 2024 | MH5-2 |  | Thrust wall casting completed
Tue (02/04) | 02 Apr 2024 | P11-2 |  | Formwork installation for column stage 1 works
Tue (02/04) | 02 Apr 2024 | P12 - P13 |  | Premix hacking and removal works for BP trial trench
Tue (02/04) | 02 Apr 2024 | N3 |  | Scaffold platform installation works. Manpower - 3
Tue (02/04) | 02 Apr 2024 | N5 |  | Current status for column rebar works
Tue (02/04) | 02 Apr 2024 | Exit 3 |  | Hardcores laying for vehicular access
Tue (02/04) | 02 Apr 2024 | ST77 |  | Hanging bar installation ongoing
Tue (02/04) | 02 Apr 2024 | ST190 |  | BC cutter rectification still ongoing
Tue (02/04) | 02 Apr 2024 | Near Exit 2 |  | Frame installation for noise barrier panel
Tue (02/04) | 02 Apr 2024 | P11-2 |  | Formwork closing continue
Tue (02/04) | 02 Apr 2024 | P10 |  | Material clearing in preparation for BP works. Tomorrow to start boring works, rebar delivery tomorrow
Tue (02/04) | 02 Apr 2024 | MH5-2 |  | Jacking frame position adjusted. Formwork closing on going for thrust block
Tue (02/04) | 02 Apr 2024 | P3 |  | Gas supports installation works ongoing
Tue (02/04) | 02 Apr 2024 | S4 |  | Installation of ERSS in progress
Tue (02/04) | 02 Apr 2024 | MH1-2 |  | Material clearing and hardcore for double flange installation. Tomorrow start installation including vortex pipe
Tue (02/04) | 02 Apr 2024 | Zone 4 |  | Point #B-154, Trial trench excavation, Hand Augering and Pipe sleeve installation completed. No more activity
Tue (02/04) | 02 Apr 2024 | Zone 4 |  | Pavement continue hacking for JGP works
Tue (02/04) | 02 Apr 2024 | Zone 3 |  | ST99 guidewall formwork closing
Tue (02/04) | 02 Apr 2024 | ST077 |  | Casting completed. Total volume 196 m3
Tue (02/04) | 02 Apr 2024 | ST073 |  | 2nd bite trenching in progress, 16/29.45m depth
Tue (02/04) | 02 Apr 2024 | ST190 |  | 1st bite trenching at 24.1m
Tue (02/04) | 02 Apr 2024 | N3 |  | Scaffold installation ongoing
Tue (02/04) | 02 Apr 2024 | P12 |  | Trial trench for BP works
Tue (02/04) | 02 Apr 2024 | P3 and MH1-2 |  | No activity
Tue (02/04) | 02 Apr 2024 | MH5-2 |  | Thrust wall pending for casting
Tue (02/04) | 02 Apr 2024 | ST187 |  | 2nd bite excavation in progress, 16m
Tue (02/04) | 02 Apr 2024 | MH5-2 |  | Concrete truck on site
Tue (02/04) | 02 Apr 2024 | Zone 4 |  | No activity
Tue (02/04) | 02 Apr 2024 | Zone 3 |  | 180T crane boom and counter weights on site
Tue (02/04) | 02 Apr 2024 | ST73 |  | Cutter teeth replacement ongoing
Tue (02/04) | 02 Apr 2024 | Exit 3 vehicular access |  | Hardcore laid and compacted
Wed (03/04) | 03 Apr 2024 | Zone 2 |  | GI pipe installation for access walkway
Wed (03/04) | 03 Apr 2024 | Zone 2 |  | CGS DIC extension and hacking works
Wed (03/04) | 03 Apr 2024 | N3 |  | Scaffold erection for pier continue
Wed (03/04) | 03 Apr 2024 | P11-2 |  | Column stump formwork closing continue
Wed (03/04) | 03 Apr 2024 | MH5-2 |  | Jacking frame and platform setting up for pipe jacking towards MH5-1
Wed (03/04) | 03 Apr 2024 | P3 |  | Traffic decking panels installation works
Wed (03/04) | 03 Apr 2024 | MH1-2 |  | Hacking works for duckfoot bend for pipe installation ongoing
Wed (03/04) | 03 Apr 2024 | Zone 1 |  | CGS excavation works for rca backfilling in progress
Wed (03/04) | 03 Apr 2024 | Exit 3 |  | Slope casting for the new access
Wed (03/04) | 03 Apr 2024 | Zone 2 |  | Bentonite pipe laying for BP works for main viaducts
Wed (03/04) | 03 Apr 2024 | N3 |  | Scaffold erection status, balance toe boards and tie backs
Wed (03/04) | 03 Apr 2024 | P13 |  | Premix hacking continue
Wed (03/04) | 03 Apr 2024 | P12 |  | TT for top piles completed. 3 piles affected by HV
Wed (03/04) | 03 Apr 2024 | P10-4 |  | Preparation for pre-boring and casing installation
Wed (03/04) | 03 Apr 2024 | MH5-2 |  | Entry opening hacking in progress
Wed (03/04) | 03 Apr 2024 | MH1-2 |  | Wall hacking for double flange installation continue. Tomorrow to install vortex pipe
Wed (03/04) | 03 Apr 2024 | Zone 1 |  | Top soil removal for road widening continue
Wed (03/04) | 03 Apr 2024 | ST187 |  | Continue 2nd bite
Wed (03/04) | 03 Apr 2024 | ST190 |  | Resume first bite excavation
Wed (03/04) | 03 Apr 2024 | ST73 |  | Trimming ongoing
Wed (03/04) | 03 Apr 2024 | S4 |  | Soldier pile installation continue. To complete tomorrow
Wed (03/04) | 03 Apr 2024 | P10-1-4 |  | Casing installation
Wed (03/04) | 03 Apr 2024 | Near gate 5 |  | Levelling works
Wed (03/04) | 03 Apr 2024 | Zone 2 |  | Barricade installation along designated access
Wed (03/04) | 03 Apr 2024 | P3 and MH1-2 |  | No activity
Wed (03/04) | 03 Apr 2024 | Zone 2 |  | Scupper pipe installation by CGS till 10pm
Wed (03/04) | 03 Apr 2024 | BC Cutter 1 |  | Cutter teeth changing ongoing
Wed (03/04) | 03 Apr 2024 | Zone 4 |  | No activity
Wed (03/04) | 03 Apr 2024 | ST187 |  | Preparing for internal koden check for B2
Wed (03/04) | 03 Apr 2024 | ST190 |  | 2nd bite in progress
Wed (03/04) | 03 Apr 2024 | Near Gate 5 |  | Steel plate laying ongoing
Thu (04/04) | 04 Apr 2024 | N3 |  | Pier rebar installation started
Thu (04/04) | 04 Apr 2024 | P10-2 |  | Casing installed
Thu (04/04) | 04 Apr 2024 | MH5-2 |  | Hacking for entry opening almost complete, trimming on going. Boring machine testing in progress before lowering
Thu (04/04) | 04 Apr 2024 | MH1-2 |  | Double flange lowered. Now preparing to cut cast iron pipe for benching at the maintenance pit. Today plan to cast 1st layer of mass concrete at vortex pit
Thu (04/04) | 04 Apr 2024 | P3 |  | Deck panel installation in progress, 38/85 completed
Thu (04/04) | 04 Apr 2024 | Zone 1 towards PRD3 |  | D1 kerb installed
Thu (04/04) | 04 Apr 2024 | S4 |  | Balance 4 SP and 8 LP to complete installation by today
Thu (04/04) | 04 Apr 2024 | Zone 2 | Prev. Bus only lane | Continue premix hacking & drop inlet pipe extension works
Thu (04/04) | 04 Apr 2024 | P16 |  | Premix hacking for BP trial trench ongoing
Thu (04/04) | 04 Apr 2024 | N3 |  | Pier rebar installation continue
Thu (04/04) | 04 Apr 2024 | Zone 2 |  | HSL bentonite pipes laying & connecting works
Thu (04/04) | 04 Apr 2024 | MH5-2 |  | Trimming completed. Debris clearing and pending RTO inspection for boring machine before lowering
Thu (04/04) | 04 Apr 2024 | S4 |  | Continue ERSS installation. Today to complete
Thu (04/04) | 04 Apr 2024 | P3 |  | Deck panel installation continue
Thu (04/04) | 04 Apr 2024 | ST190 |  | 2nd bite in progress, 17.4m
Thu (04/04) | 04 Apr 2024 | MC86 |  | NB frame installation ongoing
Thu (04/04) | 04 Apr 2024 | ST73 |  | Trimming ongoing
Thu (04/04) | 04 Apr 2024 | Zone 4 |  | JGP grouting in progress, pt. B-268. JGP plant repair works just completed. Today 1 pt can complete. 25/608 as of today
Thu (04/04) | 04 Apr 2024 | ST73 |  | Trimming at water stop side on going
Thu (04/04) | 04 Apr 2024 | ST180 |  | Positioning BC cutter to start trenching
Thu (04/04) | 04 Apr 2024 | ST190 |  | 2nd bite excavation on going, current depth 18m
Thu (04/04) | 04 Apr 2024 | ST192 |  | PB2 LSS backfilling completed. Housekeeping
Thu (04/04) | 04 Apr 2024 | Zone 2 JTC blk 2 |  | Area leveling for fissure grouting. Seongha till 7pm
Thu (04/04) | 04 Apr 2024 | Zone 3 |  | Utility King Post delivery, 18/49 pcs
Thu (04/04) | 04 Apr 2024 | P10-1-4 |  | Lowering down rebar cage in progress. Plan to cast around 10PM
Thu (04/04) | 04 Apr 2024 | MH1-2 |  | Continue clearing materials. Tonight plan to cast the invert
Fri (05/04) | 05 Apr 2024 | Zone 2 |  | Drop inlet pipe connection to existing drain continue. 19/24 completed
Fri (05/04) | 05 Apr 2024 | N3 |  | Pier rebar works continue. 3+2, 2nd day for rebar works, est 12 tonnes
Fri (05/04) | 05 Apr 2024 | Zone 3 |  | Krishco replacing waterpipe flange
Fri (05/04) | 05 Apr 2024 | ST73 |  | Trimming ongoing
Fri (05/04) | 05 Apr 2024 | ST190 |  | 2nd bite in progress, ST193: Preparation ongoing for preboring
Fri (05/04) | 05 Apr 2024 | Main viaduct P14-15 |  | Pavement hacking for BP works
Fri (05/04) | 05 Apr 2024 | P9-4 |  | Preparation for casing installation
Fri (05/04) | 05 Apr 2024 | MH5-2 |  | Water top up prior to jacking
Fri (05/04) | 05 Apr 2024 | Zone 1 |  | Preparation for NB footing construction
Fri (05/04) | 05 Apr 2024 | P28 |  | Fissure grout point, I-163 depth check and installation of PVC cotton packer
Fri (05/04) | 05 Apr 2024 | BH156 |  | SI almost completed, 42m
Fri (05/04) | 05 Apr 2024 | DW21 |  | Preparing for trenching works
Fri (05/04) | 05 Apr 2024 | Zone 1 | SB side | Road widening for stage 1 diversion continue
Fri (05/04) | 05 Apr 2024 | MH1-2 |  | Double flange installed and cast yesterday
Fri (05/04) | 05 Apr 2024 | N3 |  | Main bars installation completed. Shearlinks in progress
Fri (05/04) | 05 Apr 2024 | Zone 3 |  | Trial trench for utility KP ongoing
Fri (05/04) | 05 Apr 2024 | ST193 |  | Preboring ongoing
Fri (05/04) | 05 Apr 2024 | DW21 |  | First bite excavation in progress
Fri (05/04) | 05 Apr 2024 | P9-4 |  | Casing installed. Preparation for boring
Fri (05/04) | 05 Apr 2024 | MH5-2 |  | Control panel has technical issues, boring machine dismantled. Mechanic on the way
Fri (05/04) | 05 Apr 2024 | MH1-2 |  | Vortex pipe installation in progress
Fri (05/04) | 05 Apr 2024 | N3 |  | Pier shearlinks installation continue
Fri (05/04) | 05 Apr 2024 | P11-2 |  | Column stump final inspection completed. Waiting for concrete lorry to cast
Fri (05/04) | 05 Apr 2024 | P9-4 |  | Boring in progress, 15/21.8m. To cast tonight
Fri (05/04) | 05 Apr 2024 | MH1-2 |  | 1st layer vortex drop installed. Concrete ordered for casting
Fri (05/04) | 05 Apr 2024 | S4 |  | Lowering of ERSS almost complete. Tomorrow KTC to excavate till W1 layer
Fri (05/04) | 05 Apr 2024 | ST190 |  | 2nd bite trenching, current depth 19.15m
Fri (05/04) | 05 Apr 2024 | ST187 |  | Cleaning and desanding compl. waterstop lowering
Fri (05/04) | 05 Apr 2024 | ST180 |  | Cutter wheel maintenance. Air valve need to replace. Target to start trenching tonight
Fri (05/04) | 05 Apr 2024 | ST73 |  | Cutter wheel replacement. Current 2nd bite at 19m
Fri (05/04) | 05 Apr 2024 | ST192 |  | PB2 pre-boring works, 23m/35m
Fri (05/04) | 05 Apr 2024 | Exit 3 DW21 |  | 1st bite trenching halted due to rig engine issue. Current depth at 10m
Fri (05/04) | 05 Apr 2024 | ST-190 |  | Excavation temporary stop due to cutter teeth changing. Reached 18.9m/25.3m
Fri (05/04) | 05 Apr 2024 | P9-1-4 |  | Rebar cage lowering in progress. Plan to cast around 11PM
Fri (05/04) | 05 Apr 2024 | MH1-2 |  | Casting of mass concrete
Fri (05/04) | 05 Apr 2024 | PBH62 |  | In progress, 31m
Fri (05/04) | 05 Apr 2024 | DR1 |  | Trial trench in progress
Sat (06/04) | 06 Apr 2024 | MH1-2 |  | Mass concrete casting in progress
Sat (06/04) | 06 Apr 2024 | Zone-2 north ramp |  | P11-1-4 : casting in progress
Sat (06/04) | 06 Apr 2024 | DW21 |  | Tonight continue noise barrier panel installation
Sat (06/04) | 06 Apr 2024 | ST187 |  | Cage A (3/3 done), Cage B 3/3 lapping in progress. Tonight plan to cast
Sun (07/04) | 07 Apr 2024 | MH5-2 |  | 3rd pipe completed. Preparation to jack 4th pipe
Sun (07/04) | 07 Apr 2024 | MH1-2 |  | Vortex pipe completed. Today to install ring for incoming pipe
Sun (07/04) | 07 Apr 2024 | Zone 4 |  | Singtel cable recovery
Sun (07/04) | 07 Apr 2024 | Zone 4 |  | Soil disposal
Sun (07/04) | 07 Apr 2024 | B209 |  | JGP grouting. Today target 2 nos
Sun (07/04) | 07 Apr 2024 | ST187 |  | Casting complete, total volume 215 m3
Sun (07/04) | 07 Apr 2024 | ST180 |  | 2nd bite excavtion on going
Sun (07/04) | 07 Apr 2024 | ST73 |  | Trimmimg on going
Sun (07/04) | 07 Apr 2024 | ST190 |  | 2nd bite trenching resumed
Sun (07/04) | 07 Apr 2024 | Zone 3 |  | Seongha no activity
Sun (07/04) | 07 Apr 2024 | Exit 3 |  | DW21 BC cutter hydraulic hose burst, need to repair. 1st bite still at 10m depth
Sun (07/04) | 07 Apr 2024 | ST187 |  | Rebar cages lowering down completed. Lowering down tremie pipes in progress
Sun (07/04) | 07 Apr 2024 | Zone 4 |  | B211 JGP grouting in progress. 2nd point for the day
Sun (07/04) | 07 Apr 2024 | MH5-2 |  | 5th pipe jacking on going
Sun (07/04) | 07 Apr 2024 | ST190 |  | 2nd bite trenching continue at 23.m
Sun (07/04) | 07 Apr 2024 | ST180 |  | 2nd bite trenching at 21.8m
Sun (07/04) | 07 Apr 2024 | ST184 |  | Pre-excavation in progress
Sun (07/04) | 07 Apr 2024 | ST73 |  | Trimming paused temporarily
Sun (07/04) | 07 Apr 2024 | ST187 |  | Casting in progress, 75m3/ 190m3
Mon (08/04) | 08 Apr 2024 | ST190 |  | 2nd bite, current depth at 24.5m
Mon (08/04) | 08 Apr 2024 | ST184 |  | 1st bite at 8m. Night shift no Operator, currently at DW21
Mon (08/04) | 08 Apr 2024 | ST180 |  | Rebar cage installation, 4th cage lowering
Mon (08/04) | 08 Apr 2024 | ST73 |  | 2nd bite trimming continue
Mon (08/04) | 08 Apr 2024 | DW21 |  | 1st bite excavtion on going
Mon (08/04) | 08 Apr 2024 | DW21 |  | First bite excavation temporarily stopped due to very hot engine. Excavation to resume after about 30mins
Mon (08/04) | 08 Apr 2024 | Zone 3 |  | Rectification ongoing for 80T crane
Mon (08/04) | 08 Apr 2024 | Exit 3 |  | Vehicular access casting ongoing
Mon (08/04) | 08 Apr 2024 | Zone 2 |  | CGS excavation for drop inlet pipes installation works
Mon (08/04) | 08 Apr 2024 | Zone 2 |  | Column pre-fab rebar works for n4 in progress. Manpower - 6
Mon (08/04) | 08 Apr 2024 | P11-1 |  | Premix hacking for bp trial trenches works
Mon (08/04) | 08 Apr 2024 | N2 |  | Scaffold installation status, 50% completed
Mon (08/04) | 08 Apr 2024 | P10-1-6 |  | BP boring completed, preparation works for rebar cage lowering in progress
Mon (08/04) | 08 Apr 2024 | S4 |  | KTC excavation to W1 layer in progress, today to complete
Mon (08/04) | 08 Apr 2024 | MH5-2 to MH5-1 |  | 7th nos. Pipe jacking works ongoing. 7/47 pipes completed
Mon (08/04) | 08 Apr 2024 | MH1-2 |  | Scaffold installation for 5th layer wall casting
Mon (08/04) | 08 Apr 2024 | Zone 3 |  | Krishco continue replacing WP flange
Mon (08/04) | 08 Apr 2024 | ST180 |  | Rebar cage installation ongoing, 2/4nos
Mon (08/04) | 08 Apr 2024 | Zone 1, south bound |  | CGS hacking works for DIC installation
Mon (08/04) | 08 Apr 2024 | Zone 1, north bound |  | CGS preparing for RCA backfilling works for kerb installation
Mon (08/04) | 08 Apr 2024 | ST190 |  | 2nd bite excavation in progress
Mon (08/04) | 08 Apr 2024 | P29 |  | Fissure grout point O-101 depth checked and cotton packer installation ongoing
Mon (08/04) | 08 Apr 2024 | UKP-31 |  | Preboring started for casing installation. This is the first UKP work
Mon (08/04) | 08 Apr 2024 | P10-1-6 |  | Concrete ordered, 32.5m3
Mon (08/04) | 08 Apr 2024 | P9-1-5 |  | Casing installed. Boring started
Mon (08/04) | 08 Apr 2024 | MH5-2 |  | Jacking in progress for Pipe No-8. 7/47nos was done
Mon (08/04) | 08 Apr 2024 | BP6-1 |  | Prepare to install steel plate protection for bored pile work
Mon (08/04) | 08 Apr 2024 | P10-1-6 |  | Casting in progress, last load total volume 32.5 m3
Mon (08/04) | 08 Apr 2024 | P9-1-5 |  | Casing installed
Mon (08/04) | 08 Apr 2024 | MH5-2 |  | Pipe jacking stopped for the day. Total 8 pipes completed
Mon (08/04) | 08 Apr 2024 | S4 |  | Slope casting completed. Excavation to W1 also completed
Tue (09/04) | 09 Apr 2024 | Exit 1 |  | Krishco preparing formwork for water pipe haunching
Tue (09/04) | 09 Apr 2024 | DW21 |  | Hydraulic hose leaking, need to replace. 2nd bite yet to start
Tue (09/04) | 09 Apr 2024 | P29 |  | Fissure grout point O-95 drilling in progress
Tue (09/04) | 09 Apr 2024 | DW21 |  | First bite excavation completed, 32m
Tue (09/04) | 09 Apr 2024 | DW21 |  | BC cutter teeth replacement
Tue (09/04) | 09 Apr 2024 | MH1-2 |  | Balance scaffold erection and rebar work for shaft wall
Tue (09/04) | 09 Apr 2024 | Zone 1 | North bound | CGS Excavation for lamp post pipe laying works
Tue (09/04) | 09 Apr 2024 | Zone 1 | South bound | CGS Hardcores removal and rca levelling for DIC installation
Tue (09/04) | 09 Apr 2024 | Zone 2 |  | P9-1-5 BP boring works completed. Now preparation for rebar cage lowering
Tue (09/04) | 09 Apr 2024 | P11-1 |  | Premix removal for BP trial trench works
Tue (09/04) | 09 Apr 2024 | N1 |  | Preparation to start N1 column rebar cage prefabrication
Tue (09/04) | 09 Apr 2024 | Zone 4 |  | BH119- TT on going by Dongah for SI work
Tue (09/04) | 09 Apr 2024 | N4 |  | Column rebar cage fabrication completed
Tue (09/04) | 09 Apr 2024 | ST180 |  | Tremie pipes installed. Concrete ordered
Tue (09/04) | 09 Apr 2024 | ST73 |  | Excavation for 2nd bite continue, current depth 23.5m
Tue (09/04) | 09 Apr 2024 | ST190 |  | Excavation for 2nd bite continue, depth 24.75m
Tue (09/04) | 09 Apr 2024 | ST190 |  | Cutter wheel teeth replacement. Current depth 25.2m, balance 300mm to excavate
Tue (09/04) | 09 Apr 2024 | ST73 |  | 2nd bite trenching continue, 24.2m/29.2
Tue (09/04) | 09 Apr 2024 | ST180 |  | Casting in progress. 92/148 m3
Tue (09/04) | 09 Apr 2024 | DW21 |  | Trenching continue for 1st bite
Tue (09/04) | 09 Apr 2024 | Zone 2 |  | Material shifting and housekeeping by WH
Tue (09/04) | 09 Apr 2024 | Zone 2 |  | Hardcore segregation by WH till 9pm
Tue (09/04) | 09 Apr 2024 | ST180 |  | Casting completed. Total volume: 156m3
Tue (09/04) | 09 Apr 2024 | DR1 |  | LE to continue trial trench today
Tue (09/04) | 09 Apr 2024 | Zone 3 |  | PBH73 hand auger in progress
Tue (09/04) | 09 Apr 2024 | ST190 |  | 3rd Bite trenching started
Tue (09/04) | 09 Apr 2024 | ST184 |  | Hydraulic hose replacement and flap replacement continue
Tue (09/04) | 09 Apr 2024 | ST73 |  | Cutter wheel teeth replacement, current at 2nd bite 24.7m
Wed (10/04) | 10 Apr 2024 | MH5-2 |  | Pipe No-12 set up for jacking in progress
Wed (10/04) | 10 Apr 2024 | MH1-2 |  | Typing of balance wall rebar and formwork closing
Wed (10/04) | 10 Apr 2024 | DW21 |  | 2nd bite at 28m depth. Now cutter hoisting up to replace teeth
Wed (10/04) | 10 Apr 2024 | ST73 |  | Teeth holder welding
Wed (10/04) | 10 Apr 2024 | ST190 |  | 3rd bite trenching continue
Wed (10/04) | 10 Apr 2024 | MH1-2 |  | Formwork closing and adjusting in progress
Wed (10/04) | 10 Apr 2024 | MH5-2 |  | Pipe No-12 jacking done. Preparing for Pipe No-13 jacking
Wed (10/04) | 10 Apr 2024 | ST190 |  | 3rd bite at 20.5m depth, cutter wheel teeth replacement
Wed (10/04) | 10 Apr 2024 | ST73 |  | Excavation resume at 24.9m depth
Wed (10/04) | 10 Apr 2024 | DW21 |  | 2nd bite trenching completed. Trimming at waterstop side also done. Now teeth changing to start 3rd bite
Thu (11/04) | 11 Apr 2024 | Main viaduct P11 |  | Hacking of 22KV haunching and cable cutting
Thu (11/04) | 11 Apr 2024 | MH5-2 |  | Jacking in progress, 13/45 pipes
Thu (11/04) | 11 Apr 2024 | ST176 Single bite |  | Excavation in progress, reached 18.5m. Now changing cutter teeth
Thu (11/04) | 11 Apr 2024 | BC cutter 2 |  | No activity tonight. Machine need to repair
Thu (11/04) | 11 Apr 2024 | Zone 2 |  | CGS Excavation & Installation for Drop inlet pipe extension
Thu (11/04) | 11 Apr 2024 | Zone 4 |  | SI rig delivery and accessories to start ABH119
Thu (11/04) | 11 Apr 2024 | Zone 4 |  | Lucky joint here checking for submarine cable pulling
Thu (11/04) | 11 Apr 2024 | Zone 2 |  | Rebar cage fabrication for N1 column
Thu (11/04) | 11 Apr 2024 | P13 |  | LE preparation works to start trial trench for ERSS works
Thu (11/04) | 11 Apr 2024 | MH5-2 |  | Jacking in progress, 14/47 pipes
Thu (11/04) | 11 Apr 2024 | Zone 4 |  | JGP works in progress, B275: Completed, B215: preparation work in progress, Today target to complete 3 nos
Thu (11/04) | 11 Apr 2024 | MH1-2 |  | Continue supports installation for Formwork closing works
Thu (11/04) | 11 Apr 2024 | Zone 1 |  | CGS pvc pipe laying between d1 kerb
Thu (11/04) | 11 Apr 2024 | S4 |  | Waler beams installation in progress
Thu (11/04) | 11 Apr 2024 | Zone 3 |  | Fissure grouting 2 nos and 5 nos Drilling completed today. Housekeeping, work till 7pm
Thu (11/04) | 11 Apr 2024 | ST190 |  | End plate and water stop lowered, rebar cage installation in progress, 2/4
Thu (11/04) | 11 Apr 2024 | ST176 |  | Current at 1st bite trenching, cutter body hoist up for cleaning
Thu (11/04) | 11 Apr 2024 | Zone 3 DR1 |  | Today TT for utilities completed and delivery of SP (10 nos) and LP (15 nos). No more activity for the day
Thu (11/04) | 11 Apr 2024 | ST73 |  | Cutter wheel teeth replacement. Current depth 25.25m/27.45m
Thu (11/04) | 11 Apr 2024 | ST97 |  | BP1 pre-boring casing installed. Now bentonite pipe laying, tomorrow to start boring
Thu (11/04) | 11 Apr 2024 | DW24 |  | Trenching continue
Thu (11/04) | 11 Apr 2024 | DW21 |  | Tremie pipes installed
Thu (11/04) | 11 Apr 2024 | DW24- Single bite |  | Current excavation depth 18m/ 32.5m
Thu (11/04) | 11 Apr 2024 | P10-1-5 |  | Concrete ordered. 47.5m3
Thu (11/04) | 11 Apr 2024 | MH5-2 |  | Jacking team already went back
Thu (11/04) | 11 Apr 2024 | MH1-2 |  | Wall rebar tying in progress
Thu (11/04) | 11 Apr 2024 | Zone 2 |  | Excavation for Drop inlet pipe extension
Thu (11/04) | 11 Apr 2024 | Zone 2 North ramp |  | Rebar cage fabrication for N1 pier
Fri (12/04) | 12 Apr 2024 | BC#2 |  | No activity tonight due to engine problem. Tomorrow mechanic will check. BC#3 : no activity. Tonight will settle platform and slope protection casting. Tomorrow to start excavation
Fri (12/04) | 12 Apr 2024 | DW24 |  | Removal of waterstop end plate in progress
Fri (12/04) | 12 Apr 2024 | ST176 |  | 1st bite excavation done. Preparing for koden test
Fri (12/04) | 12 Apr 2024 | ST193 |  | LSS backfilling for PB1 preboring
Fri (12/04) | 12 Apr 2024 | ST190 |  | Casting completed at 1449hrs. Total volume: 195m3
Fri (12/04) | 12 Apr 2024 | P13 |  | TT for ERSS (Half) in progress
Fri (12/04) | 12 Apr 2024 | ST73 |  | BC cutter welding works ongoing. Preparation for 3rd bite excavation
Fri (12/04) | 12 Apr 2024 | ST97 |  | Preboring ongoing
Fri (12/04) | 12 Apr 2024 | P43 |  | GCE mobilising water tank and materials on site
Fri (12/04) | 12 Apr 2024 | P11-1-5 |  | Rig setting up for boring works
Fri (12/04) | 12 Apr 2024 | MH5-2 |  | 16/47 pipe jacking in progress
Fri (12/04) | 12 Apr 2024 | MH1-2 |  | Scaffold modification in progress for corbel formwork closing
Fri (12/04) | 12 Apr 2024 | S4 |  | Soil clearing in between SP. Balance 1 waler beam
Fri (12/04) | 12 Apr 2024 | PBH73 |  | In progress, 33m
Fri (12/04) | 12 Apr 2024 | P34 |  | HSL crane rectification ongoing
Fri (12/04) | 12 Apr 2024 | P29 |  | Fissure grout point, O-93 drilling ongoing
Fri (12/04) | 12 Apr 2024 | O-93 |  | PVC pipe and cotton packer installation
Fri (12/04) | 12 Apr 2024 | P9 |  | Boring works started
Fri (12/04) | 12 Apr 2024 | MH5-2 |  | 17/47 pipe jacking in progress
Fri (12/04) | 12 Apr 2024 | S4 |  | Diagonal strut joint welding ongoing. Balance 1 waler beam to be installed tmr
Fri (12/04) | 12 Apr 2024 | BP6 | 1 | Noise balloon set up. Boring in progress, 32m/33m. Works till 10pm
Fri (12/04) | 12 Apr 2024 | DW24 |  | Trimming ongoing, 27.7/32.5m
Fri (12/04) | 12 Apr 2024 | MH2-10 |  | TT was done near turning lane. Found HT cables. Preparing to reinstate the road
Fri (12/04) | 12 Apr 2024 | BP6-1 |  | Boring in progress, reached 33.2m
Fri (12/04) | 12 Apr 2024 | P9-1-6 |  | Casing installed. Now tidy up the area
Fri (12/04) | 12 Apr 2024 | MH5-2 |  | Pipe No-18 lowered down. Activity end for the day. One watch man provided for tonight
Fri (12/04) | 12 Apr 2024 | MH1-2 |  | New access installation for outer wall work area
Sat (13/04) | 13 Apr 2024 | Zone 3 |  | FG# O-82 commenced drilling works
Sat (13/04) | 13 Apr 2024 | ST176 |  | Casting completed
Sat (13/04) | 13 Apr 2024 | BC#2 |  | No activity due to engine problem. Mechanic checking ongoing
Sat (13/04) | 13 Apr 2024 | PBH73 |  | Driling ongoing, current depth 38.5m
Sat (13/04) | 13 Apr 2024 | Zone 3 | DR-1 | LE doing trial trenches works
Sat (13/04) | 13 Apr 2024 | ST073 |  | 3rd bite Trimming works ongoing
Sat (13/04) | 13 Apr 2024 | ST97 | PBH1 | HSL preboring works in progress
Sat (13/04) | 13 Apr 2024 | Vent shaft DW71&72 |  | Rebar work for guidewall
Sat (13/04) | 13 Apr 2024 | BC#3 |  | No activity. machine issue, repairing works ongoing
Sat (13/04) | 13 Apr 2024 | Zone 4 JGP Point B440 |  | Trial trench completed, preparing to install pipe sleeve
Sat (13/04) | 13 Apr 2024 | Zone 4 |  | Trial trench works for DR-3
Sat (13/04) | 13 Apr 2024 | Zone 4, JGP Point no. B-377 |  | Grouting halted due to machine issue, mechanic otw
Sat (13/04) | 13 Apr 2024 | Zone 4 | ABH-119 | Drilling works ongoing, depth 18m
Sat (13/04) | 13 Apr 2024 | BC cutter 2 |  | Still no activity. Yet to repair
Sat (13/04) | 13 Apr 2024 | Zone 2 |  | CGS lean concrete at DIC scupper pipes extension work areas
Sat (13/04) | 13 Apr 2024 | Zone 2 | P11-1-6 | Boring works ongoing
Sat (13/04) | 13 Apr 2024 | N2 |  | Scaffold installation for column works
Sat (13/04) | 13 Apr 2024 | P13 |  | LE trial trench works for ERSS installation
Sat (13/04) | 13 Apr 2024 | P9-1-6 |  | To continue boring after P11 completed. Today target to cast 2 BP
Sat (13/04) | 13 Apr 2024 | S4 ERSS |  | Bracket/waler beams installation works in progress
Sat (13/04) | 13 Apr 2024 | MH5-2 |  | Jacking towards MH5-1 ongoing, 19/47 nos
Sat (13/04) | 13 Apr 2024 | Zone 1 | South bound | CGS RCA backfilling and levelling works
Sat (13/04) | 13 Apr 2024 | Zone 1 | North bound | CGS kerb installation works
Sat (13/04) | 13 Apr 2024 | MH1-2 |  | Slab formwork (top part) installation works
Sat (13/04) | 13 Apr 2024 | DW024 |  | Rebar cages lapping and lowering in progress
Sat (13/04) | 13 Apr 2024 | BP6 | 1 | Continue boring works, today to cast
Sat (13/04) | 13 Apr 2024 | Zone 3 |  | I-61 depth confirmed, pipes with cotton packer installation ongoing. O-89 & O-80 grouting in progress
Sat (13/04) | 13 Apr 2024 | Zone 3 Krishco |  | Continue flange replacement works
Sat (13/04) | 13 Apr 2024 | Zone 3 | DR-1 | Current status for DR-1 ERSS installation. 2 nos. of casings installed for SP
Sat (13/04) | 13 Apr 2024 | PBH73 |  | Driling completed, current depth 47.20m. Pending QPD confirmation on termination depth
Sat (13/04) | 13 Apr 2024 | ST073 | MC96 | Excavation work temporary stop due to wheel teeth change, CD 28.60m/29.45m
Sat (13/04) | 13 Apr 2024 | DW24 |  | Preparing to install platform and will continue lower down waterstop
Sat (13/04) | 13 Apr 2024 | ST085 | SC40#02 | 1st bite excavation in process, Current depth 10.60m/34.0m
Sat (13/04) | 13 Apr 2024 | DW71 & DW72 | half | Guidewall trenching completed
Sat (13/04) | 13 Apr 2024 | ST97 | PBH1 | HSL continue preboring works
Sat (13/04) | 13 Apr 2024 | Zone 3 P43 |  | Preparation to start trial trench works for JGP
Sat (13/04) | 13 Apr 2024 | Zone 4 |  | JGP Rig repair work ongoing
Sat (13/04) | 13 Apr 2024 | MH1-2 |  | Scaffold U jack installation for soffit plywood installation
Sat (13/04) | 13 Apr 2024 | Zone 4 | ABH-119 | Drilling works ongoing, current depth 20m
Sat (13/04) | 13 Apr 2024 | Zone 2 |  | CGS continue lean concrete at DIC scupper pipes extension work areas
Sat (13/04) | 13 Apr 2024 | Zone 2 | P11-1-6 | Boring works completed. Rebar cage lowering ongoing
Sat (13/04) | 13 Apr 2024 | N2 |  | Scaffold installation for column works
Sat (13/04) | 13 Apr 2024 | N2 |  | Prefabrication works for column rebar cage
Sat (13/04) | 13 Apr 2024 | P13 |  | LE trial trench works for ERSS installation
Sat (13/04) | 13 Apr 2024 | P14 |  | Excavation for SPPG cable spiking and removal works
Sat (13/04) | 13 Apr 2024 | P9-1-6 |  | BP boring works in progress
Sat (13/04) | 13 Apr 2024 | MH1-2 |  | Slab formwork (top part) installation works
Sat (13/04) | 13 Apr 2024 | Zone 1 | South bound | CGS RCA backfilling and levelling works
Sat (13/04) | 13 Apr 2024 | MH5-2 |  | Jacking towards MH5-1 ongoing, 20/47 nos
Sat (13/04) | 13 Apr 2024 | DW24 |  | Internal koden checking in progress
Sat (13/04) | 13 Apr 2024 | S4 ERSS |  | Bracket/waler beams installation works in progress
Sat (13/04) | 13 Apr 2024 | BP6-1 |  | Casting completed
Sat (13/04) | 13 Apr 2024 | P11-1-7 |  | Casting done. Now tidy up the area
Sat (13/04) | 13 Apr 2024 | P9-1-6 |  | Boring completed. Preparing for casting platform installation. Tonight to cast
Sat (13/04) | 13 Apr 2024 | MH5-2 |  | Already stopped jacking. Current pipe jacking is Pipe No-20. Pipe No-21 jacking is still half way and to continue tomorrow
Sat (13/04) | 13 Apr 2024 | MH1-2 |  | Formwork closing for wall casting
Sat (13/04) | 13 Apr 2024 | DW024 |  | Waterstop end plate lowering in progress
Sat (13/04) | 13 Apr 2024 | Zone 3 Krishco |  | Flange replacement works
Sun (14/04) | 14 Apr 2024 | Zone 3 P22 and P23 |  | Open pit excavation for 22KV cable spiking tomorrow
Sun (14/04) | 14 Apr 2024 | P9 |  | Open pit excavation for SPPG cable spiking tomorrow
Sun (14/04) | 14 Apr 2024 | MH5-2 |  | Pipe jacking status, 21/47 pipes. Water topping up prior to jacking
Sun (14/04) | 14 Apr 2024 | MH1-2 |  | Installation of formwork for corbel on going. To cast tomorrow
Sun (14/04) | 14 Apr 2024 | S4 |  | Waler beam welding, tomorrow casting. Highlighted to improve cable management and working platform
Sun (14/04) | 14 Apr 2024 | Zone 1 |  | Backfilling of RCA for road widening
Sun (14/04) | 14 Apr 2024 | Fissure grouting O-88 |  | Drilling in progress
Sun (14/04) | 14 Apr 2024 | Zone 3 |  | Krishco here replacing flange for water pipe
Sun (14/04) | 14 Apr 2024 | DR1 |  | Augering in progress. Today target 5 nos plus installation or SP
Sun (14/04) | 14 Apr 2024 | ST73 |  | Water stop trimming
Sun (14/04) | 14 Apr 2024 | ST85 |  | 1st bite trenching at 21.9m depth
Sun (14/04) | 14 Apr 2024 | MH5-2 |  | 22nd pipe jacking in progress
Sun (14/04) | 14 Apr 2024 | ST73 |  | Preparation for C-lug welding and extraction of waterstop
Sun (14/04) | 14 Apr 2024 | ST85 |  | Cutter wheel teeth replacement, current at 24m depth
Sun (14/04) | 14 Apr 2024 | BC cutter 4 |  | Shifting to VS
Mon (15/04) | 15 Apr 2024 | ST186 |  | 1st bite trenching started
Mon (15/04) | 15 Apr 2024 | ST184 |  | To resume excavation, to use BC cutter 01
Mon (15/04) | 15 Apr 2024 | ST73 |  | Rebar cage lowering, 4/6 cages
Mon (15/04) | 15 Apr 2024 | ST85 |  | 1st bite trenching, current depth at 32m/34m
Mon (15/04) | 15 Apr 2024 | MH1-2 |  | Corbel casting completed
Mon (15/04) | 15 Apr 2024 | Zone 2 |  | System Formwork & falsework for crosshead materials arrived. Unloading in progress
Mon (15/04) | 15 Apr 2024 | Zone 2 | Bet P15-P14 | CGS preparation for lean concrete at DIC scupper pipes extension work areas
Mon (15/04) | 15 Apr 2024 | P14 |  | Excavation works to remove spiked cables
Mon (15/04) | 15 Apr 2024 | P13 |  | LE commenced preboring for ERSS works
Mon (15/04) | 15 Apr 2024 | P11-1-5 |  | BP boring works ongoing
Mon (15/04) | 15 Apr 2024 | P9-1 |  | Excavation for spiked cables removal works
Mon (15/04) | 15 Apr 2024 | MH5-2 towards MH5-1 |  | Preparation to lower pipe no.23, 22/47 nos. completed
Mon (15/04) | 15 Apr 2024 | Zone 1 |  | CGS lamp post pipe laying works
Mon (15/04) | 15 Apr 2024 | Zone 1 |  | MH1-2 Formwork closing for 5th layer wall. Today will cast
Mon (15/04) | 15 Apr 2024 | Zone 1 |  | CGS RCA levelling & compaction works
Mon (15/04) | 15 Apr 2024 | S4 |  | LE continue welding works for ERSS. Today to cast concrete packing
Mon (15/04) | 15 Apr 2024 | MH2-5 to MH2-6 |  | Cleaning of sewer line
Mon (15/04) | 15 Apr 2024 | P11-1-5 |  | Casing installed. Now preparing to install P12-3
Mon (15/04) | 15 Apr 2024 | MH1-2 |  | Continue ordered for casting
Mon (15/04) | 15 Apr 2024 | MH5-2 |  | Current status is pipe No-22 jacking done. Hydraulic jack/ frame breakdown. Repairing yet to be done
Mon (15/04) | 15 Apr 2024 | BP6B-9 |  | Boring in progress, reached 23m
Mon (15/04) | 15 Apr 2024 | Zone 2 P14-P15 |  | Open pit excavation till 10pm for SPPG cable cutting
Mon (15/04) | 15 Apr 2024 | P11-1-3 |  | Casing also installed and Rig was repaired. Tomorrow 2 BP to cast
Tue (16/04) | 16 Apr 2024 | Blk 2 |  | Fissure grout point drilling in progress, O-105
Tue (16/04) | 16 Apr 2024 | ST186 | BC 1 | B1 excavation in progress
Tue (16/04) | 16 Apr 2024 | ST184 | BC 2 | B1 excavation ongoing
Tue (16/04) | 16 Apr 2024 | DR1 |  | Today to continue ERSS installation. Awaiting for delivery — 10nos soldier pile, 10nos steel plates
Tue (16/04) | 16 Apr 2024 | ST85 | BC 3 | Machine rectification ongoing
Tue (16/04) | 16 Apr 2024 | ST98 |  | Preboring in progress
Tue (16/04) | 16 Apr 2024 | BC 4 |  | To be shifted to vent shaft. Workshop for rig movement will be held later at 4pm
Tue (16/04) | 16 Apr 2024 | ST186 |  | 1st bite trenching at 21.9m depth
Tue (16/04) | 16 Apr 2024 | ST184 |  | Gear motor replacement, plan to start around 2am, 1st bite current depth at 21.1m
Tue (16/04) | 16 Apr 2024 | ST85 |  | 1st bite trenching 33.7m depth
Tue (16/04) | 16 Apr 2024 | ST73 |  | Preparing for casting. 2 trucks already on site
Tue (16/04) | 16 Apr 2024 | DR1 |  | ERSS materials just arrived
Tue (16/04) | 16 Apr 2024 | ST73 |  | 5/6 rebar cages installed. Hanging bar installation in progress
Tue (16/04) | 16 Apr 2024 | ST85 |  | 1st bite trenching temporarily stopped for cutter wheel teeth replacement. Current depth at 32.8m
Tue (16/04) | 16 Apr 2024 | ST85 |  | Trenching resumed
Tue (16/04) | 16 Apr 2024 | P11-1-5 |  | BP boring completed, preparing to lower rebar cage
Tue (16/04) | 16 Apr 2024 | MH5-2 |  | No activity. Current pipe jacking status, 22/47 nos. Mechanic checking the issue of the jacking frame machine
Tue (16/04) | 16 Apr 2024 | Zone 1 |  | CGS continue excavation for lamp post pipe laying
Tue (16/04) | 16 Apr 2024 | MH1-2 |  | Preparation to removal 5th layer wall Formwork
Tue (16/04) | 16 Apr 2024 | Zone 1 |  | CGS installation of DIC
Tue (16/04) | 16 Apr 2024 | S4 |  | Welding work for waler beam and strut in progress
Tue (16/04) | 16 Apr 2024 | P13 |  | LE continue preboring work for ERSS
Tue (16/04) | 16 Apr 2024 | DR1 |  | LE continue ERSS installation
Tue (16/04) | 16 Apr 2024 | ST73 |  | Rebar cages all lowered
Tue (16/04) | 16 Apr 2024 | P11-1-5 |  | Tremie pipe installed. Concrete on the way, 22m
Tue (16/04) | 16 Apr 2024 | MH1-2 |  | Formwork removal
Tue (16/04) | 16 Apr 2024 | MH5-2 |  | Packer pack yet to repair. Supplyer mechanic need to come and check
Tue (16/04) | 16 Apr 2024 | BP6-9 | B | Boring works continue, now at 28m
Tue (16/04) | 16 Apr 2024 | P20 |  | Footpath casting to zone 2
Tue (16/04) | 16 Apr 2024 | MH1-2 |  | Tonight material clearing at vortex pit. Tomorrow WH to dismantle scaffold and start erectiom of shoring
Wed (17/04) | 17 Apr 2024 | Zone 3 |  | ECM pipe outlet rectification ongoing
Wed (17/04) | 17 Apr 2024 | DR1 |  | Continue soldier pile installation
Wed (17/04) | 17 Apr 2024 | ST186 |  | 2nd bite trenching in progress, current depth at 13.3m/28m
Wed (17/04) | 17 Apr 2024 | ST184 |  | 1st bite trenching at 22.2m/25.8m depth
Wed (17/04) | 17 Apr 2024 | Rig 4 |  | Wire maintenance ongoing
Wed (17/04) | 17 Apr 2024 | ST99 |  | Preboring ongoing
Wed (17/04) | 17 Apr 2024 | ST184 | rig 2 | B1 excavation temporarily stopped due to suction line bentonite leakage. Rectification ongoing. Current depth at 21.8m/25.8m
Wed (17/04) | 17 Apr 2024 | ST186 | rig 1 | B1 excavation in progress
Wed (17/04) | 17 Apr 2024 | ST186 |  | B1 depth at 27.1m/28m
Wed (17/04) | 17 Apr 2024 | P15 |  | Premix hacking to remove for BP trial trench works
Wed (17/04) | 17 Apr 2024 | P14 |  | Removal of spiked cables for bp works
Wed (17/04) | 17 Apr 2024 | P13 |  | LE continue to do ERSS preboring
Wed (17/04) | 17 Apr 2024 | P12-1-5 |  | Boring for BP in progress
Wed (17/04) | 17 Apr 2024 | S4 |  | LE continue welding works for waler beams & struts. MPI test at 3pm today
Wed (17/04) | 17 Apr 2024 | MH5-2 |  | Pipe jacking stopped due to jacking frame breakdown. Mechanic onsite to resolve. Target to resolve today. Jacking status 22/47 pipes
Wed (17/04) | 17 Apr 2024 | MH1-2 |  | Scaffold material clearing continue
Wed (17/04) | 17 Apr 2024 | Zone 1 |  | PMH-1 steel plates delivered. Preparation for welding of steel plate and I beam
Wed (17/04) | 17 Apr 2024 | Zone 1 |  | RG mobilized rig for installation of inclinometer & piezometer
Wed (17/04) | 17 Apr 2024 | UKP30 |  | Trial trench at 1.8m depth. No services
Wed (17/04) | 17 Apr 2024 | ST184 |  | 1st bite trenching in progress 21.5m
Wed (17/04) | 17 Apr 2024 | ST186 |  | 1st bite trenching at 24m depth
Wed (17/04) | 17 Apr 2024 | ST85 |  | 1st bite trenching completed. Teeth replacement then start 2nd bite
Wed (17/04) | 17 Apr 2024 | MH1-2 |  | Scaffold works for top slab casting ongoing
Wed (17/04) | 17 Apr 2024 | Zone 1 |  | DIC pipe connection and levelling works
Wed (17/04) | 17 Apr 2024 | P43 |  | BH62 trial trench was done. Found pipe at 900mm depth. Pending utility team confirmation. TT was done up till 1.7m
Wed (17/04) | 17 Apr 2024 | Zone 1 |  | CGS lamp post pipe laying works
Wed (17/04) | 17 Apr 2024 | Zone 4 LA |  | Lamp post maintenance by KSL
Wed (17/04) | 17 Apr 2024 | Zone 4 |  | Pipe sleeve installation ongoing
Wed (17/04) | 17 Apr 2024 | MH5-2 |  | Mechanic onsite to check and resolve the breakdown issue
Wed (17/04) | 17 Apr 2024 | Zone 4 |  | JGP rig sensor replacement part will be delivered on Friday
Wed (17/04) | 17 Apr 2024 | S4 |  | Welding completed for Waler and strut. Now preparation for MPI testing
Wed (17/04) | 17 Apr 2024 | PBH74 |  | SI in progress, 33m
Wed (17/04) | 17 Apr 2024 | DR1 |  | LE will continue to do manual trial trench here before proceeding for soldier pile/steel plate installation
Wed (17/04) | 17 Apr 2024 | DR1 |  | Another set of steel plates and soldier piles just arrived
Wed (17/04) | 17 Apr 2024 | P12-1-3 |  | Boring completed, preparing to lower rebar cages
Wed (17/04) | 17 Apr 2024 | P13 |  | Continue preboring for ERSS works. Target to complete half ERSS preboring today
Wed (17/04) | 17 Apr 2024 | ST184 |  | Continue line rectification
Wed (17/04) | 17 Apr 2024 | ST186 |  | B2 excavation in progress
Wed (17/04) | 17 Apr 2024 | ST85 |  | B2 excavation in progress
Wed (17/04) | 17 Apr 2024 | BP6B | 9 | COL reached 33m. Another 5m to reach toe level. Works till 10pm
Wed (17/04) | 17 Apr 2024 | P21 |  | WH exposing trench for SPPG cable spiking. Plan for spiking this Friday
Wed (17/04) | 17 Apr 2024 | ST184 |  | Trenching continue
Wed (17/04) | 17 Apr 2024 | P14 |  | Area backfilling ongoing
Wed (17/04) | 17 Apr 2024 | P12-1-3 |  | Rebar cage installation in progress, 1/3nos
Wed (17/04) | 17 Apr 2024 | MH5-2 |  | Pipe jacking no.23 in progress
Wed (17/04) | 17 Apr 2024 | BP6B-9 |  | Boring works continue, current depth 34.0 m/ 38.639m
Thu (18/04) | 18 Apr 2024 | ST186 |  | Cutter teeth replacement
Thu (18/04) | 18 Apr 2024 | ST184 |  | Cutter body also hoist up for teeth replacement
Thu (18/04) | 18 Apr 2024 | ST85 |  | 2nd bite/2nd trimming in progress, depth 26.5/34.2m
Thu (18/04) | 18 Apr 2024 | ST186 |  | 2nd bite trenching resumed, current depth at 24.6/28m
Thu (18/04) | 18 Apr 2024 | P19 area |  | Cable pulling works for netlink
Thu (18/04) | 18 Apr 2024 | P13 |  | LE ERSS preboring works
Thu (18/04) | 18 Apr 2024 | P11-1-3 |  | Boring works ongoing for BP
Thu (18/04) | 18 Apr 2024 | P10 |  | Excavation works for removal of SPPG cables and gas pipe
Thu (18/04) | 18 Apr 2024 | MH5-2 |  | Pipe jacking temporarily stopped due to power supply issue to hydraulic pump. Mechanic otw to check. Current jacking pipe status 23/47 pipes
Thu (18/04) | 18 Apr 2024 | Zone 1 |  | CGS hacking and excavation works for footpath making works
Thu (18/04) | 18 Apr 2024 | Zone 1 |  | CGS hacking and excavation works for footpath making works
Thu (18/04) | 18 Apr 2024 | MH1-2 |  | Slab vertical supports installation in progress
Thu (18/04) | 18 Apr 2024 | S4 |  | KTC excavation works to FEL commenced
Thu (18/04) | 18 Apr 2024 | P11-1-3 |  | Rebar cage installation. Tonight to cast
Thu (18/04) | 18 Apr 2024 | P12-1 |  | Prepare to install casing
Thu (18/04) | 18 Apr 2024 | ST184 |  | 1st bite trenching at 25.4m/25.8m depth
Thu (18/04) | 18 Apr 2024 | MH1-2 |  | U jack and formwork support installation for top slab
Thu (18/04) | 18 Apr 2024 | ST85 |  | 2nd bite/2nd trimming in progress, depth 31.4/34.2m
Thu (18/04) | 18 Apr 2024 | MH5-2 |  | Now control room breakdown. Need to repair tomorrow
Thu (18/04) | 18 Apr 2024 | BP6B-9 |  | Boring reached 37m
Thu (18/04) | 18 Apr 2024 | P15 |  | Hardcore levelling ongoing
Thu (18/04) | 18 Apr 2024 | MH5-2 |  | No activity
Thu (18/04) | 18 Apr 2024 | MH1-2 |  | To continue support installation for top slab
Thu (18/04) | 18 Apr 2024 | P11-1-3 |  | Casting ongoing
Thu (18/04) | 18 Apr 2024 | ST186 |  | Cutter wheel teeth changing ongoing
Thu (18/04) | 18 Apr 2024 | ST184 |  | B2 excavation was completed. Now c-lug welding for endplate loosening at ST185 side
Thu (18/04) | 18 Apr 2024 | Dear all, i will be meeting with DSTA at 9 |  | 40AM regarding with Army cable/ manhole for bored pile/Viaduct work. I wont be able to join Monthly PGI. FYI please. Thanks
Thu (18/04) | 18 Apr 2024 | ST85 |  | B1 cleaning ongoing
Thu (18/04) | 18 Apr 2024 | P11-1-3 |  | Casting completed ard 2150hrs
Fri (19/04) | 19 Apr 2024 | DW76 |  | B1 excavation in progress, 7.5m/27.4m
Fri (19/04) | 19 Apr 2024 | P12-1-1 |  | Boring works in progress. Pile depth 23m
Fri (19/04) | 19 Apr 2024 | ST97 |  | B1 excavation in progress
Fri (19/04) | 19 Apr 2024 | Zone 1 LL |  | Footpath construction. 12m
Fri (19/04) | 19 Apr 2024 | MH1-2 |  | Scaffold erection for formwork closing
Fri (19/04) | 19 Apr 2024 | Zone 1 |  | Singtel cable recovery
Fri (19/04) | 19 Apr 2024 | PMH1 |  | Cover installation for stage 1 diversion
Fri (19/04) | 19 Apr 2024 | S4 |  | Excavation to FEL
Fri (19/04) | 19 Apr 2024 | P12-1-1 |  | Casting completed
Fri (19/04) | 19 Apr 2024 | P21-P22 |  | Area leveling for Bachy silo plant construction
Fri (19/04) | 19 Apr 2024 | Zone 2 |  | Unloading of column Formwork
Fri (19/04) | 19 Apr 2024 | MH1-2 |  | Continue support installation for top slab works
Fri (19/04) | 19 Apr 2024 | P12-1-1 |  | Continue BP boring works
Fri (19/04) | 19 Apr 2024 | P15 |  | Premix hacking in progress
Fri (19/04) | 19 Apr 2024 | P13 |  | SP installation in progress, 3/12 completed
Fri (19/04) | 19 Apr 2024 | P10-1 |  | Excavation works for removal of SPPG cables
Fri (19/04) | 19 Apr 2024 | P9-2 |  | Concrete surface hacking for pier construction
Fri (19/04) | 19 Apr 2024 | Zone 2 |  | 2nd boring rig setting up works ongoing
Fri (19/04) | 19 Apr 2024 | MH1-2 |  | Scaffold erection for formwork closing
Fri (19/04) | 19 Apr 2024 | S4 |  | Excavation to FEL in progress. Target to complete tmr
Fri (19/04) | 19 Apr 2024 | ST186 |  | B2 excavation in progress
Fri (19/04) | 19 Apr 2024 | ST97 | rig 3 | B1 excavation started at 0305hrs
Fri (19/04) | 19 Apr 2024 | ST85 |  | Endplate lowering in progress
Fri (19/04) | 19 Apr 2024 | ST184 |  | C-lug welding ongoing for endplate loosening at ST183 side
Fri (19/04) | 19 Apr 2024 | BP6B | 9 | Casting completed
Fri (19/04) | 19 Apr 2024 | P12-1-1 |  | Plan for casting ard 930pm
Fri (19/04) | 19 Apr 2024 | P10 |  | Continue cables & pipes removal
Fri (19/04) | 19 Apr 2024 | MH5-2 |  | Pipe jacking works done for the day, 26/47nos
Fri (19/04) | 19 Apr 2024 | MH1-2 |  | Continue platform support installation
Fri (19/04) | 19 Apr 2024 | P22 |  | All cable exposed for spiking. Scheduled after lunch
Fri (19/04) | 19 Apr 2024 | S4 |  | Activity done for the day
Fri (19/04) | 19 Apr 2024 | Zone 2 |  | Formwork for crosshead delivery and unloading
Fri (19/04) | 19 Apr 2024 | ST186 |  | Endplate loosening in progress at ST187 side
Fri (19/04) | 19 Apr 2024 | ST184 |  | Endplate extraction at ST183 side
Fri (19/04) | 19 Apr 2024 | ST75 |  | B1 excavation in progress, 21.2/39m
Fri (19/04) | 19 Apr 2024 | ST85 |  | Rebar cage installation, 3/3nos
Fri (19/04) | 19 Apr 2024 | P15 |  | Setting out for ERSS pre-boring. WH to hack premix first
Sat (20/04) | 20 Apr 2024 | P15 |  | Continue premix and pavement hacking for Pile cap ERSS
Sat (20/04) | 20 Apr 2024 | P15 |  | Today to start TT for half pile
Sat (20/04) | 20 Apr 2024 | P13 half |  | ERSS installation continue. To complete today
Sat (20/04) | 20 Apr 2024 | P9-1-2 |  | Today plan for boring and casting
Sat (20/04) | 20 Apr 2024 | MH1-2 |  | Bracket installation in progress. Still target to cast tomorrow
Sat (20/04) | 20 Apr 2024 | P11-1-2 |  | Casting completed
Sat (20/04) | 20 Apr 2024 | ST191 |  | 1st bite excavation started, current depth 9m
Sat (20/04) | 20 Apr 2024 | ST186 |  | End plate extraction in progress
Sat (20/04) | 20 Apr 2024 | ST184 |  | All rebar cage lowered, fissure grouting pipe installation in progress
Sat (20/04) | 20 Apr 2024 | DR1 |  | Hacking of previous ECM slab then continue SP installation, 24/94 SP, 20/91 LP
Sat (20/04) | 20 Apr 2024 | UKP32 |  | Preparation for casing installation and Boring, Details:, Toe level: -9.37 msHd, COL: -0.07 msHd, Plan to lower KP by 5pm
Sat (20/04) | 20 Apr 2024 | ST75 |  | 1st bite completed. Cutter body hoist up for teeth replacement and c-lug welding
Sat (20/04) | 20 Apr 2024 | ST97 |  | 1st bite trenching at 29m/34.1m
Sat (20/04) | 20 Apr 2024 | P43 |  | TT for JGP works, 60/152 completed at zone 3
Sat (20/04) | 20 Apr 2024 | Zone 4 |  | JGP completed: B451, B336, Area preparation in progress for B219, Total completed: 58/472, Target to complete 4 points today
Sat (20/04) | 20 Apr 2024 | MH1-2 |  | Bracket installation completed. Extending scaffold in progress
Sat (20/04) | 20 Apr 2024 | PDR3 |  | Public feedback on depressed road rectification in progress
Sat (20/04) | 20 Apr 2024 | MH5-2 |  | Pip3 jacking #28 in progress
Sat (20/04) | 20 Apr 2024 | S4 |  | Excavation to FEL continue, hard soil
Sat (20/04) | 20 Apr 2024 | P11-1-2 |  | Boring completed, pending depth confirmation then install rebar cage
Sat (20/04) | 20 Apr 2024 | P13 | half | 12 nos soldier pile installed. Lagging plate installation on going. Today plan to complete
Sat (20/04) | 20 Apr 2024 | P20-21 |  | Bachy silo plan base slab rebar works
Sat (20/04) | 20 Apr 2024 | BP6B-9 |  | LSS casting completed
Sat (20/04) | 20 Apr 2024 | ST75 |  | B1 in progress, 29.3m/39m
Sat (20/04) | 20 Apr 2024 | ST85 |  | Tremie pipes fully lowered. Pending to cast
Sat (20/04) | 20 Apr 2024 | ST97 |  | B1 in progress, 26/34.1m
Sat (20/04) | 20 Apr 2024 | DW76 |  | B1 in progress, 21/27.4m
Sat (20/04) | 20 Apr 2024 | ST85 |  | Casting started at 0556hrs. Est total vol: 135m3
Sat (20/04) | 20 Apr 2024 | P11-1-2 |  | Now pending for casting
Sat (20/04) | 20 Apr 2024 | MH5-2 |  | Pipe 29 already lowered. Works done for the day. Tmr to continue
Sat (20/04) | 20 Apr 2024 | MH1-2 |  | Night team preparing to continue works for top slab
Sat (20/04) | 20 Apr 2024 | S4 |  | No activity
Sat (20/04) | 20 Apr 2024 | ST184 |  | Casting in progress, 54/100m3
Sat (20/04) | 20 Apr 2024 | UKP32 |  | Pending for casting
Sat (20/04) | 20 Apr 2024 | ST75 |  | B2 in progress, 11.5/39m
Sat (20/04) | 20 Apr 2024 | ST97 |  | B1 in progress, 33/34.1m
Sat (20/04) | 20 Apr 2024 | Exit 3 |  | TT trench for barrette pile
Sat (20/04) | 20 Apr 2024 | DW76 |  | B2 temporarily stopped due to hydraulic hose leaking. Current depth 3.8/27.4m. Now preparing for rectification
Sat (20/04) | 20 Apr 2024 | UKP32 |  | Casting ongoing
Sat (20/04) | 20 Apr 2024 | P23 |  | Premix hacking for SPPG cable cutting and retrieval
Sat (20/04) | 20 Apr 2024 | P22 |  | Open pit excavation for 66kv spiking
Sat (20/04) | 20 Apr 2024 | P20-21 |  | Area levelling for Bachy silo plant. Today to lean con the rest of the area
Sun (21/04) | 21 Apr 2024 | Exit 3 |  | ABH-12 manual trial trench ongoing
Sun (21/04) | 21 Apr 2024 | ST-196 |  | Cutter teeth replaced. Preparation to resume 1st bite excavation. CD: 22.3m/34.7m
Sun (21/04) | 21 Apr 2024 | ST-186 |  | Preparing to lowering 5th rebar cage. 4/6 rebar cages lowered
Sun (21/04) | 21 Apr 2024 | DR1 |  | LE ERSS installation in progress
Sun (21/04) | 21 Apr 2024 | ST-75 |  | Trimming works ongoing for water stop removal
Sun (21/04) | 21 Apr 2024 | Dw-76 |  | Excavation temporarily stopped. Hydraulic hose repairing works ongoing
Sun (21/04) | 21 Apr 2024 | ST-97 |  | 2nd bite current excavation depth 12m. Work temporarily stopped, due to bc operator went to help with ST-191. Today lack of bc operators
Sun (21/04) | 21 Apr 2024 | P43 |  | Excavation and trial trench works for JGP pipe sleeves installation
Sun (21/04) | 21 Apr 2024 | Zone 4, P47 |  | JGP B-218 grouting ongoing
Sun (21/04) | 21 Apr 2024 | S4 |  | Excavation to FEL in progress
Sun (21/04) | 21 Apr 2024 | MH5-2 |  | Pipe no. 31 lowered. 30/47 nos. pipe jacking completed
Sun (21/04) | 21 Apr 2024 | Zone 1 |  | CGS footpath casting works
Sun (21/04) | 21 Apr 2024 | MH1-2 |  | Formwork closing for top slab. Target to cast today night shift
Sun (21/04) | 21 Apr 2024 | MH1-2 |  | Formwork support works for top slab ongoing
Sun (21/04) | 21 Apr 2024 | S4 |  | Continue excavation to FEL. To complete excavation tmr
Sun (21/04) | 21 Apr 2024 | MH5-2 |  | Pipe no. 32 lowered. 31/47 nos. pipe jacking completed
Sun (21/04) | 21 Apr 2024 | Zone 1 |  | CGS footpath casting works completed
Sun (21/04) | 21 Apr 2024 | MH1-2 |  | Continue Formwork closing works for top slab casting
Sun (21/04) | 21 Apr 2024 | Zone 4, P47 |  | JGP B-218 grouting completed. Now JGP B-267 grouting ongoing
Sun (21/04) | 21 Apr 2024 | P43 |  | Soil levelling works in progress. Today installed 6 nos. JGP pipe sleeves
Sun (21/04) | 21 Apr 2024 | ST-97 |  | BC Cutter wheel soil cleaning ongoing
Sun (21/04) | 21 Apr 2024 | DW-76 |  | 2nd bite excavation in progress, CD 18.90m/27.50m
Sun (21/04) | 21 Apr 2024 | ST191 |  | B1 excavation in progress
Sun (21/04) | 21 Apr 2024 | ST186 |  | Rebar cage installation ongoing, 3/6nos
Sun (21/04) | 21 Apr 2024 | ST75 |  | Preparation for c-lug welding
Sun (21/04) | 21 Apr 2024 | ST-75 |  | C lug plate welding for endplate removal
Sun (21/04) | 21 Apr 2024 | ST97 |  | B2 excavation started at 0319hrs
Sun (21/04) | 21 Apr 2024 | ST-186 |  | Lowering 6th rebar cage and lapping works ongoing. 5/6 rebar cages lowered
Sun (21/04) | 21 Apr 2024 | ST-191 |  | Preparation for cutter teeth change. 1st bite excavation CD: 24m/34.7m
Sun (21/04) | 21 Apr 2024 | DW76 |  | Dayshift to continue rectification for hose leakage
Mon (22/04) | 22 Apr 2024 | ST97 |  | 2nd bite in progress, reached 26.7m
Mon (22/04) | 22 Apr 2024 | ST191 |  | 2nd bite trimming in progress, reached 24m
Mon (22/04) | 22 Apr 2024 | P16 |  | Excavation to expose SPPG cable for spiking. This week plan to spike P16 and P18
Mon (22/04) | 22 Apr 2024 | P15 |  | TT for ERRS in progress
Mon (22/04) | 22 Apr 2024 | P12-1-2 |  | Boring works in progress
Mon (22/04) | 22 Apr 2024 | Zone 1 |  | CGS pipe laying works for cable detection loop
Mon (22/04) | 22 Apr 2024 | Zone 1, PMH1 |  | Support casting for PMH1 ongoing
Mon (22/04) | 22 Apr 2024 | UKP32 |  | Removing remaining concrete. The UKP was extracted as well while extracting the casing
Mon (22/04) | 22 Apr 2024 | UKP49 and UKP50 |  | Trial trench ongoing
Mon (22/04) | 22 Apr 2024 | MH5-2 |  | Now stuck at #33 pipes, hydraulic machine again have issues
Mon (22/04) | 22 Apr 2024 | MH1-2 |  | Rebar works for roof slab continue
Mon (22/04) | 22 Apr 2024 | S4 |  | Excavation to FEL. Target to complete by today
Mon (22/04) | 22 Apr 2024 | PBH12 |  | SI started
Mon (22/04) | 22 Apr 2024 | Exit 3 |  | Guidewall excavation for BRP-04
Mon (22/04) | 22 Apr 2024 | P12-2 |  | Casting in progress
Mon (22/04) | 22 Apr 2024 | MH1-2 |  | Formwork support installation for opening. Tonight to cast
Tue (23/04) | 23 Apr 2024 | P15 |  | TT today to complete and start pre-boring
Tue (23/04) | 23 Apr 2024 | P14-1-3 |  | Boring works in progress
Tue (23/04) | 23 Apr 2024 | P11-1-1 |  | Boring works in progress
Tue (23/04) | 23 Apr 2024 | MH5-2 |  | Jacking yet to continue, hydraulic machine not repair yet
Tue (23/04) | 23 Apr 2024 | MH1-2 |  | Preparation for intermediate slab construction
Tue (23/04) | 23 Apr 2024 | Zone 1 |  | Material clearing for stage 1 diversion
Tue (23/04) | 23 Apr 2024 | S4 |  | HSL here for pile head hacking
Tue (23/04) | 23 Apr 2024 | P16 |  | Excavation for SPPG cable spiking
Tue (23/04) | 23 Apr 2024 | ST97 |  | Changing cutter teeth in progress
Tue (23/04) | 23 Apr 2024 | P16 |  | Excavation for removal of SPPG cables for BP works
Tue (23/04) | 23 Apr 2024 | P15 |  | LE trial trench works for ERSS installation ongoing
Tue (23/04) | 23 Apr 2024 | P9-1-3 |  | Boring works for BP in progress
Tue (23/04) | 23 Apr 2024 | N5 |  | RWDP installation works
Tue (23/04) | 23 Apr 2024 | Zone 2 near shell |  | SPTel cable recovery
Tue (23/04) | 23 Apr 2024 | S4 |  | KTC excavation to FEL and soil disposal works
Tue (23/04) | 23 Apr 2024 | ST-97 |  | 2nd bite excavation temporary stop. Cutter wheel/ teeth changing in progress
Tue (23/04) | 23 Apr 2024 | ST191 |  | 2nd bite trimming completed
Tue (23/04) | 23 Apr 2024 | N5 |  | Wendyng here to cut rebars and compensate for the provision of drain pipes. Drawing endorsed
Wed (24/04) | 24 Apr 2024 | P9-1-1 |  | Boring works in progress. Current depth 16.0m from TOC
Wed (24/04) | 24 Apr 2024 | MH5-2 |  | Pipe no.35 lowered. Preparation to start jacking works
Wed (24/04) | 24 Apr 2024 | DW75 |  | 1st bite excavation done. Preparing for internal koden test
Wed (24/04) | 24 Apr 2024 | Zone 1 |  | CGS footpath making
Wed (24/04) | 24 Apr 2024 | ST186 |  | Casted 22th, DW71 : will be started to cast tonight, ST191 : will ba started to cast 25th daytime, ST75 : will be started to cast 25th, ST97 : target to cast 26th, DW75 : target to cast 26th
Wed (24/04) | 24 Apr 2024 | ST87 |  | Platform preparation for excavation
Wed (24/04) | 24 Apr 2024 | Zone 1 |  | Delivery of ibeam for NB installation
Wed (24/04) | 24 Apr 2024 | Zone 1 NLL |  | Installation of D1 kerb for stage 1 diversion
Wed (24/04) | 24 Apr 2024 | Zone 1 NLL |  | Pavement hacking for footpath extension
Wed (24/04) | 24 Apr 2024 | Exit 3 |  | BRP01 guide wall continue excavation. Completing soon
Wed (24/04) | 24 Apr 2024 | PBH 12 |  | Coring continue. Current depth 35m
Wed (24/04) | 24 Apr 2024 | P18 |  | Sppg haunching also to hack today, spiking tomorrow
Wed (24/04) | 24 Apr 2024 | Zone 2 |  | Drilling for lifting point and tie rod in progress
Wed (24/04) | 24 Apr 2024 | UKP 29 |  | Casing installation completed. Preparing for boring
Wed (24/04) | 24 Apr 2024 | P12 |  | TT for ERSS work continue
Wed (24/04) | 24 Apr 2024 | P11-1-1 |  | Boring in progress
Wed (24/04) | 24 Apr 2024 | Rig 1 |  | Dwall ST 75 at DR2: desanding in progress
Wed (24/04) | 24 Apr 2024 | Rig 2 |  | Waiting for shop drawing confirmation for ST87. Currently not working
Wed (24/04) | 24 Apr 2024 | Rig 3 |  | Dwall: ST097 oil checking ongoing. After that resume 2nd bite excavation
Wed (24/04) | 24 Apr 2024 | Rig 4 |  | DW 75 vent shaft: first bite excavation in progress
Wed (24/04) | 24 Apr 2024 | MH5-2 |  | #36 pipe jacking in progress
Wed (24/04) | 24 Apr 2024 | Zone 1 |  | Loop detector pipe installation
Wed (24/04) | 24 Apr 2024 | Zone 2 |  | Sptel cable recovery
Wed (24/04) | 24 Apr 2024 | Zone 1 |  | NB ibeam installation
Wed (24/04) | 24 Apr 2024 | Zone 2 |  | P8 pier rebar cage fabrication
Wed (24/04) | 24 Apr 2024 | DR1 |  | Hacking of abandoned drain in progress
Wed (24/04) | 24 Apr 2024 | Zone 3 |  | Bachy installing secondary roof for container office and rest area
Wed (24/04) | 24 Apr 2024 | P9-1-1 |  | Casting completed
Wed (24/04) | 24 Apr 2024 | MH5-2 |  | # 37 pipe jacking in progress
Wed (24/04) | 24 Apr 2024 | S4 |  | Pile head hacking to continue till 10pm
Wed (24/04) | 24 Apr 2024 | P11-1-1 |  | Rebar cage lowering in progress. Tonight to cast
Wed (24/04) | 24 Apr 2024 | MH1-2 |  | Removal of hot air before dismantling of formwork
Wed (24/04) | 24 Apr 2024 | Zone 3 |  | Bachy contractor resumed C crane assembly. Pending PE inspection which scheduled today
Wed (24/04) | 24 Apr 2024 | Zone 3 |  | Bachy doing roofing installation works for containers
Wed (24/04) | 24 Apr 2024 | Zone 4 |  | JGP works in progress
Wed (24/04) | 24 Apr 2024 | P16 |  | SPPG cables exposed for spiking and removal works
Wed (24/04) | 24 Apr 2024 | P12 |  | LE trial trench works for ERSS installation
Thu (25/04) | 25 Apr 2024 | ST79-BC1 |  | Teeth replacement, current at 1st bite 22.6m/39m
Thu (25/04) | 25 Apr 2024 | ST75 |  | Preparation for Tremie pipes lowering
Thu (25/04) | 25 Apr 2024 | ST97- BC2 |  | C-lug welding for water stop side trimming
Thu (25/04) | 25 Apr 2024 | Blk 4 |  | Post-lugeon drilling point ongoing for O-57 to O-58
Thu (25/04) | 25 Apr 2024 | Near exit 2 |  | Singtel cable recovery
Thu (25/04) | 25 Apr 2024 | ST75 |  | Rebar cage installation ongoing, 2/4nos
Thu (25/04) | 25 Apr 2024 | ST79 |  | B1 excavation ongoing
Thu (25/04) | 25 Apr 2024 | Zone 2 |  | Column formworks dismantle works
Thu (25/04) | 25 Apr 2024 | P16 |  | SPPG cables exposed for spiking in the afternoon
Thu (25/04) | 25 Apr 2024 | P18 |  | SPPG cables exposed for spiking in the afternoon
Thu (25/04) | 25 Apr 2024 | P12 |  | Preparation works for preboring ongoing. Today will start preboring for ERSS
Thu (25/04) | 25 Apr 2024 | P10-1-3 |  | Preparation for preboring and platform laying for rig. Today to cast P10-1-3 & P14-3
Thu (25/04) | 25 Apr 2024 | DW75 |  | B2 excavation in progress, 6.5m/27.4m
Thu (25/04) | 25 Apr 2024 | Zone 2 |  | Column rebar cage prefabrication ongoing for P8-2
Thu (25/04) | 25 Apr 2024 | P14-3 |  | Casting completed
Thu (25/04) | 25 Apr 2024 | MH5-2 |  | #38 pipe jacking in progress
Thu (25/04) | 25 Apr 2024 | P43 |  | GCE repairing rig data logger & preparing trial trench prior to starting works
Thu (25/04) | 25 Apr 2024 | P43 |  | Netlink cable recovery ongoing
Thu (25/04) | 25 Apr 2024 | Zone 1 |  | Preparation for BRC laying works for footpath
Thu (25/04) | 25 Apr 2024 | Near DR1 |  | Singtel cable recovery works
Thu (25/04) | 25 Apr 2024 | DR1 |  | KTC to continue hacking of existing box culvert drain
Thu (25/04) | 25 Apr 2024 | MH1-2 |  | Caisson wall hacking in progress
Thu (25/04) | 25 Apr 2024 | MH1-2 |  | Access making works
Thu (25/04) | 25 Apr 2024 | Zone 1 |  | Noise barrier bracings and panels installation works
Thu (25/04) | 25 Apr 2024 | UKP30 |  | Preparing works ongoing before start boring
Thu (25/04) | 25 Apr 2024 | UKP48 |  | Manual trial trench & clearing in progress
Thu (25/04) | 25 Apr 2024 | ST191 |  | Casting started
Thu (25/04) | 25 Apr 2024 | S4 |  | Current pile head hacking status. 2/4 nos completed
Thu (25/04) | 25 Apr 2024 | ST97 |  | B2 internal koden check
Thu (25/04) | 25 Apr 2024 | BRP01 |  | Guidewall rebar and formwork inspected. Ready for casting
Thu (25/04) | 25 Apr 2024 | P12 |  | ERSS preboring works in progress
Thu (25/04) | 25 Apr 2024 | P10-1-3 |  | Casing installed. Now continue boring works
Thu (25/04) | 25 Apr 2024 | P13 |  | Removal of spike SPPG cables for BP works
Thu (25/04) | 25 Apr 2024 | P11-2 |  | KTC Backfilling to pilecap level
Thu (25/04) | 25 Apr 2024 | P14-3 |  | Boring completed. Now pending rto to confirm on the depth
Thu (25/04) | 25 Apr 2024 | P8-2 |  | Continue rebar cage prefabrication works
Thu (25/04) | 25 Apr 2024 | MH5-2 |  | #39 pipe jacking in progress
Thu (25/04) | 25 Apr 2024 | MH1-2 |  | Caisson wall hacking in progress
Thu (25/04) | 25 Apr 2024 | Zone 1 |  | Continue Noise barrier bracings and panels installation works
Thu (25/04) | 25 Apr 2024 | Zone 1 |  | Footpath casting ongoing
Thu (25/04) | 25 Apr 2024 | S4 |  | Pile head hacking current status
Thu (25/04) | 25 Apr 2024 | UKP30 |  | Boring done. Now pending to cast
Thu (25/04) | 25 Apr 2024 | ST191 |  | Casting completed at 1512hrs. Total vol: 165m3
Thu (25/04) | 25 Apr 2024 | ST97 | rig 2 | Trimming ongoing
Thu (25/04) | 25 Apr 2024 | Rig 3 |  | Machine maintenance ongoing
Thu (25/04) | 25 Apr 2024 | DW75 |  | B2 excavation in progress, 18.5/27.4m
Thu (25/04) | 25 Apr 2024 | ST79 |  | B1 excavation in progress, 22/39m
Thu (25/04) | 25 Apr 2024 | ST75 |  | Rebar cage installation completed, 4/4nos. Now preparing for hanging bar installation
Thu (25/04) | 25 Apr 2024 | PBH6 |  | SI in progress
Thu (25/04) | 25 Apr 2024 | BRP05 |  | Guidewall TT ongoing
Thu (25/04) | 25 Apr 2024 | BRP01 |  | Guidewall cast
Thu (25/04) | 25 Apr 2024 | P13 |  | SPPG cable Retrieved. Backfilling in progress till 10pm
Thu (25/04) | 25 Apr 2024 | MH5-2 |  | Work end for the day, stopped at #40 pipe. Balance 7 nos
Thu (25/04) | 25 Apr 2024 | Zone 1 |  | Footpath at new junction for stage 1 cast
Thu (25/04) | 25 Apr 2024 | MH1-2 |  | Tonight to bring down scaffold materials for intermediate slab
Thu (25/04) | 25 Apr 2024 | P14-3 |  | Casting in progress
Thu (25/04) | 25 Apr 2024 | PBH-6 |  | TT hand augering works ongoing
Thu (25/04) | 25 Apr 2024 | PBH-12 |  | Grouting completed. Next will shift to PBH-5
Fri (26/04) | 26 Apr 2024 | PBH05 |  | Drilling ongoing, current depth 6m
Fri (26/04) | 26 Apr 2024 | PBH06 |  | Drilling ongoing, current depth 25m
Fri (26/04) | 26 Apr 2024 | P43-44 |  | GCE preparing area for JGP works. Plan to start first point today
Fri (26/04) | 26 Apr 2024 | ST192-BC3 |  | 1st bite trenching in progress, depth at 16/34.7m
Fri (26/04) | 26 Apr 2024 | ST79-BC1 |  | 1st bite trenching continue at, 26.7/39m
Fri (26/04) | 26 Apr 2024 | VS DW70-BC4 |  | Pre-excavation done. Preparation to start trenching
Fri (26/04) | 26 Apr 2024 | VS DW75-BC4 |  | Desanding done. Preparation for final Koden and rebar cage installation
Fri (26/04) | 26 Apr 2024 | ST97 - BC2 |  | Desanding in progress
Fri (26/04) | 26 Apr 2024 | Zone 3 |  | Bachy preparation to start excavation for Guidewall ST005 & ST004
Fri (26/04) | 26 Apr 2024 | P22 |  | Pit exposed for SPPG to spike the abandoned 66kV cables
Fri (26/04) | 26 Apr 2024 | Zone 4 |  | Grouting ongoing for point B-265
Fri (26/04) | 26 Apr 2024 | P18 |  | Premix hacking for bp works
Fri (26/04) | 26 Apr 2024 | Zone 2 |  | Pile cap Rebar shifting to S4
Fri (26/04) | 26 Apr 2024 | P12-1 |  | Preboring & trial trench works for ERSS installation
Fri (26/04) | 26 Apr 2024 | P10-1-3 |  | BP boring works in progress
Fri (26/04) | 26 Apr 2024 | ST97 |  | C-lug welding ongoing for WS side trimming and removal
Fri (26/04) | 26 Apr 2024 | BRP05 |  | Guidewall rebar works ongoing
Fri (26/04) | 26 Apr 2024 | MH5-2 |  | #41 pipe jacking in progress
Fri (26/04) | 26 Apr 2024 | Zone 1 |  | Noise barrier panels installation. To complete by today
Fri (26/04) | 26 Apr 2024 | MH1-2 |  | Intermediate slab works ongoing
Fri (26/04) | 26 Apr 2024 | S4 |  | Pile head hacking completed, hardcores clearing ongoing. Today to do base lean concrete
Fri (26/04) | 26 Apr 2024 | VS DW75-BC4 |  | Trenching completed for 2nd bite
Fri (26/04) | 26 Apr 2024 | DT97-BC1 |  | 1st bite trenching continue
Fri (26/04) | 26 Apr 2024 | ST97-BC2 |  | Trimming in progress
Fri (26/04) | 26 Apr 2024 | Zone 3 |  | Dongah crane inspection ongoing
Fri (26/04) | 26 Apr 2024 | VS DW75-BC4 |  | Preparation for c-lug welding for trimming
Fri (26/04) | 26 Apr 2024 | P43 |  | JGP rig ready at first point. Pending to start. Mixer pump fixing still ongoing
Fri (26/04) | 26 Apr 2024 | DW75 |  | B1 cleaning ongoing
Fri (26/04) | 26 Apr 2024 | ST97 |  | Endplate joint removal ongoing
Fri (26/04) | 26 Apr 2024 | DR1 |  | RG rig preparing to mobilise at location
Fri (26/04) | 26 Apr 2024 | ST75 |  | Casting completed at 1328hrs. Total volume: 165m3
Fri (26/04) | 26 Apr 2024 | P10-1-3 |  | BP boring and rebar lowering completed. Concrete ordered and casting otw
Fri (26/04) | 26 Apr 2024 | P9-1-2 |  | BP boring works in progress
Fri (26/04) | 26 Apr 2024 | P9-2 |  | Column rebar cage prefabrication in progress
Fri (26/04) | 26 Apr 2024 | MH5-2 |  | #41 pipe jacking in progress
Fri (26/04) | 26 Apr 2024 | PBH6 |  | In progress, 29m
Fri (26/04) | 26 Apr 2024 | PBH5 |  | SPT in progress
Fri (26/04) | 26 Apr 2024 | Zone 1 |  | Current status of Noise barrier panels installation. Today will complete
Fri (26/04) | 26 Apr 2024 | MH1-2 |  | Supports installation for intermediate slab
Fri (26/04) | 26 Apr 2024 | MH1-2 |  | Caisson wall hacking works
Fri (26/04) | 26 Apr 2024 | P12-1 |  | Continue preboring works for ERSS
Fri (26/04) | 26 Apr 2024 | S4 |  | Pile head trimming & levelling works for base lean concrete
Fri (26/04) | 26 Apr 2024 | ST75 |  | Casting in progress, 75/140 m3
Fri (26/04) | 26 Apr 2024 | ST79- BC1 |  | 1st bite trenching continue
Fri (26/04) | 26 Apr 2024 | DW75 |  | Trimming continue at water stop side
Fri (26/04) | 26 Apr 2024 | ST97 |  | Waterstop loosening
Fri (26/04) | 26 Apr 2024 | P15 |  | TT for piling works completed. Backfilling
Fri (26/04) | 26 Apr 2024 | P9-1-2 |  | Casting in progress
Fri (26/04) | 26 Apr 2024 | MH1-2 |  | Tonight to continue formwork for intermediate slab
Fri (26/04) | 26 Apr 2024 | S4 |  | Lean concrete completed
Fri (26/04) | 26 Apr 2024 | DR1 |  | Existing box culvert already hacked ard 20m/60m. KTC will continue clearing the slurry and do trial trench. LE target to resume on Monday, concurrently KTC will continue the balance hacking works
Fri (26/04) | 26 Apr 2024 | ST75 |  | Casting ongoing, 139/156m3
Fri (26/04) | 26 Apr 2024 | ST79 |  | B1 in progress, 24.5/39m
Fri (26/04) | 26 Apr 2024 | DW75 |  | Trimming ongoing
Sat (27/04) | 27 Apr 2024 | VS DW70-BC4 |  | 2nd bite trenching started. 6m/27.4m
Sat (27/04) | 27 Apr 2024 | VS DW75 |  | Preparation for Tremie pipe installation. Tonight to cast
Sat (27/04) | 27 Apr 2024 | ST97 |  | Rebar cage lowering. 5/6 cages
Sat (27/04) | 27 Apr 2024 | Zone 3 receiving shaft area |  | JGP works stopped for the day. No more activity
Sat (27/04) | 27 Apr 2024 | ST87- BC2 |  | 1st bite trenching, 18.8m/34m
Sat (27/04) | 27 Apr 2024 | ST79-BC1 |  | 1st bite trenching, 30.2m/39m
Sat (27/04) | 27 Apr 2024 | Loyang lane gate 5 |  | SPPG here backfilling of open pit. 22KV diversion completed til LVC substation
Sat (27/04) | 27 Apr 2024 | DW75 |  | Final Koden completed
Sat (27/04) | 27 Apr 2024 | MH1-2 |  | Intermediate slab formwork done, preparation to start rebar works
Sat (27/04) | 27 Apr 2024 | ST192-BC3 |  | 1st bite trenching in progress, depth at 25/34.7m
Sat (27/04) | 27 Apr 2024 | ST79-BC1 |  | 1st bite trenching continue at, 28.5m/39m
Sat (27/04) | 27 Apr 2024 | ST192 |  | Cutter body hoisting up for teeth maintenance
Sat (27/04) | 27 Apr 2024 | DW70 |  | 1st bite trenching at 13m depth
Sat (27/04) | 27 Apr 2024 | DW75 |  | Waterstop lowering
Sat (27/04) | 27 Apr 2024 | ST97 |  | Final Koden in progress
Sat (27/04) | 27 Apr 2024 | P14-2 |  | Casting in progress, waiting for last load
Sat (27/04) | 27 Apr 2024 | P13-3 |  | Boring completed. Tonight also to cast
Sat (27/04) | 27 Apr 2024 | MH1-2 |  | Intermediate slab tonight to cast, waiting for concrete lorry
Sat (27/04) | 27 Apr 2024 | ST192-BC3 |  | 1st bite trenching resume, depth at 30/34.7m
Sun (28/04) | 28 Apr 2024 | P12 |  | No activity
Sun (28/04) | 28 Apr 2024 | P9 |  | WH loading and shifting of rebars. No other activity
Sun (28/04) | 28 Apr 2024 | Zone 2 |  | No other activity
Sun (28/04) | 28 Apr 2024 | MH5-2 |  | No activity
Sun (28/04) | 28 Apr 2024 | MH1-2 |  | Intermediate slab was cast last night. Now housekeeping ongoing
Sun (28/04) | 28 Apr 2024 | Zone 1 |  | No other activity
Sun (28/04) | 28 Apr 2024 | Zone 3 Seongha |  | No activity
Sun (28/04) | 28 Apr 2024 | ST192 |  | B2 started at 0910hrs. In progress, 8m
Sun (28/04) | 28 Apr 2024 | DR1 |  | Hardcore clearing ongoing by KTC
Sun (28/04) | 28 Apr 2024 | ST79 |  | B1 in progress, 37.4/39m
Sun (28/04) | 28 Apr 2024 | BC 2 |  | Machine maintenance ongoing
Sun (28/04) | 28 Apr 2024 | DW70 |  | B2 in progress, 22/27.4m
Sun (28/04) | 28 Apr 2024 | ST97 |  | Casting in progress, 165/240m3
Sun (28/04) | 28 Apr 2024 | P40 |  | Trial trench ongoing for ST101(half)-ST102(half)
Sun (28/04) | 28 Apr 2024 | P43 JGP |  | Point A-141 in progress
Sun (28/04) | 28 Apr 2024 | Zone 4 |  | No activity
Sun (28/04) | 28 Apr 2024 | Zone 3 UKP |  | No activity
Sun (28/04) | 28 Apr 2024 | Exit 3, BRP03 |  | Preparation for guidewall rebar works
Sun (28/04) | 28 Apr 2024 | Exit 3, BRP05 |  | Guidewall cast yesterday
Sun (28/04) | 28 Apr 2024 | S4 |  | No activity
Sun (28/04) | 28 Apr 2024 | PDR3 |  | Leychoon M&P
Sun (28/04) | 28 Apr 2024 | Zone 1 |  | Intermediate slab casting completed
Sun (28/04) | 28 Apr 2024 | P13-3 |  | Casting in progress
Sun (28/04) | 28 Apr 2024 | ST192-BC3 |  | 1st bite trenching in progress, depth at 31.85/34.7m
Sun (28/04) | 28 Apr 2024 | BRP03 |  | Guidewall rebar works ongoing
Sun (28/04) | 28 Apr 2024 | DW70 |  | 2nd bite trenching continue
Sun (28/04) | 28 Apr 2024 | DW75 |  | Casting in progress
Sun (28/04) | 28 Apr 2024 | ST97 |  | All cages installed. Hanging bar installation in progress
Sun (28/04) | 28 Apr 2024 | P43 |  | Point A-141 completed. Tmr to continue next point
Sun (28/04) | 28 Apr 2024 | Vent shaft DW77 |  | Trench setup
Sun (28/04) | 28 Apr 2024 | DW70 |  | B2 completed. C-lug welding ongoing
Sun (28/04) | 28 Apr 2024 | ST87 |  | B1 excavation resume
Sun (28/04) | 28 Apr 2024 | ST97 |  | Casting completed at 1253hrs. Total vol: 249m3
Sun (28/04) | 28 Apr 2024 | VS DW70-BC4 |  | 2nd bite trenching temporarily stop due to mud hose leaking
Sun (28/04) | 28 Apr 2024 | DW75 |  | Casting for the last load, total volume 112 m3
Sun (28/04) | 28 Apr 2024 | ST97 |  | Tremie pipes lowering
Sun (28/04) | 28 Apr 2024 | ST87- BC2 |  | 1st bite trenching continue, 33.9m/34m
Sun (28/04) | 28 Apr 2024 | ST79-BC1 |  | 1st bite trenching continue, 30.2m/39m
Sun (28/04) | 28 Apr 2024 | ST192-BC3 |  | 1st bite trenching temporarily stop for teeth replacement
Sun (28/04) | 28 Apr 2024 | Near N5 area |  | WH ground levelling for crane platform extension for mobile crane
Sun (28/04) | 28 Apr 2024 | N3 |  | No activity
Sun (28/04) | 28 Apr 2024 | N2 |  | No activity
Mon (29/04) | 29 Apr 2024 | P10-1-1 |  | Casing installed and preparation for boring
Mon (29/04) | 29 Apr 2024 | P9-1-1 |  | Prepare to start boring works for BP
Mon (29/04) | 29 Apr 2024 | P12 |  | LE continue preboring works for ERSS installation
Mon (29/04) | 29 Apr 2024 | Zone 1 |  | Eng hup cable pulling for stage 1 traffic light diversion
Mon (29/04) | 29 Apr 2024 | Zone 2 |  | Temporary stump wall & drain wall casting completed
Mon (29/04) | 29 Apr 2024 | MH1-2 |  | Formwork removal and housekeeping works
Mon (29/04) | 29 Apr 2024 | S4 |  | Rebar installation for pile cap
Mon (29/04) | 29 Apr 2024 | MH5-1 |  | Water pumping
Mon (29/04) | 29 Apr 2024 | P10-1-1 |  | Rebar cage installation in progress
Mon (29/04) | 29 Apr 2024 | P9-1-1 |  | Boring ongoing, 17/21m. Works till 930pm
Mon (29/04) | 29 Apr 2024 | Zone 1 |  | WH just finished loaded concrete barrier onto lorry crane for internal shifting within area
Mon (29/04) | 29 Apr 2024 | MH1-2 |  | No activity
Mon (29/04) | 29 Apr 2024 | S4 |  | No activity
Mon (29/04) | 29 Apr 2024 | CCW ST005 |  | Guidewall casting ongoing
Mon (29/04) | 29 Apr 2024 | ST192 |  | BC3 gearbox replacement & tightening works ongoing
Mon (29/04) | 29 Apr 2024 | ST79 |  | B2 temporarily stopped for cutter teeth changing
Mon (29/04) | 29 Apr 2024 | ST87 |  | B2 in progress, 26.6/34m
Mon (29/04) | 29 Apr 2024 | DW70 |  | Tremie pipes installation ongoing
Mon (29/04) | 29 Apr 2024 | DW77 |  | Endplate loosening ongoing
Mon (29/04) | 29 Apr 2024 | Zone 4 |  | GCE has completed works for the day
Mon (29/04) | 29 Apr 2024 | Exit 3, BRP03 |  | Guidewall pending for casting
Tue (30/04) | 30 Apr 2024 | N3 |  | Scaffold adjusting for formwork installation
Tue (30/04) | 30 Apr 2024 | P14 and 15 |  | Bored piling plan here today
Tue (30/04) | 30 Apr 2024 | P12 |  | ERSS pre-boring and soldier pile installation continue
Tue (30/04) | 30 Apr 2024 | Zone 1 |  | Hacking of temporary shaft for road diversion
Tue (30/04) | 30 Apr 2024 | Zone 1 |  | M&P machine here
Tue (30/04) | 30 Apr 2024 | S4 pile cap |  | Top bars installation in progress
Tue (30/04) | 30 Apr 2024 | Zone 1 |  | Premix laying completed
Tue (30/04) | 30 Apr 2024 | P10-1-1 |  | Casting completed
Tue (30/04) | 30 Apr 2024 | P18 |  | Excavation for SPPG spiked cables removal
Tue (30/04) | 30 Apr 2024 | Zone 4 |  | Pavement hacking for JGP works
Tue (30/04) | 30 Apr 2024 | Zone 4 |  | JGP in progress. Plan today 4 nos, 3rd point grouting in progress
Tue (30/04) | 30 Apr 2024 | P9-1-1 |  | Boring was completed. Now rebar cage installation
Tue (30/04) | 30 Apr 2024 | N3 |  | Continue scaffold adjusting for formwork installation
Tue (30/04) | 30 Apr 2024 | P12 |  | Continue ERSS preboring and soldier pile installation
Tue (30/04) | 30 Apr 2024 | P13-1-1 |  | Boring for BP in progress
Tue (30/04) | 30 Apr 2024 | BRP03 |  | Guidewall cast
Tue (30/04) | 30 Apr 2024 | Zone 4 receiving shaft area |  | JGP in progress. Today target 2 points, 1st point grouting in progress
Tue (30/04) | 30 Apr 2024 | ST192 |  | Resume B2 excavation
Tue (30/04) | 30 Apr 2024 | S4 |  | Pile cap rebar installation works
Tue (30/04) | 30 Apr 2024 | Zone 1 |  | M&P premix laying works
Tue (30/04) | 30 Apr 2024 | ST79 |  | B2 in progress, 26.7/39m
Tue (30/04) | 30 Apr 2024 | ST87 |  | B2 completed. Internal koden check ongoing
Tue (30/04) | 30 Apr 2024 | DW70 |  | Casting completed at 0302hrs. Total vol: 89m3
Tue (30/04) | 30 Apr 2024 | DW77 |  | Endplate loosening ongoing
Tue (30/04) | 30 Apr 2024 | P9-1-1 |  | Casting ongoing
Tue (30/04) | 30 Apr 2024 | CCW ST007 |  | Guidewall cast. Bachy done for the day
Tue (30/04) | 30 Apr 2024 | N3 |  | Continue scaffold adjustment
Tue (30/04) | 30 Apr 2024 | P13-1-1 |  | Boring completed. Night shift team will continue rebar cage installation and casting
Tue (30/04) | 30 Apr 2024 | MH5-2 |  | No activity
Tue (30/04) | 30 Apr 2024 | Zone 1 |  | Premix laying to continue. Now waiting for premix delivery
Tue (30/04) | 30 Apr 2024 | MH1-2 |  | No activity
Tue (30/04) | 30 Apr 2024 | S4 |  | No activity
Tue (30/04) | 30 Apr 2024 | ST192 |  | B2 internal koden check ongoing and BC cutter teeth changing
Tue (30/04) | 30 Apr 2024 | ST79 |  | B2 in progress, 27.9/39m
Tue (30/04) | 30 Apr 2024 | ST87 |  | B3 ongoing, 31m
Tue (30/04) | 30 Apr 2024 | DW77 |  | Hanging bar tightening ongoing
Tue (30/04) | 30 Apr 2024 | Exit 3 |  | BRP 02 and 06 today to start excavation for guidewall construction
Tue (30/04) | 30 Apr 2024 | Exit 3 |  | PBH 06 drilling on going
Wed (01/05) | 01 May 2024 | P13-1-1 |  | Casting started
Wed (01/05) | 01 May 2024 | P13-1-1 |  | Casting completed
Wed (01/05) | 01 May 2024 | DW77 |  | Casting ongoing, 63m3
Wed (01/05) | 01 May 2024 | ST192 |  | Endplate loosening ongoing at ST191 side
Wed (01/05) | 01 May 2024 | ST87 |  | B3 excavation ongoing
Wed (01/05) | 01 May 2024 | DW77 |  | Casting completed at 0400hrs. Total vol: 63m3
Wed (01/05) | 01 May 2024 | Vent shaft DW74 | BC4 | Target to start today
Wed (01/05) | 01 May 2024 | ST79 |  | B2 temporarily stopped due to cutter mud drum elbow leaking. CD: 28.9/39m
Thu (02/05) | 02 May 2024 | Zone 1 | North bound | Preparation to start premix works
Thu (02/05) | 02 May 2024 | Zone 1 |  | Eng Hup traffic light cable pulling works
Thu (02/05) | 02 May 2024 | Zone 2 |  | Formwork removal for temporary stump wall & drain wall
Thu (02/05) | 02 May 2024 | S4 |  | Side Formwork & rebars installation for pilecap
Thu (02/05) | 02 May 2024 | ST192 |  | Tremie pipe installation in progress
Thu (02/05) | 02 May 2024 | BC3 |  | Cutter wheel maintenance
Thu (02/05) | 02 May 2024 | ST79 |  | Gear box replacement, current at 2nd bite 30.6/39m
Thu (02/05) | 02 May 2024 | ST87 |  | Rebar cage installation, 5/6 installed. Last cage lapping
Thu (02/05) | 02 May 2024 | ST98-BC2 |  | 1st bite trenching at 22.5m/34.1m
Thu (02/05) | 02 May 2024 | DW74-BC4 |  | 2nd bite trenching preparation to start
Thu (02/05) | 02 May 2024 | DW74 |  | B1 internal koden check
Thu (02/05) | 02 May 2024 | ST98 |  | B1 excavation in progress
Thu (02/05) | 02 May 2024 | ST79 |  | BC cutter maintenance ongoing. B2 depth 30.6/39m
Thu (02/05) | 02 May 2024 | DR1 |  | RG drilling ongoing for inclinometer installation
Thu (02/05) | 02 May 2024 | DR1 |  | LE to continue ERSS installation. Materials just arrived
Thu (02/05) | 02 May 2024 | ST79 |  | B2 still on hold. Now changing the BC cutter wheel
Thu (02/05) | 02 May 2024 | ST87 |  | Rebar cage installation, 3/6nos
Thu (02/05) | 02 May 2024 | DR1 |  | Currently no activity by LE. Existing vibro was sent out for servicing. Was informed that new one coming in today
Thu (02/05) | 02 May 2024 | ST98 |  | B1 in progress, 16/34.1m
Thu (02/05) | 02 May 2024 | DW74 |  | Trimming temporarily stopped due to desander suction line leakage. CD 15/32.9m
Thu (02/05) | 02 May 2024 | UKP48 and UKP49 |  | In progress
Thu (02/05) | 02 May 2024 | ST192 |  | Hanging bar installation ongoing
Thu (02/05) | 02 May 2024 | Exit 3, BRP06 |  | Setting out for GW trial trench works
Thu (02/05) | 02 May 2024 | ST008-009 |  | Guidewall formwork installation
Thu (02/05) | 02 May 2024 | N5 |  | Column formwork installation ongoing
Thu (02/05) | 02 May 2024 | P13-2 |  | Boring ongoing
Thu (02/05) | 02 May 2024 | P12 |  | ERSS installation ongoing
Thu (02/05) | 02 May 2024 | Near MH5-2 |  | Netlink cable works
Thu (02/05) | 02 May 2024 | MH1-2 |  | Cleaning works ongoing
Thu (02/05) | 02 May 2024 | Zone 1 |  | Premix completed. Lane markings done
Thu (02/05) | 02 May 2024 | S4 |  | Pilecap rebar works in progress
Thu (02/05) | 02 May 2024 | ST008-009 |  | Guidewall casting ongoing
Thu (02/05) | 02 May 2024 | BRP06 |  | TT completed. Backfilling ongoing
Thu (02/05) | 02 May 2024 | P18 |  | Excavation to expose SPPG pipe for spiking till 10pm
Thu (02/05) | 02 May 2024 | N5 |  | Pier formwork closed. Balance propping, Wendyng went back at 7pm
Thu (02/05) | 02 May 2024 | P13-2 |  | Rebar cage installation
Thu (02/05) | 02 May 2024 | P10-1-2 |  | Boring also completed. Tonight to cast
Thu (02/05) | 02 May 2024 | Zone 1 |  | Reflective strip painting at water barrier, till 10pm
Thu (02/05) | 02 May 2024 | S4 |  | No more activity, column starter bar completed
Thu (02/05) | 02 May 2024 | P16 |  | Backfilling works
Thu (02/05) | 02 May 2024 | N5 |  | Mobile crane setting up for column formwork installation
Thu (02/05) | 02 May 2024 | P12 |  | Preboring in progress for ERSS installation
Thu (02/05) | 02 May 2024 | P10-1-2 |  | Preparation to start boring works and casing installation
Thu (02/05) | 02 May 2024 | Zone 1 |  | CGS kerb installation
Thu (02/05) | 02 May 2024 | Zone 1 |  | CGS excavation and RCA levelling works
Thu (02/05) | 02 May 2024 | Zone 1 |  | Preparation to premix the balance area
Fri (03/05) | 03 May 2024 | S4 |  | Shear links and Formwork installation for pilecap
Fri (03/05) | 03 May 2024 | N2 |  | Column Rebar installation
Fri (03/05) | 03 May 2024 | P12 |  | Preboring for ERSS installation. To complete by today
Fri (03/05) | 03 May 2024 | ST79 |  | B2 temporarily stopped for centre holder rectification. CD 30.8/39m
Fri (03/05) | 03 May 2024 | UKP23 and UKP24 |  | Platform preparation. Today to do these 2 points
Fri (03/05) | 03 May 2024 | MH1-2 |  | Precast MH cover installation
Fri (03/05) | 03 May 2024 | Zone 1 |  | Kerb installation and concrete barriers painting works
Fri (03/05) | 03 May 2024 | ST193-BC3 |  | Preparation for excavation
Fri (03/05) | 03 May 2024 | DW74-BC4 |  | 3rd bite trenching started 30/32.9m
Fri (03/05) | 03 May 2024 | ST98-BC2 |  | 1st bite trenching at 29.6m/34.1m
Fri (03/05) | 03 May 2024 | ST79-BC1 |  | 2nd bite trenching, depth at 31.7/39m
Fri (03/05) | 03 May 2024 | Exit 3 |  | Safety briefing for KP unloading was done
Fri (03/05) | 03 May 2024 | Exit 3 |  | 3nos KPs safely unloaded
Fri (03/05) | 03 May 2024 | Zone 3 |  | PBH66 trial trench ongoing
Fri (03/05) | 03 May 2024 | P14-1-1 & P15-1-2 |  | Continue boring works for BP
Fri (03/05) | 03 May 2024 | N2 |  | Column rebar cage lowered. Lapping works ongoing
Fri (03/05) | 03 May 2024 | P15-2 |  | Casing installed. Preparing to continue boring
Fri (03/05) | 03 May 2024 | P14-1 |  | Boring done. Preparing for casting
Fri (03/05) | 03 May 2024 | N2 |  | Support installation for column rebar
Fri (03/05) | 03 May 2024 | P10-1-2 |  | Casting completed. Tremie pipe dismantling and casing removal
Fri (03/05) | 03 May 2024 | DW74-BC4 |  | 2nd bite trenching in progress, 24m/32.9m
Fri (03/05) | 03 May 2024 | ST98-BC2 |  | 1st bite trenching at 28.1m/34.1m
Fri (03/05) | 03 May 2024 | ST87 |  | Tremie pipe installed. Concrete ordered
Fri (03/05) | 03 May 2024 | ST79-BC1 |  | Gear box replacement completed. Current at 2nd bite 30.6/39m
Fri (03/05) | 03 May 2024 | P15-2 |  | Balance to bore about 4m. To complete by 930pm
Fri (03/05) | 03 May 2024 | P14-1 |  | Rebar cage installation
Fri (03/05) | 03 May 2024 | Zone 2 beside shell |  | Hoarding dismantled and netting installation in progress. Tomorrow CGS plan to fo M&P here
Fri (03/05) | 03 May 2024 | DR1 |  | RG preparing for inclinometer installation
Fri (03/05) | 03 May 2024 | DR1 |  | LE to resume ERSS installation today. Preparation for trial hole before installation ongoing
Fri (03/05) | 03 May 2024 | ST87 |  | Casting in progress, 109/230m3
Fri (03/05) | 03 May 2024 | ST98 |  | B1 temporarily stopped for cutter teeth changing
Fri (03/05) | 03 May 2024 | N5 |  | Tie rod installation for column Formwork
Fri (03/05) | 03 May 2024 | P15-1-2 |  | Boring works for BP in progress
Fri (03/05) | 03 May 2024 | DW74 |  | B2 temporarily stopped for cutter wheel cleaning. CD 24.1/39m
Sat (04/05) | 04 May 2024 | Exit 3 |  | Guidewall no activity due to rain. Water pumping ongoing
Sat (04/05) | 04 May 2024 | Pbh-07 |  | Drilling in progress, CD: 31.5m
Sat (04/05) | 04 May 2024 | ST193-BC3 |  | Continue 1st bite trenching works, CD: 16m
Sat (04/05) | 04 May 2024 | Zone 3 P-31 |  | Production fissure grout point O-130 drilling in progress
Sat (04/05) | 04 May 2024 | Zone 3 |  | Preparation to start boring for UKP47
Sat (04/05) | 04 May 2024 | ST79-BC1 |  | Continue 2nd bite excavation, current depth 31.5m
Sat (04/05) | 04 May 2024 | ST193-BC3 |  | 1st bite trenching at 27/34.7m depth
Sat (04/05) | 04 May 2024 | DW74-BC4 |  | Removal of end plate ongoing
Sat (04/05) | 04 May 2024 | DW69-BC4 |  | Cutter wheel maintenance then start excavation
Sat (04/05) | 04 May 2024 | DW74 |  | Final koden in progress
Sat (04/05) | 04 May 2024 | ST98-BC2 |  | 2nd bite trenching at 22.7m/34.1m
Sat (04/05) | 04 May 2024 | ST98-BC2 |  | Flap welding & cutter teeth replacement works
Sat (04/05) | 04 May 2024 | Zone 3 |  | Trial trench for drain removal works
Sat (04/05) | 04 May 2024 | Zone 3, P43 |  | Preparation for A117 JGP drilling works. Water pumping ongoing
Sat (04/05) | 04 May 2024 | Zone 3, Loyang way |  | Krischo premix hacking for water pipe laying works
Sat (04/05) | 04 May 2024 | Zone 4 |  | B-434 jgp grouting ongoing
Sat (04/05) | 04 May 2024 | DR1,ERSS |  | No activity due to continuous rain
Sat (04/05) | 04 May 2024 | P16-1-2 |  | Boring works for BP
Sat (04/05) | 04 May 2024 | N5 |  | Formwork closing for column works
Sat (04/05) | 04 May 2024 | P15-1-2 |  | Rebar cage lowered. Afternoon to cast
Sat (04/05) | 04 May 2024 | P12 |  | Current status for ERSS installation
Sat (04/05) | 04 May 2024 | S4 |  | Formwork closing for pilecap
Sat (04/05) | 04 May 2024 | Zone 1 |  | Netlink cable pulling works
Sat (04/05) | 04 May 2024 | DW74-BC4 |  | End plate loosening in progress
Sat (04/05) | 04 May 2024 | ST98-BC2 |  | 1st bite trenching continue
Sat (04/05) | 04 May 2024 | PBH-07 |  | Drilling completed. Now pending termination depth confirmation
Sat (04/05) | 04 May 2024 | ST193-BC3 |  | 1st bite trenching works, CD: 25.2m/34.7m
Sat (04/05) | 04 May 2024 | Zone 3 P31 - P32 |  | Production fissure grout point O-134 & O-140 drilling in progress
Sat (04/05) | 04 May 2024 | Zone 3 |  | UKP47 boring completed. Preparation to start boring for UKP23
Sat (04/05) | 04 May 2024 | PBH-66 |  | Drilling in progress, CD is 20m
Sat (04/05) | 04 May 2024 | ST79-BC1 |  | Continue 2nd bite excavation
Sat (04/05) | 04 May 2024 | ST98-BC2 |  | 2nd bite excavation works ongoing, CD: 17m
Sat (04/05) | 04 May 2024 | DR1,ERSS |  | Trial trench for ERSS installation ongoing
Sat (04/05) | 04 May 2024 | DW74-BC4 |  | 2nd bite cleaning ongoing
Sat (04/05) | 04 May 2024 | Zone 3, P43 |  | A-117 JGP drilling works completed. Grouting works commenced and ongoing
Sat (04/05) | 04 May 2024 | Zone 3, Loyang way |  | Krischo pipe bend laying (3m) completed. Reinstatement works ongoing
Sat (04/05) | 04 May 2024 | Zone 4 |  | B-434 & B-318 JGP grouting completed. B-432 drilling works ongoing
Sat (04/05) | 04 May 2024 | Zone 4 |  | Mo Guan starhub trial trench works
Sat (04/05) | 04 May 2024 | P16-1-2 |  | Continue boring works for BP
Sat (04/05) | 04 May 2024 | P17 |  | Removal of spiked cables ongoing
Sat (04/05) | 04 May 2024 | P15-2 |  | BP casting completed
Sat (04/05) | 04 May 2024 | N5 Column |  | Casting works in progress
Sat (04/05) | 04 May 2024 | P14-1 |  | Casting completed
Sat (04/05) | 04 May 2024 | N3 |  | Preparation for Formwork closing works
Sat (04/05) | 04 May 2024 | P12 |  | ERSS installation completed. Backfilling ongoing for KTC works
Sat (04/05) | 04 May 2024 | Zone 2 |  | M&P works ongoing
Sat (04/05) | 04 May 2024 | Zone 1 |  | D1 kerbs patching works
Sat (04/05) | 04 May 2024 | S4 |  | Formwork closing works for pilecap. Today to cast
Sat (04/05) | 04 May 2024 | ST193-BC3 |  | 1st bite trenching in progress
Sat (04/05) | 04 May 2024 | DW74-BC4 |  | Trimming at end plate side continue
Sat (04/05) | 04 May 2024 | ST98-BC2 |  | Cutter body hoist up for maintenance. Trimming at water stop side
Sat (04/05) | 04 May 2024 | ST79-BC1 |  | Cutter body extraction for teeth replacement
Sat (04/05) | 04 May 2024 | P16-2 |  | Boring completed
Sat (04/05) | 04 May 2024 | Zone 1 |  | Kerb installation till 10pm
Sat (04/05) | 04 May 2024 | S4 |  | Casting in progress
Sun (05/05) | 05 May 2024 | P16-2 |  | Casting completed
Sun (05/05) | 05 May 2024 | ST193-BC3 |  | 1st bite trenching at 32/34.7m depth
Sun (05/05) | 05 May 2024 | DW69-BC4 |  | 1st bite trenching, 16m depth
Sun (05/05) | 05 May 2024 | DW74 |  | Rebar cage installation, 1/6 cage installed
Sun (05/05) | 05 May 2024 | ST98-BC2 |  | 2nd bite trenching at 30.5m/34.1m
Sun (05/05) | 05 May 2024 | ST79-BC1 |  | 2nd bite trenching in progress, depth at 32.9/39m
Mon (06/05) | 06 May 2024 | UKP46 |  | In progress
Mon (06/05) | 06 May 2024 | UKP26 |  | Trial trench in progress
Mon (06/05) | 06 May 2024 | PBH66 |  | SI in progress
Mon (06/05) | 06 May 2024 | DR1 |  | LE continue ERSS installation
Mon (06/05) | 06 May 2024 | ST193 |  | BC3 mud pump change in progress
Mon (06/05) | 06 May 2024 | ST79 |  | BC2 cutter maintenance ongoing. Now also preparing for final koden check & WS installation
Mon (06/05) | 06 May 2024 | DW69 |  | B2 in progress, 22/27.4m
Mon (06/05) | 06 May 2024 | ST98 |  | Trimming ongoing
Mon (06/05) | 06 May 2024 | P43 |  | JGP point A-129 completed. Now preparing for next point A-110
Mon (06/05) | 06 May 2024 | Exit 1 |  | Crane boom down inspection ongoing
Mon (06/05) | 06 May 2024 | LW | in front of gate 7 | Lane closure for Krishco for split tee and connection works
Mon (06/05) | 06 May 2024 | Zone 4 |  | JGP points B-377 and B-317 completed. Now preparing for next point, B-200
Mon (06/05) | 06 May 2024 | ST113 |  | Trial trench ongoing
Mon (06/05) | 06 May 2024 | Exit 3, BRP06 |  | Guidewall excavation in progress
Mon (06/05) | 06 May 2024 | P17-1 |  | Preparation for pre boring and casing installation
Mon (06/05) | 06 May 2024 | P18-2 |  | Boring completed
Mon (06/05) | 06 May 2024 | N3 |  | Preparation for formwork closing
Mon (06/05) | 06 May 2024 | P12 |  | Excavation to W1 layer completed. Scaffold access erection
Mon (06/05) | 06 May 2024 | P10 |  | Platform erection for rebar cage fabrication
Mon (06/05) | 06 May 2024 | P10 |  | Trial trench for ERSS on going
Mon (06/05) | 06 May 2024 | Zone 2 opp shell |  | Lane marking
Mon (06/05) | 06 May 2024 | Zone 1 |  | Premix laying in progress
Mon (06/05) | 06 May 2024 | Exit 3 |  | Excavation for barrette pile guidewall construction, BP06
Mon (06/05) | 06 May 2024 | UKP 46 |  | Tremie pipe installation on going for casting
Mon (06/05) | 06 May 2024 | ST193-BC3 |  | 2nd bite trenching at 19/34.7m depth
Mon (06/05) | 06 May 2024 | DR1 |  | SP driving continue till 7pm
Mon (06/05) | 06 May 2024 | ST79 |  | Endplate installation in progress
Mon (06/05) | 06 May 2024 | ST76-BC1 |  | 1st bite trenching in progress, depth at 9/39m
Mon (06/05) | 06 May 2024 | ST98 |  | End plate extracted
Mon (06/05) | 06 May 2024 | P43 |  | JGP works continue. 2nd point grouting for the day. Target 2 nos
Mon (06/05) | 06 May 2024 | P17-1 |  | Boring in progress
Mon (06/05) | 06 May 2024 | P12 |  | Protection concrete casting
Tue (07/05) | 07 May 2024 | ST79 |  | Rebar cage installation in progress, 3/8nos
Tue (07/05) | 07 May 2024 | BC2 |  | Suction hose replacement ongoing. This rig is planned for ST84 excavation
Tue (07/05) | 07 May 2024 | ST98 |  | Endplate joint welding ongoing
Tue (07/05) | 07 May 2024 | DW69 |  | C-lug welding ongoing for WS endplate removal
Tue (07/05) | 07 May 2024 | Zone 4 JGP |  | Preparing to start B-433
Tue (07/05) | 07 May 2024 | LW | outside gate 7 | CR1070 PUB inspection
Tue (07/05) | 07 May 2024 | N3 |  | Today to close formwork for pier
Tue (07/05) | 07 May 2024 | P12 |  | Water pumping, to continue installation waler bracket
Tue (07/05) | 07 May 2024 | Zone 2 |  | Scaffold erection for soil disposal tower inspection
Tue (07/05) | 07 May 2024 | Zone 2 opp shell |  | Premix hacking to raised up singtel MH cover
Tue (07/05) | 07 May 2024 | Zone 1 center median |  | Today to hacked premix and lay bentonite pipe
Tue (07/05) | 07 May 2024 | Zone 1 |  | Today to complete mill & patch here
Tue (07/05) | 07 May 2024 | Z4 P51 |  | Abandoned drain and footpath were hacked. Levelling ongoing
Tue (07/05) | 07 May 2024 | P43 JGP |  | Point A-139 in progress
Tue (07/05) | 07 May 2024 | ST98 |  | WS installation ongoing
Tue (07/05) | 07 May 2024 | DR1 |  | Surveying works ongoing at ERSS area
Tue (07/05) | 07 May 2024 | Zone 3 |  | Dongah 180T crane body just arrived
Tue (07/05) | 07 May 2024 | UKP22 |  | Casing installation ongoing
Tue (07/05) | 07 May 2024 | Z3 Fissure Grout |  | 2 machines in operation. Point O-146 drilling ongoing. I-93 drilling completed, cotton packer installation in progress
Tue (07/05) | 07 May 2024 | UKP21 |  | Safety briefing done prior to trial trenching works
Tue (07/05) | 07 May 2024 | DW19 and DW18 |  | Trial trench in progress
Tue (07/05) | 07 May 2024 | P17-1 |  | Casting done
Tue (07/05) | 07 May 2024 | ST98 |  | Rebar cage installation in progress, 3/6nos
Tue (07/05) | 07 May 2024 | ST79 |  | Rebar cage installation ongoing, 5/8nos
Tue (07/05) | 07 May 2024 | Zone 2 opp shell |  | Singtel MH cover exposed
Tue (07/05) | 07 May 2024 | P10-1 |  | Preparation for pre-boring for IM installation
Tue (07/05) | 07 May 2024 | P12 |  | Bracket installation for waler continue
Tue (07/05) | 07 May 2024 | P16-3 |  | Boring works continue
Tue (07/05) | 07 May 2024 | ST76 |  | B1 in progress, 27/39m
Tue (07/05) | 07 May 2024 | DR1 |  | LE materials arrived on site
Tue (07/05) | 07 May 2024 | DR1 |  | KTC clearing hardcore
Tue (07/05) | 07 May 2024 | Zone 3 fissure grout |  | Drilling ongoing for O-148. Next drilling point pending RTO inspection
Tue (07/05) | 07 May 2024 | ST193 |  | Cutter teeth replaced. Now resume B2 excavation, 30/34.7m
Tue (07/05) | 07 May 2024 | UKP21 |  | Trial trench in progress
Tue (07/05) | 07 May 2024 | UKP22 |  | In progress
Tue (07/05) | 07 May 2024 | DW19 |  | Trial trench ongoing. Found gas pipe (alr decom)
Tue (07/05) | 07 May 2024 | P17-1 |  | Casting started
Tue (07/05) | 07 May 2024 | P15 |  | Boring ongoing
Tue (07/05) | 07 May 2024 | N3 |  | Column formwork installation ongoing
Tue (07/05) | 07 May 2024 | P12 |  | Bracket installation for waler in progress
Tue (07/05) | 07 May 2024 | P10-2 |  | Pier rebar cage fabrication in progress
Tue (07/05) | 07 May 2024 | MH1-2 |  | Cleaning works ongoing
Tue (07/05) | 07 May 2024 | Zone 1 LA |  | Works done for the day. Lane reopened
Tue (07/05) | 07 May 2024 | North ramp P16-3 |  | Boring done. Preparing for rebar cage lowering
Tue (07/05) | 07 May 2024 | P15-3 |  | Boring in progress. Tonight to cast
Tue (07/05) | 07 May 2024 | Zone 3 CCW |  | Bachy to continue construction of guidewall
Tue (07/05) | 07 May 2024 | ST193 |  | B2 in progress, 26/34.7m
Tue (07/05) | 07 May 2024 | Zone 2 main viaduct |  | Today plan to do 2 nos BP, P16 and P15
Tue (07/05) | 07 May 2024 | ST76 |  | B1 in progress, 19.5/39m
Wed (08/05) | 08 May 2024 | ST79 |  | Casting in progress, 105/255m3
Wed (08/05) | 08 May 2024 | DW69 |  | WS endplate installation in progress
Wed (08/05) | 08 May 2024 | BC4 |  | Cutter teeth replacement ongoing
Wed (08/05) | 08 May 2024 | ST193-BC3 |  | Trimming completed. To extract end plate
Wed (08/05) | 08 May 2024 | BC1 |  | Engine maintenance
Wed (08/05) | 08 May 2024 | ST79 |  | Casting completed
Wed (08/05) | 08 May 2024 | P43 |  | GCE trial trench ongoing
Wed (08/05) | 08 May 2024 | P43 JGP |  | Point A-128 in progress
Wed (08/05) | 08 May 2024 | ST84-BC2 |  | Cutter wheel teeth replacement, Current at 1st bite, 32.6m/34m
Wed (08/05) | 08 May 2024 | LW | outside gate 7 | Lane closure for Krishco for PUB CCTV inspection
Wed (08/05) | 08 May 2024 | DW69 |  | Rebar cage installation. 5/6 in progress
Wed (08/05) | 08 May 2024 | Zone 4 GCE |  | Trial trench ongoing
Wed (08/05) | 08 May 2024 | Zone 4 JGP |  | Point B-204 in progress
Wed (08/05) | 08 May 2024 | Exit 3 |  | BRP 06 guidewall casting in progress
Wed (08/05) | 08 May 2024 | Zone 4 HSL |  | Crane assembly completed. Pending PE inspection
Wed (08/05) | 08 May 2024 | Zone 3 |  | Dongah 180T crane assembly in progress
Wed (08/05) | 08 May 2024 | ST84 |  | Cutter teeth replaced. Resume B1 excavation
Wed (08/05) | 08 May 2024 | ST79 |  | Casting in progress, 225/270m3
Wed (08/05) | 08 May 2024 | BC1 |  | Currently no activity. This rig will move to next panel, ST80
Wed (08/05) | 08 May 2024 | ST98 |  | Started casting
Wed (08/05) | 08 May 2024 | P43 JGP |  | Point A-108 now in progress
Wed (08/05) | 08 May 2024 | P43 GCE |  | Trial trench ongoing, found ST cable at 1.3m depth
Wed (08/05) | 08 May 2024 | Exit 1 |  | Dongah 180T crane assembly ongoing
Wed (08/05) | 08 May 2024 | DW69 |  | Rebar cage installation in progress, 3/6nos
Wed (08/05) | 08 May 2024 | BC4 |  | Currently no activity. This rig is planned for next panel, DW73
Wed (08/05) | 08 May 2024 | ST84 |  | B1 temporarily stopped for cutter teeth change. CD 32.6/34m
Wed (08/05) | 08 May 2024 | DR1 |  | LE continue ERSS installation
Wed (08/05) | 08 May 2024 | UKP27 |  | Boring ongoing
Wed (08/05) | 08 May 2024 | Zone 3 fissure grouting |  | PVC pipe and cotton packer inspection for I-104 and O-162. Depth checked for both points as well
Wed (08/05) | 08 May 2024 | P17 |  | Boring works ongoing
Wed (08/05) | 08 May 2024 | N3 |  | Formwork closing in progress
Wed (08/05) | 08 May 2024 | N2 |  | Rebar tying and preparation for formwork closing
Wed (08/05) | 08 May 2024 | P12 |  | No activity
Wed (08/05) | 08 May 2024 | Zone 1 junction |  | Traffic pole footing installation by Eng Hup
Wed (08/05) | 08 May 2024 | MH1-2 |  | Cleaning ongoing
Wed (08/05) | 08 May 2024 | Zone 1 near Loyang Rise bus stop |  | Cement patch for kerb ongoing
Wed (08/05) | 08 May 2024 | S4 |  | Continue formwork removal
Wed (08/05) | 08 May 2024 | N2 |  | RWDP and compensation bar installed. No more activity
Wed (08/05) | 08 May 2024 | Zone 1 junction |  | Enghup continue installation of traffic light pole.7/8 installed
Thu (09/05) | 09 May 2024 | DW073 |  | 1st bite trenching at 15.5m/32.90m
Thu (09/05) | 09 May 2024 | ST84-BC2 |  | Excavation temporary stopped due to sunction pipe choke, current depth 8m/34m for 2nd bite
Thu (09/05) | 09 May 2024 | Zone 3 Fissure Grout |  | Point I-101 depth checked and PVC pipe checked
Thu (09/05) | 09 May 2024 | P25 |  | Krishco excavation for water pipe rectification
Thu (09/05) | 09 May 2024 | Exit 3 barette pile, BRP4 |  | Excavation for guidewall works
Thu (09/05) | 09 May 2024 | P18-3 |  | Casting in progress
Thu (09/05) | 09 May 2024 | P17-2 |  | Casting in progress
Thu (09/05) | 09 May 2024 | DR1 |  | LE continue ERSS installation
Thu (09/05) | 09 May 2024 | BC1 |  | Main pump issue. Machine still ongoing rectification
Thu (09/05) | 09 May 2024 | ST84 |  | B1 completed, 34.2m. Cutter teeth changing ongoing
Thu (09/05) | 09 May 2024 | DW69 |  | Casting completed at 1030hrs. Total volume: 117m3
Thu (09/05) | 09 May 2024 | Zone 3 FG |  | Point O-161 in progress
Thu (09/05) | 09 May 2024 | ST193 |  | Continue cleaning
Thu (09/05) | 09 May 2024 | UKP18 |  | Trial trench in progress
Thu (09/05) | 09 May 2024 | UKP10 |  | Trial trench ongoing
Thu (09/05) | 09 May 2024 | BRP4 |  | Guidewall excavation in progress
Thu (09/05) | 09 May 2024 | P16-1 |  | Pile toe confirmed. Rebar cage inspection for lowering down
Thu (09/05) | 09 May 2024 | P15-1 |  | Preparing for casing installation
Thu (09/05) | 09 May 2024 | ST193 |  | End plate extracted. Cleaning in progress
Thu (09/05) | 09 May 2024 | ST84 |  | B1 trenching continue
Thu (09/05) | 09 May 2024 | DW69 |  | Tremie pipes installed for casting
Thu (09/05) | 09 May 2024 | Zone 1 |  | ATS cable pulling for street lights
Thu (09/05) | 09 May 2024 | BC1 |  | Currently no activity. ST79 casting was completed yesterday
Thu (09/05) | 09 May 2024 | ST84 |  | Excavation temporarily stopped for cutter teeth change
Thu (09/05) | 09 May 2024 | BC4 |  | Currently no activity. DW69 casting in progress
Thu (09/05) | 09 May 2024 | P43 SI |  | BH61 started
Thu (09/05) | 09 May 2024 | ST193-BC3 |  | Desanding completed
Thu (09/05) | 09 May 2024 | ST76 | BC1 | B1 temporarily stopped for machine rectification. CD 36.3/39m
Thu (09/05) | 09 May 2024 | DR1 |  | Drain removal almost completed. Works ongoing
Thu (09/05) | 09 May 2024 | MH2-1 area |  | Slab hacking ongoing to facilitate noise barrier footing works (change in layout for NB installation)
Fri (10/05) | 10 May 2024 | ST193 |  | Hanging bar installation in progress
Fri (10/05) | 10 May 2024 | DW073 |  | 2nd bite trenching im progress at 28m/32.90m
Fri (10/05) | 10 May 2024 | ST84-BC2 |  | Flap welding for 2nd bite trimming at 20m/34m
Fri (10/05) | 10 May 2024 | P16-1 |  | Waiting for concrete lorry for casting
Fri (10/05) | 10 May 2024 | ST193 |  | End plate+ water stop installation in progress
Fri (10/05) | 10 May 2024 | BRP4 |  | Guidewall formwork installation
Fri (10/05) | 10 May 2024 | BC1 |  | Machine rectification still ongoing. ST76 first bite temporarily on hold
Fri (10/05) | 10 May 2024 | DW73 |  | B2 in progress, 14.5/32.9m
Fri (10/05) | 10 May 2024 | ST84-BC2 |  | 2nd bite trenching continue at 17.5m/34m
Fri (10/05) | 10 May 2024 | DW073 |  | 1st bite trenching continue at 26m/32.90m
Fri (10/05) | 10 May 2024 | DR1 |  | LE trial hole completed. Now preparing to resume ERSS installation
Fri (10/05) | 10 May 2024 | ST193 |  | Rebar cage installation in progress, 5/6nos
Fri (10/05) | 10 May 2024 | ST84 |  | B2 in progress, 19.3/34m
Fri (10/05) | 10 May 2024 | ST193 |  | Rebar cage installation started. 1/6 cages
Fri (10/05) | 10 May 2024 | ST84 |  | Excavation continue for 2nd bite
Fri (10/05) | 10 May 2024 | DW073 |  | Excavation for 1st bite continue
Fri (10/05) | 10 May 2024 | P17-3 |  | Boring in progress. Tonight to cast
Fri (10/05) | 10 May 2024 | P18-1 |  | Boring done. Preparing for rebar cage lowering
Fri (10/05) | 10 May 2024 | P14 |  | Preboring for soldier installation
Fri (10/05) | 10 May 2024 | P18-3 |  | Rebar cage installation
Fri (10/05) | 10 May 2024 | P17-3 |  | Boring works completed. Pending RTO to confirm toe level
Sat (11/05) | 11 May 2024 | L.A to PRD3 |  | Traffic status moderate to heavy due to 2nd lane closure
Sat (11/05) | 11 May 2024 | MH5-1 |  | Caisson hacking work
Sat (11/05) | 11 May 2024 | P17-3 |  | Rebar cage lowering
Sat (11/05) | 11 May 2024 | P17-1 |  | Casting done
Sat (11/05) | 11 May 2024 | N2 |  | Column formwork closing
Sat (11/05) | 11 May 2024 | P18-3 |  | Casting in progress
Sat (11/05) | 11 May 2024 | ST193 |  | Casting in progress
Sat (11/05) | 11 May 2024 | Zone 1 |  | Diversion status
Sat (11/05) | 11 May 2024 | P18-3 test pile |  | Top up casting
Sat (11/05) | 11 May 2024 | P17-3 |  | Ready to cast
Sat (11/05) | 11 May 2024 | ST183 |  | B2 trimming continue
Sat (11/05) | 11 May 2024 | DW73 |  | 3rd bite excavation completed
Sat (11/05) | 11 May 2024 | ST193 |  | Casting continue, running volume 128/225m3
Sat (11/05) | 11 May 2024 | N3 |  | Formwork closed and casting platform erected. Tomorrow to cast
Sat (11/05) | 11 May 2024 | P11-1 |  | Waler beam installed
Sat (11/05) | 11 May 2024 | PDR3 to NLL lane 3 |  | Milling completed. Premix laying in progress. Traffic moderate
Sun (12/05) | 12 May 2024 | L.A to PRD3 |  | Milling completed. Premix laying in progress
Sun (12/05) | 12 May 2024 | MH1-2 |  | Continue clearing hardcore and rubbish
Sun (12/05) | 12 May 2024 | ST84-BC2 |  | 2nd bite trimming continue
Sun (12/05) | 12 May 2024 | DW68-BC4 |  | 1st bite trenching in progress, 20.4m/27.4m
Sun (12/05) | 12 May 2024 | DW73 |  | Rebar cage installation started. 1/6 installed
Mon (13/05) | 13 May 2024 | Exit 3 |  | No activity
Mon (13/05) | 13 May 2024 | MH1-2 |  | Housekeeping and materials clearing by LCH
Mon (13/05) | 13 May 2024 | P51 TPE bound |  | Full with services. Unable to do bored pile as of now
Mon (13/05) | 13 May 2024 | MH5-1 |  | Hacking of caisson for machine removal
Mon (13/05) | 13 May 2024 | N4 |  | No activity
Mon (13/05) | 13 May 2024 | N3 |  | No activity
Mon (13/05) | 13 May 2024 | N2 |  | No activity
Mon (13/05) | 13 May 2024 | Zone 1 |  | No activity
Mon (13/05) | 13 May 2024 | S4 |  | No activity
Mon (13/05) | 13 May 2024 | Zone 2 |  | No other activity
Mon (13/05) | 13 May 2024 | DW78 |  | B1 excavation in progress
Mon (13/05) | 13 May 2024 | ST84 |  | Preparing for B2 internal koden check
Tue (14/05) | 14 May 2024 | MH5-2 |  | Continue hacking of caisson shaft
Tue (14/05) | 14 May 2024 | N12 |  | Waler joint welding
Tue (14/05) | 14 May 2024 | P12 |  | Preboring for ERSS work
Tue (14/05) | 14 May 2024 | DW68 |  | Casting ongoing, 45/63m3
Tue (14/05) | 14 May 2024 | ST76 |  | LSS backfilling completed
Tue (14/05) | 14 May 2024 | ST84 |  | B2 trimming in progress
Tue (14/05) | 14 May 2024 | DW78 |  | B1 completed. Now B2 in progress
Tue (14/05) | 14 May 2024 | DW68 |  | Casting completed. Total vol: 63m3
Tue (14/05) | 14 May 2024 | Exit 2 |  | Still under control
Tue (14/05) | 14 May 2024 | P12 |  | No activity
Tue (14/05) | 14 May 2024 | Zone 1 and south ramp |  | No activities
Tue (14/05) | 14 May 2024 | BC1 |  | No activity
Tue (14/05) | 14 May 2024 | ST84 |  | B1 trimming in progress
Tue (14/05) | 14 May 2024 | DW78 |  | B3 started
Tue (14/05) | 14 May 2024 | P32 |  | Activity done for the day
Tue (14/05) | 14 May 2024 | MH1-2 |  | Continue clearing the materials
Tue (14/05) | 14 May 2024 | Exit 3, BRP03B-2 |  | B1 temporarily stopped due to suction hose leakage. Shifting of rebar cage ongoing. Current depth 17.2/32.25m
Wed (15/05) | 15 May 2024 | P12 |  | Waler beam welding, today to cast packing concrete
Wed (15/05) | 15 May 2024 | P10 |  | Drilling for inclinometer
Wed (15/05) | 15 May 2024 | P6-P7 |  | Premix hacking for TT
Wed (15/05) | 15 May 2024 | Zone 2 |  | ECS installation of half height hoarding
Wed (15/05) | 15 May 2024 | MH1-2 |  | Patching works and HDPE lining
Wed (15/05) | 15 May 2024 | Zone 1 |  | HSL preparation for mobilisation
Wed (15/05) | 15 May 2024 | Zone 1 center island |  | Replacement of water barrier to concrete barrier
Wed (15/05) | 15 May 2024 | Zone 1 |  | Tactile replacement
Wed (15/05) | 15 May 2024 | Zone 4 |  | Bentonite plant set up by HSL on going
Wed (15/05) | 15 May 2024 | Zone 4 |  | Soil disposal
Wed (15/05) | 15 May 2024 | MH1-2 |  | HDPE lining continue
Wed (15/05) | 15 May 2024 | P10 |  | Gravity block installation, today to install rebar cage
Wed (15/05) | 15 May 2024 | N4 |  | Final inspection completed
Wed (15/05) | 15 May 2024 | DW78 |  | Trimming ongoing at WS side
Wed (15/05) | 15 May 2024 | ST84 |  | Mud pump damaged. Rectification ongoing
Wed (15/05) | 15 May 2024 | Exit 3 |  | Grout tube installation for rebar cage ongoing
Wed (15/05) | 15 May 2024 | P10 |  | Rebar cage installation in progress
Wed (15/05) | 15 May 2024 | P10 |  | Column support installation ongoing
Wed (15/05) | 15 May 2024 | Zone 1 |  | No activity
Wed (15/05) | 15 May 2024 | S4 |  | No activity
Wed (15/05) | 15 May 2024 | ST254, 255 and 256 |  | Guidewall cast just now
Wed (15/05) | 15 May 2024 | P31-32 |  | Works done for the day
Wed (15/05) | 15 May 2024 | ST84 |  | Cutter teeth changing ongoing
Wed (15/05) | 15 May 2024 | DW78 |  | Rebar cage installation in progress, 5/6nos
Wed (15/05) | 15 May 2024 | DW67 |  | B1 temporarily stopped. Preparing for cutter teeth change. CD 16.4/27.4m
Wed (15/05) | 15 May 2024 | BC1 |  | No activity
Wed (15/05) | 15 May 2024 | Exit 3, BRP03B-2 |  | B1 excavation resumes. CD 19/32.25m
Wed (15/05) | 15 May 2024 | Zone 2 |  | HSL shifting materials to zone 4
Wed (15/05) | 15 May 2024 | N4 |  | Preparation for final inspection and formwork closing
Thu (16/05) | 16 May 2024 | Zone 2 |  | HSL shifting materials to zone 4
Thu (16/05) | 16 May 2024 | P15 |  | ERSS pre-boring continue
Thu (16/05) | 16 May 2024 | P10 |  | Drilling for water stand pipe. Inclinometer completed yesterday
Thu (16/05) | 16 May 2024 | P9-2 |  | Water pumping, to erection working platform today for rebar cage installation
Thu (16/05) | 16 May 2024 | P31-32 |  | KTC continue excavation. 2nos of stumps plan for casting tomorrow and 2nos on Sat
Thu (16/05) | 16 May 2024 | Zone 3 |  | Krishco open pit for internal CCTV check
Thu (16/05) | 16 May 2024 | Near MH2-1 |  | NB footing to cast. Inspection done. Concrete already batched
Thu (16/05) | 16 May 2024 | BRP03B-2 |  | B1 in progress, 31.5/32.25m
Thu (16/05) | 16 May 2024 | P6 |  | Premix hacking for TT
Thu (16/05) | 16 May 2024 | PRD3 |  | Loop detector installation
Thu (16/05) | 16 May 2024 | MH1-2 |  | HDPE lining continue
Thu (16/05) | 16 May 2024 | P12 |  | MPI done. Next to excavate to FEL
Thu (16/05) | 16 May 2024 | P10 |  | Preparation for water stand pipe installation
Thu (16/05) | 16 May 2024 | P8-2 |  | Rebar cage fabrication
Thu (16/05) | 16 May 2024 | BRP03B-2 |  | B1 in progress, 28.5/32.25m
Thu (16/05) | 16 May 2024 | ST84 |  | Trimming ongoing
Thu (16/05) | 16 May 2024 | DW78 |  | Tremie pipes lowered. Ready for casting
Thu (16/05) | 16 May 2024 | DW67 |  | B1 completed, 27.6m @ 0350hrs
Thu (16/05) | 16 May 2024 | Zone 4 P48 |  | EHT cable exposing for localised shifting or spiking
Thu (16/05) | 16 May 2024 | P45-1 |  | SI work started
Thu (16/05) | 16 May 2024 | Zone 4 JPG works |  | 3 points grouting completed. Now area preparation for the 4th point. 4 nos target today
Thu (16/05) | 16 May 2024 | P43 soft ground JPG |  | 2nd point grouting in progress
Thu (16/05) | 16 May 2024 | DW72 |  | Pre-excavation completed. BC cutter teeth replacement then start excavation
Thu (16/05) | 16 May 2024 | DW67 |  | 2nd bite trenching completed. Preparation for end plate extraction
Thu (16/05) | 16 May 2024 | DW78 |  | Casting started
Thu (16/05) | 16 May 2024 | ST84-BC2 |  | 1st bite trimming in progress
Thu (16/05) | 16 May 2024 | ST173 |  | Excavation for guidewall construction
Thu (16/05) | 16 May 2024 | P33 |  | Hacking and removing of abandoned drain
Thu (16/05) | 16 May 2024 | UKP30 |  | Boring in progress
Thu (16/05) | 16 May 2024 | BRP06 |  | Pre-excavation in progress. Tonight to start trenching
Thu (16/05) | 16 May 2024 | BRP02 |  | Koden test on going
Thu (16/05) | 16 May 2024 | BRP-02 |  | 2nd bite trimming in progress, 12m/ 32.25m
Thu (16/05) | 16 May 2024 | P9-2 |  | Working platform erection for column rebar work
Thu (16/05) | 16 May 2024 | DW67 |  | B2 in progress, 10m
Thu (16/05) | 16 May 2024 | DW78 |  | Casting in progress, 104/110m3
Thu (16/05) | 16 May 2024 | ST84 |  | Trimming temporarily stopped. Cutter wheel teeth change ongoing
Thu (16/05) | 16 May 2024 | ST173 |  | Trial trench in progres
Fri (17/05) | 17 May 2024 | BC1 |  | Pump rectification
Fri (17/05) | 17 May 2024 | DW72 |  | Preparation for trenching works. DW67: Cleaning and desanding completed. Internal koden check ongoing
Fri (17/05) | 17 May 2024 | P9-2 |  | Ground preparation for crane platform
Fri (17/05) | 17 May 2024 | P8-2 |  | Rebar cage fabrication
Fri (17/05) | 17 May 2024 | P9-2 |  | Scaffold erection for rebar cage installation
Fri (17/05) | 17 May 2024 | P6 |  | Premix hacking continue
Fri (17/05) | 17 May 2024 | MH1-2 |  | HDPE lining continue
Fri (17/05) | 17 May 2024 | Zone 1 L.A towards TPE |  | Preparation for lane closure to raised up singtel manhole
Fri (17/05) | 17 May 2024 | Zone 4 JGP |  | Point B-21 in progres
Fri (17/05) | 17 May 2024 | Zone 4 |  | Netlink cable pulling ongoing
Fri (17/05) | 17 May 2024 | P50 |  | HSL platform preparation
Fri (17/05) | 17 May 2024 | P48 |  | SPPG cables exposed for localised shifting to facilitate BP works
Fri (17/05) | 17 May 2024 | P49 |  | Trial trench by WH ongoing
Fri (17/05) | 17 May 2024 | Gate 7 |  | Krishco open pit for pipe fittings rectification
Fri (17/05) | 17 May 2024 | ST114, ST115 |  | Guidewall excavation ongoing
Fri (17/05) | 17 May 2024 | P43 |  | GCE mobilising excavator
Fri (17/05) | 17 May 2024 | ST84 |  | B2 trimming in progress
Fri (17/05) | 17 May 2024 | ST173 |  | Guidewall excavation ongoing
Fri (17/05) | 17 May 2024 | DR1 |  | LE continue steel plate installation
Fri (17/05) | 17 May 2024 | BR4C01 |  | 1st bite excavation reached 32m
Fri (17/05) | 17 May 2024 | BRP-02 |  | Desanding in progress
Fri (17/05) | 17 May 2024 | ST84 |  | Continue trimming of 2nd bite
Fri (17/05) | 17 May 2024 | Zone 2 |  | Painting of ramp area and access
Fri (17/05) | 17 May 2024 | Zone 1 diverted island |  | Seal up below concrete footing
Fri (17/05) | 17 May 2024 | P12 |  | Excavation to the base by KTC
Fri (17/05) | 17 May 2024 | ST001& ST264 |  | Guidewall casting done
Fri (17/05) | 17 May 2024 | BC cutter No-1 |  | Now main pump servicing. Tomorrow plan to top up new hydraulic oil (circulate) for the whole machine and resume work
Fri (17/05) | 17 May 2024 | BR4C01 |  | 1st bite excavation reached 22m. Now cutter teeth changing
Sat (18/05) | 18 May 2024 | BC1 |  | Engine repair works done. Now oil top up for testing
Sat (18/05) | 18 May 2024 | ST84 |  | Teeth changing, current 2nd bite 27m
Sat (18/05) | 18 May 2024 | DW72 |  | 1st bite trenching at 29.7m
Sat (18/05) | 18 May 2024 | P43 |  | CGE platform preparing to shift mixing plant. No grouting today
Sat (18/05) | 18 May 2024 | Zone 4 |  | JGP works in progress, 1st point in progress. 4 points target today
Sat (18/05) | 18 May 2024 | Zone 4 |  | HSL preparing platform for BP works
Sat (18/05) | 18 May 2024 | Zone 4 |  | Bentonite pipe laying
Sat (18/05) | 18 May 2024 | Zone 1 |  | ABH 13-1 TT
Sat (18/05) | 18 May 2024 | MH5-1 |  | Manual excavation for entry pipe opening continue. Current depth 450mm
Sat (18/05) | 18 May 2024 | P10-1 |  | Excavation for PDA
Sat (18/05) | 18 May 2024 | N1 |  | RWDP installed
Sat (18/05) | 18 May 2024 | N4 |  | Casting platform barricade installation. To cast after lunch
Sat (18/05) | 18 May 2024 | P15 |  | Pre-boring continue. Plan to complete today. Monday to complete SP and LP installation
Sat (18/05) | 18 May 2024 | P18 |  | TT for IM works
Sat (18/05) | 18 May 2024 | ST84 |  | Current depth at 27.6m. Teet changing
Sat (18/05) | 18 May 2024 | ST132 |  | TT for guidewall installation. Found abandoned gas pipe
Sat (18/05) | 18 May 2024 | Zone 4 |  | 2nd point Grouting
Sat (18/05) | 18 May 2024 | BRC01 |  | 1st bite excavation reached 28m
Sat (18/05) | 18 May 2024 | DW67 |  | Tremie pipe lowering down completed. Concrete on the way
Sat (18/05) | 18 May 2024 | Zone 2 |  | NLT cable joining
Sat (18/05) | 18 May 2024 | BR4C01 |  | 1st bite excavation reached 29m. Now cutter teeth changing
Sat (18/05) | 18 May 2024 | N4 |  | Column casting in progress
Sat (18/05) | 18 May 2024 | Exit 3 BRP 06 |  | Trenching continue, depth 29m/36.35m
Sat (18/05) | 18 May 2024 | ST114-ST115 | Receiving shaft | Guidewall formwork closing done. Concrete ordered
Sat (18/05) | 18 May 2024 | ST219-220 |  | Drain hacking for guidewall construction
Sat (18/05) | 18 May 2024 | UKP11 |  | TT on going, 1.4m depth
Sat (18/05) | 18 May 2024 | UKP16 |  | Casing installed. Boring to resume after machinery inspection
Sun (19/05) | 19 May 2024 | Zone 2 centre median & MH5-2 |  | No activity
Sun (19/05) | 19 May 2024 | MH1-2 |  | HDPE lining welding ongoing
Sun (19/05) | 19 May 2024 | Zone 1 |  | SI team trial trench ongoing for ABH12, ABH13-1, ABH13-3
Sun (19/05) | 19 May 2024 | MH5-1 |  | Preparation to continue entry pipe opening works
Sun (19/05) | 19 May 2024 | S4 |  | No activity
Sun (19/05) | 19 May 2024 | ST76 |  | B1 in progress, 15/39m
Sun (19/05) | 19 May 2024 | ST84 |  | Cutter teeth changing ongoing. B2 current depth 28.1/29.7m
Sun (19/05) | 19 May 2024 | DW72 |  | WS side trimming in progress
Sun (19/05) | 19 May 2024 | Zone 3 Krishco |  | Preparing formwork for haunching
Sun (19/05) | 19 May 2024 | ST113 |  | Guidewall excavation in progress
Sun (19/05) | 19 May 2024 | P43 |  | GCE materials and equipment shifted. Setup works ongoing
Sun (19/05) | 19 May 2024 | Exit 1 |  | WH shifting materials
Sun (19/05) | 19 May 2024 | Zone 4 |  | GCE backfilling works ongoing at pipe sleeve area. Point B-82 completed. Plan to do next point
Sun (19/05) | 19 May 2024 | Zone 4 |  | Netlink cable pulling ongoing
Sun (19/05) | 19 May 2024 | Zone 4 |  | HSL no activity
Sun (19/05) | 19 May 2024 | P35 |  | Starhub manhole raise up works by Mo Guan
Sun (19/05) | 19 May 2024 | Exit 3, BRP4C-1 |  | B2 in progress, 20/36.35m
Sun (19/05) | 19 May 2024 | P15 |  | ERSS installation in progress. Team working till 5pm
Sun (19/05) | 19 May 2024 | N1 |  | Column formwork installation ongoing
Sun (19/05) | 19 May 2024 | P12 |  | KTC continue excavation
Sun (19/05) | 19 May 2024 | MH5-1 |  | Manual soil hacking ongoing
Sun (19/05) | 19 May 2024 | BR3B-02 |  | LSS backfilling in progress
Sun (19/05) | 19 May 2024 | ST219-220 |  | Guidewall excavation ongoing
Sun (19/05) | 19 May 2024 | ST84 |  | 2nd bite in progress, reached 27.5m
Sun (19/05) | 19 May 2024 | DR1 |  | Hacking ongoing to facilitate the ERSS installation
Sun (19/05) | 19 May 2024 | Vent shaft DW72 |  | 2nd bite was done, 33.3m. Now cutter body bring up for koden test
Sun (19/05) | 19 May 2024 | ST113 |  | Guidewall rebar works in progress
Sun (19/05) | 19 May 2024 | ST76 |  | B1 in progress, 20.9/39m
Sun (19/05) | 19 May 2024 | ST84 |  | B2 in progress, 28.6/29.7m
Sun (19/05) | 19 May 2024 | DW72 |  | Rebar cage u-clip inspection
Sun (19/05) | 19 May 2024 | DW72 |  | Continue trimming
Sun (19/05) | 19 May 2024 | DW66A |  | Platform preparation ongoing
Sun (19/05) | 19 May 2024 | BRP4C-1 |  | B2 in progress, 26.2/36.35m
Sun (19/05) | 19 May 2024 | ST72 |  | 3rd bite excavation in progress, reached 32m
Sun (19/05) | 19 May 2024 | P15 |  | LE continue ERSS installation
Sun (19/05) | 19 May 2024 | P12 |  | KTC continue excavation to FEL
Sun (19/05) | 19 May 2024 | N1 |  | Today plan for column formwork closing. Preparation ongoing
Mon (20/05) | 20 May 2024 | Exit 3 BRP06 |  | 2nd bite trenching temporarily stopped due to desander faulty. Repair works in progress
Mon (20/05) | 20 May 2024 | ST76-BC1 |  | 2nd bite trenching on going, crrebt depth 18/39m
Mon (20/05) | 20 May 2024 | ST84 |  | End plate and water stop lowering
Mon (20/05) | 20 May 2024 | ST99-BC2 |  | Preparation for trenching
Mon (20/05) | 20 May 2024 | DW72 |  | Casting in progress
Mon (20/05) | 20 May 2024 | DW66A-BC4 |  | 2nd bite trenching started, depth 6.5/27.4m
Mon (20/05) | 20 May 2024 | DW72 |  | Rebar cage installation in progress, 6/6nos
Mon (20/05) | 20 May 2024 | DW66A |  | B1 in progress, 22.5/27.4m
Mon (20/05) | 20 May 2024 | P43 |  | GCE trial trench ongoing
Mon (20/05) | 20 May 2024 | P43 |  | JGP point B-237 in progress
Mon (20/05) | 20 May 2024 | ST113 |  | Guidewall construction in progress. ST114-115: Guidewall formwork dismantling ongoing
Mon (20/05) | 20 May 2024 | P18 |  | Drilling in progress for inclinometer installation
Mon (20/05) | 20 May 2024 | P15 |  | LE ERSS installation of SP & LP ongoing. Target to complete today
Mon (20/05) | 20 May 2024 | ST134 |  | Premix hacking for trial trench works
Mon (20/05) | 20 May 2024 | ST84 |  | Desanding ongoing
Mon (20/05) | 20 May 2024 | ST76 |  | B2 in progress, 8/39m
Mon (20/05) | 20 May 2024 | DR1 |  | LE dewatering works ongoing before resuming works
Mon (20/05) | 20 May 2024 | DR1 |  | Singtel cable checking ongoing
Mon (20/05) | 20 May 2024 | P12 |  | Excavation to FEL ongoing, target to complete by tmr
Mon (20/05) | 20 May 2024 | N1 |  | Formwork closing for column, target to cast tmr
Mon (20/05) | 20 May 2024 | P11-2 |  | Platform preparation for column rebar cage installation
Mon (20/05) | 20 May 2024 | P10-1-5 |  | Preparation for PDA test for pile
Mon (20/05) | 20 May 2024 | P31-32 |  | KTC continue trimming works. Rebar cutting/hardcore clearing ongoing
Mon (20/05) | 20 May 2024 | UKP17 |  | Trial trench ongoing
Mon (20/05) | 20 May 2024 | MH5-1 |  | Manual soil hacking and cleaning ongoing
Mon (20/05) | 20 May 2024 | MH1-2 |  | HDPE lining works
Mon (20/05) | 20 May 2024 | ST221 |  | Backfilling ongoing for guidewall trial trench. Found water pipe
Mon (20/05) | 20 May 2024 | BR4C-1 |  | B2 temporarily stopped. Cutter teeth changing ongoing
Mon (20/05) | 20 May 2024 | Zone 1 |  | Premix hardcores removal for ABH SI trial trench works
Mon (20/05) | 20 May 2024 | Zone 1 |  | Premix cutting for ECM perimeter drain works
Mon (20/05) | 20 May 2024 | Zone 4 side 3m dia |  | 2 points grouting done as of now. 3rd point in progress
Mon (20/05) | 20 May 2024 | ST259-260 |  | Guidewall construction in progress
Mon (20/05) | 20 May 2024 | MH3-5 |  | Setting out for drain diversion
Mon (20/05) | 20 May 2024 | P15 |  | ERSS installation in progress
Mon (20/05) | 20 May 2024 | N3 |  | Platform scaffold dismantling ongoing
Mon (20/05) | 20 May 2024 | N1 |  | Continue column formwork installation
Mon (20/05) | 20 May 2024 | P12 |  | Continue excavation to FEL
Mon (20/05) | 20 May 2024 | P11-2 |  | Column rebar cage installation ongoing
Mon (20/05) | 20 May 2024 | P10-1-5 |  | PDA test completed
Mon (20/05) | 20 May 2024 | MH5-1 |  | Access erection ongoing
Mon (20/05) | 20 May 2024 | S4 |  | No activity
Mon (20/05) | 20 May 2024 | ST259, ST260 |  | Guidewall formwork installation in progress
Mon (20/05) | 20 May 2024 | Near exit 3 |  | WH clearing abandoned cables
Mon (20/05) | 20 May 2024 | N1 |  | Last formwork panel installation in progress. Weynding work till 10pm
Mon (20/05) | 20 May 2024 | P12 excavation status |  | Balance 300mm to FEL and access location. To complete tomorrow and handover to HSL for pile head hacking
Mon (20/05) | 20 May 2024 | P11-2 |  | Rebar cages safely installed
Tue (21/05) | 21 May 2024 | DW66A |  | Trimming in progress
Tue (21/05) | 21 May 2024 | ST99 |  | B1 temporarily stopped for desander pump rubber change. CD 17.5/34.1m. Also ongoing rectification for BC2 noise barrier panel
Tue (21/05) | 21 May 2024 | ST113 |  | Guidewall formwork dismantling
Tue (21/05) | 21 May 2024 | P42 area |  | Dongah working platform preparation
Tue (21/05) | 21 May 2024 | ST76 |  | B2 completed. Now cutter body wash and prepare for 3rd bite
Tue (21/05) | 21 May 2024 | DW66A-BC4 |  | End plate + water stop lowering
Tue (21/05) | 21 May 2024 | DR1 |  | LE preparing to resume works
Tue (21/05) | 21 May 2024 | ST99-BC2 |  | 1st bite trenching, 31.5/34.1m current depth
Tue (21/05) | 21 May 2024 | ST84 |  | Casting on going. 105/215 m3
Tue (21/05) | 21 May 2024 | ST76-BC1 |  | Trimming on going
Tue (21/05) | 21 May 2024 | BRP06 |  | 2nd bite trenching
Tue (21/05) | 21 May 2024 | DW72 |  | Last load casting, 168 m3
Tue (21/05) | 21 May 2024 | BRP06 |  | 2nd bite trenching at 33.5m depth
Tue (21/05) | 21 May 2024 | DW66A-BC4 |  | 2nd bite trenching started, depth 23./27.4m
Tue (21/05) | 21 May 2024 | ST76-BC1 |  | 2nd bite trenching on going, crrebt depth 24.3/39m
Tue (21/05) | 21 May 2024 | ST84 |  | Preparation for rebar cage lowering
Tue (21/05) | 21 May 2024 | DW66A |  | Endplate extraction in progress
Tue (21/05) | 21 May 2024 | ST99-BC2 |  | 1st bite trenching, 9m current depth
Tue (21/05) | 21 May 2024 | ST99 |  | Soil clearing from cutter wheel
Tue (21/05) | 21 May 2024 | ST84 |  | Hanging bar installation ongoing
Tue (21/05) | 21 May 2024 | DR1 |  | LE vibro maintenance ongoing
Tue (21/05) | 21 May 2024 | BR4C-1 |  | B2 excavation in progres
Tue (21/05) | 21 May 2024 | Near gate 5 |  | Access erection in progress
Tue (21/05) | 21 May 2024 | P31-32 |  | KTC continue soil disposal and hacking works. Hirose plan to start on Thurs
Tue (21/05) | 21 May 2024 | P13-6 |  | HSL preparation works for PDA test. Target to do on Thurs
Tue (21/05) | 21 May 2024 | P12 |  | Excavation for FEL ongoing. Due to hard soil condition, target to complete by Wed
Tue (21/05) | 21 May 2024 | N1 Column |  | Formwork closing & working platform installation. To cast today
Tue (21/05) | 21 May 2024 | MH5-1 |  | Continue soil clearing works. Today to lower 1 no. of pipe sleeve
Tue (21/05) | 21 May 2024 | Zone 1 |  | ABH13-1 hand augering ongoing
Tue (21/05) | 21 May 2024 | Zone 4 - 3m dia |  | 2 points grouting done. 3rd point boring
Tue (21/05) | 21 May 2024 | MH1-2 |  | HDPE lining works
Tue (21/05) | 21 May 2024 | MH3-5 |  | Excavation for drain work
Tue (21/05) | 21 May 2024 | ST76-BC1 |  | 2nd bite trenching on going, crrebt depth 37.1/39m
Tue (21/05) | 21 May 2024 | ST99-BC2 |  | 1st bite trenching, 17.5/34.1m current depth. Temporary stopped due to desander pump spoil
Tue (21/05) | 21 May 2024 | ST84 |  | Rebar cage installation, 5/6 cages
Tue (21/05) | 21 May 2024 | 3m dia |  | 1st point boring done. Preparing for grouting
Tue (21/05) | 21 May 2024 | ST84 |  | Rebar cage installation in progress, 5/6nos
Tue (21/05) | 21 May 2024 | ST221 |  | Guidewall trial trench ongoing
Wed (22/05) | 22 May 2024 | MH5-1 |  | 1/6nos of steel pipes installed. Tunnel in progress
Wed (22/05) | 22 May 2024 | P10&P11 |  | Levelling for lean concrete
Wed (22/05) | 22 May 2024 | MH1-2 |  | HDPE welding
Wed (22/05) | 22 May 2024 | P12 |  | Excavation and removal of soil to COL
Wed (22/05) | 22 May 2024 | BRP-06 |  | 2nd bite cleaning in progress
Wed (22/05) | 22 May 2024 | ST220&ST221 |  | Guidewall work in progress
Wed (22/05) | 22 May 2024 | BRP12 |  | TT to check whether available to do or not
Wed (22/05) | 22 May 2024 | MH3-5 |  | Excavation for drain base lean concrete
Wed (22/05) | 22 May 2024 | MH5-1 |  | Continue tunnel for machine retrieval
Wed (22/05) | 22 May 2024 | P12 |  | Continue excavation to FEL
Wed (22/05) | 22 May 2024 | DW66A |  | Rebar cage lowering in progress
Wed (22/05) | 22 May 2024 | ST99-BC2 |  | 1st bite trenching completed. 2nd bite trenching started. 6/34.1m current depth
Wed (22/05) | 22 May 2024 | BRP06 |  | Cutter body hoist up for teeth replacement
Thu (23/05) | 23 May 2024 | ST99 |  | C-lug welding ongoing
Thu (23/05) | 23 May 2024 | DW-042 |  | LV cable crossing spiked today and cable cutting done
Thu (23/05) | 23 May 2024 | P13 |  | Preparation for PDA. 3pm testing
Thu (23/05) | 23 May 2024 | ST76 |  | Rebar cage installation in progress, 4/8nos
Thu (23/05) | 23 May 2024 | P11-2 |  | Shearlinks installation at lapping area
Thu (23/05) | 23 May 2024 | P10-2 |  | Preparation for formwork closing
Thu (23/05) | 23 May 2024 | P10-1 |  | TT for ERSS
Thu (23/05) | 23 May 2024 | Zone 4 3m dia |  | Boring for JGP work in progress
Thu (23/05) | 23 May 2024 | DW20 |  | B2 in progress
Thu (23/05) | 23 May 2024 | BRP03B-1 |  | B1 internal koden check
Thu (23/05) | 23 May 2024 | MH1-2 |  | Surface grinding
Thu (23/05) | 23 May 2024 | MH3-5 |  | Hardcore laying for temporary drain diversion base
Thu (23/05) | 23 May 2024 | Zone 1 P4 |  | CGS demob machinery and materials. HSL today to mobilise water and mud tank
Thu (23/05) | 23 May 2024 | Zone 1 P2 |  | Half height hoarding installation
Thu (23/05) | 23 May 2024 | Zone 1 P2 |  | Mobilisation of SI rig for ABH 13-2 and 13-3
Thu (23/05) | 23 May 2024 | Zone 1 |  | Preparation for above ground ECM construction
Thu (23/05) | 23 May 2024 | P12 |  | Balance hacking to FEL to complete today
Thu (23/05) | 23 May 2024 | P10-1 |  | ERSS preboring in progress
Thu (23/05) | 23 May 2024 | P10-2 |  | Formwork assembly and tie rod installation for closing
Thu (23/05) | 23 May 2024 | P50-10 |  | Boring done until 6PM
Thu (23/05) | 23 May 2024 | P49 | TPE bound | Continue drain demolition
Thu (23/05) | 23 May 2024 | Zone 4- 3m dia |  | 2nd point grouting almost done. Target one more point today
Thu (23/05) | 23 May 2024 | MH3-5 |  | Excavation for drain diversion. Will lean concrete the slope today
Thu (23/05) | 23 May 2024 | DR1 |  | Water pipe support formwork closing
Thu (23/05) | 23 May 2024 | DR1 |  | TT on going to check existing and new Singtel cable for soldier pile installation work
Thu (23/05) | 23 May 2024 | P13 |  | PDA completed
Thu (23/05) | 23 May 2024 | BRP12 |  | TT in progress. Got free space and can do
Thu (23/05) | 23 May 2024 | P13 |  | Backfilling and levelling works ongoing
Thu (23/05) | 23 May 2024 | P12 |  | KTC continue soil hacking works till 10pm
Thu (23/05) | 23 May 2024 | Zone 1 and south ramp |  | No activity
Thu (23/05) | 23 May 2024 | ST220-221 |  | Guidewall cast
Thu (23/05) | 23 May 2024 | P31-32 |  | No activities. Hirose started drilling work for bolt planting in the day
Thu (23/05) | 23 May 2024 | ST80 |  | B1 in progress, 15.3/35.6m
Thu (23/05) | 23 May 2024 | P43 GCE |  | Preparation ongoing for JGP works
Thu (23/05) | 23 May 2024 | N5 |  | Preparation for PLT
Fri (24/05) | 24 May 2024 | ST007 |  | BC cutter already at location. Noise balloon will be put up prior to trenching
Fri (24/05) | 24 May 2024 | DW20 |  | Endplate extraction in progres
Fri (24/05) | 24 May 2024 | BRP03 |  | B1 in progress
Fri (24/05) | 24 May 2024 | P11-1 |  | Area setting up for kentledge test
Fri (24/05) | 24 May 2024 | P10-1 |  | Prep for tie tod installation. Plan to cast tomorrow
Fri (24/05) | 24 May 2024 | P9-1 |  | Shearlinks installation at lapping area
Fri (24/05) | 24 May 2024 | P8-1 |  | Shearlinks installation at lapping area
Fri (24/05) | 24 May 2024 | Zone 1 center island |  | Hacking for perimeter drain
Fri (24/05) | 24 May 2024 | Zone 1 center island |  | Construction of ECM pond
Fri (24/05) | 24 May 2024 | P2-1 and P2-2 |  | TT for Bored pile completed. No utility found
Fri (24/05) | 24 May 2024 | ABH13-3 |  | Rig set up. Pending half height hoarding installation before start drilling. Now in progress
Fri (24/05) | 24 May 2024 | Zone 1 |  | Mud and water tank on site. Today mixer and desander will mobilise
Fri (24/05) | 24 May 2024 | MH5-1 |  | Mining continue. Current depth 1.5/3.3m
Fri (24/05) | 24 May 2024 | ST007 |  | B1 in progress, 4/35m
Fri (24/05) | 24 May 2024 | ST76 |  | Rebar cage installation in progress, 6/8nos
Fri (24/05) | 24 May 2024 | ST99 |  | Preparing for endplate removal
Fri (24/05) | 24 May 2024 | P43 JGP |  | Point B-121 completed. Now ongoing B-357. Tonight to complete 2 points
Fri (24/05) | 24 May 2024 | ST80 |  | B1 temporarily stopped. Now gearbox changing. CD 19.3/35.6m
Fri (24/05) | 24 May 2024 | P10-1 |  | Pre boring continue for ERSS
Fri (24/05) | 24 May 2024 | P10 |  | Formwork closing
Fri (24/05) | 24 May 2024 | DW20 |  | B2 internal koden check
Fri (24/05) | 24 May 2024 | BRP03B-1 |  | B2 completed. Now cutter body washing
Fri (24/05) | 24 May 2024 | Zone 3 BRP 18 |  | Exposing LV cable for LEW and utility team verification
Fri (24/05) | 24 May 2024 | Zone 3 |  | Lean concrete casting at base for Utility support
Fri (24/05) | 24 May 2024 | Blk 4 |  | Drilling for fissure grouting to continue till 7pm
Fri (24/05) | 24 May 2024 | ST76 |  | Casting in progress, 76/300 m3
Fri (24/05) | 24 May 2024 | ST80 |  | 1st bite trenching at 22m depth
Fri (24/05) | 24 May 2024 | ST86 |  | Pipe line preparing to start trenching
Fri (24/05) | 24 May 2024 | P44 JGP works |  | Grouting for 3rd points. Additional water tank will be delivered tomorrow to store water
Fri (24/05) | 24 May 2024 | Zone 4 |  | JGP stopped for the day as no water supply. 2 points grouted
Fri (24/05) | 24 May 2024 | P50-10 |  | Boring works in progress. Current depth 17/27m
Fri (24/05) | 24 May 2024 | P15 |  | Excavation ongoing by KTC till 10pm
Fri (24/05) | 24 May 2024 | P12 |  | Pile head hacking, 3/6nos
Fri (24/05) | 24 May 2024 | P10 |  | Formwork installation in progress
Fri (24/05) | 24 May 2024 | Zone 2 centre median |  | No activity
Fri (24/05) | 24 May 2024 | Zone 1 center island |  | WH continue ECM pond construction
Fri (24/05) | 24 May 2024 | Zone 1 |  | No other activity. Biometric has been shifted to the other side
Fri (24/05) | 24 May 2024 | P31-32 |  | No activity
Fri (24/05) | 24 May 2024 | ST76 |  | Casting ongoing
Fri (24/05) | 24 May 2024 | ST86 |  | B1 started at 2100hrs
Fri (24/05) | 24 May 2024 | ST99 |  | Endplate installation in progress
Fri (24/05) | 24 May 2024 | P43 GCE |  | JGP tonight to continue 2 points, B-122 and B-414
Fri (24/05) | 24 May 2024 | N5 |  | Reference level marking for lean concrete casting today
Sat (25/05) | 25 May 2024 | Zone 4 P50-10 |  | Casting in progress
Sat (25/05) | 25 May 2024 | DW25 |  | Cutter teeth replacement ongoing
Sat (25/05) | 25 May 2024 | BRP04B-1 |  | B1 in progress, 26/33.09m
Sat (25/05) | 25 May 2024 | BRP06 |  | LSS backfilling ongoing
Sat (25/05) | 25 May 2024 | P50-10 |  | Casting completed
Sat (25/05) | 25 May 2024 | DW20 |  | B2 cleaning ongoing
Sat (25/05) | 25 May 2024 | BRP03B-1 |  | Casting ongoing
Sat (25/05) | 25 May 2024 | ST007 |  | B1 in progress, 12/35m
Sat (25/05) | 25 May 2024 | ST76 |  | Casting in progress, 315/333m3
Sat (25/05) | 25 May 2024 | ST80 |  | B1 in progress, 25.7/35.6m
Sat (25/05) | 25 May 2024 | ST99 |  | Preparing for rebar cage installation
Sat (25/05) | 25 May 2024 | BRP4B-1 |  | B1 in progress, 12.5/33.09m
Sat (25/05) | 25 May 2024 | N5 |  | Backfilling and levelling ongoing
Sat (25/05) | 25 May 2024 | P15 |  | No more activity
Sat (25/05) | 25 May 2024 | P12 |  | Continue pile head hacking
Sat (25/05) | 25 May 2024 | P11-1 |  | Area setup for kentledge test
Sat (25/05) | 25 May 2024 | P10 |  | Formwork closing in progress
Sat (25/05) | 25 May 2024 | Zone 2 near shell |  | Premix rectification at bus lane. Thereafter the team will rectify premix at zone 1 near MH1-2
Sat (25/05) | 25 May 2024 | Zone 1 |  | No other activity
Sat (25/05) | 25 May 2024 | ST007 |  | B1 in progress, 28.5/35m
Sat (25/05) | 25 May 2024 | ST010 |  | Guidewall casting completed
Sat (25/05) | 25 May 2024 | P31-P32 |  | 2nos I-beams installed
Sat (25/05) | 25 May 2024 | ST80 |  | B1 in progress, 27.3/35.6m
Sat (25/05) | 25 May 2024 | ST99 |  | Rebar cages fully lowered
Sat (25/05) | 25 May 2024 | P43 GCE |  | JGP works continue. Tonight plan 2 points, B-356 and B-299
Sun (26/05) | 26 May 2024 | Exit 3 - DW020 |  | Rebar cages fully lowered. Preparation works for casting ongoing
Sun (26/05) | 26 May 2024 | Exit 3 - DW025 | BC04 | 1st bite excavation in progress, Current depth 31.5m/32.50m
Sun (26/05) | 26 May 2024 | ST218 |  | Trial trench in progress for Guidewall works
Sun (26/05) | 26 May 2024 | ST220-ST221 |  | Guidewall Formwork dismantal & removal
Sun (26/05) | 26 May 2024 | Zone 3 |  | Utility support beam installation & welding ongoing
Sun (26/05) | 26 May 2024 | Zone 3 |  | Krishco thrust blocks Formwork installation ongoing
Sun (26/05) | 26 May 2024 | ST-80 |  | 1st bite excavation work in progress, current depth 28.6m
Sun (26/05) | 26 May 2024 | ST-86 |  | No activity
Sun (26/05) | 26 May 2024 | Zone 3 Ventshaft | P38 | KTC excavation works ongoing
Sun (26/05) | 26 May 2024 | Zone 4 JGP area |  | Soil levelling, soil disposal and machinery maintenance works
Sun (26/05) | 26 May 2024 | Zone 3 JGP area |  | Soil levelling, soil disposal and machinery maintenance works
Sun (26/05) | 26 May 2024 | P15 |  | No activity
Sun (26/05) | 26 May 2024 | P12 |  | Continue pile head hacking works
Sun (26/05) | 26 May 2024 | P10-2 |  | Formwork closing and working platform installation works. Target to cast on Monday
Sun (26/05) | 26 May 2024 | MH5-1 |  | Continue hacking works and soil removal. Today target to install another pipe sleeve
Sun (26/05) | 26 May 2024 | MH1-2 |  | HDPE welding works
Sun (26/05) | 26 May 2024 | Zone 1 |  | No activity
Sun (26/05) | 26 May 2024 | P12 |  | Soil levelling works in progress. Today to cast base lean concrete
Sun (26/05) | 26 May 2024 | P10-2 |  | Formwork closing completed. Scaffold for working platform installation works ongoing. Target to cast on Monday
Sun (26/05) | 26 May 2024 | MH5-1 |  | Continue hacking works and soil removal
Sun (26/05) | 26 May 2024 | MH1-2 |  | HDPE welding works
Sun (26/05) | 26 May 2024 | DW20 |  | Rebar cage installation, 4/6nos. Lapping inspection ongoing
Sun (26/05) | 26 May 2024 | DW25 |  | B1 in progress, 24/32.5m
Sun (26/05) | 26 May 2024 | ST007 |  | B1 in progress, 29/35m
Sun (26/05) | 26 May 2024 | ST80 |  | Cutter teeth changing ongoing
Sun (26/05) | 26 May 2024 | ST99 |  | Casting in progress, 110/243m3
Sun (26/05) | 26 May 2024 | Exit 3 - DW020 |  | Casting works in progress
Sun (26/05) | 26 May 2024 | Exit 3 - DW025 | BC04 | 2nd bite excavation in progress, Current depth 12m/32.50m
Sun (26/05) | 26 May 2024 | Exit 3 - BR4B01/BR03 |  | Design G3 rock head 30.89m, PLT inspection done. Now cutter teeth changing
Sun (26/05) | 26 May 2024 | ST218 |  | Trial trench completed for Guidewall works. Now backfilling
Sun (26/05) | 26 May 2024 | Zone 3 |  | Current status for Utility support beam. Work stopped for the day
Sun (26/05) | 26 May 2024 | Zone 3 |  | BRP-21 trial trench works
Sun (26/05) | 26 May 2024 | ST-80 |  | 1st bite excavation work, current depth 29.4m
Sun (26/05) | 26 May 2024 | ST-86 |  | Resumed excavation, pump clearing ongoing
Sun (26/05) | 26 May 2024 | Zone 3 JGP area |  | No activity, work stopped for the day
Sun (26/05) | 26 May 2024 | Zone 4 JGP area |  | No activity, work stopped for the day
Sun (26/05) | 26 May 2024 | Exit 3 - BR03 | BC03 | Cutter teeth changing in progress
Mon (27/05) | 27 May 2024 | Exit 3 |  | WH clearing materials at previous ECM pond to extend ECM pond
Mon (27/05) | 27 May 2024 | Zone 3 |  | WH erecting alternate access
Mon (27/05) | 27 May 2024 | Exit 1 |  | Access clean up and steel plates adjustment ongoing
Mon (27/05) | 27 May 2024 | Zone 2 |  | Barricade installation along vehicle access started to put up
Mon (27/05) | 27 May 2024 | ST86 |  | B1 in progress
Mon (27/05) | 27 May 2024 | ST80 |  | B2 ongoing
Mon (27/05) | 27 May 2024 | P12 |  | Guide bar installation completed. B2 installation in progress
Mon (27/05) | 27 May 2024 | P11-1 |  | Kentledge set up on going
Mon (27/05) | 27 May 2024 | P11-2 |  | Column formwork closing
Mon (27/05) | 27 May 2024 | P10-2 |  | Column casting in progress
Mon (27/05) | 27 May 2024 | MH5-1 |  | Mining stopped for the day, depth 2m/3.3m
Mon (27/05) | 27 May 2024 | S3 |  | Rebar installed. Tomorrow to close formwork
Mon (27/05) | 27 May 2024 | S4 |  | Backfilling to pile cap level stopped for the day. Balance 1 layer
Mon (27/05) | 27 May 2024 | ST007 |  | B1 reached 31/35m
Mon (27/05) | 27 May 2024 | BR4B-01 | BR3 | 2nd bite excavation, reached 22.2m/33.09m
Mon (27/05) | 27 May 2024 | P10-2 |  | Column casting in progress
Tue (28/05) | 28 May 2024 | DW25 |  | Cleaning in progress
Tue (28/05) | 28 May 2024 | DW19 |  | 1st bite excavation in progress, reached 16.5m/ 32m
Tue (28/05) | 28 May 2024 | ST01&02 |  | Guidewall casting by Bachy
Tue (28/05) | 28 May 2024 | P12 |  | Footing rebar work
Tue (28/05) | 28 May 2024 | Zone 1& diverted island |  | No activity
Wed (29/05) | 29 May 2024 | P43 |  | GCE continue JGP works
Wed (29/05) | 29 May 2024 | MH3-5 |  | Start drain rebar works
Wed (29/05) | 29 May 2024 | Zone 4 GCE |  | JGP point B-95 in progress
Wed (29/05) | 29 May 2024 | P50-6 |  | Pending to start
Wed (29/05) | 29 May 2024 | Exit 3 |  | KTC excavation to extend the ECM pond
Wed (29/05) | 29 May 2024 | MH1-2 |  | Vent pipe line installation
Wed (29/05) | 29 May 2024 | Zone 1 |  | P2- 1 and P2-2 rebar cages on site
Wed (29/05) | 29 May 2024 | AbH13-1 |  | Drilling at 52m/56m. Balance 4m to complete today
Wed (29/05) | 29 May 2024 | MH5-1 |  | Soil clearing for pipe pushing from MH5-2
Wed (29/05) | 29 May 2024 | S3 |  | RWDP installation ongoing
Wed (29/05) | 29 May 2024 | P11 |  | Kentledge test setting up
Wed (29/05) | 29 May 2024 | ST007 |  | B2 in progress, 8.7/33.5m
Wed (29/05) | 29 May 2024 | BP2A-1D |  | Trial trench
Wed (29/05) | 29 May 2024 | ST219-218 |  | Guidewall rebar works ongoing
Wed (29/05) | 29 May 2024 | BRP16 |  | Guidewall rebar works done. Now preparing formwork
Wed (29/05) | 29 May 2024 | P31-32 |  | Support slab just cast
Wed (29/05) | 29 May 2024 | ST80 |  | Cutter teeth changing ongoing
Wed (29/05) | 29 May 2024 | ST86 |  | C-lug welding for WS removal
Wed (29/05) | 29 May 2024 | BRP27 |  | Hacking ongoing for trial trench works
Wed (29/05) | 29 May 2024 | DW25 |  | Rebar cage installation ongoing, 4/6nos
Wed (29/05) | 29 May 2024 | DW19 |  | B1 in progress
Wed (29/05) | 29 May 2024 | Zone 4 |  | Telstra pipe laying in progress. 15m
Wed (29/05) | 29 May 2024 | P50-6 |  | Current depth 25.1m/27m. Arranged Point load test to confirm rock condition. Tonight to complete boring works. Tomorrow to cast
Wed (29/05) | 29 May 2024 | P49 |  | Rig platform preparation in progress. TT completed. Tomorrow rig will shift here
Wed (29/05) | 29 May 2024 | P46 |  | GI works continue for 3rd point. 3 nos target today for this area
Wed (29/05) | 29 May 2024 | Zone 4 drain diversion for sewer 3 |  | Rebar works in progress. Balance wall inner bars and 2 layers of distribution bars. Plan to cast base slab tomorrow. Wall casting target by Sunday. Benching to complete by Tuesday
Wed (29/05) | 29 May 2024 | ST86 |  | Preparation for end plate trimming
Wed (29/05) | 29 May 2024 | ST80 |  | 2nd bite at 28.3m. Hydraulic leakage. Repair works in progress
Wed (29/05) | 29 May 2024 | Zone 3 |  | Deck beam installation for UKP23-25. Work till 10pm
Wed (29/05) | 29 May 2024 | DW25 |  | 6/6 cage installation
Wed (29/05) | 29 May 2024 | BR03 |  | Trenching continue, 32.9m depth
Wed (29/05) | 29 May 2024 | DW19 |  | 1st bite in progress, reached 28m
Wed (29/05) | 29 May 2024 | DW25 |  | Hanging bar installation in progress. Tonight to cast
Wed (29/05) | 29 May 2024 | BP2A-1 | 24 | Casing installation almost completed. HSL will go back after this
Wed (29/05) | 29 May 2024 | P12 |  | Balance top bar installation and prepare for formwork closing. Day shift work until 10PM and night shift also arranged
Wed (29/05) | 29 May 2024 | P11-2 |  | Formwork closing
Wed (29/05) | 29 May 2024 | S3 |  | Formwork closing. Now clearing materials
Wed (29/05) | 29 May 2024 | N5 |  | Today casting slab for falsework erection. WH will lay BRC then cast 150mm thick slab in addition to 1.5m x 1.5m stump to support croasshead construction
Wed (29/05) | 29 May 2024 | Zone 1 |  | No activity already
Thu (30/05) | 30 May 2024 | BRP04B-1 |  | KP hanging bar installation ongoing
Thu (30/05) | 30 May 2024 | BRP3A-1 |  | B1 in progress
Thu (30/05) | 30 May 2024 | P15 |  | Continue welding works for waler beam and struts
Thu (30/05) | 30 May 2024 | N4 |  | KTC backfilling works. Target afternoon ndt
Thu (30/05) | 30 May 2024 | P50-6 |  | Rock coring in progress. Target to cast today
Thu (30/05) | 30 May 2024 | Zone 4 | 3m dia | 1 point grouting started
Thu (30/05) | 30 May 2024 | P12 |  | Pilecap rebar works ongoing, shear links installation
Thu (30/05) | 30 May 2024 | P11-2 |  | Working platform installation works in progress. Today to cast
Thu (30/05) | 30 May 2024 | North ramp P11-2 |  | 2nd lift casting ongoing
Thu (30/05) | 30 May 2024 | MH5-1 |  | Pipe jacking still in progress
Thu (30/05) | 30 May 2024 | ABH 13-2 |  | 34m depth now
Thu (30/05) | 30 May 2024 | DW19 |  | 1st bite completed
Thu (30/05) | 30 May 2024 | Zone 1 |  | Hacking of premix for sump pit construction
Thu (30/05) | 30 May 2024 | DW25 |  | Casting in progress
Thu (30/05) | 30 May 2024 | MH5-1 |  | Continue pipe pushing from MH5-2
Thu (30/05) | 30 May 2024 | S3 |  | Propping installation for column casting
Thu (30/05) | 30 May 2024 | P11-1 |  | Column starter bar installation and formwork closing
Thu (30/05) | 30 May 2024 | P15 |  | Waler beam welding 80% completed. Today concrete packing casting. Tomorrow MPI
Thu (30/05) | 30 May 2024 | N5 |  | Slab for falsework pedestal curing. Assembly of falsework plan to start tomorrow
Thu (30/05) | 30 May 2024 | P12 |  | Continue pilecap rebar works
Thu (30/05) | 30 May 2024 | MH5-1 |  | TBM retrieval ongoing
Thu (30/05) | 30 May 2024 | S3 |  | Casting ongoing
Thu (30/05) | 30 May 2024 | Bachy ST007 |  | B3 in progress
Thu (30/05) | 30 May 2024 | Zone 1 |  | ABH11 TT
Thu (30/05) | 30 May 2024 | Zone 4 and MH3-5 |  | No more activity
Thu (30/05) | 30 May 2024 | ST86 |  | B2 cleaning ongoing
Thu (30/05) | 30 May 2024 | ST80 |  | Preparing for cutter teeth change
Thu (30/05) | 30 May 2024 | ABH13-2 |  | SI works in progress, 20/58m. SPT every 2m. Target to complete by Saturday
Fri (31/05) | 31 May 2024 | N4 |  | KTC continue backfilling & compaction works
Fri (31/05) | 31 May 2024 | P15 |  | Waler beam and struts welding completed. MPI test ongoing
Fri (31/05) | 31 May 2024 | DW19 |  | Endplate loosening ongoing
Fri (31/05) | 31 May 2024 | Zone 4- 3m dia |  | Preparation for boring work
Fri (31/05) | 31 May 2024 | P12 |  | Balance shearlinks installation and formwork closing in progress. Target to cast by 6pm
Fri (31/05) | 31 May 2024 | P11-1 |  | Delivery of steel plate for kentledge. Total 412 pcs required
Fri (31/05) | 31 May 2024 | Zone 1 P3 area |  | Premix and pavement hacking for sump pit
Fri (31/05) | 31 May 2024 | ABH11 |  | Drilling and SPT in progress. 28m/56m
Fri (31/05) | 31 May 2024 | Zone 1 |  | Premix hacking for sump pit construction
Fri (31/05) | 31 May 2024 | Zone 1 | ABH13-3 | 1st permeability test ongoing for (41.48 ~ 42.48)m depth
Fri (31/05) | 31 May 2024 | ABH11 |  | Drilling and spt continue. 46/56m depth
Fri (31/05) | 31 May 2024 | Blk 4 |  | Boring of 4 points for fissure grouting done. Grouting in progress
Fri (31/05) | 31 May 2024 | DW19 |  | B2 in progress, 15.3/32m
Fri (31/05) | 31 May 2024 | BRP03A-1 |  | B1 in progress, 27.32/29.02m
Fri (31/05) | 31 May 2024 | ST256 |  | Excavation started. B1 CD 11/34.5m
Fri (31/05) | 31 May 2024 | ST80 |  | Temporarily stopped for cutter teeth changing. B2 CD 31.5/32m
Fri (31/05) | 31 May 2024 | ST007 |  | Base toe cleaning ongoing using pump
Fri (31/05) | 31 May 2024 | BRP04B-1 |  | Tremie pipe installation ongoing
Fri (31/05) | 31 May 2024 | P15 |  | MPI completed. KTC to start excavation to FEL
Fri (31/05) | 31 May 2024 | P11-1 |  | Unloading of steel plate for kentledge
Fri (31/05) | 31 May 2024 | P12 |  | Balance shearlinks and formwork closing continue. Tonight to cast
Fri (31/05) | 31 May 2024 | N4 |  | Last layer backfilling for falsework
Fri (31/05) | 31 May 2024 | BRP4B-1 |  | Casting ongoing
Fri (31/05) | 31 May 2024 | ST256 |  | B1 in progress, 18/34.5m
Fri (31/05) | 31 May 2024 | ST007 |  | Grouting pipe preparation
Fri (31/05) | 31 May 2024 | P12 |  | Continue rebar works. Tonight plan for casting
Fri (31/05) | 31 May 2024 | Zone 2 HSL |  | Continue Kentledge setup
Fri (31/05) | 31 May 2024 | P15 |  | No activity
Fri (31/05) | 31 May 2024 | S3, S4 |  | No activity
Fri (31/05) | 31 May 2024 | Zone 3 |  | Platform preparation for Krishco water pipe thrust block casting
Fri (31/05) | 31 May 2024 | P31-32 |  | No activity
Fri (31/05) | 31 May 2024 | ST80 |  | Preparation for c-lug welding
Fri (31/05) | 31 May 2024 | P49-8 |  | Boring started
Fri (31/05) | 31 May 2024 | P47 |  | Drain side exposed. Surveyor taking as-built for BP work
Fri (31/05) | 31 May 2024 | DW19 |  | 2nd bite trenching at 24m depth
Fri (31/05) | 31 May 2024 | ST114 |  | Preparing for cutter flap replacement. B1 CD 13/39m
Fri (31/05) | 31 May 2024 | BRP04 |  | 1st bite trenching completed. Now preparing for Koden then proceed with 2nd bite
Fri (31/05) | 31 May 2024 | BRP03 |  | Casting in progress. Running volume 120 m3. Last load
Fri (31/05) | 31 May 2024 | BR3A-01 |  | B2 ongoing
Fri (31/05) | 31 May 2024 | Zone 3 CCW |  | Area preparation for KP TT
Fri (31/05) | 31 May 2024 | BP2A-1 | 24 | Boring works in progress. Current depth 25m
Sat (01/06) | 01 Jun 2024 | ST256 |  | B1 in progress, 30.2/34.5m
Sat (01/06) | 01 Jun 2024 | ST007 |  | Preparing for casting
Sat (01/06) | 01 Jun 2024 | ST80 |  | B1 cleaning completed
Sat (01/06) | 01 Jun 2024 | ST114 |  | Cutter teeth changing and preparing for internal koden check for B1
Sat (01/06) | 01 Jun 2024 | MH5-2 |  | LCH preparing to remove hoses and slurry pipes before fully push in of balance pipes
Sat (01/06) | 01 Jun 2024 | DW19 |  | Final koden check was done. Now preparing for waterstop installation
Sat (01/06) | 01 Jun 2024 | Outside gate 5 |  | Leychoon lane closure for 22kV pipe laying
Sat (01/06) | 01 Jun 2024 | ABH11& 13-1 |  | SI work in progress by Dongah
Sat (01/06) | 01 Jun 2024 | P49-8 |  | Rock coring to Toe in progress. Today to cast
Sat (01/06) | 01 Jun 2024 | MH3-5 |  | No activity. Continue raining
Sat (01/06) | 01 Jun 2024 | Exit 1 |  | Excavation for ECM pond
Sat (01/06) | 01 Jun 2024 | P45 |  | Temporary hoarding done
Sat (01/06) | 01 Jun 2024 | ST114 |  | 1st bite in progress, reached 27.5m
Sat (01/06) | 01 Jun 2024 | BR05 |  | 1st bite excavation started
Sat (01/06) | 01 Jun 2024 | BP2A-1 | 24 | Boring reached 33.3m/ 44.75m
Sat (01/06) | 01 Jun 2024 | P13 |  | Preboring for ERSS installation
Sat (01/06) | 01 Jun 2024 | P10-2 |  | Formwork dismantling
Sat (01/06) | 01 Jun 2024 | P9-2 |  | Link bar installation
Sat (01/06) | 01 Jun 2024 | MH1-2 |  | Piping work diverted island for water supply
Sat (01/06) | 01 Jun 2024 | MH5-2 |  | Bentonite hoses removal
Sat (01/06) | 01 Jun 2024 | Zone 1 |  | Today boring rig from Zone 2 will shift to Zone 1. Trailer already on site
Sat (01/06) | 01 Jun 2024 | ST007 |  | Rebar cage installation ongoing, 3/7nos
Sat (01/06) | 01 Jun 2024 | ST256 |  | B1 in progress
Sat (01/06) | 01 Jun 2024 | ST80 |  | Trimming ongoing
Sat (01/06) | 01 Jun 2024 | ST114 |  | Resume B1 excavation
Sat (01/06) | 01 Jun 2024 | ST86 |  | Slump check
Sat (01/06) | 01 Jun 2024 | ST86 |  | Casting in progress, 105/250m3
Sat (01/06) | 01 Jun 2024 | DW19 |  | Trimming
Sat (01/06) | 01 Jun 2024 | P12 |  | Casting ongoing
Sat (01/06) | 01 Jun 2024 | Zone 2 HSL |  | Continue Kentledge setup
Sun (02/06) | 02 Jun 2024 | DW19 |  | Rebar cage lowering in progress, 6/6nos completed
Sun (02/06) | 02 Jun 2024 | Exit-3 | BC-3 | BR4A-01(BR-05) 2nd bite excavation in progress, current depth 6m
Sun (02/06) | 02 Jun 2024 | Zone 3 |  | Manual Trial trench works ongoing for BP2A-2(34)
Sun (02/06) | 02 Jun 2024 | BR-21 & BR-22 |  | Formwork closing for guide wall. Today to cast both
Sun (02/06) | 02 Jun 2024 | ST-80 |  | Desanding completed
Sun (02/06) | 02 Jun 2024 | Zone 3 |  | KTC continue excavation works for vent shaft
Sun (02/06) | 02 Jun 2024 | ST114 |  | B2 excavation temporarily stopped. Cutter teeth changing works ongoing, current depth 14.8m
Sun (02/06) | 02 Jun 2024 | Exit 1 |  | KTC ecm excavation works
Sun (02/06) | 02 Jun 2024 | MH3-5 |  | Drain wall Formwork closing works in progress. To cast on Monday
Sun (02/06) | 02 Jun 2024 | Zone 4 |  | Activ tech Singtel cables recovery works
Sun (02/06) | 02 Jun 2024 | N5 |  | No activity
Sun (02/06) | 02 Jun 2024 | N4 |  | No activity
Sun (02/06) | 02 Jun 2024 | P15 |  | KTC excavation to FEL ongoing
Sun (02/06) | 02 Jun 2024 | P13 |  | No activity for ERSS works
Sun (02/06) | 02 Jun 2024 | P12 |  | Pile cap cast yesterday. Curing ongoing
Sun (02/06) | 02 Jun 2024 | P11 |  | Kentledge steel plate load laying works ongoing
Sun (02/06) | 02 Jun 2024 | P10-2 |  | Column formwork removal works ongoing
Sun (02/06) | 02 Jun 2024 | Zone 1 |  | ECM pond plastering works
Sun (02/06) | 02 Jun 2024 | Zone 1 |  | Boring rig mobilized last night. Tmr to set up
Sun (02/06) | 02 Jun 2024 | DW19 |  | Rebar cages fully lowered. Pending for casting
Sun (02/06) | 02 Jun 2024 | Exit-3 | BC-3 | BR4A-01(BR-05) 2nd bite excavation in progress, current depth 20m
Sun (02/06) | 02 Jun 2024 | Guidewall | BR-21 & BR-22 | BR-21 completed casting & BR-22 pending casting
Sun (02/06) | 02 Jun 2024 | ST-80 |  | Koden test completed. Preparing for water stop installation
Sun (02/06) | 02 Jun 2024 | ST-173 |  | Preparation to start Dwall trenching
Sun (02/06) | 02 Jun 2024 | ST114 |  | B2 excavation in progress, current depth 22m
Sun (02/06) | 02 Jun 2024 | Zone 3 Vent Shaft |  | Current status for KTC excavation works
Sun (02/06) | 02 Jun 2024 | Zone 3 Vent Shaft |  | SingTel cables recovery works
Sun (02/06) | 02 Jun 2024 | MH3-5 |  | Continue Drain wall Formwork closing works
Sun (02/06) | 02 Jun 2024 | DW19 |  | Rebar cage installation ongoing, 3/6nos
Sun (02/06) | 02 Jun 2024 | ST256 |  | B1 resume, 31.2/34.5m
Sun (02/06) | 02 Jun 2024 | ST007 |  | Casting in progress, 165/252m3
Sun (02/06) | 02 Jun 2024 | MH1-2 |  | Pipe Benching works
Sun (02/06) | 02 Jun 2024 | ST80 |  | B2 cleaning temporarily stopped due to cutter gear box hose leaking. Rectification ongoing
Sun (02/06) | 02 Jun 2024 | ST114 |  | B2 excavation temporarily stopped. Desander sand pump ring damaged. Rectification ongoing
Sun (02/06) | 02 Jun 2024 | P10-2 |  | Continue Column formwork removal works
Sun (02/06) | 02 Jun 2024 | P11 |  | Kentledge steel plate (load) laying works current status
Sun (02/06) | 02 Jun 2024 | P15 |  | KTC excavation works stopped for the day. Tmr to continue excavation to FEL
Sun (02/06) | 02 Jun 2024 | Exit 3 |  | KTC ecm pond excavation & soil disposal works
Mon (03/06) | 03 Jun 2024 | BRP4A-1 |  | Rebar cage hanging bar installation ongoing
Mon (03/06) | 03 Jun 2024 | Zone 4 |  | Drain diversion for sewer 3 formwork closing. Tomorrow to cast
Mon (03/06) | 03 Jun 2024 | Zone 1 |  | Rig set up, tonight to shift at P2 area. Tomorrow AE will inspect. WH only target to start boring by Wednesday
Mon (03/06) | 03 Jun 2024 | P13 |  | ERSS pre-boring in progress
Mon (03/06) | 03 Jun 2024 | Zone 3 |  | WH replacing access ladder to new one along ecm pond
Mon (03/06) | 03 Jun 2024 | ST80 |  | Hanging bar installation ongoing
Mon (03/06) | 03 Jun 2024 | ST256 |  | B1 in progress, 33m
Mon (03/06) | 03 Jun 2024 | ATT-Z3-TDP19 |  | Completed. Backfilling in progress
Mon (03/06) | 03 Jun 2024 | BC-4 |  | Need to change flange to 1500mm
Tue (04/06) | 04 Jun 2024 | ST173 | BC3 | B1 in progress
Tue (04/06) | 04 Jun 2024 | ST114 |  | Cage A ( 2/4 lowered down). Cage B (1/4 lowered). Tomorrow morning can cast
Tue (04/06) | 04 Jun 2024 | ST80 |  | Casting in progress, 135/220m3
Tue (04/06) | 04 Jun 2024 | ST83 | BC1 | B1 temporarily stopped for gear oil topup
Tue (04/06) | 04 Jun 2024 | Exit 1 ECM |  | Currently pumping out water thereafter continue excavation
Tue (04/06) | 04 Jun 2024 | ST173 |  | 1st bite in progress, reached 35.9m
Tue (04/06) | 04 Jun 2024 | ST114 |  | WS joint welding ongoing. BC2 currently no activity
Tue (04/06) | 04 Jun 2024 | P44 area |  | Yellow fencing with green netting installed
Tue (04/06) | 04 Jun 2024 | Zone 4 JGP |  | B-157 in progress
Tue (04/06) | 04 Jun 2024 | P49-7 |  | Currently no activity
Tue (04/06) | 04 Jun 2024 | Zone 1 island P3 area |  | Hacking for sump pit
Tue (04/06) | 04 Jun 2024 | Zone 1 P2 area |  | Lane closed for BP works
Tue (04/06) | 04 Jun 2024 | AbH12 |  | Drilling and SPT in progress
Tue (04/06) | 04 Jun 2024 | ST83 |  | B1 resume, CD14/33.5m
Tue (04/06) | 04 Jun 2024 | P31-32 cable joint area |  | Ley Choon is here for SPPG cable pulling. They just mobilised today
Tue (04/06) | 04 Jun 2024 | BRP32 |  | Hacking ongoing for trial trench works
Tue (04/06) | 04 Jun 2024 | BRP27 |  | Guidewall excavation ongoing
Tue (04/06) | 04 Jun 2024 | BP2A-1 | 24 | Current depth 43.5m
Tue (04/06) | 04 Jun 2024 | ST006 |  | Soil disposal and B1 excavation ongoing, 22/35m
Tue (04/06) | 04 Jun 2024 | ST256 |  | WS lowering ongoing
Tue (04/06) | 04 Jun 2024 | ABH12 |  | Drilling in progress, current depth 52m. Target to finish today
Tue (04/06) | 04 Jun 2024 | Zone 3 |  | 6.6kV cable pulling ongoing toward substation side
Tue (04/06) | 04 Jun 2024 | Zone 3 |  | TDP20 trial trench ongoing
Tue (04/06) | 04 Jun 2024 | P30 |  | Ley Choon open pit for cable pulling
Tue (04/06) | 04 Jun 2024 | MH5-1 |  | Patching on going for LSS grouting
Tue (04/06) | 04 Jun 2024 | S4 |  | Dismantling of struts
Tue (04/06) | 04 Jun 2024 | P11-1-1 |  | Kentledge steel plates laying works ongoing
Tue (04/06) | 04 Jun 2024 | P34 |  | Seongha has demob materials and machinery
Tue (04/06) | 04 Jun 2024 | ST114 |  | Continue WS endplate joint welding
Tue (04/06) | 04 Jun 2024 | Along LW LP23/1 |  | Netlink lane closure
Tue (04/06) | 04 Jun 2024 | P12 |  | Stump rebar works in progress
Tue (04/06) | 04 Jun 2024 | P13 |  | Pre-boring for ERSS continue
Tue (04/06) | 04 Jun 2024 | ST114 |  | Cutter teeth changing ongoing
Tue (04/06) | 04 Jun 2024 | Zone 3 |  | Seongha has started to demob their materials from site. Tmr they will demob their machine
Tue (04/06) | 04 Jun 2024 | BC4 |  | Maintenance works ongoing
Tue (04/06) | 04 Jun 2024 | ST006 |  | B1 in progress, 27/35m
Tue (04/06) | 04 Jun 2024 | ST256 |  | WS lowering completed
Tue (04/06) | 04 Jun 2024 | ST006 |  | Internal rock depth check at 26m
Tue (04/06) | 04 Jun 2024 | ST006 |  | 1st bite trenching continue, hard rock encountered at around 25m depth after lunch, now at 28.6m depth. Trenching relatively fast. 👍
Tue (04/06) | 04 Jun 2024 | N5 |  | Primary beams assembly and cross bracing in progress
Tue (04/06) | 04 Jun 2024 | P15 |  | Excavation to FEL status. To complete tomorrow
Tue (04/06) | 04 Jun 2024 | P11-1 |  | Kentledge setup status. 2nd layer 70% completed
Tue (04/06) | 04 Jun 2024 | Zone 1 |  | Mud tank and casing delivered
Tue (04/06) | 04 Jun 2024 | BC cutter-4 |  | Changing flange to 1500mm
Tue (04/06) | 04 Jun 2024 | BP2A-1-24 |  | Rebar cages lowering. To cast tonight
Tue (04/06) | 04 Jun 2024 | ST006 |  | 1st bite in progress. Reached 28.8m
Tue (04/06) | 04 Jun 2024 | North ramp P15 |  | Concrete barrier placing and barricade work by Woh Hup
Tue (04/06) | 04 Jun 2024 | P8-2 |  | Lean concrete for column formwork closing
Tue (04/06) | 04 Jun 2024 | P15 |  | Excavation to FEL continue
Tue (04/06) | 04 Jun 2024 | N3 |  | Preparation for backfilling
Tue (04/06) | 04 Jun 2024 | P13 |  | Pre-boring continue
Tue (04/06) | 04 Jun 2024 | MH3-5 |  | Concrete on site for drain casting. 15m3
Tue (04/06) | 04 Jun 2024 | P12 |  | Column stump rebar works continue. To cast on friday
Wed (05/06) | 05 Jun 2024 | BC4 |  | Maintenance ongoing
Wed (05/06) | 05 Jun 2024 | Sewer 3 |  | Temporary drain diversion no activity
Wed (05/06) | 05 Jun 2024 | Zone 4 |  | No activity
Wed (05/06) | 05 Jun 2024 | N5 |  | Falsework assembly for crosshead formwork
Wed (05/06) | 05 Jun 2024 | P13 |  | ERSS preboring works ongoing, to complete by afternoon
Wed (05/06) | 05 Jun 2024 | P10 |  | Removal of spiked cables for upcoming ERSS preboring works
Wed (05/06) | 05 Jun 2024 | P15 |  | Excavation to FEL. Today to complete
Wed (05/06) | 05 Jun 2024 | MH1-2 |  | Pipe benching and patching works
Wed (05/06) | 05 Jun 2024 | MH5-2 to MH5-1 |  | Preparation for LSS grouting
Wed (05/06) | 05 Jun 2024 | S4 |  | Waler and strut remove yesterday. Now scaffold erection to clear hardcores and start wall rebar works
Wed (05/06) | 05 Jun 2024 | ST006 |  | 1st bite in progress, reached 29.7m
Wed (05/06) | 05 Jun 2024 | ST114 |  | Cage A (3/4 cages lowered down). Cage B (3/4 cages lowering in progress)
Wed (05/06) | 05 Jun 2024 | ST173 |  | 1st bite excavation in progress, reached 38m. Now changing cutter teeth
Wed (05/06) | 05 Jun 2024 | ST83 |  | Bring up cutter body for cutter wheel maintenance. Current depth is 28.3m
Wed (05/06) | 05 Jun 2024 | P15 |  | WH installing new access
Wed (05/06) | 05 Jun 2024 | P12 |  | No activity
Wed (05/06) | 05 Jun 2024 | Zone 2 HSL |  | Continue kentledge setup till 10pm
Wed (05/06) | 05 Jun 2024 | Zone 2 centre island |  | Clearing hardcore
Wed (05/06) | 05 Jun 2024 | Zone 1 HSL |  | Bentonite hose connection rectification
Wed (05/06) | 05 Jun 2024 | ST006 |  | B1 in progress, 32.3/33.5m
Wed (05/06) | 05 Jun 2024 | P31-32 cable joint area |  | Some cables already seen here. Currently no activity
Wed (05/06) | 05 Jun 2024 | ST173 |  | B2 started
Wed (05/06) | 05 Jun 2024 | ST83 |  | B2 in progress, 5/33.5m
Wed (05/06) | 05 Jun 2024 | ST114 |  | Casting ongoing. Current vol: 111/270m3
Wed (05/06) | 05 Jun 2024 | Zone 1 |  | Preparation for BP works
Thu (06/06) | 06 Jun 2024 | P4 |  | Premix and rigid pavement hacking done. To continue trial trench
Thu (06/06) | 06 Jun 2024 | MH1-2 |  | Benching completed. Now access cover installation
Thu (06/06) | 06 Jun 2024 | P49-7 |  | Boring to Toe level in progress. Casting will be tomorrow
Thu (06/06) | 06 Jun 2024 | S4 |  | Housekeeping and stump rebar installation
Thu (06/06) | 06 Jun 2024 | MH5-2 to MH5-1 |  | Today water pressure test
Thu (06/06) | 06 Jun 2024 | P8-2 |  | Platform preparation for boomlift prior to formwork closing
Thu (06/06) | 06 Jun 2024 | P9-2 |  | Formwork closing
Thu (06/06) | 06 Jun 2024 | P10 |  | LE to shift machineries here today
Thu (06/06) | 06 Jun 2024 | P13 |  | Lagging plate installation. To complete today
Thu (06/06) | 06 Jun 2024 | N5 |  | Falsework erection status. Main beam and secondary beam completed. Now preparing to install c-channel
Thu (06/06) | 06 Jun 2024 | P16 |  | Modification of linkway to allow ERSS work
Thu (06/06) | 06 Jun 2024 | P2-1 |  | Casting started
Thu (06/06) | 06 Jun 2024 | N5 |  | Current status for Falsework installation
Thu (06/06) | 06 Jun 2024 | P11-1-1 |  | Preparation for reference beam installation
Thu (06/06) | 06 Jun 2024 | P9-2 |  | Column Formwork closing
Thu (06/06) | 06 Jun 2024 | S4 |  | Stump rebar inspection ongoing
Thu (06/06) | 06 Jun 2024 | MH5-1 to MH5-2 |  | Water pressure test ongoing
Thu (06/06) | 06 Jun 2024 | P2-5 |  | Reached toe level, 36m depth. Now mud clearing then confirm toe level
Thu (06/06) | 06 Jun 2024 | ST113 |  | Dongah prepare the area for tonight excavation
Thu (06/06) | 06 Jun 2024 | ST006 |  | B1 ongoing, 32.6/33.5m
Thu (06/06) | 06 Jun 2024 | BRP32 |  | Guidewall rebar works ongoing
Thu (06/06) | 06 Jun 2024 | ST173 |  | B2 in progress, 16/41.1m
Thu (06/06) | 06 Jun 2024 | ST83 |  | B2 in progress, 16.8/33.5m
Thu (06/06) | 06 Jun 2024 | ST114 |  | Casting completed, 272m3. BC2 currently no activity
Thu (06/06) | 06 Jun 2024 | P4 |  | BP trial trench completed
Thu (06/06) | 06 Jun 2024 | P16 |  | Linkway shifted. Now fixing hoarding panel
Thu (06/06) | 06 Jun 2024 | P11-1 |  | Continue delivery of steel plates for kentledge
Thu (06/06) | 06 Jun 2024 | P10-1 |  | LE rig mobilise to continue pre-boring for ERSS
Thu (06/06) | 06 Jun 2024 | P9-2 |  | Formwork closing and access erection for casting
Thu (06/06) | 06 Jun 2024 | Zone 1 |  | P2-1 rebar cages safely shifted
Thu (06/06) | 06 Jun 2024 | S4 |  | Abutment wall formwork closing
Thu (06/06) | 06 Jun 2024 | BC4 |  | Maintenance works ongoing
Thu (06/06) | 06 Jun 2024 | BRP32 |  | Guidewall cast. Levelling ongoing
Thu (06/06) | 06 Jun 2024 | ST173 |  | B2 temporarily stopped. Cutter teeth changing ongoing
Thu (06/06) | 06 Jun 2024 | ST83 |  | B2 temporarily stopped. Cutter teeth changing ongoing
Thu (06/06) | 06 Jun 2024 | ST113 |  | Plan to start ard 1am. Now ongoing preparation works - hose connection works, etc
Thu (06/06) | 06 Jun 2024 | Exit 1 ECM |  | Slope cast. Netting installation ongoing
Thu (06/06) | 06 Jun 2024 | Drain diversion & zone 4 |  | No activity
Thu (06/06) | 06 Jun 2024 | Zone 3 HSL |  | No activity
Thu (06/06) | 06 Jun 2024 | ST006 |  | B2 in progress, 11/33.5m
Thu (06/06) | 06 Jun 2024 | P15 |  | No activity
Thu (06/06) | 06 Jun 2024 | P12 |  | No activity
Thu (06/06) | 06 Jun 2024 | Zone 2 HSL |  | No activity
Thu (06/06) | 06 Jun 2024 | Zone 1 P2-1 |  | Tremie pipe installation in progress. Concrete alr batched
Thu (06/06) | 06 Jun 2024 | Zone 1 |  | Lane closed for P2 bored pile works
Thu (06/06) | 06 Jun 2024 | P2-5 |  | Boring started
Fri (07/06) | 07 Jun 2024 | ST83 |  | Resume B2 excavation
Fri (07/06) | 07 Jun 2024 | P2-1 |  | Casting completed
Fri (07/06) | 07 Jun 2024 | N5 falsework |  | C-channel installation in progress
Fri (07/06) | 07 Jun 2024 | P15 |  | Excavation to FEL continue
Fri (07/06) | 07 Jun 2024 | P13 |  | Excavation to FEL started
Fri (07/06) | 07 Jun 2024 | P11-1 |  | Steel plate stacking completed
Fri (07/06) | 07 Jun 2024 | P11-2 |  | Formwork dismantling
Fri (07/06) | 07 Jun 2024 | P9-2 |  | Formwork closing continue. Tomorrow to cast
Fri (07/06) | 07 Jun 2024 | MH5-2 to MH5-1 |  | Mud clearing. Water Pressure test in progress
Fri (07/06) | 07 Jun 2024 | S4 |  | Abutment wall formwork closing. Tomorrow to cast
Fri (07/06) | 07 Jun 2024 | ST255 |  | Started last night
Fri (07/06) | 07 Jun 2024 | ST006 |  | B2 temporarily stopped for cutter teeth changing. CD 21/33.5m
Fri (07/06) | 07 Jun 2024 | BRP16 |  | Guidewall rebar completed. Pending formwork fabrication
Fri (07/06) | 07 Jun 2024 | ST173 |  | B2 in progress, 28/41.1m
Fri (07/06) | 07 Jun 2024 | ST83 |  | B2 in progress, 19/33.5m
Fri (07/06) | 07 Jun 2024 | P49-7 |  | Rebar cage lowering. Today to cast
Fri (07/06) | 07 Jun 2024 | P50-9 |  | Preparing for preboring
Fri (07/06) | 07 Jun 2024 | ST113 |  | B1 in progress, 10m
Fri (07/06) | 07 Jun 2024 | BC4 |  | Continue cutter body modification
Fri (07/06) | 07 Jun 2024 | ST006 |  | Teeth replacement, current at 2nd bite 27.5m/35m
Fri (07/06) | 07 Jun 2024 | BP2-2 | 37 | Boring in progress, 32.7m/41.5m
Fri (07/06) | 07 Jun 2024 | BRP12 |  | Excavation for guidewall construction
Fri (07/06) | 07 Jun 2024 | BRP28 |  | Excavation for guidewall construction
Fri (07/06) | 07 Jun 2024 | Zone 3 |  | P31-32 slope casting
Fri (07/06) | 07 Jun 2024 | ST173 - BC3 |  | 2nd bite trenching in progress, current depth 34.7m
Fri (07/06) | 07 Jun 2024 | ST83-BC1 |  | 2nd bite trenching at 21.3/30.3m
Fri (07/06) | 07 Jun 2024 | ST113-BC2 |  | 1st bite trenching at 30.5/39m
Fri (07/06) | 07 Jun 2024 | JGP works 1.8m |  | 2nd point grouting for the day
Fri (07/06) | 07 Jun 2024 | Zone 4 |  | GI works done for the day. 3 points done
Fri (07/06) | 07 Jun 2024 | Zone 4 |  | TT for GI works stopped for the day, 5 nos completed
Fri (07/06) | 07 Jun 2024 | P49-7 |  | Tremie pipe installation in progress for casting. Concrete ordered
Fri (07/06) | 07 Jun 2024 | P50-9 |  | Casing installed. Current depth 9m
Fri (07/06) | 07 Jun 2024 | P15 |  | No activity
Fri (07/06) | 07 Jun 2024 | P13 |  | Barricade installation ongoing
Fri (07/06) | 07 Jun 2024 | P12 |  | No activity
Fri (07/06) | 07 Jun 2024 | Zone 1 |  | No activity
Fri (07/06) | 07 Jun 2024 | S4 |  | Barricades temporary remove to facilitate the casting tmr
Fri (07/06) | 07 Jun 2024 | Zone 3 HSL |  | No activity
Fri (07/06) | 07 Jun 2024 | Zone 3 |  | Ley Choon works done for the day. Now demobilising cable drums. Tmr to continue
Fri (07/06) | 07 Jun 2024 | ST006 |  | B2 temporarily stopped for cutter teeth change. CD 28.9/33.5m
Fri (07/06) | 07 Jun 2024 | ST255 | grabber | B1 excavation stopped, 23/41m and proceed to B2 excavation
Fri (07/06) | 07 Jun 2024 | P31-32 |  | Slope casting was done
Fri (07/06) | 07 Jun 2024 | ST173 |  | Cutter teeth changing ongoing. B2 CD 35.3/41.1m
Fri (07/06) | 07 Jun 2024 | ST83 |  | B2 temporarily stopped. Desander rectification ongoing. B2 CD 21.6/29.1m
Fri (07/06) | 07 Jun 2024 | ST113 |  | B1 resume, 31.2/39m
Fri (07/06) | 07 Jun 2024 | P49-7 |  | Casting completed at 2100hrs
Sat (08/06) | 08 Jun 2024 | P50-9 |  | Casting in progress
Sat (08/06) | 08 Jun 2024 | P13 |  | Access erection
Sat (08/06) | 08 Jun 2024 | P12 |  | Footing formwork removal
Sat (08/06) | 08 Jun 2024 | P11-2 |  | Column formwork removal
Sat (08/06) | 08 Jun 2024 | Loyang Way LP24 |  | Lane closure for Singtel works
Sat (08/06) | 08 Jun 2024 | P11-2 & S4 |  | Column casting will be today. Concrete pump on site
Sat (08/06) | 08 Jun 2024 | S4 |  | Abutment wall casting will be afternoon
Sat (08/06) | 08 Jun 2024 | MH5-1& MH5-2 |  | LCH clearing the materials in the shaft and preparation to start rebar work for base slab
Sat (08/06) | 08 Jun 2024 | BC4 |  | Almost completed. Maybe can start BRP27 on Monday
Sat (08/06) | 08 Jun 2024 | ZONE 1 |  | P4: exposing power duct to confirm cable for spiking
Sat (08/06) | 08 Jun 2024 | P22-2 |  | Preparing for preboring
Sat (08/06) | 08 Jun 2024 | P50-9 |  | Boring in progress. Today to cast
Sat (08/06) | 08 Jun 2024 | ST113 |  | 2nd bite in progress, reached 20m
Sat (08/06) | 08 Jun 2024 | ST173 |  | 2nd bite in progress, reached 38m
Sat (08/06) | 08 Jun 2024 | ST255 |  | 2nd bite reached 20m
Sat (08/06) | 08 Jun 2024 | N5 |  | False work erection in progress
Sat (08/06) | 08 Jun 2024 | N1 |  | KTC started backfilling
Sat (08/06) | 08 Jun 2024 | P11-2 |  | Formwork removal done
Sat (08/06) | 08 Jun 2024 | P9-2 |  | Casting in progress. Left 24m3 to complete
Sat (08/06) | 08 Jun 2024 | MH5-2& MH5-1 |  | Clearing of materials for base slab work
Sat (08/06) | 08 Jun 2024 | P4 |  | Exposing power cable for spiking
Sat (08/06) | 08 Jun 2024 | P2-2 |  | Casing installation in progress
Sat (08/06) | 08 Jun 2024 | ST006 |  | B2 temporarily stopped. Cutter teeth change ongoing. CD 31/33.5m
Sat (08/06) | 08 Jun 2024 | BP50-9 |  | Boring in progress to Toe
Sat (08/06) | 08 Jun 2024 | BRP28 |  | Guidewall rebar works
Sat (08/06) | 08 Jun 2024 | ST83 |  | B2 in progress, 22.8/29.1m
Sat (08/06) | 08 Jun 2024 | ST113 |  | B1 completed. B2 in progress
Sat (08/06) | 08 Jun 2024 | Zone 3 near ST173 |  | Cable identification for Singtel
Sat (08/06) | 08 Jun 2024 | ST173 |  | Cutter body up for teeth changing
Sat (08/06) | 08 Jun 2024 | BC4 |  | Cutter modification/maintenance ongoing
Sat (08/06) | 08 Jun 2024 | ST113 |  | 2nd bite in progress, reached 29m
Sat (08/06) | 08 Jun 2024 | ST173 |  | 2nd in progress, reached 40.6m
Sat (08/06) | 08 Jun 2024 | P15, P13, P12 |  | No activity
Sat (08/06) | 08 Jun 2024 | Zone 2 HSL |  | No more activity
Sat (08/06) | 08 Jun 2024 | P9-2 |  | Casting completed
Sat (08/06) | 08 Jun 2024 | Zone 1 LA towards TPE bound |  | Premix rectification will be done here tonight (2nd lane)
Sat (08/06) | 08 Jun 2024 | Zone 1 |  | Bund wall installation ongoing by WH
Sat (08/06) | 08 Jun 2024 | Zone 1 HSL |  | No activity
Sat (08/06) | 08 Jun 2024 | S4 |  | Casting was completed
Sat (08/06) | 08 Jun 2024 | ST255 |  | B1 resume excavation, 23/41m
Sat (08/06) | 08 Jun 2024 | ST006 |  | Trimming ongoing for WS removal
Sat (08/06) | 08 Jun 2024 | ST173 |  | B3 in progress, 20m
Sat (08/06) | 08 Jun 2024 | ST83 |  | Cutter wheel changing ongoing
Sat (08/06) | 08 Jun 2024 | Exit 3 |  | Crane and BC cutter wire inspection & NDT test also
Sat (08/06) | 08 Jun 2024 | BRP12 |  | Guidewall pending casting
Sat (08/06) | 08 Jun 2024 | BP2A-2-37 |  | Boring in progress. Reached 33.7m
Sat (08/06) | 08 Jun 2024 | ST06 |  | 2nd bite reached 31.5m
Sat (08/06) | 08 Jun 2024 | ST113 |  | B2 in progress, 32/39m
Sat (08/06) | 08 Jun 2024 | Zone 4 LA towards TPE bound |  | M&P works ongoing
Sun (09/06) | 09 Jun 2024 | ST255 |  | B1 reached 31/41m
Sun (09/06) | 09 Jun 2024 | BRP12 |  | Guidewall cast
Sun (09/06) | 09 Jun 2024 | ST113 |  | B2 completed. Now ongoing B3, 21m
Sun (09/06) | 09 Jun 2024 | ST83 |  | Resume excavation
Sun (09/06) | 09 Jun 2024 | ST173 |  | Cutter teeth changing ongoing. B3 CD 39.6/41.1m
Mon (10/06) | 10 Jun 2024 | N5 |  | Working platform installation in progress. PE will come down to check on falsework in the afternoon
Mon (10/06) | 10 Jun 2024 | P15 |  | HSL preparation for pile head hacking
Mon (10/06) | 10 Jun 2024 | P14 |  | Levelling & platform making works for next kentledge test
Mon (10/06) | 10 Jun 2024 | P13 |  | Waler beams installation in progress
Mon (10/06) | 10 Jun 2024 | N1 |  | KTC backfilling works ongoing
Mon (10/06) | 10 Jun 2024 | P12 |  | Formwork removal for pile cap
Mon (10/06) | 10 Jun 2024 | P11-1-1 |  | Kentledge set up completed. Target to start testing today
Mon (10/06) | 10 Jun 2024 | P10 |  | LE trial trench works for preboring ongoing
Mon (10/06) | 10 Jun 2024 | P8-2 |  | Formwork and propping installation for column
Mon (10/06) | 10 Jun 2024 | MH5-2 |  | Thrust block wall hacking works
Mon (10/06) | 10 Jun 2024 | MH5-1 |  | Base slab rebar installation. Target to cast today
Mon (10/06) | 10 Jun 2024 | P2-2 |  | BP Boring works in progress, current depth 22m
Mon (10/06) | 10 Jun 2024 | STN255 |  | B2 CD 30.6/38.3m, meanwhile changing of cutter wheel teeth
Mon (10/06) | 10 Jun 2024 | BP2A-1 trial trench | 21 | Found utility pipe at 1.2m depth. To confirm with utility team
Mon (10/06) | 10 Jun 2024 | STN006 |  | Casting in progress, 144/250cu.m
Mon (10/06) | 10 Jun 2024 | BRP2A-2-37 |  | Boring in progress, CD24.34/26.77m
Mon (10/06) | 10 Jun 2024 | Zone 3 |  | WH erecting new walking access along JTC area
Mon (10/06) | 10 Jun 2024 | N5 |  | Continue working platform installation works
Mon (10/06) | 10 Jun 2024 | P15 |  | HSL pile head cutting works ongoing
Mon (10/06) | 10 Jun 2024 | ST113 | BC2 | Currently no activity
Mon (10/06) | 10 Jun 2024 | Exit 1 new ECM pond |  | Current status
Mon (10/06) | 10 Jun 2024 | P11-1-1 |  | Kentledge testing in progress. Load increased to 50% of WL (652.5T) @ 15:30hrs
Mon (10/06) | 10 Jun 2024 | P14 |  | Continue Levelling & platform making works for next kentledge test
Mon (10/06) | 10 Jun 2024 | N1 |  | KTC backfilling and compaction works ongoing
Mon (10/06) | 10 Jun 2024 | P12 |  | Formwork removal for pile cap
Mon (10/06) | 10 Jun 2024 | ST83 |  | B2 trimming still ongoing. Now cutter teeth changing
Mon (10/06) | 10 Jun 2024 | P8-2 |  | Continue Formwork installation for column
Mon (10/06) | 10 Jun 2024 | P42 |  | RW110 trial trench done. Now setting up machine for installation
Mon (10/06) | 10 Jun 2024 | P10 |  | LE trial trench works for preboring
Mon (10/06) | 10 Jun 2024 | MH5-2 |  | Continue Thrust block wall hacking works
Mon (10/06) | 10 Jun 2024 | BRP20 |  | Guidewall ready to cast. At the same time, BRP19 & BRP24 guidewall also in progress
Mon (10/06) | 10 Jun 2024 | ST173 |  | Rebar cage lowering in progress
Mon (10/06) | 10 Jun 2024 | BRP21 |  | BC#3 resumed excavation, B1 CD 27.7/41.87m
Mon (10/06) | 10 Jun 2024 | P31-32 cable joint area |  | SPPG preparing for cable joining works. They’re now removing the cable skin to facilitate the joining
Mon (10/06) | 10 Jun 2024 | Zone 4 |  | 7nos of pipe sleeves install as of now
Mon (10/06) | 10 Jun 2024 | MH5-1 |  | Preparation works ongoing for base slab casting
Mon (10/06) | 10 Jun 2024 | P2-2 |  | BP Boring completed. Now preparing for rebar cage lowering
Mon (10/06) | 10 Jun 2024 | Zone 3 side |  | Preparing for 2nd point JGP grouting
Mon (10/06) | 10 Jun 2024 | MH3-5 |  | Hacking of drain to connect new to old drain
Mon (10/06) | 10 Jun 2024 | P13 |  | LE continue welding works for waler beams and brackets
Mon (10/06) | 10 Jun 2024 | ST173 |  | Cage A (4/4 cages). Cage B (3/4 cages lower down). Tonight to cast
Mon (10/06) | 10 Jun 2024 | P13 |  | Waler joint welding
Mon (10/06) | 10 Jun 2024 | P13 |  | Pile head hacking
Mon (10/06) | 10 Jun 2024 | P12 |  | Tie rod hole patch up
Mon (10/06) | 10 Jun 2024 | P10 |  | Preboring for ERSS
Mon (10/06) | 10 Jun 2024 | P8-2 |  | Formwork closing for column
Mon (10/06) | 10 Jun 2024 | MH5-2 |  | Hacking of protruding concrete for base slab
Mon (10/06) | 10 Jun 2024 | P2-2 |  | Rebar cage lapping. Tonight to cast
Tue (11/06) | 11 Jun 2024 | ST255 |  | B1 and B2 completed, 34.7m. Now machine maintenance ongoing thereafter continue B3. Today the rebar cages will be delivered (plan 3/8nos cages delivery today)
Tue (11/06) | 11 Jun 2024 | Zone 3 |  | WH preparing for TDP12 trial trench
Tue (11/06) | 11 Jun 2024 | BP2A-2 | 37 | Toe level reached 41.5m
Tue (11/06) | 11 Jun 2024 | BC4 |  | Currently only maintenance ongoing
Tue (11/06) | 11 Jun 2024 | BRP21 |  | Cleaning ongoing
Tue (11/06) | 11 Jun 2024 | BRP27 - BC4 |  | Trenching on going, depth at 9m/36.66m
Tue (11/06) | 11 Jun 2024 | ST83 - BC1 |  | Current 2nd bite trimming. Now mud drum pump repair works
Tue (11/06) | 11 Jun 2024 | ST113-BC3 |  | Water stop loosening
Tue (11/06) | 11 Jun 2024 | Zone 3 |  | ECM pond 1 started hacking
Tue (11/06) | 11 Jun 2024 | ST113 |  | No activity. BC2 still ongoing repair works
Tue (11/06) | 11 Jun 2024 | P42 |  | RG continue recharge well installation
Tue (11/06) | 11 Jun 2024 | ST173 |  | Casting in progress
Tue (11/06) | 11 Jun 2024 | N5 |  | Preparation for wing-form Formwork installation
Tue (11/06) | 11 Jun 2024 | P15 |  | HSL pile head cutting works
Tue (11/06) | 11 Jun 2024 | ST173 |  | Casting completed, 285m3
Tue (11/06) | 11 Jun 2024 | P14 |  | Steel mat laying works in progress for next kentledge location
Tue (11/06) | 11 Jun 2024 | ST83 | BC1 | Trimming temporarily stopped. Cutter wheel gear box changing still ongoing
Tue (11/06) | 11 Jun 2024 | ST113 |  | BC3 has shifted over to this panel. Now ongoing c-lug welding prior to resuming
Tue (11/06) | 11 Jun 2024 | P11-1-1 |  | Kentledge testing in progress at 200% of WL. As of now 7.17mm maximum settlement
Tue (11/06) | 11 Jun 2024 | P13 |  | Test pile hacking & struts welding works
Tue (11/06) | 11 Jun 2024 | P10-2 |  | KTC column backfilling works
Tue (11/06) | 11 Jun 2024 | P44 |  | WH hacking ongoing for trial trench works
Tue (11/06) | 11 Jun 2024 | Exit 1 |  | Pipe inlet installation to ECM pond
Tue (11/06) | 11 Jun 2024 | P49-9 |  | Boring in progress
Tue (11/06) | 11 Jun 2024 | BRP23 |  | Guidewall trial trench
Tue (11/06) | 11 Jun 2024 | BRP19 |  | Guidewall rebar installation ongoing
Tue (11/06) | 11 Jun 2024 | BC4 |  | Already shifted to BRP27
Tue (11/06) | 11 Jun 2024 | BRP21 |  | Cleaning and desanding completed. Preparation for rebar cage lowering
Tue (11/06) | 11 Jun 2024 | Zone 3 |  | Ley Choon backfilling ongoing towards substation
Tue (11/06) | 11 Jun 2024 | BP2A-2 | 37 | Rebar cage lowering ongoing
Tue (11/06) | 11 Jun 2024 | ST255 |  | BC cutter maintenance still ongoing
Tue (11/06) | 11 Jun 2024 | P10 |  | LE preboring works for ERSS installation
Tue (11/06) | 11 Jun 2024 | P8-2 |  | Column Formwork installation. Tmr to cast
Tue (11/06) | 11 Jun 2024 | MH5-2 |  | Base slab casting in progress
Tue (11/06) | 11 Jun 2024 | MH5-1 |  | Rebar works for base slab
Tue (11/06) | 11 Jun 2024 | Zone 1 |  | Boring rig and crane shifted to P3-P4 area
Tue (11/06) | 11 Jun 2024 | MH3-8 |  | Hacking existing drain for drain diversion
Tue (11/06) | 11 Jun 2024 | MH3-5 |  | Hoarding work in progress for MH3-5 work and footpath diversion
Tue (11/06) | 11 Jun 2024 | BRP23 |  | Excavation for guidewall. BRP19: formwork closing on going. Today to cast
Tue (11/06) | 11 Jun 2024 | P11-1 |  | Kentledge completed today 6pm. Now hydraulic shifting to P14 for another kentledge test. HSL working till 10pm
Tue (11/06) | 11 Jun 2024 | Zone 1 |  | No more activity
Tue (11/06) | 11 Jun 2024 | ST255 |  | 3rd bite trenching, depth at 25m/34.5m. Teeth changing in progress
Tue (11/06) | 11 Jun 2024 | ST005 |  | 1st bite trenching in progress, 6m/34.2m
Tue (11/06) | 11 Jun 2024 | BRP21 |  | Rebar cage installation in progress. 2/2 cages
Wed (12/06) | 12 Jun 2024 | BP49-9 |  | Casting completed, 46.5m3
Wed (12/06) | 12 Jun 2024 | P49-9 |  | Boring in progress, reached 25m depth
Wed (12/06) | 12 Jun 2024 | ST255 |  | Rebar cage inspection ongoing, 3/8nos. Today will deliver balance 5nos. ST005: B1 in progress
Wed (12/06) | 12 Jun 2024 | Zone 3 |  | Ley Choon continue backfilling works towards substation
Wed (12/06) | 12 Jun 2024 | N5 crosshead |  | 1 side of wing-form Formwork installed and secured
Wed (12/06) | 12 Jun 2024 | P15 |  | Pile head hacking works in progress
Wed (12/06) | 12 Jun 2024 | P14 |  | Steel frames laying for next kentledge test
Wed (12/06) | 12 Jun 2024 | P13 |  | Struts welding works in progress
Wed (12/06) | 12 Jun 2024 | P12 |  | Tie rod installation ongoing
Wed (12/06) | 12 Jun 2024 | P11 |  | Kentledge test completed. Now dismantling & unloading works
Wed (12/06) | 12 Jun 2024 | P10 |  | Preboring works for ERSS ongoing
Wed (12/06) | 12 Jun 2024 | P9 |  | Premix hacking for PDA test preparation
Wed (12/06) | 12 Jun 2024 | Column P8-2 |  | Working platform installation. Today to cast
Wed (12/06) | 12 Jun 2024 | Zone 3 side |  | Hacking of rigid pavement for pipe sleeve installation
Wed (12/06) | 12 Jun 2024 | Zone 3 side |  | 1st point of JGP grouting in progress
Wed (12/06) | 12 Jun 2024 | P42 |  | Trial trench for recharge well, RW110
Wed (12/06) | 12 Jun 2024 | ST113 |  | Rebar cage lowering started
Wed (12/06) | 12 Jun 2024 | MH5-2 |  | Base wall rebar works
Wed (12/06) | 12 Jun 2024 | MH5-1 |  | Pipe joint works
Wed (12/06) | 12 Jun 2024 | Zone 1 |  | P4 preparation for spiking in the afternoon
Wed (12/06) | 12 Jun 2024 | Zone 1 |  | HSL materials shifting works
Wed (12/06) | 12 Jun 2024 | ST005 |  | 1st bite trenching continue, 16m/34.2m
Wed (12/06) | 12 Jun 2024 | ST255 |  | 3rd bite trenching completed
Wed (12/06) | 12 Jun 2024 | BRP27 - BC4 |  | Trenching on going, depth at 20m/36.66m
Wed (12/06) | 12 Jun 2024 | BRP21 |  | Tremie pipe installation for casting
Wed (12/06) | 12 Jun 2024 | P49-9 |  | Boring in progress, reached 31m
Wed (12/06) | 12 Jun 2024 | P48 |  | Set up rig for JGP
Wed (12/06) | 12 Jun 2024 | ST83 |  | End plate welding works for trimming
Wed (12/06) | 12 Jun 2024 | ST113 |  | Trimming continue to loosen water stop
Wed (12/06) | 12 Jun 2024 | Zone 3 HSL |  | BP2A-1(25) boring current depth, 8/44.45m
Wed (12/06) | 12 Jun 2024 | Zone 3 ECM pond 2 |  | Clearing silt before dismantling pipes and hacking works
Wed (12/06) | 12 Jun 2024 | ST83 | BC1 | B2 trimming temporarily stopped. Cutter teeth changing ongoing
Wed (12/06) | 12 Jun 2024 | BC2 |  | Maintenance works ongoing
Wed (12/06) | 12 Jun 2024 | S4 |  | KTC preparing for backfilling works
Wed (12/06) | 12 Jun 2024 | MH5-1 |  | Continue pipe joint works
Wed (12/06) | 12 Jun 2024 | P4 |  | SPPG on site for cable spiking
Wed (12/06) | 12 Jun 2024 | ST113 |  | Desanding completed. Rig 3 will move to ST115
Wed (12/06) | 12 Jun 2024 | DR1 |  | Dongah hacking works ongoing between ST173 and ST172 for Starhub diversion
Wed (12/06) | 12 Jun 2024 | P4 |  | Cable spiking completed
Wed (12/06) | 12 Jun 2024 | BRP33 |  | Hacking ongoing for guidewall trial trench
Wed (12/06) | 12 Jun 2024 | Zone 3 |  | Netting installation ongoing along diverted walkway barricades
Wed (12/06) | 12 Jun 2024 | BRP23 |  | Guidewall had been inspected. Pending to cast
Wed (12/06) | 12 Jun 2024 | Zone 3 |  | Dongah ground levelling ongoing along vehicle access. BRP27 B1 excavation ongoing
Wed (12/06) | 12 Jun 2024 | Zone 1 |  | HSL continue materials shifting works
Wed (12/06) | 12 Jun 2024 | MH5-2 |  | Base slab wall rebar works
Wed (12/06) | 12 Jun 2024 | P8-2 |  | Column casting in progress
Wed (12/06) | 12 Jun 2024 | Zone 3 |  | TDP18 hacking ongoing for trial trench works
Wed (12/06) | 12 Jun 2024 | P12 |  | Formwork closing for 1st stage column. Target to cast tmr
Wed (12/06) | 12 Jun 2024 | P10 |  | Continue preboring for ERSS installation
Wed (12/06) | 12 Jun 2024 | P13 |  | Continue struts welding works. Today to cast concrete packing
Wed (12/06) | 12 Jun 2024 | P14 Kentledge |  | Steel frames & main beams installation completed. Now installation of cross beams
Wed (12/06) | 12 Jun 2024 | P15 |  | Continue Pile head hacking works
Wed (12/06) | 12 Jun 2024 | N5 crosshead |  | Both sides of wing-form formwork installed and secured
Wed (12/06) | 12 Jun 2024 | Zone 3 side |  | 2nd point pre cutting
Wed (12/06) | 12 Jun 2024 | ST113 |  | Waterstop end plate lowering. ST115- 1st bite excavation started
Wed (12/06) | 12 Jun 2024 | BC cutter 2 |  | Changing hoses
Wed (12/06) | 12 Jun 2024 | ST005 |  | Trenching temporarily stopped due to mud bin full. Current depth at 16m
Wed (12/06) | 12 Jun 2024 | ST255 |  | End plate extraction in progress
Wed (12/06) | 12 Jun 2024 | BRP21 |  | Casting in progress
Wed (12/06) | 12 Jun 2024 | N5 |  | Continue erection of wing formwork
Wed (12/06) | 12 Jun 2024 | P15 |  | Pile head hacking
Wed (12/06) | 12 Jun 2024 | P14 |  | Current status of beam set up for tesing
Wed (12/06) | 12 Jun 2024 | P12 |  | Formwork closing done
Wed (12/06) | 12 Jun 2024 | P8-2 |  | Casting in progress, total 42.5m3
Wed (12/06) | 12 Jun 2024 | MH5-2 |  | Base slab rebar work. Tonight to cast
Wed (12/06) | 12 Jun 2024 | P15 |  | No more activity
Wed (12/06) | 12 Jun 2024 | P13 |  | Railing installation to start excavation till FEL tomorrow
Wed (12/06) | 12 Jun 2024 | P12 |  | 1st layer concrete plug casting
Wed (12/06) | 12 Jun 2024 | P8-2 |  | Casting completed
Wed (12/06) | 12 Jun 2024 | ST255 |  | Preparation for end plate + waterstop installation
Wed (12/06) | 12 Jun 2024 | ST005 |  | 1st bite trenching in progress, 20m/34.2m
Wed (12/06) | 12 Jun 2024 | BRP27 - BC4 |  | Trenching ongoing, depth at 30 m/36.66 m. Desander cyclone leaking; repair work in progress
Wed (12/06) | 12 Jun 2024 | ST83 - BC1 |  | Current 2nd bite trimming continue
Wed (12/06) | 12 Jun 2024 | BC2 |  | Repair works. Hydraulic oil top up
Wed (12/06) | 12 Jun 2024 | ST113 |  | Water stop installed. Prepreparation for cage lowering. Total 8 cages
Wed (12/06) | 12 Jun 2024 | ST115 - BC3 |  | 1st bite trenching in progress. Current depth at 11m/39m. Temporary stopped due to mud pump hose leaking. Repair works in progress
Thu (13/06) | 13 Jun 2024 | BRP27 |  | B1 in progress, 35/36.66m
Thu (13/06) | 13 Jun 2024 | Zone 3 ECM pond |  | 2/4nos demolished
Thu (13/06) | 13 Jun 2024 | BC2 |  | Maintenance ongoing
Thu (13/06) | 13 Jun 2024 | Zone 4 |  | JGP works no more activity
Thu (13/06) | 13 Jun 2024 | N5 Crosshead |  | Formwork installation works in progress
Thu (13/06) | 13 Jun 2024 | P15 |  | HSL pile head hacking works
Thu (13/06) | 13 Jun 2024 | P14 |  | Kentledge set up in progress. Secondary beams installed
Thu (13/06) | 13 Jun 2024 | Zone 4 drain diversion |  | Hacking of existing footpath ongoing
Thu (13/06) | 13 Jun 2024 | P44 |  | WH continue trial trench works
Thu (13/06) | 13 Jun 2024 | ST113 |  | Rebar cage installation in progress, 6/8nos, ST115: B1 resumed, 13.5/39m
Thu (13/06) | 13 Jun 2024 | P12 |  | Working platform installation works. Today to cast 1st stage column
Thu (13/06) | 13 Jun 2024 | P13 |  | Stiffener plates welding in progress. Afternoon to complete then MPI test inspection
Thu (13/06) | 13 Jun 2024 | MH5-2 |  | Pipe joint works
Thu (13/06) | 13 Jun 2024 | ST83 |  | Trimming ongoing
Thu (13/06) | 13 Jun 2024 | S4 |  | KTC removing hardcores before continue backfilling works
Thu (13/06) | 13 Jun 2024 | MH5-1 |  | Wall Rebar works in progress
Thu (13/06) | 13 Jun 2024 | ST005 |  | 2nd bite reached 20m, rock level
Thu (13/06) | 13 Jun 2024 | ST255 |  | Endplate + waterstop fully lowered
Thu (13/06) | 13 Jun 2024 | BRP27 - BC4 |  | Trenching continue, depth at 33m/36.66m
Thu (13/06) | 13 Jun 2024 | ST83-BC1 |  | Cutter wheel teeth replacement
Thu (13/06) | 13 Jun 2024 | ST113 |  | Rebar cage installation continue. 3/8 cages installed
Thu (13/06) | 13 Jun 2024 | ST255 |  | Rebar cage installation in progress, 4/8nos
Thu (13/06) | 13 Jun 2024 | ST005 |  | B1 CD 29.5/34.2m
Thu (13/06) | 13 Jun 2024 | BRP27 |  | B1 excavation completed. Now preparing for cleaning
Thu (13/06) | 13 Jun 2024 | ST113 |  | 4th rebar cages lapping in progress
Thu (13/06) | 13 Jun 2024 | BRP33 |  | Guidewall trial trench
Thu (13/06) | 13 Jun 2024 | Between ST172 & ST173 |  | Starhub pipes exposed for diversion
Thu (13/06) | 13 Jun 2024 | ST113 |  | Hanging bar installation ongoing
Thu (13/06) | 13 Jun 2024 | Zone 4 GCE |  | Hardcore removal for JGP trial trench
Thu (13/06) | 13 Jun 2024 | Zone 4 JGP |  | Point B-477 completed. Now preparing for next point, B-472
Thu (13/06) | 13 Jun 2024 | Zone 4 HSL |  | BP50-7 preboring in progress
Thu (13/06) | 13 Jun 2024 | N5 Crosshead |  | Current status for Formwork installation
Thu (13/06) | 13 Jun 2024 | P15 |  | HSL pile head hacking works. Balance 1 more
Thu (13/06) | 13 Jun 2024 | P14 |  | Kentledge set up in progress. Steel plates laying works ongoing
Thu (13/06) | 13 Jun 2024 | P12 |  | Continue Working platform installation works
Thu (13/06) | 13 Jun 2024 | P13 |  | MPI tests done for waler beams & struts. Next KTC will excavation to FEL
Thu (13/06) | 13 Jun 2024 | P9-2 |  | Column Formwork removal works
Thu (13/06) | 13 Jun 2024 | MH5-2 |  | Continue pipe joint works
Thu (13/06) | 13 Jun 2024 | ST115 |  | B1 in progress, 15/39m
Thu (13/06) | 13 Jun 2024 | ST83 |  | Trimming temporarily stopped again. Oil leaking. Now ongoing rectification
Thu (13/06) | 13 Jun 2024 | DR2 |  | Bundwall installation along barricades
Thu (13/06) | 13 Jun 2024 | Zone 1 |  | HSL materials unloading works
Thu (13/06) | 13 Jun 2024 | P4 |  | Continue backfilling works
Thu (13/06) | 13 Jun 2024 | BC2 |  | Continue maintenance works
Thu (13/06) | 13 Jun 2024 | BRP21 |  | LSS backfilling
Thu (13/06) | 13 Jun 2024 | Exit 3 |  | Platform levelling ongoing
Thu (13/06) | 13 Jun 2024 | S4 |  | Backfilling and compaction works
Thu (13/06) | 13 Jun 2024 | MH5-1 |  | Wall rebar installation works
Thu (13/06) | 13 Jun 2024 | ST115 - BC3 |  | 1st bite trenching in resumed. Current depth at 11m/39m
Thu (13/06) | 13 Jun 2024 | ST255 |  | Rebar cage lowering in progress, 3/8 cages
Thu (13/06) | 13 Jun 2024 | BRP27 - BC4 |  | Trenching continue, depth at 34.4m/36.66m
Thu (13/06) | 13 Jun 2024 | ST005 |  | 1st bite trenching in progress, 30.7m/34.2m
Thu (13/06) | 13 Jun 2024 | ST255 |  | Rebar cage installation, 7/8 in progress
Thu (13/06) | 13 Jun 2024 | P15 |  | Balance 1 pile head manual hacking. To complete tomorrow
Thu (13/06) | 13 Jun 2024 | P12 |  | Column stump casting in progress
Thu (13/06) | 13 Jun 2024 | P12 |  | Column stump casting completed
Thu (13/06) | 13 Jun 2024 | BRP27 - BC4 |  | Trimming in progress
Thu (13/06) | 13 Jun 2024 | ST255 |  | Rebar cage lapping ongoing, 3/8nos
Thu (13/06) | 13 Jun 2024 | Zone 3 water pipe |  | Preparing for 300mm water pipe pressure test (10 bars at 30min standby) scheduled at 10am. Now at 9 bars, waiting for PUB officer
Thu (13/06) | 13 Jun 2024 | Zone 3 |  | WH preparing for next trial trench, TDP21
Thu (13/06) | 13 Jun 2024 | TDP18 |  | Trial trench was done yesterday. Found LT and EHT. Pending utility team confirmation
Thu (13/06) | 13 Jun 2024 | BP2A-1 | 25 | Boring resume from 13m/44.4m depth
Thu (13/06) | 13 Jun 2024 | ST83 - BC1 |  | Current 2nd bite trimming continue
Thu (13/06) | 13 Jun 2024 | BC2 |  | Cutter head body hydraulic hose replacement and oil top up
Thu (13/06) | 13 Jun 2024 | ST113 |  | Casting in progress, running volume 54 m3. Est volume 270 m3
Thu (13/06) | 13 Jun 2024 | ST115 - BC3 |  | 1st bite trenching, current depth at 16.8m/39m. Teeth changing in progress
Fri (14/06) | 14 Jun 2024 | N5 |  | Current status for Crosshead formwork installation
Fri (14/06) | 14 Jun 2024 | P13 |  | Excavtion to FEL in progress
Fri (14/06) | 14 Jun 2024 | P10 |  | LE continue preboring works for ERSS. Target to complete preboring tmr
Fri (14/06) | 14 Jun 2024 | N5 |  | Crosshead formwork assembly
Fri (14/06) | 14 Jun 2024 | P15 |  | Balance pile head manual hacking. Target to complete today
Fri (14/06) | 14 Jun 2024 | P14 |  | Kentledge setup
Fri (14/06) | 14 Jun 2024 | P11-1 |  | Mobile crane set up for steel plate unloading
Fri (14/06) | 14 Jun 2024 | MH5-2 |  | Pipe connection to perm sewer prior to shaft construction
Fri (14/06) | 14 Jun 2024 | P3 |  | Trial trench for BP ongoing
Fri (14/06) | 14 Jun 2024 | MH3-5 |  | Abandoned drain removal
Fri (14/06) | 14 Jun 2024 | Zone 3 side |  | 1st point JGP boring in progress
Fri (14/06) | 14 Jun 2024 | ST005 |  | 1st bite trenching continue. 31.3m/34.2m
Fri (14/06) | 14 Jun 2024 | ST255ST255 |  | All rebar cages installed. Platform preparation and Tremie pipe installation
Fri (14/06) | 14 Jun 2024 | BRP27 - BC4 |  | Trimming completed
Fri (14/06) | 14 Jun 2024 | ST83 - BC1 |  | Current 2nd bite trimming continue. Cutter teeth replacement
Fri (14/06) | 14 Jun 2024 | ST113 |  | Casting in progress, running volume 283 m3. Last 2 loads
Fri (14/06) | 14 Jun 2024 | ST115 - BC3 |  | 1st bite trenching, current depth at 18.8m/39m. Teeth changing in progress
Fri (14/06) | 14 Jun 2024 | DTP21 |  | Removing abandoned drain for TT
Fri (14/06) | 14 Jun 2024 | BP2A-1 | 25 | Boring in progress, reached 28m
Fri (14/06) | 14 Jun 2024 | TT18 |  | Checking pipe inside whether still have cables
Fri (14/06) | 14 Jun 2024 | Stn-005 |  | 1st bite trenching in progress, current depth 32m
Fri (14/06) | 14 Jun 2024 | BC2 |  | Repair works continue
Fri (14/06) | 14 Jun 2024 | ST83-BC1 |  | Trimming resumed
Fri (14/06) | 14 Jun 2024 | N5 |  | Continue crosshead formwork assembly
Fri (14/06) | 14 Jun 2024 | P15 |  | Pile head hacking completed. Hardcores removal in progress
Fri (14/06) | 14 Jun 2024 | P14 |  | Steel plate laying for kentledge test
Fri (14/06) | 14 Jun 2024 | ST115 |  | 1st bite in progress, reached 28.5m
Fri (14/06) | 14 Jun 2024 | Zone 3 side |  | Continue removal of hardcore and premix for TT
Fri (14/06) | 14 Jun 2024 | Zone 3 side |  | 2nd point JGP boring in progress
Fri (14/06) | 14 Jun 2024 | P48 |  | Pipe sleeves installation. 5nos done as of now
Fri (14/06) | 14 Jun 2024 | P47-P48 |  | Premoval of premix for JGP work
Fri (14/06) | 14 Jun 2024 | P13 |  | KTC excavation to FEL
Fri (14/06) | 14 Jun 2024 | P11 |  | HSL kentledge unloading works
Fri (14/06) | 14 Jun 2024 | P10 |  | LE continue ERSS preboring works
Fri (14/06) | 14 Jun 2024 | MH5-2 |  | Wall Rebar installation in progress
Fri (14/06) | 14 Jun 2024 | MH5-1 |  | Wall Rebar installation in progress
Fri (14/06) | 14 Jun 2024 | S4 |  | Backfilling works in progress
Fri (14/06) | 14 Jun 2024 | Zone 1 |  | P3 trial trench works
Fri (14/06) | 14 Jun 2024 | P50-7 |  | Continue boring. Target casting tomorrow
Fri (14/06) | 14 Jun 2024 | ST255 |  | Casting in progress
Fri (14/06) | 14 Jun 2024 | BRP27 |  | Desanding in progress
Fri (14/06) | 14 Jun 2024 | P14-1 |  | Current status of steel plates loading for Kentledge test. 66/482 nos
Fri (14/06) | 14 Jun 2024 | P9-2 |  | Tie rods hole path up
Fri (14/06) | 14 Jun 2024 | MH5-1 |  | Manhole wall rebar work
Fri (14/06) | 14 Jun 2024 | MH5-2 |  | Manhole wall rebar work in progress
Fri (14/06) | 14 Jun 2024 | P15 |  | Rebar protection ongoing. No other activity
Fri (14/06) | 14 Jun 2024 | P14 |  | No more activity
Fri (14/06) | 14 Jun 2024 | P13 |  | Ongoing soil hacking and excavation works
Fri (14/06) | 14 Jun 2024 | Zone 1 |  | Backfilling ongoing by WH
Fri (14/06) | 14 Jun 2024 | ST005 |  | B1 in progress, 33.9/34.2m
Fri (14/06) | 14 Jun 2024 | Zone 3 HSL |  | Activity done for the day
Fri (14/06) | 14 Jun 2024 | Zone 3 |  | TDP-21 trial trench in progress for deck post
Fri (14/06) | 14 Jun 2024 | BRP27 |  | Rebar cage was extracted due to insufficient toe cleaning. Now machine preparation ongoing for cleaning and desanding. Steel plate levelling ongoing around the area
Fri (14/06) | 14 Jun 2024 | BP2A-2 | 25 | Boring continue. Current depth 26m/44.5m
Fri (14/06) | 14 Jun 2024 | ST255 |  | Casting in progress. Balance 1 more lorry
Fri (14/06) | 14 Jun 2024 | ST005 |  | Current depth at 31.8m
Fri (14/06) | 14 Jun 2024 | Zone 3 |  | Krishco pressure testing to 10bars ongoing
Fri (14/06) | 14 Jun 2024 | ST83 | BC1 | Cutter teeth changing ongoing. B2 CD 25.3/29.1M
Fri (14/06) | 14 Jun 2024 | BC2 |  | Continue hydraulic hose replacement
Fri (14/06) | 14 Jun 2024 | ST115 |  | Cutter teeth changing ongoing. B1 CD 30.9/39m
Fri (14/06) | 14 Jun 2024 | Zone 4 |  | No more activity
Sat (15/06) | 15 Jun 2024 | P14 |  | Continue loading steel plate for testing
Sat (15/06) | 15 Jun 2024 | P13 |  | Continue excavation to FEL
Sat (15/06) | 15 Jun 2024 | P11 |  | Unloading of steel plates
Sat (15/06) | 15 Jun 2024 | P10 |  | Continue preboring for ERSS installation
Sat (15/06) | 15 Jun 2024 | P11-2 |  | Soil backfilling at completed column
Sat (15/06) | 15 Jun 2024 | P8-2 |  | Preparing for formwork removal
Sat (15/06) | 15 Jun 2024 | MH5-2 |  | Manhole wall rebar work
Sat (15/06) | 15 Jun 2024 | MH5-1 |  | Preparation to continue wall rebar work
Sat (15/06) | 15 Jun 2024 | Zone 1 |  | Clearing cables from spiking done
Sat (15/06) | 15 Jun 2024 | Zone 1 P3 |  | Afternoon plan for LSS backfilling
Sat (15/06) | 15 Jun 2024 | ST115 |  | 1st bite reached 36.8m
Sat (15/06) | 15 Jun 2024 | BC cutter 2 |  | Continue replacing hoses
Sat (15/06) | 15 Jun 2024 | BRP24 |  | Excavation in progress, reached 8.5m
Sat (15/06) | 15 Jun 2024 | TDP-21 |  | Casing installation almost completed. Hydraulic hose leaking now waiting for mechanic
Sat (15/06) | 15 Jun 2024 | ST005 |  | Now cutter maintenance
Sat (15/06) | 15 Jun 2024 | N5 |  | Status of N5 wing form
Sat (15/06) | 15 Jun 2024 | P15 |  | Plastic protection provided for pile head for lean concrete
Sat (15/06) | 15 Jun 2024 | P8-2 |  | Preparing for formwork removal
Sat (15/06) | 15 Jun 2024 | P13 |  | Excavation to FEL. Hacking of pile head
Sat (15/06) | 15 Jun 2024 | MH5-1 |  | Formwork closing in progress for manhole formwork
Sat (15/06) | 15 Jun 2024 | MH5-2 |  | Wall rebar work in progress
Sat (15/06) | 15 Jun 2024 | ST005 |  | B1 completed. Now ongoing B2, CD 28.6/34.2m
Sat (15/06) | 15 Jun 2024 | P50-7 |  | Pile toe confirm. Prepare for casting
Sat (15/06) | 15 Jun 2024 | ST83 |  | Resume B2
Sat (15/06) | 15 Jun 2024 | BC2 |  | Continue maintenance works
Sat (15/06) | 15 Jun 2024 | ST115 |  | Continue B1 excavation
Sat (15/06) | 15 Jun 2024 | BRP27 |  | Hanging bar lapping ongoing. BC4 will resume trenching for BRP24
Sat (15/06) | 15 Jun 2024 | ST115 |  | 1st point boring done. Preparing for koden test
Sat (15/06) | 15 Jun 2024 | BRP24 |  | Cutter wheel maintenance
Sat (15/06) | 15 Jun 2024 | P15 |  | Lean con done
Sat (15/06) | 15 Jun 2024 | N5 |  | Rebar delivery
Sat (15/06) | 15 Jun 2024 | P13 |  | Continue excavation and pile hacking works till 10pm
Sat (15/06) | 15 Jun 2024 | ST005 |  | B2 in progress
Sat (15/06) | 15 Jun 2024 | BRP24 |  | B1 in progress, 15.6/29.57m. Additional noise balloon installation ongoing
Sat (15/06) | 15 Jun 2024 | ST83 |  | B2 excavation temporarily stopped for cutter teeth changing. CD 28/29.1m
Sat (15/06) | 15 Jun 2024 | BC2 |  | Now going to change gear box module
Sat (15/06) | 15 Jun 2024 | ST115 |  | B1 trimming ongoing
Sat (15/06) | 15 Jun 2024 | TDP-21 |  | Preparing for casing and boring. They will try to cast today
Sat (15/06) | 15 Jun 2024 | TT18 |  | Got one LT here to confirm whether still live or not. If this one confirm not live, from 13 to 18 can do the deck post
Sun (16/06) | 16 Jun 2024 | P8-2 |  | Preparing for formwork removal
Sun (16/06) | 16 Jun 2024 | MH5-2 |  | Shaft wall rebar work was done. Will start closing formwork after inspection clear
Sun (16/06) | 16 Jun 2024 | N5 |  | Wing formwork closing with the assistance of specialist
Sun (16/06) | 16 Jun 2024 | BC cutter 2 |  | Gear box replacing
Sun (16/06) | 16 Jun 2024 | P12 |  | Backfilling in progress to 1st layer waler
Sun (16/06) | 16 Jun 2024 | P13 |  | Pile head hacking and excavation to FEL
Sun (16/06) | 16 Jun 2024 | MH5-2 |  | Shaft wall formwork closing in progress
Sun (16/06) | 16 Jun 2024 | ST224 |  | Excavation done for guidewall rebar work
Sun (16/06) | 16 Jun 2024 | ST115 |  | B1 trimming completed. Now preparing for B2 excavation. Suction line setup ongoing
Sun (16/06) | 16 Jun 2024 | BC cutter 2 |  | Gear box replacement
Sun (16/06) | 16 Jun 2024 | ST224 |  | Excavation for guidewall
Sun (16/06) | 16 Jun 2024 | TDP13 |  | Excavation and exposing of Power duct for the deck post work
Sun (16/06) | 16 Jun 2024 | N5 |  | Unable to install side formwork for cross head yesterday. So, now supplier on site guiding Wendyng for installation
Sun (16/06) | 16 Jun 2024 | P12 |  | Backfilling to 1st layer waler for waler removal
Sun (16/06) | 16 Jun 2024 | P13 |  | Excavation to FEL in progress
Mon (17/06) | 17 Jun 2024 | Zone 3 |  | Bachy & HSL no activity
Mon (17/06) | 17 Jun 2024 | Zone 3 |  | Utility support area no activity
Mon (17/06) | 17 Jun 2024 | Zone 3 |  | Housekeeping, green netting installation, clearing of stagnant water along vehicular access and utility protection barricade making in progress
Mon (17/06) | 17 Jun 2024 | Zone 3 KTC |  | Vent shaft excavation & levelling works
Mon (17/06) | 17 Jun 2024 | ST-81 |  | 1st bite excavation ongoing, depth 8.5m
Mon (17/06) | 17 Jun 2024 | ST-83 |  | Water stop removal in progress
Mon (17/06) | 17 Jun 2024 | STN-115 |  | 2nd bite excavation in progress, current depth 14.8m
Mon (17/06) | 17 Jun 2024 | Zone 4 |  | No activity
Mon (17/06) | 17 Jun 2024 | MH3-5 |  | No activity
Mon (17/06) | 17 Jun 2024 | Zone 1 |  | Backfilling works for P3 in progress. To start BP tmr
Mon (17/06) | 17 Jun 2024 | S4 |  | No activity
Mon (17/06) | 17 Jun 2024 | MH5-1 |  | No activity
Mon (17/06) | 17 Jun 2024 | MH5-2 |  | No activity
Mon (17/06) | 17 Jun 2024 | P10 |  | No activity. Preboring completed, tmr to continue ERSS installation
Mon (17/06) | 17 Jun 2024 | P11 |  | Kentledge no activity
Mon (17/06) | 17 Jun 2024 | P12 |  | KTC backfilling and compaction works
Mon (17/06) | 17 Jun 2024 | P13 |  | KTC excavation to FEL ongoing
Mon (17/06) | 17 Jun 2024 | P14 |  | Kentledge no activity
Mon (17/06) | 17 Jun 2024 | P15 |  | No activity. Tmr to start pile cap rebar works
Mon (17/06) | 17 Jun 2024 | N5 |  | No activity
Mon (17/06) | 17 Jun 2024 | Zone 3 |  | Safety signages display & led lights installation works along human access way
Mon (17/06) | 17 Jun 2024 | Zone 3 |  | Continue housekeeping works and sludge cleaning works
Mon (17/06) | 17 Jun 2024 | Zone 3 Vent shaft |  | KTC continue excavation, soil disposal & levelling works
Mon (17/06) | 17 Jun 2024 | ST-83 |  | 1st bite cleaning & desnading works in progress, ST-81 temporary stopped for ST-83 works. Current depth for 1st bite is 17m
Mon (17/06) | 17 Jun 2024 | STN-115 |  | 2nd bite excavation in progress, current depth 16m
Mon (17/06) | 17 Jun 2024 | P13 |  | KTC continue excavation to FEL
Mon (17/06) | 17 Jun 2024 | P12 |  | KTC backfilling and compaction works completed. Tmr to do NDT
Mon (17/06) | 17 Jun 2024 | Zone 1 |  | Backfilling works for P3 completed. Work stopped for the day
Tue (18/06) | 18 Jun 2024 | P46 |  | Shifting of hardcore and tidy up the area
Tue (18/06) | 18 Jun 2024 | P48 |  | TT & Pipe sleeves for JGP
Tue (18/06) | 18 Jun 2024 | Zone 4 |  | 1st point JGP boring done
Tue (18/06) | 18 Jun 2024 | P49-6 |  | Preparing to resume boring work
Tue (18/06) | 18 Jun 2024 | MH3-5 |  | Road premix removal for TT. Today Ryobi G will install instrument at Nidec boundary wall
Tue (18/06) | 18 Jun 2024 | P44 |  | Exposing traffic light and lamp post pipe for diversion out off P44 footing area
Tue (18/06) | 18 Jun 2024 | ST115 |  | 2nd bite in progress, reached 23.3m
Tue (18/06) | 18 Jun 2024 | ST115 |  | Trenching resume
Tue (18/06) | 18 Jun 2024 | ST83 |  | Tremie pipes lowering for casting. Est volume 220m3
Tue (18/06) | 18 Jun 2024 | ST81 |  | 1st bite in progress, reached 21.2m
Tue (18/06) | 18 Jun 2024 | BRP28 |  | Pre excavation done. Preparing to start excavation
Tue (18/06) | 18 Jun 2024 | BC cutter 2 |  | Mechanic checking on the pressure pump
Tue (18/06) | 18 Jun 2024 | BRP28 |  | Trenching, current depth 18/31.87m
Tue (18/06) | 18 Jun 2024 | Zone 4 |  | Telstra pipe laying in progress, 18m length
Tue (18/06) | 18 Jun 2024 | N5 |  | Working platform installation in progress
Tue (18/06) | 18 Jun 2024 | P16 |  | Hacking of concrete slab in progress for ERSS works
Tue (18/06) | 18 Jun 2024 | N4 |  | Preparation for falsework installation
Tue (18/06) | 18 Jun 2024 | P15 |  | Pile cap rebar installation works
Tue (18/06) | 18 Jun 2024 | P49-6 |  | Boring in progress, reached 22m
Tue (18/06) | 18 Jun 2024 | P48 |  | Setting out for bored pile location to confirm whether affected by existing services
Tue (18/06) | 18 Jun 2024 | P45 |  | Laying of hardcore and prepare platform for bored pile work
Tue (18/06) | 18 Jun 2024 | Zone 4 |  | JGP grouting in progress. 2nos done as of now
Tue (18/06) | 18 Jun 2024 | P14 |  | Kentledge test setting up (Steel plate laying) in progress
Tue (18/06) | 18 Jun 2024 | P13 |  | KTC excavation to FEL
Tue (18/06) | 18 Jun 2024 | P12 |  | KTC continue backfilling works for pile cap
Tue (18/06) | 18 Jun 2024 | P11 |  | Unloading of Steel plates
Tue (18/06) | 18 Jun 2024 | ST115 |  | 2nd bite in progress, reached 26.4m
Tue (18/06) | 18 Jun 2024 | ST81 |  | Preparing for cutter wheel maintenance
Tue (18/06) | 18 Jun 2024 | P10 |  | LE ERSS installation works
Tue (18/06) | 18 Jun 2024 | MH5-2 |  | Formwork closing in progress for 1st lift RC wall with ring beam. Today to cast and also pipe haunching
Tue (18/06) | 18 Jun 2024 | MH5-1 |  | Wall rebar installation works
Tue (18/06) | 18 Jun 2024 | Zone 1 |  | Premix hacking for P2 ERSS trial trench works. LE also mobilized their mini excavator for trial trench
Tue (18/06) | 18 Jun 2024 | MH5-2 |  | Today plan to cast 1st layer of wall
Tue (18/06) | 18 Jun 2024 | P8-2 |  | Continue formwork removal
Tue (18/06) | 18 Jun 2024 | P11 |  | Continue unloading of steel plates
Tue (18/06) | 18 Jun 2024 | P12 |  | Tie rod holes patch up done. Backfilling by KTC on going
Tue (18/06) | 18 Jun 2024 | P13 |  | Continue excavation to FEL. Tomorrow to complete
Tue (18/06) | 18 Jun 2024 | P14 |  | Continue loading of steel plates for kentledge WLT
Tue (18/06) | 18 Jun 2024 | ST254 |  | 1st bite reached 17.5m
Tue (18/06) | 18 Jun 2024 | BP2A-1 | 25 | Boring in progress, 34.5m
Tue (18/06) | 18 Jun 2024 | TDP-15 |  | Current status of TT. Utility team to confirm on the abandoned services
Tue (18/06) | 18 Jun 2024 | TDP-20 |  | Casing installation. TDP-21: casting in progress
Tue (18/06) | 18 Jun 2024 | BC cutter 2 |  | Checking on electrical for lowering down/ up the cutter
Tue (18/06) | 18 Jun 2024 | BRP24 |  | LSS backfilling
Tue (18/06) | 18 Jun 2024 | BRP28 |  | Excavation in progress, reached 11m
Tue (18/06) | 18 Jun 2024 | BRP33 |  | TT on going for guidewall work
Tue (18/06) | 18 Jun 2024 | ST005 |  | Trimming and cleaning in progress, preparation for end plate extraction
Tue (18/06) | 18 Jun 2024 | STN254 |  | To continue trenching tonight, current depth 17.5m
Tue (18/06) | 18 Jun 2024 | N5 crosshead |  | Scaffold access erection in progress. Work till 10pm
Tue (18/06) | 18 Jun 2024 | P15 |  | Pile cap bottom bars (3 layers) and distribution bars laying completed. Work stopped for the day
Tue (18/06) | 18 Jun 2024 | P13 |  | Excavation to FEL until 10pm. Tomorrow to complete and start pile head hacking
Tue (18/06) | 18 Jun 2024 | P12 |  | Backfilling to pile head level completed. Tomorrow NDT and concrete plug casting
Tue (18/06) | 18 Jun 2024 | MH5-2 |  | Ring beam cast
Tue (18/06) | 18 Jun 2024 | Zone 1 |  | No activity
Tue (18/06) | 18 Jun 2024 | BRP28 |  | Trenching, current depth 13/31.87m. Soil removal at cutter teeth
Tue (18/06) | 18 Jun 2024 | ST81-BC1 |  | 1st bite trenching, current depth 23/33.5m. Cutter body flap hydraulic hose replacement
Tue (18/06) | 18 Jun 2024 | ST115 |  | Teeth changing, current 26.5/39m
Wed (19/06) | 19 Jun 2024 | Zone 4 |  | No more activity. P49-6 casting completed
Wed (19/06) | 19 Jun 2024 | ST115-BC3 |  | 2nd bite trenching, current 37/39m. Teeth changing
Wed (19/06) | 19 Jun 2024 | ST81-BC1 |  | 1st bite trenching resume, current depth 26m/33.5m. Teeth changing
Wed (19/06) | 19 Jun 2024 | BRP28 |  | Trenching, current depth 29/31.87m
Wed (19/06) | 19 Jun 2024 | BRP12-BC2 |  | Bentonite hose connection and preparation for trenching
Wed (19/06) | 19 Jun 2024 | STN005 |  | Cleaning completed. Preparation for desanding
Wed (19/06) | 19 Jun 2024 | STN254 |  | Flap welding in progress
Wed (19/06) | 19 Jun 2024 | BRP28 |  | Trenching, current depth 22/31.87m
Wed (19/06) | 19 Jun 2024 | ST83 |  | Casting started. Est volume 230 m3
Wed (19/06) | 19 Jun 2024 | Zone 4 |  | 2 nos of JGP grouting done. Preparing for 3rd point boring
Wed (19/06) | 19 Jun 2024 | P49-6 |  | Toe level confirmed. Preparing for rebar cages lowering. Today to cast
Wed (19/06) | 19 Jun 2024 | N5 |  | Working platform installation in progress
Wed (19/06) | 19 Jun 2024 | N4 |  | Falsework - Secondary beams installation ongoing
Wed (19/06) | 19 Jun 2024 | ST81-BC1 |  | 1st bite trenching resume, current depth 25.1/33.5m
Wed (19/06) | 19 Jun 2024 | P15 pilecap |  | Rebar & Formwork installation works
Wed (19/06) | 19 Jun 2024 | P14 |  | Kentledge steel plate stacking ongoing
Wed (19/06) | 19 Jun 2024 | P13 |  | KTC excavation to FEL. Target to complete today
Wed (19/06) | 19 Jun 2024 | P12 |  | Concrete plug casting completed
Wed (19/06) | 19 Jun 2024 | P11 |  | Unloading of steel plates in progress
Wed (19/06) | 19 Jun 2024 | P10 |  | LE ERSS installation in progress
Wed (19/06) | 19 Jun 2024 | BRP28 |  | Current excavation depth 27.6/31.87m
Wed (19/06) | 19 Jun 2024 | MH5-1 |  | Formwork closing for 1 layer wall. Today to cast
Wed (19/06) | 19 Jun 2024 | MH5-2 |  | Wall Rebar installation for 1st layer wall
Wed (19/06) | 19 Jun 2024 | ST81-Rig 1 |  | B1 CD 25.6/33.5m
Wed (19/06) | 19 Jun 2024 | ST115-Rig 3 |  | B2 CD 36.2/39m
Wed (19/06) | 19 Jun 2024 | Zone 1 |  | P2 trial trench for ERSS installation ongoing
Wed (19/06) | 19 Jun 2024 | Zone 1 |  | P3-3 Boring works in progress. Casing installed, current depth 9m
Wed (19/06) | 19 Jun 2024 | ST83 |  | Casting continue, 180/230 m3
Wed (19/06) | 19 Jun 2024 | BRP28 |  | Trenching, current depth 23/31.87m
Wed (19/06) | 19 Jun 2024 | ST115 |  | 2nd bite trenching, current 33/39m
Wed (19/06) | 19 Jun 2024 | STN005 |  | Desanding in progress, STN254: 1st bite trenching, Current depth 29/46.9m
Wed (19/06) | 19 Jun 2024 | STN005 |  | Rebar cage installation. 6/8 cages
Wed (19/06) | 19 Jun 2024 | STN263 |  | 1st bite trenching, 4.8m/37.9m, Now Operator changed shift
Wed (19/06) | 19 Jun 2024 | STN254 |  | 2nd bite trenching, Current depth 30/35.7
Wed (19/06) | 19 Jun 2024 | P13 |  | Excavation to FEL until 10pm
Wed (19/06) | 19 Jun 2024 | MH5-2 |  | Perm structure wall 1st layer preparation for casting. Advise LCH to do housekeeping below the shaft
Wed (19/06) | 19 Jun 2024 | Zone 1 |  | P3-3 casing installed. Tomorrow to continue boring works
Thu (20/06) | 20 Jun 2024 | P14 |  | Kentledge set up. Hydraulic jack setting in progress
Thu (20/06) | 20 Jun 2024 | P11-1 |  | Unloading of steel plates
Thu (20/06) | 20 Jun 2024 | P13 |  | Excavation to FEL, levelling in progress. Today HSL to start pile head hacking
Thu (20/06) | 20 Jun 2024 | ST81 |  | B1 in progress, 26.5/33.5m
Thu (20/06) | 20 Jun 2024 | P10 |  | ERSS installation. Balance 3 SP and 5 LP
Thu (20/06) | 20 Jun 2024 | MH3-5 |  | Trial trench ongoing
Thu (20/06) | 20 Jun 2024 | MH5-1 |  | 1st layer wall formwork dismantling today and start 2nd layer rebar works
Thu (20/06) | 20 Jun 2024 | ST81 |  | Now repairing mud pump
Thu (20/06) | 20 Jun 2024 | ST172 |  | Pre excavation for excavation
Thu (20/06) | 20 Jun 2024 | Zone 4 GCE |  | JGP point B-176 in progress
Thu (20/06) | 20 Jun 2024 | Zone 4 |  | P50-8 preboring
Thu (20/06) | 20 Jun 2024 | ST115-Rig 3 |  | Excavation completed for all 3 bites
Thu (20/06) | 20 Jun 2024 | BRP23 |  | Excavation reached 7m
Thu (20/06) | 20 Jun 2024 | BRP12 |  | Excavation reached 27m
Thu (20/06) | 20 Jun 2024 | P3-3 |  | BP Boring works in progress. Today to cast
Thu (20/06) | 20 Jun 2024 | Zone 4 LA towards city |  | Telstra lane closure for pipe laying
Thu (20/06) | 20 Jun 2024 | Zone 4 |  | Netlink cable works ongoing
Thu (20/06) | 20 Jun 2024 | P49-6 |  | Preparing for LSS backfill
Thu (20/06) | 20 Jun 2024 | STN254 |  | 2nd bite trenching completed, depth 35.7/35.7
Thu (20/06) | 20 Jun 2024 | BRP12-BC2 |  | Excavation started, depth 10m. Trenching paused due to hydraulic issue
Thu (20/06) | 20 Jun 2024 | BRP28 |  | Cutter body hoist up to check manually check depth
Thu (20/06) | 20 Jun 2024 | ST81-BC1 |  | 1st bite trenching, current depth 26.2m/33.5m. Cutter body hoist up for Teeth changing
Thu (20/06) | 20 Jun 2024 | N5 |  | Preparation ongoing for crosshead rebar installation
Thu (20/06) | 20 Jun 2024 | N4 |  | Continue c-channel installation
Thu (20/06) | 20 Jun 2024 | P15 |  | Continue shearlinks and starter bar installation
Thu (20/06) | 20 Jun 2024 | P14 |  | Continue steel plate kentledge setup
Thu (20/06) | 20 Jun 2024 | P13 |  | Excavation to FEL completed
Thu (20/06) | 20 Jun 2024 | P11 |  | Unloading of kentledge steel plates
Thu (20/06) | 20 Jun 2024 | MH5-2 |  | Formwork dismantling
Thu (20/06) | 20 Jun 2024 | P3-3 |  | Boring completed. Now shifting boring machine to facilitate crane parking for rebar cage installation
Thu (20/06) | 20 Jun 2024 | BRP28 |  | Manual depth checked. Need to excavate another 300mm
Thu (20/06) | 20 Jun 2024 | ST263 |  | Excavation in progress, 28/37.9m
Thu (20/06) | 20 Jun 2024 | ST254 |  | Currently no activity. Still pending rebar cage delivery
Thu (20/06) | 20 Jun 2024 | TDP19 |  | Preboring
Thu (20/06) | 20 Jun 2024 | BRP33 |  | Guidewall cast
Thu (20/06) | 20 Jun 2024 | Zone 3 |  | All 4 ECM ponds have been demolished as of today
Thu (20/06) | 20 Jun 2024 | BRP12 |  | Excavation in progress, 15/38.17m
Thu (20/06) | 20 Jun 2024 | ST161 |  | Drain hacking ongoing for trial trench works
Thu (20/06) | 20 Jun 2024 | P38-39 |  | Ley Choon ongoing shoring installation and preparation for cable works (planned tmr)
Thu (20/06) | 20 Jun 2024 | ST81 |  | B1 resumed from 26.8/33.5m
Thu (20/06) | 20 Jun 2024 | ST115 |  | Trimming ongoing at waterstop side
Thu (20/06) | 20 Jun 2024 | MH3-5 |  | No activity
Thu (20/06) | 20 Jun 2024 | BP2A-1 | 25 | Rebar cage installation ongoing
Thu (20/06) | 20 Jun 2024 | STN005 |  | Casting in progress
Thu (20/06) | 20 Jun 2024 | ST263 |  | 1st bite, reached 31m
Thu (20/06) | 20 Jun 2024 | ST254 |  | Tonight will just do desanding. Not all rebar cages on site yet
Thu (20/06) | 20 Jun 2024 | N5 |  | Current status of rebar work
Thu (20/06) | 20 Jun 2024 | N5 |  | Access erection
Thu (20/06) | 20 Jun 2024 | N4 |  | Painting of access. Access erection done
Thu (20/06) | 20 Jun 2024 | P15 |  | Shear link installation and some welding work. Working until 10Pm
Thu (20/06) | 20 Jun 2024 | P14 |  | Welding of reference bar
Thu (20/06) | 20 Jun 2024 | P3-3 |  | Casting in progress, 48.5m3/ 56.5m3
Thu (20/06) | 20 Jun 2024 | ST005 |  | Casting in progress, 186/261m3
Thu (20/06) | 20 Jun 2024 | TDP111 |  | Trial trench ongoing, BP2A-1(25): Boring in progress, 44.2/44.45m
Thu (20/06) | 20 Jun 2024 | N5 |  | Preparation for crosshead rebar installation
Thu (20/06) | 20 Jun 2024 | Zone 3 |  | Krishco preparing for internal 200mm water pipe installation towards LVC
Thu (20/06) | 20 Jun 2024 | BRP12 |  | B1 in progres
Thu (20/06) | 20 Jun 2024 | BRP28 |  | Trimming ongoing
Thu (20/06) | 20 Jun 2024 | STN263 |  | Excavation CD 12/37.9m
Thu (20/06) | 20 Jun 2024 | ST115 |  | Trimming of waterstop end plate side for removal
Thu (20/06) | 20 Jun 2024 | BRP33 |  | Guidewall formwork installation ongoing. Today to cast
Thu (20/06) | 20 Jun 2024 | BRP35 |  | Guidewall excavation completed
Thu (20/06) | 20 Jun 2024 | P15 |  | Pile cap shearlinks installation
Thu (20/06) | 20 Jun 2024 | N4 |  | Crosshead falsework completed until secondary. Today to install c-channel and plywood laying
Fri (21/06) | 21 Jun 2024 | Zone 3 |  | Continue RW installation. Today plan RW94 and RW106
Fri (21/06) | 21 Jun 2024 | N5 crosshead |  | Rebar installation to continue today. Main bar in progress
Fri (21/06) | 21 Jun 2024 | P15 |  | Pile cap shearlinks installation. To cast tomorrow
Fri (21/06) | 21 Jun 2024 | P14 |  | Loading of steel plates for kentledge test
Fri (21/06) | 21 Jun 2024 | ST115 |  | Waterstop lowering
Fri (21/06) | 21 Jun 2024 | Between P38-39 |  | Ley Choon on site. Currently dewatering ongoing before resume works
Fri (21/06) | 21 Jun 2024 | ST81 |  | Excavation temporarily stopped for cutter wheel/teeth rectification
Fri (21/06) | 21 Jun 2024 | ST115 |  | Cleaning & desanding in progress
Fri (21/06) | 21 Jun 2024 | BC cutter No-1 |  | Gear Box changing
Fri (21/06) | 21 Jun 2024 | ST172 |  | Preparing to start excavation
Fri (21/06) | 21 Jun 2024 | P12 |  | Waler dismantling
Fri (21/06) | 21 Jun 2024 | BRP23 |  | Excavation reached 28m depth. Now cutter teeth changing
Fri (21/06) | 21 Jun 2024 | BRP12 |  | Cleaning in progress
Fri (21/06) | 21 Jun 2024 | P13 |  | Water pumping. Today to start pile head hacking
Fri (21/06) | 21 Jun 2024 | P11-1 |  | Unloading of steel plate
Fri (21/06) | 21 Jun 2024 | P10 |  | Excavation to W1 layer started
Fri (21/06) | 21 Jun 2024 | Zone 4 |  | Trial trench for BP work @ P45
Fri (21/06) | 21 Jun 2024 | Zone 4 |  | Hacking of premix for JGP @ P46-48
Fri (21/06) | 21 Jun 2024 | BRP38 |  | Trial trench for guidewall construction
Fri (21/06) | 21 Jun 2024 | BRP35 |  | Guidewall construction in progress
Fri (21/06) | 21 Jun 2024 | P32 |  | Slope backfilling and levelling ongoing
Fri (21/06) | 21 Jun 2024 | BRP23 |  | Excavation resumed from 18/30.8m
Fri (21/06) | 21 Jun 2024 | BRP12 |  | Cutter teeth changing ongoing
Fri (21/06) | 21 Jun 2024 | Zone 4 |  | Telstra lane closure continues for pipe laying towards city
Fri (21/06) | 21 Jun 2024 | MH5-2 |  | Water pumping. Backfilling to 1st layer today
Fri (21/06) | 21 Jun 2024 | MH5-1 |  | Backfilling to first layer also by today
Fri (21/06) | 21 Jun 2024 | P4-2 |  | Preboring in progress for casing installation
Fri (21/06) | 21 Jun 2024 | ST263 |  | 1st bite excavation, reached 35.5m. Now changing cutter teeth
Fri (21/06) | 21 Jun 2024 | ST254 |  | Preparing for desanding
Fri (21/06) | 21 Jun 2024 | BRP28 |  | Tremie pipe lowered down. Concrete ordered
Fri (21/06) | 21 Jun 2024 | ST161 |  | Trial trench ongoing
Fri (21/06) | 21 Jun 2024 | ST115 |  | Removal of waterstop end plate in progress
Fri (21/06) | 21 Jun 2024 | P4-2 BP |  | LSS backfilling
Fri (21/06) | 21 Jun 2024 | P3-3 |  | Casing installed. Prepreparation for boring
Fri (21/06) | 21 Jun 2024 | ST115 |  | Cleaning and desanding completed. Koden check ongoing. Rig 3 has shifted to DR1 area
Fri (21/06) | 21 Jun 2024 | ST81 |  | Gearbox rectification ongoing
Fri (21/06) | 21 Jun 2024 | Zone 3 |  | Hacking ongoing for trial trench, UKP35 and UKP36
Fri (21/06) | 21 Jun 2024 | BRP38 |  | Guidewall excavation ongoing
Fri (21/06) | 21 Jun 2024 | MH5-2 |  | 1st Layer backfilling in progress
Fri (21/06) | 21 Jun 2024 | S4 |  | LE vibro shifted here for ERSS extraction
Fri (21/06) | 21 Jun 2024 | MH5-1 |  | Backfilling of 1st layer in progress
Fri (21/06) | 21 Jun 2024 | ST258 |  | Excavation started
Fri (21/06) | 21 Jun 2024 | ST254 |  | WS endplate installation ongoing
Fri (21/06) | 21 Jun 2024 | ST263 |  | Excavation reached 36.5/37.9m
Fri (21/06) | 21 Jun 2024 | P10 |  | Excavation to W1 layer continue
Fri (21/06) | 21 Jun 2024 | P11-2 |  | Backfilling in progress
Fri (21/06) | 21 Jun 2024 | P11-1 |  | Dismantling of kentledge set up. Balance frame and primary beams
Fri (21/06) | 21 Jun 2024 | N4 |  | C-channel, plywood laying and barricade installation for crosshead falsework
Fri (21/06) | 21 Jun 2024 | N5 |  | Cutting of plywood along wingform screw jack to directly rest on secondary beams, QPS comment
Fri (21/06) | 21 Jun 2024 | Zone 4 |  | P58-8 rebar cage installation. Target to cast by 8pm
Fri (21/06) | 21 Jun 2024 | Zone 4 GI works |  | Grouting for 2nd point. This morning 2 nos drilling unable to continue due to hard strata
Fri (21/06) | 21 Jun 2024 | P44 GI works |  | Drilling for 2nd point
Fri (21/06) | 21 Jun 2024 | ST115 |  | Waterstop lowering
Fri (21/06) | 21 Jun 2024 | ST81-BC1 |  | Gear box repair works continue. Current at 1st bite 27.5m depth
Fri (21/06) | 21 Jun 2024 | BRP23 |  | Trenching in progress, depth 27.8m, BRP20: pre-excavation in progress
Fri (21/06) | 21 Jun 2024 | BRP12 |  | Internal Koden
Fri (21/06) | 21 Jun 2024 | TDP 19 |  | Casting completed, preparation to lower deck post
Fri (21/06) | 21 Jun 2024 | ST254 |  | Rebar cage lowering. 1/8 installed. Today only 2 cages delivered. Balance 6 cages will deliver tonight
Fri (21/06) | 21 Jun 2024 | ST258 |  | 1st bite trenching, depth 12m/36.2m
Fri (21/06) | 21 Jun 2024 | ST263 |  | Trenching in progress, 36.6m
Fri (21/06) | 21 Jun 2024 | ST263 |  | 1st bite in progress, 37m. Now changing cutter teeth
Fri (21/06) | 21 Jun 2024 | ST254 |  | Cage A (1/4) and Cage B (1/4) lowered down. Preparing to contine lower down. Left 2 more cages to delivered. Delivery will be tonight
Fri (21/06) | 21 Jun 2024 | N4 |  | Plywood laying. Wendyng working until 7PM
Fri (21/06) | 21 Jun 2024 | P15 |  | Current status of footing rebar work
Fri (21/06) | 21 Jun 2024 | P13 |  | Pile head hacking by KTC. They work until 10PM tonight
Fri (21/06) | 21 Jun 2024 | STN263 |  | Excavation CD 36/37.9m
Fri (21/06) | 21 Jun 2024 | STN254 |  | Desanding has just completed
Fri (21/06) | 21 Jun 2024 | P16 |  | Premix and pavement hacking for ERSS TT
Sat (22/06) | 22 Jun 2024 | ST263 |  | 1st bite in progress, reached 37.8m
Sat (22/06) | 22 Jun 2024 | ST254 |  | Cage A (2/4 cage in progress). Cage B (2/4 lowered down)
Sat (22/06) | 22 Jun 2024 | ST258 |  | Continue grabbing
Sat (22/06) | 22 Jun 2024 | BRP12 |  | Koden test in progress
Sat (22/06) | 22 Jun 2024 | BRP20 |  | Preparing to start excavation. Now cutter teeth changing
Sat (22/06) | 22 Jun 2024 | BRP23 |  | Excavation completed. Cutter body bring up for internal koden and flange welding
Sat (22/06) | 22 Jun 2024 | BC cutter 1 |  | Continue gear box changing
Sat (22/06) | 22 Jun 2024 | ST115 |  | Cage A (1/4 lowered down). Cage B (2/4 lowered down in progress)
Sun (23/06) | 23 Jun 2024 | MH2-1 &MH2-4 |  | Benching patch up by LCH
Sun (23/06) | 23 Jun 2024 | N4 |  | Barrication and signages installation
Sun (23/06) | 23 Jun 2024 | P15 |  | Column rebar work
Sun (23/06) | 23 Jun 2024 | MH5-2 |  | Manhole wall rebar work
Sun (23/06) | 23 Jun 2024 | P10 |  | Waler joint welding
Sun (23/06) | 23 Jun 2024 | P2 |  | Waler joint welding by LE before bring over to actual location
Sun (23/06) | 23 Jun 2024 | MH5-1 |  | Soffit plywood laying
Sun (23/06) | 23 Jun 2024 | MH3-5 |  | Drain as built taking by woh hup
Sun (23/06) | 23 Jun 2024 | ST115 |  | Casting in progress. Last lorry on the way
Sun (23/06) | 23 Jun 2024 | ST81 |  | Cutter teeth maintenance
Sun (23/06) | 23 Jun 2024 | ST172 |  | Cutter maintenance
Sun (23/06) | 23 Jun 2024 | BRP20 |  | Excavation reached 31m
Sun (23/06) | 23 Jun 2024 | BRP24 |  | Tremie pipe lowered down. Concrete lorry on the way
Sun (23/06) | 23 Jun 2024 | ST263 |  | Rebar cage lowering in progress, 3/4 cages
Sun (23/06) | 23 Jun 2024 | MH2-4 |  | Continue patch up at bench by LCH
Sun (23/06) | 23 Jun 2024 | N4 |  | Barricade and netting installation
Sun (23/06) | 23 Jun 2024 | P15 |  | Column rebar work in progress
Sun (23/06) | 23 Jun 2024 | P13 |  | Plastic protection to pile head. Lean concrete will be today
Sun (23/06) | 23 Jun 2024 | P10 |  | 2 sides waler installed
Sun (23/06) | 23 Jun 2024 | P8-2 |  | Tie rod hole patch up
Sun (23/06) | 23 Jun 2024 | MH5-1 |  | Slab rebar laying
Sun (23/06) | 23 Jun 2024 | MH5-2 |  | Wall rebar work in progress
Sun (23/06) | 23 Jun 2024 | ST81 |  | Cutter wheel maintenance
Sun (23/06) | 23 Jun 2024 | ST172 |  | 1st bite in progress, reached 24.7m
Sun (23/06) | 23 Jun 2024 | BRP37 |  | Guidewall casting will be tonight
Sun (23/06) | 23 Jun 2024 | BRP20 |  | Excavation in progress, reached 33m
Sun (23/06) | 23 Jun 2024 | BRP24 |  | Casting done
Sun (23/06) | 23 Jun 2024 | ST263 |  | Preparing for 1st cage lowering. Plan to cast today
Mon (24/06) | 24 Jun 2024 | P49-8 |  | Boring reached 27m. Target today casting
Mon (24/06) | 24 Jun 2024 | ST172 |  | B1 in progress. CD 36/41.3m
Mon (24/06) | 24 Jun 2024 | P46-P47 |  | Platform arrange for BP work
Mon (24/06) | 24 Jun 2024 | P47 |  | Hacking of hardcore to smaller pieces
Mon (24/06) | 24 Jun 2024 | P47 Changi bound |  | Removal of drain for BP work. One pile clash with Army cable manhole
Mon (24/06) | 24 Jun 2024 | P16 |  | LECE trial trench works for ERSS preboring
Mon (24/06) | 24 Jun 2024 | N5 |  | Rebar installation for crosshead in progress
Mon (24/06) | 24 Jun 2024 | N4 |  | Signages and housekeeping works in progress
Mon (24/06) | 24 Jun 2024 | P15 |  | Rebar installation for column stump
Mon (24/06) | 24 Jun 2024 | P14 |  | Kentledge set up completed. Today to start testing
Mon (24/06) | 24 Jun 2024 | BRP16, BRP20 |  | B1 excavation in progress
Mon (24/06) | 24 Jun 2024 | P13 |  | Pile head trimming works in progress
Mon (24/06) | 24 Jun 2024 | P12 |  | Backfilling works in progress for ERSS extraction
Mon (24/06) | 24 Jun 2024 | P10 |  | Welding works for waler beams in progress
Mon (24/06) | 24 Jun 2024 | MH5-2 |  | Rebar & Formwork installation for intermediate slab
Mon (24/06) | 24 Jun 2024 | MH5-1 |  | Rebar & Formwork installation for intermediate slab. Target to cast today
Mon (24/06) | 24 Jun 2024 | ST81 |  | 1st bite reached 28.9m
Mon (24/06) | 24 Jun 2024 | Zone 3 |  | Woh Hup provided 2 teams for UKP and KP TT work
Mon (24/06) | 24 Jun 2024 | ST172 |  | 1st bite in progress, reached 30.7m
Mon (24/06) | 24 Jun 2024 | Zone 1 |  | P3-4 boring works for casing installation in progress
Mon (24/06) | 24 Jun 2024 | BRP23 |  | LSS backfilling
Mon (24/06) | 24 Jun 2024 | BC cutter 2 |  | Hydraulic hose leakage repairing and replacing gear box in progress. This BC cutter alway have issue or breakdown
Mon (24/06) | 24 Jun 2024 | BP2A-2 | 39 | Boring in progress, reached 6m
Mon (24/06) | 24 Jun 2024 | TDP111 |  | LSS backfilling
Mon (24/06) | 24 Jun 2024 | Zone 4 |  | Sptel reinstate their work area with premix
Mon (24/06) | 24 Jun 2024 | P49-8 |  | Left one meter to toe level. Today plan to cast
Mon (24/06) | 24 Jun 2024 | P47 |  | Backfilling at completed TT area
Mon (24/06) | 24 Jun 2024 | STN258 |  | B1 CD 30/ 36m
Mon (24/06) | 24 Jun 2024 | BP2A-2 | 39 | Boring in progress, CD 18m
Mon (24/06) | 24 Jun 2024 | BRP16 Rig 4 |  | Has just started excavation
Mon (24/06) | 24 Jun 2024 | BRP20 Rig 2 |  | Excavation CD 34.2m/36m
Mon (24/06) | 24 Jun 2024 | N5 |  | Continue rebar installation for crosshead
Mon (24/06) | 24 Jun 2024 | P15 |  | Rebar installation for column stump
Mon (24/06) | 24 Jun 2024 | P14 |  | Kentledge test commenced and ongoing
Mon (24/06) | 24 Jun 2024 | P13 |  | Pile head trimming works completed. Tmr to start pile cap rebar works
Mon (24/06) | 24 Jun 2024 | P12 |  | Backfilling works in progress for ERSS extraction
Mon (24/06) | 24 Jun 2024 | P10 |  | Current status for waler beams welding works
Mon (24/06) | 24 Jun 2024 | MH5-2 |  | Rebar & Formwork installation for intermediate slab
Mon (24/06) | 24 Jun 2024 | MH5-1 |  | Formwork installation for intermediate slab
Mon (24/06) | 24 Jun 2024 | Zone 1 |  | P3-4 continue boring works. Casing installed
Mon (24/06) | 24 Jun 2024 | ST172 |  | B1 CD 34.5m
Mon (24/06) | 24 Jun 2024 | ST81-Rig 1 |  | B1 CD 29.2/33.5m, changing of wheel teeth now
Mon (24/06) | 24 Jun 2024 | 1.8m dia |  | Now rig breakdown. Mechanic on the way. 1 point of pipes sleeves installed
Mon (24/06) | 24 Jun 2024 | N5 |  | Cross head rebar work in progress
Mon (24/06) | 24 Jun 2024 | P15 |  | Column link bar installation
Mon (24/06) | 24 Jun 2024 | P14 |  | Kentledge WLT in progress
Mon (24/06) | 24 Jun 2024 | P13 |  | Pile head hacking left one pile to completed
Mon (24/06) | 24 Jun 2024 | P10 |  | Left two diagonal waler to complete
Mon (24/06) | 24 Jun 2024 | P9 |  | HSL prepare the area for PDA test
Mon (24/06) | 24 Jun 2024 | P3-4 |  | Boring left 5m to complete. Tomorrow to cast
Mon (24/06) | 24 Jun 2024 | MH5-2 |  | Intermediate slab formwork in progress. Tomorrow to cast
Mon (24/06) | 24 Jun 2024 | MH5-1 |  | Concrete on the way for intermediate slab casting
Mon (24/06) | 24 Jun 2024 | ST252 |  | Guidewall lean concrete
Mon (24/06) | 24 Jun 2024 | ST- 258 |  | Excavation in progress, reached 32.0m/36.0m
Mon (24/06) | 24 Jun 2024 | N5 |  | No activity
Mon (24/06) | 24 Jun 2024 | N4 |  | No activity
Mon (24/06) | 24 Jun 2024 | P15 |  | No activity
Mon (24/06) | 24 Jun 2024 | P14 |  | Kentledge test ongoing, 100% (6hrs). Now holding for the last hour
Mon (24/06) | 24 Jun 2024 | P13, P12 |  | No activity
Mon (24/06) | 24 Jun 2024 | P10 |  | Activity done for the day
Mon (24/06) | 24 Jun 2024 | MH5-2 |  | Slab formwork and rebar tying ongoing. Works till 10pm
Mon (24/06) | 24 Jun 2024 | MH5-1 |  | Intermediate slab casting completed. Levelling ongoing
Mon (24/06) | 24 Jun 2024 | P21 |  | Krishco washout pipe installation. Works till 10pm
Mon (24/06) | 24 Jun 2024 | ST258 |  | Rectification ongoing. B1 CD 32/36m
Mon (24/06) | 24 Jun 2024 | BRP36 |  | Guidewall cast
Mon (24/06) | 24 Jun 2024 | ST81 |  | Cutter wheel changing ongoing. B1 CD 29.2/33.5m
Mon (24/06) | 24 Jun 2024 | P49-10 |  | Casting in progress
Tue (25/06) | 25 Jun 2024 | ST264 |  | 1st bite excavation in progress. Current depth 7.5m/37.5m
Tue (25/06) | 25 Jun 2024 | ST258 |  | 1st bite excavation in progress. Current depth: 34.1m/36m
Tue (25/06) | 25 Jun 2024 | BC cutter No-3 |  | Cutter teeth changing
Tue (25/06) | 25 Jun 2024 | ST252 |  | Guidewall works in progress. Today to cast
Tue (25/06) | 25 Jun 2024 | ST81 |  | 1st bite, reached 29.6m
Tue (25/06) | 25 Jun 2024 | N5 |  | Crosshead rebar installation works in progress
Tue (25/06) | 25 Jun 2024 | P15 |  | Column stump rebar works and formwork dismantle for pile cap in progress
Tue (25/06) | 25 Jun 2024 | P14-1 |  | Kentledge test ongoing at 200% loading. Testing load 2650 tonne. To hold for 6hrs
Tue (25/06) | 25 Jun 2024 | P12 |  | KTC Backfilling & compaction works
Tue (25/06) | 25 Jun 2024 | P10 |  | ERSS Struts welding in progress
Tue (25/06) | 25 Jun 2024 | P9-1-1 |  | Access making for PDA test
Tue (25/06) | 25 Jun 2024 | P13 |  | Manual hacking & Hardcores clearing in progress
Tue (25/06) | 25 Jun 2024 | Zone 4 |  | Rig breakdown also. Need to repair sensor wire
Tue (25/06) | 25 Jun 2024 | Zone 2 |  | UT test for P2 deck posts completed
Tue (25/06) | 25 Jun 2024 | MH5-1 |  | Intermediate slab cast yst. Formwork removal ongoing
Tue (25/06) | 25 Jun 2024 | MH5-2 |  | Intermediate slab rebar & Formwork installation. Today to cast
Tue (25/06) | 25 Jun 2024 | Zone 1 |  | P3-4 boring completed. Now preparing for rebar cage lowering
Tue (25/06) | 25 Jun 2024 | Zone 1 |  | P2 trial trench for ERSS in progress
Tue (25/06) | 25 Jun 2024 | N5 |  | Crosshead rebar & RWDP installation in progress
Tue (25/06) | 25 Jun 2024 | P16 |  | Platform making for upcoming ERSS preboring works
Tue (25/06) | 25 Jun 2024 | P15 |  | Formwork installation for Column stump in progress
Tue (25/06) | 25 Jun 2024 | P14-1 |  | Kentledge testing in progress. Unloading at 0%
Tue (25/06) | 25 Jun 2024 | P12 |  | Backfilling completed
Tue (25/06) | 25 Jun 2024 | P10 |  | Struts welding works
Tue (25/06) | 25 Jun 2024 | P9-1-1 |  | PDA test completed
Tue (25/06) | 25 Jun 2024 | ST264 |  | Excavation started last night. Current depth 4/37.5m
Tue (25/06) | 25 Jun 2024 | ST258 |  | Excavation temporarily stopped for cutter wheel change. CD 34/36m
Tue (25/06) | 25 Jun 2024 | BRP16 |  | B1 in progress, 17.5/30.47m
Tue (25/06) | 25 Jun 2024 | BRP20 |  | Gearbox changing ongoing. Current depth 38.2/41.9m
Tue (25/06) | 25 Jun 2024 | ST172 |  | B1 in progress, 37.2/41.3m
Tue (25/06) | 25 Jun 2024 | ST81 |  | B1 CD 29.5/33.5m
Tue (25/06) | 25 Jun 2024 | MH5-1 |  | Scaffold making for next layer of wall casting
Tue (25/06) | 25 Jun 2024 | MH5-2 |  | Formwork installation for intermediate slab casting
Tue (25/06) | 25 Jun 2024 | P3-4 |  | Rebar cages lowered. Now preparing for BP casting
Tue (25/06) | 25 Jun 2024 | P4-3 |  | Preparation to start boring works for casing installation
Tue (25/06) | 25 Jun 2024 | P2 |  | Continue trial trench works for ERSS. Found SPPG cables at around 1.2m depth
Tue (25/06) | 25 Jun 2024 | ST172 |  | Flange welding for trimming
Tue (25/06) | 25 Jun 2024 | PBH61 |  | Boring in progress, reached 25m
Tue (25/06) | 25 Jun 2024 | BRP34 |  | Excavation for guidewall
Tue (25/06) | 25 Jun 2024 | BP2A-2-39 |  | Boring reached 34m
Tue (25/06) | 25 Jun 2024 | ST264 |  | 1st bite excavation reached 18.5m
Tue (25/06) | 25 Jun 2024 | ST252 |  | Concrete on site for guidewall casting. ST251: lean concrete for guidewall
Tue (25/06) | 25 Jun 2024 | ST258 |  | 2nd bited, reached 15m
Tue (25/06) | 25 Jun 2024 | P15 |  | Column formwork closing
Tue (25/06) | 25 Jun 2024 | P13 |  | Started footing rebar work
Tue (25/06) | 25 Jun 2024 | P10 |  | Welding of diagonal struct end in progress
Tue (25/06) | 25 Jun 2024 | N5 |  | Current status of rebar work
Tue (25/06) | 25 Jun 2024 | N5, N4 |  | No activity
Tue (25/06) | 25 Jun 2024 | P14, P15 |  | No activity
Tue (25/06) | 25 Jun 2024 | P13 |  | No activity. Rebar works will continue tmr. Now the team only housekeeping and adjusting barricades
Tue (25/06) | 25 Jun 2024 | P10 |  | No activity
Tue (25/06) | 25 Jun 2024 | MH5-2, zone 1 |  | No activity
Tue (25/06) | 25 Jun 2024 | ST264 |  | B1 in progress, 20/37.5m
Tue (25/06) | 25 Jun 2024 | ST258 |  | B2 in progress, 18.5/34.5m
Tue (25/06) | 25 Jun 2024 | ST252 |  | Guidewall cast just now
Tue (25/06) | 25 Jun 2024 | BRP16 |  | Excavation continue, 29.5/30.47m
Tue (25/06) | 25 Jun 2024 | BRP20 |  | Excavation temporarily stopped for cutter teeth change. CD 40.7/41.9m
Tue (25/06) | 25 Jun 2024 | ST81 |  | B2 in progress, 17/33.5m
Tue (25/06) | 25 Jun 2024 | MH3-5, Zone 4 |  | No activity, Nearby MH3-5: Lane closure for Singtel works ongoing
Tue (25/06) | 25 Jun 2024 | Zone 4 LA towards TPE |  | Telstra lane closure for pipe laying works
Tue (25/06) | 25 Jun 2024 | ST172 |  | B1 trimming ongoing
Tue (25/06) | 25 Jun 2024 | BRP22 |  | Boring in progress, 13.47m
Tue (25/06) | 25 Jun 2024 | BRP34 |  | Premix hacking for TT
Tue (25/06) | 25 Jun 2024 | BC cutter 2 |  | Gear box changed. Now changing teeth
Wed (26/06) | 26 Jun 2024 | BP2A-2 | 39 | Boring in progress, CD 36m
Wed (26/06) | 26 Jun 2024 | MH3-5 |  | Concrete barrier placing for shaft work
Wed (26/06) | 26 Jun 2024 | P45 |  | Tracing of LP cable to confirm it is abandoned cables
Wed (26/06) | 26 Jun 2024 | P16 |  | Preparation to start ERSS preboring
Wed (26/06) | 26 Jun 2024 | N5 Crosshead |  | Top rebar installation works
Wed (26/06) | 26 Jun 2024 | P15 |  | Propping installation for column stump casting today
Wed (26/06) | 26 Jun 2024 | P14 |  | Demobilisation of kentledge materials in progress
Wed (26/06) | 26 Jun 2024 | P13 |  | Pile cap bottom rebar installation works
Wed (26/06) | 26 Jun 2024 | P12 |  | Compaction completed for ERSS extraction
Wed (26/06) | 26 Jun 2024 | P10 |  | Struts welding works in progress
Wed (26/06) | 26 Jun 2024 | P9-2 |  | KTC column backfilling ongoing
Wed (26/06) | 26 Jun 2024 | P9 |  | PDA test area backfilled
Wed (26/06) | 26 Jun 2024 | MH5-2 |  | Intermediate slab cast yesterday. Preparing for Formwork dismantle
Wed (26/06) | 26 Jun 2024 | P6 |  | Premix removal for BP trial trench
Wed (26/06) | 26 Jun 2024 | MH5-1 |  | Backfilling in progress for next layer
Wed (26/06) | 26 Jun 2024 | P46-8 |  | Casing installed. Boring started. Now do some repairing before resume boring
Wed (26/06) | 26 Jun 2024 | P4-3 |  | BP boring works in progress. Casing installed. Current depth 9m
Wed (26/06) | 26 Jun 2024 | P2 |  | Trial trench for ERSS installation
Wed (26/06) | 26 Jun 2024 | P46-8 |  | Boring in progress, reached 17m
Wed (26/06) | 26 Jun 2024 | ST172 Rig 3 |  | B2 CD 23.5/41.3m
Wed (26/06) | 26 Jun 2024 | N5 |  | Crosshead continue rebar installation
Wed (26/06) | 26 Jun 2024 | ST81-Rig 1 |  | B2 CD 22.3/33.0m, abt to resume excavation as has completed for teeth replacement
Wed (26/06) | 26 Jun 2024 | P16 |  | Preboring for ERSS to start after worker break
Wed (26/06) | 26 Jun 2024 | P15 |  | Working platform installation for casting today
Wed (26/06) | 26 Jun 2024 | P14 |  | Demobilisation of kentledge materials in progress
Wed (26/06) | 26 Jun 2024 | P13 |  | Pile cap rebar installation works
Wed (26/06) | 26 Jun 2024 | P10 |  | Preparation for concrete packing today
Wed (26/06) | 26 Jun 2024 | P9-2 |  | KTC column backfilling works
Wed (26/06) | 26 Jun 2024 | P9 |  | PDA test pile hacking works ongoing
Wed (26/06) | 26 Jun 2024 | MH5-2 |  | Backfilling works for next layer in progress
Wed (26/06) | 26 Jun 2024 | P6 |  | Premix removal for BP trial trench
Wed (26/06) | 26 Jun 2024 | MH5-1 |  | Backfilling for next layer completed. Wall Rebar installation ongoing
Wed (26/06) | 26 Jun 2024 | ST264 |  | B1 reached 26/37.5m
Wed (26/06) | 26 Jun 2024 | ST258 |  | Cutter teeth changed. Resume B2 from 28/34.5m
Wed (26/06) | 26 Jun 2024 | BRP16 |  | B1 completed. Additional flap welding ongoing
Wed (26/06) | 26 Jun 2024 | BRP20 |  | Koden check ongoing
Wed (26/06) | 26 Jun 2024 | BRP39 |  | Guidewall rebar works in progres
Wed (26/06) | 26 Jun 2024 | ST81 |  | B2 in progress, 20.9/33.5m
Wed (26/06) | 26 Jun 2024 | ST172 |  | B2 started at 0251hrs. CD 15/41.3m
Wed (26/06) | 26 Jun 2024 | STN258 |  | B2 CD 31.4/34.5m
Wed (26/06) | 26 Jun 2024 | STN264 |  | B2 CD 21/37.5m
Wed (26/06) | 26 Jun 2024 | P4-3 |  | BP Boring currently on hold due to rig breakdown. Mechanic otw to check
Wed (26/06) | 26 Jun 2024 | P2 |  | Continue ERSS trial trench works. Found 700mm water pipe
Wed (26/06) | 26 Jun 2024 | N5 |  | No activity
Wed (26/06) | 26 Jun 2024 | P15 |  | 1st list column casting completed
Wed (26/06) | 26 Jun 2024 | P13, P14 |  | No more activity
Wed (26/06) | 26 Jun 2024 | Zone 2 | North side | No other activity
Wed (26/06) | 26 Jun 2024 | Zone 2 centre island |  | Backfilling ongoing by WH
Wed (26/06) | 26 Jun 2024 | Zone 1 |  | Now boring rig preparing for wire rope change. Mechanic already on site
Wed (26/06) | 26 Jun 2024 | STN264 |  | B2 CD 3/37.5m
Wed (26/06) | 26 Jun 2024 | STN258 |  | B2 CD 29.6/34.5m
Wed (26/06) | 26 Jun 2024 | ST81 |  | B2 internal koden check and cutter teeth change ongoing
Wed (26/06) | 26 Jun 2024 | ST172 |  | B2 in progress
Thu (27/06) | 27 Jun 2024 | P46-8 |  | Boring reached 25.1m. Preparing for rock confirmation
Thu (27/06) | 27 Jun 2024 | P48 |  | Platform prepare for JGP
Thu (27/06) | 27 Jun 2024 | BRP22 -BC2 |  | Excavation in progress. Current depth 30m/41.9m
Thu (27/06) | 27 Jun 2024 | BRP32-BC4 |  | 1st bite trenching, depth 15m/32.87m
Thu (27/06) | 27 Jun 2024 | ST172-BC3 |  | 2nd bite trenching, current depth 39.1m/41.3m. Teeth changing
Thu (27/06) | 27 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, depth 25.5m/33.5m
Thu (27/06) | 27 Jun 2024 | P45 |  | Abandoned LP cables cutting done. Preparing to remove the metal pipes
Thu (27/06) | 27 Jun 2024 | P16 |  | Preboring for ERSS started
Thu (27/06) | 27 Jun 2024 | N5 Crosshead |  | Rebar installation in progress
Thu (27/06) | 27 Jun 2024 | P15 |  | Column stump cast yesterday. Curing ongoing
Thu (27/06) | 27 Jun 2024 | P14 |  | Kentledge demobilisation works
Thu (27/06) | 27 Jun 2024 | P13 |  | Pile cap rebar installation ongoing
Thu (27/06) | 27 Jun 2024 | P12 |  | ERSS extraction in progress
Thu (27/06) | 27 Jun 2024 | P10 |  | Welding works for struts ongoing
Thu (27/06) | 27 Jun 2024 | P6 |  | Trial trench for BP in progress. Found Singtel cables, 22kV and traffic light cables
Thu (27/06) | 27 Jun 2024 | MH5-2 |  | Formwork removal and wall rebar installation
Thu (27/06) | 27 Jun 2024 | MH5-1 |  | Wall rebar installation in progress
Thu (27/06) | 27 Jun 2024 | UKP39& 40 |  | TT for utility post
Thu (27/06) | 27 Jun 2024 | Zone 1 P4-3 |  | BP Boring works in progress. Current depth 27m. Today to cast
Thu (27/06) | 27 Jun 2024 | P2 |  | Trial trench for ERSS & traffic decking works
Thu (27/06) | 27 Jun 2024 | ST258 |  | Hydrofraise cable rectification ongoing. B2 CD 32.7/34.5m
Thu (27/06) | 27 Jun 2024 | ST264 |  | Grab excavation completed. Pending hydrofraise to resume excavation. B2 CD 21/37.5m, B1 CD 26/37.5m
Thu (27/06) | 27 Jun 2024 | BRP20 |  | Tremie pipe lowered. Pending casting
Thu (27/06) | 27 Jun 2024 | BRP22 |  | Excavation started @ 0035hrs. CD 12/41.9m
Thu (27/06) | 27 Jun 2024 | ST172 |  | B2 in progress, 29/41.3m
Thu (27/06) | 27 Jun 2024 | ST81 |  | Cutter teeth change ongoing. B2 CD 24.8/33.5m
Thu (27/06) | 27 Jun 2024 | BRP20 |  | First concrete truck on site
Thu (27/06) | 27 Jun 2024 | STN258 |  | Third bite trenching completed. 34.7m depth
Thu (27/06) | 27 Jun 2024 | N5 |  | No more activity
Thu (27/06) | 27 Jun 2024 | P13 |  | Pile cap no more activity. Top bars completed. Balance shearlinks and starter bars for pier
Thu (27/06) | 27 Jun 2024 | P4-3 |  | Casting in progress
Fri (28/06) | 28 Jun 2024 | Zone 4 |  | 1st point JGP grouting in progress
Fri (28/06) | 28 Jun 2024 | P46 |  | Drain removal on going by Woh Hup
Fri (28/06) | 28 Jun 2024 | P46-8 |  | Boring to toe level in progress
Fri (28/06) | 28 Jun 2024 | BRP22 -BC2 |  | Desanding completed. Next final Koden and preparation for rebar cage installation
Fri (28/06) | 28 Jun 2024 | BRP32-BC4 |  | 1st bite trenching resume, depth 28.8m/32.87m. Teeth changing
Fri (28/06) | 28 Jun 2024 | P16 |  | Preboring for ERSS installation
Fri (28/06) | 28 Jun 2024 | N5 |  | No activity
Fri (28/06) | 28 Jun 2024 | P15 |  | Pile cap Formwork dismantle and removal
Fri (28/06) | 28 Jun 2024 | P14 |  | Kentledge demobilisation works
Fri (28/06) | 28 Jun 2024 | P13 |  | Shear links, Formwork installation for pile cap
Fri (28/06) | 28 Jun 2024 | ST172-BC3 |  | Trimming, C-lug welding on going
Fri (28/06) | 28 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, depth 27.2m/33.5m. Cutter wheel maintenance
Fri (28/06) | 28 Jun 2024 | ST264 |  | B1 temporarily stopped for welding works. CD 32.2/37.5m
Fri (28/06) | 28 Jun 2024 | ST258 |  | Preparing for WS removal
Fri (28/06) | 28 Jun 2024 | MH2-1 |  | PUB sewer inspection ongoing
Fri (28/06) | 28 Jun 2024 | DW42 |  | Guidewall pending to cast
Fri (28/06) | 28 Jun 2024 | BRP20 |  | Pending LSS backfill
Fri (28/06) | 28 Jun 2024 | BRP22 |  | Cutter teeth changing ongoing
Fri (28/06) | 28 Jun 2024 | BRP32 |  | B1 excavation in progress
Fri (28/06) | 28 Jun 2024 | PBH57 |  | Waiting for water supply before starting works
Fri (28/06) | 28 Jun 2024 | P31 |  | KTC excavation ongoing for utility support
Fri (28/06) | 28 Jun 2024 | MH3-5 |  | Hoarding frame installation
Fri (28/06) | 28 Jun 2024 | BRP41 |  | Guidewall trial trench ongoing. Found abandoned gas pipe
Fri (28/06) | 28 Jun 2024 | ST172 |  | B3 excavation completed
Fri (28/06) | 28 Jun 2024 | P12 |  | ERSS extraction completed
Fri (28/06) | 28 Jun 2024 | P10 |  | Test pile hacking and hardcores removal ongoing
Fri (28/06) | 28 Jun 2024 | P8-2 |  | KTC column backfilling works
Fri (28/06) | 28 Jun 2024 | MH5-2 |  | Wall rebar installation (3m)
Fri (28/06) | 28 Jun 2024 | MH5-1 |  | Wall rebar installation (3m)
Fri (28/06) | 28 Jun 2024 | Zone 3 |  | Hardcore clearing by Dongah ongoing
Fri (28/06) | 28 Jun 2024 | PBH70 |  | SI in progress, 23m
Fri (28/06) | 28 Jun 2024 | UKP40 |  | Trial trench ongoing
Fri (28/06) | 28 Jun 2024 | ST81 |  | B2 temporarily stopped for cutter teeth change
Fri (28/06) | 28 Jun 2024 | DR2 |  | Grass clearing ongoing by WH
Fri (28/06) | 28 Jun 2024 | P2 |  | Trial trench for ERSS installation in progress
Fri (28/06) | 28 Jun 2024 | P3-2 |  | BP boring works for casing installation in progress. Current depth 7.5m
Fri (28/06) | 28 Jun 2024 | ST250, ST249 |  | Guidewall rebar works
Fri (28/06) | 28 Jun 2024 | STN258 |  | Trimming in progress at endplate side
Fri (28/06) | 28 Jun 2024 | STN264 |  | 1st bite resume excavation, 26m/37.5m
Fri (28/06) | 28 Jun 2024 | BRP22 -BC2 |  | Excavation in progress. Current depth 36.3m/41.9m
Fri (28/06) | 28 Jun 2024 | BRP32-BC4 |  | 1st bite trenching, depth 15.3m/32.87m
Fri (28/06) | 28 Jun 2024 | BP2A-2 | 39 | Toe was confirmed this morning, 41.95m. Rebar cage lowered. Now ongoing tremie pipe installation
Fri (28/06) | 28 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, depth 26.4m/33.5m
Fri (28/06) | 28 Jun 2024 | PBH70 |  | In progress, 28m
Fri (28/06) | 28 Jun 2024 | MH5-1 |  | Continue wall rebar installation (3m)
Fri (28/06) | 28 Jun 2024 | S4 |  | Vibro rig shifted back to S4 for ERSS extraction
Fri (28/06) | 28 Jun 2024 | Zone 1 |  | P3-2 BP casing installed, continue boring works
Fri (28/06) | 28 Jun 2024 | TDP75 |  | Trial trench in progress
Fri (28/06) | 28 Jun 2024 | ST81 |  | Cutter wheel repairing still ongoing. B2 CD 26.4/33.5m
Fri (28/06) | 28 Jun 2024 | P39 |  | SPPG cable pulling ongoing
Fri (28/06) | 28 Jun 2024 | P46-8 |  | Waiting for extension for rebar cage. Rebar cage on the way. If delivery early, tonight plan to cast
Fri (28/06) | 28 Jun 2024 | P46 Changi bound |  | Drain wall removal for bored pile TT
Fri (28/06) | 28 Jun 2024 | P48 |  | Prepare platform for 2nd point boring
Fri (28/06) | 28 Jun 2024 | BRP40 |  | Now preparing area for hacking for trial trench works
Fri (28/06) | 28 Jun 2024 | PBH57 |  | Started
Fri (28/06) | 28 Jun 2024 | BRP32 |  | In progress, 26/32.87m
Fri (28/06) | 28 Jun 2024 | MH5-2 |  | Working platform making for wall rebar installation in progress
Fri (28/06) | 28 Jun 2024 | P10 |  | KTC excavation to FEL ongoing
Fri (28/06) | 28 Jun 2024 | BRP22 |  | In progress, 41.3/41.9m
Fri (28/06) | 28 Jun 2024 | P13 |  | Continue pile cap rebar installation works
Fri (28/06) | 28 Jun 2024 | P15 |  | Concrete plug cast for pile cap
Fri (28/06) | 28 Jun 2024 | P14 |  | Kentledge demobilisation works
Fri (28/06) | 28 Jun 2024 | P16 |  | ERSS preboring works ongoing
Fri (28/06) | 28 Jun 2024 | ST258 |  | WS extraction ongoing
Fri (28/06) | 28 Jun 2024 | N5 |  | Crosshead rebars inspection in progress
Fri (28/06) | 28 Jun 2024 | ST228 |  | Guidewall manual trial trench ongoing
Fri (28/06) | 28 Jun 2024 | ST264 |  | Excavation temporarily stopped. Mechanic checking on hydrofraise
Fri (28/06) | 28 Jun 2024 | MH3-5 |  | Briefing done to start actual work
Fri (28/06) | 28 Jun 2024 | From Pulling pit to Joint bay 2 |  | Cable pulling in progress
Fri (28/06) | 28 Jun 2024 | STN264 |  | 1st bite resume excavation, 32m/37.5m. Cutter body up for teeth maintenance
Fri (28/06) | 28 Jun 2024 | BRP22 -BC2 |  | Excavation in progress. Current depth 38m/41.9m
Fri (28/06) | 28 Jun 2024 | BRP32-BC4 |  | 1st bite trenching resume, depth 21m/32.87m
Fri (28/06) | 28 Jun 2024 | ST172-BC3 |  | 3rd bite trenching, current depth 21.5m/41.3m
Fri (28/06) | 28 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, depth 26.4m/33.5m. Cutter wheel maintenance
Fri (28/06) | 28 Jun 2024 | P13 |  | Pile cap status, balance 10% shearlinks and tie rod welding. Tomorrow afternoon to cast
Fri (28/06) | 28 Jun 2024 | P10 |  | Pile cap ERSS slope casting completed. Levelling in progress
Fri (28/06) | 28 Jun 2024 | Zone 1 |  | No more activity
Fri (28/06) | 28 Jun 2024 | MH5-1 |  | Permanent wall 2nd lift formwork closing. Target to cast 11pm tonight
Fri (28/06) | 28 Jun 2024 | STN264 |  | 1st bite excavation, 32.5m/37.5m
Fri (28/06) | 28 Jun 2024 | STN258 |  | Cleaning completed. Preparation for desanding
Sat (29/06) | 29 Jun 2024 | BRP16 |  | Rebar cage lowering
Sat (29/06) | 29 Jun 2024 | BRP19-BC2 |  | Trenching in progress, 17m/41.3m
Sat (29/06) | 29 Jun 2024 | BRP22 |  | For casting, waiting for concrete lorry
Sat (29/06) | 29 Jun 2024 | BRP32-BC4 |  | 1st bite trenching completed, preparation for 2nd bite trenching
Sat (29/06) | 29 Jun 2024 | ST172-BC3 |  | Rebar cage lowering in progress. 1/8 cage installed
Sat (29/06) | 29 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, depth 29.8m/33.5m. Cutter teeth replacement
Sat (29/06) | 29 Jun 2024 | MH5-1 |  | 2nd lift permanent wall casting completed
Sat (29/06) | 29 Jun 2024 | STN264 |  | 1st bite: 35.5m/37.5m, 2nd bite: 26m/37.5m. Trenching in progress
Sat (29/06) | 29 Jun 2024 | ST258 |  | Final koden done. Final depth check prior to rebar cage installation
Sat (29/06) | 29 Jun 2024 | BRP19-BC2 |  | Trenching started
Sat (29/06) | 29 Jun 2024 | BRP22 |  | Preparation for rebar cage lowering
Sat (29/06) | 29 Jun 2024 | BRP32-BC4 |  | 1st bite trenching resume, depth 32m/32.87m. Teeth changing
Sat (29/06) | 29 Jun 2024 | ST172-BC3 |  | Trimming completed. End plate extraction on going
Sat (29/06) | 29 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, depth 27.6m/33.5m
Sat (29/06) | 29 Jun 2024 | P13 |  | Casting in progress
Sat (29/06) | 29 Jun 2024 | P10 |  | Excavation to FEL till 10pm. Est to complete by Monday
Sat (29/06) | 29 Jun 2024 | P3-2 |  | Casting started
Sat (29/06) | 29 Jun 2024 | P13 |  | Casting continue. Balance 4 loads
Sat (29/06) | 29 Jun 2024 | STN264 |  | Tonight only 1 Operator, now ar STN258 for rebar cage installation, STATUS:, 1st bite: completed at 36.2m depth, 2nd bite: 32m/36.2m. Trenching in progress
Sat (29/06) | 29 Jun 2024 | STN258 |  | 8/8 cages installed. Hanging bar installation on going
Sun (30/06) | 30 Jun 2024 | BRP16 |  | Preparation for casting
Sun (30/06) | 30 Jun 2024 | BRP32 |  | 2nd bite trenching ongoing, current depth 8m
Sun (30/06) | 30 Jun 2024 | ST172 |  | Rebar cage lowering, 6/8 lowered
Sun (30/06) | 30 Jun 2024 | ST81-BC1 |  | 2nd bite trenching, current depth 30m
Sun (30/06) | 30 Jun 2024 | Zone 3 |  | Utility support work stopped due to ongoing rain
Sun (30/06) | 30 Jun 2024 | Zone 3 |  | Trial trench for deck post
Sun (30/06) | 30 Jun 2024 | MH3-5 |  | No activity
Sun (30/06) | 30 Jun 2024 | Z4 P46 |  | Trial trench for bp completed. Backfilling and levelling works in progress
Sun (30/06) | 30 Jun 2024 | N5 |  | No activity
Sun (30/06) | 30 Jun 2024 | P13 |  | Column stump rebar installation in progress
Sun (30/06) | 30 Jun 2024 | P10 |  | Excavation to FEL stopped due to ongoing rain
Sun (30/06) | 30 Jun 2024 | MH5-2 |  | No activity due to ongoing rain
Sun (30/06) | 30 Jun 2024 | MH5-1 |  | No activity due to ongoing rain
Sun (30/06) | 30 Jun 2024 | Zone 1 |  | No activity
Sun (30/06) | 30 Jun 2024 | Zone 1 |  | Lucky joint Singtel works ongoing from PRD3 to Loyang Ave
Sun (30/06) | 30 Jun 2024 | STN-264 |  | 2nd bite trenching in progress. Current depth 36.3m
Sun (30/06) | 30 Jun 2024 | STN264 |  | 1st bite: completed at 36.2m depth, 2nd bite: 32.8m/36.2m. Trenching in progress
Sun (30/06) | 30 Jun 2024 | STN258 |  | Tremie pipes installed. Concrete ordered. Estimated volume 189 m3
Sun (30/06) | 30 Jun 2024 | BRP19 |  | Trenching continue
Sun (30/06) | 30 Jun 2024 | BRP22 |  | Casting completed
Sun (30/06) | 30 Jun 2024 | BRP32 |  | 2nd bite trenching started
Sun (30/06) | 30 Jun 2024 | ST172 |  | Rebar cage lowering, 4/8 lowered
Sun (30/06) | 30 Jun 2024 | STN-228 |  | Guidewall rebar installation in progress
Sun (30/06) | 30 Jun 2024 | STN-264 |  | 2nd bite trenching in progress. Current depth 36.6m
Sun (30/06) | 30 Jun 2024 | STN-220 |  | 1st bite trenching in progress
Sun (30/06) | 30 Jun 2024 | BRP16 |  | Preparation to lower king post
Sun (30/06) | 30 Jun 2024 | N5 |  | Ducting assembly and connection works
Sun (30/06) | 30 Jun 2024 | P10 |  | Excavation to FEL ongoing
Sun (30/06) | 30 Jun 2024 | MH5-2 |  | Formwork installation for 2nd lift wall. Tmr to cast (3m)
Sun (30/06) | 30 Jun 2024 | MH5-1 |  | Cleaning & housekeeping work. Tmr to start backfilling for next layer wall
Sun (30/06) | 30 Jun 2024 | BRP19 |  | Trenching in progress, current depth 34.9m
Sun (30/06) | 30 Jun 2024 | BRP16 |  | Casting works in progress
Sun (30/06) | 30 Jun 2024 | BRP32 |  | 2nd bite trenching ongoing, current depth 12m
Sun (30/06) | 30 Jun 2024 | Zone 3 |  | Utility support welding works in progress
Sun (30/06) | 30 Jun 2024 | BRP-40 |  | Trial trench work
Sun (30/06) | 30 Jun 2024 | ST172 |  | All Rebar cages fully lowered, 8/8 lowered
Sun (30/06) | 30 Jun 2024 | ST-81 |  | 2nd bite trenching completed
Sun (30/06) | 30 Jun 2024 | Zone 4 |  | Work stopped for the day. No activity
Sun (30/06) | 30 Jun 2024 | BRP16 |  | Rebar cage + KP successfully lowered
Sun (30/06) | 30 Jun 2024 | STN258 |  | Casting in progress
Sun (30/06) | 30 Jun 2024 | STN264 |  | 1st bite: completed at 36.2m depth, 2nd bite: 35m/36.2m. Trenching continue
Mon (01/07) | 01 Jul 2024 | P14 |  | Unloading of steel plates
Mon (01/07) | 01 Jul 2024 | P13 |  | Stump rebar works in progress
Mon (01/07) | 01 Jul 2024 | P10 |  | Excavation to FEL continue. Target to complete today
Mon (01/07) | 01 Jul 2024 | P45 Changi bound |  | Marking of bored pile location. Abandoned cables already cut and remove progressively. No more services affecting the piles here
Mon (01/07) | 01 Jul 2024 | P45-5 |  | Bored pile work in progress
Mon (01/07) | 01 Jul 2024 | MH5-2 |  | 2nd lift permanent wall formwork closing done. Pending tinal inspection for casting
Mon (01/07) | 01 Jul 2024 | P46 |  | Confirming of water pipe alignment
Mon (01/07) | 01 Jul 2024 | M3-5 |  | Netting installation and removal of formwork in progress
Mon (01/07) | 01 Jul 2024 | Zone 1 |  | Rebar cage delivery for P3-1. P4-2 pre-boring
Mon (01/07) | 01 Jul 2024 | Zone 1 P3 area |  | To complete TT today. Mobilisation of vibro + steel plates from tomorrow for utility protection
Mon (01/07) | 01 Jul 2024 | MH5-1 |  | Backfilling
Mon (01/07) | 01 Jul 2024 | ST264 |  | B2 reached 37.5m. Cutter body washing ongoing
Mon (01/07) | 01 Jul 2024 | ST009 |  | B1 excavation in progress
Mon (01/07) | 01 Jul 2024 | ST228 |  | Guidewall construction ongoing
Mon (01/07) | 01 Jul 2024 | BRP19 |  | Desanding completed. Now preparing for final koden check
Mon (01/07) | 01 Jul 2024 | Zone 3 |  | Internal sump pit excavation by WH ongoing
Mon (01/07) | 01 Jul 2024 | BRP32 |  | In progress 26.2/32.87m
Mon (01/07) | 01 Jul 2024 | BRP41 |  | Guidewall casting ongoing
Mon (01/07) | 01 Jul 2024 | TDP104 |  | Trial trench
Mon (01/07) | 01 Jul 2024 | P45-5 |  | Boring in progress, reached 33m
Mon (01/07) | 01 Jul 2024 | P10 |  | Continue excavation to FEL
Mon (01/07) | 01 Jul 2024 | P16 |  | Preboring for ERSS installation
Mon (01/07) | 01 Jul 2024 | PBH69 |  | In progress, 32/33.57m
Mon (01/07) | 01 Jul 2024 | ST220 |  | B1 in progress, 24.2/37.9m
Mon (01/07) | 01 Jul 2024 | DR1 |  | Currently no activity. LE plan for sheetpile installation extension tmr (5nos)
Mon (01/07) | 01 Jul 2024 | P31-32 cable joint bay |  | No activity
Mon (01/07) | 01 Jul 2024 | BP2A-2 | 38 | Preboring was done this morning & casing installed
Mon (01/07) | 01 Jul 2024 | MH5-2 |  | Waiting for concrete truck to arrive for 2nd lift wall casting
Mon (01/07) | 01 Jul 2024 | MH5-1 |  | Backfilling in progress for next layer wall
Mon (01/07) | 01 Jul 2024 | P4-1 |  | BP boring works ongoing, current depth 9m. Casing installed
Mon (01/07) | 01 Jul 2024 | MH3-5 |  | Hacking of concrere for footing
Mon (01/07) | 01 Jul 2024 | P16 |  | Continue prep works for ERSS installation
Mon (01/07) | 01 Jul 2024 | N5 |  | Continue rebar works and installation for pipe sleeve for tendon
Mon (01/07) | 01 Jul 2024 | P15 |  | Backfilling works ongoing
Mon (01/07) | 01 Jul 2024 | P13 |  | Continue stunp rebar works
Mon (01/07) | 01 Jul 2024 | P10 |  | Continue excavation to FEL
Mon (01/07) | 01 Jul 2024 | MH5-2 |  | Wall casting in progress
Mon (01/07) | 01 Jul 2024 | P4-1 |  | Boring reached 18m. Soil disposal ongoing. Boring works until 7pm
Mon (01/07) | 01 Jul 2024 | ST264 |  | B3 completed. Now ongoing for WS extraction
Mon (01/07) | 01 Jul 2024 | ST259 |  | Excavation started @ 1800hrs
Mon (01/07) | 01 Jul 2024 | ST009 |  | B2 excavation temporarily stopped for cutter teeth and machine rectification. CD 2/39.2m
Mon (01/07) | 01 Jul 2024 | ST228 |  | Guidewall cast
Mon (01/07) | 01 Jul 2024 | BP2A-2 | 39 | Boring done for the day. Depth reached 14/42.213m
Mon (01/07) | 01 Jul 2024 | ST81 |  | WS joint welding in progress. BC1 currently no activity
Mon (01/07) | 01 Jul 2024 | BRP32 |  | Cutter body lift up for cutter teeth changing. CD 29/32.87m
Mon (01/07) | 01 Jul 2024 | BRP19 |  | Rebar cage installation in progress, 1/2nos
Mon (01/07) | 01 Jul 2024 | ST220 |  | Cutter body lift up for cutter teeth changing. B1 CD 28.3/37.9m
Mon (01/07) | 01 Jul 2024 | N5 |  | Distribution bar installation in progress
Tue (02/07) | 02 Jul 2024 | P48 |  | Trial trench for BP ongoing
Tue (02/07) | 02 Jul 2024 | Zone 4 |  | JGP point B-286 ongoing
Tue (02/07) | 02 Jul 2024 | Zone 4 |  | BP46-7 preparation for preboring. Yesterday cast BP45-5
Tue (02/07) | 02 Jul 2024 | P13 |  | Stump shearlinks installation
Tue (02/07) | 02 Jul 2024 | P10 |  | Excavation to FEL continue
Tue (02/07) | 02 Jul 2024 | TDP73 |  | Trial trench completed. No services
Tue (02/07) | 02 Jul 2024 | PBH69 and PBH70 |  | Completed. Next plan works will be at PBH67 and PBH68
Tue (02/07) | 02 Jul 2024 | TDP67 |  | Trial trench in progress
Tue (02/07) | 02 Jul 2024 | BRP41 |  | Guidewall formwork dismantling ongoing
Tue (02/07) | 02 Jul 2024 | PBH65 |  | Preparing to start
Tue (02/07) | 02 Jul 2024 | JTC blk 4 |  | HSL currently no activity
Tue (02/07) | 02 Jul 2024 | DR1 |  | Dongah clearing materials
Tue (02/07) | 02 Jul 2024 | P31-32 |  | KTC continue manual excavation for utility support works
Tue (02/07) | 02 Jul 2024 | BC2 |  | Machine setup ongoing. This rig here will start for panel BRP35
Tue (02/07) | 02 Jul 2024 | Zone 3 |  | Singtel cable works
Tue (02/07) | 02 Jul 2024 | BRP32 |  | Resume excavation from 32/32.87m
Tue (02/07) | 02 Jul 2024 | MH5-2 |  | 2nd lift wall curing
Tue (02/07) | 02 Jul 2024 | Zone 1 P2 area |  | Taking as built of utilities prior to installation of protection
Tue (02/07) | 02 Jul 2024 | ST220 |  | B1 temporarily stopped due to desander issue. CD 37.2/37.9m
Tue (02/07) | 02 Jul 2024 | Zone 1 |  | P4-2 boring completed. Cleaning in progress
Tue (02/07) | 02 Jul 2024 | BP2A-2 | 38 | Boring reached 15/42.213m
Tue (02/07) | 02 Jul 2024 | ST009 |  | B1 in progress, 17/39.2m
Tue (02/07) | 02 Jul 2024 | ST259 |  | B2 in progress, 5/35.1m
Tue (02/07) | 02 Jul 2024 | ST264 |  | WS installation in progress
Tue (02/07) | 02 Jul 2024 | MH5-1 |  | 3rd layer rebar works
Tue (02/07) | 02 Jul 2024 | ST81 |  | Casting in progress
Tue (02/07) | 02 Jul 2024 | Blk 4 |  | HSL preparing to start preboring for UKP38
Tue (02/07) | 02 Jul 2024 | DR1 |  | No activity
Tue (02/07) | 02 Jul 2024 | PBH65 |  | SI in progress
Tue (02/07) | 02 Jul 2024 | Zone 1 |  | Exposing 66kv for spiking
Tue (02/07) | 02 Jul 2024 | BRP35 |  | Excavation started at 1200hrs
Tue (02/07) | 02 Jul 2024 | BRP32 |  | B2 in progress, 32.7/32.87m
Tue (02/07) | 02 Jul 2024 | BRP16 |  | LSS backfill
Tue (02/07) | 02 Jul 2024 | Zone 1 |  | P4-1 preparing for rebar cages lowering
Tue (02/07) | 02 Jul 2024 | MH5-1 |  | Rebar works continue
Tue (02/07) | 02 Jul 2024 | MH5-2 |  | Formwork dismantle in progress
Tue (02/07) | 02 Jul 2024 | P6 |  | Trial trench completed for BP
Tue (02/07) | 02 Jul 2024 | P14 |  | Kentledge demobilisation works
Tue (02/07) | 02 Jul 2024 | P10 |  | Excavation to FEL continue
Tue (02/07) | 02 Jul 2024 | P13 |  | Preparation for stump formwork closing
Tue (02/07) | 02 Jul 2024 | P15 |  | Backfilling to pile cap level. 2nd layer
Tue (02/07) | 02 Jul 2024 | P16 |  | Preboring for ERSS installation in progress, current status: 22/26 SP & 13/26 LP
Tue (02/07) | 02 Jul 2024 | UKP38 |  | Casing installation
Tue (02/07) | 02 Jul 2024 | ST81 |  | Casting ongoing, 153/200m3
Tue (02/07) | 02 Jul 2024 | BC1 |  | Cutter maintenance ongoing
Tue (02/07) | 02 Jul 2024 | MH3-5 |  | Excavation to the next layer done for the day. Housekeeping ongoing
Tue (02/07) | 02 Jul 2024 | Zone 4 |  | P46-7 boring in progress
Tue (02/07) | 02 Jul 2024 | BRP35 |  | Excavation reached 18/32.87m
Tue (02/07) | 02 Jul 2024 | BRP32 |  | B2 completed, internal koden check done. Now cutter teeth changing before starting B3
Tue (02/07) | 02 Jul 2024 | BP2A-2 | 38 | Boring done for the day. CD 28/41.313m
Tue (02/07) | 02 Jul 2024 | ST264 |  | Rebar cage installation in progress, 2/7nos
Tue (02/07) | 02 Jul 2024 | P16 |  | Preboring for ERSS. SP: 18/26, LP:5/26
Tue (02/07) | 02 Jul 2024 | MH3-5 |  | Preparing for next layer works. Next set of BRC will be delivered today
Tue (02/07) | 02 Jul 2024 | N5 crosshead |  | Pipe sleeve for tendons installation in progress. 4/18 installed. 12 nos to install today. Additional 2 nos for future tensioning still pending confirmation from QPD
Tue (02/07) | 02 Jul 2024 | P15 |  | Backfilling in progress
Wed (03/07) | 03 Jul 2024 | ST264 |  | Preparing to start casting
Wed (03/07) | 03 Jul 2024 | P22 |  | Krishco housekeeping and preparing for flushing works this evening
Wed (03/07) | 03 Jul 2024 | N5 |  | Crosshead M&E pipe installation
Wed (03/07) | 03 Jul 2024 | P13 |  | Stump formwork closing
Wed (03/07) | 03 Jul 2024 | P12 |  | Preparation for rebar cage fabrication
Wed (03/07) | 03 Jul 2024 | MH5-2 |  | Backfilling in progress
Wed (03/07) | 03 Jul 2024 | MH3-5 |  | Exposing LP cable to support. Plan to cast 600mm caisson by today
Wed (03/07) | 03 Jul 2024 | UKP38 |  | Verticality check witness by RTO, UKP37: Preboring ongoing
Wed (03/07) | 03 Jul 2024 | PBH67 |  | SI in progress, 8m
Wed (03/07) | 03 Jul 2024 | P3-5 |  | Casing installed for boring works
Wed (03/07) | 03 Jul 2024 | BRP75 |  | Trial trench in progress
Wed (03/07) | 03 Jul 2024 | Between P38-39 |  | Ley Choon continue backfilling for cable pit
Wed (03/07) | 03 Jul 2024 | BRP75 |  | Continue trial trench for guidewall construction
Wed (03/07) | 03 Jul 2024 | BC1 |  | Maintenance ongoing
Wed (03/07) | 03 Jul 2024 | P48 |  | JGP boring work in progress
Wed (03/07) | 03 Jul 2024 | P46-7 |  | Boring reached 28.6m. Continue boring work
Wed (03/07) | 03 Jul 2024 | PBH67 |  | SI in progress, 24m
Wed (03/07) | 03 Jul 2024 | UKP38 |  | Boring in progress, UKP37: Boring completed, Today plan to cast these 2nos
Wed (03/07) | 03 Jul 2024 | TDP67 |  | Preparing for trial trench works
Wed (03/07) | 03 Jul 2024 | PBH65 |  | Coring in progress, 34/45m
Wed (03/07) | 03 Jul 2024 | BRP39 | Rig 4 | Excavation started at 1500hrs
Wed (03/07) | 03 Jul 2024 | P12 |  | Formwork assembly for pier
Wed (03/07) | 03 Jul 2024 | ST264 |  | Casting completed. Total vol: 243m3
Wed (03/07) | 03 Jul 2024 | P15 |  | Concrete plug cast
Wed (03/07) | 03 Jul 2024 | BP2A-2 | 38 | Boring reached 33.4/41.313m
Wed (03/07) | 03 Jul 2024 | P10 |  | Balance 100mm to FEL. Tomorrow HSL to start pile head hacking
Wed (03/07) | 03 Jul 2024 | P16 |  | Preboring for ERSS installation ongoing
Wed (03/07) | 03 Jul 2024 | P14 |  | Kentledge demobilisation works
Wed (03/07) | 03 Jul 2024 | MH5-2 |  | Backfilling works for next layer wall in progress
Wed (03/07) | 03 Jul 2024 | P7-1 |  | 22kV exposed for spiking. Pending confirmation from the agency
Wed (03/07) | 03 Jul 2024 | MH5-1 |  | Formwork closing for 3rd layer permanent wall (part 1)
Wed (03/07) | 03 Jul 2024 | P3-5 |  | Boring works continue. Depth 20/38.6
Wed (03/07) | 03 Jul 2024 | MH3-5 |  | Continue excavation for 2nd ring
Wed (03/07) | 03 Jul 2024 | P16 |  | No activity
Wed (03/07) | 03 Jul 2024 | N5 |  | No activity at the moment
Wed (03/07) | 03 Jul 2024 | P14 |  | Continue unloading and demobilisation of kentledge materials
Wed (03/07) | 03 Jul 2024 | P13 |  | Access platform erection ongoing by WH
Wed (03/07) | 03 Jul 2024 | P10 |  | Excavation to FEL completed. Mini excavator has been hoisted up
Wed (03/07) | 03 Jul 2024 | MH5-2 |  | Activity done for the day
Wed (03/07) | 03 Jul 2024 | MH5-1 |  | Continue formwork closing
Wed (03/07) | 03 Jul 2024 | ST259 |  | B2 in progress, 17/35.1m
Wed (03/07) | 03 Jul 2024 | ST224 |  | Excavation started at 1600hrs. Current depth 10/33.4m
Wed (03/07) | 03 Jul 2024 | BP2A-2 | 38 | Boring reached 35/41.313m
Wed (03/07) | 03 Jul 2024 | ST220 |  | WS installation in progress
Wed (03/07) | 03 Jul 2024 | BRP32 |  | Hanging bar lapping in progress
Wed (03/07) | 03 Jul 2024 | UKP37, UKP38 |  | Completed
Wed (03/07) | 03 Jul 2024 | BRP32 |  | Rebar cage hanging bar safely lowered. Thereafter continue KP hanging bar
Wed (03/07) | 03 Jul 2024 | P46-7 |  | Boring in progress
Thu (04/07) | 04 Jul 2024 | ST009 |  | Excavation temporarily stopped. Pending hydrofraise
Thu (04/07) | 04 Jul 2024 | ST227 |  | Guidewall rebar works ongoing. Target to cast today
Thu (04/07) | 04 Jul 2024 | ST224 |  | Excavation temporarily stopped for gearbox change. CD 33/33.4m
Thu (04/07) | 04 Jul 2024 | BP2A-2 | 38 | Preparing to resume boring
Thu (04/07) | 04 Jul 2024 | BRP39 |  | Bentonite line preparation ongoing. B1 CD 15/25.07m
Thu (04/07) | 04 Jul 2024 | ST82 Rig 1 |  | Excavation CD 11.38m
Thu (04/07) | 04 Jul 2024 | MH3-5 |  | Target to cast 2nd ring today
Thu (04/07) | 04 Jul 2024 | Zone 4 |  | B-346 ongoing for JGP work
Thu (04/07) | 04 Jul 2024 | P16 |  | Soldier pile installation in progress
Thu (04/07) | 04 Jul 2024 | DR2 canal |  | Grass clearing ongoing by WH
Thu (04/07) | 04 Jul 2024 | P41 |  | Today plan recharge well installation for RW100
Thu (04/07) | 04 Jul 2024 | P15 |  | Backfilling to stump level
Thu (04/07) | 04 Jul 2024 | P12 |  | Rebar cage fabrication
Thu (04/07) | 04 Jul 2024 | P9 |  | Premix hacking for ERSS trial trench
Thu (04/07) | 04 Jul 2024 | P16 |  | ERSS installation in progress
Thu (04/07) | 04 Jul 2024 | P14 |  | HSL kentledge demobilized works
Thu (04/07) | 04 Jul 2024 | ST82 |  | B1 excavation in progres
Thu (04/07) | 04 Jul 2024 | TDP65 |  | Hacking ongoing for trial trench works
Thu (04/07) | 04 Jul 2024 | PBH79 |  | Hand auger in progress
Thu (04/07) | 04 Jul 2024 | BRP32 |  | KP and rebar cage lowered
Thu (04/07) | 04 Jul 2024 | BC3 |  | Cutter wheel rectification ongoing
Thu (04/07) | 04 Jul 2024 | MH5-1 |  | 3rd layer 1st part backfilling
Thu (04/07) | 04 Jul 2024 | ST220 |  | Rebar cage installation ongoing, 2/4nos. First lapping completed. Waiting RTO inspection
Thu (04/07) | 04 Jul 2024 | BP2A-2 | 38 | Boring in progress, 36.3/41.313m
Thu (04/07) | 04 Jul 2024 | ST227 |  | Guidewall construction in progress
Thu (04/07) | 04 Jul 2024 | BP2A-1 | 22 | Trial trench ongoing. Cables exposed
Thu (04/07) | 04 Jul 2024 | ST224 |  | Excavation in progress, 26.5/33.4m
Thu (04/07) | 04 Jul 2024 | P2 |  | Trial trench - Excavation to expose 66kV
Thu (04/07) | 04 Jul 2024 | P3-5 |  | Tremie pipe lowered. Preparing for casting
Thu (04/07) | 04 Jul 2024 | Zone 3 |  | NLT cable recovery ongoing
Thu (04/07) | 04 Jul 2024 | P46-7 |  | Rebar cage lapping. Today to cast
Thu (04/07) | 04 Jul 2024 | MH3-5 |  | Formwork closing for 2nd layer casting
Thu (04/07) | 04 Jul 2024 | P41 |  | 1 point recharge well pipe installed. 2nd point boring for today
Thu (04/07) | 04 Jul 2024 | ST81 |  | 1st bite reached 24.4m. Now welding of flange
Thu (04/07) | 04 Jul 2024 | TDP65 |  | TT on going
Thu (04/07) | 04 Jul 2024 | PBH76 |  | Hand augering in progress. PBH79: TT and hand augering done
Thu (04/07) | 04 Jul 2024 | BRP39 |  | Preparing to change mud pump
Thu (04/07) | 04 Jul 2024 | MH5-2 |  | Wall rebar installation for next layer ongoing
Thu (04/07) | 04 Jul 2024 | BC cutter No-3 |  | Cutter wheel changing
Thu (04/07) | 04 Jul 2024 | N5 |  | Now no activity already
Thu (04/07) | 04 Jul 2024 | P13 |  | Tie rods installation for column
Thu (04/07) | 04 Jul 2024 | P10 |  | Lean concrete at the base
Thu (04/07) | 04 Jul 2024 | MH5-2 |  | Now no activity
Thu (04/07) | 04 Jul 2024 | P46-7 |  | Casting in progress
Thu (04/07) | 04 Jul 2024 | ST259 |  | B2 excavation temporarily stopped for cutter teeth rectification
Fri (05/07) | 05 Jul 2024 | ST259 |  | B2 in progress, 33.5m/35.1m
Fri (05/07) | 05 Jul 2024 | ST224 |  | Trimming ongoing for endplate removal
Fri (05/07) | 05 Jul 2024 | P17 |  | Excavation for PDA, Testing Tomorrow
Fri (05/07) | 05 Jul 2024 | P16 |  | ERSS SP driving, 18/26 completed
Fri (05/07) | 05 Jul 2024 | BP2A-2 | 38 | Boring ongoing
Fri (05/07) | 05 Jul 2024 | PBH79 |  | Coring in progress
Fri (05/07) | 05 Jul 2024 | TDP83 |  | Trial trench in progress
Fri (05/07) | 05 Jul 2024 | BRP74 |  | Guidewall rebar works ongoing
Fri (05/07) | 05 Jul 2024 | P13 |  | Additional tie rods installed as per QPS comment. Casting today at 6pm
Fri (05/07) | 05 Jul 2024 | P10 |  | Pipe support for unaligned steel plate in progress
Fri (05/07) | 05 Jul 2024 | BP2A-2 | 38 | Current depth 38/41.313m
Fri (05/07) | 05 Jul 2024 | ST82 |  | Excavation temporarily stopped for gear box changing. CD 31/33.5m
Fri (05/07) | 05 Jul 2024 | BRP35 |  | To cast today
Fri (05/07) | 05 Jul 2024 | BRP39 |  | B2 in progress, 4.5/25.07m. B1 temporarily stopped due to booster pump repair. B1 CD 17.1/25.07m
Fri (05/07) | 05 Jul 2024 | BC3 |  | Continue maintenance works
Fri (05/07) | 05 Jul 2024 | Exit 2 |  | Pre-excavation ongoing for DW42
Fri (05/07) | 05 Jul 2024 | MH5-1 |  | 3rd layer part 2 rebar installation
Fri (05/07) | 05 Jul 2024 | ST220 |  | Casting in progress, 27/140m3
Fri (05/07) | 05 Jul 2024 | Zone 1 P2 area |  | Exposing 66KV for spiking
Fri (05/07) | 05 Jul 2024 | P45-6 |  | Boring reached 18m. Tomorrow to cast
Fri (05/07) | 05 Jul 2024 | MH3-5 |  | Preparing for formwork removal
Fri (05/07) | 05 Jul 2024 | BRP74 |  | Formwork closing for guidewall
Fri (05/07) | 05 Jul 2024 | TDP83 |  | TT done. No services
Fri (05/07) | 05 Jul 2024 | PBH79- boring reached 22.2m. PBH76 |  | Boring reached 26m
Fri (05/07) | 05 Jul 2024 | DR1 |  | LE prepare platform for COS
Fri (05/07) | 05 Jul 2024 | BRP39 |  | 2nd bite excavation, reached 6.2m
Fri (05/07) | 05 Jul 2024 | BC cutter No-3 |  | Replacing of hydraulic hoses for cutter
Fri (05/07) | 05 Jul 2024 | BP2A-2 | 38 | Boring reached 40.5m. Now weekly inspection of wire by woh hup
Fri (05/07) | 05 Jul 2024 | ST220 |  | Casting in progress, 90m3/140m3
Fri (05/07) | 05 Jul 2024 | P16 |  | Soldier pile installation
Fri (05/07) | 05 Jul 2024 | P13 |  | Column casting
Fri (05/07) | 05 Jul 2024 | P10 |  | C channel welding to rectify the gap
Fri (05/07) | 05 Jul 2024 | MH5-2 |  | Shaft wall rebar work in progress
Fri (05/07) | 05 Jul 2024 | MH5-1 |  | Manhole wall rebar work in progress. Tomorrow to cast
Fri (05/07) | 05 Jul 2024 | ST259 |  | 3rd bite excavation done. Preparing for waterstop end plate side trimming
Fri (05/07) | 05 Jul 2024 | ST009 |  | Grabbing done. Preparing to continue excavation
Fri (05/07) | 05 Jul 2024 | N5 |  | Crosshead rebar dismantling
Fri (05/07) | 05 Jul 2024 | P48 |  | Platform preparing for JGP work
Fri (05/07) | 05 Jul 2024 | P45-6 |  | HSL installed casing. Today to continue excavation
Fri (05/07) | 05 Jul 2024 | ST81 |  | B1 temporarily stopped. Mud hose replacement ongoing
Fri (05/07) | 05 Jul 2024 | MH3-5 |  | Now tidy up the area. Will resume 3rd layer excavation today
Fri (05/07) | 05 Jul 2024 | BRP35 |  | Rebar cage installation in progress
Fri (05/07) | 05 Jul 2024 | BC3 |  | Continue cutter wheel/ teeth maintenance
Fri (05/07) | 05 Jul 2024 | BP2A-2 | 38 | Boring resumed from 37/41.313m
Sat (06/07) | 06 Jul 2024 | Zone 3 Bachy |  | STN-009 1st bite trenching in progress, current depth 27.9m/39.2m
Sat (06/07) | 06 Jul 2024 | STN-228 |  | Partial Guide wall installation works
Sat (06/07) | 06 Jul 2024 | BP2A-2 | 38 | Boring completed. Preparing for rebar cage lowering and casting
Sat (06/07) | 06 Jul 2024 | Exit 2 |  | DW42 preparation to start excavation
Sat (06/07) | 06 Jul 2024 | BRP32 |  | Preparing for LSS backfill
Sat (06/07) | 06 Jul 2024 | BRP35 |  | Preparing for LSS backfill
Sat (06/07) | 06 Jul 2024 | BRP39 |  | 2nd bite trenching temporarily stopped. Cutter teeth changing in progress
Sat (06/07) | 06 Jul 2024 | P34 |  | PBH-76 drilling completed
Sat (06/07) | 06 Jul 2024 | PBH-79 |  | Drilling in progress, current depth 24.7m
Sat (06/07) | 06 Jul 2024 | UKP33 |  | Trial trench completed. Preparing for backfilling
Sat (06/07) | 06 Jul 2024 | DR-1 |  | Excavation for ERSS installation works. Extraction of previous installed soldier pile to join another 1m soldier pile
Sat (06/07) | 06 Jul 2024 | STN160 & STN159 half |  | Trial trench completed for Guidewall. Backfilling works in progress
Sat (06/07) | 06 Jul 2024 | STN-82 |  | Trenching for 2nd bite completed. Preparing for water stop removal
Sat (06/07) | 06 Jul 2024 | BRP-74 |  | Guidewall to cast in the afternoon
Sat (06/07) | 06 Jul 2024 | RW-77 |  | Installation works ongoing
Sat (06/07) | 06 Jul 2024 | A-22 |  | JGP works ongoing, drilling completed
Sat (06/07) | 06 Jul 2024 | MH3-5 |  | Excavation for 3rd layer in progress
Sat (06/07) | 06 Jul 2024 | Zone 4 |  | P45-6 BP boring works in progress
Sat (06/07) | 06 Jul 2024 | Zone 4 |  | Point B-402 JGP completed. Now preparing for B-457 JGP works
Sat (06/07) | 06 Jul 2024 | Zone 4 |  | Road depression rectification works in progress. Area was not backfilled properly by previous contractor
Sat (06/07) | 06 Jul 2024 | P18 |  | Setting up for PDA test today
Sat (06/07) | 06 Jul 2024 | P17 |  | Preparation for PDA test today. To do after P18 PDA complete
Sat (06/07) | 06 Jul 2024 | N5 |  | Current rebar status
Sat (06/07) | 06 Jul 2024 | P16 |  | ERSS installation in progress. To complete by today
Sat (06/07) | 06 Jul 2024 | P13 |  | Column stump cast yesterday
Sat (06/07) | 06 Jul 2024 | P12 |  | Column rebar cage fabrication
Sat (06/07) | 06 Jul 2024 | P10 |  | Preparation to start pile head hacking in the afternoon
Sat (06/07) | 06 Jul 2024 | MH5-2 |  | Rebar & Formwork closing works for 3rd lift wall. Today to cast
Sat (06/07) | 06 Jul 2024 | MH5-1 |  | Formwork closing for last, Lift RC wall. Today to cast
Sat (06/07) | 06 Jul 2024 | P3-1 |  | BP boring in progress, current depth 10m
Sat (06/07) | 06 Jul 2024 | P49 |  | Drain hacking and removal works
Sat (06/07) | 06 Jul 2024 | Zone 4 |  | Trial trench & pipe sleeve installation for JGP B-352. B-457 will be done another day
Sat (06/07) | 06 Jul 2024 | Zone 4 |  | P45-6 BP boring works completed. Rebar cage lapping and lowering in progress
Sat (06/07) | 06 Jul 2024 | MH3-5 |  | Continue excavation works for 3rd layer wall
Sat (06/07) | 06 Jul 2024 | A-58 |  | JGP works, drilling in progress
Sat (06/07) | 06 Jul 2024 | BRP-74 | Guide wall | Pending concrete truck to arrive for casting
Sat (06/07) | 06 Jul 2024 | STN-82 |  | Trimming works ongoing
Sat (06/07) | 06 Jul 2024 | STN160 & STN159 half |  | Preparation for Guidewall rebar installation
Sat (06/07) | 06 Jul 2024 | PBH-79 |  | Drilling in progress, current depth 27m
Sat (06/07) | 06 Jul 2024 | DR-1 |  | Soldier pile extraction in progress for 1.0m extension works
Sat (06/07) | 06 Jul 2024 | BRP39 |  | 2nd bite trenching in progress, current depth 18m
Sat (06/07) | 06 Jul 2024 | BRP37 |  | Pre-excavation in progress
Sat (06/07) | 06 Jul 2024 | BC Cutter 03 |  | Repairing works in progress
Sat (06/07) | 06 Jul 2024 | Exit 2 |  | DW42 1st bite trenching in progress
Sat (06/07) | 06 Jul 2024 | BP2A-2 | 38 | Rebar cages lowered. Preparing for casting in progress
Sat (06/07) | 06 Jul 2024 | STN-224 |  | Rebar cages lowering in progress. 1/4 nos. lowered
Sat (06/07) | 06 Jul 2024 | STN-228 |  | Partial Guide wall Formwork closed. Pending casting
Sat (06/07) | 06 Jul 2024 | Zone 3 Bachy |  | STN-009 1st bite trenching in progress, current depth 31.5m/39.2m
Sat (06/07) | 06 Jul 2024 | Zone 3 Bachy |  | STN-259 rebar cages lowering in progress. 2/8 nos. lowered
Sat (06/07) | 06 Jul 2024 | Zone 3 Bachy |  | STN-262 1st bite trenching in progress, current depth 14m
Sat (06/07) | 06 Jul 2024 | P18 |  | PDA testing completed
Sat (06/07) | 06 Jul 2024 | P17 |  | Setting up for PDA test in progress
Sat (06/07) | 06 Jul 2024 | P16 |  | ERSS installation to required embedment depth ongoing. To complete by today
Sat (06/07) | 06 Jul 2024 | N5 Crosshead |  | Current rebar status
Sat (06/07) | 06 Jul 2024 | P12 |  | Working platform / Scaffold installation
Sat (06/07) | 06 Jul 2024 | P10 |  | Pile head hacking in progress
Sat (06/07) | 06 Jul 2024 | S4 |  | No activity
Sat (06/07) | 06 Jul 2024 | MH5-1 |  | Last lift RC wall casting in progress
Sat (06/07) | 06 Jul 2024 | MH5-2 |  | Pending concrete truck to arrive for 3rd lift wall casting
Sat (06/07) | 06 Jul 2024 | P3-1 |  | BP boring works in progress
Sat (06/07) | 06 Jul 2024 | N3 |  | Levelling for falsework erection
Sat (06/07) | 06 Jul 2024 | P12 |  | Working platform erection for column rebar lapping
Sat (06/07) | 06 Jul 2024 | MH5-2 |  | 3rd layer part 2 casting completed
Sat (06/07) | 06 Jul 2024 | Zone 1 |  | No more activity
Sat (06/07) | 06 Jul 2024 | STN262 |  | 1st bite trenching at 17m/39.6m
Sat (06/07) | 06 Jul 2024 | STN259 |  | Rebar cage lowering, 5/8 cages completed. 6th cage installation in progress
Sat (06/07) | 06 Jul 2024 | STN2009 |  | 1st bite trenching at 32.5m/39.2m
Sat (06/07) | 06 Jul 2024 | STN224 |  | Rebar cage installation. 3/4 cages installed. 3rd cage lapping in progress
Sat (06/07) | 06 Jul 2024 | DW42-BC2 |  | Hydraulic hose leaking. Need to replace. Current at 1st bite 12/30.2m depth
Sat (06/07) | 06 Jul 2024 | BRP39 |  | 1st bite: 17.1m/25.07m, 2nd bite: 18.1m/25.07m, in progress, Cutter wheel maintenance in progress
Sat (06/07) | 06 Jul 2024 | ST82 |  | End plate extraction in progress
Sat (06/07) | 06 Jul 2024 | Zone 3 Bachy |  | STN-262 1st bite trenching in progress, current depth 10m
Sat (06/07) | 06 Jul 2024 | Zone 3 Bachy |  | STN-259 water stop lowering & installation
Sun (07/07) | 07 Jul 2024 | BC cutter 1 |  | Maintenance
Sun (07/07) | 07 Jul 2024 | BC cutter 2 |  | Replacing hydraulic hoses for cutter
Sun (07/07) | 07 Jul 2024 | BC cutter 3 |  | Replacing teeth for cutter wheel. Today more on casting and machine maintenance
Sun (07/07) | 07 Jul 2024 | STN224 |  | Last cage installation in progress
Sun (07/07) | 07 Jul 2024 | STN009 |  | Trenching continue
Sun (07/07) | 07 Jul 2024 | ST82 |  | Tremie pipe lowering for casting
Sun (07/07) | 07 Jul 2024 | DW42 |  | Current excavation depth 19m
Sun (07/07) | 07 Jul 2024 | BRP39 |  | 1st bite: 17.1m/25.07m, 2nd bite: 18.1m/25.07m, resumed
Sun (07/07) | 07 Jul 2024 | ST82 |  | End plate extracted. Cleaning and desanding also completed. preparation for final koden test
Sun (07/07) | 07 Jul 2024 | STN224 |  | Tremie pipes installed.. waiting for concrete lorry
Sun (07/07) | 07 Jul 2024 | STN262 |  | Status, 1st bite at 26m/39.6m, 2nd bite at 7m/39.6
Sun (07/07) | 07 Jul 2024 | STN009 |  | 1st bite trenching at 35m/39.2m
Sun (07/07) | 07 Jul 2024 | STN259 |  | Casting in progress, 79.5/243 m3
Sun (07/07) | 07 Jul 2024 | ST224 |  | Concrete on site to start casting
Sun (07/07) | 07 Jul 2024 | N5 |  | Removal of rebars. They will try to complete today
Mon (08/07) | 08 Jul 2024 | N5 dismantling |  | Balance bottom main bars
Mon (08/07) | 08 Jul 2024 | ST262 |  | B2 in progress
Mon (08/07) | 08 Jul 2024 | ST009 |  | B2 in progress, 36/39.2m
Mon (08/07) | 08 Jul 2024 | P16 |  | Excavation to w1 layer in progress
Mon (08/07) | 08 Jul 2024 | ST16 |  | Guidewall trial trench ongoing
Mon (08/07) | 08 Jul 2024 | Blk 4 |  | 2nos HSL rigs on site — Sany400 and BG25
Mon (08/07) | 08 Jul 2024 | MH5-1 |  | 3rd layer part 2 formwork dismantling
Mon (08/07) | 08 Jul 2024 | UKP34 |  | Toe confirmed at 15.8m
Mon (08/07) | 08 Jul 2024 | DW42 Rig 3 |  | Wire rope replacement is in progress
Mon (08/07) | 08 Jul 2024 | DR1 |  | LE continue soldier pile extraction for the 1m extension
Mon (08/07) | 08 Jul 2024 | TDP69 |  | Trial trench ongoing. Found some services, dewatering ongoing
Mon (08/07) | 08 Jul 2024 | BRP32 |  | Ready to backfill with LSS
Mon (08/07) | 08 Jul 2024 | BRP37 Rig 2 |  | B2 CD 22.9/32.66m
Mon (08/07) | 08 Jul 2024 | BRP39 Rig 4 |  | B2 CD 18.8/25.07m
Mon (08/07) | 08 Jul 2024 | P16 |  | Current status of excavation
Mon (08/07) | 08 Jul 2024 | P10 |  | Pile head hacking
Mon (08/07) | 08 Jul 2024 | P3-1 |  | Tremie pipe lowering down
Mon (08/07) | 08 Jul 2024 | MH5-2 |  | Clearing materials already shaft for backfilling
Mon (08/07) | 08 Jul 2024 | ST262 |  | 2nd bite, reached 9m
Mon (08/07) | 08 Jul 2024 | BRP32 |  | LSS backfilling
Mon (08/07) | 08 Jul 2024 | BRP39 |  | Reached 18.8m
Mon (08/07) | 08 Jul 2024 | DR1 |  | Soldier lapping & welding
Mon (08/07) | 08 Jul 2024 | BC cutter 1 |  | Cutter wheel maintenance
Mon (08/07) | 08 Jul 2024 | Zone 4 |  | 4th JGP point grouting
Tue (09/07) | 09 Jul 2024 | DW42 Rig 3 |  | B2 CD 28/30.2m
Tue (09/07) | 09 Jul 2024 | P16 |  | KTC continue excavation for 1st layer waler installation
Tue (09/07) | 09 Jul 2024 | N5 |  | Now started removal of Wingform
Tue (09/07) | 09 Jul 2024 | P10 |  | Pile head hacking
Tue (09/07) | 09 Jul 2024 | P13 |  | Column formwork removal
Tue (09/07) | 09 Jul 2024 | BRP37 Rig 2 |  | B2 CD 23.4/32.66m, coolant water pipe repairing since 9am
Tue (09/07) | 09 Jul 2024 | BRP39 Rig 4 |  | B2 CD 19.35/25.07m
Tue (09/07) | 09 Jul 2024 | P46-6 |  | Boring in progress, reached 26m
Tue (09/07) | 09 Jul 2024 | MH3-5 |  | Continue excavation for next layer casting
Tue (09/07) | 09 Jul 2024 | P16 |  | Excavation to s1 layer completed. Soil disposal ongoing
Tue (09/07) | 09 Jul 2024 | P15 |  | Column rebar fabrication in progress
Tue (09/07) | 09 Jul 2024 | P13 |  | Column stump formwork dismantle and removal
Tue (09/07) | 09 Jul 2024 | P14 |  | LE trial trench works for ERSS installation
Tue (09/07) | 09 Jul 2024 | P12 |  | Uclip installation for column rebar cage
Tue (09/07) | 09 Jul 2024 | P10 |  | Pile head hacking in progress. 4/6 nos. completed
Tue (09/07) | 09 Jul 2024 | P46-6 |  | Boring in progress, reached 27m
Tue (09/07) | 09 Jul 2024 | P6 |  | 22kV spiked and cut
Tue (09/07) | 09 Jul 2024 | MH5-1 |  | 1st chamber ring installation ongoing
Tue (09/07) | 09 Jul 2024 | MH5-2 |  | Backfilling works for 1st chamber ring installation
Tue (09/07) | 09 Jul 2024 | P3-1 |  | BP cast last week
Tue (09/07) | 09 Jul 2024 | MH3-5 |  | Rebar/ BRC installed for 600mm layer casting
Tue (09/07) | 09 Jul 2024 | TDP106 |  | Boring in progress. Plan for casting today
Tue (09/07) | 09 Jul 2024 | UKP33 |  | Boring done. Will cast today
Tue (09/07) | 09 Jul 2024 | DR1 |  | Continue soldier pile lapping
Tue (09/07) | 09 Jul 2024 | BRP39 |  | Cutter teeth replacement done. Excavation reached 19.5m
Tue (09/07) | 09 Jul 2024 | BRP31 |  | Guidewall casting
Tue (09/07) | 09 Jul 2024 | ST42 |  | 1st bite excavation completed
Tue (09/07) | 09 Jul 2024 | N4 |  | Netting installation around barricade and tidy up the area
Tue (09/07) | 09 Jul 2024 | P14 |  | TT on going for preboring for ERSS work
Tue (09/07) | 09 Jul 2024 | P10 |  | Pile head hacking
Tue (09/07) | 09 Jul 2024 | MH5-2 |  | Current status of backfilling
Tue (09/07) | 09 Jul 2024 | MH5-1 |  | Formwork closing in progress. Today to cast
Tue (09/07) | 09 Jul 2024 | Zone 4 |  | No activity of HSL already
Tue (09/07) | 09 Jul 2024 | ST262 |  | B2 CD 22/39.2m
Tue (09/07) | 09 Jul 2024 | ST009 |  | B1 CD 38.9/39.2m. Chiseling (10ton) in progress at the drop height of 1m
Wed (10/07) | 10 Jul 2024 | DW42 Rig 3 |  | Trimming in progress for end plate removal
Wed (10/07) | 10 Jul 2024 | P15 |  | Column rebar cage fabrication in progress
Wed (10/07) | 10 Jul 2024 | P51 |  | Exposing of water pipe for POWS approval
Wed (10/07) | 10 Jul 2024 | Zone 4 |  | 1st point JGP grouting
Wed (10/07) | 10 Jul 2024 | BRP37 Rig 2 |  | B1 CD 32.5/32.66m
Wed (10/07) | 10 Jul 2024 | BRP39 Rig 4 |  | Gear box replacement in progress
Wed (10/07) | 10 Jul 2024 | P10 |  | Pile head hacking in progress
Wed (10/07) | 10 Jul 2024 | P9 |  | Preparation for preboring works for ERSS installation
Wed (10/07) | 10 Jul 2024 | MH5-2 |  | Installation of 1st precast chamber ring ongoing. Today to cast
Wed (10/07) | 10 Jul 2024 | MH5-1 |  | 1st precast chamber ring installed and cast yesterday
Wed (10/07) | 10 Jul 2024 | MH3-5 |  | Preparing to resume excavation
Wed (10/07) | 10 Jul 2024 | Zone 1 |  | HSL desander shifting
Wed (10/07) | 10 Jul 2024 | ST160 Rig 1 |  | B1 CD 23.5/41.15m
Wed (10/07) | 10 Jul 2024 | Zone 1 |  | Lane closed for Vibro mobilisation to P2
Wed (10/07) | 10 Jul 2024 | P2 |  | Vibro arrived, will unload after lunch
Wed (10/07) | 10 Jul 2024 | MH3-5 |  | Manual excavation to support drain
Wed (10/07) | 10 Jul 2024 | P16 |  | Waler brackets installation
Wed (10/07) | 10 Jul 2024 | N5 |  | Continue falsework dismantle
Wed (10/07) | 10 Jul 2024 | P15 |  | Column rebar cage fabrication in progress
Wed (10/07) | 10 Jul 2024 | P14 |  | Trial trench for instrumentation installation in progress. To start drilling tmr
Wed (10/07) | 10 Jul 2024 | P10 |  | Pile head hacking and trimming works
Wed (10/07) | 10 Jul 2024 | Zone 4 |  | 3rd point JGP grouting in progress
Wed (10/07) | 10 Jul 2024 | P46-6 |  | Rebar cage lowering. Today to cast
Wed (10/07) | 10 Jul 2024 | MH5-1 |  | Formwork removal ongoing for 1st precast chamber ring
Wed (10/07) | 10 Jul 2024 | MH5-2 |  | Formwork installation for 1st precast chamber ring
Wed (10/07) | 10 Jul 2024 | Zone 1 |  | LE Kelly bar set up works ongoing, boring rig otw to site
Wed (10/07) | 10 Jul 2024 | P2 |  | Vibro machine on site now
Wed (10/07) | 10 Jul 2024 | MH3-5 |  | Continue manual excavation
Wed (10/07) | 10 Jul 2024 | P37-P43 |  | Recharge well- 39/40nos done. Tomorrow can complete this last point
Wed (10/07) | 10 Jul 2024 | TDP107 |  | Boring reached 12m/14.380m. Today to cast
Wed (10/07) | 10 Jul 2024 | UKP35 |  | Boring reached 15.872m. Today to cast
Wed (10/07) | 10 Jul 2024 | DR1 |  | Soldier pile extension welding on going with 2 welders
Wed (10/07) | 10 Jul 2024 | PBH77 |  | Reached 25m/30m. PBH54: hand augering done
Wed (10/07) | 10 Jul 2024 | BC cutter 4 |  | Gear box changing
Wed (10/07) | 10 Jul 2024 | BRP37 |  | Excavation completed. Prepare platform for rebar cage lowering down
Wed (10/07) | 10 Jul 2024 | DW42 |  | Waterstop end plate removal
Wed (10/07) | 10 Jul 2024 | P16 |  | Waler bracket installation and welding
Wed (10/07) | 10 Jul 2024 | N5 |  | Status of falsework removal
Wed (10/07) | 10 Jul 2024 | P10 |  | Hardcore clearing
Wed (10/07) | 10 Jul 2024 | P9 |  | Platform preparation to start preboring work
Wed (10/07) | 10 Jul 2024 | MH5-2 |  | Shaft wall formwork closing done. Preparing for inspection and casting
Wed (10/07) | 10 Jul 2024 | MH5-1 |  | Backfilling
Wed (10/07) | 10 Jul 2024 | BRP8 |  | TT done. Found HT, Starhub and water pipe
Wed (10/07) | 10 Jul 2024 | P46-6 |  | Casting completed. Housekeeping before go back
Wed (10/07) | 10 Jul 2024 | P16 |  | Preparation for waler beam installation
Wed (10/07) | 10 Jul 2024 | N5 |  | Falsework dismantle works in progress
Thu (11/07) | 11 Jul 2024 | P15 |  | Waler bracket welding
Thu (11/07) | 11 Jul 2024 | P13 |  | Backfilling to pile cap level going to start
Thu (11/07) | 11 Jul 2024 | P9 |  | Preparation for ERSS pre-boring
Thu (11/07) | 11 Jul 2024 | MH5-2 |  | Preparation for backfilling
Thu (11/07) | 11 Jul 2024 | P48 |  | 2nd point grouting done. Preparing for 3rd point boring
Thu (11/07) | 11 Jul 2024 | P50 |  | Exposing of water pipe for POWS approval. This is the last point to expose. The rest of area done
Thu (11/07) | 11 Jul 2024 | MH3-5 |  | Preparing for rebar inspection before formwork closing. Today to cast
Thu (11/07) | 11 Jul 2024 | BRP39 Rig 4 |  | B2 CD 19.75/25.07m
Thu (11/07) | 11 Jul 2024 | DR1 |  | 14/24 soldier piles extended
Thu (11/07) | 11 Jul 2024 | ST160 Rig 1 |  | B2 CD 17/41.15m
Thu (11/07) | 11 Jul 2024 | ST219 |  | 1st bite trenching continue, depth at 27m
Thu (11/07) | 11 Jul 2024 | BRP39 |  | 2nd bite trenching at 19.85/25.07m
Thu (11/07) | 11 Jul 2024 | TDP104 &105 |  | Boring done and Tremie pipe installed. Waiting for concrete lorry
Thu (11/07) | 11 Jul 2024 | P43-44 GI works |  | Grouting for 2nd point
Thu (11/07) | 11 Jul 2024 | Zone 4 |  | HSL stopped work for the day
Thu (11/07) | 11 Jul 2024 | MH3-5 |  | 3rd layer (part 2) casting
Thu (11/07) | 11 Jul 2024 | P16 |  | Waler beam installation
Thu (11/07) | 11 Jul 2024 | P15 |  | Waler beam and bracket dismantling
Thu (11/07) | 11 Jul 2024 | P10 |  | Lean concrete completed
Thu (11/07) | 11 Jul 2024 | P46-6 |  | Cast yesterday night. Today will do LSS backfilling. Tomorrow start P46-5
Fri (12/07) | 12 Jul 2024 | P13 |  | Backfilling to pile cap level
Fri (12/07) | 12 Jul 2024 | P10 |  | Guide bar installation started
Fri (12/07) | 12 Jul 2024 | P9 |  | Pre-boring for ERSS started
Fri (12/07) | 12 Jul 2024 | Zone 4 |  | 1st point JGP in progress
Fri (12/07) | 12 Jul 2024 | P46-5 |  | Preboring started
Fri (12/07) | 12 Jul 2024 | ST228 Rig 2 |  | B1 CD 29/32.1m, now changing of teeth
Fri (12/07) | 12 Jul 2024 | BRP39 Rig 4 |  | B2 CD 20.15/25.07m
Fri (12/07) | 12 Jul 2024 | MH5-2 |  | Backfilling
Fri (12/07) | 12 Jul 2024 | Zone 1 P2 island |  | Tonight to shift rig
Fri (12/07) | 12 Jul 2024 | ST160 Rig 1 |  | B2 CD 17/41.15m
Fri (12/07) | 12 Jul 2024 | MH1-2 |  | CGS Kerb rectification and casting works
Fri (12/07) | 12 Jul 2024 | P9 |  | ERSS preboring works ongoing
Fri (12/07) | 12 Jul 2024 | P10 |  | Manual hacking works for pile head. Today to complete
Fri (12/07) | 12 Jul 2024 | P14 |  | Drilling for inclinometer installation, current depth 3m
Fri (12/07) | 12 Jul 2024 | P13 |  | Backfilling to w1 layer in progress
Fri (12/07) | 12 Jul 2024 | P15 |  | Extraction of waler beams and struts completed. Preparation for backfilling works
Fri (12/07) | 12 Jul 2024 | P46-5 |  | Boring reached 16m
Fri (12/07) | 12 Jul 2024 | P51 |  | Exposing of 22KV to get back to PowerGrid
Fri (12/07) | 12 Jul 2024 | ST17 |  | Guidewall rebar works in progress
Fri (12/07) | 12 Jul 2024 | ST228 |  | 1st bite trenching at 29.9m. Slurry pipe leaking, rectification on going
Fri (12/07) | 12 Jul 2024 | STN09 |  | 2nd bite trenching in progress, depth 38.7m
Fri (12/07) | 12 Jul 2024 | TDP63 |  | Boring works in progress. To cast today
Fri (12/07) | 12 Jul 2024 | TDP67 |  | Casing installed. To continue boring tomorrow
Fri (12/07) | 12 Jul 2024 | STN160 |  | 1st bite trenching continue
Fri (12/07) | 12 Jul 2024 | P15 |  | Waler welding in progress
Fri (12/07) | 12 Jul 2024 | N4 |  | Falsework lower down by 200mm
Fri (12/07) | 12 Jul 2024 | ST009 |  | B2 CD 36.1/39.2m
Sat (13/07) | 13 Jul 2024 | P7 |  | Soil excavation to remove abandoned gas pipe
Sat (13/07) | 13 Jul 2024 | Zone 4 GI works |  | Grouting for 1st point. 3 nos target today
Sat (13/07) | 13 Jul 2024 | P46-5 |  | Boring works, 26m depth
Sat (13/07) | 13 Jul 2024 | MH3-5 |  | Manual excavation for 4th layer
Sat (13/07) | 13 Jul 2024 | P43-44 GI works |  | Drilling for 1st point
Sat (13/07) | 13 Jul 2024 | Zone 1 |  | To shift the boring rig tonight
Sat (13/07) | 13 Jul 2024 | BH96 & 97 |  | TT in progress
Sat (13/07) | 13 Jul 2024 | STN160-BC1 |  | 3rd bite trenching started
Sat (13/07) | 13 Jul 2024 | DR1 |  | SP extension welding works on going
Sat (13/07) | 13 Jul 2024 | BR5B3-BC04 | BRP39 | Trenching continue
Sat (13/07) | 13 Jul 2024 | BP4A-2 | 43 | TT on going
Sat (13/07) | 13 Jul 2024 | STN219-BC3 |  | B1 internal Koden test
Sat (13/07) | 13 Jul 2024 | STN228-BC2 |  | Cutter wheel teeth replacement
Sat (13/07) | 13 Jul 2024 | STN009 |  | End plate lowering
Sat (13/07) | 13 Jul 2024 | STN004 |  | B1 trenching in progress
Sat (13/07) | 13 Jul 2024 | STN262 |  | B1 trenching at 28/39.6m depth
Sat (13/07) | 13 Jul 2024 | STN262 |  | Cutter body hoist up for maintenance
Sat (13/07) | 13 Jul 2024 | STN009 |  | EndPlate fully lowered. Preparation for rebar cage installation
Sat (13/07) | 13 Jul 2024 | P16 |  | Waler beam welding status. MPI on monday
Sat (13/07) | 13 Jul 2024 | P10 |  | Pier rebar installation continue
Sat (13/07) | 13 Jul 2024 | P9 |  | ERSS pre-boring continue
Sat (13/07) | 13 Jul 2024 | Zone 2 |  | Bentonite plant setting up
Sat (13/07) | 13 Jul 2024 | MH5-1 |  | Formwork dismantled. Preparation for backfilling
Sat (13/07) | 13 Jul 2024 | STN228-BC2 |  | 2nd bite trenching started
Sat (13/07) | 13 Jul 2024 | STN219-BC3 |  | 2nd bite excation in progress, depth at 13/37.9m
Sat (13/07) | 13 Jul 2024 | BP4A-2 | 43 | TT done, found HV, abandoned gas pipe and traffic light pipes
Sat (13/07) | 13 Jul 2024 | BR5B3-BC04 | BRP39 | 2nd bite Trenching continue, depth 21.10/25.07m
Sat (13/07) | 13 Jul 2024 | STN160-BC1 |  | 2nd bite cleaning on going
Sat (13/07) | 13 Jul 2024 | P43-44 GI works |  | Grouting for 2nd point
Sat (13/07) | 13 Jul 2024 | Mh3-5 |  | Excavation and soil disposal continue
Sat (13/07) | 13 Jul 2024 | P46-5 |  | Boring works continue, 28m depth
Sat (13/07) | 13 Jul 2024 | Zone 4 GI works |  | Preparation for 3rd points, 2/3 completed
Sat (13/07) | 13 Jul 2024 | ST228 |  | 2nd bite, reached 18m
Sat (13/07) | 13 Jul 2024 | ST219 |  | 2nd bite in progress, reached 19.3m
Sat (13/07) | 13 Jul 2024 | BRP39 |  | 2nd bite reached 21.6m. Now teeth changing
Sat (13/07) | 13 Jul 2024 | TDP67 |  | Prepare for toe level confirmation. Tonight to cast
Sat (13/07) | 13 Jul 2024 | ST160 |  | Preparing for koden test. Will continue with waterstop end plate lowering
Sat (13/07) | 13 Jul 2024 | MH3-5 |  | Casting almost done
Sat (13/07) | 13 Jul 2024 | P16 |  | Waler beam welding
Sat (13/07) | 13 Jul 2024 | N5 |  | Pier and slab hacking
Sun (14/07) | 14 Jul 2024 | Zone 1 |  | No activities
Sun (14/07) | 14 Jul 2024 | MH5-2 |  | Backfilling ongoing
Sun (14/07) | 14 Jul 2024 | ST009 |  | Casting in progress
Sun (14/07) | 14 Jul 2024 | ST262 |  | B2 resumed from 38/39.6m
Sun (14/07) | 14 Jul 2024 | ST228 |  | B2 in progress, 30/32.1m
Sun (14/07) | 14 Jul 2024 | ST219 |  | B2 in progress
Sun (14/07) | 14 Jul 2024 | Zone 3 |  | Trial trench ongoing for BP2B-2 (53)
Sun (14/07) | 14 Jul 2024 | BRP39 |  | Excavation temporarily stopped. Cutter teeth changing ongoing
Sun (14/07) | 14 Jul 2024 | DR1 |  | Soldier pile extension in progress
Sun (14/07) | 14 Jul 2024 | ST160 |  | Endplate joint welding in progress
Sun (14/07) | 14 Jul 2024 | BRP71 |  | Guidewall rebar works ongoing
Sun (14/07) | 14 Jul 2024 | UKP41 |  | Trial trench in progress
Sun (14/07) | 14 Jul 2024 | MH3-5 |  | No activity
Sun (14/07) | 14 Jul 2024 | Zone 4 |  | JGP point B-408 in progress
Sun (14/07) | 14 Jul 2024 | Zone 4 |  | HSL no activity
Sun (14/07) | 14 Jul 2024 | BRP74 |  | Excavation in progress
Sun (14/07) | 14 Jul 2024 | Blk 4 |  | HSL also no activity today
Sun (14/07) | 14 Jul 2024 | P16 |  | No activity
Sun (14/07) | 14 Jul 2024 | P13 |  | Barricade installed. Backfilling and compaction in progress
Sun (14/07) | 14 Jul 2024 | MH5-2 |  | Currently no activity
Sun (14/07) | 14 Jul 2024 | MH5-1 |  | MH 2nd precast chamber ring installation
Sun (14/07) | 14 Jul 2024 | ST009 |  | Casting just completed. Total vol: 312m3
Sun (14/07) | 14 Jul 2024 | ST15 |  | Guidewall pending to cast. Concrete ordered
Sun (14/07) | 14 Jul 2024 | ST262 |  | Excavation reached 39.6m/39.6m
Sun (14/07) | 14 Jul 2024 | ST004 |  | B1 reached 20/34.2m
Sun (14/07) | 14 Jul 2024 | BRP71 |  | Guidewall formwork installation. Plan for casting today too
Sun (14/07) | 14 Jul 2024 | BRP74 |  | Excavation temporarily stopped. Centre holder and cutter teeth rectification ongoing
Sun (14/07) | 14 Jul 2024 | ST160 |  | Continue endplate joint welding
Sun (14/07) | 14 Jul 2024 | DR1 |  | Continue soldier pile extension, 22/24nos completed
Sun (14/07) | 14 Jul 2024 | BRP39 |  | In progress, 21.8/25.07m
Sun (14/07) | 14 Jul 2024 | ST262 |  | 2nd bite reached 38m
Sun (14/07) | 14 Jul 2024 | ST228 |  | 2nd bite in progress, reached 28.1m. Cutter head bring up for teeth changing
Sun (14/07) | 14 Jul 2024 | ST219 |  | 2nd bite in progress, 32.3m
Sun (14/07) | 14 Jul 2024 | BRP39 |  | 2nd bite reached 21.7m. Prepare chisel for chiseling also
Sun (14/07) | 14 Jul 2024 | ST160 |  | Waterstop end plate lowering down in progress
Sun (14/07) | 14 Jul 2024 | P16 |  | Struts welding ongoing
Sun (14/07) | 14 Jul 2024 | N5 |  | Soil excavation and levelling ongoing
Sun (14/07) | 14 Jul 2024 | P15 |  | No activity
Sun (14/07) | 14 Jul 2024 | P13 |  | To continue soil backfilling works
Sun (14/07) | 14 Jul 2024 | P12 |  | No activity
Sun (14/07) | 14 Jul 2024 | P10 |  | Rebar works installation in progress
Mon (15/07) | 15 Jul 2024 | P16 |  | Barricade installation prior to excavation works. MPI for waler beam done
Mon (15/07) | 15 Jul 2024 | N5 |  | Re-levelling for falsework, to cast today
Mon (15/07) | 15 Jul 2024 | P14 |  | Inclino installation
Mon (15/07) | 15 Jul 2024 | MH5-2 |  | Rebar works for last ring
Mon (15/07) | 15 Jul 2024 | Zone 2 |  | Bentonite plant set up
Mon (15/07) | 15 Jul 2024 | MH5-1 |  | Rebar works for last ring
Mon (15/07) | 15 Jul 2024 | P46-5 |  | Boring done. Preparing for rebar cage lowering
Mon (15/07) | 15 Jul 2024 | BRP70 |  | Hardcore removal for trial trench works
Mon (15/07) | 15 Jul 2024 | BH97 |  | In progress, 10m
Mon (15/07) | 15 Jul 2024 | BH96 |  | In progress, 12m
Mon (15/07) | 15 Jul 2024 | TDP65 |  | Boring in progress
Mon (15/07) | 15 Jul 2024 | ST160 |  | Rebar cage extraction ongoing due to insufficient toe depth. 4/7 cages already extracted
Mon (15/07) | 15 Jul 2024 | Blk 4 |  | Boring ongoing for recharge well works. Today plan installation for RW39 (1/30nos). DR2 area already completed 40nos
Mon (15/07) | 15 Jul 2024 | BRP33 | Rig 4 | Excavation started at 1240hrs. Now excavation temporarily stopped for cutter wheel cleaning
Mon (15/07) | 15 Jul 2024 | BP2B-2 | 55 | Premix hacking ongoing for trial trench works
Mon (15/07) | 15 Jul 2024 | ST219 Rig 3 |  | Trimming in progress
Mon (15/07) | 15 Jul 2024 | ST262 |  | Lowering of first rebar cage, 1/8nos
Mon (15/07) | 15 Jul 2024 | ST001 |  | Excavation started today
Mon (15/07) | 15 Jul 2024 | ST18 |  | Trial trench ongoing. Now manual cleaning of found service, witnessed by utility team
Mon (15/07) | 15 Jul 2024 | ST228 |  | Endplate installation in progress, 1/3nos
Mon (15/07) | 15 Jul 2024 | BRP36 | Rig 2 | Excavation just started. CD 4.5/34.2m
Mon (15/07) | 15 Jul 2024 | BRP39 |  | LSS backfilling ongoing
Mon (15/07) | 15 Jul 2024 | Blk 4 |  | WH installing localised noise barriers
Mon (15/07) | 15 Jul 2024 | TDP108 |  | Trial trench ongoing
Mon (15/07) | 15 Jul 2024 | TDP69 |  | Boring in progress
Mon (15/07) | 15 Jul 2024 | TDP65 |  | Boring in progress
Mon (15/07) | 15 Jul 2024 | BRP70 |  | Trial trench for guidewall works
Mon (15/07) | 15 Jul 2024 | MH3-5 |  | Dewatering and cleaning ongoing
Tue (16/07) | 16 Jul 2024 | MH3-5 |  | Preparing for next layer (4th) excavation
Tue (16/07) | 16 Jul 2024 | P48 |  | WH preparing for drain hacking works. Now soil removal ongoing
Tue (16/07) | 16 Jul 2024 | Zone 4 |  | JGP point B-457 in progress
Tue (16/07) | 16 Jul 2024 | Zone 4 |  | GCE preparing for internal coring works. Yesterday completed 1st coring sample for first core point. Total 5nos of core samples to be taken for each core point
Tue (16/07) | 16 Jul 2024 | P46-5 |  | HSL continue clearing obstruction. Yesterday unable to lower the rebar cage
Tue (16/07) | 16 Jul 2024 | P46-5 |  | Toe cleaning done. Toe depth confirmation witness by RTO, 31m
Tue (16/07) | 16 Jul 2024 | Zone 4 LA sidetable | towards Selarang | Trial trench by PUB contractor (not under CR106) for drain extension
Tue (16/07) | 16 Jul 2024 | LW sidetable | near exit 1 small gate | WH trial trench for Singtel
Tue (16/07) | 16 Jul 2024 | BRP70 |  | Guidewall rebar works
Tue (16/07) | 16 Jul 2024 | BRP74 |  | Preparing for cleaning and desanding
Tue (16/07) | 16 Jul 2024 | TDP69 |  | Boring completed. Today to complete deckpost installation. Sany machine plan to proceed TDP108 thereafter
Tue (16/07) | 16 Jul 2024 | HSL BG25 |  | Currently no activity. This machine plan to start for UKP39
Tue (16/07) | 16 Jul 2024 | P15 |  | Continue excavation to FEL
Tue (16/07) | 16 Jul 2024 | P46-5 |  | Rebar cages fully lowered. Now preparing for casting
Tue (16/07) | 16 Jul 2024 | P10 |  | Shearlinks installation and formwork closing continue
Tue (16/07) | 16 Jul 2024 | Zone 4 |  | JGP point B-399 completed
Tue (16/07) | 16 Jul 2024 | Zone 4 |  | Rig currently breakdown. Repairing works ongoing
Tue (16/07) | 16 Jul 2024 | P48 |  | Drain hacking works
Tue (16/07) | 16 Jul 2024 | MH3-5 |  | Excavation works for next layer in progress (1.2m)
Tue (16/07) | 16 Jul 2024 | LW sidetable | near exit 1 small gate | WH continue trial trench for Singtel
Tue (16/07) | 16 Jul 2024 | BRP70 |  | Continue guidewall rebar works and formwork installation
Tue (16/07) | 16 Jul 2024 | DR1 |  | Continue soldier pile plate joint welding
Tue (16/07) | 16 Jul 2024 | P7 TT |  | HV exposed. Checking with utility team if need spiking
Tue (16/07) | 16 Jul 2024 | Zone 2 P2 island |  | Protection for 700mm water pipe done. Backfilling in progress prior to casing installation
Tue (16/07) | 16 Jul 2024 | Zone 2 |  | Bentonite plant set-up
Tue (16/07) | 16 Jul 2024 | P15 |  | Continue excavation to FEL
Tue (16/07) | 16 Jul 2024 | N5 |  | Falsework installation in progress
Tue (16/07) | 16 Jul 2024 | P10 |  | Pilecap rebar inspection was done. Balance formwork and final inspection prior to casting
Tue (16/07) | 16 Jul 2024 | P9-1 |  | Preboring ongoing by LE
Tue (16/07) | 16 Jul 2024 | MH5-2 |  | No activity
Tue (16/07) | 16 Jul 2024 | ST18 |  | Preparing for guidewall construction
Tue (16/07) | 16 Jul 2024 | ST228 |  | Rebar cage installation in progress, 7/8nos
Tue (16/07) | 16 Jul 2024 | ST219 |  | B2 cleaning ongoing
Tue (16/07) | 16 Jul 2024 | BP2B-2 and BP2B-2(53) | 53 | Trial trench done and utility exposed. Pending utility team confirmation
Tue (16/07) | 16 Jul 2024 | BRP33 |  | B1 completed
Tue (16/07) | 16 Jul 2024 | BRP42 |  | Premix hacking ongoing for guidewall trial trench
Tue (16/07) | 16 Jul 2024 | TDP69 |  | Deck post installation completed
Tue (16/07) | 16 Jul 2024 | TDP108 |  | Pending to cast, thereafter install deck post
Tue (16/07) | 16 Jul 2024 | UKP39 |  | Boring in progress
Tue (16/07) | 16 Jul 2024 | ST160 | Rig 1 | Continue cleaning works
Tue (16/07) | 16 Jul 2024 | BRP74 |  | Rebar cage & KP installation ongoing
Tue (16/07) | 16 Jul 2024 | P16 |  | Excavation to FEL in progress
Tue (16/07) | 16 Jul 2024 | ST262 |  | Casting in progress
Tue (16/07) | 16 Jul 2024 | ST001 |  | Continue excavation
Tue (16/07) | 16 Jul 2024 | ST004 |  | In progress
Tue (16/07) | 16 Jul 2024 | ST18 |  | Cutting of abandoned gas pipe to facilitate guidewall works
Tue (16/07) | 16 Jul 2024 | N5 |  | Falsework to start today
Tue (16/07) | 16 Jul 2024 | P15 rebar cage |  | Assembly frame dismantling
Tue (16/07) | 16 Jul 2024 | BRP33 |  | B1 in progress, 24/29.07m
Tue (16/07) | 16 Jul 2024 | BRP36 | Rig 2 | Excavation temporarily stopped for cutter teeth change
Tue (16/07) | 16 Jul 2024 | DR1 |  | MPI test was done yesterday for the soldier pile extension. Today LE continue plate joint welding for soldier pile. 2 welders on site
Tue (16/07) | 16 Jul 2024 | P7 |  | TT in progress, HV and singtel found
Wed (17/07) | 17 Jul 2024 | N5 Crosshead |  | Falsework installation in progress
Wed (17/07) | 17 Jul 2024 | MH1-2 |  | Patching works
Wed (17/07) | 17 Jul 2024 | P16 |  | Excavation to FEL
Wed (17/07) | 17 Jul 2024 | P14 RG |  | Drilling for installation of water standpipe in progress. Target to complete today
Wed (17/07) | 17 Jul 2024 | P13 |  | Column rebar cage fabrication works
Wed (17/07) | 17 Jul 2024 | BRP36 Rig 2 |  | Planning to do cleaning & desanding after suction pipe line repaired
Wed (17/07) | 17 Jul 2024 | MH3-5 |  | Plan to cast 1.2m ring after lunch
Wed (17/07) | 17 Jul 2024 | Blk 4 |  | Boring ongoing for recharge well installation. Now ongoing RW40
Wed (17/07) | 17 Jul 2024 | Blk 4 |  | Geomotion continue trial trench for subsequent RW point. Now ongoing TT for RW42
Wed (17/07) | 17 Jul 2024 | BC1 |  | Currently no activity. ST160 trench has been cleaned and now trench monitoring ongoing prior to installing rebar cage
Wed (17/07) | 17 Jul 2024 | BRP33 | Rig 4 | B2 excavation in progress
Wed (17/07) | 17 Jul 2024 | N4 |  | Column hacking works
Wed (17/07) | 17 Jul 2024 | P7 |  | Afternoon utility team to confirm 22KV is live or not
Wed (17/07) | 17 Jul 2024 | P44 |  | Pipe sleeves installatiom for JGP
Wed (17/07) | 17 Jul 2024 | P44 |  | Marking of P44 bored pile location
Wed (17/07) | 17 Jul 2024 | Zone 1 |  | Rig need some modification, mechanics at site
Wed (17/07) | 17 Jul 2024 | BRP75 |  | Excavation started just before lunch. Now current depth at 20/30.07m
Wed (17/07) | 17 Jul 2024 | ST160 |  | Rebar cage installation in progress, 4/8nos
Wed (17/07) | 17 Jul 2024 | UKP39 |  | Completed
Wed (17/07) | 17 Jul 2024 | UKP40 |  | In progress
Wed (17/07) | 17 Jul 2024 | BRP42 |  | Guidewall excavation
Wed (17/07) | 17 Jul 2024 | DR1 |  | LE continue welding of soldier pile plate
Wed (17/07) | 17 Jul 2024 | BRP36 |  | Rig 2 currently no activity. Cleaning and desanding just completed
Wed (17/07) | 17 Jul 2024 | BRP33 |  | B2 in progress, 15.5/29.07m
Wed (17/07) | 17 Jul 2024 | BP2B-2 | 55 | Abandoned utility checking witnessed by utility team
Wed (17/07) | 17 Jul 2024 | ST219 |  | Toe re-cleaning was done due to insufficient toe depth. Now realigning endplate
Wed (17/07) | 17 Jul 2024 | BC3 |  | Currently no activity
Wed (17/07) | 17 Jul 2024 | ST18 |  | Guidewall formwork installation in progress. Plan for casting today
Wed (17/07) | 17 Jul 2024 | ST008 |  | Continue B1 excavation
Wed (17/07) | 17 Jul 2024 | ST004 |  | Preparing to install rebar cage
Wed (17/07) | 17 Jul 2024 | P6 |  | Steel plate laying for rig platform. Plan to mobiles rig by tomorrow. Saturday start casing installation
Wed (17/07) | 17 Jul 2024 | P7 |  | 22KV LEW inspection done. Confirmed abandoned
Wed (17/07) | 17 Jul 2024 | P9 |  | Continue ERSS pre-boring
Wed (17/07) | 17 Jul 2024 | P10 |  | Pile cap casting
Wed (17/07) | 17 Jul 2024 | P13 |  | Pier rebar cage fabrication
Wed (17/07) | 17 Jul 2024 | P15 |  | Excavation to FEL continue. Plan to complete tomorrow
Wed (17/07) | 17 Jul 2024 | P15 |  | Continue excavation to FEL. Works until 10pm
Wed (17/07) | 17 Jul 2024 | N5 |  | Wingform installation in progress
Wed (17/07) | 17 Jul 2024 | N4 |  | Column hacking ongoing
Wed (17/07) | 17 Jul 2024 | P10 |  | Pilecap casting in progress, 147/200m3
Wed (17/07) | 17 Jul 2024 | P9 |  | Continue preboring for ERSS
Wed (17/07) | 17 Jul 2024 | P7 |  | Hacking works ongoing to extend the trial trench
Wed (17/07) | 17 Jul 2024 | ST001 |  | B1 reached 34.8/34.8m. Now cutter wheel cleaning
Wed (17/07) | 17 Jul 2024 | ST004 |  | Rebar cage installation in progress, 3/8nos
Wed (17/07) | 17 Jul 2024 | ST008 |  | B1 reached 15.8/33.2m
Wed (17/07) | 17 Jul 2024 | ST18 |  | Guidewall inspected and ready for casting
Wed (17/07) | 17 Jul 2024 | ST160 |  | Rebar cage installation in progress, 5/8nos
Wed (17/07) | 17 Jul 2024 | TDP71 |  | Continue boring due to insufficient toe depth
Wed (17/07) | 17 Jul 2024 | ST001 |  | B1 excavation resumed from 32/34.8m
Wed (17/07) | 17 Jul 2024 | ST008 |  | Excavation started last night. Now ongoing B1 excavation, 12/33.2m
Wed (17/07) | 17 Jul 2024 | ST228 |  | Casting in progress, 129/220m3
Wed (17/07) | 17 Jul 2024 | Zone 1 |  | 1st Deckpost drilling in progress
Wed (17/07) | 17 Jul 2024 | P48-8 |  | Preparing to start preboring
Wed (17/07) | 17 Jul 2024 | UKP39 |  | Boring toe depth confirmation witness by RTO. Today will cast and install UKP
Wed (17/07) | 17 Jul 2024 | BRP70 |  | Guidewall cast yesterday. Now preparing to dismantle formwork
Thu (18/07) | 18 Jul 2024 | BRP33 Rig 4 |  | B2 CD 21/29.07m
Thu (18/07) | 18 Jul 2024 | BRP38 Rig 2 |  | B1 CD 21/32.37m, now changing of teeth
Thu (18/07) | 18 Jul 2024 | P2 area |  | Pre-boring for deck post in progress. Target to LSS backfill 2 nos today
Thu (18/07) | 18 Jul 2024 | Zone 3 |  | Dongah preparing the platform area for next BRP trench, BRP74
Thu (18/07) | 18 Jul 2024 | BC1 |  | Currently no activity. This rig will move to BRP74
Thu (18/07) | 18 Jul 2024 | TDP71 |  | Yesterday completed installation. Now LSS backfill
Thu (18/07) | 18 Jul 2024 | UKP40 |  | Pending casting and installation
Thu (18/07) | 18 Jul 2024 | Blk 4 |  | Geomotion provided 2 teams for RW trial trench. Now ongoing TT for RW48 and RW42. This afternoon, another rig will be mobilised
Thu (18/07) | 18 Jul 2024 | BRP42 |  | Trial trench ongoing. Found 66kV slab at 1.7m depth
Thu (18/07) | 18 Jul 2024 | DR1 |  | LE continue welding for soldier pile plate (2 welders). Beams are planned to be delivered back to site today. Beams were sent back yesterday cos storage area was not prepared & there was no lifting team
Thu (18/07) | 18 Jul 2024 | P47-P48 |  | 1st point JGP work in progress
Thu (18/07) | 18 Jul 2024 | P48-8 |  | Coring in progress. Plan to cast today
Thu (18/07) | 18 Jul 2024 | P9 ERSS pre-boring status |  | SP: 18/26, LP: 10/26. Soil disposal in progress then continue pre-boring
Thu (18/07) | 18 Jul 2024 | P13 |  | Backfilling works to pile cap level continue
Thu (18/07) | 18 Jul 2024 | P14 |  | Water stand pipe installation
Thu (18/07) | 18 Jul 2024 | N4 |  | Pier hacking in progress
Thu (18/07) | 18 Jul 2024 | N5 |  | Crosshead formwork wing-form installation on going
Thu (18/07) | 18 Jul 2024 | MH3-5 |  | Excavator repaired. Will resume work after lucnh
Thu (18/07) | 18 Jul 2024 | Blk 4 |  | Geomotion continue manual trial trench for RW48 and RW42
Thu (18/07) | 18 Jul 2024 | N5 |  | Fitting of side formwork to adjust wing form to desired gradient. Later today to start modification of sideform
Thu (18/07) | 18 Jul 2024 | P39 |  | Ley Choon backfilling works & shoring removal for previously laid 22kV
Thu (18/07) | 18 Jul 2024 | BH95 |  | SI just started, ongoing 6m
Thu (18/07) | 18 Jul 2024 | P48-8 |  | Boring done. Toe level confirmed. Preparing for rebar cage lowering
Thu (18/07) | 18 Jul 2024 | P47-P48 |  | TT for pipe sleeves installation
Thu (18/07) | 18 Jul 2024 | N4 |  | Current status for pier column hacking works
Thu (18/07) | 18 Jul 2024 | P13 |  | Column rebar cage fabrication in progress
Thu (18/07) | 18 Jul 2024 | P10 |  | Column stump rebar installation works
Thu (18/07) | 18 Jul 2024 | P9 |  | LE ERSS preboring works
Thu (18/07) | 18 Jul 2024 | P13 |  | Compaction on going. 430 pm NDT
Thu (18/07) | 18 Jul 2024 | DR1 |  | LE beams arrived on site
Thu (18/07) | 18 Jul 2024 | BRP38 | Rig 2 | Excavation in progress, 27/32.37m
Thu (18/07) | 18 Jul 2024 | Rig 4 |  | Cutter teeth changing ongoing
Thu (18/07) | 18 Jul 2024 | ST229 |  | Trial trench ongoing
Thu (18/07) | 18 Jul 2024 | P2 |  | Deck post installation in progress
Thu (18/07) | 18 Jul 2024 | P16 |  | Excavation and levelling to FEL
Thu (18/07) | 18 Jul 2024 | N5 |  | Cutting of rebar to correct level
Thu (18/07) | 18 Jul 2024 | P15 |  | Backfilling
Thu (18/07) | 18 Jul 2024 | N4 |  | Hacking to the correct level
Thu (18/07) | 18 Jul 2024 | P9 |  | Preboring for ERSS work
Thu (18/07) | 18 Jul 2024 | P2 |  | Deck post 4&6- Waiting for LSS for backfilling
Thu (18/07) | 18 Jul 2024 | P4 |  | Beam unloading work
Thu (18/07) | 18 Jul 2024 | ST001 |  | 2nd bite completed
Thu (18/07) | 18 Jul 2024 | ST227 |  | Pre excavation and platform making for BC cutter parking
Thu (18/07) | 18 Jul 2024 | ST219 |  | Ready for casting. Will cast today
Thu (18/07) | 18 Jul 2024 | BRP33 |  | 2nd bite in progress, 21.38m
Thu (18/07) | 18 Jul 2024 | BRP38 |  | Excavation done. Preparing for koden test
Thu (18/07) | 18 Jul 2024 | BRP44 |  | TT done. Found 66KV. Need to spike
Thu (18/07) | 18 Jul 2024 | TDP75 |  | Casting in progress. TDP76: preparing for casting
Thu (18/07) | 18 Jul 2024 | ST160 |  | Casting in progress, 153/230m3
Thu (18/07) | 18 Jul 2024 | BRP75 |  | Rebar cage lowered down
Thu (18/07) | 18 Jul 2024 | BRP70 |  | Excavation reached 9m
Thu (18/07) | 18 Jul 2024 | MH3-5 |  | No activity already
Thu (18/07) | 18 Jul 2024 | Zone 4 |  | 3rd point JGP grouting done. Housekeeping
Thu (18/07) | 18 Jul 2024 | P48-8 |  | Casting in progess
Thu (18/07) | 18 Jul 2024 | ST004 |  | Casting in progress
Thu (18/07) | 18 Jul 2024 | ST001 |  | B2 CD 32/34.8m
Thu (18/07) | 18 Jul 2024 | Blk 4 |  | Geomotion preparing to install recharge well, RW41
Fri (19/07) | 19 Jul 2024 | ST008 |  | Repairing of bentonite pump is in progress
Fri (19/07) | 19 Jul 2024 | ST227 Rig 3 |  | Teeth replacement in progress
Fri (19/07) | 19 Jul 2024 | MH3-5 |  | Preparing to dismantle 5th layer formwork. Thereafter continue excavation for next layer
Fri (19/07) | 19 Jul 2024 | BRP38 Rig 2 |  | Finished excavation now the rig under maintenance
Fri (19/07) | 19 Jul 2024 | BRP33 Rig 4 |  | B2 CD 22.9m, teeth replacement now
Fri (19/07) | 19 Jul 2024 | Zone 4 |  | JGP point B-162 in progres
Fri (19/07) | 19 Jul 2024 | P48 |  | Removal of hard surface ongoing
Fri (19/07) | 19 Jul 2024 | P48-8 |  | Preparing for LSS backfill
Fri (19/07) | 19 Jul 2024 | Zone 1 P2 area |  | Preparation for Deckpost casing installation
Fri (19/07) | 19 Jul 2024 | Blk 4 |  | Geomotion preparing to start recharge well works, RW48
Fri (19/07) | 19 Jul 2024 | P32 |  | Recharge well RW42 in progress
Fri (19/07) | 19 Jul 2024 | BRP72 |  | Continue excavation
Fri (19/07) | 19 Jul 2024 | DR1 |  | WH hacking works ongoing for drain works along sump area
Fri (19/07) | 19 Jul 2024 | BRP33 |  | Cutter teeth replaced. Mow continie excavation
Fri (19/07) | 19 Jul 2024 | BC2 |  | Currently no activity. Only maintenance ongoin
Fri (19/07) | 19 Jul 2024 | TDP46 |  | Trial trench
Fri (19/07) | 19 Jul 2024 | ST227 |  | B1 in progress, 24/31.8m
Fri (19/07) | 19 Jul 2024 | ST008 |  | B1 in progress, 24/33.2m
Fri (19/07) | 19 Jul 2024 | ST001 |  | WS endplate installation in progress
Fri (19/07) | 19 Jul 2024 | P16 |  | Pile head cutting works
Fri (19/07) | 19 Jul 2024 | N5 |  | Crosshead side formwork modification works
Fri (19/07) | 19 Jul 2024 | N4 |  | Hacking of column in progress
Fri (19/07) | 19 Jul 2024 | P15 |  | Backfilling for ERSS extraction in progress
Fri (19/07) | 19 Jul 2024 | MH1-2 |  | Material clearing and HDPE lining continue
Fri (19/07) | 19 Jul 2024 | P7 |  | Exposing 66kV for spiking
Fri (19/07) | 19 Jul 2024 | P13 |  | Column Rebar cage fabrication
Fri (19/07) | 19 Jul 2024 | P9 |  | ERSS pre-boring continue. To complete today
Fri (19/07) | 19 Jul 2024 | Zone 4 |  | Buried the HDD pipe for trial boring using SI rig
Fri (19/07) | 19 Jul 2024 | MH3-5 |  | 900mm/1200mm excavation done. Tomorrow to cast
Fri (19/07) | 19 Jul 2024 | STN001 |  | Desanding completed
Fri (19/07) | 19 Jul 2024 | STN008 |  | Cutter wheel teeth replacement
Fri (19/07) | 19 Jul 2024 | ST228 |  | 1st bite trenching continue
Fri (19/07) | 19 Jul 2024 | MH3-5 |  | Excavation continue
Fri (19/07) | 19 Jul 2024 | P43-44 GI works |  | Grouting for 4th point
Fri (19/07) | 19 Jul 2024 | BRP70 |  | Excavation started
Fri (19/07) | 19 Jul 2024 | BRP72 |  | Desanding and cleaning done. Nightshift team to lower rebar cage
Fri (19/07) | 19 Jul 2024 | BRP33 |  | 2nd bite trenching resumed
Fri (19/07) | 19 Jul 2024 | BRP38 |  | Casting, last 2 trucks on site
Fri (19/07) | 19 Jul 2024 | BRP72 |  | Excavation in progress
Fri (19/07) | 19 Jul 2024 | BH95 |  | Coring in progress, 16m
Fri (19/07) | 19 Jul 2024 | ST001 |  | Extraction of WS is in progress
Fri (19/07) | 19 Jul 2024 | P16 |  | Excavation to FEL, levelling
Sat (20/07) | 20 Jul 2024 | P9 |  | Preboring work for ERSS installation
Sat (20/07) | 20 Jul 2024 | P10 |  | Column formwork closing
Sat (20/07) | 20 Jul 2024 | MH5-2 |  | Caisson hacking done. Excavator shift to MH5-1 for hacking
Sat (20/07) | 20 Jul 2024 | DP2-5 |  | Boring in progress
Sat (20/07) | 20 Jul 2024 | P48-7 |  | Preboring in progress
Sat (20/07) | 20 Jul 2024 | Zone 4 |  | 1st JGP point boring in progress
Sat (20/07) | 20 Jul 2024 | MH3-5 |  | Trimming almost completed. Today to cast
Sat (20/07) | 20 Jul 2024 | DR1 |  | Extension of soldier piles
Sat (20/07) | 20 Jul 2024 | BRP33 |  | Boring reached 29m
Sat (20/07) | 20 Jul 2024 | ST221 |  | Pre excavation work
Sat (20/07) | 20 Jul 2024 | BC cutter 3 |  | Need to replace mud pump
Sat (20/07) | 20 Jul 2024 | ST001 |  | Chieselling before continue excavation
Sat (20/07) | 20 Jul 2024 | ST249 |  | Continue excavation, reached 14m
Sat (20/07) | 20 Jul 2024 | P16 |  | Pile head hacking
Sat (20/07) | 20 Jul 2024 | P15 |  | ERSS removal
Sat (20/07) | 20 Jul 2024 | N5 |  | Side formwork closing
Sat (20/07) | 20 Jul 2024 | N4 |  | Hacking of column to correct level
Sat (20/07) | 20 Jul 2024 | P9 |  | Preboring for ERSS installation
Sat (20/07) | 20 Jul 2024 | P10 |  | Working platform erection for column caating
Sat (20/07) | 20 Jul 2024 | MH1-2 |  | HDPE lining work
Sat (20/07) | 20 Jul 2024 | DP-2-5 |  | Boring done. DP-2-1: Boring in progress
Sat (20/07) | 20 Jul 2024 | P48-7 |  | Boring reached 17m
Sat (20/07) | 20 Jul 2024 | Zone 4 |  | JGP 2nd point on going
Sat (20/07) | 20 Jul 2024 | Zone 4 |  | 2nd point sample taking
Sat (20/07) | 20 Jul 2024 | MH3-5 |  | BRC installation. Today to cast
Sat (20/07) | 20 Jul 2024 | DR1 |  | Soldier pile joint welding
Sat (20/07) | 20 Jul 2024 | BRP33 |  | Excavation reached 23m
Sat (20/07) | 20 Jul 2024 | ST221 |  | 1st bite excavation reached 12m
Sat (20/07) | 20 Jul 2024 | BC cutter 3 |  | Still replacing mud pump
Sat (20/07) | 20 Jul 2024 | P10 |  | Access erection ongoing by WH
Sat (20/07) | 20 Jul 2024 | P7 area |  | Barricade rectification and dewatering. No other activity
Sat (20/07) | 20 Jul 2024 | Zone 1 |  | No more activities
Sat (20/07) | 20 Jul 2024 | ST001 |  | Base cleaning completed. Now preparing for final koden check
Sat (20/07) | 20 Jul 2024 | ST249 |  | Preparing to resume excavation
Sat (20/07) | 20 Jul 2024 | ST008 |  | Cutter teeth changing ongoing
Sat (20/07) | 20 Jul 2024 | ST227 |  | B2 in progress, 14/31.8m
Sat (20/07) | 20 Jul 2024 | ST221 |  | B1 in progress, 20.5/38.1m
Sat (20/07) | 20 Jul 2024 | BRP33 |  | Cleaning ongoing
Sat (20/07) | 20 Jul 2024 | P31-32 |  | 22kV protection fabrication ongoing by WH
Sat (20/07) | 20 Jul 2024 | BRP70 |  | B1 cleaning ongoing
Sat (20/07) | 20 Jul 2024 | Zone 4 |  | No other activity
Sat (20/07) | 20 Jul 2024 | MH3-5 |  | Layer 6 casting in progress
Sat (20/07) | 20 Jul 2024 | ST001 |  | Rebar cage removal. Excavation was not reached actual toe level. Need to remove all rebar cages and continue excavation 1m deeper
Sat (20/07) | 20 Jul 2024 | ST249 |  | 1st bite excavation started
Sat (20/07) | 20 Jul 2024 | P16 |  | Pile head hacking
Sat (20/07) | 20 Jul 2024 | N5 |  | Prepare side formwork for installation
Sat (20/07) | 20 Jul 2024 | N4 |  | Hacking of column
Sat (20/07) | 20 Jul 2024 | P13 |  | Fit up horizontal bracing
Sun (21/07) | 21 Jul 2024 | N5 |  | Croaahead rebar installation started
Sun (21/07) | 21 Jul 2024 | P13 |  | ERSS extraction
Sun (21/07) | 21 Jul 2024 | MH5-2 |  | Access cover installation
Sun (21/07) | 21 Jul 2024 | MH1-2 |  | Benching works in progress
Sun (21/07) | 21 Jul 2024 | Zone 1 P2 area |  | LE welding SP only
Sun (21/07) | 21 Jul 2024 | zone 4 |  | BP and GI works no activity
Sun (21/07) | 21 Jul 2024 | BRP70 |  | Kingpost lowering
Sun (21/07) | 21 Jul 2024 | BRP33 |  | Preparation for KP lowering
Sun (21/07) | 21 Jul 2024 | P16 |  | Pile head hacking continue. 4/6 completed
Sun (21/07) | 21 Jul 2024 | MH5-2 |  | MH access cover installation
Sun (21/07) | 21 Jul 2024 | ST227 |  | Mud pump replacement
Sun (21/07) | 21 Jul 2024 | ST001 |  | Casting completed
Sun (21/07) | 21 Jul 2024 | BC2 |  | Bentonite pipe elbow leaking, replacement in progress
Sun (21/07) | 21 Jul 2024 | BRP33 |  | 1st KP installed
Sun (21/07) | 21 Jul 2024 | BRP70 |  | KP lowered
Sun (21/07) | 21 Jul 2024 | ST001 |  | Rebar cage installation in progress, 5/6nos. Plan for casting ard 8am
Sun (21/07) | 21 Jul 2024 | ST249 |  | B1 excavation in progress
Sun (21/07) | 21 Jul 2024 | ST008 |  | Continue excavation
Sun (21/07) | 21 Jul 2024 | ST221 |  | Oil pump ongoing
Sun (21/07) | 21 Jul 2024 | ST227 |  | B2 temporarily stopped for cutter teeeth changing
Sun (21/07) | 21 Jul 2024 | BRP33 |  | Continue cleaning
Sun (21/07) | 21 Jul 2024 | BRP70 |  | Cleaning and desanding completed
Sun (21/07) | 21 Jul 2024 | P16 |  | Pile head hacking
Mon (22/07) | 22 Jul 2024 | MH2-8 |  | LCH preparing for checking in preparation for PUB inspection (plan tmr)
Mon (22/07) | 22 Jul 2024 | Blk 4 |  | Geomotion continue drilling for recharge well installation, RW44
Mon (22/07) | 22 Jul 2024 | P16 |  | Pile head hacking works in progress. Target to complete by tmr
Mon (22/07) | 22 Jul 2024 | ST249 |  | B2 CD 15/47.9m
Mon (22/07) | 22 Jul 2024 | P31-32 |  | Utility protection completed
Mon (22/07) | 22 Jul 2024 | Blk 4 |  | Geomotion continue trial trench for next RW point, RW47
Mon (22/07) | 22 Jul 2024 | P2 area |  | Last Deckpost drilling in progress
Mon (22/07) | 22 Jul 2024 | N5 |  | Access for working platform installation in progress
Mon (22/07) | 22 Jul 2024 | N4 |  | Column hacking works in progress
Mon (22/07) | 22 Jul 2024 | ST008 |  | B1 CD 31.6/33.4m
Mon (22/07) | 22 Jul 2024 | ST161 |  | B1 temporarily stopped for cutter teeth change. CD 29/41.15m
Mon (22/07) | 22 Jul 2024 | ST227 Rig 3 |  | Trimming in progress
Mon (22/07) | 22 Jul 2024 | ST221 Rig 2 |  | B2 CD 15/38.1m, now teeth replacement in progress
Mon (22/07) | 22 Jul 2024 | P39 |  | WH erecting new designated walking access
Mon (22/07) | 22 Jul 2024 | BH95 |  | Packer test in progress
Mon (22/07) | 22 Jul 2024 | BRP41 |  | Excavation temporarily stopped for cutter teeth change. CD 25.1/34.1m
Mon (22/07) | 22 Jul 2024 | BRP36 |  | LSS backfill ongoing
Mon (22/07) | 22 Jul 2024 | P48-7 |  | Toe level confirmed. Preparing for rebar cage lowering down
Mon (22/07) | 22 Jul 2024 | P50 |  | Steel plate protection installation for drain removal work
Mon (22/07) | 22 Jul 2024 | P13 |  | Trimming in progress
Mon (22/07) | 22 Jul 2024 | P12 |  | Preparation for column rebar cage lifting
Mon (22/07) | 22 Jul 2024 | P10 |  | Column stump casting progress
Mon (22/07) | 22 Jul 2024 | P9 |  | Wire rope changing works
Mon (22/07) | 22 Jul 2024 | P16 |  | Continue pile head hacking
Mon (22/07) | 22 Jul 2024 | N5 |  | Barricade installation in progress
Mon (22/07) | 22 Jul 2024 | P12 |  | Lapping ongoing
Mon (22/07) | 22 Jul 2024 | P9 |  | Continue wire rope changing
Mon (22/07) | 22 Jul 2024 | ST249 |  | B2 reached 25/47.9m
Mon (22/07) | 22 Jul 2024 | ST227 |  | Cleaning started
Mon (22/07) | 22 Jul 2024 | ST230 |  | Guidewall was cast just now
Mon (22/07) | 22 Jul 2024 | Zone 3 |  | HSL boring machine parking and material shifting/preparation works ongoing. Tmr plan to start BP2A-1
Mon (22/07) | 22 Jul 2024 | Zone 3 |  | TDP delivery
Mon (22/07) | 22 Jul 2024 | BRP41 |  | B1 CD 26.2/34.1m
Mon (22/07) | 22 Jul 2024 | ST161 |  | B1 CD 35/41.15m
Mon (22/07) | 22 Jul 2024 | DR1 |  | H-beam installation and welding works. LE working until 9pm
Tue (23/07) | 23 Jul 2024 | Blk 4 |  | RW47 in progress
Tue (23/07) | 23 Jul 2024 | BRP41 |  | Cutter teeth changing ongoing. B1 CD 30/34.1m
Tue (23/07) | 23 Jul 2024 | DR1 |  | LE continue welding of top plate for main beam installation. 4 welders on site
Tue (23/07) | 23 Jul 2024 | P16 |  | Trimming of pile head to COL
Tue (23/07) | 23 Jul 2024 | P13 |  | Preparation for rebar cage lifting
Tue (23/07) | 23 Jul 2024 | P12 |  | Preparation for corbel rebar installation
Tue (23/07) | 23 Jul 2024 | P11 |  | Old pavement hacking for ERSS TT
Tue (23/07) | 23 Jul 2024 | Zone 3 |  | Premix hacking for PBH68 SI works
Tue (23/07) | 23 Jul 2024 | ST161 |  | B2 excavation just started
Tue (23/07) | 23 Jul 2024 | BRP63 |  | Premix hacking for trial trench
Tue (23/07) | 23 Jul 2024 | BH95 |  | Coring in progress, 39m
Tue (23/07) | 23 Jul 2024 | MH5-2 |  | Small gantry on site for HDPE lining at joint area
Tue (23/07) | 23 Jul 2024 | Zone 3 |  | Setting out for next TDP trial trench, TDP60
Tue (23/07) | 23 Jul 2024 | TDP56, TDP58 |  | Trial trench completed yesterday, found water pipe. Backfilling ongoing
Tue (23/07) | 23 Jul 2024 | ST221 |  | B2 in progress
Tue (23/07) | 23 Jul 2024 | P48-7 |  | Preparing for rebar cage lowering. Today to cast
Tue (23/07) | 23 Jul 2024 | ST008 |  | Excavation temporarily stopped for cutter teeth change. B2 CD 24/33.4m
Tue (23/07) | 23 Jul 2024 | ST249 |  | B2 CD 30/47.9m
Tue (23/07) | 23 Jul 2024 | MH2-8 |  | PUB officer on site
Tue (23/07) | 23 Jul 2024 | Exit 3 rest area |  | Perimeter drain extension towards ECM pond
Tue (23/07) | 23 Jul 2024 | MH3-5 |  | Continue excavation for ring casting
Tue (23/07) | 23 Jul 2024 | P44 |  | Prepare the area for JGP
Tue (23/07) | 23 Jul 2024 | P44 |  | Exposing army cable for protection. 2/4 piles can be done here
Tue (23/07) | 23 Jul 2024 | RW47 |  | Drilling depth check witness by RTO
Tue (23/07) | 23 Jul 2024 | BRP41 |  | Resume excavation
Tue (23/07) | 23 Jul 2024 | Blk 4 |  | Geomotion continue trial trench for next recharge well point, RW49
Tue (23/07) | 23 Jul 2024 | ST008 |  | B2 CD 26.0/33.4m
Tue (23/07) | 23 Jul 2024 | PBH68 |  | Trial trench in progress
Tue (23/07) | 23 Jul 2024 | BH95 |  | Coring reached 45.5m. Pending design team confirmation
Tue (23/07) | 23 Jul 2024 | ST227 |  | Cleaning in progress for 3rd bite
Tue (23/07) | 23 Jul 2024 | MH1-2 |  | Scaffold dismantle works completed. Soil/Debris clearing in progress
Tue (23/07) | 23 Jul 2024 | BRP66 |  | Trial trench was completed. Found M1 and abandoned gas pipe. Utility team checking ongoing
Tue (23/07) | 23 Jul 2024 | ST221 Rig 2 |  | B2 CD 29/38.1m
Tue (23/07) | 23 Jul 2024 | BRP64 |  | Premix hacking ongoing for trial trench works
Tue (23/07) | 23 Jul 2024 | P9 |  | ERSS pre-boring to complete today
Tue (23/07) | 23 Jul 2024 | N5 |  | Crosshead rebar installation continue
Tue (23/07) | 23 Jul 2024 | P13 |  | Column rebar cage lapping works in progress
Tue (23/07) | 23 Jul 2024 | P15 |  | Working platform erection for column rebar installation
Tue (23/07) | 23 Jul 2024 | P48-7 |  | Casting in progress
Tue (23/07) | 23 Jul 2024 | ST161 Rig 1 |  | B2 CD 12.0/41.15m
Tue (23/07) | 23 Jul 2024 | P16 |  | Hardcore clearing. To lean concrete today
Tue (23/07) | 23 Jul 2024 | MH3-5 |  | Continue excavation for 6.5 layer caisson casting
Tue (23/07) | 23 Jul 2024 | MH2-8 |  | Preparing for inspection
Tue (23/07) | 23 Jul 2024 | Zone 3 |  | Dongah last night has mobilised the boring rig, XCMG XR400E
Tue (23/07) | 23 Jul 2024 | Blk 4 |  | Geomotion preparation works for RW45
Wed (24/07) | 24 Jul 2024 | BRP70 |  | LSS backfilling ongoing
Wed (24/07) | 24 Jul 2024 | ST227 |  | Rebar cage lowering in progress
Wed (24/07) | 24 Jul 2024 | ST221 Rig 3 |  | B2 trimming in progress
Wed (24/07) | 24 Jul 2024 | ST218 Rig 2 |  | B1 CD 6/38.1m
Wed (24/07) | 24 Jul 2024 | TDP62 |  | Preparing to start trial trench
Wed (24/07) | 24 Jul 2024 | DR1 |  | LE continue top plate welding
Wed (24/07) | 24 Jul 2024 | BRP41 |  | Cutter teeth changing ongoing
Wed (24/07) | 24 Jul 2024 | ST161 Rig 1 |  | B2 CD 24.5/41.15m, rig now under maintenance
Wed (24/07) | 24 Jul 2024 | P2 |  | Pre-boring for ERSS in progress
Wed (24/07) | 24 Jul 2024 | MH1-2 |  | Benching patching works
Wed (24/07) | 24 Jul 2024 | P9 |  | ERSS pre-boring and SP installation
Wed (24/07) | 24 Jul 2024 | P15 |  | Pier rebar cage installation
Wed (24/07) | 24 Jul 2024 | N5 |  | RWDP installed
Wed (24/07) | 24 Jul 2024 | P16 |  | Hacking of pile head to cut off level
Wed (24/07) | 24 Jul 2024 | Blk 4 |  | WH trial trench excavation existing piles. Geomotion already parked their rig for RW49 works
Wed (24/07) | 24 Jul 2024 | P34 |  | WH erecting new access so as to facilitate the next RW point works which is located at the existing walking access
Wed (24/07) | 24 Jul 2024 | PBH68 |  | SI started
Wed (24/07) | 24 Jul 2024 | ST161 |  | Resume excavation
Wed (24/07) | 24 Jul 2024 | BRP66 |  | Services cleared. Now continue excavation for guidewall works
Wed (24/07) | 24 Jul 2024 | BRP72 |  | LSS backfilling
Wed (24/07) | 24 Jul 2024 | BRP63 |  | Trial trench for guidewall in progress
Wed (24/07) | 24 Jul 2024 | DR1 |  | LE demobilising the vibro now
Wed (24/07) | 24 Jul 2024 | BRP41 |  | B1 temporarily stopped, preparing for cutter teeth change. B1 CD 32.5/34.1m
Wed (24/07) | 24 Jul 2024 | ST218 |  | B1 in progress, 30/38.1m
Wed (24/07) | 24 Jul 2024 | BP2A-1 | 22 | Boring continue, 34.2/45.4m
Wed (24/07) | 24 Jul 2024 | ST227 |  | Rebar cage installation in progress, 6/8nos
Wed (24/07) | 24 Jul 2024 | ST008 |  | B2 reached 31/33.4m
Wed (24/07) | 24 Jul 2024 | P44 |  | 3 point JGP grouting done as of now. Prepare the area for 4th point
Wed (24/07) | 24 Jul 2024 | MH3-5 |  | Caisson shaft casting in progress
Wed (24/07) | 24 Jul 2024 | Zpne 4 |  | P49-6; base grouting completed
Wed (24/07) | 24 Jul 2024 | P44 |  | 4th point grouting in progress
Wed (24/07) | 24 Jul 2024 | BRP66 |  | Guidewall rebar works. To cast tomorrow
Wed (24/07) | 24 Jul 2024 | BRP63 |  | Excavation for Guidewall construction
Wed (24/07) | 24 Jul 2024 | ST161 |  | Current at 2nd bite 33m depth. Cutter body hoisting up for teeth replacement
Wed (24/07) | 24 Jul 2024 | DR1 |  | Top plate welding till 9pm
Wed (24/07) | 24 Jul 2024 | BRP41-BC4 |  | 1st bite trenching at 32.6m depth
Wed (24/07) | 24 Jul 2024 | STN21- BC2 |  | 1st bite trenching at 33m depth
Wed (24/07) | 24 Jul 2024 | BP2A-1 | 22 | Boring to continue till 10pm depth at 37m
Wed (24/07) | 24 Jul 2024 | STN227 |  | Rebar cage lowering, 7/8 cages
Wed (24/07) | 24 Jul 2024 | ST008 |  | B2 CD 29.4/33.4m
Wed (24/07) | 24 Jul 2024 | Blk 4 |  | Geomotion continue trial trench for RW49
Wed (24/07) | 24 Jul 2024 | PBH68 |  | Plan to start today, pending PTD
Thu (25/07) | 25 Jul 2024 | BRP66 |  | Guidewall formwork installation in progress. Today to cast
Thu (25/07) | 25 Jul 2024 | BRP41 Rig 4 |  | B1 CD 34.1/34.1m, rig is under maintenance now prior to start excavation for 2nd bite
Thu (25/07) | 25 Jul 2024 | BRP63 |  | Preparing for guidewall works
Thu (25/07) | 25 Jul 2024 | ST161 |  | B3 just started
Thu (25/07) | 25 Jul 2024 | DR1 |  | LE continue top plate welding
Thu (25/07) | 25 Jul 2024 | RW49 |  | Drilling in progress
Thu (25/07) | 25 Jul 2024 | ST218 |  | B1 temporarily stopped for cutter teeth change
Thu (25/07) | 25 Jul 2024 | ST221 |  | Endplate lowering ongoing
Thu (25/07) | 25 Jul 2024 | MH5-1 |  | MH cover installed and backfilling done
Thu (25/07) | 25 Jul 2024 | ST227 |  | Casting in progress
Thu (25/07) | 25 Jul 2024 | P46 |  | Exposing of 22KV to check on cable ID
Thu (25/07) | 25 Jul 2024 | Zone 4 |  | 5th JGP point testing in progress
Thu (25/07) | 25 Jul 2024 | Zone4 P48 |  | JGP no day shift today to give way to bored pile work. Night work was arranged to deconflict the work
Thu (25/07) | 25 Jul 2024 | P48-6 |  | Prepare the area to start preboring
Thu (25/07) | 25 Jul 2024 | BP2A-1 | 22 | Boring resumed from 37.6/45.408m
Thu (25/07) | 25 Jul 2024 | ST008 |  | B2 resumed from 32/33.4m
Thu (25/07) | 25 Jul 2024 | P9 |  | Steel installation
Thu (25/07) | 25 Jul 2024 | P10 |  | Backfilling
Thu (25/07) | 25 Jul 2024 | P11 |  | TT for ERSS
Thu (25/07) | 25 Jul 2024 | P13 |  | Preparation for corbel rebar installation and formwork closing
Thu (25/07) | 25 Jul 2024 | P14 |  | Excavation to remove abandoned 22KV cables
Thu (25/07) | 25 Jul 2024 | P16 |  | Pile cap rebar installation started
Thu (25/07) | 25 Jul 2024 | MH3-5 |  | Started excavation for next ring excavation
Thu (25/07) | 25 Jul 2024 | BRP66 |  | Guidewall cast
Thu (25/07) | 25 Jul 2024 | BRP64 |  | Trial trench for guidewall ongoing
Thu (25/07) | 25 Jul 2024 | BRP63 |  | Guidewall rebar works in progress
Thu (25/07) | 25 Jul 2024 | ST161 |  | Trimming ongoing
Thu (25/07) | 25 Jul 2024 | BRP41 |  | B2 in progress, 10.4/34.1m
Thu (25/07) | 25 Jul 2024 | Zone 1 P4 |  | Premix hacking for ERSS TT
Thu (25/07) | 25 Jul 2024 | P2 |  | Preboring of soldier pile in progress, 9/13 completed
Thu (25/07) | 25 Jul 2024 | TDP62 |  | Trial trench in progress
Thu (25/07) | 25 Jul 2024 | TDP54 |  | Trial trench in progress
Thu (25/07) | 25 Jul 2024 | Zone 3 |  | HSL BG25 has parked at TDP48. Preparation works ongoing
Thu (25/07) | 25 Jul 2024 | ST227 |  | Casting completed. Total vol: 249m3
Thu (25/07) | 25 Jul 2024 | BP2A-1 | 22 | Boring in progress
Thu (25/07) | 25 Jul 2024 | ST16 |  | Excavation started at 1525hrs
Thu (25/07) | 25 Jul 2024 | ST008 |  | B1 and B2 completed (33.4m). Now preparing for centre bite
Thu (25/07) | 25 Jul 2024 | ST249 |  | Currently waiting for hydrofraise to resume trenching works
Thu (25/07) | 25 Jul 2024 | P9 |  | Installation of ERSS in progress. To further embed into the ground
Thu (25/07) | 25 Jul 2024 | P10 |  | KTC backfilling works till pile cap level
Thu (25/07) | 25 Jul 2024 | P13 |  | Column rebar installation works in progress
Thu (25/07) | 25 Jul 2024 | P14 |  | Removal of abandoned 22KV and 66kV
Thu (25/07) | 25 Jul 2024 | P48-6 |  | Boring on going, reached 16.8m
Thu (25/07) | 25 Jul 2024 | MH3-5 |  | Excavation for next layer caisson
Thu (25/07) | 25 Jul 2024 | P48-6 |  | Boring work to continue till 9pm
Thu (25/07) | 25 Jul 2024 | P46 |  | TT for BP done for the day
Thu (25/07) | 25 Jul 2024 | MH3-5 |  | Soil disposal
Thu (25/07) | 25 Jul 2024 | BRP64 |  | Excavation for guidewall construction completed. Night shift team to install rebar cage
Thu (25/07) | 25 Jul 2024 | BRP63 |  | Guidewall Formwork closing
Thu (25/07) | 25 Jul 2024 | ST161 |  | End plate extraction
Thu (25/07) | 25 Jul 2024 | DR1 |  | Top plate welding to continue till 9pm
Thu (25/07) | 25 Jul 2024 | BRP41 |  | 2nd bite trenching at 12.1m. Hydraulic hose leaking, cutter body up for replacement
Thu (25/07) | 25 Jul 2024 | TDP62 |  | TT completed, found water pipe 300mm, est 400mm from edge for casing to edge of water pipe
Thu (25/07) | 25 Jul 2024 | TDP48 |  | Boring in progress, est depth 12m
Thu (25/07) | 25 Jul 2024 | STN218-BC2 |  | 2nd bite trenching at 25m. Cutter body hoisting up for teeth replacement
Thu (25/07) | 25 Jul 2024 | STN221 |  | Rebar cage installation, 3/4 cages installed
Thu (25/07) | 25 Jul 2024 | BP2A-1 | 22 | Boring continue at 42m
Thu (25/07) | 25 Jul 2024 | STN253 |  | Preparation for first bite trenching
Thu (25/07) | 25 Jul 2024 | P33 RC stump area |  | WH trial trench at the abandoned drain area
Thu (25/07) | 25 Jul 2024 | Blk 4 |  | Geomotion continue trial trench for RW46
Thu (25/07) | 25 Jul 2024 | P34 |  | WH continue installation for designated walking access
Thu (25/07) | 25 Jul 2024 | PBH68 |  | Coring in progress, 29m
Thu (25/07) | 25 Jul 2024 | P2 |  | Preparation for ERSS pre-boring, 8/13 completed
Fri (26/07) | 26 Jul 2024 | Blk 4/P33 |  | KTC hacking of abandoned drain
Fri (26/07) | 26 Jul 2024 | Blk 4 |  | Geomotion drilling ongoing for RW50
Fri (26/07) | 26 Jul 2024 | Along blk 4 |  | WH continue installing new designated walking access
Fri (26/07) | 26 Jul 2024 | ST249 |  | B1 CD 39.0/50.5m
Fri (26/07) | 26 Jul 2024 | ST253 |  | B1 CD 25.0/46.9m
Fri (26/07) | 26 Jul 2024 | PBH68 |  | Completed 42.3m. Now preparing for grouting
Fri (26/07) | 26 Jul 2024 | ST161 |  | Rebar cage installation in progress, 3/8nos
Fri (26/07) | 26 Jul 2024 | BRP64 |  | Guidewall inspected. Pending casting
Fri (26/07) | 26 Jul 2024 | BRP71 | BC1 | Excavation started today
Fri (26/07) | 26 Jul 2024 | BRP41 |  | B2 in progress
Fri (26/07) | 26 Jul 2024 | Blk 2 |  | WH trial trench ongoing to expose the 22kV. Plan to spike on 29 July
Fri (26/07) | 26 Jul 2024 | TDP48 |  | In progress
Fri (26/07) | 26 Jul 2024 | ST008 |  | WS extraction in progress
Fri (26/07) | 26 Jul 2024 | ST016 Rig 3 |  | B1 CD 31.0/37.2m
Fri (26/07) | 26 Jul 2024 | ST218 Rig 2 |  | Trimming in progress
Fri (26/07) | 26 Jul 2024 | P48-6 |  | Boring down. Clearing the area for rebar cage lowering down
Fri (26/07) | 26 Jul 2024 | MH3-5 |  | Excavation for caisson casting. Tomorrow to cast, to reached 9m depth
Fri (26/07) | 26 Jul 2024 | ST161 |  | Cage A (1/4) and Cage B (3/4) lowering in progress
Fri (26/07) | 26 Jul 2024 | RWN50 |  | Boring in progress. RWN46: pipe installed. Preparing for grouting
Fri (26/07) | 26 Jul 2024 | BRP41 |  | 2nd bite reached, 18.8m. Now clearing soil on cutter wheel
Fri (26/07) | 26 Jul 2024 | P27-P18 |  | Preparing spiking pit for 22KV. Total 11 location plan to do at Zone 3
Fri (26/07) | 26 Jul 2024 | P16 |  | Tie rod welding for formwork closing
Fri (26/07) | 26 Jul 2024 | N5 |  | Cross head rebar work
Fri (26/07) | 26 Jul 2024 | P15 |  | Prepare the area for concrete block ( support)
Fri (26/07) | 26 Jul 2024 | P14 |  | Preboring for ERSS
Fri (26/07) | 26 Jul 2024 | P13 |  | Column formwork closing
Fri (26/07) | 26 Jul 2024 | P12 |  | Drain pipe installation
Fri (26/07) | 26 Jul 2024 | P9 |  | Excavation for 1st layer waler
Fri (26/07) | 26 Jul 2024 | P10 |  | KTC soil backfilling
Fri (26/07) | 26 Jul 2024 | P2 |  | 9 soldier piles installed up to date. Plan for one more number today
Fri (26/07) | 26 Jul 2024 | BP2A-2-36 |  | Casing installed. Will continue boring work
Fri (26/07) | 26 Jul 2024 | ST218 |  | Excavation completed. Preparing to change wire
Fri (26/07) | 26 Jul 2024 | ST226 |  | TT for guidewall work
Fri (26/07) | 26 Jul 2024 | ST16 |  | 1st bite excavation done
Fri (26/07) | 26 Jul 2024 | P48-6 |  | Preparing for casting
Sat (27/07) | 27 Jul 2024 | P4-P5 |  | WH removing premix/hardcore for ERSS trial trench works
Sat (27/07) | 27 Jul 2024 | Zone 1 |  | CGS hacking ongoing for tactile installation at traffic light
Sat (27/07) | 27 Jul 2024 | P2 |  | LE continue preboring for ERSS installation. Later tonight ard 1AM, plan to shift rig to centre median
Sat (27/07) | 27 Jul 2024 | MH5-2 |  | Excavator maintenance
Sat (27/07) | 27 Jul 2024 | MH1-2 |  | No activity
Sat (27/07) | 27 Jul 2024 | PRD3 |  | Trailer breakdown by others
Sat (27/07) | 27 Jul 2024 | Zone 4 GI works |  | Grouting for 1st point. Target 3 nos tonight
Sat (27/07) | 27 Jul 2024 | ST249 |  | B2 reached toe level 41.2m. Cutter teeth changing ongoing
Sat (27/07) | 27 Jul 2024 | ST253 |  | B1 excavation in progress
Sat (27/07) | 27 Jul 2024 | ST16 |  | Excavation temporarily stopped. Cutter teeth changing ongoing
Sat (27/07) | 27 Jul 2024 | ST226 |  | Trial trench ongoing
Sat (27/07) | 27 Jul 2024 | BP2A-1 | 22 | Casting was completed earlier this morning ard 1am. Now HSL continue boring for BP2A-2(36)
Sat (27/07) | 27 Jul 2024 | TDP48 |  | Pending toe confirmation
Sat (27/07) | 27 Jul 2024 | BRP41 |  | B2 in progress, 29.2/34.1m
Sat (27/07) | 27 Jul 2024 | Blk 4 |  | Geomotion continue drilling for RW50, KTC continue hacking of abandoned drain, WH continue hardcore removal and excavation
Sat (27/07) | 27 Jul 2024 | ST161 |  | Casting in progress, 66/220m3
Sat (27/07) | 27 Jul 2024 | BRP71 |  | Excavation reached 29.6m
Sat (27/07) | 27 Jul 2024 | BRP68 |  | Guidewall rebar works in progres
Sat (27/07) | 27 Jul 2024 | MH3-5 |  | Pending for inspection and cast next layer
Sat (27/07) | 27 Jul 2024 | P49 |  | WH excavation for drain removal
Sat (27/07) | 27 Jul 2024 | Zone 4 |  | Singtel cable pulling
Sat (27/07) | 27 Jul 2024 | DR1 |  | LE has mobilised mobile crane for beam installation
Sat (27/07) | 27 Jul 2024 | P2 |  | ERSS preboring in progress, 12/13nos. Today to complete installation
Sat (27/07) | 27 Jul 2024 | Zone 1 |  | Continue excavation to expose services here
Sat (27/07) | 27 Jul 2024 | Zone 1 |  | CGS continue hacking for tactile installation at the other bound
Sat (27/07) | 27 Jul 2024 | P14 |  | Continue preboring for ERSS
Sat (27/07) | 27 Jul 2024 | P13 |  | Column formwork installation in progress
Sat (27/07) | 27 Jul 2024 | P9 |  | KTC continue excavation
Sat (27/07) | 27 Jul 2024 | ST249 |  | B1 and B2 completed. Now base cleaning. Target to cast this panel tmr morning
Sat (27/07) | 27 Jul 2024 | ST008 |  | Continue WS extraction. Target to cast this panel tmr night
Sat (27/07) | 27 Jul 2024 | BP2A-2 | 36 | Boring in progress
Sat (27/07) | 27 Jul 2024 | DR1 |  | Beam installation in progress, 5/12nos
Sat (27/07) | 27 Jul 2024 | PBH71 |  | Coring in progress, 17m
Sat (27/07) | 27 Jul 2024 | ST161 |  | Casting in progress
Sat (27/07) | 27 Jul 2024 | BRP68 |  | Guidewall formwork done and inspected. Pending to cast
Sat (27/07) | 27 Jul 2024 | P34 |  | Diverted walking access completed
Sat (27/07) | 27 Jul 2024 | Blk 4 |  | KTC continue hacking
Sat (27/07) | 27 Jul 2024 | P16 |  | No more activity
Sat (27/07) | 27 Jul 2024 | N5 crosshead status |  | Rebar installation only balance starter. Tendon pipe sleeves 14/18 installed
Sat (27/07) | 27 Jul 2024 | P9 |  | Excavation to W1 layer completed. Railing and scaffold access installation till 10pm. Tomorrow to start waler installation
Sat (27/07) | 27 Jul 2024 | STN249 |  | End plate and water stop installation
Sat (27/07) | 27 Jul 2024 | STN253 |  | Hydrofraise cutter teeth maintenance. 1st bite: 26/46.9m
Sat (27/07) | 27 Jul 2024 | STN008 |  | Water stop extraction
Sat (27/07) | 27 Jul 2024 | STN16-BC3 |  | 2nd trenching depth at 30/37.2m
Sat (27/07) | 27 Jul 2024 | ST229-BC2 |  | Preparation for trenching. Teeth changing in progress
Sat (27/07) | 27 Jul 2024 | P16 |  | Continue pilecap rebar works
Sat (27/07) | 27 Jul 2024 | N5 |  | Crosshead rebar works ongoing
Sat (27/07) | 27 Jul 2024 | P15 |  | No activity
Sat (27/07) | 27 Jul 2024 | BP12-2 | 36 | Boring on going, 34.3m/41.87m
Sat (27/07) | 27 Jul 2024 | ST218 |  | Waterstop lowering and preparation for rebar cage installation
Sat (27/07) | 27 Jul 2024 | TDP48 |  | Casting completed
Sat (27/07) | 27 Jul 2024 | TDP54 |  | Boring in progress, balance 1m to bore. Casting tonight
Sat (27/07) | 27 Jul 2024 | P14 |  | Preboring by LE in progress
Sat (27/07) | 27 Jul 2024 | P13 |  | Pier formwork installation in progress. Plan for casting on monday
Sat (27/07) | 27 Jul 2024 | P12 |  | No activity
Sat (27/07) | 27 Jul 2024 | BRP41 |  | Teeth replacement. Preparation for 3rd bite trenching
Sat (27/07) | 27 Jul 2024 | BRP71-BC1 |  | Cleaning in progress
Sat (27/07) | 27 Jul 2024 | P9 |  | KTC excavation to S1 level
Sun (28/07) | 28 Jul 2024 | P10 |  | KTC soil backfilling for completed footing
Sun (28/07) | 28 Jul 2024 | Zone 4 |  | GI pipe for plywood placing along gas pipe
Sun (28/07) | 28 Jul 2024 | P44 |  | Materials mobilizing for rig set up
Sun (28/07) | 28 Jul 2024 | P43 |  | TT for bored pile
Sun (28/07) | 28 Jul 2024 | BRP71 |  | Concrete ordered for casting
Sun (28/07) | 28 Jul 2024 | BRP39 |  | Preparing to resume excavation
Sun (28/07) | 28 Jul 2024 | Blk 4 |  | 2 excavators + 1 mini hacking and removal of capping beam
Sun (28/07) | 28 Jul 2024 | ST218 |  | Cage A (3/3) and cage B (3/3) lowered down. Hanging bar installation. Today to cast
Sun (28/07) | 28 Jul 2024 | Zone 1 |  | No activity. Just housekeepinh and sand bag placing along water barrier only
Sun (28/07) | 28 Jul 2024 | ST226 |  | Guide wall rebar work in progress. Today plan for casting
Sun (28/07) | 28 Jul 2024 | ST229 |  | 1st bite excavation in progress. Reached 15m depth
Sun (28/07) | 28 Jul 2024 | Zone 1 |  | Preparing to shift boring rig at P3 area
Sun (28/07) | 28 Jul 2024 | Zone 4 GI works |  | Grouting for 3rd point
Sun (28/07) | 28 Jul 2024 | ST249 |  | Cage A (3/4) and Cage B (3/4) lowered down. Preparing to continue lowering of balance 2 cages
Sun (28/07) | 28 Jul 2024 | P16 |  | Shear link installation for footing work
Sun (28/07) | 28 Jul 2024 | N5 |  | Preparing for balance formwork closing
Sun (28/07) | 28 Jul 2024 | P14 |  | No activity of preboring due to public feedback
Sun (28/07) | 28 Jul 2024 | P13 |  | Access installation for casting work
Sun (28/07) | 28 Jul 2024 | P10 |  | KTC backfilling done
Sun (28/07) | 28 Jul 2024 | P9 |  | Current status of waler installation
Sun (28/07) | 28 Jul 2024 | MH5-2 |  | Scaffold erection
Sun (28/07) | 28 Jul 2024 | ST229 |  | BC cutter gear box changing
Sun (28/07) | 28 Jul 2024 | ST218 |  | Removal of rebar cages coz trench collapse. Need to clean the trench again before lowering rebar cages
Sun (28/07) | 28 Jul 2024 | BRP41 |  | Rebar cage lowering dow
Sun (28/07) | 28 Jul 2024 | STN249 |  | Endplate and waterstop lowering continue
Sun (28/07) | 28 Jul 2024 | ST16 |  | 2nd bite excavation completed. Preparing for Koden test
Sun (28/07) | 28 Jul 2024 | ST229-BC2 |  | 1st bite trenching in progress, 15/32.4m
Sun (28/07) | 28 Jul 2024 | STN16-BC3 |  | 2nd bite trenching continue, depth at 34.3/37.2m
Sun (28/07) | 28 Jul 2024 | BP12-2 | 36 | Boring stopped at 12mn
Sun (28/07) | 28 Jul 2024 | ST218 |  | Rebar cage installation on going, 2/4 cages installed
Sun (28/07) | 28 Jul 2024 | TDP54 |  | Casting completed
Sun (28/07) | 28 Jul 2024 | BRP41 |  | 3rd bite trenching completed. Cleaning in progress
Sun (28/07) | 28 Jul 2024 | ST249 |  | Bachy lowering of rebar cage
Sun (28/07) | 28 Jul 2024 | N5 |  | Inspection of rebar. Tomorrow will be final inspection
Sun (28/07) | 28 Jul 2024 | P16 |  | Starter bar installation for column
Sun (28/07) | 28 Jul 2024 | P13 |  | Column formwork closing
Sun (28/07) | 28 Jul 2024 | P14 |  | Preboring for ERSS work
Mon (29/07) | 29 Jul 2024 | N5 crosshead |  | Railing modification for side formwork closing
Mon (29/07) | 29 Jul 2024 | P48-5 |  | Preparing for preboring work
Mon (29/07) | 29 Jul 2024 | P45 |  | Preparing for drain hacking and removal
Mon (29/07) | 29 Jul 2024 | Zone 4 |  | More or less ready for gas pipe laying. Left plywood to provide
Mon (29/07) | 29 Jul 2024 | N4 |  | Scaffold erection for pier main bar cutting and re-bending
Mon (29/07) | 29 Jul 2024 | N2 |  | Platform preparation for falsework erection
Mon (29/07) | 29 Jul 2024 | P13 pier |  | Formwork final inspection. After lunch to cast
Mon (29/07) | 29 Jul 2024 | P15 |  | Preparation for corbel rebar installation
Mon (29/07) | 29 Jul 2024 | P10 |  | Backfilling to pile cap level done. NDT completed. Afternoon to cast Concrete plug
Mon (29/07) | 29 Jul 2024 | P9 |  | Waler beam installation
Mon (29/07) | 29 Jul 2024 | MH5-2 |  | HDPE lining works
Mon (29/07) | 29 Jul 2024 | Zone 1 junction |  | Tactile installation
Mon (29/07) | 29 Jul 2024 | P2 |  | Partial ERSS installation completed
Mon (29/07) | 29 Jul 2024 | BRP41 |  | Casting completed, 134m3
Mon (29/07) | 29 Jul 2024 | Blk 4 |  | Continue hacking for capping beam and rebar cutting
Mon (29/07) | 29 Jul 2024 | BC1 |  | Currently no activity
Mon (29/07) | 29 Jul 2024 | PBH71 |  | In progress, 29m
Mon (29/07) | 29 Jul 2024 | BRP57 |  | Hacking ongoing for trial trench works
Mon (29/07) | 29 Jul 2024 | Blk 4 |  | Geomotion continue trial trench for RW54
Mon (29/07) | 29 Jul 2024 | BRP39 |  | Dongah preparing for preboring works
Mon (29/07) | 29 Jul 2024 | P9 |  | Waler beam welding status
Mon (29/07) | 29 Jul 2024 | P12 |  | Installation of corbel rebar
Mon (29/07) | 29 Jul 2024 | P13 |  | Setting of concrete pump for casting
Mon (29/07) | 29 Jul 2024 | N5 |  | Surveyor taking asbuilt lay-out
Mon (29/07) | 29 Jul 2024 | P16 |  | Ppile cap link installation continue
Mon (29/07) | 29 Jul 2024 | BRP34 | BC4 | Excavation in progress
Mon (29/07) | 29 Jul 2024 | ST218 |  | Rebar cage installation in progress, 6/6nos
Mon (29/07) | 29 Jul 2024 | BP2A-2 | 36 | Boring in progress
Mon (29/07) | 29 Jul 2024 | ST225 |  | Trial trench ongoing. Found Singtel pipe
Mon (29/07) | 29 Jul 2024 | ST003 |  | B1 excavation started this morning
Mon (29/07) | 29 Jul 2024 | TDP56 |  | Preboring and casing installation
Mon (29/07) | 29 Jul 2024 | ST008 |  | Rebar cage installation in progress, 2/8nos
Mon (29/07) | 29 Jul 2024 | ST253 |  | B1 reached 38/46.9m
Mon (29/07) | 29 Jul 2024 | ST16 |  | Desanding completed, final koden check. Thereafter will install waterstop
Mon (29/07) | 29 Jul 2024 | P46-8 |  | Boring in progress. Plan to cast tomorrow
Mon (29/07) | 29 Jul 2024 | MH3-5 |  | Excavation for next layer caisson casting
Mon (29/07) | 29 Jul 2024 | ST159 |  | 1st bite in progress, reached 6.5m
Mon (29/07) | 29 Jul 2024 | PBH71 |  | Boring reached 34m/37m
Mon (29/07) | 29 Jul 2024 | DR1 |  | Beam to soldier piles connection area welding work
Mon (29/07) | 29 Jul 2024 | BRP34 |  | Boring reached 11m depth
Mon (29/07) | 29 Jul 2024 | TDP56 |  | Casing installed
Mon (29/07) | 29 Jul 2024 | TDP46 |  | Preparing for casing installation
Mon (29/07) | 29 Jul 2024 | P16 |  | Form tie welding
Mon (29/07) | 29 Jul 2024 | P14 |  | Preboring for ERSS installation
Mon (29/07) | 29 Jul 2024 | P13 |  | Concrete already on site for column casting
Mon (29/07) | 29 Jul 2024 | P12 |  | Column rebar work
Mon (29/07) | 29 Jul 2024 | P10 |  | Prop concrete casting
Mon (29/07) | 29 Jul 2024 | P9 |  | 1st layer waler joint welding
Mon (29/07) | 29 Jul 2024 | P2 |  | Soldier pile: 13/13, Steel plate:08/08
Mon (29/07) | 29 Jul 2024 | ST253 |  | 2nd bite, reached 9.5m
Mon (29/07) | 29 Jul 2024 | ST003 |  | 1st bite grabbing reached 12.5m
Mon (29/07) | 29 Jul 2024 | ST229 |  | 2nd bite, reached 15m
Mon (29/07) | 29 Jul 2024 | BP2A-2 | 36 | Boring reached 39m
Mon (29/07) | 29 Jul 2024 | P48-5 |  | Boring until 10PM. No other activity at Zone 4
Mon (29/07) | 29 Jul 2024 | P16 |  | Pil3 cap links installation
Tue (30/07) | 30 Jul 2024 | N5 |  | Preparation for side formwork closing
Tue (30/07) | 30 Jul 2024 | P13 |  | Pier cast yesterday. Access dismantling
Tue (30/07) | 30 Jul 2024 | P12 |  | Corbel rebar installation completed. Shearlinks installation at lapping area
Tue (30/07) | 30 Jul 2024 | P7 |  | 6.6KV spiking done
Tue (30/07) | 30 Jul 2024 | P48-5 |  | Boring in progress. Today to cast
Tue (30/07) | 30 Jul 2024 | P48-5 |  | Rebar inspection
Tue (30/07) | 30 Jul 2024 | Zone 1 junction |  | Tactile installation
Tue (30/07) | 30 Jul 2024 | P4 |  | TT for ERSS
Tue (30/07) | 30 Jul 2024 | P43 |  | TT for bored pile work
Tue (30/07) | 30 Jul 2024 | BRP57 |  | Guidewall rebar work
Tue (30/07) | 30 Jul 2024 | DR1 |  | Secondary beam joining and welding. 2 welders + 1 rigger + 1Sup
Tue (30/07) | 30 Jul 2024 | BRP39 |  | Boring to break the rock. Reached 22m
Tue (30/07) | 30 Jul 2024 | BC cutter 4 |  | Teeth changing
Tue (30/07) | 30 Jul 2024 | DW16 |  | Rebar cage lowering. Today to cast
Tue (30/07) | 30 Jul 2024 | N5 crosshead |  | Rebar inspection
Tue (30/07) | 30 Jul 2024 | P14 |  | Continue preboring for ERSS
Tue (30/07) | 30 Jul 2024 | P9 |  | Continue waler beams & struts welding works, today to complete
Tue (30/07) | 30 Jul 2024 | ST003 |  | B2 CD 6.0/34.8m
Tue (30/07) | 30 Jul 2024 | ST253 |  | B2 CD 29.0/49.9m
Tue (30/07) | 30 Jul 2024 | P12 |  | Shearlinks installation continue
Tue (30/07) | 30 Jul 2024 | MH5-2 |  | HDPE lining works in progress
Tue (30/07) | 30 Jul 2024 | ST229 Rig 2 |  | Excavation in progress, CD 24.5m
Tue (30/07) | 30 Jul 2024 | BP2A-2 | 36 | Boring CD @ 41.9/41.869m. Waiting for RTO to witness toe level
Tue (30/07) | 30 Jul 2024 | TDP46 |  | Casting in progress
Tue (30/07) | 30 Jul 2024 | P48-5 |  | Rebar cage lowering. Today to cast
Tue (30/07) | 30 Jul 2024 | P49 |  | Exposing of water pipe for bitumen application
Tue (30/07) | 30 Jul 2024 | P2 |  | KTC Excavation to S1 layer in progress
Tue (30/07) | 30 Jul 2024 | BRP39 BG01 |  | B2 CD 23.0/25.7m
Tue (30/07) | 30 Jul 2024 | BRP34 Rig 4 |  | B1 CD 21.0/31.17m
Tue (30/07) | 30 Jul 2024 | DR1 |  | WHDA installing platform prior LE continues with welding work
Tue (30/07) | 30 Jul 2024 | ST159A Rig 1 |  | Loosening of WSEP has completed, waiting for crane for removal work
Tue (30/07) | 30 Jul 2024 | BRP71 |  | Backfilling of LSS in progress
Tue (30/07) | 30 Jul 2024 | BRP57 |  | Guidewall to cast by today
Tue (30/07) | 30 Jul 2024 | MH3-5 |  | Excavation half done. Tomorrow to cast
Tue (30/07) | 30 Jul 2024 | P43 |  | Bentonite plant set up by HSL
Tue (30/07) | 30 Jul 2024 | P43 |  | TT for bored pile work
Tue (30/07) | 30 Jul 2024 | STN003 |  | 2nd bite trenching in progress. Grabber hoist up for cleaning
Tue (30/07) | 30 Jul 2024 | STN253 |  | 2nd bite trenching at 34m depth
Tue (30/07) | 30 Jul 2024 | ST229 |  | 1st bite trenching at 26.8m depth
Tue (30/07) | 30 Jul 2024 | ST16 |  | All rebar cages installed. Balance hanging bar
Tue (30/07) | 30 Jul 2024 | TDP3 |  | Shoring installation for 22Kv spiking tomorrow
Tue (30/07) | 30 Jul 2024 | TDP56 |  | Boring in progress
Tue (30/07) | 30 Jul 2024 | TDP58 |  | Casing installed
Tue (30/07) | 30 Jul 2024 | DR1 |  | Secondary beam welding works for Utility support
Tue (30/07) | 30 Jul 2024 | P16 pile cap |  | Final inspection for casting
Wed (31/07) | 31 Jul 2024 | P2 |  | Railing installation prior to waler beam installation
Wed (31/07) | 31 Jul 2024 | P49 |  | Protection of water pipe for POWS approval
Wed (31/07) | 31 Jul 2024 | P9 |  | Annex C&D submitted. To proceed excavation to FEL
Wed (31/07) | 31 Jul 2024 | P12 |  | Column formwork closing
Wed (31/07) | 31 Jul 2024 | MH3-5 |  | Caisson shaft casting in progress
Wed (31/07) | 31 Jul 2024 | P43&P44 |  | GCE demob and HSL rig delivery. Rebar cage on site
Wed (31/07) | 31 Jul 2024 | ST253 |  | B2 CD 39.0/49.9m
Wed (31/07) | 31 Jul 2024 | ST010 |  | B1 excavation started
Wed (31/07) | 31 Jul 2024 | ST229 Rig 2 |  | B1 CD 30/32.4m
Wed (31/07) | 31 Jul 2024 | ST226 Rig 3 |  | Preparing to start excavation
Wed (31/07) | 31 Jul 2024 | TDP56 |  | Ongoing kingpost installation, TDP58: Boring in progress
Wed (31/07) | 31 Jul 2024 | BRP34 Rig 4 |  | B1 CD 28.5/31.17m, hydraulic hose under maintenance
Wed (31/07) | 31 Jul 2024 | BRP39 BG01 |  | B2 CD 25.5/25.7m
Wed (31/07) | 31 Jul 2024 | DR1 welding work in progress. Till date |  | 8/12 main beam, 12/26 secondary beam
Wed (31/07) | 31 Jul 2024 | P16 |  | Column rebar work started
Wed (31/07) | 31 Jul 2024 | N5 |  | Continue rectification of duct
Wed (31/07) | 31 Jul 2024 | P14 |  | Soldier pile installation for ERSS work
Wed (31/07) | 31 Jul 2024 | P15 |  | Column rebar work
Wed (31/07) | 31 Jul 2024 | P12 |  | Column formwork closing
Wed (31/07) | 31 Jul 2024 | MH5-2 |  | HDPE welding work
Wed (31/07) | 31 Jul 2024 | P2 |  | Preparation for slope protection casting
Wed (31/07) | 31 Jul 2024 | ST22 |  | Exposing 22KV for spiking tomorrow
Wed (31/07) | 31 Jul 2024 | TDP58 |  | Toe confirmation. Today to cast. TDP42: casting already done
Wed (31/07) | 31 Jul 2024 | BC cutter No-4 |  | Hydraulic hose changing
Wed (31/07) | 31 Jul 2024 | Blk4 |  | Continue hacking of drain and capping beam. Today will hack until 11PM. 3 noise balloons provided at Mapletree side
Wed (31/07) | 31 Jul 2024 | BRP41 |  | LSS backfilling
Wed (31/07) | 31 Jul 2024 | DR1 |  | Second beam installation. Tonight until 9PM
Wed (31/07) | 31 Jul 2024 | BRP68 |  | 1st bite, reached 6m
Wed (31/07) | 31 Jul 2024 | P43& P44 |  | Boring rig set up in progress. Assembling of plant also in progress
Thu (01/08) | 01 Aug 2024 | P14 |  | Balance 4 nos pre-boring for steel plate
Thu (01/08) | 01 Aug 2024 | P11 |  | Waler beam dismantling
Thu (01/08) | 01 Aug 2024 | P9 |  | Excavation to FEL
Thu (01/08) | 01 Aug 2024 | ST229 Rig 2 |  | B1 CD 30/32.4m, teeth replacement in progress
Thu (01/08) | 01 Aug 2024 | ST226 Rig 3 |  | B1 CD 25.2/33.3m
Thu (01/08) | 01 Aug 2024 | SCDF will be at car park around 10 |  | 30AM and we will go to Zone 4 for emergency drill
Thu (01/08) | 01 Aug 2024 | BRP34 Rig 4 |  | B1 CD 28.5/31.17m, hydraulic hose still under maintenance
Thu (01/08) | 01 Aug 2024 | BRP39 BG01 |  | Boring CD 22.4/25.07m
Thu (01/08) | 01 Aug 2024 | BRP68 Rig 1 |  | B1 CD 24.8/31.87m
Thu (01/08) | 01 Aug 2024 | P49 |  | Protection of water pipe at side done. Now backfilling and steel plate placing on top
Thu (01/08) | 01 Aug 2024 | P48 |  | Rig set up for bored pile work
Thu (01/08) | 01 Aug 2024 | P2 |  | Waler beam installation
Thu (01/08) | 01 Aug 2024 | P2 Deckpost |  | Frame delivery for PDA tomorrow
Thu (01/08) | 01 Aug 2024 | P48 |  | Platform prepared. Rig in position for preboring work
Thu (01/08) | 01 Aug 2024 | MH5-2 |  | HDPE lining continue
Thu (01/08) | 01 Aug 2024 | P10 |  | Preparation for rebar cage assembly
Thu (01/08) | 01 Aug 2024 | MH3-5 |  | Formwork removal and prepare to excavate for next layer caisson
Thu (01/08) | 01 Aug 2024 | N5 |  | Final inspection of duct prior to side formwork closing
Thu (01/08) | 01 Aug 2024 | STN003 |  | 1st bite trenching at 32.1m
Thu (01/08) | 01 Aug 2024 | STN253 |  | Rebar cage installation, 6/8 cage installed. 7th cage installation in progress
Thu (01/08) | 01 Aug 2024 | ST229-BC2 |  | 3rd bite trenching at 27m depth
Thu (01/08) | 01 Aug 2024 | STN226-BC3 |  | 1st bite trenching at 30m depth. Cutter body hoisting up for teeth replacement
Thu (01/08) | 01 Aug 2024 | BP2A-2 | 36 | LSS casting completed
Thu (01/08) | 01 Aug 2024 | TDP48 |  | Boring until 8pm. Depth 20m
Thu (01/08) | 01 Aug 2024 | BRP34 |  | 2nd bite trenching started
Thu (01/08) | 01 Aug 2024 | BRP39 |  | Boring works completed
Thu (01/08) | 01 Aug 2024 | BRP77 |  | TT completed. Backfilling on going
Thu (01/08) | 01 Aug 2024 | ST159A |  | End plate lowering
Thu (01/08) | 01 Aug 2024 | BRP68 |  | Single bite trenching at 25m
Thu (01/08) | 01 Aug 2024 | P16 |  | Stump links installation
Thu (01/08) | 01 Aug 2024 | N5 |  | Duct adjustment, balance 2 pipes
Thu (01/08) | 01 Aug 2024 | ST003 |  | B1 CD 31.4/34.8m
Thu (01/08) | 01 Aug 2024 | ST253 |  | Desanding in progress
Thu (01/08) | 01 Aug 2024 | ST010 |  | B1 CD 23.0/39.2m
Fri (02/08) | 02 Aug 2024 | ST229 Rig 2 |  | Teeth replacement is in progress
Fri (02/08) | 02 Aug 2024 | P49 |  | Water pipe protection done. Backfilling done
Fri (02/08) | 02 Aug 2024 | P14 |  | Today to complete ERSS installation
Fri (02/08) | 02 Aug 2024 | P9 |  | Excavation to FEL continue. Est to complete by Sunday
Fri (02/08) | 02 Aug 2024 | Zone 2 |  | Removal of D1 kerb and replace with water barrier in preparation for syage 1A diversion
Fri (02/08) | 02 Aug 2024 | P48-1 |  | Preboring started
Fri (02/08) | 02 Aug 2024 | MH3-5 |  | Excavation on going. Two more layers + base slab to complete. Target next week
Fri (02/08) | 02 Aug 2024 | P44 |  | LP cable cut. Now exposing water pipe for removal (700mm dia)
Fri (02/08) | 02 Aug 2024 | P4 |  | 22KV cut and water pipe confirmed abandoned. Pipe and cable removal in progress
Fri (02/08) | 02 Aug 2024 | N5 crosshead |  | Formwork final inspection by RE
Fri (02/08) | 02 Aug 2024 | P48-1 |  | Boring reached 18m. Tomorrow to cast
Fri (02/08) | 02 Aug 2024 | MH3-5 |  | Continue excavation. Tomorrow to cast one ring
Fri (02/08) | 02 Aug 2024 | N5 crosshead |  | Casting in progress
Fri (02/08) | 02 Aug 2024 | P16 |  | Stump formwork closing
Fri (02/08) | 02 Aug 2024 | P14 |  | Driving SP 700mm below ground level
Fri (02/08) | 02 Aug 2024 | P9 |  | Excavation to FEL continue. Est 2.5m depth
Fri (02/08) | 02 Aug 2024 | STN226-BC3 |  | 2nd bite trenching at 10m depth
Fri (02/08) | 02 Aug 2024 | ST17-BC2 |  | 1st bite trenching at 19m depth
Fri (02/08) | 02 Aug 2024 | TDP42 |  | Casting completed
Fri (02/08) | 02 Aug 2024 | TDP60 |  | Platform setting up for casting
Fri (02/08) | 02 Aug 2024 | BRP34 |  | Cutter body hoist up for teeth replacement. Nightshift to take over
Fri (02/08) | 02 Aug 2024 | BP2A-2 | 35 | Casing installed for boring works
Sat (03/08) | 03 Aug 2024 | MH5-2 |  | HDPE lining to complete by today
Sat (03/08) | 03 Aug 2024 | P9 |  | Excavation to FEL continue
Sat (03/08) | 03 Aug 2024 | P10 |  | Column rebar cage fabrication continue
Sat (03/08) | 03 Aug 2024 | P11 |  | ERSS pre-boring started
Sat (03/08) | 03 Aug 2024 | P12 column |  | Unable to cast today, missing trimmer bar for RWDP missing
Sat (03/08) | 03 Aug 2024 | P14 |  | Driving pile and steel plate 700mm from ground level
Sat (03/08) | 03 Aug 2024 | P15 |  | Preparation for corbel rebar installation
Sat (03/08) | 03 Aug 2024 | BRP63 |  | Excavation completed. Now cleaning toe
Sat (03/08) | 03 Aug 2024 | BRP34 |  | 2nd bite completed. 1st bite reached 30m
Sat (03/08) | 03 Aug 2024 | ST226 |  | 2nd bite reached 27m
Sat (03/08) | 03 Aug 2024 | ST229 |  | Removal of waterstop end plate
Sat (03/08) | 03 Aug 2024 | ST17 |  | Changing cutter teeth and welding of cutter holder
Sat (03/08) | 03 Aug 2024 | STN250 |  | 1st bite trenching at 19m depth
Sat (03/08) | 03 Aug 2024 | STN10 |  | 1st bote trenching at 29.5m depth
Sat (03/08) | 03 Aug 2024 | STN226-BC3 |  | 2nd bite trenching at 23m depth
Sat (03/08) | 03 Aug 2024 | ST17-BC2 |  | 1st bite trenching to resume, depth at 31.2m
Sat (03/08) | 03 Aug 2024 | BP2A-2 | 35 | Preparation for boring works
Sat (03/08) | 03 Aug 2024 | BRP34-BC4 |  | 2nd bite trenching, depth at 28m
Sat (03/08) | 03 Aug 2024 | DR1 |  | Secondary beam welding
Sat (03/08) | 03 Aug 2024 | BRP63-BC1 |  | 1st bite trenching, current depth 21m
Sat (03/08) | 03 Aug 2024 | BRP68 |  | Casting in progress
Sat (03/08) | 03 Aug 2024 | P43-44 |  | Crane weekly inspection
Sat (03/08) | 03 Aug 2024 | zobe 4 |  | Grouting rig demobilization
Sat (03/08) | 03 Aug 2024 | P48-1 |  | Bentonite top up and preparation to continue boring. to cast today
Sat (03/08) | 03 Aug 2024 | zone 4 |  | To continue gas pipe laying, target 14m
Sat (03/08) | 03 Aug 2024 | STN003 |  | Rebar cage installation
Sat (03/08) | 03 Aug 2024 | STN250 |  | Trenching continue for 1st bite
Sat (03/08) | 03 Aug 2024 | P16 stump |  | Platform erection for casting
Sat (03/08) | 03 Aug 2024 | P14 |  | SP and LP driving completed
Sat (03/08) | 03 Aug 2024 | P13 |  | Dismantling for column formwork continue
Sat (03/08) | 03 Aug 2024 | P12 |  | Pier bent bar installation
Sat (03/08) | 03 Aug 2024 | P11 |  | Pre-boring for ERSS continue
Sat (03/08) | 03 Aug 2024 | P10 |  | Backfilling to stump level
Sat (03/08) | 03 Aug 2024 | P10 |  | Cage fabrication continue
Sat (03/08) | 03 Aug 2024 | P9 |  | Excavation to FEL continue
Sat (03/08) | 03 Aug 2024 | P2 area |  | Traffic deck top plate installation status, 5/6 installed
Sat (03/08) | 03 Aug 2024 | P4 |  | TT backfilling and levelling continue
Sat (03/08) | 03 Aug 2024 | Zone 4 |  | Gas pipe installation in progress
Sat (03/08) | 03 Aug 2024 | P48-1 |  | Rebar installed. Platform preparation for casting
Sat (03/08) | 03 Aug 2024 | MH3-5 |  | Excavation for next layer caison
Sat (03/08) | 03 Aug 2024 | P44-4 |  | Preparation for pre-boring and casing installation
Sat (03/08) | 03 Aug 2024 | P44 |  | ECM pond slurry clearing
Sat (03/08) | 03 Aug 2024 | BRP63-BC1 |  | Trenching in progress, current depth 23m
Sat (03/08) | 03 Aug 2024 | BH98, BH100 |  | Drilling and SPT in progress
Sat (03/08) | 03 Aug 2024 | DR1 |  | Excavation started to W1 layer
Sat (03/08) | 03 Aug 2024 | BRP39 |  | Pre-boring in progress
Sat (03/08) | 03 Aug 2024 | BRP34-BC4 |  | 2nd bite trenching, depth at 30.95m
Sat (03/08) | 03 Aug 2024 | TDP62 |  | Casing installed for boring works
Sat (03/08) | 03 Aug 2024 | ST10 |  | 1st bite excavation in progress
Sat (03/08) | 03 Aug 2024 | P16 |  | Scaffold erection for column casting
Sat (03/08) | 03 Aug 2024 | P14 |  | Excavation in progress for 1st layer waler installation
Sat (03/08) | 03 Aug 2024 | P10 |  | Backfilling done. Plan for testing on Monday
Sat (03/08) | 03 Aug 2024 | P48-1 |  | Waiting for last lorry to complete casting
Sat (03/08) | 03 Aug 2024 | Zone 1 P2 area |  | Top plate welding for traffic deck
Sat (03/08) | 03 Aug 2024 | P4 |  | TT area backfilling. Today to prepare platform for rig
Sun (04/08) | 04 Aug 2024 | ST-229 |  | Preparation for cleaning works
Sun (04/08) | 04 Aug 2024 | Zone 2 CCW |  | Bachy no activity today
Sun (04/08) | 04 Aug 2024 | P16 |  | Pilecap formwork removal in progress. Monday to cast column stump
Sun (04/08) | 04 Aug 2024 | N5 |  | No activity
Sun (04/08) | 04 Aug 2024 | P14 |  | KTC excavation to S1 layer in progress
Sun (04/08) | 04 Aug 2024 | P11 |  | No activity. Preboring not allowed on Sunday due to noisy works. Monday to resume preboring
Sun (04/08) | 04 Aug 2024 | P9 |  | Access shifting ongoing for excavation to FEL
Sun (04/08) | 04 Aug 2024 | MH5-2 |  | HDPE lining completed. Cleaning works in progress. Benching to start tmr. Target to complete by tues
Sun (04/08) | 04 Aug 2024 | MH5-1 |  | No activity. Monday to continue scaffold installation then HDPE lining
Sun (04/08) | 04 Aug 2024 | P2 |  | Traffic deck top plate welding status, 2/6 completed. Water pumping in progress before resume welding works
Sun (04/08) | 04 Aug 2024 | Zone 4 |  | No activity
Sun (04/08) | 04 Aug 2024 | MH3-5 |  | No activity, curing in progress. Cast completed yesterday
Sun (04/08) | 04 Aug 2024 | Zone 4 Loyang Way |  | Netlink cable pulling works
Sun (04/08) | 04 Aug 2024 | Zone 3 BRP63-BC01 |  | King post & hanging bar welding work completed. Preparing for tremie pipe installation in progress
Sun (04/08) | 04 Aug 2024 | Zone 3 BRP34 |  | 1st bite excavation completed
Sun (04/08) | 04 Aug 2024 | Zone 3 BRP39 |  | Boring works in progress
Sun (04/08) | 04 Aug 2024 | ST003 |  | Casting in progress
Sun (04/08) | 04 Aug 2024 | ST010 |  | Chieselling before continue excavation
Sun (04/08) | 04 Aug 2024 | ST17 |  | 1st bite in progress, reached 36.6m
Sun (04/08) | 04 Aug 2024 | ST226 |  | 1st bite trimming in progress
Sun (04/08) | 04 Aug 2024 | BRP34 |  | 1st bite reached 30.2m. Now hyraulic hoses leaking. Need to repair
Sun (04/08) | 04 Aug 2024 | STN-226 |  | BC cutter shifting in progress. To resume 2nd bite excavation, STN-229: Preparation for rebar cage lowering
Sun (04/08) | 04 Aug 2024 | ST-17 |  | Continue Gearbox replacement & maintenance works in progress
Sun (04/08) | 04 Aug 2024 | BRP63 |  | Koden testing in progress. BRP64: 1st bite excavation started
Sun (04/08) | 04 Aug 2024 | BRP34 |  | 3rd bite excavation in progress
Sun (04/08) | 04 Aug 2024 | BRP39 |  | 2nd bite Boring works in progress
Sun (04/08) | 04 Aug 2024 | BRP42 |  | Guidewall trial trench & excavation works
Sun (04/08) | 04 Aug 2024 | Zone 3 BRP63 |  | Preparation for casting in progress, BRP64: BC cutter teeth changing ongoing
Sun (04/08) | 04 Aug 2024 | P2 |  | Traffic deck top plate welding status, 2/6 completed. Housekeeping ongoing. Welding to continue tmr due to ongoing heavy rain
Sun (04/08) | 04 Aug 2024 | P9 |  | Access shifting completed. Tmr to resume excavation to FEL
Sun (04/08) | 04 Aug 2024 | P14 |  | KTC excavation to S1 layer completed
Sun (04/08) | 04 Aug 2024 | P16 |  | Continue Pilecap formwork dismantle & removal
Sun (04/08) | 04 Aug 2024 | BRP34 |  | 1st bite reached 30.90m/31.17m
Sun (04/08) | 04 Aug 2024 | BRP63 |  | Handing bar installation and lowering in progress
Sun (04/08) | 04 Aug 2024 | BRP64 |  | Cutter teeth changing
Sun (04/08) | 04 Aug 2024 | ST-17 |  | Gearbox replacement in progress
Sun (04/08) | 04 Aug 2024 | ST-231 |  | Trial trench for guide wall in progress
Mon (05/08) | 05 Aug 2024 | P44 |  | Boring works stopped for the day
Mon (05/08) | 05 Aug 2024 | MH3-5 |  | Work stopped for the day
Mon (05/08) | 05 Aug 2024 | ST100 |  | Trial trench in progres
Mon (05/08) | 05 Aug 2024 | BC1 |  | Currently no activity
Mon (05/08) | 05 Aug 2024 | BH98 |  | SI in progress, 30.5m
Mon (05/08) | 05 Aug 2024 | DR1 |  | Manually clearing soil below sewer pipes
Mon (05/08) | 05 Aug 2024 | ST170 area |  | WH exposing trench for Singtel localised shifting. SPPG cable already spiked here. Plan for Lucky Joint to come in on 12-13 Aug
Mon (05/08) | 05 Aug 2024 | BRP42 |  | Guidewall plan for casting today
Mon (05/08) | 05 Aug 2024 | ST250 |  | B1 CD 31.4/38.4m
Mon (05/08) | 05 Aug 2024 | ST010 |  | B2 CD 34.9/39.2m
Mon (05/08) | 05 Aug 2024 | P16 |  | Preparation for column stump casting today
Mon (05/08) | 05 Aug 2024 | P15 |  | Corbel rebars installation works
Mon (05/08) | 05 Aug 2024 | P11 |  | LE preboring works for ERSS
Mon (05/08) | 05 Aug 2024 | P10-1 |  | Column rebar cage fabrication ongoing
Mon (05/08) | 05 Aug 2024 | P9-1 |  | Excavation to FEL in progress
Mon (05/08) | 05 Aug 2024 | BC4 |  | Now preparing for BRP39 excavation. BRP34 cleaning and desanding completed
Mon (05/08) | 05 Aug 2024 | Zone 2 | P6-P7 | Current premix status for Stage 1a. Tonight to continue
Mon (05/08) | 05 Aug 2024 | BP2A-2 | 35 | Boring in progress, CD 16.5/42.074m
Mon (05/08) | 05 Aug 2024 | BRP31 BG01 |  | Preparation work in progress
Mon (05/08) | 05 Aug 2024 | TDP62 |  | Waiting for concrete to cast it. Next will be TDP50 & TDP52
Mon (05/08) | 05 Aug 2024 | MH5-2 |  | Benching works in progress
Mon (05/08) | 05 Aug 2024 | MH5-1 |  | Scaffold installation in progress for HDPE lining
Mon (05/08) | 05 Aug 2024 | ST17 | BC2 | B1 temporarily stopped for gearbox & suction box changing. CD 36.6/36.9m
Mon (05/08) | 05 Aug 2024 | P49-5 |  | Preparing for preboring
Mon (05/08) | 05 Aug 2024 | P5 |  | Premix hacking commenced for BP trial trench works
Mon (05/08) | 05 Aug 2024 | P2 |  | Traffic deck top plate welding in progress. Target to complete today
Mon (05/08) | 05 Aug 2024 | P44-4 |  | Boring in progress, reached 13m
Mon (05/08) | 05 Aug 2024 | MH3-5 |  | Caisson formwork removal
Mon (05/08) | 05 Aug 2024 | BH100 |  | Boring reached 12m
Mon (05/08) | 05 Aug 2024 | BRP64 |  | Excavation done. BC cutter maintenance now. Will resume desanding later
Mon (05/08) | 05 Aug 2024 | DR1 |  | CGS exposing water pipe for LE to install support for sewer pipe
Mon (05/08) | 05 Aug 2024 | ST170 |  | Prepare for localise shifting of Singtel cable
Mon (05/08) | 05 Aug 2024 | BRP42 |  | Guidewall casting
Mon (05/08) | 05 Aug 2024 | BRP34 |  | Preparing for rebar cage lowering. Tonight to cast
Mon (05/08) | 05 Aug 2024 | TDP62 |  | Casting done
Mon (05/08) | 05 Aug 2024 | TDP52 |  | Removing road premix for preboring work
Mon (05/08) | 05 Aug 2024 | P16 |  | Column casting in progress
Mon (05/08) | 05 Aug 2024 | P14 |  | Pile head hacking
Mon (05/08) | 05 Aug 2024 | P9 |  | Excavation to FEL. Tonight to complete
Mon (05/08) | 05 Aug 2024 | ST10 |  | Chieselling
Mon (05/08) | 05 Aug 2024 | ST226 |  | 3rd bite completed
Mon (05/08) | 05 Aug 2024 | ST229 |  | Tremie pipe lowering for casting
Mon (05/08) | 05 Aug 2024 | BP02-2-35 |  | Boring reached 34m
Mon (05/08) | 05 Aug 2024 | P16 |  | Stump casting completed
Mon (05/08) | 05 Aug 2024 | P14 |  | Test pile hacking till W1 layer completed. Railing installation to continue until 10pm
Mon (05/08) | 05 Aug 2024 | P9 |  | Excavation to FEL till 930pm
Mon (05/08) | 05 Aug 2024 | Zone 2 bus lane |  | Tonight to continue M&P here after the last bus for stage 1A diversion
Mon (05/08) | 05 Aug 2024 | Zone 2 P6 area |  | Installation of silt fence and kerb casting
Mon (05/08) | 05 Aug 2024 | ST10 |  | Chiselling to continue tonight
Mon (05/08) | 05 Aug 2024 | STN229 |  | For casting, concrete ordered
Mon (05/08) | 05 Aug 2024 | STN226-BC3 |  | Preparation for trimming
Mon (05/08) | 05 Aug 2024 | BP2A-2 | 35 | Boring works, depth at 35.5m
Mon (05/08) | 05 Aug 2024 | BRP34 |  | Rebar cage installed. Prepreparation for Kingpost lowering
Mon (05/08) | 05 Aug 2024 | BRP39 |  | 1st bite trenching, teeth replacement. Current depth at 20m
Mon (05/08) | 05 Aug 2024 | BRP42 |  | Guidewall casting completed
Tue (06/08) | 06 Aug 2024 | BC1 |  | Currently no activity
Tue (06/08) | 06 Aug 2024 | BH100 |  | In progress, 18m
Tue (06/08) | 06 Aug 2024 | BH98 |  | In progress, 37.5m
Tue (06/08) | 06 Aug 2024 | DR1 |  | LE continue manual soil clearing prior to installing the support
Tue (06/08) | 06 Aug 2024 | ST170 area |  | WH continue excavation for the Singtel localised shifting works
Tue (06/08) | 06 Aug 2024 | P5 |  | Premix hacking for BP TT
Tue (06/08) | 06 Aug 2024 | P4 |  | Pre-boring for ERSS in progress
Tue (06/08) | 06 Aug 2024 | P2 |  | No activity, waiting for traffic deck materials. Afternoon to deliver and install
Tue (06/08) | 06 Aug 2024 | BRP39 | BC4 | Excavation temporarily stopped for cutter teeth changing
Tue (06/08) | 06 Aug 2024 | BRP34 |  | KP and rebar cage installed. Today to cast
Tue (06/08) | 06 Aug 2024 | ST194 |  | Trial trench in progres
Tue (06/08) | 06 Aug 2024 | BRP31 |  | Preboring in progress
Tue (06/08) | 06 Aug 2024 | TDP52 |  | Casing installed, pending vertically check
Tue (06/08) | 06 Aug 2024 | TDP34 |  | Premix hacking ongoing for trial trench works
Tue (06/08) | 06 Aug 2024 | BP2A-2 | 35 | Boring resumed from 36.5/42.074m
Tue (06/08) | 06 Aug 2024 | ST226 |  | Trimming completed. Now BC2 currently no activity. Was informed on site that rebar cages (8nos) for ST226 have yet to be delivered to site. Plan for delivery today
Tue (06/08) | 06 Aug 2024 | ST17 | BC3 | B1 completed, 37.1/36.9m. Now cutter teeth changing before start B2
Tue (06/08) | 06 Aug 2024 | ST10 |  | Bentonite check and cutter teeth changing ongoing
Tue (06/08) | 06 Aug 2024 | STN250 |  | 1st bite trenching in progress
Tue (06/08) | 06 Aug 2024 | P46 to P47 |  | Gas pipe laying done is 30m today. Total completed is 366m
Tue (06/08) | 06 Aug 2024 | P49-5 |  | Boring completed. Preparing for rebar cage lowering
Tue (06/08) | 06 Aug 2024 | RW37 |  | Drilling in progress
Tue (06/08) | 06 Aug 2024 | RW57 |  | Installation in progress
Tue (06/08) | 06 Aug 2024 | ST010 |  | Chiselling in progress, B1 CD 37.5/39.2m
Tue (06/08) | 06 Aug 2024 | ST100 |  | Guidewall construction in progress
Tue (06/08) | 06 Aug 2024 | P41 area |  | Dongah dismantling storage shed. Materials are being shifted to new container storage
Tue (06/08) | 06 Aug 2024 | BC1 |  | Cutter wheel maintenance ongoing
Tue (06/08) | 06 Aug 2024 | P16 |  | Column stump cast yesterday, curing ongoing
Tue (06/08) | 06 Aug 2024 | P15 |  | Levelling & steel plate laying works for crane parking
Tue (06/08) | 06 Aug 2024 | N4 |  | Column rebar adjustment in progress
Tue (06/08) | 06 Aug 2024 | P14 |  | Waler brackets installation in progress
Tue (06/08) | 06 Aug 2024 | N2 |  | Falsework current status
Tue (06/08) | 06 Aug 2024 | P11 |  | Preboring for ERSS installation
Tue (06/08) | 06 Aug 2024 | P10 |  | Premix hacking for propping installation location
Tue (06/08) | 06 Aug 2024 | P9 |  | Levelling works in progress. Today to complete
Tue (06/08) | 06 Aug 2024 | ST229 |  | Casting completed
Tue (06/08) | 06 Aug 2024 | ST10 |  | Chiselling continue
Tue (06/08) | 06 Aug 2024 | DR1 |  | CGS continue manual excavation for support works
Tue (06/08) | 06 Aug 2024 | P44-5 |  | Boring done. Preparing for rebar cage lowering
Tue (06/08) | 06 Aug 2024 | MH3-5 |  | Excavation for last layer
Tue (06/08) | 06 Aug 2024 | ST170 area |  | WH continue manual excavation for the Singtel localised shifting works
Tue (06/08) | 06 Aug 2024 | Along DR2 |  | Geomotion installing flow meters for recharge wells
Tue (06/08) | 06 Aug 2024 | MH5-2 |  | Benching & patching works ongoing
Tue (06/08) | 06 Aug 2024 | MH5-1 |  | HDPE lining works in progress
Tue (06/08) | 06 Aug 2024 | P4 |  | Preboring works ongoing for ERSS
Tue (06/08) | 06 Aug 2024 | DW44 |  | Guidewall inspected. Pending to cast
Tue (06/08) | 06 Aug 2024 | BRP39 |  | 1st bite trenching in progress. Current depth at 22.8m
Tue (06/08) | 06 Aug 2024 | P2 |  | Traffic decking top plate welding completed. 1st batch of beams delivery will arrive tmr
Tue (06/08) | 06 Aug 2024 | P16 |  | Concrete plug casting
Tue (06/08) | 06 Aug 2024 | P15 |  | Column formwork closing
Tue (06/08) | 06 Aug 2024 | P14 |  | Waler bracket welding
Tue (06/08) | 06 Aug 2024 | P9 |  | Excavation done by KTC. They prepare to remove their mini
Tue (06/08) | 06 Aug 2024 | MH5-1 |  | No activity by LCH
Tue (06/08) | 06 Aug 2024 | ST250 |  | No activity. Grabbing done
Tue (06/08) | 06 Aug 2024 | ST10 |  | 1st bite reached 38m
Tue (06/08) | 06 Aug 2024 | BC cutter 2 |  | Cutter wheel replacement
Tue (06/08) | 06 Aug 2024 | BRP31 |  | Preboring work already stopped
Tue (06/08) | 06 Aug 2024 | BRP34 |  | Concrete ordered
Tue (06/08) | 06 Aug 2024 | BRP39 |  | 1st bite reached 23.2m
Tue (06/08) | 06 Aug 2024 | Beside Blk 4 |  | KTC removal of hardcore and soil
Tue (06/08) | 06 Aug 2024 | DR1 |  | LE already end work at 7PM
Tue (06/08) | 06 Aug 2024 | TDP52 |  | Casting in progress
Tue (06/08) | 06 Aug 2024 | Blk 4 |  | KTC continue soil and hardcore removal
Tue (06/08) | 06 Aug 2024 | Blk 4 |  | RW57 in progress
Tue (06/08) | 06 Aug 2024 | P16 |  | Scaffold dismantling
Tue (06/08) | 06 Aug 2024 | P15 |  | Preparation for formwork closing
Tue (06/08) | 06 Aug 2024 | P14 |  | Area preparation for waler bracket installation
Tue (06/08) | 06 Aug 2024 | N2 |  | Falsework for crosshead started. 👍
Tue (06/08) | 06 Aug 2024 | P11 |  | Pre-boring for ERSS, 9/26 completed for SP
Tue (06/08) | 06 Aug 2024 | ST100 |  | Guidewall in progress. Plan for casting today
Tue (06/08) | 06 Aug 2024 | P9 |  | Excavation to complete this morning. Afternoon HSL to start pile head hacking
Tue (06/08) | 06 Aug 2024 | Zone 2 stage 1 pre-diversion work |  | D1 kerb installation
Wed (07/08) | 07 Aug 2024 | Blk 4 |  | Geomotion has completed RWs installation here. 2nos rigs shift to blk 2, KTC will do trial trench here
Wed (07/08) | 07 Aug 2024 | Along DR2 |  | Geomotion continue installation of flow meters for RWs & WH grass cutting ongoing
Wed (07/08) | 07 Aug 2024 | P47 to P48 |  | Gas team started trench for pipe laying. Target 30m
Wed (07/08) | 07 Aug 2024 | P48-2 |  | Preparing for preboring
Wed (07/08) | 07 Aug 2024 | P51 |  | Backfilling back the trench to give way to Dongah SI team
Wed (07/08) | 07 Aug 2024 | P39 area |  | Dongah arranging back the steel plates & BRP68 will be backfilled today
Wed (07/08) | 07 Aug 2024 | BC1 |  | Maintenance ongoing
Wed (07/08) | 07 Aug 2024 | PBH75 |  | Hand auger in progres
Wed (07/08) | 07 Aug 2024 | BH100 |  | Coring in progress, 32m
Wed (07/08) | 07 Aug 2024 | P15 |  | Column formwork closing in progress
Wed (07/08) | 07 Aug 2024 | P14 |  | Waler beams installation & welding works
Wed (07/08) | 07 Aug 2024 | BP2A-2 | 35 | Toe level inspected by QPS team, planning to cast it today
Wed (07/08) | 07 Aug 2024 | DR1 | nearer to vent shaft | Angle bar installation and welding ongoing by LE
Wed (07/08) | 07 Aug 2024 | DR1 | P34 area | CGS continue manual excavation below pumping main
Wed (07/08) | 07 Aug 2024 | N6 |  | Soil levelling works ongoing
Wed (07/08) | 07 Aug 2024 | Zone 2 |  | Pile cap rebar unloading
Wed (07/08) | 07 Aug 2024 | P11 |  | Preboring for ERSS in progress
Wed (07/08) | 07 Aug 2024 | P10-1 |  | Preparation for column rebar cage installation. To install tmr
Wed (07/08) | 07 Aug 2024 | ST194 |  | Trial trench ongoing
Wed (07/08) | 07 Aug 2024 | MH5-2 |  | Benching works completed. Balance scaffold removal
Wed (07/08) | 07 Aug 2024 | MH5-1 |  | HDPE lining ongoing
Wed (07/08) | 07 Aug 2024 | MH1-2 |  | Preparation for CCTV checking
Wed (07/08) | 07 Aug 2024 | P5 |  | Road Premix hacking ongoing for BP trial trench
Wed (07/08) | 07 Aug 2024 | P4 |  | Preboring for ERSS ongoing, 6/60nos. completed
Wed (07/08) | 07 Aug 2024 | P2 |  | Clearing of unused materials. Beams for traffic decking to deliver in the afternoon
Wed (07/08) | 07 Aug 2024 | MH3-5 |  | Excavation for last caisson
Wed (07/08) | 07 Aug 2024 | P44-4 |  | Rebar cage lowering. Today to cast
Wed (07/08) | 07 Aug 2024 | P44 TPE bound |  | Shifting of traffice light cables
Wed (07/08) | 07 Aug 2024 | Zone 4 |  | Abandoned drain wall removal for gas pipe laying
Wed (07/08) | 07 Aug 2024 | Along blk 2 |  | WH erecting new walking acces
Wed (07/08) | 07 Aug 2024 | Blk 2 |  | Trial trench for recharge well, RW32 ongoing
Wed (07/08) | 07 Aug 2024 | N6 |  | Continue soil levelling works
Wed (07/08) | 07 Aug 2024 | P16 |  | KTC backfilling to pile cap top level
Wed (07/08) | 07 Aug 2024 | Blk 4 |  | Trial trench ongoing by KTC, witness by utility engr
Wed (07/08) | 07 Aug 2024 | P15 Column |  | Formwork closing
Wed (07/08) | 07 Aug 2024 | P11 |  | LE continue preboring for ERSS
Wed (07/08) | 07 Aug 2024 | P10-1 |  | Concrete blocks installation for column rebar installation tmr
Wed (07/08) | 07 Aug 2024 | P9-1 |  | Pile head cutting in progress
Wed (07/08) | 07 Aug 2024 | P51 |  | SI rig mobilized for probing of sewer line
Wed (07/08) | 07 Aug 2024 | MH5-1 |  | Continue HDPE lining works
Wed (07/08) | 07 Aug 2024 | MH1-2 |  | CCTV checking preparation works
Wed (07/08) | 07 Aug 2024 | P48-2 |  | Casing installation
Wed (07/08) | 07 Aug 2024 | ST100 |  | Guidewall dismantling ongoin
Wed (07/08) | 07 Aug 2024 | BRP64 | BC1 | Cleaning and desanding ongoing
Wed (07/08) | 07 Aug 2024 | BH100 |  | Packer test in progress
Wed (07/08) | 07 Aug 2024 | ST159A |  | LSS backfill
Wed (07/08) | 07 Aug 2024 | P2 |  | Lane closed for unloading of primary (3nos.) & secondary beams (12nos.)
Wed (07/08) | 07 Aug 2024 | P5 |  | Current status for premix hacking
Wed (07/08) | 07 Aug 2024 | P4 |  | ERSS preboring ongoing
Wed (07/08) | 07 Aug 2024 | DR1 |  | CGS continue manual excavation
Wed (07/08) | 07 Aug 2024 | BRP39 |  | In progress, 23.4m
Wed (07/08) | 07 Aug 2024 | ST194 |  | Continue trial trench
Wed (07/08) | 07 Aug 2024 | BRP31 |  | Boring in progress
Wed (07/08) | 07 Aug 2024 | BP2B-2 | 52 | Preboring in progress
Wed (07/08) | 07 Aug 2024 | BP2A-2 | 35 | Rebar cage installation ongoing
Wed (07/08) | 07 Aug 2024 | ST17 | BC3 | B2 completed. Now cutter teeth changing
Wed (07/08) | 07 Aug 2024 | ST10 |  | Chiselling ongoing
Wed (07/08) | 07 Aug 2024 | MH3-5 |  | Excavation left around 300mm to complete. Plan to cast base and wall on 9th August
Wed (07/08) | 07 Aug 2024 | P44-4 |  | Casting in progress
Wed (07/08) | 07 Aug 2024 | P44-5 |  | Preboring in progress
Wed (07/08) | 07 Aug 2024 | P15 |  | Column formwork closing in progress
Wed (07/08) | 07 Aug 2024 | N5 |  | No activity
Wed (07/08) | 07 Aug 2024 | P14 |  | Welding works ongoing
Wed (07/08) | 07 Aug 2024 | P11 |  | Preboring ongoing
Wed (07/08) | 07 Aug 2024 | P10-1 |  | Preparing area for concrete block installation
Wed (07/08) | 07 Aug 2024 | P9 |  | Hacking of pile head currently no activity
Wed (07/08) | 07 Aug 2024 | P7 |  | Backfilling ongoing
Wed (07/08) | 07 Aug 2024 | ST250 |  | B2 reached 20/41.7m
Wed (07/08) | 07 Aug 2024 | ST10 |  | B1 reached 39/39.2m
Wed (07/08) | 07 Aug 2024 | ST17 |  | B3 in progress
Wed (07/08) | 07 Aug 2024 | Blk 4 |  | Manual trial trench ongoing
Wed (07/08) | 07 Aug 2024 | DR1 |  | LE has started to install neoprene pad around the pipe and followed by the timber and c-channel installation (for bottom support)
Wed (07/08) | 07 Aug 2024 | BP2B-2 | 52 | Casing installed
Wed (07/08) | 07 Aug 2024 | BRP39 |  | Excavation temporarily stopped for cutter teeth change. B1 CD 23.4/25.07m
Wed (07/08) | 07 Aug 2024 | BRP31 |  | Preboring temporarily stopped for bucket teeth rectification
Thu (08/08) | 08 Aug 2024 | ST226 |  | Rebar cage lowering in progresss
Thu (08/08) | 08 Aug 2024 | BRP66 | BC1 | Excavation in progres
Thu (08/08) | 08 Aug 2024 | BH100 |  | Coring in progress, 37m
Thu (08/08) | 08 Aug 2024 | P48-2 |  | Boring in progress. Today to cast
Thu (08/08) | 08 Aug 2024 | DR1 |  | LE continue neoprene pad installation around sewer pipes
Thu (08/08) | 08 Aug 2024 | DR1 |  | CGS continue manual excavation near the sewer pipes
Thu (08/08) | 08 Aug 2024 | P16 |  | KTC backfilling till pile cap level ongoing
Thu (08/08) | 08 Aug 2024 | P15 |  | Column Formwork closing
Thu (08/08) | 08 Aug 2024 | P14 |  | ERSS Struts welding in progress
Thu (08/08) | 08 Aug 2024 | P11 |  | Preboring for ERSS
Thu (08/08) | 08 Aug 2024 | P10-1 |  | Preparation to install column rebar cage
Thu (08/08) | 08 Aug 2024 | P9-1 |  | Preparation to lower mini excavator for pile head hacking
Thu (08/08) | 08 Aug 2024 | MH5-1 |  | HDPE lining welding ongoing
Thu (08/08) | 08 Aug 2024 | P4 |  | Preboring for ERSS ongoing
Thu (08/08) | 08 Aug 2024 | P2 |  | Primary & secondary beams fitting in progress
Thu (08/08) | 08 Aug 2024 | MH3-5 |  | BRC installation for last caisson. Tomorrow to cast both caisson and slab
Thu (08/08) | 08 Aug 2024 | P44-5 |  | Boring in progress. Today to cast
Thu (08/08) | 08 Aug 2024 | P10-1 |  | Column rebar cage installed. Lapping ongoing
Thu (08/08) | 08 Aug 2024 | P14 |  | Concrete packing ongoing
Thu (08/08) | 08 Aug 2024 | P14 |  | RG Robotic IS installation ongoing
Thu (08/08) | 08 Aug 2024 | DR1 |  | Continues manual excavation for pumping main area
Thu (08/08) | 08 Aug 2024 | BRP41 |  | Backfilling of LSS
Thu (08/08) | 08 Aug 2024 | P15 |  | Column formwork support installation in progress
Thu (08/08) | 08 Aug 2024 | P14 |  | Strut welding ongoing
Thu (08/08) | 08 Aug 2024 | P9 |  | Pile hacking ongoing
Thu (08/08) | 08 Aug 2024 | ST250 |  | B2 in progres
Thu (08/08) | 08 Aug 2024 | ST261 |  | B1 in progress
Thu (08/08) | 08 Aug 2024 | ST17 | BC3 | Excavation completed. BC3 will move to ST15, ST15 (BC2): B1 CD 20/32.5m. BC2 will move to new panel
Thu (08/08) | 08 Aug 2024 | ST226 |  | Rebar cage installation in progress, 8/8nos
Thu (08/08) | 08 Aug 2024 | Blk 4 |  | KTC continue trial trench until 8pm
Thu (08/08) | 08 Aug 2024 | BRP64 |  | Hanging bar lapping in progress
Thu (08/08) | 08 Aug 2024 | DR1 |  | LE continue joint welding for angle bar and bottom support
Thu (08/08) | 08 Aug 2024 | BRP39 |  | B1 temporarily stopped for cutter teeth change. B1 CD 24.5/25.07m
Thu (08/08) | 08 Aug 2024 | ST194 |  | Guidewall formwork installation in progress
Thu (08/08) | 08 Aug 2024 | TDP50 |  | In progress, 22/25.45m
Thu (08/08) | 08 Aug 2024 | Near Gate 5 |  | Preparing area for cable spiking by SPPG. SPPG already on site
Thu (08/08) | 08 Aug 2024 | Blk 2 |  | Trial trench ongoing for RW32
Thu (08/08) | 08 Aug 2024 | ST261 |  | Preparing to start excavation now
Thu (08/08) | 08 Aug 2024 | Blk 4 |  | KTC continue trial trench prior to excavation for utility support works
Fri (09/08) | 09 Aug 2024 | P2 |  | Secondary beam installation and stiffener plate welding
Fri (09/08) | 09 Aug 2024 | P43 |  | Exposing water pipe to cut
Fri (09/08) | 09 Aug 2024 | MH3-5 |  | Base slab rebar installation
Fri (09/08) | 09 Aug 2024 | BRP66 |  | Prepare platform to cast. Today to cast
Fri (09/08) | 09 Aug 2024 | ST230 |  | 1st bite, reached 18m
Fri (09/08) | 09 Aug 2024 | ST261 |  | 1st bite excavation, reached 20m
Fri (09/08) | 09 Aug 2024 | P14 |  | Waler joint & stiffener plates welding
Fri (09/08) | 09 Aug 2024 | N6 |  | Surface roughening done
Fri (09/08) | 09 Aug 2024 | P09 |  | Pile head hacking
Fri (09/08) | 09 Aug 2024 | BRP66 |  | Casting in progress
Fri (09/08) | 09 Aug 2024 | BC cutter 4 |  | Need to repair gear box
Fri (09/08) | 09 Aug 2024 | Blk 4 |  | 2nos excavation done for utility footing
Fri (09/08) | 09 Aug 2024 | P2 |  | Current status of installation
Fri (09/08) | 09 Aug 2024 | ST15 |  | 1st bite reached 20m
Fri (09/08) | 09 Aug 2024 | ST17 |  | Cleaning and desanding
Fri (09/08) | 09 Aug 2024 | ST226 |  | Casting almost completed
Fri (09/08) | 09 Aug 2024 | ST230 |  | Cutter teeth changing
Fri (09/08) | 09 Aug 2024 | ST250 |  | Excavation completed. Preparing for ST261 excavation
Fri (09/08) | 09 Aug 2024 | N6 |  | CJ roughening
Fri (09/08) | 09 Aug 2024 | P14 |  | Waler joint welding by LE
Sat (10/08) | 10 Aug 2024 | ST17 |  | Rebar cage lowering in progress. 3/4 cage lowering. Today to cast
Sat (10/08) | 10 Aug 2024 | ST15 |  | Pump oil top up. 1st bite reached 15m
Sat (10/08) | 10 Aug 2024 | ST10 |  | Water stop lowering in progress by Bachy
Sat (10/08) | 10 Aug 2024 | ST264 |  | 1st bite, reached 29m
Sat (10/08) | 10 Aug 2024 | P16 |  | Column formwork removal
Sat (10/08) | 10 Aug 2024 | N6 |  | Abudment wall rebar work
Sat (10/08) | 10 Aug 2024 | P16 |  | Scaffold erection
Sat (10/08) | 10 Aug 2024 | P9 |  | Pile head hacking
Sat (10/08) | 10 Aug 2024 | DR1 |  | Preparing for support installation for sewer pipes
Sat (10/08) | 10 Aug 2024 | BP2B-2-52 |  | Boring reached 35m
Sat (10/08) | 10 Aug 2024 | BRP31 |  | Preboring, 3/4 point in progress
Sat (10/08) | 10 Aug 2024 | BC cutter 4 |  | Gear Box changing
Sat (10/08) | 10 Aug 2024 | Blk 4 |  | Total 4nos of excavation done for footing
Sat (10/08) | 10 Aug 2024 | DR1 |  | Woh hup hacking of sewer footing and temporary support installation
Sat (10/08) | 10 Aug 2024 | DR1 |  | Manual excavation for sewer pipe installatio.ln
Sat (10/08) | 10 Aug 2024 | ST100 |  | Preexcavation done. This BC cutter 1 under maintenance. Today only two BC cutter working from Dongah. Two servicing
Sat (10/08) | 10 Aug 2024 | ST110&ST111 |  | Exposing services for guidewall work
Sat (10/08) | 10 Aug 2024 | P44-3 |  | Boring on going
Sat (10/08) | 10 Aug 2024 | P44-5 |  | LSS backfilling
Sat (10/08) | 10 Aug 2024 | MH3-5 |  | Last caisson casting. Base slab casting done
Sat (10/08) | 10 Aug 2024 | P49-4 |  | Boring reached 12m
Sun (11/08) | 11 Aug 2024 | P2 |  | Decking installation in progress
Sun (11/08) | 11 Aug 2024 | Zone 1 centre median |  | No activity
Sun (11/08) | 11 Aug 2024 | MH1-2 |  | Preparation for pump installation works
Sun (11/08) | 11 Aug 2024 | ST10 |  | Casting in progress
Sun (11/08) | 11 Aug 2024 | ST15 | BC3 | B1 resumed from 33.4/36.9m
Sun (11/08) | 11 Aug 2024 | ST230 | BC2 | B2 in progress
Sun (11/08) | 11 Aug 2024 | UKP9 |  | Trial trench in progress, 22kV cables: Spiked, Abandoned 66kV cable: To confirm with utility team
Sun (11/08) | 11 Aug 2024 | Blk 4 |  | No activity
Sun (11/08) | 11 Aug 2024 | ST170 area |  | WH hacking of sewer pipe footing and provided temporary support for the Singtel localised shifting works
Sun (11/08) | 11 Aug 2024 | DR1 |  | CGS and LE no activity today
Sun (11/08) | 11 Aug 2024 | ST111 to ST110 | half | Trial trench in progress. Found abandoned singtel, pending utility confirmation
Sun (11/08) | 11 Aug 2024 | MH3-5 |  | No activity
Sun (11/08) | 11 Aug 2024 | Zone 4 |  | No activity
Sun (11/08) | 11 Aug 2024 | BC1 |  | Currently no activity
Sun (11/08) | 11 Aug 2024 | ST102 |  | Trial trench in progress
Sun (11/08) | 11 Aug 2024 | BRP39 | BC4 | B2 in progress, 19.4/25.07m
Sun (11/08) | 11 Aug 2024 | BRP31 |  | Continue preboring
Sun (11/08) | 11 Aug 2024 | Near N5 |  | Frame erection ongoing for pier rebar cage fabrication
Sun (11/08) | 11 Aug 2024 | P14 |  | Continue excavation
Sun (11/08) | 11 Aug 2024 | P10 |  | Column formwork installation starte
Sun (11/08) | 11 Aug 2024 | P9 |  | Continue pile head hacking
Sun (11/08) | 11 Aug 2024 | ST10 |  | Casting completed (227m3)
Sun (11/08) | 11 Aug 2024 | ST15 |  | B1 in progress, 34.7/36.9m
Sun (11/08) | 11 Aug 2024 | ST230 |  | B2 in progress, 25.8/32.6m
Sun (11/08) | 11 Aug 2024 | BRP31 |  | Preboring temporarily stopped for bucket rectification
Sun (11/08) | 11 Aug 2024 | BRP39 |  | B2 temporarily stopped for flap rectification. B2 CD 19.6/25.07m
Sun (11/08) | 11 Aug 2024 | ST170 area |  | Hacking of sewer footing completed
Sun (11/08) | 11 Aug 2024 | BC1 |  | Maintenance ongoing
Sun (11/08) | 11 Aug 2024 | ST109 |  | Trial trench in progress
Sun (11/08) | 11 Aug 2024 | ST103 |  | Trial trench in progress
Sun (11/08) | 11 Aug 2024 | Near N5 |  | Platform levelling ongoing
Sun (11/08) | 11 Aug 2024 | P15 |  | Preparation works. Plan for casting tmr
Sun (11/08) | 11 Aug 2024 | P14 |  | Excavation in progres
Sun (11/08) | 11 Aug 2024 | P9 |  | Pile head hacking in progress
Mon (12/08) | 12 Aug 2024 | P30 |  | Geomotion works for recharge well ongoing, RW29, RW33, RW34: Trial trench, RW31: Drilling
Mon (12/08) | 12 Aug 2024 | P32 |  | Trial trench for water standpipe by Ryobi G ongoing
Mon (12/08) | 12 Aug 2024 | ST111 to ST109 | half | Excavation and preparation for guidewall
Mon (12/08) | 12 Aug 2024 | BC1 |  | Currently only maintenance works
Mon (12/08) | 12 Aug 2024 | ST170 area |  | Localised shifting of Singtel cable by Lucky Joint ongoing. Singtel officer is also on site
Mon (12/08) | 12 Aug 2024 | PBH75 |  | Completed, 39m. Pending termination confirmation
Mon (12/08) | 12 Aug 2024 | Blk 4 |  | WH mobilised 100T crane
Mon (12/08) | 12 Aug 2024 | ST261 |  | Chiselling in progress, B1 CD 33.0/37.5m, B2 CD 22.0/38.8m
Mon (12/08) | 12 Aug 2024 | P16 |  | Backfilling to stump level
Mon (12/08) | 12 Aug 2024 | N6 |  | Abutment wall rebar works
Mon (12/08) | 12 Aug 2024 | P16 |  | Rebar cage fabrication
Mon (12/08) | 12 Aug 2024 | P14 |  | Excavation to FEL
Mon (12/08) | 12 Aug 2024 | P11 |  | Pre-boring for ERSS
Mon (12/08) | 12 Aug 2024 | P9 |  | Pile head hacking
Mon (12/08) | 12 Aug 2024 | DR1 |  | CGS continue excavation
Mon (12/08) | 12 Aug 2024 | ST015 Rig 3 |  | B2 CD 19/32.5m
Mon (12/08) | 12 Aug 2024 | Blk 4 |  | 4nos footings already exposed. Now ongoing support works for stump construction
Mon (12/08) | 12 Aug 2024 | P49-4 |  | Platform prepare for rebar cage lowering down. Toe level confirmed
Mon (12/08) | 12 Aug 2024 | BP2B-2 | 52 | CD 37.0/38.082m, planning to cast it tomorrow
Mon (12/08) | 12 Aug 2024 | BRP39 |  | B2 in progress, 20.5/25.07m
Mon (12/08) | 12 Aug 2024 | BRP31 |  | Preboring ongoing
Mon (12/08) | 12 Aug 2024 | P4 |  | Pre-boring for erss
Mon (12/08) | 12 Aug 2024 | P44-3 |  | Preparing for casting
Mon (12/08) | 12 Aug 2024 | P44-6 |  | Preparing for preboring
Mon (12/08) | 12 Aug 2024 | P5 |  | Pavement hacking for BP TT
Mon (12/08) | 12 Aug 2024 | P2 decking |  | Area preparation for mass concert casting
Mon (12/08) | 12 Aug 2024 | Zone 1 |  | Kerb shifting for stage 1A diversion
Mon (12/08) | 12 Aug 2024 | P16 |  | Continue backfilling works
Mon (12/08) | 12 Aug 2024 | P14 |  | Excavation to FEL ongoing
Mon (12/08) | 12 Aug 2024 | P10 |  | Column formwork closing in progres
Mon (12/08) | 12 Aug 2024 | P9 |  | Clearing hardcore
Mon (12/08) | 12 Aug 2024 | ST257 |  | Excavation started today
Mon (12/08) | 12 Aug 2024 | ST261 |  | B1 in progress, 34.5/37.5m
Mon (12/08) | 12 Aug 2024 | ST15 |  | B2 in progress, 25.5/32.5m
Mon (12/08) | 12 Aug 2024 | P44-3 |  | Casting in progress
Mon (12/08) | 12 Aug 2024 | ST170 area |  | Singtel cable diversion ongoing
Tue (13/08) | 13 Aug 2024 | Blk 4 | P34 | Today plan to start stump construction
Tue (13/08) | 13 Aug 2024 | ST102 |  | Guidewall excavation ongoing
Tue (13/08) | 13 Aug 2024 | BC1 |  | Currently no activity. Cutter wheel still ongoing maintenance
Tue (13/08) | 13 Aug 2024 | ST111 to ST110 | half | Guidewall construction in progres
Tue (13/08) | 13 Aug 2024 | BH57 |  | Trial trench ongoing, exposing services
Tue (13/08) | 13 Aug 2024 | BRP66 |  | Preparing for LSS backfill
Tue (13/08) | 13 Aug 2024 | MH5-2 |  | HDPE lining for last layer to complete today. Benching to start tomorrow
Tue (13/08) | 13 Aug 2024 | PBH72 |  | Coring in progress, 19m
Tue (13/08) | 13 Aug 2024 | ST170 area |  | Singtel cable was completed yesterday. This evening plan for mandrel test
Tue (13/08) | 13 Aug 2024 | DR1 |  | CGS continue excavation
Tue (13/08) | 13 Aug 2024 | DR1 |  | WH erecting platform for utility support works by LE
Tue (13/08) | 13 Aug 2024 | P50 |  | Exposing drain for removal
Tue (13/08) | 13 Aug 2024 | P47-1 |  | Preparing to start preboring
Tue (13/08) | 13 Aug 2024 | BRP39 |  | Excavation temporarily stopped. Encountered rock. Boring rig shifted to this panel. B2 CD 20.5/25.07m. BC4 has moved to BRP31
Tue (13/08) | 13 Aug 2024 | BRP31 | BC4 | Preparation for trenching
Tue (13/08) | 13 Aug 2024 | TDP44 |  | Preparing to resume boring
Tue (13/08) | 13 Aug 2024 | MH3-5 |  | Clearing materials to give way for jacking work
Tue (13/08) | 13 Aug 2024 | UKP9 |  | Trial trench completed. Found abandoned gas pipe, 66kV. Trench will be backfilled
Tue (13/08) | 13 Aug 2024 | BP2B-2 | 52 | HSL now preparing area for mobile crane for KP installation
Tue (13/08) | 13 Aug 2024 | P44-6 |  | Started boring work
Tue (13/08) | 13 Aug 2024 | ST15 |  | B2 in progress, 30.5/32.5m
Tue (13/08) | 13 Aug 2024 | ST261 |  | B1 in progress, 35.8/37.5m
Tue (13/08) | 13 Aug 2024 | ST257 |  | B1 in progress
Tue (13/08) | 13 Aug 2024 | ST233-ST234 |  | Guidewall rebar works ongoing
Tue (13/08) | 13 Aug 2024 | ST230 |  | Rebar cage installation in progress, 3/8nos
Tue (13/08) | 13 Aug 2024 | P30 |  | RW29 drilling & RW28 trial trench ongoing
Tue (13/08) | 13 Aug 2024 | RW34 |  | Drilling in progress
Tue (13/08) | 13 Aug 2024 | ST102 |  | Preparing guidewall rebar works
Tue (13/08) | 13 Aug 2024 | BC1 |  | Maintenance ongoing, waiting for gearbox delivery
Tue (13/08) | 13 Aug 2024 | Exit 1 |  | KTC started to clear hardcore for ECM pond extension works
Tue (13/08) | 13 Aug 2024 | PBH72 |  | In progress, 23m
Tue (13/08) | 13 Aug 2024 | Zone 4 |  | Hacking and removal of abandoned drain
Tue (13/08) | 13 Aug 2024 | DR1 |  | Continue manual excavation between sewer pipes
Tue (13/08) | 13 Aug 2024 | MH5-1 |  | HPDE lining works ongoing. To complete by today
Tue (13/08) | 13 Aug 2024 | P47-5 |  | Casing installed
Tue (13/08) | 13 Aug 2024 | P4 |  | Preboring in progress for ERSS
Tue (13/08) | 13 Aug 2024 | MH3-5 |  | Jacking frame and container on site
Tue (13/08) | 13 Aug 2024 | P2 |  | Traffic deck backfilling with RCA done
Tue (13/08) | 13 Aug 2024 | P44-6 |  | Continue boring work. This week target 6 piles to cast at Zone 4
Tue (13/08) | 13 Aug 2024 | STN261 |  | Hydrofraise maintenance work
Tue (13/08) | 13 Aug 2024 | STN257 |  | 2nd bite trenching continue
Tue (13/08) | 13 Aug 2024 | STN235-236 |  | Excavation for guidewall construction
Tue (13/08) | 13 Aug 2024 | STN233-234 |  | Formwork closing for casting
Tue (13/08) | 13 Aug 2024 | ST15-BC3 |  | 3rd bite trenching in progress, 8m depth
Tue (13/08) | 13 Aug 2024 | ST225-BC2 |  | 1st bite trenching at 17.9m depth
Tue (13/08) | 13 Aug 2024 | STN230 |  | Rebar cage installation continue, 6/8 cages
Tue (13/08) | 13 Aug 2024 | BP2B- 2 | 52 | Preparation for KP lifting
Tue (13/08) | 13 Aug 2024 | P30 |  | Geomotion preparation works for RW29 drilling works
Tue (13/08) | 13 Aug 2024 | N5 crosshead |  | Side formwork dismantling
Tue (13/08) | 13 Aug 2024 | P11 |  | LE rig maintenance
Tue (13/08) | 13 Aug 2024 | P9 |  | Hardcore clearing. Today to lean concrete
Wed (14/08) | 14 Aug 2024 | P7 |  | Backfilling works for stage1A diversion
Wed (14/08) | 14 Aug 2024 | PBH72 |  | Coring in progress, 35.5/47m
Wed (14/08) | 14 Aug 2024 | ST225 Rig 2 |  | B1 CD 27.5/32.9m
Wed (14/08) | 14 Aug 2024 | DR1 |  | CGS continue manual clearing of soil at sewer pipes footings
Wed (14/08) | 14 Aug 2024 | DR1 |  | LE continue joint welding of angle bar
Wed (14/08) | 14 Aug 2024 | DR1 |  | Scaffold platform still installation in progress by WH
Wed (14/08) | 14 Aug 2024 | P34 |  | Preparing for pull-out test for stump construction. Test will be in the afternoon
Wed (14/08) | 14 Aug 2024 | P9 |  | Guidebar installation for pile cap rebar works
Wed (14/08) | 14 Aug 2024 | P10 |  | Casting platform installation
Wed (14/08) | 14 Aug 2024 | P11 |  | Pre-boring for ERSS continue. SP26/26, LP 13/26
Wed (14/08) | 14 Aug 2024 | P44-6 |  | Boring in progress. Today to cast
Wed (14/08) | 14 Aug 2024 | ST225 |  | 1st bite trenching continue, current depth 28.7m
Wed (14/08) | 14 Aug 2024 | ST18-BC3 |  | Trenching started
Wed (14/08) | 14 Aug 2024 | ST015 |  | Cleaning and desanding completed. Preparation for water stop lowering
Wed (14/08) | 14 Aug 2024 | STN261 |  | 2nd bite trenching at 33.3m depth
Wed (14/08) | 14 Aug 2024 | Blk 2 |  | Geomotion preparing for RW28 drilling
Wed (14/08) | 14 Aug 2024 | RW33 |  | Drilling in progress
Wed (14/08) | 14 Aug 2024 | ST100 | BC1 | First bite resumed from 33.1/34m
Wed (14/08) | 14 Aug 2024 | Zone 1 |  | Area preparation for stage 1A diversion. D1 kerb installation and RCA compaction. M&P for 2md and 3rd lane scheduled on 16 dayshift
Wed (14/08) | 14 Aug 2024 | ST111 , ST110, ST109(half) | half | Guidewall has been cast
Wed (14/08) | 14 Aug 2024 | P4 |  | Pre-boring for ERSS, SP 13/30, LP 9/26 completed
Wed (14/08) | 14 Aug 2024 | P5 |  | Premix and pavement hacking continue
Wed (14/08) | 14 Aug 2024 | BH57 |  | Preparing for hand auger
Wed (14/08) | 14 Aug 2024 | ST102 |  | Guidewall rebar works ongoing
Wed (14/08) | 14 Aug 2024 | P47-5 |  | Boring in progress. Today to cast
Wed (14/08) | 14 Aug 2024 | P50 |  | Abandoned drain removal for water pipe protection work
Wed (14/08) | 14 Aug 2024 | P51 |  | Try to do TT again base on changes in pile size
Thu (15/08) | 15 Aug 2024 | DR1 |  | Current status
Thu (15/08) | 15 Aug 2024 | ST261 |  | Excavation completed, WS extraction in progress
Thu (15/08) | 15 Aug 2024 | ST100 |  | Trimming ongoing
Thu (15/08) | 15 Aug 2024 | ST257 |  | B1 CD 25.0/38.0m, B2 CD 14.5/38.0m
Thu (15/08) | 15 Aug 2024 | ST018 Rig 3 |  | B1 CD 18.8/36.5m
Thu (15/08) | 15 Aug 2024 | ST015 |  | Rebar cage lowering in progress
Thu (15/08) | 15 Aug 2024 | ST225 Rig 2 |  | B1 CD 29.8/32.9m
Thu (15/08) | 15 Aug 2024 | UKP12 |  | Boring has started
Thu (15/08) | 15 Aug 2024 | P50 |  | Exposing drain and removal
Thu (15/08) | 15 Aug 2024 | P47-5 |  | Confirming the toe. Today to cast
Thu (15/08) | 15 Aug 2024 | BRP31 Rig 4 |  | Triming in progress
Thu (15/08) | 15 Aug 2024 | BRP39 BG01 |  | PB5 CD 22.3/25.07m
Thu (15/08) | 15 Aug 2024 | P44-2 |  | Will start preboring after traffic pole shifting to deconflict of work. Pole footing exposed
Thu (15/08) | 15 Aug 2024 | MH3-5 |  | Jacking frame lowered down. Preparing for thrust block. Today target to cast
Thu (15/08) | 15 Aug 2024 | Gate 5 |  | WH preparing slab formwork for genset installation for MH2-8 pump
Thu (15/08) | 15 Aug 2024 | Gate 5 |  | Hacking and excavation in progress for 300mm water pipe works (stage 2)
Thu (15/08) | 15 Aug 2024 | P29 |  | RW26 trial trench in progress
Thu (15/08) | 15 Aug 2024 | P30 |  | RW30 drilling ongoing
Thu (15/08) | 15 Aug 2024 | P16 |  | Walers & waler brackets removal ongoing
Thu (15/08) | 15 Aug 2024 | N5 |  | Falsework removal ongoing
Thu (15/08) | 15 Aug 2024 | P16 |  | Column rebar cage fabrication
Thu (15/08) | 15 Aug 2024 | BH57 |  | Coring in progress, 22m
Thu (15/08) | 15 Aug 2024 | ST100 |  | Continue trimming
Thu (15/08) | 15 Aug 2024 | P48-3 |  | Preboring done. Casing installation in progress
Thu (15/08) | 15 Aug 2024 | P50 |  | Drain removal for water pipe protection
Thu (15/08) | 15 Aug 2024 | P47-5 |  | Preparing for casting. This week target 3/6nos cast. Today will cast one number
Thu (15/08) | 15 Aug 2024 | Zone 1 |  | Marking done for stage 1 diversion
Thu (15/08) | 15 Aug 2024 | P14 |  | KTC excavation & Levelling works in progress. Today to complete
Thu (15/08) | 15 Aug 2024 | P11-1 |  | Continue ERSS preboring works
Thu (15/08) | 15 Aug 2024 | P10-1 |  | Scaffold erection in progress
Thu (15/08) | 15 Aug 2024 | P9-1 |  | Pile cap rebar installation
Thu (15/08) | 15 Aug 2024 | MH5-1 |  | Benching works in progress. Today to complete
Thu (15/08) | 15 Aug 2024 | P34 |  | Trial trench ongoing by KTC
Thu (15/08) | 15 Aug 2024 | P34 |  | RC stump rebar and formwork installation ongoing. Plan for casting tmr
Thu (15/08) | 15 Aug 2024 | DR1 |  | Preparing for access installation
Thu (15/08) | 15 Aug 2024 | P44-2 |  | Casing installed. Boring in progress
Thu (15/08) | 15 Aug 2024 | MH3-5 |  | Rebar work for thrust block. Tonight to cast
Thu (15/08) | 15 Aug 2024 | ST261 |  | Koden check in progress
Thu (15/08) | 15 Aug 2024 | ST18 |  | B1 in progress, 31/36.5m
Thu (15/08) | 15 Aug 2024 | ST22 |  | Guidewall casting
Thu (15/08) | 15 Aug 2024 | Gate 5 |  | Excavation and installation of water pipe
Thu (15/08) | 15 Aug 2024 | ST100 |  | Continue trimming
Thu (15/08) | 15 Aug 2024 | P44-2 |  | Boring ongoing
Thu (15/08) | 15 Aug 2024 | Exit 1 |  | Trial trench for ECM pond extension in progress
Thu (15/08) | 15 Aug 2024 | MH3-5 |  | Preparing for thrust block casting
Thu (15/08) | 15 Aug 2024 | DR1 |  | Welding works for utility support continue till 9pm
Thu (15/08) | 15 Aug 2024 | ST170 |  | Trial trench prior to guidewall construction ongoing
Thu (15/08) | 15 Aug 2024 | BRP31 |  | B2 in progress, 8/32.77m
Fri (16/08) | 16 Aug 2024 | ST018 Rig 3 |  | B1 CD 30.0/36.5m
Fri (16/08) | 16 Aug 2024 | P32 |  | RG started drillimg for water standpipe installation
Fri (16/08) | 16 Aug 2024 | Zone 1 |  | Lane closed for M&P works
Fri (16/08) | 16 Aug 2024 | Gate 5 |  | Continue excavation & installation for water pipe (stage 2)
Fri (16/08) | 16 Aug 2024 | Zone 1 |  | LE boring rig dismantling and demobilisation
Fri (16/08) | 16 Aug 2024 | ST112 BC Rig 1 |  | Preparation work prior commence of excavation
Fri (16/08) | 16 Aug 2024 | MH5-1 |  | Railing and vent pipe installation ongoing
Fri (16/08) | 16 Aug 2024 | P9-1 |  | Pile cap rebar installation works
Fri (16/08) | 16 Aug 2024 | P11-1 |  | Vibro shifting in progress. Prepration to start ERSS installation
Fri (16/08) | 16 Aug 2024 | P14 |  | Pile head cutting works ongoing
Fri (16/08) | 16 Aug 2024 | N4 |  | Oiling of Formwork and access making for crosshead ongoing
Fri (16/08) | 16 Aug 2024 | P16 |  | Backfilling to column stump level ongoing
Fri (16/08) | 16 Aug 2024 | P16 |  | Column Rebar cage fabrication works
Fri (16/08) | 16 Aug 2024 | P15 |  | Preparation for casting today
Fri (16/08) | 16 Aug 2024 | P48-2 |  | Boring in progress, target to cast today
Fri (16/08) | 16 Aug 2024 | MH3-5 |  | Soft eye hacking and platform installation
Fri (16/08) | 16 Aug 2024 | P44-2 |  | Preparing for casting
Fri (16/08) | 16 Aug 2024 | ST100 |  | Rebar cage installation in progress, 3/8nos
Fri (16/08) | 16 Aug 2024 | BH57 |  | Current depth 35m/43m. Packer test ongoing
Fri (16/08) | 16 Aug 2024 | ST112 | BC1 | B1 started
Fri (16/08) | 16 Aug 2024 | Exit 1 |  | Trial trench for ECM pond extension in progress, services exposed
Fri (16/08) | 16 Aug 2024 | BH109 |  | Coring in progress, 12m
Fri (16/08) | 16 Aug 2024 | ST170 |  | Pending support installation for guidewall then inspection. To cast today
Fri (16/08) | 16 Aug 2024 | Near ST170 |  | Netlink cable recovery ongoing
Fri (16/08) | 16 Aug 2024 | P34 |  | 2/4nos RC stump formwork completed & inspected. Concrete ordered
Fri (16/08) | 16 Aug 2024 | P34 |  | Continue formwork installation for next stump. Target to complete 4/4nos this week
Fri (16/08) | 16 Aug 2024 | DR1 |  | CGS continue excavation
Fri (16/08) | 16 Aug 2024 | BRP39 |  | Continue preboring
Fri (16/08) | 16 Aug 2024 | BRP31 |  | B2 temporarily stopped. Cutter wheel jam. CD 31/32.77m
Fri (16/08) | 16 Aug 2024 | ST23 |  | Hardcore removal for guidewall trial trench
Fri (16/08) | 16 Aug 2024 | BP4A-2 | 43 | Boring in progress
Fri (16/08) | 16 Aug 2024 | TDP36 |  | Casing installed
Fri (16/08) | 16 Aug 2024 | ST225 |  | Trimming temporarily stopped for rectification
Fri (16/08) | 16 Aug 2024 | ST18 |  | B1 temporarily stopped for cutter teeth changing. B1 CD 34.6/36.5m
Fri (16/08) | 16 Aug 2024 | ST261 |  | Casting completed (267m3)
Fri (16/08) | 16 Aug 2024 | ST257 |  | B1 reached 32/38m
Fri (16/08) | 16 Aug 2024 | ST11 |  | B1 in progress, 20/33.5m
Fri (16/08) | 16 Aug 2024 | ST236 to ST237 | half | Guidewall rebar inspection ongoing
Fri (16/08) | 16 Aug 2024 | P15 |  | Column casting works in progress
Fri (16/08) | 16 Aug 2024 | P16 |  | Continue Backfilling to column stump level. NDT scheduled today
Fri (16/08) | 16 Aug 2024 | N4 |  | RWDP installation ongoing
Fri (16/08) | 16 Aug 2024 | N2 |  | Falsework installation in progress
Fri (16/08) | 16 Aug 2024 | P14 |  | Continue pile head cutting works
Fri (16/08) | 16 Aug 2024 | P11-1 |  | Soldier piles installation in progress. As of now, 7pcs installed
Fri (16/08) | 16 Aug 2024 | MH3-5 |  | Soft eye hacking and platform installation work
Fri (16/08) | 16 Aug 2024 | P9-1 |  | Continue pile cap rebar works
Fri (16/08) | 16 Aug 2024 | P4 |  | ERSS installation in progress
Fri (16/08) | 16 Aug 2024 | Gate 5 |  | WH excavation for pipe laying for overpumping at MH2-8
Fri (16/08) | 16 Aug 2024 | ST100 |  | Rebar cage lapping in progress
Fri (16/08) | 16 Aug 2024 | Exit 1 |  | Hacking and excavation ongoing for ECM pond extension
Fri (16/08) | 16 Aug 2024 | MH3-5 |  | Hacking ongoing. Works till 8pm
Fri (16/08) | 16 Aug 2024 | ST112 |  | B1 in progress, 25/39m
Fri (16/08) | 16 Aug 2024 | ST170 |  | Guidewall casting
Fri (16/08) | 16 Aug 2024 | P34 |  | RC stump 2/4nos cast
Fri (16/08) | 16 Aug 2024 | BRP39 |  | Coring ongoing
Fri (16/08) | 16 Aug 2024 | BRP31 |  | B2 completed. Cutter teeth changing ongoing & preparing for internal koden check before B3
Fri (16/08) | 16 Aug 2024 | BP4A-2 | 43 | Continue boring
Fri (16/08) | 16 Aug 2024 | TDP36 |  | Boring ongoing. HSL setting up localised noise balloon
Fri (16/08) | 16 Aug 2024 | ST225 |  | Continue trimming
Fri (16/08) | 16 Aug 2024 | ST18 |  | B1 completed
Fri (16/08) | 16 Aug 2024 | ST236-237 |  | Guidewall pending casting, ST238: Guidewall excavation done, pending lean con casting
Fri (16/08) | 16 Aug 2024 | Zone 1 |  | Outer lane closing for stage 1A pre-diversion
Fri (16/08) | 16 Aug 2024 | P23 |  | Excavating for singtel pipe
Fri (16/08) | 16 Aug 2024 | ST257 |  | B1 CD 29.4/38.0m
Fri (16/08) | 16 Aug 2024 | P29 |  | Geomotion preparation for RW26 drilling
Sat (17/08) | 17 Aug 2024 | STN-257 |  | 1st bite excavation ongoing, current depth 35m
Sat (17/08) | 17 Aug 2024 | STN-11 |  | No activity. Bentonite checked
Sat (17/08) | 17 Aug 2024 | STN-018 | BC03 | Resumed 2nd bite excavation. Current depth - 25.3m/36.50m
Sat (17/08) | 17 Aug 2024 | BP4A-2 | 43 | Boring temporarily stopped due Kelly bar issue
Sat (17/08) | 17 Aug 2024 | TDP36 |  | Boring competed. Now pending for toe depth confirmation
Sat (17/08) | 17 Aug 2024 | BRP-31 |  | Boring and Desanding completed. Now preparing for rebar cage lowering
Sat (17/08) | 17 Aug 2024 | BRP-42 |  | Preparation to start preboring
Sat (17/08) | 17 Aug 2024 | DR-1 |  | CGS excavation works in progress. To cut down 1m
Sat (17/08) | 17 Aug 2024 | PBH-109 |  | Coring works ongoing, current depth 18m
Sat (17/08) | 17 Aug 2024 | ST112 |  | 1st bite excavation completed. Now preparing the platform for 2nd bite excavation
Sat (17/08) | 17 Aug 2024 | STN-100 |  | Casting completed
Sat (17/08) | 17 Aug 2024 | Exit 1 |  | KTC Excavation for ECM extension
Sat (17/08) | 17 Aug 2024 | BP43-1 |  | Preboring for casing installation in progress
Sat (17/08) | 17 Aug 2024 | MH3-5 |  | TBM arrived on site. Today to lower TBM and target to start pipe jacking today
Sat (17/08) | 17 Aug 2024 | BP49-3 |  | Boring works in progress, current depth 25m
Sat (17/08) | 17 Aug 2024 | P16 |  | Backfilling completed. Compaction ongoing now
Sat (17/08) | 17 Aug 2024 | N4 |  | Crosshead rebar works to start today
Sat (17/08) | 17 Aug 2024 | P14 |  | Pile head hacking works
Sat (17/08) | 17 Aug 2024 | N2 |  | No activity
Sat (17/08) | 17 Aug 2024 | P11-1 |  | Continue ERSS installation
Sat (17/08) | 17 Aug 2024 | P9-1 |  | Pile cap rebar works ongoing
Sat (17/08) | 17 Aug 2024 | Zone 1 |  | Lane 1 M&P completed. Now Lane 2 M&P ongoing
Sat (17/08) | 17 Aug 2024 | STN-257 |  | 1st bite excavation ongoing, current depth 35.8m
Sat (17/08) | 17 Aug 2024 | STN-238 & STN-237 | 1.5m | Guidewall Formwork closing. Today to cast
Sat (17/08) | 17 Aug 2024 | STN-225 |  | Cutter teeth changing
Sat (17/08) | 17 Aug 2024 | STN-018 | BC03 | 2nd bite excavation stopped, cutter teeth changing ongoing. Current depth - 28.5m/36.50m
Sat (17/08) | 17 Aug 2024 | STN-015 |  | LSS backfill ongoing
Sat (17/08) | 17 Aug 2024 | Gate 5 |  | Excavation & installation for water pipe (stage 2)
Sat (17/08) | 17 Aug 2024 | STN-23 |  | Trial trench for Guidewall
Sat (17/08) | 17 Aug 2024 | BP4A-2 | 43 | Wire rope changing ongoing
Sat (17/08) | 17 Aug 2024 | TDP-36 |  | Casting completed
Sat (17/08) | 17 Aug 2024 | TDP-34 |  | Boring works commenced
Sat (17/08) | 17 Aug 2024 | BRP-31 |  | Rebar cage fully lowered. KP lowering ongoing
Sat (17/08) | 17 Aug 2024 | BRP-39 |  | 2nd bite excavation ongoing. Current depth 20m
Sat (17/08) | 17 Aug 2024 | BRP-43 |  | Preboring 1st bite ongoing, current depth 22.1m
Sat (17/08) | 17 Aug 2024 | P33-P34 |  | 2 nos. RC stump formwork closing. Today to cast
Sat (17/08) | 17 Aug 2024 | DR-1 |  | CGS excavation works completed. No more excavation by CGS till sewer pipe supports complete
Sat (17/08) | 17 Aug 2024 | DR-1 area |  | Singtel cable recovery works in progress
Sat (17/08) | 17 Aug 2024 | PBH-109 |  | Coring works ongoing, current depth 29m
Sat (17/08) | 17 Aug 2024 | P43-1 |  | Casing installed. Now preparing working platform for P44-1. Monday to start boring for casing installation
Sat (17/08) | 17 Aug 2024 | Exit 1 |  | Continue Excavation for ECM extension
Sat (17/08) | 17 Aug 2024 | MH3-5 |  | Welding works ongoing for pipe jacking preparation works
Sat (17/08) | 17 Aug 2024 | P49-3 |  | Boring completed and rebar cages lowered. Pending casting
Sat (17/08) | 17 Aug 2024 | Zone 1 |  | Traffic diversion completed for Loyang Ave to PRD3, Tonight 8pm to resume M&P for lane going towards NLL and bus only lane
Sat (17/08) | 17 Aug 2024 | P4 |  | Soldier piles installation completed. Steel plates installation ongoing
Sat (17/08) | 17 Aug 2024 | P5 |  | Hardcores removal and BP trial trench works in progress
Sat (17/08) | 17 Aug 2024 | MH5-2 |  | Vent pipe installation in progress
Sat (17/08) | 17 Aug 2024 | P9-1 |  | Shear links installation in progress
Sat (17/08) | 17 Aug 2024 | P11-1 |  | Continue soldier piles installation works
Sat (17/08) | 17 Aug 2024 | N2 Crosshead |  | Falseworks (Secondary beams) installation ongoing
Sat (17/08) | 17 Aug 2024 | P14 |  | Pile head hacking works
Sat (17/08) | 17 Aug 2024 | N4 Crosshead |  | Rebar installation works
Sat (17/08) | 17 Aug 2024 | P15 |  | Scaffold dismantle works ongoing
Sat (17/08) | 17 Aug 2024 | P16 |  | ERSS extraction in progress
Sat (17/08) | 17 Aug 2024 | Zone 2 |  | Ready for tonight's diversion. Balance minor lane marking
Sun (18/08) | 18 Aug 2024 | BRP31 |  | Casting in progress, 92/108m3
Sun (18/08) | 18 Aug 2024 | Zone 4 |  | Lean concrete at gas pipe laid area
Sun (18/08) | 18 Aug 2024 | ST112 |  | 2nd bite, reached 27.5m
Sun (18/08) | 18 Aug 2024 | Zone 4 |  | No activity of HSL boring work
Sun (18/08) | 18 Aug 2024 | BRP39 |  | 2nd bite reached 21.5m
Sun (18/08) | 18 Aug 2024 | DW44 |  | 1st bite, reached 23
Sun (18/08) | 18 Aug 2024 | STN18 |  | 2nd bite trenching in progress, depth at 30.5/36.5m
Sun (18/08) | 18 Aug 2024 | STN225 |  | Preparation for waterstop lowering and rebar cage installation
Sun (18/08) | 18 Aug 2024 | DW44 |  | Preparation to start trenching
Sun (18/08) | 18 Aug 2024 | BRP31 |  | 2nd KP lowering completed. Preparation for Tremie pipe installation for casting
Sun (18/08) | 18 Aug 2024 | BRP39 |  | Teeth replacement in progress. Current 2nd bite at 21.2/25.07m depth
Sun (18/08) | 18 Aug 2024 | STN112 |  | 2nd bite trenching at 8m
Sun (18/08) | 18 Aug 2024 | ST18 |  | 3rd bite, reached 25m
Sun (18/08) | 18 Aug 2024 | ST225 |  | Rebar cages lowered down. Level checking for casting
Sun (18/08) | 18 Aug 2024 | P14 |  | Continue pile head hacking
Sun (18/08) | 18 Aug 2024 | MH5-2 |  | Railing and vent pipe installation
Sun (18/08) | 18 Aug 2024 | STN257 |  | 2nd bite trenching resumed
Sun (18/08) | 18 Aug 2024 | ST112 |  | 2nd bite, reached 27m/39m
Sun (18/08) | 18 Aug 2024 | BRP42 |  | 1st bite, reached 31m
Sun (18/08) | 18 Aug 2024 | BC cutter 4 |  | Teeth changing
Sun (18/08) | 18 Aug 2024 | BC cutter 2 |  | Teeth changing
Sun (18/08) | 18 Aug 2024 | ST18 |  | 2nd bite completed. Now trimming of 2nd bite
Sun (18/08) | 18 Aug 2024 | ST225 |  | 2/3 cage in progress
Sun (18/08) | 18 Aug 2024 | N2 |  | Falsework erection
Sun (18/08) | 18 Aug 2024 | P14 |  | Bored pile hacking
Sun (18/08) | 18 Aug 2024 | P9 |  | Tomorrow plan to cast the footing
Sun (18/08) | 18 Aug 2024 | Zone 1 |  | No activity today. Minimum traffic. No more queuing of traffic
Sun (18/08) | 18 Aug 2024 | MH5-2 |  | Vent pipe and hand rail installation by LCH
Mon (19/08) | 19 Aug 2024 | P17 |  | Material shifting for ERSS TT
Mon (19/08) | 19 Aug 2024 | N6 |  | Abutment wall rebar works
Mon (19/08) | 19 Aug 2024 | P9 |  | Pile cap to cast today
Mon (19/08) | 19 Aug 2024 | P51 |  | Preparing for water pipe protection and painting work
Mon (19/08) | 19 Aug 2024 | P47-6 |  | Boring on going. Plan for casting today
Mon (19/08) | 19 Aug 2024 | P44-1 |  | Boring in progress
Mon (19/08) | 19 Aug 2024 | Gate 5 |  | Formwork installation for MH2-8 overpumping pipe
Mon (19/08) | 19 Aug 2024 | Blk 2 |  | RW27 drilling in progress
Mon (19/08) | 19 Aug 2024 | P31 |  | RG coring works ongoing for inclinometer installation
Mon (19/08) | 19 Aug 2024 | P16 |  | ERSS extraction works
Mon (19/08) | 19 Aug 2024 | N6 |  | Abutment wall rebar installation ongoing
Mon (19/08) | 19 Aug 2024 | Blk 4 |  | Seongha currently on site waiting for barricade/steel plates delivery
Mon (19/08) | 19 Aug 2024 | N2 |  | Working platform installation works ongoing
Mon (19/08) | 19 Aug 2024 | N4 |  | Crosshead rebar installation works
Mon (19/08) | 19 Aug 2024 | P14 |  | Continue pile head hacking works
Mon (19/08) | 19 Aug 2024 | P5 |  | Exposing 22KV and gas pipe to decom
Mon (19/08) | 19 Aug 2024 | P4 |  | SP and LP installation completed. Now driving 400mm from G.L
Mon (19/08) | 19 Aug 2024 | ST103 |  | Guidewall trial trench in progres
Mon (19/08) | 19 Aug 2024 | ST112 | BC1 | Trimming ongoing
Mon (19/08) | 19 Aug 2024 | BH58 |  | Coring in progress
Mon (19/08) | 19 Aug 2024 | ST257 |  | B2 CD 32.0/38.0m
Mon (19/08) | 19 Aug 2024 | Exit 1 |  | Lean con has been cast for slope for ECM pond extension
Mon (19/08) | 19 Aug 2024 | ST018 Rig 3 |  | Trimming in progress, CD 28/34.9m
Mon (19/08) | 19 Aug 2024 | DW044 Rig 2 |  | B2 completed 29.8/29.8m, B3 excavation just started
Mon (19/08) | 19 Aug 2024 | P11-1 |  | Current ERSS installation status. Vibro now at P16 doing ERSS extraction works
Mon (19/08) | 19 Aug 2024 | BRP042 BG01 |  | PB2 - Preboring CD 20.0/34.37m
Mon (19/08) | 19 Aug 2024 | MH5-2 |  | Plastering works in progress. Today to complete
Mon (19/08) | 19 Aug 2024 | P9-1 |  | Pile cap casting started
Mon (19/08) | 19 Aug 2024 | P12 |  | Column formwork dismantling
Mon (19/08) | 19 Aug 2024 | N3 |  | Area preparation for falsework platform slab. Tomorrow plan to cast
Mon (19/08) | 19 Aug 2024 | P17 |  | Premix hacking done. Tomorrow LE to start TT for ERSS
Mon (19/08) | 19 Aug 2024 | MH3-4 |  | TT on going. Found 3 services as of now. Telecom, 22KV & 66KV
Mon (19/08) | 19 Aug 2024 | MH3-5 |  | Cable connection. Today to start jacking
Mon (19/08) | 19 Aug 2024 | P44-1 |  | Boring on going. Tomorrow to cast
Mon (19/08) | 19 Aug 2024 | STN112 |  | Cutter wheel teeth replacement. Trimming at water stop side to continue
Mon (19/08) | 19 Aug 2024 | ST103 |  | Excavation for Guidewall construction. Tonight to install rebar and close formwork
Mon (19/08) | 19 Aug 2024 | ST170 |  | Closing panel formwork closing
Mon (19/08) | 19 Aug 2024 | BRP42 |  | Pre-boring stopped for the day
Mon (19/08) | 19 Aug 2024 | BRP39 |  | 2nd bite trenching at 24.9m. Hydraulic hose replacement
Mon (19/08) | 19 Aug 2024 | DW44 |  | Trenching completed. Preparation for end plate trimming
Mon (19/08) | 19 Aug 2024 | BP4A-2 | 43 | Internal Koden test. Current depth at 34.6/35.3m
Mon (19/08) | 19 Aug 2024 | TDP32 |  | Boring works completed. Toe confirmation by RTO
Mon (19/08) | 19 Aug 2024 | ST18 |  | Cleaning in progress
Tue (20/08) | 20 Aug 2024 | BH109 |  | Completed, 40.7m
Tue (20/08) | 20 Aug 2024 | DR1 |  | MPI test ongoing for joint welding of c-channel and angle bar
Tue (20/08) | 20 Aug 2024 | Blk 4 |  | Seongha steel plates mobilisation
Tue (20/08) | 20 Aug 2024 | P33-34 |  | Soil trimming by KTC ongoing
Tue (20/08) | 20 Aug 2024 | BRP42 |  | Preboring in progress
Tue (20/08) | 20 Aug 2024 | BRP39 |  | B3 in progress, 20.5/25.07m
Tue (20/08) | 20 Aug 2024 | ST202-203 |  | Clearing hardcore to facilitate guidewall trial trench
Tue (20/08) | 20 Aug 2024 | BRP31 |  | LSS backfill
Tue (20/08) | 20 Aug 2024 | DW44 |  | Trimming temporarily stopped for c-lug welding and cutter teeth change
Tue (20/08) | 20 Aug 2024 | TDP41 |  | Preparation ongoing for preboring works
Tue (20/08) | 20 Aug 2024 | BP4A-2 | 43 | Today plan for KP installation
Tue (20/08) | 20 Aug 2024 | TDP14 |  | Hacking ongoing for trial rial trench
Tue (20/08) | 20 Aug 2024 | TDP13 |  | Trial trench in progress, manual cleaning ongoing for found services
Tue (20/08) | 20 Aug 2024 | BC3 |  | BC cutter maintenance ongoing
Tue (20/08) | 20 Aug 2024 | ST252 |  | Guidewall built-up rebar works ongoing
Tue (20/08) | 20 Aug 2024 | P10 column |  | Preparation for casting
Tue (20/08) | 20 Aug 2024 | N2 |  | MJ formwork in progress
Tue (20/08) | 20 Aug 2024 | P14 |  | Pile head hacking done. Hardcore clearing in progress
Tue (20/08) | 20 Aug 2024 | N4 |  | Crosshead rebar works continue
Tue (20/08) | 20 Aug 2024 | P15 |  | Column dismantling
Tue (20/08) | 20 Aug 2024 | P16 |  | Area leveling for crane parking. Tomorrow to lift rebar cage
Tue (20/08) | 20 Aug 2024 | P17 |  | TT for ERSS
Tue (20/08) | 20 Aug 2024 | Gate 5 |  | Ley Choon continue water pipe laying
Tue (20/08) | 20 Aug 2024 | RW25 |  | Trial trench ongoing
Tue (20/08) | 20 Aug 2024 | MH5-2 |  | All physical works completed. Housekeeping ongoing
Tue (20/08) | 20 Aug 2024 | P34 |  | Preparing platform for Seongha to do post-lugeon test for remaining 8nos
Tue (20/08) | 20 Aug 2024 | DR1 |  | LE beams delivery
Tue (20/08) | 20 Aug 2024 | Exit 1 |  | Lean con casting for ECM pond extension
Tue (20/08) | 20 Aug 2024 | ST112 |  | Trimming ongoing
Tue (20/08) | 20 Aug 2024 | BH58 |  | Coring in progress
Tue (20/08) | 20 Aug 2024 | ST103 |  | Guidewall formwork installation ongoing
Tue (20/08) | 20 Aug 2024 | BRP42 |  | PB2 preboring ongoing
Tue (20/08) | 20 Aug 2024 | BRP39 |  | Cutter teeth change completed, now resume B3 excavation
Tue (20/08) | 20 Aug 2024 | P51 |  | Protection for water pipe for bored pile work
Tue (20/08) | 20 Aug 2024 | TDP41 |  | Casing installed
Tue (20/08) | 20 Aug 2024 | P48-4 |  | Boring almost completed. Tomorrow to cast
Tue (20/08) | 20 Aug 2024 | BP4A-2 | 43 | Rebar cage installed, setting up of 160T crane for king post & dolly installation
Tue (20/08) | 20 Aug 2024 | P44-1 |  | Casting in progress. P43-1 : boring on going
Tue (20/08) | 20 Aug 2024 | MH3-5 to MH7 |  | Pipe no 6 lowering down
Tue (20/08) | 20 Aug 2024 | MH3-4 |  | TT completed. Preparing for backfilling
Tue (20/08) | 20 Aug 2024 | Zone 3 |  | Seongha continue mobilisation of site container
Tue (20/08) | 20 Aug 2024 | Gate 5 |  | Backfilling ongoing at water pipe area
Tue (20/08) | 20 Aug 2024 | BP4A-2 | 43 | Dolly installation
Tue (20/08) | 20 Aug 2024 | BP4A-2 | 43 | Lowering of KP and dolly
Tue (20/08) | 20 Aug 2024 | P29 |  | Geomotion preparing for next RW drilling works. Today plan for RW22
Tue (20/08) | 20 Aug 2024 | P31 |  | RG continue drilling for inclinometer installation
Tue (20/08) | 20 Aug 2024 | ST103 |  | Guidewall rebar installation in progress. Today plan for casting
Tue (20/08) | 20 Aug 2024 | ST101 |  | Guidewall cast yesterday. Formwork dismantling ongoing
Tue (20/08) | 20 Aug 2024 | ST112 |  | Welding ongoing. Preparing for WS extraction
Wed (21/08) | 21 Aug 2024 | Zone 1 |  | Shrubs at center divider plan to remove today
Wed (21/08) | 21 Aug 2024 | P5 |  | 22Kv haunching hacking
Wed (21/08) | 21 Aug 2024 | Blk 4 |  | Seongha continue mobilisation & setup works
Wed (21/08) | 21 Aug 2024 | Blk 4 |  | Soil trimming and levelling
Wed (21/08) | 21 Aug 2024 | DR1 |  | Hacking of footing for sewer pipe
Wed (21/08) | 21 Aug 2024 | BRP42 |  | Preboring temporarily stopped. Diesel topup ongoing
Wed (21/08) | 21 Aug 2024 | P17 |  | Trial trench for preboring in progress
Wed (21/08) | 21 Aug 2024 | BRP39 |  | B3 completed
Wed (21/08) | 21 Aug 2024 | TDP41 |  | Boring in progress
Wed (21/08) | 21 Aug 2024 | DW44 |  | Trimming ongoing
Wed (21/08) | 21 Aug 2024 | P16 |  | Preparation for column rebar cage lifting. Briefing conducted
Wed (21/08) | 21 Aug 2024 | BP2B-2, 1.6m dia | 53 | Preboring and casing installed yesterday. Now ongoing boring works
Wed (21/08) | 21 Aug 2024 | ST22 |  | B1 temporarily stopped for cutter teeth changing and centre holder rectification. CD 17/38m
Wed (21/08) | 21 Aug 2024 | ST257 |  | B2 reached toe level, 38.2m. Target to cast this panel this week, ST11: Continue bentonite check while waiting for BC cutter
Wed (21/08) | 21 Aug 2024 | P9 |  | Stump rebar installation
Wed (21/08) | 21 Aug 2024 | P10 |  | Scaffold access dismantling
Wed (21/08) | 21 Aug 2024 | N4 crosshead |  | Setting out for tendon duct and RWDP installation
Wed (21/08) | 21 Aug 2024 | ST257 |  | B3 CD 37.0/38.0m
Wed (21/08) | 21 Aug 2024 | ST022 Rig 3 |  | B1 CD 26/38m
Wed (21/08) | 21 Aug 2024 | MH3-5 |  | Pipe No-12 jacking in progress. 11/70nos done
Wed (21/08) | 21 Aug 2024 | MH3-4 |  | Ryobi G TT for instrumentation
Wed (21/08) | 21 Aug 2024 | MH3-4 |  | Preparing for premix removal
Wed (21/08) | 21 Aug 2024 | P48-4 |  | Prepare for casting
Wed (21/08) | 21 Aug 2024 | P49-2 |  | Preparing for boring
Wed (21/08) | 21 Aug 2024 | Gate 5 |  | Valve installation for water pipe
Wed (21/08) | 21 Aug 2024 | TDP41 |  | Boring in progress
Wed (21/08) | 21 Aug 2024 | ST170 |  | Filling up trench with bentonite and preparation works ongoing
Wed (21/08) | 21 Aug 2024 | BRP42 |  | 2nos preboring completed. Now awaiting BC cutter before start trenching
Wed (21/08) | 21 Aug 2024 | BRP39 |  | Cleaning ongoing
Wed (21/08) | 21 Aug 2024 | TDP41 |  | 7m/17m
Wed (21/08) | 21 Aug 2024 | BP2B-2 | 53 | Boring in progress, 27/37.7m
Wed (21/08) | 21 Aug 2024 | ST22 |  | B1 in progress, 31/38m
Wed (21/08) | 21 Aug 2024 | P29 |  | Geomotion rig setup for next RW point
Wed (21/08) | 21 Aug 2024 | BH58 |  | Coring in progress, 31m
Wed (21/08) | 21 Aug 2024 | ST112 |  | WS endplate joint welding ongoing
Wed (21/08) | 21 Aug 2024 | Exit 1 ECM pond extension |  | Barricade installation ongoing
Thu (22/08) | 22 Aug 2024 | Blk 2 |  | RW25 drilling completed. Today will install RW
Thu (22/08) | 22 Aug 2024 | P31 |  | RG has completed inclinometer installation. Today plan to move rig to gate 7
Thu (22/08) | 22 Aug 2024 | Between P42-P43 |  | Cable spiking has been arranged for 2 points today, 22kV and 6.6kv
Thu (22/08) | 22 Aug 2024 | BH58 |  | Coring in progress, 42.5m
Thu (22/08) | 22 Aug 2024 | P45 |  | Prepare to install water pipe protection
Thu (22/08) | 22 Aug 2024 | P39-2 |  | Boring on going today to cast
Thu (22/08) | 22 Aug 2024 | P9 |  | Stump rebar inspection
Thu (22/08) | 22 Aug 2024 | Blk 4 |  | Setting up works ongoing
Thu (22/08) | 22 Aug 2024 | P5 |  | Excavation to W1 layer completed. Barricade and access installation in progress
Thu (22/08) | 22 Aug 2024 | Blk 2 |  | RW22 trial trench in progress
Thu (22/08) | 22 Aug 2024 | Zone 1 center divider |  | Top soil clearing for D3 kerb removal
Thu (22/08) | 22 Aug 2024 | Zone 1 |  | Preparation for earth drain hacking
Thu (22/08) | 22 Aug 2024 | P17 |  | LE boring rig shifted, preparation to start preboring for ERSS
Thu (22/08) | 22 Aug 2024 | P16 |  | Column rebar installation works
Thu (22/08) | 22 Aug 2024 | N6 |  | Rebar installation for N6 abutment wall
Thu (22/08) | 22 Aug 2024 | ST112 |  | Rebar cage installation
Thu (22/08) | 22 Aug 2024 | P11-1 |  | KTC excavation works to S1 layer
Thu (22/08) | 22 Aug 2024 | N2 |  | Current column Formwork status
Thu (22/08) | 22 Aug 2024 | N4 |  | Ducting & rebar installation works
Thu (22/08) | 22 Aug 2024 | P14 |  | Pile head trimming completed. Cleaning works ongoing
Thu (22/08) | 22 Aug 2024 | ST170 |  | Excavation temporarily stopped for cutter teeth change
Thu (22/08) | 22 Aug 2024 | BRP42 |  | B1 in progress, 27/34.8m
Thu (22/08) | 22 Aug 2024 | Blk 4 |  | Seongha mobilised their rig
Thu (22/08) | 22 Aug 2024 | BRP39 |  | Preparing for casting
Thu (22/08) | 22 Aug 2024 | DW44 |  | Final koden check ongoing
Thu (22/08) | 22 Aug 2024 | BP2B-2 | 53 | Boring in progress
Thu (22/08) | 22 Aug 2024 | ST22 |  | B1 completed. Now cutter body hoist up
Thu (22/08) | 22 Aug 2024 | ST11 |  | B1 in progess
Thu (22/08) | 22 Aug 2024 | ST241 |  | Guidewall excavation
Thu (22/08) | 22 Aug 2024 | ST257 |  | Preparing for casting
Thu (22/08) | 22 Aug 2024 | P49-2 |  | Casting in progress
Thu (22/08) | 22 Aug 2024 | P47-7 |  | Preparing for preboring
Thu (22/08) | 22 Aug 2024 | MH3-4 |  | Premix removal and exposing of services
Thu (22/08) | 22 Aug 2024 | P49-2 |  | Casting completed
Thu (22/08) | 22 Aug 2024 | MH3-5 |  | Pipe jacking for 18th pipe
Thu (22/08) | 22 Aug 2024 | ST112 |  | Rebar cage installation. 3/8 cages installed
Thu (22/08) | 22 Aug 2024 | ST170-BC1 |  | 1st bite trenching at 23.5m/41.5m
Thu (22/08) | 22 Aug 2024 | BRP42-BC4 |  | 1st bite trenching at 29m. Now teeth replacement
Thu (22/08) | 22 Aug 2024 | BRP39 |  | Casting in progress. Balance 1 lorry. Total volume 45 m3
Thu (22/08) | 22 Aug 2024 | ST194-BC2 |  | Mud hose connection prior to trenching
Thu (22/08) | 22 Aug 2024 | TDP41 |  | Casting in progress. Last truck, total volume 14 m3
Thu (22/08) | 22 Aug 2024 | BP2B-2 | 53 | Boring works in progress, depth 36m
Thu (22/08) | 22 Aug 2024 | ST22-BC3 |  | 2nd bite trenching at 4m
Thu (22/08) | 22 Aug 2024 | STN231-232 |  | Guidewall formwork closing. To cast tonight
Thu (22/08) | 22 Aug 2024 | STN11 |  | Excavation done. Tonight to extract end plate
Thu (22/08) | 22 Aug 2024 | STN257 |  | Casting started. Estimated volume 220 m3
Thu (22/08) | 22 Aug 2024 | STN002 |  | Excavation using grabber done. Tonight to shift Hydrofraise here
Fri (23/08) | 23 Aug 2024 | Zone 1 center divider |  | Change of plan, now CGS will not proceed with TT. They will cast the area instead for access
Fri (23/08) | 23 Aug 2024 | Zone 1 |  | Hacking for earth drain construction
Fri (23/08) | 23 Aug 2024 | P4 |  | Waler bracket installation
Fri (23/08) | 23 Aug 2024 | P47-7 |  | Boring on going. Target to cast today
Fri (23/08) | 23 Aug 2024 | P9 |  | Stump scaffold erection for casting
Fri (23/08) | 23 Aug 2024 | MH3-4 |  | 1st layer excavation
Fri (23/08) | 23 Aug 2024 | P43-2 |  | Boring on going. Today to cast
Fri (23/08) | 23 Aug 2024 | Blk 2 |  | RW22 today to install pipe
Fri (23/08) | 23 Aug 2024 | P31 |  | Trial trench ongoing at utility support area
Fri (23/08) | 23 Aug 2024 | N4 |  | Main bar need to adjust to align tendon ducts
Fri (23/08) | 23 Aug 2024 | ST112 |  | Casting in progress
Fri (23/08) | 23 Aug 2024 | ST170 |  | B1 in progress, 37.3/41.3m
Fri (23/08) | 23 Aug 2024 | DR1 |  | Angle bracket fabrication ongoing
Fri (23/08) | 23 Aug 2024 | BRP40 |  | Guidewall casting
Fri (23/08) | 23 Aug 2024 | Blk 4 |  | Seongha continue setup works
Fri (23/08) | 23 Aug 2024 | ST194 | BC2 | B1 temporarily stopped. Rectification ongoing
Fri (23/08) | 23 Aug 2024 | P43-2 |  | Boring in progress
Fri (23/08) | 23 Aug 2024 | P47-7 |  | Boring done. Preparing for rebar cage lowering down
Fri (23/08) | 23 Aug 2024 | Zone 1 p4 |  | Waler bracket welding
Fri (23/08) | 23 Aug 2024 | P2 |  | Premix hacking for TT started
Fri (23/08) | 23 Aug 2024 | BRP42 |  | Excavation temporarily stopped due to hydraulic hose leakage. Rectification ongoing
Fri (23/08) | 23 Aug 2024 | P47-7 |  | Casting
Fri (23/08) | 23 Aug 2024 | ST112 |  | Casting completed. Total volume 221m3
Fri (23/08) | 23 Aug 2024 | ST170-BC1 |  | 1st bite trenching completed. Preparation for 2nd bite trenching
Fri (23/08) | 23 Aug 2024 | BRP42-BC4 |  | 2nd bite trenching at 5m
Fri (23/08) | 23 Aug 2024 | BRP39 |  | LSS backfilling in progress
Fri (23/08) | 23 Aug 2024 | ST194-BC2 |  | 1st bite trenching at 26m
Fri (23/08) | 23 Aug 2024 | BP2B-2 | 53 | Boring works in progress, depth 37.1m. Balance 600mm
Fri (23/08) | 23 Aug 2024 | TDP18 |  | Casing installed. Boring dept 13. Tomorrow to continue
Fri (23/08) | 23 Aug 2024 | ST22-BC3 |  | 2nd bite trenching at 34.2m
Fri (23/08) | 23 Aug 2024 | STN11 |  | Rebar cage installation
Fri (23/08) | 23 Aug 2024 | STN002 |  | Chiselling in progress
Sat (24/08) | 24 Aug 2024 | P4 |  | Currently no activity
Sat (24/08) | 24 Aug 2024 | P2 |  | Hardcore removal for trial trench works
Sat (24/08) | 24 Aug 2024 | Zone 2 |  | Cleaning ongoing at rest area
Sat (24/08) | 24 Aug 2024 | MH3-4 |  | Current status
Sat (24/08) | 24 Aug 2024 | BRP42 |  | 2nd bite, reached 24.1m
Sat (24/08) | 24 Aug 2024 | ST002 |  | B2 in progress
Sat (24/08) | 24 Aug 2024 | ST236 |  | B1 reached 25/34.8m
Sat (24/08) | 24 Aug 2024 | ST241 |  | Guidewall rebar works ongoing
Sat (24/08) | 24 Aug 2024 | ST194 |  | 3rd bite, reached 4m
Sat (24/08) | 24 Aug 2024 | ST22 |  | WS trimming temporarily stopped. Machine rectification ongoing
Sat (24/08) | 24 Aug 2024 | TDP18 |  | Boring in progress. Plan for casting today
Sat (24/08) | 24 Aug 2024 | BP2B-2 | 53 | Rebar cage installation ongoing. Today plan for KP installation and casting
Sat (24/08) | 24 Aug 2024 | UKP7 |  | Hacking ongoing for trial trench works
Sat (24/08) | 24 Aug 2024 | Gate 5 |  | WH trial trench ongoing for water pipe laying continuation (stage 2)
Sat (24/08) | 24 Aug 2024 | Blk 4 |  | Seongha started post-lugeon test. Today plan 2 points
Sat (24/08) | 24 Aug 2024 | MH3-4 |  | Currently no activity
Sat (24/08) | 24 Aug 2024 | MH3-5 |  | Pipe 24 lowered and preparing for joinin
Sat (24/08) | 24 Aug 2024 | P49-1 |  | Preboring
Sat (24/08) | 24 Aug 2024 | P45 |  | Exposing pipes
Sat (24/08) | 24 Aug 2024 | ST170 |  | B2 in progress, 25/41.3m
Sat (24/08) | 24 Aug 2024 | BRP42 |  | B2 temporarily stopped. Desander pump leaking, preparing for rectification
Sat (24/08) | 24 Aug 2024 | ST194 |  | B2 in progress, 21/32.16m
Sat (24/08) | 24 Aug 2024 | Zone 1 |  | Centre divider cast
Sat (24/08) | 24 Aug 2024 | N4 |  | Adjustment ongoing
Sat (24/08) | 24 Aug 2024 | N2 |  | Hacking ongoing
Sat (24/08) | 24 Aug 2024 | P11 |  | Waler installation
Sat (24/08) | 24 Aug 2024 | P9 |  | Stump casting
Sat (24/08) | 24 Aug 2024 | ST22 |  | WS trimming ongoing
Sat (24/08) | 24 Aug 2024 | BP2B-2 | 53 | KP safely rested on guide beams
Sat (24/08) | 24 Aug 2024 | RW23 |  | Trial trench in progress
Sat (24/08) | 24 Aug 2024 | PBH78 |  | Coring in progress, 24.5m
Sat (24/08) | 24 Aug 2024 | ST170 |  | B2 temporarily stopped. Cutter teeth changing ongoing
Sat (24/08) | 24 Aug 2024 | BRP42 |  | B2 in progress, 21.9/34.37m
Sat (24/08) | 24 Aug 2024 | ST194 |  | Cutter teeth changing
Sat (24/08) | 24 Aug 2024 | Gate 5 |  | Ley choon preparing to start premix removal for water pipe laying
Sat (24/08) | 24 Aug 2024 | ST22 |  | Cleaning and desanding in progress
Sat (24/08) | 24 Aug 2024 | BP2B-2-53 |  | Casting completed
Sat (24/08) | 24 Aug 2024 | ST236 |  | 2nd bite, reached 19m
Sat (24/08) | 24 Aug 2024 | ST002 |  | 2nd bite, reached 28.8m
Sat (24/08) | 24 Aug 2024 | P16 |  | Rain water drain pipe installation
Sat (24/08) | 24 Aug 2024 | N4 |  | Sealing of formwork holes
Sat (24/08) | 24 Aug 2024 | P14 |  | No activity already
Sat (24/08) | 24 Aug 2024 | MH3-5 |  | Pipe No-28 jacking in progress. Tonight they will work until 11PM
Sat (24/08) | 24 Aug 2024 | P14 |  | Pile cap rebar works ongoing
Sat (24/08) | 24 Aug 2024 | P11 |  | Angle bracket welding ongoing
Sat (24/08) | 24 Aug 2024 | P9 |  | Scaffold platform erection ongoing
Sat (24/08) | 24 Aug 2024 | Zone 1 |  | Clearing 22kV cables
Sat (24/08) | 24 Aug 2024 | Zone 1 centre divider |  | Today plan for casting
Sun (25/08) | 25 Aug 2024 | P11 |  | Waler beam welding works in progress
Sun (25/08) | 25 Aug 2024 | P4 |  | Diagonal bracing installation
Sun (25/08) | 25 Aug 2024 | Zone 4 |  | Manual excavation to expose traffic light cables
Sun (25/08) | 25 Aug 2024 | MH3-5 |  | Pipes jacking for 29th pipe in progress
Sun (25/08) | 25 Aug 2024 | ST170-BC1 |  | 2nd bite trenching completed, 41.6m. Cutter body up for teeth and start 3rd bite
Sun (25/08) | 25 Aug 2024 | BRP44 |  | TT and guidewall excavation
Sun (25/08) | 25 Aug 2024 | BRP40 |  | Preparation for pre-boring works
Sun (25/08) | 25 Aug 2024 | JTC blk 2 |  | Seongha platform preparation for post lugeon test
Sun (25/08) | 25 Aug 2024 | ST22 |  | End plate lowering
Sun (25/08) | 25 Aug 2024 | P9 |  | 1st layer concrete plug casting
Sun (25/08) | 25 Aug 2024 | ST22 |  | Desanding in progress
Sun (25/08) | 25 Aug 2024 | ST236 |  | 2nd bite, reached 20m
Sun (25/08) | 25 Aug 2024 | ST002 |  | 2nd bite, reached 28.9m
Sun (25/08) | 25 Aug 2024 | BRP42 |  | 2nd bite, reached 24.7m
Sun (25/08) | 25 Aug 2024 | ST170-BC1 |  | 3rd bite trenching in progress, 30m depth
Sun (25/08) | 25 Aug 2024 | BRP44 |  | TT and guidewall excavation, completed. Levelling for installation of rebar
Sun (25/08) | 25 Aug 2024 | ST22 |  | Preparation for rebar cage lowering, 6 cages
Sun (25/08) | 25 Aug 2024 | ST14A-BC3 |  | Trenching started. Single bite
Sun (25/08) | 25 Aug 2024 | ST194-BC2 |  | End plate trimming
Sun (25/08) | 25 Aug 2024 | ST194 |  | 3rd bite excavation done. Waterstop end plate trimming in progress
Sun (25/08) | 25 Aug 2024 | ST22 |  | Platform set up for waterstop end plate lowering
Sun (25/08) | 25 Aug 2024 | N4 crosshead |  | Formwork closing done yesterday. Waiting for COS. Plan to cast tomorrow
Sun (25/08) | 25 Aug 2024 | P14 pile cap |  | Shearlinks and formwork closing. Plan also to cast tomorrow
Mon (26/08) | 26 Aug 2024 | P49-1 |  | Rebar cage lowered down. Today to cast
Mon (26/08) | 26 Aug 2024 | P47-8 |  | Preboring started
Mon (26/08) | 26 Aug 2024 | P45 |  | Backfilling at traffic light shifting area
Mon (26/08) | 26 Aug 2024 | MH3-4 |  | Formwork closing for 1st layer. Today to cast
Mon (26/08) | 26 Aug 2024 | P43-3 |  | Boring in progress
Mon (26/08) | 26 Aug 2024 | P11 |  | Diagonal bracing installation. Highlighted to improve cable management
Mon (26/08) | 26 Aug 2024 | Zone 2 |  | TT in progress for additional ECM
Mon (26/08) | 26 Aug 2024 | ST236 |  | Both bite reached rock level & waiting for BC Cutter from ST002
Mon (26/08) | 26 Aug 2024 | BP2-2 | 30 | Casing installed & inspected, preparing to start boring
Mon (26/08) | 26 Aug 2024 | BRP40 BG01 |  | Preboring CD @ 8m
Mon (26/08) | 26 Aug 2024 | P49-1 |  | Casting in progress
Mon (26/08) | 26 Aug 2024 | MH3-4 |  | Casting started
Mon (26/08) | 26 Aug 2024 | ST170 |  | Waterstop end plate side trimming
Mon (26/08) | 26 Aug 2024 | BRP42 |  | 2nd bite, reached 27m
Mon (26/08) | 26 Aug 2024 | BRP40 |  | 1st point preboring, reached 16.6m
Mon (26/08) | 26 Aug 2024 | P32 |  | KTC TT to identify services before excavation for roof slab
Mon (26/08) | 26 Aug 2024 | ST194 |  | Cleaning and desanding
Mon (26/08) | 26 Aug 2024 | P4 |  | Fitting done. Now welders at P11
Mon (26/08) | 26 Aug 2024 | TDP18 |  | Concrete ordered for casting
Mon (26/08) | 26 Aug 2024 | P17 |  | Preboring for ERSS work
Mon (26/08) | 26 Aug 2024 | P16 |  | Current status of column
Mon (26/08) | 26 Aug 2024 | P11 |  | Diagonal bracing welding
Mon (26/08) | 26 Aug 2024 | P10 |  | Preparing for column formwork removal
Mon (26/08) | 26 Aug 2024 | Zone 2 |  | TT for ECM pond construction
Mon (26/08) | 26 Aug 2024 | Zone 1 |  | No activity
Mon (26/08) | 26 Aug 2024 | P14 |  | Concrete on site for casting
Mon (26/08) | 26 Aug 2024 | BP-2-2 | 30 | Boring on going, reached 20m depth
Mon (26/08) | 26 Aug 2024 | ST18 |  | LSS backfilling
Mon (26/08) | 26 Aug 2024 | ST22 |  | Cleaning of trench
Mon (26/08) | 26 Aug 2024 | P47-8 |  | Boring in progress
Tue (27/08) | 27 Aug 2024 | P9 |  | Backfilling
Tue (27/08) | 27 Aug 2024 | P4 |  | Packing concrete cast yesterday. Railing installation in progress, Afternoon to continue welding works
Tue (27/08) | 27 Aug 2024 | MH3-4 |  | Ryobi G started boring for instrumentation
Tue (27/08) | 27 Aug 2024 | MH3-4 |  | First layer (1.2m) cast. Preparing to expose services for next layer
Tue (27/08) | 27 Aug 2024 | P43-3 |  | Boring done. Preparing for casting
Tue (27/08) | 27 Aug 2024 | Blk 4 |  | Post-lugeon test ongoing for CH-14
Tue (27/08) | 27 Aug 2024 | ST170 | BC1 | Trimming temporarily stopped. Cutter teeth changing onging
Tue (27/08) | 27 Aug 2024 | DR1 |  | LE preparing for waler installation
Tue (27/08) | 27 Aug 2024 | P34 |  | KTC soil trimming ongoing
Tue (27/08) | 27 Aug 2024 | BRP42 |  | B2 temporarily stopped. Suction line rectification ongoin
Tue (27/08) | 27 Aug 2024 | BRP40 |  | Preboring
Tue (27/08) | 27 Aug 2024 | BC2 |  | Currently no activity
Tue (27/08) | 27 Aug 2024 | P41 area |  | Preparing area for ST105 trial trench
Tue (27/08) | 27 Aug 2024 | ST194 |  | Now preparing for G15 concrete backfill due to soil erosion
Tue (27/08) | 27 Aug 2024 | ST22 |  | KP and hanging bar installation ongoing
Tue (27/08) | 27 Aug 2024 | P47-8 |  | Boring done. Confirming the depth. Today to cast
Tue (27/08) | 27 Aug 2024 | ST14A | BC3 | Endplate loosening ongoing
Tue (27/08) | 27 Aug 2024 | BP2-2, 2.5m dia | 30 | Boring in progress
Tue (27/08) | 27 Aug 2024 | ST002 |  | B2 resumed from 34.3/34.8m
Tue (27/08) | 27 Aug 2024 | ST248-247 |  | Preparation for guidewall works
Tue (27/08) | 27 Aug 2024 | ST251 |  | B1 just started today
Tue (27/08) | 27 Aug 2024 | MH3-4 |  | Exposing services for next layer caisson
Tue (27/08) | 27 Aug 2024 | P43-3 |  | Casting in progress
Tue (27/08) | 27 Aug 2024 | MH2-10 |  | RG trial trench for instrument installation & LCH area preparation works
Tue (27/08) | 27 Aug 2024 | RW21 |  | Rig parked at location. Preparation for drilling works ongoing
Tue (27/08) | 27 Aug 2024 | P34 |  | KTC excavation ongoing
Tue (27/08) | 27 Aug 2024 | Blk 4 |  | Seongha post-lugeon test for point CH-13
Tue (27/08) | 27 Aug 2024 | Along DR2 |  | WH started excavating for ECM drain
Tue (27/08) | 27 Aug 2024 | ST101 | BC2 | B1 just started, CD 7/34m
Tue (27/08) | 27 Aug 2024 | ST105 |  | Hardcore removal for guidewall trial trench
Tue (27/08) | 27 Aug 2024 | P11 |  | To complete welding today. Plan also for packing concrete casting. Tomorrow MPI
Tue (27/08) | 27 Aug 2024 | P9 |  | Backfilling works
Tue (27/08) | 27 Aug 2024 | ST170 |  | Trimming ongoing
Tue (27/08) | 27 Aug 2024 | P50 changi bound |  | Rig shifted for preboring
Tue (27/08) | 27 Aug 2024 | P47-8 |  | Rebar cage lowered down. Prepare for casting
Tue (27/08) | 27 Aug 2024 | P17 |  | ERSS preboring ongoing
Tue (27/08) | 27 Aug 2024 | N6 |  | Abutment wall rebar works in progress
Tue (27/08) | 27 Aug 2024 | P14 |  | Strut welding and access rectification ongoing
Tue (27/08) | 27 Aug 2024 | N4 |  | Crosshead casting in progress. 3rd truck just arrived, 28/46m3
Tue (27/08) | 27 Aug 2024 | P9 |  | Rebar cage fabrication ongoing
Tue (27/08) | 27 Aug 2024 | ST248-247 |  | Guidewall formwork installation
Tue (27/08) | 27 Aug 2024 | ST251 |  | B1 reached 8/37.3m
Tue (27/08) | 27 Aug 2024 | ST002 |  | Excavation completed. Now preparing for WS removal
Tue (27/08) | 27 Aug 2024 | ST14A |  | Endplate extraction in progress
Tue (27/08) | 27 Aug 2024 | BP2-2 | 30 | Boring in progress, 28/36.967m
Tue (27/08) | 27 Aug 2024 | ST22 |  | Tremie pipes installed. Awaiting to cast
Tue (27/08) | 27 Aug 2024 | TDP17 |  | Toe level has been confirmed, 24.7m
Tue (27/08) | 27 Aug 2024 | BRP42 |  | B2 in progress
Tue (27/08) | 27 Aug 2024 | BRP40 |  | Preboring
Tue (27/08) | 27 Aug 2024 | ST170 |  | WS trimming ongoing
Tue (27/08) | 27 Aug 2024 | ST22 |  | First truck on site
Tue (27/08) | 27 Aug 2024 | Blk 2 |  | Hand auger ongoing for RW21
Wed (28/08) | 28 Aug 2024 | P50-1 |  | Boring in progress
Wed (28/08) | 28 Aug 2024 | P45 |  | Preparing for water pipe protection
Wed (28/08) | 28 Aug 2024 | Zone 1 junction |  | Manual hacking to expose traffic light cable
Wed (28/08) | 28 Aug 2024 | MH2-10 |  | Manual trial trench by LCH and RG
Wed (28/08) | 28 Aug 2024 | ST002 |  | Desanding in progress
Wed (28/08) | 28 Aug 2024 | STN251 |  | B1 CD 28/37.3m, B2 ongoing 4/37.3m
Wed (28/08) | 28 Aug 2024 | Blk 4 |  | KTC slope trimming at utility support area
Wed (28/08) | 28 Aug 2024 | ST236 |  | B1 CD 34/34.8m, B2 ongoing 32/34.8m
Wed (28/08) | 28 Aug 2024 | BP2-2 | 30 | Boring CD 30.0/36.967m
Wed (28/08) | 28 Aug 2024 | ST105, 106, 107 | half | Guidewall trial trench
Wed (28/08) | 28 Aug 2024 | BH59 |  | In progress, 31m
Wed (28/08) | 28 Aug 2024 | ST101 | BC2 | Excavation temporarily stopped. Gearbox changing ongoing
Wed (28/08) | 28 Aug 2024 | TDP17 |  | Casting in progress
Wed (28/08) | 28 Aug 2024 | TDP22 |  | Trial trench found HT cable
Wed (28/08) | 28 Aug 2024 | BRP40 Rig 4 |  | B2 CD 15/25.07m
Wed (28/08) | 28 Aug 2024 | BRP42 BG01 |  | P2 preboring CD 28.8/34.37m
Wed (28/08) | 28 Aug 2024 | ST170 |  | Preparing to extract endplate
Wed (28/08) | 28 Aug 2024 | DR1 |  | Seongha preparing area for fissure grouting works
Wed (28/08) | 28 Aug 2024 | P40 area |  | Hacking ongoing for drainage works
Wed (28/08) | 28 Aug 2024 | P9 |  | Backfilling to pile cap level continue
Wed (28/08) | 28 Aug 2024 | P40 area |  | Continue excavation for internal drainage works
Wed (28/08) | 28 Aug 2024 | P44 |  | Wee Guan shoring installation to facilitate army cable shifting
Wed (28/08) | 28 Aug 2024 | MH3-4 |  | No activity
Wed (28/08) | 28 Aug 2024 | MH3-5 |  | Preparing to join pipe no.51
Wed (28/08) | 28 Aug 2024 | ST101 | BC2 | BC machine rectification still ongoing
Wed (28/08) | 28 Aug 2024 | ST170 |  | Cleaning ongoing
Wed (28/08) | 28 Aug 2024 | BRP42 |  | Continue preboring
Wed (28/08) | 28 Aug 2024 | BRP40 |  | Excavation temporarily stopped. B2 CD 16.7/25.07m. Encountered hard rock, preboring will be done here. BC4 now at BRP57
Wed (28/08) | 28 Aug 2024 | BRP11 | BC3 | B1 started today. Current depth 6.6/38.57m. Now machine rectification ongoing
Wed (28/08) | 28 Aug 2024 | TDP17 |  | Deckpost installed
Wed (28/08) | 28 Aug 2024 | BP2-2 | 30 | Boring in progress, 32/36.967m
Wed (28/08) | 28 Aug 2024 | ST14A |  | Hanging bar installation in progress
Wed (28/08) | 28 Aug 2024 | P16 |  | Tie rod installation in progress
Wed (28/08) | 28 Aug 2024 | P17 |  | Preboring for steel plate installation in progress
Wed (28/08) | 28 Aug 2024 | MH3-4 |  | Tidy up site access and preparing for 2nd layer caisson
Wed (28/08) | 28 Aug 2024 | P9-1 |  | Rebar cage fabrication
Wed (28/08) | 28 Aug 2024 | P11 |  | Welding works for waler beams. Today to complete
Wed (28/08) | 28 Aug 2024 | P14 |  | Trimming works for column stump rebar installation
Thu (29/08) | 29 Aug 2024 | BH59 |  | Packer test ongoing
Thu (29/08) | 29 Aug 2024 | ST111 | BC1 | Preparing for cutter teeth change. Excavation just started earlier this morning
Thu (29/08) | 29 Aug 2024 | ST236 |  | Excavation has completed, waiting for machinery to do desanding after casting of ST002
Thu (29/08) | 29 Aug 2024 | BP2-2 | 30 | Boring CD 33.036.967m
Thu (29/08) | 29 Aug 2024 | UKP07 |  | Casing installation
Thu (29/08) | 29 Aug 2024 | Pipe No-52 |  | Pipe jacking in progress. With current rate target to complete this week
Thu (29/08) | 29 Aug 2024 | ST101 | BC2 | B2 in progress, 6/34m
Thu (29/08) | 29 Aug 2024 | BRP11 Rig 3 |  | B1 CD 29/38.57m
Thu (29/08) | 29 Aug 2024 | BRP42 BG01 |  | P2 preboring CD 31.0/34.37m
Thu (29/08) | 29 Aug 2024 | BRP57 |  | B1 in progress, 15.8/35.27m
Thu (29/08) | 29 Aug 2024 | ST170 |  | Rebar cage lowering in progress
Thu (29/08) | 29 Aug 2024 | Zone 1 junction |  | Manual hacking to find traffic light cable alignment
Thu (29/08) | 29 Aug 2024 | P45-P46 |  | GCE started 1st point for SPT
Thu (29/08) | 29 Aug 2024 | P45 |  | Woh hup exposing of water pipe for bitument application
Thu (29/08) | 29 Aug 2024 | P5 |  | Waler beam welding works
Thu (29/08) | 29 Aug 2024 | P3 |  | Excavation for PDA
Thu (29/08) | 29 Aug 2024 | P51-1 |  | Preparing to resume excavation. Tomorrow to cast
Thu (29/08) | 29 Aug 2024 | Zone 1 junction |  | Manual hacking to find traffic light cable continue
Thu (29/08) | 29 Aug 2024 | MH2-10 |  | LCH continue pavement hacking for trial trench works
Thu (29/08) | 29 Aug 2024 | P32 |  | Sensor installation for water standpipe by RG
Thu (29/08) | 29 Aug 2024 | P32 |  | KTC soil levelling
Thu (29/08) | 29 Aug 2024 | ST170 |  | Rebar cage extraction due to soil collapse
Thu (29/08) | 29 Aug 2024 | Blk 4 |  | WH erecting new walkway access
Thu (29/08) | 29 Aug 2024 | BH59 |  | Coring in progress, 36m
Thu (29/08) | 29 Aug 2024 | ST111 | BC1 | Mud pump rectification ongoing
Thu (29/08) | 29 Aug 2024 | ST101 |  | B2 in progress, 23/34m
Thu (29/08) | 29 Aug 2024 | BRP57 |  | Excavation temporarily stopped for rectification
Thu (29/08) | 29 Aug 2024 | ST170 |  | Now preparing for koden check
Thu (29/08) | 29 Aug 2024 | Zone 3 | south side | Platform preparation for fissure grouting works
Thu (29/08) | 29 Aug 2024 | BRP42 |  | Preboring continue
Thu (29/08) | 29 Aug 2024 | BRP11 |  | B1 in progress, 34/38.57m
Thu (29/08) | 29 Aug 2024 | DR1 |  | U-clamp installation ongoing for sewer pipe
Thu (29/08) | 29 Aug 2024 | UKP7 |  | Toe level checked, 16.35/16m
Thu (29/08) | 29 Aug 2024 | ST224A |  | Guidewall casting done
Thu (29/08) | 29 Aug 2024 | BP2-2 | 30 | Boring reached 34.5/36.967m
Thu (29/08) | 29 Aug 2024 | BP2-2 | 28 | Trial trench in progress
Thu (29/08) | 29 Aug 2024 | ST002 |  | Casting completed
Thu (29/08) | 29 Aug 2024 | ST251 |  | B1 in progress
Thu (29/08) | 29 Aug 2024 | ST236 |  | WS installation ongoing
Thu (29/08) | 29 Aug 2024 | ST246 |  | Guidewall rebar works, ST243: Guidewall excavation
Thu (29/08) | 29 Aug 2024 | ST260 |  | Excavation started
Thu (29/08) | 29 Aug 2024 | STN251 |  | 2nd bite trenching at at 25m. Now teeth replacement and operator change shift
Thu (29/08) | 29 Aug 2024 | STN260 |  | Pre-excavation in progress
Thu (29/08) | 29 Aug 2024 | STN236 |  | End plate+waterstop lowering
Thu (29/08) | 29 Aug 2024 | BP2-2 | 30 | Boring works at 35m
Thu (29/08) | 29 Aug 2024 | BP2-2 | 28 | TT in progress. Found abandoned 22KV and gas pipe
Thu (29/08) | 29 Aug 2024 | BRP11 |  | Trenching completed. Depth 38.6m
Thu (29/08) | 29 Aug 2024 | BRP42 |  | Pre-boring until 730pm
Thu (29/08) | 29 Aug 2024 | ST170 |  | Cleaning in progress
Thu (29/08) | 29 Aug 2024 | BRP57 |  | Cutter body up for teeth replacement
Thu (29/08) | 29 Aug 2024 | ST101 |  | Status 2nd bite trenching. Teeth replacement
Thu (29/08) | 29 Aug 2024 | Zone 4 |  | HSL stopped work for the day
Thu (29/08) | 29 Aug 2024 | MH3-5 |  | Pipe jacking until 11pm
Thu (29/08) | 29 Aug 2024 | ST002 |  | Casting in progress
Thu (29/08) | 29 Aug 2024 | STN251 |  | B1 ongoing 31/37.5m, B2 CD 9/37.3m
Fri (30/08) | 30 Aug 2024 | MH3-4 |  | Preparing for next layer excavation. 2nd layer plan to cast tomorrow
Fri (30/08) | 30 Aug 2024 | P51-1 |  | Continue boring to toe
Fri (30/08) | 30 Aug 2024 | P46-47 |  | Wee gaun check area for AC cable shifting
Fri (30/08) | 30 Aug 2024 | P45 |  | Water pipe protection done
Fri (30/08) | 30 Aug 2024 | Along blk 2 |  | Geomotion preparing flow meter for recharge wells amd RW19 in progress
Fri (30/08) | 30 Aug 2024 | P34 |  | RG trial trench for inclinometer and water standpipe
Fri (30/08) | 30 Aug 2024 | Blk 4 |  | Extension of ECM sump ongoing
Fri (30/08) | 30 Aug 2024 | ST111 | BC2 | B1 in progress
Fri (30/08) | 30 Aug 2024 | ST105-107 |  | Guidewall construction ongoing
Fri (30/08) | 30 Aug 2024 | BRP57 |  | Excavation temporarily stopped for cutter teeth change. CD 27.3/35.27m
Fri (30/08) | 30 Aug 2024 | ST170 |  | Cleaning ongoing
Fri (30/08) | 30 Aug 2024 | DR1 |  | Seongha has shifted their rig from blk 4 to South side
Fri (30/08) | 30 Aug 2024 | P51-1 |  | Boring reached 24m. Need to continue 4m more to reach toe. Casting will be tomorrow
Fri (30/08) | 30 Aug 2024 | BRP42 |  | Continue preboring
Fri (30/08) | 30 Aug 2024 | P32 utility support area |  | Trial trench ongoing by KTC
Fri (30/08) | 30 Aug 2024 | ST194 |  | Guidewall hacking
Fri (30/08) | 30 Aug 2024 | UKP18 |  | Casing installed
Fri (30/08) | 30 Aug 2024 | BRP11 |  | Desanding completed. Preparing for final koden check
Fri (30/08) | 30 Aug 2024 | BP2-2 | 30 | Toe level has been confirmed, 37.05m
Fri (30/08) | 30 Aug 2024 | BP2-2 | 28 | Trial trench in progress
Fri (30/08) | 30 Aug 2024 | ST14A |  | LSS backfill
Fri (30/08) | 30 Aug 2024 | ST236 |  | Tremie pipes lowering ongoing
Fri (30/08) | 30 Aug 2024 | ST260 |  | B2 in progress
Fri (30/08) | 30 Aug 2024 | P17 |  | Soldier pile installation
Fri (30/08) | 30 Aug 2024 | N3 |  | Falsework erection
Fri (30/08) | 30 Aug 2024 | ST111 |  | Status 2nd bite trenching, depth at 18.2m. Now change shift for operator
Fri (30/08) | 30 Aug 2024 | ST105-107 |  | Guidewall casting
Fri (30/08) | 30 Aug 2024 | ST101 |  | End plate loosen. BC1 will shift here to do cleaning and desanding
Fri (30/08) | 30 Aug 2024 | BRP57-BC4 |  | Trenching continue, depth 27.5
Fri (30/08) | 30 Aug 2024 | ST170 |  | Cleaning completed. Now preparing for koden
Fri (30/08) | 30 Aug 2024 | BRP42 |  | Pre-boring until 730pm
Fri (30/08) | 30 Aug 2024 | UKP 18 |  | Boring works in progress. Depth 7m
Fri (30/08) | 30 Aug 2024 | BRP11 |  | Desanding completed. Rebar cage tonight to install
Fri (30/08) | 30 Aug 2024 | BP2-2 | 30 | KP installation with doly in progress
Fri (30/08) | 30 Aug 2024 | STN236 |  | Casting in progress
Sat (31/08) | 31 Aug 2024 | BRP57 |  | Cutter teeth replaced. Excavation resume
Sat (31/08) | 31 Aug 2024 | ST101 |  | Final koden check ongoing
Sat (31/08) | 31 Aug 2024 | ST111 |  | B2 in progress
Sat (31/08) | 31 Aug 2024 | N6 |  | Preparing for abudment wall formwork closing
Sat (31/08) | 31 Aug 2024 | P17 |  | ERSS installation
Sat (31/08) | 31 Aug 2024 | P16 |  | Preparing for column casting. Will cast today
Sat (31/08) | 31 Aug 2024 | N3 |  | Secondary beam installation (false work)
Sat (31/08) | 31 Aug 2024 | N2 |  | Access erection for cross head rebar work
Sat (31/08) | 31 Aug 2024 | MH3-5 |  | No more activity
Sat (31/08) | 31 Aug 2024 | P51-1 |  | Casting
Sat (31/08) | 31 Aug 2024 | P9 |  | Column formwork removal
Sat (31/08) | 31 Aug 2024 | P10 |  | Excavation to FEL
Sat (31/08) | 31 Aug 2024 | P3 |  | Prepare platform for PDA test
Sat (31/08) | 31 Aug 2024 | P4 |  | Waler and strut end welding
Sat (31/08) | 31 Aug 2024 | P45 |  | Backfilling done. Utility post reinstated
Sat (31/08) | 31 Aug 2024 | P51-1 |  | Encounter hard rock. Left 2.5m to complete. Target to cast today
Sat (31/08) | 31 Aug 2024 | MH3-5 |  | Preparing to block jacking pipe to prevent water ingress. Today they work half day and tomorrow off
Sat (31/08) | 31 Aug 2024 | ST111 |  | 1st bite, reached 38.9m
Sat (31/08) | 31 Aug 2024 | BC cutter 1 |  | Gear oil top up
Sat (31/08) | 31 Aug 2024 | ST170 |  | Last cage lowering. Today to cast
Sat (31/08) | 31 Aug 2024 | BRP41 |  | 2nd point preboring
Sat (31/08) | 31 Aug 2024 | BRP11 |  | Casting completed
Sat (31/08) | 31 Aug 2024 | P16 |  | Pump car set up for column casting
Sat (31/08) | 31 Aug 2024 | N2 |  | Access erection done
Sat (31/08) | 31 Aug 2024 | P10 |  | Column formwork removal was done
Sat (31/08) | 31 Aug 2024 | P11 |  | Excavation to FEL
Sat (31/08) | 31 Aug 2024 | P51-1 |  | Continue boring to toe. Rock quite hard now
Sat (31/08) | 31 Aug 2024 | ST101 |  | Desanding completed.preparing for rebar cage lowerinf
Sat (31/08) | 31 Aug 2024 | DR1 |  | Waler stiffener plates welding. 2 weldilers + 1sup+ 2 signal man
Sat (31/08) | 31 Aug 2024 | P4 |  | Continue welding of waler and bracing
Sat (31/08) | 31 Aug 2024 | UKP18 |  | Reading for casting
Sat (31/08) | 31 Aug 2024 | MH2-10 |  | TT on going. As of now no services found
Sat (31/08) | 31 Aug 2024 | ST251 |  | Rebar cage installation in progress
Sat (31/08) | 31 Aug 2024 | P16 |  | Column casting in progress
Sat (31/08) | 31 Aug 2024 | P14 |  | Access installation ongoing
Sat (31/08) | 31 Aug 2024 | N3, N4 |  | No activity
Sat (31/08) | 31 Aug 2024 | N2 |  | Preparing to change access
Sat (31/08) | 31 Aug 2024 | 5th concrete truck just arrived. Total est volume for P16 |  | 49m3
Sat (31/08) | 31 Aug 2024 | Zone 1 |  | Currently no activity. Tonight plan to do lane closure along Loyang Ave for coring test
Sat (31/08) | 31 Aug 2024 | Zone 1 |  | TMA on site. Lane closure in progress
Sat (31/08) | 31 Aug 2024 | ST23 |  | 1st bite, reached 31m/37.97m
Sat (31/08) | 31 Aug 2024 | UKP17 &UKP18 |  | Plan for casting today
Sat (31/08) | 31 Aug 2024 | ST251 |  | Cleaning and desanding
Sat (31/08) | 31 Aug 2024 | ST23 | BC3 | Internal koden check
Sat (31/08) | 31 Aug 2024 | ST170 |  | Casting in progress
Sun (01/09) | 01 Sep 2024 | ST111-BC1 |  | 2nd bite trenching at 36m/39m
Sun (01/09) | 01 Sep 2024 | ST101 |  | Rebar cage lowering, 3/6 cages
Sun (01/09) | 01 Sep 2024 | BRP57-BC4 |  | Trenching at 32.5m depth
Sun (01/09) | 01 Sep 2024 | STN204-BC2 |  | 1st bite trenching in progress
Sun (01/09) | 01 Sep 2024 | STN023-BC3 |  | MC cutter engine oil replacement
Sun (01/09) | 01 Sep 2024 | N3 |  | Secondary beam installation completed. C-channel installation in progress
Sun (01/09) | 01 Sep 2024 | Zone 2 |  | Premix rectification ongoing at bus lane
Sun (01/09) | 01 Sep 2024 | ST251 |  | Rebar cage installation ongoing, 8/8nos
Sun (01/09) | 01 Sep 2024 | ST260 |  | B2 in progress
Sun (01/09) | 01 Sep 2024 | ST23 |  | B2 in progress, 25/37.97m
Sun (01/09) | 01 Sep 2024 | ST204 | BC2 | B1 in progress
Sun (01/09) | 01 Sep 2024 | STN023-BC3 |  | 2nd bite trenching continue at 32.5m
Sun (01/09) | 01 Sep 2024 | STN204-BC2 |  | 1st bite trenching in continue, depth 24.7m
Sun (01/09) | 01 Sep 2024 | ST170 |  | Casting in progress, 318/381m3
Sun (01/09) | 01 Sep 2024 | ST101 |  | Rebar cage inspection (6nos)
Sun (01/09) | 01 Sep 2024 | ST111 |  | B2 in progress, 25.3/39m
Sun (01/09) | 01 Sep 2024 | BRP57 |  | Excavation ongoing
Sun (01/09) | 01 Sep 2024 | BRP57-BC4 |  | Trenching at 33.4 m depth
Sun (01/09) | 01 Sep 2024 | ST101 |  | Rebar cage lowering, 5/6 cages
Sun (01/09) | 01 Sep 2024 | ST111-BC1 |  | Trenching completed. Now c-lug welding for trimming
Sun (01/09) | 01 Sep 2024 | Zone 2 |  | Lane reopened
Sun (01/09) | 01 Sep 2024 | STN251 |  | Casting in progress
Sun (01/09) | 01 Sep 2024 | N6 |  | Abutment wall formwork closing
Mon (02/09) | 02 Sep 2024 | P17 |  | Excavation to W1 layer
Mon (02/09) | 02 Sep 2024 | P9 |  | Scaffold dismantling for waler removal
Mon (02/09) | 02 Sep 2024 | STN260 |  | B1 CD 35.1/35.1m, B2 ongoing 15/35.1m
Mon (02/09) | 02 Sep 2024 | STN235 |  | B1 CD 11.0/38.1m
Mon (02/09) | 02 Sep 2024 | TDP13 |  | Preparation work for casing installation
Mon (02/09) | 02 Sep 2024 | ST23 Rig 3 |  | End plate lossening in progress
Mon (02/09) | 02 Sep 2024 | P44 |  | AC cable shifting and manhole hacking in progress
Mon (02/09) | 02 Sep 2024 | P51-2 |  | Boring in progress. Plan to cast tomorrow
Mon (02/09) | 02 Sep 2024 | ST204 Rig 2 |  | B2 excavation CD 33.8m
Mon (02/09) | 02 Sep 2024 | UKP-19 |  | Casing installed
Mon (02/09) | 02 Sep 2024 | BRP40 BG01 |  | P1 preboring CD 23.2/25.07m
Mon (02/09) | 02 Sep 2024 | BRP42 Rig 4 |  | B1 excavation completed, B2 ongoing 29/34.37m
Mon (02/09) | 02 Sep 2024 | BRP57 |  | Kingpost (KP25) lowering in progress
Mon (02/09) | 02 Sep 2024 | ST111 Rig 1 |  | Cleaning in progress
Mon (02/09) | 02 Sep 2024 | P3-3 |  | Preparation for PDA, Target by Wednesday
Mon (02/09) | 02 Sep 2024 | P44 |  | Cable shifted to new location. Pipe installation in progress. Will take over by night shift
Mon (02/09) | 02 Sep 2024 | ST111-BC1 |  | 1st bite cleaning completed. Now change shift, then continue 2nd bite cleaning
Mon (02/09) | 02 Sep 2024 | BRP57 |  | Hanging bar welding for KP lowering
Mon (02/09) | 02 Sep 2024 | DR1 |  | Secondary support welcome works till 9pm
Mon (02/09) | 02 Sep 2024 | BRP42-BC4 |  | 2nd bite trenching resuming at depth of 29m
Mon (02/09) | 02 Sep 2024 | BRP40 |  | Pre-boring works till 730pm
Mon (02/09) | 02 Sep 2024 | UKP19 |  | Casting completed. Now preparing to lower SHS
Mon (02/09) | 02 Sep 2024 | ST204-BC2 |  | 2nd bite trenching at 9m
Mon (02/09) | 02 Sep 2024 | TDP13 |  | Boring works completed. 16m depth
Tue (03/09) | 03 Sep 2024 | P30 |  | Flowmeter installation ongoing from recharge wells
Tue (03/09) | 03 Sep 2024 | ST106 | BC1 | B1 in progress, 8/39m
Tue (03/09) | 03 Sep 2024 | P51-2 |  | Boring to toe in progress. Today to cast
Tue (03/09) | 03 Sep 2024 | DR1 |  | CGS excavation ongoin
Tue (03/09) | 03 Sep 2024 | DR1 |  | Seongha has started fissure grouting for point O-167
Tue (03/09) | 03 Sep 2024 | ST178-ST182 |  | Excavation ongoing to facilitate guidewall hacking
Tue (03/09) | 03 Sep 2024 | BRP42 | BC4 | Excavation temporarily stopped. Cutter teeth changing ongoing
Tue (03/09) | 03 Sep 2024 | ST204 | BC2 | B2 in progress
Tue (03/09) | 03 Sep 2024 | Zone 3 |  | WH trial trench to expose existing water pipe
Tue (03/09) | 03 Sep 2024 | BC3 |  | Currently no activity
Tue (03/09) | 03 Sep 2024 | ST236 |  | Water breaking for 2nd stage grouting
Tue (03/09) | 03 Sep 2024 | BRP40 |  | Preboring in progress
Tue (03/09) | 03 Sep 2024 | ST260 |  | Chiselling ongoing. Bachy BC cutter maintenance ongoing
Tue (03/09) | 03 Sep 2024 | MH2-8 |  | Concrete plug works ongoing
Tue (03/09) | 03 Sep 2024 | MH2-10 |  | Currently no activity
Tue (03/09) | 03 Sep 2024 | MH3-5 |  | Shifting of materials and generator to MH7
Tue (03/09) | 03 Sep 2024 | MH3-4 |  | 2nd layer to cast today
Tue (03/09) | 03 Sep 2024 | ST260 |  | B2 CD 29.4/35.1m, teeth replacement in progress
Tue (03/09) | 03 Sep 2024 | P17 |  | Excavation to S1 layer completed. Access installation in progress
Tue (03/09) | 03 Sep 2024 | N2 crosshead |  | Rebar installation continue. Links installation in progress
Tue (03/09) | 03 Sep 2024 | STN235 |  | B1 CD 29.0/38.1m
Tue (03/09) | 03 Sep 2024 | P9 |  | Backfilling in progress
Tue (03/09) | 03 Sep 2024 | P14 |  | Preparation for column stump casting
Tue (03/09) | 03 Sep 2024 | N3 |  | Access erection in progress
Tue (03/09) | 03 Sep 2024 | BP2-2 | 28 | Preparation work in progress
Tue (03/09) | 03 Sep 2024 | ST224A Rig 3 |  | Excavation has just commenced
Tue (03/09) | 03 Sep 2024 | ST23 |  | Rebar cage lowering in progress
Tue (03/09) | 03 Sep 2024 | ST204 Rig 2 |  | B2 CD 18.7m, teeth replace in progress
Tue (03/09) | 03 Sep 2024 | UKP20 |  | Waiting for concrete to cast
Tue (03/09) | 03 Sep 2024 | BRP40 BG01 |  | P2 pre-boring CD 20.2/25.07m
Tue (03/09) | 03 Sep 2024 | BRP42 Rig 4 |  | B1 CD 32m, needs to excavate another 2m
Tue (03/09) | 03 Sep 2024 | DR1 |  | Fissure grouting point O-165 in progress
Tue (03/09) | 03 Sep 2024 | Zone 1 NLL |  | CGS doing watering for center median grass
Tue (03/09) | 03 Sep 2024 | P30 |  | RG manual trial trench ongoing for water standpipe and inclinometer installation
Tue (03/09) | 03 Sep 2024 | DR1 |  | CGS continues excavation
Tue (03/09) | 03 Sep 2024 | DR1 |  | LE continues beam installation for utility support
Tue (03/09) | 03 Sep 2024 | Blk 4 |  | RG drilling ongoing for piezometer
Tue (03/09) | 03 Sep 2024 | ST106 |  | B1 in progress, 27/39m
Tue (03/09) | 03 Sep 2024 | PMH26 |  | SI work. Today to complete
Tue (03/09) | 03 Sep 2024 | P50-2 |  | Rebar cage lowering. Today to caat
Tue (03/09) | 03 Sep 2024 | STN260 |  | 2nd bite trenching at 31.6/35.1m
Tue (03/09) | 03 Sep 2024 | STN235 |  | 2nd bite trenching at 12m depth. 1st bite at 28.6m
Tue (03/09) | 03 Sep 2024 | P9-1 |  | Backfilling to pile cap level untjl and 9pm
Tue (03/09) | 03 Sep 2024 | P11 |  | Pile head hacking
Tue (03/09) | 03 Sep 2024 | P17 |  | Waler bracket installation started
Wed (04/09) | 04 Sep 2024 | ST111 |  | Rebar cage inspection
Wed (04/09) | 04 Sep 2024 | ST106 |  | B1 excavation temporarily stopped due to high engine temperature. CD 38.5/39m
Wed (04/09) | 04 Sep 2024 | Eng hUp at zone 1 |  | Discussion for cable shifting or pulling to new pipe laid
Wed (04/09) | 04 Sep 2024 | P46& P47 |  | Exposing of AC cable for shifting
Wed (04/09) | 04 Sep 2024 | P51-2 |  | Boring on going to Toe level
Wed (04/09) | 04 Sep 2024 | P3 |  | Crane setting up for PDa
Wed (04/09) | 04 Sep 2024 | P51-2 |  | Continue boring to Toe level
Thu (05/09) | 05 Sep 2024 | JGP No-28 |  | Pipe sleeves installed for SPT and core sample test. Will wittness by CR105
Thu (05/09) | 05 Sep 2024 | P46-47 |  | Exposing of AC cable for shifting
Thu (05/09) | 05 Sep 2024 | P44-7 |  | Rebar cages lowering down. Afternoon to cast
Thu (05/09) | 05 Sep 2024 | P46-47 |  | Exposing of DSTA cable for shifting
Thu (05/09) | 05 Sep 2024 | P44-7 |  | Preparing for casting
Thu (05/09) | 05 Sep 2024 | P51-2 |  | Boring to toe level in progress. Tomorrow to cast
Thu (05/09) | 05 Sep 2024 | P4 |  | Excavation to FEL in progress
Thu (05/09) | 05 Sep 2024 | BRP42 |  | Ready to cast
Thu (05/09) | 05 Sep 2024 | ST194 Rig 2 |  | B1 CD 25.9/32.16m
Thu (05/09) | 05 Sep 2024 | UKP45 |  | Preparing to install casing
Thu (05/09) | 05 Sep 2024 | ST224A Rig 3 |  | B1 excavation completed 32.9/32.9m, internal koden in progress
Thu (05/09) | 05 Sep 2024 | BP2-2 | 28 | Boring CD 27.0/36.9m
Thu (05/09) | 05 Sep 2024 | STN260 |  | Rebar cage 4/8 lowering in progress
Thu (05/09) | 05 Sep 2024 | P3 |  | PDA pile hacking ongoing
Thu (05/09) | 05 Sep 2024 | P44-7 |  | Casting done
Thu (05/09) | 05 Sep 2024 | ST111 |  | Cage A (3/4) & Cage B (4/4) in progress
Thu (05/09) | 05 Sep 2024 | ST106 |  | 2nd bite, reached 34.8m/39m
Thu (05/09) | 05 Sep 2024 | DR1 |  | LE installation of sewer pipe support and welding
Thu (05/09) | 05 Sep 2024 | BRP42 |  | Casting in progress
Thu (05/09) | 05 Sep 2024 | BRP40 |  | Preboring in progress
Thu (05/09) | 05 Sep 2024 | ST194 |  | 1st bite, reached 25.9m
Thu (05/09) | 05 Sep 2024 | P17 |  | Diagonal struct installation
Thu (05/09) | 05 Sep 2024 | P18 |  | TT for ERSS work
Thu (05/09) | 05 Sep 2024 | N4 |  | Falsework removal
Thu (05/09) | 05 Sep 2024 | P15 |  | Tie rod hole patch up
Thu (05/09) | 05 Sep 2024 | N2 |  | Now no activity
Thu (05/09) | 05 Sep 2024 | P11-1 |  | Pile head hacking
Thu (05/09) | 05 Sep 2024 | P9-1 |  | Cleaning and backfilling for platform
Thu (05/09) | 05 Sep 2024 | P3 |  | PDA test pile hacking almost completed
Thu (05/09) | 05 Sep 2024 | P4 |  | Continue excavation to FEL
Thu (05/09) | 05 Sep 2024 | ST235 |  | 2nd bite completed. Preparing for 3rd bite
Thu (05/09) | 05 Sep 2024 | BP2-2-29 |  | Boring in progress. Reached 27.5m
Thu (05/09) | 05 Sep 2024 | UKP45 |  | Boring reached 9.5m. Tomorrow to cast
Thu (05/09) | 05 Sep 2024 | MH2-8& MH2-9 |  | No activity
Thu (05/09) | 05 Sep 2024 | P51-2 |  | Boring in progress to toe level. Now rock getting harder
Fri (06/09) | 06 Sep 2024 | ST111 |  | Tremie pipe installation ongoing
Fri (06/09) | 06 Sep 2024 | ST106 |  | Trimming ongoing
Fri (06/09) | 06 Sep 2024 | P9 |  | Preparation for lifting and rebar cage installation
Fri (06/09) | 06 Sep 2024 | DR2 area |  | Scaffold erection for new designated walking access
Fri (06/09) | 06 Sep 2024 | BRP50 |  | Guidewall formwork ongoin
Fri (06/09) | 06 Sep 2024 | BRP77 |  | Excavation in progress, 25.2/35.37m
Fri (06/09) | 06 Sep 2024 | P51-2 |  | Rock very hard now
Fri (06/09) | 06 Sep 2024 | P51-2 |  | Left 1m to reache toe. Today to cast
Fri (06/09) | 06 Sep 2024 | P46-47 |  | Wee Guan exposing of DSTA cable
Fri (06/09) | 06 Sep 2024 | P45 |  | Preparing to install pipe sleeves for JGP testing
Fri (06/09) | 06 Sep 2024 | MH3-5 |  | Shifting of ventilation fan to MH3-4
Fri (06/09) | 06 Sep 2024 | P46 |  | Drain removal for water pipe protection
Fri (06/09) | 06 Sep 2024 | P46-47 |  | DSTA cable haunch removal for localize shifting
Fri (06/09) | 06 Sep 2024 | P51-2 |  | Preparing for rebar cage lowering
Fri (06/09) | 06 Sep 2024 | Blk 2 |  | Trial trench ongoing for RW15 and RW16
Fri (06/09) | 06 Sep 2024 | MH3-4 |  | Manual excavation for next layer caisson casting. Found two more services below 2nd layer caisson
Fri (06/09) | 06 Sep 2024 | Blk 2 |  | WH preparing platform for transformer works at JTC
Fri (06/09) | 06 Sep 2024 | P31 area |  | Removing abandoned water pipes
Fri (06/09) | 06 Sep 2024 | P34 |  | Piezometer and water standpipe completed. RG proceed with trial trench for inclinometer works
Fri (06/09) | 06 Sep 2024 | STN252 |  | B1 CD 11.5/39.4m
Fri (06/09) | 06 Sep 2024 | BRP50 |  | Pending guidewall casting, BRP51: Guidewall trial trench ongoing
Fri (06/09) | 06 Sep 2024 | STN235 |  | Cleaning in progress
Fri (06/09) | 06 Sep 2024 | STN231 |  | Cutter under maintenance since 6.40am today
Fri (06/09) | 06 Sep 2024 | ST111 |  | Casting in progress, 222/231m3
Fri (06/09) | 06 Sep 2024 | ST106 |  | B1 and B2 cleaning completed. Pending desanding and rebar cage delivery (8nos). Rebar cages will be delivered by today
Fri (06/09) | 06 Sep 2024 | ST224A Rig 3 |  | B2 CD26.6/32.9m, now replacing of gear box
Fri (06/09) | 06 Sep 2024 | BP2-2 | 28 | Boring CD 34.5/36.9m, planning to work till 10pm today & target to cast it tomorrow
Fri (06/09) | 06 Sep 2024 | UKP45 |  | Waiting for concrete to cast
Fri (06/09) | 06 Sep 2024 | BRP77 |  | Excavation temporarily stopped for cutter teeth change. CD 26.3/35.37m
Fri (06/09) | 06 Sep 2024 | Capping beam | part 2 | Continue rebar works and formwork fabrication
Fri (06/09) | 06 Sep 2024 | ST194 Rig 2 |  | B2 CD 20.5/32.16m
Fri (06/09) | 06 Sep 2024 | BRP40 BG01 |  | B2-P2 pre-boring CD 19.6/25.07m
Fri (06/09) | 06 Sep 2024 | P17 |  | Struts installation & welding in progress
Fri (06/09) | 06 Sep 2024 | N3 |  | Continue Pier hacking to correct level
Fri (06/09) | 06 Sep 2024 | P11 |  | Last pile head hacking in progress. 5/6 completed
Fri (06/09) | 06 Sep 2024 | P10 |  | Portal frame assembly
Fri (06/09) | 06 Sep 2024 | P14 |  | Preparation for column rebar cage fabrication
Fri (06/09) | 06 Sep 2024 | N1 |  | Falsework - primary beam installation
Fri (06/09) | 06 Sep 2024 | P9-1 |  | Column rebar cage installed
Fri (06/09) | 06 Sep 2024 | ST102 |  | 1st bite excavation started
Fri (06/09) | 06 Sep 2024 | BC cutter 4 |  | Cutter wheel changing
Fri (06/09) | 06 Sep 2024 | P4 |  | Access shifting & installation works before resuming FEL excavation
Fri (06/09) | 06 Sep 2024 | BRP50- guidewall today casting. BRP51 |  | TT on going
Fri (06/09) | 06 Sep 2024 | ST194 |  | 2nd bite, reached 20m. Now bentonite leakage at desander. Repairing on going
Fri (06/09) | 06 Sep 2024 | P31 |  | KTC continue excavation and removal of water pipe
Fri (06/09) | 06 Sep 2024 | ST204 |  | Lowering waterstop end plate
Fri (06/09) | 06 Sep 2024 | UKP45 |  | Casting in progress
Fri (06/09) | 06 Sep 2024 | P17 |  | Current status of waler to diagonal strut welding. LE work until 7PM today
Fri (06/09) | 06 Sep 2024 | P18 |  | Road premix removal and TT work
Fri (06/09) | 06 Sep 2024 | N2 |  | Formwork closing for crosshead
Fri (06/09) | 06 Sep 2024 | N1 |  | Falsework adjusting
Fri (06/09) | 06 Sep 2024 | P11 |  | Pile head hacking
Fri (06/09) | 06 Sep 2024 | P4 |  | Continue excavation work
Fri (06/09) | 06 Sep 2024 | P51-2 |  | Casting started
Fri (06/09) | 06 Sep 2024 | P50-3 |  | Preboring started
Fri (06/09) | 06 Sep 2024 | MH2-10 |  | RG drilling ongoing for inclinometer
Fri (06/09) | 06 Sep 2024 | BP2-2 | 28 | Boring in progress, 32/36.9m
Fri (06/09) | 06 Sep 2024 | ST224A |  | B2 in progress, 25/32.9m
Fri (06/09) | 06 Sep 2024 | UKP44 |  | Trial trench ongoing
Fri (06/09) | 06 Sep 2024 | UKP45 |  | Boring in progress
Fri (06/09) | 06 Sep 2024 | ST194 |  | B2 temporarily stopped. Desander rectification ongoing
Fri (06/09) | 06 Sep 2024 | P31 area |  | Hardcore removal ongoing
Sat (07/09) | 07 Sep 2024 | P8 |  | Excavation ongoing for internal cable pipes installation to facilitate the vehicle access diversion
Sat (07/09) | 07 Sep 2024 | Zone 2 |  | Hump hacking ongoing
Sat (07/09) | 07 Sep 2024 | P4 |  | Excavation to FEL in progress
Sat (07/09) | 07 Sep 2024 | Zone 2 | south side | Side door installation near Shell area
Sat (07/09) | 07 Sep 2024 | ST252 |  | B1 excavation in progress
Sat (07/09) | 07 Sep 2024 | ST235 |  | Rebar cage installation in progress, 8/8nos
Sat (07/09) | 07 Sep 2024 | BP2-2 | 28 | Boring in progress, 34.5/36.9m
Sat (07/09) | 07 Sep 2024 | UKP44 |  | Preboring and casing installation
Sat (07/09) | 07 Sep 2024 | ST209-211 |  | Preparation for guidewall trial trench
Sat (07/09) | 07 Sep 2024 | Blk 2 |  | Drilling ongoing for RW16
Sat (07/09) | 07 Sep 2024 | P31 area |  | Hardcore removal ongoing
Sat (07/09) | 07 Sep 2024 | ST102 |  | 2nd bite reached 23.3m
Sat (07/09) | 07 Sep 2024 | BRP77 |  | Preparing for rebar cage lowering
Sat (07/09) | 07 Sep 2024 | DR1 |  | LE strut fabrication ongoing
Sat (07/09) | 07 Sep 2024 | BRP51 |  | Guidewall construction in progress
Sat (07/09) | 07 Sep 2024 | BRP77 |  | Excavation in progress, 32.5/35.37m
Sat (07/09) | 07 Sep 2024 | BRP40 |  | Preboring on going
Sat (07/09) | 07 Sep 2024 | ST102 |  | B1 completed. Cutter body lift up and washing
Sat (07/09) | 07 Sep 2024 | MH3-4 |  | Preparing for 3rd layer works
Sat (07/09) | 07 Sep 2024 | P44-8 |  | Boring in progress
Sat (07/09) | 07 Sep 2024 | P46-47 |  | Continue cable haunch removal for localised shifting
Sat (07/09) | 07 Sep 2024 | P50-3 |  | Boring ongoing. Plan for casting today
Sat (07/09) | 07 Sep 2024 | P45 |  | GCE preparing area for SPT26 works
Sat (07/09) | 07 Sep 2024 | MH2-9 |  | Hacking ongoing
Sat (07/09) | 07 Sep 2024 | MH2-10 |  | Water standpipe installation completed. Balance to install inclinometer, target to complete tmr
Sat (07/09) | 07 Sep 2024 | P31 area |  | Excavation ongoing to remove abandoned water pipe
Sat (07/09) | 07 Sep 2024 | BRP40 |  | Preboring ongoing
Sat (07/09) | 07 Sep 2024 | DR1 |  | Excavation ongoing
Sat (07/09) | 07 Sep 2024 | P34 |  | RG drilling ongoing for inclinometer installation
Sat (07/09) | 07 Sep 2024 | DR2 |  | WH installing new walking access
Sat (07/09) | 07 Sep 2024 | BRP48 |  | Trial trench for guidewall ongoing
Sat (07/09) | 07 Sep 2024 | ST194 |  | Cleaning ongoing
Sat (07/09) | 07 Sep 2024 | BRP77 |  | Cleaning ongoing
Sat (07/09) | 07 Sep 2024 | ST102 |  | B2 in progress
Sat (07/09) | 07 Sep 2024 | P44-8 |  | Rebar cage lowering ongoing
Sat (07/09) | 07 Sep 2024 | MH3-4 |  | Manual excavation ongoing
Sat (07/09) | 07 Sep 2024 | UKP44 |  | Boring ongoing
Sat (07/09) | 07 Sep 2024 | ST224A |  | B3 ongoing
Sat (07/09) | 07 Sep 2024 | BP2-2 | 28 | Boring in progress
Sat (07/09) | 07 Sep 2024 | ST231 |  | B2 in progress
Sat (07/09) | 07 Sep 2024 | ST252 |  | B1 ongoing, 28/39.4m
Sat (07/09) | 07 Sep 2024 | ST235 |  | Casting in progress, 96/290m3
Sat (07/09) | 07 Sep 2024 | BP2-2-28 |  | Balance 500mm to complete. Now internal koden check
Sat (07/09) | 07 Sep 2024 | ST231 |  | 1st bite in progress
Sat (07/09) | 07 Sep 2024 | ST235 |  | Last load casting in progress
Sat (07/09) | 07 Sep 2024 | Zone 2 |  | CGS will be working after bus hours for bentonite hoses laying at bus only lane
Sat (07/09) | 07 Sep 2024 | Zone 4 |  | P50-3: bored pile casting done. Now housekeeping before go back
Sat (07/09) | 07 Sep 2024 | P17 |  | Joint welding works ongoing
Sat (07/09) | 07 Sep 2024 | P18 |  | LE trial trench for preboring ongoing
Sat (07/09) | 07 Sep 2024 | P13 |  | Column rebar cage fabrication ongoin
Sat (07/09) | 07 Sep 2024 | N2 |  | Crosshead formwork installation in progress
Sat (07/09) | 07 Sep 2024 | N1 |  | Falsework in progress
Sat (07/09) | 07 Sep 2024 | P11 |  | Pile head hardcore clearing ongoing
Sun (08/09) | 08 Sep 2024 | P17 |  | Waler beam welding today to complete. Tomorrow AM MPI
Sun (08/09) | 08 Sep 2024 | Zone 4 |  | JGP testing/SPT. 1st layer completed. N=100>30
Sun (08/09) | 08 Sep 2024 | StN102-BC1 |  | 2nd bite trenching at 33.5m temporarily stopped due desander maintenance
Sun (08/09) | 08 Sep 2024 | BRP77 |  | Casting in progress
Sun (08/09) | 08 Sep 2024 | BRP50 |  | Pre-boring works started
Sun (08/09) | 08 Sep 2024 | DR1 |  | Temp sewer concrete stump hacking. Advise the team to arrange platform for hacking
Sun (08/09) | 08 Sep 2024 | ST194 |  | Rebar cage installation 3/6
Sun (08/09) | 08 Sep 2024 | ST204-BC3 |  | Cleaning and desanding in progress
Sun (08/09) | 08 Sep 2024 | MH2-9 |  | Excavation for 11th layer in progress
Sun (08/09) | 08 Sep 2024 | ST231 |  | 1st bite, reached 37.7m
Sun (08/09) | 08 Sep 2024 | BRP40 |  | Trenching started
Sun (08/09) | 08 Sep 2024 | StN102-BC1 |  | 2nd bite trenching completed. Preparation for 3rd bite trenching
Sun (08/09) | 08 Sep 2024 | MH7 |  | Hacking of caisson for TBM retrieval
Sun (08/09) | 08 Sep 2024 | ST102 |  | 2nd bite reached 26.2m
Sun (08/09) | 08 Sep 2024 | BRP77 |  | Rebar cage and KP lowering completed. Hanging bar installation
Mon (09/09) | 09 Sep 2024 | Blk 2 |  | WH dismantling old walking access
Mon (09/09) | 09 Sep 2024 | P31 area |  | KTC soil trimming
Mon (09/09) | 09 Sep 2024 | P34 |  | RG drilling ongoing for inclinometer installation
Mon (09/09) | 09 Sep 2024 | ST102 |  | B3 in progress
Mon (09/09) | 09 Sep 2024 | BRP50 |  | Preboring ongoing, BRP51: Guidewall dismantling
Mon (09/09) | 09 Sep 2024 | C1 |  | Rig set up and preparing for SPT & coring
Mon (09/09) | 09 Sep 2024 | P46-47 |  | Continue exposing of DSTA cables
Mon (09/09) | 09 Sep 2024 | P51-3 |  | Preparing for preboring
Mon (09/09) | 09 Sep 2024 | P11 |  | Guide bar installation started
Mon (09/09) | 09 Sep 2024 | P9 |  | Tie rod installation for formwork closing
Mon (09/09) | 09 Sep 2024 | DR1 |  | LE continue joint welding for top plate and soldier pile
Mon (09/09) | 09 Sep 2024 | DR1 |  | LE preparing area for utility support works
Mon (09/09) | 09 Sep 2024 | P8 |  | Premix hacking for TT
Mon (09/09) | 09 Sep 2024 | Zone 2 |  | VSK to mobilise machinery tomorrow to start telco duct construction
Mon (09/09) | 09 Sep 2024 | DR1 |  | Drilling ongoing for fissure grout point, O-164
Mon (09/09) | 09 Sep 2024 | Zone 3 | south side | Seongha continue exposing the fissure grout point
Mon (09/09) | 09 Sep 2024 | BRP40 | BC4 | Excavation temporarily stopped for cutter teeth change. CD 18/25.07m
Mon (09/09) | 09 Sep 2024 | BC3 |  | Maintenance ongoing
Mon (09/09) | 09 Sep 2024 | ST204 |  | Rebar cage installation in progress, 2/6nos
Mon (09/09) | 09 Sep 2024 | MH3-4 |  | Preparing for 3rd layer rebar inspection. Today to cast
Mon (09/09) | 09 Sep 2024 | BP2-2 | 28 | Boring completed. Today plan for rebar cage and KP installation
Mon (09/09) | 09 Sep 2024 | ST14 |  | B1 in progress
Mon (09/09) | 09 Sep 2024 | P18 pre-boring status |  | 5/52
Mon (09/09) | 09 Sep 2024 | P51-3 |  | Boring in progress
Mon (09/09) | 09 Sep 2024 | MH2-9 |  | Excavation 11th layer
Mon (09/09) | 09 Sep 2024 | MH2-10 |  | Drilling ongoing for water standpipe installation. Plan for installation today
Mon (09/09) | 09 Sep 2024 | P27 |  | Platform preparation ongoing for subsequent recharge well points
Mon (09/09) | 09 Sep 2024 | RW15 |  | In progress
Mon (09/09) | 09 Sep 2024 | STN231 |  | B1 CD 39/38.75m, B2 ongoing 23/33.350m
Mon (09/09) | 09 Sep 2024 | ST102 |  | B3 in progress
Mon (09/09) | 09 Sep 2024 | ST106 |  | Rebar cage installation ongoing, 4/8nos
Mon (09/09) | 09 Sep 2024 | ST194 Rig3 |  | Cleaning in progress
Mon (09/09) | 09 Sep 2024 | Zone 2 |  | Mobilization of bentonite plant for piling works
Mon (09/09) | 09 Sep 2024 | P34 |  | Inclinometer installation ongoing
Mon (09/09) | 09 Sep 2024 | C1 |  | SPT& coring in progress. One layer of SPT did not achieve requirement
Mon (09/09) | 09 Sep 2024 | P46-P47 |  | Exposing of DSTA cable for shifting
Mon (09/09) | 09 Sep 2024 | MH3-4 |  | Formwork closing in progress. Today to cast
Mon (09/09) | 09 Sep 2024 | P14 |  | Barricade installation
Mon (09/09) | 09 Sep 2024 | N1 |  | Scaffold access erection in progress
Mon (09/09) | 09 Sep 2024 | N1 |  | Top barricade installation
Mon (09/09) | 09 Sep 2024 | P11 |  | Rebar works ongoing
Mon (09/09) | 09 Sep 2024 | P9 |  | Column formwork installation ongoing
Mon (09/09) | 09 Sep 2024 | ST14 |  | B1 temporarily stopped for cutter teeth change. CD 29/32.5m
Mon (09/09) | 09 Sep 2024 | BP2-2 | 28 | KP and dolly lowering ongoing. To cast thereafter
Mon (09/09) | 09 Sep 2024 | ST194 |  | B2 cleaning temporarily stopped. Mud pump rectification ongoing
Mon (09/09) | 09 Sep 2024 | BRP40 |  | B1 in progres
Mon (09/09) | 09 Sep 2024 | ST102 |  | Endplate loosening ongoing
Mon (09/09) | 09 Sep 2024 | ST106 |  | Rebar cage installation ongoing, 6/8nos
Tue (10/09) | 10 Sep 2024 | P17 |  | Today to start excavation
Tue (10/09) | 10 Sep 2024 | P8 |  | Premix and apron slab hacking continue
Tue (10/09) | 10 Sep 2024 | Zone 2 |  | Mobilisation and bentonite plant set up for piling works
Tue (10/09) | 10 Sep 2024 | P51-3 |  | Boring on going. Tomorrow to cast
Tue (10/09) | 10 Sep 2024 | P48-49 |  | Wee Guan excavation and ERSS for Power duct
Tue (10/09) | 10 Sep 2024 | P47-P46 |  | Wee Guan exposing DSTA cable for shifting
Tue (10/09) | 10 Sep 2024 | P45 |  | GCE boring for SPT test
Tue (10/09) | 10 Sep 2024 | P44 |  | HSL demobbing rig and materials
Tue (10/09) | 10 Sep 2024 | MH3-4 |  | 3rd layer caisson curing. Proper utility support to continue today
Tue (10/09) | 10 Sep 2024 | MH2-9 |  | Hacking ongoing for 11th layer
Tue (10/09) | 10 Sep 2024 | MH2-10 |  | RG has completed instruments installation and demob their rig. Currently no other activity here
Tue (10/09) | 10 Sep 2024 | P27 |  | WH preparing platform for next recharge well points
Tue (10/09) | 10 Sep 2024 | P4 |  | Balance levelling. Today to shift long arm at P17
Tue (10/09) | 10 Sep 2024 | P51-3 |  | Continue boring to toe level
Tue (10/09) | 10 Sep 2024 | P31 area |  | KTC manual clearing of soil near the services haunching and slope trimming ongoing
Tue (10/09) | 10 Sep 2024 | P32 |  | Backfilling ongoing behind BC cutter to address PGI comment this morning
Tue (10/09) | 10 Sep 2024 | Near DR2 |  | WH erecting storage area
Tue (10/09) | 10 Sep 2024 | ST106 |  | Casting completed at 1430hrs (248m3)
Tue (10/09) | 10 Sep 2024 | N3 |  | Continue hacking works for pier
Tue (10/09) | 10 Sep 2024 | ST102 |  | Trimming temporarily stopped. Cutter teeth changing ongoing
Tue (10/09) | 10 Sep 2024 | BRP50 |  | Continue preboring
Tue (10/09) | 10 Sep 2024 | BRP48 |  | Guidewall rebar works ongoing
Tue (10/09) | 10 Sep 2024 | P14 |  | Continue rebar cage fabrication
Tue (10/09) | 10 Sep 2024 | N1 |  | Scaffold erection in progress
Tue (10/09) | 10 Sep 2024 | P9-1 |  | Continue formwork closing works
Tue (10/09) | 10 Sep 2024 | DR1 |  | Installation of last piece of seconday beam
Tue (10/09) | 10 Sep 2024 | DR1 |  | Current status of excavation. Now CGS ongoing debris hacking
Tue (10/09) | 10 Sep 2024 | BRP40 |  | B1 in progres
Tue (10/09) | 10 Sep 2024 | ST194 |  | Rebar cage installation in progress, 4/6nos
Tue (10/09) | 10 Sep 2024 | SPT1 |  | 2nd layer SPT done. Result satisfactory
Tue (10/09) | 10 Sep 2024 | P47 |  | Exposing of DSTA manhole
Tue (10/09) | 10 Sep 2024 | P48 |  | Wee Guan continue ERSS for duct laying
Tue (10/09) | 10 Sep 2024 | ST204 |  | B1 cleaning ongoing
Tue (10/09) | 10 Sep 2024 | ST209-211 |  | Guidewall backfilling
Tue (10/09) | 10 Sep 2024 | ST14 | BC2 | Excavation temporarily stopped. Cutter mud hose replacement ongoin
Tue (10/09) | 10 Sep 2024 | ST246 |  | Excavation started
Tue (10/09) | 10 Sep 2024 | P18 |  | Continue ERSS preboring works
Tue (10/09) | 10 Sep 2024 | N3 |  | Hacking works ongoing
Tue (10/09) | 10 Sep 2024 | N1 |  | Scaffold erection ongoing
Tue (10/09) | 10 Sep 2024 | P11 |  | Pipe cap rebar works in progress
Tue (10/09) | 10 Sep 2024 | P9 |  | Continue column formwork closin
Tue (10/09) | 10 Sep 2024 | P8 |  | Trial trench ongoing
Tue (10/09) | 10 Sep 2024 | Zone 2 |  | HSL mobilisation and setup works
Tue (10/09) | 10 Sep 2024 | ST246 |  | Setting up hydrofraise to resume excavation until ard 10m depth. Thereafter continue using grabber & hydrofraise will resume at ST252
Tue (10/09) | 10 Sep 2024 | ST14 |  | Resume excavation
Tue (10/09) | 10 Sep 2024 | BP2-2 | 28 | LSS backfill
Tue (10/09) | 10 Sep 2024 | ST194 |  | Rebar cage installation ongoing, 5/6nos
Tue (10/09) | 10 Sep 2024 | TDP22 |  | Casing installed, BP4A-1(40), 1600mm dia: Boring reached 19/39.042m
Wed (11/09) | 11 Sep 2024 | STN231 |  | WS extraction in progress
Wed (11/09) | 11 Sep 2024 | STN246 |  | B1 CD 18.5/43.83m
Wed (11/09) | 11 Sep 2024 | P10-1 |  | Area preparation for falsework installation
Wed (11/09) | 11 Sep 2024 | TDP22 |  | Boring CD 10m/22.378
Wed (11/09) | 11 Sep 2024 | BP4A-1 | 40 | Boring CD 20/39.042m
Wed (11/09) | 11 Sep 2024 | P9-2 |  | Pier formwork closing
Wed (11/09) | 11 Sep 2024 | P7-P8 |  | HSL delivery of steel plate. VSK mobilisation of excavator
Wed (11/09) | 11 Sep 2024 | BRP40 Rig 4 |  | B1 CD 22.5/25.07m
Wed (11/09) | 11 Sep 2024 | Zone 2 |  | Bentonite plant set up. Crane and rig tomorrow to mobilise
Wed (11/09) | 11 Sep 2024 | ST102 Rig 1 |  | Excavation has completed & prepare for cleaning
Wed (11/09) | 11 Sep 2024 | C3 |  | TT and pipe sleeves installation
Wed (11/09) | 11 Sep 2024 | P47 |  | Exposing of DSTA cable
Wed (11/09) | 11 Sep 2024 | P48-P49 |  | ERSS for power duct laying
Wed (11/09) | 11 Sep 2024 | P19 area |  | Area ready for sewer line sealing works
Wed (11/09) | 11 Sep 2024 | P18 |  | Pre-boring continue
Wed (11/09) | 11 Sep 2024 | P8 |  | 22kv and gas pipe (abandoned) removal
Wed (11/09) | 11 Sep 2024 | Zone 1 P5 |  | Soil/premix disposal
Wed (11/09) | 11 Sep 2024 | STN252 |  | 1st bite trenching at 42/43.9m
Wed (11/09) | 11 Sep 2024 | STN231 |  | Timming for end plate extraction
Wed (11/09) | 11 Sep 2024 | ST14-BC3 |  | End plate trimming in progress
Wed (11/09) | 11 Sep 2024 | TDP22 |  | Casting in progress, total vol 19m3
Wed (11/09) | 11 Sep 2024 | BP4A-1 | 40 | Boring works continue at 33m
Wed (11/09) | 11 Sep 2024 | ST204 |  | Rebar cage installation in progress. 3/6 installed
Wed (11/09) | 11 Sep 2024 | BRP50 |  | Trenching works at 26.6m depth
Wed (11/09) | 11 Sep 2024 | BRP49 |  | Pre-boring in progress
Wed (11/09) | 11 Sep 2024 | Zone 4 |  | Point C3 coring and SPT. Balance 2 nos each
Wed (11/09) | 11 Sep 2024 | P17, P18 |  | No more activity
Wed (11/09) | 11 Sep 2024 | N3 |  | Clearing debris
Wed (11/09) | 11 Sep 2024 | N1 |  | Ladder access erection ongoing
Wed (11/09) | 11 Sep 2024 | N2, P11 |  | No activity
Wed (11/09) | 11 Sep 2024 | P8 |  | Backfilling ongoing
Wed (11/09) | 11 Sep 2024 | Zone 2 HSL |  | Barricade installation/setup ongoing
Wed (11/09) | 11 Sep 2024 | P9 |  | Scaffold access installation in progress
Wed (11/09) | 11 Sep 2024 | ST231 |  | WS removal in progress
Wed (11/09) | 11 Sep 2024 | ST252 |  | Cutter teeth checking ongoing
Wed (11/09) | 11 Sep 2024 | ST14 |  | Endplate loosening ongoing
Wed (11/09) | 11 Sep 2024 | P27 |  | Ground levelling ongoing
Wed (11/09) | 11 Sep 2024 | P31-32 |  | Protection installation ongoing for existing cable haunching
Wed (11/09) | 11 Sep 2024 | Blk 4 |  | Erection of storage area by WH
Wed (11/09) | 11 Sep 2024 | BRP50 |  | Preparing for internal koden check
Wed (11/09) | 11 Sep 2024 | Receiving shaft/MH3-4 |  | No activity
Wed (11/09) | 11 Sep 2024 | Zone 4 |  | Cable pulling by Vistek
Wed (11/09) | 11 Sep 2024 | P51-3 |  | Casting completed. No other activity by HSL
Wed (11/09) | 11 Sep 2024 | P17 |  | Waiting for long arm excavator from zone 1
Wed (11/09) | 11 Sep 2024 | MH7 |  | Preparation ongoing for TBM retrieval
Wed (11/09) | 11 Sep 2024 | P51-3 |  | Boring to toe in progress. Today to cast
Thu (12/09) | 12 Sep 2024 | P45 |  | TT for pipe sleeves installation. Today plan to test C4
Thu (12/09) | 12 Sep 2024 | P47 |  | Manhole hacking to shift DSTA cables
Thu (12/09) | 12 Sep 2024 | P48-P49 |  | Lean concrete done yesterday. Today to lay pipe
Thu (12/09) | 12 Sep 2024 | P50-4 |  | Boring to toe level. Today to cast
Thu (12/09) | 12 Sep 2024 | N3 pier hacking |  | Target to complete today
Thu (12/09) | 12 Sep 2024 | N2 |  | Final inspection this morning. Afternoon plan to cast
Thu (12/09) | 12 Sep 2024 | P6-7 |  | Mobilisation of mobile crane for rig setting up today. Tomorrow crawler crane to follow
Thu (12/09) | 12 Sep 2024 | P5 |  | Exposing traffic light cables for localised shifting
Thu (12/09) | 12 Sep 2024 | P4 |  | Pile head cutting and hacking
Thu (12/09) | 12 Sep 2024 | ST231 |  | Base cleaning ongoing
Thu (12/09) | 12 Sep 2024 | ST252 |  | B1 resumed from 29.5/39.4m
Thu (12/09) | 12 Sep 2024 | ST14 |  | C-lug welding ongoing for WS side trimmin
Thu (12/09) | 12 Sep 2024 | ST204 |  | Hanging bar installation ongoing
Thu (12/09) | 12 Sep 2024 | MH7 |  | TBM retrieval completed
Thu (12/09) | 12 Sep 2024 | STN246 |  | B1 CD 34.0/43.93m
Thu (12/09) | 12 Sep 2024 | STN231 |  | Rebar cage installation in progress
Thu (12/09) | 12 Sep 2024 | BP4A-1 | 40 | Boring CD 37/39.042m
Thu (12/09) | 12 Sep 2024 | BRP50 |  | KP & rebar cage installation in progress
Thu (12/09) | 12 Sep 2024 | P17 |  | KTC excavation to FEL
Thu (12/09) | 12 Sep 2024 | P50-4 |  | Left 1.5m. Rock getting hard. If canot cast today. Tomorrow can cast
Thu (12/09) | 12 Sep 2024 | N3 |  | Continue pier hacking works
Thu (12/09) | 12 Sep 2024 | P14 |  | NDT test in progress
Thu (12/09) | 12 Sep 2024 | N1 |  | Netting & toeboard installation works
Thu (12/09) | 12 Sep 2024 | P11 |  | Continue shear links installation works
Thu (12/09) | 12 Sep 2024 | P6-P7 |  | HSL setting up works in progress. Boring rig to set up today
Thu (12/09) | 12 Sep 2024 | P9-1 |  | Formwork closing completed. Rectifying some minor comments. Target to cast ard 6-7pm
Thu (12/09) | 12 Sep 2024 | P19 |  | Sewer sealing works completed. Power will be turned on at 6am
Thu (12/09) | 12 Sep 2024 | P8 |  | Continue BP, ERSS trial trench works
Thu (12/09) | 12 Sep 2024 | ST246 |  | B1 reached 22/43.93m
Thu (12/09) | 12 Sep 2024 | ST231 |  | WS installation in progres
Thu (12/09) | 12 Sep 2024 | ST252 |  | B1 in progress. Encountered rock at 30/39.4m
Thu (12/09) | 12 Sep 2024 | ST14 |  | Trimming ongoing
Thu (12/09) | 12 Sep 2024 | ST224A |  | Trimming ongoing
Thu (12/09) | 12 Sep 2024 | P4 |  | Preparation to start pile head hacking works
Thu (12/09) | 12 Sep 2024 | P47 |  | Continue exposing DSTA cable. Target to complete tomorrow
Thu (12/09) | 12 Sep 2024 | ST107 | BC1 | Excavation started
Thu (12/09) | 12 Sep 2024 | P43&P43 |  | HSL boring rig already demobbed
Thu (12/09) | 12 Sep 2024 | MH3-4 |  | Continue excavation for the next layer
Thu (12/09) | 12 Sep 2024 | ST107 |  | 1st bite reached 34m
Thu (12/09) | 12 Sep 2024 | ST105& ST104 |  | Formwork for guidewall
Thu (12/09) | 12 Sep 2024 | BRP77 |  | LSS backfilling. Almost completed
Thu (12/09) | 12 Sep 2024 | BRP50 |  | Hanging bar welding. Today to cast
Thu (12/09) | 12 Sep 2024 | P32 |  | 4nos drilling and 3nos grouting today
Thu (12/09) | 12 Sep 2024 | P31 |  | Manual excavation by KTC and support installation
Thu (12/09) | 12 Sep 2024 | P17 |  | Excavation to FEL
Thu (12/09) | 12 Sep 2024 | P18 |  | Preboring for ERSS installation
Thu (12/09) | 12 Sep 2024 | P14 |  | Concrete plug casting
Thu (12/09) | 12 Sep 2024 | N2 |  | Pump set up for casting
Thu (12/09) | 12 Sep 2024 | P9-1 |  | Column rebar work
Thu (12/09) | 12 Sep 2024 | P11-1 |  | Formwork closing for pier footing. Tomorrow to cast
Thu (12/09) | 12 Sep 2024 | P8-1 |  | Rigid pavement hacking and TT work
Thu (12/09) | 12 Sep 2024 | P4 |  | Pile head hacking work
Thu (12/09) | 12 Sep 2024 | ST252 |  | Loosening of waterstop for removal
Thu (12/09) | 12 Sep 2024 | ST237 |  | 1st bite reached 4.5m
Thu (12/09) | 12 Sep 2024 | ST231 |  | Left two cages to complete. Tonight to cast
Thu (12/09) | 12 Sep 2024 | UKP4 |  | Preparing for casting
Thu (12/09) | 12 Sep 2024 | ST204 |  | Waterstop stopper side trimming
Thu (12/09) | 12 Sep 2024 | MH2-9& MH2-10 |  | Now no activity already
Fri (13/09) | 13 Sep 2024 | P18 |  | ERSS preboring works, 26/50 completed
Fri (13/09) | 13 Sep 2024 | P27 |  | Trial trench ongoing for RW14
Fri (13/09) | 13 Sep 2024 | P17 |  | Prepration to lower mini excavator for FEL excavation works
Fri (13/09) | 13 Sep 2024 | N3 |  | Pier hacking completed yst. Now access erection for rebar installation
Fri (13/09) | 13 Sep 2024 | N2 |  | Crosshead cast last night. Curing works ongoing
Fri (13/09) | 13 Sep 2024 | N1 |  | Continue plywood platform laying works
Fri (13/09) | 13 Sep 2024 | ST102 |  | Cleaning ongoing
Fri (13/09) | 13 Sep 2024 | P45 |  | TT for next point JGP testing
Fri (13/09) | 13 Sep 2024 | P46 |  | Woh hup exposing 22KV to check on shifting
Fri (13/09) | 13 Sep 2024 | P46-47 |  | Exposing of DSTA cable today or tomorrow to complete here
Fri (13/09) | 13 Sep 2024 | P50-4 |  | Toe confirmation. Today to cast
Fri (13/09) | 13 Sep 2024 | P11-1 |  | Preparation works for Pile cap casting today
Fri (13/09) | 13 Sep 2024 | P10-2 |  | Falsework - Portal frame installation works
Fri (13/09) | 13 Sep 2024 | P9-1 |  | Column casting completed
Fri (13/09) | 13 Sep 2024 | P7 |  | VSK to start trial trench for TMH02 today
Fri (13/09) | 13 Sep 2024 | P7 |  | HSL setting up of boring rig and crawler crane mobilization
Fri (13/09) | 13 Sep 2024 | BRP49 |  | Cleaning and desanding completed
Fri (13/09) | 13 Sep 2024 | P5 |  | Exposing traffic light cables for localised shifting
Fri (13/09) | 13 Sep 2024 | P4 |  | Pile head hacking works in progress
Fri (13/09) | 13 Sep 2024 | MH3-4 |  | Manual excavation for next layer caisson
Fri (13/09) | 13 Sep 2024 | P28 |  | RG drilling ongoing for inclinometer installation
Fri (13/09) | 13 Sep 2024 | MH2-9 |  | Currently no activity. Mini excavator broke down, new one coming after lunch
Fri (13/09) | 13 Sep 2024 | MH2-10 |  | WH installing green mesh fencing, LCH fabricating barricade for work area
Fri (13/09) | 13 Sep 2024 | ST102 |  | B2 cleaning ongoing
Fri (13/09) | 13 Sep 2024 | Zone 3 |  | Dongah boring rig no activity. Only maintenance ongoing
Fri (13/09) | 13 Sep 2024 | BRP48 |  | Guidewall construction in progress, BRP49: Rebar cage installed
Fri (13/09) | 13 Sep 2024 | DR1 |  | Inclinometer in wall installation ongoing by RG
Fri (13/09) | 13 Sep 2024 | DR1 |  | CGS continue excavation to strut level
Fri (13/09) | 13 Sep 2024 | P47 |  | Already exposed DSTA cable. Now putting into new pipe in progress
Fri (13/09) | 13 Sep 2024 | P48 |  | Preparing for next stage excavation and backfilling
Fri (13/09) | 13 Sep 2024 | P50-4 |  | Concrete on site for casting
Fri (13/09) | 13 Sep 2024 | P51-4 |  | Casing installation
Fri (13/09) | 13 Sep 2024 | Near blk 2 JTC |  | 66kV already spiked. Now backfilling
Fri (13/09) | 13 Sep 2024 | BP4A-1 | 40 | Now preparing for rebar cage & KP installation
Fri (13/09) | 13 Sep 2024 | ST14 | BC2 | Currently no activity
Fri (13/09) | 13 Sep 2024 | P18 |  | ERSS preboring works, 30/50 completed
Fri (13/09) | 13 Sep 2024 | P17 |  | FEL excavation works
Fri (13/09) | 13 Sep 2024 | N3 |  | Pier rebar bending works in progress
Fri (13/09) | 13 Sep 2024 | N1 |  | Plywood platform laying works
Fri (13/09) | 13 Sep 2024 | P14 |  | Backfilling works ongoing for ERSS extraction
Fri (13/09) | 13 Sep 2024 | P11-1 |  | Pile cap casting works commenced
Fri (13/09) | 13 Sep 2024 | P10 |  | Materials shifting works for primary beam installation
Fri (13/09) | 13 Sep 2024 | P8-1 |  | Trial trench works in progress
Fri (13/09) | 13 Sep 2024 | TMH-02 |  | Trial trench excavation commenced
Fri (13/09) | 13 Sep 2024 | P5 |  | Continue exposing traffic light cables for localised shifting
Fri (13/09) | 13 Sep 2024 | P4 |  | Pile head hacking works in progress. 1/6 nos completed
Fri (13/09) | 13 Sep 2024 | MH3-4 |  | Next layer can cast tomorrow
Fri (13/09) | 13 Sep 2024 | ST102 |  | Desanding in progress
Fri (13/09) | 13 Sep 2024 | BRP49 |  | Hanging bar lowering. Today to cast
Fri (13/09) | 13 Sep 2024 | DR1 |  | 12m length waler installed. GCE continue excavation
Fri (13/09) | 13 Sep 2024 | BRP40 |  | Prepare to start excavation
Fri (13/09) | 13 Sep 2024 | ST194 |  | Pre excavation. BC cutter 3 will excavate this
Fri (13/09) | 13 Sep 2024 | P17 |  | Excavation to FEL
Fri (13/09) | 13 Sep 2024 | N1 |  | Cross head formwork in progress. Now housekeeping
Fri (13/09) | 13 Sep 2024 | P11-1 |  | Pier footing casting
Fri (13/09) | 13 Sep 2024 | P9 |  | Excavation for lean concrete
Fri (13/09) | 13 Sep 2024 | P8 |  | Exposing LV cable. Tonight to check whether life or not
Fri (13/09) | 13 Sep 2024 | Zone 2 |  | HSL crane assembling
Fri (13/09) | 13 Sep 2024 | P5 |  | Traffic light cable exposing
Fri (13/09) | 13 Sep 2024 | P4 |  | Pile head hacking
Fri (13/09) | 13 Sep 2024 | MH3-4 |  | Excavation almost done. Tomorrow to cast
Sat (14/09) | 14 Sep 2024 | STN-252 |  | Last rebar cage lowering in progress
Sat (14/09) | 14 Sep 2024 | STN-237 |  | 1st bite excavation in progress, depth 30m
Sat (14/09) | 14 Sep 2024 | STN-224A |  | 7th rebar cage lowering. 6/8 completed
Sat (14/09) | 14 Sep 2024 | STN-14 |  | Preparing for rebar cage lowering
Sat (14/09) | 14 Sep 2024 | STN-195 |  | 1st bite excavation in progress, depth 11m
Sat (14/09) | 14 Sep 2024 | BRP-40 |  | Excavation temporary stopped due to monitoring panel power issue. Mechanic checking now
Sat (14/09) | 14 Sep 2024 | DR-1 |  | CGS excavation & LE ERSS installation works
Sat (14/09) | 14 Sep 2024 | STN-102 |  | Rebar cage lowering in progress. 4/6 lowered
Sat (14/09) | 14 Sep 2024 | STN-107 |  | 2nd bite excavation, depth 12.5m
Sat (14/09) | 14 Sep 2024 | MH3-4 |  | 4th layer manual excavation in progress. To cast today
Sat (14/09) | 14 Sep 2024 | Gate 7 Loyang Way |  | Krischo excavation works for link up works tonight
Sat (14/09) | 14 Sep 2024 | Zone 4 |  | Power usd backfilling works
Sat (14/09) | 14 Sep 2024 | Zone 4 |  | USD excavation works in progress
Sat (14/09) | 14 Sep 2024 | P51-4 |  | BP boring works in progress, current depth 20m
Sat (14/09) | 14 Sep 2024 | BC3 |  | Maintenance ongoing
Sat (14/09) | 14 Sep 2024 | BRP40 |  | B2 temporarily stopped. Cutter teeth change ongoing
Sat (14/09) | 14 Sep 2024 | P17 |  | Excavation to FEL ongoing
Sat (14/09) | 14 Sep 2024 | P18 |  | Preboring for ERSS installation, 41/50 nos. completed
Sat (14/09) | 14 Sep 2024 | N3 |  | Crosshead Rebar installation works
Sat (14/09) | 14 Sep 2024 | P11-1 |  | Column rebar cage fabrication
Sat (14/09) | 14 Sep 2024 | P11-1 |  | Pile cap cast yst
Sat (14/09) | 14 Sep 2024 | N1 |  | Plywood platform laying completed. Now preparing scaffold for pier hacking to correct level
Sat (14/09) | 14 Sep 2024 | P10 |  | Falsework erection works
Sat (14/09) | 14 Sep 2024 | P9-1 |  | Column cast yst
Sat (14/09) | 14 Sep 2024 | TMH-02 |  | VSK continue excavation works
Sat (14/09) | 14 Sep 2024 | P7 |  | HSL boring rig setting up works
Sat (14/09) | 14 Sep 2024 | P5 |  | Exposing of traffic light cables for localize shifting
Sat (14/09) | 14 Sep 2024 | P4 |  | Pile head hacking works, 2/6 completed
Sat (14/09) | 14 Sep 2024 | MH2-9 |  | Excavation & hacking works for 12th layer
Sat (14/09) | 14 Sep 2024 | STN-252 |  | Tremie pipe lowered. Preparing for casting
Sat (14/09) | 14 Sep 2024 | STN-237 |  | 1st bite excavation in progress, depth 38m
Sat (14/09) | 14 Sep 2024 | STN-14 |  | Rebar cage lowered. Hanging bar lowering in progress
Sat (14/09) | 14 Sep 2024 | UKP-05 |  | Boring work in progress
Sat (14/09) | 14 Sep 2024 | STN-224A |  | Rebar cages fully lowered. Now preparing for tremie pipe installation
Sat (14/09) | 14 Sep 2024 | Exit 2 |  | Leychoon excavation for tonight water pipe capping works
Sat (14/09) | 14 Sep 2024 | STN-205 to STN-207 1/2 |  | Excavation for Guidewall works
Sat (14/09) | 14 Sep 2024 | STN-195 |  | 1st bite excavation in progress, depth 21m
Sat (14/09) | 14 Sep 2024 | DR-1 |  | CGS excavation & LE ERSS installation works
Sat (14/09) | 14 Sep 2024 | STN-102 |  | Last Rebar cage lapping and lowering in progress. 5/6 lowered
Sat (14/09) | 14 Sep 2024 | STN-107 |  | 2nd bite excavation, depth 18m
Sat (14/09) | 14 Sep 2024 | STN-109 |  | Excavation for removal of abandoned 700mm water pipe and manhole
Sat (14/09) | 14 Sep 2024 | MH3-4 |  | 4th layer BRC rebar installed. Preparing for Formwork closing
Sat (14/09) | 14 Sep 2024 | Gate 7 Loyang Way |  | Krishco continue exposing the existing and new water pipe for link up works tonight
Sat (14/09) | 14 Sep 2024 | P44 |  | Leychoon Exposing for 2nd water pipe cap off location
Sat (14/09) | 14 Sep 2024 | Zone 4 |  | JGP testing ongoing for Pt No. C24
Sat (14/09) | 14 Sep 2024 | Zone 4 |  | Preparing for concrete haunching casting for shifted army cables
Sat (14/09) | 14 Sep 2024 | Zone 4 |  | USD shoring works in progress
Sat (14/09) | 14 Sep 2024 | P51-4 |  | BP boring works in progress, current depth 22.5m
Sat (14/09) | 14 Sep 2024 | P17 |  | Continue excavation to FEL
Sat (14/09) | 14 Sep 2024 | P18 |  | Preboring for ERSS installation, 48/50 nos. completed. Today to complete preboring works
Sat (14/09) | 14 Sep 2024 | N3 |  | Crosshead Rebar installation works
Sat (14/09) | 14 Sep 2024 | P14 |  | Struts dismantle and removal works
Sat (14/09) | 14 Sep 2024 | N1 |  | Pier hacking to correct level ongoing
Sat (14/09) | 14 Sep 2024 | P11-1 |  | Column rebar cage fabrication
Sat (14/09) | 14 Sep 2024 | P10 |  | Continue Falsework erection works
Sat (14/09) | 14 Sep 2024 | P9-1 |  | Scaffold dismantle works
Sat (14/09) | 14 Sep 2024 | P8-1 |  | Trial trench completed. Backfilling in progress
Sat (14/09) | 14 Sep 2024 | TMH-02 |  | VSK continue excavation works
Sat (14/09) | 14 Sep 2024 | P7 |  | HSL boring rig assembled. AE inspection at 6.30pm today
Sat (14/09) | 14 Sep 2024 | P5 |  | Exposing of traffic light cables for localized shifting completed
Sat (14/09) | 14 Sep 2024 | P4 |  | Continue pile head hacking works, 5/6 nos. completed
Sat (14/09) | 14 Sep 2024 | P44 area |  | D3 shut
Sat (14/09) | 14 Sep 2024 | Loyang Way | near exit 1-gate 7 | Now cutting existing water pipe for linkup works
Sat (14/09) | 14 Sep 2024 | Linkup point near DR1 |  | In progress
Sun (15/09) | 15 Sep 2024 | ST102 |  | Casting in progress 206/268m3
Sun (15/09) | 15 Sep 2024 | ST107 |  | 2nd bite reached 37.1m
Sun (15/09) | 15 Sep 2024 | DR1 |  | LE provide 7 workers. Welding of waler beam joint and utility support
Sun (15/09) | 15 Sep 2024 | DR1 |  | CGS provide 7 workers for excavation
Sun (15/09) | 15 Sep 2024 | ST195 |  | 1st bite, reached 28.8m. Now cutter holder welding
Sun (15/09) | 15 Sep 2024 | BC cutter 4 |  | No work today. No operator
Sun (15/09) | 15 Sep 2024 | ST246 |  | Bachy lowering down tremie pipe. Will cast after lunch
Sun (15/09) | 15 Sep 2024 | P14 |  | Waler and brackets removal
Sun (15/09) | 15 Sep 2024 | N1 |  | Column trimming to correct level
Sun (15/09) | 15 Sep 2024 | P11-1 |  | Surface roughening for column work
Sun (15/09) | 15 Sep 2024 | P10-2 |  | False work erection
Sun (15/09) | 15 Sep 2024 | ST107 |  | B2 in progress, 30.8/39m
Sun (15/09) | 15 Sep 2024 | ST224A |  | Casting in progress, 179/249m3
Sun (15/09) | 15 Sep 2024 | ST246 |  | WS installation ongoing
Sun (15/09) | 15 Sep 2024 | ST237 |  | B1 in progress
Sun (15/09) | 15 Sep 2024 | ST232 |  | Preparing for excavation
Sun (15/09) | 15 Sep 2024 | P44 |  | Capping point done. Pending thrust block haunching
Sun (15/09) | 15 Sep 2024 | P17 |  | Excavation to FEL
Sun (15/09) | 15 Sep 2024 | N6 |  | Woh hup removal of materials and levelling for retaining wall
Sun (15/09) | 15 Sep 2024 | N3 |  | Cross head rebar work
Sun (15/09) | 15 Sep 2024 | N1 |  | Column trimming to correct level
Sun (15/09) | 15 Sep 2024 | P14 |  | Pile head backing
Sun (15/09) | 15 Sep 2024 | ST195 |  | Resume excavation
Sun (15/09) | 15 Sep 2024 | DR1 |  | LE continue waler joint welding
Sun (15/09) | 15 Sep 2024 | ST107 |  | Continue boring work
Sun (15/09) | 15 Sep 2024 | ST107 |  | B2 temporarily stopped for cutter teeth change. CD 35/39m
Sun (15/09) | 15 Sep 2024 | BRP51 |  | P1 preboring in progress
Sun (15/09) | 15 Sep 2024 | ST195 | BC3 | B1 in progress
Sun (15/09) | 15 Sep 2024 | ST14 |  | Casting in progress
Sun (15/09) | 15 Sep 2024 | ST224A |  | Casting completed
Sun (15/09) | 15 Sep 2024 | ST246 |  | Rebar cage installation in progress
Sun (15/09) | 15 Sep 2024 | P46 |  | Woh Hup installation of utility protection for bored pile work
Mon (16/09) | 16 Sep 2024 | P51-4 |  | Casting completed
Mon (16/09) | 16 Sep 2024 | P18 |  | ERSS installation works in progress
Mon (16/09) | 16 Sep 2024 | P17 |  | Excavation to FEL
Mon (16/09) | 16 Sep 2024 | P45 |  | GCE preparing to shift rig to P44
Mon (16/09) | 16 Sep 2024 | P46 |  | 22KV protection done. Left for water pipe
Mon (16/09) | 16 Sep 2024 | P48-49 |  | Duct laying. Today to cast, 15m
Mon (16/09) | 16 Sep 2024 | P51-4 |  | Boring to toe. Today to cast
Mon (16/09) | 16 Sep 2024 | MH3-4 |  | Excavation for next layer caisson
Mon (16/09) | 16 Sep 2024 | N3 |  | Crosshead rebar installation
Mon (16/09) | 16 Sep 2024 | P14 |  | Extraction of waler & strut completed. Backfilling in progress
Mon (16/09) | 16 Sep 2024 | P11-1 |  | Column rebar cage fabrication
Mon (16/09) | 16 Sep 2024 | N1 |  | Pier hacking to correct level
Mon (16/09) | 16 Sep 2024 | P11-1 |  | Rebar installation for column stump
Mon (16/09) | 16 Sep 2024 | P10 |  | Falseworks - primary beams installation
Mon (16/09) | 16 Sep 2024 | TMH-02 |  | VSK continue excavation works for TMH
Mon (16/09) | 16 Sep 2024 | P8 |  | Boring rig pending AE inspection. Today to carry out AE inspection
Mon (16/09) | 16 Sep 2024 | P8 |  | 3 nos. of Rebar cages for P8 BP delivered
Mon (16/09) | 16 Sep 2024 | P4 |  | Pile head hacking completed, Hardcores clearing in progress
Mon (16/09) | 16 Sep 2024 | BRP48 |  | Preparing to start excavation. Preboring was done
Mon (16/09) | 16 Sep 2024 | ST107 |  | Cleaning on going
Mon (16/09) | 16 Sep 2024 | ST108half and ST109 |  | Guidewall rebar work
Mon (16/09) | 16 Sep 2024 | P44 |  | TT by GCE. Tomorrow start JGP testing with two machines
Mon (16/09) | 16 Sep 2024 | P17 |  | Excavation to FEL
Mon (16/09) | 16 Sep 2024 | P18 |  | ERSS installation
Mon (16/09) | 16 Sep 2024 | P10 |  | Falsework erection
Mon (16/09) | 16 Sep 2024 | N1 |  | Hacking of column to correct level
Mon (16/09) | 16 Sep 2024 | P4 |  | Hardcore clear. Now levelling
Mon (16/09) | 16 Sep 2024 | P1 |  | Road premix removal. Now already end work
Mon (16/09) | 16 Sep 2024 | P17 |  | Excavation to FEL continue till 10pm
Mon (16/09) | 16 Sep 2024 | P10 |  | Falsework installation almost done for the day
Mon (16/09) | 16 Sep 2024 | ST237 |  | B2 in progress
Mon (16/09) | 16 Sep 2024 | ST232 |  | B1 in progress
Mon (16/09) | 16 Sep 2024 | ST210 | BC2 | B1 in progress, 39/40m
Mon (16/09) | 16 Sep 2024 | BRP48 |  | Excavation in progress, BRP51: Rebar cage lowered. Pending KP installation
Mon (16/09) | 16 Sep 2024 | BC1 |  | Machine maintenance ongoing
Mon (16/09) | 16 Sep 2024 | Exit 1 |  | Hacking and excavation for internal drain pipe installation towards ECM pond
Mon (16/09) | 16 Sep 2024 | P48 |  | Utility duct haunching completed. Levelling ongoing
Mon (16/09) | 16 Sep 2024 | P51-4 |  | Casting in progress, 32/40m3. Balance 1 more truck
Tue (17/09) | 17 Sep 2024 | P17 |  | Excavation to FEL ongoing. Target to complete today
Tue (17/09) | 17 Sep 2024 | P18 |  | ERSS installation for steel plate in progress. Soldier pile installation completed
Tue (17/09) | 17 Sep 2024 | N6 |  | Excavation in progress for retaining wall base slab
Tue (17/09) | 17 Sep 2024 | N3 |  | Crosshead rebar & ducting installation
Tue (17/09) | 17 Sep 2024 | P14 |  | Backfilling & compaction works completed
Tue (17/09) | 17 Sep 2024 | N1 |  | Pier hacking till correct level in progress
Tue (17/09) | 17 Sep 2024 | P11-1 |  | Column rebar cage fabrication completed
Tue (17/09) | 17 Sep 2024 | P10 |  | Falsework - secondary beams installation
Tue (17/09) | 17 Sep 2024 | P11-1 |  | Formwork closing for column stump
Tue (17/09) | 17 Sep 2024 | TMH-02 |  | VSK trial trench completed for TMH-02. Excavation & levelling works in progress
Tue (17/09) | 17 Sep 2024 | P8 |  | Boring rig / Crane pending AE inspection. Target to complete inspection today
Tue (17/09) | 17 Sep 2024 | ST107 |  | 6/8 cages lowering down. Tonight to cast
Tue (17/09) | 17 Sep 2024 | Zone 1 |  | Sump pit excavation completed. To cast today
Tue (17/09) | 17 Sep 2024 | Zone 1 |  | Soil inspection tower scaffold erection
Tue (17/09) | 17 Sep 2024 | P4 |  | Pile cap bottom rebar installation in progress
Tue (17/09) | 17 Sep 2024 | P43 |  | SPT44 & C33 JGP testing work in progress
Tue (17/09) | 17 Sep 2024 | MH3-4 |  | Support installation
Tue (17/09) | 17 Sep 2024 | ST210 |  | B2 in progress
Tue (17/09) | 17 Sep 2024 | ST203 |  | B1 in progress, 14/34.2m
Tue (17/09) | 17 Sep 2024 | BRP40 |  | Preboring ongoing
Tue (17/09) | 17 Sep 2024 | BRP48 |  | Excavation in progress, 24.8/27.07m
Tue (17/09) | 17 Sep 2024 | BRP51 |  | Ready for casting
Tue (17/09) | 17 Sep 2024 | ST107 |  | Preparing for rebar cage lowering
Tue (17/09) | 17 Sep 2024 | ST232 |  | B2 in progress, 10/40.7m
Tue (17/09) | 17 Sep 2024 | ST237 |  | B2 in progress, 37/40.57m
Tue (17/09) | 17 Sep 2024 | P45 |  | Checking of water pipe protection area was done. Will mix quarry dust with cement to strengthen the area. Bored pile area will backfill with LSS
Tue (17/09) | 17 Sep 2024 | MH3-4 |  | Pipe supporting was done
Tue (17/09) | 17 Sep 2024 | DR1 |  | LE &CGS working until 10PM
Tue (17/09) | 17 Sep 2024 | BC cutter 2 |  | Night shift take over from day shift
Tue (17/09) | 17 Sep 2024 | MH2-9 |  | 12layer caisson formwork closed. Waiting for concrete. Tonight to cast
Wed (18/09) | 18 Sep 2024 | P45 |  | Premix removal to shift DSTA cable that affecting column
Wed (18/09) | 18 Sep 2024 | MH2-9 |  | Hacking and excavation ongoing for last layer (13th)
Wed (18/09) | 18 Sep 2024 | MH2-10 |  | Works for 1st layer started
Wed (18/09) | 18 Sep 2024 | P17 |  | Excavation to FEL and levelling works ongoing
Wed (18/09) | 18 Sep 2024 | P18 |  | ERSS installation completed. ERSS to further embed into the ground in progress
Wed (18/09) | 18 Sep 2024 | N3 |  | Crosshead rebar and ducting installation
Wed (18/09) | 18 Sep 2024 | P29 |  | Geomotion rig maintenance ongoin
Wed (18/09) | 18 Sep 2024 | P30 |  | Water standpipe installation ongoing by RG
Wed (18/09) | 18 Sep 2024 | P14 |  | Levelling and preparation works in progress for column rebar installation tmr
Wed (18/09) | 18 Sep 2024 | N1 |  | Pier hacking to correct level
Wed (18/09) | 18 Sep 2024 | P11-1 |  | Scaffold erection for column stump casting
Wed (18/09) | 18 Sep 2024 | P10 |  | C-channel installation works ongoing
Wed (18/09) | 18 Sep 2024 | P8-1-5 |  | HSL BP Boring work in progress, current depth 12m
Wed (18/09) | 18 Sep 2024 | P31 area |  | Manual clearing of soil at existing services area
Wed (18/09) | 18 Sep 2024 | ST103 |  | B1 in progress, 31.5/34m
Wed (18/09) | 18 Sep 2024 | BRP55 |  | Trial trench
Wed (18/09) | 18 Sep 2024 | BRP48 |  | Rebar cage installation
Wed (18/09) | 18 Sep 2024 | DR1 |  | CGS continue excavation, LE continue waler bracket welding. Currently crane breakdown & rectification ongoing. Will continue waler installation once rectification done
Wed (18/09) | 18 Sep 2024 | BRP43 |  | Guidewall rebar works ongoing
Wed (18/09) | 18 Sep 2024 | BC4 |  | Cutter teeth rectification ongoing. This machine will start for BRP40 excavation
Wed (18/09) | 18 Sep 2024 | TMH-02 |  | VSK continue excavation and levelling works for manhole construction
Wed (18/09) | 18 Sep 2024 | Zone 1 |  | P1 ECM sump pit completed yst
Wed (18/09) | 18 Sep 2024 | P1 |  | Preparation to start premix hacking for trial trench works
Wed (18/09) | 18 Sep 2024 | P4 |  | Rebar installation for pile cap
Wed (18/09) | 18 Sep 2024 | ST247 |  | B1 in progress, 25/47.92m
Wed (18/09) | 18 Sep 2024 | ST232 |  | B2 in progress
Wed (18/09) | 18 Sep 2024 | ST237 |  | Rebar cage installation temporarily stopped. Current status: 6/10nos lowered, Crane auxiliary hook maintenance ongoing
Wed (18/09) | 18 Sep 2024 | ST103 |  | B1 completed. Now ongoing B2 excavation
Wed (18/09) | 18 Sep 2024 | P47 |  | Woh hup exposing water pipe for protection
Wed (18/09) | 18 Sep 2024 | P45 |  | Wee Guan exposing DSTA cable for shifting
Wed (18/09) | 18 Sep 2024 | P45 TPE |  | Last pile boring in progress. Tomorrow to cast
Wed (18/09) | 18 Sep 2024 | P17 |  | Exacation to FEL completed. Levelling works in progress
Wed (18/09) | 18 Sep 2024 | Bet. P15-P14 |  | LE materials shifting to P44 and boring rig dismantle works in progress
Wed (18/09) | 18 Sep 2024 | N3 |  | Crosshead rebar and ducting works
Wed (18/09) | 18 Sep 2024 | P14 |  | Preparation for concrete blocks laying for column rebar installation tmr
Wed (18/09) | 18 Sep 2024 | N1 |  | Continue pier hacking to correct level
Wed (18/09) | 18 Sep 2024 | P11-1 |  | Scaffold erection for casting works
Wed (18/09) | 18 Sep 2024 | P10 |  | Continue falsework erection
Wed (18/09) | 18 Sep 2024 | P36-37 |  | Abandoned drain hacking ongoin
Wed (18/09) | 18 Sep 2024 | DR1 |  | Waler beam installation ongoing
Wed (18/09) | 18 Sep 2024 | BRP43 |  | Guidewall formwork in progress
Wed (18/09) | 18 Sep 2024 | ST203 | BC3 | B2 excavation temporarily stopped due to mud hose leaking. Rectification ongoing
Wed (18/09) | 18 Sep 2024 | ST205-206 |  | Guidewall formwork dismantling
Wed (18/09) | 18 Sep 2024 | MH3-4 |  | Lehoboth addressing comment for changes of drawing. Tomorrow plan to settle
Wed (18/09) | 18 Sep 2024 | P44 |  | Continue testing of two JGP points
Wed (18/09) | 18 Sep 2024 | BP4A-1 | 41 | KP lowering in progress
Wed (18/09) | 18 Sep 2024 | MH2-9 |  | Continue hacking for 13th layer
Wed (18/09) | 18 Sep 2024 | MH2-10 |  | Hardcore clearing ongoing
Wed (18/09) | 18 Sep 2024 | TMH-02 |  | VSK levelling works ongoing, preparing for slope lean concrete
Wed (18/09) | 18 Sep 2024 | P8-1-5 |  | BP boring completed. Preparing for rebar cages lowering
Wed (18/09) | 18 Sep 2024 | P1 |  | Premix hacking for trial trench works
Wed (18/09) | 18 Sep 2024 | P4 |  | Continue pile cap rebar installation works
Wed (18/09) | 18 Sep 2024 | BRP43 |  | Tonight plan to cast the guidewall
Wed (18/09) | 18 Sep 2024 | DR1 |  | CGS continue excavation until 10PM
Wed (18/09) | 18 Sep 2024 | BRP48 |  | Tonight plan to cast
Wed (18/09) | 18 Sep 2024 | ST108 |  | 2nd bite, reached 13m
Wed (18/09) | 18 Sep 2024 | P45-4 |  | Continue boring. Tomorrow plan to cast
Wed (18/09) | 18 Sep 2024 | P45 |  | Current status of exposing DSTA cable. Wee Guan already end work
Wed (18/09) | 18 Sep 2024 | BRP40 |  | Hoses connection. Tonight to resume excavation
Wed (18/09) | 18 Sep 2024 | ST195 |  | 2nd bite, reached 24.4m
Wed (18/09) | 18 Sep 2024 | ST203 |  | 2nd bite, reached 31m. Now cutter body bring up to change teeth
Wed (18/09) | 18 Sep 2024 | BP41 |  | Concrete on site for casting
Wed (18/09) | 18 Sep 2024 | DR4 |  | Exposing DSTA cable around 30m distance. Will raise up from 1.3m to 600mm for DR4 work
Thu (19/09) | 19 Sep 2024 | ST103 |  | B2 in progress, 33/34m
Thu (19/09) | 19 Sep 2024 | P17 |  | HSL excavator lowered for pile head hacking. Preparation for pile head cutting ongoing
Thu (19/09) | 19 Sep 2024 | BRP44 |  | Preboring ongoing
Thu (19/09) | 19 Sep 2024 | DR1 |  | CGS continue excavation, LE continue waler welding works
Thu (19/09) | 19 Sep 2024 | BRP40 |  | Excavation temporarily stopped. Cutter teeth changing ongoing, CD 21.6/25.07m
Thu (19/09) | 19 Sep 2024 | N3 |  | Rebar installation completed. Ducting installation works ongoing
Thu (19/09) | 19 Sep 2024 | P14 |  | Preparation for column rebar installation. Afternoon to install
Thu (19/09) | 19 Sep 2024 | Zone 2 |  | LE boring rig dismantle and shifting to P44
Thu (19/09) | 19 Sep 2024 | Zone 2 |  | Viaduct Formwork unloading
Thu (19/09) | 19 Sep 2024 | N1 |  | Continue pier hacking to correct level. Today to complete
Thu (19/09) | 19 Sep 2024 | P45-4 |  | Boring to toe. Today to cast
Thu (19/09) | 19 Sep 2024 | P45 |  | Wee Guan exposing DSTA cable
Thu (19/09) | 19 Sep 2024 | P44 |  | GCE continue testing of 2 JGP points
Thu (19/09) | 19 Sep 2024 | MH3-4 |  | Plan to get endorsement for changes by today. To resume tomorrow
Thu (19/09) | 19 Sep 2024 | P11-1 |  | Scaffold erection for column stump casting in progress. To cast today
Thu (19/09) | 19 Sep 2024 | P10 |  | Falsework erection current status
Thu (19/09) | 19 Sep 2024 | TMH-02 |  | Continue excavation and slope levelling for manhole works
Thu (19/09) | 19 Sep 2024 | P7-1-5 |  | HSL BP boring works in progress. Yesterday cast P8-1-5
Thu (19/09) | 19 Sep 2024 | MH2-9 |  | Currently no activity. Current mini excavator will be replaced with a new one after lunch (already on site)
Thu (19/09) | 19 Sep 2024 | MH2-10 |  | Manual excavation and clearing works for 1st layer
Thu (19/09) | 19 Sep 2024 | P4 |  | Pile cap rebar & formwork installation
Thu (19/09) | 19 Sep 2024 | P1 |  | Premix hacking for trial trench works
Thu (19/09) | 19 Sep 2024 | ST103 |  | B2 completed. Now ongoing B3, 25/24m
Thu (19/09) | 19 Sep 2024 | BRP54, BRP55 |  | Trial trench
Thu (19/09) | 19 Sep 2024 | P47 |  | Continue DSTA manhole removal
Thu (19/09) | 19 Sep 2024 | P45 |  | Continue exposing DSTA cable for shifting
Thu (19/09) | 19 Sep 2024 | MH3-5 |  | Lehoboth preparing to address PE comment tomorrow target to resume excavation. This week to cast one ring
Thu (19/09) | 19 Sep 2024 | P44 |  | CR105 witness the testing
Thu (19/09) | 19 Sep 2024 | P44 |  | LE mobilising kelly bar and rig for preboring
Thu (19/09) | 19 Sep 2024 | P31 area |  | Manual excavation at existing utilities area
Thu (19/09) | 19 Sep 2024 | BRP44 |  | Preboring ongoing
Thu (19/09) | 19 Sep 2024 | DR1 |  | Wall hacking ongoing to facilitate ERSS installation
Thu (19/09) | 19 Sep 2024 | BRP40 |  | Excavation in progress, 21.8/25.07m
Thu (19/09) | 19 Sep 2024 | ST195 |  | Endplate extraction ongoing
Thu (19/09) | 19 Sep 2024 | P17 |  | Pile head hacking ongoing
Thu (19/09) | 19 Sep 2024 | P14 |  | Column rebar installed
Thu (19/09) | 19 Sep 2024 | P11 |  | Stump casting ongoing
Thu (19/09) | 19 Sep 2024 | P7-1-5 |  | Casting ongoing
Thu (19/09) | 19 Sep 2024 | BP2A-1, 1600mm dia | 21 | Preboring started at 1720hrs
Thu (19/09) | 19 Sep 2024 | DR1 |  | LE preparing 2nos struts for installation, Waler welding ongoing
Thu (19/09) | 19 Sep 2024 | BRP44 |  | Preboring ongoing
Thu (19/09) | 19 Sep 2024 | P29 |  | Geomotion rig maintenance ongoing
Thu (19/09) | 19 Sep 2024 | BRP51 |  | LSS backfill
Fri (20/09) | 20 Sep 2024 | N2 |  | Formwork dismantle ongoing
Fri (20/09) | 20 Sep 2024 | P11-1 |  | Column stump cast yesterday
Fri (20/09) | 20 Sep 2024 | P10 |  | Falsework erection (C-channel) in progress
Fri (20/09) | 20 Sep 2024 | P9-1 |  | ERSS (soldier piles) extraction works ongoing
Fri (20/09) | 20 Sep 2024 | TMH-02 |  | VSK continue excavation and levelling works for MH construction
Fri (20/09) | 20 Sep 2024 | P6 |  | HSL Area Preparation for boring rig to shift to P6 for bored piling
Fri (20/09) | 20 Sep 2024 | P4 |  | Shear links and formwork closing for pile cap. Target to cast tmr
Fri (20/09) | 20 Sep 2024 | P1 |  | Continue premix hacking and clearing for trial trench works
Fri (20/09) | 20 Sep 2024 | P47 |  | Preparation for water pipe coating and steel plate installation
Fri (20/09) | 20 Sep 2024 | P46-2 |  | BP preparation works
Fri (20/09) | 20 Sep 2024 | P45 |  | Manual excavation in progress for army cables shifting
Fri (20/09) | 20 Sep 2024 | P43 | C42 & SPT42 | Trial trench completed, drilling works in progress
Fri (20/09) | 20 Sep 2024 | MH3-4 |  | Currently no activity
Fri (20/09) | 20 Sep 2024 | P18 |  | KTC excavation to s1 layer in progress
Fri (20/09) | 20 Sep 2024 | P17 |  | Pile head hacking ongoing, 5/6 nos. completed
Fri (20/09) | 20 Sep 2024 | N2 |  | Continue formwork dismantle works
Fri (20/09) | 20 Sep 2024 | P10 |  | Falsework erection (C-channel) and netting installation in progress. Scaffold erection ongoing
Fri (20/09) | 20 Sep 2024 | P9-1 |  | ERSS (soldier piles) extraction works
Fri (20/09) | 20 Sep 2024 | TMH-02 |  | VSK continue excavation and levelling works for MH construction
Fri (20/09) | 20 Sep 2024 | P6-1-5 |  | BP boring works in progress, current depth 8m. Casing installed
Fri (20/09) | 20 Sep 2024 | P4 |  | Pile cap rebar & Formwork closing works
Fri (20/09) | 20 Sep 2024 | P1 |  | Trial trench works started
Fri (20/09) | 20 Sep 2024 | P45 |  | Continue manual excavation for army cables shifting
Fri (20/09) | 20 Sep 2024 | P46-2 |  | Preboring finished and casing installed. To continue boring works
Fri (20/09) | 20 Sep 2024 | P47 |  | Water pipe coating completed now preparing for steel plate installation
Fri (20/09) | 20 Sep 2024 | P43 | C42 & SPT42 | SPT & Coring tests in progress
Fri (20/09) | 20 Sep 2024 | P43 |  | LE boring rig and Kelly bar delivered on site
Fri (20/09) | 20 Sep 2024 | P18 |  | ERSS installation completed. KTC to start excavation to s1 layer
Fri (20/09) | 20 Sep 2024 | P17 |  | Pile head hacking ongoing, 3/6 nos. completed
Fri (20/09) | 20 Sep 2024 | N3 |  | Debris cleaning works for crosshead ongoing
Fri (20/09) | 20 Sep 2024 | P14 |  | Column rebar cage installed yesterday
Fri (20/09) | 20 Sep 2024 | N1 |  | Hacking works completed yst. Scaffold erection in progress for rebar installation works
Mon (23/09) | 23 Sep 2024 | MH2-9 |  | 13th layer excavation ongoing. Plan to cast today
Mon (23/09) | 23 Sep 2024 | N3 |  | PLT in progress, 3rd cylce in progress
Mon (23/09) | 23 Sep 2024 | MH2-10 |  | Currently no activity. First layer has been cast
Mon (23/09) | 23 Sep 2024 | P45-2 |  | Boring in progress, reached 20m. Now encounter rock and start coring
Mon (23/09) | 23 Sep 2024 | P46 |  | JGP testing with both rigs. Witness by 105
Mon (23/09) | 23 Sep 2024 | P48-P49 |  | Pipe installation for power duct. Today plan to lean concrete for complete excavation area
Mon (23/09) | 23 Sep 2024 | DR2 |  | Exposing trench for utility stump works
Mon (23/09) | 23 Sep 2024 | ST105 |  | B2 in progress, 38/39m
Mon (23/09) | 23 Sep 2024 | P44 |  | Preparing for rig set up
Mon (23/09) | 23 Sep 2024 | MH3-5 |  | Base rebar done. Plan to cast permanent base slab tomorrow or the day after tomorrow
Mon (23/09) | 23 Sep 2024 | P44 |  | TT on going by LE
Mon (23/09) | 23 Sep 2024 | P10 portal frame |  | Scaffold access and railing installation
Mon (23/09) | 23 Sep 2024 | DR1 |  | Scaffold erection for instrument monitoring
Mon (23/09) | 23 Sep 2024 | DR1 |  | CGS continue excavation for next section of strutting works
Mon (23/09) | 23 Sep 2024 | DR1 |  | CGS manual excavation near Singtel haunching
Mon (23/09) | 23 Sep 2024 | P33 |  | KTC continue exposing services here for utility support works
Mon (23/09) | 23 Sep 2024 | BRP40 | BC4 | Excavation temporarily stopped. BC4 pulley rectification ongoing. B2 completed, B1 CD 17.1/25.07m
Mon (23/09) | 23 Sep 2024 | BRP43 |  | Rebar cage lowered
Mon (23/09) | 23 Sep 2024 | ST205 | BC2 | B1 in progress
Mon (23/09) | 23 Sep 2024 | ST23A |  | B1 excavation started
Mon (23/09) | 23 Sep 2024 | BP2A-1 | 21 | Boring reached 33/45.624m
Mon (23/09) | 23 Sep 2024 | ST238 |  | B1 in progress
Mon (23/09) | 23 Sep 2024 | ST242 |  | Excavation temporarily stopped. Machine rectification ongoing
Mon (23/09) | 23 Sep 2024 | ST247 |  | Casting in progress
Mon (23/09) | 23 Sep 2024 | P44 |  | Assembling of boring rig
Mon (23/09) | 23 Sep 2024 | P17 |  | Pile head trimming ongoing
Mon (23/09) | 23 Sep 2024 | P18 |  | Angle bracket welding in progress
Mon (23/09) | 23 Sep 2024 | N2 |  | Formwork dismantling
Mon (23/09) | 23 Sep 2024 | P10 portal frame |  | Scaffold access & railing installation ongoing
Mon (23/09) | 23 Sep 2024 | P8-1-2 |  | Casting
Mon (23/09) | 23 Sep 2024 | S4 |  | Abutment wall rebar works and hacking ongoing
Mon (23/09) | 23 Sep 2024 | ST247 |  | Casting in progress, 224/360m3
Mon (23/09) | 23 Sep 2024 | ST242 |  | Machine swivel rectification ongoing
Mon (23/09) | 23 Sep 2024 | ST238 |  | Continue B1 trenching
Mon (23/09) | 23 Sep 2024 | BP2A-1 | 21 | Boring reached 34/45.624m
Mon (23/09) | 23 Sep 2024 | ST222 |  | Hacking ongoing for guidewall works
Mon (23/09) | 23 Sep 2024 | ST23A |  | B1 in progress
Mon (23/09) | 23 Sep 2024 | TDP80 |  | Casing installed
Tue (24/09) | 24 Sep 2024 | Zone 3 |  | Utility stump rebar fabrication
Tue (24/09) | 24 Sep 2024 | TDP80 |  | Verticality and depth check
Tue (24/09) | 24 Sep 2024 | ST105 |  | Trimming in progress
Tue (24/09) | 24 Sep 2024 | P48-P48 |  | Yesterday cast 3m length of duct. Today to continue 9m length and casting
Tue (24/09) | 24 Sep 2024 | P47 |  | Working platform prepare for bored pile work
Tue (24/09) | 24 Sep 2024 | P45-2 |  | Boring in progress. Today to cast
Tue (24/09) | 24 Sep 2024 | MH3-5 |  | Base slab rebar work in progress
Tue (24/09) | 24 Sep 2024 | BRP53 |  | Excavation for guidewall
Tue (24/09) | 24 Sep 2024 | DR1 |  | CGS continue excavation for next section of strutting works. Can complete by tmr
Tue (24/09) | 24 Sep 2024 | P10 |  | Plywood laying works in progress
Tue (24/09) | 24 Sep 2024 | P7-1-2 |  | BP boring works in progress, depth 13m
Tue (24/09) | 24 Sep 2024 | MH2-9 |  | Layer 13 cast yesterday. Now ongoing hacking for base slab
Tue (24/09) | 24 Sep 2024 | MH2-10 |  | Barricade installation ongoing. Thereafter to proceed manual excavation for next layer
Tue (24/09) | 24 Sep 2024 | P44 |  | Rig assembly. Today to complete. Continue TT
Tue (24/09) | 24 Sep 2024 | Zone 1 |  | Eng hup now here for traffic cable shifting
Tue (24/09) | 24 Sep 2024 | Blk 2 |  | Geomotion continue trial trench for recharge well, RW7. Yesterday completed RW6
Tue (24/09) | 24 Sep 2024 | P48-P49 |  | Preparing to cast 9m lengtj of duct
Tue (24/09) | 24 Sep 2024 | P31 |  | Manual excavation below SPPG haunching
Tue (24/09) | 24 Sep 2024 | DR2 |  | Excavation for utility stump works
Tue (24/09) | 24 Sep 2024 | ST105 |  | Continue trimming
Tue (24/09) | 24 Sep 2024 | BRP53 |  | Guidewall construction in progress
Tue (24/09) | 24 Sep 2024 | DR1 |  | Continue excavation
Tue (24/09) | 24 Sep 2024 | BC4 |  | Fixing hydraulic hose
Tue (24/09) | 24 Sep 2024 | TMH2 |  | Sump pit formwork installation
Tue (24/09) | 24 Sep 2024 | P10 |  | Plywood laying for working platform
Tue (24/09) | 24 Sep 2024 | ST23A |  | B2 in progress, 17.7/37.72m
Tue (24/09) | 24 Sep 2024 | BP2A-1 | 21 | Boring reached 38/45.624m
Tue (24/09) | 24 Sep 2024 | ST238 |  | Waiting for BC cutter
Tue (24/09) | 24 Sep 2024 | ST242 |  | B1 completed. Now cutter body up for depth checking
Tue (24/09) | 24 Sep 2024 | MH2-9 |  | Target to cast base slab tmr
Tue (24/09) | 24 Sep 2024 | MH3-5 |  | Caisson wall rebar work in progress
Tue (24/09) | 24 Sep 2024 | P45-2 |  | Rebar cages lowering down. Today to cast
Tue (24/09) | 24 Sep 2024 | P44 |  | TT for ERSS work
Tue (24/09) | 24 Sep 2024 | MH2-10 |  | Singtel haunching exposed. Manual excavation to be done
Tue (24/09) | 24 Sep 2024 | ST23A |  | 2nd bite trenching continue, 33m depth
Tue (24/09) | 24 Sep 2024 | BP2A-1 | 21 | Boring continue at 39/45.624m
Tue (24/09) | 24 Sep 2024 | BC2 |  | Teeth replacement to start ST209
Tue (24/09) | 24 Sep 2024 | BC4 |  | Hydraulic hose replacement completed. Oil top up in progress
Tue (24/09) | 24 Sep 2024 | ST205 |  | Rebar cage installation, 2/3 cages installed
Tue (24/09) | 24 Sep 2024 | BRP43 |  | LSS casting in progress
Tue (24/09) | 24 Sep 2024 | DR1 |  | Strut welding continue
Tue (24/09) | 24 Sep 2024 | BRP53 |  | Guidewall Formwork closed. Tonight to cast
Tue (24/09) | 24 Sep 2024 | TDP80 |  | Casting completed
Tue (24/09) | 24 Sep 2024 | ST105 |  | End plate extraction
Tue (24/09) | 24 Sep 2024 | P44 |  | Singtel cable recovery
Tue (24/09) | 24 Sep 2024 | P45-2 |  | Casting in progress
Tue (24/09) | 24 Sep 2024 | BC4 |  | Still ongoing rectification works
Tue (24/09) | 24 Sep 2024 | P17 |  | Guide bar installation started for pile cap rebar works
Wed (25/09) | 25 Sep 2024 | P10 |  | Plywood laying
Wed (25/09) | 25 Sep 2024 | P9 area |  | Excavation for telco duct
Wed (25/09) | 25 Sep 2024 | TMH2 |  | Lean con completed yesterday
Wed (25/09) | 25 Sep 2024 | P6 |  | Rig shifted. Area preparation for casing installation
Wed (25/09) | 25 Sep 2024 | P46-3 |  | Rebar cage delivery. Boring work in progress
Wed (25/09) | 25 Sep 2024 | P49-P8 |  | Wee Guan preparing to lay one more span of Power duct
Wed (25/09) | 25 Sep 2024 | P51 |  | TT on going to check on Starhub alignment
Wed (25/09) | 25 Sep 2024 | DR2 |  | Geomotion continue trial trench for recharge well installation. Have informed on site to clear the plant to make way for rig mobilisation
Wed (25/09) | 25 Sep 2024 | DR2 |  | WH continue excavation for utility stump works and RG drilling ongoing for inclinometer in-wall installation
Wed (25/09) | 25 Sep 2024 | Zone 1 |  | Eng Hup on site for traffic light cable shifting
Wed (25/09) | 25 Sep 2024 | ST105 |  | Desanding and cleaning
Wed (25/09) | 25 Sep 2024 | MH2-9 |  | Hacking and excavation ongoing for base slab
Wed (25/09) | 25 Sep 2024 | MH2-10 |  | Currently no activity. Manpower assisting at MH5-1
Wed (25/09) | 25 Sep 2024 | P44 |  | TT and exposing gas pipe for removal
Wed (25/09) | 25 Sep 2024 | MH3-5 |  | Base slab to cast today
Wed (25/09) | 25 Sep 2024 | Blk 2 |  | Drilling for RW7 temporarily stopped. Rig breakdown, rectification otw
Wed (25/09) | 25 Sep 2024 | P31 area |  | Manual soil clearing below SPPG haunching
Wed (25/09) | 25 Sep 2024 | P17 |  | Top bar T2 installed. T1 preparation for installation
Wed (25/09) | 25 Sep 2024 | N3 |  | Crosshead casting ongoing
Wed (25/09) | 25 Sep 2024 | DR2 |  | RG continue drilling for IW installation and WH works ongoing for RC stump
Wed (25/09) | 25 Sep 2024 | ST105 |  | WS endplate installation in progress
Wed (25/09) | 25 Sep 2024 | BC1 |  | Cutter teeth replacement ongoing
Wed (25/09) | 25 Sep 2024 | P14 |  | Continue column formwork closing
Wed (25/09) | 25 Sep 2024 | TDP73 |  | Casing installed. Boring in progress
Wed (25/09) | 25 Sep 2024 | DR1 |  | Cutting of protruding rebars ongoing & excavation in progress
Wed (25/09) | 25 Sep 2024 | BRP44 |  | Preboring in progress
Wed (25/09) | 25 Sep 2024 | BRP40 |  | Gear motor replacement in progress, B1 CD 17.6/25.07m, B2 completed
Wed (25/09) | 25 Sep 2024 | ST211 |  | B1 temporarily stopped, CD 17/41.9m. Mud pump changing ongoing
Wed (25/09) | 25 Sep 2024 | N2 |  | Falsework dismantle works
Wed (25/09) | 25 Sep 2024 | P6-1-2 |  | BP boring in progress, current depth 13m
Wed (25/09) | 25 Sep 2024 | S4 |  | Abutment wall rebar works
Wed (25/09) | 25 Sep 2024 | ST23A |  | Cleaning ongoing
Wed (25/09) | 25 Sep 2024 | ST238 |  | Excavation temporarily stopped. BC cutter servicing ongoing
Wed (25/09) | 25 Sep 2024 | ST242 |  | Preparing for desanding
Wed (25/09) | 25 Sep 2024 | ST248 |  | B1 in progress
Wed (25/09) | 25 Sep 2024 | P46-3 |  | Boring done. Today to cast
Wed (25/09) | 25 Sep 2024 | P46-P47 |  | JGP testing on going with 2 teams. Today target 3 points
Wed (25/09) | 25 Sep 2024 | P48-P49 |  | Today to cast one span
Wed (25/09) | 25 Sep 2024 | P48-P49 |  | Continue excavation to lean concrete
Wed (25/09) | 25 Sep 2024 | MH2-9 |  | Excavation & disposal ongoing. Today to cast lean con
Wed (25/09) | 25 Sep 2024 | MH2-10 |  | Toe board and painting works
Wed (25/09) | 25 Sep 2024 | BP2A-1 | 21 | Boring reached 43.5/45.624m
Wed (25/09) | 25 Sep 2024 | MH3-5 |  | Formwork closing done. Tomorrow to cast
Wed (25/09) | 25 Sep 2024 | P46-3 |  | Rebar cage lowering
Wed (25/09) | 25 Sep 2024 | ST105 |  | Rebar cage lowering, 2/8 installed
Wed (25/09) | 25 Sep 2024 | TDP73 |  | Pending casting
Wed (25/09) | 25 Sep 2024 | BRP40 |  | 2nd bite trenching completed. 1st bite 16m, now continue trenching
Wed (25/09) | 25 Sep 2024 | ST211 |  | 1st bite trenching at 22.9m depth
Wed (25/09) | 25 Sep 2024 | BC3 |  | Maintenance
Wed (25/09) | 25 Sep 2024 | MH2-9 |  | Base slab lean concrete completed
Wed (25/09) | 25 Sep 2024 | P17 |  | Bottom bars completed. Bar chair installation in progress
Wed (25/09) | 25 Sep 2024 | N3 crosshead |  | 2pm to cast
Thu (26/09) | 26 Sep 2024 | P44 |  | No activity as of now due to rain
Thu (26/09) | 26 Sep 2024 | MH3-5 |  | Formwork closing done for base slab. Today to cast
Thu (26/09) | 26 Sep 2024 | P47 |  | Shifting of rig to start boring
Thu (26/09) | 26 Sep 2024 | ST105 |  | Rebar cage installation in progress
Thu (26/09) | 26 Sep 2024 | BRP44 |  | Preboring continue
Thu (26/09) | 26 Sep 2024 | BRP40 |  | Continue trimming
Thu (26/09) | 26 Sep 2024 | BC3 |  | Currently no activity. Maintenance works ongoing
Thu (26/09) | 26 Sep 2024 | ST211 |  | B1 in progress, 34/41.9m
Thu (26/09) | 26 Sep 2024 | ST23A |  | Rebar cage installation ongoing, 2/3nos
Thu (26/09) | 26 Sep 2024 | BP2A-1 | 21 | Boring almost completed, awaiting toe level checking
Thu (26/09) | 26 Sep 2024 | ST238 |  | B1 in progress
Thu (26/09) | 26 Sep 2024 | ST242 |  | Rebar cage installation ongoing
Thu (26/09) | 26 Sep 2024 | ST248 |  | B2 ongoing
Thu (26/09) | 26 Sep 2024 | MH2-9 |  | Base slab lean con cast yesterday. Now dewatering ongoing before start rebar works
Thu (26/09) | 26 Sep 2024 | MH2-10 |  | No activity. Have informed site team to pump out water
Thu (26/09) | 26 Sep 2024 | P47-3 |  | Boring on going
Thu (26/09) | 26 Sep 2024 | P17 |  | Shear links and rebar installation works
Thu (26/09) | 26 Sep 2024 | P18 |  | Concrete packing casting ongoing
Thu (26/09) | 26 Sep 2024 | MH2-10 |  | Manual excavation ongoing
Thu (26/09) | 26 Sep 2024 | MH2-9 |  | Preparing to lower BRC
Thu (26/09) | 26 Sep 2024 | Blk 2 |  | Geomotion currently no activity. Rig breakdown
Thu (26/09) | 26 Sep 2024 | P10 |  | Portal frame erection continue
Thu (26/09) | 26 Sep 2024 | P6-1-2 |  | Rebar cage lowering ongoing, to cast today
Thu (26/09) | 26 Sep 2024 | BRP67 |  | Trial trench
Thu (26/09) | 26 Sep 2024 | MH3-5 |  | Casting in progress. Waiting for 1 more truck
Thu (26/09) | 26 Sep 2024 | ST110 |  | B1 in progress
Thu (26/09) | 26 Sep 2024 | ST105 |  | Rebar cage fully lowered. Now preparing for tremie pipe installation
Thu (26/09) | 26 Sep 2024 | TDP73 |  | Preparing for casting
Thu (26/09) | 26 Sep 2024 | BRP52 |  | Guidewall cast
Thu (26/09) | 26 Sep 2024 | BRP44 |  | Continue preboring
Thu (26/09) | 26 Sep 2024 | DR1 |  | LE continue strut welding works
Thu (26/09) | 26 Sep 2024 | BRP40 |  | B1 trimming reached 18.5/25.07m
Thu (26/09) | 26 Sep 2024 | BC3 |  | Maintenance
Thu (26/09) | 26 Sep 2024 | BP2A-1 | 21 | Hanging bar installation ongoing
Fri (27/09) | 27 Sep 2024 | P11 |  | Access installed for casting. Tomorrow to cast
Fri (27/09) | 27 Sep 2024 | P8-1-6 |  | Boring completed. Preparation for rebar installation
Fri (27/09) | 27 Sep 2024 | TMH2 |  | Rebar for sump pit on site
Fri (27/09) | 27 Sep 2024 | P4 |  | 1st stage concrete stump casting
Fri (27/09) | 27 Sep 2024 | P7-1-6 |  | Pre-boring for casing installation in progress
Fri (27/09) | 27 Sep 2024 | TMH2 |  | Base slab rebar works started. Plan to cast on Sunday
Fri (27/09) | 27 Sep 2024 | P8-1-6 |  | Casting in progress
Fri (27/09) | 27 Sep 2024 | P14 |  | Casting platform netting installation. Tomorrow AM to cast
Fri (27/09) | 27 Sep 2024 | P17 pile cap |  | Rebar and formwork completed. Tomorrow to cast
Fri (27/09) | 27 Sep 2024 | DP5-1 |  | Boring works in progress, 28m. Noise ballon erection to continue boring until 10pm
Fri (27/09) | 27 Sep 2024 | ST211 |  | Trimming in progress at end plate side
Sat (28/09) | 28 Sep 2024 | STN241 |  | 2nd bite trenching at 31m, 2nd bite at 8.5m
Sat (28/09) | 28 Sep 2024 | STN238 |  | Preparation for rebar cage installation. Total 12 cages
Sat (28/09) | 28 Sep 2024 | ST222-BC2 |  | 1st bite trenching at 9m depth
Sat (28/09) | 28 Sep 2024 | ST206-BC3 |  | Trimming at end plate in progress
Sat (28/09) | 28 Sep 2024 | BRP40-BC4 |  | Teeth changing in progress. Status 2nd bite at 23.8m
Sat (28/09) | 28 Sep 2024 | BRP55 |  | Rig bucket teeth broken, arranged for replacement
Sat (28/09) | 28 Sep 2024 | BRP60 |  | Guidewall formwork closing
Sat (28/09) | 28 Sep 2024 | ST104 |  | 1st bite trenching at 11.2m depth
Sat (28/09) | 28 Sep 2024 | P14 |  | Column casting completed
Sat (28/09) | 28 Sep 2024 | STN248 |  | 1st bite trenching in progress using Hydrofraise, current depth at 33m
Sun (29/09) | 29 Sep 2024 | BRP40 |  | 2nd bite excavation in progress
Sun (29/09) | 29 Sep 2024 | ST104 |  | 1st bite, reached 31.2.m
Sun (29/09) | 29 Sep 2024 | P17 |  | Pile cap casting completed
Sun (29/09) | 29 Sep 2024 | ST104 |  | 1st bite trenching continue at 17.8m depth
Sun (29/09) | 29 Sep 2024 | STN248 |  | 1st bite trenching continue using Hydrofraise, current depth at 36.5m
Sun (29/09) | 29 Sep 2024 | STN238 |  | Rebar cage installation, 6/12 cages
Sun (29/09) | 29 Sep 2024 | ST222-BC2 |  | 1st bite trenching continue at 15m depth
Sun (29/09) | 29 Sep 2024 | ST244 |  | 1st bite reached 42m
Sun (29/09) | 29 Sep 2024 | ST206-BC3 |  | Trimming at end plate continue
Sun (29/09) | 29 Sep 2024 | P18 |  | Continue excavation to FEL
Sun (29/09) | 29 Sep 2024 | P10 |  | Continue trimming column and falsework erection
Sun (29/09) | 29 Sep 2024 | ST206 |  | Cleaning and desanding
Sun (29/09) | 29 Sep 2024 | BRP52 |  | 1st point preboring in progress
Sun (29/09) | 29 Sep 2024 | DR2 |  | Stump casting in progress. 3nos
Sun (29/09) | 29 Sep 2024 | P44 |  | Sump pit cast. Left to shift traffic light cable
Sun (29/09) | 29 Sep 2024 | STN248 |  | 1st bite trenching continue using Hydrofraise, current depth at 39m
Sun (29/09) | 29 Sep 2024 | STN238 |  | Rebar cage installation continue, 8/12 cages
Sun (29/09) | 29 Sep 2024 | ST222-BC2 |  | 1st bite trenching continue at 22.5m depth
Sun (29/09) | 29 Sep 2024 | ST206-BC3 |  | Trimming at end plate continue
Sun (29/09) | 29 Sep 2024 | BC cutter 2 |  | Top up hydraulic hoil
Sun (29/09) | 29 Sep 2024 | P18 |  | Excavation to FEL
Sun (29/09) | 29 Sep 2024 | P17 |  | Curing of pier footing
Mon (30/09) | 30 Sep 2024 | MH2-9 |  | Base slab was cast. Currently no activity
Mon (30/09) | 30 Sep 2024 | MH2-10 |  | Soil disposal ongoing. Today target to cast half of 2nd layer and do support for the utility at haunching area
Mon (30/09) | 30 Sep 2024 | P48-P49 |  | Casting of duct, 3m length. Lean concrete, 6m length
Mon (30/09) | 30 Sep 2024 | P11 |  | Waler beam dismantling
Mon (30/09) | 30 Sep 2024 | P9 |  | Falsework erection started
Mon (30/09) | 30 Sep 2024 | P10 |  | Plywood laying
Mon (30/09) | 30 Sep 2024 | P6-6 |  | Boring works in progress
Mon (30/09) | 30 Sep 2024 | PRD3 |  | SPPG Working here
Mon (30/09) | 30 Sep 2024 | Near DR2 |  | RG drilling ongoing for water standpipe installation, Geomotion drilling ongoing for recharge well
Mon (30/09) | 30 Sep 2024 | DR1 |  | CGS continue excavation for 2nd layer
Mon (30/09) | 30 Sep 2024 | DR1 |  | Hacking ongoing
Mon (30/09) | 30 Sep 2024 | BRP52 |  | Preboring temporarily stopped. Operator assisting for rebar cage lowering
Mon (30/09) | 30 Sep 2024 | BC4 |  | Cutter teeth replacement ongoing. This machine will start for panel BRP55
Mon (30/09) | 30 Sep 2024 | ST162 |  | Trench preparation for guidewall construction
Mon (30/09) | 30 Sep 2024 | TDP79 |  | In progress. Today target to complete
Mon (30/09) | 30 Sep 2024 | BRP59 |  | Guidewall excavation
Mon (30/09) | 30 Sep 2024 | P46-4 |  | Boring done. To cast today
Mon (30/09) | 30 Sep 2024 | P44 |  | Shifting of traffic light cable
Mon (30/09) | 30 Sep 2024 | MH3-4 |  | Raise up support for Singtel as per QP comment
Mon (30/09) | 30 Sep 2024 | Zone 4 |  | P51 TT for piling works
Mon (30/09) | 30 Sep 2024 | P46-4 |  | Rebar cage installation in progress
Mon (30/09) | 30 Sep 2024 | BC1 |  | Maintenance work, hydraulic oil leaking
Mon (30/09) | 30 Sep 2024 | BRP52 |  | Cutter wheel teeth replacement
Mon (30/09) | 30 Sep 2024 | BRP55 |  | Pre-boring works
Mon (30/09) | 30 Sep 2024 | DR1 |  | Waler bracket welding till 10pm
Mon (30/09) | 30 Sep 2024 | BRP40 |  | Hanging bar welding for KP lowering, 1/2 KP
Mon (30/09) | 30 Sep 2024 | ST206-BC3 |  | 1st bite trenching at 28.6m
Tue (01/10) | 01 Oct 2024 | MH2-10 |  | Dewatering ongoing. Today to continue utility support and cast 2nd laye
Tue (01/10) | 01 Oct 2024 | Near gate 5 |  | Platform preparation for fissure grouting works
Tue (01/10) | 01 Oct 2024 | Blk 2 |  | Drilling ongoing for recharge well installation, RW8
Tue (01/10) | 01 Oct 2024 | Near DR2 |  | RG continue instrument installation & Geomotion ongoing drilling for RW68
Tue (01/10) | 01 Oct 2024 | DR2 |  | Formwork dismantling for utility stump
Tue (01/10) | 01 Oct 2024 | P10-2 |  | Pier hacking to correct level
Tue (01/10) | 01 Oct 2024 | P10 |  | Crosshead formwork installation
Tue (01/10) | 01 Oct 2024 | ST104 |  | WS trimming
Tue (01/10) | 01 Oct 2024 | BRP62 |  | Trial trench for guidewall
Tue (01/10) | 01 Oct 2024 | BRP59 |  | Preparation for guidewall construction
Tue (01/10) | 01 Oct 2024 | TDP79 |  | Completed yesterday. Now LSS backfill
Tue (01/10) | 01 Oct 2024 | BRP55 |  | B1 in progress, 23/30.17m
Tue (01/10) | 01 Oct 2024 | DR1 |  | CGS continue excavation & LE welding works ongoing
Tue (01/10) | 01 Oct 2024 | ST209 |  | B1 in progress
Tue (01/10) | 01 Oct 2024 | BC2 |  | Machine rectification ongoing
Tue (01/10) | 01 Oct 2024 | BP2-1 | 32 | Boring in progress, 38.5/41.1m
Tue (01/10) | 01 Oct 2024 | ST248 |  | B2 in progress, 43/50.65m
Tue (01/10) | 01 Oct 2024 | MH2-10 |  | BRC installation for 2nd layer
Tue (01/10) | 01 Oct 2024 | Near DR2 |  | Installation for waterstandpipe and recharge well ongoing respectively
Tue (01/10) | 01 Oct 2024 | MH3-4 |  | Preparing for cable protection
Tue (01/10) | 01 Oct 2024 | ST104 |  | WS trimming completed
Tue (01/10) | 01 Oct 2024 | P11-1 |  | Waler & strut dismantle works
Tue (01/10) | 01 Oct 2024 | P6-1-6 |  | BP boring works completed. Rebar cage lowering in progress
Tue (01/10) | 01 Oct 2024 | P10 |  | Crosshead formwork installation continue
Tue (01/10) | 01 Oct 2024 | P10 |  | Pier hacking to correct level continue
Tue (01/10) | 01 Oct 2024 | MH3-5 |  | Thrust block hacking ongoing
Tue (01/10) | 01 Oct 2024 | Zone 4 P50 |  | Power duct pipe laid 6m. Casting ongoing
Tue (01/10) | 01 Oct 2024 | P51 |  | Excavation for power duct pipe laying ongoing
Tue (01/10) | 01 Oct 2024 | Zone 4 |  | JGP testing in progress
Tue (01/10) | 01 Oct 2024 | P47-3 |  | Boring in progress
Tue (01/10) | 01 Oct 2024 | P44 |  | 1nos preboring was done
Tue (01/10) | 01 Oct 2024 | BRP55 |  | B1 in progress, 27.3/30.17m
Tue (01/10) | 01 Oct 2024 | Zone 2 |  | Pier rebar cage fabrication in progres
Tue (01/10) | 01 Oct 2024 | P10 |  | Crosshead formwork installation ongoing
Tue (01/10) | 01 Oct 2024 | P6-1-6 |  | Casting ongoing
Tue (01/10) | 01 Oct 2024 | S4 |  | Abutment wall formwork closing in progress
Tue (01/10) | 01 Oct 2024 | ST248 |  | B3 completed. Base cleaning ongoing. BC cutter shifting to make way for crane for WS extraction
Wed (02/10) | 02 Oct 2024 | STN248 |  | Installing of tremie pipe prior desanding for the panel
Wed (02/10) | 02 Oct 2024 | STN241 |  | B1 has just completed 41.27/41.27m, B2 CD 28/41.2m
Wed (02/10) | 02 Oct 2024 | STN233 |  | B1 CD 17.5/40.65m
Wed (02/10) | 02 Oct 2024 | ST222 | Rig 3 | B1 CD 33.6/33.7m
Wed (02/10) | 02 Oct 2024 | ST209 | Rig 2 | B1 CD 37.3/40.0m
Wed (02/10) | 02 Oct 2024 | P10-2 |  | Pier hacking to required level, plan to complete today
Wed (02/10) | 02 Oct 2024 | P8-1-3 |  | Casing installation
Wed (02/10) | 02 Oct 2024 | DR1 |  | Ongoing hacking & welding by WHDA & LE, respectively
Wed (02/10) | 02 Oct 2024 | Beside DR2 |  | WSP & RW installation by Ryobi.G & Geomotion, respectively
Wed (02/10) | 02 Oct 2024 | BRP62 |  | Guidewall rebar & formwork installation in progress
Wed (02/10) | 02 Oct 2024 | S4 abutment wall |  | Level peg marking for casting
Wed (02/10) | 02 Oct 2024 | P10 |  | Phase 2 pad footing rebar works
Wed (02/10) | 02 Oct 2024 | P47-3 |  | Boring to toe done. Today to cast. Work area to tidy up by today
Wed (02/10) | 02 Oct 2024 | P50 |  | Wee guan backfilling the completed duct laid
Wed (02/10) | 02 Oct 2024 | P51 |  | Continue excavation for duct laying
Wed (02/10) | 02 Oct 2024 | ST104 |  | WS removal in progress
Wed (02/10) | 02 Oct 2024 | MH3-5 |  | Formwork removal for invert cast
Wed (02/10) | 02 Oct 2024 | P1 |  | Manual excavation to localised shift 22KV
Wed (02/10) | 02 Oct 2024 | P51 |  | Continue excavation for next span of Power duct
Wed (02/10) | 02 Oct 2024 | MH3-5 |  | Elbow installation for back drop
Wed (02/10) | 02 Oct 2024 | P45-1 |  | Casing installed. Preparing to continue boring
Wed (02/10) | 02 Oct 2024 | P47-3 |  | Casting in progress
Wed (02/10) | 02 Oct 2024 | MH3-4 |  | Extension of access and rectification of Singtel support
Wed (02/10) | 02 Oct 2024 | P44 |  | Preboring in progress
Wed (02/10) | 02 Oct 2024 | ST104 |  | 2nd bite excavation done
Wed (02/10) | 02 Oct 2024 | TDP93 |  | Casing installation done. Continue boring work
Wed (02/10) | 02 Oct 2024 | BRP55 |  | Casting in progress. BRP52: excavation reached 16m
Wed (02/10) | 02 Oct 2024 | BRP40 |  | LSS backfilling
Wed (02/10) | 02 Oct 2024 | P17 |  | Column formwork closing
Wed (02/10) | 02 Oct 2024 | P18 |  | Excavation to FEL
Wed (02/10) | 02 Oct 2024 | P11 |  | Backfilling
Wed (02/10) | 02 Oct 2024 | P8-1-3 |  | Casting done. Now tidy up the area. P7-1-3 : casing installed
Wed (02/10) | 02 Oct 2024 | TMH02 |  | Base slab rebar work
Wed (02/10) | 02 Oct 2024 | P4 |  | Final layer soil backfilling
Wed (02/10) | 02 Oct 2024 | MH2-10 |  | LCH working until 10PM
Wed (02/10) | 02 Oct 2024 | P51 |  | Platform prepare for bored pile work
Thu (03/10) | 03 Oct 2024 | P51 |  | Platform prepare for bored pile work
Thu (03/10) | 03 Oct 2024 | P51 |  | Power duct laying. Today plan to cast around 24m
Thu (03/10) | 03 Oct 2024 | P45 |  | Last pile boring done. Toe confirmed. Today to cast
Thu (03/10) | 03 Oct 2024 | P46 |  | JGP testing on going. CR105 on site
Thu (03/10) | 03 Oct 2024 | P47 |  | LSS backfilling for completed pile
Thu (03/10) | 03 Oct 2024 | N1 |  | Alignment of wingform prior to rebar installation
Thu (03/10) | 03 Oct 2024 | N1 |  | Erection of scaffold access for rebar works
Thu (03/10) | 03 Oct 2024 | P10-2 |  | Pier hacking to required level. Balance 50mm
Thu (03/10) | 03 Oct 2024 | P9 |  | Portal frame assembly
Thu (03/10) | 03 Oct 2024 | TMH2 |  | Base slab rebar works, today to cast after 7pm
Thu (03/10) | 03 Oct 2024 | MH3-4 |  | Continue excavation for next layer caisson
Thu (03/10) | 03 Oct 2024 | P44 |  | Continue preboring for ERSS
Thu (03/10) | 03 Oct 2024 | MH3-5 |  | Formwork closing for permanent manhole casti.g
Thu (03/10) | 03 Oct 2024 | P7-1-3 |  | Rebar cage installed
Thu (03/10) | 03 Oct 2024 | MH2-10 |  | Manual hacking for temporary drain diversion
Thu (03/10) | 03 Oct 2024 | STN233 |  | 2nd bite trenching continue
Thu (03/10) | 03 Oct 2024 | ST222 |  | 2nd bite trenching completed, internal koden in progress
Thu (03/10) | 03 Oct 2024 | ST211 |  | Casting in progress. Running volume 149 m3
Thu (03/10) | 03 Oct 2024 | ST209 |  | Water stop trimming
Thu (03/10) | 03 Oct 2024 | BRP44 |  | Trenching started. 6m depth
Thu (03/10) | 03 Oct 2024 | DR1 |  | Excavation till 9pm
Thu (03/10) | 03 Oct 2024 | BRP52 |  | Preparation for KP lifting and lowering
Thu (03/10) | 03 Oct 2024 | TDP93 |  | KP lowered for casting. Waiting for concrete lorry
Thu (03/10) | 03 Oct 2024 | ST110 |  | C-lug welding for trimming
Thu (03/10) | 03 Oct 2024 | P45-1 |  | Preparation for casting
Thu (03/10) | 03 Oct 2024 | STN248 |  | Casting in progress
Thu (03/10) | 03 Oct 2024 | STN241 |  | Excavation completed for all bites, next will remove WS
Thu (03/10) | 03 Oct 2024 | STN233 |  | B2 CD 17/40.65m
Fri (04/10) | 04 Oct 2024 | P18 |  | Continue excavation to FEL
Fri (04/10) | 04 Oct 2024 | N1 |  | Access erection and tidy up the area before rebar installation for cross head
Fri (04/10) | 04 Oct 2024 | P11 |  | Surface roughening for column work
Fri (04/10) | 04 Oct 2024 | P10 |  | Comments from DD site walk are addressed and closed
Fri (04/10) | 04 Oct 2024 | P10 |  | Clearing debris from column
Fri (04/10) | 04 Oct 2024 | MH2-10 |  | Manual hacking for temporary drain diversion. Balance 2nd layer plan to cast tmr
Fri (04/10) | 04 Oct 2024 | DR2 |  | Utility stump construction ongoing
Fri (04/10) | 04 Oct 2024 | P37 |  | Recharge well drilling ongoing. Geomotion provided 3 rigs for RW works — 1 rig at blk 2, 2 rigs along DR2
Fri (04/10) | 04 Oct 2024 | DR2 |  | WH making access across DR2
Fri (04/10) | 04 Oct 2024 | P6-1-3 |  | Rig will shift over after lunch and start boring for bored pile
Fri (04/10) | 04 Oct 2024 | BRP67 |  | Preboring ongoing
Fri (04/10) | 04 Oct 2024 | ST110 |  | Desanding completed
Fri (04/10) | 04 Oct 2024 | P5 |  | Shifting of traffic light cable
Fri (04/10) | 04 Oct 2024 | TDP93 |  | Completed yesterday, ntoday to backfill LSS. HSL plan to expedite TDP74 next
Fri (04/10) | 04 Oct 2024 | ST144 |  | Trial trench ongoing
Fri (04/10) | 04 Oct 2024 | P4 |  | Today LE will come and remove this struct so Wendyng can continue with column work
Fri (04/10) | 04 Oct 2024 | DR2 |  | Removal of the existing drain and retaining wall hacking for utility hanging work
Fri (04/10) | 04 Oct 2024 | ST233 |  | Trenching completed. Waiting for crane to remove end plate
Fri (04/10) | 04 Oct 2024 | ST214 |  | Rebar cage installation in progress, 8/10 installed
Fri (04/10) | 04 Oct 2024 | STN222 |  | Mud drum elbow damage. Preparation for repair works. Current trimming
Fri (04/10) | 04 Oct 2024 | BC2 |  | To shift for STN209 desanding and cleaning
Fri (04/10) | 04 Oct 2024 | BRP42-BC4 |  | Teeth replacement, current at 21.8m depth
Fri (04/10) | 04 Oct 2024 | DR1 |  | Excavation to FEL continue for night shift
Fri (04/10) | 04 Oct 2024 | BRP53-BG1 |  | Preparation for pre-boring
Fri (04/10) | 04 Oct 2024 | ST108-BC1 |  | 1st bite trenching at 17m depth
Fri (04/10) | 04 Oct 2024 | ST110 |  | Rebar cage installation, 3/8 cages installed
Fri (04/10) | 04 Oct 2024 | DR1 |  | Current status. LE continue welding works and CGS continue 2nd layer excavation
Fri (04/10) | 04 Oct 2024 | BRP44 |  | B1 temporarily stopped for cutter teeth change. CD 18.5/23.77m
Fri (04/10) | 04 Oct 2024 | P33 |  | Hirose plan for main beam installation today (1nos)
Fri (04/10) | 04 Oct 2024 | P32 |  | KTC exposing services
Fri (04/10) | 04 Oct 2024 | ST201-202 |  | Trial trench for guidewall construction
Fri (04/10) | 04 Oct 2024 | ST222 |  | C-lug welding for WS trimming ongoing
Fri (04/10) | 04 Oct 2024 | ST245 |  | B1 in progress, 3/43.53m, ST241: Today plan for rebar cage installation
Fri (04/10) | 04 Oct 2024 | BC2 |  | Currently no activity. This machine plan to move to ST216 next
Fri (04/10) | 04 Oct 2024 | BP2-1 | 27 | Hacking ongoing for trial trench works
Fri (04/10) | 04 Oct 2024 | P51 |  | Today to start balance bored pile at TPE bound
Fri (04/10) | 04 Oct 2024 | P44 |  | 3 soldier piles + one steel plate installed before lunch
Fri (04/10) | 04 Oct 2024 | MH3-4 |  | To cast one ring by today
Fri (04/10) | 04 Oct 2024 | P18 |  | KTC excavation and disposal
Fri (04/10) | 04 Oct 2024 | P17 |  | Formwork removal
Fri (04/10) | 04 Oct 2024 | STN241 |  | Rebar cage lowering in progress
Fri (04/10) | 04 Oct 2024 | STN245 |  | B1 excavation has just started & now grab under repair
Fri (04/10) | 04 Oct 2024 | STN233 |  | B2 excavation has just completed, 39.45/39.45m
Fri (04/10) | 04 Oct 2024 | N1 |  | Cross head rebar work and lifting of rebar to cross head level
Fri (04/10) | 04 Oct 2024 | P11 |  | Hacking of column head and prepare the area for concrete block placing
Fri (04/10) | 04 Oct 2024 | P10 |  | Assembly of cross head formwork
Fri (04/10) | 04 Oct 2024 | BP2-1 | 23 | Boring CD 28/45.7m
Fri (04/10) | 04 Oct 2024 | ST222 | Rig 3 | WS trimming in progress
Fri (04/10) | 04 Oct 2024 | P10 cross head level |  | Column head hacking
Fri (04/10) | 04 Oct 2024 | Zone 1 |  | Shifting of traffic light pipe <This message was edited>
Fri (04/10) | 04 Oct 2024 | Zone 4 |  | HSL crane boom down inspection
Fri (04/10) | 04 Oct 2024 | P44 |  | Continue soldier pile installation
Fri (04/10) | 04 Oct 2024 | MH3-4 |  | Formwork closing for caisson ring casting
Fri (04/10) | 04 Oct 2024 | P51-6 |  | Casing installed
Fri (04/10) | 04 Oct 2024 | MH2-10 |  | Excavation ongoing
Fri (04/10) | 04 Oct 2024 | DR1 |  | Hardcore laying ongoing
Fri (04/10) | 04 Oct 2024 | DR1 |  | LE continue waler welding works
Fri (04/10) | 04 Oct 2024 | ST110 |  | Rebar cage installation in progress
Fri (04/10) | 04 Oct 2024 | ST108 |  | B1 in progress, 12/39m
Fri (04/10) | 04 Oct 2024 | MH3-4 |  | Caisson ring formwork completed
Fri (04/10) | 04 Oct 2024 | TDP74 |  | Preparing for casting
Fri (04/10) | 04 Oct 2024 | DR2 |  | Retaining wall hacking ongoing
Fri (04/10) | 04 Oct 2024 | BP2-1 | 23 | Boring reached 29.5/45.7m. Now setting up noise balloon
Fri (04/10) | 04 Oct 2024 | BP2-1 | 27 | Trial trench ongoing. This BP is within the alignment of the live water pipe, BP2-1(26) and BP2-2(29) also affected by the water pipe
Fri (04/10) | 04 Oct 2024 | ST241 |  | Rebar cage installation ongoing, 6/10nos
Fri (04/10) | 04 Oct 2024 | P17 |  | Casting platform erection. Tomorrow to cast
Fri (04/10) | 04 Oct 2024 | P18 |  | Excavation to FEL continue until 10pm
Fri (04/10) | 04 Oct 2024 | P17 |  | Pier footing side formwork removal
Sat (05/10) | 05 Oct 2024 | BC2 |  | To shift to ST166. Pre excavation done
Sat (05/10) | 05 Oct 2024 | BRP53-BG1 |  | Pre-boring in progress
Sat (05/10) | 05 Oct 2024 | ST108-BC1 |  | Mud pump replacement, current at 2nd bite trenching at 39.2m depth
Sat (05/10) | 05 Oct 2024 | ST110 |  | Casting completed, total volume 216 m3
Sat (05/10) | 05 Oct 2024 | P10 |  | Checking and assembly formwork at ground level
Sat (05/10) | 05 Oct 2024 | N1 |  | Cross head rebar work
Sat (05/10) | 05 Oct 2024 | P11 |  | Platform preparation. After lunch to install column rebar cage
Sat (05/10) | 05 Oct 2024 | P10 |  | Assembling of falsework for bus lane cross over
Sat (05/10) | 05 Oct 2024 | P10 |  | Trimming of column and housekeeping
Sat (05/10) | 05 Oct 2024 | P6-1-3 |  | Rebar cage inspection. Today to cast
Sat (05/10) | 05 Oct 2024 | P5 |  | Lane closure started for TT at lane 1
Sat (05/10) | 05 Oct 2024 | Zone 4 P51 |  | Premix removal for TT work
Sat (05/10) | 05 Oct 2024 | P51-6 |  | Boring on going
Sat (05/10) | 05 Oct 2024 | MH3-5 |  | Today to cast this 2.250m hight wall. Next layer will be precast already
Sat (05/10) | 05 Oct 2024 | P44 |  | Preboring in progress
Sat (05/10) | 05 Oct 2024 | MH3-4 |  | Preparing for next layer caisson excavation work
Sat (05/10) | 05 Oct 2024 | ST108 |  | 1st bite reached 32m
Sat (05/10) | 05 Oct 2024 | DR2 |  | KTC hacking and removal of abandoned drain
Sat (05/10) | 05 Oct 2024 | P32 |  | Excavation by KTC and barricade along excavation area
Sat (05/10) | 05 Oct 2024 | ST209 |  | Desanding completed
Sat (05/10) | 05 Oct 2024 | ST214 |  | Rebar cage installation continue, 9/10 installed
Sat (05/10) | 05 Oct 2024 | ST245 |  | LSS backfilling back. Excavation done around 4m for both bites
Sat (05/10) | 05 Oct 2024 | P17 |  | Column formwork inspection done. Today to cast
Sat (05/10) | 05 Oct 2024 | P18 |  | Excavation done to FEL
Sat (05/10) | 05 Oct 2024 | N1 |  | Cross head rebar work in progress
Sat (05/10) | 05 Oct 2024 | P10 |  | Continue assembling of formwork at ground level
Sat (05/10) | 05 Oct 2024 | P11 |  | Column rebar cage installed
Sat (05/10) | 05 Oct 2024 | P9 |  | Frame set up for cross head
Sat (05/10) | 05 Oct 2024 | P5 |  | No cable slack for traffic light. Woh hup to decide internally how to shift for bored pile work
Sat (05/10) | 05 Oct 2024 | ST222 |  | Cleaning and desanding
Sat (05/10) | 05 Oct 2024 | DR1 |  | Waler to strut end welding
Sat (05/10) | 05 Oct 2024 | DR1 |  | CGS marking the level of drain and center line
Sat (05/10) | 05 Oct 2024 | ST214 |  | All cages installed. Tremie pipe installation in progress
Sat (05/10) | 05 Oct 2024 | ST233 |  | Cleaning in progress
Sat (05/10) | 05 Oct 2024 | STN222 |  | Trimming in progress
Sat (05/10) | 05 Oct 2024 | STN209-BC2 |  | Bc cutter shifted for desanding and cleaning
Sat (05/10) | 05 Oct 2024 | DR1 |  | Continue excavation to FEL
Sat (05/10) | 05 Oct 2024 | BRP44-BC4 |  | Trenching at 22.7m depth
Sat (05/10) | 05 Oct 2024 | MH2-10 |  | Target to cast tonight. Late night
Sat (05/10) | 05 Oct 2024 | Zone 1 |  | Traffic light cable safety shifted
Sat (05/10) | 05 Oct 2024 | Zone 2 |  | Falsework materials unloading
Sat (05/10) | 05 Oct 2024 | STN222 |  | Cleaning in progress
Sat (05/10) | 05 Oct 2024 | STN209 |  | End plate and water stop lowered. Preparation for rebar cage lowering
Sat (05/10) | 05 Oct 2024 | ST222 |  | Taking of waterstop end plate and cutter teeth changing in progress
Sat (05/10) | 05 Oct 2024 | BP33 |  | Boring reached 30.500mm
Sat (05/10) | 05 Oct 2024 | P17 |  | This column to cast today
Sat (05/10) | 05 Oct 2024 | P18 |  | Today to complete excavation to FEL
Sat (05/10) | 05 Oct 2024 | BRP44-BC4 |  | 2nd bite trenching at 15.2m depth
Sun (06/10) | 06 Oct 2024 | STN222 |  | Rebar cage installation. 5/8 cages
Sun (06/10) | 06 Oct 2024 | STN216 |  | 1st bite trenching at 32.5m depth
Sun (06/10) | 06 Oct 2024 | STN209 |  | Casting on going, waiting for last load
Sun (06/10) | 06 Oct 2024 | BRP44-BC4 |  | 2nd bite trenching at 23.6m depth. Cutter wheel teeth replacement
Sun (06/10) | 06 Oct 2024 | BRP53-BG1 |  | Pre-boring in progress
Sun (06/10) | 06 Oct 2024 | ST166-BC2 |  | 1st bite trenching at 20m depth
Sun (06/10) | 06 Oct 2024 | ST108-BC1 |  | 2nd bite trenching at 20m depth
Sun (06/10) | 06 Oct 2024 | STN222 |  | Cleaning and desanding done. Preparation for koden test
Sun (06/10) | 06 Oct 2024 | STN209 |  | Rebar cage cage installation, 3/3 installation
Sun (06/10) | 06 Oct 2024 | STN166 |  | Excavation now in progress
Mon (07/10) | 07 Oct 2024 | P17 |  | Pile cap formwork dismantle and removal in progress
Mon (07/10) | 07 Oct 2024 | P18 |  | Pile head cutting works ongoing, 5/6 completed
Mon (07/10) | 07 Oct 2024 | P31 |  | Excavation by KTC ongoing
Mon (07/10) | 07 Oct 2024 | P33 |  | Beam welding ongoing by Hirose
Mon (07/10) | 07 Oct 2024 | BRP44 |  | Cleaning ongoing
Mon (07/10) | 07 Oct 2024 | P51-6 |  | Concrete ordered for casting
Mon (07/10) | 07 Oct 2024 | BRP46 |  | Guidewall rebar works ongoing. Plan for casting today
Mon (07/10) | 07 Oct 2024 | BC2 |  | Cutter wheel changing ongoing
Mon (07/10) | 07 Oct 2024 | BRP53 |  | Preboring ongoing
Mon (07/10) | 07 Oct 2024 | DR2 |  | Recharge well works ongoing for RW63, 69, 73. Geomotion has provided 3 rigs here
Mon (07/10) | 07 Oct 2024 | DR2 |  | Retaining wall hacking ongoing
Mon (07/10) | 07 Oct 2024 | ST108 |  | WS trimming in progress
Mon (07/10) | 07 Oct 2024 | STN240 |  | B1 CD 22/45.32m
Mon (07/10) | 07 Oct 2024 | STN233 |  | Desanding & WS installation in progress
Mon (07/10) | 07 Oct 2024 | BP2-1 | 23 | Boring CD 38.5/45.7m
Mon (07/10) | 07 Oct 2024 | N1 |  | Rebar & ducting installation works
Mon (07/10) | 07 Oct 2024 | P10 |  | Crosshead formwork assembly works
Mon (07/10) | 07 Oct 2024 | ST222 |  | Casting in progress
Mon (07/10) | 07 Oct 2024 | DR1 |  | CGS preparing rebars for base slab & continue excavation
Mon (07/10) | 07 Oct 2024 | DR1 |  | LE continue welding works. Currently on tea break
Mon (07/10) | 07 Oct 2024 | C23 |  | Coring work in progress
Mon (07/10) | 07 Oct 2024 | P47-1 |  | Preparing to start casing installation
Mon (07/10) | 07 Oct 2024 | MH2-10 |  | Excavation for 4th layer
Mon (07/10) | 07 Oct 2024 | MH2-9 |  | Currently no activity. Pending crane inspection by WH safety
Mon (07/10) | 07 Oct 2024 | MH3-5 |  | Formwork removal
Mon (07/10) | 07 Oct 2024 | P44 |  | Continue preboring and TT work
Mon (07/10) | 07 Oct 2024 | MH3-4 |  | Mini lowering for excavation
Mon (07/10) | 07 Oct 2024 | P9 |  | C-channel installation works in progress
Mon (07/10) | 07 Oct 2024 | P8-2 |  | Telco duct pipe laying works
Mon (07/10) | 07 Oct 2024 | TMH-02 |  | Formwork dismantled
Mon (07/10) | 07 Oct 2024 | P6-1-4 |  | BP boring works ongoing, current depth 19m
Mon (07/10) | 07 Oct 2024 | P5 |  | Backfilling and compaction completed
Mon (07/10) | 07 Oct 2024 | P4 |  | Rebar works for column stump ongoing
Mon (07/10) | 07 Oct 2024 | STN222 |  | Rebar cage installation continue. 7/8 cages
Mon (07/10) | 07 Oct 2024 | ST166-BC2 |  | 1st bite trenching at 20m depth
Mon (07/10) | 07 Oct 2024 | BRP53-BG1 |  | Pre-boring continue, depth 30.6m
Mon (07/10) | 07 Oct 2024 | ST108 |  | Water stop end plate side trimming for removal
Mon (07/10) | 07 Oct 2024 | ST108-BC1 |  | 2nd bite trenching at 29m depth
Mon (07/10) | 07 Oct 2024 | TDP17A |  | Boring in progress
Mon (07/10) | 07 Oct 2024 | DR2 |  | Drain hacking and removal
Mon (07/10) | 07 Oct 2024 | BRP53 |  | Preboring work
Mon (07/10) | 07 Oct 2024 | DR1 |  | Drain rebar work started
Mon (07/10) | 07 Oct 2024 | DR1 |  | Waler joint welding
Mon (07/10) | 07 Oct 2024 | BRP44 |  | Desanding in progress
Mon (07/10) | 07 Oct 2024 | P32-33 |  | Premix removal and continue excavation
Mon (07/10) | 07 Oct 2024 | MH2-8 |  | Checking of over pumping pump
Mon (07/10) | 07 Oct 2024 | P17 |  | Removal of formwork support
Mon (07/10) | 07 Oct 2024 | P18 |  | Pile head hacking
Mon (07/10) | 07 Oct 2024 | N1 |  | Cross head rebar work
Mon (07/10) | 07 Oct 2024 | P9 |  | Shelter linkway erection
Mon (07/10) | 07 Oct 2024 | P6-1-3 |  | Boring in progress, reached 24m. Tomorrow to cast
Mon (07/10) | 07 Oct 2024 | P4 |  | Column rebar work
Mon (07/10) | 07 Oct 2024 | MH2-10 |  | Hacking of hard soil for next layer caisson casting
Tue (08/10) | 08 Oct 2024 | P47-1 |  | Boring in progress
Tue (08/10) | 08 Oct 2024 | BRP67 |  | Excavation temporarily stopped for cutter wheel cleaning and teeth changing. Current depth 28/33.7m
Tue (08/10) | 08 Oct 2024 | ST108 |  | Trimming ongoing
Tue (08/10) | 08 Oct 2024 | N1 |  | Preparation for tendon duct installation
Tue (08/10) | 08 Oct 2024 | P10 |  | Formwork assembly in progress. 17 pax
Tue (08/10) | 08 Oct 2024 | ST146-ST150 |  | Hacking and excavation ongoing for guidewall TT
Tue (08/10) | 08 Oct 2024 | P9 |  | Netting installation
Tue (08/10) | 08 Oct 2024 | DKP17A |  | Boring almost completed. Today plan for casting
Tue (08/10) | 08 Oct 2024 | BRP46 |  | Guidewall formwork ongoing. Today to cast
Tue (08/10) | 08 Oct 2024 | ST166 |  | Excavation temporarily stopped. BC2 cutter teeth changing ongoing
Tue (08/10) | 08 Oct 2024 | P32 |  | Abandoned water pipe exposed. Cutting of pipe ongoing
Tue (08/10) | 08 Oct 2024 | P31-32 |  | Current status of excavation
Tue (08/10) | 08 Oct 2024 | DR1 |  | CGS preparing rebars for base slab and hardcore laying
Tue (08/10) | 08 Oct 2024 | DR1 |  | LE preparing for concrete packing. To cast today
Tue (08/10) | 08 Oct 2024 | BP2A-1 | 23 | Boring in progress, 41.5/45.7m
Tue (08/10) | 08 Oct 2024 | ST233 |  | Rebar cages lowered. Now preparing for casting
Tue (08/10) | 08 Oct 2024 | ST240 |  | Excavation temporarily stopped. Hydrofraise machine breakdown. Rectification ongoing
Tue (08/10) | 08 Oct 2024 | ST243 |  | Preparation works ongoing prior to excavation. Plan to start today
Tue (08/10) | 08 Oct 2024 | MH3-4 |  | Continue excavation for caisson casting
Tue (08/10) | 08 Oct 2024 | P44 |  | Continue preboring for ERSS installation
Tue (08/10) | 08 Oct 2024 | MH3-5 |  | Sewer pipe installation for backdrop
Tue (08/10) | 08 Oct 2024 | MH2-10 |  | Hacking and excavation ongoing for 4th layer
Tue (08/10) | 08 Oct 2024 | MH2-9 |  | Currently no activity. Still settling crane parking matters with WH safety
Tue (08/10) | 08 Oct 2024 | STN233 |  | Casting in progress
Tue (08/10) | 08 Oct 2024 | STN243 |  | B1 excavation started, CD 9.0/44.66m
Tue (08/10) | 08 Oct 2024 | P18 |  | Pile head hacking, 4/6 completed
Tue (08/10) | 08 Oct 2024 | DR2 |  | Geomotion continues to trial trench for RW62, RW69 & RW73 drilling ongoing
Tue (08/10) | 08 Oct 2024 | DR2 |  | Retaining wall hacking ongoing
Tue (08/10) | 08 Oct 2024 | BRP60 |  | Pre-excavation
Tue (08/10) | 08 Oct 2024 | BRP67 | BC4 | Excavation resume
Tue (08/10) | 08 Oct 2024 | ST108 |  | Trimming in progress
Tue (08/10) | 08 Oct 2024 | STN240 |  | B1 CD 37.7/45.32m
Tue (08/10) | 08 Oct 2024 | ST144-145 |  | Guidewall formwork dismantling
Tue (08/10) | 08 Oct 2024 | ST146 |  | Guidewall trial trench. Found HT cable pipes
Tue (08/10) | 08 Oct 2024 | BP2-1 | 23 | Boring CD 43.5/45.7m
Tue (08/10) | 08 Oct 2024 | Zone 3 |  | HSL preparing to install KP for DKP17A. CAAS officers currently on site for machinery ops height inspection
Tue (08/10) | 08 Oct 2024 | ST216 | Rig 3 | B2 CD 34.2/37.1m
Tue (08/10) | 08 Oct 2024 | BRP53 |  | Preboring ongoing
Tue (08/10) | 08 Oct 2024 | ST166 |  | Excavation temporarily stopped due to very hard ground. BC2 will move to new panel and ST166 plan for preboring, B1 CD 20.3/27.4m
Tue (08/10) | 08 Oct 2024 | N1 |  | Pending column main rebar bending before start on ducting installation
Tue (08/10) | 08 Oct 2024 | P10 |  | Continue formwork assembly works
Tue (08/10) | 08 Oct 2024 | P11-1 |  | Excavation and levelling works for base lean concrete and concrete blocks installation
Tue (08/10) | 08 Oct 2024 | P9 |  | Netting installation works
Tue (08/10) | 08 Oct 2024 | P8-P9 |  | Continue excavation for telco duct pipe laying works
Tue (08/10) | 08 Oct 2024 | DR1 |  | Pending concrete packing casting
Tue (08/10) | 08 Oct 2024 | DR1 |  | CGS continue manual excavation
Tue (08/10) | 08 Oct 2024 | MH2-10 |  | 4th layer excavation in progress. Target to cast this layer tomorrow
Tue (08/10) | 08 Oct 2024 | MH2-9 |  | Crane inspection by WH safety
Tue (08/10) | 08 Oct 2024 | P47-1 |  | Boring on going. Tomorrow to cast
Tue (08/10) | 08 Oct 2024 | MH3-4 |  | Back drop pipe installed. Tomorrow precast ring installation
Tue (08/10) | 08 Oct 2024 | P6-1-4 |  | BP casting in progress
Tue (08/10) | 08 Oct 2024 | PRD3 to Loyang Ave |  | Pipe laying for lamp post shifting works
Tue (08/10) | 08 Oct 2024 | P44 |  | Continue TT and preboring
Tue (08/10) | 08 Oct 2024 | MH3-4 |  | Continue excavation. Tomorrow to cast
Tue (08/10) | 08 Oct 2024 | P4 |  | Column stump rebar works
Tue (08/10) | 08 Oct 2024 | BKP17A |  | Hanging bar welding for casting
Tue (08/10) | 08 Oct 2024 | BRP53 |  | Continue preboring
Tue (08/10) | 08 Oct 2024 | DR1 |  | Lagging plate welding below Singtel
Tue (08/10) | 08 Oct 2024 | P31-P32 |  | Manual excavation for utility support installation
Tue (08/10) | 08 Oct 2024 | P18 |  | Pile head hacking and cleaning
Tue (08/10) | 08 Oct 2024 | N1 |  | Adjusting of rebar for PT duct installation
Tue (08/10) | 08 Oct 2024 | P10 |  | Formwork assembly
Tue (08/10) | 08 Oct 2024 | P11 |  | Level marking for base casting for column formwork closing
Tue (08/10) | 08 Oct 2024 | P8 |  | Boring rig shifting to P8 for boring work
Tue (08/10) | 08 Oct 2024 | P4 |  | Tie rod installation
Tue (08/10) | 08 Oct 2024 | Near DR2 |  | Geomotion trial trench ongoing for recharge well works, RW62
Tue (08/10) | 08 Oct 2024 | DR2 |  | Hacking and excavation ongoing to expose utility posts for support works
Tue (08/10) | 08 Oct 2024 | P46-P45 |  | JGP testing in progress
Wed (09/10) | 09 Oct 2024 | MH2-10 |  | Preparing for 4th layer BRC installation
Wed (09/10) | 09 Oct 2024 | Near Gate 5 |  | Seongha continue setting up their plant and containers
Wed (09/10) | 09 Oct 2024 | Blk 2 |  | Geomotion hand auger ongoing for recharge well, RW13
Wed (09/10) | 09 Oct 2024 | N1 |  | Tendon duct installation, 6/18 installed. Plan to complete tendon duct today. Tomorrow complete shearlinks and start formwork closing
Wed (09/10) | 09 Oct 2024 | P28 |  | WH internal water pipe installation
Wed (09/10) | 09 Oct 2024 | P32 |  | Soil trimming and disposal ongoing
Wed (09/10) | 09 Oct 2024 | DR1 |  | PLT ongoing for base slab, 3rd cycle. Plan to cast lean con for remaining part 1 base slab today
Wed (09/10) | 09 Oct 2024 | DR1 |  | Waler concrete packing for the other section completed last night
Wed (09/10) | 09 Oct 2024 | BRP44 |  | LSS backfill ongoing
Wed (09/10) | 09 Oct 2024 | BRP54 | BC4 | Excavation started
Wed (09/10) | 09 Oct 2024 | BRP53 |  | Preboring in progress
Wed (09/10) | 09 Oct 2024 | DR2 |  | Trial trench ongoing for utility support works
Wed (09/10) | 09 Oct 2024 | DR2 |  | Water topup ongoing for RW70 and preparing to shift rig 3 to RW72
Wed (09/10) | 09 Oct 2024 | DR2 |  | Material shifting before continuing remaining retaining wall hacking
Wed (09/10) | 09 Oct 2024 | P8-1-4 |  | For casting, concrete ordered
Wed (09/10) | 09 Oct 2024 | Next to MH3-4 |  | Removing of old ECM pond to facilitate material storage area
Wed (09/10) | 09 Oct 2024 | P44 |  | Preboring in progress
Wed (09/10) | 09 Oct 2024 | MH3-5 |  | Backdrop installation and parching ongoing
Wed (09/10) | 09 Oct 2024 | Zone 4 |  | Continue JGP test, C-3
Wed (09/10) | 09 Oct 2024 | Zone 4 |  | Hacking ongoing for power duct works
Wed (09/10) | 09 Oct 2024 | Zone 4 |  | HSL boring rig now parked at P51 area
Wed (09/10) | 09 Oct 2024 | P47-1 |  | Rebar cage lowering
Wed (09/10) | 09 Oct 2024 | Zone 4 |  | Lucky Joint on site for Telstra pipe laying works
Wed (09/10) | 09 Oct 2024 | STN243 |  | B2 CD 23.5/44.66m
Wed (09/10) | 09 Oct 2024 | STN240 |  | B2 CD 39.42/39.42
Wed (09/10) | 09 Oct 2024 | BP2-1 | 23 | Rebar cage installation in progress
Wed (09/10) | 09 Oct 2024 | ST216 | Rig 3 | B2 CD 37.1/37.1m, gonna start B3 excavation
Wed (09/10) | 09 Oct 2024 | MH3-4 |  | Inspection ongoing for next layer BRC
Wed (09/10) | 09 Oct 2024 | P44 |  | LE trial trench ongoing
Wed (09/10) | 09 Oct 2024 | BRP60 | BC2 | Excavation temporarily stopped for cutter teeth change
Wed (09/10) | 09 Oct 2024 | DR2 |  | Drilling ongoing for RW62 installation
Wed (09/10) | 09 Oct 2024 | P18 |  | Pile head hacking in progress
Wed (09/10) | 09 Oct 2024 | Zone 2 |  | WH erecting shelter for rest area
Wed (09/10) | 09 Oct 2024 | N1 |  | Ducting works ongoing. Works till 10pm
Wed (09/10) | 09 Oct 2024 | P11 |  | Column formwork closing in progress
Wed (09/10) | 09 Oct 2024 | Zone 2 |  | Telco duct pending casting. Manpower currently on dinner break
Wed (09/10) | 09 Oct 2024 | P4 |  | Formwork closing ongoing
Wed (09/10) | 09 Oct 2024 | P7-1-4 |  | Preboring in progress
Wed (09/10) | 09 Oct 2024 | ST244-245 |  | Preparing to base lean con casting for guidewall construction
Wed (09/10) | 09 Oct 2024 | ST240 |  | Centre bite completed
Wed (09/10) | 09 Oct 2024 | ST243 |  | Grabber excavation completed. Soil disposal ongoin
Wed (09/10) | 09 Oct 2024 | BP2A-1 | 23 | Hanging bar installation ongoing
Wed (09/10) | 09 Oct 2024 | BP4A-2, 2500mm dia | 44 | Preboring started at 1720hrs. Casing installed
Wed (09/10) | 09 Oct 2024 | MH2-10 |  | Preparing to resume 4th layer construction. Today to cast
Wed (09/10) | 09 Oct 2024 | ST243 |  | B2 in progress, 8/44.66m
Wed (09/10) | 09 Oct 2024 | ST240 |  | B2 in progress, 31/39.42m
Thu (10/10) | 10 Oct 2024 | DR2 |  | RW62 in progress. Today Geomotion plan to complete balance 3nos of recharge wells — RW62, RW70, RW72
Thu (10/10) | 10 Oct 2024 | DR2 |  | Retaining wall rebar cutting ongoing
Thu (10/10) | 10 Oct 2024 | ST109 |  | BC1 cutter teeth replacement ongoing
Thu (10/10) | 10 Oct 2024 | ST108 |  | WS joint welding in progress
Thu (10/10) | 10 Oct 2024 | ST146 |  | Guidewall construction ongoing, ST147-148: Continue guidewall excavation
Thu (10/10) | 10 Oct 2024 | BRP62 | BC2 | Excavation temporarily stopped for cutter teeth change. CD 19.2/29.72m
Thu (10/10) | 10 Oct 2024 | DKP18 |  | Coring in progress, 23m
Thu (10/10) | 10 Oct 2024 | BRP53 | BC4 | Excavation in progress, 14/40.27m
Thu (10/10) | 10 Oct 2024 | ST166 |  | Preboring temporarily stopped. Boring bucket damaged, rectification in progress
Thu (10/10) | 10 Oct 2024 | DR1 |  | Base slab rebar (part 1) in progress
Thu (10/10) | 10 Oct 2024 | P32 |  | Soil disposal and manual excavation in progress
Thu (10/10) | 10 Oct 2024 | P44 |  | Continue preboring and casing installation for preboring
Thu (10/10) | 10 Oct 2024 | MH3-4 |  | Left one layer of caisson to reach base
Thu (10/10) | 10 Oct 2024 | MH3-5 |  | Benching on going. Today will deliver precast ring and cast to jacking level
Thu (10/10) | 10 Oct 2024 | ST200 |  | Guidewall trial trench
Thu (10/10) | 10 Oct 2024 | BC3 |  | Maintenance ongoing
Thu (10/10) | 10 Oct 2024 | BP4A-2 | 44 | Bentonite topup ongoing, ST216: WS installation ongoing
Thu (10/10) | 10 Oct 2024 | ST240 |  | Desanding
Thu (10/10) | 10 Oct 2024 | ST243 |  | Rebar cage delivery
Thu (10/10) | 10 Oct 2024 | P18 |  | Pile head trimming to COL. 5/6
Thu (10/10) | 10 Oct 2024 | MH2-10 |  | Formwork support removal
Thu (10/10) | 10 Oct 2024 | N1 |  | Shear links installation works
Thu (10/10) | 10 Oct 2024 | DR2 |  | Geomotion continue to drilling and installation for RW62, RW70 and RW72, WH erecting access
Thu (10/10) | 10 Oct 2024 | DR2 |  | Hirose preparing top plate installation for UKP
Thu (10/10) | 10 Oct 2024 | DR2 |  | Debris rebar cutting and disposal ongoing
Thu (10/10) | 10 Oct 2024 | P51-7 |  | Boring in progress, reached 17.5m
Thu (10/10) | 10 Oct 2024 | P51-DR4 |  | Abandoned drain removal for Power duct work
Thu (10/10) | 10 Oct 2024 | ST109 | BC1 | Gear motor replacement ongoing
Thu (10/10) | 10 Oct 2024 | BRP62 | BC2 | Excavation in progress, 22/29.72m
Thu (10/10) | 10 Oct 2024 | ST146-ST147 |  | Guidewall construction in progres
Thu (10/10) | 10 Oct 2024 | ST150 |  | Guidewall trial trench backfilling
Thu (10/10) | 10 Oct 2024 | DKP18 |  | Boring in progress, 24m
Thu (10/10) | 10 Oct 2024 | P11-1 |  | Column formwork closing in progress
Thu (10/10) | 10 Oct 2024 | P7-1-4 |  | BP Rebar cage lowering in progress
Thu (10/10) | 10 Oct 2024 | BRP53 |  | Excavation in progress
Thu (10/10) | 10 Oct 2024 | ST166 |  | Preboring ongoing
Thu (10/10) | 10 Oct 2024 | DR1 |  | Clearing of vegetation inside canal
Thu (10/10) | 10 Oct 2024 | DR1 |  | Base slab rebar works ongoing
Thu (10/10) | 10 Oct 2024 | DR1 |  | Strut preloading
Thu (10/10) | 10 Oct 2024 | P44 |  | Continue preboring
Thu (10/10) | 10 Oct 2024 | MH3-4 |  | Formwork remove. By this week will reach base slab level
Thu (10/10) | 10 Oct 2024 | MH3-5 |  | Precast ring and cover put. By this week, permanent manhole will cast until jacking level
Thu (10/10) | 10 Oct 2024 | ST243 |  | Hydrofraise hose rectification ongoing
Thu (10/10) | 10 Oct 2024 | ST240 |  | Rebar cage installation in progress, 5/10nos
Thu (10/10) | 10 Oct 2024 | BP4A-2 | 44 | Boring in progress, 20/35.65m
Thu (10/10) | 10 Oct 2024 | ST216 |  | WS lowering in progress
Thu (10/10) | 10 Oct 2024 | ST200 |  | Guidewall rebar works in progress
Thu (10/10) | 10 Oct 2024 | P32 |  | KTC has stopped works for the day
Thu (10/10) | 10 Oct 2024 | DR1 |  | Base slab rebar works in progress. Dayshift team working till 8pm, thereafter nightshift team will take over (rebar works and excavation)
Thu (10/10) | 10 Oct 2024 | ST166 |  | Preboring ongoing
Thu (10/10) | 10 Oct 2024 | DR2 |  | Hacking works ongoing
Thu (10/10) | 10 Oct 2024 | ST108 | BC1 | Cleaning ongoing
Thu (10/10) | 10 Oct 2024 | P44/MH3-4 |  | No more activity
Thu (10/10) | 10 Oct 2024 | ST146-147 |  | Guidewall plan for casting tonight
Thu (10/10) | 10 Oct 2024 | BRP62 | BC2 | Excavation temporarily stopped for cutter wheel cleaning and teeth changing. CD 25/29.72m
Thu (10/10) | 10 Oct 2024 | DKP18 |  | Boring reached 28/38m. Works till 10pm
Thu (10/10) | 10 Oct 2024 | BRP53 |  | Excavation reached 23/40.27m. Now cutter body washing for teeth changing
Thu (10/10) | 10 Oct 2024 | P51-DR4 |  | Wee Guan continue TT to locate water pipe. Now only one team
Thu (10/10) | 10 Oct 2024 | P51-7 |  | Boring in progress, reached 10m depth
Thu (10/10) | 10 Oct 2024 | MH2-10 |  | 4th layer was cast last night
Fri (11/10) | 11 Oct 2024 | N1 |  | Fina inspection done last night. Now railing dismantling for formwork closing
Fri (11/10) | 11 Oct 2024 | P9 |  | Scaffold access erection
Fri (11/10) | 11 Oct 2024 | DR2 |  | Geomotion continue drilling for balance RW62 and RW71. Yesterday completed 2nos (RW70, 72)
Fri (11/10) | 11 Oct 2024 | DR2 |  | KTC continue hacking and excavation for utility support works
Fri (11/10) | 11 Oct 2024 | ST108 |  | 4/8nos rebar cages installed. Balance 4nos have yet to be delivered. Plan for delivery this afternoon
Fri (11/10) | 11 Oct 2024 | P10 |  | Formwork bottom part adjustable jack installation
Fri (11/10) | 11 Oct 2024 | P8-9 |  | Telco duct backfilling
Fri (11/10) | 11 Oct 2024 | TMH2 |  | Top slab rebar works
Fri (11/10) | 11 Oct 2024 | P8-1-1 |  | Boring works
Fri (11/10) | 11 Oct 2024 | P51-7 |  | Boring on going, reached 21.5m
Fri (11/10) | 11 Oct 2024 | BRP46 |  | Preboring in progress
Fri (11/10) | 11 Oct 2024 | DR1 |  | Continue cleaning works inside canal
Fri (11/10) | 11 Oct 2024 | DR1 |  | Base slab (part 1) pending inspection. Plan for casting this afternoon
Fri (11/10) | 11 Oct 2024 | ST200 |  | Guidewall construction in progress. Plan for casting today
Fri (11/10) | 11 Oct 2024 | ST216 |  | Hanging bar lapping ongoing
Fri (11/10) | 11 Oct 2024 | BP4A-2 | 44 | Boring in progress, 25/35.65m
Fri (11/10) | 11 Oct 2024 | MH3-4 |  | Excavation for last layer caisson. Tomorrow to cast
Fri (11/10) | 11 Oct 2024 | P44 |  | Soldier pile installation
Fri (11/10) | 11 Oct 2024 | MH3-5 |  | BRC installation for manhole casting. Today to cast until jacking level
Fri (11/10) | 11 Oct 2024 | P4 |  | Concrete surface hacking for rectification
Fri (11/10) | 11 Oct 2024 | P2 |  | Barricade extension to start utility support
Fri (11/10) | 11 Oct 2024 | MH2-9 |  | Dewatering ongoing
Fri (11/10) | 11 Oct 2024 | MH2-10 |  | Preparing to resume 5th layer. Target to cast tmr
Sat (12/10) | 12 Oct 2024 | P50-5 |  | Casing installed. Tomorrow to continue boring
Sat (12/10) | 12 Oct 2024 | Zone 4 |  | P51-7 casting in progress. This is the 3rd piles cast this week
Sat (12/10) | 12 Oct 2024 | P11 column |  | Preparation for casting
Sat (12/10) | 12 Oct 2024 | N1 |  | Tie rod tightening and tendon duct securing. Formwork and duct alignment inspection today AM
Sat (12/10) | 12 Oct 2024 | MH3-4 |  | Caisson casting done. Left base slab to complete
Sat (12/10) | 12 Oct 2024 | BRP60 |  | Trimming on going
Sat (12/10) | 12 Oct 2024 | BRP53 |  | Cleaning and desanding
Sat (12/10) | 12 Oct 2024 | ST166 |  | Excavated done. Waterstop end plate side trimming
Sat (12/10) | 12 Oct 2024 | STN243 |  | Rebar cage lowering. 3/10 completed
Sat (12/10) | 12 Oct 2024 | BRP46 |  | Bucket changing for preboring
Sat (12/10) | 12 Oct 2024 | STN234 |  | 2nd bite trenching at 27m depth
Sat (12/10) | 12 Oct 2024 | BP4A-2 | 44 | Internal koden test
Sat (12/10) | 12 Oct 2024 | ST208 |  | 1st bite, reached 20.2m
Sat (12/10) | 12 Oct 2024 | ST208-BC3 |  | 1st bite trenching at 20m depth. Gearbox maintenance in progress
Sat (12/10) | 12 Oct 2024 | P34 |  | Manual excavation for utility support installation
Sat (12/10) | 12 Oct 2024 | BRP46-BG1 |  | Pre-boring in progress
Sat (12/10) | 12 Oct 2024 | STN166-BC2 |  | Trimming in progress
Sat (12/10) | 12 Oct 2024 | BRP53-BC4 |  | Trenching completed. Now preparing for trimming
Sat (12/10) | 12 Oct 2024 | P36-37 |  | Excavation for Utility support installation
Sat (12/10) | 12 Oct 2024 | MH3-4 |  | Excavation for 7th layer
Sat (12/10) | 12 Oct 2024 | P44 |  | ERSS installation, SP: 18/46, LL: 5/46
Sat (12/10) | 12 Oct 2024 | Zone 4 |  | Abandoned drain hacking for power duct installation
Sat (12/10) | 12 Oct 2024 | P51-7 |  | Boring in progress
Sat (12/10) | 12 Oct 2024 | P51 |  | TT for ERSS
Sat (12/10) | 12 Oct 2024 | STN108 |  | Casting in progress
Sat (12/10) | 12 Oct 2024 | BRP53-BC4 |  | Trimming in progress
Sat (12/10) | 12 Oct 2024 | STN166 |  | 1 side trimming completed
Sat (12/10) | 12 Oct 2024 | BP2A-1 | 20 | Pre-boring for casing in progress
Sat (12/10) | 12 Oct 2024 | MH2-9 |  | Jacking frame installation
Sat (12/10) | 12 Oct 2024 | MH2-9 |  | Thrust block casting completed
Sat (12/10) | 12 Oct 2024 | MH2-10 |  | Excavation in progress. Plan to cast tomorrow. Tomorrow LCH will be working for both MH2-9 & MH2-10
Sat (12/10) | 12 Oct 2024 | BP4A-2-44 |  | Casting in progress
Sat (12/10) | 12 Oct 2024 | BP2A-1-20 |  | Casing installed. Monday to continue boring. Today HSL working until 10PM for Zone 3. Zone 4 will be working late coz got casting
Sat (12/10) | 12 Oct 2024 | ST243 |  | 9/10 cages lowered down. Tonight to cast
Sat (12/10) | 12 Oct 2024 | ST234 |  | 2nd bite reached 36m
Sat (12/10) | 12 Oct 2024 | P14 |  | Column formwork removal
Sat (12/10) | 12 Oct 2024 | P18 |  | Pier footing rebar work
Sat (12/10) | 12 Oct 2024 | N1 |  | Cross head casting in progress
Sat (12/10) | 12 Oct 2024 | P10 |  | Tonight Wendyng will adjust the jack location
Sat (12/10) | 12 Oct 2024 | P9 |  | Tonight will erect falsework around column
Sun (13/10) | 13 Oct 2024 | P11 |  | Access dismantling ongoing
Sun (13/10) | 13 Oct 2024 | P10 |  | Falsework installation in progress
Sun (13/10) | 13 Oct 2024 | TMH2 |  | Manhole formwork construction in progress
Sun (13/10) | 13 Oct 2024 | Zone 2 |  | HSL no activity
Sun (13/10) | 13 Oct 2024 | ST245 |  | Excavation encountered rebars at 4.5m depth
Sun (13/10) | 13 Oct 2024 | BP2A-1 | 20 | No activity
Sun (13/10) | 13 Oct 2024 | BP4A-2 | 44 | KP installation and casting completed last night. Tmr plan for LSS backfill
Sun (13/10) | 13 Oct 2024 | P32 |  | Excavation ongoing
Sun (13/10) | 13 Oct 2024 | DR1 |  | Base slab (part 1) unable to proceed casting as per planned on Friday due to difference on dwgs. Geotextile unable to install on site. As per RE’s comment, WH to advice on the way forward prior to casting
Sun (13/10) | 13 Oct 2024 | DR1 |  | CGS continue excavation at next section
Sun (13/10) | 13 Oct 2024 | ST166 | BC2 | Trimming ongoing
Sun (13/10) | 13 Oct 2024 | BRP45 |  | Trial trench for guidewall ongoing
Sun (13/10) | 13 Oct 2024 | BRP46 |  | Preboring in progress
Sun (13/10) | 13 Oct 2024 | DR2 |  | Soil trimming ongoing by KTC. Hirose start to install main beam, 1/5nos main beams installed
Sun (13/10) | 13 Oct 2024 | DKP18 |  | Boring machine maintenance ongoing. Thereafter to resume boring
Sun (13/10) | 13 Oct 2024 | BRP60 |  | Hanging bar lapping
Sun (13/10) | 13 Oct 2024 | ST148-150 |  | Guidewall formwork installation in progress
Sun (13/10) | 13 Oct 2024 | ST109 | BC1 | Excavation temporarily stopped. Cutter teeth change
Sun (13/10) | 13 Oct 2024 | MH3-4 |  | No activity
Sun (13/10) | 13 Oct 2024 | P44 |  | Preboring in progress
Sun (13/10) | 13 Oct 2024 | P45 |  | GCE trial trench ongoing
Sun (13/10) | 13 Oct 2024 | P50-5 |  | Boring in progress
Sun (13/10) | 13 Oct 2024 | MH2-10 |  | BRC installation in progress for 5th layer
Sun (13/10) | 13 Oct 2024 | MH2-9 |  | Entry opening hacking ongoing
Sun (13/10) | 13 Oct 2024 | P18 |  | Current status of pier footing rebar work
Sun (13/10) | 13 Oct 2024 | P9 |  | Barricade installation
Sun (13/10) | 13 Oct 2024 | P32 |  | KTC continue soil trimming
Sun (13/10) | 13 Oct 2024 | DR1 |  | Excavation in progress
Sun (13/10) | 13 Oct 2024 | P10 |  | Jack installation for the platform
Sun (13/10) | 13 Oct 2024 | ST166 |  | Trimming in progress
Sun (13/10) | 13 Oct 2024 | DR2 |  | Hirose preparing beam & KTC continue soil trimming
Sun (13/10) | 13 Oct 2024 | DKP18 |  | Boring resume. CD 35/38.3m. The team is working until 5pm today
Sun (13/10) | 13 Oct 2024 | P44 |  | ERSS installation in progress
Sun (13/10) | 13 Oct 2024 | BRP60 |  | Pending casting
Sun (13/10) | 13 Oct 2024 | ST208 |  | Continue 1st bite excavation
Sun (13/10) | 13 Oct 2024 | BRP53 |  | WS removal
Sun (13/10) | 13 Oct 2024 | ST208 |  | B1 in progress, 36.8/37.6m
Sun (13/10) | 13 Oct 2024 | MH2-9 |  | Jacking frame & thrust block casting completed last night. Now ongoing pump installation
Sun (13/10) | 13 Oct 2024 | MH2-10 |  | 5th layer construction ongoing. Today to cast
Sun (13/10) | 13 Oct 2024 | Exit 3 |  | Drilling ongoing for fissure grouting, O-04
Mon (14/10) | 14 Oct 2024 | MH2-9 |  | Entry point hacking ongoing
Mon (14/10) | 14 Oct 2024 | MH2-10 |  | Dewatering in progress. Thereafter to proceed 5th layer formwork dismantling and continue excavation for 6th layer
Mon (14/10) | 14 Oct 2024 | ST234 |  | WS extraction in progress
Mon (14/10) | 14 Oct 2024 | ST109 |  | B2 temporarily stopped due to hydraulic hose leakage. Rectification ongoing. CD 35.3/39m
Mon (14/10) | 14 Oct 2024 | ST148-149 |  | Dewatering & guidewall formwork dismantling ongoing
Mon (14/10) | 14 Oct 2024 | BP2A-1 | 20 | Boring CD @ 24m
Mon (14/10) | 14 Oct 2024 | DKP18 |  | Boring in progress, 38/38.5m. Plan to cast today
Mon (14/10) | 14 Oct 2024 | BRP56 | BC2 | Excavation started
Mon (14/10) | 14 Oct 2024 | BP46 |  | Hacking in progress for trial trench
Mon (14/10) | 14 Oct 2024 | P10 |  | Bottom formwork status
Mon (14/10) | 14 Oct 2024 | TMH2 |  | Top slab to cast today
Mon (14/10) | 14 Oct 2024 | P4 |  | Pile cap cleaning for rectification works
Mon (14/10) | 14 Oct 2024 | P10 |  | Current bottom formwork status
Mon (14/10) | 14 Oct 2024 | TMH2 |  | Top slab casting completed. Levelling ongoing
Mon (14/10) | 14 Oct 2024 | ST245 |  | Reached 10.3/24.1m
Mon (14/10) | 14 Oct 2024 | ST239 |  | Excavation started, ST234: Middle bite completed. Tonight plan for cleaning/desanding. Target to cast tmr
Mon (14/10) | 14 Oct 2024 | BP2A-1 | 20 | Boring reached 25/45.72m
Mon (14/10) | 14 Oct 2024 | BP4A-2 | 44 | Casing removal
Mon (14/10) | 14 Oct 2024 | BRP46 |  | Preboring in progress
Mon (14/10) | 14 Oct 2024 | ST166 |  | Casting in progress, 111/129m3
Mon (14/10) | 14 Oct 2024 | P37 |  | Manual excavation at nearby services ongoing
Mon (14/10) | 14 Oct 2024 | DKP18 |  | Preparing for KP installation
Tue (15/10) | 15 Oct 2024 | N4-N5 |  | Excavation to find end of previously completed telco
Tue (15/10) | 15 Oct 2024 | MH2-9 |  | Entry point hacking ongoing
Tue (15/10) | 15 Oct 2024 | MH2-10 |  | 6th layer excavation in progress
Tue (15/10) | 15 Oct 2024 | Exit 3 |  | Fissure grouting drilling ongoing
Tue (15/10) | 15 Oct 2024 | P51-8 |  | Boring on going. Reached 18m
Tue (15/10) | 15 Oct 2024 | P36 |  | Rebars/debris disposal
Tue (15/10) | 15 Oct 2024 | P36 |  | Installation of flow meter pipes by Geomotion along DR2
Tue (15/10) | 15 Oct 2024 | P37 |  | Excavation ongoing for utility support works
Tue (15/10) | 15 Oct 2024 | ST138-139 |  | Premix removal for guidewall trial trench
Tue (15/10) | 15 Oct 2024 | ST109 |  | WS extraction in progress
Tue (15/10) | 15 Oct 2024 | BRP56 | BC2 | Cutter wheel and teeth replacement ongoing
Tue (15/10) | 15 Oct 2024 | BRP54 | BC4 | Excavation in progress, 24/30.17m
Tue (15/10) | 15 Oct 2024 | BRP46 |  | Preboring in progress
Tue (15/10) | 15 Oct 2024 | P10 |  | Preparation to install side formwork part A
Tue (15/10) | 15 Oct 2024 | P10 |  | Hook eye installation for formwork propping
Tue (15/10) | 15 Oct 2024 | DR1 |  | Base slab (part 1) re-inspection was done and acceptable. Today plan for casting
Tue (15/10) | 15 Oct 2024 | DR1 |  | Continue excavation at next section
Tue (15/10) | 15 Oct 2024 | P32 |  | Excavation ongoing
Tue (15/10) | 15 Oct 2024 | ST208 | BC3 | B2 completed. Now preparing internal koden check before start 3rd bite
Tue (15/10) | 15 Oct 2024 | BP4A-2, BP4A-1(47) | 45 | Trial trench
Tue (15/10) | 15 Oct 2024 | BP2A-1 | 20 | Boring reached 28/45.72m
Tue (15/10) | 15 Oct 2024 | ST234 |  | Rebar cage installation in progress
Tue (15/10) | 15 Oct 2024 | P6-1-1 |  | Boring completed. To cast today
Tue (15/10) | 15 Oct 2024 | MH3-5 |  | LSS backfilling in progress, total 86.5m3. Next stage of work will be platform prepare for jacking
Tue (15/10) | 15 Oct 2024 | P44-P45 |  | TT for JGP grouting. 8nos of TT done
Tue (15/10) | 15 Oct 2024 | P44 |  | Preboring for ERSS installation
Tue (15/10) | 15 Oct 2024 | MH3-4 |  | Excavation to base slab level
Tue (15/10) | 15 Oct 2024 | P10 |  | Formwork installation in progress
Tue (15/10) | 15 Oct 2024 | P18 |  | Pile cap links installation in progress
Tue (15/10) | 15 Oct 2024 | P6-1-1 |  | Casting ongoing
Tue (15/10) | 15 Oct 2024 | ST245 |  | Excavation temporarily stopped due to hydraulic leaking. Rectification ongoing. B1 CD 39/43.53m
Tue (15/10) | 15 Oct 2024 | ST239 |  | B2 in progress
Tue (15/10) | 15 Oct 2024 | BP2A-1 | 20 | Boring reached 30/45.72m
Tue (15/10) | 15 Oct 2024 | ST234 |  | Rebar cage installation, 8/10nos
Tue (15/10) | 15 Oct 2024 | DR1 |  | Base slab casting in progress
Tue (15/10) | 15 Oct 2024 | UKP57 |  | Preboring and casing installation done. Tmr to start boring
Tue (15/10) | 15 Oct 2024 | BRP46 |  | Preboring in progress, 22.3m
Wed (16/10) | 16 Oct 2024 | P10 |  | 1st side form assembly for panel 4&5
Wed (16/10) | 16 Oct 2024 | P35 |  | Recharge well permeability and functional test in progress
Wed (16/10) | 16 Oct 2024 | STN239 |  | B2 CD 20.0/53.22m
Wed (16/10) | 16 Oct 2024 | P51-8 |  | Boring reached 21.6m. Tomorrow to cast
Wed (16/10) | 16 Oct 2024 | BP2A-1 | 20 | Boring CD @ 31.0/45.72m
Wed (16/10) | 16 Oct 2024 | ST138-140 |  | Guidewall trial trench in progress
Wed (16/10) | 16 Oct 2024 | ST123 |  | Trial trench in progress. Found water valve and utility service. Water valve is abandoned. Utility team to confirm power cable is abandoned
Wed (16/10) | 16 Oct 2024 | ST109 |  | WS installation in progress
Wed (16/10) | 16 Oct 2024 | ST103A | BC1 | Excavation started earlier this morning. Currently stopped temporarily due to desander issue. CD 9/34m
Wed (16/10) | 16 Oct 2024 | P37 |  | KTC continue manual excavation at nearby services for utility support works
Wed (16/10) | 16 Oct 2024 | P10 side formwork | NE side | 4/5 built up panels installed. Balance 1 panel to install tonight during non-traffic hours
Wed (16/10) | 16 Oct 2024 | Zone 2 |  | Dismantling of the desanding machine to be shifted to Zone 1
Wed (16/10) | 16 Oct 2024 | MH2-10 |  | Levelling ongoing for 6th layer. Target to cast tonight, dayshift team to continue
Wed (16/10) | 16 Oct 2024 | MH2-9 |  | Entry point hacking completed. Now ongoing pumping system testing
Wed (16/10) | 16 Oct 2024 | Blk 2 |  | Trial trench ongoing for recharge well, RW4
Wed (16/10) | 16 Oct 2024 | ST103A | BC1 | B1 in progress, 20/34m
Wed (16/10) | 16 Oct 2024 | ST109 |  | Rebar cage installation in progress, 5/8nos
Wed (16/10) | 16 Oct 2024 | P44 |  | Preboring casing installation ongoing
Wed (16/10) | 16 Oct 2024 | P51-8 |  | Boring in progress
Wed (16/10) | 16 Oct 2024 | UKP57 |  | Casting completed. KP installation in progress
Wed (16/10) | 16 Oct 2024 | BP2A-1 | 20 | Boring reached 34/45.72m. Encountered G3 layer at 33m at 2:40pm. Works continue till 10pm
Wed (16/10) | 16 Oct 2024 | MH2-9 |  | Continue entry point hacking
Wed (16/10) | 16 Oct 2024 | MH2-10 |  | Hacking and excavation ongoing for 6th layer. Target to cast today
Wed (16/10) | 16 Oct 2024 | Near Gate 5 |  | RG drilling ongoing for inclinometer installation
Wed (16/10) | 16 Oct 2024 | Exit 3 |  | Seongha drilling ongoing for fissure grouting point, I-02
Wed (16/10) | 16 Oct 2024 | N5-N6 |  | Excavation to continue telco duct construction
Wed (16/10) | 16 Oct 2024 | STN245 |  | B2 CD 30.0/43.53m
Thu (17/10) | 17 Oct 2024 | MH2-10 |  | RTO inspection for 6th layer. Today to cast. LCH ended work at 10pm last night, no continuation. This week target to cast another layer on Sunday
Thu (17/10) | 17 Oct 2024 | MH2-9 |  | Preparing for tbm mobilisation
Thu (17/10) | 17 Oct 2024 | P27 |  | Trial trench for RW12
Thu (17/10) | 17 Oct 2024 | P51-8 |  | Boring reached 29.6m, need to go 200mm more to toe. Tonight to cast
Thu (17/10) | 17 Oct 2024 | P32 |  | Manual excavation below SPPG
Thu (17/10) | 17 Oct 2024 | ST138-139 |  | Guidewall formwork installation
Thu (17/10) | 17 Oct 2024 | ST122 |  | Trial trench for guidewall
Thu (17/10) | 17 Oct 2024 | ST103A | BC1 | B2 in progress, 9/34m
Thu (17/10) | 17 Oct 2024 | DR1 |  | Excavation in progress
Thu (17/10) | 17 Oct 2024 | BRP46 |  | Preboring in progres
Thu (17/10) | 17 Oct 2024 | UKP58 |  | In progress. Target to cast and install KP today
Thu (17/10) | 17 Oct 2024 | BRP56 |  | Casting completed
Thu (17/10) | 17 Oct 2024 | Between P36-37 |  | Continue manual soil clearing near services
Thu (17/10) | 17 Oct 2024 | N4-N5 |  | Telco duct excavated for 6m pipe laying. Concrete ordered for slope protection
Thu (17/10) | 17 Oct 2024 | P10 |  | 2nd formwork fabrication, 3/5 built up panels
Thu (17/10) | 17 Oct 2024 | ST109 |  | B-side cage extracted as unable to lower it. Koden check done
Thu (17/10) | 17 Oct 2024 | Near Gate 5 |  | RG drilling ongoing for inclinometer installation
Thu (17/10) | 17 Oct 2024 | Exit 3 |  | Fissure grouting completed 4nos today — I-01, I-03, I-05, I-07
Thu (17/10) | 17 Oct 2024 | Zone 2 |  | HSL material shifting to zone 1
Thu (17/10) | 17 Oct 2024 | MH3-5 |  | Manhole was covered. Preparing to lower down jacking frame. Early next week try to start jacking
Thu (17/10) | 17 Oct 2024 | P45 |  | Hardcore removal and TT for JGP
Thu (17/10) | 17 Oct 2024 | MH3-4 |  | Base slab rebar work. Tomorrow to cast
Thu (17/10) | 17 Oct 2024 | P44 |  | Boom down to demob the rig. Preboring was done
Thu (17/10) | 17 Oct 2024 | ST109 |  | Removal of rebar cage to rectify the cages
Thu (17/10) | 17 Oct 2024 | DR1 |  | CGS excavation to FEL
Thu (17/10) | 17 Oct 2024 | DR1 |  | LE installation and welding of laggin plates
Thu (17/10) | 17 Oct 2024 | BRP46 |  | 2nd point preboring
Thu (17/10) | 17 Oct 2024 | UKP58 |  | Preparing for casting
Thu (17/10) | 17 Oct 2024 | BRP45 |  | 1st bite reached 13.5m
Thu (17/10) | 17 Oct 2024 | P31-32 |  | Excavation on going by KTC
Thu (17/10) | 17 Oct 2024 | P18 |  | Pier footing casting in progress
Thu (17/10) | 17 Oct 2024 | P10 |  | Platform erection for cross head rebar work
Thu (17/10) | 17 Oct 2024 | P10 |  | Access erection for cross head rebar work
Thu (17/10) | 17 Oct 2024 | P9 |  | Soffit plywood placing
Thu (17/10) | 17 Oct 2024 | P4 |  | KTC already stopped backfilling work. Tomorrow to resume
Thu (17/10) | 17 Oct 2024 | ST245 |  | Cage A (2/4) and Cage B (2/4 cages in progress). Tonight to cast
Thu (17/10) | 17 Oct 2024 | ST239 |  | 2nd bite, reached 34m
Thu (17/10) | 17 Oct 2024 | P51-8 |  | Tremie pipe lowering
Fri (18/10) | 18 Oct 2024 | MH2-10 |  | 6th layer cast yesterday. Today will dismantle formwork and then excavate next laye
Fri (18/10) | 18 Oct 2024 | MH2-9 |  | Today plan to start jacking after lunch
Fri (18/10) | 18 Oct 2024 | STN245 |  | Casting has completed
Fri (18/10) | 18 Oct 2024 | N4-N5 |  | Preparation for telco duct pipe laying
Fri (18/10) | 18 Oct 2024 | BP2A-1 | 20 | Boring CD @ 40.0/45.72m
Fri (18/10) | 18 Oct 2024 | P12 |  | Main viaduct pad footing to start installation after lunch
Fri (18/10) | 18 Oct 2024 | ST122 | half | Trial trench completed. No services here
Fri (18/10) | 18 Oct 2024 | ST139 |  | Guidewall formwork dismantling, ST137-136: Premix hacking for trial trench and guidewall construction
Fri (18/10) | 18 Oct 2024 | ST109 |  | Minor damage on rebar cage rectifying on site. One of the bottom cages were badly damaged and a new one has been ordered for new fabrication. Plan for delivery to site tmr
Fri (18/10) | 18 Oct 2024 | P2 |  | Premix hacking for ERSS TT
Fri (18/10) | 18 Oct 2024 | P37 |  | Continue manual excavation along services
Fri (18/10) | 18 Oct 2024 | MH2-9 |  | Setting up laser alignment before start jacking
Fri (18/10) | 18 Oct 2024 | MH2-10 |  | 7th layer hacking & excavation in progress. Target to cast Sunday
Fri (18/10) | 18 Oct 2024 | P27 |  | Hand augering in progress for recharge well, RW11
Fri (18/10) | 18 Oct 2024 | Blk 2 |  | Geomotion mobilised rig replacement for recharge well works
Fri (18/10) | 18 Oct 2024 | P32 |  | Excavation in progress
Fri (18/10) | 18 Oct 2024 | DR1 |  | Plate load test ongoing
Fri (18/10) | 18 Oct 2024 | BRP45 | BC4 | Cutter teeth changing ongoing
Fri (18/10) | 18 Oct 2024 | BRP46 |  | Preboring in progress
Fri (18/10) | 18 Oct 2024 | UKP59 |  | Unable to start. Boring machine breakdown, rectification ongoing
Fri (18/10) | 18 Oct 2024 | P33 |  | Scaffold erection for c-channel installation for utility support
Fri (18/10) | 18 Oct 2024 | BRP56 |  | LSS backfill
Fri (18/10) | 18 Oct 2024 | P37 |  | Hirose preparing beam for utility support works
Fri (18/10) | 18 Oct 2024 | DR1 |  | Wall rebar inspection was done (part 1)
Fri (18/10) | 18 Oct 2024 | MH3-4 |  | Pending base slab casting
Fri (18/10) | 18 Oct 2024 | ST103A | BC1 | WS trimming ongoing, 29/34m
Fri (18/10) | 18 Oct 2024 | BP2A-1 | 20 | Boring reached 43/45.72m. Target to cast tmr
Fri (18/10) | 18 Oct 2024 | P44 |  | Preboring completed. Now no activity
Fri (18/10) | 18 Oct 2024 | MH3-4 |  | Base slab rebar work was done. Concrete on the way
Fri (18/10) | 18 Oct 2024 | MH3-5 |  | Jacking frame installation on going
Fri (18/10) | 18 Oct 2024 | P45 |  | TT and pipe sleeves installation
Fri (18/10) | 18 Oct 2024 | P46-1 |  | Boring reached 23m. Tomorrow to cast
Fri (18/10) | 18 Oct 2024 | ST122 |  | Preparing for guidewall rebar work
Fri (18/10) | 18 Oct 2024 | ST109 |  | Rebar cage rectification
Fri (18/10) | 18 Oct 2024 | DR2 |  | Exposing of Power duct to provide support
Fri (18/10) | 18 Oct 2024 | BRP56 |  | LSS backfilling work
Fri (18/10) | 18 Oct 2024 | DR1 |  | Lagging plate installation by LE and PLT by woh hup
Fri (18/10) | 18 Oct 2024 | P17 |  | Hardcore clear and to continue soil backfilling
Fri (18/10) | 18 Oct 2024 | P10 |  | Cross head rebar work
Fri (18/10) | 18 Oct 2024 | ST239 |  | Loosening of waterstop end plate for removal
Fri (18/10) | 18 Oct 2024 | MH2-10 |  | Excavation for next layer caisson casting. Working until 10PM
Fri (18/10) | 18 Oct 2024 | MH2-9 |  | Slurry pipe installation for jacking work
Fri (18/10) | 18 Oct 2024 | MH3-4 |  | Base slab casting was done
Sat (19/10) | 19 Oct 2024 | ST244 |  | Continue grabbing. Chieselling will stop for tonight. I heard receive feedback from LVC for Chiselling. They feedback on vibration from chiselling
Sat (19/10) | 19 Oct 2024 | P8 |  | LE rig and vibro on site
Sat (19/10) | 19 Oct 2024 | BRP45 |  | 1st bite excavation in progress. Reached 16m
Sat (19/10) | 19 Oct 2024 | DR1 |  | Rebar work for drain work
Sat (19/10) | 19 Oct 2024 | ST162 |  | Shifting of BC cutter to start excavation
Sat (19/10) | 19 Oct 2024 | BC cutter No-1 |  | Replacing cutter hydraulic hose. Left one to complete. Tonight to resume excavation
Sat (19/10) | 19 Oct 2024 | P45 |  | TT for GI works
Sat (19/10) | 19 Oct 2024 | ST122 |  | Guidewall rebar installation
Sat (19/10) | 19 Oct 2024 | ST103-BC1 |  | Trimming in progress. Hydraulic hose leaking, cutter body hoist up for rectification
Sat (19/10) | 19 Oct 2024 | P36-37 |  | Utility support installation. Primary beam installation in progress
Sat (19/10) | 19 Oct 2024 | DR1 |  | Slab rebar works
Sat (19/10) | 19 Oct 2024 | BRP54 |  | LSS backfilling
Sat (19/10) | 19 Oct 2024 | UKP59 |  | Casing installed. BG repair works in progress
Sat (19/10) | 19 Oct 2024 | BRP45-BC4 |  | 1st bite trenching at 15.9m. Teeth changing
Sat (19/10) | 19 Oct 2024 | P31-32 |  | Excavation to roof slab level
Sat (19/10) | 19 Oct 2024 | BP2A-1 | 48 | Preparation for pre-boring and casing installation
Sat (19/10) | 19 Oct 2024 | BP2A-1 | 20 | Rebar cage lowering
Sat (19/10) | 19 Oct 2024 | STN244 |  | Chiselling in progress
Sat (19/10) | 19 Oct 2024 | N4-N5 |  | Excavation completed to lay 12m pipe. Concrete ordered for lean casting
Sat (19/10) | 19 Oct 2024 | P9 1st part bottom formwork |  | Runner beam installation in progress
Sat (19/10) | 19 Oct 2024 | P8 |  | Boring rig assembly
Sat (19/10) | 19 Oct 2024 | P10 |  | Continue rebar work for cross head
Sat (19/10) | 19 Oct 2024 | TMH02 |  | Manhole neck casting was done
Sat (19/10) | 19 Oct 2024 | MH2-10 |  | LCH installation of caisson casting. Tonight plan to cast. Casting will be late. 7th layer
Sat (19/10) | 19 Oct 2024 | MH2-9 |  | No activity already
Sat (19/10) | 19 Oct 2024 | P17 |  | Backfilling to stump level to complete today
Sat (19/10) | 19 Oct 2024 | BP2A-1-20 |  | Casting completed
Sat (19/10) | 19 Oct 2024 | ST239 |  | Cage A (5/6 done). Cage B (5/6 done). Tonight to cast
Sun (20/10) | 20 Oct 2024 | MH2-10 |  | Formwork closing. Concrete on the way
Sun (20/10) | 20 Oct 2024 | P9 |  | Runner placing and preparing cross head formwork
Sun (20/10) | 20 Oct 2024 | P10 |  | Continue rebar work for cross head
Sun (20/10) | 20 Oct 2024 | DR1 |  | Now no activity due to rain
Mon (21/10) | 21 Oct 2024 | P10 |  | Tendon duct pipe installation
Mon (21/10) | 21 Oct 2024 | P9-2 |  | Preparation for column hacking to correct level
Mon (21/10) | 21 Oct 2024 | P8 |  | Balance 2 side TT in progress. Plan to start pre-boring tomorrow
Mon (21/10) | 21 Oct 2024 | MH3-5 |  | Entry opening hacking for pipe jacking to MH3-4. Tentative to complete by tomorrow
Mon (21/10) | 21 Oct 2024 | Zone 4 |  | TT for JGP testing
Mon (21/10) | 21 Oct 2024 | STN244 |  | B1 CD 11.6/44.3m
Mon (21/10) | 21 Oct 2024 | BRP46 |  | P3 Preboring CD 18/27.27m
Mon (21/10) | 21 Oct 2024 | ST103A | Rig 1 | Excavation has completed, preparing for final koden check
Mon (21/10) | 21 Oct 2024 | MH2-10 |  | 8th layer excavation is in progress
Mon (21/10) | 21 Oct 2024 | P10 |  | Rebar installation and PT duct installation continue
Mon (21/10) | 21 Oct 2024 | P17 |  | Column rebar cage preparation for lifting and installation
Tue (22/10) | 22 Oct 2024 | BRP45 |  | B2 in progress
Tue (22/10) | 22 Oct 2024 | P36 |  | Manual excavation ongoing below starhub/SPPG, Cutting of abandoned water pipe and slope trimming ongoing
Tue (22/10) | 22 Oct 2024 | DR1 |  | Welding ongoing between water seepage area
Tue (22/10) | 22 Oct 2024 | P44 |  | Now no activity
Tue (22/10) | 22 Oct 2024 | P43 |  | Platform preparation and plant set up for balance bored piles work
Tue (22/10) | 22 Oct 2024 | MH3-5 to MH3-4 |  | All jacking pipes delivery. Tomorrow or Wednesday can start jacking work
Tue (22/10) | 22 Oct 2024 | MH3-5 |  | Soft eye hacking
Tue (22/10) | 22 Oct 2024 | Blk 4 |  | HSL boring machine no activity. Machine plan to shift to P44 area
Tue (22/10) | 22 Oct 2024 | BRP46 |  | Preboring
Tue (22/10) | 22 Oct 2024 | Zone 1 |  | Crawler crane body on site. Today to assemble
Tue (22/10) | 22 Oct 2024 | N4-N5 |  | Telco duct formwork dismantling. To backfill immediately after formwork dismantling
Tue (22/10) | 22 Oct 2024 | MH2-9 |  | Preparing to resume pipe jacking. Current status: 2/30nos completed
Tue (22/10) | 22 Oct 2024 | MH2-10 |  | Hacking and excavation in progress for 8th layer
Tue (22/10) | 22 Oct 2024 | BRP13 |  | Cables clearing ongoing, witnessed by utility team. All these are abandoned
Tue (22/10) | 22 Oct 2024 | BRP14 |  | Guidewall formwork in progress. Plan for casting today
Tue (22/10) | 22 Oct 2024 | BP2B-1 | 48 | Boring in progress, 27/36.09m
Tue (22/10) | 22 Oct 2024 | P51-9 |  | Boring in progress, reached 24m
Tue (22/10) | 22 Oct 2024 | DR1 |  | Base slab has been cast earlier this morning
Wed (23/10) | 23 Oct 2024 | P8 |  | Pre-boring in progress
Wed (23/10) | 23 Oct 2024 | P9 |  | Falsework erection resume
Wed (23/10) | 23 Oct 2024 | P44 |  | Delivery of soldier pile. Today to continue installation
Wed (23/10) | 23 Oct 2024 | Zone 4 |  | Wee guan materials clearing and demobilisation
Wed (23/10) | 23 Oct 2024 | BRP14 |  | Pre-excavation in progress to start trenching
Wed (23/10) | 23 Oct 2024 | BP2A-1 | 48 | No more activity from HSL
Wed (23/10) | 23 Oct 2024 | BRP 29&30 |  | Guidewall formwork closing
Wed (23/10) | 23 Oct 2024 | P31-32 |  | Excavation to roof level continue until 10pm
Wed (23/10) | 23 Oct 2024 | ST162-BC2 |  | Trimming in progress
Wed (23/10) | 23 Oct 2024 | P36 |  | Excavation for Utility support installation
Wed (23/10) | 23 Oct 2024 | P36-37 |  | Installation of secondary beams for Utility support
Wed (23/10) | 23 Oct 2024 | ST109 |  | Cleaning in progress
Wed (23/10) | 23 Oct 2024 | P44 |  | Today 6 nos soldier pile installed and 5 nos steel plate installed
Wed (23/10) | 23 Oct 2024 | P47-4 |  | Boring works in progress, 10m depth
Thu (24/10) | 24 Oct 2024 | ST109 | BC1 | Mud pump rectification ongoing
Thu (24/10) | 24 Oct 2024 | ST162 | BC2 | B3 in progress
Thu (24/10) | 24 Oct 2024 | P37 |  | Utility support works in progress
Thu (24/10) | 24 Oct 2024 | DR1 |  | Base slab rebar works in progress. To cast today
Thu (24/10) | 24 Oct 2024 | BRP46 |  | Preboring in progress
Thu (24/10) | 24 Oct 2024 | P32 |  | Currently no activit
Thu (24/10) | 24 Oct 2024 | BRP29, BRP30 |  | Guidewall cast
Thu (24/10) | 24 Oct 2024 | BRP25, BRP26 |  | Hacking ongoing for guidewall trial trench
Thu (24/10) | 24 Oct 2024 | BRP15 |  | Hacking ongoing for guidewall trial trench
Thu (24/10) | 24 Oct 2024 | BRP14 |  | Excavation in progress, 15/38.4m
Thu (24/10) | 24 Oct 2024 | BP2B-1 | 48 | Boring in progress, 34.5/36.09m. Encountered first layer G3 at 26m on 22 Oct
Thu (24/10) | 24 Oct 2024 | BC3 |  | Currently no activity
Thu (24/10) | 24 Oct 2024 | MH3-5 to MH3-4 |  | Jacking in progress. 5/27 pipes in progress
Thu (24/10) | 24 Oct 2024 | P47-4 |  | Boring in progress, reached 15m
Thu (24/10) | 24 Oct 2024 | P9-2 |  | Pier hacking to correct level in progress
Thu (24/10) | 24 Oct 2024 | P8 |  | Preboring for ERSS ongoing. 6/52 nos. completed
Thu (24/10) | 24 Oct 2024 | P25 |  | Seongha drilling ongoing for fissure grout point, I-20
Thu (24/10) | 24 Oct 2024 | BP6 | 13 | Trial trench completed. Old lamp post cable cut
Thu (24/10) | 24 Oct 2024 | BP6 | 14 | Hacking ongoing for BP trial trench
Thu (24/10) | 24 Oct 2024 | P24 |  | Bachy guidewall hacking ongoing
Thu (24/10) | 24 Oct 2024 | ST244 |  | WS extraction in progress
Thu (24/10) | 24 Oct 2024 | Exit 3 |  | RG drilling ongoing for inclinometer installation
Thu (24/10) | 24 Oct 2024 | P44 |  | Unloading of soldier piles and continue installation
Thu (24/10) | 24 Oct 2024 | MH2-9 |  | Pipe jacking #12 in progress
Thu (24/10) | 24 Oct 2024 | MH2-10 |  | 9th layer hacking and excavation ongoing
Thu (24/10) | 24 Oct 2024 | P17 |  | Column formwork closing in progress
Thu (24/10) | 24 Oct 2024 | P18 |  | Stump formwork closing in progress
Thu (24/10) | 24 Oct 2024 | N4-N5 |  | Telco duct area backfilled and compacted. Progressively dismantling formwork and cast base lean con
Thu (24/10) | 24 Oct 2024 | P10 |  | Continue tendon duct pipe installation for crosshead
Thu (24/10) | 24 Oct 2024 | P9-2 |  | Hacking ongoing
Thu (24/10) | 24 Oct 2024 | Zone 2 |  | LE works done for the day
Thu (24/10) | 24 Oct 2024 | BP4A-1 | 46 | Preboring done, casing installed
Thu (24/10) | 24 Oct 2024 | BC3 |  | No activity
Thu (24/10) | 24 Oct 2024 | BP2B-1 | 48 | Boring reached 35.6/36.09m. Tmr plan for pile casting
Thu (24/10) | 24 Oct 2024 | DR1 |  | Base slab rebar works almost completed. Tonight to cast
Thu (24/10) | 24 Oct 2024 | BP6 | 14 | Trial trench ongoing, found abandoned 300mm dia water pipe
Thu (24/10) | 24 Oct 2024 | BRP14 |  | Excavation in progress, 28/38.4m
Thu (24/10) | 24 Oct 2024 | BRP46 |  | Preboring ongoing. Noise balloon setup
Thu (24/10) | 24 Oct 2024 | ST162 |  | B3 in progress
Thu (24/10) | 24 Oct 2024 | MH2-9 |  | Preparing to resume pipe jacking. 8/30nos pipes done
Thu (24/10) | 24 Oct 2024 | MH2-10 |  | Hacking and excavation in progress for 9/16 layers. Target to cast 9th layer tmr
Thu (24/10) | 24 Oct 2024 | P32 |  | Manual clearing of soil below SPPG
Fri (25/10) | 25 Oct 2024 | DR1 |  | CH43-70: Base slab cast, CH82-70: 1st lift wall cast
Fri (25/10) | 25 Oct 2024 | P36-37 |  | Preparing for utility support installation
Fri (25/10) | 25 Oct 2024 | ST162 | BC2 | Cutter teeth changing ongoing. B3 CD 41m
Fri (25/10) | 25 Oct 2024 | BRP46 |  | Preboring ongoing
Fri (25/10) | 25 Oct 2024 | P10 |  | Tendon duct installation at south side today to start
Fri (25/10) | 25 Oct 2024 | P33 |  | Clearing premix/RCA
Fri (25/10) | 25 Oct 2024 | P32 |  | Currently no excavation and other activity
Fri (25/10) | 25 Oct 2024 | BRP26 |  | Guidewall excavation ongoing
Fri (25/10) | 25 Oct 2024 | BRP25 |  | Preparing guidewall rebar installation
Fri (25/10) | 25 Oct 2024 | BRP14 |  | Excavation in progress, 36/38.4m
Fri (25/10) | 25 Oct 2024 | BRP15 |  | Guidewall rebar installation ongoing
Fri (25/10) | 25 Oct 2024 | BP2B-1 | 48 | Toe level checked, 36.2m. Now preparing for rebar cage & KP installation
Fri (25/10) | 25 Oct 2024 | ST217 | BC3 | B1 excavation resume
Fri (25/10) | 25 Oct 2024 | ST244 |  | Desanding completed. Final koden check in progress
Fri (25/10) | 25 Oct 2024 | Exit 3 |  | RG drilling ongoing for inclinometer installation
Fri (25/10) | 25 Oct 2024 | MH3-5 |  | Pipe no- 10 jacking in progress
Fri (25/10) | 25 Oct 2024 | P45-P46 |  | Continue investigation and exposing of cable
Fri (25/10) | 25 Oct 2024 | MH2-10 |  | 9th layer rebar works in progress
Fri (25/10) | 25 Oct 2024 | MH2-9 |  | Pipe 14/30 in progress
Fri (25/10) | 25 Oct 2024 | ST217 |  | B1 in progress, 26/37.1m
Fri (25/10) | 25 Oct 2024 | BP2B-1 | 48 | KP installation in progress
Fri (25/10) | 25 Oct 2024 | BRP15 |  | Guidewall ready to cast
Fri (25/10) | 25 Oct 2024 | BRP17 |  | Guidewall trial trench ongoing
Fri (25/10) | 25 Oct 2024 | BRP25 |  | Guidewall formwork installation in progress
Fri (25/10) | 25 Oct 2024 | MH3-5 |  | Pipe jacking #11 ongoing
Fri (25/10) | 25 Oct 2024 | Zone 4 |  | Telstra pipe laying 8m done today. Backfilling ongoing
Fri (25/10) | 25 Oct 2024 | P51-10 |  | Preparing to start boring
Fri (25/10) | 25 Oct 2024 | ST109 |  | Desanding completed. Now preparing final koden check
Fri (25/10) | 25 Oct 2024 | ST162 |  | B3 completed. Now preparing for trimming
Fri (25/10) | 25 Oct 2024 | DR1 |  | Wall rebar works continue
Fri (25/10) | 25 Oct 2024 | BRP46 |  | Preboring completed. Boring machine shift to BRP45
Fri (25/10) | 25 Oct 2024 | BRP45 |  | Preboring in progress
Fri (25/10) | 25 Oct 2024 | Zone 3 |  | Concrete barriers installation for vehicle access diversion in progress
Fri (25/10) | 25 Oct 2024 | Zone 2 |  | Telco duct pipes casting completed 12m
Fri (25/10) | 25 Oct 2024 | P10 | north side | Tendon duct pipes and RWDP installation completed. Now ongoing support rebar installation
Fri (25/10) | 25 Oct 2024 | P8 |  | Preboring ongoing till 7pm
Fri (25/10) | 25 Oct 2024 | ST244 |  | Rebar cage installation in progress, 7/10nos
Fri (25/10) | 25 Oct 2024 | MH3-5 |  | Pipe No-12 jacking in progress
Fri (25/10) | 25 Oct 2024 | BRP14 |  | Desanding
Fri (25/10) | 25 Oct 2024 | BRP15 |  | Guidewall cast
Fri (25/10) | 25 Oct 2024 | BRP17 |  | Trial trench in progress
Fri (25/10) | 25 Oct 2024 | BP2B-1 | 48 | Casting done
Fri (25/10) | 25 Oct 2024 | P51 |  | Yesterday HSL work late, so afternoon only they will come
Fri (25/10) | 25 Oct 2024 | MH2-9 |  | Preparing to resume pipe jacking. Current status: 13/30nos
Fri (25/10) | 25 Oct 2024 | MH2-10 |  | Preparing 9th layer construction. Today to cast
Fri (25/10) | 25 Oct 2024 | P45-46 |  | Trial pit to assit SPPG on to trace cable fault
Fri (25/10) | 25 Oct 2024 | P33 |  | Manual soil clearing below SPPG/Starhub
Sat (26/10) | 26 Oct 2024 | Zone 3 Fissure Grout, bet P25-P24 |  | Pt. O-04 drilling works in progress
Sat (26/10) | 26 Oct 2024 | BP2B-1 | 48 | LSS backfilling preparation
Sat (26/10) | 26 Oct 2024 | BP4A-1 | 46 | Boring works in progress, current depth 26m
Sat (26/10) | 26 Oct 2024 | Exit 2 ST217 |  | 2nd bite excavation in progress, current depth 13m
Sat (26/10) | 26 Oct 2024 | Bet. P33-P32 |  | Manual Excavation for utility support installation ongoing
Sat (26/10) | 26 Oct 2024 | BRP-45 |  | 1st bite preboring ongoing, current depth 19.8m
Sat (26/10) | 26 Oct 2024 | BRP-46 |  | Preparation to start trenching works
Sat (26/10) | 26 Oct 2024 | P36-P37 |  | Manual excavation and utility support installation ongoing
Sat (26/10) | 26 Oct 2024 | DR-1 |  | Drain wall rebar and formwork installation works
Sat (26/10) | 26 Oct 2024 | ST162 |  | Trenching completed. Final koden check in progress
Sat (26/10) | 26 Oct 2024 | ST-139 |  | 1st bite excavation, current depth 21.5m/34.5m
Sat (26/10) | 26 Oct 2024 | ST-109 |  | Rebar cages lowering and lapping in progress. 3/8 completed
Sat (26/10) | 26 Oct 2024 | ST-123 |  | Trial trench for Guidewall in progress
Sat (26/10) | 26 Oct 2024 | P44 |  | LE steel plate arranging in progress
Sat (26/10) | 26 Oct 2024 | MH3-5 |  | Pipe jacking for pipe no.14 ongoing
Sat (26/10) | 26 Oct 2024 | Near MH3-5 |  | Powergas lane closed for link up works. Premix hacking in progress
Sat (26/10) | 26 Oct 2024 | Zone 4 |  | Continue manual excavation works to expose the cables. SPPG repair team will come back in the afternoon
Sat (26/10) | 26 Oct 2024 | P51-10 |  | BP boring in progress, current depth 17.5m
Sat (26/10) | 26 Oct 2024 | P50 |  | Trial trench in progress for Telstra cable pipe laying works
Sat (26/10) | 26 Oct 2024 | MH2-10 |  | Excavation for 10th layer ongoing
Sat (26/10) | 26 Oct 2024 | MH2-9 |  | Pipe jacking for pipe no. 16 completed
Sat (26/10) | 26 Oct 2024 | P18 |  | Column stump casting completed
Sat (26/10) | 26 Oct 2024 | P17 |  | Scaffold installation for column casting ongoing. To cast tmr
Sat (26/10) | 26 Oct 2024 | N4-N3 |  | Preparation for 12m base lean concrete for telco duct
Sat (26/10) | 26 Oct 2024 | P10 |  | Crosshead tendon duct at south side and shear links installation works
Sat (26/10) | 26 Oct 2024 | P9 |  | Pier hacking to correct level in progress
Sat (26/10) | 26 Oct 2024 | P8 |  | Preboring for ERSS installation
Sat (26/10) | 26 Oct 2024 | Zone 1 |  | LCH plastering works for new sewer line to existing sewer line ongoing
Sat (26/10) | 26 Oct 2024 | P4 |  | Backfilling works in progress
Sat (26/10) | 26 Oct 2024 | P2-6 |  | BP boring in progress, casing installed. Current depth 8m
Sat (26/10) | 26 Oct 2024 | BP4A-1 | 46 | Boring works in progress, current depth 31m
Sat (26/10) | 26 Oct 2024 | BP2B-1 | 48 | LSS backfilling completed
Sat (26/10) | 26 Oct 2024 | Exit 2 ST217 |  | 2nd bite excavation in progress, current depth 31m
Sat (26/10) | 26 Oct 2024 | BRP-14 |  | Preparation for casting
Sat (26/10) | 26 Oct 2024 | BRP-26 |  | Guidewall casting in progress
Sat (26/10) | 26 Oct 2024 | Bet. P33-P32 |  | Continue Manual Excavation for utility support installation
Sat (26/10) | 26 Oct 2024 | BRP-45 |  | 1st bite preboring ongoing, current depth 21.8m
Sat (26/10) | 26 Oct 2024 | BRP-46 |  | 3rd bite trenching in progress, current depth 11.5m
Sat (26/10) | 26 Oct 2024 | DR-1 |  | Continue wall formwork installation works
Sat (26/10) | 26 Oct 2024 | ST-162 |  | Rebar cages lowering and lapping in progress, 3/8 nos. completed
Sat (26/10) | 26 Oct 2024 | BRP-59 |  | Trenching ongoing, current depth 8.9m
Sat (26/10) | 26 Oct 2024 | ST-139 |  | 1st bite excavation, current depth 29m/34.5m
Sat (26/10) | 26 Oct 2024 | ST-109 |  | Rebar cages lowering and lapping in progress. 6/8 completed
Sat (26/10) | 26 Oct 2024 | P44 |  | LE ERSS installation completed
Sat (26/10) | 26 Oct 2024 | MH3-5 |  | Pipe no. 16 pipe jacking ongoing
Sat (26/10) | 26 Oct 2024 | Near MH3-5 |  | Powergas preparation for link up works tonight
Sat (26/10) | 26 Oct 2024 | Zone 4 |  | SPPG spiked the damaged cables. Repairing works in progress
Sat (26/10) | 26 Oct 2024 | P51-10 |  | BP boring in progress, current depth 20m
Sat (26/10) | 26 Oct 2024 | STN217 |  | Trimming in progress
Sat (26/10) | 26 Oct 2024 | BRP14 |  | Casting on going. Last lorry, total 65 m3
Sat (26/10) | 26 Oct 2024 | BRP45-BG1 |  | Pre-boring in progress, depth 23.7m
Sat (26/10) | 26 Oct 2024 | BRP46-BC4 |  | 1st bite trenching at 13.5m, teeth replacement
Sat (26/10) | 26 Oct 2024 | DR1 |  | Drain wall casting in progress
Sat (26/10) | 26 Oct 2024 | STN162 |  | Rebar cage lowering, 5/8 cages installed
Sat (26/10) | 26 Oct 2024 | BRP59-BC2 |  | Trenching at 15m depth
Sat (26/10) | 26 Oct 2024 | STN139-BC1 |  | 1st bite trenching at 31m depth . Cutter body up for teeth replacement
Sat (26/10) | 26 Oct 2024 | STN109 |  | Rebar cage lowering in progress. 7/8 cages installed
Sat (26/10) | 26 Oct 2024 | P10 |  | Tendon duct pipe installation in progress
Sat (26/10) | 26 Oct 2024 | ST244 |  | Bachy last panel casting in progress
Sat (26/10) | 26 Oct 2024 | BP6 | 14 | Trial trench completed. Pending utility team to check for removal of utility
Sat (26/10) | 26 Oct 2024 | BP6 | 11 | Trial trench completed. Pending utility team to check for removal of utility
Sun (27/10) | 27 Oct 2024 | P17 |  | Concrete ordered for column casting
Sun (27/10) | 27 Oct 2024 | N4-N3 |  | Teleco duct laying. Today plan for 12m
Sun (27/10) | 27 Oct 2024 | P14 |  | Column formwork removal
Sun (27/10) | 27 Oct 2024 | P10 |  | Rebar inspection for half span. Can continue with formwork closing
Sun (27/10) | 27 Oct 2024 | P9 |  | No activity today
Sun (27/10) | 27 Oct 2024 | MH3-5 to MH3-4 |  | Pipe No-21 jacking in progress. Today or tomorrow can complete jacking
Sun (27/10) | 27 Oct 2024 | P51-10 |  | Boring in progress, reached 22.5m
Sun (27/10) | 27 Oct 2024 | ST109 |  | Casting done
Sun (27/10) | 27 Oct 2024 | BC cutter 1 |  | Cutter teeth replacement
Sun (27/10) | 27 Oct 2024 | BRP59 |  | Cleaning in progress
Sun (27/10) | 27 Oct 2024 | DR2 |  | Manual excavation for cable support installation
Sun (27/10) | 27 Oct 2024 | ST162 |  | Rebar cage lowering
Sun (27/10) | 27 Oct 2024 | BRP46 |  | 1st bite reached 13.8m
Sun (27/10) | 27 Oct 2024 | DR1 |  | Continue wall formwork closing
Sun (27/10) | 27 Oct 2024 | P10 |  | Links installation 60% completed, 3W+1S
Sun (27/10) | 27 Oct 2024 | P17 |  | Column casting in progress
Sun (27/10) | 27 Oct 2024 | P9 |  | No activity as of now
Sun (27/10) | 27 Oct 2024 | P9 |  | Started formwork closing
Sun (27/10) | 27 Oct 2024 | South ramp- MH5-1 |  | Preparation to block the old sewer pipe
Sun (27/10) | 27 Oct 2024 | BC cutter 1 |  | Continue machine maintenance
Sun (27/10) | 27 Oct 2024 | BRP45 |  | 2nd point preboring in progress
Sun (27/10) | 27 Oct 2024 | ST217 |  | Waterstop end plate trimming for removal
Sun (27/10) | 27 Oct 2024 | STN217 |  | Trimming continue. C-lug welding
Sun (27/10) | 27 Oct 2024 | STN162 |  | Rebar cage lowering, 6/8 cages installed. Hoisting 7th cage for lapping
Sun (27/10) | 27 Oct 2024 | BRP59-BC2 |  | Trenching at 23m depth
Sun (27/10) | 27 Oct 2024 | STN139-BC1 |  | 1st bite trenching at 32.3m depth
Sun (27/10) | 27 Oct 2024 | STN109 |  | Casting in progress, running volume 38.5 m5. Est 260 m3
Sun (27/10) | 27 Oct 2024 | TDP10 |  | Trial trench in progress
Mon (28/10) | 28 Oct 2024 | P17 |  | Column cast yesterday. Curing in progress
Mon (28/10) | 28 Oct 2024 | Bet. N3-N4 |  | 12m telco duct to cast today. Continue excavation for telco duct in progress
Mon (28/10) | 28 Oct 2024 | P10 |  | Crosshead tendon duct and rebar installation at south side in progress
Mon (28/10) | 28 Oct 2024 | MH2-9 |  | Pipe jacking completed 23/30nos
Mon (28/10) | 28 Oct 2024 | MH2-10 |  | Layer 10 in progress. Today to cast
Mon (28/10) | 28 Oct 2024 | BP4A-1 | 46 | Boring CD 35.6/39.196m
Mon (28/10) | 28 Oct 2024 | ST139 | BC1 | B1 CD 34.5m
Mon (28/10) | 28 Oct 2024 | BRP45 | BG01 | P2 Preboring CD 22.3/24.67m
Mon (28/10) | 28 Oct 2024 | ST124-125 |  | Guidewall rebar works in progress, ST126-127: Guidewall trial trench ongoing
Mon (28/10) | 28 Oct 2024 | Near BC2 |  | Hacking ongoing to divert bentonite pipe alignment
Mon (28/10) | 28 Oct 2024 | ST144 | BC2 | B1 in progress, 10/39.6m
Mon (28/10) | 28 Oct 2024 | P9 |  | Pier hacking to correct level and lipped channel installation in progress
Mon (28/10) | 28 Oct 2024 | P8-1 |  | ERSS preboring ongoing, 39/52 completed. Tmr to complete
Mon (28/10) | 28 Oct 2024 | Sew 1 & Sew 5 |  | LCH sealing off decom pipeline works in progress
Mon (28/10) | 28 Oct 2024 | ST162 |  | Casting
Mon (28/10) | 28 Oct 2024 | P33 |  | Ground levelling for access at utility support area
Mon (28/10) | 28 Oct 2024 | P43 |  | HSL prepare the area for trial trench
Mon (28/10) | 28 Oct 2024 | MH3-4 |  | Hacking almost done for TBM retrieval
Mon (28/10) | 28 Oct 2024 | Exit 3 |  | RG coring ongoing for inclinometer installation, 33.5/35m
Mon (28/10) | 28 Oct 2024 | P2-6 |  | Rebar cage lowering in progress. To cast today
Mon (28/10) | 28 Oct 2024 | P51-10 |  | Bored pile reached 27.5m
Tue (29/10) | 29 Oct 2024 | P32 |  | Continue manual soil clearing below Starhub
Tue (29/10) | 29 Oct 2024 | P36-37 |  | Manual excavation below services for utility support works
Tue (29/10) | 29 Oct 2024 | ST124-126 |  | Guidewall formwork installation ongoing. Today to cast
Tue (29/10) | 29 Oct 2024 | ST139 | BC1 | B2 in progress, 22.5/34.5m
Tue (29/10) | 29 Oct 2024 | ST144 | BC2 | B1 in progress, 26/39.6m
Tue (29/10) | 29 Oct 2024 | MH3-5 |  | Now no activity. Lifting sup MC. Tomorrow will take our TBM
Tue (29/10) | 29 Oct 2024 | BRP45 |  | Preboring in progress
Tue (29/10) | 29 Oct 2024 | DR1 |  | CH80-60 benching cast last night
Tue (29/10) | 29 Oct 2024 | DR1 |  | CH43-58 first lift wall cast yesterday
Tue (29/10) | 29 Oct 2024 | P32 |  | Current status of roof slab excavation
Tue (29/10) | 29 Oct 2024 | P10 |  | SB side tendon duct fixing and installation of polyfoam
Tue (29/10) | 29 Oct 2024 | BRP13 | BC4 | Excavation in progress, 23.7/30.87m
Tue (29/10) | 29 Oct 2024 | BP4A-1 | 46 | Today to install KP and cast, ST217 (BC3): Cleaning ongoing
Tue (29/10) | 29 Oct 2024 | Exit 3 |  | RG preparing for inclinometer pipe installation
Tue (29/10) | 29 Oct 2024 | Exit 3 |  | Seongha post-lugeon test in progress
Tue (29/10) | 29 Oct 2024 | P44 |  | Now no activity. Need to settle shop drawing
Tue (29/10) | 29 Oct 2024 | P43 |  | TT will start after lunch
Tue (29/10) | 29 Oct 2024 | MH3-4 |  | Hacking almost complete. Tomorrow plan for TBM retrieval
Tue (29/10) | 29 Oct 2024 | MH1-2 |  | Preparation for LSS backfilling
Tue (29/10) | 29 Oct 2024 | P4 |  | Material delivery to start column rebar cage fab
Tue (29/10) | 29 Oct 2024 | P43 |  | TT on going for bored pile work
Tue (29/10) | 29 Oct 2024 | P51-10 |  | Bored hole collapse during toe cleaning. Now LSS backfill back
Tue (29/10) | 29 Oct 2024 | N4-N3 |  | Telco duct pending casting, 12m
Tue (29/10) | 29 Oct 2024 | P9 |  | Continue hacking to correct level, Bottom formwork fabrication ongoing
Tue (29/10) | 29 Oct 2024 | P8 |  | ERSS preboring all completed. Now preparation for ERSS installation
Tue (29/10) | 29 Oct 2024 | S4 |  | Backfilling done for the day
Tue (29/10) | 29 Oct 2024 | BP4A-1 | 46 | Casting in progress
Tue (29/10) | 29 Oct 2024 | ST217 |  | Rebar cage installation ongoing, 3/6nos
Tue (29/10) | 29 Oct 2024 | ST202 | BC3 | Excavation started this afternoon. CD 5m
Tue (29/10) | 29 Oct 2024 | BRP46 |  | Resume preboring
Tue (29/10) | 29 Oct 2024 | P33 |  | Continue manual excavation below SPPG
Tue (29/10) | 29 Oct 2024 | MH2-9 |  | Pipe jacking in progess, 26/30nos
Tue (29/10) | 29 Oct 2024 | MH2-10 |  | 10th layer cast yesterday. Now preparing formwork opening and thereafter continue next layer
Tue (29/10) | 29 Oct 2024 | P12 |  | Falsework material all here. Erection started
Tue (29/10) | 29 Oct 2024 | P51-10 |  | Balance 300mm to reach toe. Today to cast
Wed (30/10) | 30 Oct 2024 | BP6A | 10 | Preparation work in progress
Wed (30/10) | 30 Oct 2024 | P51-5 |  | Today casing will install. P43-5 also will install casting today
Wed (30/10) | 30 Oct 2024 | P51-10 |  | LSS curing
Wed (30/10) | 30 Oct 2024 | P33 |  | Continue manual excavation ongoing below utility
Wed (30/10) | 30 Oct 2024 | P38 |  | Grass cutting ongoing
Wed (30/10) | 30 Oct 2024 | ST217 |  | Preparing to extract rebar cage
Wed (30/10) | 30 Oct 2024 | BRP13 | Rig 4 | Desanding in progress
Wed (30/10) | 30 Oct 2024 | P10 |  | 2nd side formwork closing, 2/5 built up panels
Wed (30/10) | 30 Oct 2024 | ST139 | BC1 | BC cutter electrical box rectification ongoing. B1 & B2 completed
Wed (30/10) | 30 Oct 2024 | ST144 | BC2 | B1 temporarily stopped. Mud drum elbow leaking, waiting for boom lift for rectification works
Wed (30/10) | 30 Oct 2024 | DR1 |  | Today plan to cast benching for CH60-CH40 & to bsckfill for CH58-CH38
Wed (30/10) | 30 Oct 2024 | BRP46 | BG01 | P1 Preboring CD 17.0/27.27m
Wed (30/10) | 30 Oct 2024 | MH3-5 |  | Pipe No-26 fully push in. Now start the removal of materials and part of preparation for MH3-4 to existing jacking work
Wed (30/10) | 30 Oct 2024 | Zone 3 facing Selarang |  | RG drilling ongoing for piezometer and water standpipe installation
Wed (30/10) | 30 Oct 2024 | P9 |  | Barricade installation at the completed bottom formwork
Wed (30/10) | 30 Oct 2024 | P8 |  | 2 nos SP installed yesterday. Preboring completed
Wed (30/10) | 30 Oct 2024 | P5-6 |  | Preparation for pre-boring. WH will do again TT to confirm no utility below before proceeding with preboring
Wed (30/10) | 30 Oct 2024 | P43-5 |  | Preboring for casing installation
Wed (30/10) | 30 Oct 2024 | MH3-4 |  | Preparing for TBM retrieval. Today to remove from shaft
Wed (30/10) | 30 Oct 2024 | P51-5 |  | Setting out to start preboring
Wed (30/10) | 30 Oct 2024 | P4 |  | Casing installed. Boring to resume on friday
Wed (30/10) | 30 Oct 2024 | MH2-10 |  | Hacking and excavation ongoing for 11th layer
Wed (30/10) | 30 Oct 2024 | P33 |  | Manual excavation ongoing below utility
Wed (30/10) | 30 Oct 2024 | P33 |  | Excavation ongoing for trenching works along utility alignment
Wed (30/10) | 30 Oct 2024 | P10 |  | Installation of additional tendon duct and preparation for installation of cast in pipe
Wed (30/10) | 30 Oct 2024 | P36-37 |  | Continue excavation and utility support welding works
Wed (30/10) | 30 Oct 2024 | P38 |  | WH erecting rain shelter
Wed (30/10) | 30 Oct 2024 | ST139 |  | WS trimming in progress
Wed (30/10) | 30 Oct 2024 | ST144 |  | Resume B1 excavation
Wed (30/10) | 30 Oct 2024 | ST158-159 |  | Guidewall trial trench
Wed (30/10) | 30 Oct 2024 | P43-5 |  | Adjusting of casing verticality
Wed (30/10) | 30 Oct 2024 | BRP45 |  | Preboring ongoing
Wed (30/10) | 30 Oct 2024 | DR1 |  | 2nd lift rebar works and formwork installation
Wed (30/10) | 30 Oct 2024 | DR1 |  | Benching construction ongoing
Wed (30/10) | 30 Oct 2024 | BC4 |  | Now preparing to park at next panel, BRP26. BRP13 desanding completed
Wed (30/10) | 30 Oct 2024 | BC3 |  | Currently no activity. This machine will do cleaning at ST217
Wed (30/10) | 30 Oct 2024 | ST217 |  | Rebar cage extraction ongoing due to trench collapse. Panel cleaning will be done
Wed (30/10) | 30 Oct 2024 | BP6A | 10 | Preboring and casing installation. Now waiting for ECC check before continuing lowering and start boring works
Wed (30/10) | 30 Oct 2024 | Exit 3 |  | Seongha post-lugeon test ongoing
Wed (30/10) | 30 Oct 2024 | P10 |  | Formwork installation in progress
Wed (30/10) | 30 Oct 2024 | P9 |  | Preparing for falsework installation
Wed (30/10) | 30 Oct 2024 | S3 |  | Column hacking to correct level
Wed (30/10) | 30 Oct 2024 | S4 |  | No activity
Wed (30/10) | 30 Oct 2024 | BP6A | 10 | HSL no more activity
Wed (30/10) | 30 Oct 2024 | BRP26 | BC4 | Excavation started
Wed (30/10) | 30 Oct 2024 | BR1 excavation |  | No activity
Wed (30/10) | 30 Oct 2024 | BRP45 |  | Noise balloon setup for preboring works
Wed (30/10) | 30 Oct 2024 | DR1 |  | LSS backfill ongoing
Wed (30/10) | 30 Oct 2024 | P36 |  | Utility support welding ongoing
Wed (30/10) | 30 Oct 2024 | MH2-9 |  | Currently no activity. Pipe jacking completed, 27nos
Wed (30/10) | 30 Oct 2024 | MH2-10 |  | 11th layer construction in progress. Target to cast today
Thu (31/10) | 31 Oct 2024 | ST217 |  | Re-installation of rebar cage
Thu (31/10) | 31 Oct 2024 | ST202 | BC3 | Excavation resume, 22.5/34.2m
Thu (31/10) | 31 Oct 2024 | BRP26 | BC4 | Excavation in progress
Thu (31/10) | 31 Oct 2024 | BR1 excavation |  | No activity
Thu (31/10) | 31 Oct 2024 | DR1 |  | CH45-60 benching completed yesterday
Thu (31/10) | 31 Oct 2024 | DR1 |  | CH38-58 LSS backfill done yesterday
Thu (31/10) | 31 Oct 2024 | DR1 |  | CH80-60 roof slab formwork ongoing
Thu (31/10) | 31 Oct 2024 | BRP45 |  | Preboring no activity
Thu (31/10) | 31 Oct 2024 | P33 |  | No activity
Thu (31/10) | 31 Oct 2024 | P36-37 |  | No activity
Thu (31/10) | 31 Oct 2024 | ST144 | BC2 | B2 in progress, 24/39.6m
Thu (31/10) | 31 Oct 2024 | ST139 |  | Final koden checked. Preparing for rebar cage installation
Thu (31/10) | 31 Oct 2024 | Exit 3 |  | No activity
Thu (31/10) | 31 Oct 2024 | ST217 |  | Rebar cage installation in progress, 4/6nos
Thu (31/10) | 31 Oct 2024 | ST202 |  | Excavation in progress, 32.5/34.2m
Thu (31/10) | 31 Oct 2024 | BRP26 |  | CD 26/32.5m. Now cutter body washing for teeth changing
Thu (31/10) | 31 Oct 2024 | BRP52 |  | Guidewall hacking ongoing. Noise balloon is in placed
Thu (31/10) | 31 Oct 2024 | P12 |  | Secondary beam installation in progress
Thu (31/10) | 31 Oct 2024 | P10 |  | Duct pipe inspection ongoing
Thu (31/10) | 31 Oct 2024 | P9 |  | No activity
Thu (31/10) | 31 Oct 2024 | P6/Zone 1 |  | No activity
Fri (01/11) | 01 Nov 2024 | P33 |  | Manual excavation ongoing for utility support works
Fri (01/11) | 01 Nov 2024 | P36-37 |  | Utility support welding ongoing
Fri (01/11) | 01 Nov 2024 | ST144 | BC3 | B2 temporarily stopped. Cutter teeth changing ongoing
Fri (01/11) | 01 Nov 2024 | ST139 |  | Preparing for casting
Fri (01/11) | 01 Nov 2024 | ST127 |  | Trial trench in progress
Fri (01/11) | 01 Nov 2024 | ST122 | BC2 | B1 in progress, 22/39m
Fri (01/11) | 01 Nov 2024 | P51-10 |  | Preparing to resume boring work
Fri (01/11) | 01 Nov 2024 | ST158-159 |  | Guidewall formwork dismantling ongoing
Fri (01/11) | 01 Nov 2024 | DR1 |  | CH80-73 top slab rebar works ongoing. Target to cast tmr
Fri (01/11) | 01 Nov 2024 | DR3 |  | Rebar cage delivery
Fri (01/11) | 01 Nov 2024 | DR1 |  | Hacking ongoing for weepholes that are covered & benching cement patching ongoing
Fri (01/11) | 01 Nov 2024 | BRP45 |  | Preboring ongoing
Fri (01/11) | 01 Nov 2024 | P33 |  | Utility KP exposed for beam installation
Fri (01/11) | 01 Nov 2024 | BR1 excavation |  | Continue soil disposal
Fri (01/11) | 01 Nov 2024 | Zone 3 facing Selarang |  | RG drilling ongoing for piezometer installation, 20/25m
Fri (01/11) | 01 Nov 2024 | BRP26 | BC4 | Excavation in progress, 27/32.5m
Fri (01/11) | 01 Nov 2024 | ST202 | BC1 | WS trimming ongoing
Fri (01/11) | 01 Nov 2024 | ST217 |  | Casting in progress, 173.5/191m3
Fri (01/11) | 01 Nov 2024 | MH3-5 |  | Clearing materials. Preparing to start water test on completed jacking pipes
Fri (01/11) | 01 Nov 2024 | TDP11 |  | Pending utility team to check on services
Fri (01/11) | 01 Nov 2024 | BP6A | 10 | Waiting for casing vertically check before start boring
Fri (01/11) | 01 Nov 2024 | Exit 3 |  | Seongha post-lugeon test for CH-04
Fri (01/11) | 01 Nov 2024 | P43-4 |  | Now preparing to start boring work after bentonite check
Fri (01/11) | 01 Nov 2024 | MH3-4 |  | Now inspection for water test
Fri (01/11) | 01 Nov 2024 | BRP26 |  | Trenching on going at 32.8m
Fri (01/11) | 01 Nov 2024 | ST202 |  | Trimming continue
Fri (01/11) | 01 Nov 2024 | P32-33 |  | Manual excavation for Utility support installation continue
Fri (01/11) | 01 Nov 2024 | BRP45 |  | Pre-boring continue
Fri (01/11) | 01 Nov 2024 | DR1 |  | Benching formwork closing
Fri (01/11) | 01 Nov 2024 | DR1 |  | Old drain hacking
Fri (01/11) | 01 Nov 2024 | P36-37 |  | Utility support welding and excavation till 10pm
Fri (01/11) | 01 Nov 2024 | ST144-BC3 |  | Trenching completed. C-lug welding for trimming
Fri (01/11) | 01 Nov 2024 | STN139 |  | Casting in progress, running volume 97m3
Fri (01/11) | 01 Nov 2024 | STN122 |  | 1st bite trenching at 31m
Fri (01/11) | 01 Nov 2024 | P51-10 |  | To continue boring until 10pm
Fri (01/11) | 01 Nov 2024 | MH2-9 |  | No activity. Current pipe jacking status: 27/30nos
Fri (01/11) | 01 Nov 2024 | MH2-10 |  | Pumping out water before continue 12th layer. Current status: 11/16 layers completed
Fri (01/11) | 01 Nov 2024 | Zone 4 |  | PUB sewer clearing the materials inside the manhole
Sat (02/11) | 02 Nov 2024 | P10 |  | Side formwork closing. Shear link inspection with RTO at 10:30AM
Sat (02/11) | 02 Nov 2024 | P9 |  | Column head hacking and rebar bending
Sat (02/11) | 02 Nov 2024 | P6 |  | Trial trench with two teams. Supervise by both utility and construction team. Found gas pipe turning toward NLL. Should be abandoned
Sat (02/11) | 02 Nov 2024 | P5-6 |  | Inspection by RTO. Today to cast
Sat (02/11) | 02 Nov 2024 | ST202 |  | Cleaning and desanding
Sat (02/11) | 02 Nov 2024 | BRP26 |  | Rebar cage lowering done. Preparing to lower KP
Sat (02/11) | 02 Nov 2024 | BRP45 |  | Pre-boring in progress
Sat (02/11) | 02 Nov 2024 | STN122 |  | 2nd bite trenching started
Sat (02/11) | 02 Nov 2024 | ST144-BC3 |  | Cleaning and desanding in progress. Desander maintenance
Sat (02/11) | 02 Nov 2024 | P8 |  | Steel plate installation in progress
Sat (02/11) | 02 Nov 2024 | P51-10 |  | Now toe confirmation. Today to cast
Sat (02/11) | 02 Nov 2024 | MH3-5 |  | Now continue clearing materials. Today to extend the sewer pipe
Sat (02/11) | 02 Nov 2024 | Receiving shaft, BC cutter 2 |  | Cutter teeth maintenance
Sat (02/11) | 02 Nov 2024 | ST144 |  | Waterstop end plate removal
Sat (02/11) | 02 Nov 2024 | BRP46 |  | Bentonite hoses laying to start excavation
Sat (02/11) | 02 Nov 2024 | DR1 |  | Strut removal
Sat (02/11) | 02 Nov 2024 | DR1 |  | Abandoned slab hacking to extend DR1 base slab
Sat (02/11) | 02 Nov 2024 | DR1 |  | Top slab rebar work
Sat (02/11) | 02 Nov 2024 | BRP45 |  | 4th point preboring
Sat (02/11) | 02 Nov 2024 | P31 to P32 |  | Excavation for roof slab and utility support installation
Sat (02/11) | 02 Nov 2024 | ST202 |  | C lock welding for waterstop end plate trimming
Sat (02/11) | 02 Nov 2024 | MH2-10 |  | Continue excavation for 12th layer caisson
Sat (02/11) | 02 Nov 2024 | P16-P18 |  | Wendyng tidy up the area as per comment from woh hup safety audit
Sat (02/11) | 02 Nov 2024 | P12 |  | Hard barricade installation around working platform. Woh hup also erection of access to go up
Sat (02/11) | 02 Nov 2024 | P10 |  | Inspection on going by RTO
Sat (02/11) | 02 Nov 2024 | P8 |  | Left 6nos of steel plate to install. Then excavate and push down 500mm for all the ERSS installed
Sat (02/11) | 02 Nov 2024 | P6 |  | Now shift out the affected traffic light. To complete today
Sat (02/11) | 02 Nov 2024 | P51-10 |  | Casting completed. Clearing the area
Sat (02/11) | 02 Nov 2024 | P43-4 |  | Continue boring. Casting will be late night or tomorrow
Sat (02/11) | 02 Nov 2024 | ST122 |  | Boring in progress, 1st bite reached 38m
Sat (02/11) | 02 Nov 2024 | ST144 |  | Desanding in progress
Sat (02/11) | 02 Nov 2024 | DR1 |  | Current status of DR1 top slab work
Sat (02/11) | 02 Nov 2024 | P12 |  | C-channel and plywood laying to complete tonight at bus lane during non-traffic hours
Sat (02/11) | 02 Nov 2024 | P10 |  | 3/5 section formwork closed. Tonight to close 4th section
Sat (02/11) | 02 Nov 2024 | BP6A-10 |  | Boring reached 26.5m
Sat (02/11) | 02 Nov 2024 | P12 |  | Preparation to install hard barricade for completed falsework
Sun (03/11) | 03 Nov 2024 | BRP26 |  | Tremie pipe lowering in progress
Sun (03/11) | 03 Nov 2024 | BRP-45 |  | Preboring in progress, current depth 18.9m
Sun (03/11) | 03 Nov 2024 | BRP46 |  | Cutter wheel maintenance in progress. Current depth, 17.3m/27.27m
Sun (03/11) | 03 Nov 2024 | BRP47 |  | Trial trench works in progress
Sun (03/11) | 03 Nov 2024 | DR1 |  | Wall 2nd lift and top slab formwork closing and support installation
Sun (03/11) | 03 Nov 2024 | ST144-BC3 |  | Waterstop lowering completed
Sun (03/11) | 03 Nov 2024 | P36 |  | Utility support and excavation works
Sun (03/11) | 03 Nov 2024 | STN122 | BC02 | 2nd bite excavation in progress, current depth 29/39m
Sun (03/11) | 03 Nov 2024 | P43-5 |  | Boring in progress, current depth 30m
Sun (03/11) | 03 Nov 2024 | Zone 4, P45-1&2 |  | Base grouting stage 2 ongoing
Sun (03/11) | 03 Nov 2024 | P51-5 |  | BP boring in progress, current depth is 21m/28.406m
Sun (03/11) | 03 Nov 2024 | P12 |  | Scaffold access signages and netting installation
Sun (03/11) | 03 Nov 2024 | P10 |  | Formwork closing and cleaning for crosshead in progress. Last section adjustment works for rebars in progress
Sun (03/11) | 03 Nov 2024 | P9 |  | No activity
Sun (03/11) | 03 Nov 2024 | P4 |  | Setting up works in progress for column rebar cage installation
Sun (03/11) | 03 Nov 2024 | P10 |  | Section 4 formwork closed. Section 5 links installation continue
Sun (03/11) | 03 Nov 2024 | Bet. P25 & P26 |  | I27 drilling in progress for fissure grouting
Sun (03/11) | 03 Nov 2024 | ST207 |  | 1st bite excavation in progress. Current depth 11m
Sun (03/11) | 03 Nov 2024 | BRP26 |  | Casting completed
Sun (03/11) | 03 Nov 2024 | BRP45 |  | Preboring in progress, current depth 19.3m
Sun (03/11) | 03 Nov 2024 | P12 |  | C-channel and railing installation continue. Tonight to complete plywood laying
Sun (03/11) | 03 Nov 2024 | BRP46 |  | Continue Cutter wheel maintenance works
Sun (03/11) | 03 Nov 2024 | BRP47 |  | Continue trial trench works
Sun (03/11) | 03 Nov 2024 | DR1 |  | Current drain works status. Activity stopped for the day. Housekeeping ongoing
Sun (03/11) | 03 Nov 2024 | P36 |  | Current status for Utility support and excavation works. Housekeeping ongoing
Sun (03/11) | 03 Nov 2024 | ST144 |  | Rebar cage lowering in progress. 4/8 nos. completed
Sun (03/11) | 03 Nov 2024 | STN122 |  | 2nd bite excavation in progress, current depth 29.8m/39m
Sun (03/11) | 03 Nov 2024 | P43-5 |  | BP boring work stopped for the day, current depth 33m
Sun (03/11) | 03 Nov 2024 | P51-5 |  | BP boring work stopped for the day, current depth is 24.5m/28.406m
Sun (03/11) | 03 Nov 2024 | P10 Crosshead |  | Dayshift team work stopped for the day. Night shift team will continue with the balance formwork closing later
Sun (03/11) | 03 Nov 2024 | P4 |  | Column rebar cage installed
Sun (03/11) | 03 Nov 2024 | ST202 |  | Cleaning and desanding completed. Koden test on going
Sun (03/11) | 03 Nov 2024 | BRP26 |  | Kingpost lowering completed
Sun (03/11) | 03 Nov 2024 | BRP45 |  | Pre-boring continue
Sun (03/11) | 03 Nov 2024 | BRP46-BC4 |  | Center bite trenching at 18m depth. Teeth changing in progress
Sun (03/11) | 03 Nov 2024 | DR1 |  | Wall 2nd lift and top slab formwork closing
Sun (03/11) | 03 Nov 2024 | ST144-BC3 |  | Cleaning and desanding completed. Preparation for end plate and waterstop lowering
Sun (03/11) | 03 Nov 2024 | Bet. P25 & P26 |  | I23 drilling in progress for fissure grouting
Mon (04/11) | 04 Nov 2024 | MH2-9 |  | Pipe jacking completed, 29/30nos
Mon (04/11) | 04 Nov 2024 | MH2-10 |  | 12/16 layers completed. Formwork removal ongoing. Thereafter hacking of entry opening for balance 1 pipe from MH2-9
Mon (04/11) | 04 Nov 2024 | Blk 2 |  | RW14 drilling completed
Mon (04/11) | 04 Nov 2024 | P33 |  | Utility support installation in progress
Mon (04/11) | 04 Nov 2024 | P4 |  | Links installation at lapping area
Mon (04/11) | 04 Nov 2024 | P36 |  | Manual excavation below services ongoing
Mon (04/11) | 04 Nov 2024 | ST108A | BC3 | B1 in progress
Mon (04/11) | 04 Nov 2024 | ST122 | BC2 | B2 in progress, 31.2/39m
Mon (04/11) | 04 Nov 2024 | P51-5 |  | Preparing for toe confirmation. Today to cast
Mon (04/11) | 04 Nov 2024 | BRP45 | BG01 | P4 Preboring CD 21.5/24.67m
Mon (04/11) | 04 Nov 2024 | P36-37 |  | Slope trimming/levelling ongoing. Steel cover protection ongoing for utility service (Starhub/22kV)
Mon (04/11) | 04 Nov 2024 | P10 status |  | Formwork tie rod installation
Mon (04/11) | 04 Nov 2024 | Zone 3 facing Selarang |  | RG drilling ongoing for water standpipe. Piezometer installation completed
Mon (04/11) | 04 Nov 2024 | P43-4 |  | Checking of toe. Plan to cast today
Mon (04/11) | 04 Nov 2024 | P45 |  | Machine maintenance and housekeeping. Tomorrow to start trial trench for JGP work
Mon (04/11) | 04 Nov 2024 | P9 |  | Currently no activity
Mon (04/11) | 04 Nov 2024 | N4 area |  | Backfilling
Mon (04/11) | 04 Nov 2024 | P8 |  | Excavation ongoing
Mon (04/11) | 04 Nov 2024 | S3 |  | Pier hacking
Mon (04/11) | 04 Nov 2024 | BP6A | 10 | Boring reached 37.2/37.88m as at 1900hrs. No more activity
Mon (04/11) | 04 Nov 2024 | BRP26 |  | Casting completed yesterday. Now LSS backfill
Mon (04/11) | 04 Nov 2024 | P32 |  | KTC hacking and soil disposal ongoing
Mon (04/11) | 04 Nov 2024 | DR1 |  | CH74-80 top slab casting in progress
Tue (05/11) | 05 Nov 2024 | P36-37 |  | WH installing protection for utility pipe alignment
Tue (05/11) | 05 Nov 2024 | DR2 |  | Canal cleaning ongoing
Tue (05/11) | 05 Nov 2024 | P10 |  | Woh hup left 8nos of cast in anchor and wendyng left a few tie rods. Today to complete all this. Woh hup plan to cast around 5PM tomorrow coz casting will be going over bus lane also
Tue (05/11) | 05 Nov 2024 | ST122 | BC2 | B2 temporarily stopped. Cutter wheel maintenance ongoing
Tue (05/11) | 05 Nov 2024 | P9 |  | Woh hup erection of access for cross head work
Tue (05/11) | 05 Nov 2024 | P8 |  | KTC excavation for 1st layer waler
Tue (05/11) | 05 Nov 2024 | P6 |  | Found abandoned 22KV haunching. Now exposing for removal
Tue (05/11) | 05 Nov 2024 | ST108A | BC3 | Excavation resumed. B1 CD 33.5/39m
Tue (05/11) | 05 Nov 2024 | P33 |  | Continue excavation for utility support works
Tue (05/11) | 05 Nov 2024 | BRP46 |  | Trench collapsed and was backfilled with G15 yesterday. Now Hacking the guidewall thereafter will reconstruct new guidewall
Tue (05/11) | 05 Nov 2024 | BRP45 |  | Continue preboring
Tue (05/11) | 05 Nov 2024 | P2-5 |  | Boring. Today target to cast
Tue (05/11) | 05 Nov 2024 | DR4 |  | Current status of soil stockpile
Tue (05/11) | 05 Nov 2024 | P51-11 |  | Yesterday HSl work late. So, after 12 only then will come and start casing installation
Tue (05/11) | 05 Nov 2024 | DR1 |  | 4th strut removal
Tue (05/11) | 05 Nov 2024 | DR1 |  | CH74-80 top slab and 2nd lift wall cast
Tue (05/11) | 05 Nov 2024 | DR1 |  | Now ongoing falseworks for next section
Tue (05/11) | 05 Nov 2024 | BR1 |  | Currently no activity
Tue (05/11) | 05 Nov 2024 | Zone 3 facing Selarang |  | RG drilling ongoing for water standpipe
Tue (05/11) | 05 Nov 2024 | ST207 | BC1 | Excavation temporarily stopped. Gearbox and cutter wheel changing ongoing
Tue (05/11) | 05 Nov 2024 | BRP15 | BC4 | Excavation temporarily stopped due to desander issue. CD 25.7/31.1m
Tue (05/11) | 05 Nov 2024 | P51-11 |  | Shifting generator and materials and preparation to start preboring work
Tue (05/11) | 05 Nov 2024 | MH2-9 |  | Pipe 29 already lowered
Tue (05/11) | 05 Nov 2024 | MH2-10 |  | Preparing to take out TBM
Tue (05/11) | 05 Nov 2024 | P4 |  | Excavation for column formwork installation in progress. Today will lean concrete
Tue (05/11) | 05 Nov 2024 | P2-5 |  | BP rebar cage lowering in progesss
Tue (05/11) | 05 Nov 2024 | DR2 |  | Continue canal cleaning
Tue (05/11) | 05 Nov 2024 | P36-37 |  | Continue protection installation for utility alignment
Tue (05/11) | 05 Nov 2024 | P8-1 |  | Excavation to s1 layer in progress. Today to complete
Tue (05/11) | 05 Nov 2024 | S3 |  | Pier hacking to correct level ongoing
Tue (05/11) | 05 Nov 2024 | Zone 3 |  | Dongah hacking ongoing for abandoned sewer MH to facilitate guidewall works
Tue (05/11) | 05 Nov 2024 | ST122 |  | B2 in progress, 33.3/39m
Tue (05/11) | 05 Nov 2024 | ST108A |  | B1 completed
Tue (05/11) | 05 Nov 2024 | BP6A | 10 | Toe level inspected, to cast today
Tue (05/11) | 05 Nov 2024 | BRP15 | Rig 4 | Excavation CD 26.5/31.1m
Tue (05/11) | 05 Nov 2024 | ST207 | Rig 1 | B1 CD 33.3/37.1m, gear box replacement now in progress
Tue (05/11) | 05 Nov 2024 | P43 |  | Platform preparing for next bored pile boring work
Tue (05/11) | 05 Nov 2024 | MH3-5 |  | Clearing materials and housekeeping. Tomorrow precast ring will deliver and will start manhole work
Tue (05/11) | 05 Nov 2024 | P10 |  | Installation of bar cast-in anchor in progress. 18/24 completed
Tue (05/11) | 05 Nov 2024 | P9 |  | Scaffold erection in progress
Tue (05/11) | 05 Nov 2024 | BRP45 | BG01 | P5 Preboring CD 24.6/24.67m
Tue (05/11) | 05 Nov 2024 | P6 |  | Preparation works in progress. Preboring for ERSS to start today
Tue (05/11) | 05 Nov 2024 | P12 |  | Falsework work installation in progress
Tue (05/11) | 05 Nov 2024 | N2-N3 |  | Excavation for telco duct in progress
Tue (05/11) | 05 Nov 2024 | P17 |  | Patching up of tie rod holes completed. LE to start ERSS extraction today
Tue (05/11) | 05 Nov 2024 | BP6B, 1500mm diam | 8 | Preboring started
Tue (05/11) | 05 Nov 2024 | BP6A | 10 | Preparing for casting
Tue (05/11) | 05 Nov 2024 | BRP46 |  | Guidewall hacking completed. Now backfilling, tmr to re-construct guidewall
Tue (05/11) | 05 Nov 2024 | P36-37 |  | Utility protection installation in progres
Tue (05/11) | 05 Nov 2024 | DR1 |  | Falsework erection ongoing
Tue (05/11) | 05 Nov 2024 | BRP45 |  | Continue preboring
Tue (05/11) | 05 Nov 2024 | P32 |  | Slope trimming
Tue (05/11) | 05 Nov 2024 | BRP15 |  | Excavation temporarily stopped due to mud drum elbow leaking. CD 26.5/31.1m, ST207: B2 excavation started
Tue (05/11) | 05 Nov 2024 | P17 |  | Now Wendyng patch up tie rods holes. LE will take over the area here for ERSS removal
Tue (05/11) | 05 Nov 2024 | MH2-10 |  | 12/16 layers completed. Now Preparing for TBM breakthrough
Tue (05/11) | 05 Nov 2024 | N3-N2 |  | Today VSK plan to cast 6m length of Telecom duct
Tue (05/11) | 05 Nov 2024 | P12 |  | Preparing for jack installation
Wed (06/11) | 06 Nov 2024 | P51-11 |  | Boring reached 17.5m
Wed (06/11) | 06 Nov 2024 | BP6B | 8 | Boring current depth 15.0m
Wed (06/11) | 06 Nov 2024 | BRP15 | Rig 4 | Cleaning in progress
Wed (06/11) | 06 Nov 2024 | ST207 | Rig 1 | B2 CD 23.0/37.1m
Wed (06/11) | 06 Nov 2024 | BRP45 | BG01 | P6 Preboring CD 20.50/24.67m
Wed (06/11) | 06 Nov 2024 | ST108A | Rig 3 | WS trimming in progress
Wed (06/11) | 06 Nov 2024 | ST122 | Rig2 | B3 CD 10/39m
Wed (06/11) | 06 Nov 2024 | P18 |  | KTC Backfilling ongoing for ERSS extraction
Wed (06/11) | 06 Nov 2024 | P17 |  | LE ERSS extraction works in progress
Wed (06/11) | 06 Nov 2024 | Bet. N4-N3 |  | Vsk Compaction works ongoing. Tmr to do ndt
Wed (06/11) | 06 Nov 2024 | N3 |  | Telco duct 6m to cast today
Wed (06/11) | 06 Nov 2024 | P12 |  | Baseform installation in progress
Wed (06/11) | 06 Nov 2024 | MH3-5 |  | Precast installed for 3m height today. Now preparing BRC. Tomorrow to cast 3m height
Wed (06/11) | 06 Nov 2024 | P44 |  | Exposing around ERSS to push down 500mm
Wed (06/11) | 06 Nov 2024 | P12 |  | Sideform assembly works
Wed (06/11) | 06 Nov 2024 | P10 |  | Adjustment of bar cast-in anchor and side formwork in progress
Wed (06/11) | 06 Nov 2024 | P9 |  | Scaffold erection current status for rebar installation
Wed (06/11) | 06 Nov 2024 | P8-1 |  | Waler brackets installation ongoing
Wed (06/11) | 06 Nov 2024 | P6 |  | Preboring for ERSS in progress
Wed (06/11) | 06 Nov 2024 | P5-3 |  | BP boring works in progress, current depth 18m
Wed (06/11) | 06 Nov 2024 | P4 |  | Column formwork closing ongoing
Wed (06/11) | 06 Nov 2024 | P44 |  | Current status of excavation to push down steel plate 1m
Wed (06/11) | 06 Nov 2024 | P43-6 |  | Boring in progress. Reached 16m
Wed (06/11) | 06 Nov 2024 | ST122 |  | 3rd bite, reached 24m
Wed (06/11) | 06 Nov 2024 | Near DR2 |  | Steel plate protection installation for utilities
Wed (06/11) | 06 Nov 2024 | DR1 |  | Drain wall formwork closing and roof slab rebar work
Wed (06/11) | 06 Nov 2024 | ST207 |  | 2nd bite, reached 28m
Wed (06/11) | 06 Nov 2024 | BRP15 |  | Cleaning in progress
Wed (06/11) | 06 Nov 2024 | P18 |  | KTC backfilling
Wed (06/11) | 06 Nov 2024 | P12 |  | Cross head soffit plywood laying
Wed (06/11) | 06 Nov 2024 | P10 |  | Link bar typing and cast in anchor installation
Wed (06/11) | 06 Nov 2024 | P9 |  | Scaffolding erection by woh hup
Wed (06/11) | 06 Nov 2024 | P8 |  | Slope protection lean concrete
Wed (06/11) | 06 Nov 2024 | P4 |  | Column formwork closing
Wed (06/11) | 06 Nov 2024 | P5-3 |  | Boring work already stopped
Thu (07/11) | 07 Nov 2024 | P10 |  | Rebar level and alignment adjusting. Plan to cast today at 5pm
Thu (07/11) | 07 Nov 2024 | THM4 |  | Today PLT
Thu (07/11) | 07 Nov 2024 | P51-11 |  | Boring in progress, reached 21m
Thu (07/11) | 07 Nov 2024 | P50 |  | GCE will start TT after lunch
Thu (07/11) | 07 Nov 2024 | P10 |  | SRE formwork inspection ongoing
Thu (07/11) | 07 Nov 2024 | P44 |  | Woh hup started pushing down of steel plates
Thu (07/11) | 07 Nov 2024 | P51-11 |  | Continue boring. Encounter hard rock now
Thu (07/11) | 07 Nov 2024 | P8 |  | Waler bracket welding
Thu (07/11) | 07 Nov 2024 | P10 |  | Rectification works base on SRE comment
Thu (07/11) | 07 Nov 2024 | TMH4 |  | Plate load test in progress
Thu (07/11) | 07 Nov 2024 | MH3-5 |  | Rebar installed around precast. Left to close formwork
Thu (07/11) | 07 Nov 2024 | P44 |  | Continue pushing down of steel plates
Thu (07/11) | 07 Nov 2024 | P43 |  | Continue exposing and steel plates driving down
Thu (07/11) | 07 Nov 2024 | MH3-4 |  | Prepare base slab to cast
Thu (07/11) | 07 Nov 2024 | P43-6 |  | Boring reached 29.5m
Thu (07/11) | 07 Nov 2024 | BP6B | 8 | Boring continue until 7pm. Depth 25m
Thu (07/11) | 07 Nov 2024 | P10 |  | Pump car set up For casting
Thu (07/11) | 07 Nov 2024 | P8 |  | 2 side waler beam installed
Thu (07/11) | 07 Nov 2024 | P5-3 |  | Boring works
Fri (08/11) | 08 Nov 2024 | MH2-9 |  | Preparing to remove jacking frame. Pipe jacking to MH2-10 completed, 29/29nos
Fri (08/11) | 08 Nov 2024 | MH2-10 |  | Excavation for 13th layer. Target to cast today
Fri (08/11) | 08 Nov 2024 | BRP45 |  | Excavation temporarily stopped for cutter teeth changing. CD 24.1/24.67m
Fri (08/11) | 08 Nov 2024 | ST138 | BC2 | Cutter wheel soil cleaning ongoing
Fri (08/11) | 08 Nov 2024 | ST122 |  | Rebar cage lapping ongoing, 6/8nos
Fri (08/11) | 08 Nov 2024 | ST144A | BC3 | B1 in progress, 22.5/39.6m
Fri (08/11) | 08 Nov 2024 | P36-37 |  | Continue installation for utility protection
Fri (08/11) | 08 Nov 2024 | BRP46, BRP47 |  | Currently no activity. Guidewalls have been constructed
Fri (08/11) | 08 Nov 2024 | DR1 |  | CH58-35.5 — Preparing for 2nd lift wall rebar works
Fri (08/11) | 08 Nov 2024 | DR1 |  | CH74-58 top slab & 2nd lift wall cast
Fri (08/11) | 08 Nov 2024 | BRP45 |  | Preboring temporarily stopped. Waiting for soil shifting
Fri (08/11) | 08 Nov 2024 | ST207 | BC1 | B2 in progress, 31/37.1m
Fri (08/11) | 08 Nov 2024 | BP6B | 8 | Boring in progress, 26/34m
Fri (08/11) | 08 Nov 2024 | Exit 3 |  | Slurry tank repair works
Fri (08/11) | 08 Nov 2024 | MH2-9 |  | Clearing of rubbish from the shaft
Fri (08/11) | 08 Nov 2024 | MH2-10 |  | Excavation for caisson casting. Tonight plan to cast
Fri (08/11) | 08 Nov 2024 | BRP15 |  | Preparing for LSS backfilling
Fri (08/11) | 08 Nov 2024 | ST207 |  | Cutter body up for teeth maintenance
Fri (08/11) | 08 Nov 2024 | DR1 |  | Preparing for wall formwork closing
Fri (08/11) | 08 Nov 2024 | BC cutter 4 |  | Cutter teeth changing
Fri (08/11) | 08 Nov 2024 | DR1 |  | CH58 to CH80 top slab casting was done. Curing
Fri (08/11) | 08 Nov 2024 | Near DR2 |  | Utility protection steel plate installation
Fri (08/11) | 08 Nov 2024 | BC cutter 3 |  | Cutter teeth changing
Fri (08/11) | 08 Nov 2024 | ST138 |  | 1st bite, reached 28.5m
Fri (08/11) | 08 Nov 2024 | ST122 |  | 8/8 cages lowering on going. Today to cast
Fri (08/11) | 08 Nov 2024 | TMH4 |  | Base slab rebar works in progress
Fri (08/11) | 08 Nov 2024 | P9 |  | Rebar installation started. 5W+1S
Fri (08/11) | 08 Nov 2024 | BP6B | 8 | Boring in progress, 28/34m
Fri (08/11) | 08 Nov 2024 | MH3-4 |  | Preparing for base slab casting
Fri (08/11) | 08 Nov 2024 | P53-6 |  | Boring to toe
Fri (08/11) | 08 Nov 2024 | P51-11 |  | Boring reached 28.5m. Tomorrow to cast
Fri (08/11) | 08 Nov 2024 | P12 |  | Wingform also to install tonight
Fri (08/11) | 08 Nov 2024 | ST207 |  | Trenching resume
Fri (08/11) | 08 Nov 2024 | BRP45 |  | 1st bite trenching at 24.3m
Fri (08/11) | 08 Nov 2024 | DR1 |  | Formwork closing for sewer stump
Fri (08/11) | 08 Nov 2024 | P36-37 |  | Welding of steel plate for Utility support to continue until 10pm
Sat (09/11) | 09 Nov 2024 | P8 |  | Diagonal strut welding ongoing
Sat (09/11) | 09 Nov 2024 | P6 |  | ERSS preboring
Sat (09/11) | 09 Nov 2024 | P4 |  | Spacer installation and today plan for final inspection
Sat (09/11) | 09 Nov 2024 | P2-4 |  | Pending toe confirmation
Sat (09/11) | 09 Nov 2024 | P2-4 |  | Rebar cage inspection by RTO
Sat (09/11) | 09 Nov 2024 | ST108 |  | 7/8 cages lowering in progress. Tonight to cast
Sat (09/11) | 09 Nov 2024 | BP6B | 8 | Boring in progress, 30.5/38.57m
Sat (09/11) | 09 Nov 2024 | ST138 |  | 2nd bite, reached 13m
Sat (09/11) | 09 Nov 2024 | Zone 3 |  | Weekly crane inspection
Sat (09/11) | 09 Nov 2024 | Exit 2 |  | Current desander status
Sat (09/11) | 09 Nov 2024 | P33 |  | KTC excavation. Soil internal shift to vent shaft for segregation
Sat (09/11) | 09 Nov 2024 | DR1 CH58-35 |  | 2nd lift wall rebar works ongoing
Sat (09/11) | 09 Nov 2024 | P36-37 |  | Continue steel plate protection for utilities
Sat (09/11) | 09 Nov 2024 | ST150-151 |  | LSS type 3 backfill for soil mixing prior to guidewall excavation/construction
Sat (09/11) | 09 Nov 2024 | ST144A | BC3 | B1 in progress, 31.5/39.6m
Sat (09/11) | 09 Nov 2024 | DR1 |  | Wall rebar formwork closing
Sat (09/11) | 09 Nov 2024 | ST202 |  | Trimming for waterstop end plate for removal
Sat (09/11) | 09 Nov 2024 | ST138 | BC2 | Diesel topup before resuming B1
Sat (09/11) | 09 Nov 2024 | ST133-134 |  | Guidewall trial trench
Sat (09/11) | 09 Nov 2024 | ST122 |  | Casting completed
Sat (09/11) | 09 Nov 2024 | P43-6 |  | Rebar cage lowering ongoing
Sat (09/11) | 09 Nov 2024 | Zone 4 |  | Trial trench done to find the Singtel actual alignment
Sat (09/11) | 09 Nov 2024 | P50 |  | Trial trench by GCE. Awaiting for utility team confirmation
Sat (09/11) | 09 Nov 2024 | P51-11 |  | Rebar cage installation
Sat (09/11) | 09 Nov 2024 | MH2-9 |  | No activity. Waiting for mini excavator thereafter to start thrust wall hacking
Sat (09/11) | 09 Nov 2024 | MH2-10 |  | Hacking ongoing for 14th layer. As to date, 13/16 layers completed
Sat (09/11) | 09 Nov 2024 | Exit 3 |  | Inclinometer in-wall installation by RG ongoing
Sat (09/11) | 09 Nov 2024 | TMH4 |  | Today to cast base slab
Sat (09/11) | 09 Nov 2024 | P12 |  | C-channel installation ongoing
Sat (09/11) | 09 Nov 2024 | P10 |  | No activity
Sat (09/11) | 09 Nov 2024 | P9 |  | Crosshead rebar works in progress
Sat (09/11) | 09 Nov 2024 | P7 |  | Unloading soldier piles
Sat (09/11) | 09 Nov 2024 | P6 |  | Preboring ongoing
Sat (09/11) | 09 Nov 2024 | BP6B | 8 | Boring reached 31m
Sat (09/11) | 09 Nov 2024 | ST207 |  | Rebar cage inspection
Sat (09/11) | 09 Nov 2024 | ST207 | BC1 | WS trimming temporarily stopped. Cutter machine issue
Sat (09/11) | 09 Nov 2024 | BRP25 |  | Preboring in progress
Sat (09/11) | 09 Nov 2024 | P33 |  | Hacking works & excavation ongoing
Sat (09/11) | 09 Nov 2024 | BRP45 |  | B1 completed. Cutter teeth changing ongoing
Sat (09/11) | 09 Nov 2024 | DR1 CH58-35 |  | Falsework erection and 2nd lift wall formwork in progress
Sat (09/11) | 09 Nov 2024 | P2-4 |  | Casting in progress
Sat (09/11) | 09 Nov 2024 | P16 |  | Base casting done
Sat (09/11) | 09 Nov 2024 | P12 |  | Cross head soffit playwood placing and jack installation
Sat (09/11) | 09 Nov 2024 | P9 |  | Erection of GI pipes support for rebar work and side bar installation
Sat (09/11) | 09 Nov 2024 | Exit 3 |  | Stockpile status
Sat (09/11) | 09 Nov 2024 | Zone 2 |  | Housekeeping at rest area
Sat (09/11) | 09 Nov 2024 | P12 |  | Wingforms installed. Falseworks installation ongoing
Sat (09/11) | 09 Nov 2024 | TMH4 |  | Rebar works in progress
Sat (09/11) | 09 Nov 2024 | P9 |  | Crosshead rebar works ongoing
Sun (10/11) | 10 Nov 2024 | DR1 |  | Inspection to continue inner formwork closing
Sun (10/11) | 10 Nov 2024 | ST138 |  | 2nd bite excavation. Current depth is 26m/34.50m
Sun (10/11) | 10 Nov 2024 | ST144A |  | Waterstop side trimming on going. Current trimming depth 33m
Sun (10/11) | 10 Nov 2024 | ST108A |  | Concrete casting started
Mon (11/11) | 11 Nov 2024 | P51-12 |  | Casing installed. Boring going to start
Mon (11/11) | 11 Nov 2024 | Zone 1 |  | Half height hoarding replacement to wire mesh
Mon (11/11) | 11 Nov 2024 | P3 |  | Hacking of premix for ERSS TT. Tomorrow LE will start TT
Mon (11/11) | 11 Nov 2024 | P5-2 |  | Pre-boring completed
Mon (11/11) | 11 Nov 2024 | ST133-134 |  | Guidewall construction in progres
Mon (11/11) | 11 Nov 2024 | P38 |  | Rain shelter erection ongoing
Mon (11/11) | 11 Nov 2024 | ST138 | BC2 | WS trimming completed. Now c-lug removal and preparation for endplate removal
Mon (11/11) | 11 Nov 2024 | P36-37 |  | Steel plate protection installation ongoing
Mon (11/11) | 11 Nov 2024 | MH2-10 |  | 14th layer excavation in progress
Mon (11/11) | 11 Nov 2024 | MH2-9 |  | No activity
Mon (11/11) | 11 Nov 2024 | P8 |  | Waler beam MPI scheduel to tomorrow
Mon (11/11) | 11 Nov 2024 | P9 |  | Access installation for rebar works
Mon (11/11) | 11 Nov 2024 | TMH4 |  | Wall rebar works. To cast tomorrow
Mon (11/11) | 11 Nov 2024 | MH3-5 |  | Today no activity. Tomorrow will resume
Mon (11/11) | 11 Nov 2024 | P44 |  | Woh hup started excavation to segregate hardcore and soil
Mon (11/11) | 11 Nov 2024 | MH3-4 |  | Preparing for wall casting. 600mm height
Mon (11/11) | 11 Nov 2024 | Exit 1 |  | Current status of soil stockpile
Mon (11/11) | 11 Nov 2024 | ST138 |  | Cleaning in progress
Mon (11/11) | 11 Nov 2024 | ST159 |  | Started excavation, reached 9m
Mon (11/11) | 11 Nov 2024 | DR1 |  | Formwork closing for sewer pipe support
Mon (11/11) | 11 Nov 2024 | BRP25 |  | KP lowering in progress
Mon (11/11) | 11 Nov 2024 | P18 |  | Packing concrete removal and soil backfilling
Mon (11/11) | 11 Nov 2024 | P12 |  | Cross head formwork installation
Mon (11/11) | 11 Nov 2024 | P9 |  | Access erection by woh hup
Mon (11/11) | 11 Nov 2024 | P8 |  | No activity already
Mon (11/11) | 11 Nov 2024 | P5-5 |  | Boring work until 7PM
Mon (11/11) | 11 Nov 2024 | MH2-10 |  | Excavation for next layer caisson work
Mon (11/11) | 11 Nov 2024 | P51-12 |  | Boring reached 15.5m
Mon (11/11) | 11 Nov 2024 | P51-7,8,9 |  | Base grouting. GCE already end work. Tomorrow will resume with two teams
Tue (12/11) | 12 Nov 2024 | P3 status |  | Today to continue premix hacking for ERSS TT
Tue (12/11) | 12 Nov 2024 | P51-12 |  | Boring in progress, reached 16.5m
Tue (12/11) | 12 Nov 2024 | P33 |  | Manual excavation below services and KTC exposing utility posts
Tue (12/11) | 12 Nov 2024 | BRP45 |  | Cutter teeth change and diesel topup ongoing
Tue (12/11) | 12 Nov 2024 | BRP47 |  | Preboring ongoing
Tue (12/11) | 12 Nov 2024 | DR1 CH58-35 |  | Top slab formwork and 2nd lift wall works ongoing
Tue (12/11) | 12 Nov 2024 | P6 |  | Shifting of soldier pile for installation
Tue (12/11) | 12 Nov 2024 | P8 |  | Waiting for tester to do MPI
Tue (12/11) | 12 Nov 2024 | P9 |  | Fabrication of tendon ducts and rings
Tue (12/11) | 12 Nov 2024 | DR1 |  | Stump support formwork fabrication ongoing
Tue (12/11) | 12 Nov 2024 | DR1 |  | Today LE on site and plan to strut removal at CH80
Tue (12/11) | 12 Nov 2024 | ST159 | BC3 | B1 in progress, 22/35m
Tue (12/11) | 12 Nov 2024 | P36-37 |  | Currently no activit
Tue (12/11) | 12 Nov 2024 | ST150-151 |  | Guidewall cast, ST152: Premix hacking for guidewall trial trench
Tue (12/11) | 12 Nov 2024 | BC2 |  | Shifted from ST138 to next panel at receving shaft
Tue (12/11) | 12 Nov 2024 | MH3-5 |  | Today plan to cast 3m height of permanent manhole
Tue (12/11) | 12 Nov 2024 | P9 crosshead rebar installation status |  | Main bars: 70% completed, Distribution bars: 70% completed, Stirrups: 50% completed
Tue (12/11) | 12 Nov 2024 | ST138 |  | Cleaning and desanding completed. Rebar cage inspection ongoin
Tue (12/11) | 12 Nov 2024 | BR1 |  | Hacking ongoing to expose couplers
Tue (12/11) | 12 Nov 2024 | P12 |  | Side formwork installed. Adjusting in progress
Tue (12/11) | 12 Nov 2024 | BP6B | 8 | Boring in progress, 36/38.75m
Tue (12/11) | 12 Nov 2024 | MH3-4 |  | Clearing materials for formwork removal
Tue (12/11) | 12 Nov 2024 | P43-4 |  | Boring reached 12m
Tue (12/11) | 12 Nov 2024 | P44 |  | Woh hup just segregate hardcore and soil only
Tue (12/11) | 12 Nov 2024 | P18 |  | Backfilling to stump level
Tue (12/11) | 12 Nov 2024 | P51-12 |  | Boring continue. Reached 18m. Encounter hard rock
Tue (12/11) | 12 Nov 2024 | P44 |  | Hardcore and soil segregation. No access for excavation as of now
Tue (12/11) | 12 Nov 2024 | P43-4 |  | Boring reached 20m depth
Tue (12/11) | 12 Nov 2024 | P6 |  | Soldier pile installation in progress
Tue (12/11) | 12 Nov 2024 | MH2-9 |  | Thrust block hacking ongoing. Currently workers on break
Tue (12/11) | 12 Nov 2024 | MH2-10 |  | 14th layer construction in progress
Tue (12/11) | 12 Nov 2024 | Exit 3 |  | Trial trench ongoing for TKP
Tue (12/11) | 12 Nov 2024 | BP6B | 8 | Boring in progress, 37/38.57m. Target to cast tmr
Tue (12/11) | 12 Nov 2024 | TMH4 |  | Waiting for concrete truck for wall casting
Tue (12/11) | 12 Nov 2024 | P12 |  | Pier hacking ongoing
Tue (12/11) | 12 Nov 2024 | P9 |  | Continue crosshead rebar works and preparing tendon duct pipes installation
Tue (12/11) | 12 Nov 2024 | P6 |  | No activity
Tue (12/11) | 12 Nov 2024 | Gate 5 |  | Reinstalling height limit gantry
Tue (12/11) | 12 Nov 2024 | ST207 | BC1 | Cleaning ongoing
Tue (12/11) | 12 Nov 2024 | BR1 |  | Continue exposing couplers and excavation
Tue (12/11) | 12 Nov 2024 | P33 |  | Removing hardcores
Tue (12/11) | 12 Nov 2024 | BRP45 | BC4 | Cutter wheel maintenance ongoing. CD 20.4/24.67m
Tue (12/11) | 12 Nov 2024 | ST138 |  | 3/6nos rebar cages lowered
Tue (12/11) | 12 Nov 2024 | ST121 | BC2 | Cutter body washing ongoing. CD 12/39m
Tue (12/11) | 12 Nov 2024 | P43-4 |  | Boring in progress
Tue (12/11) | 12 Nov 2024 | ST159 | BC3 | Excavation temporarily stopped. Gearbox replacement ongoing, CD 28/35m
Tue (12/11) | 12 Nov 2024 | DR1 CH58-35 |  | Top slab rebar works & 2nd lift wall formwork in progress. Dayshift team has ended works, night team to takeover
Tue (12/11) | 12 Nov 2024 | BR1 |  | Slope protection casting
Tue (12/11) | 12 Nov 2024 | MH2-10 |  | 14th layer hacking and excavation in progress. Today plan for casting
Tue (12/11) | 12 Nov 2024 | MH2-9 |  | Delivery of compressor for thrust wall hacking
Tue (12/11) | 12 Nov 2024 | BP5-5 |  | Boring works in progress. Current soil stockpile at zone 1
Wed (13/11) | 13 Nov 2024 | P32 | GL19-20 | Hacking ongoing to expose couplers
Wed (13/11) | 13 Nov 2024 | P33 |  | Manual excavation below utilities
Wed (13/11) | 13 Nov 2024 | ST207 |  | Rebar cage lowering in progress
Wed (13/11) | 13 Nov 2024 | ST138 |  | Preparing for casting
Wed (13/11) | 13 Nov 2024 | ST132-131A |  | Trial trench
Wed (13/11) | 13 Nov 2024 | ST121 | BC2 | Cutter teeth replacement ongoing
Wed (13/11) | 13 Nov 2024 | BRP45 | Rig 4 | B2 CD 23.7/24.67m
Wed (13/11) | 13 Nov 2024 | BRP47 | BG01 | P1 Preboring CD 25.35/25.87m
Wed (13/11) | 13 Nov 2024 | ST150-151 |  | Guidewall formwork removal, ST152-153: Guidewall construction in progress, ST154: Trial trench
Wed (13/11) | 13 Nov 2024 | P43-4 |  | Boring reached 22.5m
Wed (13/11) | 13 Nov 2024 | MH3-4 |  | Today plan to cast 600mm height of permanent manhole
Wed (13/11) | 13 Nov 2024 | P9 |  | RWDP and Tendon duct installation started
Wed (13/11) | 13 Nov 2024 | ST154 |  | Abandoned cables. Have checked with utility team and they have started to clear out these since yesterday for along this stretch
Wed (13/11) | 13 Nov 2024 | ST159 | BC3 | Internal koden check
Wed (13/11) | 13 Nov 2024 | P2-3 |  | Pre-boring for casing installation
Wed (13/11) | 13 Nov 2024 | MH2-9 |  | Continue thrust block hackin
Wed (13/11) | 13 Nov 2024 | MH2-10 |  | Currently no activity yet. Manpower just came and finished TBM
Wed (13/11) | 13 Nov 2024 | P18 |  | Compaction, 4pm NDT
Wed (13/11) | 13 Nov 2024 | GL19-20 |  | Current status of exposed couplers. Hacking continue
Wed (13/11) | 13 Nov 2024 | BR1 |  | Soil trimming continue and access installation ongoing
Wed (13/11) | 13 Nov 2024 | P38 |  | RG trial trench in progress for inclino, water standpipe and piezometer
Wed (13/11) | 13 Nov 2024 | ST138 |  | Casting in progress, 180/240m3
Wed (13/11) | 13 Nov 2024 | ST131A |  | Trial trench in progress
Wed (13/11) | 13 Nov 2024 | MH3-4 |  | Current status
Wed (13/11) | 13 Nov 2024 | ST121 |  | B1 in progress, 30.8/39m
Wed (13/11) | 13 Nov 2024 | MH3-5 |  | Rebars for cast in wall inspection done. Now formwork installation ongoing
Wed (13/11) | 13 Nov 2024 | P43-4 |  | Boring temporarily stopped. Machine broke down, mechanic on site checking
Wed (13/11) | 13 Nov 2024 | P50 |  | GCE trial trench in progress
Wed (13/11) | 13 Nov 2024 | P51-12 |  | Depth check ongoing
Wed (13/11) | 13 Nov 2024 | P2-3 |  | Boring works and soil disposal
Wed (13/11) | 13 Nov 2024 | ST159 | BC3 | WS trimming completed
Wed (13/11) | 13 Nov 2024 | BR5 |  | KTC excavation ongoing
Wed (13/11) | 13 Nov 2024 | BRP47 |  | P1 preboring completed. Preparing to start next preboring point
Wed (13/11) | 13 Nov 2024 | BRP45 |  | B1 completed. Cutter teeth maintenance ongoing
Wed (13/11) | 13 Nov 2024 | DR1 |  | LE removing main & secondary beams from CH80
Wed (13/11) | 13 Nov 2024 | CH58-45 |  | Top slab works in progress
Wed (13/11) | 13 Nov 2024 | Nearby BR1 |  | Sump pit relocation to facilitate platform for machinery parking
Wed (13/11) | 13 Nov 2024 | ST201 |  | B1 in progres
Wed (13/11) | 13 Nov 2024 | ST207 |  | Last rebar cage lapping, 6/6nos
Wed (13/11) | 13 Nov 2024 | BP6B | 8 | KP installed. Now ongoing dolly welding
Wed (13/11) | 13 Nov 2024 | BP6 | 13 | Preboring completed. Casing installed
Wed (13/11) | 13 Nov 2024 | MH2-9 |  | Continue thrust block hacking
Wed (13/11) | 13 Nov 2024 | MH2-10 |  | Formwork dismantled for 14th layer. Now hacking ongoing for 15th layer
Wed (13/11) | 13 Nov 2024 | BP6 | 13 | Boring in progress
Wed (13/11) | 13 Nov 2024 | BP6B | 8 | Casting
Wed (13/11) | 13 Nov 2024 | ST207 |  | Hanging bar lapping in progress
Wed (13/11) | 13 Nov 2024 | BR1 |  | Continue slope trimming
Wed (13/11) | 13 Nov 2024 | ST201 |  | B1 in progress, 31.5/34.2m
Wed (13/11) | 13 Nov 2024 | MH2-9 |  | Preparing to resume thrust block hacking
Wed (13/11) | 13 Nov 2024 | MH2-10 |  | 14th layer casting completed earlier this morning. The team will come back this afternoon
Wed (13/11) | 13 Nov 2024 | Exit 3 |  | Inclinometer IW31003 coring in progress, 34m
Wed (13/11) | 13 Nov 2024 | P48 |  | Woh hup doing TT to find 300mm water pipe bend. Yesterday found Tee Joint
Wed (13/11) | 13 Nov 2024 | P50 |  | GCE continue 4th TT
Wed (13/11) | 13 Nov 2024 | P51-12 |  | Boring reached 22.5m
Wed (13/11) | 13 Nov 2024 | P12 |  | Side formwork adjusting
Thu (14/11) | 14 Nov 2024 | ST207 |  | Casting in progress
Thu (14/11) | 14 Nov 2024 | P6 |  | Soldier pile driving. 22/26
Thu (14/11) | 14 Nov 2024 | BR1 |  | Continues excavation & exposing of couplers
Thu (14/11) | 14 Nov 2024 | MH2-9 |  | Thrust block hacking ongoing
Thu (14/11) | 14 Nov 2024 | MH2-10 |  | Hacking & excavation ongoing for 15th layer
Thu (14/11) | 14 Nov 2024 | BRP47 | BG01 | P2 Preboring CD 18.0/25.87m
Thu (14/11) | 14 Nov 2024 | BR5 |  | Excavation in progress
Thu (14/11) | 14 Nov 2024 | ST131 - ST132 |  | Guide wall construction in progress
Thu (14/11) | 14 Nov 2024 | P8 |  | Tendon duct installation in progress. 30% completed
Thu (14/11) | 14 Nov 2024 | TMH4 |  | 2nd stage wall and top slab formwork closing
Thu (14/11) | 14 Nov 2024 | Zone 4 |  | P51-12 boring CD 28.7/29.63m
Thu (14/11) | 14 Nov 2024 | BR1 | GL19-20 | Couplers exposed
Thu (14/11) | 14 Nov 2024 | BR1 |  | Soil trimming in progress
Thu (14/11) | 14 Nov 2024 | Zone 4 near LP 107 |  | TT to find 300mm water pipe T joint
Thu (14/11) | 14 Nov 2024 | P51-12 |  | Rebar cage inspection prior to lowering
Thu (14/11) | 14 Nov 2024 | P50 |  | TT for ERSS JGP. Found singtel, army cable, 300mm and 700mm waterpipe
Thu (14/11) | 14 Nov 2024 | MH3-4 |  | 2nd lift wall precast chamber was lean con
Thu (14/11) | 14 Nov 2024 | P43-4 |  | Boring in progress, 30m
Thu (14/11) | 14 Nov 2024 | ST121 |  | B1 in progress, 36.6/39m
Thu (14/11) | 14 Nov 2024 | ST132-131A |  | Guidewall rebar works ongoing
Thu (14/11) | 14 Nov 2024 | ST150 | BC3 | B1 just started. CD 3m
Thu (14/11) | 14 Nov 2024 | ST152-154 |  | Guidewall rebar works ongoing
Thu (14/11) | 14 Nov 2024 | BR5 |  | Excavation in progress
Thu (14/11) | 14 Nov 2024 | BRP47 |  | P2 preboring ongoing
Thu (14/11) | 14 Nov 2024 | DR1 |  | Starhub protection completed
Thu (14/11) | 14 Nov 2024 | ST201 |  | WS trimming completed. Endplate extraction ongoing
Thu (14/11) | 14 Nov 2024 | BP6 | 13 | Boring in progress, 24.5/36.5m
Thu (14/11) | 14 Nov 2024 | P9 |  | Girder box rebar installation in progress
Thu (14/11) | 14 Nov 2024 | MH2-10 |  | 14/16 layers completed. Now Now hacking of concrete slab
Thu (14/11) | 14 Nov 2024 | MH2-9 |  | Currently no activity
Thu (14/11) | 14 Nov 2024 | Exit 3 |  | Removal of backfill soil (1m) before capping beam works
Thu (14/11) | 14 Nov 2024 | BP6 | 13 | Boring continue till 7pm
Thu (14/11) | 14 Nov 2024 | BR5 |  | Excavation ongoing
Thu (14/11) | 14 Nov 2024 | ST159 |  | WS joint welding ongoing
Thu (14/11) | 14 Nov 2024 | P43-4 |  | Boring in progress, 34m
Thu (14/11) | 14 Nov 2024 | ST121 |  | B2 in progress, 6m
Thu (14/11) | 14 Nov 2024 | BR1 |  | Soil trimming ongoing. Utility kingposts have been painted in luminous colour
Thu (14/11) | 14 Nov 2024 | BP6 | 13 | Boring CD 22.5/36.5m
Fri (15/11) | 15 Nov 2024 | P50 |  | TT for pipe sleeves installation
Fri (15/11) | 15 Nov 2024 | P8 |  | Excavation to FEL
Fri (15/11) | 15 Nov 2024 | P5-2 |  | Boring works on going
Fri (15/11) | 15 Nov 2024 | P10 |  | Formwork dismantling
Fri (15/11) | 15 Nov 2024 | BP6-13 |  | Boring reached 29m
Fri (15/11) | 15 Nov 2024 | BRP18 |  | Boring reached 26.5m. Now preparing to change teeth
Fri (15/11) | 15 Nov 2024 | ST201 |  | 3/3 lowering in progress. Tonight to cast
Fri (15/11) | 15 Nov 2024 | DR1 |  | CGS no activity already
Fri (15/11) | 15 Nov 2024 | P43-4 |  | Casting in progress. Left one test pile here to complete
Sat (16/11) | 16 Nov 2024 | P6 |  | ERSS installation completed
Sat (16/11) | 16 Nov 2024 | Zone 1 |  | Preparing to shift column formwork to zone 2
Sat (16/11) | 16 Nov 2024 | P5-2 |  | Boring in progress. Today plan for casting
Sat (16/11) | 16 Nov 2024 | P9 |  | Tonight will continue formwork closing
Sat (16/11) | 16 Nov 2024 | BP5-2 |  | Tremie pipe lowered down. Now tidy up the area for casting. Concrete ordered
Sat (16/11) | 16 Nov 2024 | BP6 | 13 | Boring in progress, 30/36.5m. G3 layer was encountered at 22m on 14/11
Sat (16/11) | 16 Nov 2024 | BRP18 | BC4 | Excavation ongoing 32.8/38.47m
Sat (16/11) | 16 Nov 2024 | BR1 |  | Soil trimming and excavation ongoin
Sat (16/11) | 16 Nov 2024 | P33 |  | Continue manual excavation below services
Sat (16/11) | 16 Nov 2024 | BRP47 |  | Preboring ongoing 21.4/25.87m
Sat (16/11) | 16 Nov 2024 | BR5 |  | Excavation ongoing
Sat (16/11) | 16 Nov 2024 | ST152-154 |  | Guidewall cast
Sat (16/11) | 16 Nov 2024 | ST150 | BC3 | B2 in progress,19/31.3m
Sat (16/11) | 16 Nov 2024 | MH3-4 |  | Preparing for LSS backfill
Sat (16/11) | 16 Nov 2024 | P43 |  | HSL no boring activity
Sat (16/11) | 16 Nov 2024 | ST121 | BC2 | B2 in progress, 36.5/36.65m
Sat (16/11) | 16 Nov 2024 | MH3-5 |  | No activity
Sat (16/11) | 16 Nov 2024 | P50 |  | Trial trench ongoing by GCE. 1nos pipe sleeve installed
Sat (16/11) | 16 Nov 2024 | Zone 4 |  | HSL boring right now dismantling ongoing. This rig plan to move to zone 3
Sat (16/11) | 16 Nov 2024 | MH2-10 |  | Dewatering ongoing before continuing for 15th layer
Sat (16/11) | 16 Nov 2024 | MH2-9 |  | Thrust block hacking completed. Surface levelling to be done. Currently no activity due to heavy rain
Sat (16/11) | 16 Nov 2024 | ST24 | BC1 | B2 in progress
Sat (16/11) | 16 Nov 2024 | BP6 | 13 | Boring in progress, 31.5/36.5m
Sat (16/11) | 16 Nov 2024 | DR1 |  | LE demobilising their materials
Sat (16/11) | 16 Nov 2024 | Exit 3 |  | Woh hup shifting of soil and levelling
Sat (16/11) | 16 Nov 2024 | ST124 |  | 2nd bite, reached 32m
Sat (16/11) | 16 Nov 2024 | BRP18 |  | Boring reached 34m. Now teeth changing
Sat (16/11) | 16 Nov 2024 | BRP47 |  | Preboring reached 22.5m
Sat (16/11) | 16 Nov 2024 | DR1 |  | Woh hup levelling along Dwall until 10PM
Sat (16/11) | 16 Nov 2024 | ST150 |  | 1st & 2nd bite excavation completed. Now changing teeth
Sat (16/11) | 16 Nov 2024 | ST121 |  | C lock welding for waterstop end plate trimming
Sat (16/11) | 16 Nov 2024 | P18 |  | No activity
Sat (16/11) | 16 Nov 2024 | TMH4 |  | Today plan for manhole neck rebar fabrication
Sat (16/11) | 16 Nov 2024 | P12 |  | 1 side of the crosshead formwork installed
Sat (16/11) | 16 Nov 2024 | Zone 4 Junction |  | PowerGas doing M&P for their completed work area
Sat (16/11) | 16 Nov 2024 | P10 |  | Crosshead formwork dismantling ongoing
Sat (16/11) | 16 Nov 2024 | P9 |  | Tendon duct pipes installation in progress. Today also plan for side formwork installation
Sat (16/11) | 16 Nov 2024 | P9 |  | Formwork closing for cross head
Sat (16/11) | 16 Nov 2024 | P12 |  | No activity tonight
Sat (16/11) | 16 Nov 2024 | P10 |  | Tonight will do formwork removal at bus lane area after last bus
Sat (16/11) | 16 Nov 2024 | P8 |  | Current status of excavation to FEL
Sun (17/11) | 17 Nov 2024 | P9 |  | Continue formwork installation
Sun (17/11) | 17 Nov 2024 | ST124 |  | 2nd bite, reached 33.5m
Sun (17/11) | 17 Nov 2024 | BRP18 |  | Now cutter teeth changing
Sun (17/11) | 17 Nov 2024 | BRP47 |  | Preboring reached 25m
Mon (18/11) | 18 Nov 2024 | BP5-4 |  | Boring works on going
Mon (18/11) | 18 Nov 2024 | P6 |  | Today KTC to mobilise for excavation
Mon (18/11) | 18 Nov 2024 | P8 |  | Excavation completed. Lean concrete at 5pm
Mon (18/11) | 18 Nov 2024 | P9 |  | Crosshead formwork closing and continue tendon duct installation
Mon (18/11) | 18 Nov 2024 | P10 |  | Installation of working platform for post tensioning
Mon (18/11) | 18 Nov 2024 | N2-N3 |  | Excavation to continue telco duct construction
Mon (18/11) | 18 Nov 2024 | Near DR4 |  | Woh hup doing TT to locate water pipe
Mon (18/11) | 18 Nov 2024 | P51 |  | TT by GCE and hand augering
Mon (18/11) | 18 Nov 2024 | MH3-5 |  | Today to install back drop pipe
Mon (18/11) | 18 Nov 2024 | BRP29 |  | Excavation just started. 6m depth
Mon (18/11) | 18 Nov 2024 | BR2 |  | Manual excavation for Utility support installation to continue until 10pm
Mon (18/11) | 18 Nov 2024 | BRP47 |  | Pre boring continue. Current depth 15.60m
Mon (18/11) | 18 Nov 2024 | DR1 roof slab work |  | No more activity. Night shift team to take over
Mon (18/11) | 18 Nov 2024 | ST150 |  | Rebar cage installation continue, 4/6 cages installed
Mon (18/11) | 18 Nov 2024 | ST145 |  | B1 trenching continue at 27m depth
Mon (18/11) | 18 Nov 2024 | ST134 |  | 2nd bite trenching in progress at 9m depth
Mon (18/11) | 18 Nov 2024 | ST121 |  | Rebar cage installation, 6/8 cages installed
Tue (19/11) | 19 Nov 2024 | P18 |  | Rain water drain pipe installation
Tue (19/11) | 19 Nov 2024 | Gate 5 |  | Manual excavation for water pipe link up tonight
Tue (19/11) | 19 Nov 2024 | STN24 |  | Cleaning in progress
Tue (19/11) | 19 Nov 2024 | BP3 | 17 | Pre-boring and preparation for casing installation
Tue (19/11) | 19 Nov 2024 | BP6B | 4 | Pre boring and casing installation completed
Tue (19/11) | 19 Nov 2024 | P18 column |  | RWDP installed. Prepreparation for formwork closing
Tue (19/11) | 19 Nov 2024 | N2-N3 |  | Telco duct formwork closing. To cast tonight. 12m
Tue (19/11) | 19 Nov 2024 | P9 |  | Side formwork modification
Tue (19/11) | 19 Nov 2024 | P10 |  | Tendon wire pulling for PT. Bottom part completed
Tue (19/11) | 19 Nov 2024 | P9 |  | Links installation
Tue (19/11) | 19 Nov 2024 | P8 |  | Pile head hacking, 2/6
Tue (19/11) | 19 Nov 2024 | P6 |  | Excavation to FEL until 10pm
Tue (19/11) | 19 Nov 2024 | MH2-10 |  | 15th layer casting in progress
Wed (20/11) | 20 Nov 2024 | BP3 | 17 | Pre-boring and preparation for casing installation completed, Waiting for verticality check
Wed (20/11) | 20 Nov 2024 | BP6 | 13 | Casted yesterday
Wed (20/11) | 20 Nov 2024 | Link up location 2 |  | Pipe cutting completed
Wed (20/11) | 20 Nov 2024 | Location 1 |  | Cutting in progress
Wed (20/11) | 20 Nov 2024 | Location 1 |  | Cutting done. Preparing for link up to new pipe
Wed (20/11) | 20 Nov 2024 | Location 1 |  | Pipe link up completed. Note: left to install Bakau pile, BRC and haunching
Wed (20/11) | 20 Nov 2024 | Location 2 |  | Pipe link up done. Tightening in progress
Wed (20/11) | 20 Nov 2024 | DR1 |  | Drain top slab casting done
Wed (20/11) | 20 Nov 2024 | P10 |  | Tendon wire pulling for PT
Wed (20/11) | 20 Nov 2024 | Location 2 |  | Haunch casting completed
Wed (20/11) | 20 Nov 2024 | Location 1 |  | Haunch casting in progress
Wed (20/11) | 20 Nov 2024 | P9 |  | Scaffold access dismantling
Wed (20/11) | 20 Nov 2024 | P8 |  | Pile head hacking. 3/6
Wed (20/11) | 20 Nov 2024 | P6 |  | Excavation to FEL completed. Railing and access installation in progress
Wed (20/11) | 20 Nov 2024 | P3 |  | TT completed. Preparing working platform for pre-boring
Wed (20/11) | 20 Nov 2024 | P44-45 |  | TT for JGP works. 7/23 completed at this area
Wed (20/11) | 20 Nov 2024 | P44 |  | Excavation to S1 layer status. Work stopped for the day
Wed (20/11) | 20 Nov 2024 | ST127 |  | 1st bite trenching started
Wed (20/11) | 20 Nov 2024 | ST134 |  | Rebar cage lowering, 2/6 installed
Wed (20/11) | 20 Nov 2024 | ST145 |  | 2nd bite trenching at 27.6m. Now gear oil top up
Wed (20/11) | 20 Nov 2024 | BRP47 |  | 3rd bite trenching at 22.4m depth
Wed (20/11) | 20 Nov 2024 | BR1 |  | Hacking to expose coupler head
Wed (20/11) | 20 Nov 2024 | BRP29-BC4 |  | Desanding in progress
Wed (20/11) | 20 Nov 2024 | ST24 |  | Desanding completed. Preparation for final koden test
Thu (21/11) | 21 Nov 2024 | N2-N3 |  | Telco duct pipe laying. 12m to cast today
Thu (21/11) | 21 Nov 2024 | P10 |  | Tendon wire pulling continue
Thu (21/11) | 21 Nov 2024 | MH3-5 |  | LSS ordered for backfilling of 3m height
Thu (21/11) | 21 Nov 2024 | MH3-4 |  | No activity now
Thu (21/11) | 21 Nov 2024 | P44 |  | Current status of exposing for steel plate installation
Thu (21/11) | 21 Nov 2024 | P4 half |  | Preboring started
Thu (21/11) | 21 Nov 2024 | P3 |  | Pre-boring continue
Thu (21/11) | 21 Nov 2024 | P44 |  | Steel plate installation work on going
Thu (21/11) | 21 Nov 2024 | MH3-5 |  | LSS backfilling
Thu (21/11) | 21 Nov 2024 | P45 |  | Hand augering in progress
Thu (21/11) | 21 Nov 2024 | P36 |  | Current status of roof slab excavation
Thu (21/11) | 21 Nov 2024 | BRP47 |  | Bring up cutter body for teeth changing
Thu (21/11) | 21 Nov 2024 | DR1 fissure grouting |  | 4nos boring done and 3nos grouting done as of today
Thu (21/11) | 21 Nov 2024 | DR1 |  | Woh hup closing formwork for sewer pipe support & CGS install Geotextile at drain opening
Thu (21/11) | 21 Nov 2024 | BRP29 |  | Hanging bar installation
Thu (21/11) | 21 Nov 2024 | P18 |  | Column formwork closing
Thu (21/11) | 21 Nov 2024 | N2 |  | VSK plan to cast 12m length of teleco duct
Thu (21/11) | 21 Nov 2024 | P10 |  | Crack rectification and cable pulling
Thu (21/11) | 21 Nov 2024 | P9 |  | Woh hup, Wendyng & Utracon working. 3 contractors. Tendon duct, tendon box and starter bar installation
Thu (21/11) | 21 Nov 2024 | P6 |  | Now LE preparing to shift vibro for 1st layer waler work
Thu (21/11) | 21 Nov 2024 | P8 |  | HSL hacking of pile head
Thu (21/11) | 21 Nov 2024 | P3 |  | Total preboring done, 03/19
Thu (21/11) | 21 Nov 2024 | MH2-10 |  | Continue excavation for 16th layer
Fri (22/11) | 22 Nov 2024 | MH3-5 |  | LSS backfilling need 2 loads more
Fri (22/11) | 22 Nov 2024 | P44 |  | KTC excavation for steel plate installation. No access for soil disposal until now
Fri (22/11) | 22 Nov 2024 | BP5-1 |  | Pre-boring started for casing installation
Fri (22/11) | 22 Nov 2024 | P6 |  | Bracket welding completed. Waler to install today
Fri (22/11) | 22 Nov 2024 | Zone 2/1 junction beside P6 |  | Condition ok. No discharge of silty water to public
Fri (22/11) | 22 Nov 2024 | P3 |  | Pre-boring ror ERSS in progress
Sat (23/11) | 23 Nov 2024 | P10 |  | Wedges and base plate installation
Sat (23/11) | 23 Nov 2024 | P9 |  | Shear link installation. Duct installation and preparing for side formwork closing
Sat (23/11) | 23 Nov 2024 | N1-N2 |  | Lean concrete for next telco duct pipe laying completed
Sat (23/11) | 23 Nov 2024 | P8 |  | Clearing hardcore. Today will lean concrete the base
Sat (23/11) | 23 Nov 2024 | P6 |  | Waler joint welding
Sat (23/11) | 23 Nov 2024 | P5-1 |  | Boring work. Today to cast
Sat (23/11) | 23 Nov 2024 | P3 |  | Preboring for ERSS, 06/19 done
Sat (23/11) | 23 Nov 2024 | P9 |  | Formwork tie tod installation at section 1-3
Sat (23/11) | 23 Nov 2024 | P8 |  | Lean concrete in progress
Sat (23/11) | 23 Nov 2024 | P44 |  | Continue excavation and steel plate installation
Sat (23/11) | 23 Nov 2024 | MH3-5 |  | Shifting of jacking machine control room to MH3-4
Sat (23/11) | 23 Nov 2024 | P45 |  | Hand augering for JGP
Sat (23/11) | 23 Nov 2024 | P50 |  | Pipe sleeve installation
Sat (23/11) | 23 Nov 2024 | ST145 |  | 3rd bite cleaning and desanding
Sat (23/11) | 23 Nov 2024 | P36 |  | Current status of excavation
Sat (23/11) | 23 Nov 2024 | BRP47 |  | 1st bite, trimming in progress
Sat (23/11) | 23 Nov 2024 | DR1 |  | As of now no activity
Sat (23/11) | 23 Nov 2024 | ST200 |  | 1st bite, reached 30m
Sat (23/11) | 23 Nov 2024 | Exit 2 |  | Woh hup clearing hardcore and tidy up the area
Sat (23/11) | 23 Nov 2024 | P18 |  | Column casting
Sat (23/11) | 23 Nov 2024 | P9 |  | Continue lift up formwork materials and prepare formwork for closing
Sat (23/11) | 23 Nov 2024 | P8 |  | Clearing hardcore for lean concrete
Sat (23/11) | 23 Nov 2024 | P6 |  | Now no activity. LE having break time
Sat (23/11) | 23 Nov 2024 | P5-1 |  | Lowering rebar cage for casting
Sat (23/11) | 23 Nov 2024 | BRP29 |  | LSS backfilling
Sat (23/11) | 23 Nov 2024 | P32 |  | Preparing for lean concrete
Sat (23/11) | 23 Nov 2024 | DR1 |  | Seongha will work until 7PM today
Sat (23/11) | 23 Nov 2024 | DR1 |  | LSS backfilling at drain side was done
Sat (23/11) | 23 Nov 2024 | P45 |  | Hand augering for JGP work
Sat (23/11) | 23 Nov 2024 | P44 |  | Plan complete installation of all lagging plates today. KTC mobilized excavator
Sat (23/11) | 23 Nov 2024 | ST200-BC1 |  | Teeth replacement, current at 1st bite 32m
Sat (23/11) | 23 Nov 2024 | P33-34 |  | Manual excavation for Utility support installation, until 10pm
Sat (23/11) | 23 Nov 2024 | BRP47-BC4 |  | Teet changing. Current at 1st bite 24.43m
Sat (23/11) | 23 Nov 2024 | STN149-BC3 |  | Pre-excavation completed. Tonight to start trenching
Sat (23/11) | 23 Nov 2024 | STN133-BC2 |  | Current at 1st bite, 15m depth. Now soil cleaning at cutter wheel
Sat (23/11) | 23 Nov 2024 | STN145 |  | Preparation for final koden test
Sat (23/11) | 23 Nov 2024 | STN133-BC2 |  | Current at 1st bite, 15m depth. Now soil cleaning at cutter wheel
Sat (23/11) | 23 Nov 2024 | BP3-17 |  | Reached 27.5m
Sat (23/11) | 23 Nov 2024 | BP6B-4 |  | Reached 36.2/ 39.731m
Sat (23/11) | 23 Nov 2024 | Exit 3 |  | Exposing Dwall for capping beam
Sat (23/11) | 23 Nov 2024 | P18 |  | Column casting will be after lunch. Now concrete pump on site already
Sat (23/11) | 23 Nov 2024 | N2-N3 |  | VSK will continue excavation for teleco duct
Sat (23/11) | 23 Nov 2024 | P12 |  | Now no work
Sun (24/11) | 24 Nov 2024 | ST200 |  | Trenching resume at 1st bite
Sun (24/11) | 24 Nov 2024 | BRP47-BC4 |  | Teet changing. Current at 1st bite 22.6m
Sun (24/11) | 24 Nov 2024 | STN149-BC3 |  | Trenching started
Sun (24/11) | 24 Nov 2024 | STN145 |  | End plate installation
Sun (24/11) | 24 Nov 2024 | STN127 |  | Rebar cage installation. 2/3 cages installed
Mon (25/11) | 25 Nov 2024 | MH2-10 |  | Hacking and excavation for base slab
Mon (25/11) | 25 Nov 2024 | MH2-9 |  | No activity
Mon (25/11) | 25 Nov 2024 | P10 crosshead |  | Tensioning in progress, T2a in progress, 4/12 completed, 22s
Mon (25/11) | 25 Nov 2024 | BR5 |  | Soil trimming/levelling and guidewall hacking ongoin
Mon (25/11) | 25 Nov 2024 | P9 |  | Cast in anchor installation
Mon (25/11) | 25 Nov 2024 | BRP47 | BC4 | Cutter wheel replacement ongoing, B1 CD 23.55/25.87m
Mon (25/11) | 25 Nov 2024 | Zone 4, P50 |  | Trial Trench excavation for JGP point P50-31, P50-30 trial trench, hand augering and pipe sleeve installation completed
Mon (25/11) | 25 Nov 2024 | Zone 4, P44-P45 |  | JGP grouting completed for Point C9, Preparation for Point C35 JGP drilling and grouting in progress
Mon (25/11) | 25 Nov 2024 | MH3-4 |  | Pipe jacking setting up works in progress
Mon (25/11) | 25 Nov 2024 | P44 |  | Excavation to S1 layer completed. Levelling works in progress
Mon (25/11) | 25 Nov 2024 | Exit 3 |  | Exposing capping beam
Mon (25/11) | 25 Nov 2024 | BP6B | 4 | Kingpost installation ongoing
Mon (25/11) | 25 Nov 2024 | Exit 2 |  | Excavation for SPPG localised shifting to facilitate balance dwall here
Mon (25/11) | 25 Nov 2024 | BP3 | 17 | Boring in progress
Mon (25/11) | 25 Nov 2024 | ST200 | BC1 | B2 excavation temporarily stopped. Machine hose rectification ongoing
Mon (25/11) | 25 Nov 2024 | ST19 |  | Guidewall rebar works
Mon (25/11) | 25 Nov 2024 | ST133 | BC2 | Night shift operator handover
Mon (25/11) | 25 Nov 2024 | BR5 |  | Soil trimming and slope protection lean con casting ongoing
Mon (25/11) | 25 Nov 2024 | BR1 |  | Survey check ongoing
Tue (26/11) | 26 Nov 2024 | P33 | CJ2 | Utility support works ongoing
Tue (26/11) | 26 Nov 2024 | DR1 |  | Housekeeping ongoing by CGS
Tue (26/11) | 26 Nov 2024 | DR1 |  | Support installation ongoing by WH
Tue (26/11) | 26 Nov 2024 | BR1 |  | Base clean up and preparation for next section of lean con casting
Tue (26/11) | 26 Nov 2024 | ST200 | BC1 | B2 in progress, 33.9/34.2m
Tue (26/11) | 26 Nov 2024 | BRP47 | BC4 | Machine rectification ongoing
Tue (26/11) | 26 Nov 2024 | BR5 |  | Hacking and excavation ongoing, Slope protection lean con casting/levelling
Tue (26/11) | 26 Nov 2024 | P38 |  | RG trial trench ongoing for piezometer and water standpipe
Tue (26/11) | 26 Nov 2024 | P10 | south side | Preparation for tensioning
Tue (26/11) | 26 Nov 2024 | ST133 | BC2 | B2 in progress, 32/34m
Tue (26/11) | 26 Nov 2024 | N5 |  | Soil backfilling and levelling in preparation for segment launching
Tue (26/11) | 26 Nov 2024 | Exit 2 |  | Desander status
Tue (26/11) | 26 Nov 2024 | Exit 1 |  | Stockpile
Tue (26/11) | 26 Nov 2024 | Z4 LA | Changi bound | Lane closure by other contractor
Tue (26/11) | 26 Nov 2024 | P44/45 |  | JGP point D10 grouting in progress
Tue (26/11) | 26 Nov 2024 | P50 |  | GCE trial trench and pipe sleeve installation
Tue (26/11) | 26 Nov 2024 | MH3-4 |  | Pipe jacking setting u
Tue (26/11) | 26 Nov 2024 | P43 |  | No activity
Tue (26/11) | 26 Nov 2024 | Loyang Way | opposite exit 1 gate | Telstra lane closure
Tue (26/11) | 26 Nov 2024 | N5 |  | Continue excavation and levelling works preparation for segment launching
Tue (26/11) | 26 Nov 2024 | Bet. N1-N2 |  | 12m telco duct pipe laying completed. Preparation to close formwork and cast today
Tue (26/11) | 26 Nov 2024 | MH2-10 |  | Continue hacking and preparation for base lean con
Tue (26/11) | 26 Nov 2024 | Exit 3 |  | Hacking of capping beam
Tue (26/11) | 26 Nov 2024 | P50 |  | Premix hacking to continue TT for ERSS
Tue (26/11) | 26 Nov 2024 | Zone 4 P44-45 |  | JGP grouting works for C-34
Tue (26/11) | 26 Nov 2024 | Exit 3 |  | HSL preparing platform
Tue (26/11) | 26 Nov 2024 | ST19, ST20 |  | Guidewall ready to cast
Tue (26/11) | 26 Nov 2024 | ST200 |  | WS trimming in progress
Tue (26/11) | 26 Nov 2024 | DR2 canal |  | Observed no silty discharge
Tue (26/11) | 26 Nov 2024 | P12 |  | Crosshead rebar delivery ongoing, 2/3 trucks on site
Tue (26/11) | 26 Nov 2024 | P10 | south side | Tendon stressing works ongoing, 2/12 nos. completed
Tue (26/11) | 26 Nov 2024 | Exit 3 |  | Hacking of capping beam ongoing
Tue (26/11) | 26 Nov 2024 | Exit 3 |  | Preboring started for TKP A8-AC
Tue (26/11) | 26 Nov 2024 | P10 |  | Tendon stressing in progress. 3/12nos completed
Tue (26/11) | 26 Nov 2024 | BP6B | 5 | Boring in progress, 22/39.37m, BP3(17): Boring in progress, 33/37.53m
Tue (26/11) | 26 Nov 2024 | BRP47 |  | Excavation in progress, 24/25m
Tue (26/11) | 26 Nov 2024 | MH2-10 |  | Excavation ongoing for base slab. Today plan to cast lean con
Tue (26/11) | 26 Nov 2024 | MH2-9 |  | No activity
Wed (27/11) | 27 Nov 2024 | P18 |  | Column formwork dismantled
Wed (27/11) | 27 Nov 2024 | P10 |  | Post-tensioning works completed, 12/12nos. Now housekeeping
Wed (27/11) | 27 Nov 2024 | P9 |  | Crosshead rebar works in progress
Wed (27/11) | 27 Nov 2024 | P8 |  | Pilecap casting ongoing
Wed (27/11) | 27 Nov 2024 | BP6B | 5 | Boring in progress, BP3(17): Boring in progress, 36/37.53m
Wed (27/11) | 27 Nov 2024 | Exit 3 |  | TKP A8-AC boring in progress
Wed (27/11) | 27 Nov 2024 | Gate 5 |  | Bachy crane body on standby. Plan to demob tonight
Wed (27/11) | 27 Nov 2024 | ST19-20 |  | Guidewall formwork dismantling
Wed (27/11) | 27 Nov 2024 | BR1 |  | Pumping out water
Wed (27/11) | 27 Nov 2024 | P33 |  | Premix removal to facilitate temporary sump pit
Wed (27/11) | 27 Nov 2024 | DR1 |  | Benching hacking was done. Currently no activity
Wed (27/11) | 27 Nov 2024 | BR5 |  | No activity
Wed (27/11) | 27 Nov 2024 | BRP47 | BC4 | Cutter body up to clear hard rock. CD 24.7/25.87m
Wed (27/11) | 27 Nov 2024 | ST149 | BC3 | B2 in progress, 28.9/31.3m
Thu (28/11) | 28 Nov 2024 | Stage 0 slip road |  | Material segregation for shifting
Thu (28/11) | 28 Nov 2024 | MH2-10 |  | Base slab rebar works. Today plan for casting
Thu (28/11) | 28 Nov 2024 | MH2-9 |  | No activity
Thu (28/11) | 28 Nov 2024 | Exit 3 |  | TKP A8-AC boring in progress, 17/30.23m
Thu (28/11) | 28 Nov 2024 | Exit 3 |  | Capping beam hacking
Thu (28/11) | 28 Nov 2024 | P9 |  | All formwork close. Final alignment on going
Thu (28/11) | 28 Nov 2024 | BP6B | 5 | Boring in progress 28.5/39.37
Thu (28/11) | 28 Nov 2024 | BP3 | 17 | Boring completed plan to cast 4pm
Thu (28/11) | 28 Nov 2024 | BR1 |  | Another set of coupler rebars on site
Thu (28/11) | 28 Nov 2024 | Exit 2 |  | Area preparation for SPPG localised shifting. The stockpiles are for the backfilling of this area
Thu (28/11) | 28 Nov 2024 | ST200 |  | Rebar cage installation
Thu (28/11) | 28 Nov 2024 | BR1 |  | Preparing for next section lean con casting
Thu (28/11) | 28 Nov 2024 | DR1 |  | Existing benching hacking done, debris clearing ongoin
Thu (28/11) | 28 Nov 2024 | DR1 |  | Constructed drain formwork dismantling
Thu (28/11) | 28 Nov 2024 | BP3-17 |  | Casting in progress, running volume 15/22 m3
Thu (28/11) | 28 Nov 2024 | BP2-1 | 33 | Pre-boring in progress
Thu (28/11) | 28 Nov 2024 | ST20-BC1 |  | Excavation continue
Thu (28/11) | 28 Nov 2024 | ST200 |  | Rebar cage lowering, 5/6 cages
Thu (28/11) | 28 Nov 2024 | BRP47-BG1 |  | Preboring continue, depth at 24.4m
Thu (28/11) | 28 Nov 2024 | STN49-BC3 |  | Cleaning and end plate extraction
Thu (28/11) | 28 Nov 2024 | ST127 |  | Trenching started
Thu (28/11) | 28 Nov 2024 | Zone 4 JGP |  | Grouting for 3rd points
Thu (28/11) | 28 Nov 2024 | P51 |  | Premix hacking for ERSS TT to continue until 10pm
Fri (29/11) | 29 Nov 2024 | P9 |  | Rebar and tendon still need to adjust at section 5 and 6 and cast in achor support installation. Now raining, no activity. Plan to cast tomorrow instead
Fri (29/11) | 29 Nov 2024 | P9 |  | Cast in anchor support installation in progress
Fri (29/11) | 29 Nov 2024 | P11-2 |  | Hardcore backfilling and levelling
Fri (29/11) | 29 Nov 2024 | P12 |  | Rebar installation in progress
Fri (29/11) | 29 Nov 2024 | P11 | south side | Area leveling for lean concrete
Fri (29/11) | 29 Nov 2024 | BP6B | 5 | Boring continue at 33.1m depth. HSL to work until 10pm
Fri (29/11) | 29 Nov 2024 | BP2-1 | 33 | Boring in progress. Depth at 27m. Boring to stopped at 8pm
Fri (29/11) | 29 Nov 2024 | ST20-BC1 |  | Machine Idle, operator change shift
Fri (29/11) | 29 Nov 2024 | BRP30-BC4 |  | Trenching in progress, 10m depth
Fri (29/11) | 29 Nov 2024 | BR1 |  | Lean concrete in progress
Fri (29/11) | 29 Nov 2024 | TKP-A8-AC |  | Boring in progress at 25m depth
Fri (29/11) | 29 Nov 2024 | Exit 3 |  | Barricade installation at capping beam area and soil stockpiling
Fri (29/11) | 29 Nov 2024 | P10 |  | Dismantling works ongoing
Fri (29/11) | 29 Nov 2024 | P8 |  | No activity
Fri (29/11) | 29 Nov 2024 | P12 |  | Crosshead rebar works in progress
Fri (29/11) | 29 Nov 2024 | BP6B | 5 | Boring continue till 10pm. CD 33.5/39.377m
Fri (29/11) | 29 Nov 2024 | BP2-1 | 33 | WLT pile, 1600mm dia. Boring started today. Now CD 28/40.41m, working till 10pm
Fri (29/11) | 29 Nov 2024 | BRP30 | BC4 | Excavation in progress, 10/31.8m
Fri (29/11) | 29 Nov 2024 | BR1 |  | No activity
Fri (29/11) | 29 Nov 2024 | BRP47 |  | Preboring in progress (PB5), 16/25.87m
Fri (29/11) | 29 Nov 2024 | BR5 |  | Excavation ongoing till 10pm
Fri (29/11) | 29 Nov 2024 | ST20 | BC1 | Excavation temporarily stopped. BC cutter suction hose replacement ongoing
Fri (29/11) | 29 Nov 2024 | ST158 | BC3 | B1 in progress, 10/35m
Fri (29/11) | 29 Nov 2024 | ST149 |  | Rebar cage installation in progress, 3/6nos
Fri (29/11) | 29 Nov 2024 | ST127A | BC2 | Excavation in progress, 28.4/34m
Sat (30/11) | 30 Nov 2024 | P50 |  | GCE trial trench ongoing
Sat (30/11) | 30 Nov 2024 | BP6B | 5 | Boring continue at 34.5m depth
Sat (30/11) | 30 Nov 2024 | BP2-1 | 33 | Boring in progress. Depth at 30m
Sat (30/11) | 30 Nov 2024 | BRP30-BC4 |  | Cutter wheel teeth replacement
Sat (30/11) | 30 Nov 2024 | BRP47-BG1 |  | Preboring continue
Sat (30/11) | 30 Nov 2024 | BR5 |  | Barrete pile hacking
Sat (30/11) | 30 Nov 2024 | MH3-4 |  | Boring machine installed and 1st pipe setting for pipe jacking
Sat (30/11) | 30 Nov 2024 | P44 ERSS |  | Waler beam yet to install. Waiting for vibro mobilisation. Expect today
Sat (30/11) | 30 Nov 2024 | Zone 4 |  | Area preparation for JGP
Sat (30/11) | 30 Nov 2024 | P9 |  | Crosshead casting in progress
Sat (30/11) | 30 Nov 2024 | P1-5 |  | Boring continue. Plan to cast today
Sat (30/11) | 30 Nov 2024 | P9 |  | Cast in anchor pipe support installation
Sat (30/11) | 30 Nov 2024 | Zone 4 C83 |  | Grouting in progress
Sat (30/11) | 30 Nov 2024 | BRP30-BC4 |  | Trenching continue at 28.2m depth
Sat (30/11) | 30 Nov 2024 | BP2-1 | 33 | Boring in progress. Depth at 30m. Stopped work due to bentonite pipe leaking. Repair in progress
Sat (30/11) | 30 Nov 2024 | ST20-BC1 |  | Excavation completed for 1st bite
Sat (30/11) | 30 Nov 2024 | BP6B | 5 | Boring continue at 35.3m depth
Sat (30/11) | 30 Nov 2024 | BRP18 |  | LSS backfilling
Sat (30/11) | 30 Nov 2024 | BP3-17 |  | LSS backfilling
Sat (30/11) | 30 Nov 2024 | Exit 3 |  | TKP A8-AC kingpost lowering. To cast tonight
Sat (30/11) | 30 Nov 2024 | Between N2-N3 |  | Backfilling ongoing
Sat (30/11) | 30 Nov 2024 | P10 |  | Dismantling works ongoing
Sat (30/11) | 30 Nov 2024 | P9 |  | Crosshead final inspection ongoing. To cast tonight. Concrete pump on site
Sat (30/11) | 30 Nov 2024 | P8 |  | No activity
Sat (30/11) | 30 Nov 2024 | BP6B | 5 | Boring continue till 10pm
Sat (30/11) | 30 Nov 2024 | ST20 | BC1 | B2 in progress, 11/36.2m
Sat (30/11) | 30 Nov 2024 | BRP30 | BC4 | Excavation temporarily stopped due to hydraulic leaking. CD 30.5/31.8m. Preparing for rectification
Sat (30/11) | 30 Nov 2024 | BR1 |  | Lean con done. No more activity now
Sat (30/11) | 30 Nov 2024 | BR5 |  | Excavation ongoing till 10pm
Sat (30/11) | 30 Nov 2024 | BRP47 |  | Preboring no activity. PB5 CD 19.9/25.87m
Sat (30/11) | 30 Nov 2024 | ST149 |  | Casting in progress, 162/224.5m
Sat (30/11) | 30 Nov 2024 | ST127A |  | WS trimming ongoing
Sat (30/11) | 30 Nov 2024 | MH3-4 |  | Pipe no.9 lowered. Works till 10pm only
Sat (30/11) | 30 Nov 2024 | TKP-A8-AC |  | Boring continue
Sat (30/11) | 30 Nov 2024 | Zone 4 junction |  | No activity tonight
Sun (01/12) | 01 Dec 2024 | ST20 |  | B2 CD 25/36.2m. Excavation temporarily stopped for cutter teeth change
Sun (01/12) | 01 Dec 2024 | BRP30 |  | Trimming ongoing
Sun (01/12) | 01 Dec 2024 | ST149 |  | Casting was completed. Total vol: 234.5m3
Sun (01/12) | 01 Dec 2024 | P12 |  | Crosshead rebar works ongoing
Sun (01/12) | 01 Dec 2024 | P10 |  | Continue dismantling works
Sun (01/12) | 01 Dec 2024 | P9 |  | Crosshead casting in progress, 229.5/304m3
Mon (02/12) | 02 Dec 2024 | MH2-9 |  | Manhole wall rebar works in progress
Mon (02/12) | 02 Dec 2024 | DW17 |  | Guidewall trial trench in progress
Mon (02/12) | 02 Dec 2024 | Exit 3 |  | Hacking ongoing for capping beam works
Mon (02/12) | 02 Dec 2024 | Exit 3 |  | Preboring started for TKP A6-AD
Mon (02/12) | 02 Dec 2024 | BP6B | 5 | Reached toe. Today plan for casting
Mon (02/12) | 02 Dec 2024 | BP2-1 | 33 | Boring in progress, 31/40.41m
Mon (02/12) | 02 Dec 2024 | Exit 2 |  | Area prepared for SPPG localised diversion. The team target to mobilise tmr
Mon (02/12) | 02 Dec 2024 | BR1 |  | Wendyng continue exposing couplers and ground trimming works
Mon (02/12) | 02 Dec 2024 | BP1-3 |  | Platform preparation for boring works
Mon (02/12) | 02 Dec 2024 | BR1 |  | Today plan to continue laying plywood and endplate welding for 2nos kingposts
Mon (02/12) | 02 Dec 2024 | DR1 |  | Currently no activity
Mon (02/12) | 02 Dec 2024 | BR5 |  | Continue excavation
Mon (02/12) | 02 Dec 2024 | BP1-3 |  | Casing installed. Boring to continue tomorrow
Tue (03/12) | 03 Dec 2024 | BR5 |  | Excavation in progress
Tue (03/12) | 03 Dec 2024 | BRP47 |  | Continue preboring
Tue (03/12) | 03 Dec 2024 | BC3 |  | BC cutter teeth maintenance ongoing. ST158 cleaning completed
Tue (03/12) | 03 Dec 2024 | P38 |  | RG drilling ongoing for water standpipe installation
Tue (03/12) | 03 Dec 2024 | ST119, ST120 |  | Hacking ongoing for guidewall works
Tue (03/12) | 03 Dec 2024 | MH3-4 |  | No activity
Tue (03/12) | 03 Dec 2024 | P44 |  | Waler joint welding works ongoing
Tue (03/12) | 03 Dec 2024 | ST127A |  | Casting in progress
Tue (03/12) | 03 Dec 2024 | BR1 |  | Roof slab rebar works started. Wendyng manpower: 16 rebar workers + 2 formwork workers + 1 safety + 1 sup
Tue (03/12) | 03 Dec 2024 | BR1 |  | Base plate welding ongoing for 2nos KPs (by WH)
Tue (03/12) | 03 Dec 2024 | CJ2 |  | Utility support works ongoing
Tue (03/12) | 03 Dec 2024 | BC4 |  | Currently no activity
Tue (03/12) | 03 Dec 2024 | Exit 2 |  | Ley Choon is here for the SPPG localised shifting works
Tue (03/12) | 03 Dec 2024 | ST20 | BC1 | C-lug welding works ongoing for WS trimming
Tue (03/12) | 03 Dec 2024 | BP2-1 | 33 | Boring in progress, 35/40.41m
Tue (03/12) | 03 Dec 2024 | BP6 | 14 | Preboring started
Tue (03/12) | 03 Dec 2024 | BP6B | 5 | LSS backfill
Tue (03/12) | 03 Dec 2024 | DR1 |  | Preparing for the water pipe installation for diversion
Tue (03/12) | 03 Dec 2024 | Exit 3 |  | TKP A6-AD boring in progress
Tue (03/12) | 03 Dec 2024 | Exit 3 |  | Manual trimming ongoing for capping beam works
Tue (03/12) | 03 Dec 2024 | P44 |  | Waler beam (double layer welding in progress)
Tue (03/12) | 03 Dec 2024 | P12 |  | Continue Crosshead rebar and tendon ducts installation works
Tue (03/12) | 03 Dec 2024 | P10 |  | Falseworks dismantling works
Tue (03/12) | 03 Dec 2024 | P8 |  | Platform access installation for column stump casting
Tue (03/12) | 03 Dec 2024 | P6 |  | Excavation to FEL
Tue (03/12) | 03 Dec 2024 | Zone 4 |  | JGP grouting in progress
Tue (03/12) | 03 Dec 2024 | P1-3 |  | BP rebar cages installation and lowering in progress
Tue (03/12) | 03 Dec 2024 | P3 |  | SP welding and jointing works
Tue (03/12) | 03 Dec 2024 | P3 |  | Preboring for 6m steel plate installation ongoing. Balance 4 nos
Tue (03/12) | 03 Dec 2024 | Exit 3 |  | Dwall hacking for capping beam works
Tue (03/12) | 03 Dec 2024 | BP3-14 |  | Boring works at 13m depth. Work until 8pm
Tue (03/12) | 03 Dec 2024 | P11 |  | Working platform assembly on ground
Tue (03/12) | 03 Dec 2024 | P3 |  | Pre-boring for steel plate, last no. Tomorrow 2pm MPI for soldier pile then start installation
Tue (03/12) | 03 Dec 2024 | P11 |  | Pad footing installation. To continue work for night shift
Tue (03/12) | 03 Dec 2024 | P12 |  | Tendon duct installation, 24 nos achor installed
Tue (03/12) | 03 Dec 2024 | MH2-9 |  | Manhole wall rebar works in progress
Tue (03/12) | 03 Dec 2024 | DW18 |  | Guidewall trial trench in progress
Wed (04/12) | 04 Dec 2024 | MH2-9 |  | Permanent MH base slab casting in progress
Wed (04/12) | 04 Dec 2024 | P12 crosshead |  | Tendon duct pipe installation, Crosshead: 24/32 completed, Segment: 9/42 completed
Wed (04/12) | 04 Dec 2024 | Exit 2 |  | Shifting SPPG cables ongoing by Ley Choon
Wed (04/12) | 04 Dec 2024 | P3 |  | No activity. MPI of SP completed
Wed (04/12) | 04 Dec 2024 | BR1 |  | RTO inspections were done for coupler threads, KPs endplates and structural surfaces. Maxbond also informed WH of the waterproofing points
Wed (04/12) | 04 Dec 2024 | ST127A |  | Cutter wheel teeth replacement
Wed (04/12) | 04 Dec 2024 | BR5 |  | Hacking and excavation to continue until 10pm
Wed (04/12) | 04 Dec 2024 | BR1 |  | Coupler bar installation continue
Wed (04/12) | 04 Dec 2024 | BR1 |  | KP location LSS backfilling
Thu (05/12) | 05 Dec 2024 | P50 |  | Briefing before start pipe sleeves installation. 23nos done as of now
Thu (05/12) | 05 Dec 2024 | TKP A6-AD |  | Boring in progress, 27/31.1m
Thu (05/12) | 05 Dec 2024 | BP6 | 14 | Boring in progress, 14/36.7m
Thu (05/12) | 05 Dec 2024 | BP2-1 | 33 | Toe level checking
Thu (05/12) | 05 Dec 2024 | ST20 |  | Rebar cage and hanging bar lowered. BC1 currently no activity
Thu (05/12) | 05 Dec 2024 | Exit 2 |  | SPPG cables shifted. Now ongoing backfilling quarry dust and provide concrete warning slabs
Thu (05/12) | 05 Dec 2024 | BR5 |  | Continue roof slab rebar works and waiting for manpower for rebar planting
Thu (05/12) | 05 Dec 2024 | DR1 |  | Concrete blocks and bund wall installation at exisiting drain
Thu (05/12) | 05 Dec 2024 | BRP47 | BC4 | B2 temporarily stopped. Cutter teeth change ongoing. CD 18/25.87m
Thu (05/12) | 05 Dec 2024 | BR5 |  | Hacking and excavation ongoing
Thu (05/12) | 05 Dec 2024 | ST148 | BC3 | B1 temporarily stopped for cutter teeth change. CD 34.8/39.6m
Thu (05/12) | 05 Dec 2024 | P38 |  | Rain shelter erection ongoing. RG IM installation ongoing
Thu (05/12) | 05 Dec 2024 | P38-P39 | CG-5 | Drilling in progress for curtain grouting permeability test
Thu (05/12) | 05 Dec 2024 | ST137 | BC2 | B3 in progress, 26m
Thu (05/12) | 05 Dec 2024 | ST119-120 |  | Guidewall cast
Thu (05/12) | 05 Dec 2024 | P44 |  | Continue welding work with 9 welders
Thu (05/12) | 05 Dec 2024 | MH3-5 |  | Cement patch up. Excavator on site for caisson hacking
Thu (05/12) | 05 Dec 2024 | P50 |  | TT done to install pipe sleeves. Minor adjustment to be done coz clashed with Sptel
Thu (05/12) | 05 Dec 2024 | DW17-18 |  | Guidewall formwork installation ongoing
Thu (05/12) | 05 Dec 2024 | MH2-9 |  | Joining of short pipe for permanent manhole
Thu (05/12) | 05 Dec 2024 | Exit 3 |  | Trimming ongoing for capping beam works
Thu (05/12) | 05 Dec 2024 | TKP A6-AD |  | Boring in progress
Thu (05/12) | 05 Dec 2024 | BP6 | 14 | Boring in progress, 27.8/36.7m
Thu (05/12) | 05 Dec 2024 | BP2-1 | 33 | Rebar cage installation ongoing
Thu (05/12) | 05 Dec 2024 | BC1 |  | Cutter wheel maintenance
Thu (05/12) | 05 Dec 2024 | ST20 |  | Tremie pipe installation ongoing
Thu (05/12) | 05 Dec 2024 | BR1 |  | Roof slab rebar works and preparing for lean con casting. KTC soil trimming ongoing
Thu (05/12) | 05 Dec 2024 | BRP47 |  | Resume B2 excavation
Thu (05/12) | 05 Dec 2024 | BR5 |  | Continue hacking and excavation works
Thu (05/12) | 05 Dec 2024 | P38 |  | Piezometer and water standpipe installation completed. RG will move their rig to P23
Thu (05/12) | 05 Dec 2024 | N5 |  | Excavation for segment launching
Thu (05/12) | 05 Dec 2024 | P11 |  | Falsework erection on going
Thu (05/12) | 05 Dec 2024 | ST148 | BC3 | Resume B1 excavation, 34.9/39.6m
Thu (05/12) | 05 Dec 2024 | ST137 |  | WS trimming
Thu (05/12) | 05 Dec 2024 | ST116 |  | Guidewall trial trench and removal of abandoned water pipe
Thu (05/12) | 05 Dec 2024 | P44 |  | Packing concrete casting done. Continue strut end and stiffener plate welding work
Thu (05/12) | 05 Dec 2024 | MH3-5 |  | Cement patch up work
Thu (05/12) | 05 Dec 2024 | P45 |  | Continue JGP grouting
Thu (05/12) | 05 Dec 2024 | P1-4 |  | Boring works hold at 33m depth, waiting of truck for spoil disposal
Thu (05/12) | 05 Dec 2024 | N5 |  | Continue excavation
Thu (05/12) | 05 Dec 2024 | N1 area |  | Trial trench & hacking ongoing for abandoned drain removal
Thu (05/12) | 05 Dec 2024 | P11 |  | Falsework erection in progress
Thu (05/12) | 05 Dec 2024 | P6 |  | Levelling works ongoing
Thu (05/12) | 05 Dec 2024 | BP6 | 14 | Boring in progress, 28/36.7m
Thu (05/12) | 05 Dec 2024 | BP3 | 19 | Preboring and casing installation
Thu (05/12) | 05 Dec 2024 | TKP A6-AD |  | Boring in progress, 29/32.1m. Noise balloon installation ongoing
Thu (05/12) | 05 Dec 2024 | ST20 |  | Casting in progress
Thu (05/12) | 05 Dec 2024 | BP2-1 | 33 | Kingpost installation
Thu (05/12) | 05 Dec 2024 | BR1 |  | Continue rebar works and soil trimming at CJ area
Thu (05/12) | 05 Dec 2024 | MH2-9 |  | Permanent MH base slab cast yesterday. Today continue wall rebar works
Thu (05/12) | 05 Dec 2024 | MH2-10 |  | Housekeeping and preparing area for pipe jacking works
Thu (05/12) | 05 Dec 2024 | DW17-18 |  | Guidewall rebar works ongoing. Today plan for casting
Fri (06/12) | 06 Dec 2024 | N1-P11 |  | Drain hacking and excavation for telco duct construction
Fri (06/12) | 06 Dec 2024 | P44 |  | Ryobi G installed the instrument. LE continue welding. Target today to complete
Fri (06/12) | 06 Dec 2024 | MH3-5 |  | Hacking of caisson in progress
Fri (06/12) | 06 Dec 2024 | P45 |  | Current status of soil stockpile. No JGP grouting at day time. Just night shift only
Fri (06/12) | 06 Dec 2024 | P11 |  | Falsework assembly status
Fri (06/12) | 06 Dec 2024 | ST148 |  | 2nd bite, reached 5m
Fri (06/12) | 06 Dec 2024 | MH2-10 |  | Preparing area for pipe jacking setup works
Fri (06/12) | 06 Dec 2024 | MH2-9 |  | Unloading rebars for MH wall
Fri (06/12) | 06 Dec 2024 | BRP8 |  | Trial trench in progress
Fri (06/12) | 06 Dec 2024 | P11 |  | Leg frame assembly
Fri (06/12) | 06 Dec 2024 | BC4 |  | Cutter teeth maintenance
Fri (06/12) | 06 Dec 2024 | DR1 |  | Barricade removal. Today will start drain wall hacking. Pipe provided to channel the water away from work area
Fri (06/12) | 06 Dec 2024 | Exit 2 |  | Backfilling of cable diverted area done. Briefing by woh hup to dongah on the safe work. Today 4+ 3 panels left to be done here
Fri (06/12) | 06 Dec 2024 | Exit 3 |  | Manual trimming ongoing for capping beam works
Fri (06/12) | 06 Dec 2024 | TKP A6-AD |  | Boring in progress
Fri (06/12) | 06 Dec 2024 | BP6 | 14 | Boring in progress
Fri (06/12) | 06 Dec 2024 | ST20 |  | Casting completed last night. LSS backfilling ongoing
Fri (06/12) | 06 Dec 2024 | BP3 | 19 | Casing installed. Preparing for boring works
Fri (06/12) | 06 Dec 2024 | P12 Area |  | KTC preparation for drain hacking works
Fri (06/12) | 06 Dec 2024 | P50 |  | 3nos of pipe sleeves installed as of now
Fri (06/12) | 06 Dec 2024 | P12 |  | Cast in anchor installation and rebar adjustment in progress
Fri (06/12) | 06 Dec 2024 | BR5 |  | Continue excavation and exposing deck posts
Fri (06/12) | 06 Dec 2024 | BRP47 |  | B2 in progress, 20.4/25.87m
Fri (06/12) | 06 Dec 2024 | P11 |  | Primary beam installation
Fri (06/12) | 06 Dec 2024 | ST148 | BC3 | B2 in progress
Fri (06/12) | 06 Dec 2024 | Zone 3 |  | Dongah crane boom down to replace red white checkered flag
Fri (06/12) | 06 Dec 2024 | Exit 1 |  | Stockpile status at desander area
Fri (06/12) | 06 Dec 2024 | ST116 |  | Guidewall construction in progress
Fri (06/12) | 06 Dec 2024 | ST118 | BC2 | Excavation just started this afternoon
Fri (06/12) | 06 Dec 2024 | Bet. N1 and P11 |  | Vsk excavation for telco duct works ongoing
Fri (06/12) | 06 Dec 2024 | P11 |  | Primary beam installation ongoing
Fri (06/12) | 06 Dec 2024 | P44 |  | Welding done. Preparing for testing. Woh hup started barricade installation also
Fri (06/12) | 06 Dec 2024 | MH3-5 |  | Current status of caisson hacking
Fri (06/12) | 06 Dec 2024 | BR1 |  | Pull-out test was done for the planted rebars
Fri (06/12) | 06 Dec 2024 | BR1 |  | Continue roof slab rebar works, B2-B3 layers
Fri (06/12) | 06 Dec 2024 | DR1 CH30-22 |  | Start drain wall hacking
Fri (06/12) | 06 Dec 2024 | Exit 3 |  | Continue manual trimming for capping beam
Fri (06/12) | 06 Dec 2024 | P23 |  | RG rig has shifted to this location
Fri (06/12) | 06 Dec 2024 | BP6 | 14 | Boring in progress
Fri (06/12) | 06 Dec 2024 | Exit 2 |  | Levelling works
Fri (06/12) | 06 Dec 2024 | BR1 |  | Roof slab rebar works ongoing
Fri (06/12) | 06 Dec 2024 | BRP47 | BC4 | Cutter teeth change ongoing
Fri (06/12) | 06 Dec 2024 | BR5 |  | TDPs exposed. Level checking ongoing. To continue lean con casting
Fri (06/12) | 06 Dec 2024 | TKP A6-AD |  | Kingpost lowered
Fri (06/12) | 06 Dec 2024 | DW18 |  | Excavation just started this afternoon
Fri (06/12) | 06 Dec 2024 | Zone 2 |  | Material shifting for stage 2 diversion
Fri (06/12) | 06 Dec 2024 | P50 |  | TT on going with two teams foe pipe sleeves installation
Fri (06/12) | 06 Dec 2024 | N5-N6 |  | Excavation and levelling continue for segment launching
Sat (07/12) | 07 Dec 2024 | P12 |  | Adjusting the rebar. Will continue shear link after this
Sat (07/12) | 07 Dec 2024 | P22 |  | Fissure grouting with one rig
Sat (07/12) | 07 Dec 2024 | P11 |  | Runner jointing
Sat (07/12) | 07 Dec 2024 | P8 |  | Now no activity
Sat (07/12) | 07 Dec 2024 | P6 |  | Pile head hacking
Sat (07/12) | 07 Dec 2024 | P1-2 |  | Platform preparation. Today will start casing installation and boring work
Sat (07/12) | 07 Dec 2024 | P12 |  | Adjusting crosshead tendon duct and links installation, WH: 5+1, Wendyng: 4+1
Sat (07/12) | 07 Dec 2024 | P11 |  | Working platform installation
Sat (07/12) | 07 Dec 2024 | P50 |  | Continue TT for pipe sleeves installation
Sat (07/12) | 07 Dec 2024 | ST118 |  | Preparing to resume 1st bite excavation. Cutter teeth changing done
Sat (07/12) | 07 Dec 2024 | ST137 |  | Tremie pipe lowering for casting
Sat (07/12) | 07 Dec 2024 | ST148 |  | 2nd bite, reached 33.8m
Sat (07/12) | 07 Dec 2024 | BRP47 |  | 2nd bite excavation in progress
Sat (07/12) | 07 Dec 2024 | DR1 |  | Existing drain hacking for new drain construction
Sat (07/12) | 07 Dec 2024 | Exit 2 |  | Excavation for guidewall started
Sat (07/12) | 07 Dec 2024 | Near Exit 3 |  | TT on going for bored pile work
Sat (07/12) | 07 Dec 2024 | DW18 |  | 2nd bite excavation, reached 21m
Sat (07/12) | 07 Dec 2024 | Exit 3 |  | Preboring started for TKP
Sat (07/12) | 07 Dec 2024 | BP6-14 |  | Rebar cage lowering. Today to cast. Crack inducer installed
Sat (07/12) | 07 Dec 2024 | BP3-19 |  | Boring reached 24m
Sat (07/12) | 07 Dec 2024 | P11 |  | Netting installation to prevent falling object
Sat (07/12) | 07 Dec 2024 | P12 |  | Rebar inspection by RTO and continue tightening of rebars
Sat (07/12) | 07 Dec 2024 | ST148 |  | 2nd bite in progress, reached 38.9m
Sat (07/12) | 07 Dec 2024 | P36 |  | Slope protection casting and access erection by woh hup. KTC continue excavation
Sat (07/12) | 07 Dec 2024 | BRP47 |  | 2nd bite in progress, reached 22m
Sat (07/12) | 07 Dec 2024 | DR1 |  | Continue hacking of drain wall
Sat (07/12) | 07 Dec 2024 | BRP17 |  | Preboring in progress
Sat (07/12) | 07 Dec 2024 | TKP-A8-AD |  | Boring works to continue until 10pm. Est depth 12m
Sat (07/12) | 07 Dec 2024 | DW18 |  | Koden test in progress
Sat (07/12) | 07 Dec 2024 | BRP47 |  | 2nd bite trenching at 27m depth. Now teeth replacement
Sat (07/12) | 07 Dec 2024 | STN148 |  | 2nd bite completed. Preparation for koden test and start trimming
Sat (07/12) | 07 Dec 2024 | STN137 |  | Casting completed, volume 262 m3
Sat (07/12) | 07 Dec 2024 | STN118 |  | 1st bite completed. C-lug welding for trimming
Sat (07/12) | 07 Dec 2024 | DW18 |  | 1st bite completed. Preparing for 2nd bite excavation. Now replacing hydraulic pipe
Sat (07/12) | 07 Dec 2024 | BRP8 |  | Excavation for guidewall
Sat (07/12) | 07 Dec 2024 | TKPA6-AD |  | LSS backfilling done
Sun (08/12) | 08 Dec 2024 | P8 |  | Column stump formwork dismantling
Sun (08/12) | 08 Dec 2024 | P6 and zone 1 |  | No activity
Sun (08/12) | 08 Dec 2024 | BRP9 |  | Trial trench
Sun (08/12) | 08 Dec 2024 | BR1 |  | Roof slab rebar works in progress. About 40% completed. 8 workers today
Sun (08/12) | 08 Dec 2024 | Exit 2 |  | Desander status
Sun (08/12) | 08 Dec 2024 | DR1 |  | No activity
Sun (08/12) | 08 Dec 2024 | BRP47 |  | B2 temporarily stopped. Cutter teeth changing ongoing. CD 23.19/25.87m
Sun (08/12) | 08 Dec 2024 | BR5 |  | Excavation and hacking works ongoing
Sun (08/12) | 08 Dec 2024 | ST148 | BC3 | B3 completed. Now ongoing cutter teeth changing and u-holder welding works
Sun (08/12) | 08 Dec 2024 | Exit 1 |  | Desander status
Sun (08/12) | 08 Dec 2024 | ST118 | BC2 | B2 in progress
Sun (08/12) | 08 Dec 2024 | MH3-4 |  | No activity
Sun (08/12) | 08 Dec 2024 | P44 |  | Excavation in progress
Sun (08/12) | 08 Dec 2024 | P46 |  | GCE tidying up area
Sun (08/12) | 08 Dec 2024 | Zone 4 |  | Stockpile
Sun (08/12) | 08 Dec 2024 | P50 |  | GCE trial trench and pipe sleeve installation
Sun (08/12) | 08 Dec 2024 | DW18 | BC1 | Trimming completed
Sun (08/12) | 08 Dec 2024 | Exit 3 |  | HSL no activity
Sun (08/12) | 08 Dec 2024 | P12 |  | Links installation continue
Sun (08/12) | 08 Dec 2024 | Exit 2 |  | ST212-213 preparing for guidewall works
Sun (08/12) | 08 Dec 2024 | BRP17 |  | Preboring ongoing. Noise balloon installed
Sun (08/12) | 08 Dec 2024 | BR1 |  | Continue rebar works
Sun (08/12) | 08 Dec 2024 | P34 |  | Premix/hardcore removal ongoing
Sun (08/12) | 08 Dec 2024 | BRP47 |  | Resume B2 excavation
Sun (08/12) | 08 Dec 2024 | BR5 |  | Clearing hardcores
Sun (08/12) | 08 Dec 2024 | BRP47-BC4 |  | 2nd bite trenching at 23m depth
Sun (08/12) | 08 Dec 2024 | DW18 |  | WS extraction
Sun (08/12) | 08 Dec 2024 | STN148-BC3 |  | Trimming completed for 2nd bite. Cutter body up to start 3rd bite
Sun (08/12) | 08 Dec 2024 | DW18 |  | Trimming in progress
Sun (08/12) | 08 Dec 2024 | P21 |  | Stockpile status
Sun (08/12) | 08 Dec 2024 | N5 area |  | No activity
Sun (08/12) | 08 Dec 2024 | P14 |  | Soil stockpile
Sun (08/12) | 08 Dec 2024 | N1 area |  | No activity for drain hacking
Sun (08/12) | 08 Dec 2024 | P12 |  | Tendon duct pipes & shearlinks installation ongoing
Sun (08/12) | 08 Dec 2024 | P11 |  | Falsework installation in progress
Mon (09/12) | 09 Dec 2024 | P50 |  | Hacking of drain wall for removal
Mon (09/12) | 09 Dec 2024 | P50 |  | Backfilling of completed. Pipe sleeves installed. 41/59 nos pipe sleeves installed. Target around Wednesday to complete
Mon (09/12) | 09 Dec 2024 | N5-N6 |  | Soil levelling and old drain hacking in progress for segment launching
Mon (09/12) | 09 Dec 2024 | MH2-9 |  | MH wall rebar works in progres
Mon (09/12) | 09 Dec 2024 | DW18 |  | Rebar cage lapping in progress
Mon (09/12) | 09 Dec 2024 | BR1 |  | Rebar works ongoing
Mon (09/12) | 09 Dec 2024 | DR1 |  | Drain wall hacking in progres
Mon (09/12) | 09 Dec 2024 | P34 |  | Preparing to cut abandoned water pipe and painting of luminous colour on UKP
Mon (09/12) | 09 Dec 2024 | BRP47 | BC4 | B2 in progress, 24.25/25.87m
Mon (09/12) | 09 Dec 2024 | ST151 | BC3 | B1 in progress
Mon (09/12) | 09 Dec 2024 | ST148 |  | WS joint works ongoing
Mon (09/12) | 09 Dec 2024 | BR5 |  | Excavation in progress
Mon (09/12) | 09 Dec 2024 | P12 |  | Crosshead adjusting alignment of PT duct and installation of cast in achor. Plan to cast on Wednesday
Mon (09/12) | 09 Dec 2024 | P11 |  | Bottom formwork jack installation started
Mon (09/12) | 09 Dec 2024 | ST118 | BC2 | B2 completed. Now cutter body washing
Mon (09/12) | 09 Dec 2024 | Exit 1 |  | Desander status
Mon (09/12) | 09 Dec 2024 | BP6C | 12 | Casing installation in progress
Mon (09/12) | 09 Dec 2024 | BP3 | 19 | Boring CD 25.5/37.602m
Mon (09/12) | 09 Dec 2024 | P44 |  | Continue excavation for 2nd layer waler. Wednesday to complete
Mon (09/12) | 09 Dec 2024 | MH3-4 |  | Jacking fully done
Mon (09/12) | 09 Dec 2024 | Exit 2 |  | ST214-215 guidewall excavation, ST212-213: Guidewall formwork in progress
Mon (09/12) | 09 Dec 2024 | Exit 3 |  | Capping beam rebar works in progress
Mon (09/12) | 09 Dec 2024 | MH2-9 |  | Permanent MH 1st lift wall casting
Mon (09/12) | 09 Dec 2024 | N1 |  | Excavation to expose abandoned drain for hacking
Mon (09/12) | 09 Dec 2024 | P12 crosshead |  | Final inspection completed for 1st half. Tonight to close formwork
Mon (09/12) | 09 Dec 2024 | P11 |  | Bottom form runner beam and c-channel installation
Mon (09/12) | 09 Dec 2024 | STN19 |  | 1st bite trenching, 32.35m. Cutter body hoist up for teeth replacement
Mon (09/12) | 09 Dec 2024 | BR1 |  | Top bar installation
Mon (09/12) | 09 Dec 2024 | BRP47 |  | 2nd bite trenching, current depth 24.60m. Now cutter body hoist up for teeth replacement
Tue (10/12) | 10 Dec 2024 | P12 |  | Girder box formwork closing
Tue (10/12) | 10 Dec 2024 | N2 |  | Exposing abandoned drain for hacking works
Tue (10/12) | 10 Dec 2024 | DW18 |  | Casting completed
Tue (10/12) | 10 Dec 2024 | Near gate 5 |  | WH temporarily remove walking access to facilitate trailer movement
Tue (10/12) | 10 Dec 2024 | TKP A8-AD |  | Temporarily stopped cos machine unable to work. Mechanic on the way. Current depth 23m/31.65m
Tue (10/12) | 10 Dec 2024 | BP3 | 19 | Boring in progress, 28/37.6m, BP6C(12): Boring in progress, 23/38.86m
Tue (10/12) | 10 Dec 2024 | BP2-1 | 33 | LSS backfill
Tue (10/12) | 10 Dec 2024 | ST19 |  | B1 excavation temporarily stopped. Hydraulic leakage, rectification ongoing. CD 34/38.49m
Tue (10/12) | 10 Dec 2024 | ST212-213 |  | Guidewall cast, ST214-215: Guidewall construction in progress
Tue (10/12) | 10 Dec 2024 | BRP17 |  | Preboring temporarily stopped. Machine checking ongoing. CD 27.2/38.49m
Tue (10/12) | 10 Dec 2024 | BRP30 |  | LSS backfill
Tue (10/12) | 10 Dec 2024 | Exit 2 |  | Desander status
Tue (10/12) | 10 Dec 2024 | P1-2 |  | Trench collapse yesterday evening and backfilled with LSS last night
Tue (10/12) | 10 Dec 2024 | P3 ERSS |  | Balance 8 LP for installation
Tue (10/12) | 10 Dec 2024 | BR1 |  | Roof slab rebar works & hyrib installation in progress
Tue (10/12) | 10 Dec 2024 | DR1 |  | Drain wall hacking completed. Level checking ongoing
Tue (10/12) | 10 Dec 2024 | BR5 |  | Excavation in progress
Tue (10/12) | 10 Dec 2024 | BR2 |  | Excavation in progress
Tue (10/12) | 10 Dec 2024 | Zone 3 |  | Ground levelling and cleaning ongoing
Tue (10/12) | 10 Dec 2024 | BRP47 | BC4 | B2 in progress, 25/25.87m
Tue (10/12) | 10 Dec 2024 | P44 |  | Excavation will complete by today and handover to LE
Tue (10/12) | 10 Dec 2024 | MH3-4 |  | Removal of bentonite pipes for water tightness test
Tue (10/12) | 10 Dec 2024 | MH3-5 |  | Plastering inside. This week to complete
Tue (10/12) | 10 Dec 2024 | P45-P46 |  | Woh hup TT to locate the HT. Preparation for water pipe diversion
Tue (10/12) | 10 Dec 2024 | ST148 |  | Rebar cage installation
Tue (10/12) | 10 Dec 2024 | P38-P39 | CG-5 | Drilling in progress for curtain grouting permeability test
Tue (10/12) | 10 Dec 2024 | ST118 | BC2 | Cleaning in progress
Tue (10/12) | 10 Dec 2024 | Exit 3 |  | Capping beam rebar inspection
Tue (10/12) | 10 Dec 2024 | P3 |  | Continue ERSS installation works
Tue (10/12) | 10 Dec 2024 | P6 |  | Pile head hacking for last pile. Plan to complete today. Tomorrow to clear debris
Tue (10/12) | 10 Dec 2024 | P8 |  | LSS backfilling to pile cap level started
Tue (10/12) | 10 Dec 2024 | P11 |  | Column hacking to correct level
Tue (10/12) | 10 Dec 2024 | P12 |  | Formwork closing. Tie rod installation in progress
Tue (10/12) | 10 Dec 2024 | BP6e-12 |  | Boring works in progress at 27m depth, to continue until 10pm. Noise ballon erection
Tue (10/12) | 10 Dec 2024 | ST19 |  | End plate extraction
Tue (10/12) | 10 Dec 2024 | BRP17 |  | Pre-boring continue
Tue (10/12) | 10 Dec 2024 | MH2-9 |  | 1st lift wall cast yesterday. Today to dismantle formwork and continue MH wall rebar works
Tue (10/12) | 10 Dec 2024 | MH2-10 |  | Area setup for pipe jacking
Tue (10/12) | 10 Dec 2024 | Exit 3 |  | Capping beam rebar works ongoing
Wed (11/12) | 11 Dec 2024 | P12 |  | Segment tendon still adjusting after rebar alignment adjustment. Box girder formwork also yet to be installed. Comfortably to cast only by tomorrow
Wed (11/12) | 11 Dec 2024 | P9 |  | Platform preparation for crane parking. Today to dismantle formwork
Wed (11/12) | 11 Dec 2024 | P44 |  | 2nd layer waler installation
Wed (11/12) | 11 Dec 2024 | BR1 |  | Continue roof slab rebar works and dowel bars installation. Also start to install formwork
Wed (11/12) | 11 Dec 2024 | BR2 |  | Excavation ongoing
Wed (11/12) | 11 Dec 2024 | Zone 3 | GL24 area | Clearing up rebars
Wed (11/12) | 11 Dec 2024 | BR5 |  | Continue excavation
Wed (11/12) | 11 Dec 2024 | MH2-9 |  | Next lift wall formwork installation in progress
Wed (11/12) | 11 Dec 2024 | MH2-10 |  | No activity
Wed (11/12) | 11 Dec 2024 | P5 |  | RG drilling for inclino
Wed (11/12) | 11 Dec 2024 | P20 |  | Trial trench works for BP in progress
Wed (11/12) | 11 Dec 2024 | N5 segment U01-U06 |  | Supports installation for segment launching in progress
Wed (11/12) | 11 Dec 2024 | Exit 3 capping beam area |  | DW1-4 retaining wall formwork installation ongoin
Wed (11/12) | 11 Dec 2024 | BP6C | 12 | Boring CD 35.0/38.683m
Wed (11/12) | 11 Dec 2024 | BRP9 |  | Trial trench in progress
Wed (11/12) | 11 Dec 2024 | BP3 | 19 | Boring CD 32.0/37.602m
Wed (11/12) | 11 Dec 2024 | BRP47 |  | Final koden checking
Wed (11/12) | 11 Dec 2024 | BR1 |  | Continue rebar tying and formwork installation
Wed (11/12) | 11 Dec 2024 | BR2 |  | Continue excavation
Wed (11/12) | 11 Dec 2024 | P12 |  | Continue Segment tendon and rebar alignment adjustment
Wed (11/12) | 11 Dec 2024 | P11-2 |  | Column hacking to correct level
Wed (11/12) | 11 Dec 2024 | P11 |  | Continue bottom formwork plywood laying
Wed (11/12) | 11 Dec 2024 | BR5 |  | Hacking and excavation in progress
Wed (11/12) | 11 Dec 2024 | ST151 | BC3 | Cutter teeth changing in progress. B1 CD 20.8/31.3m
Wed (11/12) | 11 Dec 2024 | P38-P39 | CG-5 | Drilling in progress for curtain grouting permeability test
Wed (11/12) | 11 Dec 2024 | P9 |  | Preparing for formwork dismantle
Wed (11/12) | 11 Dec 2024 | P8 |  | KTC backfilling and compaction works
Wed (11/12) | 11 Dec 2024 | P6-1 |  | Hardcores debris clearing in progress
Wed (11/12) | 11 Dec 2024 | BP1-2 |  | Preparing for LSS backfill
Wed (11/12) | 11 Dec 2024 | P5 |  | Preboring for ERSS installation commenced
Wed (11/12) | 11 Dec 2024 | ST128 | BC2 | B1 in progres
Wed (11/12) | 11 Dec 2024 | ST118 |  | WS joint welding in progress
Wed (11/12) | 11 Dec 2024 | MH3-4 |  | Permanent MH works in progress
Wed (11/12) | 11 Dec 2024 | P44 |  | 2nd layer waler installation in progress
Wed (11/12) | 11 Dec 2024 | P44 |  | Stockpile
Wed (11/12) | 11 Dec 2024 | P50 |  | Continue TT & hand augering
Wed (11/12) | 11 Dec 2024 | MH3-4 |  | Lowering the precast chamber. Today planned to cast this two rings
Wed (11/12) | 11 Dec 2024 | P44 |  | 2nd layer walers and strut to complete early next week
Wed (11/12) | 11 Dec 2024 | ST118 |  | Lowering of waterstop end plate
Wed (11/12) | 11 Dec 2024 | ST118 |  | Changing mud pump
Wed (11/12) | 11 Dec 2024 | N5 segment U01-U06 |  | Hardcore and steel plate laid. Today to start shoring for segment launching
Wed (11/12) | 11 Dec 2024 | P50 |  | Continue TT for pipe sleeves installation. This location a bit tight with services
Thu (12/12) | 12 Dec 2024 | P5 |  | Boring rig maintenance
Thu (12/12) | 12 Dec 2024 | MH2-9 |  | 2nd lift wall casting in progress
Thu (12/12) | 12 Dec 2024 | BRP9 |  | Abandoned cables verified. Removal & hacking works ongoing
Thu (12/12) | 12 Dec 2024 | BC4 |  | Cutter maintenance ongoing
Thu (12/12) | 12 Dec 2024 | P6 |  | Hardcore cleared. Tonight to lean concrete
Thu (12/12) | 12 Dec 2024 | BR1 |  | Continue bar chair installation, Walking platform installation, 4 layers RGT installed
Thu (12/12) | 12 Dec 2024 | DR1 CH20 |  | Area clearing to shift water pipe to this location
Thu (12/12) | 12 Dec 2024 | P12 |  | Adjusting tendon dict. Final inspection at 5pm
Thu (12/12) | 12 Dec 2024 | BR2 |  | Excavation in progres
Thu (12/12) | 12 Dec 2024 | BR5 |  | Rebar cutting and preparing excavated area (near dwall) for LSS backfill. Concrete pump on site
Thu (12/12) | 12 Dec 2024 | BR5 |  | Hacking ongoing
Thu (12/12) | 12 Dec 2024 | Exit 2 |  | Desander status
Thu (12/12) | 12 Dec 2024 | ST151 | BC3 | B1 trimming in progress
Thu (12/12) | 12 Dec 2024 | Exit 1 |  | Dongah soil internal shifting to exit 2
Thu (12/12) | 12 Dec 2024 | Exit 1 |  | Desander status
Thu (12/12) | 12 Dec 2024 | ST118 |  | Rebar cage installation in progress, 5/8nos
Thu (12/12) | 12 Dec 2024 | ST128 | BC2 | Soil clearing and cutter teeth replacement. B2 CD 18.2/34.2m
Thu (12/12) | 12 Dec 2024 | P44 |  | Continue welding of waler joint
Thu (12/12) | 12 Dec 2024 | MH3-4 |  | Today plan to cast the permanent manhole
Thu (12/12) | 12 Dec 2024 | N5 |  | Segment support installation no activity
Thu (12/12) | 12 Dec 2024 | BRP17 |  | Preboring in progress
Thu (12/12) | 12 Dec 2024 | BRP47 |  | Casting completed
Thu (12/12) | 12 Dec 2024 | ST19 | BC3 | Cutter teeth changing & wheel cleaning. B3 CD 3/35.8m
Thu (12/12) | 12 Dec 2024 | BP3 | 19 | Boring in progress, 36/37.6m
Thu (12/12) | 12 Dec 2024 | BP6C | 12 | Boring in progress, 34/38.86m
Thu (12/12) | 12 Dec 2024 | P23 |  | RG drilling ongoing for piezometer installation. Inclinometer installation completed
Thu (12/12) | 12 Dec 2024 | P21 |  | Soil segregation ongoing
Thu (12/12) | 12 Dec 2024 | Exit 3 |  | Desander status
Thu (12/12) | 12 Dec 2024 | Exit 3 |  | TKP A8-AC: Pending to cast, TKP A7-AC: Preboring started
Thu (12/12) | 12 Dec 2024 | P20 |  | TT for BP works completed
Thu (12/12) | 12 Dec 2024 | P8 |  | Backfilling to pile cap level, 4th layer
Thu (12/12) | 12 Dec 2024 | P6 |  | Level peg installation for lean concrete casting
Thu (12/12) | 12 Dec 2024 | P51 |  | Levelling of completed pipe sleeves area and preparing to continue TT
Thu (12/12) | 12 Dec 2024 | BP6C | 12 | Boring CD 34.5/38.683m
Thu (12/12) | 12 Dec 2024 | BP3 | 19 | Boring CD 35.0/37.602m
Thu (12/12) | 12 Dec 2024 | MH3-4 |  | Plan to cast the ring two layers by today
Thu (12/12) | 12 Dec 2024 | P44 |  | Continue 2nd layer waler joint welding
Fri (13/12) | 13 Dec 2024 | P51 |  | Checking of services against JGP point
Fri (13/12) | 13 Dec 2024 | BR1 |  | Continue rebar installation & formwork installation
Fri (13/12) | 13 Dec 2024 | N5 |  | Segment supports installation in progress
Fri (13/12) | 13 Dec 2024 | BR2 |  | Excavation in progress, GL24 onwards preparation to continue utility support works
Fri (13/12) | 13 Dec 2024 | BRP46 |  | Platform preparation
Fri (13/12) | 13 Dec 2024 | BR5 |  | A section was backfilled with LSS yesterday
Fri (13/12) | 13 Dec 2024 | BR5 |  | Continue excavation and preparing for next section of LSS backfill. Plan for backfilling tmr
Fri (13/12) | 13 Dec 2024 | ST151 | BC3 | B2 in progress, 24/31.3m
Fri (13/12) | 13 Dec 2024 | ST128 | BC2 | C-lug welding for WS trimming
Fri (13/12) | 13 Dec 2024 | Exit 1 |  | Desander status
Fri (13/12) | 13 Dec 2024 | ST118 |  | Casting in progress, 188.5/260m3
Fri (13/12) | 13 Dec 2024 | BP6C | 12 | Boring CD 37.5/38.683m
Fri (13/12) | 13 Dec 2024 | BP3 | 19 | Boring has completed, to cast today
Fri (13/12) | 13 Dec 2024 | P12 |  | Crosshead cast last night
Fri (13/12) | 13 Dec 2024 | Bet. P11-P12 |  | Excavation for telco duct in progress
Fri (13/12) | 13 Dec 2024 | P11-2 |  | Column pier hacking to correct level in progress
Fri (13/12) | 13 Dec 2024 | P44 |  | Double layer waler installation in progress. Today to complete
Fri (13/12) | 13 Dec 2024 | MH3-4 |  | Preparing to install Tee pipe
Fri (13/12) | 13 Dec 2024 | ST019 | Rig 1 | B3 CD 6/35.8m, meanwhile cutter teeth replacement in progress
Fri (13/12) | 13 Dec 2024 | BRP17 | BG01 | Preboring P2 CD 31.6/38.495m
Fri (13/12) | 13 Dec 2024 | P9 |  | Crosshead formwork dismantling ongoing
Fri (13/12) | 13 Dec 2024 | ST135 |  | Guidewall excavation
Fri (13/12) | 13 Dec 2024 | P6 |  | Surveying works in progress for pile cap. Afternoon to start rebar shifting
Fri (13/12) | 13 Dec 2024 | zone 2 |  | Material shifting and preparation for drain hacking
Fri (13/12) | 13 Dec 2024 | N5 |  | Shoring erection for segment launching
Fri (13/12) | 13 Dec 2024 | P5 |  | Trial trench works in progress for ERSS installation
Fri (13/12) | 13 Dec 2024 | P12-13 |  | Excavation for telco duct construction
Fri (13/12) | 13 Dec 2024 | Zone 1 |  | RyobiG Preparing for drilling works for RX installation
Fri (13/12) | 13 Dec 2024 | P1-1 BP |  | Boring works in progress, current depth 14.5m
Fri (13/12) | 13 Dec 2024 | P8 |  | Backfilling to pile cap level 4th layer completed, NDT today at 4pm
Fri (13/12) | 13 Dec 2024 | P50 |  | Abandoned drain removal and pipe sleeves installation
Fri (13/12) | 13 Dec 2024 | P1-1 |  | Drilling continue. Depth 30m.plan to cast tomorrow
Fri (13/12) | 13 Dec 2024 | Zone 3 |  | Trial trench ongoing to find manhole caisson
Fri (13/12) | 13 Dec 2024 | BR1 |  | Continue top rebar installation, Formwork closing
Fri (13/12) | 13 Dec 2024 | BR2 |  | Excavation in progress
Fri (13/12) | 13 Dec 2024 | DR1 |  | Existing base slab hacking ongoing
Fri (13/12) | 13 Dec 2024 | Near DR1 access |  | Temporary sump pit excavation completed. Waiting to cast lean con
Fri (13/12) | 13 Dec 2024 | P12-13 |  | Slope protection casting for telco duct construction
Fri (13/12) | 13 Dec 2024 | N5-N6 |  | Shoring support for segment launching installation status
Fri (13/12) | 13 Dec 2024 | P44 |  | Continue waler joint welding
Fri (13/12) | 13 Dec 2024 | MH3-4 |  | Hacking of manhole for Tee pipe connection
Fri (13/12) | 13 Dec 2024 | ST128 |  | Trimming of waterstop end plate side for removal
Fri (13/12) | 13 Dec 2024 | ST151 |  | 2nd bite, reached 30m
Fri (13/12) | 13 Dec 2024 | BR1 |  | Continue top slab rebar and side formwork closing
Fri (13/12) | 13 Dec 2024 | BRP17 |  | 2nd point preboring, reached 33.3m
Fri (13/12) | 13 Dec 2024 | BP47 WLT |  | Preparing for preboring
Fri (13/12) | 13 Dec 2024 | ST19 |  | 3rd bite, reached 25m
Fri (13/12) | 13 Dec 2024 | N1-N2 |  | Soil compaction at teleco duct laid area
Fri (13/12) | 13 Dec 2024 | P11 |  | Hacking of column to correct level and soffit plywood installation
Fri (13/12) | 13 Dec 2024 | P9 |  | Formwork removal
Fri (13/12) | 13 Dec 2024 | P8 |  | Backfilling on going
Fri (13/12) | 13 Dec 2024 | P1-1 |  | Boring work already stopped. Housekeeping and tidy up the area
Fri (13/12) | 13 Dec 2024 | P6 |  | Rebar shifted. Tonight to start rebar work
Fri (13/12) | 13 Dec 2024 | BP3-19 |  | Casting in progress
Fri (13/12) | 13 Dec 2024 | P51 |  | GCE continue TT and pipe sleeves installation
Fri (13/12) | 13 Dec 2024 | MH2-9 |  | Wall formwork dismantling ongoing
Fri (13/12) | 13 Dec 2024 | Exit 3 |  | Preparing area for BRP10 trial trench
Fri (13/12) | 13 Dec 2024 | Exit 3 |  | Excavation for capping beam ongoing
Fri (13/12) | 13 Dec 2024 | BC4 |  | Maintenance ongoing
Fri (13/12) | 13 Dec 2024 | BRP17 |  | Preboring in progress, 31.6/38.5m
Sat (14/12) | 14 Dec 2024 | N1 |  | Teleco duct laying. Planned for 6m today
Sat (14/12) | 14 Dec 2024 | P11 |  | Hacking of column to the correct level
Sat (14/12) | 14 Dec 2024 | P8 |  | Continue soil backfilling
Sat (14/12) | 14 Dec 2024 | P6 |  | Rebar work in progresd
Sat (14/12) | 14 Dec 2024 | P5 |  | Preboring for ERSS work
Sat (14/12) | 14 Dec 2024 | P1-1 |  | Continue boring work
Sat (14/12) | 14 Dec 2024 | P11 |  | Preparation for end form installation
Sat (14/12) | 14 Dec 2024 | P50 |  | 1st point JGP boring work in progress
Sat (14/12) | 14 Dec 2024 | MH3-4 |  | Tee pipe installation
Sat (14/12) | 14 Dec 2024 | ST128 |  | Waterstop end plate removal
Sat (14/12) | 14 Dec 2024 | BR5 |  | Protruding rebar cutting and levelling
Sat (14/12) | 14 Dec 2024 | BC cutter 3 |  | Cutter wheel teeth changing
Sat (14/12) | 14 Dec 2024 | BRP46 |  | 1st bite, reached 10m
Sat (14/12) | 14 Dec 2024 | DR1 |  | Drain slab hacking in progress
Sat (14/12) | 14 Dec 2024 | BRP17 |  | Preboring in progress
Sat (14/12) | 14 Dec 2024 | P50 |  | 1st point grouting done. 2nd point in progress
Sat (14/12) | 14 Dec 2024 | P50 |  | Balance TT work in progress for pipe sleeves installation
Sat (14/12) | 14 Dec 2024 | P11 |  | Formwork assembling for installation
Sat (14/12) | 14 Dec 2024 | P9 |  | Formwork dismantling
Sat (14/12) | 14 Dec 2024 | P8 |  | Backfilling in progress
Sat (14/12) | 14 Dec 2024 | P6 |  | Current status of rebar work
Sat (14/12) | 14 Dec 2024 | P5 |  | Continue preboring work
Sat (14/12) | 14 Dec 2024 | BC cutter 1 |  | Now mud hose blocked. Clearing debris inside the hose
Sat (14/12) | 14 Dec 2024 | BRP17 |  | Continue preboring
Sat (14/12) | 14 Dec 2024 | BR1 |  | Top bar installation in progress
Sat (14/12) | 14 Dec 2024 | DR1 |  | Existing drain base slab hacking at CH20
Sat (14/12) | 14 Dec 2024 | MH2-9 |  | LSS backfilling around manhole
Sat (14/12) | 14 Dec 2024 | BR5 |  | LSS backfilling for base slab
Sat (14/12) | 14 Dec 2024 | BR1 |  | Transfer beam top bars installation
Sat (14/12) | 14 Dec 2024 | BRP46-BC4 |  | 1st bite trenching at 17m depth
Sat (14/12) | 14 Dec 2024 | BR5 |  | KTC working here tonight to expedite soil disposal
Sat (14/12) | 14 Dec 2024 | ST128 |  | Cleaning and desanding completed. Preparation for koden test
Sat (14/12) | 14 Dec 2024 | TKP87-8C |  | Boring reached 22.2m
Sat (14/12) | 14 Dec 2024 | Zone 4 P51 |  | Nights team for ERSS JGP TT. Target 4 points tonight with pipe sleeve installation
Sat (14/12) | 14 Dec 2024 | ST19 |  | 3rd bite excavation resume
Sat (14/12) | 14 Dec 2024 | BP6C | 12 | Boring done. Preparing for rebar cage lowering
Sun (15/12) | 15 Dec 2024 | BR1 |  | T1 laying in progress
Sun (15/12) | 15 Dec 2024 | BRP46 |  | Trenching continue at 17.9m depth
Sun (15/12) | 15 Dec 2024 | ST128 |  | Waterstop installed. Cage lifting and lowering in progress
Mon (16/12) | 16 Dec 2024 | P50 |  | Woh hup preparing for TT to confirm the sewer manhole size for water pipe diversion
Mon (16/12) | 16 Dec 2024 | P50 |  | JGP grouting 1st point done today. Prepare for 2nd point
Mon (16/12) | 16 Dec 2024 | P44 |  | Waler and strut end welding. Tomorrow to resume excavation
Mon (16/12) | 16 Dec 2024 | MH3-4 |  | LSS backfilling. Next week to complete the manhole work
Mon (16/12) | 16 Dec 2024 | BR1 |  | Formwork support installation and links installation. Est 30% links installed
Mon (16/12) | 16 Dec 2024 | BRP17 |  | 2nd bite pre-boring in progress, est depth 26.5m
Mon (16/12) | 16 Dec 2024 | BP4A-1 |  | Boring works in progress at 33m
Mon (16/12) | 16 Dec 2024 | BP3-19 |  | LSS casting in progress
Mon (16/12) | 16 Dec 2024 | P20 |  | Depcie here hacking abandoned singtel manhole
Mon (16/12) | 16 Dec 2024 | Stage 2 diversion slip road |  | Material shifting continue
Mon (16/12) | 16 Dec 2024 | N1-p11 |  | Telco duct backfilling
Mon (16/12) | 16 Dec 2024 | P11 |  | Rebar support installation on going. Tonight to start rebar installation
Mon (16/12) | 16 Dec 2024 | P6 |  | Links and formwork closing
Tue (17/12) | 17 Dec 2024 | P50 |  | JGP grouting in progress
Tue (17/12) | 17 Dec 2024 | DKP1C-2 |  | Boring CD 26.0/38.394m
Tue (17/12) | 17 Dec 2024 | BP4A-1 | 47 | Boring CD 35.0/38.86m
Tue (17/12) | 17 Dec 2024 | Zone 4 |  | Now almost all soil stockpile clear at Zone 4
Tue (17/12) | 17 Dec 2024 | BRP46 | Rig 4 | B1 CD 22.5/27.27m
Tue (17/12) | 17 Dec 2024 | P44 |  | Welding work completed. KTC mobilizing for excavation
Tue (17/12) | 17 Dec 2024 | MH3-4 |  | Manhole precast installation
Tue (17/12) | 17 Dec 2024 | BRP46 | Rig 4 | B2 CD 3.0/27.27m, currently replacing of suction elbow
Tue (17/12) | 17 Dec 2024 | ST119 | Rig 2 | B2 CD 12/38.9m
Tue (17/12) | 17 Dec 2024 | Zone 2 slip road |  | Drain hacking status for stage 2 diversion
Tue (17/12) | 17 Dec 2024 | N5-N6 |  | Shoring erection status
Tue (17/12) | 17 Dec 2024 | P11 |  | Crosshead rebar installation in progress
Tue (17/12) | 17 Dec 2024 | P9 |  | Wedge plate installation on going. Tomorrow plan to do PT
Tue (17/12) | 17 Dec 2024 | P8 |  | Waler diagonal bracing dismantled. Tomorrow to continue
Tue (17/12) | 17 Dec 2024 | P1-2 |  | Rebar cage installed. Casting platform installation
Wed (18/12) | 18 Dec 2024 | P11 crosshead |  | Rebar installation in progress
Wed (18/12) | 18 Dec 2024 | P50 |  | Continue JGP for base
Wed (18/12) | 18 Dec 2024 | MH3-4 |  | Plan to complete manhole work next week
Wed (18/12) | 18 Dec 2024 | P44 |  | Excavation to FEL in progress
Wed (18/12) | 18 Dec 2024 | P5 |  | Pre-boring status
Wed (18/12) | 18 Dec 2024 | MH2-9 |  | 3rd lift wall rebar works in progress. Tmr plan for casting
Wed (18/12) | 18 Dec 2024 | MH2-10 |  | Setting up jacking machine and other preparation works in progress
Wed (18/12) | 18 Dec 2024 | DW17 | BC1 | B2 in progress
Wed (18/12) | 18 Dec 2024 | Exit 3 | Loyang Lane | Hacking ongoing for capping beam works
Wed (18/12) | 18 Dec 2024 | BRP9 |  | Guidewall to cast today
Wed (18/12) | 18 Dec 2024 | ST19 |  | Casting completed, 175m3
Wed (18/12) | 18 Dec 2024 | BP4A-1, WLT pile | 47 | Rebar cage lowering in progress
Wed (18/12) | 18 Dec 2024 | BR1 |  | Briefing before roof slab casting works. Concrete otw
Wed (18/12) | 18 Dec 2024 | BR1 |  | First truck on site (G50) for column kicker
Wed (18/12) | 18 Dec 2024 | Zone 4 |  | Ley Choon started excavation for water pipe laying
Wed (18/12) | 18 Dec 2024 | P51 |  | Continue set up for testing
Wed (18/12) | 18 Dec 2024 | P51 |  | Continue TT. Two pipes sleeves installed today
Wed (18/12) | 18 Dec 2024 | BR1 |  | Casting of column kicker has started
Wed (18/12) | 18 Dec 2024 | P44 |  | Excavation to FEL
Wed (18/12) | 18 Dec 2024 | MH3-4 |  | Permanent manhole cast to Singtel duct laying. The next stage will be reducer to avoid Singtel duct
Wed (18/12) | 18 Dec 2024 | BR1 |  | Slump check for G40 concrete
Wed (18/12) | 18 Dec 2024 | BR1 |  | Progressive casting vol 365/1030m3
Wed (18/12) | 18 Dec 2024 | BR1 |  | Progressive casting vol 429/1030m3
Wed (18/12) | 18 Dec 2024 | BR1 |  | Progressive vol, 549/1030m3
Thu (19/12) | 19 Dec 2024 | P51-1 WLT |  | Inspection on going. Will start around 10:30AM
Thu (19/12) | 19 Dec 2024 | P50 |  | JGP grouting on going
Thu (19/12) | 19 Dec 2024 | Zone 2 slip road |  | Drain hacking status for stage 2 diversion
Thu (19/12) | 19 Dec 2024 | Zone 2 slip road |  | Premix hacking status for stage 2 diversion
Thu (19/12) | 19 Dec 2024 | P11 |  | Crosshead rebar installation and ducting preparations works in progress
Thu (19/12) | 19 Dec 2024 | P44 |  | Excavation to FEL. Lean concrete will be after lunch
Thu (19/12) | 19 Dec 2024 | MH3-4 |  | Preparing for sewer precast installation
Thu (19/12) | 19 Dec 2024 | Zone 4 |  | Ley Choon preparing for water pipe laying. Today plan for 24m length of Newater and 24m length of portable water
Thu (19/12) | 19 Dec 2024 | P10 |  | Concrete slab hacking for telco duct laying works
Thu (19/12) | 19 Dec 2024 | P9 Crosshead |  | Preparation for post tensioning works and formwork dismantling
Thu (19/12) | 19 Dec 2024 | P8 |  | Backfilling for ERSS extraction and removal in progress
Thu (19/12) | 19 Dec 2024 | P6 |  | Pilecap CJ roughening works
Thu (19/12) | 19 Dec 2024 | P5 |  | Preparation for ERSS trial trench works. Clearing of obstruction in progress
Thu (19/12) | 19 Dec 2024 | Zone 1 |  | HSL demobilization of materials
Thu (19/12) | 19 Dec 2024 | DKP1C-2 |  | Boring CD 36.0/38.934m
Thu (19/12) | 19 Dec 2024 | BP3 | 18 | Casing installed, preparing to start boring soon
Thu (19/12) | 19 Dec 2024 | MH2-9 |  | Preparing for backdrop pipe connection and 3rd lift wall in progress. Target to cast tmr
Thu (19/12) | 19 Dec 2024 | MH2-10 |  | Setting up jacking frame and other preparatory works
Thu (19/12) | 19 Dec 2024 | BRP46 | Rig 4 | B2 CD 12.0/27.27m
Thu (19/12) | 19 Dec 2024 | BR5 |  | Dwall panel ST76, ST77 rectification works ongoing
Thu (19/12) | 19 Dec 2024 | Zone 3 |  | LE demob their materials
Fri (20/12) | 20 Dec 2024 | DW17 | BC1 | Cleaning completed
Fri (20/12) | 20 Dec 2024 | P51 |  | This location of cable quite tight
Fri (20/12) | 20 Dec 2024 | Exit 3 |  | Abandoned sewer manhole top was already hacked by WH yesterday
Fri (20/12) | 20 Dec 2024 | BC4 |  | Maintenance works ongoing
Fri (20/12) | 20 Dec 2024 | BR1 |  | No activity
Fri (20/12) | 20 Dec 2024 | DKP1C-2 |  | Boring has completed, target to cast it today
Fri (20/12) | 20 Dec 2024 | BP3 | 18 | Boring CD 16.0/37.636m
Fri (20/12) | 20 Dec 2024 | P20 |  | HSL boring rig mobilized from zone 1
Fri (20/12) | 20 Dec 2024 | Zone 2 |  | Hacking of drain and premix in progress for stage 2 diversion
Fri (20/12) | 20 Dec 2024 | P44 |  | Prop concrete still curing. Afternoon will test the concrete cube
Fri (20/12) | 20 Dec 2024 | MH3-4 |  | Benching work in progress
Fri (20/12) | 20 Dec 2024 | BR2 |  | Excavation in progres
Fri (20/12) | 20 Dec 2024 | DR1 |  | Hacking ongoing
Fri (20/12) | 20 Dec 2024 | N5-N6 |  | Shoring erection current status
Fri (20/12) | 20 Dec 2024 | BRP46 |  | Preboring in progress
Fri (20/12) | 20 Dec 2024 | BR5 |  | ST76, ST77 cleaning and rectification ongoing
Fri (20/12) | 20 Dec 2024 | P39 |  | Erecting new access
Fri (20/12) | 20 Dec 2024 | P12 |  | Crosshead formwork dismantling in progress
Fri (20/12) | 20 Dec 2024 | P11 |  | Rebar, ducting and GI pipes supports installation ongoing
Fri (20/12) | 20 Dec 2024 | ST119 | BC3 | WS trimming
Fri (20/12) | 20 Dec 2024 | Exit 1 |  | Desander status
Fri (20/12) | 20 Dec 2024 | P10-P11 |  | Vsk excavation for telco duct in progress
Fri (20/12) | 20 Dec 2024 | P9 |  | Preparation for balance stage 1 tendon stressing works. 7/12 nos. completed. Today to complete
Fri (20/12) | 20 Dec 2024 | P8 |  | NDT done. KTC to continue with backfilling works
Fri (20/12) | 20 Dec 2024 | P6 |  | Rebar lowering for column stage 1 installation
Fri (20/12) | 20 Dec 2024 | P5 |  | LE preparing for ERSS installation and trial trench works
Fri (20/12) | 20 Dec 2024 | P3 |  | Mobilisation of excavator for P3 excavation works
Fri (20/12) | 20 Dec 2024 | P44 |  | Pile head hacking and erection of platform
Fri (20/12) | 20 Dec 2024 | DW17 |  | Cage A ( 3/3 in progress). Cage B ( 2/3 done). Tonight to cast
Fri (20/12) | 20 Dec 2024 | BR1 |  | Curing
Fri (20/12) | 20 Dec 2024 | DR1 |  | Continue hacking of existing drain. Left at the side and wall
Fri (20/12) | 20 Dec 2024 | P33-34 |  | Hirose continue utility support installation
Fri (20/12) | 20 Dec 2024 | BR5 |  | Barricade installation by Woh Hup and rectification of Dwall panel
Fri (20/12) | 20 Dec 2024 | BRP17 |  | Preparing to resume excavation
Fri (20/12) | 20 Dec 2024 | ST212 |  | Cutter teeth changing. Preparing to start excavation
Fri (20/12) | 20 Dec 2024 | DKP16-2 |  | Casting in progress
Fri (20/12) | 20 Dec 2024 | P12 |  | Formwork removal
Fri (20/12) | 20 Dec 2024 | P11 |  | Rebar work
Fri (20/12) | 20 Dec 2024 | Zone 1 |  | No activity already
Fri (20/12) | 20 Dec 2024 | P6 |  | Rebar work for column
Fri (20/12) | 20 Dec 2024 | MH2-9 |  | Currently no activity. Preparing for HDPE lining
Fri (20/12) | 20 Dec 2024 | MH2-10 |  | Preparing to hoist down TBM
Sat (21/12) | 21 Dec 2024 | P9 |  | Tendon stressing completed
Sat (21/12) | 21 Dec 2024 | P8 |  | Backfilling in progress
Sat (21/12) | 21 Dec 2024 | P6 |  | Column rebar works in progress
Sat (21/12) | 21 Dec 2024 | P5 |  | Hardcore clearing for ERSS trial trench
Sat (21/12) | 21 Dec 2024 | Zone 1 |  | HSL equipment demobilisation. To shift to P20 area
Sat (21/12) | 21 Dec 2024 | BP6A | 11 | Boring in progress
Sat (21/12) | 21 Dec 2024 | BP3 | 18 | Boring in progress
Sat (21/12) | 21 Dec 2024 | ST212 | BC1 | B1 in progress
Sat (21/12) | 21 Dec 2024 | BRP17 | BC4 | Excavation in progress, 25.6/38.4m
Sat (21/12) | 21 Dec 2024 | Exit 2 |  | Desander status
Sat (21/12) | 21 Dec 2024 | BR1 |  | Propping removal
Sat (21/12) | 21 Dec 2024 | BR2 |  | Excavation ongoing by KTC and preparing for bracing support installation by Hirose, GL24 onwards: Progressively install utility protection
Sat (21/12) | 21 Dec 2024 | DR1 |  | Continue existing drain wall hacking
Sat (21/12) | 21 Dec 2024 | DW17 |  | Casting in progress
Sat (21/12) | 21 Dec 2024 | MH2-9 |  | To cast 3rd lift wall today
Sat (21/12) | 21 Dec 2024 | MH2-10 |  | First pipe lowered for pipe jacking towards PUB manhole, 1/18nos
Sat (21/12) | 21 Dec 2024 | BRP46 |  | PB02 (B2) preboring in progress
Sat (21/12) | 21 Dec 2024 | BR5 |  | Endplate welding for KPs and hacking ongoing
Sat (21/12) | 21 Dec 2024 | BR5 |  | ST76, ST77 rectification casting completed last night
Sat (21/12) | 21 Dec 2024 | Exit 1 |  | Desander status
Sat (21/12) | 21 Dec 2024 | MH3-5 |  | Caisson ring hacking ongoing
Sat (21/12) | 21 Dec 2024 | Zone 4 |  | Water pipe laying in progress
Sat (21/12) | 21 Dec 2024 | P51 |  | JGP works ongoing, B50 & B53
Sat (21/12) | 21 Dec 2024 | ST119 |  | WS lowering in progress, BC2: Currently no activity, WH unloading rebars
Sat (21/12) | 21 Dec 2024 | ST147 |  | Rebar cage installation in progress, 3/8nos
Sat (21/12) | 21 Dec 2024 | P30 |  | Excavation for RC stump ongoing
Sat (21/12) | 21 Dec 2024 | DKP1C-2 |  | LSS backfill
Sat (21/12) | 21 Dec 2024 | TKP A8-AE |  | Boring in progress
Sat (21/12) | 21 Dec 2024 | Zone 2 |  | Hacking ongoing for stage 2 diversion
Sat (21/12) | 21 Dec 2024 | N1 |  | Backfilling
Sat (21/12) | 21 Dec 2024 | P12 |  | Crosshead formwork dismantling ongoing
Sat (21/12) | 21 Dec 2024 | P11 |  | Crosshead rebar works and tendon pipes installation in progress
Mon (23/12) | 23 Dec 2024 | P20 |  | HSL Boring rig setting up works ongoing
Mon (23/12) | 23 Dec 2024 | Zone 2 |  | KTC drain hacking works for stage 2 diversion ongoing
Mon (23/12) | 23 Dec 2024 | P12 |  | Access and platform making for tendon stressing works
Mon (23/12) | 23 Dec 2024 | P11 |  | Rebar and tendon duct installation. Today target to inspect for 1st 3 sections
Mon (23/12) | 23 Dec 2024 | P10-P11 |  | Excavation for telco duct in progress
Mon (23/12) | 23 Dec 2024 | P9 |  | Falsework dismantle works in progress
Mon (23/12) | 23 Dec 2024 | P8 |  | -1 Preparation for column rebar cage installation in the afternoon
Mon (23/12) | 23 Dec 2024 | P6 |  | Preparation for scaffold platform making for casting
Mon (23/12) | 23 Dec 2024 | P45-P46 |  | Ley Choon rigid pavement removal for water pipe laying. 88m completed for both water pipe and Newater pipe as of now
Mon (23/12) | 23 Dec 2024 | P51 |  | Left 3 TT and pipe sleeves to complete
Mon (23/12) | 23 Dec 2024 | P44 |  | Pile head hacking and platform erection for strut dismantling
Mon (23/12) | 23 Dec 2024 | P5 |  | Backfilling and platform making for preboring works
Mon (23/12) | 23 Dec 2024 | Zone 1 |  | HSL materials and mobile crane shifting to zone 2 in progress
Mon (23/12) | 23 Dec 2024 | P3 |  | KTC excavation in progress to S1 layer
Mon (23/12) | 23 Dec 2024 | P20 |  | HSL Boring rig setting up and materials shifting ongoing
Mon (23/12) | 23 Dec 2024 | MH2-9 |  | No activity. 3rd lift wall cast
Mon (23/12) | 23 Dec 2024 | MH2-10 |  | Pipe jacking, 6/18nos in progress
Mon (23/12) | 23 Dec 2024 | Zone 2 |  | KTC backfilling works for hacked drain area
Mon (23/12) | 23 Dec 2024 | Zone 2 |  | ATS preparation works for stage 2 diversion
Mon (23/12) | 23 Dec 2024 | BR1 |  | No activity
Mon (23/12) | 23 Dec 2024 | BR2 |  | Excavation in progress
Mon (23/12) | 23 Dec 2024 | DR1 |  | Continue hacking of existing drain wall
Mon (23/12) | 23 Dec 2024 | P12 |  | Preparation works for tendon stressing works
Mon (23/12) | 23 Dec 2024 | P10-P11 |  | Continue telco duct excavation works for slope lean concrete
Mon (23/12) | 23 Dec 2024 | P11 |  | Inspection for section 1-3 for tendon ducts completed. Shear links for section 1-3 and tendon ducts installation ongoing
Mon (23/12) | 23 Dec 2024 | P9 |  | Continue falsework dismantle works
Mon (23/12) | 23 Dec 2024 | P8-1 |  | Preparation for column rebar cage installation
Mon (23/12) | 23 Dec 2024 | BRP46 | BC4 | B2 temporarily stopped for cutter teeth change. CD 18/27.27m
Mon (23/12) | 23 Dec 2024 | BR5 |  | Dwall area no activity
Mon (23/12) | 23 Dec 2024 | BR5 |  | Slope protection casting ongoing
Mon (23/12) | 23 Dec 2024 | P45 to P46 |  | Rigid pavement hacking for Newater pipe laying, today plan for 4 pipes
Mon (23/12) | 23 Dec 2024 | P50 |  | Preparing to resume JGP. Drawing approved for wall grouting
Mon (23/12) | 23 Dec 2024 | P51 |  | One more row of JGP additional to be done due to congested services
Mon (23/12) | 23 Dec 2024 | ST152 | BC3 | B1 in progress
Mon (23/12) | 23 Dec 2024 | ST117 | BC2 | B2 in progress, 28/38.9m
Mon (23/12) | 23 Dec 2024 | P6 |  | Platform making for casting works
Mon (23/12) | 23 Dec 2024 | P44 |  | Waler dismantling
Mon (23/12) | 23 Dec 2024 | P44 |  | Pile head hacking
Mon (23/12) | 23 Dec 2024 | MH3-4 |  | Formwork closed for permanent manhole. Concrete on the way
Mon (23/12) | 23 Dec 2024 | ST152 |  | Excavation done. Now preparing for waterstop end plate side trimming
Mon (23/12) | 23 Dec 2024 | P36-37 |  | Platform preparation and KP covering plate welding
Mon (23/12) | 23 Dec 2024 | DR1 |  | Wall rebar cutting and removal
Mon (23/12) | 23 Dec 2024 | BRP17 |  | Test pile. KP lowering
Mon (23/12) | 23 Dec 2024 | ST212 |  | 1st bite, reached 36m
Mon (23/12) | 23 Dec 2024 | BP3 | 18 | Boring reached 28.5m
Mon (23/12) | 23 Dec 2024 | BP6A | 11 | Boring reached 34m
Mon (23/12) | 23 Dec 2024 | TKP A8 | AE | Boring reached 30m
Mon (23/12) | 23 Dec 2024 | MH2-10 to existing manhole |  | Pipe No-8 jacking in progress. Working until 7PM
Mon (23/12) | 23 Dec 2024 | P5 |  | No activity already. Drizzling
Mon (23/12) | 23 Dec 2024 | P8 |  | Rebar cage installation in progress
Mon (23/12) | 23 Dec 2024 | P9 |  | Falsework dismantling
Mon (23/12) | 23 Dec 2024 | P11 |  | Rebar work in progress
Mon (23/12) | 23 Dec 2024 | P6 |  | Scaffold access erection
Tue (24/12) | 24 Dec 2024 | MH3-4 |  | Formwork removal. Left benching work to complete Sewer 3 network
Tue (24/12) | 24 Dec 2024 | P44 |  | Waler and strut removal
Tue (24/12) | 24 Dec 2024 | MH3-5 |  | Caisson hacking
Tue (24/12) | 24 Dec 2024 | P51 |  | This location services very tight also. Encounter drain at 2m depth
Tue (24/12) | 24 Dec 2024 | P51 |  | Coring sample taken to confirm drain slab
Tue (24/12) | 24 Dec 2024 | CR106 GATE 2 LANE 1 IN/IP |  | 10.126.16.11/SN:6728324060000444
Tue (24/12) | 24 Dec 2024 | CR106 GATE 2 LANE 1 OUT/IP |  | 10.126.16.12/SN:6728324060000373
Tue (24/12) | 24 Dec 2024 | Zone 4 |  | Discussion with Ley choon & woh hup for water pipe laying on live road
Tue (24/12) | 24 Dec 2024 | MH2-9 |  | Scaffold erection for permanent manhole work
Tue (24/12) | 24 Dec 2024 | MH2-10 |  | 9th pipe jacking done. Preparing to lower 10th pipe
Tue (24/12) | 24 Dec 2024 | P3 |  | Access scaffold erection and excavation
Tue (24/12) | 24 Dec 2024 | P11 |  | Tendom duct installation and rebar work for cross head
Tue (24/12) | 24 Dec 2024 | P12 |  | Tendom cable pulling
Tue (24/12) | 24 Dec 2024 | P8 |  | Water drain pipe installation
Tue (24/12) | 24 Dec 2024 | P6 |  | Column casting
Tue (24/12) | 24 Dec 2024 | P9 |  | Falsework dismantling
Tue (24/12) | 24 Dec 2024 | ST212 |  | Need to repair mud hose
Tue (24/12) | 24 Dec 2024 | P50 |  | Continue grouting for wall grout block
Tue (24/12) | 24 Dec 2024 | BRP7 |  | Removal of abandoned cables and TT work
Tue (24/12) | 24 Dec 2024 | DW27& DW27 |  | Excavation for guidewall work
Tue (24/12) | 24 Dec 2024 | Exit 2 |  | Teeth changing for BC cutter 1
Tue (24/12) | 24 Dec 2024 | P32-33 |  | KTC preparing to excavate to final level. Left 300mm to complete
Tue (24/12) | 24 Dec 2024 | ST157 |  | Machine maintenance and mud hose connection
Tue (24/12) | 24 Dec 2024 | ST152 |  | Final koden check
Tue (24/12) | 24 Dec 2024 | DR1 |  | Drain wall hacking and removal
Wed (25/12) | 25 Dec 2024 | P12 |  | Preparing for tendon stressing works
Wed (25/12) | 25 Dec 2024 | P11 |  | Tendon duct pipe installation. Plan for inspection today
Wed (25/12) | 25 Dec 2024 | P9 |  | Crosshead falsework dismantling ongoing
Wed (25/12) | 25 Dec 2024 | P8 |  | Preparing area for column formwork installation
Wed (25/12) | 25 Dec 2024 | P6 and zone 1 |  | No activities
Wed (25/12) | 25 Dec 2024 | ST212 | BC1 | B2 in progress, 31.4/42.4m
Wed (25/12) | 25 Dec 2024 | BR1 |  | No activity
Wed (25/12) | 25 Dec 2024 | BR2 |  | Excavation up to GL23 almost completed & hacking of existing bored pile (4/5nos) in progress
Wed (25/12) | 25 Dec 2024 | DR1 |  | Debris removal. Target to lean con this week
Wed (25/12) | 25 Dec 2024 | BRP46 | BC4 | B3 in progress, 20.6/27.27m
Wed (25/12) | 25 Dec 2024 | BR5 |  | Dwall area no activity
Wed (25/12) | 25 Dec 2024 | BR5 |  | LSS backfilling in progress
Wed (25/12) | 25 Dec 2024 | ST157 | BC3 | B1 in progress
Wed (25/12) | 25 Dec 2024 | P44 |  | Pile head hacking in progress, WH clearing debris and installing another access at this area
Wed (25/12) | 25 Dec 2024 | MH3-4 |  | No activity
Wed (25/12) | 25 Dec 2024 | ST117 |  | Rebar cage installation in progres
Wed (25/12) | 25 Dec 2024 | BC2 |  | No activity
Wed (25/12) | 25 Dec 2024 | DW27 |  | Preparing for guidewall construction, DW26: Guidewall excavation
Wed (25/12) | 25 Dec 2024 | Exit 3 | loyang lane | Capping beam excavation
Wed (25/12) | 25 Dec 2024 | BRP7 |  | Guidewall pending casting
Wed (25/12) | 25 Dec 2024 | Exit 3 |  | HSL no activity
Wed (25/12) | 25 Dec 2024 | MH2-10 |  | Pipe 13 lowered. Pipe jacking done, 12/18nos
Wed (25/12) | 25 Dec 2024 | MH2-9 |  | No activity
Wed (25/12) | 25 Dec 2024 | P12 |  | Tendon cable pulling in progress. Works till 5pm
Wed (25/12) | 25 Dec 2024 | P11 |  | Inspection ongoing
Wed (25/12) | 25 Dec 2024 | P9 |  | Continue falsework dismantling
Wed (25/12) | 25 Dec 2024 | BRP7 |  | Guidewall cast
Wed (25/12) | 25 Dec 2024 | DW26 |  | Trial trench found cable pipes. Tmr to confirm with utility team, DW27: Preparing for guidewall rebar works
Wed (25/12) | 25 Dec 2024 | ST212 | BC1 | B2 in progress, 32.5/42.4m
Wed (25/12) | 25 Dec 2024 | BR2 |  | Continue excavation. Works till 5pm
Wed (25/12) | 25 Dec 2024 | P30 |  | Barricade installation at RC stump locations
Wed (25/12) | 25 Dec 2024 | BR5 |  | No activity currently
Wed (25/12) | 25 Dec 2024 | P44 |  | No activity currently
Wed (25/12) | 25 Dec 2024 | ST117 |  | Rebar cage lapping in progress, 5/8nos
Wed (25/12) | 25 Dec 2024 | ST126 | BC2 | B1 in progress, 20/34m
Wed (25/12) | 25 Dec 2024 | ST157 | BC3 | B1 completed. Cutter body washing ongoing
Wed (25/12) | 25 Dec 2024 | BRP46 | BC4 | B3 CD 23/27.27m. Cutter teeth changing now ongoing
Wed (25/12) | 25 Dec 2024 | DW27 |  | Guidewall rebar works in progress
Wed (25/12) | 25 Dec 2024 | P20 |  | HSL no activity
Wed (25/12) | 25 Dec 2024 | Zone 2 |  | ATS continue excavation for stage 2 diversion
Thu (26/12) | 26 Dec 2024 | Exit 3 |  | Stockpile current status
Thu (26/12) | 26 Dec 2024 | CR106 |  | *Suspected M1 utility damage*, Date: 26/12/2024, Time: 8.00am, Location: from Zone 2 to Zone 3: Pipeline between MH216093 (after P20) towards MH216094 (after P22), Subcontractor : Seongha Geological Engineering Pte Ltd, On 26/12/2024 at 8:00 am, LTA PJT and WH were informed by M1 that they had received feedback from a customer (BLK 275 Pasir Ris Street 21) reporting a service outage. M1's enforcement team, arrived at CR106 during the early hours of 26/12/24 but was unable to contact the correct personnel in charge to enter the site, Upon contacting WH and LTA PJT in the morning, M1 Term Contractor, Lucky Joint arrived at site at 9:00 am to begin cable tracing based on the feedback received. They discovered that the pipeline between manhole MH216093 (after P20) and MH216094 (after P22) was blocked. Cables between the manholes were observed to be under tension, A pipeline damage between the two manholes is suspected. Works ongoing along the pipeline are fissure grouting’s slurry pit works. WH is currently assisting in clearing the slurry pit area to expose the pipe alignment, Detailed investigation is currently ongoing
Thu (26/12) | 26 Dec 2024 | P20-1 |  | BP boring works in progress. Current depth 8m
Thu (26/12) | 26 Dec 2024 | P18 |  | KTC continue drain hacking works for stage 2 diversion
Thu (26/12) | 26 Dec 2024 | Zone 2 |  | ATS premix removal & KTC excavation works for stage 2 diversion
Thu (26/12) | 26 Dec 2024 | Zone 2 |  | Stockpile current status
Thu (26/12) | 26 Dec 2024 | P12 |  | Tendon strands installation in progress. (15/16 nos. completed)
Thu (26/12) | 26 Dec 2024 | P11 |  | Shear links installation for section 3-5 and Tendon ducts installation for the balance section in progress
Thu (26/12) | 26 Dec 2024 | P11-P12 |  | VSK backfilling & levelling works in progress
Thu (26/12) | 26 Dec 2024 | P9 |  | Falsework dismantle & removal in progress
Thu (26/12) | 26 Dec 2024 | P8-1 |  | Column formwork closing & tie rod installation
Thu (26/12) | 26 Dec 2024 | P6 |  | Column stump curing ongoing
Thu (26/12) | 26 Dec 2024 | P3 |  | Preparation for slope lean concrete works
Thu (26/12) | 26 Dec 2024 | P5 |  | Preboring for ERSS installation ongoing
Thu (26/12) | 26 Dec 2024 | P4 |  | ERSS extraction works
Thu (26/12) | 26 Dec 2024 | BP3 | 18 | Boring in progress, 32.5/37.6m
Thu (26/12) | 26 Dec 2024 | BP2A-1 | 26 | Boring in progress
Thu (26/12) | 26 Dec 2024 | BC1 |  | Cutter wheel and machine rectification ongoing
Thu (26/12) | 26 Dec 2024 | BR2 |  | Continue hacking and soil trimming works
Thu (26/12) | 26 Dec 2024 | DW27, DW26 | half | Guidewall waiting to cast
Thu (26/12) | 26 Dec 2024 | MH2-9 |  | 2/5nos precast chamber installed
Thu (26/12) | 26 Dec 2024 | UKP1 |  | Boring completed, 17m. Casting in progress
Thu (26/12) | 26 Dec 2024 | BR1 |  | Formwork striking ongoing
Thu (26/12) | 26 Dec 2024 | BR5 |  | Soil levelling and hacking ongoing
Thu (26/12) | 26 Dec 2024 | BRP46 |  | Cutter teeth replacement and change of operator
Thu (26/12) | 26 Dec 2024 | DR1 |  | No activity. Target to cast lean con by Saturday
Fri (27/12) | 27 Dec 2024 | P12 |  | Tendom wire pulling
Fri (27/12) | 27 Dec 2024 | P11 |  | Formwork closing and support tightening. Target this month casting
Fri (27/12) | 27 Dec 2024 | P9 |  | Falsework dismantling
Fri (27/12) | 27 Dec 2024 | P8 |  | Column fromwork closing. Tomorrow to cast
Fri (27/12) | 27 Dec 2024 | MH2-9 |  | No activity. 4th lift cast and 2/5nos precast rings installed. Tmr plan for LSS backfill
Fri (27/12) | 27 Dec 2024 | MH2-10 |  | Pipe 17 lowered. Pipe jacking completed, 16/18nos
Fri (27/12) | 27 Dec 2024 | P12 |  | Tendom wire pulling
Fri (27/12) | 27 Dec 2024 | P11 |  | Shear link installation and cast in anchor installation
Fri (27/12) | 27 Dec 2024 | P8 |  | Column to cast tomorrow. Support installation
Fri (27/12) | 27 Dec 2024 | P9 |  | Removal of falsework
Fri (27/12) | 27 Dec 2024 | DW27-DW26 | half | Guidewall cast, Now ongoing guidewall construction for another half of DW26
Fri (27/12) | 27 Dec 2024 | P30 RC stump location |  | Informed WH to indicate the utility signage at this location
Fri (27/12) | 27 Dec 2024 | BR1 |  | Formwork dismantling
Fri (27/12) | 27 Dec 2024 | BR2 |  | Trimming works and hacking ongoing to expose couplers
Fri (27/12) | 27 Dec 2024 | P21-2 |  | Preboring in progress
Fri (27/12) | 27 Dec 2024 | DR1 |  | Hardcore clearing. Drain wall hacking almost completed
Fri (27/12) | 27 Dec 2024 | BR5 |  | Exposing KPs ongoing. Part of the dwall couplers have been exposed
Fri (27/12) | 27 Dec 2024 | BRP46 | BC4 | Cutter teeth changing ongoing. B2 CD 21.2/27.27m
Fri (27/12) | 27 Dec 2024 | BP3 | 18 | Boring CD 33.5/37.63m
Fri (27/12) | 27 Dec 2024 | BP2A-1 | 26 | Boring CD 27.5/40.783m
Fri (27/12) | 27 Dec 2024 | ST157 | BC3 | B2 cleaning in progress
Fri (27/12) | 27 Dec 2024 | ST212 | Rig 1 | B2 excavation CD 42.6/42.4m, cutter teeth replacement in progress
Fri (27/12) | 27 Dec 2024 | BRP65 |  | Guidewall excavation
Fri (27/12) | 27 Dec 2024 | ST126 | Rig 2 | B2 excavation CD 33.5/34.0m
Fri (27/12) | 27 Dec 2024 | BR2 |  | Lean con casting
Fri (27/12) | 27 Dec 2024 | P44 |  | Rebar works in progress
Fri (27/12) | 27 Dec 2024 | P49 |  | Road premix removal and TT on going
Fri (27/12) | 27 Dec 2024 | MH3-5 |  | Caisson hacking and removal
Fri (27/12) | 27 Dec 2024 | MH3-4 |  | Access erection for lining work
Fri (27/12) | 27 Dec 2024 | P44 |  | Rebar work in progress
Fri (27/12) | 27 Dec 2024 | P21-2 |  | Boring reached 8m. P20-1: casting done
Fri (27/12) | 27 Dec 2024 | UKP2 |  | Depth checking for casting
Fri (27/12) | 27 Dec 2024 | BP2-1 |  | Boring reached 26m
Fri (27/12) | 27 Dec 2024 | BP3 |  | Boring reached 32m
Fri (27/12) | 27 Dec 2024 | TDP27 |  | TT on going. Found starhub. Steel plate protection to be installed
Fri (27/12) | 27 Dec 2024 | Exit 2 |  | BC cutter gear box changing
Fri (27/12) | 27 Dec 2024 | BRP46 |  | 3rd bite, 24.60m
Fri (27/12) | 27 Dec 2024 | M1 THREE NEW CABLES RECTIFICATION STATUS AS BELOW |  | MH-201016, 1 CABLE CLOSER JOINT COMPLETED, MH-206094, 3 CABLE CLOSER JOINT COMPLETED, MH-206092, 2 CABLE CLOSER JOINT COMPLETED, TOTAL 6 CLOSER JOINT COMPLETED BY 1.30am (27-12-2024)
Fri (27/12) | 27 Dec 2024 | BR5 |  | Levelling for lean concrete
Sat (28/12) | 28 Dec 2024 | BP2A-1 | 26 | Boring CD 30/40.783m
Sat (28/12) | 28 Dec 2024 | BP3 | 18 | Boring CD 34.5/37.63m
Sat (28/12) | 28 Dec 2024 | Bet. P23-P22 |  | Post lugeon test in progress @ CCW
Sat (28/12) | 28 Dec 2024 | Bet. P23-P22 |  | 2 rigs preparation for fissure grouting drilling works
Sat (28/12) | 28 Dec 2024 | P21-2 |  | BP boring works in progress. Current depth 13m
Sat (28/12) | 28 Dec 2024 | Bet P21-P23 |  | Recharge wells works in progress
Sat (28/12) | 28 Dec 2024 | Bet. P18-P20 |  | KTC disposal works in progress
Sat (28/12) | 28 Dec 2024 | Bet. P18-P20 |  | ATS preparation for RCA backfilling for stage 2 diversion. Surveying works ongoing
Sat (28/12) | 28 Dec 2024 | P44 |  | Current status of rebar work
Sat (28/12) | 28 Dec 2024 | ST126 |  | Koden testing
Sat (28/12) | 28 Dec 2024 | Zone 2 |  | Stockpile current status
Sat (28/12) | 28 Dec 2024 | P12 |  | Crosshead tendon wires pulling works in progress
Sat (28/12) | 28 Dec 2024 | ST157 |  | Tremie pipe lowering for casting
Sat (28/12) | 28 Dec 2024 | BC cutter 4 |  | Teeth changing
Sat (28/12) | 28 Dec 2024 | BRP46 |  | Preboring
Sat (28/12) | 28 Dec 2024 | P11 crosshead |  | Rebar installation & cleaning works in progress for section 5-7 before formwork closing
Sat (28/12) | 28 Dec 2024 | Bet P10-P11 |  | Preparation for telco duct casting 6m today
Sat (28/12) | 28 Dec 2024 | P9 |  | Falsework fully dismantled
Sat (28/12) | 28 Dec 2024 | P8-1 |  | Preparation for column casting. Site briefing conducted
Sat (28/12) | 28 Dec 2024 | P6 |  | No activity
Sat (28/12) | 28 Dec 2024 | P5 |  | Trial trench for ERSS installation in progress
Sat (28/12) | 28 Dec 2024 | P3 |  | Welding works for waler beams and struts in progress
Sat (28/12) | 28 Dec 2024 | Zone 4 |  | P50-7 JGP grouting completed. Now preparing for P50-9
Sat (28/12) | 28 Dec 2024 | P49-11 & P49-42 |  | JGP Trial trench works in progress
Sat (28/12) | 28 Dec 2024 | MH3-5 |  | No activity
Sat (28/12) | 28 Dec 2024 | Exit 1 |  | Current stockpile status
Sat (28/12) | 28 Dec 2024 | MH3-4 |  | HDPE lining works
Sat (28/12) | 28 Dec 2024 | P44 |  | Rebar installation for pile cap
Sat (28/12) | 28 Dec 2024 | ST126 |  | Trimming for Waterstop ongoing, current depth 29m
Sat (28/12) | 28 Dec 2024 | ST-153 |  | Excavation in progress, current depth 21m/31.30m
Sat (28/12) | 28 Dec 2024 | Zone 3 BR5 |  | Roof slab bottom level trimming & formwork closing works
Sat (28/12) | 28 Dec 2024 | STN-157 |  | Rebar cages lapping and lowering in progress
Sat (28/12) | 28 Dec 2024 | BRP-46 |  | Preboring in progress
Sat (28/12) | 28 Dec 2024 | BR2 |  | Continue excavation works
Sat (28/12) | 28 Dec 2024 | ST-212 |  | 3rd bite excavation ongoing
Sat (28/12) | 28 Dec 2024 | Exit 2 |  | Stockpile current status
Sat (28/12) | 28 Dec 2024 | MH2-9 |  | LSS backfilling in progress
Sat (28/12) | 28 Dec 2024 | TDP-27 |  | Boring in progress. Current depth 6m
Sat (28/12) | 28 Dec 2024 | Exit 3 |  | Stockpile current status
Sat (28/12) | 28 Dec 2024 | BP2A-1 | 26 | Boring in progress. Current depth 33m/40.783m
Sat (28/12) | 28 Dec 2024 | BP3 | 18 | Boring in progress. Current depth 36m/37.63m
Sat (28/12) | 28 Dec 2024 | ST-212 |  | Preparation for Trimming works for Waterstop
Sat (28/12) | 28 Dec 2024 | BRP-46 |  | 2nd bite excavation works in progress. Current depth 26m
Sat (28/12) | 28 Dec 2024 | DR-1 |  | Drain hacking works in progress
Sat (28/12) | 28 Dec 2024 | BR2 |  | Excavation works ongoing
Sat (28/12) | 28 Dec 2024 | Zone 3 BR5 |  | Preparation for lean concrete works
Sat (28/12) | 28 Dec 2024 | STN-157 |  | Rebar cages lowering completed
Sat (28/12) | 28 Dec 2024 | ST-153 |  | Excavation in progress, current depth 26.5m/31.30m
Sat (28/12) | 28 Dec 2024 | BRP-65 |  | Preparation for guidewall casting
Sat (28/12) | 28 Dec 2024 | ST126 |  | Trimming completed. Cleaning in progress for 1st bite
Sat (28/12) | 28 Dec 2024 | MH3-4 |  | HDPE lining works
Sat (28/12) | 28 Dec 2024 | P44 |  | Pile cap rebar installation ongoing
Sat (28/12) | 28 Dec 2024 | Zone 4 |  | P50-9 JGP grouting completed. Now preparing for P50-26
Sat (28/12) | 28 Dec 2024 | P3 |  | Continue welding works for struts
Sat (28/12) | 28 Dec 2024 | P5 |  | ERSS installation in progress
Sat (28/12) | 28 Dec 2024 | P6 |  | Concrete plug cast. Formwork removal for column stump in progress
Sat (28/12) | 28 Dec 2024 | P8-1 |  | Column casting completed
Sat (28/12) | 28 Dec 2024 | P11 |  | Crosshead Formwork closing for section 5-7
Sat (28/12) | 28 Dec 2024 | Bet P10-P11 |  | Telco duct 6m casting completed
Sat (28/12) | 28 Dec 2024 | P12 |  | Continue Crosshead tendon wires pulling works
Sat (28/12) | 28 Dec 2024 | P14 |  | Falsework adjustment in progress
Sat (28/12) | 28 Dec 2024 | Bet. P18-P20 |  | ATS RCA backfilling for stage 2 diversion in progress
Sat (28/12) | 28 Dec 2024 | P21-2 |  | BP boring works in progress. Current depth 33.3m
Sat (28/12) | 28 Dec 2024 | TDP27 |  | Casting almost completed
Sat (28/12) | 28 Dec 2024 | UKP3 |  | Setting out
Sat (28/12) | 28 Dec 2024 | BP3-18 |  | Working until 9:30PM
Sat (28/12) | 28 Dec 2024 | BP1-2 |  | Boring reached, 33m
Sat (28/12) | 28 Dec 2024 | P11 |  | Shear link installation and formwork bolts installation
Sat (28/12) | 28 Dec 2024 | Zone 4 |  | Ley Choon lane closure done for TT for water pipe laying. TMA provided
Sat (28/12) | 28 Dec 2024 | P49 |  | TT in progress. Target 5 nos of pipe sleeves
Sun (29/12) | 29 Dec 2024 | P14 |  | Falsework erection in progress
Sun (29/12) | 29 Dec 2024 | P12 |  | Tendon cable pulling in progress
Sun (29/12) | 29 Dec 2024 | P8 |  | Access platform dismantling
Sun (29/12) | 29 Dec 2024 | P5 |  | Excavation ongoing for balance ERSS installation
Sun (29/12) | 29 Dec 2024 | P3 |  | Strut joint welding ongoing. Also preparing for packing concrete for waler
Sun (29/12) | 29 Dec 2024 | P3 |  | RG strain gauge data logger monitoring
Sun (29/12) | 29 Dec 2024 | P9 |  | Formwork installation
Sun (29/12) | 29 Dec 2024 | P20-CCW |  | HSL no activity
Sun (29/12) | 29 Dec 2024 | UKP6 |  | Trial trench
Sun (29/12) | 29 Dec 2024 | DW27 |  | Boring machine set up. Preparing noise balloon before continuing works
Sun (29/12) | 29 Dec 2024 | P30 |  | Excavation ongoing for RC stump
Sun (29/12) | 29 Dec 2024 | BRP46 | BC4 | B2 on progress, 25.5/27.27m
Sun (29/12) | 29 Dec 2024 | BR5 |  | Excavation & slope trimming ongoing
Sun (29/12) | 29 Dec 2024 | BRP61 |  | Trial trench in progress. Found ST cable (abandoned)
Sun (29/12) | 29 Dec 2024 | Exit 1 |  | Desander stockpile status
Sun (29/12) | 29 Dec 2024 | P44 |  | Rebar works in progress
Sun (29/12) | 29 Dec 2024 | BC2 |  | Cutter cleaning and teeth replacement
Sun (29/12) | 29 Dec 2024 | P49 |  | CGE trial trench in progress
Sun (29/12) | 29 Dec 2024 | P50-25 |  | JGP in progress
Sun (29/12) | 29 Dec 2024 | MH2-9 |  | 4/5nos precast rings installed
Sun (29/12) | 29 Dec 2024 | UKP6 |  | Found ST cable (abandoned). Boring able to proceed
Sun (29/12) | 29 Dec 2024 | ST212 | BC1 | Trimming ongoing
Sun (29/12) | 29 Dec 2024 | Exit 2 |  | Desander stockpile status
Sun (29/12) | 29 Dec 2024 | BR1 |  | No activity
Sun (29/12) | 29 Dec 2024 | BR2 | GL21-23 | Excavation completed
Sun (29/12) | 29 Dec 2024 | DR1 |  | No activity
Sun (29/12) | 29 Dec 2024 | Exit 3 |  | Desander stockpile status
Sun (29/12) | 29 Dec 2024 | P3 |  | Continue waler beam welding works
Sun (29/12) | 29 Dec 2024 | ST157 |  | Casting in progress
Sun (29/12) | 29 Dec 2024 | P11 |  | Formwork support tightening and securing the hard barricade
Sun (29/12) | 29 Dec 2024 | ST212 |  | C lock welding for trimming
Sun (29/12) | 29 Dec 2024 | DW27 |  | Preboring for sewer manhole removal ongoing
Sun (29/12) | 29 Dec 2024 | BRP46 |  | Resume excavation
Sun (29/12) | 29 Dec 2024 | ST116 |  | Started 1st bite
Sun (29/12) | 29 Dec 2024 | P44 |  | Bar chair installation in progress
Sun (29/12) | 29 Dec 2024 | Zone 2 |  | KTC debris disposal ongoing
Mon (30/12) | 30 Dec 2024 | P14 |  | Falsework erection for cross head
Mon (30/12) | 30 Dec 2024 | P12 |  | Prepare for prestressing
Mon (30/12) | 30 Dec 2024 | P11 |  | Final inspection will be 4PM. To cast today
Mon (30/12) | 30 Dec 2024 | P5 |  | Preparing for ERSS installation
Mon (30/12) | 30 Dec 2024 | P20-2 |  | Setting out for boring work
Mon (30/12) | 30 Dec 2024 | P21-2 |  | Koden checked. Preparing for rebar cage lowering
Mon (30/12) | 30 Dec 2024 | P49 |  | TT for pipe sleeves installation
Mon (30/12) | 30 Dec 2024 | P50 |  | Continue JGP grouting
Mon (30/12) | 30 Dec 2024 | MH2-9 |  | 4/5nos precast chambers installed. Outer wall casting done
Mon (30/12) | 30 Dec 2024 | DW27 |  | Preboring in progress
Mon (30/12) | 30 Dec 2024 | ST212 |  | WS installation in progres
Mon (30/12) | 30 Dec 2024 | Exit 2 |  | Desander stockpile status
Mon (30/12) | 30 Dec 2024 | BR2 |  | Hacking ongoing for existing bored pile/barette pile & exposing couplers
Mon (30/12) | 30 Dec 2024 | BR1 |  | WH erecting new access
Mon (30/12) | 30 Dec 2024 | P14 |  | Falsework erection
Mon (30/12) | 30 Dec 2024 | P11 |  | Final inspection on going by RE
Mon (30/12) | 30 Dec 2024 | P30 |  | Hacking of abandoned drain
Mon (30/12) | 30 Dec 2024 | DR1 |  | Balance about 1m existing drain wall hacking to complete
Mon (30/12) | 30 Dec 2024 | DR1 |  | ERSS removal at completed drain section
Mon (30/12) | 30 Dec 2024 | P12 |  | Set up for prestressing
Mon (30/12) | 30 Dec 2024 | P5 |  | Preboring for soldier pile work
Mon (30/12) | 30 Dec 2024 | BR5 |  | Soil trimming ongoing in preparation for lean con casting & hacking of bulging concrete ongoing at dwall area
Mon (30/12) | 30 Dec 2024 | BRP46 | BC4 | Cutter teeth changing ongoing. B2 CD 26.7/27.27m
Mon (30/12) | 30 Dec 2024 | ST153 |  | WS installation in progres
Mon (30/12) | 30 Dec 2024 | BRP58 |  | Premix hacking ongoing for guideway trial trench
Mon (30/12) | 30 Dec 2024 | BRP61 |  | Guidewall pending casting
Mon (30/12) | 30 Dec 2024 | ST116 | BC2 | B1 in progress
Mon (30/12) | 30 Dec 2024 | Exit 1 |  | Desander stockpile status
Mon (30/12) | 30 Dec 2024 | ST126 |  | Hanging bar lapping in progress
Mon (30/12) | 30 Dec 2024 | Exit 3 |  | Desander stockpile status
Mon (30/12) | 30 Dec 2024 | P20-2 |  | Boring ongoing
Mon (30/12) | 30 Dec 2024 | P21-2 |  | Casting in progress
Mon (30/12) | 30 Dec 2024 | BP3, 2.5m dia | 16 | Casing installation ongoing
Mon (30/12) | 30 Dec 2024 | UKP3 |  | Boring ongoing
Mon (30/12) | 30 Dec 2024 | BP2A-1 | 26 | Boring in progress
Mon (30/12) | 30 Dec 2024 | BRP9 |  | B1 in progress
Mon (30/12) | 30 Dec 2024 | ST212 |  | Rebar cage lowering started, 1/8nos
Mon (30/12) | 30 Dec 2024 | BRP46 |  | B2 reached 26.8/27.27m. Target to install kingpost tmr and cast
Mon (30/12) | 30 Dec 2024 | DW27 |  | Preboring stopped for the day
Tue (31/12) | 31 Dec 2024 | P20-2 |  | Prepare the platform for casting
Tue (31/12) | 31 Dec 2024 | P14 |  | Continue installation of runner
Tue (31/12) | 31 Dec 2024 | P12 |  | Set up for prestressing
Tue (31/12) | 31 Dec 2024 | P44 |  | Placing of polyform for the casting work
Tue (31/12) | 31 Dec 2024 | Zone 4 |  | P50 JGP grouting and P49 TT for pipe sleeves installation
Tue (31/12) | 31 Dec 2024 | UKP9 |  | Preboring for casing installation
Tue (31/12) | 31 Dec 2024 | BR2 |  | Exposing coupler for next span of roof slab work
Tue (31/12) | 31 Dec 2024 | DR1 |  | Drain hacking almost completed
Tue (31/12) | 31 Dec 2024 | BRP46 |  | 3rd bite excavation in progress
Tue (31/12) | 31 Dec 2024 | BR5 |  | Levelling for lean concrete. Today lean concrete
Tue (31/12) | 31 Dec 2024 | MH2-10 |  | No activity
Tue (31/12) | 31 Dec 2024 | MH2-9 |  | LSS backfilling done
Tue (31/12) | 31 Dec 2024 | P14 |  | Secondary beam installation and formwork assembling work
Tue (31/12) | 31 Dec 2024 | P9-P10 |  | Excavation for duct laying
Tue (31/12) | 31 Dec 2024 | BRP9 |  | Excavation done. Prepare for koden check
Tue (31/12) | 31 Dec 2024 | DW27 |  | Sewer manhole demolition using BG
Tue (31/12) | 31 Dec 2024 | BP2-1 | 26 | Boring reached 40.4m
Tue (31/12) | 31 Dec 2024 | BP3-16 |  | Casing installation
Thu (02/01) | 02 Jan 2025 | P20-P19 |  | ATS continue RCA backfilling works for stage 2 diversion
Thu (02/01) | 02 Jan 2025 | P17-P18 |  | KTC excavation and drain removal works for stage 2 preparation works
Thu (02/01) | 02 Jan 2025 | Zone 2 |  | Current stockpile status
Thu (02/01) | 02 Jan 2025 | P14 |  | Netting installation in progress
Thu (02/01) | 02 Jan 2025 | P20-3 |  | Preparation to start BP boring works
Thu (02/01) | 02 Jan 2025 | P50 |  | JGP left 9 point to complete
Thu (02/01) | 02 Jan 2025 | P49 |  | JGP pipe sleeves installation left 7 points to complete
Thu (02/01) | 02 Jan 2025 | MH2-9 |  | 5/5nos precast rings installed. Now preparing access and outer wall casting works
Thu (02/01) | 02 Jan 2025 | BRP7 |  | Trimming ongoing
Thu (02/01) | 02 Jan 2025 | UKP9 |  | Boring in progress, 14m
Thu (02/01) | 02 Jan 2025 | ST215 |  | Pre-excavation for dwall works
Thu (02/01) | 02 Jan 2025 | BC4 |  | Preparing to modify cutter size from 1.5m to 800mm
Thu (02/01) | 02 Jan 2025 | BR1 |  | Parapet wall formwork closing
Thu (02/01) | 02 Jan 2025 | BR2 |  | Hacking ongoing to expose couplers
Thu (02/01) | 02 Jan 2025 | BR2 |  | Hacking and cutting rebars for existing bored pile
Thu (02/01) | 02 Jan 2025 | DR1 |  | Hacking of existing drain wall almost completed. Target to lean con by Sat
Thu (02/01) | 02 Jan 2025 | BRP46 |  | Concrete casting done. Now waiting for LSS
Thu (02/01) | 02 Jan 2025 | BR5 |  | Hacking of bulging concrete ongoing
Thu (02/01) | 02 Jan 2025 | P44 |  | Prepare for casting. Concrete on site
Thu (02/01) | 02 Jan 2025 | MH3-5 |  | Hacking caisson done. Backfilling on going
Thu (02/01) | 02 Jan 2025 | ST146 | BC3 | B2 temporarily stopped. Cutter teeth change ongoing. CD 33/39.6m
Thu (02/01) | 02 Jan 2025 | MH3-4 |  | Lining work in progress
Thu (02/01) | 02 Jan 2025 | Exit 1 |  | Desander stockpile status
Thu (02/01) | 02 Jan 2025 | P44 |  | Pilecap casting in progress
Thu (02/01) | 02 Jan 2025 | BRP46 |  | LSS truck arrived
Thu (02/01) | 02 Jan 2025 | ST116 | BC2 | Trimming started
Thu (02/01) | 02 Jan 2025 | P30-31 |  | Hacking ongoing to facilitate RC stump works
Thu (02/01) | 02 Jan 2025 | ST212 |  | Tremie pipe installation ongoing
Thu (02/01) | 02 Jan 2025 | DW27 |  | Preboring temporarily stopped. Crawler track cleaning ongoing
Thu (02/01) | 02 Jan 2025 | P21 |  | RG manual trial trench for instrument cluster installation. Geomotion has completed RW installation here
Thu (02/01) | 02 Jan 2025 | P24 |  | 2 rigs here for RW works. Preparation ongoing
Thu (02/01) | 02 Jan 2025 | BP6 | 15 | Boring in progress
Thu (02/01) | 02 Jan 2025 | BP3 | 16 | Boring in progress, 20/37.49m
Thu (02/01) | 02 Jan 2025 | Exit 3 |  | Desander stockpile status
Thu (02/01) | 02 Jan 2025 | P44 |  | Casting in progress
Thu (02/01) | 02 Jan 2025 | ST116 |  | Waterstop side trimming
Thu (02/01) | 02 Jan 2025 | DR1 |  | Soldier piles and steel plate removal
Thu (02/01) | 02 Jan 2025 | BR2 |  | Exposing couplet
Thu (02/01) | 02 Jan 2025 | BC4 |  | Cutter size changing
Thu (02/01) | 02 Jan 2025 | P12 |  | Soffit formwork and falsework removal
Thu (02/01) | 02 Jan 2025 | P3 |  | Excavation for S2 layer
Thu (02/01) | 02 Jan 2025 | P5 |  | Preboring work
Thu (02/01) | 02 Jan 2025 | MH2-9& 2-10 |  | No activity already
Fri (03/01) | 03 Jan 2025 | BR1 |  | CJ cleaning in progress
Fri (03/01) | 03 Jan 2025 | P18 to P17 |  | KTC drain hacking and removal works ongoing for stage 2 diversion
Fri (03/01) | 03 Jan 2025 | BR5 |  | Locating area for waterproofing works at dwall area
Fri (03/01) | 03 Jan 2025 | ST146 | BC3 | B2 internal koden check
Fri (03/01) | 03 Jan 2025 | P44 |  | GCE clearing the area for their plant setup
Fri (03/01) | 03 Jan 2025 | P44 |  | Pilecap no activity. Cast yesterday
Fri (03/01) | 03 Jan 2025 | MH3-4 |  | Lining works ongoing
Fri (03/01) | 03 Jan 2025 | Near MH3-4 |  | Levelling works and arranging steel plates ongoing
Fri (03/01) | 03 Jan 2025 | MH3-5 |  | No activity
Fri (03/01) | 03 Jan 2025 | Zone 2 |  | Stockpile status
Fri (03/01) | 03 Jan 2025 | P14 |  | Netting installation works
Fri (03/01) | 03 Jan 2025 | P12 |  | Falsework dismantling works in progress
Fri (03/01) | 03 Jan 2025 | P10 to P9 |  | Excavation for telco duct in progress
Fri (03/01) | 03 Jan 2025 | Zone 4 |  | JGP point P50-22 in progress
Fri (03/01) | 03 Jan 2025 | P8-1 |  | Column formwork dismantled. Backfilling and leveling works in progress
Fri (03/01) | 03 Jan 2025 | P6 |  | Backfilling works in progress
Fri (03/01) | 03 Jan 2025 | P5 |  | Preboring for ERSS in progress
Fri (03/01) | 03 Jan 2025 | P3 |  | Excavation to s2 layer
Fri (03/01) | 03 Jan 2025 | P20-3 |  | BP Rebar cages lowered. Preparation for casting
Fri (03/01) | 03 Jan 2025 | P21-1 |  | BP boring in progress, depth 6m
Fri (03/01) | 03 Jan 2025 | DW27 |  | Preboring completed
Fri (03/01) | 03 Jan 2025 | ST215 | BC1 | B1 in progress
Fri (03/01) | 03 Jan 2025 | Exit 2 |  | Dismantling noise barriers at desander
Fri (03/01) | 03 Jan 2025 | BR1 |  | CJ cleaning in progress
Fri (03/01) | 03 Jan 2025 | BR2 |  | Slope trimming and preparing to backfill LSS at kingpost area
Fri (03/01) | 03 Jan 2025 | P18 |  | KTC continue drain removal for stage 2 TD
Fri (03/01) | 03 Jan 2025 | P19-P20+ |  | ATS RCA backfilling and levelling works
Fri (03/01) | 03 Jan 2025 | Beside N5 |  | Trial trench works for stage 2 TD
Fri (03/01) | 03 Jan 2025 | P14 |  | Plywood platform installation works in progress
Fri (03/01) | 03 Jan 2025 | P12 |  | Continue falsework dismantling works
Fri (03/01) | 03 Jan 2025 | P9-P10 |  | Preparation for 18m lean concrete for telco duct
Fri (03/01) | 03 Jan 2025 | P9 |  | Patching rectification works in progress
Fri (03/01) | 03 Jan 2025 | BR5 |  | Partial backfilling in progress to facilitate BC movement to CCE side
Fri (03/01) | 03 Jan 2025 | BR5 |  | Continue hacking of bulging concrete
Fri (03/01) | 03 Jan 2025 | BRP58 |  | Guidewall construction in progres
Fri (03/01) | 03 Jan 2025 | BRP76 |  | Premix hacking for guidewall trial trench
Fri (03/01) | 03 Jan 2025 | ST146 | BC3 | B3 completed, 39.8m/39.6m
Fri (03/01) | 03 Jan 2025 | ST116 | BC2 | Cleaning and desanding completed. Now area preparation for BC to move to next panel, ST120
Fri (03/01) | 03 Jan 2025 | DR1 |  | ERSS extraction in progress
Fri (03/01) | 03 Jan 2025 | UKP6 |  | Boring completed. Waiting for depth check
Fri (03/01) | 03 Jan 2025 | BP3 | 16 | Boring in progress, 23.4/37.49m
Fri (03/01) | 03 Jan 2025 | BP6 | 15 | Boring in progress
Fri (03/01) | 03 Jan 2025 | S3 |  | Falsework installation in progress
Fri (03/01) | 03 Jan 2025 | P6 |  | Backfilling and compaction works ongoing
Fri (03/01) | 03 Jan 2025 | P21 |  | RG continue manual trial trench for instrument cluster installation
Fri (03/01) | 03 Jan 2025 | P21-1 |  | Casing installation
Fri (03/01) | 03 Jan 2025 | P5 |  | ERSS installation in progress
Fri (03/01) | 03 Jan 2025 | P3 |  | Continue excavation to s2 layer
Fri (03/01) | 03 Jan 2025 | BP6 | 15 | Boring CD 24.0/36.303m
Fri (03/01) | 03 Jan 2025 | MH2-9 |  | 3rd lift outer wall cast yesterday
Fri (03/01) | 03 Jan 2025 | P20-3 |  | BP boring completed. Pending RTO inspection on the depth. Today to cast
Fri (03/01) | 03 Jan 2025 | BR2 |  | Exposing couplers
Sat (04/01) | 04 Jan 2025 | Exit 2 |  | STN215 B1 excavation in progress, 34.50m/35.90m
Sat (04/01) | 04 Jan 2025 | BP3 | 16 | Boring in progress, current depth 23.4m
Sat (04/01) | 04 Jan 2025 | BP6 | 15 | Boring in progress, current depth 30m
Sat (04/01) | 04 Jan 2025 | ST120 |  | Preparing for 1st bite excavation
Sat (04/01) | 04 Jan 2025 | Bet. P24-P23 RWS-24 & RWS-26 |  | Drilling works in progress for recharge well installation
Sat (04/01) | 04 Jan 2025 | ST146 |  | Waterstop side trimming
Sat (04/01) | 04 Jan 2025 | No activity at BR2 |  | Lean concrete and slope protection cast
Sat (04/01) | 04 Jan 2025 | BC2 |  | Cutter size changing
Sat (04/01) | 04 Jan 2025 | ST215 |  | 2nd bite, reached 15m
Sat (04/01) | 04 Jan 2025 | P21-1 |  | BP boring ongoing, target to cast today
Sat (04/01) | 04 Jan 2025 | P19 |  | ATS backfilling works for stage 2 TD
Sat (04/01) | 04 Jan 2025 | P18 |  | KTC drain hacking and disposal works ongoing
Sat (04/01) | 04 Jan 2025 | N5 |  | Segment supports adjustment works
Sat (04/01) | 04 Jan 2025 | Zone 2 |  | Stockpile status
Sat (04/01) | 04 Jan 2025 | P14 |  | Jack installation & adjustment in progress for base formwork
Sat (04/01) | 04 Jan 2025 | P14 |  | Pier hacking to correct level in progress
Sat (04/01) | 04 Jan 2025 | P12 |  | Primary beam dismantle and removal works in progress
Sat (04/01) | 04 Jan 2025 | P10 |  | Telco duct pipe laying works ongoing. Target to cast 12m today
Sat (04/01) | 04 Jan 2025 | P9 |  | Retifcation works in progress
Sat (04/01) | 04 Jan 2025 | S3 |  | Crosshead falsework installation
Sat (04/01) | 04 Jan 2025 | P6 |  | KTC backfilling works ongoing
Sat (04/01) | 04 Jan 2025 | P5 |  | ERSS installation in progress
Sat (04/01) | 04 Jan 2025 | P3 |  | KTC excavation to s2 layer in progress
Sat (04/01) | 04 Jan 2025 | P50-19 |  | JGP grouting in progress
Sat (04/01) | 04 Jan 2025 | Zone 4, P49 |  | Exposed tree roots waiting for extraction
Sat (04/01) | 04 Jan 2025 | ST-120 |  | 1st bite excavation in progress, current 30m
Sat (04/01) | 04 Jan 2025 | ST-116 |  | Rebar cages lowering in progress, 5/8 nos. completed
Sat (04/01) | 04 Jan 2025 | P44 |  | No activity
Sat (04/01) | 04 Jan 2025 | Exit 1 |  | Stockpile current status
Sat (04/01) | 04 Jan 2025 | ST-146 |  | Waterstop trimming works ongoing
Sat (04/01) | 04 Jan 2025 | BR5 |  | Dwall hacking, exposing rebar coupler
Sat (04/01) | 04 Jan 2025 | BR2 |  | KTC excavation works in progress
Sat (04/01) | 04 Jan 2025 | Exit 2 |  | Stockpile current status
Sat (04/01) | 04 Jan 2025 | Exit 3 |  | Stockpile current status
Sat (04/01) | 04 Jan 2025 | P21-1 |  | BP boring completed. Koden check and rebar cages preparation in progress
Sat (04/01) | 04 Jan 2025 | Zone 3 CCW P21-P22 |  | Post lugeon test in progress for CHW-10 (WO-66/WO-67)
Sat (04/01) | 04 Jan 2025 | Bet. P24-P23 RWS-24 & RWS-26 |  | Recharge well installation completed for RWS-26. Drilling in progress for RWS-24
Sat (04/01) | 04 Jan 2025 | BP6 | 15 | Boring in progress, current depth 31m
Sat (04/01) | 04 Jan 2025 | BP3 | 16 | Boring in progress, current depth 24m
Sat (04/01) | 04 Jan 2025 | Exit 2 ST-215 |  | B1 excavation completed. Now wheel teeth changing
Sat (04/01) | 04 Jan 2025 | Exit 2 |  | Base platform for desander, casting in progress
Sat (04/01) | 04 Jan 2025 | BR1 |  | CJ hacking at coupler to roughen the surface in progress
Sat (04/01) | 04 Jan 2025 | DR-1 |  | Preparation ongoing for base lean concrete today
Sat (04/01) | 04 Jan 2025 | BR2 |  | KTC continue excavation works and preparation for slope lean concrete
Sat (04/01) | 04 Jan 2025 | BR5 |  | Continue Dwall hacking, exposing rebar coupler
Sat (04/01) | 04 Jan 2025 | ST-146 |  | Waterstop trimming works ongoing
Sat (04/01) | 04 Jan 2025 | ST-116 |  | 7th Rebar cage lapping and lowering in progress, 6/8 nos. completed
Sat (04/01) | 04 Jan 2025 | ST-120 |  | 1st bite excavation in progress, current 33m
Sat (04/01) | 04 Jan 2025 | MH3-4 |  | Lining works in progress
Sat (04/01) | 04 Jan 2025 | Zone 4 |  | JGP grouting completed for P50-19 & P50-17. Now preparation for drilling for P50-15
Sat (04/01) | 04 Jan 2025 | P19 |  | ATS surveying for next section of TD backfilling works
Sat (04/01) | 04 Jan 2025 | P18-P17 |  | KTC continue hardcores disposal and drain hacking works
Sat (04/01) | 04 Jan 2025 | P14 |  | Wingform formwork installation and pier hacking ongoing
Sat (04/01) | 04 Jan 2025 | P12 |  | Continue falsework dismantle and removal works
Sat (04/01) | 04 Jan 2025 | P9-P10 |  | Formwork closed for 12m telco duct. Preparation for casting
Sat (04/01) | 04 Jan 2025 | S3 |  | Crosshead falsework installation current status
Sat (04/01) | 04 Jan 2025 | P6 |  | KTC backfilling works till pilecap top level
Sat (04/01) | 04 Jan 2025 | P5 |  | ERSS installation completed
Sat (04/01) | 04 Jan 2025 | P3 |  | Excavation to S2 layer in progress
Sat (04/01) | 04 Jan 2025 | P1 |  | Preparation works for PDA testing next week
Sat (04/01) | 04 Jan 2025 | Opp MH2-10 |  | Manual hacking of existing MH wall for TBM retrieval
Sat (04/01) | 04 Jan 2025 | MH9 | PUB sewer manhole | 4 workers+ 1sup provided for manhole hacking for jacking machine retrieval
Sat (04/01) | 04 Jan 2025 | P14 |  | Soffit formwork and wing form installation and adjusting
Sat (04/01) | 04 Jan 2025 | Zone 4 |  | Tonight GCE working until 3AM. Clearing soil from P49 and shift to P50. This night shift team will come back to day shift on monday for receiving shaft side grouting work
Sat (04/01) | 04 Jan 2025 | P50 |  | Left 2 points to complete JGP grouting. Tomorrow to complete
Sat (04/01) | 04 Jan 2025 | P49 |  | Left 3 points to complete pipe sleeves installation. Will install on monday after tree roots removal
Sun (05/01) | 05 Jan 2025 | P14 |  | Crosshead formwork installation in progress
Sun (05/01) | 05 Jan 2025 | P12 |  | Falsework dismantling in progress
Sun (05/01) | 05 Jan 2025 | P3 |  | 2nd layer excavation in progress
Sun (05/01) | 05 Jan 2025 | Zone 1 |  | LE no activity
Sun (05/01) | 05 Jan 2025 | ST215 | BC1 | B2 in progress, 28.5/35.9m
Sun (05/01) | 05 Jan 2025 | Exit 2 |  | Desander shifted nearer to LVC side. Accessories setup ongoing
Sun (05/01) | 05 Jan 2025 | BC4 |  | Cutter size modification in progress
Sun (05/01) | 05 Jan 2025 | BR2 |  | Housekeeping
Sun (05/01) | 05 Jan 2025 | BR1 |  | No activity
Sun (05/01) | 05 Jan 2025 | DR1 |  | Currently no activity. Lean con cast yesterday
Sun (05/01) | 05 Jan 2025 | BR5 |  | Hacking of bulging concrete ongoing
Sun (05/01) | 05 Jan 2025 | BR5 |  | KTC partial backfilling in progress to facilitate BC machine crossover. Plan for 10T roller compaction tmr
Sun (05/01) | 05 Jan 2025 | BRP76A, 76B |  | Guidewall rebar works in progres
Sun (05/01) | 05 Jan 2025 | ST146 | BC3 | WS trimming completed
Sun (05/01) | 05 Jan 2025 | BC2 |  | Currently no activity
Sun (05/01) | 05 Jan 2025 | Exit 1 |  | Desander stockpile status
Sun (05/01) | 05 Jan 2025 | P44 |  | No activity
Sun (05/01) | 05 Jan 2025 | ST116 |  | Casting in progress
Sun (05/01) | 05 Jan 2025 | MH3-5 |  | No activity
Sun (05/01) | 05 Jan 2025 | Zone 4 |  | GCE shifting 1nos silo plant to P44 area
Sun (05/01) | 05 Jan 2025 | P50-18 |  | JGP drilling in progress
Sun (05/01) | 05 Jan 2025 | P50 |  | WH trial trench for pumping main probe drill
Sun (05/01) | 05 Jan 2025 | P14 |  | Bus lane closed and soffit formwork adjusting
Sun (05/01) | 05 Jan 2025 | P12 |  | Beam dismantling
Sun (05/01) | 05 Jan 2025 | MH2-9 |  | No activity
Sun (05/01) | 05 Jan 2025 | BC1 |  | Machine rectification ongoing
Sun (05/01) | 05 Jan 2025 | BR1 |  | Retaining wall formwork installation ongoing
Sun (05/01) | 05 Jan 2025 | BR2 |  | Inverted column kicker formwork installation ongoing
Sun (05/01) | 05 Jan 2025 | DR1 CH20-35 |  | Rebar works started
Sun (05/01) | 05 Jan 2025 | BR5 |  | Slope casting
Sun (05/01) | 05 Jan 2025 | ST146 | BC3 | Cleaning works
Sun (05/01) | 05 Jan 2025 | Near exit 1 |  | GCE setting up their plant
Sun (05/01) | 05 Jan 2025 | ST120 | BC2 | Bentonite line hose rectification ongoing
Sun (05/01) | 05 Jan 2025 | ST-146 |  | Waterstop end plate trimming for removal
Sun (05/01) | 05 Jan 2025 | Exit 3 |  | Desander stockpile status
Sun (05/01) | 05 Jan 2025 | P20 |  | HSL no activity
Sun (05/01) | 05 Jan 2025 | Zone 2 stage 2 diversion |  | RCA levelling ongoing
Sun (05/01) | 05 Jan 2025 | N5 |  | Support adjustment ongoing
Mon (06/01) | 06 Jan 2025 | P49 |  | Removal of tree roots
Mon (06/01) | 06 Jan 2025 | P49 |  | One team doing JGP
Mon (06/01) | 06 Jan 2025 | P51 |  | Current status of stockpiles
Mon (06/01) | 06 Jan 2025 | P17 to P19 |  | Trial trench, Drain hacking, soil disposal and rca backfilling works ongoing for stage 2 TD diversion
Mon (06/01) | 06 Jan 2025 | Zone 2 |  | Stockpile current status
Mon (06/01) | 06 Jan 2025 | P15 |  | Falsework erection in progress
Mon (06/01) | 06 Jan 2025 | P14 |  | Side formwork installation ongoing
Mon (06/01) | 06 Jan 2025 | P11 |  | Preparation for formwork dismantling
Mon (06/01) | 06 Jan 2025 | Zone 2 |  | 12m telco duct cast last week. Now pending materials shifting for working space
Mon (06/01) | 06 Jan 2025 | P8-1 |  | Preparation for ERSS extraction
Mon (06/01) | 06 Jan 2025 | P3 |  | Falsework current status
Mon (06/01) | 06 Jan 2025 | P6-1 |  | Backfilling to pile cap level completed
Mon (06/01) | 06 Jan 2025 | P5 |  | Excavation to s1 layer completed. Welding of waler brackets in progress
Mon (06/01) | 06 Jan 2025 | P3 |  | Excavation to S2 layer in progress
Mon (06/01) | 06 Jan 2025 | P1-1 |  | Setting up for PDA test in progress. Today to carry out testing
Mon (06/01) | 06 Jan 2025 | MH3-4 |  | Manhole cover installation. Lining work completed
Mon (06/01) | 06 Jan 2025 | P43 |  | Cut down the soil around 500mm. Tomorrow GCE will mobilized the rig
Mon (06/01) | 06 Jan 2025 | BP6 | 15 | Boring in progress, 35.5/36.3m
Mon (06/01) | 06 Jan 2025 | BP3 | 16 | Boring in progress, 27/37.49m
Mon (06/01) | 06 Jan 2025 | TDP10 |  | Boring completed. Waiting for rto checking
Mon (06/01) | 06 Jan 2025 | ST215 | BC1 | WS trimming
Mon (06/01) | 06 Jan 2025 | Exit 2 |  | Setting up frame for noise barrier panel & BC4 modification works ongoing
Mon (06/01) | 06 Jan 2025 | DR1 CH35-20 |  | Rebar works in progress
Mon (06/01) | 06 Jan 2025 | BR2 |  | Side lean con casting ongoing
Mon (06/01) | 06 Jan 2025 | BR5 |  | Levelling and compaction at partial backfilled area
Mon (06/01) | 06 Jan 2025 | BR5 dwall area |  | Exposing couplers
Mon (06/01) | 06 Jan 2025 | ST146 |  | Rebar cage lapping in progress, 7/8nos
Mon (06/01) | 06 Jan 2025 | ST136 | BC3 | B1 temporarily stopped. CD 21/34.4m. Cutter cleaning and teeth replacement ongoing
Mon (06/01) | 06 Jan 2025 | ST120 | BC2 | B2 completed
Tue (07/01) | 07 Jan 2025 | BR2 |  | Preparing for drilling for skin wall starter bars
Tue (07/01) | 07 Jan 2025 | BR2 |  | Debonding sheet on site
Tue (07/01) | 07 Jan 2025 | P9-10 |  | Preparing to excavate for teleco duct laying
Tue (07/01) | 07 Jan 2025 | P8 |  | ERSS removal
Tue (07/01) | 07 Jan 2025 | DR1 CH35-20 |  | Rebar works in progress
Tue (07/01) | 07 Jan 2025 | P5 |  | Waler joint welding
Tue (07/01) | 07 Jan 2025 | BR5 |  | Continue exposing couplers and side formwork installation
Tue (07/01) | 07 Jan 2025 | BRP73 |  | Guidewall trial trench in progress
Tue (07/01) | 07 Jan 2025 | ST146 |  | Casting in progress
Tue (07/01) | 07 Jan 2025 | BR5 |  | Continue partial backfilling soil+ hardcore
Tue (07/01) | 07 Jan 2025 | P49 |  | Continue JGP grouting
Tue (07/01) | 07 Jan 2025 | P51 |  | Removal of hoarding joint and prepare for probing work on live road
Tue (07/01) | 07 Jan 2025 | ST136 | BC3 | B1 in progress, 32/34.4m
Tue (07/01) | 07 Jan 2025 | ST120 | BC2 | Trimming ongoing
Tue (07/01) | 07 Jan 2025 | Near blk 2 |  | HSL preparing rig for BP2B-2(51)
Tue (07/01) | 07 Jan 2025 | BP3 | 16 | Boring in progress
Tue (07/01) | 07 Jan 2025 | BP6 | 15 | Boring in progress. Target to complete this pile today
Tue (07/01) | 07 Jan 2025 | P21 |  | RG drilling ongoing for inclinometer installation
Tue (07/01) | 07 Jan 2025 | P20 |  | HSL demob equipment
Tue (07/01) | 07 Jan 2025 | MH3-4 |  | Plaster for manhole cover
Tue (07/01) | 07 Jan 2025 | P20 |  | HSL cleaning of materials in progress and preparation for WLT mobilisation tmr
Tue (07/01) | 07 Jan 2025 | P17-P18 |  | KTC continue drain hacking and soil disposal for stage 2 TD
Tue (07/01) | 07 Jan 2025 | P19-P18 |  | ATS RCA backfilling ongoing
Tue (07/01) | 07 Jan 2025 | P19 |  | WH to excavate for internal water pipe and power supply shifting
Tue (07/01) | 07 Jan 2025 | Exit 2 desander |  | Noise barrier panel installed in progress
Tue (07/01) | 07 Jan 2025 | P30 |  | Stump formwork installation for UKP19, UKP20 in progress. Plan for casting tomorrow
Tue (07/01) | 07 Jan 2025 | P49 |  | 5nos of JGP grouting done. Preparing for 6th point
Tue (07/01) | 07 Jan 2025 | P15 |  | Falsework installation in progress
Tue (07/01) | 07 Jan 2025 | P14 |  | Rebars arrived on site. Preparation for rebar installation
Tue (07/01) | 07 Jan 2025 | BR2 |  | Ground surface patch up and cleaning ongoin
Tue (07/01) | 07 Jan 2025 | BR2 |  | RGT installation in progress
Tue (07/01) | 07 Jan 2025 | BR2 |  | Installation of skin wall starter bars
Tue (07/01) | 07 Jan 2025 | P11 |  | Formwork dismantle and removal ongoing
Tue (07/01) | 07 Jan 2025 | P10 |  | Backfilling and levelling ongoing for telco duct
Tue (07/01) | 07 Jan 2025 | P8-1 |  | ERSS extraction in progress
Tue (07/01) | 07 Jan 2025 | P6 |  | No activity. Concrete plug cast yesterday
Tue (07/01) | 07 Jan 2025 | P5 |  | Continue welding for walers & struts
Tue (07/01) | 07 Jan 2025 | DR1 CH35-20 |  | Continue rebar works
Tue (07/01) | 07 Jan 2025 | P3 |  | Excavation to S2 layer completed. Now preparation for test pile hacking
Tue (07/01) | 07 Jan 2025 | P2 |  | Trial trench for ERSS in progress
Tue (07/01) | 07 Jan 2025 | Zone 2 |  | KTC continue hardcore disposal
Tue (07/01) | 07 Jan 2025 | P15 |  | Falsework installation in progress
Tue (07/01) | 07 Jan 2025 | P14 |  | Unloading of rebars
Tue (07/01) | 07 Jan 2025 | P11 |  | Crosshead formwork dismantling ongoin
Tue (07/01) | 07 Jan 2025 | P10 |  | Telco duct backfilling and continue barricade rectification
Tue (07/01) | 07 Jan 2025 | P8 |  | ERSS extraction
Tue (07/01) | 07 Jan 2025 | BP6 | 15 | Rebar cage installation in progress
Tue (07/01) | 07 Jan 2025 | BP3 | 16 | Boring in progress, 28.8/37.49m. Noise balloon setup ongoing
Tue (07/01) | 07 Jan 2025 | Near exit 3 |  | 1 boring rig no activity. This rig will resume tmr for BP works
Tue (07/01) | 07 Jan 2025 | Near blk 2 |  | BP2B-2(51) preboring & casing installation
Tue (07/01) | 07 Jan 2025 | ST215 |  | Final koden check & BC1 cutter replacement ongoing
Tue (07/01) | 07 Jan 2025 | BR5 |  | Final layer ongoing at partial backfilled area
Tue (07/01) | 07 Jan 2025 | MH2-9 |  | No activity
Tue (07/01) | 07 Jan 2025 | MH2-10 |  | Housekeeping. Opposite MH, balance work to retrieve the machine
Tue (07/01) | 07 Jan 2025 | Exit 3 |  | KTC hardcore removal ongoing
Tue (07/01) | 07 Jan 2025 | ST215 | BC1 | Cleaning
Tue (07/01) | 07 Jan 2025 | Exit 2 |  | Frame setup for desander noise control panel and BC4 modification works in progress
Wed (08/01) | 08 Jan 2025 | P30 |  | 2nos stump formwork done
Wed (08/01) | 08 Jan 2025 | BR2 |  | Cleaning of couplers (wendyng) and Maxbond preparing to continue RGT installation
Wed (08/01) | 08 Jan 2025 | P49 |  | Continue JGP grouting
Wed (08/01) | 08 Jan 2025 | P14 |  | Railing installation for rebar installation
Wed (08/01) | 08 Jan 2025 | DR1 CH35-20 |  | Continue base slab rebar works
Wed (08/01) | 08 Jan 2025 | BR5 |  | Partial backfilled area has completed and steel plates laid. Pending COS prior to proceeding with BC machine crossover
Wed (08/01) | 08 Jan 2025 | BRP73 |  | Guidewall construction in progress
Wed (08/01) | 08 Jan 2025 | MH3-5 |  | Balance lining work
Wed (08/01) | 08 Jan 2025 | ST136 | BC3 | B2 in progress
Wed (08/01) | 08 Jan 2025 | P9-10 |  | 66KV expose for Utility team verification
Wed (08/01) | 08 Jan 2025 | Near exit 1 desander |  | Stockpile status
Wed (08/01) | 08 Jan 2025 | ST120 | BC2 | B3 in progress, 18.7/39m
Wed (08/01) | 08 Jan 2025 | MH2-10 |  | Removal of slurry pipes
Wed (08/01) | 08 Jan 2025 | P49 |  | Continue grouting JGP
Wed (08/01) | 08 Jan 2025 | BR2 |  | Rectifying the uneven ground surface at the section as per commented during at joint inspection this morning
Wed (08/01) | 08 Jan 2025 | BR2 |  | Partial laying of the debonding sheet ongoing
Wed (08/01) | 08 Jan 2025 | TDP110 |  | Casing installed
Wed (08/01) | 08 Jan 2025 | BP2-1 | 27 | Boring CD at 14m
Wed (08/01) | 08 Jan 2025 | BP2B-2 | 51 | Boring CD at 17m
Wed (08/01) | 08 Jan 2025 | BR5 dwall area |  | Continue to expose couplers
Wed (08/01) | 08 Jan 2025 | P16-17 |  | Drain hacking for stage 2 diversion
Wed (08/01) | 08 Jan 2025 | ST136 | BC3 | Internal koden check
Wed (08/01) | 08 Jan 2025 | ST120 | BC2 | C-lug welding for WS trimming ongoing
Wed (08/01) | 08 Jan 2025 | TMH3 |  | Excavation in progress
Wed (08/01) | 08 Jan 2025 | Exit 3 |  | Excavation ongoing for removal of machinery platform
Wed (08/01) | 08 Jan 2025 | P18 |  | Excavation ongoing for ERSS removal
Wed (08/01) | 08 Jan 2025 | P15 |  | Continue falsework installation
Wed (08/01) | 08 Jan 2025 | P14 |  | Crosshead rebar works in progress
Wed (08/01) | 08 Jan 2025 | P11 |  | Crosshead formwork dismantling
Wed (08/01) | 08 Jan 2025 | BP6 | 15 | LSS backfill completed. Casing extraction ongoing
Wed (08/01) | 08 Jan 2025 | BP3 | 16 | Boring in progress, 35/37.49m
Wed (08/01) | 08 Jan 2025 | BP2-1 | 27 | Boring in progress
Wed (08/01) | 08 Jan 2025 | TDP110 |  | Boring reached 12m
Wed (08/01) | 08 Jan 2025 | BP2B-2 | 51 | Boring reached 19m
Wed (08/01) | 08 Jan 2025 | ST215 |  | Rebar cage lapping in progress, 3/8nos
Wed (08/01) | 08 Jan 2025 | DR1 CH35-20 |  | Cleaning ongoing before inspection. Plan for base slab casting tonight
Wed (08/01) | 08 Jan 2025 | Exit 3 |  | BC1 has shifted to next barette pile panel
Wed (08/01) | 08 Jan 2025 | P20-2 |  | Today to deliver hardcore and prepare the area for Kentledge test
Thu (09/01) | 09 Jan 2025 | ST136 | Rig 3 | B2 cleaning in progress
Thu (09/01) | 09 Jan 2025 | ST120 | Rig 2 | B2 Trimming in progress
Thu (09/01) | 09 Jan 2025 | BR2 |  | Ground surface needs to be rectified again before laying the debonding sheet
Thu (09/01) | 09 Jan 2025 | Exit 2 desander |  | Noise barrier panel installed in progress
Thu (09/01) | 09 Jan 2025 | Exit 3 |  | Manual excavation for utility goal post signage installation
Thu (09/01) | 09 Jan 2025 | Exit 3 |  | Desander status
Thu (09/01) | 09 Jan 2025 | BP2B-2 | 51 | Boring CD 20.0/37.501m
Thu (09/01) | 09 Jan 2025 | BP2-1 | 27 | Boring CD 27.0/40.427m
Thu (09/01) | 09 Jan 2025 | BP3 | 16 | Boring CD 32.0/37.492m
Thu (09/01) | 09 Jan 2025 | TDP110 |  | Boring CD 22.6/22.68m
Thu (09/01) | 09 Jan 2025 | P21 |  | RG continue drilling for piezometer installation. Inclinometer installation has been completed
Thu (09/01) | 09 Jan 2025 | Near exit 3 |  | Guidewall hacking ongoing
Thu (09/01) | 09 Jan 2025 | BRP10 | BC1 | Replacing of suction pump ongoing
Thu (09/01) | 09 Jan 2025 | P49 |  | Current status of JGP
Thu (09/01) | 09 Jan 2025 | P49 |  | Tree roots exposing and removal
Thu (09/01) | 09 Jan 2025 | P49 |  | Continue JGP grouting
Thu (09/01) | 09 Jan 2025 | MH3-5 |  | Lining work
Thu (09/01) | 09 Jan 2025 | P49 |  | Continue JGP grouting
Thu (09/01) | 09 Jan 2025 | zone 2 |  | Old drain hacking status
Thu (09/01) | 09 Jan 2025 | P11 |  | Strand pulling on going
Thu (09/01) | 09 Jan 2025 | P9-10 |  | 6m telco duct excavated. Railing installation in progress
Thu (09/01) | 09 Jan 2025 | P5 |  | Preparation for FEL excavation
Thu (09/01) | 09 Jan 2025 | P3 |  | Welding in progress for S2 layer waler and struts
Thu (09/01) | 09 Jan 2025 | ST196 |  | Abandoned drain hacking ongoing
Thu (09/01) | 09 Jan 2025 | BR2 |  | Surface rectification in progress
Thu (09/01) | 09 Jan 2025 | ST120 | BC2 | Cleaning completed
Thu (09/01) | 09 Jan 2025 | BR5 |  | Removing the BC crossover platform. Excavation and soil sieving ongoing
Thu (09/01) | 09 Jan 2025 | BC3 |  | Cutter teeth changing ongoing
Thu (09/01) | 09 Jan 2025 | BC4 |  | Setup works
Thu (09/01) | 09 Jan 2025 | BR5 |  | Dwall rectification works
Thu (09/01) | 09 Jan 2025 | Exit 3 |  | Hacking ongoing at capping beam area
Thu (09/01) | 09 Jan 2025 | P20 |  | Steel mat laying works for WLT ongoing
Thu (09/01) | 09 Jan 2025 | P5 |  | KTC long arm excavator mobilise for excavation til FEL
Thu (09/01) | 09 Jan 2025 | P3 |  | LE to continue waler bracket installation until 10pm
Thu (09/01) | 09 Jan 2025 | BP3 | 16 | Boring in progress, 34.5/37.49m. Noise balloon setup
Thu (09/01) | 09 Jan 2025 | STN215 |  | Tremie pipes installation. Concrete ordered
Thu (09/01) | 09 Jan 2025 | DR1 CH35-20 |  | Base slab cast last evening. Today to continue wall rebar works
Fri (10/01) | 10 Jan 2025 | Exit 3 |  | Desander status
Fri (10/01) | 10 Jan 2025 | P21 |  | RG continue drilling for piezometer installation. Today plan to complete
Fri (10/01) | 10 Jan 2025 | TDP110 |  | Yesterday completed installation. Now preparing for LSS backfill
Fri (10/01) | 10 Jan 2025 | BP3 | 16 | Boring in progress. Tomorrow target to complete this pile
Fri (10/01) | 10 Jan 2025 | BP2-1 | 27 | Boring in progress
Fri (10/01) | 10 Jan 2025 | Near exit 3 |  | Seongha continue drilling for fissure grouting points
Fri (10/01) | 10 Jan 2025 | BRP10 | BC1 | B2 in progress, 13/28.1m
Fri (10/01) | 10 Jan 2025 | DW27 |  | Guidewall (800mm) hacking ongoing
Fri (10/01) | 10 Jan 2025 | BP2B-1 | 51 | Boring in progress, 22/37.5m
Fri (10/01) | 10 Jan 2025 | ST156 | Rig 4 | B1 excavation CD 12.0/34.0m
Fri (10/01) | 10 Jan 2025 | Exit 3 |  | Hacking ongoing at capping beam area
Fri (10/01) | 10 Jan 2025 | ST136 |  | Rebar cage installation in progress
Fri (10/01) | 10 Jan 2025 | ST120 | Rig 2 | Waterstop removal in progress
Fri (10/01) | 10 Jan 2025 | P44 |  | Removal of temperature monitoring machine
Fri (10/01) | 10 Jan 2025 | P20-2 |  | Frame delivered for kentledge test. Today to continue delivery of other accessories
Fri (10/01) | 10 Jan 2025 | P49 |  | Current status of grouting completed
Fri (10/01) | 10 Jan 2025 | P49 |  | Set up rig for JGP grouting
Fri (10/01) | 10 Jan 2025 | P50 |  | Briefing for soldier pile TT
Sat (11/01) | 11 Jan 2025 | P15 |  | Soffit plywood laying. Continue drizzling so they put canvas as rain protection
Sat (11/01) | 11 Jan 2025 | P14 |  | Relocation of CCTV and tendom duct installation
Sat (11/01) | 11 Jan 2025 | STN129 |  | 1st bite trenching in progress, depth 13m
Sat (11/01) | 11 Jan 2025 | STN120 |  | Rebar cage installation. 3/8 installed. 4th cage preparation for installation and lowering
Sat (11/01) | 11 Jan 2025 | P6 |  | Waler cutting and removal
Sat (11/01) | 11 Jan 2025 | Zone 4 |  | P49 pile cap ERSS grouting. Tonight target 3 points
Sat (11/01) | 11 Jan 2025 | P5 |  | Pumping out water only
Sat (11/01) | 11 Jan 2025 | DR1 |  | Preparing for formwork closing
Sat (11/01) | 11 Jan 2025 | BR2 |  | No activity
Sat (11/01) | 11 Jan 2025 | STN156 |  | 1st bite trenching at 25m depth
Sat (11/01) | 11 Jan 2025 | BRP61-BC3 |  | Final koden inspection
Sat (11/01) | 11 Jan 2025 | BRP10-BC1 |  | 3rd bite trenching at 21.4m depth
Sat (11/01) | 11 Jan 2025 | P49 |  | Continue JGP grouting and prepare TT for P50
Sat (11/01) | 11 Jan 2025 | BRP10 |  | 2nd bite, reached 32m
Sat (11/01) | 11 Jan 2025 | BP3-16 & TDP11 |  | Preparing this two piles for casting. HSL 4 rigs working
Sat (11/01) | 11 Jan 2025 | P15 |  | Hacking of column to correct level and jacking installation for cross head formwork
Sat (11/01) | 11 Jan 2025 | P15 |  | Tendom duct and box installation
Sat (11/01) | 11 Jan 2025 | P6 |  | Diagonal strut and waler removal
Sat (11/01) | 11 Jan 2025 | BR2 |  | Resume roof slab rebar work
Sat (11/01) | 11 Jan 2025 | BRP61 |  | 1st bite cleaning on going
Sat (11/01) | 11 Jan 2025 | ST156 |  | Cutter head bring up for maintenance
Sat (11/01) | 11 Jan 2025 | ST129 |  | 1st bite just started
Sat (11/01) | 11 Jan 2025 | ST120 |  | 1st rebar cage lowering
Sat (11/01) | 11 Jan 2025 | P14 |  | Tonighy have 4 WH workers to continue PT duct installation
Sat (11/01) | 11 Jan 2025 | BRP10 |  | 2nd bite, reached 28m. Now repairing mud pump
Sat (11/01) | 11 Jan 2025 | BP2-1 | 27 | Boring reached 35.2m
Sat (11/01) | 11 Jan 2025 | BP3-16 |  | Boring reached 37m
Sat (11/01) | 11 Jan 2025 | TDP11 |  | Boring reached 20m
Sat (11/01) | 11 Jan 2025 | BP3 | 16 | Casting completed. Total vol 22 m3
Sat (11/01) | 11 Jan 2025 | TDP11 |  | Casting also completed
Sun (12/01) | 12 Jan 2025 | BRP-10 |  | Preparation for rebar cages lowering
Sun (12/01) | 12 Jan 2025 | BRP-8 |  | Pre excavation in progress
Sun (12/01) | 12 Jan 2025 | Exit 2 |  | Stockpile current status
Sun (12/01) | 12 Jan 2025 | BR1 |  | No activity
Sun (12/01) | 12 Jan 2025 | BR2 |  | Bottom rebars installation works in progress
Sun (12/01) | 12 Jan 2025 | BR5 |  | No activity
Sun (12/01) | 12 Jan 2025 | ST156 |  | 1st bite excavation in progress. Current depth 25.8m
Sun (12/01) | 12 Jan 2025 | BRP-61 |  | Rebar cages lowering in progress. 2/4 nos. completed
Sun (12/01) | 12 Jan 2025 | ST135 |  | 1st bite excavation in progress. Current depth 4m
Sun (12/01) | 12 Jan 2025 | ST129 |  | 1st bite excavation in progress. Current depth 27m
Sun (12/01) | 12 Jan 2025 | ST120 |  | Rebar cage lowering in progress. 7/8 nos. completed
Sun (12/01) | 12 Jan 2025 | P44 |  | No activity
Sun (12/01) | 12 Jan 2025 | Exit 1 |  | Current stockpile status
Sun (12/01) | 12 Jan 2025 | Zone 4 JGP P49 |  | P49-53 grouting completed. Now preparing for P49-45 drilling works
Sun (12/01) | 12 Jan 2025 | P15 |  | Wingform formwork and plywood formwork platform installation in progress
Sun (12/01) | 12 Jan 2025 | P19-P18 |  | ATS currently no activity due to ongoing rain
Sun (12/01) | 12 Jan 2025 | P14 |  | Current status for tendon duct installation
Sun (12/01) | 12 Jan 2025 | P11 |  | Tendon cables pulling and installation work
Sun (12/01) | 12 Jan 2025 | Zone 2 |  | Current stockpile status
Sun (12/01) | 12 Jan 2025 | P6-1 |  | No activity
Sun (12/01) | 12 Jan 2025 | Zone 1 P5 |  | No activity for excavation works
Sun (12/01) | 12 Jan 2025 | P3 |  | S2 layer welding works in progress for waler beams
Sun (12/01) | 12 Jan 2025 | P15 |  | Bus lane closed for bottom formwork installation
Sun (12/01) | 12 Jan 2025 | P15 |  | Bottom formwork installation
Sun (12/01) | 12 Jan 2025 | BRP10 |  | Rebar cages lowered. Hanging bar installation in progress
Sun (12/01) | 12 Jan 2025 | BRP8 |  | Preparation for trenching works
Sun (12/01) | 12 Jan 2025 | BP4A-2 | 42 | Trial trench in progress
Sun (12/01) | 12 Jan 2025 | BR2 |  | Continue Bottom rebars installation works
Sun (12/01) | 12 Jan 2025 | BR5 |  | Current status
Sun (12/01) | 12 Jan 2025 | ST156 |  | Cutter teeth changing in progress. 1st bite excavation current depth 27.6m
Sun (12/01) | 12 Jan 2025 | BRP61 |  | Rebar cages lowering in progress. 3/4 nos. completed
Sun (12/01) | 12 Jan 2025 | ST135 |  | 1st bite excavation in progress. Current depth 15m
Sun (12/01) | 12 Jan 2025 | ST129 |  | Cutter teeth changing in progress. 1st bite current depth 28m
Sun (12/01) | 12 Jan 2025 | ST120 |  | Rebar cages lowered and hanging bar installation in progress. 8/8 nos. completed
Sun (12/01) | 12 Jan 2025 | Zone 4 JGP |  | P49-45 grouting completed. Work stopped for the day
Sun (12/01) | 12 Jan 2025 | P3 |  | Continue welding works for waler beams
Sun (12/01) | 12 Jan 2025 | Zone 1 |  | Joint welding for ERSS works ongoing
Sun (12/01) | 12 Jan 2025 | STN129 |  | Cutter wheel soil cleaning
Sun (12/01) | 12 Jan 2025 | STN120 |  | 6th rebar cage installation
Sun (12/01) | 12 Jan 2025 | BRP61 |  | Crane shifting for rebar cage installation
Sun (12/01) | 12 Jan 2025 | P15 |  | Wingform formwork adjustment in progress
Sun (12/01) | 12 Jan 2025 | P14 |  | Current status for tendon duct installation
Sun (12/01) | 12 Jan 2025 | P11 |  | Tendon cables pulling and installation stopped for the day
Sun (12/01) | 12 Jan 2025 | P18-P19 |  | Current status for stage 2 diversion work
Sun (12/01) | 12 Jan 2025 | P20 |  | WLT preparation current status
Sun (12/01) | 12 Jan 2025 | Exit 3 |  | Current status of stockpile
Sun (12/01) | 12 Jan 2025 | BRP10 |  | Cleaning and desanding completed
Mon (13/01) | 13 Jan 2025 | BRP8 |  | B1 in progress. Cutter teeth changing ongoing
Mon (13/01) | 13 Jan 2025 | P5 |  | Excavation to FEL
Mon (13/01) | 13 Jan 2025 | BR2 |  | Continue surface cleaning & rebar installation
Mon (13/01) | 13 Jan 2025 | DR1 CH35-20 |  | Continue first lift rebar works & formwork
Mon (13/01) | 13 Jan 2025 | P14 |  | Section 3 links installation
Mon (13/01) | 13 Jan 2025 | TDP12 |  | Preparation work in progress
Mon (13/01) | 13 Jan 2025 | BP2-1 | 27 | Boring CD 40.0/40.427m
Mon (13/01) | 13 Jan 2025 | BP2B-2 | 51 | Boring CD 21.0/37.501m
Mon (13/01) | 13 Jan 2025 | P20-2 |  | Kentledge setting up. Secondary beam installation in progress
Mon (13/01) | 13 Jan 2025 | ST135 | Rig 3 | B2 excavation has resumed
Mon (13/01) | 13 Jan 2025 | ST120 | Rig 2 | B2 excavation CD 32.0/34.3m, now replacing of wheel teeth
Mon (13/01) | 13 Jan 2025 | BP2B-2 | 51 | Trench collapse as reported by HSL. Told them to shift the rig away from the trench. LSS ordered for backfilling
Mon (13/01) | 13 Jan 2025 | BR2 |  | Unsound concrete hacking for inspection and rectification
Mon (13/01) | 13 Jan 2025 | STN156-BC4 |  | 2nd bite trenching at 18m depth
Mon (13/01) | 13 Jan 2025 | STN135-BC3 |  | Cutter wheel teeth replacement
Tue (14/01) | 14 Jan 2025 | BR2 |  | Continue roof slab rebar works and RGT installation
Tue (14/01) | 14 Jan 2025 | DR1 CH20-35 |  | Continue formwork installation
Tue (14/01) | 14 Jan 2025 | BR5 |  | KTC continue removing of the backfilled soil used for BC crossover
Tue (14/01) | 14 Jan 2025 | BR5 |  | Surface cleaning ongoing near dwall area
Tue (14/01) | 14 Jan 2025 | ST156 | BC4 | Mud drum elbow rectification ongoing
Tue (14/01) | 14 Jan 2025 | ST135 | BC3 | B2 in progress
Tue (14/01) | 14 Jan 2025 | ST129 | BC2 | Cutter teeth rectification and preparing for c-lug welding for WS trimming
Tue (14/01) | 14 Jan 2025 | P44 |  | Formwork removal ongoing
Tue (14/01) | 14 Jan 2025 | P43 |  | GCE marking points for SPT works and continue setup plant
Tue (14/01) | 14 Jan 2025 | MH3-5 |  | Lining works ongoing
Tue (14/01) | 14 Jan 2025 | P49-47 |  | JGP works in progress
Tue (14/01) | 14 Jan 2025 | BP2B-2 | 51 | LSS backfill ongoing. Trench collapsed yesterday at 27/37.5m
Tue (14/01) | 14 Jan 2025 | BP4A-2 | 45 | Preboring and casing installation
Tue (14/01) | 14 Jan 2025 | TDP12 |  | In progress
Tue (14/01) | 14 Jan 2025 | Near exit 3 |  | RG drilling ongoing for inclinometer installation
Tue (14/01) | 14 Jan 2025 | P20 |  | Kentledge setup in progress
Tue (14/01) | 14 Jan 2025 | P3 |  | No activity for welding due to wet weather
Tue (14/01) | 14 Jan 2025 | TDP12 |  | Reached toe level, waiting for inspection
Tue (14/01) | 14 Jan 2025 | P20-3 |  | Steel plates laying for WLT in progress
Tue (14/01) | 14 Jan 2025 | BR2 |  | Continue roof slab rebar installation and hacking of unsound dwall surface
Tue (14/01) | 14 Jan 2025 | BP2-1 | 27 | Preparing for rebar cage installation
Tue (14/01) | 14 Jan 2025 | BP4A-2 | 45 | Boring CD @ 10m
Tue (14/01) | 14 Jan 2025 | ST213 | Rig 1 | Excavation has just started
Tue (14/01) | 14 Jan 2025 | P11 |  | Post tensioning on going for 22s
Tue (14/01) | 14 Jan 2025 | P16-P17 |  | KTC hacking and hardcore removal works ongoing for stage 2 diversion
Tue (14/01) | 14 Jan 2025 | P18 |  | ATS excavation and soil disposal for RCA backfilling
Tue (14/01) | 14 Jan 2025 | DR1 CH20-35 |  | Continues formwork installation, target to cast it tomorrow
Tue (14/01) | 14 Jan 2025 | P15 |  | Scaffold erection for crosshead rebar works
Tue (14/01) | 14 Jan 2025 | ST129 | Rig 2 | WS endplate removal in progress
Tue (14/01) | 14 Jan 2025 | ST135 | Rig 3 | B2 excavation CD 23/34.4m
Tue (14/01) | 14 Jan 2025 | BRP8 |  | Rebar cage lapping ongoing
Tue (14/01) | 14 Jan 2025 | P18-17 |  | Excavation to subgrade level status. No more activity
Tue (14/01) | 14 Jan 2025 | P15 |  | Scaffold erection continue for rebar installation
Tue (14/01) | 14 Jan 2025 | P14 |  | Section 2 side form preparation for oiling. Tonight to install
Tue (14/01) | 14 Jan 2025 | P11 |  | 11/12 tensioning completed. Last # in progress
Tue (14/01) | 14 Jan 2025 | MH2-10 |  | Clearing materials
Tue (14/01) | 14 Jan 2025 | MH2-9 |  | No activity
Tue (14/01) | 14 Jan 2025 | Exit 3 |  | Clearing access for soil disposal
Tue (14/01) | 14 Jan 2025 | Near gate 5 |  | Hirose mobilised their crane last night. This crane for CCW area
Tue (14/01) | 14 Jan 2025 | DW27 |  | Guidewall cast. Now preparing for DW26 guidewall works
Tue (14/01) | 14 Jan 2025 | Exit 2 |  | Desander status
Tue (14/01) | 14 Jan 2025 | ST196 |  | Guidewall excavation ongoing. Plan for rebar works today
Wed (15/01) | 15 Jan 2025 | MH2-10 |  | Water test just completed
Wed (15/01) | 15 Jan 2025 | MH2-9 |  | Crane wire rope changing
Wed (15/01) | 15 Jan 2025 | BRP8 |  | Concrete casting completed. Now LSS backfilling in progress
Wed (15/01) | 15 Jan 2025 | P20-3 |  | Unloading of steel plates delivery
Wed (15/01) | 15 Jan 2025 | P16 |  | KTC continue drain hacking works for stage 2 diversion
Wed (15/01) | 15 Jan 2025 | TMH3 |  | Excavation in progress
Wed (15/01) | 15 Jan 2025 | Zone 2 |  | Current stockpile status
Wed (15/01) | 15 Jan 2025 | P15 |  | Current status. Pending rebar delivery
Wed (15/01) | 15 Jan 2025 | P14 |  | Shear links installation for section 2-3
Wed (15/01) | 15 Jan 2025 | P13 - RX22602 |  | Manual trial trench in progress for IM installation
Wed (15/01) | 15 Jan 2025 | SPT29 |  | Preparing for 2nd stage SPT
Wed (15/01) | 15 Jan 2025 | P44 |  | Side formwork removal
Wed (15/01) | 15 Jan 2025 | P11 |  | Tendon stressing works ongoing
Wed (15/01) | 15 Jan 2025 | BP4A-2 | 45 | Boring in progress
Wed (15/01) | 15 Jan 2025 | BP2B-2 | 51 | Currently no activity. LSS backfilled yesterday. Plan to resume tmr
Wed (15/01) | 15 Jan 2025 | ST129 |  | Cage A (1/3 ) and Cage B (2/3) cages lowering in progress
Wed (15/01) | 15 Jan 2025 | ST135 |  | Trimming for waterstop end plate removal
Wed (15/01) | 15 Jan 2025 | DR5 |  | Cleaning of lean concrete surface, exposing of coupler and slope formwork in progress
Wed (15/01) | 15 Jan 2025 | DR1 |  | Plan to cast wall today. Now waiting for water level to reduce
Wed (15/01) | 15 Jan 2025 | BC1 |  | Cutter teeth maintenance
Wed (15/01) | 15 Jan 2025 | BP2A-2 | 34 | Preparing for preboring
Wed (15/01) | 15 Jan 2025 | P14 |  | Shear link installation and assembling formwork for closing
Wed (15/01) | 15 Jan 2025 | P11 |  | Set up for post tension work
Wed (15/01) | 15 Jan 2025 | P5 |  | Current status of excavation
Wed (15/01) | 15 Jan 2025 | P39-46 |  | Started boring for JGP grouting
Thu (16/01) | 16 Jan 2025 | P20-3 WLT |  | Steel plates stacking for 12th layer onwards
Thu (16/01) | 16 Jan 2025 | P50 |  | TT done for UKP
Thu (16/01) | 16 Jan 2025 | P17-18 |  | Today to manually expose starhub pipes
Thu (16/01) | 16 Jan 2025 | P15 status |  | No activity
Thu (16/01) | 16 Jan 2025 | P49 |  | JGP left 10 points to complete
Thu (16/01) | 16 Jan 2025 | Zone 2 |  | Current stockpile status
Thu (16/01) | 16 Jan 2025 | P11 |  | Cutting of tendon wires and installation of grouting cap in progress
Thu (16/01) | 16 Jan 2025 | P43 |  | Coring for testing in progress. 1/24nos done
Thu (16/01) | 16 Jan 2025 | ST125 | Rig 2 | B1 excavation 30.4/39.0m
Thu (16/01) | 16 Jan 2025 | BRP58b | Rig 4 | Preparing to start excavation
Thu (16/01) | 16 Jan 2025 | BRP73 | Rig 3 | Preparing to start excavation
Thu (16/01) | 16 Jan 2025 | P6 |  | TT for piling and ERSS work
Thu (16/01) | 16 Jan 2025 | BR1 |  | No activity
Thu (16/01) | 16 Jan 2025 | BR5 |  | Continue surface levelling and cleaning
Thu (16/01) | 16 Jan 2025 | P7 shell area |  | Hoarding to erect next week and start TT
Thu (16/01) | 16 Jan 2025 | Bet. P9-P10 |  | Access making for telco duct works. Today to lean concrete slope and shoring for TMH
Thu (16/01) | 16 Jan 2025 | P3 |  | Welding in progress for s2 layer walers and struts
Thu (16/01) | 16 Jan 2025 | P49 |  | JGP grouting. This week to complete for this pier
Thu (16/01) | 16 Jan 2025 | BR2 |  | Unloading bar chairs and continue rebar works
Thu (16/01) | 16 Jan 2025 | DR1 |  | Preparing to dismantle first lift wall formwork
Thu (16/01) | 16 Jan 2025 | P14 |  | Balance installation of cast in anchor support and segment PT duct verticality alignment
Thu (16/01) | 16 Jan 2025 | TMH3 |  | Preparation for abandoned gas pipe cutting. Slope protection to cast today
Thu (16/01) | 16 Jan 2025 | ST129 |  | Casting in progress
Thu (16/01) | 16 Jan 2025 | BR5 |  | Started laying debonding sheet
Thu (16/01) | 16 Jan 2025 | BR5 |  | Sandbag installation along perimeter
Thu (16/01) | 16 Jan 2025 | BRP58-B | BC4 | Excavation in progress
Thu (16/01) | 16 Jan 2025 | Exit 3 |  | RG rig has shifted here for balance IW installation
Thu (16/01) | 16 Jan 2025 | BP2A-2 | 34 | Boring works at 22m depth
Thu (16/01) | 16 Jan 2025 | BP4A-2 | 45 | Boring works continue at 32.5m
Thu (16/01) | 16 Jan 2025 | BP2B-2 | 51 | Boring works continue at 23m
Thu (16/01) | 16 Jan 2025 | ST213 |  | 1st bite trenching completed. Now teeth replacement to start 2nd bite
Thu (16/01) | 16 Jan 2025 | BR2 |  | Bar chair installation in progress
Thu (16/01) | 16 Jan 2025 | BR5 |  | Excavation until 8pm
Thu (16/01) | 16 Jan 2025 | STN156 |  | Rebar cage lowering, 3/4
Thu (16/01) | 16 Jan 2025 | BRP58B-BC4 |  | 1st bite trenching continue
Thu (16/01) | 16 Jan 2025 | BRP73-BC3 |  | 1st bite trenching continue
Thu (16/01) | 16 Jan 2025 | STN129 |  | Casting in progress. Running volume 207/250 m3
Thu (16/01) | 16 Jan 2025 | STN125-BC2 |  | 1st bite trenching at 33.3m
Thu (16/01) | 16 Jan 2025 | P43 |  | Drilling forJGP point C-26
Fri (17/01) | 17 Jan 2025 | TMH3 |  | Cutting and removal of abandoned gas pipe
Fri (17/01) | 17 Jan 2025 | P5 |  | Excavation to FEL final levelling. Today HSL to mobilise excavator for pile head hacking
Fri (17/01) | 17 Jan 2025 | MH2-10 |  | Clearing materials/equipmen
Fri (17/01) | 17 Jan 2025 | Exit 3 |  | RG drilling ongoing for IW
Fri (17/01) | 17 Jan 2025 | P3 |  | Packing concrete casting
Fri (17/01) | 17 Jan 2025 | BR2 roof slab |  | Debonding surface cleaning ongoing, Continue rebar works, Formwork installation in progress
Fri (17/01) | 17 Jan 2025 | P20-3 |  | Continue steel plates stacking for WLT
Fri (17/01) | 17 Jan 2025 | P16-P18 |  | KTC drain hacking and soil disposal works. ATS RCA backfilling and levelling works in progress
Fri (17/01) | 17 Jan 2025 | P15 |  | No activity. Pending rebar delivery
Fri (17/01) | 17 Jan 2025 | Sewer 3 |  | CCTV will be on Monday
Fri (17/01) | 17 Jan 2025 | P49 |  | Preparing to continue JGP grouting
Fri (17/01) | 17 Jan 2025 | C29 |  | Coring test wittness by CR105
Fri (17/01) | 17 Jan 2025 | ST125 |  | Continue trimming of 2nd bite
Fri (17/01) | 17 Jan 2025 | ST135 |  | 2nd bite, cleaning in progress
Fri (17/01) | 17 Jan 2025 | P9-P10 |  | Slope lean concrete for telco MH works
Fri (17/01) | 17 Jan 2025 | P6 |  | ERSS extraction in progress
Fri (17/01) | 17 Jan 2025 | P14 |  | Adjustment works in progress. Today to cast crosshead
Fri (17/01) | 17 Jan 2025 | ST156 |  | Casting in progress
Fri (17/01) | 17 Jan 2025 | DR1 |  | Formwork closing for invert
Fri (17/01) | 17 Jan 2025 | BR2 |  | Cleaning of soffit and preparing for top bar rebar work
Fri (17/01) | 17 Jan 2025 | ST213 |  | 2nd bite, reached 30m
Fri (17/01) | 17 Jan 2025 | BP45 |  | Preparing for rebar cage lowering
Fri (17/01) | 17 Jan 2025 | P17 |  | Base lean concrete for falsework erection
Fri (17/01) | 17 Jan 2025 | P11 |  | Preparing for tonight dismantling
Fri (17/01) | 17 Jan 2025 | P2 |  | TT for ERSS
Fri (17/01) | 17 Jan 2025 | P5 |  | Excavation status
Fri (17/01) | 17 Jan 2025 | BP45 |  | Preparing for koden checking
Fri (17/01) | 17 Jan 2025 | P49 |  | Platform prepare for next point JGP
Sat (18/01) | 18 Jan 2025 | Zone 4 LA | TPE bound | Lane closure for water pipe laying works. TMA on site
Sat (18/01) | 18 Jan 2025 | P14 |  | Casting was done and now housekeeping and tidy up the area
Sat (18/01) | 18 Jan 2025 | P9-P10 |  | Preparation for teleco manhole
Sat (18/01) | 18 Jan 2025 | P6 |  | ERSS removal. Banksman provided at public area
Sat (18/01) | 18 Jan 2025 | P5 |  | Preparing for pile head hacking
Sat (18/01) | 18 Jan 2025 | P3 |  | Strut end welding
Sat (18/01) | 18 Jan 2025 | P2 |  | TT on going by Woh Hup and LE
Sat (18/01) | 18 Jan 2025 | ST125 |  | Now trimming of waterstop end plate for removal
Sat (18/01) | 18 Jan 2025 | ST135 |  | Cage A ( 3/3) and Cage B (1/2) cages lowered down. Today to cast
Sat (18/01) | 18 Jan 2025 | BC3 & BC4 |  | Both rig cutter teeth maintenace
Sat (18/01) | 18 Jan 2025 | BR5 |  | Cleaning of the base and prepare for base slab rebar work
Sat (18/01) | 18 Jan 2025 | BR2 |  | Top bar work in progress
Sat (18/01) | 18 Jan 2025 | BP45 |  | Preparation for test pile
Sat (18/01) | 18 Jan 2025 | P17 |  | Adjusting of hoarding for falswork erection
Sat (18/01) | 18 Jan 2025 | P11 |  | Continue dismantling of soffit plywood and falsework
Sat (18/01) | 18 Jan 2025 | P3 |  | No activity already
Sat (18/01) | 18 Jan 2025 | P5 |  | Pile head hacking
Sat (18/01) | 18 Jan 2025 | ST213 |  | 2nd bite, reached 35m
Sat (18/01) | 18 Jan 2025 | BR5 |  | Top bar installation and side formwork closing
Sat (18/01) | 18 Jan 2025 | BRP73 |  | Now cutter teeth changing
Sat (18/01) | 18 Jan 2025 | DR1 |  | Formwork closing for LSS backfilling
Sat (18/01) | 18 Jan 2025 | Exit 3 |  | Slope protection casting ongoing
Sat (18/01) | 18 Jan 2025 | P15 |  | Currently no activity
Sat (18/01) | 18 Jan 2025 | P11 |  | Dismantling works ongoing
Sat (18/01) | 18 Jan 2025 | P20, CCW |  | No more activity
Sat (18/01) | 18 Jan 2025 | ST213 | BC1 | B2 CD 36/42.4m. Now cutter flap changing ongoing & setting up another noise balloon
Sat (18/01) | 18 Jan 2025 | BR2 |  | Continue roof slab top rebar works. Overall status 60% completed
Sat (18/01) | 18 Jan 2025 | P49 |  | JGP 100% completed. Up to date: P49 & P50 JGP grouting completed
Sat (18/01) | 18 Jan 2025 | BRP58-B | BC4 | B1 completed. B2 temporarily stopped for suction line rectification works
Sat (18/01) | 18 Jan 2025 | BRP73 | BC3 | B1 completed. Cutter teeth changing ongoing
Sat (18/01) | 18 Jan 2025 | ST135 |  | Tremie pipe lowering in progress
Sat (18/01) | 18 Jan 2025 | ST125 | BC2 | B3 in progress
Sat (18/01) | 18 Jan 2025 | BP51 |  | Boring reached 27m
Sat (18/01) | 18 Jan 2025 | BP34 |  | Boring reached, 31m
Sun (19/01) | 19 Jan 2025 | BRP58B-BC4 |  | 2nd bite trenching at 12m
Sun (19/01) | 19 Jan 2025 | BRP73-BC3 |  | Cutter wheel teeth replacement
Sun (19/01) | 19 Jan 2025 | STN125-BC2 |  | Cutter wheel teeth replacement
Sun (19/01) | 19 Jan 2025 | P43 |  | Today GCE to do preparation only for JGP testing tomorrow
Sun (19/01) | 19 Jan 2025 | Zone 4 |  | Today only soil disposal to KTC dumping ground
Sun (19/01) | 19 Jan 2025 | MH2-10 |  | Benching works
Sun (19/01) | 19 Jan 2025 | Zone 4 LA |  | Water pipe laying in progress
Sun (19/01) | 19 Jan 2025 | BR2 |  | Top bars installation continue
Sun (19/01) | 19 Jan 2025 | BR5 |  | Excavation and soil disposal continue to 5pm
Sun (19/01) | 19 Jan 2025 | ST213 |  | B2 in progress
Sun (19/01) | 19 Jan 2025 | BR2 |  | Continue top bar installation
Sun (19/01) | 19 Jan 2025 | P43 |  | C31 coring done for testing tomorrow
Sun (19/01) | 19 Jan 2025 | P13-14 |  | RG TT for tunnel IM installation
Sun (19/01) | 19 Jan 2025 | P13 |  | Material clearing to prepare ground for lean concrete
Sun (19/01) | 19 Jan 2025 | StN213 |  | Current at 2nd bite, teeth replacement
Mon (20/01) | 20 Jan 2025 | P44 |  | Preparing for NDT test
Mon (20/01) | 20 Jan 2025 | P15 |  | Crosshead rebar installation. Est 20% completed
Mon (20/01) | 20 Jan 2025 | BR2 |  | Continue roof slab rebar works and formwork installation. About 75% completed
Mon (20/01) | 20 Jan 2025 | BR5 |  | RGT installation
Mon (20/01) | 20 Jan 2025 | BRP58B | Rig 4 | B2 CD 26.5/30.3m, teeth replacement in progress
Mon (20/01) | 20 Jan 2025 | BRP73 | Rig 3 | B2 CD 22.9/28.2m
Mon (20/01) | 20 Jan 2025 | ST130 | Rig 2 | Ready to start excavation
Mon (20/01) | 20 Jan 2025 | Exit 3 |  | IW installation in progress
Mon (20/01) | 20 Jan 2025 | P50 |  | Continue TT for preboring
Mon (20/01) | 20 Jan 2025 | P51 |  | 1st point JGP in progress
Mon (20/01) | 20 Jan 2025 | ST125 |  | Water stop end plate lowering down
Mon (20/01) | 20 Jan 2025 | ST130 |  | 1st bite, started excavation
Mon (20/01) | 20 Jan 2025 | BC3& BC4 |  | Cutter teeth changing
Mon (20/01) | 20 Jan 2025 | BR5 |  | Slope protection casting and exposing of coupler
Mon (20/01) | 20 Jan 2025 | DR1 |  | CJ roughening
Mon (20/01) | 20 Jan 2025 | BR2 |  | Cleaning of soffit and top bar installation
Mon (20/01) | 20 Jan 2025 | BP2B-2-51 |  | Boring reached 31m
Mon (20/01) | 20 Jan 2025 | BP45 |  | LSS backfilling
Mon (20/01) | 20 Jan 2025 | BP42 |  | Boring reached 8M
Mon (20/01) | 20 Jan 2025 | P15 |  | Cross head rebar work
Mon (20/01) | 20 Jan 2025 | P11 |  | Current status of falsework dismantling
Mon (20/01) | 20 Jan 2025 | P3 |  | Tomorrow to start excavation
Mon (20/01) | 20 Jan 2025 | P5 |  | Current status of pile hacking
Tue (21/01) | 21 Jan 2025 | P15 |  | Tendon and rebar installation in progress
Tue (21/01) | 21 Jan 2025 | Near exit 2 |  | Ground levelling and arranging steel plates
Tue (21/01) | 21 Jan 2025 | BR2 |  | Continue shearlinks installation, Formwork installation, 1m retaining wall rebar works ongoing, Cleaning works ongoing
Tue (21/01) | 21 Jan 2025 | BR5 |  | Currently no roof slab activity
Tue (21/01) | 21 Jan 2025 | BR5 |  | Slope trimming and disposal ongoing
Tue (21/01) | 21 Jan 2025 | BRP58B | BC4 | B2 temporarily stopped. Cutter teeth changing ongoing
Tue (21/01) | 21 Jan 2025 | BRP73 | BC3 | B2 temporarily stopped. Cutter teeth changing ongoing
Tue (21/01) | 21 Jan 2025 | DW83 |  | Guidewall cast
Tue (21/01) | 21 Jan 2025 | ST130 | BC2 | B1 in progress, 23.5/34.3m
Tue (21/01) | 21 Jan 2025 | P50 |  | Trial trench for UP50-10
Tue (21/01) | 21 Jan 2025 | P51 |  | Currently no JGP activity
Tue (21/01) | 21 Jan 2025 | ST125 |  | Rebar cage lapping
Tue (21/01) | 21 Jan 2025 | MH2-9 |  | Currently no activity
Tue (21/01) | 21 Jan 2025 | P20-3 |  | WLT continue setting up works. To start testing tmr
Tue (21/01) | 21 Jan 2025 | BP2A-2 | 34 | Boring CD 37.0/42.21m
Tue (21/01) | 21 Jan 2025 | BP4A-2 | 42 | Boring CD 18.0/35.785m
Tue (21/01) | 21 Jan 2025 | BP2-2B | 51 | Boring CD 33.5/37.501m
Tue (21/01) | 21 Jan 2025 | ST213 | Rig 1 | Waterstop trimming has resumed
Tue (21/01) | 21 Jan 2025 | P16-P18 |  | Continue RCA backfilling and compaction works
Tue (21/01) | 21 Jan 2025 | P15-P16 |  | Drain hacking and hardcore disposal works
Tue (21/01) | 21 Jan 2025 | P15 |  | Crosshead rebars and tendon ducts installation in progress
Tue (21/01) | 21 Jan 2025 | DR1 CH35-20 |  | Preparing falsework materials for 2nd lift works and roof slab
Tue (21/01) | 21 Jan 2025 | BR2 |  | Continue rebar works for 1m retaining wall, Shearlinks and coupler rebars installation, 4nos thermocouples have been installed. Wiring works ongoing
Tue (21/01) | 21 Jan 2025 | P30 |  | 2nos RC stumps cast yesterday
Tue (21/01) | 21 Jan 2025 | Exit 3 |  | Excavation in progress
Tue (21/01) | 21 Jan 2025 | BRP58B | Rig 4 | B2 CD 28.3/30.3m
Tue (21/01) | 21 Jan 2025 | BRP73 | Rig 3 | B2 CD 23.0/28.2m, teeth replacement in progress
Tue (21/01) | 21 Jan 2025 | ST130 | Rig 2 | B1 excavation 24.5/34.3m, teeth replacement in progress
Tue (21/01) | 21 Jan 2025 | ST125 |  | Rebar cage installation in progress
Tue (21/01) | 21 Jan 2025 | P20 |  | Continue kentledge setup works
Tue (21/01) | 21 Jan 2025 | P17 |  | Hoarding panel rectification ongoing
Tue (21/01) | 21 Jan 2025 | P15 |  | Continue crosshead rebar works and tendon ducts installation
Tue (21/01) | 21 Jan 2025 | P11 |  | Continue dismantling of leg frame falsework
Tue (21/01) | 21 Jan 2025 | TMH3 |  | Activity done for the day
Tue (21/01) | 21 Jan 2025 | BR2 |  | Continue roof slab rebar works. Tmr plan to install additional rebars as per eAC comments
Tue (21/01) | 21 Jan 2025 | Exit 3 |  | Current status of excavation. Access installation in progress for IM monitoring
Tue (21/01) | 21 Jan 2025 | P16 |  | RG drilling for tunnel IM
Tue (21/01) | 21 Jan 2025 | Zone 3 |  | Hirose excavator mobilisation
Tue (21/01) | 21 Jan 2025 | Exit 3 |  | Soil and hardcore disposal ongoing, Hacking at capping beam areas ongoing
Wed (22/01) | 22 Jan 2025 | BR2 |  | Cleaning ongoing, Shearlinks installation, Corrugated pipes installation
Wed (22/01) | 22 Jan 2025 | DR1 CH35-20 |  | LE removing strut to facilitate next lift
Wed (22/01) | 22 Jan 2025 | BP2A-2 | 34 | Boring CD 38.0/42.21m
Wed (22/01) | 22 Jan 2025 | BP4A-2 | 42 | Boring CD 26.0/35.785m
Wed (22/01) | 22 Jan 2025 | BP2-2B | 51 | Boring CD 37.0/37.501m
Wed (22/01) | 22 Jan 2025 | ST213 |  | Waterstop installation in progress
Wed (22/01) | 22 Jan 2025 | BR5 |  | Cleaning ongoing and RGT installation
Wed (22/01) | 22 Jan 2025 | BRP58B | Rig 4 | B2 CD 28.5/30.3m, teeth replacement in progress
Wed (22/01) | 22 Jan 2025 | BRP73 | Rig 3 | B2 CD 23.0/28.2m, teeth replacement in progress
Wed (22/01) | 22 Jan 2025 | ST130 | Rig 2 | B2 excavation started, CD 4.0/ 34.3m
Wed (22/01) | 22 Jan 2025 | ST213 |  | Rebar cage lapping in progress
Wed (22/01) | 22 Jan 2025 | DR1 |  | LE demobilising ERSS materials
Wed (22/01) | 22 Jan 2025 | DR1 |  | CGS preparing for next lift
Wed (22/01) | 22 Jan 2025 | BR5 |  | Preparing for slope protection casting
Wed (22/01) | 22 Jan 2025 | Exit 3 |  | Hacking of capping beam ongoing
Wed (22/01) | 22 Jan 2025 | Exit 3 |  | Current status of excavation
Wed (22/01) | 22 Jan 2025 | P20 |  | Kentledge test on going
Wed (22/01) | 22 Jan 2025 | BP2A-2 | 34 | Boring reached 41/42.21m
Wed (22/01) | 22 Jan 2025 | BP4A-2 | 42 | Boring in progress, BP2B-2(51): Preparing for KP installation
Wed (22/01) | 22 Jan 2025 | BC1 |  | Parked at DW27. Now teeth replacing before start excavation
Wed (22/01) | 22 Jan 2025 | Exit 3 |  | Debris cleaning and hacking ongoing at capping beam area
Wed (22/01) | 22 Jan 2025 | BR5 |  | Slope protection casting in progress
Wed (22/01) | 22 Jan 2025 | BR2 |  | Continue shearlinks installation
Wed (22/01) | 22 Jan 2025 | BRP58-B | BC4 | B2 CD 29.3/30.3m. Cutter teeth changing ongoing
Wed (22/01) | 22 Jan 2025 | BRP73 |  | Preparing for chiselling. B2 CD 23.1/28.2m
Wed (22/01) | 22 Jan 2025 | ST130 | BC2 | B1 in progress, 19.2/34.3m
Wed (22/01) | 22 Jan 2025 | P43 GCE |  | Continue trial trench, SPT34 (stage 1) temporarily stopped due to pump issue
Wed (22/01) | 22 Jan 2025 | DW27 |  | Start excavation
Thu (23/01) | 23 Jan 2025 | P20-3 WLT 2nd cycle |  | Loading @ 100% in progress
Thu (23/01) | 23 Jan 2025 | P51 |  | Current status of grouting done
Thu (23/01) | 23 Jan 2025 | P51 |  | Continue grouting of JGP work
Thu (23/01) | 23 Jan 2025 | P16-P18 |  | Continue RCA backfilling and compaction works
Thu (23/01) | 23 Jan 2025 | P16 |  | RX227002 IM installation completed. Preparing for reinstate and shift to next RX location
Thu (23/01) | 23 Jan 2025 | Bet. P15-P16 |  | Soil disposal and hardcores hacking works
Thu (23/01) | 23 Jan 2025 | P15 |  | Continue rebar and tendon duct installation
Thu (23/01) | 23 Jan 2025 | Zone 2 |  | Current stockpile status
Thu (23/01) | 23 Jan 2025 | BP2B-2 | 51 | Completed. Last evening KP installation and casting
Thu (23/01) | 23 Jan 2025 | DR1 |  | Continue 2nd lift wall formwork
Thu (23/01) | 23 Jan 2025 | BR5 |  | Started bottom rebar layin
Thu (23/01) | 23 Jan 2025 | DW27 | BC4 | B1 in progress, 31/32.7m
Thu (23/01) | 23 Jan 2025 | P44 |  | Final layer backfilling today. Plan to cast prop concrete also
Thu (23/01) | 23 Jan 2025 | P14 |  | Preparation for formwork removal
Thu (23/01) | 23 Jan 2025 | TMH-3 |  | Formwork closing for 1st layer wall casting
Thu (23/01) | 23 Jan 2025 | P6 |  | ERSS shifting in progress
Thu (23/01) | 23 Jan 2025 | P6-2 |  | Lane closed for traffic light pipe laying. Premix hacking ongoing
Thu (23/01) | 23 Jan 2025 | P5 |  | Bottom rebar installation for pile cap in progress
Thu (23/01) | 23 Jan 2025 | P3 |  | Excavation to FEL
Thu (23/01) | 23 Jan 2025 | P2 |  | Trial trench works and platform preparation for preboring
Thu (23/01) | 23 Jan 2025 | N4-N5 |  | Hackingbof drain and old pavement continue
Thu (23/01) | 23 Jan 2025 | P51 |  | 2nd point grouting for today
Thu (23/01) | 23 Jan 2025 | P15 |  | Section 1 PT duct inspection completed. Now links installation. Plan to close formwork tonight. Section 2 and 3 PT duct installation in progress, inspection plan tomorrow
Thu (23/01) | 23 Jan 2025 | P14-13 |  | RG preparing for drilling
Thu (23/01) | 23 Jan 2025 | TMH3 |  | Formwork closed and inspection completed. Concrete ordered for casting
Thu (23/01) | 23 Jan 2025 | BP2A-2 | 34 | Rebar cage lowering
Thu (23/01) | 23 Jan 2025 | BP4A-2 | 42 | Boring in progress, 31/35.7m
Thu (23/01) | 23 Jan 2025 | ST213 |  | Casting in progress, 169/260m3
Fri (24/01) | 24 Jan 2025 | P50 |  | TT on going for soldier pile preboring
Fri (24/01) | 24 Jan 2025 | P51 |  | 10th point JGP grouting in progress
Fri (24/01) | 24 Jan 2025 | Exit 3 |  | Stockpile status
Fri (24/01) | 24 Jan 2025 | P20-3 |  | WLT completed. Now unloading steel plates and demobilisation works
Fri (24/01) | 24 Jan 2025 | P17-P18 |  | RCA backfilling and compaction works ongoing
Fri (24/01) | 24 Jan 2025 | N4 |  | Drain hacking and hardcores removal for TD stage 2 in progress
Fri (24/01) | 24 Jan 2025 | DR1 |  | Falsework installation for roof slab
Fri (24/01) | 24 Jan 2025 | BR5 |  | Bottom rebar installation
Fri (24/01) | 24 Jan 2025 | BRP58B | BC4 | B3 in progress, 20/30.3m
Fri (24/01) | 24 Jan 2025 | P15 |  | Tendon duct installation for section 3 and section 1 preparation for formwork clsoing
Fri (24/01) | 24 Jan 2025 | Near P14 |  | IM RX226002 drilling in progress
Fri (24/01) | 24 Jan 2025 | P14 |  | No activity
Fri (24/01) | 24 Jan 2025 | TMH-3 |  | 1st layer wall cast yesterday. Formwork dismantled
Fri (24/01) | 24 Jan 2025 | P6-1 |  | Continue ERSS shifting works
Fri (24/01) | 24 Jan 2025 | P6-1 |  | Premix hacking for traffic light pipe laying in progress
Fri (24/01) | 24 Jan 2025 | P5 |  | Pile cap rebar installation ongoing
Fri (24/01) | 24 Jan 2025 | P2 |  | Preboring in progress for ERSS installation. 1 no. completed
Fri (24/01) | 24 Jan 2025 | P3 |  | Excavation to FEL ongoing
Fri (24/01) | 24 Jan 2025 | P50 |  | Shifting of access for preboring TT for soldier pile. One point finish as of this morning
Fri (24/01) | 24 Jan 2025 | P51 |  | 2nd point JGP on going for today
Fri (24/01) | 24 Jan 2025 | BR2 casting |  | G50: 3.5m3 completed, Waterproofing concrete: 18/140m3, G40: 52/1090m3
Fri (24/01) | 24 Jan 2025 | BRP58B |  | B3 temporarily stopped. Rectification ongoing for damaged desander pump rubber. Depth 24.3/30.3m
Fri (24/01) | 24 Jan 2025 | P16-P17 |  | RCA backfilling and compaction
Fri (24/01) | 24 Jan 2025 | Zone 2 |  | Stockpile current status
Fri (24/01) | 24 Jan 2025 | N3-N4 |  | Drain hacking and soil/hardcores disposal works
Fri (24/01) | 24 Jan 2025 | Near P14 |  | IM RX226002 continue drilling works
Fri (24/01) | 24 Jan 2025 | P10 |  | New IM rig mobilized for RX installation
Fri (24/01) | 24 Jan 2025 | TMH-3 |  | Backfilling for next layer wall works
Fri (24/01) | 24 Jan 2025 | BRP73 | BC3 | B2 temporarily stopped. Cutter gearbox rectification in progress
Fri (24/01) | 24 Jan 2025 | P6-1 |  | ERSS shifting works
Fri (24/01) | 24 Jan 2025 | Near P6-1 |  | Manual excavation for trafflic light pipe laying
Fri (24/01) | 24 Jan 2025 | P5 |  | Pile cap rebar works
Fri (24/01) | 24 Jan 2025 | P3 |  | Excavation to FEL
Fri (24/01) | 24 Jan 2025 | P2 |  | Preboring for ERSS installation ongoing, 2 nos. completed
Fri (24/01) | 24 Jan 2025 | BR2 casting |  | G50: 3.5/3.5m3, G40WP: 54/140m3, G40: 141/1090m3, Total vol: 198.5/1233.5m3
Fri (24/01) | 24 Jan 2025 | P44 |  | Column rebar work started. Today will do prop concrete casting too
Fri (24/01) | 24 Jan 2025 | DW82 |  | Preparing to remove premix for guidewall work
Fri (24/01) | 24 Jan 2025 | ST130 |  | Desanding in progress
Fri (24/01) | 24 Jan 2025 | BC cutter 3 |  | Cutter wheel maintenance
Fri (24/01) | 24 Jan 2025 | DR1 |  | Hollow section placing for top slab work
Fri (24/01) | 24 Jan 2025 | BR2 |  | Casting in progress, batch out 487/ 1200m3
Fri (24/01) | 24 Jan 2025 | BP42 |  | Boring reached 34m/35.8m. Tomorrow to cast
Fri (24/01) | 24 Jan 2025 | BP34 |  | Casting completed
Fri (24/01) | 24 Jan 2025 | P26 |  | Seongha prepare to park Fissure grouting rig for grouting work
Fri (24/01) | 24 Jan 2025 | P15 |  | Tendom duct inspection by RTO
Fri (24/01) | 24 Jan 2025 | BR2 casting |  | G50: 3.5/3.5m3, G40WP: 112.5/140m3, G40: 358/1090m3, Total vol: 474/1233.5m3
Fri (24/01) | 24 Jan 2025 | BR2 casting |  | G50: 3.5/3.5m3, G40WP: 121.5/140m3, G40: 454.5/1090m3, Total vol: 578.5/1233.5m3
Fri (24/01) | 24 Jan 2025 | BR2 casting |  | G50: 3.5/3.5m3, G40WP: 148/140m3, G40: 570/1090m3, Total vol: 721.5/1233.5m3
Sat (25/01) | 25 Jan 2025 | P43 |  | Area preparation for JGP
Sat (25/01) | 25 Jan 2025 | TMH3 |  | Wall formwork and preparation works ongoing for top slab
Sat (25/01) | 25 Jan 2025 | P6 junction |  | Bus lane closure at right turn lane for traffic light pipe laying works
Sat (25/01) | 25 Jan 2025 | STN130 |  | Casting in progress
Sat (25/01) | 25 Jan 2025 | P5 |  | Rebar works in progress
Sat (25/01) | 25 Jan 2025 | P3 |  | Excavation in progress
Sat (25/01) | 25 Jan 2025 | P2 |  | Preboring ongoing for ERSS works
Sat (25/01) | 25 Jan 2025 | Zone 1 LA | TPE bound | Singtel lane closure
Sat (25/01) | 25 Jan 2025 | BRP65-BC3 |  | B1 excavation on going, 27.5m
Sat (25/01) | 25 Jan 2025 | STN155 |  | Excavation resume, BRP58B: rebar cage installed
Sat (25/01) | 25 Jan 2025 | Exit 3 |  | Continue excavation
Sat (25/01) | 25 Jan 2025 | Exit 3 DW21-23 |  | Surface inspection was done for capping beam works, WH erecting access for instrument monitoring
Sat (25/01) | 25 Jan 2025 | BP4A-2 | 42 | Today plan for casting, Along LVC area: Continue fissure grouting and recharge well works
Sat (25/01) | 25 Jan 2025 | DR1 |  | Top slab formwork in progress. Target to cast balance wall and top slab on Monday
Sat (25/01) | 25 Jan 2025 | P43 |  | SPT coring tests ongoing
Sat (25/01) | 25 Jan 2025 | P44 |  | Currently no activity
Sat (25/01) | 25 Jan 2025 | P51-27 |  | JGP in progress
Sat (25/01) | 25 Jan 2025 | ST130 |  | Rebar cage lapping in progress
Sat (25/01) | 25 Jan 2025 | BR2 |  | Casting of last truck
Sat (25/01) | 25 Jan 2025 | MH2-10 |  | Manhole rebars on site. Currently no activity. Plan to resume tmr
Sat (25/01) | 25 Jan 2025 | MH2-9 |  | No activity currently
Sat (25/01) | 25 Jan 2025 | BR2 |  | Curing compound application
Sat (25/01) | 25 Jan 2025 | DW82-81 | half | Guidewall excavation in progress
Sat (25/01) | 25 Jan 2025 | BP2B-1 | 55 | Preboring and casing installed
Sat (25/01) | 25 Jan 2025 | BRP58B |  | Rebar cage lapping in progress
Sat (25/01) | 25 Jan 2025 | BR5 |  | Slope trimming, Roof slab rebar works in progress, 20%
Sat (25/01) | 25 Jan 2025 | BP2-2 | 29 | Preboring
Sat (25/01) | 25 Jan 2025 | Exit 3 |  | Pile hacking ongoing
Sat (25/01) | 25 Jan 2025 | P20 |  | Continue demobilising kentledge steel plates
Sat (25/01) | 25 Jan 2025 | P15 |  | Balance links and trimmer bar installation at section 3. Plan to install formwork tonight. Scheduled to cast on monday
Sat (25/01) | 25 Jan 2025 | P5 pile cap |  | Balance links installation. Scheduled to cast on Monday
Sat (25/01) | 25 Jan 2025 | Exit 3 |  | WH to work late to complete lean concrete. Tomorrow CGW to construct capping beam here. Est length 16m
Sat (25/01) | 25 Jan 2025 | DW27 |  | Final koden test
Sat (25/01) | 25 Jan 2025 | BP4A-2 | 42 | Area preparation for casting
Sat (25/01) | 25 Jan 2025 | P20 |  | Kentledge steel plates demobilisation
Sat (25/01) | 25 Jan 2025 | Between P15 and N4 |  | Excavation ongoing for stage 2 diversion
Sat (25/01) | 25 Jan 2025 | P15 |  | Shearlinks installation
Sat (25/01) | 25 Jan 2025 | Near P14 |  | RG drilling ongoing for rod extensometer (RX226002) installation. Today plan to complete
Sat (25/01) | 25 Jan 2025 | Near P10 |  | RG 2nd rig preparation works for rod extensometer (RX222002)
Sun (26/01) | 26 Jan 2025 | P15 |  | Crosshead section 3 formwork closing now
Sun (26/01) | 26 Jan 2025 | DW27 |  | Final koden test completed. Crane shifted for rebar installation
Sun (26/01) | 26 Jan 2025 | STN155 |  | 1st bite trenching continue, BRP58B: rebar cage installed, Tremie pipe installation in progress
Sun (26/01) | 26 Jan 2025 | BRP65-BC3 |  | B1 excavation completed. Cutter body hoist up for maintenance
Sun (26/01) | 26 Jan 2025 | P43 |  | JGP completed for the night. Housekeeping
Mon (27/01) | 27 Jan 2025 | P50 |  | Backfilling of completed TT for preboring
Mon (27/01) | 27 Jan 2025 | P51 |  | Continue JGP. Total completed 17 points as of last week
Mon (27/01) | 27 Jan 2025 | P44 |  | Column stump rebar inspection for formwork closing
Mon (27/01) | 27 Jan 2025 | MH2-10 |  | Preparing rebar works for base slab
Mon (27/01) | 27 Jan 2025 | ST196 | BC1 | Currently no activity
Mon (27/01) | 27 Jan 2025 | DR1 |  | Today plan for top slab and 2nd lift wall casting
Mon (27/01) | 27 Jan 2025 | Zone 1 junction |  | Hacking for traffic pipe laying
Mon (27/01) | 27 Jan 2025 | BR2 |  | Prop support dismantling
Mon (27/01) | 27 Jan 2025 | P25 |  | Trial trench in progress for recharge well
Mon (27/01) | 27 Jan 2025 | P5 |  | Final inspection completed for casting
Mon (27/01) | 27 Jan 2025 | BR5 |  | Roof slab rebar works in progress
Mon (27/01) | 27 Jan 2025 | BR5 |  | KP area preparing to install shoring for further works
Mon (27/01) | 27 Jan 2025 | BR5 |  | Slope trimming almost completed. Thereafter to lean con today
Mon (27/01) | 27 Jan 2025 | Zone 1 junction |  | Continue hacking and installation of traffic cable pipes
Mon (27/01) | 27 Jan 2025 | P6 |  | RG mobilisation of rig for tunnel IM installation
Mon (27/01) | 27 Jan 2025 | P13 |  | Rebar mesh installation. Casting later at 530pm
Mon (27/01) | 27 Jan 2025 | P15 crosshead |  | Concrete pump set up for casting. Level peg installation in progress
Mon (27/01) | 27 Jan 2025 | P16 |  | Premix hacking for bus stop construction
Mon (27/01) | 27 Jan 2025 | P51 |  | 2nd point grouting done for today. Prepare for 3rd point
Mon (27/01) | 27 Jan 2025 | P49 |  | 1st point TT for soldier pile preboring. P50 all TT done for soldier pile
Mon (27/01) | 27 Jan 2025 | ST155 | BC4 | B1 in progress, 27.2/34m
Mon (27/01) | 27 Jan 2025 | BRP65 | BC3 | Cutter body washing. B2 completed
Mon (27/01) | 27 Jan 2025 | DW82 |  | Guidewall excavation in progress
Mon (27/01) | 27 Jan 2025 | ST124 | BC2 | Cutter teeth changing ongoing
Mon (27/01) | 27 Jan 2025 | BRP73 |  | Currently no activity. To resume after BRP65 (BC3) complete cleaning/desanding
Mon (27/01) | 27 Jan 2025 | DR1 |  | Shearlinks installation
Mon (27/01) | 27 Jan 2025 | Exit 2 |  | Dongah hacking ongoing for bentonite pipe alignment
Mon (27/01) | 27 Jan 2025 | BP4A-2 | 42 | LSS backfill in progress
Mon (27/01) | 27 Jan 2025 | BP2-2 | 29 | No activity. Boring works will resume on friday
Mon (27/01) | 27 Jan 2025 | Exit 3 |  | Slope trimming and erection of step ladder access
Mon (27/01) | 27 Jan 2025 | P20 |  | Continue demobilising kentledge steel mats
Mon (27/01) | 27 Jan 2025 | P15 |  | Concrete pump setup for crosshead casting. Plan for casting ard 8pm
Mon (27/01) | 27 Jan 2025 | P14 |  | Formwork dismantling
Mon (27/01) | 27 Jan 2025 | P5 |  | Pile cap casting in progress, 100/355m3. Now waiting for next concrete truck
Mon (27/01) | 27 Jan 2025 | P20, CCW |  | No more activity. HSL housekeeping ongoing
Mon (27/01) | 27 Jan 2025 | DR1 |  | Top slab, 2nd lift wall cleaning ongoing. Concrete pump already on site for casting
Mon (27/01) | 27 Jan 2025 | BR5 |  | Slope protection lean con completed
Mon (27/01) | 27 Jan 2025 | Exit 3 |  | No more activity
Tue (28/01) | 28 Jan 2025 | P51 |  | Continue grouting of JGP
Tue (28/01) | 28 Jan 2025 | P16 |  | ATS Premix clearing for bus stop preparation works
Tue (28/01) | 28 Jan 2025 | ST124 | BC2 | B2 in progress, 26/39m
Tue (28/01) | 28 Jan 2025 | DW116 |  | Guidewall excavation
Tue (28/01) | 28 Jan 2025 | DW82 |  | Guidewall construction in progress
Tue (28/01) | 28 Jan 2025 | BRP65 |  | Casting in progress
Tue (28/01) | 28 Jan 2025 | BR5 |  | Roof slab rebar works in progress
Tue (28/01) | 28 Jan 2025 | BR5 |  | Slope protection completed yesterday. Now barricade and toe boards installation
Tue (28/01) | 28 Jan 2025 | P14 |  | Scaffold erection for tendon-stressing works
Tue (28/01) | 28 Jan 2025 | TMH-3 |  | Formwork closing for 2nd layer wall
Tue (28/01) | 28 Jan 2025 | BC3, BC4 |  | No activity, ST155: Pending LSS backfill
Tue (28/01) | 28 Jan 2025 | P43 |  | Two team doing testing for JGP
Tue (28/01) | 28 Jan 2025 | P44 |  | Waiting for concrete for stump casting
Tue (28/01) | 28 Jan 2025 | Exit 3 | near gate 5 | Backfilling ongoing at capping beam area
Tue (28/01) | 28 Jan 2025 | MH2-10 |  | Base slab rebar lowered
Tue (28/01) | 28 Jan 2025 | MH2-9 |  | Access installation
Tue (28/01) | 28 Jan 2025 | BRP73-BC3 |  | Cutter wheel teeth replacement
Tue (28/01) | 28 Jan 2025 | STN124-BC2 |  | 2nd bite trenching continue
Tue (28/01) | 28 Jan 2025 | P43 |  | Grouting completed. Pipe extraction in progress
Tue (28/01) | 28 Jan 2025 | Zone 4 |  | Water pipe laying in progress. Today 16.5m laid
Tue (28/01) | 28 Jan 2025 | MH2-10 |  | Base slab rebar works in progress
Tue (28/01) | 28 Jan 2025 | ST196 | BC1 | No activity
Tue (28/01) | 28 Jan 2025 | BR1, BR2 |  | No activity
Tue (28/01) | 28 Jan 2025 | DR1 |  | Casting completed
Thu (30/01) | 30 Jan 2025 | Zone 2 |  | 2 locations RG doing TT for Tunnel IM installation
Thu (30/01) | 30 Jan 2025 | Zone 1 |  | Slope backfilling and compaction at P2. Completed
Thu (30/01) | 30 Jan 2025 | STN124 |  | B2 excavation in progress, CD - 37.2m/39m
Thu (30/01) | 30 Jan 2025 | BRP73 |  | 2nd bite trenching at 26m depth
Thu (30/01) | 30 Jan 2025 | BR5 |  | Top bars installation
Thu (30/01) | 30 Jan 2025 | STN124 |  | 2nd bite trenching completed. Trimming started
Thu (30/01) | 30 Jan 2025 | BRP73-BC3 |  | Teeth replacement, current at 2nd bite 27.1m
Thu (30/01) | 30 Jan 2025 | BR5 |  | Top bars installation continue
Thu (30/01) | 30 Jan 2025 | BR2 |  | Wall formwork closing
Thu (30/01) | 30 Jan 2025 | Sewer diversion location 1 |  | Sewer waste that leaked already pump out
Fri (31/01) | 31 Jan 2025 | BR5 |  | Continue rebar installation and coupler tightening
Fri (31/01) | 31 Jan 2025 | P51 |  | JGP grouting done as of now
Fri (31/01) | 31 Jan 2025 | ST155 | BC4 | No activity
Fri (31/01) | 31 Jan 2025 | BRP73 | BC3 | Cutter maintenance ongoing
Fri (31/01) | 31 Jan 2025 | DW82 |  | Guidewall formwork dismantling
Fri (31/01) | 31 Jan 2025 | P44 |  | Formwork removal for stump
Fri (31/01) | 31 Jan 2025 | P20 |  | Unloading of steel plates continue
Fri (31/01) | 31 Jan 2025 | P49 |  | TT for soldier pile preboring
Fri (31/01) | 31 Jan 2025 | P50 |  | Excavation for water pipe laying
Fri (31/01) | 31 Jan 2025 | P51 |  | One point grouting done. Platform prepare for 2nd point grouting
Fri (31/01) | 31 Jan 2025 | P14-13 |  | Old pavement hacking
Fri (31/01) | 31 Jan 2025 | BR5 |  | Continue roof slab rebar works
Fri (31/01) | 31 Jan 2025 | BRP73 |  | B2 CD 27.3/28.2m. Now cutter teeth changing
Fri (31/01) | 31 Jan 2025 | BC4 |  | No activity
Fri (31/01) | 31 Jan 2025 | P14 |  | Polyfoam removal to expose anchor head for PT
Fri (31/01) | 31 Jan 2025 | ST124 | BC2 | WS trimming to extract endplate. Now trying to extract
Fri (31/01) | 31 Jan 2025 | BR2 |  | Removing barricade for retaining wall works
Fri (31/01) | 31 Jan 2025 | DR1 |  | Formwork removal ongoing
Fri (31/01) | 31 Jan 2025 | S3 |  | Secondary beam installation
Fri (31/01) | 31 Jan 2025 | Zone 1 Junction |  | Eng Hup cable pulling for stage 2 TD
Fri (31/01) | 31 Jan 2025 | BP2B-1, 1600mm dia | 55 | Boring in progress, 19/35.53m
Fri (31/01) | 31 Jan 2025 | BP2-2, 2500mm dia | 29 | Boring in progress, 10/36.35m
Fri (31/01) | 31 Jan 2025 | P5 |  | Formwork dismantling and surface chipping for stump
Fri (31/01) | 31 Jan 2025 | Exit 3 |  | Hirose started drilling for waler brackets
Fri (31/01) | 31 Jan 2025 | Exit 3 |  | Capping beam works ongoing
Fri (31/01) | 31 Jan 2025 | P44 |  | Formwork removal done
Fri (31/01) | 31 Jan 2025 | P17 |  | Falsework erection ongoing
Fri (31/01) | 31 Jan 2025 | P13 |  | Falsework erection ongoing
Fri (31/01) | 31 Jan 2025 | TMH3 |  | Casting completed
Fri (31/01) | 31 Jan 2025 | S3 |  | Secondary beam installation in progress
Fri (31/01) | 31 Jan 2025 | P20 |  | No more activity
Fri (31/01) | 31 Jan 2025 | BP2-2 | 29 | Boring reached 15m
Fri (31/01) | 31 Jan 2025 | BP2B-1 | 55 | Boring reached 23m
Fri (31/01) | 31 Jan 2025 | BR5 |  | Continue roof slab rebar works, Shoring removal at KP area prior to LSS backfilling
Fri (31/01) | 31 Jan 2025 | BR2 |  | Propping dismantling and installation of formwork for retaining wall
Fri (31/01) | 31 Jan 2025 | Exit 3 |  | DW12,13,14 preparing to cast capping beam
Fri (31/01) | 31 Jan 2025 | Zone 3 |  | Access cleaning & housekeeping ongoing
Fri (31/01) | 31 Jan 2025 | DR1 |  | CGS housekeeping ongoing before dismantling formwork
Fri (31/01) | 31 Jan 2025 | ST196 | BC1 | No activity
Fri (31/01) | 31 Jan 2025 | P5 |  | Plan to remove formworks today
Sat (01/02) | 01 Feb 2025 | BP2-2 | 29 | Boring works at 21m depth
Sat (01/02) | 01 Feb 2025 | BP2B-1 | 55 | Boring worka at 24m depth
Sat (01/02) | 01 Feb 2025 | P51 |  | Grouting done. This team will go to receiving shaft
Sat (01/02) | 01 Feb 2025 | P15 |  | Formwork bolts removal
Sat (01/02) | 01 Feb 2025 | DR1 |  | Formwork dismantling
Sat (01/02) | 01 Feb 2025 | BR5 |  | Soil clearing, today to lean con on the balance area
Sat (01/02) | 01 Feb 2025 | BR5 |  | Rebar tying and installation of debonding sheets
Sat (01/02) | 01 Feb 2025 | BRP73-BC3 |  | 2nd bite trenching at 28m depth
Sat (01/02) | 01 Feb 2025 | ST155-BC4 |  | 1st bite trenching at 18.5m depth
Sat (01/02) | 01 Feb 2025 | STN124 |  | Cleaning in progress
Sat (01/02) | 01 Feb 2025 | P43-44 |  | 2 rigs working for JGP testing
Sat (01/02) | 01 Feb 2025 | P43-44 |  | Preparation and drilling for 3rd and 4th points
Sat (01/02) | 01 Feb 2025 | STN124 |  | Cleaning completed. Desanding in progress
Sat (01/02) | 01 Feb 2025 | ST155-BC4 |  | 1st bite trenching at 22.9m depth
Sat (01/02) | 01 Feb 2025 | BRP73-BC3 |  | 2nd bite trenching at 28.1m depth
Sat (01/02) | 01 Feb 2025 | BP2B-1 | 55 | Boring worka at 26.5m depth
Sat (01/02) | 01 Feb 2025 | BP2-2 | 29 | Boring works at 24m depth
Sat (01/02) | 01 Feb 2025 | Exit 3 |  | Drilling for waler bracket installation continue
Sat (01/02) | 01 Feb 2025 | BP2-2-29 |  | Boring reached 25m
Sat (01/02) | 01 Feb 2025 | BP5 |  | Boring reach 29m
Sat (01/02) | 01 Feb 2025 | ST196 |  | Prepare for pre excavation
Sat (01/02) | 01 Feb 2025 | BC1 |  | Tonight no activity
Sat (01/02) | 01 Feb 2025 | BR5 |  | Lean concrete for balance area
Sat (01/02) | 01 Feb 2025 | BR5 |  | Rebar work in progress. Tonight to start shear link
Sat (01/02) | 01 Feb 2025 | BRP73 |  | Preparing for koden check. Will continue 3rd bite after that
Sat (01/02) | 01 Feb 2025 | ST155 |  | Preparing for waterstop end plate side trimming
Sat (01/02) | 01 Feb 2025 | ST131 |  | 1st bite just started
Sat (01/02) | 01 Feb 2025 | ST124 |  | Koden test
Sat (01/02) | 01 Feb 2025 | Exit 3 |  | Hirose today to install waler brackets
Sun (02/02) | 02 Feb 2025 | TMH3 |  | Neck formwork closing ongoing
Sun (02/02) | 02 Feb 2025 | P5 |  | No activity
Sun (02/02) | 02 Feb 2025 | P3 |  | Continue excavation to FEL
Sun (02/02) | 02 Feb 2025 | S3 |  | Access erection
Sun (02/02) | 02 Feb 2025 | P20, zone 3 |  | HSL and Seongha no activity
Sun (02/02) | 02 Feb 2025 | Exit 3 |  | Hirose no activity. KTC continue soil disposal works
Sun (02/02) | 02 Feb 2025 | ST196 | BC1 | B1 excavation started today
Sun (02/02) | 02 Feb 2025 | Near BC1 |  | Arranging steel plates
Sun (02/02) | 02 Feb 2025 | BR1/BR2 |  | No activity
Sun (02/02) | 02 Feb 2025 | DR1 |  | Wall surface patch up
Sun (02/02) | 02 Feb 2025 | BR5 |  | Ground surface levelling and continue roof slab rebar works
Sun (02/02) | 02 Feb 2025 | ST155 | BC4 | B1 completed. Now cutter body washing
Sun (02/02) | 02 Feb 2025 | BRP73 | BC3 | B3 cleaning ongoing
Sun (02/02) | 02 Feb 2025 | ST131 | BC2 | B1 in progress
Sun (02/02) | 02 Feb 2025 | ST124 |  | Rebar cage lapping in progress
Sun (02/02) | 02 Feb 2025 | P43 |  | 2 rigs working respectively for coring test, C30 and SPT (40)
Sun (02/02) | 02 Feb 2025 | P44 |  | No activity
Sun (02/02) | 02 Feb 2025 | P51 |  | GCE preparation works ongoing for JGP, P51-18. Plastic bit will be used for drilling
Sun (02/02) | 02 Feb 2025 | MH2-9/2-10 |  | No activity
Sun (02/02) | 02 Feb 2025 | Zone 2 |  | Continue levelling and compaction works for stage 2 diversion
Sun (02/02) | 02 Feb 2025 | P51-18 |  | Drilling stopped at 6.94m. Encountered obstruction
Sun (02/02) | 02 Feb 2025 | P51-17 |  | Drilling also stopped at 6.76m. Encountered obstruction
Sun (02/02) | 02 Feb 2025 | Zone 4 |  | Now preparing next point, P51-19
Sun (02/02) | 02 Feb 2025 | TMH3 |  | No activity
Sun (02/02) | 02 Feb 2025 | S3 |  | Access installation done. Now preparing side formwork
Sun (02/02) | 02 Feb 2025 | BR5 |  | Shear link installation
Sun (02/02) | 02 Feb 2025 | ST155 |  | Waterstop end plate side trimming
Sun (02/02) | 02 Feb 2025 | BRP73 |  | 1st bite cleaning
Sun (02/02) | 02 Feb 2025 | ST131 |  | Cutter body bring up for teeth changing
Sun (02/02) | 02 Feb 2025 | ST124 |  | CageA (1/4) and cage B (2/4) lowered down
Sun (02/02) | 02 Feb 2025 | P22-23 |  | KTC excavation for decking works
Sun (02/02) | 02 Feb 2025 | ST196 |  | B1 in progress, 16.5/32.75m
Sun (02/02) | 02 Feb 2025 | BR5 |  | Continue roof slab rebar works, Formwork installed at KP area, Continue ground surface levelling
Sun (02/02) | 02 Feb 2025 | BRP73 |  | Preparing for rebar cage lowering
Sun (02/02) | 02 Feb 2025 | A03 |  | Grouting in progress
Sun (02/02) | 02 Feb 2025 | ST-131 |  | 2st bite excavation in progress reached - 27m/34.3m
Sun (02/02) | 02 Feb 2025 | ST-124 |  | Continue rebar cage lowering. Today to cast
Mon (03/02) | 03 Feb 2025 | P13-14 |  | Previous road premix hacking for stage 2 diversion
Mon (03/02) | 03 Feb 2025 | P51 |  | Current status of completed grouting
Mon (03/02) | 03 Feb 2025 | P49 |  | TT for soldier pile preboring
Mon (03/02) | 03 Feb 2025 | P48 |  | TT started for pipe sleeves installation
Mon (03/02) | 03 Feb 2025 | P51 |  | Grouting of JGP near TPE bound
Mon (03/02) | 03 Feb 2025 | P20-3 |  | Demob of WLT materials
Mon (03/02) | 03 Feb 2025 | P14 |  | Pulling of strand for PT
Mon (03/02) | 03 Feb 2025 | Exit 3 |  | DW12,13,14, capping beam casted 1st February
Mon (03/02) | 03 Feb 2025 | Exit 3 |  | DW21 to 24, Formwork closing, planning to cast tmr
Mon (03/02) | 03 Feb 2025 | ST196 | Rig 1 | B2 CD 19/32.75m
Mon (03/02) | 03 Feb 2025 | P3 |  | Half of the area to cast concrete plug today. Tomorrow HSL will mobilise for pile head hacking and also cast balance concrete plug
Mon (03/02) | 03 Feb 2025 | BR5 |  | Rebar installation in progress
Mon (03/02) | 03 Feb 2025 | S3 |  | Preparation for rebar installation works for crosshead
Mon (03/02) | 03 Feb 2025 | ST131 | Rig 2 | B2 CD 29.7/34.3m
Mon (03/02) | 03 Feb 2025 | ST131 |  | 2nd bite completed
Mon (03/02) | 03 Feb 2025 | ST80& ST81 |  | Exposing abandoned cable for guidewall work
Mon (03/02) | 03 Feb 2025 | BC#3 |  | Cutter head maintenance
Mon (03/02) | 03 Feb 2025 | BRP55 |  | Cleaning and desanding
Mon (03/02) | 03 Feb 2025 | BR5 |  | Current status of top bar laying
Mon (03/02) | 03 Feb 2025 | BR5 |  | Exposing for strut end plate installation
Mon (03/02) | 03 Feb 2025 | DR1 |  | Woh hup prepare for LSS backfilling. CGS clearing their unused materials
Mon (03/02) | 03 Feb 2025 | ST169 |  | 2nd bite, reached 24.5m
Mon (03/02) | 03 Feb 2025 | BP2B-1-55 |  | Boring reached 35m
Mon (03/02) | 03 Feb 2025 | BP29 |  | Boring reached 30.50m
Mon (03/02) | 03 Feb 2025 | S3 |  | Base lean concrete
Mon (03/02) | 03 Feb 2025 | P51 |  | Prepare platform for JGP grouting
Tue (04/02) | 04 Feb 2025 | S3 |  | Cross head rebar work and woh hup preparing for rain water drain pipe installation
Tue (04/02) | 04 Feb 2025 | P14 |  | Surface grinding
Tue (04/02) | 04 Feb 2025 | P11 |  | Excavation for teleco duct
Tue (04/02) | 04 Feb 2025 | P6 |  | Scaffold materials shifting
Tue (04/02) | 04 Feb 2025 | BR2 |  | CJ hacking at couplers to roughen surface, Retaining wall plan for casting today
Tue (04/02) | 04 Feb 2025 | Exit 3 |  | Formwork closing for the wall
Tue (04/02) | 04 Feb 2025 | BR5 |  | Roof slab rebaf works in progress
Tue (04/02) | 04 Feb 2025 | ST131 | BC2 | B3 in progress. Diesel topup ongoing
Tue (04/02) | 04 Feb 2025 | BP29 |  | Boring reached 33m
Tue (04/02) | 04 Feb 2025 | BP2-1 WLT | 33 | Today inspection and plan for testing tomorrow
Tue (04/02) | 04 Feb 2025 | RWS37 |  | TT for boring work
Tue (04/02) | 04 Feb 2025 | P43 |  | 2 rigs working respectively for SPT39 and coring works
Tue (04/02) | 04 Feb 2025 | BP2B-1-49 |  | Boring reached 15m
Tue (04/02) | 04 Feb 2025 | BP2B-1 | 55 | Prepare platform for casting
Tue (04/02) | 04 Feb 2025 | ST196 |  | 3rd bite in progress
Tue (04/02) | 04 Feb 2025 | DR1 |  | Formwork making for LSS backfilling
Tue (04/02) | 04 Feb 2025 | P44 |  | No activity
Tue (04/02) | 04 Feb 2025 | P48-1 |  | Trial trench in progress
Tue (04/02) | 04 Feb 2025 | P51-16 |  | Survey checking for obstructed point
Tue (04/02) | 04 Feb 2025 | P51-24 |  | Platform preparation
Tue (04/02) | 04 Feb 2025 | Exit 3 |  | Currently no activity. Lunch break. Hirose to continue drilling for waler brackets below the ladder access
Tue (04/02) | 04 Feb 2025 | DW21-24 |  | Retaining wall works
Tue (04/02) | 04 Feb 2025 | ST196 | BC1 | Excavation completed, Water stop trimming ongoing
Tue (04/02) | 04 Feb 2025 | MH2-10 |  | Short pipe connection in progress
Tue (04/02) | 04 Feb 2025 | MH2-9 |  | Backfilling in progress
Tue (04/02) | 04 Feb 2025 | P51 |  | Current status of grouting done
Tue (04/02) | 04 Feb 2025 | P50 |  | Exposing of telstra pipe for mandrel test
Tue (04/02) | 04 Feb 2025 | P51 |  | Continue JGP grouting work
Tue (04/02) | 04 Feb 2025 | P15 to P19 |  | Premix laying for B1 layer
Tue (04/02) | 04 Feb 2025 | BR5 |  | Continue roof slab rebar works
Tue (04/02) | 04 Feb 2025 | P14 |  | Preparation for tendon stressing works
Tue (04/02) | 04 Feb 2025 | P14-P13 |  | Excavation and hardcores removal for stage 2 diversion
Tue (04/02) | 04 Feb 2025 | P11 |  | Preparation for slope lean concrete for telco duct
Tue (04/02) | 04 Feb 2025 | TMH-3 |  | Formwork dismantling and patching works in progress
Tue (04/02) | 04 Feb 2025 | P6-1 |  | Scaffold erection for column works
Tue (04/02) | 04 Feb 2025 | S3 |  | Rebars and tendon ducts installation
Tue (04/02) | 04 Feb 2025 | Zone 2 |  | Current stockpile status
Tue (04/02) | 04 Feb 2025 | P5 |  | NDT test pile cap backfilling ongoing
Tue (04/02) | 04 Feb 2025 | P3 |  | Preparation for base lean concrete
Tue (04/02) | 04 Feb 2025 | P2 |  | Preboring for ERSS installation
Tue (04/02) | 04 Feb 2025 | ST131 |  | Waterstop trimming
Tue (04/02) | 04 Feb 2025 | DW80& DW81 |  | Prepare for guidewall
Tue (04/02) | 04 Feb 2025 | BC cutter 3 |  | Cutter size changing
Tue (04/02) | 04 Feb 2025 | ST155 |  | Prepare for cleaning and desanding
Tue (04/02) | 04 Feb 2025 | BR5 |  | Bar chair installation and prepare for top bar laying
Tue (04/02) | 04 Feb 2025 | BR2 |  | Casting of wall in progress
Tue (04/02) | 04 Feb 2025 | Exit 3 |  | Waiting for lorry crane to cast. Will cast today
Tue (04/02) | 04 Feb 2025 | BP29 |  | Boring reached 34.5m
Tue (04/02) | 04 Feb 2025 | P51 |  | Continue JGP grouting work
Tue (04/02) | 04 Feb 2025 | MH2-10 |  | Base slab was cast last night
Tue (04/02) | 04 Feb 2025 | MH2-9 |  | Preparation works ongoing for soil backfilling
Tue (04/02) | 04 Feb 2025 | P5 |  | NDT test. Left one layer for backfilling
Tue (04/02) | 04 Feb 2025 | P2 |  | Preboring for ERSS installation
Tue (04/02) | 04 Feb 2025 | P3 |  | Exacavation and levelling. Today plan to lean con
Wed (05/02) | 05 Feb 2025 | MH2-9 |  | Soil backfill done yesterday. Today only 1 team working at MH2-10
Wed (05/02) | 05 Feb 2025 | MH2-10 |  | Unloading of MH rebars for first lift works
Wed (05/02) | 05 Feb 2025 | Exit 3 |  | HSL preparing platform for 1 boring rig demobilisation
Wed (05/02) | 05 Feb 2025 | Exit 3 |  | Hirose preparing waler bracket plates. Tmr morning plan for pull-out test
Wed (05/02) | 05 Feb 2025 | P14 to P20+ |  | Premix laying and compaction works for stage 2 TD diversion works
Wed (05/02) | 05 Feb 2025 | Bet. P14-P15 |  | Drilling in progress for GWV225012
Wed (05/02) | 05 Feb 2025 | BP33 |  | Bidirectional load test in progress. Now loading at 100%, holding time 6hrs
Wed (05/02) | 05 Feb 2025 | BP2-2 | 29 | Boring in progress, 35/36.7m. Target to cast tmr
Wed (05/02) | 05 Feb 2025 | Exit 3 |  | Soil trimming at capping beam area. Retaining wall for DW20-23 already cast
Wed (05/02) | 05 Feb 2025 | BP2B-1 | 49 | Boring in progress, 29/35.08m
Wed (05/02) | 05 Feb 2025 | BP2B-1 | 55 | Pile was cast last night. Now preparing for LSS backfill
Wed (05/02) | 05 Feb 2025 | P30 |  | Manual trial trench at stump area
Wed (05/02) | 05 Feb 2025 | DR1 |  | LSS backfill
Wed (05/02) | 05 Feb 2025 | P14 |  | Stressing of tendon cables in progress. T2b completed
Wed (05/02) | 05 Feb 2025 | ST196 | BC1 | Mud drum rectification ongoing
Wed (05/02) | 05 Feb 2025 | BR5 |  | Continue rebar works and formwork installation
Wed (05/02) | 05 Feb 2025 | BRP76B | BC4 | B2 in progress, 30.1/30.35m
Wed (05/02) | 05 Feb 2025 | DW81-80 |  | Guidewall rebar works
Wed (05/02) | 05 Feb 2025 | BC2 |  | Currently maintenance work. ST131 WS lowering ongoing
Wed (05/02) | 05 Feb 2025 | P15 |  | Formwork dismantle and removal in progress
Wed (05/02) | 05 Feb 2025 | P14-P13 |  | KTC continue excavation for stage 2 TD
Wed (05/02) | 05 Feb 2025 | TMH-3 |  | Backfilling in progress
Wed (05/02) | 05 Feb 2025 | S3 |  | Rebars and formwork installation in progress. Target to cast on Fri
Wed (05/02) | 05 Feb 2025 | Near P6-2 |  | Trial trench completed. Reinstatement in progress
Wed (05/02) | 05 Feb 2025 | P5 |  | Struts removal in progress
Wed (05/02) | 05 Feb 2025 | P3 |  | Pile head hacking in progress
Wed (05/02) | 05 Feb 2025 | P2 |  | Preboring in progress for ERSS installation
Wed (05/02) | 05 Feb 2025 | ST131 |  | Waterstop end plate lowering
Wed (05/02) | 05 Feb 2025 | BRP76 |  | 2nd bite completed. Prepare for koden test
Wed (05/02) | 05 Feb 2025 | BR5 |  | Bar chair installation
Wed (05/02) | 05 Feb 2025 | ST196 |  | Waterstop end trimming
Wed (05/02) | 05 Feb 2025 | Zone 2 |  | Current stockpile status
Wed (05/02) | 05 Feb 2025 | Exit 2 |  | Boring 3nos done for fissure grouting. Today plan to grout
Wed (05/02) | 05 Feb 2025 | BP2B-1 | 49 | Boring reached 28.5m
Wed (05/02) | 05 Feb 2025 | BP2-2-29 |  | Boring reached 36m
Wed (05/02) | 05 Feb 2025 | P1 |  | Preboring
Wed (05/02) | 05 Feb 2025 | P5 |  | No activity already
Wed (05/02) | 05 Feb 2025 | Exit 3 |  | Current status of bracket installation done. 8nos
Wed (05/02) | 05 Feb 2025 | P51 |  | Continue JGP grouting
Thu (06/02) | 06 Feb 2025 | BRP76B | Rig 4 | B3 CD 7.0/30.35m
Thu (06/02) | 06 Feb 2025 | BR5 |  | Continue rebar works and partial formwork installation
Thu (06/02) | 06 Feb 2025 | BR1, BR2 |  | No activity
Thu (06/02) | 06 Feb 2025 | DR1 |  | Housekeeping. Yesterday LSS backfill
Thu (06/02) | 06 Feb 2025 | ST123 | Rig 2 | B1 CD 30.2/39.0m
Thu (06/02) | 06 Feb 2025 | P10-11 |  | Area levelling for temp access to south ramp
Thu (06/02) | 06 Feb 2025 | ST131 |  | Rebar cage lowering in progress
Thu (06/02) | 06 Feb 2025 | MH2-10 |  | MH rebar works in progress
Thu (06/02) | 06 Feb 2025 | P48-28 |  | Pipe sleeve installed. Backfilling ongoing
Thu (06/02) | 06 Feb 2025 | P50 |  | Telstra pipe rectification at this location as mandrel test was unable to complete here
Thu (06/02) | 06 Feb 2025 | P51-22 |  | JGP in progress
Thu (06/02) | 06 Feb 2025 | P44 |  | No activity
Thu (06/02) | 06 Feb 2025 | P43 |  | Coring test & SPT in progress — C40, SPT36
Thu (06/02) | 06 Feb 2025 | ST123 | BC2 | Cutter teeth changing ongoing. B1 CD 31.5/39m
Thu (06/02) | 06 Feb 2025 | DW83 | BC3 | Rectifying bentonite pipe due to leaking. B1 CD 4/21.1m
Thu (06/02) | 06 Feb 2025 | DW81-80 |  | Guidewall casting in progress
Thu (06/02) | 06 Feb 2025 | BRP69 |  | Trial trench in progress
Thu (06/02) | 06 Feb 2025 | BRP76B | BC4 | B2 cleaning in progress
Thu (06/02) | 06 Feb 2025 | BR2 |  | CJ hacking at couplers to roughen
Thu (06/02) | 06 Feb 2025 | DR1 |  | Debris clearing
Thu (06/02) | 06 Feb 2025 | ST196 | BC1 | B2 cleaning in progress
Thu (06/02) | 06 Feb 2025 | Exit 3 |  | Total 14nos waler brackets installed
Thu (06/02) | 06 Feb 2025 | Zone 2 |  | SB bus stop platform formwork closing completed. Waiting for casting
Thu (06/02) | 06 Feb 2025 | P15 |  | Crosshead formwork dismantling ongoin
Thu (06/02) | 06 Feb 2025 | P14 |  | Stressing works ongoing (facing LVC), 10/12 completed
Thu (06/02) | 06 Feb 2025 | S3 |  | Crosshead plan for casting tmr morning
Thu (06/02) | 06 Feb 2025 | BP2-2 | 29 | KP lowered. Now tremie pipe lowering ongoing
Thu (06/02) | 06 Feb 2025 | ST196 | BC1 | Cleaning temporarily stopped. Mud pump rectification ongoing
Thu (06/02) | 06 Feb 2025 | BR5 |  | Continue rebar works
Thu (06/02) | 06 Feb 2025 | Exit 3 |  | Preparing platform for Hirose crane
Thu (06/02) | 06 Feb 2025 | P20 |  | Hardcore cleared from kentledge test. Saturday mobile to mobilise at north ramp for progressive dismantling of silo plant
Thu (06/02) | 06 Feb 2025 | MH2-10 |  | Permanent MH wall rebar works in progres
Thu (06/02) | 06 Feb 2025 | MH2-9 |  | No activity. Excavator to be repaired due to some issue
Thu (06/02) | 06 Feb 2025 | ST196 | Rig 1 | Cleaning in progress
Fri (07/02) | 07 Feb 2025 | P51 |  | Current status of grouting done. Next week can complete
Fri (07/02) | 07 Feb 2025 | P51 |  | Continue grouting
Fri (07/02) | 07 Feb 2025 | P48 |  | TT for pipe sleeves installation
Fri (07/02) | 07 Feb 2025 | P43-44 |  | Two teams testing. One SPT and One team for coring test
Fri (07/02) | 07 Feb 2025 | MH2-10 |  | Formwork installation for permanent MH wall. Today to cast
Fri (07/02) | 07 Feb 2025 | MH2-9 |  | No activity. Excavator still waiting for WH safety clearance
Fri (07/02) | 07 Feb 2025 | N6 |  | HSL mud clearing and housekeeping works for silo removal
Fri (07/02) | 07 Feb 2025 | Between N4-N5 |  | Soil clearing for segment supports base preparation
Fri (07/02) | 07 Feb 2025 | BRP76B |  | Rebar cage lowering in progress
Fri (07/02) | 07 Feb 2025 | ST154 | Rig 4 | B1 CD 9.5/33.9m
Fri (07/02) | 07 Feb 2025 | BR5 |  | Continue rebar works, cleaning and corrugated pipes installation
Fri (07/02) | 07 Feb 2025 | DW83 | Rig 3 | B3 CD 15.0/21.1m
Fri (07/02) | 07 Feb 2025 | Near BR5 |  | Manual excavation for drilling for bracket installation
Fri (07/02) | 07 Feb 2025 | ST123 | Rig 2 | B2 CD 17.0/39.0m
Fri (07/02) | 07 Feb 2025 | ST196 |  | Rebar cage lowering in progress
Fri (07/02) | 07 Feb 2025 | P14 |  | Continue bottom formwork removal
Fri (07/02) | 07 Feb 2025 | Bet P12 - P13 |  | Premix hacking and disposal ongoing
Fri (07/02) | 07 Feb 2025 | P10 |  | 6m telco pipe laying in progress. Target to cast today
Fri (07/02) | 07 Feb 2025 | P8-P7 |  | Hacking of premix for stage 2 TD
Fri (07/02) | 07 Feb 2025 | P51 |  | Continue JGP grouting
Fri (07/02) | 07 Feb 2025 | P50 |  | Preparing for preboring TT
Fri (07/02) | 07 Feb 2025 | P43-44 |  | One SPT and one coring point testing done
Fri (07/02) | 07 Feb 2025 | P48 |  | TT for pipe sleeves installation
Fri (07/02) | 07 Feb 2025 | Near P16 |  | Footpath construction ongoing. Tmr plan to cast ~30m
Fri (07/02) | 07 Feb 2025 | P14 |  | Exposing anchor head for post-tensioning works
Fri (07/02) | 07 Feb 2025 | P9 |  | Telco duct plan for casting, 6m
Fri (07/02) | 07 Feb 2025 | Near P8 |  | Hardcore removal for stage 2 diversion
Fri (07/02) | 07 Feb 2025 | S3 |  | Crosshead casting was completed
Fri (07/02) | 07 Feb 2025 | DW26 | BC1 | B1 in progress, 9/32.7m
Fri (07/02) | 07 Feb 2025 | Exit 3 |  | Waler and runner beams arrived on site
Fri (07/02) | 07 Feb 2025 | TDP38 |  | Boring completed. Pending depth check by RTO
Fri (07/02) | 07 Feb 2025 | ST196 |  | Rebar cage lapping in progress
Fri (07/02) | 07 Feb 2025 | BR2 |  | Formwork dismantling
Fri (07/02) | 07 Feb 2025 | BR5 |  | Rebar inspection, continue rebar works & formwork installation
Fri (07/02) | 07 Feb 2025 | Exit 3 |  | RG to extend pipe for GWV/GWS31003 monitoring
Sat (08/02) | 08 Feb 2025 | Zone 4 |  | JGP for ERSS. 1 pt to complete here tonight. Then they will shift to P43 to do JGP for another point
Sat (08/02) | 08 Feb 2025 | Zone 4 |  | Water pipe laying by Leychoon
Sat (08/02) | 08 Feb 2025 | P14 |  | Clearing materials and lowering down
Sat (08/02) | 08 Feb 2025 | P7 |  | KTC removal of road premix for road diversion
Sat (08/02) | 08 Feb 2025 | P9 |  | Vsk excavation and prepare for duct laying
Sat (08/02) | 08 Feb 2025 | STN123-BC2 |  | Preparation for c-lug welding
Sat (08/02) | 08 Feb 2025 | DW80-BC3 |  | 1st bite trenching completed. Preparation for internal Koden
Sat (08/02) | 08 Feb 2025 | DW83 |  | All cages installed. Prepreparation for Tremie pipe installation
Sat (08/02) | 08 Feb 2025 | STN154-BC4 |  | 1st bite trenching, depth at 28.5m
Sat (08/02) | 08 Feb 2025 | P2 |  | TT for preboring and ERSS installation
Sat (08/02) | 08 Feb 2025 | P3 |  | Hacking of pile head for pier footing
Sat (08/02) | 08 Feb 2025 | P5 |  | Prepare formwork for column stump
Sat (08/02) | 08 Feb 2025 | BP2-1 | 49 | Casting completed
Sat (08/02) | 08 Feb 2025 | DW26-BC1 |  | 2nd bite trenching
Sat (08/02) | 08 Feb 2025 | P51 |  | Current status of grouting done
Sat (08/02) | 08 Feb 2025 | P43-44 |  | Continue JGP testing. Two teams
Sat (08/02) | 08 Feb 2025 | P44 |  | Started backfilling
Sat (08/02) | 08 Feb 2025 | ST123 |  | 2nd bite, reached 34.8m
Sat (08/02) | 08 Feb 2025 | DW83 |  | Rebar cage lowering. Tonight to cast
Sat (08/02) | 08 Feb 2025 | BRP76B |  | Concrete on site for casting
Sat (08/02) | 08 Feb 2025 | ST154 |  | Mud pumping changing
Sat (08/02) | 08 Feb 2025 | BR5 |  | Top bar continue installation
Sat (08/02) | 08 Feb 2025 | BR2 |  | CJ surface roughening
Sat (08/02) | 08 Feb 2025 | Exit 2 |  | Access installation and shear stud planting
Sat (08/02) | 08 Feb 2025 | ST26 |  | 1st bite excavation in progress
Sat (08/02) | 08 Feb 2025 | Exit 3 |  | KTC exposing service to provide support
Sat (08/02) | 08 Feb 2025 | P15 |  | Access erection by woh hup for ultracon
Sat (08/02) | 08 Feb 2025 | P5 |  | Preparing for column formwork closing
Sat (08/02) | 08 Feb 2025 | P2 |  | Preboring for ERSS installation
Sat (08/02) | 08 Feb 2025 | P3 |  | Pile head hacking
Sat (08/02) | 08 Feb 2025 | ST123 |  | 1st bite, reached 14m
Sat (08/02) | 08 Feb 2025 | DW88 |  | 1st bite, reached 14m, DW83: continue lowering down rebar cage
Sat (08/02) | 08 Feb 2025 | ST154 |  | 1st bite, reached 26m
Sat (08/02) | 08 Feb 2025 | BRP76B |  | Continue casting
Sat (08/02) | 08 Feb 2025 | BR5 |  | Top bar installation and side formwork closing
Sat (08/02) | 08 Feb 2025 | DR1 |  | Formwork closing for sewer pipe support
Sat (08/02) | 08 Feb 2025 | BR2 |  | CJ surface roughening
Sat (08/02) | 08 Feb 2025 | BP2B-1-49 |  | Rebar cage lowered for casting
Sat (08/02) | 08 Feb 2025 | Exit 2 |  | Prepare for fissure grouting work
Sat (08/02) | 08 Feb 2025 | P51 |  | Continue JGP grouting
Sat (08/02) | 08 Feb 2025 | P14 Housekeeping |  | Working platform to be dismantled after the last bus
Sat (08/02) | 08 Feb 2025 | Exit 3 |  | Woh hup erection of access
Sat (08/02) | 08 Feb 2025 | ST26 |  | Now O ring leak. Replacing in progress
Sat (08/02) | 08 Feb 2025 | BP49 |  | Boring completed. Preparing for toe confirmation
Sat (08/02) | 08 Feb 2025 | RWS38 |  | Prepare for pipe installation
Sun (09/02) | 09 Feb 2025 | Zone 2 |  | HSL no activity
Sun (09/02) | 09 Feb 2025 | P15 |  | Cable pulling ongoing
Sun (09/02) | 09 Feb 2025 | P14 |  | Falsework dismantling ongoing, Excavation and abandoned water pipe removal for stage 2 TD
Sun (09/02) | 09 Feb 2025 | Near P8 |  | Debris clearing
Sun (09/02) | 09 Feb 2025 | P6 |  | Housekeeping
Sun (09/02) | 09 Feb 2025 | P5 |  | Coulmn formwork installation
Sun (09/02) | 09 Feb 2025 | Zone 1 |  | LE no activity
Sun (09/02) | 09 Feb 2025 | P3 |  | No activity
Sun (09/02) | 09 Feb 2025 | P25 |  | Excavation ongoing for utility support works
Sun (09/02) | 09 Feb 2025 | Zone 3 |  | HSL no activity
Sun (09/02) | 09 Feb 2025 | DW26 | BC1 | B2 in progress, 26/32.7m
Sun (09/02) | 09 Feb 2025 | BR1, BR2 |  | No activity
Sun (09/02) | 09 Feb 2025 | DR1 |  | 7nos stumps cast yesterday
Sun (09/02) | 09 Feb 2025 | BR5 |  | Top bars installation. About 65% completed, target to cast on Wednesday
Sun (09/02) | 09 Feb 2025 | ST154 | BC4 | B1 completed. Now ongoing B2
Sun (09/02) | 09 Feb 2025 | DW80 | BC3 | Preparing for internal koden check
Sun (09/02) | 09 Feb 2025 | ST123 | BC2 | Preparing for endplate loosening
Sun (09/02) | 09 Feb 2025 | P43 |  | 2 rigs working respectively for SPT and coring test
Sun (09/02) | 09 Feb 2025 | P44 |  | Backfilling works
Sun (09/02) | 09 Feb 2025 | P51-58 |  | JGP completed, P51-60: Now preparation works
Sun (09/02) | 09 Feb 2025 | P14 |  | Platform dismantling in progress
Sun (09/02) | 09 Feb 2025 | Exit 3 |  | 4nos waler beams installed. Today plan for diagonal strut installation (DS-1)
Sun (09/02) | 09 Feb 2025 | MH2-10 |  | Formwork support installation for 2nd lift
Sun (09/02) | 09 Feb 2025 | P14 |  | Continue falsework dismantling
Sun (09/02) | 09 Feb 2025 | Near P9 |  | Telco duct pipe laying in progress, 9m
Sun (09/02) | 09 Feb 2025 | DW26 | BC1 | Cutter teeth changing ongoing. B2 CD 29/32.7m
Sun (09/02) | 09 Feb 2025 | DW26-BC1 |  | 2nd bite trenching at 15m. Now teeth replacement
Sun (09/02) | 09 Feb 2025 | ST154 | BC4 | B2 in progress, 9/33.9m
Sun (09/02) | 09 Feb 2025 | DW80 | BC3 | WS trimming
Sun (09/02) | 09 Feb 2025 | DW115 |  | Pre-excavation
Sun (09/02) | 09 Feb 2025 | ST123 | BC2 | WS trimming
Sun (09/02) | 09 Feb 2025 | P43 |  | Coring test, C-38 completed. SPT35 in progress
Sun (09/02) | 09 Feb 2025 | STN154-BC4 |  | 1st bite trenching, depth at 32m. Teeth changing in progress
Sun (09/02) | 09 Feb 2025 | DW80-BC3 |  | Trimming in progress for 1st bite
Sun (09/02) | 09 Feb 2025 | DW83 |  | Casting in progress
Sun (09/02) | 09 Feb 2025 | STN123-BC2 |  | Trimming in progress
Sun (09/02) | 09 Feb 2025 | P43 |  | Grouting in progress
Sun (09/02) | 09 Feb 2025 | MH2-10 |  | LCH preparing HDPE lining and 2nd lift wall rebar works
Sun (09/02) | 09 Feb 2025 | MH2-9 |  | No activity
Sun (09/02) | 09 Feb 2025 | Exit 3 |  | Waler beams installation in progress , 2/4nos done
Mon (10/02) | 10 Feb 2025 | P48 |  | TT continue for pipe sleeves installation
Mon (10/02) | 10 Feb 2025 | P50 |  | Additional TT doing for preboring work
Mon (10/02) | 10 Feb 2025 | P51 |  | Continue JGP grouting
Mon (10/02) | 10 Feb 2025 | P8-9 |  | TT for tunnel RX installation
Mon (10/02) | 10 Feb 2025 | Zone 4 |  | Water pipe laying done. Road reinstate on going
Mon (10/02) | 10 Feb 2025 | P44 |  | Backfilling in progress
Mon (10/02) | 10 Feb 2025 | Exit 3 |  | Waler beam welding, Installation of rebars for packing concrete (to cast tomorrow)
Mon (10/02) | 10 Feb 2025 | P8 |  | Utility checking by utility team
Tue (11/02) | 11 Feb 2025 | MH2-10 |  | 2nd lift cast yesterday. Now formwork removal and plan for LSS backfill today
Tue (11/02) | 11 Feb 2025 | MH2-9 |  | No activity
Tue (11/02) | 11 Feb 2025 | BR5 |  | Shearlinks installation, column starter bar installation & formwork in progress
Tue (11/02) | 11 Feb 2025 | ST154 | BC4 | B3 in progress, 11/21.6m
Tue (11/02) | 11 Feb 2025 | BRP69 | BC2 | B1 in progress
Tue (11/02) | 11 Feb 2025 | DW80 | BC3 | Cutter teeth changing ongoing
Tue (11/02) | 11 Feb 2025 | ST123 |  | Rebar cage lapping in progress
Tue (11/02) | 11 Feb 2025 | P44 |  | Levelling ongoing
Tue (11/02) | 11 Feb 2025 | P43 |  | Point C-37 in progress
Tue (11/02) | 11 Feb 2025 | BR1, BR2 |  | Scaffold erection for utility protection works
Tue (11/02) | 11 Feb 2025 | Exit 2 |  | Seongha fissure grouting in progress
Tue (11/02) | 11 Feb 2025 | Exit 3 |  | Waler beam welding and preparing for concrete packing
Tue (11/02) | 11 Feb 2025 | BR5 |  | Continues rebar & formwork installation
Tue (11/02) | 11 Feb 2025 | MH2-10 |  | LSS backfilling ongoing
Tue (11/02) | 11 Feb 2025 | Zone 2 |  | Preparation for silo dismantling
Tue (11/02) | 11 Feb 2025 | ST199 | BC1 | B1 excavation started at 2:47pm. Now temporarily stopped due to hydraulic leaking. Rectification ongoing
Tue (11/02) | 11 Feb 2025 | ST154 | Rig 4 | B3 CD 17.0/21.6m
Tue (11/02) | 11 Feb 2025 | BRP69 | Rig 2 | B1 CD 22.0/29.4m
Tue (11/02) | 11 Feb 2025 | DW80 | Rig 3 | WS trimming in progress
Tue (11/02) | 11 Feb 2025 | ST123 |  | Rebar cage lowering in progress
Tue (11/02) | 11 Feb 2025 | DR1 |  | No activity
Tue (11/02) | 11 Feb 2025 | BR5 |  | Corrugated pipes installation, Continue shearlinks and formwork installation, To progressively prepare platform for concrete pumps tonight
Tue (11/02) | 11 Feb 2025 | P50 |  | TT for preboring
Tue (11/02) | 11 Feb 2025 | P51 |  | Continue JGP grouting
Tue (11/02) | 11 Feb 2025 | P43 |  | TT on going for P43 ERSS. Found services. Utility team need fo confirm before remove
Tue (11/02) | 11 Feb 2025 | P43 |  | JGP testing last point done
Tue (11/02) | 11 Feb 2025 | P44 |  | Backfilling and compaction
Tue (11/02) | 11 Feb 2025 | DW26 |  | Rebar cage extraction. The rebar cage could not be fully lowered due to suspected soil collapse
Tue (11/02) | 11 Feb 2025 | BP2-2 | 31 | Boring at 27m
Tue (11/02) | 11 Feb 2025 | BR5 |  | Rebar and formwork closing continue
Tue (11/02) | 11 Feb 2025 | ST154 |  | Cutter body hoist up for teeth replacement
Tue (11/02) | 11 Feb 2025 | BRP69 |  | B1 trenching. Cutter body up for gear box cleaning
Tue (11/02) | 11 Feb 2025 | DW80-BC3 |  | C-lug welding for trimming
Tue (11/02) | 11 Feb 2025 | ST123 |  | Rebar cage installation. 8/8
Tue (11/02) | 11 Feb 2025 | Zone 4 P51 |  | JGP work stopped for the day. 3 nos completed. Night shift team to take over
Wed (12/02) | 12 Feb 2025 | ST199 | Rig 1 | B1 excavation about to resume
Wed (12/02) | 12 Feb 2025 | BR5 |  | Balance shearlinks installation, cast-in bolts installation & slope side formwork, Hyrib installation & cleaning ongoing, Concrete pumps platform ok. Pending COS
Wed (12/02) | 12 Feb 2025 | P17 |  | Hard barricade installation. Tonight will close bus lane for runner and soffit plywood installation
Wed (12/02) | 12 Feb 2025 | P43 |  | LE trial trench for ERSS works
Wed (12/02) | 12 Feb 2025 | P43 |  | GCE preparing area for next JGP works
Wed (12/02) | 12 Feb 2025 | P44 |  | No activity
Wed (12/02) | 12 Feb 2025 | ST154 | Rig 4 | WS trimming in progress
Wed (12/02) | 12 Feb 2025 | BRP69 | Rig 2 | B1 completed 29.4/29.4m. Cutter teeth replacement in progress
Wed (12/02) | 12 Feb 2025 | DW80 | Rig 3 | Cutter teeth replacement in progress
Wed (12/02) | 12 Feb 2025 | P48-07 |  | Trial trench
Wed (12/02) | 12 Feb 2025 | ST123 |  | Casting in progress
Wed (12/02) | 12 Feb 2025 | P50 |  | Trial trench for preboring
Wed (12/02) | 12 Feb 2025 | P51-56 |  | JGP works in progress
Wed (12/02) | 12 Feb 2025 | Zone 4 |  | Stockpile status & sieving works
Wed (12/02) | 12 Feb 2025 | BR5 |  | Top bar inspection for double slab area, Continue shearlinks and cast-in bolts installation
Wed (12/02) | 12 Feb 2025 | P18 |  | HSL to demob 3rd silo out today
Wed (12/02) | 12 Feb 2025 | P18 to P19+ |  | Footpath formwork installation. Today to cast 42m
Wed (12/02) | 12 Feb 2025 | P17 |  | Continue working platform c-channel installation
Wed (12/02) | 12 Feb 2025 | P15 |  | Wedge plate installation completed. Pending cube test result for stressing works
Wed (12/02) | 12 Feb 2025 | MH2-10 |  | Preparing for intermediate slab works
Wed (12/02) | 12 Feb 2025 | BR5 |  | Slope side formwork installation, Additional lighting and barricades installation ongoing, Cleaning in progress, Continue housekeeping works and prepare for 2 more concrete pumps parking
Wed (12/02) | 12 Feb 2025 | P43 |  | GCE excavation for pipe sleeves installation
Wed (12/02) | 12 Feb 2025 | ST154 | BC4 | WS trimming temporarily stopped. Mud pump rectification ongoing
Wed (12/02) | 12 Feb 2025 | BRP69 | BC2 | B2 in progress, 15/29.4m
Wed (12/02) | 12 Feb 2025 | DW80 | BC3 | B1 cleaning completed & first part of endplate extracted
Wed (12/02) | 12 Feb 2025 | BR5 |  | Slope side formwork almost completed, Balance corrugated pipes to be installed & cleaning/housekeeping ongoing
Wed (12/02) | 12 Feb 2025 | Exit 2 |  | RG drilling ongoing for inclinometer installation
Wed (12/02) | 12 Feb 2025 | Exit 2 |  | Seongha fissure grouting works in progress
Wed (12/02) | 12 Feb 2025 | TDP39 |  | Boring was resumed
Wed (12/02) | 12 Feb 2025 | BR5 |  | Final inspection was done. Now housekeeping and cleaning ongoing, 2 concrete pumps parked on site, 1 more pump truck will be parked once crane has moved out. Ordering concrete ard 730pm
Wed (12/02) | 12 Feb 2025 | Exit 3 |  | 4nos of strut installed. Strut end welding on going
Wed (12/02) | 12 Feb 2025 | Station/ Exit 3 |  | Exposing services below for utility support
Wed (12/02) | 12 Feb 2025 | BP31 |  | Boring reached, 31m. Working until 10PM
Wed (12/02) | 12 Feb 2025 | DW26 |  | Hanging bar installation for casting tonight
Wed (12/02) | 12 Feb 2025 | BP49 |  | LSS backfilling
Wed (12/02) | 12 Feb 2025 | BR5 |  | 2 trucks just arrived, G50 concrete for column kicker casting
Wed (12/02) | 12 Feb 2025 | ST199 |  | 1st bite, reached 13m
Wed (12/02) | 12 Feb 2025 | BR5 |  | Continue casting with two pump car as of now. 3rd pump car for waterproofing concrete
Wed (12/02) | 12 Feb 2025 | ST154 |  | Waterstop end plate side trimming
Wed (12/02) | 12 Feb 2025 | BRP69 |  | 2nd bite, reached 22m
Wed (12/02) | 12 Feb 2025 | DW115 |  | 1st bite started excavation
Wed (12/02) | 12 Feb 2025 | DW80 |  | Prepare for waterstop and rebar cage lowering
Thu (13/02) | 13 Feb 2025 | BR5 |  | Casting in progress, 1275.5/1320m3
Thu (13/02) | 13 Feb 2025 | DW117-118 |  | Trial trench
Thu (13/02) | 13 Feb 2025 | DW115 |  | B2 in progress
Thu (13/02) | 13 Feb 2025 | P43 |  | Ground levelling ongoing
Thu (13/02) | 13 Feb 2025 | P44 |  | No activity
Thu (13/02) | 13 Feb 2025 | Zone 4 |  | Sieving works ongoing
Thu (13/02) | 13 Feb 2025 | P48-36 |  | Trial trench completed. Backfilling ongoing
Thu (13/02) | 13 Feb 2025 | P51 |  | GCE no activity yet. Only soil disposal
Thu (13/02) | 13 Feb 2025 | DR4 |  | Premix removal & excavation for water pipe laying works
Thu (13/02) | 13 Feb 2025 | MH1-2 |  | Manual excavation to shift OG box
Thu (13/02) | 13 Feb 2025 | Near zone 4 junction |  | Other contractor working at sidetable for SI works under PUB
Thu (13/02) | 13 Feb 2025 | BR5 |  | Casting almost completing. Current volume: 1421/1439m3
Thu (13/02) | 13 Feb 2025 | DR1 |  | Vibro just mobilised on site. LE to facilitate the utility support dismantling
Thu (13/02) | 13 Feb 2025 | P43 |  | GCE preparation works
Thu (13/02) | 13 Feb 2025 | BR5 |  | All the 3 pump cars in use for the casting
Thu (13/02) | 13 Feb 2025 | Blk200 |  | Reading within allowable level
Thu (13/02) | 13 Feb 2025 | Blk 222 |  | Reading breach. Woh hup to control lorry movement
Thu (13/02) | 13 Feb 2025 | DW80 |  | Rebar cages lowering completed
Thu (13/02) | 13 Feb 2025 | DW115 |  | 1st bite excavation, reachex 14.5m
Thu (13/02) | 13 Feb 2025 | MH2-10 |  | Intermediate slab rebar inspection done. To cast today
Thu (13/02) | 13 Feb 2025 | BR5 |  | Continue casting. No issue of concrete supply. Concrete truck continue queuing
Thu (13/02) | 13 Feb 2025 | BR5/BR6 localised area |  | Rebar planting for waler brackets installation works
Thu (13/02) | 13 Feb 2025 | BR5 |  | Casting was completed ard noon, total vol: 1439m3. Now ongoing levelling works ongoing
Thu (13/02) | 13 Feb 2025 | ST199 | Rig 1 | B1 CD 28.4/28.5m
Thu (13/02) | 13 Feb 2025 | Exit 2 |  | RG preparing for inclinometer in-wall pipe
Thu (13/02) | 13 Feb 2025 | Exit 2 |  | Seongha rig idle. Unable to attach subsequent casing. Rectification ongoing
Thu (13/02) | 13 Feb 2025 | TDP39 |  | Preparing for casting. Rig has shifted to next boring point
Thu (13/02) | 13 Feb 2025 | ST154 | Rig 4 | WS trimming in progress
Thu (13/02) | 13 Feb 2025 | BRP69 | Rig 2 | B3 CD 15.0/29.4m
Thu (13/02) | 13 Feb 2025 | BP2-2 | 31 | Boring in progress, 32/36.42m
Thu (13/02) | 13 Feb 2025 | DW80 |  | Casting has completed with total volume of 80m3
Thu (13/02) | 13 Feb 2025 | DW115 | Rig 3 | B3 excavation paused due to damaged of cutter suction box
Thu (13/02) | 13 Feb 2025 | Exit 3 |  | Excavation ongoing for utility support works
Thu (13/02) | 13 Feb 2025 | Exit 3 |  | Welding works ongoing
Thu (13/02) | 13 Feb 2025 | BR6 |  | Chemical bolts installed. Tmr plan for pull out test
Thu (13/02) | 13 Feb 2025 | P43 |  | JGP works continue
Thu (13/02) | 13 Feb 2025 | MH2-10 |  | Intermediate slab construction in progress
Thu (13/02) | 13 Feb 2025 | MH2-9 |  | No activity
Fri (14/02) | 14 Feb 2025 | BR5 |  | Curing
Fri (14/02) | 14 Feb 2025 | ST199 | Rig 1 | B1 CD 21.5/28.55m
Fri (14/02) | 14 Feb 2025 | DR1 |  | No activity
Fri (14/02) | 14 Feb 2025 | Zone 4 |  | Portable water pipe laying reached to link up area. Newater pipe laying left around 6 to 7m to reach link up point
Fri (14/02) | 14 Feb 2025 | Exit 2 |  | Seongha rig rectification ongoing
Fri (14/02) | 14 Feb 2025 | ST154 | Rig 4 | Desanding in progress
Fri (14/02) | 14 Feb 2025 | BRP69 | Rig 2 | Desanding has completed, preparing for final koden check
Fri (14/02) | 14 Feb 2025 | P51 |  | Completed grouting for whichever can be done now. Left at pumping main area
Fri (14/02) | 14 Feb 2025 | DW115 | Rig 3 | The endplate has fully extracted
Fri (14/02) | 14 Feb 2025 | P43/ receiving shaft |  | Grouting target to complete by next week
Fri (14/02) | 14 Feb 2025 | P44 |  | Backfilling done
Fri (14/02) | 14 Feb 2025 | MH2-10 |  | Preparing for pipe joint
Fri (14/02) | 14 Feb 2025 | BR2 |  | Continue surface roughening
Fri (14/02) | 14 Feb 2025 | DR1 |  | Continue removing c-channel. Currently workers on tea break
Fri (14/02) | 14 Feb 2025 | ST199 |  | B2 in progress, 24.8/28.55m
Fri (14/02) | 14 Feb 2025 | Exit 2 |  | Seongha rig back in operation. Now ongoing drilling for O-65
Fri (14/02) | 14 Feb 2025 | BP2-2 | 31 | Boring in progress, 35/36.5m
Fri (14/02) | 14 Feb 2025 | Zone 4 |  | Exposing services to continue laying Newater pipe
Fri (14/02) | 14 Feb 2025 | Exit 3 |  | Continue manual excavation for utility support works
Fri (14/02) | 14 Feb 2025 | Compensation pile, BP6E-4A |  | Casing was unable to be installed. Continue preboring
Fri (14/02) | 14 Feb 2025 | Exit 3 |  | MPI test was done for S1 struts
Fri (14/02) | 14 Feb 2025 | P50 |  | TT on going two teams for preboring
Fri (14/02) | 14 Feb 2025 | P48 |  | TT for pipe sleeves installation
Fri (14/02) | 14 Feb 2025 | DW115 |  | Excavation done. Now machine servicing
Fri (14/02) | 14 Feb 2025 | BC cutter 2 |  | Teeth changing
Fri (14/02) | 14 Feb 2025 | BRP69 |  | 4/6 cages lowering in progress
Fri (14/02) | 14 Feb 2025 | DW54 |  | Waterstop end plate lowering down
Fri (14/02) | 14 Feb 2025 | BRP58A |  | Started excavation
Fri (14/02) | 14 Feb 2025 | BR5 |  | Waler end plate installation
Fri (14/02) | 14 Feb 2025 | BR2&3 |  | Exposing coupler
Fri (14/02) | 14 Feb 2025 | ST199 |  | 2nd bite, reached 27m
Fri (14/02) | 14 Feb 2025 | P17 |  | Soffit plywood for platform and cross head soffit formwork laying in progress
Fri (14/02) | 14 Feb 2025 | P6 |  | Column rebar in progress
Fri (14/02) | 14 Feb 2025 | MH2-10 |  | Intermediate slab cast yesterday. Now ongoing formwork dismantling
Fri (14/02) | 14 Feb 2025 | MH2-9 |  | No activity
Fri (14/02) | 14 Feb 2025 | BR2 |  | CJ roughening
Fri (14/02) | 14 Feb 2025 | Zone 2 |  | Water barrier delivery for stage 2 TD
Sat (15/02) | 15 Feb 2025 | N4-N5 |  | Falsework materials delivery. Preparing to erect
Sat (15/02) | 15 Feb 2025 | P6 |  | Column rebar work in progress
Sat (15/02) | 15 Feb 2025 | P3 |  | Exposing of pile head and clearing hardcore
Sat (15/02) | 15 Feb 2025 | P2 |  | TT for preboring
Sat (15/02) | 15 Feb 2025 | P5 |  | Column rebar cage fabrication
Sat (15/02) | 15 Feb 2025 | P48 |  | Current status of TT done
Sat (15/02) | 15 Feb 2025 | P51 |  | Current status of JGP done
Sat (15/02) | 15 Feb 2025 | P49 |  | TT on going. Two teams
Sat (15/02) | 15 Feb 2025 | P50 |  | TT and services protection
Sat (15/02) | 15 Feb 2025 | P51 |  | Balance water pipes laying
Sat (15/02) | 15 Feb 2025 | BC cutter 2 |  | Cutter teeth changing
Sat (15/02) | 15 Feb 2025 | DW81 |  | 1st bite, 13m reached
Sat (15/02) | 15 Feb 2025 | ST154 |  | Hanging bar preparation. Today to cast
Sat (15/02) | 15 Feb 2025 | BRP58A |  | 1st bite, reached 20m
Sat (15/02) | 15 Feb 2025 | BR5 |  | 7nos of waler bracket installed
Sat (15/02) | 15 Feb 2025 | DR1 |  | ERSS removal
Sat (15/02) | 15 Feb 2025 | BR2&3 |  | Woh hup continue clearing unused materials
Sat (15/02) | 15 Feb 2025 | Exit 3 |  | Hirose doing housekeeping and clearing unused materials
Sat (15/02) | 15 Feb 2025 | Exit 3/ CCW |  | Continue exposing utility for supporting
Sat (15/02) | 15 Feb 2025 | P17 |  | Wingform installation in progress
Sat (15/02) | 15 Feb 2025 | N4-N5 |  | Falsework erection
Sat (15/02) | 15 Feb 2025 | P6 |  | Current status of column rebar work
Sat (15/02) | 15 Feb 2025 | P5 |  | Rebar cage fabrication
Sat (15/02) | 15 Feb 2025 | P2 |  | ERSS installation
Sat (15/02) | 15 Feb 2025 | P3 |  | Clearing soil around piles
Sat (15/02) | 15 Feb 2025 | DR1 |  | ERSS removal using vibro
Sat (15/02) | 15 Feb 2025 | ST199 |  | Cleaning and desanding
Sat (15/02) | 15 Feb 2025 | Exit 2 & near JTC |  | Seongha provide two rigs for fissure grouting
Sat (15/02) | 15 Feb 2025 | Exit 3 |  | Hirose no more activity
Sat (15/02) | 15 Feb 2025 | Exit 3 |  | Clearing debris
Sat (15/02) | 15 Feb 2025 | BP2-2 | 31 | Casting in progress
Sat (15/02) | 15 Feb 2025 | DR1 |  | LE no more activity
Sat (15/02) | 15 Feb 2025 | BR5 |  | No activity. 7nos waler brackets were installed
Sat (15/02) | 15 Feb 2025 | BC4 |  | Currently no activity
Sat (15/02) | 15 Feb 2025 | DW81 | BC3 | B2 in progress
Sat (15/02) | 15 Feb 2025 | ST132 | BC2 | B2 in progress
Sat (15/02) | 15 Feb 2025 | P43 |  | GCE continue JGP works. Tonight plan 2 points
Sat (15/02) | 15 Feb 2025 | ST199 |  | Final koden checking in progress
Sat (15/02) | 15 Feb 2025 | Exit 3 |  | Covering stockpile with canvas. No other activity
Sat (15/02) | 15 Feb 2025 | BP6E-4A |  | Boring done for the day. CD 26/39.89m. Hit rock at 24m depth
Sat (15/02) | 15 Feb 2025 | Exit 3 |  | Install bolts on the struts
Sat (15/02) | 15 Feb 2025 | P17 |  | Crosshead formwork installation
Sat (15/02) | 15 Feb 2025 | BP2-2 | 31 | Boring completed
Sat (15/02) | 15 Feb 2025 | P10 |  | Telco duct, 18m pending to cast
Sat (15/02) | 15 Feb 2025 | P17 |  | One side soffit formwork installed. Prepare for the balance side
Sun (16/02) | 16 Feb 2025 | BP2-2 | 31 | Casting was completed ard 2343hrs
Sun (16/02) | 16 Feb 2025 | P17 |  | Wendyng briefing done for wingform installation works
Sun (16/02) | 16 Feb 2025 | ST154 |  | Casting in progress
Sun (16/02) | 16 Feb 2025 | P43 |  | First point completed. Now preparing 2nd point
Sun (16/02) | 16 Feb 2025 | DW81 & ST132 |  | B2 in progress
Sun (16/02) | 16 Feb 2025 | ST197 | BC1 | B1 now in progress, ST199: Rebar cage lowering
Sun (16/02) | 16 Feb 2025 | P17 |  | Boomlift cleared from bus lane
Sun (16/02) | 16 Feb 2025 | ST154 |  | Casting ongoing
Mon (17/02) | 17 Feb 2025 | MH2-10 |  | Rebar works for next lift. Today plan to cast
Mon (17/02) | 17 Feb 2025 | MH2-9 |  | No activity. Manpower at MH1-2. Now only shifting of formwork materials
Mon (17/02) | 17 Feb 2025 | BR5 |  | Wendyng drilling ongoing for starter bar installation for DR1
Mon (17/02) | 17 Feb 2025 | BR6 |  | Currently no activity
Mon (17/02) | 17 Feb 2025 | BRP76A | BC4 | B1 in progress
Mon (17/02) | 17 Feb 2025 | Zone 4 |  | Ley Choon no activity during day shift. Today onward will be night shift for balance water pipe laying
Mon (17/02) | 17 Feb 2025 | Zone 4 |  | Wee Guan mobilizing for Power Manhole
Mon (17/02) | 17 Feb 2025 | BC3 |  | Currently no activity
Mon (17/02) | 17 Feb 2025 | ST132 | BC2 | Cutter teeth changing & c-lug welding ongoing
Mon (17/02) | 17 Feb 2025 | DR1 |  | Continue removal of steel plates and soldier piles
Mon (17/02) | 17 Feb 2025 | BR1, BR2 |  | No activity
Mon (17/02) | 17 Feb 2025 | ST197 | BC1 | B2 in progress
Mon (17/02) | 17 Feb 2025 | PRD3 |  | Pavement hacking for pipe installation for J-eye shifting
Mon (17/02) | 17 Feb 2025 | P49 |  | Two numbers of TT done for preboring
Mon (17/02) | 17 Feb 2025 | Zone 4 |  | Current status of stockpile
Mon (17/02) | 17 Feb 2025 | P17 |  | Crosshead rebar works in progress
Mon (17/02) | 17 Feb 2025 | Zone 2 |  | Footpath casting in progress, 57m
Mon (17/02) | 17 Feb 2025 | Z2 north bound side |  | Hoarding installation behind bus stop
Mon (17/02) | 17 Feb 2025 | Near P11 |  | Soil backfilling and levelling works
Mon (17/02) | 17 Feb 2025 | S3 |  | Formwork dismantling ongoing
Mon (17/02) | 17 Feb 2025 | BP6E-4A |  | Boring works continue till 10pm
Mon (17/02) | 17 Feb 2025 | BP2-1 | 54 | Boring in progress, 24m
Mon (17/02) | 17 Feb 2025 | Near exit 3 |  | Hirose continue welding works at UKP area
Mon (17/02) | 17 Feb 2025 | ST197 | BC1 | Cutter wheel cleaning ongoing. B2 CD 21/32.75m
Mon (17/02) | 17 Feb 2025 | BR5 |  | Exposing starter bars for DR1. Tmr plan to start dismantling side formwork
Mon (17/02) | 17 Feb 2025 | MH2-10 |  | Casting ongoing
Tue (18/02) | 18 Feb 2025 | BR5 |  | Continue exposing starter bars for DR1 connection works & formwork dismantling ongoing
Tue (18/02) | 18 Feb 2025 | BR6 |  | Today plan for MPI test and 2nos waler beams to instal
Tue (18/02) | 18 Feb 2025 | DW79 |  | Guidewall construction in progress
Tue (18/02) | 18 Feb 2025 | DW76A |  | Cleaning and desanding completed
Tue (18/02) | 18 Feb 2025 | BC4 |  | Machine checking ongoing before dismantling works
Tue (18/02) | 18 Feb 2025 | ST132 | BC2 | WS trimming ongoing
Tue (18/02) | 18 Feb 2025 | DW116 | BC3 | B2 in progress
Tue (18/02) | 18 Feb 2025 | P43 |  | JGP in progress, point A-23
Tue (18/02) | 18 Feb 2025 | P44 |  | No activity
Tue (18/02) | 18 Feb 2025 | P48-46 |  | Trial trench ongoing for pipe sleeve installation
Tue (18/02) | 18 Feb 2025 | Zone 4 |  | UKP14, UKP16 trial trench
Tue (18/02) | 18 Feb 2025 | Zone 4 PMH24 |  | Wee Guan on site. Current works location is nearby gas pipe and water pipe
Tue (18/02) | 18 Feb 2025 | MH3-5 |  | Backfilling
Tue (18/02) | 18 Feb 2025 | DR1 |  | ERSS removal
Tue (18/02) | 18 Feb 2025 | BR1, BR2 |  | No activity
Tue (18/02) | 18 Feb 2025 | ST197 | BC1 | B2 in progress, 23/32.75m
Tue (18/02) | 18 Feb 2025 | Exit 2 |  | Fissure grouting works in progress, Oa-7
Tue (18/02) | 18 Feb 2025 | BRP17 |  | Testing in progress. Now loading at 50% for 1hr
Tue (18/02) | 18 Feb 2025 | BP2B-1 | 54 | Boring in progress
Tue (18/02) | 18 Feb 2025 | BP2-2 | 31 | LSS backfill
Tue (18/02) | 18 Feb 2025 | Exit 3 |  | Utility support welding works ongoing
Tue (18/02) | 18 Feb 2025 | Exit 3 |  | Hacking ongoing for utility stump works
Tue (18/02) | 18 Feb 2025 | BP6E-4A |  | Boring in progress, 32m/39.89m
Tue (18/02) | 18 Feb 2025 | MH2-10 |  | LSS backfilling ongoing
Tue (18/02) | 18 Feb 2025 | MH2-9 |  | 1nos precast chamber has been installed
Tue (18/02) | 18 Feb 2025 | BR5 |  | Continue exposing starter bars for DR1 connection works, Formwork dismantling ongoing, Progressively installing toe boards
Tue (18/02) | 18 Feb 2025 | BR6 |  | Preparing for localised excavation for strut installation. Waler beam plan for installation tmr
Tue (18/02) | 18 Feb 2025 | BRP76A |  | Rebar cage lapping ongoing
Tue (18/02) | 18 Feb 2025 | P43 |  | JGP progress
Tue (18/02) | 18 Feb 2025 | MH3-5 |  | Backfilling completed
Tue (18/02) | 18 Feb 2025 | P48-46 |  | Pipe sleeve installed. Backfilling ongoing
Tue (18/02) | 18 Feb 2025 | PMH24 |  | Trial trench ongoing
Tue (18/02) | 18 Feb 2025 | P5 |  | NDT ongoing for backfilling works
Tue (18/02) | 18 Feb 2025 | P3 |  | Extraction for s2 layer
Tue (18/02) | 18 Feb 2025 | P2 |  | Preboring and ERSS installation
Tue (18/02) | 18 Feb 2025 | P6-1 |  | Tie rod installation
Tue (18/02) | 18 Feb 2025 | BP6E-4A |  | Boring in progress, 33.5/39.89m, Preparing to set up noise balloon
Tue (18/02) | 18 Feb 2025 | Exit 2 |  | Preparation works for next dwall panel ST214 excavation
Tue (18/02) | 18 Feb 2025 | BP2B-1 | 54 | Boring in progress, 32/35.49m
Tue (18/02) | 18 Feb 2025 | ST197 | BC1 | Gearbox changing ongoing. B2 CD 23/32.75m
Tue (18/02) | 18 Feb 2025 | Near BR1 |  | KTC trimming lean concrete for backfilling works
Tue (18/02) | 18 Feb 2025 | BR5 |  | Continue exposing starter bars, Formwork dismantling
Tue (18/02) | 18 Feb 2025 | BR6 |  | Localised excavation in progress
Tue (18/02) | 18 Feb 2025 | ST132 | BC2 | Cleaning in progress, DW116: Rebar cage lapping, 3/4nos, DW82 (BC3): B1 in progress
Tue (18/02) | 18 Feb 2025 | BRP76A |  | Tremie pipe lowering
Tue (18/02) | 18 Feb 2025 | MH2-10 |  | Formwork dismantling. Today plan for LSS backfill
Tue (18/02) | 18 Feb 2025 | MH2-9 |  | Today plan to install balance precast chamber. Now ongoing barricade removal inside MH to facilitate works
Wed (19/02) | 19 Feb 2025 | PMH24 |  | Wee Guan prepare for PLT
Wed (19/02) | 19 Feb 2025 | P49 |  | TT on going for preboring with two teams
Wed (19/02) | 19 Feb 2025 | S1-1 |  | Current status of beams installation
Wed (19/02) | 19 Feb 2025 | P48 JGP TT |  | Left 8 points to complete
Wed (19/02) | 19 Feb 2025 | MH1-2 |  | To clear hardcore today
Wed (19/02) | 19 Feb 2025 | P48 |  | Left 6nos of point to install pipe sleeves
Wed (19/02) | 19 Feb 2025 | P49 |  | Continue TT for preboring work. Two teams
Wed (19/02) | 19 Feb 2025 | MH2-9 |  | Balance precast chamber and top slab installed
Wed (19/02) | 19 Feb 2025 | MH2-10 |  | Wall rebar works ongoing for last lift of in-situ wall
Wed (19/02) | 19 Feb 2025 | BR5 |  | Continue exposing starter bars for DR1 connection, Formwork dismantling ongoing. Once formwork all dismantled, RTO will be called for surface inspection
Wed (19/02) | 19 Feb 2025 | BR6 |  | 1nos waler beam installed, Barricade installation ongoing, Unsound concrete observed at panel ST162. WH to advise rectification method
Wed (19/02) | 19 Feb 2025 | ST132 |  | Rebar cage lapping in progress, DW82 (BC3): B2 in progress, BC2: No activity
Wed (19/02) | 19 Feb 2025 | BC4 |  | Noise barrier panel dismantling
Wed (19/02) | 19 Feb 2025 | BR2 |  | No activity
Wed (19/02) | 19 Feb 2025 | DR1 |  | Soldier pile extraction in progress
Wed (19/02) | 19 Feb 2025 | BR1 |  | Slope trimming ongoing
Wed (19/02) | 19 Feb 2025 | P17 |  | Continue rebar and PT duct installatio
Wed (19/02) | 19 Feb 2025 | Opp P6 |  | Premix removal ongoing for diversion works
Wed (19/02) | 19 Feb 2025 | P6 |  | Column formwork installation
Wed (19/02) | 19 Feb 2025 | BP6E-4A |  | Boring reached 35/39.89m
Wed (19/02) | 19 Feb 2025 | S1-1 |  | Formwork closing for 1nos utility stump, 2nos primary beam installation
Wed (19/02) | 19 Feb 2025 | BR1 |  | Backfilling works ongoing
Wed (19/02) | 19 Feb 2025 | BR5 |  | Continue formwork removal and exposing starter bars
Wed (19/02) | 19 Feb 2025 | BR6 |  | No activity
Thu (20/02) | 20 Feb 2025 | PMH25 |  | Wee Guan marking for PLT testing
Thu (20/02) | 20 Feb 2025 | P49 |  | Continue TT for preboring work
Thu (20/02) | 20 Feb 2025 | P48 |  | JGP grouting in progress. Last night completed 2nos
Thu (20/02) | 20 Feb 2025 | BR1 |  | Backfilling and NDT
Thu (20/02) | 20 Feb 2025 | BR5 |  | Continue bottom formwork removal & exposing starter bars for drain connection
Thu (20/02) | 20 Feb 2025 | BR6 |  | Currently no activity
Thu (20/02) | 20 Feb 2025 | BP2B-1 | 54 | Boring reached toe level. Today to cast
Thu (20/02) | 20 Feb 2025 | Blk 2 |  | Seongha continue fissure grouting works
Thu (20/02) | 20 Feb 2025 | Rig 2 |  | Changing of cutter head width from 1200mm to 800mm
Thu (20/02) | 20 Feb 2025 | Rig 4 |  | Dismantling of noise panels for its demobilisation
Thu (20/02) | 20 Feb 2025 | Rig 3 |  | Idling on site
Thu (20/02) | 20 Feb 2025 | DW82 |  | Preparing for final koden check
Thu (20/02) | 20 Feb 2025 | ST132 |  | : Casting in progress
Thu (20/02) | 20 Feb 2025 | Exit 3 |  | Soil trimming to expose water pipe
Thu (20/02) | 20 Feb 2025 | S1-1 |  | Continue excavation for utility support works, 1nos utility stump cast last night
Thu (20/02) | 20 Feb 2025 | BP6E-4A |  | Boring in progress, 33.8/39.89m
Thu (20/02) | 20 Feb 2025 | MH3-4 |  | Lehoboth prepare to remove caisson
Thu (20/02) | 20 Feb 2025 | P6-1 |  | Scaffold installation for column casting tmr
Thu (20/02) | 20 Feb 2025 | P3 |  | Continue s2 ERSS extraction works
Thu (20/02) | 20 Feb 2025 | P48 |  | Balance only two pipe sleeves to install
Thu (20/02) | 20 Feb 2025 | P48 |  | Continue JGP grouting. 2nd point in progress
Thu (20/02) | 20 Feb 2025 | P50 |  | Checking of SPPG cable joint location
Thu (20/02) | 20 Feb 2025 | P1 test pile |  | Area preparation for hacking
Thu (20/02) | 20 Feb 2025 | MH2-10 |  | Inspection for in-situ wall last lift. To cast today
Thu (20/02) | 20 Feb 2025 | MH2-9 |  | No activity
Thu (20/02) | 20 Feb 2025 | ST197 | BC1 | B2 in progress, 30.8/32.75m
Fri (21/02) | 21 Feb 2025 | P17 crosshead |  | Section 2 and 3 installation of girder box rebar and PT duct support
Fri (21/02) | 21 Feb 2025 | P13 |  | Excavation for pad footing foundation
Fri (21/02) | 21 Feb 2025 | P12-8 |  | W3B laying
Fri (21/02) | 21 Feb 2025 | MH2-10 |  | Last lift casting in progress. Yesterday didn’t cast as there was some adjustments and cleaning to do
Fri (21/02) | 21 Feb 2025 | MH2-10 |  | Precast chambers delivered to site today. Balance 2 more to be delivered
Fri (21/02) | 21 Feb 2025 | MH2-9 |  | Preparing for some chamber adjustments
Fri (21/02) | 21 Feb 2025 | Zone 1 island of current bus lane |  | Kerb hacking for TD 2. Tonight street light post will remove
Fri (21/02) | 21 Feb 2025 | P49 |  | TT for preboring work
Fri (21/02) | 21 Feb 2025 | Zone 4 |  | Ley Choon TT for balance Newater pipe laying work. All services need to undercross toward link up area
Fri (21/02) | 21 Feb 2025 | P2 |  | Driving SP and LP 1m below ground level
Fri (21/02) | 21 Feb 2025 | BR1 |  | Continue backfilling
Fri (21/02) | 21 Feb 2025 | BR6 |  | 2/7nos raker struts installed
Fri (21/02) | 21 Feb 2025 | BR5 |  | Rebar works for flood wall in progress, Rebar works and formwork installation for DR1 connection works
Fri (21/02) | 21 Feb 2025 | P48 |  | Left two points to complete pipe sleeves work
Fri (21/02) | 21 Feb 2025 | P48 |  | 10th point grouting in progress
Fri (21/02) | 21 Feb 2025 | MH3-4 |  | Caisson hacking on going. CCTV inspection was done this morning
Sat (22/02) | 22 Feb 2025 | P17 |  | Tendom duct installation
Sat (22/02) | 22 Feb 2025 | P8 to P12 |  | Preparing for lane marking
Sat (22/02) | 22 Feb 2025 | P3 |  | Clearing debris
Sat (22/02) | 22 Feb 2025 | P5 |  | CJ roughening
Sat (22/02) | 22 Feb 2025 | P48 |  | Marking and checking of water pipe and JGP grouting area
Sat (22/02) | 22 Feb 2025 | Zone 4 |  | Left around 7m to 8m to complete Newater pipe laying. Today target to complete
Sat (22/02) | 22 Feb 2025 | MH3-4 |  | Caisson removal
Sat (22/02) | 22 Feb 2025 | P44 |  | Vibro mobilized. Ryobi G rig also here ready
Sat (22/02) | 22 Feb 2025 | BR5 |  | CJ hyrib removal
Sat (22/02) | 22 Feb 2025 | ST197 |  | Rebar cage lowering in progress
Sat (22/02) | 22 Feb 2025 | ST214 |  | 1st bite excavation in progress, 23m
Sat (22/02) | 22 Feb 2025 | P17 |  | Tendom duct installation and formwork bolt tightening
Sat (22/02) | 22 Feb 2025 | Premix work near slip road will be around 5 | pasir ris dr3 | 30 or 6PM. Now doing premix work at other end
Sat (22/02) | 22 Feb 2025 | P5 |  | Column CJ roughening
Sat (22/02) | 22 Feb 2025 | P3 |  | Prepare for rebar work
Sat (22/02) | 22 Feb 2025 | P1 |  | As of now no activity
Sat (22/02) | 22 Feb 2025 | Exit 3/Station |  | Utility support installation
Sat (22/02) | 22 Feb 2025 | ST214 |  | Cutter teeth changing
Sat (22/02) | 22 Feb 2025 | MH2-10 |  | LSS backfilling around complete caisson
Sat (22/02) | 22 Feb 2025 | MH2-9 |  | Formwork closed for caisson casting
Sat (22/02) | 22 Feb 2025 | P14 to P19 |  | M&P works in progress for W3B layer
Sat (22/02) | 22 Feb 2025 | P17 |  | Rebar, tendon ducts and RWDP installation in progress
Sat (22/02) | 22 Feb 2025 | ST214 |  | 1st bite excavation in progress, 30m depth
Sat (22/02) | 22 Feb 2025 | ST197 |  | Hanging bar lapping ongoing
Sat (22/02) | 22 Feb 2025 | DW079 |  | Waterstop side trimming in progress
Sat (22/02) | 22 Feb 2025 | Zone 4 |  | Work stopped for the day. No activity
Sun (23/02) | 23 Feb 2025 | ST214 |  | 1st bite excavation temporary stopped. To change wheel teeth. Current depth 31.8m
Sun (23/02) | 23 Feb 2025 | ST197 |  | Tremie pipe installation ongoing
Sun (23/02) | 23 Feb 2025 | DW079 |  | Continue trimming works, current depth 20m
Sun (23/02) | 23 Feb 2025 | P17 |  | Rebar installation for crosshead ongoing
Sun (23/02) | 23 Feb 2025 | P8 to P6 |  | Premix laying and M&P works in progress
Sun (23/02) | 23 Feb 2025 | Loyang Ave - PRD3 junction |  | Traffic light shifting in progress. APO provided
Sun (23/02) | 23 Feb 2025 | P3 |  | Pile cap bottom rebar works in progress
Sun (23/02) | 23 Feb 2025 | Stage 2 TD |  | Preparation for lane opening for bus-only lane
Sun (23/02) | 23 Feb 2025 | P3 |  | Pile cap rebar installation
Sun (23/02) | 23 Feb 2025 | ST214 |  | Resumed 1st bite trenching works. Current depth 32.5m
Sun (23/02) | 23 Feb 2025 | ST197 |  | Casting in progress
Sun (23/02) | 23 Feb 2025 | DW079 |  | WS trimming completed
Mon (24/02) | 24 Feb 2025 | P17 |  | Installation of cast-in anchor and preparation for final inspection. Target to cast crosshead tmr
Mon (24/02) | 24 Feb 2025 | P3 |  | Rebar installation for pile cap
Mon (24/02) | 24 Feb 2025 | MH2-10 |  | 2nos precast chambers installed. Outer wall casting ongoing
Mon (24/02) | 24 Feb 2025 | MH2-9 |  | No activity
Mon (24/02) | 24 Feb 2025 | BP2B-2 | 50 | Boring in progress, 31/37.95m
Mon (24/02) | 24 Feb 2025 | BR1, BR2 |  | Hardcore laying, Compaction ongoing, Barricade and toe board installation, Guidewall to be hacked
Mon (24/02) | 24 Feb 2025 | BR5 |  | Formwork closing for DR1 connection. Tmr plan for casting, Flood wall formwork closing at temporary construction opening. Tmr plan for casting
Mon (24/02) | 24 Feb 2025 | BR6 |  | No activity. MPI test was done just now
Mon (24/02) | 24 Feb 2025 | DW79 |  | WS joint welding ongoing
Mon (24/02) | 24 Feb 2025 | P48-30 |  | JGP grouting ongoin
Mon (24/02) | 24 Feb 2025 | P50-05 |  | Casing installation
Tue (25/02) | 25 Feb 2025 | BR6 |  | Currently no activity
Tue (25/02) | 25 Feb 2025 | BR5 |  | Drain wall formwork closing ongoing & flood wall formwork closing. Both plan for casting today
Tue (25/02) | 25 Feb 2025 | DW118 | Rig 2 | B1 CD 15.7/21.1m
Tue (25/02) | 25 Feb 2025 | P48 |  | JGP grouting in progress, 17nos completed as of today
Tue (25/02) | 25 Feb 2025 | P49 |  | TT for UKP
Tue (25/02) | 25 Feb 2025 | P50 |  | UKP boring in progress. Today will cast one number
Tue (25/02) | 25 Feb 2025 | P44 |  | Waler cutting and removal
Tue (25/02) | 25 Feb 2025 | MH2-10 |  | 2nos precast chambers installed yesterday and wall cast. Now formwork dismantling. Balance 4 more precast chambers to be installed
Tue (25/02) | 25 Feb 2025 | MH2-9 |  | No activity
Wed (26/02) | 26 Feb 2025 | Zone 2 |  | Patching of D1 Kerbs
Wed (26/02) | 26 Feb 2025 | P19 |  | Premix and hardcore removal for upcoming BP works
Wed (26/02) | 26 Feb 2025 | P17 |  | Crosshead cast yesterday
Wed (26/02) | 26 Feb 2025 | P13 |  | Premix removal for p13 falsework installation
Wed (26/02) | 26 Feb 2025 | BR6 |  | No activity. Waiting for UT test and then preloading. WH target to start excavation this week
Wed (26/02) | 26 Feb 2025 | DW118 | BC2 | Preparing for WS trimming
Wed (26/02) | 26 Feb 2025 | P6-1 |  | Column formwork removal
Wed (26/02) | 26 Feb 2025 | Near P6-1 |  | Tactile installation in progress
Wed (26/02) | 26 Feb 2025 | P44 |  | Current status of waler removal
Wed (26/02) | 26 Feb 2025 | P1 |  | Trial trench for ERSS preboring in progress
Wed (26/02) | 26 Feb 2025 | P3 |  | Pile cap rebars installation
Wed (26/02) | 26 Feb 2025 | BP2B-2 | 50 | Toe level check by RTO. Depth reached 38.1m. Today to cast
Wed (26/02) | 26 Feb 2025 | Blk 2 |  | 1 rig working for fissure grouting works
Wed (26/02) | 26 Feb 2025 | DW24-25 |  | Capping beam cast
Wed (26/02) | 26 Feb 2025 | S1-1 |  | Manual excavation below services
Wed (26/02) | 26 Feb 2025 | MH2-9 |  | Ladder cage remove to facilitate access installation for MH lining works
Wed (26/02) | 26 Feb 2025 | MH2-10 |  | 2nos precast chambers installed. Total 4nos installed, balance 2nos. Outer wall formwork installation ongoing
Wed (26/02) | 26 Feb 2025 | Exit 3 |  | Dwall hacking ongoing
Wed (26/02) | 26 Feb 2025 | P19 |  | Continue premix and hardcore removal
Wed (26/02) | 26 Feb 2025 | P6 |  | Column formwork dismantling
Wed (26/02) | 26 Feb 2025 | P3 |  | Continue pile cap rebar works
Wed (26/02) | 26 Feb 2025 | P1 |  | Trial trench completed for the day. Tmr to continue. SPPG cable nearby
Wed (26/02) | 26 Feb 2025 | GL W5 |  | Excavation to expose dwall
Wed (26/02) | 26 Feb 2025 | Exit 3 | near gate 5 | Trimming ongoing along water pipe alignment. Manual excavation will be done at the water pipe area
Wed (26/02) | 26 Feb 2025 | BP2B-2 | 50 | Rebar cage and KP installed. Preparing for casting, ST214 (BC1): Cutter teeth changing
Wed (26/02) | 26 Feb 2025 | BR1, BR2 |  | Access hardcore backfilling
Wed (26/02) | 26 Feb 2025 | DW118 | BC2 | Desanding ongoing
Wed (26/02) | 26 Feb 2025 | SW23 |  | Slurry wall removal completed. Now adjusting platform for LSS backfill
Wed (26/02) | 26 Feb 2025 | MH2-10 |  | Formwork dismantling ongoing. LSS backfill yesterday. Another 2 precast chambers plan for installation today
Wed (26/02) | 26 Feb 2025 | MH2-9 |  | No activity
Wed (26/02) | 26 Feb 2025 | Exit 3 | near gate 5 | Manual excavation below water pipe and retaining wall works
Wed (26/02) | 26 Feb 2025 | BR1, BR2 access |  | Hardcore hacking, hardcore platform laying ongoing
Wed (26/02) | 26 Feb 2025 | BR5 |  | Both drain wall connection and flood wall cast yesterday
Wed (26/02) | 26 Feb 2025 | P48 |  | JGP grouting in progress, 19nos finish up to date
Wed (26/02) | 26 Feb 2025 | P49 |  | Balance one number for preboring in progress
Wed (26/02) | 26 Feb 2025 | P50 |  | 1st point UKP installed. Today plan for 2 numbers
Thu (27/02) | 27 Feb 2025 | MH2-9 |  | Currently no activity. Today plan to start lining works after lunch
Thu (27/02) | 27 Feb 2025 | BR1, BR2 |  | Access hardcore backfilling and slope excavation ongoing
Thu (27/02) | 27 Feb 2025 | P48 |  | Continue JGP grouting
Thu (27/02) | 27 Feb 2025 | P48 & P49 |  | Two locations: removal of 22KV cable slab at joint bay area. Tomorrow SPPG want to come and see the condition
Thu (27/02) | 27 Feb 2025 | P50 |  | Removal of old gas pipe for UKP boring work
Thu (27/02) | 27 Feb 2025 | P16 |  | Preparation for PLT
Thu (27/02) | 27 Feb 2025 | P13 |  | Preparation for pad footing installation for falsework
Thu (27/02) | 27 Feb 2025 | BR5, BR6 |  | Currently no activity
Thu (27/02) | 27 Feb 2025 | DW79A |  | B1 in progress, MC86 rig dismantling
Thu (27/02) | 27 Feb 2025 | DW118 |  | Rebar cage lapping in progress
Thu (27/02) | 27 Feb 2025 | P43 receiving shaft |  | RG drilling ongoing for inclinometer in-soil
Thu (27/02) | 27 Feb 2025 | SW23 |  | LSS backfill yesterday
Thu (27/02) | 27 Feb 2025 | P5 |  | Crane setting up for P5 column rebar installation
Thu (27/02) | 27 Feb 2025 | P3 |  | Shear link installation in progress for pile cap. Target to cast tmr
Thu (27/02) | 27 Feb 2025 | P1 |  | Trial trench works for P1 ERSS
Thu (27/02) | 27 Feb 2025 | MH2-10 |  | LSS backfilling ongoing. Waiting for next truc
Thu (27/02) | 27 Feb 2025 | MH2-9 |  | Currently no activity
Thu (27/02) | 27 Feb 2025 | BR2 |  | Hardcore laying in progress
Thu (27/02) | 27 Feb 2025 | Exit 3 |  | KTC preparation for ramp making
Thu (27/02) | 27 Feb 2025 | P19 |  | Trial trench for BP
Thu (27/02) | 27 Feb 2025 | BR5 |  | Housekeeping
Thu (27/02) | 27 Feb 2025 | DW118 |  | Preparing for casting
Thu (27/02) | 27 Feb 2025 | SW14 |  | Slurry wall removal ongoing, 2/15 panels completed
Thu (27/02) | 27 Feb 2025 | DW79A |  | Continue B1 excavation
Thu (27/02) | 27 Feb 2025 | MC86 |  | Continue dismantling works
Thu (27/02) | 27 Feb 2025 | P48 |  | Checking of pipe sleeves before start boring for JGP
Thu (27/02) | 27 Feb 2025 | P50 |  | Boring for utility support in progress
Thu (27/02) | 27 Feb 2025 | BR6 |  | Exposing top end plate for last short member support. Thereafter to start preloading
Thu (27/02) | 27 Feb 2025 | P15 |  | Hacking for rectification works ongoing
Thu (27/02) | 27 Feb 2025 | P6-1 |  | Patching works in progress
Thu (27/02) | 27 Feb 2025 | P5 |  | Column rebar cage installed. Propping installation ongoing
Thu (27/02) | 27 Feb 2025 | P3 |  | Continue shear links and formwork closing for pile cap
Thu (27/02) | 27 Feb 2025 | P1 |  | Trial trench for ERSS
Thu (27/02) | 27 Feb 2025 | ST214 | BC1 | B3 in progress
Thu (27/02) | 27 Feb 2025 | Blk 2 |  | Seongha has completed 3 grouting points. Now housekeeping and shift materials to next location near exit 2 desander
Thu (27/02) | 27 Feb 2025 | Exit 3 |  | Exposing guidewall to facilitate utility support works
Thu (27/02) | 27 Feb 2025 | S1-1 |  | No activity
Thu (27/02) | 27 Feb 2025 | P44 |  | Soil backfilling for ERSS removal
Thu (27/02) | 27 Feb 2025 | P46 |  | Excavation done for water pipe laying
Thu (27/02) | 27 Feb 2025 | GL W7 |  | Exposing dwall ongoing
Thu (27/02) | 27 Feb 2025 | Exit 3 |  | Dwall hacking ongoing
Thu (27/02) | 27 Feb 2025 | P19 |  | Trial trench
Thu (27/02) | 27 Feb 2025 | P13 |  | Preparing platform for crane parkin
Thu (27/02) | 27 Feb 2025 | P9 |  | Crosshead surface grinding
Thu (27/02) | 27 Feb 2025 | Between Z2/Z3 walking access |  | Netlink cable pulling
Thu (27/02) | 27 Feb 2025 | GL W8 |  | HSL removing bentonite pipes
Thu (27/02) | 27 Feb 2025 | Exit 3 |  | Soil disposal & manual clearing of soil below water pipe
Thu (27/02) | 27 Feb 2025 | ST214 |  | B3 completed. Now preparing for WS trimming
Thu (27/02) | 27 Feb 2025 | BR2 |  | No activity
Thu (27/02) | 27 Feb 2025 | MH2-10 |  | Formwork dismantling. Today to backfill LSS. Balance 1 precast chamber and reducer slab
Fri (28/02) | 28 Feb 2025 | P48 |  | JGP grouting at center and woh hup TT near TPE bound for preboring
Fri (28/02) | 28 Feb 2025 | ST214 | Rig 1 | WS trimming in progress, CD 35.0/42.4m
Fri (28/02) | 28 Feb 2025 | DW79A | Rig 2 | B2 CD 21.7/22.1m, now changing of cutter teeth
Fri (28/02) | 28 Feb 2025 | BR5 |  | Flood wall formwork dismantling, BR6: Raker strut preloading in progress
Fri (28/02) | 28 Feb 2025 | BR2 |  | Continue hardcore laying
Fri (28/02) | 28 Feb 2025 | P44 |  | Plan to complete backfilling today
Fri (28/02) | 28 Feb 2025 | P19 |  | Trial trench for BP in progress
Fri (28/02) | 28 Feb 2025 | P16 |  | Formwork assembly works
Fri (28/02) | 28 Feb 2025 | MH2-10 |  | Precast chamber and reducer slab installation
Fri (28/02) | 28 Feb 2025 | MH2-9 |  | Preparation for lining works
Fri (28/02) | 28 Feb 2025 | Exit 3 | near gate 5 | Retaining wall formwork dismantling
Fri (28/02) | 28 Feb 2025 | Exit 3 |  | Continue exposing barette pile guidewall
Fri (28/02) | 28 Feb 2025 | P48 |  | Woh hup provided two teams for trial trench
Fri (28/02) | 28 Feb 2025 | P48 |  | GCE preparing the area for next point grouting
Fri (28/02) | 28 Feb 2025 | P50 |  | Setting out for preboring. Target two points for today
Fri (28/02) | 28 Feb 2025 | BR5 |  | Continue dismantling formwork for flood wall and drain wall
Fri (28/02) | 28 Feb 2025 | BR6 |  | No activity. Preloading couldn’t achieve above 90% when at 100% load. Pending way forward
Fri (28/02) | 28 Feb 2025 | P43 |  | RG continue drilling for inclinometer in-soil
Fri (28/02) | 28 Feb 2025 | P14 |  | Side gate installation
Fri (28/02) | 28 Feb 2025 | P13 |  | Falsework work installation in progress
Fri (28/02) | 28 Feb 2025 | P10 |  | Rectification works ongoing
Fri (28/02) | 28 Feb 2025 | P1 |  | Trial trench for ERSS installation
Fri (28/02) | 28 Feb 2025 | P5 |  | RWDP installation works
Fri (28/02) | 28 Feb 2025 | P3 |  | Pile cap to cast tmr
Fri (28/02) | 28 Feb 2025 | BR1 |  | Laying steel plates
Fri (28/02) | 28 Feb 2025 | Near exit 2 desander |  | Seongha preparing area for next fissure grouting works
Fri (28/02) | 28 Feb 2025 | ST214 | BC1 | Repairing suction hose, DW39: Trial trench
Fri (28/02) | 28 Feb 2025 | S1-1 |  | No activity
Fri (28/02) | 28 Feb 2025 | GL W7-W8 |  | Exposing dwall. Now ongoing soil disposal
Fri (28/02) | 28 Feb 2025 | Near exit 3 desander |  | KTC backfilling and compaction for new vehicle ramp access
Fri (28/02) | 28 Feb 2025 | SW19 |  | Continue removal of clayshot
Fri (28/02) | 28 Feb 2025 | BR5 |  | 2 Raker strut preloading achieve 90% already
Fri (28/02) | 28 Feb 2025 | BC cutter 1 |  | Cutter teeth maintenance
Fri (28/02) | 28 Feb 2025 | P13 |  | Runner installation
Fri (28/02) | 28 Feb 2025 | P3 |  | Formwork preparation
Fri (28/02) | 28 Feb 2025 | P48 |  | Continue 2nd point TT for preboring
Fri (28/02) | 28 Feb 2025 | P48 |  | Continue JGP grouting
Fri (28/02) | 28 Feb 2025 | P50 |  | Preparation for UKP casting
Fri (28/02) | 28 Feb 2025 | MH2-10 |  | Preparing to remove ladder cage and continue installation for balance 1nos precast chamber and reducer slab
Fri (28/02) | 28 Feb 2025 | MH2-9 |  | No activity
Fri (28/02) | 28 Feb 2025 | Exit 3 |  | Manual clearing of soil near water pipe
Fri (28/02) | 28 Feb 2025 | BR5 |  | Flood wall formwork removal ongoing
Fri (28/02) | 28 Feb 2025 | BR6 |  | Pending for preloading
Sat (01/03) | 01 Mar 2025 | P23-24 |  | Old road premix removal and will continue with excavation
Sat (01/03) | 01 Mar 2025 | Zone 4 LA | south bound | Lane closure for trial trench works for butterfly valve
Sat (01/03) | 01 Mar 2025 | P13 |  | Prepare for crosshead formwork
Sat (01/03) | 01 Mar 2025 | P17 |  | Guide frame removal
Sat (01/03) | 01 Mar 2025 | P15 |  | Falsework dismantling
Sat (01/03) | 01 Mar 2025 | P16 |  | Excavation around pier to LSS
Sat (01/03) | 01 Mar 2025 | P13 |  | Removal of road premix for footing
Sat (01/03) | 01 Mar 2025 | DW05-10 |  | Preparing for capping beam casting
Sat (01/03) | 01 Mar 2025 | P5 |  | Preparation for column closing
Sat (01/03) | 01 Mar 2025 | P3 |  | Pump car on site for casting
Sat (01/03) | 01 Mar 2025 | P48 |  | TT for preboring
Sat (01/03) | 01 Mar 2025 | P48 |  | Continue JGP grouting
Sat (01/03) | 01 Mar 2025 | P50 |  | Casing installation for UKP
Sat (01/03) | 01 Mar 2025 | P44 |  | Preparing for ERSS removal
Sat (01/03) | 01 Mar 2025 | DR5 |  | Formwork and support continue removal
Sat (01/03) | 01 Mar 2025 | ST214 |  | Prepare for left side waterstop plate lift up. Right side lift up done
Sat (01/03) | 01 Mar 2025 | Exit 3 |  | Capping beam rebar work
Sat (01/03) | 01 Mar 2025 | P13 |  | Prepare cross head side formwork
Sat (01/03) | 01 Mar 2025 | P15 |  | Falsework dismantling
Sat (01/03) | 01 Mar 2025 | P16 |  | Removal of soil for LSS backfilling
Sat (01/03) | 01 Mar 2025 | P5 |  | Tie rod installation for formwork closing
Sat (01/03) | 01 Mar 2025 | P3 |  | Casting in progress with two pumps
Sat (01/03) | 01 Mar 2025 | P50 |  | Boring for UKP installation. 2nos
Sat (01/03) | 01 Mar 2025 | P48 |  | Reinstate the TT completed area
Sat (01/03) | 01 Mar 2025 | P48 |  | Continue JGP grouting
Sat (01/03) | 01 Mar 2025 | P44 |  | Continue ERSS removal
Sat (01/03) | 01 Mar 2025 | Exit 3 capping beam |  | Rebar works, hyrib installation and cleaning ongoing
Sat (01/03) | 01 Mar 2025 | P19 |  | Backfilling at trial trench area
Sat (01/03) | 01 Mar 2025 | P3 |  | Pile cap casting in progress, 410/615m3
Sat (01/03) | 01 Mar 2025 | P15 |  | Night team preparing to resume falsework dismantling works
Sat (01/03) | 01 Mar 2025 | Exit 3 |  | Temporary support installation for water pipe
Sat (01/03) | 01 Mar 2025 | ST214 |  | Final koden check
Sat (01/03) | 01 Mar 2025 | BR1, BR2 |  | Steel plates laid
Sat (01/03) | 01 Mar 2025 | BR6 |  | Excavation started this afternoon. KTC works done for the day
Sat (01/03) | 01 Mar 2025 | DW79A |  | Hanging bar installation
Sun (02/03) | 02 Mar 2025 | Exit 3 |  | Excavation for capping beam works
Sun (02/03) | 02 Mar 2025 | P25 |  | Excavation for utility support ongoing
Sun (02/03) | 02 Mar 2025 | DW39 & DW39A |  | Excavation completed for Guidewall. Preparation for BRC installation
Sun (02/03) | 02 Mar 2025 | ST214 |  | Cleaning and Desanding works in progress
Sun (02/03) | 02 Mar 2025 | BR-1/BR-2 |  | Steel plates arranging
Sun (02/03) | 02 Mar 2025 | BR-6 |  | Excavation in progress
Sun (02/03) | 02 Mar 2025 | DW-79A |  | Last truck casting in progress
Sun (02/03) | 02 Mar 2025 | P43 |  | RG drilling works in progress for IS instrument
Sun (02/03) | 02 Mar 2025 | P48-19 |  | JGP grouting completed
Sun (02/03) | 02 Mar 2025 | Zone 4,P50 |  | Trial trench for UP50-7
Sun (02/03) | 02 Mar 2025 | P19 |  | Backfilling works
Sun (02/03) | 02 Mar 2025 | P16 |  | Preparation for pad footing installation
Sun (02/03) | 02 Mar 2025 | P15 |  | Falsework dismantling
Sun (02/03) | 02 Mar 2025 | P13 |  | Falsework installation in progress
Sun (02/03) | 02 Mar 2025 | P5 |  | Column Formwork installation
Sun (02/03) | 02 Mar 2025 | P3 |  | Pile cap cast yesterday
Sun (02/03) | 02 Mar 2025 | P3 pile cap casting completed. Total vol |  | 605.5m3
Sun (02/03) | 02 Mar 2025 | DW05-10 |  | Capping beam casting done
Sun (02/03) | 02 Mar 2025 | Exit 3 |  | Continue excavation for capping beam works
Sun (02/03) | 02 Mar 2025 | Exit 3 |  | Ramp making in progress
Sun (02/03) | 02 Mar 2025 | Exit 3 |  | Stockpile status
Sun (02/03) | 02 Mar 2025 | P15 |  | Falsework dismantling ongoing
Sun (02/03) | 02 Mar 2025 | ST214 |  | Re-cleaning in progress
Sun (02/03) | 02 Mar 2025 | P25 |  | Excavation for utility support ongoing
Sun (02/03) | 02 Mar 2025 | DW79A |  | Preparing for casting
Sun (02/03) | 02 Mar 2025 | DW39 & DW39A |  | BRC installation for Guidewall
Sun (02/03) | 02 Mar 2025 | ST214 |  | Cleaning and Desanding completed. Koden test ongoing
Sun (02/03) | 02 Mar 2025 | Exit 2 |  | Stockpile status
Sun (02/03) | 02 Mar 2025 | BR1/BR2 |  | No activity
Sun (02/03) | 02 Mar 2025 | BR-6 |  | Excavation in progress
Sun (02/03) | 02 Mar 2025 | DW-79A |  | Casting completed
Sun (02/03) | 02 Mar 2025 | Slurry Wall S16 |  | LSS backfilling in progress
Sun (02/03) | 02 Mar 2025 | P43 |  | RG work stopped for the day, to resume drilling tmr. Housekeeping ongoing
Sun (02/03) | 02 Mar 2025 | Exit 1 |  | Stockpile status
Sun (02/03) | 02 Mar 2025 | Zone 4 |  | Work stopped for the day. P48-16 grouting and P47 silo tank erection completed
Sun (02/03) | 02 Mar 2025 | P5 |  | 2/4 column formwork closing completed. Housekeeping ongoing
Sun (02/03) | 02 Mar 2025 | P13 |  | Current status for falsework installation
Sun (02/03) | 02 Mar 2025 | P16 |  | Excavation completed for falsework base preparation
Sun (02/03) | 02 Mar 2025 | P19 |  | Backfilling completed for BP
Mon (03/03) | 03 Mar 2025 | Zone 6 |  | TBM Cutter head fixing in progress
Mon (03/03) | 03 Mar 2025 | P5 |  | Formwork closing for column. 3/4 nos. completed
Mon (03/03) | 03 Mar 2025 | P3 |  | Rebar installation for column stump ongoing
Mon (03/03) | 03 Mar 2025 | P11 |  | Abandoned Singtel manhole hacking in progress
Mon (03/03) | 03 Mar 2025 | P13 |  | Falsework installation in progress
Mon (03/03) | 03 Mar 2025 | BR6 |  | Current status of excavation
Mon (03/03) | 03 Mar 2025 | BR5 |  | Access installation and CJ roughening ongoing
Mon (03/03) | 03 Mar 2025 | BR1, BR2 access |  | Concrete barrier installation
Mon (03/03) | 03 Mar 2025 | P43 |  | RG coring ongoing for inclinometer in-soil
Mon (03/03) | 03 Mar 2025 | MH2-9 |  | Manhole lining works ongoing
Mon (03/03) | 03 Mar 2025 | MH2-10 |  | All precast chambers installed. Now ongoing rebar works for outer wall. Today plan for casting
Mon (03/03) | 03 Mar 2025 | P16 |  | LSS backfill completed for the base of falsework
Mon (03/03) | 03 Mar 2025 | P19-2 |  | BP boring in progress
Mon (03/03) | 03 Mar 2025 | P48-41 |  | JGP grouting in progress
Mon (03/03) | 03 Mar 2025 | Zone 4 |  | Current stockpile
Mon (03/03) | 03 Mar 2025 | Zone 4 |  | UP50-6 boring in progress
Tue (04/03) | 04 Mar 2025 | GL W7-8 onwards |  | Exposing dwall
Tue (04/03) | 04 Mar 2025 | S1-1 |  | Manual clearing of soil nearby services
Tue (04/03) | 04 Mar 2025 | Near P25 |  | Geolutions (RG subcon) rig on site to support IM installation works. Preparation works ongoing
Tue (04/03) | 04 Mar 2025 | DW39, 39A |  | Guidewall cast yesterday
Tue (04/03) | 04 Mar 2025 | ST198 | BC1 | B2 in progress, 13/28.05m
Tue (04/03) | 04 Mar 2025 | Blk 2 |  | 1 Seongha rig no activity, Near exit 2: Seongha continue fissure grouting works, O-111. Today plan 4nos
Tue (04/03) | 04 Mar 2025 | BR1, BR2 |  | Concrete barriers installation ongoing
Tue (04/03) | 04 Mar 2025 | Near BR2 |  | Soil from BR6 excavation currently stockpile at this area
Tue (04/03) | 04 Mar 2025 | BR6 |  | Excavation in progress
Tue (04/03) | 04 Mar 2025 | DW117 | BC2 | Cutter wheel cleaning done. Now resume B2 excavation
Tue (04/03) | 04 Mar 2025 | SW15 |  | Slurry wall panel removal ongoing, Yesterday done SW18
Tue (04/03) | 04 Mar 2025 | P43 |  | GCE coring works ongoing for C29B
Tue (04/03) | 04 Mar 2025 | P43 |  | LE on site for trial trench works
Tue (04/03) | 04 Mar 2025 | P48-14 |  | JGP in progress
Tue (04/03) | 04 Mar 2025 | UP16 |  | Trial trench ongoing
Tue (04/03) | 04 Mar 2025 | UP08 |  | Trial trench ongoing
Tue (04/03) | 04 Mar 2025 | P46 |  | Trial trench ongoing to find SPPG cable joint
Tue (04/03) | 04 Mar 2025 | Exit 3 |  | Stockpile status
Tue (04/03) | 04 Mar 2025 | Exit 3 |  | Backfilling and compaction for new ramp access completed
Tue (04/03) | 04 Mar 2025 | P19-2 |  | BP Rebar cage lowered. Preparing for casting
Tue (04/03) | 04 Mar 2025 | P13 |  | Falsework installation in progress
Tue (04/03) | 04 Mar 2025 | Zone 2 |  | Unloading of concrete blocks for P14 segment temporary support
Tue (04/03) | 04 Mar 2025 | Rig 4 |  | Dismantling of BC cutter
Tue (04/03) | 04 Mar 2025 | ST147-ST153 |  | Base grouting in progress
Tue (04/03) | 04 Mar 2025 | ST144 & ST144A |  | Preparing for guidewall removal
Tue (04/03) | 04 Mar 2025 | DW117 | Rig 2 | B3 CD 4/21.1m
Tue (04/03) | 04 Mar 2025 | P3 |  | Rebar installation for column stump
Tue (04/03) | 04 Mar 2025 | P5 |  | Scaffold installation for column casting. Target to cast tmr
Tue (04/03) | 04 Mar 2025 | MH2-9 |  | Continue lining works
Tue (04/03) | 04 Mar 2025 | MH2-10 |  | Telescopic excavator has been demob. Excavator from MH2-9 shifted to 2-10
Tue (04/03) | 04 Mar 2025 | Exit 3 |  | Temporary support installation ongoing for water pipe & exposing DP
Tue (04/03) | 04 Mar 2025 | ST198 | BC1 | B2 in progress, 24.5/28.05m
Tue (04/03) | 04 Mar 2025 | Near exit 2 |  | Fissure grouting works ongoing for last point of the day. Waiting for RTO checking. 3nos has been completed
Tue (04/03) | 04 Mar 2025 | BR1, BR2 |  | Concrete barriers installation
Tue (04/03) | 04 Mar 2025 | BR6 |  | Excavation in progress
Tue (04/03) | 04 Mar 2025 | P44 |  | Steel plates extraction ongoing
Tue (04/03) | 04 Mar 2025 | UP50-17 |  | Boring in progress
Tue (04/03) | 04 Mar 2025 | MH2-10 |  | Completed. Now preparing for formwork removal. Today plan to demob telescopic excavator
Tue (04/03) | 04 Mar 2025 | MH2-9 |  | Lining works ongoing
Wed (05/03) | 05 Mar 2025 | BR6 |  | Excavation in progress
Wed (05/03) | 05 Mar 2025 | BR2 access |  | GI pipes installation on top of concrete barriers
Wed (05/03) | 05 Mar 2025 | P17 |  | Formwork removal in progress
Wed (05/03) | 05 Mar 2025 | P13 |  | Falsework installation and assembly in progress
Wed (05/03) | 05 Mar 2025 | ST198 | Rig 1 | Trimming in progress
Wed (05/03) | 05 Mar 2025 | BR3 |  | Started excavation. Pipe along the area to be checked by utility team
Wed (05/03) | 05 Mar 2025 | Near exit 2 |  | Fissure grouting works ongoing
Wed (05/03) | 05 Mar 2025 | ST198 | BC1 | Trimming ongoing
Wed (05/03) | 05 Mar 2025 | Rig 4 |  | Continues dismantling
Wed (05/03) | 05 Mar 2025 | P5 |  | Preparation for column casting today. Concrete pump setting up in progress
Wed (05/03) | 05 Mar 2025 | ST145-ST147 |  | Guidewall removal in progress
Wed (05/03) | 05 Mar 2025 | P3 |  | Tie rod installation for column stump works
Wed (05/03) | 05 Mar 2025 | DW117 | Rig 2 | B3 cleaning in progress
Wed (05/03) | 05 Mar 2025 | MH2-10 |  | Debris hacking and clearing works ongoing
Wed (05/03) | 05 Mar 2025 | MH2-9 |  | Lining works in progress
Wed (05/03) | 05 Mar 2025 | P46-47 |  | Woh hup TT to check 22KV cable joint area
Wed (05/03) | 05 Mar 2025 | P48 |  | TT for preboring work
Wed (05/03) | 05 Mar 2025 | P48 |  | Prepare area for JGP. Left 4 points to complete
Wed (05/03) | 05 Mar 2025 | P50 |  | Prepare to start boring for UP7&8. 4nos completed for monday & Tuesday
Wed (05/03) | 05 Mar 2025 | P43 |  | JGP testing by GCE
Wed (05/03) | 05 Mar 2025 | P44 |  | Continue ERSS removal
Wed (05/03) | 05 Mar 2025 | MH2-10 |  | Road cleaning and housekeeping ongoing
Wed (05/03) | 05 Mar 2025 | DW19 |  | Rebar works ongoing for capping beam
Wed (05/03) | 05 Mar 2025 | ST198 | BC1 | C-lug welding for WS trimming
Wed (05/03) | 05 Mar 2025 | Near exit 2 |  | Fissure grouting works in progress, O-108. Today plan to complete 4nos
Wed (05/03) | 05 Mar 2025 | BR3 |  | Pipe has been checked and it’s empty. Continue excavation
Wed (05/03) | 05 Mar 2025 | ST145-147 |  | Guidewall hacking ongoing
Wed (05/03) | 05 Mar 2025 | SW20 |  | Slurry wall pane removal in progress
Wed (05/03) | 05 Mar 2025 | BR6 |  | Excavation in progres
Wed (05/03) | 05 Mar 2025 | DW37-38 |  | Trial trench in progress
Wed (05/03) | 05 Mar 2025 | GL W4 |  | Dwall hacking ongoing
Wed (05/03) | 05 Mar 2025 | P19-2 |  | LSS backfill completed
Wed (05/03) | 05 Mar 2025 | P16 |  | Hardcores laying for falsework foundation in progress
Wed (05/03) | 05 Mar 2025 | P17 |  | Crosshead formwork dismantling in progress
Wed (05/03) | 05 Mar 2025 | P13 |  | Falsework and scaffold installation in progress
Wed (05/03) | 05 Mar 2025 | P6 |  | Bund wall casting along hoarding perimeter
Wed (05/03) | 05 Mar 2025 | P48 |  | Continue JGP grouting
Wed (05/03) | 05 Mar 2025 | P48 |  | TT for preboring by woh hup
Wed (05/03) | 05 Mar 2025 | P50 |  | Set up for 2 point preboring
Wed (05/03) | 05 Mar 2025 | P3 |  | Formwork closing for column stump ongoing
Wed (05/03) | 05 Mar 2025 | P5 |  | Column casting in progress
Wed (05/03) | 05 Mar 2025 | P43 |  | GCE and Ryobi G already stopped work. Continue drizzling
Wed (05/03) | 05 Mar 2025 | SW20 |  | Clayshot removal
Wed (05/03) | 05 Mar 2025 | DW117 |  | Rebar cage lowering
Wed (05/03) | 05 Mar 2025 | BR3 |  | Top layer removal
Wed (05/03) | 05 Mar 2025 | BR5 |  | Exposing coupler and excavation
Wed (05/03) | 05 Mar 2025 | Station to Exit 2 |  | Checking of abandoned water pipe for removal
Wed (05/03) | 05 Mar 2025 | BP19-1 |  | Casing installed
Wed (05/03) | 05 Mar 2025 | P3 |  | Column stump formwork support installation
Wed (05/03) | 05 Mar 2025 | P5 |  | Column casting
Wed (05/03) | 05 Mar 2025 | P20 |  | LE Mini excavator mobilized for ERSS trial trench works
Wed (05/03) | 05 Mar 2025 | P19-2 |  | BP cast yesterday. Preparing for LSS backfill
Wed (05/03) | 05 Mar 2025 | Bet. P18-P19 |  | Housekeeping, material shifting and hoarding installation
Thu (06/03) | 06 Mar 2025 | DW19 |  | Rebar works ongoing for capping beam and retaining wall
Thu (06/03) | 06 Mar 2025 | DR1 connection |  | Preparing for balance wall hacking works towards DR2
Thu (06/03) | 06 Mar 2025 | BR6 |  | Exposing couplers
Thu (06/03) | 06 Mar 2025 | ST198 | Rig 1 | Suction line cleaning in progress
Thu (06/03) | 06 Mar 2025 | P19-1 |  | BP boring in progress, current depth 10m
Thu (06/03) | 06 Mar 2025 | P17 |  | Formwork dismantling in progress
Thu (06/03) | 06 Mar 2025 | P16 |  | Hardcores laying works
Thu (06/03) | 06 Mar 2025 | Zone 2 |  | WH site walk inspection with their chairman
Thu (06/03) | 06 Mar 2025 | P13 |  | Falsework assembly and installation works
Thu (06/03) | 06 Mar 2025 | P44 |  | Now KTC preparing for balance backfilling
Thu (06/03) | 06 Mar 2025 | BC Rig 4 |  | Continues dismantling
Thu (06/03) | 06 Mar 2025 | Rig 2 |  | Idling
Thu (06/03) | 06 Mar 2025 | DW117 |  | Casting has completed with total volume 116m3
Thu (06/03) | 06 Mar 2025 | P7-2 |  | Trial trench works to expose utility in progress
Thu (06/03) | 06 Mar 2025 | P6 |  | Singtel cable retrieval works
Thu (06/03) | 06 Mar 2025 | P2 |  | Excavation for utility support works
Thu (06/03) | 06 Mar 2025 | P3 |  | Scaffold installation for column stump casting
Thu (06/03) | 06 Mar 2025 | P5 |  | Column cast yesterday
Thu (06/03) | 06 Mar 2025 | P48 |  | TT for preboring by woh hup
Thu (06/03) | 06 Mar 2025 | P46-P47 |  | Exposing 22KV joint bay. Yesterday one point done
Thu (06/03) | 06 Mar 2025 | Zone 2 |  | Bund wall making along hoarding perimeter
Thu (06/03) | 06 Mar 2025 | P19-1 |  | BP boring completed. Rebar cage lowering in progress
Thu (06/03) | 06 Mar 2025 | MH2-10 |  | Backfilling ongoing
Thu (06/03) | 06 Mar 2025 | MH2-9 |  | No activity
Thu (06/03) | 06 Mar 2025 | P13 |  | Plywood platform laying and netting installation in progress
Thu (06/03) | 06 Mar 2025 | P17 |  | Formwork dismantling in progress
Thu (06/03) | 06 Mar 2025 | DW19 |  | Capping beam formwork in progress
Thu (06/03) | 06 Mar 2025 | DW37 |  | Preparing for guidewall works, DW38: Continue excavation for guidewall
Thu (06/03) | 06 Mar 2025 | Near exit 2 |  | Fissure grouting works in progress. Two points completed, today plan 3 points
Thu (06/03) | 06 Mar 2025 | ST198 | BC1 | B2 cleaning in progress
Thu (06/03) | 06 Mar 2025 | BR3 |  | Excavation in progress
Thu (06/03) | 06 Mar 2025 | DR1 connection |  | Hacking ongoing
Thu (06/03) | 06 Mar 2025 | BR6 |  | Exposing couplers
Thu (06/03) | 06 Mar 2025 | SW20 |  | LSS backfill
Thu (06/03) | 06 Mar 2025 | SW22 |  | Slurry wall removal in progress
Thu (06/03) | 06 Mar 2025 | P7-2 |  | Trial trench completed
Thu (06/03) | 06 Mar 2025 | P6-2 |  | Trial trench in progress
Thu (06/03) | 06 Mar 2025 | P47 |  | Status of exposing of 22KV joint
Thu (06/03) | 06 Mar 2025 | P48 |  | GCE prepare for last point JGP
Thu (06/03) | 06 Mar 2025 | P50 |  | Today will cast two UPs. Left two numbers to complete all after this two cast
Thu (06/03) | 06 Mar 2025 | P2 |  | Preparation for footing installation for utility support
Thu (06/03) | 06 Mar 2025 | P3 |  | Dismantling of pile cap Formwork and installation trimmer bar ongoing
Thu (06/03) | 06 Mar 2025 | BR5 |  | Exposing sewer manhole for removal
Thu (06/03) | 06 Mar 2025 | GL19-22 |  | Exposing of 22KV and removal
Thu (06/03) | 06 Mar 2025 | P19-1 |  | Casting in progress
Thu (06/03) | 06 Mar 2025 | P13 |  | Soffit plywood laying
Thu (06/03) | 06 Mar 2025 | P7 |  | Current status of TT. Now worker go for break
Thu (06/03) | 06 Mar 2025 | Exit 3 |  | Preparing for the beam installation
Fri (07/03) | 07 Mar 2025 | S1 |  | Preparation for platform hacking for trial trench works
Fri (07/03) | 07 Mar 2025 | P6-2 |  | HSL bentonite tank shifting ongoing from P19
Fri (07/03) | 07 Mar 2025 | Between P8 and P9 |  | RG setting up for IM installation works
Fri (07/03) | 07 Mar 2025 | BR6 |  | Excavation in progress. Old sewer manhole to be hacked
Fri (07/03) | 07 Mar 2025 | BR3 |  | Excavation in progress
Fri (07/03) | 07 Mar 2025 | ST198 |  | Preparing for casting
Fri (07/03) | 07 Mar 2025 | MH2-10 |  | Barricade removal to facilitate caisson hacking
Fri (07/03) | 07 Mar 2025 | P5 |  | Scaffold dismantling works
Fri (07/03) | 07 Mar 2025 | P3 |  | Preparing for column stump casting. Concrete ordered
Fri (07/03) | 07 Mar 2025 | P2 |  | Preparation for RC footing installation for utility support
Fri (07/03) | 07 Mar 2025 | 05 Mar |  | Good soil: 23 loads, 06 Mar:, Good soil: 17 loads, Hardcore mix: 19 loads
Fri (07/03) | 07 Mar 2025 | MH2-10 |  | Caisson hacking
Fri (07/03) | 07 Mar 2025 | Near exit 2 |  | Fissure grouting works ongoing, ST198: Casting in progress
Fri (07/03) | 07 Mar 2025 | BR6 |  | Exposing couplers, Slope trimming ongoing
Fri (07/03) | 07 Mar 2025 | P43 |  | Inclinometer in-soil completed. Tmr to shift to new location (plan for CCE)
Fri (07/03) | 07 Mar 2025 | SW13 |  | Slurry wall removal completed, Now preparing for next panel
Fri (07/03) | 07 Mar 2025 | Exit 3 |  | Ramp excavation for RC drainage pipe installation
Fri (07/03) | 07 Mar 2025 | Exit 2 |  | Desander status
Fri (07/03) | 07 Mar 2025 | BR3 |  | Excavation in progress
Fri (07/03) | 07 Mar 2025 | BC1 |  | Cutter wheel modification to 800mm size
Fri (07/03) | 07 Mar 2025 | DW19 |  | Capping beam wall formwork ongoing
Fri (07/03) | 07 Mar 2025 | P17 |  | Continue formwork dismantling
Fri (07/03) | 07 Mar 2025 | P13 |  | Baseform formwork and plywood installation ongoing
Fri (07/03) | 07 Mar 2025 | P13 |  | Pier hacking to correct level in progress
Fri (07/03) | 07 Mar 2025 | P11 |  | Column surface grinding works
Fri (07/03) | 07 Mar 2025 | Bet P8-P9 |  | RG trial trench works for IM installation works
Fri (07/03) | 07 Mar 2025 | S1 |  | Platform hacking for trial trench works
Fri (07/03) | 07 Mar 2025 | P43 |  | Continue compensation SPT
Fri (07/03) | 07 Mar 2025 | P44 |  | LE shifting vibro to rectify PGI comment
Fri (07/03) | 07 Mar 2025 | P44 |  | Backfilling done. Compaction in progress
Fri (07/03) | 07 Mar 2025 | P3 |  | Column (1st stage) cast completed
Fri (07/03) | 07 Mar 2025 | P50-9 |  | Boring for UP casting
Fri (07/03) | 07 Mar 2025 | P48 |  | TT for preboring work
Fri (07/03) | 07 Mar 2025 | P46 |  | Exposing 22KV joint for SPPG to wittness
Fri (07/03) | 07 Mar 2025 | P2 |  | Continue excavation for utility support works
Fri (07/03) | 07 Mar 2025 | P19-3 |  | Preparation for preboring works
Fri (07/03) | 07 Mar 2025 | ST198 |  | Casting in progress
Fri (07/03) | 07 Mar 2025 | Exit 3 |  | Platform erection for wall formwork closing
Fri (07/03) | 07 Mar 2025 | P19-1 |  | BP cast yesterday. Preparing for LSS backfill
Fri (07/03) | 07 Mar 2025 | P17 |  | Formwork dismantling in progress
Fri (07/03) | 07 Mar 2025 | P13 |  | Baseform installation and pier hacking to correct level in progress
Sat (08/03) | 08 Mar 2025 | P6&P7 |  | TT and removal of hardcore
Sat (08/03) | 08 Mar 2025 | P13 |  | Hanging bar removal and side formwork closing
Sat (08/03) | 08 Mar 2025 | P3 |  | Materials clearing
Sat (08/03) | 08 Mar 2025 | P50 |  | Confirmation of services before last point boring
Sat (08/03) | 08 Mar 2025 | P47 |  | New silo plant set up
Sat (08/03) | 08 Mar 2025 | P46 |  | Two locations expose to show the status of cable to powergrid
Sat (08/03) | 08 Mar 2025 | BR6 |  | Lean concrete casting completed
Sat (08/03) | 08 Mar 2025 | P43 |  | TT for preboring
Sat (08/03) | 08 Mar 2025 | BR5 |  | Surface roughening and clearing of debris
Sat (08/03) | 08 Mar 2025 | BR5 |  | Lowering of water pump to clear stagnant water
Sat (08/03) | 08 Mar 2025 | Exit 2 |  | Fissure grouting in progress
Sat (08/03) | 08 Mar 2025 | P19-3 |  | Casting in progress
Sat (08/03) | 08 Mar 2025 | P17 |  | Polyfoam removal
Sat (08/03) | 08 Mar 2025 | P13 |  | Side formwork closing
Sat (08/03) | 08 Mar 2025 | Exit 3 & CCW |  | Excavation ongoing
Sat (08/03) | 08 Mar 2025 | P17 |  | Polyfoam removal
Sat (08/03) | 08 Mar 2025 | P13 |  | Formwork installation
Sat (08/03) | 08 Mar 2025 | Exit 3 |  | Hirose no more activity
Sat (08/03) | 08 Mar 2025 | BC1 |  | Cutter maintenance
Sat (08/03) | 08 Mar 2025 | BR3 |  | Current status of excavation
Sat (08/03) | 08 Mar 2025 | BR6 |  | Base lean con casting on progress. Waiting for last truck
Sat (08/03) | 08 Mar 2025 | SW21 |  | Slurry wall removal ongoing
Sat (08/03) | 08 Mar 2025 | Zone 4 junction |  | Lane closure for SI coring works
Sat (08/03) | 08 Mar 2025 | Eixt 3 |  | Excavation
Sat (08/03) | 08 Mar 2025 | P19-3 |  | Boring in progress, 10m
Sat (08/03) | 08 Mar 2025 | P17 |  | Platform erection for tendom stressing work
Sun (09/03) | 09 Mar 2025 | P13 |  | Crosshead wingform formwork installation in progress
Sun (09/03) | 09 Mar 2025 | BC1 |  | Continue cleaning & maintenance
Sun (09/03) | 09 Mar 2025 | Zone 4 junction |  | S1-01 SPT-1 completed
Sun (09/03) | 09 Mar 2025 | Zone 4 junction |  | S1-01 SPT-2 completed
Sun (09/03) | 09 Mar 2025 | Zone 4 |  | TMA shifted to facilitate next SI point at junction
Mon (10/03) | 10 Mar 2025 | Exit 3 |  | Compaction in progress for ramp
Mon (10/03) | 10 Mar 2025 | P19 |  | HSL shifting materials
Mon (10/03) | 10 Mar 2025 | P17 |  | Tendon strand installation
Mon (10/03) | 10 Mar 2025 | P15 |  | Surface grinding rectification works ongoing
Mon (10/03) | 10 Mar 2025 | P13 |  | Crosshead rebar installation in progress
Mon (10/03) | 10 Mar 2025 | N5 |  | Segment supports installation works
Mon (10/03) | 10 Mar 2025 | P2 |  | Excavation for utility support in progress
Mon (10/03) | 10 Mar 2025 | P3 |  | No activity
Mon (10/03) | 10 Mar 2025 | P5 |  | Column formwork fully dismantled
Mon (10/03) | 10 Mar 2025 | MH2-10 |  | Caisson hacking ongoing
Mon (10/03) | 10 Mar 2025 | MH2-9 |  | Manhole cover works
Mon (10/03) | 10 Mar 2025 | P46 |  | Trial trench in progress to expose SPPG cable joint
Mon (10/03) | 10 Mar 2025 | P48-09 |  | Trial trench
Mon (10/03) | 10 Mar 2025 | P49-2 |  | Casing installed. Today plan to complete this UKP
Mon (10/03) | 10 Mar 2025 | Between P42-43 |  | Pumping main pipe laying for connection towards MH3-4
Mon (10/03) | 10 Mar 2025 | P43 |  | Trial trench for ERSS preboring
Mon (10/03) | 10 Mar 2025 | BR6 |  | Rebar works started, Continue exposing couplers, U-bar welding at kingpost area
Mon (10/03) | 10 Mar 2025 | BR6 |  | Continue hacking of abandoned sewer manhole and slope trimming
Mon (10/03) | 10 Mar 2025 | Near JTC blk 2 |  | Dongah exposing sonic logging pipes
Mon (10/03) | 10 Mar 2025 | BR3 |  | Excavation in progress, IW33008 is affected. WH and RG to coordinate
Mon (10/03) | 10 Mar 2025 | BC1 |  | Maintenance
Mon (10/03) | 10 Mar 2025 | S1-1 |  | Utility support welding works
Mon (10/03) | 10 Mar 2025 | P17 |  | Tendon strands installation
Mon (10/03) | 10 Mar 2025 | P13 |  | Crosshead rebar works in progress
Mon (10/03) | 10 Mar 2025 | Exit 3 |  | Continue excavation
Tue (11/03) | 11 Mar 2025 | MH2-10 |  | First layer hacking completed. Now clearing rebars and preparing to dispose debris
Tue (11/03) | 11 Mar 2025 | GL W4-W8 |  | Dwall hacking in progres
Tue (11/03) | 11 Mar 2025 | Exit 3 |  | Support welding works ongoing
Tue (11/03) | 11 Mar 2025 | DW37-38 |  | Platform ready for BC cutter parking
Tue (11/03) | 11 Mar 2025 | Exit 2 desander |  | Noise barrier panels dismantled
Tue (11/03) | 11 Mar 2025 | P48 |  | Trial trench for UP preboring work
Tue (11/03) | 11 Mar 2025 | P49 |  | Boring and casing installation for UP. Today target 3nos
Tue (11/03) | 11 Mar 2025 | P50 |  | GCE preparing to start coring work
Tue (11/03) | 11 Mar 2025 | Near exit 2 |  | Excavation for guidewall removal for ST196-199
Tue (11/03) | 11 Mar 2025 | BR3 |  | Current excavation status
Tue (11/03) | 11 Mar 2025 | BR6 |  | Debris disposal and continue hacking of abandoned sewer manhole
Tue (11/03) | 11 Mar 2025 | BR6 |  | Drilling ongoing for PU grout tube installation
Tue (11/03) | 11 Mar 2025 | Between P42-43 |  | Stump formwork in progress for pumping main pipes
Tue (11/03) | 11 Mar 2025 | Exit 3 |  | Mobilising of LE boring rig to P21 area
Tue (11/03) | 11 Mar 2025 | P49 |  | 4nos of casing installation for UP. Target 4nos today
Tue (11/03) | 11 Mar 2025 | P48 |  | Continue TT for UP preboring. Encounter abandoned drain and HT cable inside drain
Tue (11/03) | 11 Mar 2025 | P50 |  | TT for JGP testing. Total 4 coring + 4 SPT
Tue (11/03) | 11 Mar 2025 | P21 |  | Trial trench for ERSS installation
Tue (11/03) | 11 Mar 2025 | P19 |  | HSL dismantle of boring rig and material shifting to P6-1 area
Tue (11/03) | 11 Mar 2025 | P17 |  | Installation of anchor block and wedge for post tension works
Tue (11/03) | 11 Mar 2025 | P15 |  | Surface grinding rectification works
Tue (11/03) | 11 Mar 2025 | P13 |  | Rebar and RWDP installation in progress
Tue (11/03) | 11 Mar 2025 | P3 |  | Formwork dismantled for column stump. Patching works in progress
Tue (11/03) | 11 Mar 2025 | P2 |  | Utility supports welding works in progress
Tue (11/03) | 11 Mar 2025 | P1 |  | LE shifting materials to P21 area
Tue (11/03) | 11 Mar 2025 | S1 |  | BP Trial trench completed. Pending utility team to confirm utilities before backfilling works
Tue (11/03) | 11 Mar 2025 | P8-P9 |  | RG IM installation ongoing
Tue (11/03) | 11 Mar 2025 | P43 |  | Preboring started for ERSS
Tue (11/03) | 11 Mar 2025 | BR3 |  | Continue excavation by KTC
Tue (11/03) | 11 Mar 2025 | BR6 |  | Coupler bar installation
Tue (11/03) | 11 Mar 2025 | DR1/2 connection area |  | Drilling for starter bar planting
Tue (11/03) | 11 Mar 2025 | Exit 2 |  | Fissure grouting 3nos grouting done today. One point grouting in progress
Tue (11/03) | 11 Mar 2025 | Exit 3 |  | Current status of deck beam installation
Tue (11/03) | 11 Mar 2025 | P13 |  | Crosshead coupler bar installation
Tue (11/03) | 11 Mar 2025 | P9 |  | Boring for inclinometer, reached 45m. Today they will work until 7PM
Tue (11/03) | 11 Mar 2025 | P2 |  | Installation of services support
Tue (11/03) | 11 Mar 2025 | P6&7 |  | Now no activity. Boring rig on the way
Tue (11/03) | 11 Mar 2025 | Exit 3 |  | Excavation in progress
Wed (12/03) | 12 Mar 2025 | Zone 1 |  | Eng Hup OG box shifting works
Wed (12/03) | 12 Mar 2025 | P2 |  | Current utility support status
Wed (12/03) | 12 Mar 2025 | P5 |  | ERSS extraction ongojng
Wed (12/03) | 12 Mar 2025 | MH2-10 |  | Backfilling done. Now area preparation for gantry crane to facilitate lining works
Wed (12/03) | 12 Mar 2025 | MH2-9 |  | Currently no activity
Wed (12/03) | 12 Mar 2025 | BR3 |  | Preparing for slope rectification and lean con casting
Wed (12/03) | 12 Mar 2025 | P49 |  | Boring for UP. Will cast two numbers today
Wed (12/03) | 12 Mar 2025 | P50 |  | TT for JGP testing
Wed (12/03) | 12 Mar 2025 | P49 |  | JGP testing for coring point. Today to complete
Wed (12/03) | 12 Mar 2025 | P43 |  | Preboring for ERSS. Now continue raining
Wed (12/03) | 12 Mar 2025 | P21 |  | LE setting up works for ERSS installation
Wed (12/03) | 12 Mar 2025 | P6-1 |  | HSL boring rig setting up works
Wed (12/03) | 12 Mar 2025 | S1 |  | Backfilling in progress
Wed (12/03) | 12 Mar 2025 | P13 |  | Rebar and tendon ducts installation
Wed (12/03) | 12 Mar 2025 | P15 |  | Surface grinding rectification works
Wed (12/03) | 12 Mar 2025 | P16 |  | Hardcore laying and compaction
Wed (12/03) | 12 Mar 2025 | P13 |  | Duct installation by Woh Hup and rebar work also in progress
Wed (12/03) | 12 Mar 2025 | P6&P7 |  | Rebar cage delivery
Wed (12/03) | 12 Mar 2025 | P2 |  | Utility support installation
Wed (12/03) | 12 Mar 2025 | P21 |  | TT for ERSS work
Wed (12/03) | 12 Mar 2025 | BR3 |  | Current status of lean concrete of slope
Wed (12/03) | 12 Mar 2025 | P49 |  | Two UP today
Thu (13/03) | 13 Mar 2025 | P43 |  | Preboring for ERSS installation
Thu (13/03) | 13 Mar 2025 | P49 |  | Casing installation. Today plan for 2 casting and two casing installation
Thu (13/03) | 13 Mar 2025 | P48 |  | TT for UP preboring
Thu (13/03) | 13 Mar 2025 | P46 |  | Checking and exposing of 22KV cable joint. Could find yet. Found some abandoned 22KV
Thu (13/03) | 13 Mar 2025 | BR3 |  | Partial slope lean con done along IM area. WH now preparing to erect platform for IM monitoring, Excavation continue
Thu (13/03) | 13 Mar 2025 | P21 |  | Marking for ERSS trial trench works in progress
Thu (13/03) | 13 Mar 2025 | P17 |  | Tendon strands stressing works in progress
Thu (13/03) | 13 Mar 2025 | P16 |  | Steel plates arranging for crane parking for falsework installation
Thu (13/03) | 13 Mar 2025 | P13 |  | Tendon ducts and rebar installation
Thu (13/03) | 13 Mar 2025 | MH2-9 |  | Caisson hacking started
Thu (13/03) | 13 Mar 2025 | MH2-10 |  | Preparing for manhole cover works
Thu (13/03) | 13 Mar 2025 | P49 |  | LSS backfilling for completed piles
Thu (13/03) | 13 Mar 2025 | P48 |  | 3 SPT& 2 coring done as of now. Today to do is 8nos
Thu (13/03) | 13 Mar 2025 | P8 |  | RG IM instrumentation installation
Thu (13/03) | 13 Mar 2025 | S1 |  | Hardcores clearing works
Thu (13/03) | 13 Mar 2025 | P6-1 |  | HSL bentonite tanks setting up and pipe connection ongoing
Thu (13/03) | 13 Mar 2025 | P2 |  | Utility supports works in progress
Thu (13/03) | 13 Mar 2025 | P5 |  | ERSS extraction ongoing
Thu (13/03) | 13 Mar 2025 | P43 |  | Preboring in progress for ERSS removal
Thu (13/03) | 13 Mar 2025 | P45 |  | TT to check cable joint
Thu (13/03) | 13 Mar 2025 | P48 |  | TT for preboring
Thu (13/03) | 13 Mar 2025 | P50 |  | Preboring for UP casting. Two number today
Thu (13/03) | 13 Mar 2025 | P50 |  | Waiting for cable detection before start boring
Thu (13/03) | 13 Mar 2025 | P50 |  | JGP testing to complete tonight
Thu (13/03) | 13 Mar 2025 | BR3 |  | WH installing access for IM monitoring
Thu (13/03) | 13 Mar 2025 | BR6 |  | Rebar works in progress
Thu (13/03) | 13 Mar 2025 | P21 |  | Trial trench for ERSS ongoing
Thu (13/03) | 13 Mar 2025 | P17 |  | Tendon stressing works in progress
Thu (13/03) | 13 Mar 2025 | P16 |  | Falsework installation
Thu (13/03) | 13 Mar 2025 | P13 |  | Tendon ducts installation
Thu (13/03) | 13 Mar 2025 | S1 |  | Trial trench works in progress
Thu (13/03) | 13 Mar 2025 | P8 |  | Driling completed. Preparation for pipe installation
Thu (13/03) | 13 Mar 2025 | P6-2-1 |  | Preparation for BP preboring and casing installation
Thu (13/03) | 13 Mar 2025 | P5 |  | ERSS extraction ongoing
Thu (13/03) | 13 Mar 2025 | P2 |  | Excavation to s1 layer in progress
Thu (13/03) | 13 Mar 2025 | P43 |  | Continue preboring
Thu (13/03) | 13 Mar 2025 | BR6 |  | Current status of rebar work
Thu (13/03) | 13 Mar 2025 | BR3 |  | Manhole hacking for removal
Thu (13/03) | 13 Mar 2025 | BR3 |  | Scaffold erection for rebar cutting and platform making
Thu (13/03) | 13 Mar 2025 | Exit 3 |  | Continue excavation and drilling for bolt planting
Thu (13/03) | 13 Mar 2025 | P17 |  | Set up for post tendom work
Thu (13/03) | 13 Mar 2025 | P16 |  | Secondary beam installation
Thu (13/03) | 13 Mar 2025 | P6-2-1 |  | Casing installed
Thu (13/03) | 13 Mar 2025 | P13 |  | Woh hup continue tendom duct installation
Thu (13/03) | 13 Mar 2025 | P5 |  | ERSS removal
Thu (13/03) | 13 Mar 2025 | P2 |  | 1st layer excavation
Thu (13/03) | 13 Mar 2025 | DR1 connection to DR2 |  | Rebar works in progress
Thu (13/03) | 13 Mar 2025 | BR6 |  | Abandoned manhole hacking completed. Today plan to complete excavation and cast lean concrete for balance portion ~9m
Thu (13/03) | 13 Mar 2025 | BR6 |  | Rebar works in progress, Cleaning ongoing, Exposing top part couplers, PU grout tubes installed, Target to cast roof slab on 18 Mar
Fri (14/03) | 14 Mar 2025 | P46 |  | Woh hup unable to locate 22KV cable joint as of now. They continue search along drain. If unable to find, will get advice from SPPG
Fri (14/03) | 14 Mar 2025 | PMH24 |  | Precast start to deliver. By today to be fully deliver for PMH23& PMH24. PMH25 precast to be fully deliver by next wednesday
Fri (14/03) | 14 Mar 2025 | P48 |  | TT on going for preboring and provide services protection
Fri (14/03) | 14 Mar 2025 | P49 |  | Preboring on going. Today to cast 2nos of UP
Fri (14/03) | 14 Mar 2025 | MH2-9 |  | Currently no activity. Top layer caisson hacking was done yesterday
Fri (14/03) | 14 Mar 2025 | BR3 |  | Hacking of abandoned manhole ongoing
Fri (14/03) | 14 Mar 2025 | Drain connection to DR2 |  | Formwork installation ongoing
Fri (14/03) | 14 Mar 2025 | BR6 |  | Slope trimming ongoing. Today plan for lean con casting
Fri (14/03) | 14 Mar 2025 | BR6 |  | Rebar works in progress
Fri (14/03) | 14 Mar 2025 | P50 |  | Today to complete JGP testing
Fri (14/03) | 14 Mar 2025 | P21 |  | Preparation to resume trial trench works for ERSS installation
Fri (14/03) | 14 Mar 2025 | P16 |  | Falsework installation
Fri (14/03) | 14 Mar 2025 | P13 |  | Tendon ducts installation works
Fri (14/03) | 14 Mar 2025 | P17 |  | Tendon Stressing in progress
Fri (14/03) | 14 Mar 2025 | P8 |  | RG IM pipe installation ongoing
Fri (14/03) | 14 Mar 2025 | P6-2-1 |  | BP rebar cage lowered. Lowering of tremie pipe in progress for casting
Fri (14/03) | 14 Mar 2025 | P2 |  | Excavation to S1 layer in progress
Fri (14/03) | 14 Mar 2025 | P5 |  | ERSS extraction completed. Levelling works in progress
Fri (14/03) | 14 Mar 2025 | P50 |  | Last point JGP testing. SPT
Fri (14/03) | 14 Mar 2025 | P49 |  | Prepare for two UP casting
Fri (14/03) | 14 Mar 2025 | P49 |  | Doing last point of TT for preboring. The other one backfilling
Fri (14/03) | 14 Mar 2025 | P43 |  | Continue preboring and soldier pile installation
Fri (14/03) | 14 Mar 2025 | BR3 |  | Exposing of couplet bars
Fri (14/03) | 14 Mar 2025 | BR6 |  | Slope protection casting work and rebar work for slab
Fri (14/03) | 14 Mar 2025 | Exit 2 |  | Dwall one rig working. Fissure grouting no activity
Fri (14/03) | 14 Mar 2025 | Exit 3 |  | Exposing of starter bars
Fri (14/03) | 14 Mar 2025 | P13 |  | Tendom duct installation completed. Left for inspection only
Sat (15/03) | 15 Mar 2025 | Exit 3 |  | Waler brackets installation works
Sat (15/03) | 15 Mar 2025 | P49 |  | GCE marking to start TT for JGP testing
Sat (15/03) | 15 Mar 2025 | P21 |  | New access making. Casting ongoing
Sat (15/03) | 15 Mar 2025 | P21 |  | Trial trench for ERSS in progress
Sat (15/03) | 15 Mar 2025 | Exit 2 - DW37 | BC01 | B3 excavation completed
Sat (15/03) | 15 Mar 2025 | Exit 2 |  | Seongha materials shifting works
Sat (15/03) | 15 Mar 2025 | BR3 |  | Removal of abandoned manhole
Sat (15/03) | 15 Mar 2025 | BR6 |  | Rebar works and coupler exposing
Sat (15/03) | 15 Mar 2025 | P43 |  | Machinery checking in progress
Sat (15/03) | 15 Mar 2025 | P44 |  | Current ERSS extraction status
Sat (15/03) | 15 Mar 2025 | P48 |  | Trial trench completed for UP48-14. Preparing for backfill
Sat (15/03) | 15 Mar 2025 | P40-P41 |  | Trial trench ongoing for instrumentation drilling
Sat (15/03) | 15 Mar 2025 | P49 |  | UP49-8 boring in progress. Today target to cast 2 UP
Sat (15/03) | 15 Mar 2025 | P51-C2 |  | JGP testing in progress
Sat (15/03) | 15 Mar 2025 | P50 |  | KTC started excavation till 1.5m depth
Sat (15/03) | 15 Mar 2025 | P13 |  | Falsework & netting installation ongoing
Sat (15/03) | 15 Mar 2025 | P13 |  | Current rebar & tendon ducts installation status
Sat (15/03) | 15 Mar 2025 | S2 |  | Trial trench for BP completed
Sat (15/03) | 15 Mar 2025 | P8 |  | RG IM instrument installed. To shift to next point in afternoon
Sat (15/03) | 15 Mar 2025 | P7-2-2 |  | BP boring completed. To cast in the afternoon
Sat (15/03) | 15 Mar 2025 | MH1-2 |  | PLT in progress
Sat (15/03) | 15 Mar 2025 | P5 |  | No activity
Sat (15/03) | 15 Mar 2025 | P3 |  | Backfilling to pile cap top level in progress
Sat (15/03) | 15 Mar 2025 | P2 |  | Excavation to S1 layer completed. Waler brackets installation ongoing
Sat (15/03) | 15 Mar 2025 | Exit 3 |  | Excavation works and current status for waler brackets installation
Sat (15/03) | 15 Mar 2025 | Exit 2- DW37 |  | C lug plate welding for water stop side trimming
Sat (15/03) | 15 Mar 2025 | BR3 |  | Continue excavation and removal of materials
Sat (15/03) | 15 Mar 2025 | BR6 |  | Continue rebars installation works
Sat (15/03) | 15 Mar 2025 | P40-P41 |  | Hand augering ongoing for instrumentation works
Sat (15/03) | 15 Mar 2025 | P43 |  | Preboring and trial trench for ERSS installation
Sat (15/03) | 15 Mar 2025 | Exit 1 |  | Current Stockpile status
Sat (15/03) | 15 Mar 2025 | P48 |  | Trial trench for UP48-4 in progress
Sat (15/03) | 15 Mar 2025 | P49 |  | Preparation for 2 UPs casting
Sat (15/03) | 15 Mar 2025 | P51-C2 |  | JGP testing completed
Sat (15/03) | 15 Mar 2025 | P50 |  | KTC excavation works ongoing
Sat (15/03) | 15 Mar 2025 | P3 |  | Backfilling works ongoing to pile cap top
Sat (15/03) | 15 Mar 2025 | P2 |  | Waler brackets installation completed. Preparing to lower Waler beam
Sat (15/03) | 15 Mar 2025 | MH1-2 |  | PLT test completed. Demob of excavator ongoing and Preparing for lane opening
Sat (15/03) | 15 Mar 2025 | P7-2-2 |  | BP casting completed. Preparing for casing removal
Sat (15/03) | 15 Mar 2025 | P6-2-2 |  | BP boring completed. Toe depth confirmation in progress. To cast BP today
Sat (15/03) | 15 Mar 2025 | S2 |  | Abandoned drain hacking in progress for BP works
Sat (15/03) | 15 Mar 2025 | P8 |  | Drilling in progress for piezometer installation
Sat (15/03) | 15 Mar 2025 | P13 |  | Current status for rebar and tendon duct installation
Sat (15/03) | 15 Mar 2025 | P16 |  | Platform laying and netting installation in progress
Sat (15/03) | 15 Mar 2025 | P17 |  | Scaffold access dismantling ongoing
Sat (15/03) | 15 Mar 2025 | P19 |  | LE unloading of soldier piles and steel plates
Sat (15/03) | 15 Mar 2025 | P21 |  | Trial trench for ERSS
Sat (15/03) | 15 Mar 2025 | Exit 3 |  | Current status of excavation. Now Ryobi G taking reading of instruement and woh hup working for wall rebar work
Sat (15/03) | 15 Mar 2025 | DW37 |  | Waterstop end plate trimming for removal
Sat (15/03) | 15 Mar 2025 | P16 |  | Opening making to install support for crosshead
Sat (15/03) | 15 Mar 2025 | P13 |  | Now no activity
Sat (15/03) | 15 Mar 2025 | South ramp and Zone 1 |  | No activity already
Sat (15/03) | 15 Mar 2025 | Exit 3 |  | Preparing for capping beam casting. Concrete on site
Sat (15/03) | 15 Mar 2025 | Exit 3 desander |  | Current stockpile status
Sun (16/03) | 16 Mar 2025 | Drain connection to DR2 |  | Casted
Sun (16/03) | 16 Mar 2025 | P16 |  | Cutting of soffit plywoof for U jacking installation
Sun (16/03) | 16 Mar 2025 | P13 |  | No activity tonight
Mon (17/03) | 17 Mar 2025 | DW39A | Rig 1 | B1 excavation has just started
Mon (17/03) | 17 Mar 2025 | BR3 |  | Exposing of couplers & prepare for lean concrete
Mon (17/03) | 17 Mar 2025 | BR6 |  | Continues shear links & top bar installation, and closing of formwork
Mon (17/03) | 17 Mar 2025 | P21 |  | ERSS marking for Preboring works in progress. To start Preboring today
Mon (17/03) | 17 Mar 2025 | Exit 3 |  | Current status of new ramp access
Mon (17/03) | 17 Mar 2025 | P18 |  | Excavation for crosshead foundation works
Mon (17/03) | 17 Mar 2025 | P17 |  | Current falsework dismantling status
Mon (17/03) | 17 Mar 2025 | P16 |  | Side formwork installation
Mon (17/03) | 17 Mar 2025 | P13 |  | Tendon duct alignment checking in progress by QPS team
Mon (17/03) | 17 Mar 2025 | P7-2-1 |  | BP boring completed. Preparing to lower rebar cage
Mon (17/03) | 17 Mar 2025 | P6-2-3 |  | Preparation for BP preboring and casing installation
Mon (17/03) | 17 Mar 2025 | Rig 2 |  | Drilling for inclinometer @ CCE
Mon (17/03) | 17 Mar 2025 | Rig 1 |  | Drilling for piezometer @ CCE
Mon (17/03) | 17 Mar 2025 | P3 |  | KTC backfilling works to pile cap top level
Mon (17/03) | 17 Mar 2025 | P2 |  | Installation of waler and strut for S1 layer
Mon (17/03) | 17 Mar 2025 | P51-SPT1 |  | SPT test completed
Mon (17/03) | 17 Mar 2025 | P51-C3 |  | Preparing for coring and SPT test
Mon (17/03) | 17 Mar 2025 | P50 |  | KTC current excavation status
Mon (17/03) | 17 Mar 2025 | UP49-9 & UP49-15 |  | Boring completed. Preparation for casting
Mon (17/03) | 17 Mar 2025 | P44 |  | Current ERSS extraction status
Mon (17/03) | 17 Mar 2025 | P43 |  | Installation and Preboring for ERSS installation ongoing
Tue (18/03) | 18 Mar 2025 | P13 |  | PT duct pipe and anti burst link installation
Tue (18/03) | 18 Mar 2025 | P6-2-3 |  | Boring completed. Toe completed. Preparation for rebar cage lowering, P7-2-4: preparation for boring. Today also to cast
Tue (18/03) | 18 Mar 2025 | P51 |  | JGP testing for ERSS, 7/8 completed
Tue (18/03) | 18 Mar 2025 | P50 half |  | Slope excavation 1m below EGL completed. Now KTC only doing soil disposal
Tue (18/03) | 18 Mar 2025 | P49-10 & 11 |  | Boring works for UKP installation. To install and cast today, 2 nos
Tue (18/03) | 18 Mar 2025 | P46 |  | Excavation to expose 22kv cable joint for SPPG verification
Tue (18/03) | 18 Mar 2025 | P43 |  | Pre-boring for ERSS in progress
Tue (18/03) | 18 Mar 2025 | P43 area |  | Excavation to continue sewer pipe laying towards MH3-4
Tue (18/03) | 18 Mar 2025 | STN | GL 1-3 | Cleaning in progress for capping beam construction
Tue (18/03) | 18 Mar 2025 | DW39A |  | Trenching at 25m
Tue (18/03) | 18 Mar 2025 | P16 |  | Scaffold access and rebar support installation. Plan to start rebar installation this evening
Wed (19/03) | 19 Mar 2025 | P21 |  | Pre-boring for ERSS. 5/51 completed
Wed (19/03) | 19 Mar 2025 | P6-2-4 & P7-2-3 |  | Casing installation for boring works
Wed (19/03) | 19 Mar 2025 | P3 column |  | Rebar cage fabrication in progress
Wed (19/03) | 19 Mar 2025 | Zone 2 |  | Cement patching works along the hoarding of covered linkway
Wed (19/03) | 19 Mar 2025 | P50 |  | No activity on site. Pending initial reading of waterstandpipe
Wed (19/03) | 19 Mar 2025 | P7-2-3 |  | BP Boring completed. Preparing for rebar cage lowering
Wed (19/03) | 19 Mar 2025 | P6-2-4 |  | BP boring works in progress
Wed (19/03) | 19 Mar 2025 | P16 |  | Continue rebar installation for crosshead
Wed (19/03) | 19 Mar 2025 | P3 |  | Column rebar fabrication works ongoing
Wed (19/03) | 19 Mar 2025 | P51 |  | 8th point for ERSS testing in progress. After this they will shift to P47
Wed (19/03) | 19 Mar 2025 | P43 |  | Casing installation for ERSS preboring. 2 nos 18m completed today
Thu (20/03) | 20 Mar 2025 | P8 |  | Tunnel Rx installation no activity
Thu (20/03) | 20 Mar 2025 | P7-2-3 |  | LSS casting completed. No other activity of HSL
Thu (20/03) | 20 Mar 2025 | GL 1-2 |  | Drilling for capping beam starter bars
Thu (20/03) | 20 Mar 2025 | BR3 |  | Pumping temporary stopped due to ECM full at exit 2
Thu (20/03) | 20 Mar 2025 | BR5 |  | Arranging 6 inches pump
Thu (20/03) | 20 Mar 2025 | SW09 & 10 |  | Slurry removal completed. Tomorrow LSS backfilling
Fri (21/03) | 21 Mar 2025 | Near gate 5 |  | Ground levelling ongoing
Fri (21/03) | 21 Mar 2025 | Near exit 2 |  | Barrette pile guidewall hacking
Fri (21/03) | 21 Mar 2025 | BR3 |  | No activity. Have asked WH to arrange water pumping
Fri (21/03) | 21 Mar 2025 | DR1 connection | near BR6 | Preparation works ongoing for dwall hacking
Fri (21/03) | 21 Mar 2025 | ST149 |  | Sonic logging test done
Fri (21/03) | 21 Mar 2025 | SW9, SW10 |  | Slurry wall LSS backfill
Fri (21/03) | 21 Mar 2025 | DW115-118 |  | Guidewall removal ongoing
Fri (21/03) | 21 Mar 2025 | P43 |  | Preboring for ERSS ongoing
Fri (21/03) | 21 Mar 2025 | P21 |  | ERSS preboring ongoing. Current status for Preboring: 8/26 SP and 2/25 LP
Fri (21/03) | 21 Mar 2025 | P17 |  | Falsework dismantling in progress
Fri (21/03) | 21 Mar 2025 | P48 |  | Preboring for UKP in progress
Fri (21/03) | 21 Mar 2025 | P27 |  | Inclinometer in-soil, IS31006 works in progress
Fri (21/03) | 21 Mar 2025 | P16 |  | PT duct and rebar installation in progress
Fri (21/03) | 21 Mar 2025 | P13 |  | Preparation works to install cast in anchor
Fri (21/03) | 21 Mar 2025 | P6-2-4 |  | BP casting completed
Fri (21/03) | 21 Mar 2025 | S1 |  | Platform preparation for boring rig shifting. To start Preboring and casing installation for S1
Fri (21/03) | 21 Mar 2025 | P2 |  | Continue water pumping
Fri (21/03) | 21 Mar 2025 | P3 |  | Continue water pumping
Fri (21/03) | 21 Mar 2025 | P3 |  | Column rebar cage fabrication in progress
Sat (22/03) | 22 Mar 2025 | Exit 3 |  | Unloading waler & runner beams for installation. 1 team working here tonight
Sat (22/03) | 22 Mar 2025 | Zone 3 | GL1-3 | Temporary support installation and tonight wendyng working for capping beam rebar works
Sat (22/03) | 22 Mar 2025 | DW38 | BC1 | B1 excavation started. Noise balloon installation ongoing
Sat (22/03) | 22 Mar 2025 | BR3 |  | Base lean con casting in progress
Sat (22/03) | 22 Mar 2025 | BR6 |  | Access temporarily closed off
Sat (22/03) | 22 Mar 2025 | P49 |  | GCE preparing for trial trench works
Sat (22/03) | 22 Mar 2025 | Zone 4 |  | HSL activity done for the day
Sat (22/03) | 22 Mar 2025 | P39 area |  | Dongah clearing rebars
Sat (22/03) | 22 Mar 2025 | Zone 2 |  | Shifting crosshead formwork
Sat (22/03) | 22 Mar 2025 | P16 |  | Crosshead rebar works
Sun (23/03) | 23 Mar 2025 | P13 |  | Cast in anchor support bar installation
Sun (23/03) | 23 Mar 2025 | DW38 |  | Hydraulic hose repair works
Sun (23/03) | 23 Mar 2025 | BR3 |  | Water pumping
Sun (23/03) | 23 Mar 2025 | P49 |  | Coring for JGP testing. Highlighted to improve housekeeping
Sun (23/03) | 23 Mar 2025 | P13 |  | No more activity
Sun (23/03) | 23 Mar 2025 | DW38 |  | B1 in progress
Sun (23/03) | 23 Mar 2025 | Zone 3 | GL1-2 | Continue rebar works for capping beam and water pumping in progress
Sun (23/03) | 23 Mar 2025 | P16 |  | Crosshead rebar works in progress
Sun (23/03) | 23 Mar 2025 | N5 |  | I-beam installation in progress
Sun (23/03) | 23 Mar 2025 | Near gate 5 |  | Steel plates laid for access
Sun (23/03) | 23 Mar 2025 | Exit 3 |  | Currently no activity
Sun (23/03) | 23 Mar 2025 | P43 |  | ERSS pre-boring and installation of SP continue
Sun (23/03) | 23 Mar 2025 | P50 |  | Top plate installation for Utility support
Mon (24/03) | 24 Mar 2025 | S1-3 |  | Platform preparation to install casing today
Mon (24/03) | 24 Mar 2025 | S2-1 |  | Boring works in progress. Today to cast
Mon (24/03) | 24 Mar 2025 | BR6 |  | Dismantling of formwork
Mon (24/03) | 24 Mar 2025 | BR4 |  | No activity
Mon (24/03) | 24 Mar 2025 | BR3 |  | Bottom bar installation in progress
Mon (24/03) | 24 Mar 2025 | BRP19, BRP20, BRP25 & BRP26 |  | 1st stage base grouting in progress
Mon (24/03) | 24 Mar 2025 | DW38 | Rig 1 | B2 CD 27/30.54m
Mon (24/03) | 24 Mar 2025 | P18 |  | Excavation for falsework footing
Mon (24/03) | 24 Mar 2025 | S1-1 |  | Capping beam formwork installation in progress @ GL2-4
Mon (24/03) | 24 Mar 2025 | CCW S1B |  | Cutting of hanging bar in progress
Mon (24/03) | 24 Mar 2025 | CCW S1A |  | Welding work only
Mon (24/03) | 24 Mar 2025 | CCW S1D |  | Dewatering in progress prior to drill for bracket installation
Mon (24/03) | 24 Mar 2025 | Exit 3 |  | 1 strut (DS1-1-6) installed today
Mon (24/03) | 24 Mar 2025 | P48 |  | 2 nos UKP casting done. Preboring and casing installation for 3rd UKP for today
Mon (24/03) | 24 Mar 2025 | PMH23 |  | Rig shifted and set up for JGP works. To start tomorrow
Mon (24/03) | 24 Mar 2025 | BR3 |  | Guide bar ins, CJ roughening, levelling for the balance area to be lean con by 8pm
Tue (25/03) | 25 Mar 2025 | P20 |  | Trial trench for ERSS works ongoing
Tue (25/03) | 25 Mar 2025 | P51 |  | Trial Trench for UKP
Tue (25/03) | 25 Mar 2025 | Ryobi.G team 2 |  | Trial trench in progress for cluster 36002
Tue (25/03) | 25 Mar 2025 | P13 |  | No activity. Wendyng will help install support bars for cast-in anchors on behalf of WH
Tue (25/03) | 25 Mar 2025 | P50 |  | Excavation work in progress
Tue (25/03) | 25 Mar 2025 | P51 |  | Trial Trench work for ukp
Tue (25/03) | 25 Mar 2025 | P5 |  | Falsework leg frame assembly
Wed (26/03) | 26 Mar 2025 | RG Rig 2 |  | Waiting for RTO to inspect toe level prior to install GWV35006
Wed (26/03) | 26 Mar 2025 | ST107-ST103 |  | Guide wall removal work
Wed (26/03) | 26 Mar 2025 | P5 |  | Assembly of falsework leg frame. To start installation at NB side today
Wed (26/03) | 26 Mar 2025 | P21 |  | Continue Preboring works for ERSS
Wed (26/03) | 26 Mar 2025 | P20 |  | Trial trench in progress for ERSS Preboring
Wed (26/03) | 26 Mar 2025 | P16 |  | RWDP and tendon ducts installation
Wed (26/03) | 26 Mar 2025 | P13 |  | Current status for cast in anchor
Wed (26/03) | 26 Mar 2025 | S2-2 |  | Boring completed. Preparaing for rebar cage lowering
Wed (26/03) | 26 Mar 2025 | P5 |  | Leg frame installation for falsework started
Wed (26/03) | 26 Mar 2025 | P2 |  | S2 layer excavation to complete by tomorrow
Wed (26/03) | 26 Mar 2025 | Rig 2 |  | Drilling in progress for GWS35006 installations
Wed (26/03) | 26 Mar 2025 | S1-1 | GL2-4 | Formwork removal & barricade installation
Wed (26/03) | 26 Mar 2025 | CCW S1D |  | Bracket installation in progress
Wed (26/03) | 26 Mar 2025 | P21 |  | ERSS preboring, 4th SP for today
Wed (26/03) | 26 Mar 2025 | P18-19 |  | Area preparation for segment delivery for tomorrow night
Wed (26/03) | 26 Mar 2025 | P16 |  | PT duct installation continue at section 3. To complete tonight and inspect by tomorrow
Wed (26/03) | 26 Mar 2025 | Exit 3 |  | Welding work for DS1-1(7) strut connection to waler joint in progress
Wed (26/03) | 26 Mar 2025 | North ramp N5 |  | Site is ready for first pair segment launching. Shimboxes and hydraulic jacks are in place
Wed (26/03) | 26 Mar 2025 | P13 |  | Extension bar for column starter bar welding
Wed (26/03) | 26 Mar 2025 | BP S2-2 |  | Casting completed
Wed (26/03) | 26 Mar 2025 | BP S1-2 |  | Casing installed. Tomorrow to continue boring and cast
Wed (26/03) | 26 Mar 2025 | P6 |  | Pad footing construction
Wed (26/03) | 26 Mar 2025 | P2 |  | Excavator lowered down to expedite excavation for S2 layer. Plan to complete tomorrow AM. Afternoon to start bracket installation for S2
Wed (26/03) | 26 Mar 2025 | P2 |  | 15th load now loading for disposal
Wed (26/03) | 26 Mar 2025 | P21 |  | Preboring for ERSS continue. 11/26 completed
Thu (27/03) | 27 Mar 2025 | Exit 2 |  | Fissure grouting works in progress
Thu (27/03) | 27 Mar 2025 | P51 |  | Trial Trench work in progress
Thu (27/03) | 27 Mar 2025 | BR3 |  | Preparing for u-bar welding. Base slab was re-cast lean con yesterday
Thu (27/03) | 27 Mar 2025 | BR4 |  | No activity
Thu (27/03) | 27 Mar 2025 | DR1 connection |  | Currently no activity
Thu (27/03) | 27 Mar 2025 | P38 |  | Preparing for hacking to facilitate RC stump works
Thu (27/03) | 27 Mar 2025 | BR6 |  | Backfilling ongoing
Thu (27/03) | 27 Mar 2025 | RbG rig 2 |  | Has reached toe level for GWS35006
Thu (27/03) | 27 Mar 2025 | RbG Rig 1 |  | Still waiting for lorry crane, understand that is otw & will shift during lunch time
Thu (27/03) | 27 Mar 2025 | P18 |  | Preparation for BRC laying. To cast today
Thu (27/03) | 27 Mar 2025 | P16 |  | Support bar installation for PT duct
Thu (27/03) | 27 Mar 2025 | BR3 |  | Base lean con inspection has been checked by RTO. Partial installation of debonding sheet in progress, Cleaning ongoing
Thu (27/03) | 27 Mar 2025 | BR6 |  | Continue backfilling
Thu (27/03) | 27 Mar 2025 | P13 |  | Section 1 formwork closing. Section 2 and 3 continue links installation
Thu (27/03) | 27 Mar 2025 | P48 |  | ERSS in progress
Thu (27/03) | 27 Mar 2025 | P43 |  | ERSS preboring work in progress
Thu (27/03) | 27 Mar 2025 | Zone 1 junction |  | Removal of D1 kerb and hoarding for segment delivery tonight. D1 kerb will be temporarily replaced with a water barrier
Thu (27/03) | 27 Mar 2025 | Exit 3 CB3 Status |  | Clearing protruding rebars
Thu (27/03) | 27 Mar 2025 | CCW section 1D |  | Welding works continue
Thu (27/03) | 27 Mar 2025 | DW39 |  | 1st bite trenching started
Thu (27/03) | 27 Mar 2025 | BR3 |  | Guide bar and spacer block installation in progress
Thu (27/03) | 27 Mar 2025 | P37 |  | Hacking of stump
Thu (27/03) | 27 Mar 2025 | P43 |  | ERSS pre-boring and installation of SP. 70% completed
Thu (27/03) | 27 Mar 2025 | P48 |  | UKP 11 and 9 king post installation
Thu (27/03) | 27 Mar 2025 | P50 |  | 2 nos stump to install tonight
Thu (27/03) | 27 Mar 2025 | P21 |  | Pre-boring for erss. 28/50
Fri (28/03) | 28 Mar 2025 | RbG Rig 1 |  | Drilling in progress for IW36002
Fri (28/03) | 28 Mar 2025 | MH2-10 |  | Lining works ongoing
Fri (28/03) | 28 Mar 2025 | Exit 2 |  | Fissure grouting in progress, 2/4nos done for the day
Fri (28/03) | 28 Mar 2025 | BR3 |  | Rebar works and surface roughening in progress
Fri (28/03) | 28 Mar 2025 | P21 |  | Pre-boring for erss, balance SP 6nos
Fri (28/03) | 28 Mar 2025 | P18 |  | Falsework leg frame assembly
Fri (28/03) | 28 Mar 2025 | BR3 |  | Roof slab rebar works in progress
Fri (28/03) | 28 Mar 2025 | BR6 |  | Backfilling in progress
Sat (29/03) | 29 Mar 2025 | P21 |  | Preboring for ERSS ongoing
Sat (29/03) | 29 Mar 2025 | Exit 2 | DW039 | C lug plate welding for ws side trimming (DW039A side)
Sat (29/03) | 29 Mar 2025 | BR3 |  | Bottom bar installation, 7 workers
Sat (29/03) | 29 Mar 2025 | Exit 2 | O-92 | Driling completed for fissure grouting. Casing removal ongoing
Sat (29/03) | 29 Mar 2025 | Zone 3 |  | Hacking of Guidewall ongoing
Sat (29/03) | 29 Mar 2025 | BR3 |  | Slab B1, B2 bottom bar inspection ongoing
Sat (29/03) | 29 Mar 2025 | BR6 |  | Soil Leveling works ongoing
Sat (29/03) | 29 Mar 2025 | RG Rig 1 |  | Drilling completed for IW36002. Installation in progress
Sat (29/03) | 29 Mar 2025 | P43 |  | ERSS Soldier piles and steel plates installation ongoing
Sat (29/03) | 29 Mar 2025 | RG Rig 25 |  | Drilling in progress for IW36006
Sat (29/03) | 29 Mar 2025 | Zone 4 JGP P47 Point no |  | A4 drilling completed. Preparation for grouting works
Sat (29/03) | 29 Mar 2025 | P48 |  | HSL materials shifting to P45 area
Sat (29/03) | 29 Mar 2025 | P50 |  | Manual excavation ongoing for utility support works
Sat (29/03) | 29 Mar 2025 | P50 |  | KTC Manual excavation to expose utilities
Sat (29/03) | 29 Mar 2025 | P16 |  | Additional rebar installation and welding ongoing
Sat (29/03) | 29 Mar 2025 | P13 |  | Formwork closing in progress
Sat (29/03) | 29 Mar 2025 | Zone 2 |  | Primary beams shifting to P5
Sat (29/03) | 29 Mar 2025 | P5 |  | Falsework erection in progres
Sat (29/03) | 29 Mar 2025 | P3 |  | Backfilling completed. Afternoon to cast concrete plug
Sat (29/03) | 29 Mar 2025 | P2 |  | Installation of S2 layer walers in progress. Brackets installation completed
Sat (29/03) | 29 Mar 2025 | Exit 3 |  | Continue struts/bracing installation and excavation works
Sat (29/03) | 29 Mar 2025 | P21 |  | Preboring for ERSS ongoing
Sat (29/03) | 29 Mar 2025 | Exit 2 | DW039 | Ws side trimming (DW039A side) completed, now preparation for trimming for DW038 side
Sat (29/03) | 29 Mar 2025 | Exit 2 |  | Driling completed for fissure grouting. Grouting and housekeeping works in progress
Sat (29/03) | 29 Mar 2025 | BR3 |  | Continue bottom rebar installation works
Sat (29/03) | 29 Mar 2025 | Zone 3 |  | RG works stop for the day
Sat (29/03) | 29 Mar 2025 | P43 |  | Continue ERSS installation works
Sat (29/03) | 29 Mar 2025 | Exit 1 |  | Current stockpile status
Sat (29/03) | 29 Mar 2025 | Sewer 3 |  | Hacking of MH3-4 wall for pipe laying works
Sat (29/03) | 29 Mar 2025 | Z4,P47 PMH23, JGP point no |  | B1: Grouting in progress, Grouting completed for Pt. A4 and B7
Sat (29/03) | 29 Mar 2025 | P50 |  | Utility supports and manual excavation in progress
Sat (29/03) | 29 Mar 2025 | Zone 4 |  | HSL continue materials shifting works
Sat (29/03) | 29 Mar 2025 | P3 |  | Concrete plug to cast tmr
Sat (29/03) | 29 Mar 2025 | P2 |  | Installation of walers in progress for s2 layer
Sat (29/03) | 29 Mar 2025 | P5 |  | Falsework current status. Unloading of primary beams and materials in progress
Sat (29/03) | 29 Mar 2025 | S1 |  | HSL housekeeping works ongoing
Sat (29/03) | 29 Mar 2025 | P13 |  | Top rebars installation works
Sat (29/03) | 29 Mar 2025 | P16 |  | Continue rebar installation works
Sat (29/03) | 29 Mar 2025 | P16-P17 |  | Crane setting up works in progress
Sat (29/03) | 29 Mar 2025 | Exit 3 |  | Night shit to continue welding of bracing
Sat (29/03) | 29 Mar 2025 | P2 |  | S2 layer waler beam installation status. No more activity
Sat (29/03) | 29 Mar 2025 | P18 |  | 60 tonnes mobile crane setting up for pad footing and leg frame installation
Sat (29/03) | 29 Mar 2025 | Exit 3 |  | Desander Stockpile status
Sat (29/03) | 29 Mar 2025 | Exit 3 |  | Struts bracing installation and excavation works ongoing
Sat (29/03) | 29 Mar 2025 | CCW section 1D |  | Strut installation
Sun (30/03) | 30 Mar 2025 | Zone 4 junction |  | JGP testing, SPT. 1st point completed, 2nd point now preparing
Sun (30/03) | 30 Mar 2025 | P18 |  | Falsework leg frame installation
Sun (30/03) | 30 Mar 2025 | BR3 |  | Bar chair installation in progress
Mon (31/03) | 31 Mar 2025 | DR1 |  | Wall hacking
Tue (01/04) | 01 Apr 2025 | P21 |  | Pre-boring for ERSS, last boring for SP
Tue (01/04) | 01 Apr 2025 | P50 |  | Exposing of services to provide support
Tue (01/04) | 01 Apr 2025 | P50 |  | KTC also exposing services to support
Tue (01/04) | 01 Apr 2025 | P51 |  | TT for UKP preboring
Tue (01/04) | 01 Apr 2025 | Rig 2 |  | Drilling in progress for GWV26002
Tue (01/04) | 01 Apr 2025 | P13 |  | Pump car set up for casting
Tue (01/04) | 01 Apr 2025 | P50 |  | Manual excavation and exposing utilities
Wed (02/04) | 02 Apr 2025 | BR3 |  | Top bar installation in progres
Wed (02/04) | 02 Apr 2025 | BR6 |  | Preparation for DR1 drain wall connection
Wed (02/04) | 02 Apr 2025 | BR6 |  | Soil levelling & compaction for BC cutter platform
Wed (02/04) | 02 Apr 2025 | Rig 2 |  | Drilling in progress for GWV36002
Wed (02/04) | 02 Apr 2025 | Rig 1 |  | Waiting for lorry crane to shift to next cluster which is 36004
Wed (02/04) | 02 Apr 2025 | DR4 |  | Material shifting to clear space for traffic diversion
Wed (02/04) | 02 Apr 2025 | P43 |  | Site clearance, preparing for excavation work
Wed (02/04) | 02 Apr 2025 | P16 |  | Crosshead rebars installation
Wed (02/04) | 02 Apr 2025 | Zone 2 | N5 side | PLT test (3 cycle) for 600T Crane outrigger ongoing
Wed (02/04) | 02 Apr 2025 | Exit 2 |  | Excavation for fissure grouting. As of this morning, completed 3 points. Today plan for 5nos
Wed (02/04) | 02 Apr 2025 | BR3 |  | Rebar works & hyrib installation ongoing
Wed (02/04) | 02 Apr 2025 | P6 - S1 |  | HSL housekeeping and demob of materials ongoing
Wed (02/04) | 02 Apr 2025 | BR6 |  | Drain wall connection rebar works in progress
Wed (02/04) | 02 Apr 2025 | MH3-4 |  | LCH pipe joining works in progress
Wed (02/04) | 02 Apr 2025 | P43 |  | No activity
Wed (02/04) | 02 Apr 2025 | P30 |  | Shoring installation ongoing for stump works
Wed (02/04) | 02 Apr 2025 | P27 |  | IW31006 installation in progress
Wed (02/04) | 02 Apr 2025 | Exit 3 |  | Excavation ongoing
Wed (02/04) | 02 Apr 2025 | P50 North |  | Manual excavation to expose utilities
Wed (02/04) | 02 Apr 2025 | P50 South |  | Manual excavation to expose utilities
Wed (02/04) | 02 Apr 2025 | P45 |  | Trial Trench for UKP
Wed (02/04) | 02 Apr 2025 | P43 |  | No activity. Tomorrow KTC will start excavation
Wed (02/04) | 02 Apr 2025 | Exit 3 |  | D wall hacking for capping beam construction, hacking until 7pm only
Wed (02/04) | 02 Apr 2025 | P21 |  | 7 nos SP installed. Vibro breakdown. Mechanics on the way
Wed (02/04) | 02 Apr 2025 | DR3 |  | 3 nos casing installed for boring works
Wed (02/04) | 02 Apr 2025 | P50 |  | Excavation and bundwall construction at south side
Thu (03/04) | 03 Apr 2025 | P51 |  | Trial Trench for UKP
Thu (03/04) | 03 Apr 2025 | P21 |  | Vibro hummer head yet to replace. Parts OTW
Thu (03/04) | 03 Apr 2025 | P50 |  | Manual excavation work and welding for utility support
Thu (03/04) | 03 Apr 2025 | P45 |  | Rig set up for JGP grouting
Thu (03/04) | 03 Apr 2025 | DR3 |  | 3nos of casing installed
Thu (03/04) | 03 Apr 2025 | P45 |  | TT for UKP installation
Thu (03/04) | 03 Apr 2025 | Rig 2 |  | Continue drilling for GWV36002
Thu (03/04) | 03 Apr 2025 | Rig 1 |  | Drilling for IW36014
Thu (03/04) | 03 Apr 2025 | BR3 |  | Continue rebar works and side formwork installation
Thu (03/04) | 03 Apr 2025 | P2 |  | 2nd layer waler installation. Highlighted to improve Housekeeping and working platform
Thu (03/04) | 03 Apr 2025 | BR3 |  | Shearlink & formwork installation
Thu (03/04) | 03 Apr 2025 | BR6 |  | Hardcore backfilling for BC cutter platform
Thu (03/04) | 03 Apr 2025 | P21 |  | ERSS installation works in progress
Thu (03/04) | 03 Apr 2025 | P20 |  | Preboring for ERSS
Thu (03/04) | 03 Apr 2025 | P50 |  | Exposing services and utility support installation
Thu (03/04) | 03 Apr 2025 | P45 |  | 3nos of TT for UKP done
Thu (03/04) | 03 Apr 2025 | DR3 |  | One pile will cast today. 1/6nos
Thu (03/04) | 03 Apr 2025 | MH3-4 |  | Sewer pipe haunch casting done
Thu (03/04) | 03 Apr 2025 | Exit 3 |  | Exposing below services for utility support
Thu (03/04) | 03 Apr 2025 | P20 |  | Preboring for soldier pile. P21: soldier pile and steel plate installation
Thu (03/04) | 03 Apr 2025 | P16 |  | Pump car set up for crosshead casting. Casting will be around 9PM
Thu (03/04) | 03 Apr 2025 | P6 |  | HSL clearing their materials
Thu (03/04) | 03 Apr 2025 | P2 |  | Packing concrete casting
Thu (03/04) | 03 Apr 2025 | P5 |  | Base lean concrete
Thu (03/04) | 03 Apr 2025 | P50 |  | No activity already
Fri (04/04) | 04 Apr 2025 | Rig 2 |  | Waiting for RTO to inspect toe level prior installation of GWV36002
Fri (04/04) | 04 Apr 2025 | Rig 1 |  | Waiting for RTO to inspect toe level prior installation of IW36004
Fri (04/04) | 04 Apr 2025 | P50 |  | Woh hup exposing services for support and KTC excavation of top soil
Fri (04/04) | 04 Apr 2025 | DW66 - Rig 2 |  | Single bite excavation has started
Fri (04/04) | 04 Apr 2025 | P48 |  | JGP testing work
Fri (04/04) | 04 Apr 2025 | P45 |  | TT for preboring work
Fri (04/04) | 04 Apr 2025 | P45 |  | Continue JGP grouting. 2nos done
Fri (04/04) | 04 Apr 2025 | DR3 |  | 2nd bored pile boring work
Fri (04/04) | 04 Apr 2025 | P43 |  | Excavation for slope protection casting
Fri (04/04) | 04 Apr 2025 | P48 |  | Continue SPT testing
Fri (04/04) | 04 Apr 2025 | DR3 |  | Rebar inspection for 2nd pile
Fri (04/04) | 04 Apr 2025 | P45 |  | Two point grouting done for JGP today
Fri (04/04) | 04 Apr 2025 | DR3 |  | Rebar cage lowering for 2nd piles
Fri (04/04) | 04 Apr 2025 | P43 |  | Lagging plate installation
Fri (04/04) | 04 Apr 2025 | BR3 |  | Shear link installation
Fri (04/04) | 04 Apr 2025 | Exit 3 |  | Exposing services to provide support
Fri (04/04) | 04 Apr 2025 | P18 |  | Falsework base installation. Tonight to install primary beam
Fri (04/04) | 04 Apr 2025 | P2 |  | Packing concrete casting and welding work
Fri (04/04) | 04 Apr 2025 | P5 |  | Falsework erection
Fri (04/04) | 04 Apr 2025 | P21 |  | Adjusting of steel plate and soldier pile to premix level
Fri (04/04) | 04 Apr 2025 | BR3 |  | Shearlinks and formwork installation, Thermocouple to be installed today, Platform preparation for concrete pump truck
Sat (05/04) | 05 Apr 2025 | Exit 3 |  | Preparing for capping beam works
Sat (05/04) | 05 Apr 2025 | Exit 3 |  | Excavation ongoing
Sat (05/04) | 05 Apr 2025 | P25 |  | Drilling ongoing for water standpipe, GWS31006
Sat (05/04) | 05 Apr 2025 | Exit 2 |  | BC cutter maintenance
Sat (05/04) | 05 Apr 2025 | BR3 |  | Adjusting pump truck for parking. COS received for concrete pump trucks platform, Tying of shearlinks and cleaning ongoing. Final inspection plan at 10am
Sat (05/04) | 05 Apr 2025 | BR3 casting status |  | 560/880 m3
Sat (05/04) | 05 Apr 2025 | P18 |  | Working platform assembly. To install after last bus
Sat (05/04) | 05 Apr 2025 | P21 |  | Excavation to S1 completed. No more activity
Sat (05/04) | 05 Apr 2025 | P43 |  | Excavation in progress
Sat (05/04) | 05 Apr 2025 | P45-31 |  | JGP in progress
Sat (05/04) | 05 Apr 2025 | DR3-BP3 |  | Preboring
Sat (05/04) | 05 Apr 2025 | P50 |  | Continue exposing utilities and support installation
Sat (05/04) | 05 Apr 2025 | P48 |  | SPT ongoing
Sat (05/04) | 05 Apr 2025 | BR3 casting status |  | 688/880 m3
Sat (05/04) | 05 Apr 2025 | BR3 |  | Final inspection & cleaning
Sat (05/04) | 05 Apr 2025 | P18 |  | Secondary beam installation
Sat (05/04) | 05 Apr 2025 | P2 |  | Welding works ongoing
Sat (05/04) | 05 Apr 2025 | P3 |  | No activity
Sat (05/04) | 05 Apr 2025 | Exit 3 |  | Continue excavation
Sat (05/04) | 05 Apr 2025 | BR3 |  | Briefing done for casting. Concrete ordered
Sat (05/04) | 05 Apr 2025 | P45-05 |  | JGP in progress
Sat (05/04) | 05 Apr 2025 | BR3 |  | Casting started at 1555hrs
Sat (05/04) | 05 Apr 2025 | BR3 casting status |  | 453/880 m3
Sat (05/04) | 05 Apr 2025 | DW66 |  | C-lug welding for trimming
Sat (05/04) | 05 Apr 2025 | P43 |  | Excavation to S1 layer util 10pm
Sat (05/04) | 05 Apr 2025 | P48 |  | Tonighg coring for JGP testing
Sun (06/04) | 06 Apr 2025 | P21 |  | KTC excavation and send out soil. LE will continue with hang bar cutting and access and waler work
Sun (06/04) | 06 Apr 2025 | P18 |  | Falsework and soffit plywood laying for platform
Sun (06/04) | 06 Apr 2025 | P3 |  | Waler dismantling work
Sun (06/04) | 06 Apr 2025 | P2 |  | Excavation by KTC
Sun (06/04) | 06 Apr 2025 | P5 |  | Platform preparation. To install after lunch
Sun (06/04) | 06 Apr 2025 | P48 |  | Silo dismantling to give way for P49
Sun (06/04) | 06 Apr 2025 | P49 |  | Excavation started
Sun (06/04) | 06 Apr 2025 | P50 |  | Manual excavation and utility support installation
Sun (06/04) | 06 Apr 2025 | P49 |  | Excavation started
Sun (06/04) | 06 Apr 2025 | P45 |  | 1st point JGP grouting for today
Sun (06/04) | 06 Apr 2025 | P45 |  | TT for preboring by Woh hup
Sun (06/04) | 06 Apr 2025 | P43 |  | Waler bracket welding by LE
Sun (06/04) | 06 Apr 2025 | DW66 |  | Dwall excavation work
Sun (06/04) | 06 Apr 2025 | DR1/2 |  | No activity. Wall curing work
Sun (06/04) | 06 Apr 2025 | BR3 |  | No activity. Slab curing
Sun (06/04) | 06 Apr 2025 | BR3 casting status |  | Running volume 771 m3
Sun (06/04) | 06 Apr 2025 | P18 |  | Primary beam installation
Sun (06/04) | 06 Apr 2025 | DW66 |  | Trimming in progress
Sun (06/04) | 06 Apr 2025 | P42 |  | Pumping main line 2 division completed. Installation of additional support in progress
Sun (06/04) | 06 Apr 2025 | Exit 3 |  | Guidewall rebar work
Sun (06/04) | 06 Apr 2025 | Exit 3 below decking |  | Drilling of waler bracket bolts
Sun (06/04) | 06 Apr 2025 | P18 |  | Netting installation below platform and preparing to install hard barricade
Sun (06/04) | 06 Apr 2025 | P21 |  | Access erection done. Lowering of waler brackets
Sun (06/04) | 06 Apr 2025 | P48 |  | Grouting in progress
Sun (06/04) | 06 Apr 2025 | P5 |  | Lifting up materials to working platform level
Sun (06/04) | 06 Apr 2025 | P2 |  | Waler beam dismantling
Sun (06/04) | 06 Apr 2025 | P2 |  | Current status of excavation. KTC already end work
Sun (06/04) | 06 Apr 2025 | P50 |  | Continue welding work with 3 welders
Sun (06/04) | 06 Apr 2025 | P49 |  | Current status of bund wall and excavation
Sun (06/04) | 06 Apr 2025 | P45 |  | GCE end stop work for the day
Sun (06/04) | 06 Apr 2025 | P43 |  | Waler bracket and waler installation for S1. One side waler installed
Sun (06/04) | 06 Apr 2025 | DW66 |  | Continue excavation
Sun (06/04) | 06 Apr 2025 | Exit 3 |  | Prepare to start drilling for waler brackets
Sun (06/04) | 06 Apr 2025 | Exit 2 |  | No activity of Dongah
Mon (07/04) | 07 Apr 2025 | P38 |  | Preparing rebar planting for UKP66 stump
Mon (07/04) | 07 Apr 2025 | P13 |  | Formwork dismantling to start today
Mon (07/04) | 07 Apr 2025 | P50 |  | Utility support installation
Mon (07/04) | 07 Apr 2025 | P48 |  | JGP testing
Mon (07/04) | 07 Apr 2025 | P45 |  | JGP grouting work
Mon (07/04) | 07 Apr 2025 | DW66 |  | Trimming ongoing
Mon (07/04) | 07 Apr 2025 | P45 |  | 2nd point JGP grouting
Mon (07/04) | 07 Apr 2025 | DR3 |  | 3rd bored pile boring. Today to cast
Mon (07/04) | 07 Apr 2025 | P48 |  | 5th point JGP testing
Mon (07/04) | 07 Apr 2025 | P49 |  | Continue excavation for support
Mon (07/04) | 07 Apr 2025 | P50 |  | Exposing services and provide support
Mon (07/04) | 07 Apr 2025 | P43 |  | Waler bracket installation done. Will continue with waler installation
Mon (07/04) | 07 Apr 2025 | P21 |  | Waler bracket installation
Mon (07/04) | 07 Apr 2025 | Rig 1 |  | Shifted from IW36004 to IW36014
Mon (07/04) | 07 Apr 2025 | Rig 2 |  | GWS36002 has just installed, it’ll shift to IW36008 later
Mon (07/04) | 07 Apr 2025 | Exit 3 |  | Capping beam formwork closing. To cast today
Mon (07/04) | 07 Apr 2025 | GL3-4 |  | Preparing rebar for capping beam works
Mon (07/04) | 07 Apr 2025 | P20 |  | Preboring
Mon (07/04) | 07 Apr 2025 | P18 |  | Shifting materials
Mon (07/04) | 07 Apr 2025 | P13 |  | Formwork support dismantling
Mon (07/04) | 07 Apr 2025 | P21 |  | Waler beam joint welding works
Mon (07/04) | 07 Apr 2025 | Exit 3 |  | Capping beam works in progress
Mon (07/04) | 07 Apr 2025 | Exit 3 |  | Manual excavation in progress at utilities area
Mon (07/04) | 07 Apr 2025 | BR3 |  | Formwork support dismantling
Tue (08/04) | 08 Apr 2025 | BC1 |  | Cutter maintenance
Tue (08/04) | 08 Apr 2025 | Exit 2 |  | Fissure grouting works ongoing. Today plan 4nos
Tue (08/04) | 08 Apr 2025 | BR3 |  | No activity
Tue (08/04) | 08 Apr 2025 | BR4 |  | Partial access removal to facilitate pumping main removal
Tue (08/04) | 08 Apr 2025 | Zone 4 |  | Preparing for internal pressure test. Will be at 2:30PM today
Tue (08/04) | 08 Apr 2025 | Zone 4 near pumping main station |  | Premix removal for lamp post pipe laying
Tue (08/04) | 08 Apr 2025 | DKP23-1A, UKP66 |  | Stump rebar works
Tue (08/04) | 08 Apr 2025 | P3 |  | Packing concrete hacking and housekeeping
Tue (08/04) | 08 Apr 2025 | P2 |  | Final levelling and access installation. Today HSL to mob in their excavator
Tue (08/04) | 08 Apr 2025 | P50 |  | Main beam installation at TPE bound and support installation at Changi bound
Tue (08/04) | 08 Apr 2025 | P49 |  | Excavation and exposing of services
Tue (08/04) | 08 Apr 2025 | DW65 |  | BC cutter maintenance before start works
Tue (08/04) | 08 Apr 2025 | P30 |  | Slope trimming
Tue (08/04) | 08 Apr 2025 | UKP17 |  | Manual soil remova
Tue (08/04) | 08 Apr 2025 | Exit 3 |  | Capping beam cast yesterday
Tue (08/04) | 08 Apr 2025 | P21 |  | Struts welding works current status
Tue (08/04) | 08 Apr 2025 | P20 |  | Preboring for ERSS in progress
Tue (08/04) | 08 Apr 2025 | P18 |  | Pier column hacking to correct level ongoing
Tue (08/04) | 08 Apr 2025 | P13 |  | Continue Formwork dismantle & removal works
Tue (08/04) | 08 Apr 2025 | P6 |  | HSL materials clearing in progress
Tue (08/04) | 08 Apr 2025 | P50 South |  | Main beam installation
Tue (08/04) | 08 Apr 2025 | P20 |  | Preboring ongoing
Tue (08/04) | 08 Apr 2025 | P21 |  | Slope lean con casting ongoing
Tue (08/04) | 08 Apr 2025 | UKP66 |  | Stump rebar works
Tue (08/04) | 08 Apr 2025 | Exit 3 |  | No activity
Wed (09/04) | 09 Apr 2025 | P21 |  | Strut welding
Wed (09/04) | 09 Apr 2025 | P13 |  | Working platform erection for Post tensioning works
Wed (09/04) | 09 Apr 2025 | P50 |  | Exposing services at TPE bound
Wed (09/04) | 09 Apr 2025 | P49 |  | Exposing services for support
Wed (09/04) | 09 Apr 2025 | Zone 2 |  | HSL boring rig kelly bar demob. Tomorrow the body will be shifted out
Wed (09/04) | 09 Apr 2025 | P45 |  | Set up rig for 2nd point JGP
Wed (09/04) | 09 Apr 2025 | DR3 |  | Rebar cage lowering for 4th pile casting. 4/6 by today
Wed (09/04) | 09 Apr 2025 | P43 |  | Double waler installation and welding
Wed (09/04) | 09 Apr 2025 | Exit 2 |  | Guidewall hacking and removal
Wed (09/04) | 09 Apr 2025 | Exit 2 |  | Grouting done 3 points. Preparing for 4th point fissure grouting work
Wed (09/04) | 09 Apr 2025 | P20 |  | Preboring for ERSS installation
Wed (09/04) | 09 Apr 2025 | P18 |  | Column rebar welding and jacking installation for crosshead formwork
Wed (09/04) | 09 Apr 2025 | P21 |  | Waler welding. Today to cast packing concretr
Thu (10/04) | 10 Apr 2025 | Zone 2 |  | LG/LM checked for load testing
Thu (10/04) | 10 Apr 2025 | P45 |  | 1st point of JGP grouting started for today
Thu (10/04) | 10 Apr 2025 | P43 |  | Welding of steffener plates for double waler
Thu (10/04) | 10 Apr 2025 | P47 |  | TT for coring works at PMH23 location
Thu (10/04) | 10 Apr 2025 | DW65 |  | Excavation in progress. 10m/23.3m
Thu (10/04) | 10 Apr 2025 | Rig 1 |  | Waiting for RTO to inspect toe level prior to IW36014 installation
Thu (10/04) | 10 Apr 2025 | Rig 2 |  | IW36008 installed, gonna shift the rig to IW36003
Thu (10/04) | 10 Apr 2025 | Zone 2 |  | Load testing for spreader beam completed
Thu (10/04) | 10 Apr 2025 | DR1-DR2 connection |  | Formwork preparation and closing in progress. Today will cast
Thu (10/04) | 10 Apr 2025 | P16 |  | Falsework dismantling in progress
Thu (10/04) | 10 Apr 2025 | P13 |  | Tendon strands installation
Thu (10/04) | 10 Apr 2025 | P6 |  | HSL Boring rig dismantling in progress
Thu (10/04) | 10 Apr 2025 | P50 TPE bound |  | Exposing services for support
Thu (10/04) | 10 Apr 2025 | P49 |  | Current status of excavation
Thu (10/04) | 10 Apr 2025 | DR3 |  | Boring for bored pile
Thu (10/04) | 10 Apr 2025 | P5 |  | Plywood platform laying works
Thu (10/04) | 10 Apr 2025 | P3 |  | NDT completed. KTC to continue backfilling works
Thu (10/04) | 10 Apr 2025 | P2 |  | Pile head hacking in progress
Thu (10/04) | 10 Apr 2025 | P20 |  | Preboring and Installation of ERSS ongoing
Thu (10/04) | 10 Apr 2025 | P21 |  | Walers and struts installation completed. MPI test scheduled in the afternoon
Thu (10/04) | 10 Apr 2025 | P21 |  | MPI testing completed. RG strain gauge installation ongoing
Thu (10/04) | 10 Apr 2025 | P20 |  | Continue Preboring for ERSS installation
Thu (10/04) | 10 Apr 2025 | P18 |  | Rebar welding works in progress
Thu (10/04) | 10 Apr 2025 | Bet P16-P17 |  | Hoarding removal for trial crane setting up
Thu (10/04) | 10 Apr 2025 | Bet. P16-P17 |  | Preparation to shift segment to next storage location
Thu (10/04) | 10 Apr 2025 | P45 |  | Platform making for JGP grouting work
Thu (10/04) | 10 Apr 2025 | P45 |  | TT for UKP
Thu (10/04) | 10 Apr 2025 | DR3 |  | Casing installation for bored pile
Thu (10/04) | 10 Apr 2025 | P16 |  | Scaffold access erection ongoing
Thu (10/04) | 10 Apr 2025 | P13 |  | Tendon strands installation in progress
Thu (10/04) | 10 Apr 2025 | P6 |  | HSL continue boring rig dismantle and demob of materials
Thu (10/04) | 10 Apr 2025 | P5 |  | Continue Falsework installation
Thu (10/04) | 10 Apr 2025 | P2 |  | Pile head hacking ongoing
Thu (10/04) | 10 Apr 2025 | P3 |  | KTC Backfilling and compaction in progress
Thu (10/04) | 10 Apr 2025 | DR1-DR2 connection |  | Removing concrete blocks
Thu (10/04) | 10 Apr 2025 | Exit 3 |  | Hacking of bulging concrete done. Backfilled and levelling ongoing, Drilling for waler bracket
Thu (10/04) | 10 Apr 2025 | P16 |  | Formwork dismantling
Thu (10/04) | 10 Apr 2025 | P16-17 |  | Setting out of crane paltform for trial lift
Fri (11/04) | 11 Apr 2025 | P45 |  | Continue grouting of JGP
Fri (11/04) | 11 Apr 2025 | DR3 |  | 5th bored pile boring done. Preparing for rebar cage lowering
Fri (11/04) | 11 Apr 2025 | PMH23 |  | JGP testing work
Fri (11/04) | 11 Apr 2025 | P50 |  | Secondary beam installation at TPE bound
Fri (11/04) | 11 Apr 2025 | P49 |  | Continue exposing of services
Fri (11/04) | 11 Apr 2025 | P43 |  | Double waler joint welding. 5 welders
Fri (11/04) | 11 Apr 2025 | Zone 3 Exit 2 |  | Fissure Grouting work in progress (today O-82,80; I-60,62), tomorrow I-61
Fri (11/04) | 11 Apr 2025 | P16 |  | Formwork dismantling in progress
Sat (12/04) | 12 Apr 2025 | P43 |  | Installation of strut at S1 layer
Sat (12/04) | 12 Apr 2025 | P45 |  | Drilling for ERSS grouting
Sat (12/04) | 12 Apr 2025 | DR3 |  | Pre-boring for casing installation, last pile
Sat (12/04) | 12 Apr 2025 | P49 |  | Soil disposal
Sat (12/04) | 12 Apr 2025 | P49 |  | Excavation to expose utility
Sat (12/04) | 12 Apr 2025 | P50 |  | Manual excavation for Utility support installation
Sat (12/04) | 12 Apr 2025 | Zone 4 |  | Premix and top soil removal for road diversion. Plan for RCA backfilling today for this location
Sat (12/04) | 12 Apr 2025 | P18 |  | Soffit plywood laying for crosshead
Sat (12/04) | 12 Apr 2025 | P16 |  | Tonight will work after last bus
Sat (12/04) | 12 Apr 2025 | P5 |  | Netting installation. No other activity
Sat (12/04) | 12 Apr 2025 | P6 |  | HSL demobing crane
Sat (12/04) | 12 Apr 2025 | P18 |  | Bottom formwork assembly. To complete installation by tomorrow. Rebar delivery eta today
Sat (12/04) | 12 Apr 2025 | P2 |  | Pile head hacking and hardcore clearing continue
Sat (12/04) | 12 Apr 2025 | BR4 |  | Excavation to dwall cut off level in progress
Sat (12/04) | 12 Apr 2025 | DW65 |  | Rebar cage lowering
Sat (12/04) | 12 Apr 2025 | Exit 3 |  | Waler bracket installation. Plan to install waler tonight. Monday to cast CB6
Sat (12/04) | 12 Apr 2025 | P43 |  | S1 layer strut installation
Sat (12/04) | 12 Apr 2025 | P45 |  | 2nd point grouting for ERSS
Sat (12/04) | 12 Apr 2025 | DR3 |  | Boring works for last pile in progress
Sat (12/04) | 12 Apr 2025 | P49 |  | Excavtion to expose utility status
Sat (12/04) | 12 Apr 2025 | P50 |  | Manual excavation for Utility support installation continue at south side
Sat (12/04) | 12 Apr 2025 | P50 |  | Primary beam welding works
Sat (12/04) | 12 Apr 2025 | Zone 4 after SIA |  | RCA backfilling and compaction for road diversion
Sat (12/04) | 12 Apr 2025 | P49 |  | Current status of excavation
Sat (12/04) | 12 Apr 2025 | P50 TPE bound |  | Main beam installed. Secondary beam and support installation in progress
Sat (12/04) | 12 Apr 2025 | Exit 3 |  | Preparation to continue waler beam bracket installation
Sat (12/04) | 12 Apr 2025 | STN | GL 6-7 NB side | Excavation to expose utility for support installation
Sat (12/04) | 12 Apr 2025 | P43 |  | Two welders provided for double layer waler and stiffener plates welding
Sat (12/04) | 12 Apr 2025 | DW65 |  | Tremie pipe lowered down. Access making for casting work
Sat (12/04) | 12 Apr 2025 | BR3-BR4 |  | Twin pipe pumping main remove. Today to excavate until dwall cutoff level
Sun (13/04) | 13 Apr 2025 | 1st SPT done. N valve |  | Satisfactory
Sun (13/04) | 13 Apr 2025 | P18 |  | Lift up materials for crosshead formwork
Sun (13/04) | 13 Apr 2025 | P43 |  | Stiffener plate welding on waler
Sun (13/04) | 13 Apr 2025 | P18 |  | One side wing form installation. Preparing for installation at other side
Mon (14/04) | 14 Apr 2025 | P18 |  | Erection of scaffold support for rebar installation
Mon (14/04) | 14 Apr 2025 | Rig 1 |  | Ready to start drilling for GWV36009
Mon (14/04) | 14 Apr 2025 | Rig 3- TT02 |  | Ready to start drilling for IW36007
Mon (14/04) | 14 Apr 2025 | Rig 2- TT01 |  | Coring in progress for IW36003
Mon (14/04) | 14 Apr 2025 | P43 |  | MPI test done. Handover to KTC for excavation
Mon (14/04) | 14 Apr 2025 | P20 |  | Installation of steel plates. Left 5nos to complete
Mon (14/04) | 14 Apr 2025 | P18 |  | Rebar welding and hard barricade installation for rebar installation
Mon (14/04) | 14 Apr 2025 | P16 |  | Tendom wire pulling
Mon (14/04) | 14 Apr 2025 | P13 |  | Falsework dismantling
Mon (14/04) | 14 Apr 2025 | P3 |  | Concrete block installation and CJ roughening
Mon (14/04) | 14 Apr 2025 | P2 |  | Pile head hacking
Mon (14/04) | 14 Apr 2025 | P45 |  | Soil disposal and tidy up work area
Mon (14/04) | 14 Apr 2025 | DR3 |  | Last bored pile casting
Mon (14/04) | 14 Apr 2025 | P50 |  | Utility support installation
Mon (14/04) | 14 Apr 2025 | DR3 |  | Last pile casting
Tue (15/04) | 15 Apr 2025 | P50 |  | Utility support installation
Tue (15/04) | 15 Apr 2025 | P50 |  | Checking cable serial number for unknown cable
Tue (15/04) | 15 Apr 2025 | P49 |  | Exposing of KP and base plates welding work
Tue (15/04) | 15 Apr 2025 | BR4 |  | Excavation in progress
Tue (15/04) | 15 Apr 2025 | BR3 |  | CJ hacking in progress
Tue (15/04) | 15 Apr 2025 | GL16 |  | Preparing for slope protection casting
Tue (15/04) | 15 Apr 2025 | Near blk 4 |  | Preparing for jtc drain diversion
Tue (15/04) | 15 Apr 2025 | DR1 |  | No activity
Tue (15/04) | 15 Apr 2025 | BR6 |  | No activity
Tue (15/04) | 15 Apr 2025 | P45 |  | Rig set up done. To continue with boring
Tue (15/04) | 15 Apr 2025 | P43 |  | Excavation to start after lunch
Tue (15/04) | 15 Apr 2025 | MH2-9/2-10 |  | Preparing for PUB CCTV inspection
Tue (15/04) | 15 Apr 2025 | P16 |  | Tendom wire pulling
Tue (15/04) | 15 Apr 2025 | P18 |  | Cross head rebar work in progress
Tue (15/04) | 15 Apr 2025 | Rig 1 |  | Final inspection in progress prior to install GWV36012
Tue (15/04) | 15 Apr 2025 | P5 |  | Now no activity. Tonight road closure and will work
Tue (15/04) | 15 Apr 2025 | Rig 3 | TT02 | Continues coring for IW36007, target to install it tomorrow morning
Tue (15/04) | 15 Apr 2025 | Rig 2 | TT01 | Continues coring for IW36003, target to install it tomorrow morning
Tue (15/04) | 15 Apr 2025 | P2 |  | Woh hup clearing the base to address QPS comment
Tue (15/04) | 15 Apr 2025 | P3 |  | Column rebar work
Tue (15/04) | 15 Apr 2025 | P49 |  | Exposing of services
Tue (15/04) | 15 Apr 2025 | P50 |  | Manual excavation and utility support installation
Tue (15/04) | 15 Apr 2025 | P43 |  | Preparing to install barricade for 1st layer waler
Tue (15/04) | 15 Apr 2025 | P45 |  | 2nd point JGP for today
Tue (15/04) | 15 Apr 2025 | BR4 |  | Hardcore and soil clearing
Tue (15/04) | 15 Apr 2025 | P18 |  | Lifting up rebar for cross head rebar work
Tue (15/04) | 15 Apr 2025 | P16 |  | Tendom wire pulling
Tue (15/04) | 15 Apr 2025 | P13 |  | Status of falsework dismantling
Tue (15/04) | 15 Apr 2025 | P3 |  | Column rebar installed
Tue (15/04) | 15 Apr 2025 | P5 |  | Tonight will have night work
Tue (15/04) | 15 Apr 2025 | P2 |  | Clearing muds to address comment
Tue (15/04) | 15 Apr 2025 | P20 |  | Expose steel plates and soldier pile to push down
Tue (15/04) | 15 Apr 2025 | P21 |  | Pile head hacking
Wed (16/04) | 16 Apr 2025 | Zone 4 P45 |  | JGP Point P45-40 grouting in progress
Wed (16/04) | 16 Apr 2025 | BR4 |  | Hardcore hacking and excavation in progress
Wed (16/04) | 16 Apr 2025 | Zone 3 | GL17 | Manual excavation for utility support in progress, ICE - 2 workers
Wed (16/04) | 16 Apr 2025 | BR3 |  | Slope lean concrete works ongoing
Wed (16/04) | 16 Apr 2025 | UKP17 |  | Preparing excavation for stump works
Wed (16/04) | 16 Apr 2025 | Rig 1 |  | Drilling for GWS36012
Wed (16/04) | 16 Apr 2025 | Rig 3 | TT02 | Preparing to install IW36007
Wed (16/04) | 16 Apr 2025 | Rig 2 | TT01 | Preparing to install IW36003
Wed (16/04) | 16 Apr 2025 | P5 |  | Jack installation for crosshead soffit platform
Wed (16/04) | 16 Apr 2025 | P3 |  | Shear link installation
Wed (16/04) | 16 Apr 2025 | P2 |  | S2 struts removal
Wed (16/04) | 16 Apr 2025 | P29 |  | Excavation in progress prior to shoring provision for RC stump construction
Wed (16/04) | 16 Apr 2025 | P21 |  | Status of pile head hacking
Wed (16/04) | 16 Apr 2025 | P20 |  | Pushing down soldier piles and steel plates
Wed (16/04) | 16 Apr 2025 | P18 |  | Cross head rebar work in progress
Wed (16/04) | 16 Apr 2025 | Zone 4 |  | RCA backfilling for road diversion
Wed (16/04) | 16 Apr 2025 | P49 |  | Continue exposing services
Wed (16/04) | 16 Apr 2025 | P50 |  | Slope protection casting and utility support installation
Wed (16/04) | 16 Apr 2025 | P43 |  | Excavation for S2 layer waler
Wed (16/04) | 16 Apr 2025 | BR4 |  | Excavation for slab work
Wed (16/04) | 16 Apr 2025 | Exit 2 |  | Packing concrete casting
Wed (16/04) | 16 Apr 2025 | Exit 3 |  | Waler beam packing concrete casting completed
Wed (16/04) | 16 Apr 2025 | P21 |  | Scaffold erection in progress
Wed (16/04) | 16 Apr 2025 | P18 |  | Crosshead rebar installation ongoing
Wed (16/04) | 16 Apr 2025 | P16 |  | 1 lane closed for crane setting up works. Traffic controllers provided
Wed (16/04) | 16 Apr 2025 | P14 |  | Scaffold erection works
Wed (16/04) | 16 Apr 2025 | P3 |  | Base lean concrete completed
Thu (17/04) | 17 Apr 2025 | GL17-15 |  | Continue manual excavation for utility support works. ICE - 2 workers
Thu (17/04) | 17 Apr 2025 | BR4 |  | Continue excavation
Thu (17/04) | 17 Apr 2025 | P2 |  | Dismantling of S2 layer walers and struts
Thu (17/04) | 17 Apr 2025 | P3 |  | Tie rod installation for column
Thu (17/04) | 17 Apr 2025 | P5 |  | Plywood laying works
Thu (17/04) | 17 Apr 2025 | P49 TPE bound |  | Exposing of services started
Thu (17/04) | 17 Apr 2025 | P50 |  | Continue utility support welding
Thu (17/04) | 17 Apr 2025 | P43 |  | New access making and excavation to S2 layer
Thu (17/04) | 17 Apr 2025 | P16 |  | Crane setting up ongoing
Thu (17/04) | 17 Apr 2025 | Zone 2 |  | N5 segment arrived on site
Thu (17/04) | 17 Apr 2025 | P5 |  | Preparation for road closure (TPE bound) for falsework installation works after last bus
Thu (17/04) | 17 Apr 2025 | P5 | South bound | Primary beam installation in progress
Thu (17/04) | 17 Apr 2025 | P16 |  | Spreader beam installed for N5 segment launching
Thu (17/04) | 17 Apr 2025 | P43 |  | KTC continue excavation to S2 and Woh hup lowering down mini for pile head hacking work
Thu (17/04) | 17 Apr 2025 | CCE4 |  | Continue soil disposal
Thu (17/04) | 17 Apr 2025 | P39 area |  | Dongah progressively demob materials
Thu (17/04) | 17 Apr 2025 | BRP66 |  | Guidewall removal
Thu (17/04) | 17 Apr 2025 | DKP24-1 |  | Stump rebar works in progres
Thu (17/04) | 17 Apr 2025 | UKP66 stump |  | Currently no activity
Thu (17/04) | 17 Apr 2025 | P37 | south side | Fissure grouting works in progress. 2/4nos done for the day
Thu (17/04) | 17 Apr 2025 | P49 |  | Continue exposing services and provide pipe clamp for water pipe
Thu (17/04) | 17 Apr 2025 | N5-D01 |  | Crosshead segment lowered. Preparing to demob crane
Thu (17/04) | 17 Apr 2025 | P5 |  | Secondary beams installation completed
Thu (17/04) | 17 Apr 2025 | Blk 4 |  | ECM plant shifted away from upcoming dwall works area
Thu (17/04) | 17 Apr 2025 | GL17 |  | Continue manual excavation below utility
Thu (17/04) | 17 Apr 2025 | UKP17 | at P29 area | Shoring installation done. Works to resume after tea break
Thu (17/04) | 17 Apr 2025 | P5 |  | Road opened back to traffic
Thu (17/04) | 17 Apr 2025 | P16 |  | Crane counterweight dismantle in progress
Thu (17/04) | 17 Apr 2025 | P21 |  | Scaffold erection in progress
Thu (17/04) | 17 Apr 2025 | P20 |  | Excavation to S1 layer
Thu (17/04) | 17 Apr 2025 | P19 |  | Trial trench for ERSS works
Thu (17/04) | 17 Apr 2025 | P18 |  | Crosshead rebar installation
Thu (17/04) | 17 Apr 2025 | P16 |  | Preparation for tendon stressing works
Thu (17/04) | 17 Apr 2025 | P14 |  | Scaffold erection works ongoing
Thu (17/04) | 17 Apr 2025 | P13 |  | Crosshead surface grinding works
Fri (18/04) | 18 Apr 2025 | Exit 3 desander are |  | Preparing to continue dismantling works
Fri (18/04) | 18 Apr 2025 | P18 |  | Rebar works and tendon duct installation
Fri (18/04) | 18 Apr 2025 | P13 |  | Falsework dismantling ongoing
Fri (18/04) | 18 Apr 2025 | P2 |  | Preparing to dismantle S2 walers
Fri (18/04) | 18 Apr 2025 | P3 |  | Preparing for column formwork installation
Fri (18/04) | 18 Apr 2025 | P5 |  | Tightening rebars
Fri (18/04) | 18 Apr 2025 | GL17 towards blk 2 |  | Manual excavation below utilities ongoing. ICE - 2 workers, KTC excavation ongoing
Fri (18/04) | 18 Apr 2025 | BR4 |  | Continue excavation and hacking works
Fri (18/04) | 18 Apr 2025 | ST174, ST175 |  | Guidewall cast yesterday
Fri (18/04) | 18 Apr 2025 | UKP67 |  | Preparation works ongoing
Fri (18/04) | 18 Apr 2025 | DKP24-1 |  | Currently no activity
Fri (18/04) | 18 Apr 2025 | P20 |  | Scaffold access erection in progres
Fri (18/04) | 18 Apr 2025 | P21 |  | No activity
Fri (18/04) | 18 Apr 2025 | P43 |  | Bracket welding works ongoing
Fri (18/04) | 18 Apr 2025 | Zone 4 |  | GCE JGP no activity. Only trial trench for P46-23
Fri (18/04) | 18 Apr 2025 | P49, P50 |  | Utility support welding works in progress
Fri (18/04) | 18 Apr 2025 | Exit 3 |  | CB6 formwork closing
Fri (18/04) | 18 Apr 2025 | Exit 3 |  | Dongah continue dismantling works
Fri (18/04) | 18 Apr 2025 | Exit 3 Washing bay |  | Casting of access widening
Fri (18/04) | 18 Apr 2025 | UKP17 |  | Hacking ongoing before stump rebar works
Fri (18/04) | 18 Apr 2025 | GL17-16 |  | Continue manual excavation near utilities
Fri (18/04) | 18 Apr 2025 | P21 |  | Access installation completed. Now ongoing toe board installation and waler bracket installation
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Excavation works ongoing
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Silo dismantling in progress
Sat (19/04) | 19 Apr 2025 | P21 |  | Excavation to FEL
Sat (19/04) | 19 Apr 2025 | P20 |  | Pile head hacking works
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Welding works ongoing
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | KTC excavation works
Sat (19/04) | 19 Apr 2025 | P18 |  | Jacking installation and tightening works
Sat (19/04) | 19 Apr 2025 | P16 |  | Crosshead materials dismantling works
Sat (19/04) | 19 Apr 2025 | BRP-32 |  | Guidewall removal
Sat (19/04) | 19 Apr 2025 | BR3-BR4 |  | Access making and barricade installation ongoing
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Diagonal strut installation, Strut bracing welding works
Sat (19/04) | 19 Apr 2025 | BR4 |  | Excavation works ongoing
Sat (19/04) | 19 Apr 2025 | BR1/2 |  | Formwork installation works
Sat (19/04) | 19 Apr 2025 | UKP67 |  | Preparation for RC stump works
Sat (19/04) | 19 Apr 2025 | BRP65 |  | Guidewall removal
Sat (19/04) | 19 Apr 2025 | P43 |  | S2 layer waler brackets welding works
Sat (19/04) | 19 Apr 2025 | Exit 1 |  | Current stockpile status
Sat (19/04) | 19 Apr 2025 | P45 |  | GCE work temporarily stopped due to excavator breakdown. Repairing ongoing
Sat (19/04) | 19 Apr 2025 | P48 |  | Trial trench in progress to locate OG box cables
Sat (19/04) | 19 Apr 2025 | Zone 4 JGP |  | C50 trial trench in progress
Sat (19/04) | 19 Apr 2025 | P49 |  | Excavation for UKP bracket installation
Sat (19/04) | 19 Apr 2025 | P50 |  | Manual excavation and welding works for UKP beam stiffiners
Sat (19/04) | 19 Apr 2025 | Zone 4 |  | Weeguan trial trench for army cable shifting works
Sat (19/04) | 19 Apr 2025 | Zone 4 |  | ATS excavation for road diversion & widening works
Sat (19/04) | 19 Apr 2025 | Zone 4 |  | ATS excavation for road diversion & widening works
Sat (19/04) | 19 Apr 2025 | P2 |  | Removal of S2 walers in progress
Sat (19/04) | 19 Apr 2025 | P3 |  | Column formwork closing
Sat (19/04) | 19 Apr 2025 | P5 |  | Column rebar welding works
Sat (19/04) | 19 Apr 2025 | P6 |  | Unloading of materials
Sat (19/04) | 19 Apr 2025 | P18 |  | Crosshead rebars and tendon ducts installation works
Sat (19/04) | 19 Apr 2025 | P5 |  | Falsework assembly works
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Silo dismantling ongoing
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Strutting bracing installation works
Sat (19/04) | 19 Apr 2025 | Exit 3 |  | Excavation works
Sat (19/04) | 19 Apr 2025 | P21 |  | Excavation to FEL ongoing
Sat (19/04) | 19 Apr 2025 | P20 |  | S1 layer welding works for waler brackets in progress
Sat (19/04) | 19 Apr 2025 | BRP-32 |  | Guidewall hacking ongoing
Sat (19/04) | 19 Apr 2025 | BR1/2 |  | Current status for formwork installation works
Sat (19/04) | 19 Apr 2025 | BR4 |  | KTC Excavation works
Sat (19/04) | 19 Apr 2025 | Zone 3 |  | Barricades and access making for RC stump works
Sat (19/04) | 19 Apr 2025 | P43 |  | Waler brackets welding works
Sat (19/04) | 19 Apr 2025 | P43 |  | Joint welding for waler beams
Sat (19/04) | 19 Apr 2025 | P45-15 |  | JGP grouting works ongoing
Sat (19/04) | 19 Apr 2025 | P48 |  | Continue Manual trial trench to locate OG box cables
Sat (19/04) | 19 Apr 2025 | P49 |  | Manual Excavation for UKP bracket installation and access barricade installation in progress
Sat (19/04) | 19 Apr 2025 | P50 |  | Continue manual excavation and welding works
Sat (19/04) | 19 Apr 2025 | P51 |  | Trial trench for UKP-10
Sat (19/04) | 19 Apr 2025 | P2 |  | Removal of S2 walers and hardcores in progress
Sat (19/04) | 19 Apr 2025 | P3 |  | Working platform installation ongoing
Sat (19/04) | 19 Apr 2025 | P5 |  | 1 side wingform formwork installed. Falsework & formwork assembly in progress
Sat (19/04) | 19 Apr 2025 | P12 |  | Crosshead surface grinding works
Sat (19/04) | 19 Apr 2025 | P16 |  | Crosshead formwork and scaffold removal in progress
Sat (19/04) | 19 Apr 2025 | P18 |  | Rebar and cast-in anchor installation
Sat (19/04) | 19 Apr 2025 | UKP17 |  | Stump casting
Sat (19/04) | 19 Apr 2025 | Zone 4 junction |  | Briefing for GCE coring works at junction. Plan for coring and witness by CR105, TMA on site along loyang ave (SB) and 2 traffic marshalls on standby
Sun (20/04) | 20 Apr 2025 | Zone 4 junction |  | SI-2B drilling ongoing
Sun (20/04) | 20 Apr 2025 | SI-2B |  | Stage 1 SPT
Sun (20/04) | 20 Apr 2025 | SI-2B |  | Stage 2 SPT
Sun (20/04) | 20 Apr 2025 | Zone 1 |  | Briefing for P5 beam installation
Sun (20/04) | 20 Apr 2025 | P5 |  | Preparation works ongoing
Sun (20/04) | 20 Apr 2025 | Zone 1 LA | TPE bound | Road closed
Sun (20/04) | 20 Apr 2025 | P5 |  | Beam installation in progress
Sun (20/04) | 20 Apr 2025 | P5 |  | Beam installation completed. Now aligning platform
Sun (20/04) | 20 Apr 2025 | SI-2B |  | SPT-3
Sun (20/04) | 20 Apr 2025 | SI-2B |  | SPT-4
Sun (20/04) | 20 Apr 2025 | P5 |  | Works done for the night — 1 beam installation + 1 working platform. Road safely reopened
Sun (20/04) | 20 Apr 2025 | Exit 3 |  | Diagonal struts installation & bracing works ongoing
Sun (20/04) | 20 Apr 2025 | SI-2B |  | SPT-5
Sun (20/04) | 20 Apr 2025 | SI-2B |  | SPT-6
Sun (20/04) | 20 Apr 2025 | SI-2B |  | Drilling for stage 8 in progress
Mon (21/04) | 21 Apr 2025 | BRP75 |  | Guidewall removal in progres
Mon (21/04) | 21 Apr 2025 | UKP17 |  | Stump formwork dismantling
Mon (21/04) | 21 Apr 2025 | BR4 |  | Excavation in progress
Mon (21/04) | 21 Apr 2025 | BR1, 2 |  | ECM wall formwork closing in progress
Mon (21/04) | 21 Apr 2025 | GL18-17 |  | Manual clearing of soil below utilities
Mon (21/04) | 21 Apr 2025 | ST174 |  | B1 in progress, 12/41.6m
Mon (21/04) | 21 Apr 2025 | Rig 3 | TT02 | Continue drilling for GWV36007
Mon (21/04) | 21 Apr 2025 | Rig 2 | TT01 | Continue drilling for GWV36003
Mon (21/04) | 21 Apr 2025 | Rig 1 |  | GWV36009 has just installed. Next will shift the rig to IS36013
Mon (21/04) | 21 Apr 2025 | P45-17 |  | JGP in progress
Mon (21/04) | 21 Apr 2025 | P48-C49 |  | Coring in progress
Mon (21/04) | 21 Apr 2025 | P49 |  | Excavation for utility support works ongoing
Mon (21/04) | 21 Apr 2025 | P50 |  | Utility support welding works ongoing
Mon (21/04) | 21 Apr 2025 | Zone 4 |  | Shoring installation for DSTA fibre manhole hacking works by Wee Guan
Mon (21/04) | 21 Apr 2025 | Zone 4 LA | SB | ATS works for traffic diversion. Clearing hardcore ongoing
Mon (21/04) | 21 Apr 2025 | N5 U-01 and D-01 |  | Segment adjustments and survey points were taken earlier this afternoon. If alignment is okay, Wendyng will proceed with stitching works tomorrow
Mon (21/04) | 21 Apr 2025 | P43 |  | Preparing waler beams for S2 layer
Mon (21/04) | 21 Apr 2025 | STN-174 |  | 16m / 41.6m
Mon (21/04) | 21 Apr 2025 | P36 |  | Abandoned drain hacking ongoing
Mon (21/04) | 21 Apr 2025 | P19 |  | Preparation for pre-boring. 3 sides TT Completed
Mon (21/04) | 21 Apr 2025 | P20 |  | S1 waler installation. Water to pump out
Mon (21/04) | 21 Apr 2025 | STN-174 |  | 18m / 41.6m
Mon (21/04) | 21 Apr 2025 | GL18-16 |  | Manual excavation in progress. 2 workers
Mon (21/04) | 21 Apr 2025 | P16 |  | Falsework dismantling
Mon (21/04) | 21 Apr 2025 | P3 |  | Column casting in progress
Mon (21/04) | 21 Apr 2025 | P19 |  | Preboring
Mon (21/04) | 21 Apr 2025 | P20 |  | Concrete packing ongoing
Mon (21/04) | 21 Apr 2025 | Exit 3 |  | Drilling ongoing for GWS31003A
Tue (22/04) | 22 Apr 2025 | Near P48 |  | GCE doing SPT testing for Tunnel JGP
Tue (22/04) | 22 Apr 2025 | P49 |  | Exposing services and provide support
Tue (22/04) | 22 Apr 2025 | P49 TPE bound |  | KTC continue exposing services
Tue (22/04) | 22 Apr 2025 | P50 |  | Welding and balance support work target to complete today or tomorrow
Tue (22/04) | 22 Apr 2025 | P51 |  | TT for preboring
Tue (22/04) | 22 Apr 2025 | Rig 1 |  | Waiting for lorry crane to shift from GWV36009 to IS36013
Tue (22/04) | 22 Apr 2025 | Rig 3 | TT02 | Continues drilling and target to install GWV36007 today
Tue (22/04) | 22 Apr 2025 | Rig 2 | TT0Q | Continues drilling and target to install GWV36003 today
Tue (22/04) | 22 Apr 2025 | P8 |  | Area preparation for falsework foundation
Tue (22/04) | 22 Apr 2025 | P5 formwork assembly |  | Plan to install north side today
Tue (22/04) | 22 Apr 2025 | P45 |  | JGP left 4nos to complete. Target tonight to complete
Tue (22/04) | 22 Apr 2025 | P43 |  | Double waler welding in progress
Tue (22/04) | 22 Apr 2025 | P21 |  | Excavation to FEL in progress
Tue (22/04) | 22 Apr 2025 | P19 |  | Preboring for ERSS
Tue (22/04) | 22 Apr 2025 | P18 |  | Installation of links in progress
Tue (22/04) | 22 Apr 2025 | BR4 |  | Continue excavation. Today plan for LSS backfilling
Tue (22/04) | 22 Apr 2025 | GL17-16 |  | Continue exposing utility alignment & manual clearing below services
Tue (22/04) | 22 Apr 2025 | ST174 |  | Excavation temporarily stopped due to desander issue. B1 CD 27.5/41.6m
Tue (22/04) | 22 Apr 2025 | BRP57 |  | Guidewall hacking ongoing
Tue (22/04) | 22 Apr 2025 | DKP24-1 |  | Stump formwork installation in progress
Tue (22/04) | 22 Apr 2025 | P49 |  | Continue exposing services and provide support
Tue (22/04) | 22 Apr 2025 | P48 |  | SPT test for tunnel JGP
Tue (22/04) | 22 Apr 2025 | P50 |  | Continue welding of support
Tue (22/04) | 22 Apr 2025 | North ramp N4-N3 |  | Tunnel RX drilling
Tue (22/04) | 22 Apr 2025 | N5 U-01 and D-01 |  | Sealant application around duct opening. Alignment and level verification still in process
Tue (22/04) | 22 Apr 2025 | Zone 6 |  | Installation of roof truss for noise enclosure
Tue (22/04) | 22 Apr 2025 | P45 |  | Boring started for 1st UP
Tue (22/04) | 22 Apr 2025 | P18 |  | Section 1 links installation. Section 2 and 3 RWDP and PT duct installation
Tue (22/04) | 22 Apr 2025 | P19 |  | Preboring for ERSS continue
Tue (22/04) | 22 Apr 2025 | P20 |  | S1 MP1 completed. KTC to start excavation tomorrow
Tue (22/04) | 22 Apr 2025 | P21 |  | Excavation to FEL continue
Tue (22/04) | 22 Apr 2025 | P19 |  | Preboring for ERSS
Tue (22/04) | 22 Apr 2025 | P18 |  | Continue RWDP and PT duct installatio
Tue (22/04) | 22 Apr 2025 | P14 |  | Preparing platform for lifting frame installation works
Tue (22/04) | 22 Apr 2025 | P20 |  | Currently no activity
Tue (22/04) | 22 Apr 2025 | P21 |  | Continue excavation
Tue (22/04) | 22 Apr 2025 | BR4 |  | LSS backfilling ongoing
Tue (22/04) | 22 Apr 2025 | GL16 |  | Exposing utilities
Tue (22/04) | 22 Apr 2025 | Exit 3 |  | Strut DS1-8 preloading completed
Tue (22/04) | 22 Apr 2025 | P21 |  | Excavation to FEL. Balance 1m
Wed (23/04) | 23 Apr 2025 | P51 |  | TT for preboring
Wed (23/04) | 23 Apr 2025 | P50 |  | Hard barricade installation around utility support area
Wed (23/04) | 23 Apr 2025 | P14 |  | Assembly of lifting frame for balance cantilever segment launching
Wed (23/04) | 23 Apr 2025 | P45 |  | Casing installation for UP. Today plan to cast 2nos
Wed (23/04) | 23 Apr 2025 | P43 |  | Double layer waler installation and welding
Wed (23/04) | 23 Apr 2025 | P5 |  | Side formwork installation
Wed (23/04) | 23 Apr 2025 | Exit 2 |  | Exposing deckpost
Wed (23/04) | 23 Apr 2025 | GL16 |  | Exposing utilities and manual excavation ongoing
Wed (23/04) | 23 Apr 2025 | BR4 |  | Currently no activity. Partial LSS backfill last evening
Wed (23/04) | 23 Apr 2025 | ST174 |  | B1 in progress, 34/41.6m
Wed (23/04) | 23 Apr 2025 | Near DR2 |  | Soil backfilling ongoing
Wed (23/04) | 23 Apr 2025 | BR1, BR2 |  | ECM wall casting in progress
Wed (23/04) | 23 Apr 2025 | UKP17 |  | Backfilling and shoring dismantling
Wed (23/04) | 23 Apr 2025 | P8 |  | Excavation for LSS backfilling
Wed (23/04) | 23 Apr 2025 | P43 |  | Current status of double waler
Wed (23/04) | 23 Apr 2025 | P45 |  | Continue boring for UKP
Wed (23/04) | 23 Apr 2025 | P48 |  | Continue SPT for tunnel JGP
Wed (23/04) | 23 Apr 2025 | P49 |  | KTC continue exposing services at TPE bound
Wed (23/04) | 23 Apr 2025 | P49 |  | Current status at Changi bound
Wed (23/04) | 23 Apr 2025 | N5 D-01 |  | Alignment verification by Surveyor
Wed (23/04) | 23 Apr 2025 | P14 |  | Material shifting for lifting frame assembly
Wed (23/04) | 23 Apr 2025 | Exit 2 |  | Geomotion just mobilised their rig
Wed (23/04) | 23 Apr 2025 | Exit 2 |  | Continue exposing deck post and installation of access ladder
Wed (23/04) | 23 Apr 2025 | BR1, BR2 |  | ECM wall casting in progress
Thu (24/04) | 24 Apr 2025 | Exit 2 |  | Geomotion manual trial pit in progress for RWS50
Thu (24/04) | 24 Apr 2025 | Exit 2 |  | 2nos beams installed for decking works
Thu (24/04) | 24 Apr 2025 | GL16 |  | Manual soil clearing below utilities
Thu (24/04) | 24 Apr 2025 | BR1, 2 |  | ECM wall formwork support dismantling. Yesterday cast wall
Thu (24/04) | 24 Apr 2025 | BRP58A |  | Guidewall hacking ongoing
Thu (24/04) | 24 Apr 2025 | DKP24-2 |  | Waiting for hammer test
Thu (24/04) | 24 Apr 2025 | IW36013 |  | Machine broke down. Now repairing machine
Thu (24/04) | 24 Apr 2025 | N5 D-01 |  | PT duct connected for wet stitching
Thu (24/04) | 24 Apr 2025 | N5 U-01 |  | Segment alignment in progress
Thu (24/04) | 24 Apr 2025 | P18 |  | Section 1 formwork closing, Section 2 and 3 links installation
Thu (24/04) | 24 Apr 2025 | P49 |  | KTC maintaining slope and LE continue utility support welding work
Thu (24/04) | 24 Apr 2025 | P50 |  | Exposing unknown cable for SPPG to witness tomorrow
Thu (24/04) | 24 Apr 2025 | P50 |  | Addressing comment from PD safety tour
Thu (24/04) | 24 Apr 2025 | P45 |  | Casing installation. Tomorrow to cast two numbers
Thu (24/04) | 24 Apr 2025 | P43 |  | Double layer S2 layer welding
Thu (24/04) | 24 Apr 2025 | DR2 |  | LSS backfilling beside drain
Thu (24/04) | 24 Apr 2025 | BR4 |  | Exposing coupler and prepare for slope lean concrete
Thu (24/04) | 24 Apr 2025 | P19 |  | Preboring for ERSS
Thu (24/04) | 24 Apr 2025 | P5 |  | Barricade and rebar cage support installation
Thu (24/04) | 24 Apr 2025 | P2 |  | Rebar and formwork installation
Thu (24/04) | 24 Apr 2025 | P20 |  | Pile head hacking work
Thu (24/04) | 24 Apr 2025 | P21 |  | Current status of pile head hacking work
Fri (25/04) | 25 Apr 2025 | DKP24-2 |  | Will handover to Wenndyng after hammer test later
Fri (25/04) | 25 Apr 2025 | BRP59 |  | Preparing for guidewall removal
Fri (25/04) | 25 Apr 2025 | Rig 2 | TT01 | Waiting for RTO to inspect toe level prior to installation of GWS36003
Fri (25/04) | 25 Apr 2025 | Rig 3 | TT02 | Waiting for RTO to inspect toe level prior to installation of GWS36007
Fri (25/04) | 25 Apr 2025 | Rig1 |  | Continues drilling for IS36013, target to install today
Fri (25/04) | 25 Apr 2025 | P50 |  | Cable spiking done. Now removal of cable
Fri (25/04) | 25 Apr 2025 | P45 |  | 2 casing installed. Today to cast two UKP
Fri (25/04) | 25 Apr 2025 | P48 |  | Pipe sleeves installation for JGP
Fri (25/04) | 25 Apr 2025 | P49 |  | Manual exposing for support installation
Fri (25/04) | 25 Apr 2025 | P49 |  | Continue support installation
Fri (25/04) | 25 Apr 2025 | P2 |  | Formwork closing and links installation
Fri (25/04) | 25 Apr 2025 | P14 |  | Starter hanger working platform assembly
Fri (25/04) | 25 Apr 2025 | BR4 |  | Exposing couplers and today to lean con
Fri (25/04) | 25 Apr 2025 | Near DR2 |  | Soil backfilling ongoing
Fri (25/04) | 25 Apr 2025 | BR6 |  | No activity
Fri (25/04) | 25 Apr 2025 | GL16 |  | Hirose to start day and night works from tomorrow. Currently KTC excavation progressing towards GL12
Fri (25/04) | 25 Apr 2025 | P19 |  | Preboring for ERSS
Fri (25/04) | 25 Apr 2025 | P18 |  | Shear link installation
Fri (25/04) | 25 Apr 2025 | P21 |  | Continue pile head hackinv
Fri (25/04) | 25 Apr 2025 | P5 |  | Now no activity. Heavy rain started
Sat (26/04) | 26 Apr 2025 | P18 |  | Rectification of barricade
Sat (26/04) | 26 Apr 2025 | P19 |  | TT and prepboring for ERSS
Sat (26/04) | 26 Apr 2025 | P20 |  | Pile head hacking
Sat (26/04) | 26 Apr 2025 | P21 |  | Pile head hacking and pile surface roughening
Sat (26/04) | 26 Apr 2025 | BR4 |  | CJ roughening
Sat (26/04) | 26 Apr 2025 | N5 |  | PVC installation and prepare for working platform installatiom
Sat (26/04) | 26 Apr 2025 | STN174 |  | B1 excavation
Sat (26/04) | 26 Apr 2025 | P5 |  | Lowering down unused materials and GI pipes installation for rebar work
Sat (26/04) | 26 Apr 2025 | P5 |  | Crosshead formwork adjusting work
Sat (26/04) | 26 Apr 2025 | Zone 4 |  | Lane close by singtel contractor
Sat (26/04) | 26 Apr 2025 | P2 |  | Footing top coupler bar installation
Sat (26/04) | 26 Apr 2025 | Zone 4 |  | Eng Hup on site for traffic light cable pulling work
Sat (26/04) | 26 Apr 2025 | P51 |  | TT for preboring work
Sat (26/04) | 26 Apr 2025 | P45 |  | Reading taking for instrument
Sat (26/04) | 26 Apr 2025 | P49 |  | Status of main beam and secondary beam installation
Sat (26/04) | 26 Apr 2025 | P43 |  | Diagonal strut installed. By today plan to complete horizontal strut also
Sat (26/04) | 26 Apr 2025 | P45 |  | 4nos of UKP cast. Today will cast two
Sat (26/04) | 26 Apr 2025 | BR4 |  | Pump car on site for lean concrete
Sat (26/04) | 26 Apr 2025 | Exit 3 |  | Hard barricade installation for access and strut end welding
Sat (26/04) | 26 Apr 2025 | P21 |  | Pile head hacking done. Need to trim the surface only
Sat (26/04) | 26 Apr 2025 | P20 |  | Continue pile head hacking
Sat (26/04) | 26 Apr 2025 | P19 |  | Preboring for ERSS
Sat (26/04) | 26 Apr 2025 | P18 |  | Current status of rebar work. Now no activity
Sat (26/04) | 26 Apr 2025 | N5 |  | PVC pipe putting inside tendom duct
Sat (26/04) | 26 Apr 2025 | P2 |  | Continue top bar installation
Sat (26/04) | 26 Apr 2025 | P50 |  | Stiffener plate welding and prepare for next stage excavation
Sat (26/04) | 26 Apr 2025 | P48 |  | Balance JGP grouting and testing
Sat (26/04) | 26 Apr 2025 | P43 |  | Packing concrete casting
Sat (26/04) | 26 Apr 2025 | Exit 1 |  | Access dismantling and pumping main pipe removal
Sat (26/04) | 26 Apr 2025 | BR4 |  | Pump set up for lean concrete
Sat (26/04) | 26 Apr 2025 | Exit 2 |  | Deck beam installation
Sat (26/04) | 26 Apr 2025 | Exit 2 |  | Two TT done for recharge well. Monday will start boring
Sat (26/04) | 26 Apr 2025 | Exit 3 |  | Continue excavation below decking
Sat (26/04) | 26 Apr 2025 | P2 |  | Links installation 95% completed
Sat (26/04) | 26 Apr 2025 | P5 |  | Scaffold support installation for rebar works
Sat (26/04) | 26 Apr 2025 | Exit 3 |  | Angle bracket installation on strut
Sun (27/04) | 27 Apr 2025 | Zone 4 |  | TT for JGP
Sun (27/04) | 27 Apr 2025 | Exit 3 |  | Strut angle bracket installed
Mon (28/04) | 28 Apr 2025 | P49 |  | Manual excavation to expose utilities
Mon (28/04) | 28 Apr 2025 | P45 |  | UKP preboring work
Mon (28/04) | 28 Apr 2025 | P46 |  | JGP Grouting works
Mon (28/04) | 28 Apr 2025 | Rig 1 |  | Has shifted to IW35005 @ vent shaft
Mon (28/04) | 28 Apr 2025 | P2 pile cap |  | Pump car set up for casting
Mon (28/04) | 28 Apr 2025 | CCE4 |  | Continues excavation & soil disposal
Mon (28/04) | 28 Apr 2025 | P43 |  | MPI test for S2 strut on going
Mon (28/04) | 28 Apr 2025 | P8 |  | Drilling for tunnel RX
Mon (28/04) | 28 Apr 2025 | P8 |  | Hardcore laying for falsework foundation
Mon (28/04) | 28 Apr 2025 | Exit 2 |  | Decking welding works ongoing
Mon (28/04) | 28 Apr 2025 | P20 |  | Scaffold access erection and dismantling to continue excavation
Mon (28/04) | 28 Apr 2025 | P21 |  | Bar chair installation
Mon (28/04) | 28 Apr 2025 | UKP16 |  | Slope lean con cast. Area preparation for stump works
Mon (28/04) | 28 Apr 2025 | GL15-16 |  | Continue exposing utility
Mon (28/04) | 28 Apr 2025 | ST71-72 |  | Guidewall casting in progress
Mon (28/04) | 28 Apr 2025 | GL17 |  | Utility support installation in progress
Mon (28/04) | 28 Apr 2025 | ST174 |  | B2 in progress, 22.5/41.6m
Mon (28/04) | 28 Apr 2025 | BR4 |  | Area preparation for next section of lean concrete casting, Started debonding sheet laying, unloading rebars and continue exposing couplers
Mon (28/04) | 28 Apr 2025 | P19 |  | Last preboring point for ERSS installation
Mon (28/04) | 28 Apr 2025 | P20 |  | No activity
Mon (28/04) | 28 Apr 2025 | P21 |  | Rebar works in progress
Mon (28/04) | 28 Apr 2025 | P22 |  | Excavation in progress
Mon (28/04) | 28 Apr 2025 | Exit 3 |  | Welding works ongoing
Tue (29/04) | 29 Apr 2025 | Exit 2 |  | Preparing for welding works at decking area
Tue (29/04) | 29 Apr 2025 | RWS56 |  | In progress
Tue (29/04) | 29 Apr 2025 | RWS51 |  | Preparing to start
Tue (29/04) | 29 Apr 2025 | UKP16 |  | Today plan for hammer test and start rebar planting
Tue (29/04) | 29 Apr 2025 | DKP23-1C |  | Dewatering ongoing. Today plan for hammer test and start rebar planting
Tue (29/04) | 29 Apr 2025 | Zone P8 |  | Drilling for tunnel RX
Tue (29/04) | 29 Apr 2025 | P8-1 |  | Lean con completed for falsework foundation
Tue (29/04) | 29 Apr 2025 | CCE4 |  | Excavation in progress
Tue (29/04) | 29 Apr 2025 | P14 |  | Assembly of spreader beams
Tue (29/04) | 29 Apr 2025 | N5 U-01 |  | Surveyor taking asbuilt alignment for verification
Tue (29/04) | 29 Apr 2025 | P18 |  | Anti burst link installation
Tue (29/04) | 29 Apr 2025 | P43 |  | No activity
Tue (29/04) | 29 Apr 2025 | P22 TB area |  | Excavation in progress
Tue (29/04) | 29 Apr 2025 | Exit 3 |  | Runner beam bolt tightening & waler joint welding works
Tue (29/04) | 29 Apr 2025 | P45 |  | UKP pre-boring works on-going
Tue (29/04) | 29 Apr 2025 | P46 |  | JGP works on-going
Tue (29/04) | 29 Apr 2025 | P49 |  | Welding works for utility support
Tue (29/04) | 29 Apr 2025 | P50 |  | Excavation to1st layer of caison
Tue (29/04) | 29 Apr 2025 | P51 |  | UKP trial trench works
Tue (29/04) | 29 Apr 2025 | Blk 2 |  | Excavation started to expose area for subsequent stump work
Tue (29/04) | 29 Apr 2025 | GL16-15 |  | Continue exposing utilities for support works
Tue (29/04) | 29 Apr 2025 | BR4 |  | Continue rebar works
Tue (29/04) | 29 Apr 2025 | P19 |  | No more activity. SP 100% completed. LP 50% completed
Wed (30/04) | 30 Apr 2025 | P18 |  | Waiting for formwork COS. This evening to cast
Wed (30/04) | 30 Apr 2025 | P14 |  | Spreader beam hydraulic installation
Wed (30/04) | 30 Apr 2025 | P43 |  | Excavation for BP exposing
Wed (30/04) | 30 Apr 2025 | P45 |  | UKP installation
Wed (30/04) | 30 Apr 2025 | P46 |  | JGP in progress
Wed (30/04) | 30 Apr 2025 | P48 |  | SPT 51 coring works
Wed (30/04) | 30 Apr 2025 | PMH26 |  | Plate load test
Fri (02/05) | 02 May 2025 | P2 |  | Formwork dismantling
Fri (02/05) | 02 May 2025 | P8 |  | Falsework installation
Fri (02/05) | 02 May 2025 | P8 | south side | Today to lean con for falsework foundation
Fri (02/05) | 02 May 2025 | P14 |  | Hydraulic jack and hydraulic hose connection at starter hanger
Fri (02/05) | 02 May 2025 | P19 |  | Driving ERSS 700mm below ground level. Tomorrow excavation to S1 will start
Fri (02/05) | 02 May 2025 | P43 |  | Excavation to expose BP
Fri (02/05) | 02 May 2025 | P45 |  | Preboring for UKP installation
Fri (02/05) | 02 May 2025 | P48 |  | Coring works P48-SPT48
Sat (03/05) | 03 May 2025 | P21 |  | Column stump rebar completed
Sat (03/05) | 03 May 2025 | P8 |  | Falsework leg frame assembly
Sat (03/05) | 03 May 2025 | P6-7 |  | Lifting frame material unloading
Sat (03/05) | 03 May 2025 | N5 |  | Screw jack installation for 2nd pair segment launching
Sat (03/05) | 03 May 2025 | P50 |  | Excavation to 1stlayer caison in progress
Sat (03/05) | 03 May 2025 | P49 |  | Manual excavation to expose utility
Sat (03/05) | 03 May 2025 | P47-48 point C45 |  | Preparation for JGP testing
Sat (03/05) | 03 May 2025 | P43 |  | Excavation to FEL
Sat (03/05) | 03 May 2025 | Opp blk 4 |  | Excavation for Utility support
Sat (03/05) | 03 May 2025 | Opp blk 2 |  | Stump rebar and formwork closing
Sat (03/05) | 03 May 2025 | P8 |  | Falsework assembly continue
Sat (03/05) | 03 May 2025 | GL 3-4 |  | Installation of traffic deck frame
Sat (03/05) | 03 May 2025 | P49 |  | No more activity
Sat (03/05) | 03 May 2025 | P50 |  | Excavation continue
Mon (05/05) | 05 May 2025 | P43 |  | Excavation and levelling of the base for lean concrete. Tomorrow plan for lean concrete
Mon (05/05) | 05 May 2025 | P50 |  | 2nd layer hacking of abandoned drain and grout
Mon (05/05) | 05 May 2025 | P49 |  | Manual excavation to install utility support. To complete welding work in 3 days
Mon (05/05) | 05 May 2025 | P45 |  | 2 UP will cast today. Boring done
Mon (05/05) | 05 May 2025 | P48 |  | Now rig hydraulic hose leak. Mechanic on the way
Mon (05/05) | 05 May 2025 | P46 |  | Boring for grouting work
Mon (05/05) | 05 May 2025 | P21 |  | Formwork dismantling for pilecap in progress. Tonight to cast column stump
Mon (05/05) | 05 May 2025 | P20 |  | Preparation for pile head cutting works
Mon (05/05) | 05 May 2025 | P19 |  | Waler brackets welding in progress
Mon (05/05) | 05 May 2025 | P17 |  | Surface grinding works in progress
Mon (05/05) | 05 May 2025 | N5 Segment |  | Formwork materials segregation in progress
Mon (05/05) | 05 May 2025 | P14 |  | Crane setting up for starter hanger lifting works
Mon (05/05) | 05 May 2025 | BR4 |  | Corrugated pipes and rebar installation in progress, Preparing KP area
Mon (05/05) | 05 May 2025 | GL18 |  | Manual cleaning of soil on top of utility
Mon (05/05) | 05 May 2025 | ST174 |  | Casting in progress
Mon (05/05) | 05 May 2025 | ST72 |  | B1 in progress
Mon (05/05) | 05 May 2025 | P9 |  | RG drilling works in progress for piezometer installation
Mon (05/05) | 05 May 2025 | P7 |  | Exisiting drain hacking for ERSS works in progress
Mon (05/05) | 05 May 2025 | P8 |  | Falsework and scaffold installation ongoing
Mon (05/05) | 05 May 2025 | CCE4 |  | Current excavation status
Mon (05/05) | 05 May 2025 | P4 |  | Housekeeping ongoing. Rebar delivery for p5 will arrive tonight
Mon (05/05) | 05 May 2025 | P2 |  | Pile cap no activity
Mon (05/05) | 05 May 2025 | UKP15 |  | Stump formwork installation ongoing
Tue (06/05) | 06 May 2025 | P46 |  | Tonight to continue TT and pipe sleeve installation
Tue (06/05) | 06 May 2025 | Rig 2-TT02 |  | IE35008 installation in progress
Tue (06/05) | 06 May 2025 | Rig 1-TT01 |  | IE35007 toe level has inspected, installation will commence in a short while
Tue (06/05) | 06 May 2025 | P49 |  | Slope casting and welding works for utility support
Tue (06/05) | 06 May 2025 | P43 |  | Excavation to FEL (2nd stage)
Tue (06/05) | 06 May 2025 | P48 |  | Excavation to utilities level
Tue (06/05) | 06 May 2025 | P50 |  | Excavation to 1st caison level
Tue (06/05) | 06 May 2025 | P46 |  | JGP drilling works on going
Tue (06/05) | 06 May 2025 | P45 |  | UKP preboring works
Tue (06/05) | 06 May 2025 | P48 |  | Coring work SPT-46
Tue (06/05) | 06 May 2025 | N5 |  | Stitching formwork closing
Tue (06/05) | 06 May 2025 | CCW | GL W8 | Excavation in progress
Tue (06/05) | 06 May 2025 | CCW | GL W1 | Welding works ongoing
Tue (06/05) | 06 May 2025 | S1-1 |  | Preparing for deck post end plate welding works
Tue (06/05) | 06 May 2025 | GL9 |  | UKP12, UKP13 stumps plan for casting tomorrow
Tue (06/05) | 06 May 2025 | GL10 |  | UKP14 stump cast
Tue (06/05) | 06 May 2025 | GL11 |  | UKP15 stump cast
Tue (06/05) | 06 May 2025 | GL12 |  | Current status of excavation for utility support works
Tue (06/05) | 06 May 2025 | S2 |  | Fire hydrant decommissioned
Tue (06/05) | 06 May 2025 | P8 |  | 100T crane setup for Primary beam installation across bus lane tonight
Tue (06/05) | 06 May 2025 | P8 |  | Bottom formwork installation
Tue (06/05) | 06 May 2025 | GL17 |  | Utility support angle bar installation
Tue (06/05) | 06 May 2025 | BR4 |  | Continue top bar installation and exposing the KP area
Tue (06/05) | 06 May 2025 | ST72 |  | Cutter teeth changing ongoing. B1 CD 16.3/25.9m
Tue (06/05) | 06 May 2025 | P2 |  | Excavator mobilise for backfilling. To start tomorrow
Tue (06/05) | 06 May 2025 | P43 |  | Preparing for base lean concrete
Tue (06/05) | 06 May 2025 | Exit 3 |  | No activity
Wed (07/05) | 07 May 2025 | P8 |  | Working platform assembly. To install later after last bus
Wed (07/05) | 07 May 2025 | P5 crosshead |  | Installation of GI pipe support for top bar installation
Wed (07/05) | 07 May 2025 | N5 |  | Stitching formwork closing in progress
Wed (07/05) | 07 May 2025 | P21 |  | Column stump cast yst. Materials removal in progress
Wed (07/05) | 07 May 2025 | P20 |  | Pile head hacking ongoing
Wed (07/05) | 07 May 2025 | P19 |  | Welding ongoing for stiffener & triangular plates
Wed (07/05) | 07 May 2025 | P18 |  | Preparation for formwork removal
Wed (07/05) | 07 May 2025 | P14 |  | Starter hanger beam connection & installation in progress
Wed (07/05) | 07 May 2025 | P8-1 |  | Pier column hacking to correct level in progress
Wed (07/05) | 07 May 2025 | P9 |  | RG drilling for IM piezometer installation ongoing
Wed (07/05) | 07 May 2025 | S2 to P6-2 |  | LPs removal in progress. 1/4 nos. completed
Wed (07/05) | 07 May 2025 | P7-2 |  | Utility team checking on abandoned utility services before resuming of ERSS works
Wed (07/05) | 07 May 2025 | P5 |  | Crosshead bottom rebars installation in progress
Wed (07/05) | 07 May 2025 | P3 |  | Column surface grinding & patching works
Wed (07/05) | 07 May 2025 | P2 |  | KTC preparation for backfilling works. Afternoon to start
Wed (07/05) | 07 May 2025 | P48 |  | Ley Choon exposing 300mm dia pipe to adjust it for 800mm dia pipe laying work
Wed (07/05) | 07 May 2025 | P49 |  | Utility support welding. Today to complete
Wed (07/05) | 07 May 2025 | P50 |  | Continue removal of cement grout and excavation
Wed (07/05) | 07 May 2025 | P8 |  | Preparing to close bus lane for Primary beam installation
Wed (07/05) | 07 May 2025 | P50 |  | Continue hacking of cement grout and excavation. Tomorrow will have two mini excavators for the work
Wed (07/05) | 07 May 2025 | P48 |  | Ley choon laying of 300mm dia water pipe for future connection to 800mm dia
Wed (07/05) | 07 May 2025 | P48 |  | KTC started excavation yesterday
Wed (07/05) | 07 May 2025 | P49 |  | Bundwall levelling for lean concrete. Concrete ordered
Wed (07/05) | 07 May 2025 | S1-1 |  | 1nos main beam & 4nos secondary beams installed. Welding works in progress
Wed (07/05) | 07 May 2025 | GL17 |  | Continue angle bar installation
Wed (07/05) | 07 May 2025 | BR4 |  | Continue top bar installation
Wed (07/05) | 07 May 2025 | ST72 |  | Preparing for cutter teeth changing. B1 CD 16.4/25.9m
Wed (07/05) | 07 May 2025 | P5 |  | Crosshead rebar installation works
Wed (07/05) | 07 May 2025 | P2 |  | Backfilling in progress
Wed (07/05) | 07 May 2025 | P3 |  | Column Patching works
Wed (07/05) | 07 May 2025 | P43 |  | Prepare to lower down excavator for hacking
Wed (07/05) | 07 May 2025 | P7-2 |  | Backfilling works in progress
Wed (07/05) | 07 May 2025 | S2 to P6-2 |  | LPs removal completed. 4/4 nos. completed
Wed (07/05) | 07 May 2025 | P8-1 |  | Pier column hacking to correct level and plywood laying for bottom formwork in progress
Wed (07/05) | 07 May 2025 | P14 |  | Lifting frame assembly works
Wed (07/05) | 07 May 2025 | N5 |  | Stitching outer and inner formwork closing
Wed (07/05) | 07 May 2025 | P18 |  | Formwork dismantling in progress
Wed (07/05) | 07 May 2025 | P19 |  | Welding completed. MPI tests in progress
Wed (07/05) | 07 May 2025 | P20 |  | Pile head hacking current status
Wed (07/05) | 07 May 2025 | P21 |  | Hacking of abandoned POB pile prior to concrete plug casting
Wed (07/05) | 07 May 2025 | Exit 3 |  | Excavation ongoing
Wed (07/05) | 07 May 2025 | CCW | GL-W6 | Excavation in progress
Wed (07/05) | 07 May 2025 | Zone 4 |  | 1 lane closed for vibro shifting from P49 to P48
Wed (07/05) | 07 May 2025 | S1-1 |  | Continue deck post end plate welding works
Wed (07/05) | 07 May 2025 | Near exit 2 |  | Decking panel installation in progress
Wed (07/05) | 07 May 2025 | GL11 | SB | Deck post end plate welding in progress
Wed (07/05) | 07 May 2025 | GL9 |  | UKP12, UKP13 formwork closed. To cast tmr
Wed (07/05) | 07 May 2025 | GL15-12 |  | Rearranging concrete barriers and slope levelling
Wed (07/05) | 07 May 2025 | BR4 |  | KP stump casting in progress
Wed (07/05) | 07 May 2025 | ST72 |  | B1 CD 16.5/25.9m. Only 300mm since last night. Now cutter teeth changing ongoing
Wed (07/05) | 07 May 2025 | N5 D-01 |  | Formwork 0% completed
Thu (08/05) | 08 May 2025 | P5 crosshead |  | Bottom bar installation continue
Thu (08/05) | 08 May 2025 | P45 |  | Expose street light cable. Preparation for UKP drilling works
Thu (08/05) | 08 May 2025 | P46 |  | Preparation for JGP works
Thu (08/05) | 08 May 2025 | DR03 |  | Trial Trench for UKP
Thu (08/05) | 08 May 2025 | P47 |  | Trial Trench for coring works
Thu (08/05) | 08 May 2025 | P47 |  | Coring works in progress
Thu (08/05) | 08 May 2025 | P48 |  | Excavation until utilities level
Thu (08/05) | 08 May 2025 | P49 |  | No activity
Thu (08/05) | 08 May 2025 | P21 |  | Hacking of abandoned POB pile in progress
Thu (08/05) | 08 May 2025 | P20 |  | Pile head hacking in progress
Thu (08/05) | 08 May 2025 | P19 |  | Pending strain gauge installation @ 4pm today. Excavation will start tmr
Thu (08/05) | 08 May 2025 | P18 |  | Formwork dismantling in progress
Thu (08/05) | 08 May 2025 | P14 |  | Lifting frame assembly in progress
Thu (08/05) | 08 May 2025 | N5 |  | Stitching Formwork closing in progress. 85% completed for U-01
Thu (08/05) | 08 May 2025 | Near exit 2 |  | 6nos secondary beams & 4nos main beams installed. Welding works in progress
Thu (08/05) | 08 May 2025 | BR4 |  | No activity
Thu (08/05) | 08 May 2025 | ST72 |  | Preparing for cutter teeth changing again. B1 CD 16.6/25.9m
Thu (08/05) | 08 May 2025 | P9 |  | RG Piezometer installation completed. Preparation to shift to next location
Thu (08/05) | 08 May 2025 | P8 |  | Falsework and Formwork installation
Thu (08/05) | 08 May 2025 | P7-2 |  | Continue removal of abandoned services for ERSS works. Tmr to start Preboring
Thu (08/05) | 08 May 2025 | P5 |  | Crosshead Rebar installation and Formwork assembly in progress
Thu (08/05) | 08 May 2025 | P2 |  | KTC backfilling works
Fri (09/05) | 09 May 2025 | Exit 3/CCW |  | Excavation in progres
Fri (09/05) | 09 May 2025 | S1-1 |  | Unloading decking panels
Fri (09/05) | 09 May 2025 | P22 |  | Currently no activity. Today plan to start rebar works
Fri (09/05) | 09 May 2025 | GL9 |  | UKP12, UKP13 stumps cast yesterday
Fri (09/05) | 09 May 2025 | GL13 |  | Manual clearing of soil below services
Fri (09/05) | 09 May 2025 | BR4 |  | Manual trimming at KP area, Balance lean con cast yesterday. Today plan to continue debonding sheet laying and rebar works
Fri (09/05) | 09 May 2025 | ST72 |  | Cutter teeth changing ongoing. B1 CD 16.8/25.9m. Was informed on site that BG machine will be mobilised tmr
Fri (09/05) | 09 May 2025 | Rig TT01 |  | Waiting for RTO to inspect toe level prior to install GWV35007
Fri (09/05) | 09 May 2025 | Rig TT02 |  | Drilling continues for GWV35008
Fri (09/05) | 09 May 2025 | P20 |  | Pile head hacking
Fri (09/05) | 09 May 2025 | P18 |  | Scaffold access erection for stressing works
Fri (09/05) | 09 May 2025 | P2 |  | Backfilling to pile cap level. 2/5 layer
Fri (09/05) | 09 May 2025 | P5 |  | Side formwork assembly
Fri (09/05) | 09 May 2025 | P7-2 |  | Pre-boring for ERSS started
Fri (09/05) | 09 May 2025 | Near exit 2 |  | Continue decking panel installation
Fri (09/05) | 09 May 2025 | GL15 |  | Utility support c-channel installation in progress
Fri (09/05) | 09 May 2025 | BR4 |  | Continue bottom rebars installation
Fri (09/05) | 09 May 2025 | GL E5 | PTD 3694 | Continue exposing abandoned 700mm dia water pipe
Fri (09/05) | 09 May 2025 | Near blk 2 |  | KTC preparing work area for abandoned drain hacking from GL12-10
Fri (09/05) | 09 May 2025 | CCE4 |  | Levelling ongoing for S1 waler works
Fri (09/05) | 09 May 2025 | P50 |  | 2nd layer excavation on going
Fri (09/05) | 09 May 2025 | P43 |  | Bored pile hacking
Fri (09/05) | 09 May 2025 | P46 |  | JGP works on going
Fri (09/05) | 09 May 2025 | P46 |  | Trial Trench for UKP
Fri (09/05) | 09 May 2025 | P48 |  | GWS51023 installation
Fri (09/05) | 09 May 2025 | P48 |  | Excavation until utilities level
Fri (09/05) | 09 May 2025 | P49 |  | Manual excavation on going
Fri (09/05) | 09 May 2025 | P8 |  | Bottom formwork installation
Fri (09/05) | 09 May 2025 | P14 |  | Suspended working platform assembly
Fri (09/05) | 09 May 2025 | N5 D-01 |  | Stitching formwork 40% completed
Fri (09/05) | 09 May 2025 | P18 |  | Strand arranged for pulling
Sat (10/05) | 10 May 2025 | P49 |  | Today to start excavation at the center for mini excavator access
Sat (10/05) | 10 May 2025 | GL5 |  | Beam welding ongoing
Sat (10/05) | 10 May 2025 | GL5-6 |  | Formwork closing for capping beam. To cast today
Sat (10/05) | 10 May 2025 | Exit 2 |  | Guidewall hacking ongoing
Sat (10/05) | 10 May 2025 | Exit 2 |  | RWS54 trial pit ongoing
Sat (10/05) | 10 May 2025 | GL8-11 | SB | Decking panel installation done
Sat (10/05) | 10 May 2025 | S1-2 | SB | Decking beam installed up till GL12, GL13: Continue deck post endplate welding works
Sat (10/05) | 10 May 2025 | GL13-14 | Near blk 2 | Manual clearing of soil below services and utility support welding works ongoing
Sat (10/05) | 10 May 2025 | BR4 |  | Continue rebar works, Starting to install hyrib and formwork
Sat (10/05) | 10 May 2025 | ST175 |  | BC1 has shifted to this panel. Excavation started this morning
Sat (10/05) | 10 May 2025 | ST72 |  | Excavation temporarily stopped. B1 CD 16.8/25.9mz BG machine will be mobilised here today
Sat (10/05) | 10 May 2025 | N5 D-01 |  | Stitching formwork 70% completed. Casting after last bus as mobile crane need to park at the bus lane for casting
Sat (10/05) | 10 May 2025 | P14 |  | Ultracon material shifting in preparation for load test next week
Sat (10/05) | 10 May 2025 | P8 |  | Side formwork to start installation today
Sat (10/05) | 10 May 2025 | P6-2 |  | Hoarding shifted. TT to start today
Sat (10/05) | 10 May 2025 | CCE4 |  | Continue levelling for S1 waler works
Sat (10/05) | 10 May 2025 | CCW | GL-W7 | S2 1nos waler beam installed. Plan to do concrete packing today
Sat (10/05) | 10 May 2025 | GL-W7 |  | Access installation ongoing. Runner beam preparation ongoing
Sat (10/05) | 10 May 2025 | CCW | GL-W6 | Continue S2 excavation
Sat (10/05) | 10 May 2025 | Exit 3 |  | Continue excavation
Sat (10/05) | 10 May 2025 | P7-2 |  | Boring rig weekly inspection and pre-boring
Sat (10/05) | 10 May 2025 | GL5-6 |  | Capping beam cast
Sat (10/05) | 10 May 2025 | BR4 |  | Bar chair installation ongoing
Sat (10/05) | 10 May 2025 | GL-E6 |  | Exposing utility alignment
Sat (10/05) | 10 May 2025 | CCE4 |  | Hirose marking for S1 waler bracket installation
Sat (10/05) | 10 May 2025 | ST72 |  | Preboring machine arrived on site
Sat (10/05) | 10 May 2025 | P48 |  | Water pipe branching exposed. UKP top plate 7 nos installed
Sat (10/05) | 10 May 2025 | Exit 3 |  | Excavation in progres
Sat (10/05) | 10 May 2025 | CCW | GL-W7 | Today to continue waler beam and runner beam installation
Sat (10/05) | 10 May 2025 | CCW | GL-W6 | Excavation in progress
Sat (10/05) | 10 May 2025 | P22 |  | Rebar works in progress
Sat (10/05) | 10 May 2025 | CCW between | GL-W8 to GL1 | Excavation ongoing
Mon (12/05) | 12 May 2025 | P19 |  | Current status for FEL excavation
Mon (12/05) | 12 May 2025 | P18 |  | Preparation for tendon stressing works. Tmr to start
Mon (12/05) | 12 May 2025 | N5 |  | Stitching casting completed for D01 & U01. Tendon duct and strand installation completed. Stressing to be done after achieve of cube strength
Mon (12/05) | 12 May 2025 | P14 |  | Spreader beam connection and setting up works
Mon (12/05) | 12 May 2025 | P8 |  | Pier hacking to correct level and side formwork assembly in progress. 1 of the wingform formwork installed
Mon (12/05) | 12 May 2025 | P7-2 & P6-2 |  | No activity
Mon (12/05) | 12 May 2025 | P5 |  | Steel anchor for PT duct installation and rebar installation for box grider ongoing
Mon (12/05) | 12 May 2025 | P2 |  | No activity
Mon (12/05) | 12 May 2025 | Zone 4 P46-P47 |  | Trial trench works for UP-9 ongoing
Mon (12/05) | 12 May 2025 | Zone 4 |  | Other areas no activity except housekeeping
Mon (12/05) | 12 May 2025 | P43 |  | Excavation works ongoing
Mon (12/05) | 12 May 2025 | Bet. P38-P39 |  | Removal of abandoned water pipe ongoing
Mon (12/05) | 12 May 2025 | BR4 |  | Rebar works installation in progress
Mon (12/05) | 12 May 2025 | JTC/BLK 4 - STN072 | BG 01 | PB01 Preboring ongoing
Mon (12/05) | 12 May 2025 | Selarang Camp - STN175 | BC 01 | 2nd bite excavation in progress
Mon (12/05) | 12 May 2025 | Exit 1 Desander |  | Current stockpile status
Mon (12/05) | 12 May 2025 | Near JTC blk 2, Bet. P28-P29 |  | KTC excavation works ongoing
Mon (12/05) | 12 May 2025 | P5 |  | Continue steel anchor for PT duct and rebar installation for box grider
Mon (12/05) | 12 May 2025 | P8 |  | Pier hacking to correct level and Formwork assembly ongoing
Mon (12/05) | 12 May 2025 | P18 |  | No activity. Stressing to start tmr
Mon (12/05) | 12 May 2025 | P20 |  | Continue rebar installation for pilecap
Mon (12/05) | 12 May 2025 | P22 |  | Continue rebar installation works
Mon (12/05) | 12 May 2025 | Exit 3 |  | KTC excavation works
Mon (12/05) | 12 May 2025 | Near JTC blk 2, Bet. P29-P30 |  | Excavation for utility support works in progress
Mon (12/05) | 12 May 2025 | BR4 |  | Continue rebar and Formwork installation works
Mon (12/05) | 12 May 2025 | Selarang Camp - STN175 | BC 01 | Continue 2nd bite excavation
Mon (12/05) | 12 May 2025 | JTC/BLK 4 - STN072 | BG 01 | PB01 Preboring ongoing, current depth 18m
Mon (12/05) | 12 May 2025 | Bet. P38-P39 |  | Removal of abandoned water pipe completed
Mon (12/05) | 12 May 2025 | P43 |  | Excavation work stopped for the day
Mon (12/05) | 12 May 2025 | Zone 4 |  | Work stopped for the day. Housekeeping ongoing
Mon (12/05) | 12 May 2025 | Exit 3 |  | KTC excavation works
Mon (12/05) | 12 May 2025 | P22 |  | Rebar works in progress (CGW)
Mon (12/05) | 12 May 2025 | P21 |  | Water pumping in progress
Mon (12/05) | 12 May 2025 | P20 |  | Pile cap rebar and formworks installation
Tue (13/05) | 13 May 2025 | P18 |  | Preparation for post tensioning
Tue (13/05) | 13 May 2025 | SB P14 U-01 on site |  | Barricade installation for load testing
Tue (13/05) | 13 May 2025 | P7-2 |  | Pre-boring for ERSS
Tue (13/05) | 13 May 2025 | S3-1 BR4 works in progress |  | RC wall starter bar, CJ starter bar, Transfer beam top rebar, Hydrophilic strip installation
Tue (13/05) | 13 May 2025 | Linkway/exit 1 |  | Clearing of hardcore in progress
Tue (13/05) | 13 May 2025 | P14 SB U-01 |  | Unloading from trailer
Tue (13/05) | 13 May 2025 | P8-2 |  | Hacking to correct level continue
Tue (13/05) | 13 May 2025 | P7-2 |  | Pre-boring for ERSS, 30% completed
Tue (13/05) | 13 May 2025 | P5 crosshead |  | Installation of steel anchor and girder box rebar
Wed (14/05) | 14 May 2025 | TT02 Rig |  | Started drilling for GWS35008
Wed (14/05) | 14 May 2025 | TT01 Rig |  | Waiting to shift to 35010
Wed (14/05) | 14 May 2025 | DR03 |  | HSL shifting from P45 to DR3, today preparation work. Tomorrow start UKP installation at DR03
Wed (14/05) | 14 May 2025 | P46 |  | JGP Grouting works on going
Wed (14/05) | 14 May 2025 | P43 |  | Hacking of BP and excavation on going
Wed (14/05) | 14 May 2025 | P49 |  | No activity
Wed (14/05) | 14 May 2025 | P5 |  | Tendon ducts installation and Formwork assembly
Wed (14/05) | 14 May 2025 | P2 |  | Water pumping ongoing
Wed (14/05) | 14 May 2025 | P50 |  | 2nd stage Excavation on going at north side
Wed (14/05) | 14 May 2025 | P46 |  | JGP works on going
Wed (14/05) | 14 May 2025 | P47 |  | Coring works on going
Wed (14/05) | 14 May 2025 | BR4 |  | Shearlinks installation
Wed (14/05) | 14 May 2025 | ST175 |  | B2 in progress, 34/41.6m
Wed (14/05) | 14 May 2025 | ST72 |  | No preboring works, Housekeeping ongoing
Wed (14/05) | 14 May 2025 | S1-1 |  | Decking panel installation and welding works ongoing
Wed (14/05) | 14 May 2025 | Exit 3 |  | No activity
Wed (14/05) | 14 May 2025 | BR4 |  | Casting started at 1853hrs
Wed (14/05) | 14 May 2025 | CCW | GL-W7 | Current status of S2 struts
Wed (14/05) | 14 May 2025 | Exit 3 |  | No activity
Wed (14/05) | 14 May 2025 | P22 |  | No activity
Wed (14/05) | 14 May 2025 | S1-1 |  | Decking panel installation in progress
Wed (14/05) | 14 May 2025 | BR4 |  | Casting in progress. Noise balloon installed, Vol: 224/1170m3 as at 9pm
Wed (14/05) | 14 May 2025 | ST175 |  | Temporary stopped for BC cutter maintenance. B2 CD 36/41.6m
Wed (14/05) | 14 May 2025 | ST72 |  | Preparing for PB02 preboring works, 2 noise balloons installed and noise barrier panel installed at machine
Wed (14/05) | 14 May 2025 | P19 |  | Excavator breakdown. Mechanic called
Thu (15/05) | 15 May 2025 | P21 |  | Backfilling to pile cap top level in progress
Thu (15/05) | 15 May 2025 | P20 |  | Pile cap rebar and Formwork RTO inspection ongoing. Today to cast
Thu (15/05) | 15 May 2025 | P19 |  | Current FEL excavation status
Thu (15/05) | 15 May 2025 | P18 |  | Dismantling of Formwork in progress. Stressing completed
Thu (15/05) | 15 May 2025 | N5 |  | Scaffold erection for tendon installation and stressing works
Thu (15/05) | 15 May 2025 | P14 |  | Preparation for load tests. Today 3pm to carry out spreader beam load test
Thu (15/05) | 15 May 2025 | P50 |  | Continue excavation
Thu (15/05) | 15 May 2025 | P50 |  | Platform prepare for crane rebar lowering down
Thu (15/05) | 15 May 2025 | P8 |  | Crosshead bottom rebar installation and Formwork assembly
Thu (15/05) | 15 May 2025 | P7-2 |  | Preboring for ERSS in progress
Thu (15/05) | 15 May 2025 | GLE4-E5 |  | KTC excavation to expose utility prior handover to ICE for manual excavation
Thu (15/05) | 15 May 2025 | TT02 Rig |  | Waiting for RTO inspection for its toe level prior installation of GWS35008
Thu (15/05) | 15 May 2025 | P6-2 |  | Premix hacking for trial trench works
Thu (15/05) | 15 May 2025 | P5 |  | Crosshead Formwork assembly, rebar and tendon ducts installation
Thu (15/05) | 15 May 2025 | DR3 |  | Setting out for 1st UKP
Thu (15/05) | 15 May 2025 | P46 |  | JGP grouting in progress
Thu (15/05) | 15 May 2025 | Set 3 |  | Prepare for last SPT
Thu (15/05) | 15 May 2025 | P50 |  | Excavator provided for excavation
Thu (15/05) | 15 May 2025 | P2 |  | Vibro mobilized for ERSS extraction
Thu (15/05) | 15 May 2025 | P2 |  | Backfilling to pile cap top level to start in afternoon
Thu (15/05) | 15 May 2025 | BC1 |  | Maintenance ongoing
Thu (15/05) | 15 May 2025 | BR4 |  | Casting ongoing. Progressive vol: 701/1175m3 as at 1am
Thu (15/05) | 15 May 2025 | ST72 |  | PB02 preboring in progress, 16.3/25.9m
Thu (15/05) | 15 May 2025 | P43 |  | Hacking BP to COL
Thu (15/05) | 15 May 2025 | P46 |  | JGP on going
Thu (15/05) | 15 May 2025 | DR03 |  | UP01 & UP03 preboring completed, going to install I beam
Thu (15/05) | 15 May 2025 | P47 |  | Coring works for tunneling
Thu (15/05) | 15 May 2025 | P48 |  | Installation of main beam for utility support
Thu (15/05) | 15 May 2025 | P49 |  | 2nd stage excavation
Thu (15/05) | 15 May 2025 | P50 |  | 2nd stage excavation and levelling. Meanwhile, setting up crane for caisson installation tomorrow
Thu (15/05) | 15 May 2025 | BR4 |  | Now only 1 pump truck on site. Progressive vol: 1091/1145m3
Thu (15/05) | 15 May 2025 | BR4 completed. Total vol |  | 1154m3
Thu (15/05) | 15 May 2025 | Exit 3 |  | No activity
Thu (15/05) | 15 May 2025 | S1-2 |  | Welding works ongoing
Thu (15/05) | 15 May 2025 | S2-1 |  | Tonight plan for decking beam installation. Preparation works ongoing
Thu (15/05) | 15 May 2025 | ST175 |  | Cutter teeth changing ongoing. B2 CD 40.2/41.6m
Thu (15/05) | 15 May 2025 | ST72 |  | PB02 preboring in progress
Thu (15/05) | 15 May 2025 | CCE4, Linkway |  | No activity
Fri (16/05) | 16 May 2025 | P49 |  | 2nd stage Excavation on going
Fri (16/05) | 16 May 2025 | P48 |  | Installation of main beam for utility support
Fri (16/05) | 16 May 2025 | P46 |  | JGP work on going
Fri (16/05) | 16 May 2025 | P43 |  | Hacking of BP
Fri (16/05) | 16 May 2025 | TT02 Rig |  | GWS35008 installed yesterday, the rig will shift to IW35009
Fri (16/05) | 16 May 2025 | TT01 Rig 1 |  | Continues drilling for IW35010
Fri (16/05) | 16 May 2025 | P21 |  | Column rebar fabrication and railing installation
Fri (16/05) | 16 May 2025 | P21 |  | LSS backfilling till pile cap top level in progress
Fri (16/05) | 16 May 2025 | P20 |  | Pile cap cast yesterday
Fri (16/05) | 16 May 2025 | P19 |  | Current FEL excavation status
Fri (16/05) | 16 May 2025 | P18 |  | Formwork dismantling ongoing
Fri (16/05) | 16 May 2025 | N5 |  | No activity
Fri (16/05) | 16 May 2025 | P15 |  | Scaffold erection in progress
Fri (16/05) | 16 May 2025 | P14 |  | Load testing completed. Now dismantling of counter weights and preparation for segment launching tmr
Fri (16/05) | 16 May 2025 | P8 |  | Formwork assembly, rebar installation and pier hacking to correct level ongoing
Fri (16/05) | 16 May 2025 | P7-2 |  | Preboring for ERSS
Fri (16/05) | 16 May 2025 | P5 |  | Rebar and tendon ducts installation
Fri (16/05) | 16 May 2025 | ST175 |  | B2 completed. Resume B1 excavation from 33.2/41.6m
Fri (16/05) | 16 May 2025 | ST72 |  | PB02 preboring in progress
Fri (16/05) | 16 May 2025 | P3 |  | ERSS extraction in progress
Fri (16/05) | 16 May 2025 | P2 |  | KTC backfilling till pile cap top level
Sat (17/05) | 17 May 2025 | P51 |  | Levelling to start 9.3m + 6m+6m length
Sat (17/05) | 17 May 2025 | P48 |  | Welding of stiffener plates
Sat (17/05) | 17 May 2025 | P46 |  | Soil disposal before resume JGP
Sat (17/05) | 17 May 2025 | P43 |  | Casing installation and preparing to lower down equipement for testing
Sat (17/05) | 17 May 2025 | P20 |  | Stump rebar work
Sat (17/05) | 17 May 2025 | P19 |  | Excavation to FEL to complete today
Sat (17/05) | 17 May 2025 | P14 |  | One segment delivery. Segment installation will be after lunch
Sat (17/05) | 17 May 2025 | P15 |  | Access erection
Sat (17/05) | 17 May 2025 | P8 |  | Pile head hacking to correct level and rebar work
Sat (17/05) | 17 May 2025 | P3 |  | ERSS extraction
Sat (17/05) | 17 May 2025 | P5 |  | Tendom duct installation
Sat (17/05) | 17 May 2025 | S1-2 | GL6-7 | RWS47 - hand augering in progress
Sat (17/05) | 17 May 2025 | S1-1 | GL4-5 | Deck 7 - Deck post plate welding work ongoing
Sat (17/05) | 17 May 2025 | P2 |  | Soil backfilling
Sat (17/05) | 17 May 2025 | P3 |  | Continue ERSS removal
Sat (17/05) | 17 May 2025 | P5 |  | Now woh hup calling for duct inspection
Sat (17/05) | 17 May 2025 | P7-2 |  | Unloading of ERSS materials for installation
Sat (17/05) | 17 May 2025 | P8 |  | GI pipe removal for side bar installation
Sat (17/05) | 17 May 2025 | STN-72 Point 2 Pre-boring in progress, current depth |  | 25.5m / 25.9m
Sat (17/05) | 17 May 2025 | CCE2 | GL E4-E6 | Mini excavator and manual digging in progress. ICE worker: 1, sup 1
Sat (17/05) | 17 May 2025 | P46 |  | GCE give way for HSL UKP work. GCE will work at Changi bounf later
Sat (17/05) | 17 May 2025 | DR3 |  | UKP boring work. Will cast 2nos today
Sat (17/05) | 17 May 2025 | P48 |  | Stiffener plate welding work
Sat (17/05) | 17 May 2025 | P49 |  | Excavation at utility free area and 1st bay at TPE bound
Sat (17/05) | 17 May 2025 | Exit 1 Desander |  | Current stockpile status
Sat (17/05) | 17 May 2025 | P50 |  | Access erection and rebar work started for 1st layer caisson
Mon (19/05) | 19 May 2025 | P5 |  | Section 1 and 2 PT duct completed. Plan to install links tonight
Mon (19/05) | 19 May 2025 | P49 |  | KTC continue excavation. 3/5 bays excavation in progress
Mon (19/05) | 19 May 2025 | P50 |  | Soil trimming for caisson work at TPE bound
Mon (19/05) | 19 May 2025 | P50 |  | Rebar work in progress at Changi bound for 1st layer caisson
Mon (19/05) | 19 May 2025 | P48 |  | Exposing of valve to main point joint area for haunching
Mon (19/05) | 19 May 2025 | P46 |  | JGP grouting work
Mon (19/05) | 19 May 2025 | P8 crosshead |  | Top bar installation at NB side. 40% completed
Mon (19/05) | 19 May 2025 | GL13-11 |  | Manual excavation for utility support installation, KTC excavation ongoing
Mon (19/05) | 19 May 2025 | GL E5 |  | Excavation for utility support works in progress
Mon (19/05) | 19 May 2025 | BR4 |  | No activity
Mon (19/05) | 19 May 2025 | P14-15 |  | Area leveling for crane working platform
Mon (19/05) | 19 May 2025 | P14-13 |  | Area preparation for linkway access diversion
Mon (19/05) | 19 May 2025 | CCE4 |  | Waler welding works. Tmr plan for concrete packing, Excavation continue, Struts preparation ongoing. Tmr plan for struts installation
Mon (19/05) | 19 May 2025 | P6-2 |  | TT for ERSS preboring work
Mon (19/05) | 19 May 2025 | P3 |  | ERSS removal was done. Now loading to send out
Mon (19/05) | 19 May 2025 | P2 |  | Tomorrow plan for LSS backfilling
Mon (19/05) | 19 May 2025 | P5 |  | Duct pipe installation
Mon (19/05) | 19 May 2025 | P7-2 |  | Soldier pile installation
Mon (19/05) | 19 May 2025 | P8 |  | Top bar installation
Mon (19/05) | 19 May 2025 | P14 |  | Casting for footpath diversion
Mon (19/05) | 19 May 2025 | P19 |  | Pile head trimming. Two number done as of now
Mon (19/05) | 19 May 2025 | P21 |  | Stump formwork closing
Mon (19/05) | 19 May 2025 | P22 |  | No activity
Mon (19/05) | 19 May 2025 | Exit 3 W7-8 |  | Exposing couplers
Mon (19/05) | 19 May 2025 | GL12 |  | Exposing utilities, GL13: Utility support installation
Mon (19/05) | 19 May 2025 | BR4 |  | No activity
Mon (19/05) | 19 May 2025 | ST72 |  | Trimming ongoing
Tue (20/05) | 20 May 2025 | P14 NB U-01 |  | Barricade installation for launching tonight
Tue (20/05) | 20 May 2025 | CCE4 |  | Struts installation ongoing
Tue (20/05) | 20 May 2025 | BR4 |  | Formwork propping dismantling ongoing
Tue (20/05) | 20 May 2025 | GL12-11 |  | Excavation ongoing for utility support works
Tue (20/05) | 20 May 2025 | P8 |  | Main bar installation. PT duct installation yet to start
Tue (20/05) | 20 May 2025 | P6-2 |  | Rig shifted for IM installation
Tue (20/05) | 20 May 2025 | P6-2 |  | WH internal cable and water supply diverting for ERSS pre-boring
Tue (20/05) | 20 May 2025 | P50 |  | Rebar works for L1 caisson. Preparing access and scaffold for rectification works on the utility support
Tue (20/05) | 20 May 2025 | P43 |  | No activity
Tue (20/05) | 20 May 2025 | P46 |  | JGP works on going
Tue (20/05) | 20 May 2025 | DR3 |  | UKP installation
Tue (20/05) | 20 May 2025 | P47 |  | Trial Trench work for UKP
Tue (20/05) | 20 May 2025 | P49 |  | 2nd stage excavation at north side. South side excavation completed. Tomorrow will start levelling work
Tue (20/05) | 20 May 2025 | P48 |  | Excavation to expose utilities
Tue (20/05) | 20 May 2025 | GL11-10 |  | Continue excavation for utility support works
Tue (20/05) | 20 May 2025 | BR4 |  | Propping and formwork dismantling ongoing
Tue (20/05) | 20 May 2025 | ST72 |  | Preparing for cutter teeth change. CD 17.2/25.9m
Tue (20/05) | 20 May 2025 | GL E5-4 |  | KTC continue excavation
Tue (20/05) | 20 May 2025 | CCE4 |  | Concrete packing at waler side ongoing
Wed (21/05) | 21 May 2025 | BR4 |  | Continue formwork removal
Wed (21/05) | 21 May 2025 | CCE4 |  | Current status of struts installation, 4/14nos
Wed (21/05) | 21 May 2025 | GL11-10 |  | Continue excavation for utility support
Wed (21/05) | 21 May 2025 | P2 |  | LSS backfilling completed for 5th and 6th layer to pile cap level
Wed (21/05) | 21 May 2025 | GL11-10 |  | Continue excavation for utility support works
Wed (21/05) | 21 May 2025 | P5 |  | Section 1 and 2 final inspection completed. Preparing to close formwork
Wed (21/05) | 21 May 2025 | P8-2 |  | Steel anchor installation by ultracon. Tomorrow to start PT duct installation
Wed (21/05) | 21 May 2025 | 600T crane |  | Setting up for NB P14 U-01 installation tonight
Wed (21/05) | 21 May 2025 | P46 |  | Excavation to expose New water pipe cap off point for tomorrow night's diversion
Wed (21/05) | 21 May 2025 | P48 |  | Excavation works to utility main beam level
Wed (21/05) | 21 May 2025 | P49 |  | No activity, short arm excavator breakdown. Mechanic called
Wed (21/05) | 21 May 2025 | P50 |  | 1st layer caison rebar installation and formwork closing
Wed (21/05) | 21 May 2025 | P50 caison 1st layer status |  | Green: casting completed, Blue: rebar and formwork closing closing. To cast tomorrow, Red: Rebar installation to start tomorrow
Thu (22/05) | 22 May 2025 | GL11-9 |  | KTC excavation & ICE manual soil clearing for utility support ongoing
Thu (22/05) | 22 May 2025 | BR4 |  | CJ hacking ongoing. Today plan for surface inspection
Thu (22/05) | 22 May 2025 | ST72 |  | Cutter teeth changing ongoing. CD 25.4/25.9m
Thu (22/05) | 22 May 2025 | CCE4 |  | 7/15nos struts installed, Dwall hacking ongoing
Thu (22/05) | 22 May 2025 | GL10 |  | Continue excavation for utility support & preparing for slope casting
Thu (22/05) | 22 May 2025 | BR4 |  | CJ hacking ongoing
Thu (22/05) | 22 May 2025 | ST72 |  | B1 completed. Now ongoing B2, 21/25.9m
Thu (22/05) | 22 May 2025 | CCE4 |  | Welding works and excavation ongoing, Linkway: Excavation ongoing
Thu (22/05) | 22 May 2025 | S1-1 |  | Excavation ongoing
Thu (22/05) | 22 May 2025 | Exit 3 |  | 4nos decking beams installed. Welding works in progress
Thu (22/05) | 22 May 2025 | Exit 3 | GL W-7 to W-8 | Lean concrete casting
Fri (23/05) | 23 May 2025 | P46 |  | JGP work on going
Fri (23/05) | 23 May 2025 | P48 |  | Excavation to expose utitlies
Fri (23/05) | 23 May 2025 | P49 |  | Excavation on going
Fri (23/05) | 23 May 2025 | P50 |  | Rebar installation for L1 caisson
Fri (23/05) | 23 May 2025 | GL E6-E9 |  | Continue excavation for utility support works
Fri (23/05) | 23 May 2025 | GL E5 |  | Pending beam delivery. Plan to arrive today. Hirose crane has shifted here
Fri (23/05) | 23 May 2025 | GL E1 |  | Excavation completed for waler beam installation
Fri (23/05) | 23 May 2025 | BR33 |  | Excavation to coupler level, Linkway: Dongah hacking guidewall
Fri (23/05) | 23 May 2025 | P43 |  | Removal of S2 strut
Fri (23/05) | 23 May 2025 | P46 |  | JGP works ongoing
Fri (23/05) | 23 May 2025 | P47 |  | HSL done shifting to P47 from DR3 and ground preparation. Tomorrow will start UKP at P47
Fri (23/05) | 23 May 2025 | P49 |  | Excavation on going
Fri (23/05) | 23 May 2025 | P50 |  | Closing formwork at the centre part and rebar installation at the end of south side
Fri (23/05) | 23 May 2025 | P48 |  | Excavation to expose utilities on going
Sat (24/05) | 24 May 2025 | P46 |  | JGP works ongoing
Sat (24/05) | 24 May 2025 | P47 |  | UKP installation start at P47
Sat (24/05) | 24 May 2025 | PMH24 |  | Preparation work
Sat (24/05) | 24 May 2025 | P48 |  | Excavation to expose utilities
Sat (24/05) | 24 May 2025 | P49 |  | Machine breakdown. Mechanics is on the way coming
Sat (24/05) | 24 May 2025 | P50 |  | Formwork installation, going to cast today
Sat (24/05) | 24 May 2025 | P20 |  | No activity
Sat (24/05) | 24 May 2025 | P19 |  | Pile cap rebar installation
Sat (24/05) | 24 May 2025 | P14 |  | No activity
Sat (24/05) | 24 May 2025 | P11-P12 |  | Rod dismantling for instrument RX224001
Sat (24/05) | 24 May 2025 | P08 |  | No activity
Sat (24/05) | 24 May 2025 | P6-2 |  | Pre-boring for ERSS
Sat (24/05) | 24 May 2025 | P2 |  | S1 strut removal
Sat (24/05) | 24 May 2025 | P47 |  | UKP installation
Sat (24/05) | 24 May 2025 | PMH23 |  | ERSS installation
Sat (24/05) | 24 May 2025 | P48 |  | Excavation to expose utilities
Sat (24/05) | 24 May 2025 | P49 |  | Excavator resume excavation works
Sat (24/05) | 24 May 2025 | P50 |  | Casting final section of L1 caisson
Sat (24/05) | 24 May 2025 | P5 |  | Crosshead rebar installation and formwork closing
Sat (24/05) | 24 May 2025 | P2 |  | Removal of S1 strut
Sat (24/05) | 24 May 2025 | P16 |  | Trial Trench work
Sat (24/05) | 24 May 2025 | P21 |  | Installation pier rebar cage
Sat (24/05) | 24 May 2025 | P20 |  | LSS backfilling
Sat (24/05) | 24 May 2025 | P19 |  | Pile cap rebar works
Sat (24/05) | 24 May 2025 | BR33 works in progress |  | Excavation to coupler level (target tomorrow lay lean concrete), Exposing couplers
Sat (24/05) | 24 May 2025 | Exit 1 Desander |  | Current stockpile status
Mon (26/05) | 26 May 2025 | P50 |  | Strut installation and formwork removal
Mon (26/05) | 26 May 2025 | P49 |  | Trimming and levelling at TPE bound for caisson work
Mon (26/05) | 26 May 2025 | P48 |  | Current status of excavation
Mon (26/05) | 26 May 2025 | P47 |  | Today will cast two UKP
Mon (26/05) | 26 May 2025 | PMH23 |  | Continue excavation for precast installation
Mon (26/05) | 26 May 2025 | P14 |  | Preparation work for segment adjusting
Mon (26/05) | 26 May 2025 | N5 |  | Resources will come in tonight for launching of 1 upchainage segment. The Downchainage will be launching the following night
Mon (26/05) | 26 May 2025 | P8 |  | Resources will continue crosshead works tomorrow
Mon (26/05) | 26 May 2025 | P7-S |  | LE handed over the site after completing ERSS works. KTC will commence excavation tomorrow
Mon (26/05) | 26 May 2025 | EB P12 |  | 3rd segment 5L feeding to ring build area
Tue (27/05) | 27 May 2025 | P2 |  | Platform making for stump casting. Tonight to cast
Tue (27/05) | 27 May 2025 | P5 |  | Now tidy up and preparation for final inspection
Tue (27/05) | 27 May 2025 | P3 |  | Prepare platform for P2 column rebar fabrication
Tue (27/05) | 27 May 2025 | P7-2 |  | Now no activity. Waiting for KTC to start excavation
Tue (27/05) | 27 May 2025 | P7-1 |  | Today to complete preboring
Tue (27/05) | 27 May 2025 | P8 |  | Today no activity. All workers at P5 for casting
Tue (27/05) | 27 May 2025 | CCE 4 & Linkway | BR33 | Waler bracket welding work & coupler exposure ongoing
Tue (27/05) | 27 May 2025 | P40 TB |  | Preparation work in progress
Tue (27/05) | 27 May 2025 | P20 |  | Strut and waler removal
Tue (27/05) | 27 May 2025 | P21 |  | Column formwork closing work
Tue (27/05) | 27 May 2025 | P19 |  | Hard barricade installation
Tue (27/05) | 27 May 2025 | P50 |  | Left 2 horizontal and 4 diagonal strut to complete
Tue (27/05) | 27 May 2025 | P49 |  | Rebar work for caisson at Changi Bound and trimming by KTC at TPE bound
Tue (27/05) | 27 May 2025 | PMH23 |  | Continue removal of JGP grout for manhole installation
Tue (27/05) | 27 May 2025 | P47 |  | Two UKPs will cast today
Tue (27/05) | 27 May 2025 | DR3 |  | Now JGP rig breakdown. Waiting for mechanic
Tue (27/05) | 27 May 2025 | P45 |  | TT by woh hup to confirm services location
Tue (27/05) | 27 May 2025 | P43 |  | KTC clearing soil and hardcore. Tomorrow can start rebar work
Wed (28/05) | 28 May 2025 | N5 |  | Tendom wire installation
Wed (28/05) | 28 May 2025 | P20 |  | Waler removal
Wed (28/05) | 28 May 2025 | P19 |  | Stump rebar work started
Wed (28/05) | 28 May 2025 | P21 |  | Column formwork closing
Wed (28/05) | 28 May 2025 | CCE4 |  | Continues strut installation & excavation at the other end
Wed (28/05) | 28 May 2025 | P45 |  | Preparing for pipe sleeves installation for JGP testing
Wed (28/05) | 28 May 2025 | P45 |  | Ley Choon doing TT for water pipe laying
Wed (28/05) | 28 May 2025 | P46 |  | JGP rig repairing
Wed (28/05) | 28 May 2025 | P47 |  | Today will cast 2nos of UKP
Wed (28/05) | 28 May 2025 | PMH23 |  | Excavation and ERSS installation
Wed (28/05) | 28 May 2025 | P48 |  | Excavation and provide utility support
Wed (28/05) | 28 May 2025 | P49 |  | Caisson rebar work
Wed (28/05) | 28 May 2025 | P45 |  | TT for JGP testing work
Wed (28/05) | 28 May 2025 | P46 |  | Resume JGP grouting work
Wed (28/05) | 28 May 2025 | DR3 |  | Preparing for UKP casting
Wed (28/05) | 28 May 2025 | PMH23 |  | ERSS Installation for manhole work
Wed (28/05) | 28 May 2025 | P48 |  | Current status of excavation
Wed (28/05) | 28 May 2025 | P49 |  | Caisson rebar inspection by RTO
Wed (28/05) | 28 May 2025 | P50 |  | 1st layer struts installation done. Now continue welding
Wed (28/05) | 28 May 2025 | P43 |  | Current status of rebar work for pier footing
Wed (28/05) | 28 May 2025 | P49 |  | L1 rebar caisson work
Wed (28/05) | 28 May 2025 | DR3 |  | Trial Trench work ongoing
Wed (28/05) | 28 May 2025 | P2 column |  | Manpower was not arranged for today. Will start work tomorrow
Wed (28/05) | 28 May 2025 | P2 |  | Preparing for final inspection
Wed (28/05) | 28 May 2025 | P5 |  | Clearing of cement grout
Wed (28/05) | 28 May 2025 | P7-2 |  | KTC started excavation
Wed (28/05) | 28 May 2025 | P6-2 |  | LE clearing materials for ERSS installation
Wed (28/05) | 28 May 2025 | P8 |  | Bring up duct for installation
Thu (29/05) | 29 May 2025 | P14 |  | 1st pair adjustment
Thu (29/05) | 29 May 2025 | P8 |  | PT duct installation
Thu (29/05) | 29 May 2025 | GL10 |  | Manual clearing of soil below utilities
Thu (29/05) | 29 May 2025 | BR10 |  | Clearing abandoned services
Thu (29/05) | 29 May 2025 | ST175 |  | Preparing for G15 concrete backfilling
Thu (29/05) | 29 May 2025 | ST71 |  | BC cutter mud pump changing before resume excavation
Thu (29/05) | 29 May 2025 | CCE4 works in progress |  | P40 coupler exposing, Welding work for 2 nos. struts installed, Excavation near RS for the remaining 3 nos. struts
Thu (29/05) | 29 May 2025 | Exit 3 |  | Lean con completed for remaining areas near skin wall edge
Thu (29/05) | 29 May 2025 | BR33 / Exit 1 link way works in progress |  | B1, B2 rebar installation, RGT pipe installation
Thu (29/05) | 29 May 2025 | S2 |  | Material shifting to start TT for ERSS
Thu (29/05) | 29 May 2025 | BR10 |  | Abandoned cables removal & guidewall removal
Thu (29/05) | 29 May 2025 | Between | GL15-16 | Manual clearing of soil below services
Thu (29/05) | 29 May 2025 | GL13-11 |  | Waiting for Hirose to continue works
Thu (29/05) | 29 May 2025 | ST175 |  | G15 concrete backfilling ongoing
Thu (29/05) | 29 May 2025 | ST71 |  | Mud pump changing ongoing. Target to resume excavation tonight
Thu (29/05) | 29 May 2025 | P40 |  | Continue exposing couplers
Thu (29/05) | 29 May 2025 | BR33 |  | Continue rebar works, Skin wall starter bar pull-out test ongoing, RGT installation ongoing
Thu (29/05) | 29 May 2025 | P50 |  | 1st layer strut welding
Thu (29/05) | 29 May 2025 | P49 |  | Cast in bolt welding works at 1st layer caison
Thu (29/05) | 29 May 2025 | P49 |  | Tonight to cast 1st part of 1st layer caison
Thu (29/05) | 29 May 2025 | PMH23 |  | Excavation and strutting works
Thu (29/05) | 29 May 2025 | P47 |  | UKP 10&11 boring completed. To cast today
Thu (29/05) | 29 May 2025 | P22 |  | Transfer beam formwork closing ongoing
Thu (29/05) | 29 May 2025 | CCW W7 |  | S2 struts bracing welding works ongoing
Thu (29/05) | 29 May 2025 | P23 |  | Rebar works in progress
Thu (29/05) | 29 May 2025 | S1-1 |  | Current excavation status
Thu (29/05) | 29 May 2025 | Exit 3 |  | Skinwall formwork closing. Plan for casting today
Thu (29/05) | 29 May 2025 | P21 |  | Preparation for access installation for casting tomorrow
Thu (29/05) | 29 May 2025 | N5 |  | 2nd pair segment stressing completed. Strand cutting in progress. Tonight to install N5 U-03 during non traffic hours
Thu (29/05) | 29 May 2025 | N4 |  | Ground preparation for falsework erection
Fri (30/05) | 30 May 2025 | BR10 |  | KTC disposal ongoing, Dongah guidewall removal for DW62-64
Fri (30/05) | 30 May 2025 | GL11 |  | WH erecting intermediate access, Hirose will continue utility support works tmr. Manpower now at decking area
Fri (30/05) | 30 May 2025 | ST71 |  | B1 in progress, 13.8/24.13m
Fri (30/05) | 30 May 2025 | P8 |  | U shape anchor installation
Fri (30/05) | 30 May 2025 | S2 |  | Preparation for TT
Fri (30/05) | 30 May 2025 | Preparation work for Exit 3 Deck 8 |  | Hanging bars cutting and excavation in progress
Fri (30/05) | 30 May 2025 | P43 |  | Pile cap rebar installation
Fri (30/05) | 30 May 2025 | PMH23 |  | Quary dust backfilling and compaction. Tomorrow to install MH
Fri (30/05) | 30 May 2025 | P19 stump |  | Casting platform erection
Fri (30/05) | 30 May 2025 | P8 |  | PT duct and cast in anchor installation. Plan to install links at section 1 tomorrow night
Fri (30/05) | 30 May 2025 | P22 |  | TB final inspection. Pump truck arrived on site
Sat (31/05) | 31 May 2025 | Exit 3 |  | Surface levelling ongoing
Sat (31/05) | 31 May 2025 | P23 |  | Lean concrete casting ongoing for platform, Rebar welding works
Sat (31/05) | 31 May 2025 | CCW/BR16A |  | No other activity
Sat (31/05) | 31 May 2025 | Exit 3 utility area |  | No activity
Sat (31/05) | 31 May 2025 | Blk 2 |  | Hirose preparing for utility support beam installation
Sat (31/05) | 31 May 2025 | BR10 |  | No activity
Sat (31/05) | 31 May 2025 | ST175 |  | B2 in progress, 14/41.6m
Sat (31/05) | 31 May 2025 | ST71 |  | Preboring in progress, 16.7/24.13m
Sat (31/05) | 31 May 2025 | CCE4 |  | No activity. 9/12nos struts installed. Balance 3 more struts to be installed, P40, BR33: No activity
Sat (31/05) | 31 May 2025 | GL E4-E6 |  | No activity
Sun (01/06) | 01 Jun 2025 | Blk 2 |  | Utility support beams installed from GL11-9.5. Welding works ongoing
Sun (01/06) | 01 Jun 2025 | ST175 |  | B2 in progress, 31/41.6m
Sun (01/06) | 01 Jun 2025 | ST71 |  | PB02 preboring in progress, 19.7/24.13m
Sun (01/06) | 01 Jun 2025 | P23 |  | No activity
Mon (02/06) | 02 Jun 2025 | P21 |  | Column tie back removal in progress
Mon (02/06) | 02 Jun 2025 | P20 |  | Column Tie rod installation
Mon (02/06) | 02 Jun 2025 | P19 |  | Concrete plug casting
Mon (02/06) | 02 Jun 2025 | Bet. P14-P15 |  | IM installation ongoing
Mon (02/06) | 02 Jun 2025 | S2 |  | Trial trench for ERSS
Mon (02/06) | 02 Jun 2025 | P8 |  | Rebar and shear links installation
Mon (02/06) | 02 Jun 2025 | P7-2 |  | Demob of KTC mini excavator and mobilize of HSL mini excavator for pile head hacking works
Mon (02/06) | 02 Jun 2025 | P6-2 |  | Installation of ERSS in progress
Mon (02/06) | 02 Jun 2025 | P2 |  | Column rebar fabrication ongoing
Mon (02/06) | 02 Jun 2025 | P5 |  | Preparation for Formwork dismantling
Mon (02/06) | 02 Jun 2025 | PMH23 |  | Lowering precast for manhole work
Mon (02/06) | 02 Jun 2025 | DR3 |  | Continue TT for pipe sleeves installation
Mon (02/06) | 02 Jun 2025 | P47 |  | Today will cast two ukp
Mon (02/06) | 02 Jun 2025 | P49 |  | Formwork closing and balance rebar work at TPE bound
Mon (02/06) | 02 Jun 2025 | P50 |  | Today no activity
Mon (02/06) | 02 Jun 2025 | P14 |  | Segment adjustment works
Mon (02/06) | 02 Jun 2025 | P21 |  | Column formwork dismantling
Mon (02/06) | 02 Jun 2025 | Exit 3 |  | Continue excavation for utility support
Mon (02/06) | 02 Jun 2025 | BR13 |  | Started debonding sheet laying earlier today and installation of RGT
Mon (02/06) | 02 Jun 2025 | S1-1 |  | Clearing hardcores
Mon (02/06) | 02 Jun 2025 | P23 |  | Rebar works in progress
Mon (02/06) | 02 Jun 2025 | GL11 |  | Continue utility support works and erection of access
Mon (02/06) | 02 Jun 2025 | BR10 |  | Continue excavation
Mon (02/06) | 02 Jun 2025 | ST175 |  | Rebar cage installation in progress, 4/8nos
Mon (02/06) | 02 Jun 2025 | ST71 |  | Preparation works ongoing for BC cutter. Tonight continue excavation
Mon (02/06) | 02 Jun 2025 | GL E4 |  | Continue excavation
Mon (02/06) | 02 Jun 2025 | P40 |  | Hacking of bulging concrete was done
Mon (02/06) | 02 Jun 2025 | CCE4 |  | Balance strut installation in progress. Tmr to continue installation
Tue (03/06) | 03 Jun 2025 | BR10 |  | Backfill and levelling for temporary access diversion to facilitate cut slope at BR9 area. Thereafter continue excavation and reinstate access
Tue (03/06) | 03 Jun 2025 | GL11 |  | Utility support welding works ongoing
Tue (03/06) | 03 Jun 2025 | ST175 |  | Casting in progress, 281/317m3
Tue (03/06) | 03 Jun 2025 | ST71 |  | B1 in progress
Tue (03/06) | 03 Jun 2025 | P21 |  | Column Formwork dismantled
Tue (03/06) | 03 Jun 2025 | P20 |  | Column Formwork installation ongoing. 1/4 nos. completed
Tue (03/06) | 03 Jun 2025 | P19 |  | Patching works in progress
Tue (03/06) | 03 Jun 2025 | Bet. P14-P15 |  | Tunnel IM installation ongoing
Tue (03/06) | 03 Jun 2025 | P14 |  | Segment adjustment in progress
Tue (03/06) | 03 Jun 2025 | N4 |  | Ground preparation for segment falsework installation ongoing
Tue (03/06) | 03 Jun 2025 | P50 |  | Mini excavator mobilized for excavation work
Tue (03/06) | 03 Jun 2025 | P49 |  | Formwork closing to complete today. Last span of caisson will cast tomorrow
Tue (03/06) | 03 Jun 2025 | P49 |  | KTC continue excavation and LE prepare for support installation
Tue (03/06) | 03 Jun 2025 | GL E3-E9 |  | Excavation ongoing
Tue (03/06) | 03 Jun 2025 | P40 |  | Debonding sheet laid. Dwall surface hacking ongoing
Tue (03/06) | 03 Jun 2025 | CCE4 |  | Balance struts installation in progress. Waler concrete packing done
Tue (03/06) | 03 Jun 2025 | BR13 |  | Coupler checking ongoing. Today plan to start rebar works
Tue (03/06) | 03 Jun 2025 | P14 |  | Lifting frame assembly in progress
Tue (03/06) | 03 Jun 2025 | S2 |  | Trial trench completed. Hacking and removal of abandoned drain in progress
Tue (03/06) | 03 Jun 2025 | P8 |  | Rebar and tendon ducts installation in progress. Tonight to start Formwork closing
Tue (03/06) | 03 Jun 2025 | P7-2 |  | No activity. Mini excavator for pile head hacking to mobilize in tmr
Tue (03/06) | 03 Jun 2025 | P6-2 |  | ERSS installation completed
Tue (03/06) | 03 Jun 2025 | P5 |  | Prepration for Formwork dismantling
Tue (03/06) | 03 Jun 2025 | P2 |  | S1 layer struts and Waler dismantling
Tue (03/06) | 03 Jun 2025 | P2 |  | Rebar fabrication for column
Tue (03/06) | 03 Jun 2025 | P23 transfer beam |  | Rebar works ongoing, Hacking ongoing for stitching works
Tue (03/06) | 03 Jun 2025 | BR16A |  | Erecting platform scaffold for KP cross-bracing installation
Tue (03/06) | 03 Jun 2025 | MH2-10 |  | Drain reinstatement ongoing. Now waiting to cast base
Tue (03/06) | 03 Jun 2025 | DR3 |  | TT in progress by GCE
Tue (03/06) | 03 Jun 2025 | P46 |  | Preboring for UKP. Tomorrow target to cast 3nos
Tue (03/06) | 03 Jun 2025 | PMH23 |  | Rebar work in progress for stitching work
Tue (03/06) | 03 Jun 2025 | P43 |  | Formwork support installation. Tomorrow to cast
Tue (03/06) | 03 Jun 2025 | Exit 1 Desander |  | Current stockpile status
Tue (03/06) | 03 Jun 2025 | CCE4 |  | Balance struts installation in progress
Wed (04/06) | 04 Jun 2025 | GL7 |  | UKP9 stump cast yesterday
Wed (04/06) | 04 Jun 2025 | GL8 |  | UKP11 stump cast yesterday
Wed (04/06) | 04 Jun 2025 | GL10 |  | Utility support works ongoing till here
Wed (04/06) | 04 Jun 2025 | BR10 |  | Continue preparing for temporary access diversion & preparing for BRC installation for slope protection
Wed (04/06) | 04 Jun 2025 | ST71 |  | B1 completed. Now ongoing B2 excavation
Wed (04/06) | 04 Jun 2025 | P49 |  | Formwork closing done for last span of caisson. Today to cast
Wed (04/06) | 04 Jun 2025 | P50 |  | KTC started excavation for next layer
Wed (04/06) | 04 Jun 2025 | P21 |  | Preparation for ERSS extraction
Wed (04/06) | 04 Jun 2025 | P20 |  | Column Formwork closing in progress. 2/4 nos. completed
Wed (04/06) | 04 Jun 2025 | P19 |  | Removal of S1 layer Waler and struts
Wed (04/06) | 04 Jun 2025 | Bet. P14-P15 |  | Tunnel IM drilling and installation
Wed (04/06) | 04 Jun 2025 | N4 |  | Ground preparation works for falsework erection
Wed (04/06) | 04 Jun 2025 | N5 |  | Tendon strands installation for stressing works ongoing
Wed (04/06) | 04 Jun 2025 | DR3 |  | GCE continue pipe sleeves installation
Wed (04/06) | 04 Jun 2025 | P46 |  | Today plan to cast 2UKPs
Wed (04/06) | 04 Jun 2025 | PMH23 |  | Rebar work done. Preparing for inspection
Wed (04/06) | 04 Jun 2025 | P48 |  | LE resume main beam installation
Wed (04/06) | 04 Jun 2025 | P14 |  | Segment adjustment ongoing
Wed (04/06) | 04 Jun 2025 | S2 |  | Hacking and removal of abandoned drain
Wed (04/06) | 04 Jun 2025 | P8 |  | Shear links installation ongoing
Wed (04/06) | 04 Jun 2025 | P7-2 |  | No activity. Mini excavator to mob in and lower in the afternoon
Wed (04/06) | 04 Jun 2025 | P5 |  | Preparation for Formwork dismantling
Wed (04/06) | 04 Jun 2025 | P2 |  | Column rebar cage fabrication
Wed (04/06) | 04 Jun 2025 | P2 |  | KTC Backfilling works ongoing
Wed (04/06) | 04 Jun 2025 | CCE4 |  | Balance 3nos struts have been installed — 12/12nos completed
Wed (04/06) | 04 Jun 2025 | GL E5-E6 |  | Utility support welding works
Wed (04/06) | 04 Jun 2025 | GL E7-E8 |  | Excavation ongoing
Wed (04/06) | 04 Jun 2025 | ST71 | BC01 | B1 completed. B2 in progress, 14/24.13m
Wed (04/06) | 04 Jun 2025 | P21 |  | ERSS extraction ongoing
Wed (04/06) | 04 Jun 2025 | P20 |  | Column Formwork closing. 3/4 nos. completed
Wed (04/06) | 04 Jun 2025 | P19 |  | Struts and walers removal for s1 layer
Wed (04/06) | 04 Jun 2025 | Bet. P14-P15 |  | Tunnel IM installation ongoing
Wed (04/06) | 04 Jun 2025 | N5 |  | Erection of jacking system platform
Wed (04/06) | 04 Jun 2025 | P14 |  | Continue segment adjustment
Wed (04/06) | 04 Jun 2025 | S2 |  | Backfilling for ERSS Preboring ongoing
Wed (04/06) | 04 Jun 2025 | P8 |  | Shear links installation
Wed (04/06) | 04 Jun 2025 | P7-2 |  | Pile head hacking in progress
Wed (04/06) | 04 Jun 2025 | P5 |  | Formwork dismantling
Wed (04/06) | 04 Jun 2025 | P2 |  | Column rebar fabrication
Wed (04/06) | 04 Jun 2025 | P2 |  | KTC continue backfilling works
Wed (04/06) | 04 Jun 2025 | BR14 |  | Exposing couplers
Wed (04/06) | 04 Jun 2025 | BR13 |  | Coupler rebars installation ongoing (CGW), Drilling ongoing for missing couplers installation (Dongah)
Wed (04/06) | 04 Jun 2025 | P23 |  | Top bar installation. Thereafter to install shearlinks
Wed (04/06) | 04 Jun 2025 | BR10 |  | Continue backfilling for temporary access diversion
Wed (04/06) | 04 Jun 2025 | GL E8 |  | Continue excavation
Wed (04/06) | 04 Jun 2025 | P40 |  | Transfer beam rebar works in progress
Wed (04/06) | 04 Jun 2025 | CCE4 |  | No other activity
Wed (04/06) | 04 Jun 2025 | P43 |  | Pilecap casting in progress
Wed (04/06) | 04 Jun 2025 | Deck panel 8 |  | VIG installation
Wed (04/06) | 04 Jun 2025 | P43 |  | Pile cap casting
Wed (04/06) | 04 Jun 2025 | Dr3 |  | Trial Trench for JGP and pipe sleeve installation
Wed (04/06) | 04 Jun 2025 | P49 |  | No activity. L1 caissson 3rd section casting completed
Wed (04/06) | 04 Jun 2025 | P50 |  | Excavation to L2 caisson level
Wed (04/06) | 04 Jun 2025 | P48 |  | Setting up working platform
Thu (05/06) | 05 Jun 2025 | P5 |  | Formwork dismantling in progress
Thu (05/06) | 05 Jun 2025 | P21 |  | ERSS extraction ongoing
Thu (05/06) | 05 Jun 2025 | P7-2 |  | Pile head hacking in progress. 1/4 nos. completed
Thu (05/06) | 05 Jun 2025 | S2 |  | Machinery Parking platform making ongoing
Thu (05/06) | 05 Jun 2025 | P8 |  | Crosshead Formwork closing in progress
Thu (05/06) | 05 Jun 2025 | BR10 |  | Temporary access diversion ongoin
Thu (05/06) | 05 Jun 2025 | ST71 |  | B2 in progress, 16.8/24.13m
Thu (05/06) | 05 Jun 2025 | P14 |  | Segment adjustment ongoing
Thu (05/06) | 05 Jun 2025 | Bet. P14 & P15 |  | Tunnel IM installation
Thu (05/06) | 05 Jun 2025 | N4 |  | Platform making for segment falsework erection
Thu (05/06) | 05 Jun 2025 | N5 |  | Erection of jacking system platform
Thu (05/06) | 05 Jun 2025 | P19 |  | Struts and Waler dismantling
Thu (05/06) | 05 Jun 2025 | P20 |  | Column Propping installation
Thu (05/06) | 05 Jun 2025 | ST71 | BC01 | B2 CD 17.6/24.13m. Now teeth changing in progress
Thu (05/06) | 05 Jun 2025 | P21 |  | Continue ERSS extraction. Target to complete tmr
Thu (05/06) | 05 Jun 2025 | P20 |  | Scaffold erection in progress. Target to cast column tmr
Thu (05/06) | 05 Jun 2025 | Bet. P14-P15 |  | Tunnel IM installation works. Target to complete next week
Thu (05/06) | 05 Jun 2025 | N4 |  | Platform making for segment falsework erection current status
Thu (05/06) | 05 Jun 2025 | N5 |  | Erection of jacking system platform
Thu (05/06) | 05 Jun 2025 | P14 |  | Segment adjustment
Thu (05/06) | 05 Jun 2025 | P8 |  | Crosshead Formwork closing completed. To cast tmr
Thu (05/06) | 05 Jun 2025 | S2 |  | Preboring for ERSS in progress. 2 nos. completed
Thu (05/06) | 05 Jun 2025 | P7-2 |  | Pile head hacking in progress. 1/4 nos. completed
Thu (05/06) | 05 Jun 2025 | P5 |  | Continue Formwork dismantling
Thu (05/06) | 05 Jun 2025 | P2 |  | Column rebar cage fabrication completed
Thu (05/06) | 05 Jun 2025 | P2 |  | Backfilling ongoing
Thu (05/06) | 05 Jun 2025 | BR13 |  | Bottom coupler rebar pull-out test ongoin
Thu (05/06) | 05 Jun 2025 | P23 |  | Drilling ongoing for stitching works, Top bar rebar works and inspection
Thu (05/06) | 05 Jun 2025 | Deck 8 |  | VIG welding works ongoing
Thu (05/06) | 05 Jun 2025 | BR10 |  | Current status
Thu (05/06) | 05 Jun 2025 | GL E8 |  | Manual excavation below utilitie
Thu (05/06) | 05 Jun 2025 | GL E3-E9 |  | Continue excavation
Thu (05/06) | 05 Jun 2025 | P40 |  | Continue bar chair & top bar installation
Thu (05/06) | 05 Jun 2025 | CCE4 |  | Preparing for preloading works
Thu (05/06) | 05 Jun 2025 | ST71 |  | B2 in progress
Fri (06/06) | 06 Jun 2025 | Gate 5 |  | Starter bar rebar planting. Today plan to start ramp access construction for access diversion this weekend
Fri (06/06) | 06 Jun 2025 | Exit 2 |  | Backfilling ongoing for access diversion
Fri (06/06) | 06 Jun 2025 | BR10 |  | Current status of diverted access
Fri (06/06) | 06 Jun 2025 | GL9 |  | Utility support welding works ongoing
Fri (06/06) | 06 Jun 2025 | ST71 |  | B2 temporarily stopped for cutter teeth change. Current depth 18.5/24.13m
Fri (06/06) | 06 Jun 2025 | Drain at blk 4 |  | Observed no silty discharge
Fri (06/06) | 06 Jun 2025 | BR13 rebar works |  | CGW 3 workers
Fri (06/06) | 06 Jun 2025 | P43 |  | Pile cap curing
Fri (06/06) | 06 Jun 2025 | P46 |  | UP-11 boring works in progress. Today to cast UP-7 and UP-11
Fri (06/06) | 06 Jun 2025 | Zone 4, DR3 |  | JGP grouting works for Point B37 in progress
Fri (06/06) | 06 Jun 2025 | P48 |  | Excavation, utility support, installation of end plate and welding in progress
Fri (06/06) | 06 Jun 2025 | PMH-23 |  | Formwork closing for wall casting
Fri (06/06) | 06 Jun 2025 | Zone 4 |  | Wee Guan excavation for duct laying works
Fri (06/06) | 06 Jun 2025 | P50 |  | KTC Excavation going
Fri (06/06) | 06 Jun 2025 | P49 |  | ERSS installation and strut to cast-in plate welding in progress
Fri (06/06) | 06 Jun 2025 | P2 |  | Column rebar cage installed. Adjustment ongoing
Fri (06/06) | 06 Jun 2025 | P5 |  | Formwork dismantling in progress
Fri (06/06) | 06 Jun 2025 | Gate 5 |  | Current existing vehicle access closed for ramp construction, Raising of 2nos water valves to match the access level
Fri (06/06) | 06 Jun 2025 | Exit 2 |  | Continue levelling works for access diversion
Fri (06/06) | 06 Jun 2025 | P7-2 |  | Pile head hacking in progress. 2/4 nos. completed
Fri (06/06) | 06 Jun 2025 | P8 |  | Concrete pump setting up for crosshead casting today
Fri (06/06) | 06 Jun 2025 | S2 |  | Preboring for ERSS installation
Fri (06/06) | 06 Jun 2025 | P14 |  | Ongoing segment adjustment
Fri (06/06) | 06 Jun 2025 | Bet. P14-P15 |  | Tunnel IM installation
Fri (06/06) | 06 Jun 2025 | N4 |  | Levelling works in progress
Fri (06/06) | 06 Jun 2025 | N5 |  | Erection of jacking system platform
Fri (06/06) | 06 Jun 2025 | P20 |  | Column casting in progress
Fri (06/06) | 06 Jun 2025 | P21 |  | ERSS extraction completed
Sat (07/06) | 07 Jun 2025 | Exit 1 Desander |  | Current stockpile status
Mon (09/06) | 09 Jun 2025 | P21 |  | Ground preparation works ongoing for Falseworks installation
Mon (09/06) | 09 Jun 2025 | P21 |  | Falsework assembly works
Mon (09/06) | 09 Jun 2025 | P20 |  | Trial trench ongoing for Tunnel IM instrumentation
Mon (09/06) | 09 Jun 2025 | P19 |  | Setting up for column rebar cage fabrication
Mon (09/06) | 09 Jun 2025 | P19 |  | KTC backfilling till column stump level
Mon (09/06) | 09 Jun 2025 | P50 |  | 2nd layer caisson rebar work
Mon (09/06) | 09 Jun 2025 | ST71 | BC1 | Cleaning in progres
Mon (09/06) | 09 Jun 2025 | GLE2-E5 |  | Current excavation status
Mon (09/06) | 09 Jun 2025 | P45 |  | JGP testing work
Mon (09/06) | 09 Jun 2025 | P46 |  | Today plan to cast two UKP
Mon (09/06) | 09 Jun 2025 | DR3 |  | Continue JGP grouting. 3 points done as of today
Mon (09/06) | 09 Jun 2025 | PMH23 |  | Backfilling and prepare for compaction
Mon (09/06) | 09 Jun 2025 | P48 |  | Exposing UKP for main beam plate installation
Mon (09/06) | 09 Jun 2025 | P48 |  | Exposing services for support
Mon (09/06) | 09 Jun 2025 | P49 |  | Balance 2 Diagonal strut installed. And continue welding work
Mon (09/06) | 09 Jun 2025 | P50 |  | BRC installation for caisson casting
Mon (09/06) | 09 Jun 2025 | Bet. P14-P15 |  | Tunnel IM installation ongoing
Mon (09/06) | 09 Jun 2025 | N5 |  | Stressing done for D05 & U05
Mon (09/06) | 09 Jun 2025 | P14 |  | Segment adjustment and asbuilt taking ongoing. Target to complete today
Mon (09/06) | 09 Jun 2025 | S2 |  | Preboring for ERSS installation ongoing
Mon (09/06) | 09 Jun 2025 | P7-2 |  | Manual hacking & trimming of pile head in progress
Mon (09/06) | 09 Jun 2025 | P6-2 |  | Excavation to S1 layer completed
Mon (09/06) | 09 Jun 2025 | P5 |  | Setting up for CH stressing works ongoing
Mon (09/06) | 09 Jun 2025 | P2 |  | Column Formwork closing
Tue (10/06) | 10 Jun 2025 | BR10 |  | Excavation in progress
Tue (10/06) | 10 Jun 2025 | GL E7-E8 |  | Utility support installation
Tue (10/06) | 10 Jun 2025 | CCE2 |  | Hacking to dwall COL ongoing
Tue (10/06) | 10 Jun 2025 | P48 |  | Exposing services for support
Tue (10/06) | 10 Jun 2025 | P49 |  | Cleaning of welding area for MPI test
Tue (10/06) | 10 Jun 2025 | P50 |  | Caisson rebar work (1st stage)
Tue (10/06) | 10 Jun 2025 | Blk 4 |  | No silty discharge observed inside the drain
Tue (10/06) | 10 Jun 2025 | ST71 |  | Preparing for casting
Tue (10/06) | 10 Jun 2025 | P45 |  | JGP testing work
Tue (10/06) | 10 Jun 2025 | DR3 |  | TT for pipe sleeves installation
Tue (10/06) | 10 Jun 2025 | P46 |  | Preboring for UKP installation
Tue (10/06) | 10 Jun 2025 | DR3 |  | No activity of JGP as of now. Arrange for soil disposal
Tue (10/06) | 10 Jun 2025 | PMH23 |  | Current status
Tue (10/06) | 10 Jun 2025 | P43 |  | CJ roughening for column stump work
Tue (10/06) | 10 Jun 2025 | P43 |  | Trimming of surface for rectification
Tue (10/06) | 10 Jun 2025 | BR13 |  | Rebar works in progress
Tue (10/06) | 10 Jun 2025 | BR16A |  | KP bracing works ongoing
Tue (10/06) | 10 Jun 2025 | P23 transfer beam |  | Tie rod installation and partial formwork installation ongoing, Stitching wall rebar works ongoing
Tue (10/06) | 10 Jun 2025 | BR10 |  | Excavation in progress
Tue (10/06) | 10 Jun 2025 | P51 |  | Woh hup clearing materials to open up space for UKP work
Tue (10/06) | 10 Jun 2025 | P50 |  | Continue formwork closing and excavation for caisson work
Tue (10/06) | 10 Jun 2025 | P49 |  | Ryobi G on site to install string guage on strut
Tue (10/06) | 10 Jun 2025 | P21 |  | Falsework assembly in progress
Tue (10/06) | 10 Jun 2025 | P21 |  | ERSS materials shifting to S2
Tue (10/06) | 10 Jun 2025 | P20 |  | Prepration for Formwork removal
Tue (10/06) | 10 Jun 2025 | P19 |  | Column rebar cage fabrication
Tue (10/06) | 10 Jun 2025 | P19 |  | KTC continue backfilling till stump level
Tue (10/06) | 10 Jun 2025 | Bet. P14-P15 |  | Tunnel IM installation works
Tue (10/06) | 10 Jun 2025 | N5 |  | Falseworks erection for segment ongoing
Tue (10/06) | 10 Jun 2025 | P14 |  | Tendon ducts joining works
Tue (10/06) | 10 Jun 2025 | P14 |  | Lifting frame assembly
Tue (10/06) | 10 Jun 2025 | S2 |  | Preboring for ERSS. To complete tmr
Tue (10/06) | 10 Jun 2025 | P7-2 |  | Pile hacking completed. Preparation for lean concrete
Tue (10/06) | 10 Jun 2025 | P6-2 |  | Walers installation and welding in progress for s1 layer
Tue (10/06) | 10 Jun 2025 | P48 |  | Utility support installation by LE
Tue (10/06) | 10 Jun 2025 | P45 |  | JGP coring test for tunnel
Tue (10/06) | 10 Jun 2025 | P46 |  | Today to cast two UKP
Tue (10/06) | 10 Jun 2025 | DR3 |  | TT for JGP
Tue (10/06) | 10 Jun 2025 | DR3 |  | Preparing for JGP grouting work
Tue (10/06) | 10 Jun 2025 | PMH23 |  | Access erection for manhole work
Tue (10/06) | 10 Jun 2025 | Exit 3 |  | Excavation ongoing
Tue (10/06) | 10 Jun 2025 | BR13 |  | Bar chair installation in progress
Tue (10/06) | 10 Jun 2025 | BR10 |  | Continue excavation
Tue (10/06) | 10 Jun 2025 | ST71 |  | Casting completed
Wed (11/06) | 11 Jun 2025 | P50 |  | Excavation to L2 caisson level
Wed (11/06) | 11 Jun 2025 | P50 |  | Rebar installation for l2 caisson
Wed (11/06) | 11 Jun 2025 | P49 |  | No activity
Wed (11/06) | 11 Jun 2025 | DR3 |  | JGP works on going
Wed (11/06) | 11 Jun 2025 | P43 |  | Backfilling side of pile cap
Wed (11/06) | 11 Jun 2025 | P45 |  | Preparation for JGP coring work
Wed (11/06) | 11 Jun 2025 | P46 |  | Preparation for UKP preboring work
Wed (11/06) | 11 Jun 2025 | P50 |  | Mini shifted to TPE bound to resume excavation
Wed (11/06) | 11 Jun 2025 | P2 |  | QPS inspection ongoing. Target to cast column tmr
Wed (11/06) | 11 Jun 2025 | S2 |  | Preboring for ERSS. To complete Preboring today
Wed (11/06) | 11 Jun 2025 | Zone 4 |  | Woh hup continue clearing materials to give way for Power duct work
Wed (11/06) | 11 Jun 2025 | P21 |  | Preparation for falsework erection
Wed (11/06) | 11 Jun 2025 | P20 |  | Column Formwork dismantled
Wed (11/06) | 11 Jun 2025 | P19 |  | Column rebar cage fabrication
Wed (11/06) | 11 Jun 2025 | P50 |  | 2nd layer caisson (1st part) to cast today
Wed (11/06) | 11 Jun 2025 | P50 | TPE bound | Excavation to complete tomorrow
Wed (11/06) | 11 Jun 2025 | P49 |  | Now no activity. Ryobi to take base reading for String Guage
Wed (11/06) | 11 Jun 2025 | P19 |  | 1st lift pier column top surface hacking for const. joint
Wed (11/06) | 11 Jun 2025 | P48 |  | Manual exposing services below for support
Wed (11/06) | 11 Jun 2025 | PMH23 |  | Platform erection for manhole wall and top slab
Wed (11/06) | 11 Jun 2025 | DR3 |  | Rig set up for JGP grouting work
Wed (11/06) | 11 Jun 2025 | P46 |  | Boring one number done for UKP
Wed (11/06) | 11 Jun 2025 | P45 |  | TT for JGP testing
Wed (11/06) | 11 Jun 2025 | P46 |  | TT for UKP
Wed (11/06) | 11 Jun 2025 | Between P14-P15 |  | Tunnel IM installation works
Wed (11/06) | 11 Jun 2025 | N4 |  | Falsework erection for 1st pair segment in progress
Wed (11/06) | 11 Jun 2025 | P14 |  | PVC pipes installation for ducts
Wed (11/06) | 11 Jun 2025 | P14 |  | Continue assembly for 2nd lifting frame
Wed (11/06) | 11 Jun 2025 | S2 |  | Preboring for ERSS in progress. Today to complete
Wed (11/06) | 11 Jun 2025 | P7-2 |  | Rebar works for pile cap in progress
Wed (11/06) | 11 Jun 2025 | P6-2 |  | Welding works for walers in progress
Wed (11/06) | 11 Jun 2025 | P2 |  | Scaffold erection for column casting works tmr
Wed (11/06) | 11 Jun 2025 | Blk 4 |  | Dongah preboring machine boom down. Tonight plan to demob. Balance dwall to complete: ST70
Wed (11/06) | 11 Jun 2025 | GL E8 |  | Utility support welding works ongoing
Wed (11/06) | 11 Jun 2025 | CCE3 |  | Continue excavation
Wed (11/06) | 11 Jun 2025 | P20 |  | Scaffold access dismantling. Balance 1 side formwork to remove today
Wed (11/06) | 11 Jun 2025 | Zone 4 |  | Woh hup clearing materials to give way for power duct work
Thu (12/06) | 12 Jun 2025 | P14-15 |  | Tunnel RX installation
Thu (12/06) | 12 Jun 2025 | P14 SB |  | Strand pulling for first pair segment
Thu (12/06) | 12 Jun 2025 | P45 |  | Trial Trench for JGP coring work
Thu (12/06) | 12 Jun 2025 | P46 |  | Preparation work for UKP installation
Thu (12/06) | 12 Jun 2025 | DR3 |  | Preparation work for JGP work
Thu (12/06) | 12 Jun 2025 | PMH23 |  | Current status on site
Thu (12/06) | 12 Jun 2025 | P48 |  | Manual excavation to expose utilities
Thu (12/06) | 12 Jun 2025 | P48 |  | Utility support welding work
Thu (12/06) | 12 Jun 2025 | P50 |  | Excavation to L2 caisson level
Thu (12/06) | 12 Jun 2025 | P49 |  | No activity
Thu (12/06) | 12 Jun 2025 | P48 TPE bound |  | Utility support installation and welding
Thu (12/06) | 12 Jun 2025 | P48 |  | No activity
Thu (12/06) | 12 Jun 2025 | P50 |  | Rebar installation for 2nd stage of caisson
Thu (12/06) | 12 Jun 2025 | P50 TPE bound |  | KTC hacking of cement grout
Thu (12/06) | 12 Jun 2025 | P45 |  | Coring point testing
Thu (12/06) | 12 Jun 2025 | DR3 |  | JGP grouting. P46: last point boring for UKP. Today to cast
Thu (12/06) | 12 Jun 2025 | P14 NB |  | Pipe sleeve installation at tendon ducts
Thu (12/06) | 12 Jun 2025 | P14 SB U-01 |  | Segment adjusting in progress
Thu (12/06) | 12 Jun 2025 | P43 |  | Access dismantling and will relocate for backfilling
Thu (12/06) | 12 Jun 2025 | Blk 2 |  | Installation of alternate walking access
Thu (12/06) | 12 Jun 2025 | P7-2 |  | Area leveling for column rebar cage fabrication
Thu (12/06) | 12 Jun 2025 | P21 |  | Falsework leg frame assembly and installation
Thu (12/06) | 12 Jun 2025 | P19 |  | Lowering of rebar cage for 2nd layer main bar installation
Fri (13/06) | 13 Jun 2025 | P50 |  | Excavation to L2 caisson level
Fri (13/06) | 13 Jun 2025 | P49 |  | Preparation work on going, this afternoon going to start excavation to L2 caisson level
Fri (13/06) | 13 Jun 2025 | P43 |  | Backfilling work
Fri (13/06) | 13 Jun 2025 | P45 |  | Coring work no activity, waiting for access
Fri (13/06) | 13 Jun 2025 | DR3 |  | JGP work on going
Fri (13/06) | 13 Jun 2025 | PMH23 |  | Formwork preparation
Fri (13/06) | 13 Jun 2025 | P48 |  | Manual excavation and utility support installation
Fri (13/06) | 13 Jun 2025 | P47 |  | HSL checking location of last point UKP, pending main con further instruction. Today target to install last UKP at P47 and partial material shifting to P51
Fri (13/06) | 13 Jun 2025 | PMH25-PMH26 |  | Material cleared, today going to excavate 4m and lean con. Tomorrow pipe laying
Fri (13/06) | 13 Jun 2025 | ST70 | BC01 | B1 CD 22.8/24.13m
Fri (13/06) | 13 Jun 2025 | GL E3-E5 |  | Continues hacking of Dwall
Sat (14/06) | 14 Jun 2025 | Exit 1 Desander |  | Current stockpile status
Mon (16/06) | 16 Jun 2025 | P21 |  | Bottom formwork installation and column CJ roughening
Mon (16/06) | 16 Jun 2025 | P7-1 |  | Winch assembly for lifting frame
Mon (16/06) | 16 Jun 2025 | P51 to DR4 |  | Space open up for Wee Guan Power duct work
Mon (16/06) | 16 Jun 2025 | PMH26 |  | Excavation for PMH work
Mon (16/06) | 16 Jun 2025 | P50 |  | Continue formwork closing for balance caisson to cast
Mon (16/06) | 16 Jun 2025 | P49 |  | KTC continue excavation and disposal
Mon (16/06) | 16 Jun 2025 | P48 |  | LE continue utility support welding
Mon (16/06) | 16 Jun 2025 | PMH12 |  | Rebar work for wall and top slab
Mon (16/06) | 16 Jun 2025 | P45 |  | Coring test for JGP
Mon (16/06) | 16 Jun 2025 | P43 |  | Strut removal
Mon (16/06) | 16 Jun 2025 | P20 |  | Levelling of hardcore
Mon (16/06) | 16 Jun 2025 | N4 |  | Adjusting of segment one side completed
Mon (16/06) | 16 Jun 2025 | P7-S |  | Stump formwork closed
Mon (16/06) | 16 Jun 2025 | P6-S |  | Access erection
Mon (16/06) | 16 Jun 2025 | P5 |  | Continue tendom stressing work
Mon (16/06) | 16 Jun 2025 | P2 |  | Formwork dismantling
Mon (16/06) | 16 Jun 2025 | P21 |  | Crosshead side formwork closing
Mon (16/06) | 16 Jun 2025 | P50 |  | Rebar work for 2nd layer caisson
Mon (16/06) | 16 Jun 2025 | P49 |  | Excavation for 2nd layer caisson
Tue (17/06) | 17 Jun 2025 | CCE | GL E3-E5 | Current status of work, hacking down of dwall
Tue (17/06) | 17 Jun 2025 | P5 |  | Strand pulling completed. Preparation for post tensioning
Tue (17/06) | 17 Jun 2025 | Exit 1 Linkway |  | Access diversion ongoing
Tue (17/06) | 17 Jun 2025 | PMH46 |  | Current status of ERSS installation
Tue (17/06) | 17 Jun 2025 | P21 |  | Barricades and Formwork installation works in progress
Tue (17/06) | 17 Jun 2025 | P20 |  | BRC laying for ground foundation works
Tue (17/06) | 17 Jun 2025 | P19 |  | ERSS extraction in progress
Tue (17/06) | 17 Jun 2025 | P15 |  | 3rd Lifting frame assembly works
Tue (17/06) | 17 Jun 2025 | P14 |  | Formwork closing for stitching works
Tue (17/06) | 17 Jun 2025 | Zone 2 |  | LE boring rig preparation for dismantling and shift to zone 4
Tue (17/06) | 17 Jun 2025 | P50 near TPE bound |  | Last part formwork closing
Tue (17/06) | 17 Jun 2025 | P50 |  | 2nd part casting
Tue (17/06) | 17 Jun 2025 | P6-2 |  | Excavation to FEL. Mini breaker breakdown, mechanic on the way
Tue (17/06) | 17 Jun 2025 | P8 |  | Tomorrow to start strand pulling
Tue (17/06) | 17 Jun 2025 | N4 |  | Segment adjustment in progress for 1st pair
Tue (17/06) | 17 Jun 2025 | N4 |  | Falsework erection for segment launching
Tue (17/06) | 17 Jun 2025 | DR3 |  | Continue JGP work
Tue (17/06) | 17 Jun 2025 | P48 |  | Current no work. Need to settle the detail support of bend area
Tue (17/06) | 17 Jun 2025 | P49 |  | Continue excavation
Tue (17/06) | 17 Jun 2025 | P43 |  | Waler cutting and removal
Tue (17/06) | 17 Jun 2025 | P45 |  | SPT for tunnel JGP
Tue (17/06) | 17 Jun 2025 | P21 |  | GI pipes installation for crosshead rebar work
Tue (17/06) | 17 Jun 2025 | P20 |  | Lean concrete laying for cross head falsework
Tue (17/06) | 17 Jun 2025 | N5 |  | Stressing already done. Install end cap in progress
Tue (17/06) | 17 Jun 2025 | N4 |  | Adjusting of segment to continue tomorrow. Now tidy up work area
Tue (17/06) | 17 Jun 2025 | P7-2 |  | Stump casting on going. Now wait for last load
Tue (17/06) | 17 Jun 2025 | P6-2 |  | Now no activity already
Tue (17/06) | 17 Jun 2025 | P5 |  | Cutting of tendom wire
Tue (17/06) | 17 Jun 2025 | P51 |  | HSL unloading of materials
Tue (17/06) | 17 Jun 2025 | P50 |  | Continue caisson formwork closing
Tue (17/06) | 17 Jun 2025 | P49 |  | KTC continue excavation until 11PM
Tue (17/06) | 17 Jun 2025 | DR3 |  | GCE tidy up area to handover to night shift
Wed (18/06) | 18 Jun 2025 | P6-2 |  | Lowering of new excavator
Wed (18/06) | 18 Jun 2025 | P21 |  | Crosshead rebar and Formwork assembly works
Wed (18/06) | 18 Jun 2025 | P19 |  | ERSS extraction in progress
Wed (18/06) | 18 Jun 2025 | Zone 1 |  | TT for water stand pipe and piezometer for Tunnel
Wed (18/06) | 18 Jun 2025 | Exit 2 |  | Exposing utility alignment for support works. Will continue after tea break
Wed (18/06) | 18 Jun 2025 | GL 9-8 |  | Current status of excavation for utility support works
Wed (18/06) | 18 Jun 2025 | BR10 |  | Continue exposing couplers
Wed (18/06) | 18 Jun 2025 | Blk 2 |  | Dismantling BC cutter mud drums
Wed (18/06) | 18 Jun 2025 | N4 |  | Continue segment adjustment works
Wed (18/06) | 18 Jun 2025 | P14 |  | Formwork closing for stitching works
Wed (18/06) | 18 Jun 2025 | P6-2 |  | Excavation to FEL. To complete tomorrow
Wed (18/06) | 18 Jun 2025 | PMH25-PMH26 |  | Excavation and ERSS for duct laying
Wed (18/06) | 18 Jun 2025 | P51 |  | HSL prepare platform for UKP work. Tomorrow to start
Wed (18/06) | 18 Jun 2025 | PMH26 |  | Now no activity
Wed (18/06) | 18 Jun 2025 | CCE2 |  | Excavation ongoing
Wed (18/06) | 18 Jun 2025 | Exit 1 |  | Desander status
Wed (18/06) | 18 Jun 2025 | BR31 |  | Coupler rebar installation & RGT installation ongoing
Wed (18/06) | 18 Jun 2025 | P50 |  | Last part of 2nd layer caisson casting
Wed (18/06) | 18 Jun 2025 | P49 |  | 70% of area ready to handover for rebar work. Tomorrow to complete excavation for 2nd layer caisson
Wed (18/06) | 18 Jun 2025 | P48 |  | Now no activity. Left water pipes to support
Wed (18/06) | 18 Jun 2025 | PMH23 |  | Rebar work completed. Prepare for inspection and formwork closing
Wed (18/06) | 18 Jun 2025 | DR3 |  | JGP grouting work
Wed (18/06) | 18 Jun 2025 | P45 |  | Coring test for tunnel grouting
Wed (18/06) | 18 Jun 2025 | P43 |  | Prepare for to cast defect area of pile cap. Concrete ordered
Wed (18/06) | 18 Jun 2025 | BR16A |  | Continue rebar works, Hirose: KP bracing welding works ongoing
Wed (18/06) | 18 Jun 2025 | P23 |  | Removal of formwork support
Wed (18/06) | 18 Jun 2025 | Exit 2 |  | Continue exposing utilities
Wed (18/06) | 18 Jun 2025 | BR10 |  | Surface ground levelling & excavation ongoing. Lean concrete otw
Wed (18/06) | 18 Jun 2025 | BR14 |  | Continue excavation
Wed (18/06) | 18 Jun 2025 | P20 |  | Steel plate laying and assembling of falsework for crosshead platform
Wed (18/06) | 18 Jun 2025 | P19 |  | Preparing for concrete block placing for column support
Wed (18/06) | 18 Jun 2025 | P4 |  | Continue adjusting of segment
Wed (18/06) | 18 Jun 2025 | CCE2 |  | Continue excavation
Wed (18/06) | 18 Jun 2025 | BR31 |  | Coupler rebar tightening ongoing
Wed (18/06) | 18 Jun 2025 | CCE4 |  | Excavation ongoing
Wed (18/06) | 18 Jun 2025 | S2 |  | Current status of excavation
Wed (18/06) | 18 Jun 2025 | P7-2 |  | No activity
Wed (18/06) | 18 Jun 2025 | P7 |  | Clearing materials
Wed (18/06) | 18 Jun 2025 | P6-2 |  | Excavation to FEL. Tomorrow KTC will handover
Wed (18/06) | 18 Jun 2025 | P5 |  | Stressing work
Wed (18/06) | 18 Jun 2025 | P21 |  | Crosshead rebar work
Wed (18/06) | 18 Jun 2025 | P43 |  | Rectification of pile cap surface
Wed (18/06) | 18 Jun 2025 | P50 |  | Casting completed
Thu (19/06) | 19 Jun 2025 | P21 |  | Crosshead Rebar installation ongoing
Thu (19/06) | 19 Jun 2025 | P20 |  | Falsework erection in progress
Thu (19/06) | 19 Jun 2025 | P19 |  | Crane setting up for column installation
Thu (19/06) | 19 Jun 2025 | PMH26 |  | Precast delivered near to the area to install
Thu (19/06) | 19 Jun 2025 | N4 |  | Segment adjustment ongoing. Target to complete today
Thu (19/06) | 19 Jun 2025 | BR10 |  | Current status
Thu (19/06) | 19 Jun 2025 | P15 |  | Formwork closing for rectification works
Thu (19/06) | 19 Jun 2025 | Bet. P14-P15 |  | Lifting frame assembly works
Thu (19/06) | 19 Jun 2025 | PMH29 |  | Trial Trench work
Thu (19/06) | 19 Jun 2025 | CCE 3 |  | Current excavation status
Thu (19/06) | 19 Jun 2025 | MC96 |  | BG body dismantling ongoing, target to demob next week
Thu (19/06) | 19 Jun 2025 | P14 |  | 4 workers installing stitching formwork at SB U-01. Target to cast SB side only by Saturday
Thu (19/06) | 19 Jun 2025 | P43 |  | Steel plates removal
Thu (19/06) | 19 Jun 2025 | P7-1 |  | Today to complete material clearing
Thu (19/06) | 19 Jun 2025 | P6-2 |  | Final levelling. Afternoon HSL excavator to mobilise
Thu (19/06) | 19 Jun 2025 | Zone 1 |  | Vibro mobilise for P2 ERSS extraction and deck removal at P3
Thu (19/06) | 19 Jun 2025 | P45 |  | Coring work in progress
Thu (19/06) | 19 Jun 2025 | DR3 |  | Preparation work for JGP
Thu (19/06) | 19 Jun 2025 | PMH23 |  | Rebar work on going
Thu (19/06) | 19 Jun 2025 | P48 |  | No activity
Thu (19/06) | 19 Jun 2025 | P49 |  | Rebar work for L2 caisson work. meanwhile, excavation at south side on going
Thu (19/06) | 19 Jun 2025 | P50 |  | Formwork removal
Thu (19/06) | 19 Jun 2025 | P43 |  | Preparation work for backfilling
Thu (19/06) | 19 Jun 2025 | PMH28 |  | Traffic light shifting done
Thu (19/06) | 19 Jun 2025 | P14 SB U-01 |  | Wet stitching outer frame formwork closing continue. 4+1
Thu (19/06) | 19 Jun 2025 | P2 |  | ERSS removal in progress
Thu (19/06) | 19 Jun 2025 | Bet. P3-P2 |  | Trial trench and drilling for Tunnel IM in progress
Thu (19/06) | 19 Jun 2025 | GL9 |  | Excavation ongoing for utility support works
Thu (19/06) | 19 Jun 2025 | DR3 |  | JGP grouting work
Thu (19/06) | 19 Jun 2025 | PMH23 |  | Formwork closing in progress
Thu (19/06) | 19 Jun 2025 | P48 |  | Now no activity
Thu (19/06) | 19 Jun 2025 | P49 |  | Rebar work for 2nd layer caisson
Thu (19/06) | 19 Jun 2025 | P49 |  | Excavation for 2nd layer to complete tomorrow
Thu (19/06) | 19 Jun 2025 | P50 |  | Formwork removal almost completed
Thu (19/06) | 19 Jun 2025 | PMH26 |  | Continue excavation for precast placing
Thu (19/06) | 19 Jun 2025 | P5 |  | Stressing works completed. Dismantling ongoing
Thu (19/06) | 19 Jun 2025 | P45 |  | 1st point coring test. Today to complete
Thu (19/06) | 19 Jun 2025 | P43 |  | Status of ERSS removal. Protection of stump rebar done
Thu (19/06) | 19 Jun 2025 | BR16A |  | Securing working platforms for subsequent rebar works
Thu (19/06) | 19 Jun 2025 | P23 TB |  | Formwork dismantling
Thu (19/06) | 19 Jun 2025 | Zone 4 DR3 |  | Grouting continue for point A8
Thu (19/06) | 19 Jun 2025 | S1-1 | GL4-5 | Excavation ongoing
Thu (19/06) | 19 Jun 2025 | BR10 |  | Continue exposing couplers and balance excavation towards GL16
Thu (19/06) | 19 Jun 2025 | PMH23 |  | Top slab and wall side formwork closing
Thu (19/06) | 19 Jun 2025 | P19 |  | Tonight to lower down RWDP and install links at the lapping area. Tomorrow to close formwork
Thu (19/06) | 19 Jun 2025 | P14 lifter |  | 3rd set winch assembly started
Thu (19/06) | 19 Jun 2025 | S2 |  | Waler bracket completed. 2 side waler installed. No more activity
Thu (19/06) | 19 Jun 2025 | PMH28 |  | Mini mobilized for shifting of traffic light cable to give way for PMH work
Thu (19/06) | 19 Jun 2025 | PMH28 |  | Materials clearing
Fri (20/06) | 20 Jun 2025 | CCE 4 |  | Excavation for S2 started
Fri (20/06) | 20 Jun 2025 | BR31 |  | Current status
Fri (20/06) | 20 Jun 2025 | P21 |  | Tendon ducts installation in progress
Fri (20/06) | 20 Jun 2025 | P20 |  | Formwork assembly in progress
Fri (20/06) | 20 Jun 2025 | P19 |  | Preparation for Column Formwork closing
Fri (20/06) | 20 Jun 2025 | P14 |  | Stitching Formwork installation
Fri (20/06) | 20 Jun 2025 | P14 |  | Lifting frame assembly works
Fri (20/06) | 20 Jun 2025 | GL9 |  | Excavation for utility support ongoing
Fri (20/06) | 20 Jun 2025 | GL9 |  | Also manual clearing of soil on utilities
Fri (20/06) | 20 Jun 2025 | BR10 |  | CJ roughening and excavation in progress. Balance excavation towards GL16
Fri (20/06) | 20 Jun 2025 | PMH26 |  | Excavation to FEL for PMH precast lowering
Fri (20/06) | 20 Jun 2025 | PMH28 |  | Clearing materials by Woh Hup
Fri (20/06) | 20 Jun 2025 | P8 |  | Crosshead stressing works ongoing
Fri (20/06) | 20 Jun 2025 | S2 |  | Waler and struts installation current status
Fri (20/06) | 20 Jun 2025 | P7-1 |  | Premix hacking for trial trench works
Fri (20/06) | 20 Jun 2025 | P7-2 |  | Water pumping ongoing
Fri (20/06) | 20 Jun 2025 | P6-1 |  | Materials shifting in progress
Fri (20/06) | 20 Jun 2025 | P6-2 |  | Pile head hacking
Fri (20/06) | 20 Jun 2025 | Zone 1 |  | Lane closed for ATS works
Fri (20/06) | 20 Jun 2025 | Zone 1 |  | Tunnel IM installation in progress
Fri (20/06) | 20 Jun 2025 | DR3 |  | Continue JGP work. Maximum two weeks to complete all
Fri (20/06) | 20 Jun 2025 | P48 |  | No activity
Fri (20/06) | 20 Jun 2025 | P49 |  | 2nd layer caisson work
Fri (20/06) | 20 Jun 2025 | P50 |  | KTC to mobilize excavator tomorrow
Fri (20/06) | 20 Jun 2025 | P51 |  | 2nos of casing installed for UKP
Fri (20/06) | 20 Jun 2025 | Zone 4 |  | Footing for signage installation
Fri (20/06) | 20 Jun 2025 | Exit 1/ Linkway |  | Access diversion ongoing
Sat (21/06) | 21 Jun 2025 | BR14 |  | CJ hacking ongoing, Excavation in progress at GL2
Sat (21/06) | 21 Jun 2025 | BR13 |  | Formwork dismantling ongoing
Sat (21/06) | 21 Jun 2025 | BR16A |  | Rebar works in progress
Sat (21/06) | 21 Jun 2025 | Zone 1 |  | Current status of decking removal. LE prepare to remove soldier pile and steel plates
Sat (21/06) | 21 Jun 2025 | Zone 4 PMH28 |  | Traffic light cable shifting done
Sat (21/06) | 21 Jun 2025 | PMH29 |  | Preparing to shift footpath for Wee Guan work
Sat (21/06) | 21 Jun 2025 | Near P22 |  | Slope lean con done
Sat (21/06) | 21 Jun 2025 | S1-1 |  | Continue excavation
Sat (21/06) | 21 Jun 2025 | GL11 |  | Manual soil clearing on utilities ongoing
Sat (21/06) | 21 Jun 2025 | BR10 |  | Continue soil disposal at GL16. Target to complete balance excavation tmr, GL21-18: RTO inspection for couplers & surface lean con before debonding sheet installation
Sat (21/06) | 21 Jun 2025 | Near blk 4 |  | BC cutter cleaning and dismantling works. Plan to demob BC cutter and mud drums on Tuesday, Housekeeping
Sat (21/06) | 21 Jun 2025 | PMH26 |  | To continue excavation for ERSS installation
Sat (21/06) | 21 Jun 2025 | P51 |  | Woh hup clearing materials. HSL installed 2 casing and 2 casing to install today
Sat (21/06) | 21 Jun 2025 | P51 |  | KTC lowered down mini
Sat (21/06) | 21 Jun 2025 | P49 |  | Formwork closing for caisson. Excavation completed by KTC
Sat (21/06) | 21 Jun 2025 | P48 |  | No activity as of now
Sat (21/06) | 21 Jun 2025 | PMH23 |  | Casting started
Sat (21/06) | 21 Jun 2025 | DR3 |  | JGP grouting work
Sat (21/06) | 21 Jun 2025 | P46 |  | JGP testing
Sat (21/06) | 21 Jun 2025 | BR31 |  | Decking beam rebar works, Drilling of missing couplers at north side, Preparation ongoing for lean con casting for 800mm wall, KP end plate welding ongoing
Sat (21/06) | 21 Jun 2025 | CCE4/RS |  | Excavation ongoing
Sat (21/06) | 21 Jun 2025 | P43 |  | Backfilling completed and LE started steel plate removal
Sat (21/06) | 21 Jun 2025 | P21 crosshead |  | Tying of rebar and duct installation by woh hup
Sat (21/06) | 21 Jun 2025 | P19 |  | Column formwork closing
Sat (21/06) | 21 Jun 2025 | P20 |  | Status of falsework assembling
Sat (21/06) | 21 Jun 2025 | P15 |  | Level checking for starter lifter. Assembling of lifting frame
Sat (21/06) | 21 Jun 2025 | S2 |  | Walee installed
Sat (21/06) | 21 Jun 2025 | P6-2 |  | Pile head hacking and clear debris
Sat (21/06) | 21 Jun 2025 | P7-2 |  | KTC soil backfilling
Sat (21/06) | 21 Jun 2025 | S2 |  | Now no activity
Sat (21/06) | 21 Jun 2025 | BR14 |  | Continue soil disposal, Surface cleaning ongoing at lean concreted area before laying debonding sheet
Sat (21/06) | 21 Jun 2025 | BR13 |  | Barricade painting
Sat (21/06) | 21 Jun 2025 | BR16A |  | Continue rebar works
Sat (21/06) | 21 Jun 2025 | BR10 |  | Start laying debonding sheet & preparing bottom rebars (Wendyng), RGT installation by Maxbond, Continue balance excavation
Sat (21/06) | 21 Jun 2025 | PMH26 |  | Continue excavation and ERSS work
Sat (21/06) | 21 Jun 2025 | P51 |  | Casing installation for UKP
Sat (21/06) | 21 Jun 2025 | P50 |  | No activity
Sat (21/06) | 21 Jun 2025 | P49 |  | Manual excavation for balance caisson rebar work
Sat (21/06) | 21 Jun 2025 | P49 TPE bound |  | 1st caisson for 2nd layer casting done
Sat (21/06) | 21 Jun 2025 | S1-1 |  | Clearing hardcores
Sat (21/06) | 21 Jun 2025 | Deck 9 |  | Pending backfilling then install beam
Sat (21/06) | 21 Jun 2025 | Blk 4 |  | Dongah continue housekeeping
Sat (21/06) | 21 Jun 2025 | P46 |  | Continue testing of JGP
Sat (21/06) | 21 Jun 2025 | DR3 |  | Continue JGP work
Sat (21/06) | 21 Jun 2025 | PMH23 |  | Casting done
Sat (21/06) | 21 Jun 2025 | BR31 |  | Rebar planting at north side, Preparatory works for lean con for 800mm wall, Backfilled at KP area
Sat (21/06) | 21 Jun 2025 | P21 |  | Tendom duct installation and rebar adjustment
Sat (21/06) | 21 Jun 2025 | P20 |  | Current status of false work assembling
Sat (21/06) | 21 Jun 2025 | P15 |  | Level checking for lifter
Sat (21/06) | 21 Jun 2025 | P19 |  | Column formwork closing
Mon (23/06) | 23 Jun 2025 | PMH26 |  | Excavation and ERSS installation done. Will lean concrete at 4PM
Mon (23/06) | 23 Jun 2025 | PMH28 |  | Woh hup clearing materials for drain hacking
Mon (23/06) | 23 Jun 2025 | P19 |  | Pump car setting up for casting
Mon (23/06) | 23 Jun 2025 | GLE3-E5 |  | Casting for decking beam ongoing
Mon (23/06) | 23 Jun 2025 | BR31 |  | Current status
Mon (23/06) | 23 Jun 2025 | P14 | SB side | Stitching formwork tie rod and filler plate completed. NB side to continue until 10pm. They only target to cast tomorrow, SB: dayshift, NB: nightshift
Mon (23/06) | 23 Jun 2025 | BR31 |  | Pull out test for coupler rebar ongoing, debonding sheet laying in progress
Mon (23/06) | 23 Jun 2025 | CCE4 |  | No activity
Mon (23/06) | 23 Jun 2025 | BR 10 | up till GL 18 | Bottom rebars tying / laying ongoing
Mon (23/06) | 23 Jun 2025 | GL 18-17 |  | Coupler exposure ongoing
Mon (23/06) | 23 Jun 2025 | GL 17-15 |  | Excavation/ soil disposal ongoing
Mon (23/06) | 23 Jun 2025 | P51 |  | Boring for UKP. Today 2nos to cast
Mon (23/06) | 23 Jun 2025 | P51 |  | As of now no activity yet
Mon (23/06) | 23 Jun 2025 | P45 |  | LE preparing to set up crane
Mon (23/06) | 23 Jun 2025 | DR3 |  | Preparing for JGP grouting
Mon (23/06) | 23 Jun 2025 | PMH23 |  | ERSS removal
Mon (23/06) | 23 Jun 2025 | P48 |  | No activity
Mon (23/06) | 23 Jun 2025 | P50 |  | Concrete ordered for 2nd stage casting. Rebar work for 3rd stage casting
Mon (23/06) | 23 Jun 2025 | Zone 1 RG works |  | Still need to do 2 nos RX, 2 pizometer, and 1 inclinometer. Target to complete all next week
Mon (23/06) | 23 Jun 2025 | P3-P2 |  | Premix hacking for mini road realignment
Mon (23/06) | 23 Jun 2025 | P43 |  | KTC exposing soldier pile for LE to remove
Tue (24/06) | 24 Jun 2025 | PMH28 |  | Wee Guan clearing material and prepare materials for ERSS
Tue (24/06) | 24 Jun 2025 | PMH28 |  | Abandoned drain removal
Tue (24/06) | 24 Jun 2025 | BR31 |  | Current status, fwk closure / rebar tying for RC struts ongoing, bottom rebar laying / tying ongoing
Tue (24/06) | 24 Jun 2025 | GL13 |  | Clearing excess soil from utilities
Tue (24/06) | 24 Jun 2025 | Blk 4 |  | Dongah housekeeping ongoing. Mud drums have been demob
Tue (24/06) | 24 Jun 2025 | BR10 |  | GL19-18 bottom rebars inspection ongoing, GL17: Lean con done. Surface levelling ongoing, Balance excavation ongoing at GL16
Tue (24/06) | 24 Jun 2025 | GL E3 |  | Decking beam status & delivery of I-beam for construction deck
Tue (24/06) | 24 Jun 2025 | PMH26 |  | Precast lowering
Tue (24/06) | 24 Jun 2025 | DR3 |  | Continue JGP grouting work
Tue (24/06) | 24 Jun 2025 | P45 |  | Assembling of rig. Left to deliver kelly bar
Tue (24/06) | 24 Jun 2025 | PMH23 |  | Prepare formwork for manhole neck
Tue (24/06) | 24 Jun 2025 | P48 |  | No activity
Tue (24/06) | 24 Jun 2025 | P49 |  | Concrete ordered for 3 stages caisson casting. 4th stage prepare for formwork closing
Tue (24/06) | 24 Jun 2025 | P50 |  | Need to shift in long arm to start excavation
Tue (24/06) | 24 Jun 2025 | P51 |  | Today to cast two UKP
Tue (24/06) | 24 Jun 2025 | Zone 1 |  | Tunnel IM trial trench works
Tue (24/06) | 24 Jun 2025 | Zone 1 |  | Road realignment preparation works
Tue (24/06) | 24 Jun 2025 | P5 |  | Formwork dismantling and materials shifting ongoing
Tue (24/06) | 24 Jun 2025 | P6-2 |  | Pile head manual hacking works
Tue (24/06) | 24 Jun 2025 | P7-2 |  | Concrete plug to cast tonight
Tue (24/06) | 24 Jun 2025 | P7-1 |  | Platform preparation for trial trench works
Tue (24/06) | 24 Jun 2025 | S2 |  | Excavation to FEL
Tue (24/06) | 24 Jun 2025 | Zone 2 |  | Lifting frame wires connection works
Tue (24/06) | 24 Jun 2025 | P14 |  | Tendon strands installation
Tue (24/06) | 24 Jun 2025 | N4 |  | Falsework installation for Segment
Tue (24/06) | 24 Jun 2025 | P15 |  | Crosshead Rectification works
Tue (24/06) | 24 Jun 2025 | P20 |  | Crosshead Falsework erection
Tue (24/06) | 24 Jun 2025 | P21 |  | Crosshead tendon duct and rebars installation
Tue (24/06) | 24 Jun 2025 | P21 |  | No activity. Materials for balance ducting will deliver tomorrow only
Tue (24/06) | 24 Jun 2025 | P15 |  | Grouting completed
Tue (24/06) | 24 Jun 2025 | BR14 |  | Rebar tying and surveyor works ongoing, RGT installation
Tue (24/06) | 24 Jun 2025 | BR16A |  | Partial formwork closing
Tue (24/06) | 24 Jun 2025 | P6-2 |  | Hacking of pile head
Tue (24/06) | 24 Jun 2025 | S2 |  | Current status of excavation
Tue (24/06) | 24 Jun 2025 | S1-1/1-2 |  | Current status
Tue (24/06) | 24 Jun 2025 | BR10 |  | Rebar works in progress
Tue (24/06) | 24 Jun 2025 | CCE | GL-E3 | Decking beam installation & welding works in progress, Capping beam formwork dismantling ongoing
Tue (24/06) | 24 Jun 2025 | BR31 |  | Rebar works in progress
Tue (24/06) | 24 Jun 2025 | P49 |  | 3rd stage caisson casting done
Tue (24/06) | 24 Jun 2025 | P51 |  | UKP casting done
Wed (25/06) | 25 Jun 2025 | P14 |  | Today, plan to dismantle part of the inner formwork. Materials will be shifted to N4 for stitching works. Today, also expect concrete AI results. If concrete strength >80%, stressing to start tomorrow
Wed (25/06) | 25 Jun 2025 | PMH29 |  | Night shift doing pipe sleeves installation
Wed (25/06) | 25 Jun 2025 | PMH28 |  | Abandoned drain removal
Wed (25/06) | 25 Jun 2025 | PMH26 |  | Base and stitching rebar work. Today to cast
Wed (25/06) | 25 Jun 2025 | Zone 1 |  | Lampost shifting today before 5pm
Wed (25/06) | 25 Jun 2025 | P2 area |  | Excavation for RCA backfilling. Today plan to lay B1 from P3- P2
Wed (25/06) | 25 Jun 2025 | P49 |  | Last part formwork closing for caisson
Wed (25/06) | 25 Jun 2025 | DR3 |  | JGP grouting
Wed (25/06) | 25 Jun 2025 | P14 |  | Strand pulling for stressing. 👍
Wed (25/06) | 25 Jun 2025 | BR10 |  | GL16: Soil disposal ongoing, GL19-17: Rebar works in progress
Wed (25/06) | 25 Jun 2025 | BR31 |  | Continues rebar work
Wed (25/06) | 25 Jun 2025 | CCE2 |  | Decking beam installation in progress
Wed (25/06) | 25 Jun 2025 | PMH28 |  | Woh hup continue drain removal. To complete today
Wed (25/06) | 25 Jun 2025 | P45 |  | Preboring right setting up
Wed (25/06) | 25 Jun 2025 | P46 |  | Coring test in progress
Wed (25/06) | 25 Jun 2025 | DR3 |  | JGP trial trench work
Wed (25/06) | 25 Jun 2025 | PMH23 |  | Formwork closing for necking part, target today cast
Wed (25/06) | 25 Jun 2025 | P48 |  | No activity
Wed (25/06) | 25 Jun 2025 | P49 |  | Formwork closing. Tomorrow casting last section
Wed (25/06) | 25 Jun 2025 | P50 |  | Excavation to 3rd caisson level
Wed (25/06) | 25 Jun 2025 | P51 |  | UKP installation in progress
Wed (25/06) | 25 Jun 2025 | PMH25-26 |  | Excavation for pipe laying
Wed (25/06) | 25 Jun 2025 | PMH26 |  | Rebar installation
Wed (25/06) | 25 Jun 2025 | PMH28 |  | Drain hacking in progress
Wed (25/06) | 25 Jun 2025 | P43 |  | Left 16nos of soldier piles to remove. Tomorow can complete
Wed (25/06) | 25 Jun 2025 | BR14 |  | Drilling ongoing for coupler rebars, Partial corrugated pipes installation
Wed (25/06) | 25 Jun 2025 | BR16A |  | Currently no activity
Wed (25/06) | 25 Jun 2025 | BR15A & BR15B |  | Excavation in progress
Wed (25/06) | 25 Jun 2025 | P20 |  | Falsework erection for crosshead
Wed (25/06) | 25 Jun 2025 | N4 |  | Tendom wire pulling. Woh hup to start work for stitching tomorrow
Wed (25/06) | 25 Jun 2025 | P14 |  | Tendom wire pulling. Tomorrow plan for stressing
Wed (25/06) | 25 Jun 2025 | P6-2 |  | Clearing soil. Tonight plan for lean con
Wed (25/06) | 25 Jun 2025 | S2 |  | Continue excavation to FEL
Wed (25/06) | 25 Jun 2025 | S1-2 |  | Excavation in progress for utility support works
Wed (25/06) | 25 Jun 2025 | Exit 2 |  | Guidewall exposed
Wed (25/06) | 25 Jun 2025 | GL9 |  | Hirose resume utility support beam installation
Wed (25/06) | 25 Jun 2025 | BR10 |  | GL16 excavation completed. Now pending lean concrete casting to facilitate remaining debonding sheet laying & rebar works, GL19-17: Rebar works & shearlinks installation in progress
Wed (25/06) | 25 Jun 2025 | Blk 4 |  | Dongah hardcore disposal
Wed (25/06) | 25 Jun 2025 | CCE2 |  | Decking beam installation in progress
Wed (25/06) | 25 Jun 2025 | BR31 |  | Continue rebar works
Wed (25/06) | 25 Jun 2025 | PMH23 |  | Manhole neck casting
Wed (25/06) | 25 Jun 2025 | P51 |  | Two UKP casting
Wed (25/06) | 25 Jun 2025 | P50 |  | Continue excavation
Thu (26/06) | 26 Jun 2025 | MH2-9 |  | Drain rebar reinstatement in progress
Thu (26/06) | 26 Jun 2025 | MH2-10 |  | CCTV inspection completed
Thu (26/06) | 26 Jun 2025 | Along sewer 2 |  | Green railing reinstatement
Thu (26/06) | 26 Jun 2025 | GL15 |  | Manual clearing of soil on top of utilities
Thu (26/06) | 26 Jun 2025 | BR10 |  | Balance lean con for base slab & slope protection casting completed, Continue rebar works
Thu (26/06) | 26 Jun 2025 | GL8-9 |  | Utility support beams welding ongoing
Thu (26/06) | 26 Jun 2025 | Exit 2 |  | Excavation for utility stump works
Thu (26/06) | 26 Jun 2025 | CCE2 |  | Cotninues decking beam installation
Thu (26/06) | 26 Jun 2025 | CCE4 |  | Excavation to roof level in progress
Thu (26/06) | 26 Jun 2025 | BR31 |  | Rebar & formwork installation in progress
Thu (26/06) | 26 Jun 2025 | P14 |  | Stressing jack installation. Tmr to start stressing
Thu (26/06) | 26 Jun 2025 | PMH26 |  | Base and wall to cast today
Thu (26/06) | 26 Jun 2025 | PMH29 |  | Drain removal by woh hup
Thu (26/06) | 26 Jun 2025 | PMH28 |  | Excavation and levelling for PLT
Thu (26/06) | 26 Jun 2025 | P50 |  | Sewer pipe cutting done and plugging with cement
Thu (26/06) | 26 Jun 2025 | P45 |  | Casing installation for preboring for soldier pile installation
Thu (26/06) | 26 Jun 2025 | DR3 |  | JGP grouting by GCE
Thu (26/06) | 26 Jun 2025 | PMH23 |  | Formwork removal for completed manhole
Thu (26/06) | 26 Jun 2025 | P48 |  | No activity
Thu (26/06) | 26 Jun 2025 | P50 |  | Continue excavation for 3rd layer caisson
Thu (26/06) | 26 Jun 2025 | P49 |  | Removal of protruding concrete
Thu (26/06) | 26 Jun 2025 | P51 |  | Will cast two UKP today. Total will be 10/17nos as of today
Thu (26/06) | 26 Jun 2025 | P43 |  | Vibro hydraulic hose leakage. Balance 8nos of soldier piles. Tomorrow only can complete
Thu (26/06) | 26 Jun 2025 | P21 crosshead |  | Section 1 links installation in progress
Thu (26/06) | 26 Jun 2025 | P16 |  | Scaffold access for segment launching erection started
Fri (27/06) | 27 Jun 2025 | P21 |  | Rebar installation and adjustment in progress
Fri (27/06) | 27 Jun 2025 | P20 |  | Scaffold erection for crosshead works
Fri (27/06) | 27 Jun 2025 | P19 |  | Column Formwork dismantling
Fri (27/06) | 27 Jun 2025 | Bet. P19-P20 |  | Tunnel IM drilling works
Fri (27/06) | 27 Jun 2025 | P16 |  | Scaffold erection for segment launching works
Fri (27/06) | 27 Jun 2025 | P14 |  | Stitching Formwork dismantle and removal in progress
Fri (27/06) | 27 Jun 2025 | PMH16 |  | Formwork removal and falsework erection for top slab
Fri (27/06) | 27 Jun 2025 | PMH28 |  | Plate load test
Fri (27/06) | 27 Jun 2025 | N3 |  | Ground preparation for falsework erection ongoing
Fri (27/06) | 27 Jun 2025 | P12 |  | Lifting frame railing installation
Fri (27/06) | 27 Jun 2025 | P9-P10 |  | Stressing cage assembly ongoing
Fri (27/06) | 27 Jun 2025 | S2 |  | Excavation to FEL ongoing
Fri (27/06) | 27 Jun 2025 | P7-2 |  | KTC Backfilling and compaction works
Fri (27/06) | 27 Jun 2025 | P6-2 |  | Rebar installation for pile cap
Fri (27/06) | 27 Jun 2025 | P2 |  | ERSS extraction
Fri (27/06) | 27 Jun 2025 | P5 |  | No activity
Fri (27/06) | 27 Jun 2025 | Bet. P3-P2 |  | Premix laying and compaction works
Fri (27/06) | 27 Jun 2025 | P2 |  | Trial trench for Tunnel IM
Fri (27/06) | 27 Jun 2025 | P51 |  | Two UKP to cast today. 10+2Nos/ 17nos
Fri (27/06) | 27 Jun 2025 | P50 |  | Continue excavation
Fri (27/06) | 27 Jun 2025 | P48 |  | No activity
Fri (27/06) | 27 Jun 2025 | DR3 |  | Continue grouting JGP. To complete today
Fri (27/06) | 27 Jun 2025 | PMH23 |  | Formwork removal
Fri (27/06) | 27 Jun 2025 | P45 |  | Preboring 2nos of soldier piles
Sat (28/06) | 28 Jun 2025 | P6-2 |  | Footing rebar work
Sat (28/06) | 28 Jun 2025 | P7 |  | LE levelling for platform
Sat (28/06) | 28 Jun 2025 | P6-2 |  | KTC soil backfilling for ERSS removal
Sat (28/06) | 28 Jun 2025 | S2 |  | Now mini breakdown. Mechanic on the way
Sat (28/06) | 28 Jun 2025 | Exit 2 |  | Guidewall exposed
Sat (28/06) | 28 Jun 2025 | GL8-9 |  | Utility support welding works ongoing
Sat (28/06) | 28 Jun 2025 | BR10 |  | Continue rebar works and hyrib installation
Sat (28/06) | 28 Jun 2025 | Opp blk 4 |  | Seongha containers and materials mobilisation. Plan to resume remaining fissure grouting points next week
Sat (28/06) | 28 Jun 2025 | Blk 4 |  | Dongah removing barette pile guidewall, Starhub MH removal ongoing
Sat (28/06) | 28 Jun 2025 | BR31 |  | Cleaning ongoing. Preparing for casting. Pump car is currently parked near exit 1 & platform ready for pump car parking
Sat (28/06) | 28 Jun 2025 | GL E5 |  | Partial decking panel installation & welding works
Sat (28/06) | 28 Jun 2025 | CCE4 |  | Excavation in progress
Sat (28/06) | 28 Jun 2025 | DE160 |  | Lane closure for diversion work. Today they plan to swing road
Sat (28/06) | 28 Jun 2025 | P43 |  | No activity
Sat (28/06) | 28 Jun 2025 | GL10 |  | Manual clearing of excess soil on utilities
Sat (28/06) | 28 Jun 2025 | P48 & P49 |  | No activity today
Sat (28/06) | 28 Jun 2025 | P50 |  | Excavation to next layer caisson
Sat (28/06) | 28 Jun 2025 | P51 |  | Plan to cast two UKP today
Sat (28/06) | 28 Jun 2025 | PMH26 |  | Falsework erection for top slab
Sat (28/06) | 28 Jun 2025 | PMH28 |  | Found unknow concrete haunch. Checking on going
Sat (28/06) | 28 Jun 2025 | P45 |  | 4nos boring done
Sat (28/06) | 28 Jun 2025 | DR3 |  | Continue JGP grouting
Sat (28/06) | 28 Jun 2025 | Near blk 2 |  | Excavation ongoing
Sat (28/06) | 28 Jun 2025 | BR10 |  | Continue rebar works and partial side formwork installation
Sat (28/06) | 28 Jun 2025 | P14 |  | Preparation for starter hanger platform dismantling also
Sat (28/06) | 28 Jun 2025 | P14 |  | Stressing done. Cutting of wire and capping work
Sat (28/06) | 28 Jun 2025 | P16 |  | Access erection on going
Sat (28/06) | 28 Jun 2025 | P20 |  | Working platform work
Sat (28/06) | 28 Jun 2025 | P21 |  | Wendyng started shear link installation
Sat (28/06) | 28 Jun 2025 | BR31 |  | Casting in progress, 90/210m3. Waiting for next truck
Sat (28/06) | 28 Jun 2025 | P6-2 |  | Shear link installation for pier footing
Sat (28/06) | 28 Jun 2025 | S2 |  | Lowering down mini to resume excavation
Sat (28/06) | 28 Jun 2025 | P43/44 |  | No activity
Sat (28/06) | 28 Jun 2025 | Blk 4 |  | Starhub MH hacking completed. Now preparing to install temporary suppor
Sat (28/06) | 28 Jun 2025 | Blk 4 |  | No other activity
Sat (28/06) | 28 Jun 2025 | BR15A & 15B |  | Current status of excavation
Sat (28/06) | 28 Jun 2025 | BR16A |  | Top bar installation ongoing
Sat (28/06) | 28 Jun 2025 | PMH26 |  | Sideformwork and falsework erection
Sat (28/06) | 28 Jun 2025 | PMH28 |  | Drain hacking for removal
Sat (28/06) | 28 Jun 2025 | P45 |  | Preboring for soldier pile installation, 6nos done
Sat (28/06) | 28 Jun 2025 | DR3 |  | Continue grouting of JGP. Lefr 20nos to complete
Sat (28/06) | 28 Jun 2025 | PMH23 |  | Patch up at the base
Sat (28/06) | 28 Jun 2025 | P48 |  | No activity
Sat (28/06) | 28 Jun 2025 | P39 |  | Hacking of protruding concrete
Sat (28/06) | 28 Jun 2025 | P50 |  | Continue excavation for caisson
Sat (28/06) | 28 Jun 2025 | P51 |  | Boring for UKP
Sat (28/06) | 28 Jun 2025 | BR31 |  | Casting in progress, 168/210m3
Sat (28/06) | 28 Jun 2025 | BR31 |  | Casting in progress, 186m3
Sat (28/06) | 28 Jun 2025 | P20 |  | Barricade installation around working platform and formwork assembling
Sat (28/06) | 28 Jun 2025 | P21 |  | Crosshead level checking and piping work by woh hup
Sat (28/06) | 28 Jun 2025 | BR15A |  | Partial lean con was done. Balance excavation and levelling works ongoing
Sat (28/06) | 28 Jun 2025 | Exit 3 DW16 |  | Drilling ongoing for couplers (Dongah)
Sat (28/06) | 28 Jun 2025 | Exit 3 |  | Drilling ongoing for couplers (CGW)
Sat (28/06) | 28 Jun 2025 | BR14 |  | Currently no activity
Sat (28/06) | 28 Jun 2025 | BR15B |  | Excavation in progress
Sat (28/06) | 28 Jun 2025 | BR16A |  | Continue rebar works
Sat (28/06) | 28 Jun 2025 | P14 |  | Stressing work. Today to complete
Sat (28/06) | 28 Jun 2025 | P16 |  | Access erection by woh hup
Mon (30/06) | 30 Jun 2025 | BR15B |  | Lean con casting ongoing
Mon (30/06) | 30 Jun 2025 | GL E3-E5 |  | Decking installation work;, GL E5-E7: Excavation to Dwall COL
Mon (30/06) | 30 Jun 2025 | CCE4 |  | Excavation to roof level
Mon (30/06) | 30 Jun 2025 | Exit 2 status |  | Hammer test done for 4 nos. RC stumps, tomorrow start rebar works
Mon (30/06) | 30 Jun 2025 | P7-2 |  | Backfilling to column stump level in progress
Mon (30/06) | 30 Jun 2025 | P19 |  | LSS backfilling completed
Mon (30/06) | 30 Jun 2025 | P20 |  | Base Formwork installation in progress
Mon (30/06) | 30 Jun 2025 | P21 |  | Crosshead to cast today
Mon (30/06) | 30 Jun 2025 | BR14 |  | No activity
Mon (30/06) | 30 Jun 2025 | BR15B |  | Preparing for lean concrete casting
Mon (30/06) | 30 Jun 2025 | BR16A |  | Rebar adjustments ongoing
Mon (30/06) | 30 Jun 2025 | Exit 2 |  | Surveyor works. No other activity. Tmr plan to hack guidewall
Mon (30/06) | 30 Jun 2025 | GL8-9 |  | No activity
Mon (30/06) | 30 Jun 2025 | Near blk 4 |  | Netting installation for new designated walking access
Mon (30/06) | 30 Jun 2025 | BR10 |  | Continue rebar works
Mon (30/06) | 30 Jun 2025 | Near blk 4/Lincstech |  | No activity
Mon (30/06) | 30 Jun 2025 | BR31/CCE2 |  | No activity
Mon (30/06) | 30 Jun 2025 | CCE4 |  | Continue excavation
Tue (01/07) | 01 Jul 2025 | BR15B |  | Lean con cast
Tue (01/07) | 01 Jul 2025 | BR16A |  | No activity
Tue (01/07) | 01 Jul 2025 | P21 |  | Crosshead casting
Tue (01/07) | 01 Jul 2025 | PMH25-26 |  | Today will cast around 24.5m
Tue (01/07) | 01 Jul 2025 | PMH26 |  | Manhole wall rebar work
Tue (01/07) | 01 Jul 2025 | PMH29 |  | Ley Choon exposing water pipe for CCTV inspection
Tue (01/07) | 01 Jul 2025 | PMH28 |  | ERSS work
Tue (01/07) | 01 Jul 2025 | P21 |  | Crosshead cast yesterday. Curing works now
Tue (01/07) | 01 Jul 2025 | P20 |  | Crosshead Wingform Formwork installation
Tue (01/07) | 01 Jul 2025 | P19 |  | Curing ongoing for crosshead ground foundation works
Tue (01/07) | 01 Jul 2025 | P15 |  | Preparation for tonight segment launching works
Tue (01/07) | 01 Jul 2025 | N4 |  | Side formwork closing for stitching works. Today to cast
Tue (01/07) | 01 Jul 2025 | S2 |  | Setting up for lateral load test
Tue (01/07) | 01 Jul 2025 | BR10 |  | Continue coupler tightening works & formwork closing
Tue (01/07) | 01 Jul 2025 | CCE4 |  | Continue excavation
Tue (01/07) | 01 Jul 2025 | P7-2 |  | ERSS extraction ongoing
Tue (01/07) | 01 Jul 2025 | P7-1 |  | LE boring rig assembly ongoing
Tue (01/07) | 01 Jul 2025 | P6-2 |  | Pile cap cast yesterday
Tue (01/07) | 01 Jul 2025 | Bet. P6-2 & P7-2 |  | Singtel cable splicing works ongoing
Tue (01/07) | 01 Jul 2025 | P50 |  | Excavation done for 3rd layer caisson. Preparing for caisson rebar work
Tue (01/07) | 01 Jul 2025 | P49 |  | Excavation for 3rd layer caisson
Tue (01/07) | 01 Jul 2025 | P48 |  | Exposing water pipe for support
Tue (01/07) | 01 Jul 2025 | DR3 |  | TT for pipe sleeves installation.Balance 7nos to complete
Tue (01/07) | 01 Jul 2025 | P45 |  | Unloading of soldier piles materials
Tue (01/07) | 01 Jul 2025 | P1 |  | SPPG cables spiked
Tue (01/07) | 01 Jul 2025 | P2 |  | ERSS extraction ongoing, today to complete
Tue (01/07) | 01 Jul 2025 | Zone 1 |  | Hoarding shifting for ATS works tmr
Tue (01/07) | 01 Jul 2025 | P2 |  | Tunnel IM drilling and installation ongoing. Balance 2 nos. IM at zone 1
Tue (01/07) | 01 Jul 2025 | P5 |  | Falsework dismantling in progress
Tue (01/07) | 01 Jul 2025 | GL E5-E7 |  | Continues excavation to Dwall COL
Tue (01/07) | 01 Jul 2025 | CCE4 |  | Continues excavation to roof level & soil disposal
Tue (01/07) | 01 Jul 2025 | P45 |  | Preboring done 11/17nos
Tue (01/07) | 01 Jul 2025 | BR16A |  | Rebar works and formwork support installation in progress
Tue (01/07) | 01 Jul 2025 | CCW W7-8 |  | Continue excavation
Tue (01/07) | 01 Jul 2025 | N4 stitching formwork completed |  | Tonight will cast after last bus
Tue (01/07) | 01 Jul 2025 | 600T crane |  | Preparation for shifting. Tonight plan to install segment at P15 down chainage
Tue (01/07) | 01 Jul 2025 | P14 NB up chainage |  | Lifting frame installed
Tue (01/07) | 01 Jul 2025 | Exit 2 |  | No activity
Tue (01/07) | 01 Jul 2025 | S2 |  | Lateral load test set up. Jack installed. Balance instruments to install
Tue (01/07) | 01 Jul 2025 | BR10 |  | Rebars, shearlinks installation in progress
Tue (01/07) | 01 Jul 2025 | Blk 4 |  | No activity
Tue (01/07) | 01 Jul 2025 | CCE4 |  | Continue excavation
Wed (02/07) | 02 Jul 2025 | P21 |  | No activity
Wed (02/07) | 02 Jul 2025 | P20 |  | 1 side Formwork installation in progress
Wed (02/07) | 02 Jul 2025 | P19 |  | Ground preparation for falsework installation
Wed (02/07) | 02 Jul 2025 | P15 |  | Spreader beam shifting for tonight segment launching
Wed (02/07) | 02 Jul 2025 | P15 |  | Segment adjustment ongoing
Wed (02/07) | 02 Jul 2025 | N4 |  | Segment stitching cast yesterday
Wed (02/07) | 02 Jul 2025 | N3 |  | Falsework erection for segment launching
Wed (02/07) | 02 Jul 2025 | P14 |  | 1/4 nos. of lifting frame installed
Wed (02/07) | 02 Jul 2025 | P50 |  | Starter bar bending for caisson work
Wed (02/07) | 02 Jul 2025 | PMH24 |  | Clearing materials. Tomorrow to start excavation
Wed (02/07) | 02 Jul 2025 | P49 |  | Excavation for 3rd layer caisson
Wed (02/07) | 02 Jul 2025 | P49 |  | Remove of JGP grout below caisson
Wed (02/07) | 02 Jul 2025 | P48 |  | Exposing service by woh hup
Wed (02/07) | 02 Jul 2025 | DR3 |  | JGP left 4 points to complete
Wed (02/07) | 02 Jul 2025 | P45 |  | Preboring on going. 12/17nos done
Wed (02/07) | 02 Jul 2025 | S2 |  | Lateral load test setting up. Target to complete set up today
Wed (02/07) | 02 Jul 2025 | P7-2 |  | ERSS extraction ongoing
Wed (02/07) | 02 Jul 2025 | P7-1 |  | Preparation to start Preboring for ERSS today
Wed (02/07) | 02 Jul 2025 | P6-2 |  | Preparation for column rebar cage fabrication
Wed (02/07) | 02 Jul 2025 | P5 |  | Falsework dismantling
Wed (02/07) | 02 Jul 2025 | P2 |  | ERSS extraction completed
Wed (02/07) | 02 Jul 2025 | P2 |  | Tunnel IM installation works
Wed (02/07) | 02 Jul 2025 | N4 |  | Crane set up for casting
Wed (02/07) | 02 Jul 2025 | P15 NB D01 |  | Spreader beam installation for launching
Wed (02/07) | 02 Jul 2025 | BR10 |  | Shearlinks installation
Wed (02/07) | 02 Jul 2025 | BR14, BR16A |  | No activity
Wed (02/07) | 02 Jul 2025 | P15 NB D01 |  | Launching completed
Wed (02/07) | 02 Jul 2025 | P15 SB D-01 |  | Installation of spreader beam for launching
Wed (02/07) | 02 Jul 2025 | P20 |  | 1 side formwork installation ongoing
Wed (02/07) | 02 Jul 2025 | P15 |  | Spreader beam shifting ongoing
Wed (02/07) | 02 Jul 2025 | P15 |  | Segment adjustment in progress
Wed (02/07) | 02 Jul 2025 | N3 |  | Falsework erection current status
Wed (02/07) | 02 Jul 2025 | S2 |  | Continue set up of lateral load test
Wed (02/07) | 02 Jul 2025 | P7-2 |  | ERSS extraction, today to complete
Wed (02/07) | 02 Jul 2025 | P7-1 |  | Removing of abandoned services for Preboring works
Wed (02/07) | 02 Jul 2025 | P6-1 |  | Rebar installation for column stump
Wed (02/07) | 02 Jul 2025 | P6-1 |  | Setting up for Column rebar fabrication
Wed (02/07) | 02 Jul 2025 | P2 - P3 |  | Removal of Premix and RCA for lane lowering
Wed (02/07) | 02 Jul 2025 | P5 |  | Falsework dismantling in progress
Wed (02/07) | 02 Jul 2025 | P2 |  | Tunnel IM installation
Wed (02/07) | 02 Jul 2025 | BR10 |  | Rebar works completed. Now wire tying and pending cleaning. Final inspection will be done soon
Wed (02/07) | 02 Jul 2025 | CCE4 |  | Continue excavation
Thu (03/07) | 03 Jul 2025 | P15 |  | Alignment in progress and preparation for stressing cage installation
Thu (03/07) | 03 Jul 2025 | P14 |  | Lifter installation to continue tonight
Thu (03/07) | 03 Jul 2025 | P15 |  | Stitching formwork assembly
Thu (03/07) | 03 Jul 2025 | S2 |  | Lateral load test in progress. 25% loading
Thu (03/07) | 03 Jul 2025 | S1 |  | Crane setting up for material shifting
Thu (03/07) | 03 Jul 2025 | P7-1 |  | Today only to start preboring
Thu (03/07) | 03 Jul 2025 | P7-1 |  | Concrete block installation..plan to install rebar cage today
Thu (03/07) | 03 Jul 2025 | PMH28 |  | ERSS installation
Thu (03/07) | 03 Jul 2025 | PMH26-28 |  | Woh hup clearing materials
Thu (03/07) | 03 Jul 2025 | PMH25 |  | Wee Guan clearing materials to start work
Thu (03/07) | 03 Jul 2025 | PMH26 |  | To cast today
Thu (03/07) | 03 Jul 2025 | P50 |  | Starter bar bending
Thu (03/07) | 03 Jul 2025 | PMH29 |  | Steel plate lowering for slope protection
Thu (03/07) | 03 Jul 2025 | P49 |  | Continue excavation for caisson work
Thu (03/07) | 03 Jul 2025 | P48 |  | Two workers exposing services
Thu (03/07) | 03 Jul 2025 | P46 |  | JGP testing work
Thu (03/07) | 03 Jul 2025 | P45 |  | Preboring left 3nos to complete
Thu (03/07) | 03 Jul 2025 | DR3 |  | TT for soldier pile installation
Thu (03/07) | 03 Jul 2025 | GL E5-E7 |  | Continue excavation/hacking to Dwall COL
Thu (03/07) | 03 Jul 2025 | CCE4 |  | Continues excavation & soil disposal to roof level
Thu (03/07) | 03 Jul 2025 | BR31 |  | Formwork installation for temporary ECM pond
Thu (03/07) | 03 Jul 2025 | GL E3-E5 |  | Decking installation progress
Thu (03/07) | 03 Jul 2025 | Zone 1 |  | Excavation for road level lowering
Thu (03/07) | 03 Jul 2025 | P20 |  | Continue scaffold support installation for rebar works
Thu (03/07) | 03 Jul 2025 | P19 |  | Ground preparation works for falsework ongoing
Thu (03/07) | 03 Jul 2025 | P15 |  | Stressing cage installation ongoing. 1/4 nos. installed
Thu (03/07) | 03 Jul 2025 | N3 |  | Falsework erection and platform making for segment launching
Thu (03/07) | 03 Jul 2025 | P14 |  | Stressing cage shifting to P15 area
Thu (03/07) | 03 Jul 2025 | PMH28 |  | Excavation and ERSS installation. Need to extend 3m to complete
Thu (03/07) | 03 Jul 2025 | S2 |  | Lateral load test in progress. 12.5% unloading - 1st cycle
Thu (03/07) | 03 Jul 2025 | S1 |  | Materials shifting to P19
Thu (03/07) | 03 Jul 2025 | P7-1 |  | Preboring for ERSS in progress
Thu (03/07) | 03 Jul 2025 | P6-2 |  | Rebar cage fabrication
Thu (03/07) | 03 Jul 2025 | P6-2 |  | Formwork closing for 1st lift column
Thu (03/07) | 03 Jul 2025 | P1 |  | RG trial trench works for next tunnel IM
Thu (03/07) | 03 Jul 2025 | P2 |  | ATS road realignment works ongoing
Thu (03/07) | 03 Jul 2025 | P48 |  | Checking on utility support
Thu (03/07) | 03 Jul 2025 | P48 |  | Continue utility support work
Thu (03/07) | 03 Jul 2025 | P49 |  | KTC continue excavation
Thu (03/07) | 03 Jul 2025 | P50 |  | Caisson rebar work
Thu (03/07) | 03 Jul 2025 | PMH26 |  | Casting in progress
Thu (03/07) | 03 Jul 2025 | P45 |  | Preboring for last 3 points
Thu (03/07) | 03 Jul 2025 | P46 |  | Coring test
Thu (03/07) | 03 Jul 2025 | DR3 |  | Premix removal for TT
Thu (03/07) | 03 Jul 2025 | DR3 |  | Starhub removal of abandoned cables
Thu (03/07) | 03 Jul 2025 | P43 |  | Woh hup clearing materials and barricade
Thu (03/07) | 03 Jul 2025 | P19 |  | Platform prepare for crosshead
Thu (03/07) | 03 Jul 2025 | P20 |  | Rebar lifting up to cross head platform for rebar work
Thu (03/07) | 03 Jul 2025 | Testing in progress. Cycle 2 |  | Load applied: 100%. Holding time is 3hrs. 9.12mm settle as of now
Thu (03/07) | 03 Jul 2025 | P6-2 |  | Stump formwork closing and column rebar work
Thu (03/07) | 03 Jul 2025 | Zone 1 |  | ATS premix removal
Thu (03/07) | 03 Jul 2025 | DR3 |  | Woh hup premix removal for TT
Thu (03/07) | 03 Jul 2025 | P49 |  | KTC continue excavation for 3rd layer caisson
Fri (04/07) | 04 Jul 2025 | P19 |  | Hardcore laying
Fri (04/07) | 04 Jul 2025 | GL E3-E5 |  | Continues decking installation work
Fri (04/07) | 04 Jul 2025 | N4 |  | Strand pulling for tensioning works
Fri (04/07) | 04 Jul 2025 | P15 |  | Segment adjusting in progress
Fri (04/07) | 04 Jul 2025 | BR31 |  | Continues formwork installation for temporary ECM pond
Fri (04/07) | 04 Jul 2025 | CCE4 |  | Continues excavation to roof level & soil disposal
Fri (04/07) | 04 Jul 2025 | GL E5-E7 |  | Excavation has reached Dwall COL & continues arrange for soil disposal
Fri (04/07) | 04 Jul 2025 | JTC Blk 4 |  | Continue preparing for fissure grouting while waiting for generator & pressure pump to be fixed
Fri (04/07) | 04 Jul 2025 | P20 |  | Crosshead rebar installation
Fri (04/07) | 04 Jul 2025 | P19 |  | Ground foundation levelling and compaction works
Fri (04/07) | 04 Jul 2025 | P15 |  | Segment adjustment ongoing
Fri (04/07) | 04 Jul 2025 | Bet. P14-P15 |  | Movable hoarding fabrication ongoing
Fri (04/07) | 04 Jul 2025 | N3 |  | Falsework erection & Platform making for segment launching
Fri (04/07) | 04 Jul 2025 | N4 |  | Preparation works for stressing
Fri (04/07) | 04 Jul 2025 | S2 |  | Lateral load test materials removal ongoing
Fri (04/07) | 04 Jul 2025 | P7-2 |  | Column rebar cage installation and lapping ongoing
Fri (04/07) | 04 Jul 2025 | P7-1 |  | Preboring for ERSS in progress
Fri (04/07) | 04 Jul 2025 | P6-2 |  | Column rebar cage fabrication
Fri (04/07) | 04 Jul 2025 | P6-2 |  | 1st lift column preparation for casting today
Fri (04/07) | 04 Jul 2025 | P3 |  | PLT test completed
Fri (04/07) | 04 Jul 2025 | P2-P3 |  | Continue lane lowering works
Fri (04/07) | 04 Jul 2025 | P1 |  | RG Tunnel IM drilling works. To complete next week
Fri (04/07) | 04 Jul 2025 | PMH28 |  | ERSS and shoring installation to complete today. Base lean concrete to cast today
Fri (04/07) | 04 Jul 2025 | PMH26 |  | Top neck wall formwork closing. To cast today
Fri (04/07) | 04 Jul 2025 | PMH25 |  | PLT test ongoing
Fri (04/07) | 04 Jul 2025 | P50 |  | 3rd layer caisson wall rebar works installation
Fri (04/07) | 04 Jul 2025 | P49 |  | Excavation works for 3rd layer caisson
Fri (04/07) | 04 Jul 2025 | P46 |  | GCE Coring works in progress for Point C17
Fri (04/07) | 04 Jul 2025 | P45 |  | LE Preboring for ERSS completed
Sat (05/07) | 05 Jul 2025 | P51 |  | No activity
Sat (05/07) | 05 Jul 2025 | PMH25 |  | Excavation and ERSS
Sat (05/07) | 05 Jul 2025 | P50 |  | Rebar works for L3 caisson
Sat (05/07) | 05 Jul 2025 | P49 |  | Excavation work to L3 caisson level
Sat (05/07) | 05 Jul 2025 | P48 |  | Welding utility support
Sat (05/07) | 05 Jul 2025 | DR3 |  | Shifting JGP machinery and batching plant to PMH29, target to start JGP on Monday
Sat (05/07) | 05 Jul 2025 | P51 |  | Preparation work for soldier pile preboring
Sat (05/07) | 05 Jul 2025 | P46 |  | Instrument installation, waiting cable detection
Sat (05/07) | 05 Jul 2025 | P43 |  | No activity
Sat (05/07) | 05 Jul 2025 | P2-P3 |  | Continue lane lowering works
Sat (05/07) | 05 Jul 2025 | P6-2 |  | Column rebar work ongoing..1st lift column casting going to start now, concrete truck just arrive
Sat (05/07) | 05 Jul 2025 | P7-2 |  | Column rebar installation
Sat (05/07) | 05 Jul 2025 | N4 |  | Segment’s formwork dismantling in progress
Sat (05/07) | 05 Jul 2025 | P14 |  | No activity
Sat (05/07) | 05 Jul 2025 | P13 |  | Lifter frame assembling work on going
Sat (05/07) | 05 Jul 2025 | P20 |  | Crosshead rebar installation work
Sat (05/07) | 05 Jul 2025 | P21 |  | No activity
Sat (05/07) | 05 Jul 2025 | P20 |  | Crosshead rebar installation work
Sat (05/07) | 05 Jul 2025 | P15 |  | Segment adjustment..Lifting work finish
Sat (05/07) | 05 Jul 2025 | P14 |  | Currently no activity. Winch will be unload today
Sat (05/07) | 05 Jul 2025 | P7-2 |  | Column formwork closing
Sat (05/07) | 05 Jul 2025 | P6-2 |  | 1st lift column casting completed
Sat (05/07) | 05 Jul 2025 | P7-1 |  | Preboring no work
Sat (05/07) | 05 Jul 2025 | P6-2 |  | Column rebar works on going
Sat (05/07) | 05 Jul 2025 | P45 |  | Soldier pile installation
Sat (05/07) | 05 Jul 2025 | P48 |  | Utility support welding work on going
Sat (05/07) | 05 Jul 2025 | P48 |  | Pile hacking by woh hup
Sat (05/07) | 05 Jul 2025 | P50 |  | L3 rebar caisson work
Sat (05/07) | 05 Jul 2025 | PMH25 |  | Excavation and ERSS
Sat (05/07) | 05 Jul 2025 | PMH26 |  | Backfilling work
Sat (05/07) | 05 Jul 2025 | PMH28 |  | Lowering precast manhole
Mon (07/07) | 07 Jul 2025 | P20 crosshead |  | Steel anchor and anti burst link installation in progress
Mon (07/07) | 07 Jul 2025 | P20 crosshead |  | Box girder rebar installation in progress
Mon (07/07) | 07 Jul 2025 | P19 |  | Falsework erection for crosshead construction
Mon (07/07) | 07 Jul 2025 | P15 |  | 1st pair segment adjusting in progress
Mon (07/07) | 07 Jul 2025 | P14 |  | Preparation for winch installation at lifting frame. Today target to install at Upchainage
Mon (07/07) | 07 Jul 2025 | PMH28 |  | Complete casting base slab
Mon (07/07) | 07 Jul 2025 | P50 |  | Preparing work access for PMH25. L3 caisson (north side) 15m going to cast today
Mon (07/07) | 07 Jul 2025 | P14 SB Upchainage |  | Winch installed safely
Mon (07/07) | 07 Jul 2025 | P45 |  | Machinery check before proceed steel plate installation
Mon (07/07) | 07 Jul 2025 | DR3 |  | Trial Trench for soldier piles
Mon (07/07) | 07 Jul 2025 | 300 water pipe |  | Official CCTV completed. All Pass. Currently backfilling
Mon (07/07) | 07 Jul 2025 | P48 |  | No activity
Mon (07/07) | 07 Jul 2025 | P49 |  | Levelling for L3. Today going to bring down materials for L3 caisson work
Mon (07/07) | 07 Jul 2025 | N3 D-01 |  | Falsework installation for segment launching tonight
Mon (07/07) | 07 Jul 2025 | P7-2 |  | Column formwork closing. To cast tomorrow
Mon (07/07) | 07 Jul 2025 | P7-1 |  | Preboring for ERSS, 50% completed
Mon (07/07) | 07 Jul 2025 | BR31 |  | Dismantling of formwork for temporary ECM pond
Mon (07/07) | 07 Jul 2025 | CCE4 |  | Continues excavation to roof level & soil disposal
Mon (07/07) | 07 Jul 2025 | PMH29 |  | Shifted the JGP grouting rig. Tentatively to start grouting work tomorrow
Mon (07/07) | 07 Jul 2025 | PMH28 |  | Wall and base stitching casting done
Mon (07/07) | 07 Jul 2025 | GL E4.5-E7 |  | Steel beam installation for traffic deck
Mon (07/07) | 07 Jul 2025 | GL E7-E9 |  | Ongoing excavation to Dwall COL
Mon (07/07) | 07 Jul 2025 | P1 |  | Drilling for piezometer installation
Mon (07/07) | 07 Jul 2025 | BR10 |  | Surface roughening for wall rebar area, Wall rebar works on progress
Mon (07/07) | 07 Jul 2025 | PMH25 |  | Manual excavation for ERSS installation
Mon (07/07) | 07 Jul 2025 | P50 |  | 3rd layer caisson casting (1st part)
Mon (07/07) | 07 Jul 2025 | Near BR6 | Selarang side | Exposing deck posts (4nos)
Mon (07/07) | 07 Jul 2025 | P48 |  | Excavation completed for 3rd layer caisson. Now levelling and will handover to RC contractor
Mon (07/07) | 07 Jul 2025 | DR3 |  | Trial trench and confirming of services
Mon (07/07) | 07 Jul 2025 | Exit 2 |  | Stump rebar works in progress
Mon (07/07) | 07 Jul 2025 | S1-1 |  | Excavation for utility support in progress
Mon (07/07) | 07 Jul 2025 | CCW W5-7 |  | S3 excavation in progress
Mon (07/07) | 07 Jul 2025 | BR14 |  | Rebar works and formwork installation ongoing
Mon (07/07) | 07 Jul 2025 | BR15B |  | KP endplate welding work ongoing
Mon (07/07) | 07 Jul 2025 | BR15A |  | 1nos KP endplate welding completed. Area backfilled
Mon (07/07) | 07 Jul 2025 | BR15A & BR15B |  | Levelling ongoing at balance area for lean con. Tonight plan for lean con casting
Mon (07/07) | 07 Jul 2025 | P20 |  | Crosshead rebar work for side and maintenance access area
Mon (07/07) | 07 Jul 2025 | P19 |  | Falsework erection for crosshead
Mon (07/07) | 07 Jul 2025 | CCE4 |  | Current status of excavation
Mon (07/07) | 07 Jul 2025 | GL E4.5-7 |  | Steel beam welding works ongoing
Mon (07/07) | 07 Jul 2025 | GL E7-9 |  | Hacking ongoing to dwall COL & stockpile disposal ongoing
Mon (07/07) | 07 Jul 2025 | P7 |  | Preboring work stop for the night
Mon (07/07) | 07 Jul 2025 | P7-2 |  | Preparing for barricade installation for casting platform
Mon (07/07) | 07 Jul 2025 | BR10 |  | Housekeeping. Wendyng working till 8pm
Mon (07/07) | 07 Jul 2025 | Zone 1 |  | Pad footing casting done
Mon (07/07) | 07 Jul 2025 | BR14 |  | Continue rebar works and formwork installation
Mon (07/07) | 07 Jul 2025 | CCW W5-7 |  | S3 excavation in progress
Mon (07/07) | 07 Jul 2025 | P50 |  | Caisson 1st part casting done
Mon (07/07) | 07 Jul 2025 | P49 |  | Levelling for 3rd layer caisson
Mon (07/07) | 07 Jul 2025 | PMH28 |  | Lean concrete around PMH and tidy up work area
Tue (08/07) | 08 Jul 2025 | P21 |  | Side formwork dismantling started
Tue (08/07) | 08 Jul 2025 | P20 crosshead |  | Section 1 PT duct inspection completed. Links installation in progress
Tue (08/07) | 08 Jul 2025 | P19 crosshead falsework |  | Secondary beam installation on going
Tue (08/07) | 08 Jul 2025 | CCE4 |  | Status for excavation to roof level
Tue (08/07) | 08 Jul 2025 | GL E4.5-E7 |  | Continues steel decking installation
Tue (08/07) | 08 Jul 2025 | P14 LF |  | All winch sets installed
Tue (08/07) | 08 Jul 2025 | P15 |  | Segment 1st pair adjustment in progress. Upchainage plan to complete by today
Tue (08/07) | 08 Jul 2025 | P7-2 |  | 2nd stage column casting in progress
Wed (09/07) | 09 Jul 2025 | Zone 1 |  | Lane 2 premix hacking for road lowering. Balance less than 10m span to hack and lower
Wed (09/07) | 09 Jul 2025 | CCE4 |  | Hacking of Dwall is in progress
Wed (09/07) | 09 Jul 2025 | BR10 |  | 1st lift retaining wall rebar tying ongoing, Partial roof slab formwork dismantled
Wed (09/07) | 09 Jul 2025 | Blk 4 | north side | Drilling ongoing for fissure grouting works. Today plan 5nos — O-206, O-208, O-210, O-212, O-214, Opp blk 4 (south side):, 4nos grouting completed — O-169, O-171, O-173, O-175
Wed (09/07) | 09 Jul 2025 | Z3 | GL28 south side | Dwall hacking to COL in progress
Wed (09/07) | 09 Jul 2025 | P6-2 |  | LSS backfilling to pile cap level. Tmr 2nd layer of concrete plug to cast
Wed (09/07) | 09 Jul 2025 | P7-1 |  | Last pre-boring for SP in progress. Tmr to start SP and LP installation
Wed (09/07) | 09 Jul 2025 | BR14 |  | Parapet wall rebar works, rebar tying and formwork closing in progress
Wed (09/07) | 09 Jul 2025 | BR16A |  | Formwork dismantling ongoing
Wed (09/07) | 09 Jul 2025 | CCW W5-7 |  | S3 excavation in progress
Wed (09/07) | 09 Jul 2025 | GL E4.5-7 |  | Has finished excavation & handed over Hirose for decking work
Wed (09/07) | 09 Jul 2025 | GL E9-E7 |  | Ongoing excavation & soil disposal
Wed (09/07) | 09 Jul 2025 | N3 |  | 1st pair segment adjustment started
Wed (09/07) | 09 Jul 2025 | N4 |  | 1st pair segment stressing completed. Tonight to install N4 U-02
Wed (09/07) | 09 Jul 2025 | P19 |  | Falsework main beam cross bracing installation in progress
Wed (09/07) | 09 Jul 2025 | P21 crosshead |  | Formwork dismantling in progress
Thu (10/07) | 10 Jul 2025 | JTC Blk 4/North side |  | Preparation work to start for RW58
Thu (10/07) | 10 Jul 2025 | CCE4 |  | Continues hacking of Dwall
Thu (10/07) | 10 Jul 2025 | CCW W5-7 |  | S3 excavation
Thu (10/07) | 10 Jul 2025 | BR10 |  | Rebar works for retaining wall in progress, Scaffold erection ongoing for upper lift rebar works
Thu (10/07) | 10 Jul 2025 | Opp blk 4 | Selarang side | Drilling ongoing for fissure grouting works — O-168
Thu (10/07) | 10 Jul 2025 | GL E4.5-7 |  | Steel stump & beam installation for decking
Thu (10/07) | 10 Jul 2025 | GL E7-E9 |  | Ongoing excavation & soil disposal
Thu (10/07) | 10 Jul 2025 | Exit 1 |  | Removing of silo/desander platform
Thu (10/07) | 10 Jul 2025 | JTC BlK 4 | North side | Fissure grouting has completed for O-210, O-212 & O-214 this morning
Thu (10/07) | 10 Jul 2025 | S-1-2 |  | GL5-7, Excavation and manual digging for utility support in progress
Thu (10/07) | 10 Jul 2025 | P21 |  | Crosshead formwork dismantling in progress
Thu (10/07) | 10 Jul 2025 | P20 |  | Crosshead rebars and tendon ducts installation
Thu (10/07) | 10 Jul 2025 | P19 |  | Netting and falsework installation for crosshead ongoing
Thu (10/07) | 10 Jul 2025 | P15 |  | Segment adjustment completed. PVC pipes installation prior to commence of stitching formwork. Tmr to start Formwork installation for stitching
Thu (10/07) | 10 Jul 2025 | P7-1 |  | ERSS installation in progress. To complete by sat
Thu (10/07) | 10 Jul 2025 | PMH29 |  | 1st JGP grouting done
Thu (10/07) | 10 Jul 2025 | PMH28 |  | Wall and top slab rebar work. Tomorrow to cast. 2/7nos of manhole cast as of today
Thu (10/07) | 10 Jul 2025 | GL E7-E9 |  | Continue excavation & soil disposal
Thu (10/07) | 10 Jul 2025 | CCE4 |  | Continue excavation & disposal
Thu (10/07) | 10 Jul 2025 | P51 |  | HSL boring rig demob from site
Thu (10/07) | 10 Jul 2025 | PMH25 |  | Excavation and ERSS installation work
Thu (10/07) | 10 Jul 2025 | PMH26 to PMH28 |  | Excavation and ERSS for 22KV duct laying
Thu (10/07) | 10 Jul 2025 | P50 |  | Formwork closing for 3rd layer caisson. Tomorrow will complete casting for 3rd layer (100%)
Thu (10/07) | 10 Jul 2025 | P45 |  | Soldier pile installation completed. Steel plates left 4nos to complete. Tomorrow to complete all
Thu (10/07) | 10 Jul 2025 | DR3 |  | TT to confirm services location for ERSS installation
Thu (10/07) | 10 Jul 2025 | P43& P44 |  | Segregation of hard core and soil. Cutting down the soil for stump construction started
Thu (10/07) | 10 Jul 2025 | BR13 |  | Balance portion rebar works in progress
Thu (10/07) | 10 Jul 2025 | CCW W5 |  | S3 excavation in progress
Thu (10/07) | 10 Jul 2025 | BR10 |  | Continue retaining wall rebar works
Thu (10/07) | 10 Jul 2025 | GL28 | Selarang side | Continue dwall hacking to COL
Thu (10/07) | 10 Jul 2025 | CCE1 |  | Continue soil disposal
Thu (10/07) | 10 Jul 2025 | GL7-8 |  | Beam installation for utility support works
Thu (10/07) | 10 Jul 2025 | BR14 |  | Final inspection ongoing
Thu (10/07) | 10 Jul 2025 | BR15A |  | Debonding sheet laying and rebar works
Fri (11/07) | 11 Jul 2025 | PMH28 |  | Shear link and side formwork closing. Today plan to cast
Fri (11/07) | 11 Jul 2025 | PMH29 |  | 4/20nos JGP grouting done. Today target 5nos
Fri (11/07) | 11 Jul 2025 | PMH26-PMH28 |  | Continue excavation and ERSS for duct laying
Fri (11/07) | 11 Jul 2025 | P51 |  | HSL clearing materials and will demob from site
Fri (11/07) | 11 Jul 2025 | PMH25 |  | Continue clearing stagnant water. Today will continue hardcore laying for the base
Fri (11/07) | 11 Jul 2025 | P50 |  | Caisson formwork support installation for 3rd layer. Today will cast and complete 100% for 3rd layer
Fri (11/07) | 11 Jul 2025 | P49 |  | Caisson rebar at TPE bound side done. Continue with the rest of area. Total 7 rebar workers
Fri (11/07) | 11 Jul 2025 | P45 |  | Steel plate left 3nos to complete. Today LE will complete and shift out machinery and materials to give way for excavation work
Fri (11/07) | 11 Jul 2025 | P46 |  | Ryobi G doing TT and hand augering for inclinometer and water stand pipe work
Fri (11/07) | 11 Jul 2025 | DR3 |  | Testing rig shift back from P51. Today will resume JGP test for ERSS work
Fri (11/07) | 11 Jul 2025 | P21 |  | Bottom formwork dismantling
Fri (11/07) | 11 Jul 2025 | P20 |  | Rebars & Tendon ducts installation ongoing
Fri (11/07) | 11 Jul 2025 | P14 |  | Preparation for Lifter - spreader beam installation
Fri (11/07) | 11 Jul 2025 | N4 |  | Strands installation for stressing works ongoing
Fri (11/07) | 11 Jul 2025 | P7-1 |  | ERSS installation. To complete by sat
Fri (11/07) | 11 Jul 2025 | BR10 |  | Continue retaining wall rebar works & dewatering
Fri (11/07) | 11 Jul 2025 | GL28 | Selarang side | Hacking works done. Disposal has been arranged
Fri (11/07) | 11 Jul 2025 | Blk 4 |  | Seongha: Drilling ongoing for fissure grouting work at north side. Today plan 6 points. At south side, grouting works ongoing. Today plan 4nos, Geomotion: Manual trial pit in progress for RW60. Today plan to start drilling for RW58
Fri (11/07) | 11 Jul 2025 | GL7-8 |  | Preparing for welding works for utility support
Fri (11/07) | 11 Jul 2025 | P44 |  | Lean concrete done for column stump. Now installation of hard barricade
Fri (11/07) | 11 Jul 2025 | P43 |  | Clear of hardcore and excavation for stump
Fri (11/07) | 11 Jul 2025 | GL E7-E9 |  | Continues excavation & soil disposal
Fri (11/07) | 11 Jul 2025 | GL E3-E5 |  | MPI test for stiffener plates
Fri (11/07) | 11 Jul 2025 | CCE4 |  | Pumping out of water
Fri (11/07) | 11 Jul 2025 | PMH29 |  | JGP grouting, 9/22nos completed
Fri (11/07) | 11 Jul 2025 | P51 |  | Going to boom down boring rig and demob from site. Techinician already on site
Fri (11/07) | 11 Jul 2025 | PMH25 |  | Hardcore laying at the base
Fri (11/07) | 11 Jul 2025 | P50 |  | Formwork support installed. concrete ordered for 3rd layer caisson casting
Fri (11/07) | 11 Jul 2025 | P21 |  | Continue formwork dismantling
Fri (11/07) | 11 Jul 2025 | P20 |  | Shear links installation in progress
Fri (11/07) | 11 Jul 2025 | P19 |  | Falsework & railing installation ongoing
Fri (11/07) | 11 Jul 2025 | N4 |  | Stressing works in progress
Fri (11/07) | 11 Jul 2025 | P7-1 |  | ERSS installation
Sat (12/07) | 12 Jul 2025 | BR13 Balanced slab |  | Cleaning in progress, planning to cast it today
Sat (12/07) | 12 Jul 2025 | P21 |  | Box girder formwork dismantling and preparation for stressing works
Sat (12/07) | 12 Jul 2025 | P20 |  | Shear links and tendon ducts installation ongoing
Sat (12/07) | 12 Jul 2025 | P19 |  | Netting installation for railing in progress
Sat (12/07) | 12 Jul 2025 | P18 |  | Tunnel IM works ongoing
Sat (12/07) | 12 Jul 2025 | P15 |  | Inner formwork for stitching - installation in progress at SB
Sat (12/07) | 12 Jul 2025 | BR15A |  | Bottom bar installation in progress
Sat (12/07) | 12 Jul 2025 | BR15B |  | Laying of debinding sheet in progress
Sat (12/07) | 12 Jul 2025 | P14 LF |  | Wire rope installation in progress for spreader beam installation
Sat (12/07) | 12 Jul 2025 | S2 |  | Pile cap rebar works commenced
Sat (12/07) | 12 Jul 2025 | P7-1 |  | ERSS installation in progress. To complete today
Sat (12/07) | 12 Jul 2025 | CCW1 |  | South site, Clearing of excavated soil in progress
Sat (12/07) | 12 Jul 2025 | S1-2 |  | GL5-8, Excavation, manual digging & utility support work in progress
Sat (12/07) | 12 Jul 2025 | Exit 2 |  | Excavation for utility support in progress
Sat (12/07) | 12 Jul 2025 | BR10 |  | Continues rebar installation for retaining wall
Sat (12/07) | 12 Jul 2025 | PMH28 |  | Neck formwork and rebar installation ongoing. Today to cast
Sat (12/07) | 12 Jul 2025 | PMH29 |  | JGP grouting, 11/22nos completed
Sat (12/07) | 12 Jul 2025 | P50 |  | Strutting installation for 3rd layer cassion wall
Sat (12/07) | 12 Jul 2025 | P49 |  | 3rd layer cassion wall rebar and Formwork closing works
Sat (12/07) | 12 Jul 2025 | P45 |  | LE ERSS materials shifting works to DR3 area
Sat (12/07) | 12 Jul 2025 | P44 |  | Hard barricades installed for column stump works. Afternoon to start rebar works
Sat (12/07) | 12 Jul 2025 | JTC Blk 4 |  | Drilling in progress for RW58
Sat (12/07) | 12 Jul 2025 | GL E7-E9 |  | Continues excavation & soil disposal
Sat (12/07) | 12 Jul 2025 | GL E5-E7 |  | Metro decks has been delivered on site
Sat (12/07) | 12 Jul 2025 | CCE4 |  | Hacking of Dwall has completed
Sat (12/07) | 12 Jul 2025 | BR30 |  | Excavation in progress
Sat (12/07) | 12 Jul 2025 | RS Waler 1 |  | Shear link & formwork installation in progress
Sat (12/07) | 12 Jul 2025 | Exit 1 |  | Continue removal of silo/desander platform
Sat (12/07) | 12 Jul 2025 | BR13 balanced slab |  | Final inspection has cleared, going to cast it later
Sat (12/07) | 12 Jul 2025 | P44 |  | Rebar installation ongoing for column stump
Sat (12/07) | 12 Jul 2025 | BR15A / BR15B |  | Continues bottom bar installation & debonding sheet laying repectively
Sat (12/07) | 12 Jul 2025 | BR16A |  | Roughening of the slab surface in progress
Sat (12/07) | 12 Jul 2025 | P46 |  | LE materials shifting works in progress
Sat (12/07) | 12 Jul 2025 | PMH28 |  | Neck wall Formwork and rebar installation completed. Concrete ordered for casting
Sat (12/07) | 12 Jul 2025 | PMH29 |  | JGP grouting, 13/22nos completed
Sat (12/07) | 12 Jul 2025 | S1-1 & S1-2 |  | Continues excavation & manual digging work for utility support
Sat (12/07) | 12 Jul 2025 | BR10 retaining wall |  | Rebar installation & backfilling work in progress
Sat (12/07) | 12 Jul 2025 | JTC Blk 4/DR2 |  | Fissure grouting in progress: O-219, O-217 & I-161, Drilling in progress for I-157
Sat (12/07) | 12 Jul 2025 | P7-1 |  | ERSS installation completed. KTC preparation for excavation works to s1 layer
Sat (12/07) | 12 Jul 2025 | S2 |  | Rebar installation for pile cap in progress
Sat (12/07) | 12 Jul 2025 | GL E7-E9 |  | Continues excavation & expose of deck post
Sat (12/07) | 12 Jul 2025 | P14 |  | Wire rope for spread beam installation ongoing
Sat (12/07) | 12 Jul 2025 | P15 |  | Formwork installation for stitching in progress
Sat (12/07) | 12 Jul 2025 | P20 |  | Formwork closing for 1 section of crosshead
Sat (12/07) | 12 Jul 2025 | P21 |  | Preparation for crosshead stressing works
Sun (13/07) | 13 Jul 2025 | BR10 |  | Inner fomwork installation for retaining wall in progress, Outer part pending scaffold installation for working platform. Yesterday backfilled and cast lean con
Sun (13/07) | 13 Jul 2025 | Blk 4 |  | Geomotion no activity today
Sun (13/07) | 13 Jul 2025 | CCE | GL-E5 | Preparing for decking beam works
Sun (13/07) | 13 Jul 2025 | BR30 & CCE4 |  | No activity
Sun (13/07) | 13 Jul 2025 | GL-E5 |  | KTC ground preparation for access making
Sun (13/07) | 13 Jul 2025 | Exit 1 |  | Debris disposal at previous desander area
Sun (13/07) | 13 Jul 2025 | GL5-8 |  | Current status of utility support works
Sun (13/07) | 13 Jul 2025 | Exit 2 |  | Continue exposing utility alignment near decking area
Sun (13/07) | 13 Jul 2025 | BR15A, BR15B |  | Continue rebar works
Sun (13/07) | 13 Jul 2025 | BR10 |  | Continue inner formwork installation for retaining wall
Sun (13/07) | 13 Jul 2025 | GL E5 |  | Bracing installation for decking works
Sun (13/07) | 13 Jul 2025 | CCW W5 |  | No activity
Mon (14/07) | 14 Jul 2025 | PMH28 |  | Formwork removal for completed manhole. 3/6nos completed
Mon (14/07) | 14 Jul 2025 | PMH26-PMH28 |  | ERSS installation for Power duct laying
Mon (14/07) | 14 Jul 2025 | P50 |  | Left 6 struts to complete for 2nd layer. Thursday to complete
Mon (14/07) | 14 Jul 2025 | PMH25 |  | Precast segment lowering. Today to complete
Mon (14/07) | 14 Jul 2025 | GL E7-E9 |  | Soil segregation & disposal
Mon (14/07) | 14 Jul 2025 | GL E5-E7 |  | Beam installation in progress for decking
Mon (14/07) | 14 Jul 2025 | GL E3-E5 |  | Excavation & soil disposal in progress
Mon (14/07) | 14 Jul 2025 | Exit 1 |  | Continue removing of silo/desander platform
Mon (14/07) | 14 Jul 2025 | P45-46 |  | Excavation for 800mm dia water pipe laying started
Mon (14/07) | 14 Jul 2025 | 300mm dia portable water pipe |  | PUB officer will officially approved on CCTV report and allow to start flushing work tomorrow. Work already arranged to start tomorrow
Mon (14/07) | 14 Jul 2025 | RS Waler 1 |  | Welding for the top bar in progress, target to cast it tomorrow
Mon (14/07) | 14 Jul 2025 | CCE4 |  | Has started exposing of couplers
Mon (14/07) | 14 Jul 2025 | P21 |  | Crosshead stressing preparation works ongoing
Mon (14/07) | 14 Jul 2025 | P20 |  | Tendon ducts & rebar installation in progress
Mon (14/07) | 14 Jul 2025 | P19 |  | Side formwork installation ongoing
Mon (14/07) | 14 Jul 2025 | P15 |  | Stitching Formwork installation ongoing. Target to cast tmr
Mon (14/07) | 14 Jul 2025 | P7-2 |  | Column Formwork dismantled
Mon (14/07) | 14 Jul 2025 | P44 |  | Stump rebar completed
Mon (14/07) | 14 Jul 2025 | P44 |  | Platform prepare for column rebar cage fabrication
Mon (14/07) | 14 Jul 2025 | S1-1, S1-2 |  | Continue excavation below decking and manual excavation for utility support works
Mon (14/07) | 14 Jul 2025 | BR15A, BR15B |  | Rebar works in progress
Mon (14/07) | 14 Jul 2025 | BR10 |  | Retaining wall rebar works (inner) & outer part working platform erection in progress
Mon (14/07) | 14 Jul 2025 | GL E5-E7 |  | Continue decking beam installation
Mon (14/07) | 14 Jul 2025 | GL E3-E5 |  | Excavation in progress
Mon (14/07) | 14 Jul 2025 | RS waler 1 |  | Continue of top bar in progress
Mon (14/07) | 14 Jul 2025 | CCE4 |  | Continue exposing couplers
Mon (14/07) | 14 Jul 2025 | Blk 4 | GL26-27 | Excavation for utility support started today
Tue (15/07) | 15 Jul 2025 | BR10 |  | Continue working platform erection at outer side & inner formwork installation ongoing
Tue (15/07) | 15 Jul 2025 | Blk 4 | GL25-26 | KTC continue excavation to facilitate utility support works
Tue (15/07) | 15 Jul 2025 | GL E3-5 |  | Excavation in progress
Tue (15/07) | 15 Jul 2025 | GL E5-7 |  | Decking welding works ongoing
Tue (15/07) | 15 Jul 2025 | RS waler 1 |  | RTO inspection
Tue (15/07) | 15 Jul 2025 | CCE4 |  | Continue exposing couplers
Tue (15/07) | 15 Jul 2025 | Blk 4 Geomotion |  | 1/4nos recharge wells completed. Today to start drilling for next point. Now ongoing manual trial trench
Tue (15/07) | 15 Jul 2025 | S1-1,S-2 |  | Continue excavating below decking & manual excavation below utility alignment
Tue (15/07) | 15 Jul 2025 | BR15A, BR15B |  | Rebar works in progress
Tue (15/07) | 15 Jul 2025 | BR10 |  | Retaining wall rebar inspection
Tue (15/07) | 15 Jul 2025 | P21 |  | Crosshead Stressing works in progress
Tue (15/07) | 15 Jul 2025 | P20 |  | Cast in items installation ongoing. Crosshead target to cast on Thurs
Tue (15/07) | 15 Jul 2025 | P19 |  | Scaffold erection for crosshead rebars and tendon ducts work in progress
Tue (15/07) | 15 Jul 2025 | P15 |  | Stitching formwork installation ongoing. Target to cast today
Tue (15/07) | 15 Jul 2025 | GL E8-E9 |  | Has finished exposing of deck posts
Tue (15/07) | 15 Jul 2025 | GL E5-E8 |  | Beam installation in progress for the decking
Tue (15/07) | 15 Jul 2025 | GL E3-E5 |  | Excavation for BR30 is in progress
Tue (15/07) | 15 Jul 2025 | Blk 4 |  | Geomotion drilling ongoing for recharge well, 2/4nos
Tue (15/07) | 15 Jul 2025 | Exit 1 |  | Status for the removal of silo/desander platform
Tue (15/07) | 15 Jul 2025 | RS Waler 1 |  | Final inspection has cleared & concrete pump arrived site for the casting, estimated volume 245m3
Tue (15/07) | 15 Jul 2025 | P6-2 |  | Manual backfilling works ongoing for ERSS removal
Tue (15/07) | 15 Jul 2025 | PMH29 |  | JGP works ongoing
Tue (15/07) | 15 Jul 2025 | PMH28 |  | Going to backfill after inspection
Tue (15/07) | 15 Jul 2025 | PMH25 |  | Casting base slab
Tue (15/07) | 15 Jul 2025 | P50 |  | S2 strut welding ongoing
Tue (15/07) | 15 Jul 2025 | P49 |  | L3 caisson (mid) formwork closing
Tue (15/07) | 15 Jul 2025 | P49 |  | L3 caisson (north) casting
Tue (15/07) | 15 Jul 2025 | DR3 |  | Trial Trench for soldier pile
Tue (15/07) | 15 Jul 2025 | P45 |  | Excavation on going
Tue (15/07) | 15 Jul 2025 | P44 |  | Column rebar works ongoing
Wed (16/07) | 16 Jul 2025 | P21 |  | Continue crosshead stressing works
Wed (16/07) | 16 Jul 2025 | P20 |  | Rebars installation for parapet wall ongoing
Wed (16/07) | 16 Jul 2025 | P19 |  | Crosshead Rebars installation
Wed (16/07) | 16 Jul 2025 | P15 |  | Stitching Formwork cast last night
Wed (16/07) | 16 Jul 2025 | P45-P46 |  | Excavation and ERSS installation for 800mm dia water pipe laying
Wed (16/07) | 16 Jul 2025 | P45 |  | Top soil removal and clearing. New access provided
Wed (16/07) | 16 Jul 2025 | P46 |  | TT on going for JGP testing
Wed (16/07) | 16 Jul 2025 | P48 |  | As of now no activity
Wed (16/07) | 16 Jul 2025 | P49 |  | Formwork removal for completed caisson. Last part of caisson for 3rd layer will complete casting today. Plan to cast after lunch
Wed (16/07) | 16 Jul 2025 | PMH45 |  | Materials clearing for 22KV mamhole construction work
Wed (16/07) | 16 Jul 2025 | BR10 |  | Continue inner formwork installation
Wed (16/07) | 16 Jul 2025 | Blk 4 | GL25-26 | Continue excavation for utility supports works
Wed (16/07) | 16 Jul 2025 | PMH26-28 |  | Excavation and ERSS for power duct laying
Wed (16/07) | 16 Jul 2025 | P50 |  | S2 strut installation completed. Today to complete welding. Tomorrow MPI test. String guage installed
Wed (16/07) | 16 Jul 2025 | PMH25 |  | Prop concrete casting around manhole
Wed (16/07) | 16 Jul 2025 | GL E5-E8 |  | Contines beam installation for decking
Wed (16/07) | 16 Jul 2025 | GL E3-E5 |  | Continues excavation for BR30
Wed (16/07) | 16 Jul 2025 | Exit 1 |  | Continues removal of silo/desander platform
Wed (16/07) | 16 Jul 2025 | CCE4 |  | Continues exposing of couplers
Wed (16/07) | 16 Jul 2025 | S1 |  | Preboring for ERSS in progress
Wed (16/07) | 16 Jul 2025 | P7-1 |  | Welding in progress for strutting. MPI test at 1pm
Wed (16/07) | 16 Jul 2025 | P6-2 |  | Backfilling completed. Preparation for Waler and struts removal
Wed (16/07) | 16 Jul 2025 | P50 |  | S2 layer strut welding completed
Wed (16/07) | 16 Jul 2025 | PMH25 |  | Side wall formwork closing
Wed (16/07) | 16 Jul 2025 | PMH26-28 |  | Excavation and ERSS for 22KV duct laying
Wed (16/07) | 16 Jul 2025 | PMH28 |  | Housekeeping before backfilling
Wed (16/07) | 16 Jul 2025 | PMH29 |  | JGP grouting completed. Going to demob back the rig to P47
Wed (16/07) | 16 Jul 2025 | BR10 |  | Continue retaining wall formwork installation
Wed (16/07) | 16 Jul 2025 | P21 |  | Stressing completed. Strand cutting ongoing
Wed (16/07) | 16 Jul 2025 | GL27-28 , BR8B | Selarang side | Trial trench ongoing to expose utilities
Wed (16/07) | 16 Jul 2025 | BR30 |  | Excavation in progress
Wed (16/07) | 16 Jul 2025 | Blk 4 |  | Geomotion has completed installation for RW60. Current status 2/4nos recharge well done. Now preparing platform for next point
Wed (16/07) | 16 Jul 2025 | P20 |  | Formwork closing in progress
Wed (16/07) | 16 Jul 2025 | P19 |  | Rebars installation in progress
Wed (16/07) | 16 Jul 2025 | P15 |  | Tunnel IM installation works
Wed (16/07) | 16 Jul 2025 | P14 SB D02 |  | Preparation for load test tmr
Wed (16/07) | 16 Jul 2025 | P6-2 |  | Waler and strutting removal works
Wed (16/07) | 16 Jul 2025 | P6-2 |  | Tunnel IM installation
Wed (16/07) | 16 Jul 2025 | P7-1 |  | Excavation to FEL in progress
Wed (16/07) | 16 Jul 2025 | P49 |  | L3 caisson casting
Wed (16/07) | 16 Jul 2025 | DR3 |  | Trial Trench for coring point
Wed (16/07) | 16 Jul 2025 | BR15B |  | Rebar works in progress
Wed (16/07) | 16 Jul 2025 | S1-2 |  | Excavation for utility supports works in progress
Wed (16/07) | 16 Jul 2025 | BR10 |  | Retaining wall formwork installation in progress
Wed (16/07) | 16 Jul 2025 | CCE4 |  | Continue exposing couplers
Wed (16/07) | 16 Jul 2025 | Blk 4 | GL25-26 | Current status of excavation for utility support works
Thu (17/07) | 17 Jul 2025 | BR31 |  | Status quo
Thu (17/07) | 17 Jul 2025 | BR30 |  | Excavation ongoing
Thu (17/07) | 17 Jul 2025 | P43 |  | FYI WH plan to park the telescopic arm here to continue excavation for W2 at RS. 2 nos of IM affected too
Thu (17/07) | 17 Jul 2025 | GL E8-E9 |  | Has exposed deck post
Thu (17/07) | 17 Jul 2025 | GL E5-E8 |  | Continues decking work in progress
Thu (17/07) | 17 Jul 2025 | P3 |  | Excavation and levelling for P3 falsework footing work
Thu (17/07) | 17 Jul 2025 | PMH26-PMH28 |  | Preparing for pipe laying (12m)
Thu (17/07) | 17 Jul 2025 | P49 |  | S2 strut installation
Thu (17/07) | 17 Jul 2025 | PMH24 |  | Excavation and ERSS
Thu (17/07) | 17 Jul 2025 | P48 |  | Installation of working platform and access
Thu (17/07) | 17 Jul 2025 | P45 |  | Excavation to expose utilities
Thu (17/07) | 17 Jul 2025 | P7 |  | Current status of excavation using long arm
Thu (17/07) | 17 Jul 2025 | S2 |  | Stump rebar inspection
Thu (17/07) | 17 Jul 2025 | S1 |  | LE preparing to change kelly bar for the rig
Thu (17/07) | 17 Jul 2025 | P6-2 |  | Ryobi G boring for RX. Reaching toe level now
Thu (17/07) | 17 Jul 2025 | N4 |  | Tonight will launch one segment
Thu (17/07) | 17 Jul 2025 | N3 |  | Segement adjusting done
Thu (17/07) | 17 Jul 2025 | P15 |  | Preparation for stressing. Formwork for stitching will shift over N3 once cube test result achieve
Thu (17/07) | 17 Jul 2025 | P14 |  | 2/4nos load test done. Today will complete the balance two load test
Thu (17/07) | 17 Jul 2025 | P19 |  | Crosshead top rebar installation work
Thu (17/07) | 17 Jul 2025 | CCE4 |  | Continues exposing of couplers
Thu (17/07) | 17 Jul 2025 | Exit 1 |  | Continues removing of silo/desander platform
Thu (17/07) | 17 Jul 2025 | P20 |  | Adjusting of crosshead formwork support. Tomorrow target to cast this crosshead
Thu (17/07) | 17 Jul 2025 | P21 |  | Clearing polyfoam around duct. Tomorrow will start dismantling of falsework
Thu (17/07) | 17 Jul 2025 | PMH29 |  | GCE demobbing JGP rig, grouting machine and container
Thu (17/07) | 17 Jul 2025 | PMH28 |  | Backfilling around manhole
Thu (17/07) | 17 Jul 2025 | P21 |  | Clearing polyfoam around duct
Thu (17/07) | 17 Jul 2025 | P20 |  | Adjusting of crosshead formwork support
Thu (17/07) | 17 Jul 2025 | P19 |  | Crosshead rebar installation work
Thu (17/07) | 17 Jul 2025 | N4 |  | Segment stressing
Thu (17/07) | 17 Jul 2025 | P15 |  | Preparation for stressing
Thu (17/07) | 17 Jul 2025 | P14 |  | 2/4nos load test done (upchainage). Today will complete the balance two load test (downchainage)
Thu (17/07) | 17 Jul 2025 | P7 |  | Excavation on going
Thu (17/07) | 17 Jul 2025 | S2 |  | Stump formwork closing
Thu (17/07) | 17 Jul 2025 | P6-2 |  | Backfilling on going
Thu (17/07) | 17 Jul 2025 | P3 |  | No activity
Thu (17/07) | 17 Jul 2025 | Zone 1 |  | Lane 2 completed, going to open lane
Thu (17/07) | 17 Jul 2025 | BR10 |  | Continue retaining wall formwork installation
Thu (17/07) | 17 Jul 2025 | P50 |  | Long arm shifted. Preparing to lower down mini. Tomorrow to start excavation for 4th layer caisson
Thu (17/07) | 17 Jul 2025 | PMH25 |  | Wall and top slab rebar work. Target to cast this week
Thu (17/07) | 17 Jul 2025 | PMH26-28 |  | Power duct laying in progress, 16m length
Thu (17/07) | 17 Jul 2025 | P49 |  | Overall housekeeping and clearing materials to fully handover the area to LE for struting work
Thu (17/07) | 17 Jul 2025 | P49 |  | 2nos of Diagonal strut installed
Thu (17/07) | 17 Jul 2025 | PMH24 |  | Excavation and ERSS for manhole and duct laying work
Thu (17/07) | 17 Jul 2025 | P48 |  | Current status of platform erection for utility support
Thu (17/07) | 17 Jul 2025 | P45 |  | Exposing of UKP for utility support installation
Thu (17/07) | 17 Jul 2025 | P45-46 |  | Clearing abandoned pipe for 800mm dia water pipe laying
Thu (17/07) | 17 Jul 2025 | DR3 |  | JGP 1st coring point work in progress
Thu (17/07) | 17 Jul 2025 | P43 |  | Clearing of materials and access preparation for receiving shaft excavation
Thu (17/07) | 17 Jul 2025 | P44 |  | Column rebar cage fabrication. To install by this week
Thu (17/07) | 17 Jul 2025 | BR15 |  | Rebar works and adjusting the planks
Thu (17/07) | 17 Jul 2025 | Exit 2 |  | Stump formwork installation
Thu (17/07) | 17 Jul 2025 | BR10 |  | Continue retaining wall formwork installation
Thu (17/07) | 17 Jul 2025 | BR30 |  | Excavation in progress
Thu (17/07) | 17 Jul 2025 | CCE4 |  | Preparing working platform to continue exposing of couplers
Thu (17/07) | 17 Jul 2025 | P20 |  | Final inspection done for crosshead. Tomorrow morning start casting
Thu (17/07) | 17 Jul 2025 | P19 |  | Crosshead top rebar work
Thu (17/07) | 17 Jul 2025 | P14 |  | All the 4nos load test done. Tonight plan for this 4 segments launch here
Thu (17/07) | 17 Jul 2025 | N4 |  | Tonight plan to launch one segement also
Thu (17/07) | 17 Jul 2025 | Blk 4 | GL25-26 | Excavation & soil disposal for utility support
Thu (17/07) | 17 Jul 2025 | Zone 1 |  | No activity already. Lane opened back to public
Thu (17/07) | 17 Jul 2025 | P7 |  | KTC already end work. Current status of excavation
Thu (17/07) | 17 Jul 2025 | S2 |  | Stump formwork closed
Thu (17/07) | 17 Jul 2025 | DR4 |  | Clearing materials and housekeeping
Thu (17/07) | 17 Jul 2025 | PMH25 |  | No activity already
Thu (17/07) | 17 Jul 2025 | P51 |  | Tomorrow to start 4th layer excavation for caisson
Thu (17/07) | 17 Jul 2025 | DR3 |  | GCE tidy up area before go back
Thu (17/07) | 17 Jul 2025 | P43 |  | Barricade installation around column stump
Fri (18/07) | 18 Jul 2025 | P20 |  | Preparation for crosshead casting. Briefing ongoing prior casting works
Fri (18/07) | 18 Jul 2025 | Blk 4 | GL26 | Access installation for instrument monitoring
Fri (18/07) | 18 Jul 2025 | Blk 4 |  | Geomotion plan to complete 3rd point recharge well today. As to date, 2/4nos completed
Fri (18/07) | 18 Jul 2025 | P19 |  | Crosshead Rebar installation
Fri (18/07) | 18 Jul 2025 | P14 |  | 4 nos. of segments launched last night
Fri (18/07) | 18 Jul 2025 | S1 |  | Preboring for ERSS in progress
Fri (18/07) | 18 Jul 2025 | P7-1 |  | Excavation to FEL. Scaffold access erection and shifting ongoing
Fri (18/07) | 18 Jul 2025 | P6-2 |  | Preparation for column rebar installation
Fri (18/07) | 18 Jul 2025 | P44 |  | Column rebar fabrication on going
Fri (18/07) | 18 Jul 2025 | P45 |  | Excavation to expose utilities
Fri (18/07) | 18 Jul 2025 | 800 water pipe |  | Excavation and erss
Fri (18/07) | 18 Jul 2025 | DR3 |  | Coring test on going
Fri (18/07) | 18 Jul 2025 | P48 |  | Installation of water pipe support
Fri (18/07) | 18 Jul 2025 | P49 |  | S2 strut installation
Fri (18/07) | 18 Jul 2025 | PMH24 |  | Excavation and erss
Fri (18/07) | 18 Jul 2025 | PMH25 |  | Manhole rebar installation
Fri (18/07) | 18 Jul 2025 | PMH26-28 |  | Power duct casting in progress, 16m length
Fri (18/07) | 18 Jul 2025 | PMH28 |  | Backfilling and removal of ERSS
Fri (18/07) | 18 Jul 2025 | RS / P43 |  | No activity. Pending excavation for RS
Fri (18/07) | 18 Jul 2025 | P20 |  | Crosshead casting in progress
Fri (18/07) | 18 Jul 2025 | P19 |  | Crosshead rebar installation
Fri (18/07) | 18 Jul 2025 | P14 |  | Stressing cage shifting and installation ongoing
Fri (18/07) | 18 Jul 2025 | S2 |  | Column stump to cast today
Fri (18/07) | 18 Jul 2025 | Bet. P7-P8 |  | Tunnel IM trial trench works
Fri (18/07) | 18 Jul 2025 | S1 |  | Preboring for ERSS in progress. Target to complete this week
Fri (18/07) | 18 Jul 2025 | P7-1 |  | Excavation to FEL
Fri (18/07) | 18 Jul 2025 | P6-2 |  | Preparation for column rebar cage installation. Today will install
Fri (18/07) | 18 Jul 2025 | BR15A, BR15B |  | Continue rebar works. Partial formwork installation started at BR15B area
Fri (18/07) | 18 Jul 2025 | Exit 2 |  | 2nos stumps formwork completed. Waiting for casting
Fri (18/07) | 18 Jul 2025 | Exit 2 |  | Dongah preparing hacking of dwall guidewall — DW41-43
Fri (18/07) | 18 Jul 2025 | P45 |  | Exposing UKP and soil shifting
Fri (18/07) | 18 Jul 2025 | 800mm dia |  | Continue excavation and ERSS work
Fri (18/07) | 18 Jul 2025 | DR3 |  | Rig repair done. Shifting of stockpile to do 2nd coring point testing
Fri (18/07) | 18 Jul 2025 | P48 |  | LE continue utility support installation. Target mid of next week to complete
Fri (18/07) | 18 Jul 2025 | P49 |  | 5/15nos struts installed. Target next Wednesday to complete
Fri (18/07) | 18 Jul 2025 | PMH25 |  | Continue excavation and ERSS for duct laying and manhole work
Fri (18/07) | 18 Jul 2025 | P50 |  | Excavation for 4th layer caisson. Early next week to complete
Fri (18/07) | 18 Jul 2025 | PMH25 |  | Preparing for formwork closing. Tomorrow to cast
Fri (18/07) | 18 Jul 2025 | GL25-26 |  | Continue excavation for utility support
Fri (18/07) | 18 Jul 2025 | Blk 4 |  | Geomotion has completed 3/4nos. Tomorrow to continue for last point
Fri (18/07) | 18 Jul 2025 | BR10 |  | Continue retaining wall formwork installation
Fri (18/07) | 18 Jul 2025 | S1-2 |  | Secondary beam installation for utility support works in progress
Fri (18/07) | 18 Jul 2025 | P20 |  | Crosshead casting completed
Fri (18/07) | 18 Jul 2025 | P19 |  | Continue crosshead rebar work. 9 workers
Fri (18/07) | 18 Jul 2025 | P14 |  | Preparing to lift up stressing cage on lifter
Fri (18/07) | 18 Jul 2025 | S2 |  | Stump casting done. Now housekeeping
Fri (18/07) | 18 Jul 2025 | P7 |  | KTC continue excavation to FEL
Fri (18/07) | 18 Jul 2025 | P6-2 |  | Column rebar cage installation
Fri (18/07) | 18 Jul 2025 | P49 |  | Strut installation and strut end welding
Fri (18/07) | 18 Jul 2025 | P49 |  | Utility support welding by LE
Fri (18/07) | 18 Jul 2025 | P44 |  | No activity already
Fri (18/07) | 18 Jul 2025 | Exit 1 |  | Backfilling of existing ECM pond & excavation to expose dwall alignment
Fri (18/07) | 18 Jul 2025 | BR30 |  | Removal of barrette pile & exposing dwall coupler ongoing. partial lean con also completed
Fri (18/07) | 18 Jul 2025 | BR15A, BR15B |  | Continue rebar works
Fri (18/07) | 18 Jul 2025 | Exit 2 |  | Stump formwork fabrication in progress
Fri (18/07) | 18 Jul 2025 | BR10 |  | Continue retaining wall formwork installation
Sat (19/07) | 19 Jul 2025 | P21 |  | Bottom formwork dismantling
Sat (19/07) | 19 Jul 2025 | P20 |  | Crosshead cast yesterday
Sat (19/07) | 19 Jul 2025 | P19 |  | Crosshead rebar installation
Sat (19/07) | 19 Jul 2025 | N4 |  | Tendon Strands installation for U05 and D05 segment. To stress today
Sat (19/07) | 19 Jul 2025 | P14 |  | SB stressing cage installed. Tendon strands installation in progress
Sat (19/07) | 19 Jul 2025 | S2 |  | Column rebar cage fabrication
Sat (19/07) | 19 Jul 2025 | S2 |  | Column stump cast yesterday. Pile cap formwork dismantling in progress
Sat (19/07) | 19 Jul 2025 | S1 |  | Preboring for ERSS in progress
Sat (19/07) | 19 Jul 2025 | P7-1 |  | Excavation to FEL ongoing. Today to complete
Sat (19/07) | 19 Jul 2025 | BR10 |  | Retaining wall formwork closing ongoing
Sat (19/07) | 19 Jul 2025 | GL28-29 | Selarang side | KTC slope trimming and disposal
Sat (19/07) | 19 Jul 2025 | BR30 |  | Exposing couplers below decking & disposal works ongoing
Sat (19/07) | 19 Jul 2025 | CCE4 |  | Continue exposing couplers
Sat (19/07) | 19 Jul 2025 | P44 |  | Column rebar cage fabrication ongoing. Today to complete
Sat (19/07) | 19 Jul 2025 | PMH25 |  | Wall and slab formwork closing in progress. Today to cast
Sat (19/07) | 19 Jul 2025 | P50 |  | Excavation for 4th layer cassion wall ongoing
Sat (19/07) | 19 Jul 2025 | PMH24 |  | Excavation and shoring for PMH ongoing
Sat (19/07) | 19 Jul 2025 | P49 |  | Strutting works ongoing for 3rd layer
Sat (19/07) | 19 Jul 2025 | P48 |  | Utility supports works ongoing
Sat (19/07) | 19 Jul 2025 | Zone 4, DR3 |  | GCE coring test in progress
Sat (19/07) | 19 Jul 2025 | Bet. P45-P46 |  | Excavation and shoring works for 800mm water pipe
Sat (19/07) | 19 Jul 2025 | P45 |  | Excavation for 1st layer cassion
Sat (19/07) | 19 Jul 2025 | BR15 |  | Continue rebar works, formwork installation
Sat (19/07) | 19 Jul 2025 | Exit 2 |  | Dongah continue guidewall hacking, 2nos stump formwork removal
Sat (19/07) | 19 Jul 2025 | BR10 |  | Continue retaining wall formwork installation
Sat (19/07) | 19 Jul 2025 | BR3 & 4 |  | Starter bar planting for retaining wall in progress
Sat (19/07) | 19 Jul 2025 | GL28-29 | Selarang side | Drilling for decking stump
Sat (19/07) | 19 Jul 2025 | CCE4 |  | Coupler exposing temporarily stopped near soil disposal area
Sat (19/07) | 19 Jul 2025 | BR30 |  | Hacking of excess concrete and preparing for next section of lean con casting
Sat (19/07) | 19 Jul 2025 | CCE1 |  | Preparing top plate welding for deck posts
Sat (19/07) | 19 Jul 2025 | Blk 4 | GL25-26 | Soil disposal ongoing
Sat (19/07) | 19 Jul 2025 | P21 |  | Continue bottom formwork dismantling
Sat (19/07) | 19 Jul 2025 | P19 |  | Crosshead rebar installation
Sat (19/07) | 19 Jul 2025 | P15 |  | Stitching formwork dismantling
Sat (19/07) | 19 Jul 2025 | P14 |  | SB segment preparation for stressing works. Today to complete
Sat (19/07) | 19 Jul 2025 | N4 |  | Preparation for stressing works for U05/D05. Today to complete
Sat (19/07) | 19 Jul 2025 | S2 |  | Continue column rebar cage fabrication
Sat (19/07) | 19 Jul 2025 | S1 |  | Pile cap formwork dismantling
Sat (19/07) | 19 Jul 2025 | Bet. P8-P9 |  | Tunnel IM installation
Sat (19/07) | 19 Jul 2025 | S1 |  | Preboring for ERSS. Target to complete today
Sat (19/07) | 19 Jul 2025 | P7-1 |  | Ecavation to FEL and levelling in progress. Today to complete
Sat (19/07) | 19 Jul 2025 | P3 |  | Pad footing installation in progress
Sat (19/07) | 19 Jul 2025 | PMH26-PMH28 |  | Backfilling and shoring works ongoing
Sat (19/07) | 19 Jul 2025 | P50 |  | Excavation for 4th layer ongoing
Sat (19/07) | 19 Jul 2025 | PMH24 |  | Shoring works in progress
Sat (19/07) | 19 Jul 2025 | P49 |  | Strutting installation and welding works ongoing
Sat (19/07) | 19 Jul 2025 | P48 |  | Utility supports works
Sat (19/07) | 19 Jul 2025 | DR3 |  | Coring works in progress
Sat (19/07) | 19 Jul 2025 | P45-P46 |  | Excavation and shoring works for 800mm water pipe laying
Sat (19/07) | 19 Jul 2025 | P45 |  | Excavation for 1st layer in progress
Sat (19/07) | 19 Jul 2025 | P44 |  | Column rebar cage fabrication
Sat (19/07) | 19 Jul 2025 | P44 |  | Backfilling and levelling for column rebar cage installation
Sat (19/07) | 19 Jul 2025 | BR15B |  | Continue rebar works, preparing shearlinks, corrugated pipes and formwork, BR15A: Waiting for rebar delivery. Plan for today
Sat (19/07) | 19 Jul 2025 | CCW W5-7 |  | S3 currently no activity
Sat (19/07) | 19 Jul 2025 | GL5-7 |  | Utility beam support works & manual excavation below utilities
Sat (19/07) | 19 Jul 2025 | Exit 2 |  | Dongah guidewall hacking in progress, 2nos utility stump cast yesterday
Mon (21/07) | 21 Jul 2025 | BR10 RW |  | Current status
Mon (21/07) | 21 Jul 2025 | CCE 4 |  | Excavation beneath P40 started
Mon (21/07) | 21 Jul 2025 | CCE2 | P38 | I beam installation for construction deck ongoing
Mon (21/07) | 21 Jul 2025 | P6-2 |  | Column formwork closing
Mon (21/07) | 21 Jul 2025 | P7-1 |  | Pier rebar cage fabrication started
Mon (21/07) | 21 Jul 2025 | P7-1 |  | Pile head hacking started. Target top complete by Thursday and lean concrete
Mon (21/07) | 21 Jul 2025 | S1 |  | Pre-boring for ERSS completed. Preparing to shift rig for ERSS installation
Mon (21/07) | 21 Jul 2025 | P44 |  | Column rebar cage installation
Mon (21/07) | 21 Jul 2025 | P45 |  | Exposing of UKP for utility support installation
Mon (21/07) | 21 Jul 2025 | P14 |  | 2nd pair stressing completed. Strand cutting and grouting cap installation on going
Mon (21/07) | 21 Jul 2025 | P15 |  | 1st pair installation of hydraulic jack and preparation for stressing
Mon (21/07) | 21 Jul 2025 | DR3 |  | Pipe sleeve installation for SPT test
Mon (21/07) | 21 Jul 2025 | DR3 |  | SPT test in progress. Today to complete
Mon (21/07) | 21 Jul 2025 | P15 |  | Stitching formwork dismantling in progress
Mon (21/07) | 21 Jul 2025 | P50 |  | Excavation to 4th layer of caisson
Mon (21/07) | 21 Jul 2025 | PMH24 |  | Excavation and ERSS
Mon (21/07) | 21 Jul 2025 | PMH25 |  | Formwork for necking of manhole completed, going to cast today
Mon (21/07) | 21 Jul 2025 | P48 |  | LE continue utility support installation
Mon (21/07) | 21 Jul 2025 | P49 |  | S2 strut installation ongoing
Mon (21/07) | 21 Jul 2025 | P21 |  | Working platform & falsework dismantling
Mon (21/07) | 21 Jul 2025 | P19 |  | As of now no activity of ducting work
Mon (21/07) | 21 Jul 2025 | P14 |  | All stressing done. Now preparing to shift out stressing platform for next segment launching
Mon (21/07) | 21 Jul 2025 | N3 |  | Inner formwork for stitching done. Outter formwork will start after dinner break
Mon (21/07) | 21 Jul 2025 | P6-2 |  | Formwork closed for column. Boom lift break down. Tomorrow mechanic will come to repair
Mon (21/07) | 21 Jul 2025 | P7-1 |  | Current status of pile head hacking
Mon (21/07) | 21 Jul 2025 | P7-1 |  | Continue fabrication of column rebar cage
Mon (21/07) | 21 Jul 2025 | P44 |  | Rebar cage installation completed
Mon (21/07) | 21 Jul 2025 | P45-46 |  | Ley Choon continue excavation for water pipe laying
Mon (21/07) | 21 Jul 2025 | PMH24 |  | Wee Guan already end work
Tue (22/07) | 22 Jul 2025 | P44 |  | Column formwork closing
Tue (22/07) | 22 Jul 2025 | P45 |  | Exposing of UKP for utility support installation
Tue (22/07) | 22 Jul 2025 | P45-46 |  | Continue excavation for 800mm dia water pipe laying
Tue (22/07) | 22 Jul 2025 | DR3 |  | Last point of SPT in progress
Tue (22/07) | 22 Jul 2025 | P48 |  | Continue utility support installation. Tomorrow plan to start partial excavation
Tue (22/07) | 22 Jul 2025 | P49 |  | S2 layer struts welding done. Now prepare for MPI test
Tue (22/07) | 22 Jul 2025 | PMH24 |  | Preparing to lower down precast for the manhole
Tue (22/07) | 22 Jul 2025 | P50 |  | KTC partial handover the area to woh hup for pile head hacking
Tue (22/07) | 22 Jul 2025 | PMH25 |  | Clearing materials
Tue (22/07) | 22 Jul 2025 | P50 |  | Pile cap rebar delivery
Tue (22/07) | 22 Jul 2025 | P14 SB 3rd pair |  | Stressing in progress
Tue (22/07) | 22 Jul 2025 | CCE4 |  | Excavation in progress
Tue (22/07) | 22 Jul 2025 | Exit 1 |  | Clearing stockpile
Tue (22/07) | 22 Jul 2025 | P15 |  | Stitching formwork dismantled at SB. Tonight to complete NB side after last bus
Tue (22/07) | 22 Jul 2025 | P19 crosshead section 1 |  | PT duct installation. Tomorrow inspection for links installation
Tue (22/07) | 22 Jul 2025 | Blk 4 |  | Geomotion has completed the last recharge well point, 4/4nos. Now clearing materials from the area. Tmr will expedite the pipe connection
Tue (22/07) | 22 Jul 2025 | GL25-26 |  | Currently no activity
Tue (22/07) | 22 Jul 2025 | BR10 |  | Retaining wall casting in progress, 90/186m3
Tue (22/07) | 22 Jul 2025 | PMH28 |  | ERSS removal and backfilling
Tue (22/07) | 22 Jul 2025 | PMH26-28 |  | Continue excavation and ERSS installation
Tue (22/07) | 22 Jul 2025 | PMH24 |  | Precast lowering. After this manhole, left only PMH29 to complete. Should not be any issue to handover to SPPG for cable pulling by 1st week of September
Tue (22/07) | 22 Jul 2025 | P45 |  | Bund wall making to lean concrete and install barricade around pile cap ERSS as fall prevention
Tue (22/07) | 22 Jul 2025 | P19 |  | Woh hup going for break
Tue (22/07) | 22 Jul 2025 | P14 |  | Stressing done. Tonight will adjust the stressing cage. Plan for two segment launch tonight
Tue (22/07) | 22 Jul 2025 | P15 |  | Tonight will lower down the stressing cage
Tue (22/07) | 22 Jul 2025 | N3 |  | Formwork closing done for stitching. Plan to cast tonight after last bus
Tue (22/07) | 22 Jul 2025 | BR15A |  | Continue rebar works, BR15B: Shearlinks installation & welding works ongoing
Tue (22/07) | 22 Jul 2025 | BR17 |  | Excavation and disposal in progress, GL5-7 (Area 3A): Utility support welding works in progress
Tue (22/07) | 22 Jul 2025 | P7 |  | Continue rebar cage fabrication for column
Tue (22/07) | 22 Jul 2025 | Blk 4 | GL25-27 | Continue excavation for utility support works
Tue (22/07) | 22 Jul 2025 | CCE4 |  | Excavation in progress
Tue (22/07) | 22 Jul 2025 | BR30 |  | Exposing couplers and surface cleaning
Tue (22/07) | 22 Jul 2025 | P44 |  | Column formwork installation in progress
Wed (23/07) | 23 Jul 2025 | P19 |  | PT ducts installation ongoing
Wed (23/07) | 23 Jul 2025 | P15 |  | Cage ladder installation for stressing cage
Wed (23/07) | 23 Jul 2025 | P15 |  | Lifting hanger to shift to P16 tonight
Wed (23/07) | 23 Jul 2025 | P14 |  | Tendon strands installation for NB side segment. Today to complete stressing
Wed (23/07) | 23 Jul 2025 | P9 |  | Tunnel IM installation
Wed (23/07) | 23 Jul 2025 | P7-1 |  | Pile head hacking in progress
Wed (23/07) | 23 Jul 2025 | P7-1 |  | Column rebar cage fabrication
Wed (23/07) | 23 Jul 2025 | BR3, BR4 |  | Retaining wall rebar and formwork installation. Tmr plan for casting, BR10: Retaining wall cast yesterday
Wed (23/07) | 23 Jul 2025 | Blk 4 | GL25 | Exposing utility alignment. Manual excavation will be done near utilities
Wed (23/07) | 23 Jul 2025 | CCE4 |  | Excavation in progress
Wed (23/07) | 23 Jul 2025 | BR30 |  | Surface cleaning
Wed (23/07) | 23 Jul 2025 | Blk 4 |  | Seongha setting up for post-lugeon test
Wed (23/07) | 23 Jul 2025 | PMH26-PMH-28 |  | Excavation and shoring works ongoing for pipe laying works
Wed (23/07) | 23 Jul 2025 | PMH24 |  | Preparation for rebar installation works
Wed (23/07) | 23 Jul 2025 | P50 |  | Excavation for 4th layer ongoing
Wed (23/07) | 23 Jul 2025 | DR3 |  | SPT-2 testing ongoing
Wed (23/07) | 23 Jul 2025 | P45 |  | Excavation for 800mm water pipe laying
Wed (23/07) | 23 Jul 2025 | P45 |  | Excavation of 1st layer for utility support works
Wed (23/07) | 23 Jul 2025 | P44 |  | Tie rod installation for column works
Wed (23/07) | 23 Jul 2025 | P19 crosshead |  | Section PT duct installation completed. Inspection later at 5pm
Wed (23/07) | 23 Jul 2025 | P44 |  | Column formwork closing to complete tonight. Preparing to install casting platform. To cast on Friday
Wed (23/07) | 23 Jul 2025 | CCE4 |  | Coupler exposure ongoing
Wed (23/07) | 23 Jul 2025 | P16 |  | Stressing cage dismantled from p15. Tonight to shift starter hanger here from P15
Wed (23/07) | 23 Jul 2025 | P14 NB 3rd pair |  | Stressing in progress
Wed (23/07) | 23 Jul 2025 | S1 ERSS |  | Soldier pile installation in progress
Wed (23/07) | 23 Jul 2025 | P45 |  | Removal of top soil to expose UKP
Wed (23/07) | 23 Jul 2025 | 800mm dia water pipe |  | Continue excavation for 800mm dia water pipe laying
Wed (23/07) | 23 Jul 2025 | DR3 |  | Materials clearing to handover to KTC to expose UKP for utility support
Wed (23/07) | 23 Jul 2025 | P48 |  | 4 welders + 2 workers working for utility support
Wed (23/07) | 23 Jul 2025 | P49 |  | Now no activity. Need to complete string gauage for KTC to start excavation
Wed (23/07) | 23 Jul 2025 | PMH24 |  | Formwork closing done for stitching
Wed (23/07) | 23 Jul 2025 | P50 |  | Woh hup pile head hacking
Wed (23/07) | 23 Jul 2025 | PMH26-28 |  | Continue excavation and ERSS for power duct laying
Wed (23/07) | 23 Jul 2025 | P6-2 |  | New boomlift on site. To resume formwork alignment and casting platform installation. Plan to cast tomorrow
Wed (23/07) | 23 Jul 2025 | P3 |  | In-situ pad footing casting in progress at south side
Wed (23/07) | 23 Jul 2025 | BR15A, BR15B |  | Continue rebar works and formwork closing
Wed (23/07) | 23 Jul 2025 | BR17 |  | Continue excavation
Wed (23/07) | 23 Jul 2025 | Exit 2 |  | Stump rebar installation & excavation for utility support in progress
Wed (23/07) | 23 Jul 2025 | BR3 & BR4 |  | Continue retaining wall formwork closing
Wed (23/07) | 23 Jul 2025 | Blk 4 | GL 26 | Exposing KP
Wed (23/07) | 23 Jul 2025 | GL28-29 | Selarang side | Preparing for top plate welding for decking stump
Wed (23/07) | 23 Jul 2025 | P19 |  | Woh hup installation of ducting. Tonight they will handover half of the crosshead for shear link installation
Wed (23/07) | 23 Jul 2025 | P14 |  | Tonight plan to install two segments at south bound
Wed (23/07) | 23 Jul 2025 | CCE1-CCE2 |  | Decking panel installation and beam welding works ongoing
Wed (23/07) | 23 Jul 2025 | BR30 |  | RGT installation & surface cleaning
Wed (23/07) | 23 Jul 2025 | BR30 | ST97-95 | Rebar works for waler in progress
Wed (23/07) | 23 Jul 2025 | CCE4 |  | Excavation in progress
Wed (23/07) | 23 Jul 2025 | P6-2 |  | Column formwork tie rod securing
Wed (23/07) | 23 Jul 2025 | P7-1 |  | Current status of pile head hacking
Wed (23/07) | 23 Jul 2025 | S1 |  | Current status of ERSS installation
Wed (23/07) | 23 Jul 2025 | 800mm dia water pipe |  | Reinstate back barricade before end work
Wed (23/07) | 23 Jul 2025 | P48 |  | Current status of utility support
Wed (23/07) | 23 Jul 2025 | P50 |  | KTC will continue excavation for 4th layer caisson during night shift
Wed (23/07) | 23 Jul 2025 | P44 |  | Already end work
Thu (24/07) | 24 Jul 2025 | P21 |  | Falsework dismantling in progress
Thu (24/07) | 24 Jul 2025 | P19 |  | Shear links installation in progress
Thu (24/07) | 24 Jul 2025 | P16 |  | Starter hanger installed
Thu (24/07) | 24 Jul 2025 | P14 |  | Tendon strands installation for stressing works
Thu (24/07) | 24 Jul 2025 | S1 |  | ERSS installation. Today to complete
Thu (24/07) | 24 Jul 2025 | P7-1 |  | Pile head hacking completed. Removal of hardcores in progress
Thu (24/07) | 24 Jul 2025 | P6-2 |  | Preparation for column casting. Scaffold erection ongoing
Thu (24/07) | 24 Jul 2025 | P3 |  | Preparation for pad footing installation for falsework towards TPE side
Thu (24/07) | 24 Jul 2025 | Blk 4 | GL25 | Manual excavation below utilities
Thu (24/07) | 24 Jul 2025 | Blk 4 |  | Seongha fissure grouting post-lugeon test in progress, CH22 (O-208 to O-209), CH23 (O-212 to O-213)
Thu (24/07) | 24 Jul 2025 | Exit 1 |  | Current status
Thu (24/07) | 24 Jul 2025 | BR30 |  | Rebar works ongoing & KP welding in progress
Thu (24/07) | 24 Jul 2025 | BR31 |  | Status quo
Thu (24/07) | 24 Jul 2025 | CCE4 |  | Exposing coupler ongoing
Thu (24/07) | 24 Jul 2025 | BR3, BR4 |  | Retaining wall casting in progress
Thu (24/07) | 24 Jul 2025 | CCE 3 |  | This part of the decking clashes with BR30, target to remove part of it tmr. Currently access preparation ongoing
Thu (24/07) | 24 Jul 2025 | Exit 1/Gate 7 |  | Current status
Thu (24/07) | 24 Jul 2025 | P21 |  | Continue crosshead Falsework dismantling
Thu (24/07) | 24 Jul 2025 | P19 |  | Crosshead shear links installation
Thu (24/07) | 24 Jul 2025 | P14 |  | Stressing works ongoing for SB 4th pair
Thu (24/07) | 24 Jul 2025 | N1 |  | Scaffold erection for segment launching
Thu (24/07) | 24 Jul 2025 | P44 |  | Column formwork closing, plan to cast tomorrow
Thu (24/07) | 24 Jul 2025 | P45 |  | Excavation to expose utilities
Thu (24/07) | 24 Jul 2025 | S2 |  | Concrete plug casting
Thu (24/07) | 24 Jul 2025 | P8-P9 |  | Trial trench for tunnel IM
Thu (24/07) | 24 Jul 2025 | S1 |  | ERSS installation completed
Thu (24/07) | 24 Jul 2025 | P7-1 |  | Manual hacking and hardcores removal in progress
Thu (24/07) | 24 Jul 2025 | P6-2 |  | Concrete order for column casting
Thu (24/07) | 24 Jul 2025 | P47 |  | JGP trial trench and pipe sleeve installation
Thu (24/07) | 24 Jul 2025 | DR3 |  | Coring test in progress
Thu (24/07) | 24 Jul 2025 | 800mm |  | Welding for the pipe joint
Thu (24/07) | 24 Jul 2025 | P48 |  | Excavation to expose utilities and welding for utility support
Thu (24/07) | 24 Jul 2025 | P3 |  | Falsework installation ongoing
Fri (25/07) | 25 Jul 2025 | CCE4 |  | Removal of hard soil layer ongoing beneath (circled in green)
Fri (25/07) | 25 Jul 2025 | BR3, BR4 |  | Retaining wall cast yesterday
Fri (25/07) | 25 Jul 2025 | Blk 4 | GL25-26 | Manual excavation below utilities
Fri (25/07) | 25 Jul 2025 | Blk 4 | GL27-29 | KTC continue excavation and soil disposal, Geomotion and Seongha have completed their works here
Fri (25/07) | 25 Jul 2025 | Opp blk 4 | Selarang side | Seongha will continue post-lugeon test here. Only left this area to complete. Currently machine hydraulic hose leaking, preparing for rectification
Fri (25/07) | 25 Jul 2025 | Exit 1/Linkway |  | No activity
Fri (25/07) | 25 Jul 2025 | BR30 |  | Rebar work ongoing
Fri (25/07) | 25 Jul 2025 | BR31 |  | Status quo
Fri (25/07) | 25 Jul 2025 | P40 |  | Coupler exposure ongoing below
Fri (25/07) | 25 Jul 2025 | BR8B |  | Main beam welding ongoing
Fri (25/07) | 25 Jul 2025 | GL E7-E9 |  | Decking installation work is in progress
Fri (25/07) | 25 Jul 2025 | Exit 1 |  | Will continue drilling for bracket installation after pumping out of water
Fri (25/07) | 25 Jul 2025 | PMH26-28 |  | Today plan to cast around 12m length of Power duct
Fri (25/07) | 25 Jul 2025 | PMH24 |  | Platform & access erection for the manhole casting tomorrow. We will left only one manhole (PMH29) for 22KV diversion after this manhole cast
Fri (25/07) | 25 Jul 2025 | P50 |  | KTC and WH continue hacking pile head for 4th layer caisson
Fri (25/07) | 25 Jul 2025 | DR3, P46, P47, 800mm dia water pipe laying |  | On site dicussion with woh hup on deconflic of work on site
Fri (25/07) | 25 Jul 2025 | 800mm dia |  | Two pipes laid and joint welding to complete today and backfilling
Fri (25/07) | 25 Jul 2025 | P48 TPE bound |  | KTC and woh hup will handover the area for rebar work today
Fri (25/07) | 25 Jul 2025 | P46-DR3 |  | Today ley choon will tidy up this instrument bored hole area. Tomorrow Ryobi G will start work. Woh hup will assit them with machinery shifting
Fri (25/07) | 25 Jul 2025 | P45 |  | KTC continue exposing UKP. Tomorrow will handover Changi bound to LE and next Tuesday will be the whole area
Fri (25/07) | 25 Jul 2025 | P3 |  | Falsework installation and platform assembly works
Fri (25/07) | 25 Jul 2025 | P7-1 |  | Hacking and hardcore removal ongoing
Fri (25/07) | 25 Jul 2025 | P14 |  | Stressing works for U04/D04 NB segment
Fri (25/07) | 25 Jul 2025 | Blk 4 | GL25 | ICE continue manual excavation below utilities
Fri (25/07) | 25 Jul 2025 | BR10 |  | Dismantling retaining wall formwork
Fri (25/07) | 25 Jul 2025 | Exit 2 |  | 1nos RC stump cast just now
Fri (25/07) | 25 Jul 2025 | P44 |  | Column casting in progress. First column cast for Zone 4
Sat (26/07) | 26 Jul 2025 | PMH29 |  | No activity
Sat (26/07) | 26 Jul 2025 | PMH26-PMH28 |  | ERSS removal and backfilling
Sat (26/07) | 26 Jul 2025 | P50 |  | Bored pile hacking
Sat (26/07) | 26 Jul 2025 | PMH24 |  | Rebar works ongoing
Sat (26/07) | 26 Jul 2025 | P49 |  | No activity
Sat (26/07) | 26 Jul 2025 | P48 |  | Excavation south side completed, shifting excavator to P49
Sat (26/07) | 26 Jul 2025 | P48 | north | Water pipe support installation ongoing
Sat (26/07) | 26 Jul 2025 | P47 |  | Trial Trench for JGP
Sat (26/07) | 26 Jul 2025 | DR3 |  | Testing for tunnel JGP on going
Sat (26/07) | 26 Jul 2025 | DR3 |  | Excavation in progress
Sat (26/07) | 26 Jul 2025 | 800 water pipe |  | Backfilling work
Sat (26/07) | 26 Jul 2025 | P45 |  | Excavation to expose utilities
Sat (26/07) | 26 Jul 2025 | P3 |  | Falsework installation and platform assembly works
Sat (26/07) | 26 Jul 2025 | Zone 1 |  | Road hacking works
Sat (26/07) | 26 Jul 2025 | P1 |  | Trial Trench wok ongoing
Sat (26/07) | 26 Jul 2025 | P7-1 |  | Hacking and hardcore removal ongoing
Sat (26/07) | 26 Jul 2025 | S1 erss |  | Waler beam bracket installation and welding works
Sat (26/07) | 26 Jul 2025 | N3 |  | U/D-01 Preparing for Segment stressing work
Sat (26/07) | 26 Jul 2025 | P14 |  | Stressing work completed
Sat (26/07) | 26 Jul 2025 | P7-1 |  | Hacking and hardcore removal ongoing
Sat (26/07) | 26 Jul 2025 | P3 |  | Falsework installation
Sat (26/07) | 26 Jul 2025 | PMH26-PMH28 |  | ERSS removal and backfilling
Sat (26/07) | 26 Jul 2025 | P50 |  | Pile hacking and clearing debris
Sat (26/07) | 26 Jul 2025 | PMH24 |  | Rebar works ongoing
Sat (26/07) | 26 Jul 2025 | P48 |  | Utility support welding work on going
Sat (26/07) | 26 Jul 2025 | P47 |  | Trial Trench for JGP
Sat (26/07) | 26 Jul 2025 | DR3 |  | Coring test for tunnelling JGP on going
Sat (26/07) | 26 Jul 2025 | DR3 |  | Machine breakdown
Sat (26/07) | 26 Jul 2025 | P45/P46 |  | Instrument installation ongoing
Sat (26/07) | 26 Jul 2025 | 800 mm water pipe |  | ERSS removal and backfilling work
Sat (26/07) | 26 Jul 2025 | P44 |  | Column curing. No activity
Sat (26/07) | 26 Jul 2025 | P45 |  | Excavation to expose utilities
Mon (28/07) | 28 Jul 2025 | P16 1st pair |  | Segment adjusting in progress
Mon (28/07) | 28 Jul 2025 | N3 |  | Falsework erection for 3rd pair segment launching
Mon (28/07) | 28 Jul 2025 | P14 SB U05 |  | Stressing in progress
Mon (28/07) | 28 Jul 2025 | PMH29 |  | Tonight to resume excavation. Planned to lower down precast on Wednesday. This is the last manhole for 22KV diversion
Mon (28/07) | 28 Jul 2025 | PMH29 /800mm dia water pipe link up area |  | Ley Choon, Wee Guan and Woh hup discuss on deconflict of work area
Mon (28/07) | 28 Jul 2025 | PMH28 |  | Reinstate the area and levelling work
Mon (28/07) | 28 Jul 2025 | PMH26-PMH28 |  | Continue excavation and ERSS for power duct laying. Today plan for 8m length lean concrete of base
Mon (28/07) | 28 Jul 2025 | P7-1 pile cap |  | Bottom bar installation in progress. Target to cast on 31st July
Mon (28/07) | 28 Jul 2025 | BR30 |  | Top bar installation in progress
Mon (28/07) | 28 Jul 2025 | Exit 1 |  | Ongoing welding work for strut, plan to preload tomorrow
Mon (28/07) | 28 Jul 2025 | CCE4 |  | Lean con has completed together with RS
Mon (28/07) | 28 Jul 2025 | P50 |  | Levelling work. Handover first part to WD
Mon (28/07) | 28 Jul 2025 | P48 Changi Bound |  | MPI test done for utility support. Handover to KTC for excavation. Working platform need to remove
Mon (28/07) | 28 Jul 2025 | P48 TPE bound |  | 1st layer caisson rebar work in progress
Mon (28/07) | 28 Jul 2025 | P49 |  | Excavation at center portion for 4th layer caisson
Mon (28/07) | 28 Jul 2025 | PMH24 |  | Casting completed
Mon (28/07) | 28 Jul 2025 | P45 |  | 1st part handover to LE for utility support. Slope protection lean concrete done
Mon (28/07) | 28 Jul 2025 | P44 |  | Clearing materials and prepare the area for falsework platform. Tomorrow mobile crane will mobilized for column formwork removal
Tue (29/07) | 29 Jul 2025 | P19 crosshead |  | Formwork closed. Cast in anchor adjusting. Tmr dayshift to cast
Tue (29/07) | 29 Jul 2025 | P16 |  | 1st pair segment adjusting continue. Initial asbuilt of geometry control reading taken. Pending YWL confirmation
Tue (29/07) | 29 Jul 2025 | 800mm dia water pipe |  | Ley Choon started excavation and ERSS installation for pipe laying (near link up area)
Tue (29/07) | 29 Jul 2025 | PMH29 |  | Already excavated to the bass. Wee Guan working night shift and Ley Choon working day shift to deconflict of work area
Tue (29/07) | 29 Jul 2025 | CCE4 |  | Expose couplers ongoing
Tue (29/07) | 29 Jul 2025 | BR30 |  | Removal of 2 nos I-beams in progress & rebar works continue
Tue (29/07) | 29 Jul 2025 | P45 |  | KTC working at TPE bound and LE working at Changi bound. Should be handover the whole area by Thursday as per planned
Tue (29/07) | 29 Jul 2025 | P46 |  | Left 2nos SPT test and 1nos of coring test to complete Tunnel JGP testing
Tue (29/07) | 29 Jul 2025 | DR3 |  | Continue exposing UKP for utility support
Tue (29/07) | 29 Jul 2025 | P48 |  | 1st layer (1st part) caisson rebar work completed. Tie rods installation for formwork closing
Tue (29/07) | 29 Jul 2025 | P48 Changi Bound |  | Working platform dismantling done. KTC to resume excavation here
Tue (29/07) | 29 Jul 2025 | P49 |  | Continue excavation for 4th layer caisson
Tue (29/07) | 29 Jul 2025 | PMH24 |  | Neck casting done
Tue (29/07) | 29 Jul 2025 | P50 |  | Rebar delivery for pile cap
Tue (29/07) | 29 Jul 2025 | PMH26-28 |  | Today to cast 8m length of power duct. Continue excavation for lean concrete also
Tue (29/07) | 29 Jul 2025 | PMH29 |  | Preparing for footpath diversion
Tue (29/07) | 29 Jul 2025 | P50 |  | Levelling for 4th layer caisson (1st part)
Tue (29/07) | 29 Jul 2025 | Exit 1/Linkway |  | Current status
Tue (29/07) | 29 Jul 2025 | GL E8 towards BR6 |  | Secondary beam installation in progress
Tue (29/07) | 29 Jul 2025 | 800mm PW |  | Excavation and ERSS
Tue (29/07) | 29 Jul 2025 | P44 |  | Column formwork suppprt removal
Tue (29/07) | 29 Jul 2025 | P7-1 |  | Top bars completed. Links installation in progress
Tue (29/07) | 29 Jul 2025 | P14-13 |  | Area preparation for crane working platform to install N3 D02 tonight
Tue (29/07) | 29 Jul 2025 | P20 crosshead |  | Formwork dismantling completed. Scaffold erection for Strand pulling and post tensioning
Tue (29/07) | 29 Jul 2025 | CR106 safety timeout |  | Sharing on the recent incident at Tanjong Katong sinkhole
Tue (29/07) | 29 Jul 2025 | P48 |  | Tie rod installation completed. Baseplate for strut installation in progress
Tue (29/07) | 29 Jul 2025 | P49 |  | Excavation for 4th layer caison continue. Tonight KTC arranged for soil disposal
Tue (29/07) | 29 Jul 2025 | P50 |  | Excavation for 4th layer caison and 3rd layer caison soffit hacking continue till 10pm
Wed (30/07) | 30 Jul 2025 | P45 |  | LE installation and welding of UKP base plate. KTC working at TPE bound
Wed (30/07) | 30 Jul 2025 | P43 |  | Checking of the area for PLT
Wed (30/07) | 30 Jul 2025 | P16 |  | 1st pair still need minor adjustment. WH preparing wet stitching formwork for installation
Wed (30/07) | 30 Jul 2025 | N3 2nd pair |  | Strand pulling for stressing
Wed (30/07) | 30 Jul 2025 | P48 |  | KTC resume excavation
Wed (30/07) | 30 Jul 2025 | P48 |  | 1st stage caisson casting target today
Wed (30/07) | 30 Jul 2025 | DR3 |  | Continue removal top soil
Wed (30/07) | 30 Jul 2025 | PMH29 |  | Lean con completed. Today afternoon lowering precast manhole
Wed (30/07) | 30 Jul 2025 | 800mm PW |  | Excavation and ERSS
Wed (30/07) | 30 Jul 2025 | PMH26-PMH28 |  | Excavation and ERSS
Wed (30/07) | 30 Jul 2025 | P50 |  | Preparation for caisson rc work
Wed (30/07) | 30 Jul 2025 | P49 |  | Excavation on going
Wed (30/07) | 30 Jul 2025 | P1 |  | Pre-boring for ERSS continue
Wed (30/07) | 30 Jul 2025 | P3 platform |  | Plywood laying in progress. tonight to install bottom formwork
Wed (30/07) | 30 Jul 2025 | CCE4 |  | Hacking of bulging Dwall
Wed (30/07) | 30 Jul 2025 | BR30 |  | Continues rebar installation
Wed (30/07) | 30 Jul 2025 | GL E8-BR6 |  | Continues secondary beam installation for decking
Wed (30/07) | 30 Jul 2025 | P19 crosshead |  | Casting in progress
Wed (30/07) | 30 Jul 2025 | S1 |  | Erection of new access to FEL
Wed (30/07) | 30 Jul 2025 | Blk 4 | GL25-26 | Utility support welding works in progress
Wed (30/07) | 30 Jul 2025 | Blk 4 | GL27 | Manual excavation below utilities ongoing
Wed (30/07) | 30 Jul 2025 | GL28-29 | Selarang side | Temporary decking works in progress
Wed (30/07) | 30 Jul 2025 | GL27 |  | Exposing utilities alignment
Wed (30/07) | 30 Jul 2025 | BR4 |  | Corrugated pipes grouting works, 31/31nos completed
Wed (30/07) | 30 Jul 2025 | P4 |  | Premix hacking stopped for the day. Preparation for cutting and hardcore disposal
Wed (30/07) | 30 Jul 2025 | P1 |  | 4 nos SP pre-boring completed. Setting out for the next line of SP
Wed (30/07) | 30 Jul 2025 | P6-1 |  | Column formwork dismantling
Wed (30/07) | 30 Jul 2025 | N3 U03 |  | Scaffold platform erection for segment launching tonight
Wed (30/07) | 30 Jul 2025 | P19 crosshead |  | Casting continue, 178/204 m3
Wed (30/07) | 30 Jul 2025 | BR18 |  | Excavation & disposal in progress
Wed (30/07) | 30 Jul 2025 | BR17 |  | KP endplate welding works ongoing
Wed (30/07) | 30 Jul 2025 | P24 |  | No activity
Wed (30/07) | 30 Jul 2025 | CCW W2-W5 |  | Excavation and disposal in progress
Wed (30/07) | 30 Jul 2025 | BR15 |  | Formwork dismantling ongoing
Wed (30/07) | 30 Jul 2025 | Exit 2 |  | Excavation to dwall COL
Wed (30/07) | 30 Jul 2025 | Blk 4 | GL25-26 | Utility support welding works ongoing
Wed (30/07) | 30 Jul 2025 | BR6 |  | Preparing N plates to facilitate decking works
Wed (30/07) | 30 Jul 2025 | BR5 |  | Fin plate welding for beam decking ongoing
Wed (30/07) | 30 Jul 2025 | P44 |  | Column formwork dismantled
Wed (30/07) | 30 Jul 2025 | BR30 |  | Continue rebar works
Wed (30/07) | 30 Jul 2025 | CCE4 tunnel roof slab |  | No activity. Tmr plan to start rebar works
Wed (30/07) | 30 Jul 2025 | Receiving shaft S2 waler |  | Continue exposing couplers and clearing debris
Thu (31/07) | 31 Jul 2025 | P16 |  | Segment all alignment ok as per surveyor's check. Now pending YWL confirmation. Today to start wet stitching formwork at NB side
Thu (31/07) | 31 Jul 2025 | BR4 |  | Preparing non-shrink grout for dwall side, Surface grinding ongoing, Dewatering ongoing for corrugated pipes
Thu (31/07) | 31 Jul 2025 | Blk 4 | GL27 | Excavation for utility support works in progress
Thu (31/07) | 31 Jul 2025 | Blk 4 | GL26 | Manually exposing utilities
Thu (31/07) | 31 Jul 2025 | BR6 |  | N-plates installation in progress
Thu (31/07) | 31 Jul 2025 | PMH29 |  | Preparing formwork, today going to cast base slab
Thu (31/07) | 31 Jul 2025 | 800mm PW |  | Excavation and ERSS
Thu (31/07) | 31 Jul 2025 | PMH26-PMH28 |  | Pipe laying on going
Thu (31/07) | 31 Jul 2025 | P49 |  | Excavation to L4 caisson level
Thu (31/07) | 31 Jul 2025 | P48 | south | Closing L1 caisson formwork
Thu (31/07) | 31 Jul 2025 | P48 | north | Excavation to L1 caisson level ongoing
Thu (31/07) | 31 Jul 2025 | P47 |  | JGP trial trench ongoing
Thu (31/07) | 31 Jul 2025 | DR3 |  | Part 1 going to start expose utilities, Part 2 start excavation, Part 3 material shifting to make access
Thu (31/07) | 31 Jul 2025 | P46 |  | JGP Testing for tunneling works
Thu (31/07) | 31 Jul 2025 | P45 |  | Excavation to expose utilities
Thu (31/07) | 31 Jul 2025 | P13-14 |  | Area leveling for crane parking tonight
Thu (31/07) | 31 Jul 2025 | N3 D03 |  | Scaffold erection for segment launching tonight
Thu (31/07) | 31 Jul 2025 | S1 |  | Excavation to FEL plan to complete tomorrow
Thu (31/07) | 31 Jul 2025 | P7-1 |  | Final inspection at 1030 for casting
Thu (31/07) | 31 Jul 2025 | CCE2-3 |  | Excavation for BR29 ongoing
Thu (31/07) | 31 Jul 2025 | BR30 |  | Current status
Thu (31/07) | 31 Jul 2025 | CCE4 |  | Laying of debonding membrane for tunnel roof slab ongoing
Thu (31/07) | 31 Jul 2025 | CCE4 | next to P40 | Cutting down Dwall / planting couple rebar for tunnel roof slab
Thu (31/07) | 31 Jul 2025 | P44 |  | No activity
Thu (31/07) | 31 Jul 2025 | P43 |  | Excavation on going
Thu (31/07) | 31 Jul 2025 | P1 |  | Installation of SP to be progressively done after pre-boring due to soft soil condition
Thu (31/07) | 31 Jul 2025 | CR1070 |  | Water pipe pre DLP inspection with PUB officer
Thu (31/07) | 31 Jul 2025 | 800mm dia water pipe |  | Link up location confirmed. Now continue excavation and ERSS for water pipe laying
Thu (31/07) | 31 Jul 2025 | PMH29 |  | Stitching between precast panels. This last manhole to complete by early next week
Thu (31/07) | 31 Jul 2025 | PMH26 to PMH28 |  | Preparing for casting of Power duct. 10m length. Yesterday cast 6m
Thu (31/07) | 31 Jul 2025 | P1 |  | 4 nos SP installed
Thu (31/07) | 31 Jul 2025 | BR30 |  | Shear link & formwork installation in progress, target to cast tomorrow
Thu (31/07) | 31 Jul 2025 | P3 |  | Plywood laying in progress
Thu (31/07) | 31 Jul 2025 | BR10 |  | Inner side retaining wall formwork dismantling
Thu (31/07) | 31 Jul 2025 | P7-1 |  | Casting in progress
Thu (31/07) | 31 Jul 2025 | P50 |  | 4th layer 1st part caisson rebar work
Thu (31/07) | 31 Jul 2025 | P49 |  | Excavation for 4th layer caisson done around 50%
Thu (31/07) | 31 Jul 2025 | P48 |  | Continue excavation toward Changi bound side. Highlighted to provide height limiter
Thu (31/07) | 31 Jul 2025 | P48 TPE bound |  | 1st layer 1st part will cast today. Concrete ordered
Thu (31/07) | 31 Jul 2025 | P45 |  | LE continue installation of base plate for utility support
Thu (31/07) | 31 Jul 2025 | P46 |  | Coring test in progress. This is the last coring point for tunnel testing
Thu (31/07) | 31 Jul 2025 | DR3 |  | Current status of exposing UKP
Thu (31/07) | 31 Jul 2025 | P47 |  | Pipe sleeves installation for JGP grouting
Thu (31/07) | 31 Jul 2025 | P44 |  | Column formwork removal done
Thu (31/07) | 31 Jul 2025 | P24 |  | Exposing couplers
Thu (31/07) | 31 Jul 2025 | BR15 |  | Patching of tie rod holes
Thu (31/07) | 31 Jul 2025 | BR18 |  | Hacking of excess concrete around KP area
Thu (31/07) | 31 Jul 2025 | P20 |  | Duct wire pulling for stressing work
Thu (31/07) | 31 Jul 2025 | N3 |  | Tendom wire pulling for stressing work
Thu (31/07) | 31 Jul 2025 | Blk 4 | GL27 | Continue excavation for utility support works
Thu (31/07) | 31 Jul 2025 | GL28-29 | Selarang side | Decking welding works, BR6: End plate installation for secondary beam in progress
Thu (31/07) | 31 Jul 2025 | CCE2 |  | Excavation in progress
Thu (31/07) | 31 Jul 2025 | BR30 |  | Continue shearlinks and formwork installation
Thu (31/07) | 31 Jul 2025 | CCE1 |  | Decking panels installation in progress
Thu (31/07) | 31 Jul 2025 | CCE4-tunnel roof slab |  | Rebar installation in progress
Thu (31/07) | 31 Jul 2025 | Receiving shaft W2 layer |  | Continue exposing couplers
Thu (31/07) | 31 Jul 2025 | S1 |  | Current status of excavation to FEL
Thu (31/07) | 31 Jul 2025 | P7-1 |  | Casting of pile cap. Now worker rest during waiting for concrete
Thu (31/07) | 31 Jul 2025 | P5 |  | Clearing and shifting of formwork materials
Thu (31/07) | 31 Jul 2025 | P3 |  | Soffit plywood laying
Thu (31/07) | 31 Jul 2025 | P7-1 |  | Continue casting
Thu (31/07) | 31 Jul 2025 | P45 |  | Two main beams installed today
Thu (31/07) | 31 Jul 2025 | DR3 |  | KTC already end work
Thu (31/07) | 31 Jul 2025 | P48 |  | Caisson casting
Thu (31/07) | 31 Jul 2025 | P20 |  | Strand pulling for stressing works
Fri (01/08) | 01 Aug 2025 | Blk 4 | GL26-27 | Manual clearing of soil below utilities
Fri (01/08) | 01 Aug 2025 | GL28-29 | Selarang side | Beam welding works ongoing
Fri (01/08) | 01 Aug 2025 | CCE4 |  | Rebar installation in progress
Fri (01/08) | 01 Aug 2025 | BR30 |  | Cleaning in progres, target to cast it today
Fri (01/08) | 01 Aug 2025 | GL E5-E7 |  | Ongoing excavation & soil disposal
Fri (01/08) | 01 Aug 2025 | BR4 |  | Plastering work for 300mm waterproofing termination in progress
Fri (01/08) | 01 Aug 2025 | BR4 |  | Continue clearing materials to facilitate grouting of corrugated pipes
Fri (01/08) | 01 Aug 2025 | BR10 |  | Retaining wall scaffold dismantling
Fri (01/08) | 01 Aug 2025 | P46 |  | JGP Testing for tunneling work
Fri (01/08) | 01 Aug 2025 | P47 |  | Trial Trench for JGP
Fri (01/08) | 01 Aug 2025 | P48 |  | Soil disposal ongoing
Fri (01/08) | 01 Aug 2025 | P45 |  | Utility support installation work on going
Fri (01/08) | 01 Aug 2025 | Zone 1 |  | P1 ERSS pre-boring and SP installation
Fri (01/08) | 01 Aug 2025 | PMH29 |  | Formwork removal done. Now clearing materials. Will continue with working platform erection for top slab work
Fri (01/08) | 01 Aug 2025 | 800mm dia water pipe |  | Confirmation of services location and ERSS installation
Fri (01/08) | 01 Aug 2025 | PMH26-PMH28 |  | Today will extend 4.8m length of lean concrete to lay one span of power duct
Fri (01/08) | 01 Aug 2025 | Exit 2 |  | Continue excavation for utility support works
Fri (01/08) | 01 Aug 2025 | Exit 2 |  | Manual clearing of soil below utilities
Fri (01/08) | 01 Aug 2025 | BR4 |  | Retaining wall formwork dismantling ongoing
Fri (01/08) | 01 Aug 2025 | BR4 |  | Plastering work for 300mm waterproofing termination in progress
Fri (01/08) | 01 Aug 2025 | Blk 4 | GL27 | Continue manual excavation below utilities
Fri (01/08) | 01 Aug 2025 | GL28-29 | Selarang side | Decking beam installation and welding works
Fri (01/08) | 01 Aug 2025 | P3 |  | Bottom formwork installation
Fri (01/08) | 01 Aug 2025 | S1 |  | Excavation to pile level completed. HSL to mobilise excavator today for pile head hacking
Fri (01/08) | 01 Aug 2025 | P47 |  | Pipe sleeves installed
Fri (01/08) | 01 Aug 2025 | P48 |  | Continue excavation toward Changi bound. Height limiter provided to precent accidental damage of services
Fri (01/08) | 01 Aug 2025 | P49 |  | Woh hup hacking pile head and KTC excavation
Fri (01/08) | 01 Aug 2025 | PMH25 |  | Today will cast 13m length of Power duct
Fri (01/08) | 01 Aug 2025 | P45 |  | Current status of main beam and secondary beam installation
Fri (01/08) | 01 Aug 2025 | DR3 |  | Current status of exposing UKP
Fri (01/08) | 01 Aug 2025 | P44 |  | Shifting out the column formwork
Fri (01/08) | 01 Aug 2025 | P20 |  | Top and bottom tendom wire pulling done. Preparing for the center role
Fri (01/08) | 01 Aug 2025 | P20 |  | Wendyng clearing polyfoam and debris
Fri (01/08) | 01 Aug 2025 | S2 |  | Backfilling for ERSS removal
Fri (01/08) | 01 Aug 2025 | S1 |  | Excavation done to FEL. HSL to hack the pile head tomorrow
Fri (01/08) | 01 Aug 2025 | P7-1 |  | Stump rebar work
Fri (01/08) | 01 Aug 2025 | P4 |  | LSS backfilling for crosshead head falsework platform
Fri (01/08) | 01 Aug 2025 | P3 TPE bound |  | Jack installation for crosshead soffit formwork
Fri (01/08) | 01 Aug 2025 | P49 |  | Continue excavation and disposal
Fri (01/08) | 01 Aug 2025 | P50 |  | Wee Guan casting of Power duct
Fri (01/08) | 01 Aug 2025 | P48 |  | As of now no activity already
Fri (01/08) | 01 Aug 2025 | P50 |  | LSS casting
Sat (02/08) | 02 Aug 2025 | P43 |  | Water pumping in progress. Today to erect scaffold for starter bar at lapping area for stage 2 column
Sat (02/08) | 02 Aug 2025 | P45 |  | Welding works for Utility support
Sat (02/08) | 02 Aug 2025 | P45 |  | Excavation to utility level at SB side
Sat (02/08) | 02 Aug 2025 | P49 |  | Excavation for 4th layer caison
Sat (02/08) | 02 Aug 2025 | PMH25 |  | Overcast PVC pipe hacking
Sat (02/08) | 02 Aug 2025 | P14 |  | Drilling for tunnel IM
Sat (02/08) | 02 Aug 2025 | N3 |  | Strand pulling for U4 stressing
Sat (02/08) | 02 Aug 2025 | P7-1 |  | Stump rebar works completed. Afternoon final inspection and start formwork closing
Sat (02/08) | 02 Aug 2025 | P3 | SB side | Bottom formwork plywood laying
Sat (02/08) | 02 Aug 2025 | P4 |  | Soil internal shifting
Sat (02/08) | 02 Aug 2025 | P7-1 stump |  | Tie rod installation for formworkclosing
Sat (02/08) | 02 Aug 2025 | P43 |  | Mud clear. Preparation for scaffold access erection
Sat (02/08) | 02 Aug 2025 | P47 |  | JGP permeability test on going
Mon (04/08) | 04 Aug 2025 | P14 |  | Drilling for tunnel IM installation
Mon (04/08) | 04 Aug 2025 | N3 |  | TPT dismantling
Mon (04/08) | 04 Aug 2025 | P7-1 stump |  | Pending final inspection for casting. Tonight to cast
Mon (04/08) | 04 Aug 2025 | CCE4 |  | Rebar installation in progress
Mon (04/08) | 04 Aug 2025 | BR4/3 |  | Preparing for grouting of corrugated pipes
Mon (04/08) | 04 Aug 2025 | GL E6-E8 |  | Excavation & soil disposal ongoing for BR28
Mon (04/08) | 04 Aug 2025 | 800mm PW |  | Excavation and ERSS
Mon (04/08) | 04 Aug 2025 | PMH29 |  | Manhole rebar work ongoing
Mon (04/08) | 04 Aug 2025 | PMH26-PMH28 |  | Excavation and ERSS
Mon (04/08) | 04 Aug 2025 | P50 |  | 4th layer caisson casting in progress
Mon (04/08) | 04 Aug 2025 | P49 |  | Bored pile hacking in progress
Mon (04/08) | 04 Aug 2025 | P48 |  | Excavation to 1st layer of caisson
Mon (04/08) | 04 Aug 2025 | P47 |  | Machine maintenance, JGP no work
Mon (04/08) | 04 Aug 2025 | P47 |  | Trial Trench for JGP
Mon (04/08) | 04 Aug 2025 | DR3 |  | Excavation to expose utilities
Mon (04/08) | 04 Aug 2025 | P45 |  | Excavation completed. Utility support installation ongoing
Mon (04/08) | 04 Aug 2025 | P43 |  | Stump rebar installation
Mon (04/08) | 04 Aug 2025 | P44 |  | Preparing platform for falsework
Mon (04/08) | 04 Aug 2025 | P24 TB |  | Rebar works in progress
Mon (04/08) | 04 Aug 2025 | Exit 3 |  | Levelling works ongoing before handover to Hirose
Mon (04/08) | 04 Aug 2025 | P16 stitching formwork closing |  | SB side 30% completed for upchainage and downchainage
Mon (04/08) | 04 Aug 2025 | P20 |  | Crosshead post tensioning in progress
Mon (04/08) | 04 Aug 2025 | BR17, BR18A |  | Rebar works ongoing before handover progress
Mon (04/08) | 04 Aug 2025 | Exit 2 |  | Exposing utility alignment
Mon (04/08) | 04 Aug 2025 | BR3 |  | Corrugated pipes grouting completed 17nos today
Mon (04/08) | 04 Aug 2025 | P43 stump |  | Links installation in progress
Mon (04/08) | 04 Aug 2025 | P44 |  | Lean concrete casting on going
Mon (04/08) | 04 Aug 2025 | BR8B, BR6 |  | Decking welding works in progress
Mon (04/08) | 04 Aug 2025 | GL E6-E8 |  | Hacking and excavation in progress for BR28
Mon (04/08) | 04 Aug 2025 | CCE4 |  | Rebar works in progress
Mon (04/08) | 04 Aug 2025 | P47 |  | JGP in progress, 3rd point for today
Mon (04/08) | 04 Aug 2025 | P48 |  | Utility support welding
Tue (05/08) | 05 Aug 2025 | P19 |  | Wing formwork dismantling
Tue (05/08) | 05 Aug 2025 | GL E6-E8 |  | Continues excavation & soil disposal for BR28
Tue (05/08) | 05 Aug 2025 | P16 |  | Stitching formwork closing, SB: today to complete, NB: 30% completed
Tue (05/08) | 05 Aug 2025 | 800mm dia water pipe |  | 7.5m length water pipe lowered down. Preparing for next pipe joining
Tue (05/08) | 05 Aug 2025 | Near DR4 |  | Abandoned drain removal for 22KV duct laying
Tue (05/08) | 05 Aug 2025 | PMH29 |  | Top slab formwork completed. Shifting of rebar to start rebar work
Tue (05/08) | 05 Aug 2025 | BR6/BR8B |  | Current decking status
Tue (05/08) | 05 Aug 2025 | CCE4 |  | Continues rebar installation work for tunnel roof slab
Tue (05/08) | 05 Aug 2025 | N3 D05 |  | Falsework erection for tonight's launching
Tue (05/08) | 05 Aug 2025 | PMH26-28 |  | Today plan to lean concrete 10m length
Tue (05/08) | 05 Aug 2025 | P50 |  | 4th layer caisson formwork removal. By today will complete 75% of 4th layer caisson casting
Tue (05/08) | 05 Aug 2025 | P48 |  | KTC already handover around 80% of 1st layer. By Thursday should complete 80% of caisson. Balance 20% will cast together with 2nd layer coz existing services are at S2 level
Tue (05/08) | 05 Aug 2025 | P45 |  | KTC already fully handover the first layer. LE welding of utility support and ICE exposing services for support
Tue (05/08) | 05 Aug 2025 | DR3 |  | Abandoned services removal and continue exposing of services. Note: RES for this activity is under WH
Tue (05/08) | 05 Aug 2025 | P43 |  | Working platform erection for stump. To cast by Friday
Tue (05/08) | 05 Aug 2025 | P44 |  | Current status. Falsework will start to install tomorrow for crosshead. Crosshead casting earliest end of this month or 1st week of Sep
Tue (05/08) | 05 Aug 2025 | P43 2nd stage column |  | Preparation for fabrication
Wed (06/08) | 06 Aug 2025 | P16 stitching formwork |  | SB: 90% completed, NB: 50% completed
Wed (06/08) | 06 Aug 2025 | PMH28 road crossing |  | Decking installed one lane for duct laying. Tonight to continue 2nd lane
Wed (06/08) | 06 Aug 2025 | 800mm dia water pipe laying |  | 22.5m length laid up to date
Wed (06/08) | 06 Aug 2025 | PMH29 |  | Will cast tomorrow. This will be the last manhole to complete for SPPG cable diversion
Wed (06/08) | 06 Aug 2025 | PMH28-29 |  | Current status of excavation and ERSS
Wed (06/08) | 06 Aug 2025 | S1 pile head hacking |  | Trimming on going
Wed (06/08) | 06 Aug 2025 | Exit 2 |  | Utility alignment exposed. To continue manual excavation below services for support works
Wed (06/08) | 06 Aug 2025 | BR4, BR3 |  | Materials arrived for waterproofing works. Plan for Maxbond to start works tmr, Today WH plan to continue grouting for another 58nos corrugated pipes. As to date, 41/99nos done, Now ongoing surface grinding and cleaning prior to grouting works
Wed (06/08) | 06 Aug 2025 | CCE4 |  | Rebar work in progress for tunnel roof slab
Wed (06/08) | 06 Aug 2025 | GL25-26 |  | Current status for beam installation for utility support works. Balance 1nos beam to be installed here
Wed (06/08) | 06 Aug 2025 | Blk 4 GL27.5-28.5 |  | Excavation ongoing for utility support works
Wed (06/08) | 06 Aug 2025 | Opp blk 4 |  | Exposing utility alignment
Wed (06/08) | 06 Aug 2025 | BR7B |  | Excavation in progress
Wed (06/08) | 06 Aug 2025 | GL E6-E8 |  | Continues excavation & soil disposal for BR28
Wed (06/08) | 06 Aug 2025 | DR3 |  | Current status of excavation. Dispose abandoned pipes
Wed (06/08) | 06 Aug 2025 | P47 |  | Preparation of mud tank for 4th point JGP grouting
Wed (06/08) | 06 Aug 2025 | P48 Changi bound |  | WH clearing materials to handover to Wendyng
Wed (06/08) | 06 Aug 2025 | P48 TPE bound |  | Today to complete 70% of rebar work for 1st layer caisson
Wed (06/08) | 06 Aug 2025 | P48 TPE bound |  | KTC to handover 80% of work area for rebar work by today
Wed (06/08) | 06 Aug 2025 | P50 |  | Concrete on site for 4th layer caisson casting
Wed (06/08) | 06 Aug 2025 | PMH26-28 |  | Today to cast 10m length of Power duct
Wed (06/08) | 06 Aug 2025 | P48 |  | Caisson rebar work
Wed (06/08) | 06 Aug 2025 | P50 |  | Hacking LSS
Wed (06/08) | 06 Aug 2025 | P47 |  | Preparation work for JGP
Wed (06/08) | 06 Aug 2025 | DR3 |  | Excavation to expose utilities
Wed (06/08) | 06 Aug 2025 | P45 |  | Utility support installation
Wed (06/08) | 06 Aug 2025 | P44 |  | Platform preparation for falsework
Wed (06/08) | 06 Aug 2025 | P43 |  | Column rebar fabrication work
Wed (06/08) | 06 Aug 2025 | P16 stitching |  | NB 60% completed. Balance below bus lane. To complete tonight
Wed (06/08) | 06 Aug 2025 | N3 segment 5th pair |  | Installation of hydraulic jack for post tensioning
Wed (06/08) | 06 Aug 2025 | PMH26-28 |  | Inspection for Power duct. Concrete ordered
Wed (06/08) | 06 Aug 2025 | 800mm dia water pipe |  | Welding done. Preparing for leakage test and holiday test
Wed (06/08) | 06 Aug 2025 | PMH29 |  | Current status of top bar installation. Tomorrow to cast
Wed (06/08) | 06 Aug 2025 | PMH28-29 |  | Drain removal for Power duct laying
Wed (06/08) | 06 Aug 2025 | S2 |  | Area leveling for rebar cage installation
Wed (06/08) | 06 Aug 2025 | P50 |  | 4th layer caisson casting in progress
Wed (06/08) | 06 Aug 2025 | BR4, BR3 |  | Grouting in progress for corrugated pipes
Wed (06/08) | 06 Aug 2025 | Opp blk 4 |  | Current status of exposing utilities for Singtel & Starhub
Wed (06/08) | 06 Aug 2025 | BR6/BR8B |  | Decking panels installation & welding works ongoing
Wed (06/08) | 06 Aug 2025 | S1 |  | Balance 1 pile to trim. Tonight to clear hardcore
Wed (06/08) | 06 Aug 2025 | P7-1 |  | LSS backfilling to pile cap level
Wed (06/08) | 06 Aug 2025 | DR4 |  | Eng hup installation of meter box. They expedite from their end
Wed (06/08) | 06 Aug 2025 | P50 |  | 4th layer caisson casting in progress. 80% completed for 4th layer. This week to complete 100%
Wed (06/08) | 06 Aug 2025 | P45 Changi bound |  | Utility support installation
Wed (06/08) | 06 Aug 2025 | DR3 |  | Exposing UKP and prepare to remove abandoned drain
Wed (06/08) | 06 Aug 2025 | P47 |  | JGP grouting
Wed (06/08) | 06 Aug 2025 | P48 |  | 2nd span rebar installed. Preparing for base plate installation
Wed (06/08) | 06 Aug 2025 | P48 |  | KTC will handover 80% of 4th layer caisson work area by today
Wed (06/08) | 06 Aug 2025 | P48 Changi bound |  | Clearing debris for caisson work
Wed (06/08) | 06 Aug 2025 | P44 |  | Pad footing installation
Wed (06/08) | 06 Aug 2025 | BR28 |  | Hacking works ongoing & continue excavation and soil disposal
Wed (06/08) | 06 Aug 2025 | BR30 |  | Formwork dismantling
Wed (06/08) | 06 Aug 2025 | CCE4 tunnel roof slab |  | Continue rebar works
Wed (06/08) | 06 Aug 2025 | CCE4 |  | Hacking for coupler exposing
Wed (06/08) | 06 Aug 2025 | Receiving shaft W2 |  | Rebar works in progress
Wed (06/08) | 06 Aug 2025 | DR3 |  | Abandoned drain removal
Wed (06/08) | 06 Aug 2025 | P48 |  | Base plate installation for 1st layer strut in progress
Wed (06/08) | 06 Aug 2025 | BR6 |  | Continue decking panel installation
Wed (06/08) | 06 Aug 2025 | GL12-14 |  | Temporary backfilling and levelling for access diversion. Current access between GL10-11 will be blocked to facilitate the next part of excavation works
Wed (06/08) | 06 Aug 2025 | Exit 2 |  | Hirose materials on site. Tmr plan to start works here
Wed (06/08) | 06 Aug 2025 | BR17, BR18A |  | Rebar works in progress
Wed (06/08) | 06 Aug 2025 | P24 TB |  | Rebar works in progress
Wed (06/08) | 06 Aug 2025 | S1 |  | Hardcore clearing. Tonight to lean concrete
Wed (06/08) | 06 Aug 2025 | P7-1 |  | LSS backfilling to pile cap level completed
Wed (06/08) | 06 Aug 2025 | S2 |  | Pier rebar cage installed. Prepreparation for propping installation
Wed (06/08) | 06 Aug 2025 | N3 5th pair |  | Strand pulling for post tensioning
Thu (07/08) | 07 Aug 2025 | PMH28 |  | Decking installed for both lanes
Thu (07/08) | 07 Aug 2025 | PMH26-28 |  | Preparing to backfill back completed duct cast area
Thu (07/08) | 07 Aug 2025 | 800mm dia water pipe |  | Preparing to back and install chamber
Thu (07/08) | 07 Aug 2025 | PMH29 |  | Side formwork closing
Thu (07/08) | 07 Aug 2025 | PMH28- PMH29 |  | Excavation and ERSS installation for Power duct laying
Thu (07/08) | 07 Aug 2025 | P16 |  | Wedge plate installation in progress
Thu (07/08) | 07 Aug 2025 | P16 |  | Stitching formworks all completed. Tonight 7pm to start casting at SB side. After last bus to follow at NB side
Thu (07/08) | 07 Aug 2025 | GL E6-E8 |  | BR28 excavation status & soil disposal
Thu (07/08) | 07 Aug 2025 | Exit 2 |  | Levelling works ongoing. Today plan to lean con
Thu (07/08) | 07 Aug 2025 | GL12-13 |  | Levelling works ongoing, GL13-14: Steel plates laid for new vehicle access
Thu (07/08) | 07 Aug 2025 | BR4, BR3 |  | Yesterday completed 55nos of grouting of corrugated pipes — 96/96nos done. Now ongoing surface grinding and cleaning
Thu (07/08) | 07 Aug 2025 | BR7B |  | Platform preparation for machinery parking to facilitate the next section of utility support works near decking area
Thu (07/08) | 07 Aug 2025 | GL27-28 | Selarang side | Exposing utility alignment to facilitate decking works. Starhub pipes will be localised diverted about 1m away. Singtel will be supported to facilitate the dwall hacking works. Abandoned water pipe and SPPG will be cleared
Thu (07/08) | 07 Aug 2025 | N3 |  | Scaffold erection for segment D06 launching tonight
Thu (07/08) | 07 Aug 2025 | Zone 1 |  | LG installation
Thu (07/08) | 07 Aug 2025 | P48 |  | Formwork close for mid section
Thu (07/08) | 07 Aug 2025 | P47 |  | JGP works ongoing
Thu (07/08) | 07 Aug 2025 | DR3 |  | Excavation to expose utilities
Thu (07/08) | 07 Aug 2025 | P45 |  | Manual excavation and utility support installation
Thu (07/08) | 07 Aug 2025 | CCE4 |  | Ongoing rebar work for tunnel roof slab
Thu (07/08) | 07 Aug 2025 | P44 |  | Falsework preparation for crosshead
Thu (07/08) | 07 Aug 2025 | P1 |  | Pre-boring for ERSS continue
Thu (07/08) | 07 Aug 2025 | PMH29 |  | Neck rebar work and formwork closing
Thu (07/08) | 07 Aug 2025 | 800mm dia water pipe |  | Capping installation and backfilling to road level
Thu (07/08) | 07 Aug 2025 | PMH28-29 |  | Lean concrete done for Power duct laying
Thu (07/08) | 07 Aug 2025 | PMH26-28 |  | Excavation and ERSS installation for Power duct laying
Thu (07/08) | 07 Aug 2025 | P7-1 |  | LSS trimming. Tonight to cast 2nd layer concrete plug
Thu (07/08) | 07 Aug 2025 | S2 column rebar cage |  | Links installation at lapping area
Thu (07/08) | 07 Aug 2025 | Exit 2 | LVC side | WH to install barricades and proper access for Hirose to facilitate their works. Have requested WH to expedite
Thu (07/08) | 07 Aug 2025 | BR3 |  | Plastering work for 300mm waterproofing termination in progress, Cutting of groove line along the retaining wall, Slab surface grinding ongoing
Thu (07/08) | 07 Aug 2025 | P14 |  | Drilling for tunnel RX
Thu (07/08) | 07 Aug 2025 | P49 |  | Removal of soft soil and backfill with good soil for 4th layer working platform
Thu (07/08) | 07 Aug 2025 | P50 |  | Balance this 20% for caisson to cast for 4th layer. Rebar work in progress
Thu (07/08) | 07 Aug 2025 | P48 |  | Formwork closing done. Final inspection before cast this 2nd part of caisson
Thu (07/08) | 07 Aug 2025 | P45 |  | Continue utility support welding by LE
Thu (07/08) | 07 Aug 2025 | DR3 |  | Continue exposing UKP and levelling
Thu (07/08) | 07 Aug 2025 | P47 |  | Continue JGP grouting. 7nos done as of today
Thu (07/08) | 07 Aug 2025 | P44 |  | Falsework installation on going for crosshead
Thu (07/08) | 07 Aug 2025 | P43 |  | Working platform erection for stump casting
Thu (07/08) | 07 Aug 2025 | N1 |  | Woh hup preparing platform for segment launching
Thu (07/08) | 07 Aug 2025 | S2 |  | Column rebar cage installed
Thu (07/08) | 07 Aug 2025 | S1 |  | Lean concrete done
Thu (07/08) | 07 Aug 2025 | P7-1 |  | Concrete ordered for prop concrete casting. On the way
Thu (07/08) | 07 Aug 2025 | P48 |  | Preparing for caisson casting
Thu (07/08) | 07 Aug 2025 | P47 |  | GCE tidy up their grouting area
Thu (07/08) | 07 Aug 2025 | P44 |  | Current status of falsework installation. P43: continue rebar cage fabrication
Thu (07/08) | 07 Aug 2025 | P49 |  | CJ hacking to start rebar work
Fri (08/08) | 08 Aug 2025 | BR8A |  | Continue excavation and exposing utility alignment
Fri (08/08) | 08 Aug 2025 | BR7A |  | Continue utility support welding works. Now workers on teabreak
Fri (08/08) | 08 Aug 2025 | BR3 |  | Continue cleaning and surface grinding, Plastering work for 300mm waterproofing termination in progress
Fri (08/08) | 08 Aug 2025 | CCE4 |  | Laying of debonding sheet prior to start with rebar installation
Fri (08/08) | 08 Aug 2025 | 800mm dia water pipe |  | Backfilling at completed area
Fri (08/08) | 08 Aug 2025 | PMH29 |  | Manhole cast. All manhole completed for 22KV diversion
Fri (08/08) | 08 Aug 2025 | PMH28-29 |  | Power duct laid
Fri (08/08) | 08 Aug 2025 | PMH26-28 |  | Abandoned drain hacking for removal
Fri (08/08) | 08 Aug 2025 | P45 |  | Current status of utility support installation
Fri (08/08) | 08 Aug 2025 | DR3 |  | Continue exposing of services for support installation
Fri (08/08) | 08 Aug 2025 | P47 |  | 11nos JGP grouting done
Fri (08/08) | 08 Aug 2025 | P48 Changi bound |  | KTC clearing materials
Fri (08/08) | 08 Aug 2025 | P49 |  | Rebar bending for 4th layer caisson work
Fri (08/08) | 08 Aug 2025 | P50 |  | New access erection and balance area formwork closing for 4th layer
Fri (08/08) | 08 Aug 2025 | P44 |  | Currently no activity of falsework erection. Crane supporting for stump casting
Fri (08/08) | 08 Aug 2025 | P43 |  | Stump casting done
Fri (08/08) | 08 Aug 2025 | Zone 1 |  | Now day shift dinner break
Fri (08/08) | 08 Aug 2025 | S2 |  | Column formwork closing. Tomorrow to cast
Fri (08/08) | 08 Aug 2025 | N1 |  | Platform prepared for segment launching. Tonight 3 segments to launch. Tomorrow 2nos
Fri (08/08) | 08 Aug 2025 | P44 |  | Current status of false work
Fri (08/08) | 08 Aug 2025 | P43 |  | Stump cast
Fri (08/08) | 08 Aug 2025 | P49 |  | Lowering down rebar for 4th layer caisson. P50: closing formwork for balance caisson
Fri (08/08) | 08 Aug 2025 | P47 |  | GCE end work
Fri (08/08) | 08 Aug 2025 | PMH28-29 |  | Started Power duct laying
Fri (08/08) | 08 Aug 2025 | PMH29 |  | Today to cast
Fri (08/08) | 08 Aug 2025 | PMH28-PMH29 |  | Pipe laying done, going to cast today
Fri (08/08) | 08 Aug 2025 | PMH29 |  | Ready to cast today afternoon
Fri (08/08) | 08 Aug 2025 | 800mm pipe laying |  | Removal of ERSS
Fri (08/08) | 08 Aug 2025 | PMH26-PMH28 |  | Excavation and ERSS
Fri (08/08) | 08 Aug 2025 | P48 |  | No activity
Fri (08/08) | 08 Aug 2025 | DR3 |  | Excavation on going
Sat (09/08) | 09 Aug 2025 | Exit 2 |  | ICE manual digging below services
Sat (09/08) | 09 Aug 2025 | Partial BR4 & partial BR3 |  | Waterproofing primer was applied and now continue membrane laying
Sat (09/08) | 09 Aug 2025 | BR3 |  | WH continue groove cutting at dwall side
Sat (09/08) | 09 Aug 2025 | GL28-29 | Selarang side | Excavation by WH to prepare area for hacking works & handover to Hirose. Singtel and Starhub alignment exposed. Starhub localised diversion planned for Monday
Sat (09/08) | 09 Aug 2025 | Blk 4 | GL26-27 | Utility support works completed
Sat (09/08) | 09 Aug 2025 | BR7A |  | Excavation ongoing
Sat (09/08) | 09 Aug 2025 | BR28 |  | Excavation on progress
Sat (09/08) | 09 Aug 2025 | Exit 1 ECM |  | Levelling ongoing. Today plan for casting
Sat (09/08) | 09 Aug 2025 | BR34 |  | Excavation in progress
Sat (09/08) | 09 Aug 2025 | Receiving shaft W2 |  | Formwork installation in progress. Target to cast on Monday
Sat (09/08) | 09 Aug 2025 | CCE4 |  | Rebar works in progress
Sat (09/08) | 09 Aug 2025 | BR17, BR18 |  | Continue rebar works
Sat (09/08) | 09 Aug 2025 | P24 TB |  | Rebar works and formwork installation in progress
Sat (09/08) | 09 Aug 2025 | Partial BR4, BR3 |  | Primer was applied. Currently no other activity
Sat (09/08) | 09 Aug 2025 | CCE4 |  | Continue exposing couplers and rebar works
Sat (09/08) | 09 Aug 2025 | BR28 |  | Continue excavation amd hacking works
Sat (09/08) | 09 Aug 2025 | Receiving shaft W2 |  | RTO inspection ongoing
Sat (09/08) | 09 Aug 2025 | BR17, BR18 |  | Rebar works in progress
Sat (09/08) | 09 Aug 2025 | Exit 3 |  | No activity. Preloading planned tmr
Sat (09/08) | 09 Aug 2025 | P24 TB |  | Rebar works ongoing
Mon (11/08) | 11 Aug 2025 | P14 SB |  | 6th pair stressing in progress
Mon (11/08) | 11 Aug 2025 | 800mm dia water pipe |  | ERSS installation and will continue with backfilling for traffic decking installation
Mon (11/08) | 11 Aug 2025 | PMH29 |  | Neck formwork closing
Mon (11/08) | 11 Aug 2025 | PMH28-29 |  | Duct laying
Mon (11/08) | 11 Aug 2025 | PMH26-28 |  | Abandoned drain removal
Mon (11/08) | 11 Aug 2025 | S1 |  | Pier rebar and formwork completed. Waiting for formwork COS to cast
Mon (11/08) | 11 Aug 2025 | CCE4 |  | Continue exposing of couplers & rebar installation work
Mon (11/08) | 11 Aug 2025 | RS W2 |  | Cleaning in progress, plan to cast it today
Mon (11/08) | 11 Aug 2025 | Exit 1 |  | Ongoing BR34 excavation & soil disposal
Mon (11/08) | 11 Aug 2025 | BR29 |  | Exposing of couplers it’s about to finish
Mon (11/08) | 11 Aug 2025 | BR27 |  | Excavation & hacking work is progress
Mon (11/08) | 11 Aug 2025 | P51 |  | Boring for inclinometer. Today to complete and tomorrow morning to install pipe
Mon (11/08) | 11 Aug 2025 | P50 |  | Balance caisson casting
Mon (11/08) | 11 Aug 2025 | P49 |  | Rebar completed around 50% for 4th layer caisson. Preparing for formwork closing
Mon (11/08) | 11 Aug 2025 | P49 Changi bound |  | Soil backfilling for platform. Wendyng to takeover the whole area after this
Mon (11/08) | 11 Aug 2025 | P48 |  | Today woh hup will handover this 1st layer 20% of balance caisson
Mon (11/08) | 11 Aug 2025 | DR3 |  | Current status of exposing services
Mon (11/08) | 11 Aug 2025 | P47 |  | 17nos of JGP points grouting done up to date
Mon (11/08) | 11 Aug 2025 | P45 |  | Continue welding of utility support. LE provided 9 workers
Mon (11/08) | 11 Aug 2025 | P45 |  | Today will cast utility stump
Mon (11/08) | 11 Aug 2025 | P3 |  | Side formwork assembly
Mon (11/08) | 11 Aug 2025 | P6-2 |  | ERSS extraction
Mon (11/08) | 11 Aug 2025 | P7-2 |  | Backfilling to pile cap level
Mon (11/08) | 11 Aug 2025 | P43 |  | Column rebar cage fabrication almost completed
Mon (11/08) | 11 Aug 2025 | P43 |  | Stump formwork removal
Mon (11/08) | 11 Aug 2025 | P44 |  | Now no activity. Settling document for the crane
Mon (11/08) | 11 Aug 2025 | Exit 2 |  | Continue manual excavation below services
Mon (11/08) | 11 Aug 2025 | BR7A |  | Excavation in progress. Now waiting for disposal to APSG
Mon (11/08) | 11 Aug 2025 | GL28-29 | Selarang side | Localised diversion for Starhub done
Mon (11/08) | 11 Aug 2025 | BR8A |  | Continue excavation for utility support
Mon (11/08) | 11 Aug 2025 | BR27 |  | Hacking works ongoing
Mon (11/08) | 11 Aug 2025 | Receiving shaft W2 |  | Casting started at 1750hrs
Mon (11/08) | 11 Aug 2025 | P16 |  | Preparing for PT bar stressing
Mon (11/08) | 11 Aug 2025 | P14 |  | Tonight will launch two segments
Mon (11/08) | 11 Aug 2025 | P7-1 |  | Current status of backfilling
Mon (11/08) | 11 Aug 2025 | S1 |  | Current status of pile cap rebar and formwork
Mon (11/08) | 11 Aug 2025 | S2 |  | Column casting done
Mon (11/08) | 11 Aug 2025 | P3 |  | Crosshead rebar work in progress
Mon (11/08) | 11 Aug 2025 | P45 |  | Utility support welding by LE
Mon (11/08) | 11 Aug 2025 | P47 |  | No activity already
Mon (11/08) | 11 Aug 2025 | P49 |  | Formwork closing for 4th layer caisson
Tue (12/08) | 12 Aug 2025 | P45 |  | Exposing services and utility support welding in progress. Note: LE provided 9 workers and ICE only one worker
Tue (12/08) | 12 Aug 2025 | P43 |  | Column rebar cage fabrication done. Today plan for final inspection
Tue (12/08) | 12 Aug 2025 | P14 |  | Setting up of 200T crane for stressing cage dismantling
Tue (12/08) | 12 Aug 2025 | BR4 |  | Continue waterproofing membrane laying
Tue (12/08) | 12 Aug 2025 | BR10 |  | Cutting groove lines along retaining wall for waterproofing works
Tue (12/08) | 12 Aug 2025 | BR7A |  | Excavation in progress
Tue (12/08) | 12 Aug 2025 | P51 |  | Preparing for installation of inclinometer
Tue (12/08) | 12 Aug 2025 | P50 |  | Formwork removal and clearing materials
Tue (12/08) | 12 Aug 2025 | P49 |  | 4th layer rebar installation done around 75%
Tue (12/08) | 12 Aug 2025 | P49 |  | Will casting around 25% of 4th layer caisson today
Tue (12/08) | 12 Aug 2025 | P48 |  | Manual excavation below services for balance caisson work
Tue (12/08) | 12 Aug 2025 | P47 |  | GCE should complete JGP in two days and handover to KTC
Tue (12/08) | 12 Aug 2025 | DR3 |  | Part 1 excavation completed. Will extend at P47 area
Tue (12/08) | 12 Aug 2025 | BR29 |  | Preparing to lay debonding sheet & exposing barrette piles to slab COL
Tue (12/08) | 12 Aug 2025 | BR28 |  | Excavation ongoing
Tue (12/08) | 12 Aug 2025 | CCE4 |  | Tunnel roof slab rebar, coupler exposure & P41 rebar work ongoing
Tue (12/08) | 12 Aug 2025 | 800mm dia water pipe |  | Preparing for traffic decking installation
Tue (12/08) | 12 Aug 2025 | PMH26-28 |  | Continue excavation and ERSS for duct laying
Tue (12/08) | 12 Aug 2025 | PMH26-PMH28 |  | Balance around 30m length power duct to complete this week
Tue (12/08) | 12 Aug 2025 | CCE4 |  | Ongoing rebar installation for tunnel roof slab
Tue (12/08) | 12 Aug 2025 | BR10 |  | Preparing to continue plastering work for 300mm waterproofing termination
Tue (12/08) | 12 Aug 2025 | P47 1st part |  | GCE will handover tomorrow
Tue (12/08) | 12 Aug 2025 | P45 |  | Main beam installation done. Balance secondary beam and utility support to be completed
Tue (12/08) | 12 Aug 2025 | BR7A |  | Excavation in progress
Tue (12/08) | 12 Aug 2025 | DR3 |  | Current excavation status. Excavation to expose utilities ongoing
Tue (12/08) | 12 Aug 2025 | P47 |  | Preparation for JGP work
Tue (12/08) | 12 Aug 2025 | P48 |  | No activity
Tue (12/08) | 12 Aug 2025 | P49 |  | L4 rebar works
Tue (12/08) | 12 Aug 2025 | P50 |  | Removal of L4 caisson formwork
Tue (12/08) | 12 Aug 2025 | Exit 1 |  | Continues BR34 excavation and soil disposal
Tue (12/08) | 12 Aug 2025 | P44 |  | Falsework installation in progress
Tue (12/08) | 12 Aug 2025 | P43 |  | Column rebar cage fabrication
Tue (12/08) | 12 Aug 2025 | 800mm PW |  | Traffic decking installation
Tue (12/08) | 12 Aug 2025 | PMH28-29 |  | Balance around 35m here to complete
Tue (12/08) | 12 Aug 2025 | P19 |  | Tendom wire pulling. Plan start stressing around Thursday
Tue (12/08) | 12 Aug 2025 | P16 |  | Clearing materials on crosshead. Tonight to lower down starter hanger to shift to P17
Tue (12/08) | 12 Aug 2025 | P14 |  | Tonight to continue work LF to shift to P15
Tue (12/08) | 12 Aug 2025 | S1 |  | Pile cap casting done
Tue (12/08) | 12 Aug 2025 | P7-1 |  | Waler and strut removal
Tue (12/08) | 12 Aug 2025 | P3 |  | Crosshead rebar work
Tue (12/08) | 12 Aug 2025 | P50 |  | Formwork removal and bring up to ground level
Tue (12/08) | 12 Aug 2025 | P49 |  | Rebar work continue. 1st part casting done for 4th layer
Tue (12/08) | 12 Aug 2025 | P48 |  | Access erection
Wed (13/08) | 13 Aug 2025 | P50 |  | Annex C&D received. Today will start excavation to final layer for pile cap
Wed (13/08) | 13 Aug 2025 | P49 |  | 1st part for 4th layer casting done. Continue rebar and formwork for balance area. This week will complete 100% for this layer
Wed (13/08) | 13 Aug 2025 | P48 |  | Rebar work for balance 20% of caisson for 1st layer. This week to complete
Wed (13/08) | 13 Aug 2025 | P47 |  | JGP grouting at 2nd part. 1st part handover to WH & KTC
Wed (13/08) | 13 Aug 2025 | DR3 |  | KTC resume excavation to expose services at 1st part
Wed (13/08) | 13 Aug 2025 | P45 |  | Continue exposing services and support welding. ICE/WH : 3 workers. LE- 9 workers
Wed (13/08) | 13 Aug 2025 | P14 |  | Preparation for stressing cage lowering down
Wed (13/08) | 13 Aug 2025 | P17 |  | Tidy up barricade and toe board installation. Preparation for starter hanger shifting
Wed (13/08) | 13 Aug 2025 | Zone 1 P1 |  | Boring rig demob. Left kelly bar to demob this evening
Wed (13/08) | 13 Aug 2025 | P3 |  | Bottom main bar installation in progress. Manpower 9+1
Wed (13/08) | 13 Aug 2025 | P4 |  | Falsework erection started
Wed (13/08) | 13 Aug 2025 | CCE4 |  | Ongoing rebar installation for tunnel roof slab
Wed (13/08) | 13 Aug 2025 | Exit 1 |  | Continues excavation for BR34
Wed (13/08) | 13 Aug 2025 | BR29 |  | Rebar installation is in progress
Wed (13/08) | 13 Aug 2025 | P4 |  | Falsework erection in progress
Wed (13/08) | 13 Aug 2025 | Exit 2 |  | Utility support works in progress
Wed (13/08) | 13 Aug 2025 | 800mm dia water pipe laying |  | Decking installed. Will open back lane soon
Wed (13/08) | 13 Aug 2025 | P1 |  | Soldier pile installation in progress
Wed (13/08) | 13 Aug 2025 | S1 |  | Rebar installation for column stump
Wed (13/08) | 13 Aug 2025 | P7-1 |  | Waler brackets dismantling in progress
Wed (13/08) | 13 Aug 2025 | BR3 |  | Waterproofing membrane laying in progress
Wed (13/08) | 13 Aug 2025 | BR10 |  | Dewatering ongoing
Wed (13/08) | 13 Aug 2025 | BR7A |  | Excavation in progress
Wed (13/08) | 13 Aug 2025 | BR8B |  | Levelling and soil disposal works
Wed (13/08) | 13 Aug 2025 | P49 |  | L4 formwork closing
Wed (13/08) | 13 Aug 2025 | P48 | north | L1 rebar work ongoing
Wed (13/08) | 13 Aug 2025 | P19 |  | Strand pulling for PT
Wed (13/08) | 13 Aug 2025 | P45 |  | Utility support installation
Wed (13/08) | 13 Aug 2025 | DR3 |  | Excavation to expose utilities
Wed (13/08) | 13 Aug 2025 | P47 |  | JGP work ongoing
Wed (13/08) | 13 Aug 2025 | P47 |  | Instrument installation (last point)
Wed (13/08) | 13 Aug 2025 | P44 |  | Falsework main beam installation
Wed (13/08) | 13 Aug 2025 | P19 |  | Tendom wire pulling. Tomorrow to complete
Wed (13/08) | 13 Aug 2025 | P16 |  | Dismantling of spreader beam to shift to P17
Wed (13/08) | 13 Aug 2025 | P14 |  | Preparing to dismantle winch and shift to P15 tonight
Wed (13/08) | 13 Aug 2025 | S1 |  | Preparing for stump link bar installation
Wed (13/08) | 13 Aug 2025 | BR29 |  | Rebar works in progress
Wed (13/08) | 13 Aug 2025 | CCE4 |  | Rebar works in progress
Wed (13/08) | 13 Aug 2025 | BR34 |  | Excavation in progress
Wed (13/08) | 13 Aug 2025 | BR3 |  | Waterproofing membrane sealing works ongoing. Maxbond working till 9pm
Wed (13/08) | 13 Aug 2025 | BR7A |  | Excavation and disposal ongoing
Wed (13/08) | 13 Aug 2025 | Exit 2 |  | Utility support works ongoing
Wed (13/08) | 13 Aug 2025 | BR17, BR18A |  | Rebar works and partial formwork installation
Wed (13/08) | 13 Aug 2025 | P3 |  | Assembling of side formwork
Wed (13/08) | 13 Aug 2025 | P1 |  | Balance 12nos soldier pile to complete. Tomorrow plan to complete. Now preparing to demob kelly bar
Wed (13/08) | 13 Aug 2025 | P3 |  | Crosshead rebar work in progress
Wed (13/08) | 13 Aug 2025 | DR3 |  | Access erection to excavated area
Wed (13/08) | 13 Aug 2025 | P48 |  | LE prepare strut base plate. Tomorrow Woh Hup will arrange for overall housekeeping, access, barricade and tidy up work area
Wed (13/08) | 13 Aug 2025 | P50 |  | KTC started excavation for caisson final layer
Wed (13/08) | 13 Aug 2025 | PMH28-29 |  | Balance around 25m to complete excavation and ERSS for duct laying
Wed (13/08) | 13 Aug 2025 | PMH26-PMH28 |  | Excavation completed, around 40m length. Balance levelling and lean concrete for Power duct laying
Wed (13/08) | 13 Aug 2025 | 800mm dia water pipe |  | Today to complete excavation. Tomorrow move to 2nd lane for decking installation
Thu (14/08) | 14 Aug 2025 | Exit 1 |  | Continues BR34 excavation & soil disposal
Thu (14/08) | 14 Aug 2025 | Tunnel Roof Slab towards P42 |  | Coupler drilling ongoing
Thu (14/08) | 14 Aug 2025 | P42 |  | Bottom coupler rebar installation ongoing
Thu (14/08) | 14 Aug 2025 | P41 |  | Current status
Thu (14/08) | 14 Aug 2025 | Below P40 |  | Top bar installation/tying ongoing
Thu (14/08) | 14 Aug 2025 | P3 |  | Top Rebar installation in progress crosshead
Thu (14/08) | 14 Aug 2025 | P4 |  | Falsework erection ongoing
Thu (14/08) | 14 Aug 2025 | P1 |  | Soldier piles and steel plates installation for ERSS works. Target to complete tmr morning
Thu (14/08) | 14 Aug 2025 | PMH26-28 |  | Prepare pipe head to connect the power duct
Thu (14/08) | 14 Aug 2025 | PMH28-29 |  | Lean concrete done for one span. Tonight to continue duct laying for 22KV
Thu (14/08) | 14 Aug 2025 | P19 |  | Tendon wires installation in progress. Tmr to start stressing works
Thu (14/08) | 14 Aug 2025 | P17 |  | Starter hanger installation works. Tonight to commence segment launching
Thu (14/08) | 14 Aug 2025 | P15 |  | Lifting frame installation works in progress
Thu (14/08) | 14 Aug 2025 | N1 |  | Scaffold erection for segment launching
Thu (14/08) | 14 Aug 2025 | S2 |  | Column formwork dismantling
Thu (14/08) | 14 Aug 2025 | S1 |  | Column stump rebar works installation
Thu (14/08) | 14 Aug 2025 | P7-1 |  | KTC backfilling work ongoing
Thu (14/08) | 14 Aug 2025 | P50 |  | KTC continue excavation for final layer caisson
Thu (14/08) | 14 Aug 2025 | P48 |  | Preparing to close formwork for the last 15% of caisson for 1st layer. Working space a bit tight due to cluster of services here. The next level will be a bit more flexible to work
Thu (14/08) | 14 Aug 2025 | DR3 |  | Exposing of services and UKP for supporting. P47 1st part area handover to KTC already by GCE
Thu (14/08) | 14 Aug 2025 | P45 |  | Utility support installation
Thu (14/08) | 14 Aug 2025 | P43 |  | Column rebar erection
Thu (14/08) | 14 Aug 2025 | P44 |  | Falsework main beam installation
Thu (14/08) | 14 Aug 2025 | Zone 4 |  | Site inspection with QPS, Contractor and Subcontractor to keep up site safety ( access, barricade, machinery, utility support, ERSS, housekeeping, etc)
Thu (14/08) | 14 Aug 2025 | Exit 2 |  | Utility support works in progress. Target to complete by this week
Thu (14/08) | 14 Aug 2025 | BR4, BR3 |  | Membrane cleaning ongoing. Today plan for protection screeding works, BR10: Surface grinding and plastering works ongoing
Thu (14/08) | 14 Aug 2025 | BR29 |  | Continues rebar installation work
Thu (14/08) | 14 Aug 2025 | BR28 |  | Exposing of couplers is in progress
Fri (15/08) | 15 Aug 2025 | PMH26-28 |  | Preparing duct laying. Note: excavated depth at DR4 area is less than 1m. ERSS is to support casting only
Fri (15/08) | 15 Aug 2025 | 800mm dia water pipe laying |  | Premix removal for decking installation
Fri (15/08) | 15 Aug 2025 | P49 |  | Formwork closing at north side, today casting (last section)
Fri (15/08) | 15 Aug 2025 | P50 |  | Excavation to L5 caisson ongoing
Fri (15/08) | 15 Aug 2025 | P19 |  | Stressing works in progress
Fri (15/08) | 15 Aug 2025 | P17 |  | 2 segment launched last night. Adjustment works ongoing
Fri (15/08) | 15 Aug 2025 | P15 |  | Lifting frame installation works
Fri (15/08) | 15 Aug 2025 | P14 |  | Dismantling of balance 2 nos. of lifting frame to P15
Fri (15/08) | 15 Aug 2025 | N1 |  | Scaffold erection for segment launching in progress
Fri (15/08) | 15 Aug 2025 | P45 |  | Utility support installation
Fri (15/08) | 15 Aug 2025 | DR3 |  | Excavation to expose utilities in progress
Fri (15/08) | 15 Aug 2025 | P48 | south | S1 strut installation
Fri (15/08) | 15 Aug 2025 | P48 | north | Caisson formwork closing, will do housekeeping before casting today
Fri (15/08) | 15 Aug 2025 | P1 |  | Continue ERSS installation. Today to complete
Fri (15/08) | 15 Aug 2025 | P3 |  | Rebar installation for crosshead
Fri (15/08) | 15 Aug 2025 | P4 |  | Falsework erection ongoing
Fri (15/08) | 15 Aug 2025 | S1 |  | Rebar for column stump completed. Pending inspection before Formwork closing. Tmr to cast
Fri (15/08) | 15 Aug 2025 | P7-1 |  | KTC backfilling completed
Fri (15/08) | 15 Aug 2025 | S2 |  | Column formwork dismantled
Fri (15/08) | 15 Aug 2025 | Exit 1 |  | Partial lean con was done last night, will continue BR34 excavation & soil disposal
Fri (15/08) | 15 Aug 2025 | CCE4 |  | Continues with rebar installation for tunnel roof slab
Fri (15/08) | 15 Aug 2025 | BR27 |  | Continues excavation & soil disposal
Fri (15/08) | 15 Aug 2025 | BR29 |  | Rebar installation is in progress
Fri (15/08) | 15 Aug 2025 | PMH28-29 |  | 12m length of Power duct casting
Fri (15/08) | 15 Aug 2025 | 800mm dia water pipe laying |  | Abandoned drain removal for decking installation
Fri (15/08) | 15 Aug 2025 | PMH26-28 |  | Power duct laying
Fri (15/08) | 15 Aug 2025 | P50 |  | Excavation to final layer with long arm
Fri (15/08) | 15 Aug 2025 | P49 |  | Casting of 4th layer last part. 100% casting done for 4th layer after this
Fri (15/08) | 15 Aug 2025 | P48 |  | 4nos diagonal struts installed. Continue welding
Fri (15/08) | 15 Aug 2025 | P45 |  | Utility support welding completed. MPI test done
Fri (15/08) | 15 Aug 2025 | DR3 |  | Top soil removal and preparing for utility support installation
Fri (15/08) | 15 Aug 2025 | P19 |  | Continue crosshead stressing works
Fri (15/08) | 15 Aug 2025 | P17 |  | Segment adjustment ongoing
Fri (15/08) | 15 Aug 2025 | P15 |  | 3rd LF installation works ongoing
Fri (15/08) | 15 Aug 2025 | N1 |  | Current scaffold erection status
Fri (15/08) | 15 Aug 2025 | S1 |  | Formwork closing for column stump. Tmr to cast
Fri (15/08) | 15 Aug 2025 | P7-1 |  | ERSS extraction ongoing
Fri (15/08) | 15 Aug 2025 | P4 |  | Materials unloading for tonight Falsework installation
Fri (15/08) | 15 Aug 2025 | P3 |  | Crosshead rebar installation
Fri (15/08) | 15 Aug 2025 | P1 |  | ERSS installation completed. Balance further lowering of the ERSS. Today to complete
Fri (15/08) | 15 Aug 2025 | PMH28-29 |  | Duct laying done for last night. Today to cast
Sat (16/08) | 16 Aug 2025 | P44 |  | Crosshead Falsework erection in progress
Sat (16/08) | 16 Aug 2025 | P43 |  | Column rebar works ongoing
Sat (16/08) | 16 Aug 2025 | DR3 |  | Top soil removal and preparation for utility support installation
Sat (16/08) | 16 Aug 2025 | P47 |  | JGP for P47-54 completed. Preparation to shift to P47-11
Sat (16/08) | 16 Aug 2025 | P48 |  | Strutting installation works
Sat (16/08) | 16 Aug 2025 | P49 |  | Formwork dismantling for 4th layer cassion wall
Sat (16/08) | 16 Aug 2025 | P50 |  | KTC Excavation for final layer
Sat (16/08) | 16 Aug 2025 | PMH26-28 |  | Power ducts laying works
Sat (16/08) | 16 Aug 2025 | Zone 4 |  | Decking installation for 800mm dia water pipe laying
Sat (16/08) | 16 Aug 2025 | P1 |  | KTC Exacation to S1 layer
Sat (16/08) | 16 Aug 2025 | P3 |  | Crosshead rebar installation ongoing
Sat (16/08) | 16 Aug 2025 | P4 |  | Falsework current status
Sat (16/08) | 16 Aug 2025 | P4 |  | Premix removal for Falsework erection works
Sat (16/08) | 16 Aug 2025 | P7-1 |  | ERSS extraction completed. column CJ roughening ongoing
Sat (16/08) | 16 Aug 2025 | S1 |  | Scffold erection for column stump casting
Sat (16/08) | 16 Aug 2025 | N1 |  | Scaffold erection current status
Sat (16/08) | 16 Aug 2025 | P15 |  | Lifter frame installation works
Sat (16/08) | 16 Aug 2025 | P17 |  | Netting installation for segment in progress
Sat (16/08) | 16 Aug 2025 | P19 |  | Cutting of excess tendon wire strand and installation of capping, Dismantling of falsework support ongoing
Sat (16/08) | 16 Aug 2025 | P44 |  | Falsework erection current status. Workers on break now
Sat (16/08) | 16 Aug 2025 | P43 |  | Column rebar rectification works ongoing as per RTO comments prior to Formwork closing
Sat (16/08) | 16 Aug 2025 | P48 |  | LE Continue strutting installation works
Sat (16/08) | 16 Aug 2025 | Zone 4 |  | HSL mobilisation of excavator and materials for P50 BP hacking
Sat (16/08) | 16 Aug 2025 | DR3 |  | Preparation for utility support installation
Sat (16/08) | 16 Aug 2025 | PMH26-28 |  | Power ducts laying works
Sat (16/08) | 16 Aug 2025 | Zone 4 |  | Decking installation completed for 1 lane. Tmr to continue decking installation on the next lane
Sat (16/08) | 16 Aug 2025 | P1 |  | KTC Excavation to s1 layer in progress
Sat (16/08) | 16 Aug 2025 | P3 |  | Crosshead Rebar and tendon ducts installation
Sat (16/08) | 16 Aug 2025 | P4 |  | Falsework assembly works in progress
Sat (16/08) | 16 Aug 2025 | P7-1 |  | ERSS extraction completed
Sat (16/08) | 16 Aug 2025 | S1 |  | Column stump casting ongoing
Sat (16/08) | 16 Aug 2025 | P15 |  | Stressing cage installation ongoing
Sat (16/08) | 16 Aug 2025 | P17 |  | Segment adjustment in progress
Sat (16/08) | 16 Aug 2025 | P19 |  | Falsework support dismantling
Sat (16/08) | 16 Aug 2025 | P20 |  | Column surface grinding works
Mon (18/08) | 18 Aug 2025 | P17 1st pair |  | Segment adjusting on going
Mon (18/08) | 18 Aug 2025 | PMH26-PMH28 |  | Power laying and casting 100% completed. Note: duct will not cast at DR4 area to facilitate for drain work
Mon (18/08) | 18 Aug 2025 | PMH28-29 |  | Balance this area to complete excavation and duct laying
Mon (18/08) | 18 Aug 2025 | CCE4 |  | Ongoing rebar installation for tunnel roof slab
Mon (18/08) | 18 Aug 2025 | P15 |  | Installation of counterweights for load testing
Mon (18/08) | 18 Aug 2025 | 22KV branch out at PMH26 |  | Continue expose services to undercross the duct
Mon (18/08) | 18 Aug 2025 | BR29 |  | Rebar installation is in progress
Mon (18/08) | 18 Aug 2025 | BR27 |  | Continues excavation & soil disposal
Mon (18/08) | 18 Aug 2025 | Exit 1 |  | Exposing of couplers for BR34
Mon (18/08) | 18 Aug 2025 | Exit 1 |  | Continue BR34 excavation
Mon (18/08) | 18 Aug 2025 | S2 |  | Scaffold support assembly for pier rebar cage fabrication
Mon (18/08) | 18 Aug 2025 | P7-1 |  | ERSS fully extracted. Preparation for backfilling to ground level
Mon (18/08) | 18 Aug 2025 | P3 |  | PT duct installation in progress
Mon (18/08) | 18 Aug 2025 | P45 |  | Current status of falsework/ working platform erection for crosshead
Mon (18/08) | 18 Aug 2025 | P43 |  | Formwork closing for column
Mon (18/08) | 18 Aug 2025 | P44 |  | Access scaffold erection for crosshead
Mon (18/08) | 18 Aug 2025 | P50 |  | No activity
Mon (18/08) | 18 Aug 2025 | P44 |  | Access scaffold erection for crosshead
Mon (18/08) | 18 Aug 2025 | P43 |  | Formwork closing for column
Mon (18/08) | 18 Aug 2025 | N1 |  | 1st pair segment adjusting
Mon (18/08) | 18 Aug 2025 | P17 1st pair |  | Segment adjusting on going
Mon (18/08) | 18 Aug 2025 | P19 |  | Falsework dismantling
Mon (18/08) | 18 Aug 2025 | P15 |  | No activity
Mon (18/08) | 18 Aug 2025 | S1 |  | Stump casting completed
Mon (18/08) | 18 Aug 2025 | P4 |  | Falsework erection
Mon (18/08) | 18 Aug 2025 | P3 |  | PT duct installation in progress
Mon (18/08) | 18 Aug 2025 | P44-P45 |  | Preparation work for Junction JGP TT
Mon (18/08) | 18 Aug 2025 | DR3 & P47 |  | No soil disposal activity
Tue (19/08) | 19 Aug 2025 | P42-41 w tunnel roof slab |  | Rebar work / coupler planting ongoing
Tue (19/08) | 19 Aug 2025 | Exit 1 |  | Exposing of couplers @ BR34
Tue (19/08) | 19 Aug 2025 | Exit 1 |  | BR34 continues excavation & soil disposal, target to complete by today
Tue (19/08) | 19 Aug 2025 | Exit 2 |  | Utility support works completed
Tue (19/08) | 19 Aug 2025 | BR7A |  | Current status of excavation. ~85% excavation completed. Today plan for lean con casting at dwall side
Tue (19/08) | 19 Aug 2025 | GL28-29 |  | Current status of decking stump
Tue (19/08) | 19 Aug 2025 | GL29-GL E1 |  | Decking panels completed. VIG welding wokrs ongoing
Tue (19/08) | 19 Aug 2025 | BR3 |  | Waterproofing membrane works in progress, BR10: Preparation for waterproofing works & balance retaining wall works ongoing
Tue (19/08) | 19 Aug 2025 | BR29 |  | Rebar & formwork installation is in progress
Tue (19/08) | 19 Aug 2025 | BR28 |  | Started laying of debonding sheet
Tue (19/08) | 19 Aug 2025 | BR27 |  | Excavation and hardcore/soil disposal
Tue (19/08) | 19 Aug 2025 | BR19, BR20 |  | Excavation in progress
Tue (19/08) | 19 Aug 2025 | GL28-29 | Blk 4 | Top plate welding for utility supports works ongoing and disposal works
Tue (19/08) | 19 Aug 2025 | PMH28-PM29 |  | Today plan for lean concrete. 20m length
Tue (19/08) | 19 Aug 2025 | 800mm dia water pipe laying |  | Reinstate the decking to open back to public
Tue (19/08) | 19 Aug 2025 | PMH28 branch out |  | 12m duct laid. Backfilling and reinstate the area
Tue (19/08) | 19 Aug 2025 | P19 |  | Falsework dismantling
Tue (19/08) | 19 Aug 2025 | P17 1st pair |  | Segment adjusting on going
Tue (19/08) | 19 Aug 2025 | P17 |  | 4nos load test completed. Now dismantling the load. Tonight going to launch Northbound 2nos segments
Tue (19/08) | 19 Aug 2025 | P13 |  | Scaffold access installation
Tue (19/08) | 19 Aug 2025 | N1 |  | Segment adjustment ongoing
Tue (19/08) | 19 Aug 2025 | S1 |  | Formwork dismantling
Tue (19/08) | 19 Aug 2025 | P7-1 |  | Chipping work for pile CJ
Tue (19/08) | 19 Aug 2025 | P3 |  | PT duct installation in progress
Tue (19/08) | 19 Aug 2025 | P4 |  | Falsework installation in progress
Tue (19/08) | 19 Aug 2025 | PMH28-PMH29 |  | Lean concrete completed, tomorrow do pipe laying
Tue (19/08) | 19 Aug 2025 | PMH28 branch out |  | 12m duct laid. Backfilling completed
Tue (19/08) | 19 Aug 2025 | P50 |  | No activity
Tue (19/08) | 19 Aug 2025 | P45 |  | Utility support work in progress
Tue (19/08) | 19 Aug 2025 | P44 |  | Scaffolding erection and falsework installation
Tue (19/08) | 19 Aug 2025 | P43 |  | Column formwork closing
Wed (20/08) | 20 Aug 2025 | P17 |  | 1st pair final alignment to confirm today. WH shifting stitching formwork for installation tonight
Wed (20/08) | 20 Aug 2025 | PMH29 to link up point |  | Clearing materials and plants to continue excavation
Wed (20/08) | 20 Aug 2025 | PMH28-29 |  | Preparing for balance area for duct laying
Wed (20/08) | 20 Aug 2025 | P7-1 |  | Column compensation bar pull out test
Wed (20/08) | 20 Aug 2025 | P1 |  | MPI test for s1 layer waler and struts ongoing
Wed (20/08) | 20 Aug 2025 | P3 |  | Tendon duct installation ongoing
Wed (20/08) | 20 Aug 2025 | P4 |  | Falsework installation in progress
Wed (20/08) | 20 Aug 2025 | BR34 |  | Today target to lean concrete for the remaining portion
Wed (20/08) | 20 Aug 2025 | CCE4 |  | Formwork installation for P41
Wed (20/08) | 20 Aug 2025 | CCE4 |  | Started bottom bar installation for P42 side
Wed (20/08) | 20 Aug 2025 | BR10 |  | Waterproofing membrane installation and sealing application, Plastering ongoing for waterproofing works termination
Wed (20/08) | 20 Aug 2025 | P50 |  | Bored pile hacking in progress
Wed (20/08) | 20 Aug 2025 | P49 |  | No activity
Wed (20/08) | 20 Aug 2025 | BR7A |  | Excavation ~90% completed
Wed (20/08) | 20 Aug 2025 | GL28-29 | Blk 4 | Excavation for utility support works. Top plate welding for UKP completed
Wed (20/08) | 20 Aug 2025 | BR10 balance retaining wall |  | Hyrib hacking ongoing
Wed (20/08) | 20 Aug 2025 | BR29 |  | Rebar installation is in progress
Wed (20/08) | 20 Aug 2025 | BR27 |  | Continues hacking & disposal work
Wed (20/08) | 20 Aug 2025 | P48 |  | Formwork closing for L1 caisson
Wed (20/08) | 20 Aug 2025 | P47 |  | JGP no activity
Wed (20/08) | 20 Aug 2025 | DR3 |  | No activity
Wed (20/08) | 20 Aug 2025 | P45 |  | Utility support installation
Wed (20/08) | 20 Aug 2025 | Gate 5 |  | Pre-DLP inspection for PW300 before inspection by PUB NS team
Wed (20/08) | 20 Aug 2025 | P43 |  | Column ready for casting today
Wed (20/08) | 20 Aug 2025 | P44 |  | Falsework installation ongoing
Wed (20/08) | 20 Aug 2025 | BR17, BR18A |  | Casting in progress
Wed (20/08) | 20 Aug 2025 | PMH28-29 |  | Power duct laying in progress
Wed (20/08) | 20 Aug 2025 | 800mm dia water pipe laying |  | ERSS installed. Prepare to reinstate the area
Wed (20/08) | 20 Aug 2025 | P50 |  | Bored pile hacking in progress
Wed (20/08) | 20 Aug 2025 | P49 |  | Excavation to L5 caisson layer started
Wed (20/08) | 20 Aug 2025 | PMH23 branch out |  | Excavation and erss on going
Wed (20/08) | 20 Aug 2025 | P47 |  | JGP works
Wed (20/08) | 20 Aug 2025 | Partial BR3 and BR10 |  | Waterproofing membrane installation, Balance BR10 area: Continue groove line cutting and cleaning ongoing before handover to Maxbond
Wed (20/08) | 20 Aug 2025 | Balance BR10 retaining wall |  | CJ cleaning. Tmr plan for rebar pull-out test
Wed (20/08) | 20 Aug 2025 | BR7A |  | Hacking of excess concrete at UKP area
Wed (20/08) | 20 Aug 2025 | BR8B |  | Waiting for COS for crane parking at decking area to facilitate decking works
Wed (20/08) | 20 Aug 2025 | P7-1 |  | Soil backfilling and levelling for 2nd stage column installation
Wed (20/08) | 20 Aug 2025 | P4 | NB side | Primary beam installation in progress
Wed (20/08) | 20 Aug 2025 | P3 crosshead section 1 |  | Cast in anchor installation on going
Wed (20/08) | 20 Aug 2025 | P1 |  | Railing installation. Tonight KTC will mobilise long arm excavator
Wed (20/08) | 20 Aug 2025 | CCW W4-W7 |  | Struts welding and installation works in progress
Wed (20/08) | 20 Aug 2025 | P24 |  | Exposing couplers
Wed (20/08) | 20 Aug 2025 | P15 |  | NB Strand pulling for post tensioning, SB ready for 2nos segment launching
Wed (20/08) | 20 Aug 2025 | P17 |  | Strand pulling for post tensioning
Wed (20/08) | 20 Aug 2025 | BR19, BR20 |  | Exposing couplers and preparing for lean con works
Wed (20/08) | 20 Aug 2025 | BR28 |  | Rebar works in progress
Wed (20/08) | 20 Aug 2025 | BR29 |  | Rebar works in progress
Wed (20/08) | 20 Aug 2025 | CCE4 |  | P41 transfer beam shearlinks installation in progress
Wed (20/08) | 20 Aug 2025 | CCE4 P42 side |  | Rebar works ongoing
Wed (20/08) | 20 Aug 2025 | S1 |  | No activity
Wed (20/08) | 20 Aug 2025 | P7-1 |  | No activity
Wed (20/08) | 20 Aug 2025 | P1 |  | KTC long arm and excavator ready at P1, going to start excavation
Wed (20/08) | 20 Aug 2025 | P3 crosshead section 1 |  | Cast in anchor installation on going
Wed (20/08) | 20 Aug 2025 | P4 | NB side | Primary beam installation in progress
Wed (20/08) | 20 Aug 2025 | PMH29+ |  | Excavation and ERSS
Wed (20/08) | 20 Aug 2025 | P43 |  | Column ready for casting. Pump truck standby, waiting for concrete
Wed (20/08) | 20 Aug 2025 | PMH26-28 |  | Reinstate the area. Left some levelling
Thu (21/08) | 21 Aug 2025 | Partial BR3 & BR10 |  | Membrane cleaning works ongoing, Balance BR10 retaining wall works: Preparing for rebar pull-out test
Thu (21/08) | 21 Aug 2025 | BR7A |  | Hacking on dwall surface to expose couplers
Thu (21/08) | 21 Aug 2025 | P3 crosshead |  | Section 1: links installation, Section 2 and 3: PT duct installation
Thu (21/08) | 21 Aug 2025 | P15 |  | 2nd pair strand pulling and post tensioning
Thu (21/08) | 21 Aug 2025 | Exit 1 |  | Clearing of stockpile from the new ECM pond
Thu (21/08) | 21 Aug 2025 | N1 1st pair |  | Adjustment completed. Now shifting of formwork for stitching. Target to cast on Saturday night
Thu (21/08) | 21 Aug 2025 | P50 |  | Bored pile hacking at south side
Thu (21/08) | 21 Aug 2025 | Exit 1 |  | BR34 remaining portion plan to lean concrete by today
Thu (21/08) | 21 Aug 2025 | CCE4 |  | Continues rebar installation for tunnel roof slab
Thu (21/08) | 21 Aug 2025 | P48 |  | Slope protection casting
Thu (21/08) | 21 Aug 2025 | P49 |  | Excavation to L6 caisson level
Thu (21/08) | 21 Aug 2025 | BR27 |  | Continues hacking work
Thu (21/08) | 21 Aug 2025 | BR28 |  | Started rebar installation work
Thu (21/08) | 21 Aug 2025 | BR29 |  | Continues rebar & formwork installation
Thu (21/08) | 21 Aug 2025 | P47 |  | JGP works on going
Thu (21/08) | 21 Aug 2025 | P44 |  | Base formwork installation
Thu (21/08) | 21 Aug 2025 | P43 |  | Column concrete curing. No activity
Thu (21/08) | 21 Aug 2025 | BR20 |  | Excavation in progress
Thu (21/08) | 21 Aug 2025 | BR19 |  | Exposing couplers
Thu (21/08) | 21 Aug 2025 | Exit 2 |  | Continue straightening of rebars for capping beam works
Thu (21/08) | 21 Aug 2025 | P15 2nd pair |  | NB: stressing completed, SB: hydraulic jack installation for stressing
Thu (21/08) | 21 Aug 2025 | BR7A |  | Partial LSS backfill done
Thu (21/08) | 21 Aug 2025 | GL28-29 | Selarang side | COS received for crane parking at completed decking area. Now Hirose has resumed main beam installation for decking. Balance materials to be delivered today
Thu (21/08) | 21 Aug 2025 | GL28-29 | blk 4 | Current status of abandoned drain hacking
Thu (21/08) | 21 Aug 2025 | Balance BR3 and partial BR10 |  | BRC laying for waterproofing protection screeding. Thereafter to cast
Thu (21/08) | 21 Aug 2025 | GL11-13 | blk 2 | Utilities protection steel plates installation in progress
Thu (21/08) | 21 Aug 2025 | 800mm PW |  | Completed 7.5m pipe laying today, now closing back the traffic deck and ready to open back the lane
Thu (21/08) | 21 Aug 2025 | PMH28-PMH29 |  | Pipe laying 10m casting completed, balance 6m going to cast tonight
Thu (21/08) | 21 Aug 2025 | P3 |  | PT duct and cast in anchor installation continue
Thu (21/08) | 21 Aug 2025 | PMH23 branch out |  | Pipe laying completed for the day
Thu (21/08) | 21 Aug 2025 | P48 |  | Last section for 1st layer caison to cast tonight
Thu (21/08) | 21 Aug 2025 | P15 2nd pair |  | Stressing completed. Strand cutting and grouting cap installation in progress
Thu (21/08) | 21 Aug 2025 | P6-2 |  | Soldier pile demob from site
Thu (21/08) | 21 Aug 2025 | P4 |  | Working platform 90% completed. Tonight to lay plywoods
Thu (21/08) | 21 Aug 2025 | P3 section 2 and 3 |  | PT duct and cast in anchor to complete tomorrow. 70% completed
Thu (21/08) | 21 Aug 2025 | P1 |  | Scaffold access erection to S2 layer
Thu (21/08) | 21 Aug 2025 | P1 |  | Side gate gantry erection
Thu (21/08) | 21 Aug 2025 | BR17, BR18A |  | Casting in progress. Waiting for another 2 more trucks
Fri (22/08) | 22 Aug 2025 | P42 |  | Bottom bar inspection ongoing
Fri (22/08) | 22 Aug 2025 | PMH28-PMH29 |  | ERSS dismantling
Fri (22/08) | 22 Aug 2025 | Exit 1 | BR34 | Lean con completed, pending coupler exposure
Fri (22/08) | 22 Aug 2025 | Exit 1 | BR34 GL BC | Current status
Fri (22/08) | 22 Aug 2025 | BR29 & P38 |  | Rebar work ongoing
Fri (22/08) | 22 Aug 2025 | BR28 |  | Bottom rebar laying ongoing & excavation ongoing for BR25-27
Fri (22/08) | 22 Aug 2025 | BR3, partial BR10 |  | Waterproofing protection screeding completed yesterday
Fri (22/08) | 22 Aug 2025 | Balance area for BR10 waterproofing |  | Partial primer applied
Fri (22/08) | 22 Aug 2025 | Balance BR10 retaining wall |  | Waiting for scaffold erection at other side before start rebar works
Fri (22/08) | 22 Aug 2025 | BR7A |  | LSS backfilling completed earlier this morning. Now WH erecting access
Fri (22/08) | 22 Aug 2025 | BR20 |  | Excavation in progress
Fri (22/08) | 22 Aug 2025 | GL28-29 | Blk 4 | Hirose secondary beam installation in progress for utility support and access installation ongoing by WH
Fri (22/08) | 22 Aug 2025 | P43 |  | Tomorrow plan to dismantle formwork
Fri (22/08) | 22 Aug 2025 | P45 |  | Excavation to L1 caisson level
Fri (22/08) | 22 Aug 2025 | PMH23 branching out |  | Excavation and ERSS
Fri (22/08) | 22 Aug 2025 | P48 |  | Formwork dismantling
Fri (22/08) | 22 Aug 2025 | P50 |  | Hacking of bored pile at south side
Fri (22/08) | 22 Aug 2025 | P17 |  | SB side formwork installation for 1st pair wet stitching
Fri (22/08) | 22 Aug 2025 | P15 |  | Stressing works in progress for NB-U03 and NB-D03
Fri (22/08) | 22 Aug 2025 | P7-1 |  | Crane parking platform preparation for column rebar cage installation
Fri (22/08) | 22 Aug 2025 | 800mm dia water pipe laying |  | Preparing to lower down 6m length pipe
Fri (22/08) | 22 Aug 2025 | PMH29 to link up area |  | Duct laying almost completed. 12m length to extend
Fri (22/08) | 22 Aug 2025 | P4 |  | Scaffold erection completed. Continue Falsework installation
Fri (22/08) | 22 Aug 2025 | P3 |  | Shear links installation in progress
Fri (22/08) | 22 Aug 2025 | Exit 2 |  | Capping beam rebar works ongoing
Fri (22/08) | 22 Aug 2025 | P1 |  | Excavation and soil clearing for S2 layer in progress. Today to complete
Fri (22/08) | 22 Aug 2025 | BR8B |  | Primary beam installation ongoing
Fri (22/08) | 22 Aug 2025 | BR8A |  | Utility beams welding works ongoing
Fri (22/08) | 22 Aug 2025 | P50 |  | Pile head hacking at TPE bound was done. Tomorrow plan for platform casting. Changi bound hacking to complete tomorrow
Fri (22/08) | 22 Aug 2025 | P49 |  | Excavation at center portion was done. Prepareing to hack the pile head
Fri (22/08) | 22 Aug 2025 | P48 |  | Manual excavation for strut installation
Fri (22/08) | 22 Aug 2025 | PMH23 branch out |  | 24m duct laid. To continue at live road area. Now reinstate the area
Fri (22/08) | 22 Aug 2025 | P44 |  | Crosshead soffit platform installation
Fri (22/08) | 22 Aug 2025 | P45 |  | Started removal of soil at utility free area
Fri (22/08) | 22 Aug 2025 | P17 |  | Shifting of pvc pipe to install at duct area to prevent chokage
Fri (22/08) | 22 Aug 2025 | P15 |  | Tonight plan to install two segments
Fri (22/08) | 22 Aug 2025 | P4 |  | To continue soffit plywood laying for working platform
Fri (22/08) | 22 Aug 2025 | P4 |  | Continue soffit plywood laying
Fri (22/08) | 22 Aug 2025 | P7 |  | Column rebar cage installation
Fri (22/08) | 22 Aug 2025 | S1 |  | No activity as of now
Fri (22/08) | 22 Aug 2025 | P1 |  | Pile head hacking until 9PM
Fri (22/08) | 22 Aug 2025 | P3 |  | Trimming bar around opening installation
Fri (22/08) | 22 Aug 2025 | P44 |  | Current status of wingform for crosshead
Fri (22/08) | 22 Aug 2025 | PMH29 to link up area |  | Current excavation and ERSS installation. Note: this activity is doing during night shift to deconflict work with water pipe laying work
Fri (22/08) | 22 Aug 2025 | 800mm dia water pipe laying |  | Today plan for 6m length water pipe laying
Fri (22/08) | 22 Aug 2025 | Exit 2 capping beam |  | Starter bar straightening ongoing (CGW). Today to complete straightening and start CB rebar works
Sat (23/08) | 23 Aug 2025 | CCW-W4-W7 |  | Strut installation in progress, target to install 2 struts today
Sat (23/08) | 23 Aug 2025 | P17 |  | Formwork installation for wet stitching
Sat (23/08) | 23 Aug 2025 | P15 |  | SB D03/U03 - Tendon wires installation for stressing works
Sat (23/08) | 23 Aug 2025 | P14 |  | Scaffold erection for stage 2 stressing works
Sat (23/08) | 23 Aug 2025 | P7-1 |  | Column rebar cage installed yesterday
Sat (23/08) | 23 Aug 2025 | P4 Crosshead |  | Platform installation ongoing
Sat (23/08) | 23 Aug 2025 | P3 |  | Shear links installation in progress. Inspection for Formwork closing in progress
Sat (23/08) | 23 Aug 2025 | Exit 3 |  | Drilling for waler bracket installation
Sat (23/08) | 23 Aug 2025 | BR20 |  | Continues excavation & soil disposal
Sat (23/08) | 23 Aug 2025 | Exit 2 |  | Ongoing rebar work for capping beam
Sat (23/08) | 23 Aug 2025 | BR10 |  | Ongoing rebar work for remaining retain wall
Sat (23/08) | 23 Aug 2025 | P1 |  | KTC levelling works for test pile hacking
Sat (23/08) | 23 Aug 2025 | BR7A |  | Leaned concrete last night, today will proceed to expose of couplers
Sat (23/08) | 23 Aug 2025 | BR7b |  | General housekeeping works only
Sat (23/08) | 23 Aug 2025 | BR8a & BR8b |  | Secondary beam installation for utility support / traffic deck
Sat (23/08) | 23 Aug 2025 | Zone 4 800mm water pipe |  | Pipe joint - MPI test and pressure test completed. Preparation for backfilling works
Sat (23/08) | 23 Aug 2025 | CCE4 |  | Continues rebar installation for tunnel roof slab
Sat (23/08) | 23 Aug 2025 | CCE-BR28 |  | Rebar installation is in progress
Sat (23/08) | 23 Aug 2025 | CCE-BR27/BR26 |  | Ongoing excavation and soil disposal
Sat (23/08) | 23 Aug 2025 | Exit 1 |  | Exposing of couplers is in progress for BR34
Sat (23/08) | 23 Aug 2025 | Exit 1 |  | Meanwhile stockpile has been cleared from new ECM pond
Sat (23/08) | 23 Aug 2025 | Zone 4 |  | Pipe laying excavation for PMH26 branching works
Sat (23/08) | 23 Aug 2025 | PMH23 branch out |  | Excavation works for pipe laying towards live road area ongoing
Sat (23/08) | 23 Aug 2025 | P50 |  | KTC excavation and levelling works ongoing
Sat (23/08) | 23 Aug 2025 | P49 |  | HSL Pile head hacking current status
Sat (23/08) | 23 Aug 2025 | P45 |  | No activity. Current status
Sat (23/08) | 23 Aug 2025 | P44 |  | Crosshead Formwork installation and assembly works
Sat (23/08) | 23 Aug 2025 | P17 |  | SB formwork closing for wet stitching and NB pvc pipe installation
Sat (23/08) | 23 Aug 2025 | P15 |  | Stressing works for SB 3rd pair segment
Sat (23/08) | 23 Aug 2025 | P14 |  | Scaffold erection for 2nd stage stressing
Sat (23/08) | 23 Aug 2025 | CCW-P24 |  | Continues rebar installation & target to cast next week
Sat (23/08) | 23 Aug 2025 | P7-1 |  | Lowering of RWDP and rebar installation ongoing
Sat (23/08) | 23 Aug 2025 | P4 |  | Continue Falsework installation works
Sat (23/08) | 23 Aug 2025 | P4 |  | Preparation for base jack installation
Sat (23/08) | 23 Aug 2025 | P3 |  | Shear links installation ongoing
Sat (23/08) | 23 Aug 2025 | BR20 |  | Continues excavation & soil disposal
Sat (23/08) | 23 Aug 2025 | Exit 2 |  | Continue capping beam rebar installation @ target to cast it next week
Sat (23/08) | 23 Aug 2025 | BR10 |  | Continues rebar work for remaining retaining wall & PU grouting by Maxbond
Sat (23/08) | 23 Aug 2025 | Zone 1 |  | Mobilisation of SI rig BH test
Sat (23/08) | 23 Aug 2025 | BR8B |  | Ongoing beam installation for traffic deck
Sat (23/08) | 23 Aug 2025 | BR7b |  | Beams installation has completed for utility
Sat (23/08) | 23 Aug 2025 | P1 |  | Soil removal and levelling works for S2 layer
Sat (23/08) | 23 Aug 2025 | Zone 4 | PMH28-29 | Backfilling and levelling works
Sat (23/08) | 23 Aug 2025 | Zone 4 800mm water pipe |  | Backfilling and reinstatement works in progress
Sat (23/08) | 23 Aug 2025 | CCE4 |  | Tunnel roof slab, Rebar installation in progress for B2-46
Sat (23/08) | 23 Aug 2025 | Zone 4 |  | Trial trench for PMH26 branching works
Sat (23/08) | 23 Aug 2025 | BR27 |  | Target to lean concrete by today
Sat (23/08) | 23 Aug 2025 | BR28 |  | Rebar installation in progress, target to cast it tgt with BR29 by end of the mont
Sat (23/08) | 23 Aug 2025 | Exit 1 |  | Continue exposing of couplers
Sat (23/08) | 23 Aug 2025 | P50 |  | KTC continue excavation works for next layer
Sat (23/08) | 23 Aug 2025 | P49 |  | HSL Pile head hacking south side
Sat (23/08) | 23 Aug 2025 | Zone 4, P47 |  | JGP grouting for P47-19 in progress
Sat (23/08) | 23 Aug 2025 | P45 |  | Current excavation status
Sat (23/08) | 23 Aug 2025 | P44 |  | Crosshead Formwork assembly in progress
Sat (23/08) | 23 Aug 2025 | CCW-P24 |  | Rebar installation is in progress
Sun (24/08) | 24 Aug 2025 | CCW W4-W7 |  | S3 struts installation in progress
Sun (24/08) | 24 Aug 2025 | BR10 |  | Dewatering ongoing at waterproofing membrane layer
Sun (24/08) | 24 Aug 2025 | BR28 |  | Rebar works ongoing
Sun (24/08) | 24 Aug 2025 | BR27 |  | Base lean con cast
Sun (24/08) | 24 Aug 2025 | GL28-29 | Selarang side | Beam welding works ongoing for decking
Sun (24/08) | 24 Aug 2025 | GL28-29 | Blk 4 | Beams installation for utility support works completed. Pending c-channel & angle bar installation
Sun (24/08) | 24 Aug 2025 | BR34 |  | Hacking at dwall side to expose couplers
Sun (24/08) | 24 Aug 2025 | CCE4 |  | Rebar works & formwork installation in progress. Plan for casting tmr
Sun (24/08) | 24 Aug 2025 | BR17, BR18A |  | Formwork dismantled
Sun (24/08) | 24 Aug 2025 | BR17 |  | Continue roughening works
Sun (24/08) | 24 Aug 2025 | BR19 |  | Drilling ongoing for couplers
Sun (24/08) | 24 Aug 2025 | BR15B |  | Bolt planting for raker struts installation
Sun (24/08) | 24 Aug 2025 | Exit 3 |  | Preparing for struts installation
Sun (24/08) | 24 Aug 2025 | P24 TB |  | Shearlinks and corrugated pipes installation
Sun (24/08) | 24 Aug 2025 | Exit 2 capping beam & balance BR10 retaining wall |  | No activity
Sun (24/08) | 24 Aug 2025 | GL28-29 |  | Abandoned drain exposed. Tmr to start hacking
Sun (24/08) | 24 Aug 2025 | BR28 |  | Rebar works in progress
Sun (24/08) | 24 Aug 2025 | CCE4 |  | Continue rebar works
Sun (24/08) | 24 Aug 2025 | Exit 3 |  | Waler installed. Today plan for struts installation
Sun (24/08) | 24 Aug 2025 | BR19 |  | Coupler exposed and continue excavation
Sun (24/08) | 24 Aug 2025 | BR17 |  | Formwork dismantling and CJ hacking ongoing
Sun (24/08) | 24 Aug 2025 | P24 TB |  | Continue rebar works and partial formwork installation in progress
Mon (25/08) | 25 Aug 2025 | BR28 |  | Rebar works in progress, 10 workers
Mon (25/08) | 25 Aug 2025 | CCE4 |  | 2nos pump trucks setting up
Mon (25/08) | 25 Aug 2025 | BR34 |  | Continie exposing couplers, 2 workers
Mon (25/08) | 25 Aug 2025 | CCE4 |  | 3 concrete trucks already on site
Mon (25/08) | 25 Aug 2025 | CCE -4 |  | B2-44, 45 & 46 TUNNEL ROOF SLAB CASTING IN PROGRESS (25/08/2025), Casting Started : 22.25pm, G40 WP - 10m³/244m³, G40 PBFC- 00m³/976m³
Mon (25/08) | 25 Aug 2025 | 800mm dia water pipe laying |  | Checking of 54mm dia copper pipe for water pipe link up work
Mon (25/08) | 25 Aug 2025 | PMH29 to link up area |  | Now no activity. Wee Guan working night shift
Mon (25/08) | 25 Aug 2025 | P15 SB 4th pair |  | Stressing in progress
Mon (25/08) | 25 Aug 2025 | P17 |  | Wet stitching to cast tonight at 10pm. Start at SB
Mon (25/08) | 25 Aug 2025 | Exit 1 |  | Exposing of couplers @ BR34
Mon (25/08) | 25 Aug 2025 | P24 |  | Fwk closure / shear links installation & RGT test ongoing
Mon (25/08) | 25 Aug 2025 | N1 |  | Strand pulling for tensioning
Mon (25/08) | 25 Aug 2025 | P50 |  | Woh hup clearing soil at TPE bound and KTC hacking of cement grout at changi bound
Mon (25/08) | 25 Aug 2025 | CCW S3 | South Side | Rebar work ongoing
Mon (25/08) | 25 Aug 2025 | P49 |  | Pile head hacking at TPE bound
Mon (25/08) | 25 Aug 2025 | P48 |  | Preparing for diagonal strut installation
Mon (25/08) | 25 Aug 2025 | CCW S3 | North | RC Waler status
Mon (25/08) | 25 Aug 2025 | P44 |  | Crosshead side formwork closing
Mon (25/08) | 25 Aug 2025 | DR3 |  | LE preparing materials to start utility support. GCE rig maintenance. Tomorrow they will resume JGP at junction
Mon (25/08) | 25 Aug 2025 | P45 |  | Excavation at utility free area
Mon (25/08) | 25 Aug 2025 | CCE4 |  | Shearlinks installation continues for P42
Mon (25/08) | 25 Aug 2025 | CCE4 |  | Started cleaning work @ B2-44
Mon (25/08) | 25 Aug 2025 | P7-1 |  | Column formwork closing
Mon (25/08) | 25 Aug 2025 | P4 |  | Bottom formwork c-channel installation
Mon (25/08) | 25 Aug 2025 | P44 |  | Cross head side formwork closing. Tomorrow to start rebar work
Mon (25/08) | 25 Aug 2025 | P43 |  | As of now no activity
Mon (25/08) | 25 Aug 2025 | P3 |  | 2nd section formwork closed. 3rd section links installation on going
Mon (25/08) | 25 Aug 2025 | P1 |  | 2nd layer waler beam installation
Mon (25/08) | 25 Aug 2025 | P17 |  | PVC pipe placing inside duct to prevent grout go in. Woh hup will start stitching casting around 9PM
Mon (25/08) | 25 Aug 2025 | P15 |  | Stressing done. Strand cutting. Tonight plan to launch two segments
Mon (25/08) | 25 Aug 2025 | P7 |  | Column formwork closing
Mon (25/08) | 25 Aug 2025 | P3 |  | Shear link installation
Mon (25/08) | 25 Aug 2025 | P4 |  | Crosshead soffit plywood laying
Mon (25/08) | 25 Aug 2025 | P1 |  | Waler joint welding until 9PM
Mon (25/08) | 25 Aug 2025 | P49 |  | KTC stop work at 8PM
Mon (25/08) | 25 Aug 2025 | P50 |  | Woh hup continue hacking of pile head until 10PM
Mon (25/08) | 25 Aug 2025 | P48 |  | LE continue diagonal strut installation
Mon (25/08) | 25 Aug 2025 | DR3 |  | No activity
Mon (25/08) | 25 Aug 2025 | P44 |  | One side of formwork for crosshead closed
Mon (25/08) | 25 Aug 2025 | Exit 3 |  | Struts installed near BR13
Mon (25/08) | 25 Aug 2025 | Between BR13 & BR14 |  | Struts installation
Mon (25/08) | 25 Aug 2025 | BR19 |  | Exposing couplers
Mon (25/08) | 25 Aug 2025 | BR15B |  | Welding works ongoing for raker struts
Mon (25/08) | 25 Aug 2025 | P24 TB |  | Formwork installation in progress, Between BR16A & P24 TB: Rebar works ongoing for downhang wall
Mon (25/08) | 25 Aug 2025 | CCW W4-W7 |  | S3 strutting works ongoing. Hirose working until 10pm
Mon (25/08) | 25 Aug 2025 | Exit 3 |  | S2 waler installation ongoing
Mon (25/08) | 25 Aug 2025 | Exit 2 |  | No activity
Mon (25/08) | 25 Aug 2025 | BR10 |  | Current status of balance waterproofing membrane laying. No activity now
Mon (25/08) | 25 Aug 2025 | BR7B |  | Abandoned drain hacking in progress
Mon (25/08) | 25 Aug 2025 | BR7A |  | Coupler exposing in progress
Tue (26/08) | 26 Aug 2025 | BR10 remaining part for waterproofing |  | No activity due to hot weather condition water proofing not able to do now, only can resume after 6pm. Target tomorrow cast protective concrete, Current status: waterproofing membrane laid (85%)
Tue (26/08) | 26 Aug 2025 | BR7A/7B |  | Disposal works ongoing
Tue (26/08) | 26 Aug 2025 | BR7A |  | Continue exposing couplers
Tue (26/08) | 26 Aug 2025 | BR28 |  | Rebar works in progress
Tue (26/08) | 26 Aug 2025 | CCE -4 |  | B2-44, 45 & 46 TUNNEL ROOF SLAB CASTING IN PROGRESS (25/08/2025), Casting Started : 22.25, G40 WP - 140m³/244m³, G40 PBFC- 240m³/976m³
Tue (26/08) | 26 Aug 2025 | BR34 |  | Formwork preparation for skin wall area lean con casting
Tue (26/08) | 26 Aug 2025 | BR19 |  | Drilling for couplers in progress
Tue (26/08) | 26 Aug 2025 | P24 TB |  | No activity
Tue (26/08) | 26 Aug 2025 | P20-21 |  | Unloading of materials for 2nd set of SH
Tue (26/08) | 26 Aug 2025 | P19 |  | Scaffold erection for segment launching
Tue (26/08) | 26 Aug 2025 | P15 NB 5th pair |  | Strand pulling completed. Preparation for PT
Tue (26/08) | 26 Aug 2025 | CCE4 |  | B2-44, 45 & 46 Tunnel Roof Slab, casting completed at 3pm
Tue (26/08) | 26 Aug 2025 | S1 |  | Scaffold support erection for rebar cage fabrication
Tue (26/08) | 26 Aug 2025 | P7-1 column |  | Formwork closing in progress. To cast by 28 August
Tue (26/08) | 26 Aug 2025 | 800mm PW |  | Excavation and ERSS. Meanwhile, waiting for main con to relocate the street light
Tue (26/08) | 26 Aug 2025 | BR28/29 |  | Rebar work ongoing, BR27: survey marking ongoing
Tue (26/08) | 26 Aug 2025 | BR34 |  | Continue coupler exposure
Tue (26/08) | 26 Aug 2025 | Exit 1 ECM |  | Current status
Tue (26/08) | 26 Aug 2025 | P50 |  | Bored pile hacking at north side
Tue (26/08) | 26 Aug 2025 | P49 |  | Bored pile hacking at north side
Tue (26/08) | 26 Aug 2025 | P48 |  | S1 strut installation
Tue (26/08) | 26 Aug 2025 | P1 |  | Concrete packing ongoing for s2 layer ERSS
Tue (26/08) | 26 Aug 2025 | PMH25 |  | Checking pipe condition for Mandrel test
Tue (26/08) | 26 Aug 2025 | P4 |  | Falsework and bottom Formwork assembly and installation works
Tue (26/08) | 26 Aug 2025 | P3 |  | Formwork closing and top rebar installation. Tmr to cast crosshead
Tue (26/08) | 26 Aug 2025 | P45 |  | Excavation to L1 caisson layer
Tue (26/08) | 26 Aug 2025 | P44 |  | Crosshead rebar installation work
Tue (26/08) | 26 Aug 2025 | P43 |  | Formwork dismantling
Tue (26/08) | 26 Aug 2025 | BR7B |  | Current status of abandoned drain hacking
Tue (26/08) | 26 Aug 2025 | BR7A |  | Works done for the night. Housekeeping now
Tue (26/08) | 26 Aug 2025 | BR29 |  | Rebar tying ongoing, BR28: Continue rebar works
Tue (26/08) | 26 Aug 2025 | CCE -4 |  | B2-44, 45 & 46 TUNNEL ROOF SLAB CASTING IN PROGRESS (25/08/2025), Casting Started : 22.25, G40 WP - 214m³/244m³, G40 PBFC- 593m³/976m³
Tue (26/08) | 26 Aug 2025 | P15 SB |  | Preparation for segment launching tonight
Tue (26/08) | 26 Aug 2025 | P15 |  | New bus stop slab ready for casting. Concrete ordered
Tue (26/08) | 26 Aug 2025 | S1 |  | Column rebar cage fabrication started
Tue (26/08) | 26 Aug 2025 | P4 |  | Side formwork assembly. To install tonight
Tue (26/08) | 26 Aug 2025 | P3 |  | Cast in anchor alignment. Good to go for casting tmr
Tue (26/08) | 26 Aug 2025 | P1 |  | 2nd layer double waler welding works. Tmr MPI
Tue (26/08) | 26 Aug 2025 | P48 |  | 1st layer strut installation
Tue (26/08) | 26 Aug 2025 | DR3 |  | UKP top plate welding until 10pm
Tue (26/08) | 26 Aug 2025 | P44 crosshead |  | Bottom bar installation continue
Wed (27/08) | 27 Aug 2025 | P19 |  | Area leveling for crane working platform. COS plan to apply today, steel plates to be laid
Wed (27/08) | 27 Aug 2025 | GL14-15 |  | Preparing for steel plate protection for utilities
Wed (27/08) | 27 Aug 2025 | P15 bus stop relocation |  | Today to install bollard and shift bus shelter
Wed (27/08) | 27 Aug 2025 | BR7A |  | Lean concrete 90% completed, Continue exposing couplers, CJ roughening at BR2 area, Today also plan to install netting protection below utilities & luminous painting of KPs
Wed (27/08) | 27 Aug 2025 | Balance BR10 |  | Balance retaining wall formwork closing (1st lift), Polyethylene sheet laying. Today to cast protection screeding
Wed (27/08) | 27 Aug 2025 | BR27 |  | Exposing of couplers is in progress
Wed (27/08) | 27 Aug 2025 | BR28 |  | Ongoing shear links & formwork installation, target to cast it tomorrow
Wed (27/08) | 27 Aug 2025 | S1 |  | Backfilled soil levelling and compaction. 1pm NDT
Wed (27/08) | 27 Aug 2025 | P7-1 |  | Casting platform erection
Wed (27/08) | 27 Aug 2025 | GL28-29 |  | Utility support works ongoing
Wed (27/08) | 27 Aug 2025 | BR19 |  | Debonding sheet laying, Continue drilling for couplers
Wed (27/08) | 27 Aug 2025 | BR20 |  | Hacking dwall to COL
Wed (27/08) | 27 Aug 2025 | Exit 1 |  | Exposing of couplers for BR34
Wed (27/08) | 27 Aug 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Wed (27/08) | 27 Aug 2025 | BR18B |  | Preparing for waler bracket installation
Wed (27/08) | 27 Aug 2025 | P24 TB |  | Shearlinks and formwork installation in progress. Formwork installation for 1m wall also ongoing
Wed (27/08) | 27 Aug 2025 | Exit 3 |  | S2 strutting works in progress
Wed (27/08) | 27 Aug 2025 | CCW south side S3 waler |  | Shearlinks and formwork installation in progress
Wed (27/08) | 27 Aug 2025 | CCW W5-W7 |  | S3 strutting works ongoing
Wed (27/08) | 27 Aug 2025 | P15 SB 5th pair |  | Stressing in progress
Wed (27/08) | 27 Aug 2025 | PMH29 ++ |  | ERSS dismantling
Wed (27/08) | 27 Aug 2025 | BR7A |  | Coupler exposing & cleaning ongoing, Luminous painting for UKPs done
Wed (27/08) | 27 Aug 2025 | BR7B |  | Disposing materials, GL28-29: Continue decking panels installation
Wed (27/08) | 27 Aug 2025 | BR10 |  | Polyethylene sheet laying completed. Now preparing for BRC installation thereafter protection screeding
Wed (27/08) | 27 Aug 2025 | 800mm PW |  | Street light shifting completed, continue Excavation and ERSS
Wed (27/08) | 27 Aug 2025 | PMH26 |  | Pipe laying (9m) to be completed by today
Wed (27/08) | 27 Aug 2025 | P48 |  | Preparing steel plate for water pipe protection
Wed (27/08) | 27 Aug 2025 | P49 |  | Bored pile hacking at north side
Wed (27/08) | 27 Aug 2025 | DR3 |  | Main beam installation for utility support
Wed (27/08) | 27 Aug 2025 | P44 |  | Crosshead rebar installation
Wed (27/08) | 27 Aug 2025 | P43 |  | Column formwork dismantling
Wed (27/08) | 27 Aug 2025 | BR20 |  | Continue hacking dwall to COL
Wed (27/08) | 27 Aug 2025 | BR19 |  | Rebars installation in progress
Wed (27/08) | 27 Aug 2025 | Exit 3 |  | S2 strutting works in progress
Wed (27/08) | 27 Aug 2025 | P24 TB |  | Formwork installation in progress
Wed (27/08) | 27 Aug 2025 | CCW W5-W7 |  | Continue S3 strutting welding works
Wed (27/08) | 27 Aug 2025 | N1 stitching formwork status |  | Upchainage: 80%, Downchainage: 60%
Wed (27/08) | 27 Aug 2025 | P7-1 |  | Scaffold access for casting erection. Tmr to cast
Wed (27/08) | 27 Aug 2025 | Exit 2 capping beam |  | Rebar works ongoing
Wed (27/08) | 27 Aug 2025 | BR7A |  | Cement patching works at lean concrete area. Tonight plan to start installing netting below utilities area
Wed (27/08) | 27 Aug 2025 | BR10 |  | Balance WP area BRC laid. To do protection screeding soon
Wed (27/08) | 27 Aug 2025 | BR8B |  | Continue decking panels installation
Wed (27/08) | 27 Aug 2025 | BR28 |  | Formwork installation in progress
Wed (27/08) | 27 Aug 2025 | P3 |  | Pump car set up for casting. Concrete ordered. Est volume 270 m3
Wed (27/08) | 27 Aug 2025 | BR34 |  | Lean concrete area casting at skin wall area & contimue exposing couplers
Wed (27/08) | 27 Aug 2025 | BR18B |  | Bolt planting for waler brackets
Thu (28/08) | 28 Aug 2025 | PMH29 |  | Duct laying done. Today to cast
Thu (28/08) | 28 Aug 2025 | 800mm dia water pipe |  | Today to lay 3.5m length bend pipe toward butterfly valve
Thu (28/08) | 28 Aug 2025 | BR7A |  | Current status
Thu (28/08) | 28 Aug 2025 | BR8B |  | Decking welding works ongoing. Balance metro decks plan for delivery tomorrow, BR8A: Utility support works ongoing
Thu (28/08) | 28 Aug 2025 | BR7B |  | Clearing rebars
Thu (28/08) | 28 Aug 2025 | Exit 1 |  | BR34 exposing of couplers
Thu (28/08) | 28 Aug 2025 | Exit 1 |  | Clearing of stockpile from new ECM pond
Thu (28/08) | 28 Aug 2025 | P50 |  | WD preparing to start RC work at south, KTC hacking bored pile and levelling at north
Thu (28/08) | 28 Aug 2025 | P49 |  | Bored pile hacking at north side
Thu (28/08) | 28 Aug 2025 | P48 |  | MPI test for S1 strut on going
Thu (28/08) | 28 Aug 2025 | DR3 |  | Utility support main beam installation by LE and manual excavation by ICE
Thu (28/08) | 28 Aug 2025 | BR10 |  | Balance WP area screeding completed last night. Remaining WP location to be done is at the scaffold area for retaining wall, Balance retaining wall 1st lift cast last night
Thu (28/08) | 28 Aug 2025 | P44 |  | Crosshead rebar installation
Thu (28/08) | 28 Aug 2025 | P43 |  | Clearing material and ground preparation
Thu (28/08) | 28 Aug 2025 | PMH29 |  | ERSS removal and clearing materials
Thu (28/08) | 28 Aug 2025 | PMH29 |  | Duct casting done. Balance levelling
Thu (28/08) | 28 Aug 2025 | P19 |  | Dry pack concrete casting for SH installation
Thu (28/08) | 28 Aug 2025 | 800mm dia water pipe laying |  | Clearing soil. Today will lay bend pipe
Thu (28/08) | 28 Aug 2025 | P17 |  | Cube test results came out. Preparation for post tensioning. Tonight to start dismantling of stressing cage
Thu (28/08) | 28 Aug 2025 | P15 new bus stop |  | Earthing installation ongoing
Thu (28/08) | 28 Aug 2025 | BR19 |  | RGT installation & rebar works in progress
Thu (28/08) | 28 Aug 2025 | BR20 |  | Hacking ongoing
Thu (28/08) | 28 Aug 2025 | BR17 |  | Inner formwork dismantling ongoing
Thu (28/08) | 28 Aug 2025 | BR18B |  | Endplate installation for waler bracket works
Thu (28/08) | 28 Aug 2025 | P24 TB |  | Preparing for casting. Pump truck already on standby
Thu (28/08) | 28 Aug 2025 | P7-1 |  | Column casting in progress
Thu (28/08) | 28 Aug 2025 | N1 |  | Formwork closing for wet stitching
Thu (28/08) | 28 Aug 2025 | S1 |  | Rebar fabrication for column and KTC backfilling works
Thu (28/08) | 28 Aug 2025 | BR15A |  | Endplate installation for struts installation
Thu (28/08) | 28 Aug 2025 | BR7A |  | Starter bar rebar planting. Tmr plan for pull-out test, Dongah to expedite on the grouting works at dwall side, Preparing formwork for kicker area
Thu (28/08) | 28 Aug 2025 | BR7B |  | Material disposal works ongoing
Thu (28/08) | 28 Aug 2025 | P50 |  | KTC handover the area to Woh Hup and Wendyng. Wendyng started caisson rebar work
Thu (28/08) | 28 Aug 2025 | P24 transfer beam casting started at 16 |  | 20 hrs, G40 WP-9m³/63m³, G40PBFC-00/644m³
Thu (28/08) | 28 Aug 2025 | P49 |  | Pile head hacking and clearing debris
Thu (28/08) | 28 Aug 2025 | P48 |  | MPI test done for struts. Tomorrow to resume excavation for 2nd layer caisson
Thu (28/08) | 28 Aug 2025 | DR3 |  | Secondary beam installation and welding
Thu (28/08) | 28 Aug 2025 | P45 |  | Current status of excavation
Thu (28/08) | 28 Aug 2025 | P44 |  | Crosshead rebar can finish today or tomorrow. Woh hup will start ducting work tomorrow
Thu (28/08) | 28 Aug 2025 | P43 |  | Top soil removal for LSS backfilling
Thu (28/08) | 28 Aug 2025 | BR7A |  | Dwall surface cleaning prior to inspection, Netting installation ongoing below utilities, Preparing for casting at kicker and slab area
Thu (28/08) | 28 Aug 2025 | BR7B |  | Excavation ongoing
Thu (28/08) | 28 Aug 2025 | BR8A |  | Continue utility support works, BR8B: Unloading metro decks
Thu (28/08) | 28 Aug 2025 | BR27 |  | Clearing debris
Thu (28/08) | 28 Aug 2025 | BR28 |  | Rebar and formwork installation in progress
Thu (28/08) | 28 Aug 2025 | P17 |  | U1-D1 segment TPT stressing (south side completed, north side on going)
Thu (28/08) | 28 Aug 2025 | P15 |  | Strand pulling
Thu (28/08) | 28 Aug 2025 | BR34 |  | Starter bar planting & preparing for casting at the drop area
Thu (28/08) | 28 Aug 2025 | P41 |  | Coupler bar installation in progress
Thu (28/08) | 28 Aug 2025 | P42 |  | Coupler bar installation status
Thu (28/08) | 28 Aug 2025 | N1 |  | No activity
Thu (28/08) | 28 Aug 2025 | S1 |  | Pile cap no activity
Thu (28/08) | 28 Aug 2025 | S1 |  | Column rebar cage fabrication
Thu (28/08) | 28 Aug 2025 | P7-1 |  | Column casting in progress
Thu (28/08) | 28 Aug 2025 | P3 |  | No activity
Thu (28/08) | 28 Aug 2025 | P1 |  | No activity
Thu (28/08) | 28 Aug 2025 | Exit 3 |  | S2 strutting works ongoing
Thu (28/08) | 28 Aug 2025 | P50 |  | L5 caisson rebar works ongoing
Thu (28/08) | 28 Aug 2025 | P44 |  | Crosshead rebar works ongoing
Thu (28/08) | 28 Aug 2025 | P43 |  | Ground preparation work ongoing
Thu (28/08) | 28 Aug 2025 | S1-2 |  | BR19, rebar works in progress
Fri (29/08) | 29 Aug 2025 | BR7A |  | Started bottom coupler rebar installation
Fri (29/08) | 29 Aug 2025 | BR7B |  | Current status of excavation
Fri (29/08) | 29 Aug 2025 | P44 |  | Crosshead rebar installation
Fri (29/08) | 29 Aug 2025 | P43 |  | Ground preparation for crosshead falsework
Fri (29/08) | 29 Aug 2025 | P45 |  | Excavation to L1 caisson layer
Fri (29/08) | 29 Aug 2025 | DR3 |  | Utility support installation
Fri (29/08) | 29 Aug 2025 | BR8A |  | Continue utility support works, BR8B: KTC telescopic excavator preparing for stockpile disposal works. Construction decking panels installation by Hirose plan for completion by this Sun
Fri (29/08) | 29 Aug 2025 | CCE4 tunnel roof slab |  | No activity
Fri (29/08) | 29 Aug 2025 | BR27 |  | Continues exposing of couplers
Fri (29/08) | 29 Aug 2025 | BR28 |  | Shear links installation
Fri (29/08) | 29 Aug 2025 | Exit 1 BR34 |  | Cleaning in progress prior to start laying of debonding sheet;, RGT installation is in progress
Fri (29/08) | 29 Aug 2025 | Exit 1 |  | Clearing of stockpile @ new ECM pond
Fri (29/08) | 29 Aug 2025 | S1-2 |  | BR19, rebar works in progress
Fri (29/08) | 29 Aug 2025 | P19 |  | 600T crane setting up for SH installation. Tonight to lunch downchainage
Fri (29/08) | 29 Aug 2025 | CCW W5-W7 |  | Current status of struts installation. Balance struts (3nos) installation will be near the waler sides which will be done after waler casts
Fri (29/08) | 29 Aug 2025 | Exit 3 |  | S2 struts installation in progress, 1/4nos completed
Fri (29/08) | 29 Aug 2025 | 800mm dia water pipe laying |  | Bend pipe lowering down. Welding in progress
Fri (29/08) | 29 Aug 2025 | PMH29 |  | Wee Guan clearing their materials and housekeeping
Fri (29/08) | 29 Aug 2025 | BR19 |  | Rebar works in progress
Fri (29/08) | 29 Aug 2025 | BR20 |  | Hacking ongoing
Fri (29/08) | 29 Aug 2025 | BR18B |  | Waler bracket installation
Fri (29/08) | 29 Aug 2025 | Exit 2 | near substation | Utilities protection using steel plates ongoing
Fri (29/08) | 29 Aug 2025 | GL11-12 |  | Excavation and disposal ongoing
Fri (29/08) | 29 Aug 2025 | Exit 2 capping beam |  | Formwork installation in progress
Fri (29/08) | 29 Aug 2025 | P7-1 |  | Backfilled to stump level, NDT in progress
Fri (29/08) | 29 Aug 2025 | BR7A |  | Rebar works and continue laying debonding sheet, Dongah formwork installation for grouting works
Fri (29/08) | 29 Aug 2025 | BR7B |  | Disposal works ongoing
Fri (29/08) | 29 Aug 2025 | CCE4 |  | Unloading materials for scaffold installation
Fri (29/08) | 29 Aug 2025 | CCE4- P41, P42 |  | Current status. Coupler tightening inspection was done in the morning
Fri (29/08) | 29 Aug 2025 | P50 |  | Lowering down materials. Tomorrow to cast the TPE bound side
Fri (29/08) | 29 Aug 2025 | BR28, BR29 |  | Preparing for final inspection
Fri (29/08) | 29 Aug 2025 | P4 crosshead |  | Rebar installation started
Fri (29/08) | 29 Aug 2025 | P49 |  | Hacking of grout for final layer caisson work
Fri (29/08) | 29 Aug 2025 | P48 |  | No activity. Tomorrow woh hup will arrange for prism base reading and start excavation
Fri (29/08) | 29 Aug 2025 | DR3 |  | Currently 3 main beam and 6 secondary beams installed. Welding in progress
Fri (29/08) | 29 Aug 2025 | BR8A |  | Continue utility support welding works, BR8B: Stockpile disposal ongoing
Fri (29/08) | 29 Aug 2025 | P45 |  | Grout hacking at utility free area was done. Now changing bucket to remove soil
Fri (29/08) | 29 Aug 2025 | P43 |  | Current status of platform prepare for LSS backfilling
Fri (29/08) | 29 Aug 2025 | P44 |  | Spiral link and tendom end box installation in progress
Fri (29/08) | 29 Aug 2025 | P19 |  | SH installation
Fri (29/08) | 29 Aug 2025 | P17 |  | No activity
Fri (29/08) | 29 Aug 2025 | P15 |  | Stressing work completed, currently strand trimming
Fri (29/08) | 29 Aug 2025 | S1 |  | Current column rebar fabrication status. No activity
Fri (29/08) | 29 Aug 2025 | S1 |  | Current pile cap backfilling status. No activity
Fri (29/08) | 29 Aug 2025 | P4 |  | Crosshead rebar installation
Fri (29/08) | 29 Aug 2025 | P2-P3 |  | SI for tunnelling work
Fri (29/08) | 29 Aug 2025 | P1 |  | Excavation ongoing
Fri (29/08) | 29 Aug 2025 | P50 |  | Working platform casting
Fri (29/08) | 29 Aug 2025 | P49 |  | Soil disposal
Fri (29/08) | 29 Aug 2025 | P48 |  | Surveyor taking prism reading
Fri (29/08) | 29 Aug 2025 | BR19 |  | Rebar works in progress
Fri (29/08) | 29 Aug 2025 | Exit 2 old ECM |  | Soil mixing and shifting internally to Gate 7 before disposal
Fri (29/08) | 29 Aug 2025 | Exit 2 capping beam |  | Rebar works and hyrib installation ongoing
Sat (30/08) | 30 Aug 2025 | Exit 2 | near substation | Continue protection installation for utilities alignment
Sat (30/08) | 30 Aug 2025 | GL11-12 |  | Continue excavation
Sat (30/08) | 30 Aug 2025 | BR7B |  | Excavation in progress
Sat (30/08) | 30 Aug 2025 | BR8A |  | Excavation in progress, BR7B:, Continue rebar works, RGT installation ongoing, Today plan for MPI test for KP endplates thereafter to complete lean concrete casting
Sat (30/08) | 30 Aug 2025 | P4 |  | Spacer block and guide bar installation at NB side for rebar works
Sat (30/08) | 30 Aug 2025 | N1 |  | Excavation continue to FEL
Sat (30/08) | 30 Aug 2025 | CCE4 |  | Scaffold erection in progress, Formwork support removal
Sat (30/08) | 30 Aug 2025 | Zone 4 opp pumping station |  | Water pipe welding in progress
Sat (30/08) | 30 Aug 2025 | DR3 |  | Utility support welding in progress
Sat (30/08) | 30 Aug 2025 | P45 |  | Excavation to first layer
Sat (30/08) | 30 Aug 2025 | P44 crosshead |  | Section 1 PT duct installation for crosshead. Balance T1-4
Sat (30/08) | 30 Aug 2025 | P44 crosshead |  | PT duct installation continue
Sat (30/08) | 30 Aug 2025 | P43 |  | Hardcore backfilling started
Sat (30/08) | 30 Aug 2025 | P42 |  | Stump rebar works completed
Sat (30/08) | 30 Aug 2025 | P41 |  | Stump rebar works in progress
Sat (30/08) | 30 Aug 2025 | Near BR15A |  | Struts installation, 4/4nos done. Welding works and bolt tightening ongoing
Sat (30/08) | 30 Aug 2025 | BR17 |  | Continue surface roughening
Sat (30/08) | 30 Aug 2025 | Zone 4 |  | TT to find existing water pipe for link up
Sat (30/08) | 30 Aug 2025 | BR19 |  | Continue rebar works
Sat (30/08) | 30 Aug 2025 | BR7B |  | Continue excavation and WH preparing access for IM monitoring
Sat (30/08) | 30 Aug 2025 | BR7A |  | Continue rebar works and preparing MPI test for KP
Sat (30/08) | 30 Aug 2025 | CCE4 |  | Continue scaffold erection
Sat (30/08) | 30 Aug 2025 | BR34 |  | Rebar works in progress
Sat (30/08) | 30 Aug 2025 | BR27 |  | Continue exposing couplers and preparing for lean con casting
Sat (30/08) | 30 Aug 2025 | BR8B |  | Bracing installation at decking area
Sat (30/08) | 30 Aug 2025 | BR7B |  | Excavation and disposal ongoing
Sat (30/08) | 30 Aug 2025 | Exit 2 |  | Continue steel plates installation for utility alignment protection
Sat (30/08) | 30 Aug 2025 | P1 |  | Excavation to FEL continue
Sat (30/08) | 30 Aug 2025 | P4 crosshead |  | Rebar works continue
Sat (30/08) | 30 Aug 2025 | S1 |  | Waler beam dismantling
Sat (30/08) | 30 Aug 2025 | P15 |  | New bus stop, shelter painting completed. Balance bollard reflective stripes and kerb painting
Sat (30/08) | 30 Aug 2025 | P15 |  | Stressing cage dismantling. Tonight plan to shift lifter at P16, 2/4 nos
Sat (30/08) | 30 Aug 2025 | P24 TB |  | Formwork support removal ongoing
Sat (30/08) | 30 Aug 2025 | P15 |  | Mobilisation of 300T crane for lifter frame dismantling
Sat (30/08) | 30 Aug 2025 | P15 |  | New bus stop painting
Sat (30/08) | 30 Aug 2025 | BR17 |  | Exposing couplers and surface roughening
Sat (30/08) | 30 Aug 2025 | BR19 |  | Rebar works in progress (30 workers)
Sat (30/08) | 30 Aug 2025 | BR20 |  | Preparing for rebars cutting
Sun (31/08) | 31 Aug 2025 | S1-1 |  | 18A, Raker strut installation ongoing
Sun (31/08) | 31 Aug 2025 | S1-2 |  | BR20, Rebar work ongoing
Mon (01/09) | 01 Sep 2025 | P19 |  | Lifter frame fixing in progress
Mon (01/09) | 01 Sep 2025 | P15 |  | Dismantling of lifter
Mon (01/09) | 01 Sep 2025 | CCE4 |  | Pumping out of water prior to start with rebar work for retaining wall near RS
Mon (01/09) | 01 Sep 2025 | CCE4 |  | Dismantling of formwork for P42
Mon (01/09) | 01 Sep 2025 | P50 |  | Rebar installation for final layer caisson completed around 75%. This week to complete 100% of caisson for final layer
Mon (01/09) | 01 Sep 2025 | 800mm dia water pipe laying |  | Trial trench for butterfly valve ERSS installation
Mon (01/09) | 01 Sep 2025 | 22KV diversion |  | Mandrel test 90% completed. Today target to complete 100%. This week ready to handover to SPPG
Mon (01/09) | 01 Sep 2025 | P14-P15 |  | Tendon wire cutting and installation for 2nd stage stressing
Mon (01/09) | 01 Sep 2025 | P49 |  | KTC removing soft soil. Today WH will cast concrete at the base as working platform
Mon (01/09) | 01 Sep 2025 | BR27 |  | Continues exposing of couplers & Dwall rectification work
Mon (01/09) | 01 Sep 2025 | P48 |  | Excavation for 2nd layer caisson in progress
Mon (01/09) | 01 Sep 2025 | GL14 onwards |  | Steel plates installation for utility protection and continue manual digging below services
Mon (01/09) | 01 Sep 2025 | BR7A |  | Rebar works in progress. Plan for casting this week
Mon (01/09) | 01 Sep 2025 | BR34 |  | Rebar installation is in progress
Mon (01/09) | 01 Sep 2025 | Exit 1 |  | Clearing of stockpile from new ECM pond
Mon (01/09) | 01 Sep 2025 | P45 |  | Continue removal of grout for 1st layer caisson
Mon (01/09) | 01 Sep 2025 | DR3 |  | Manual excavation to expose services
Mon (01/09) | 01 Sep 2025 | BR8A |  | Balance abandoned drain hacking and utility support to be done here
Mon (01/09) | 01 Sep 2025 | BR8B |  | Decking welding works in progress. Aso preparing materials for VIG installation
Mon (01/09) | 01 Sep 2025 | BR7B |  | Continue excavation and hacking works
Mon (01/09) | 01 Sep 2025 | P4 crosshead |  | Bottom bar installation completed. Top bar installation started at south side
Mon (01/09) | 01 Sep 2025 | P44 |  | Main bar inspection half completed. Tomorrow WH will handover 50% of area for shear link installation
Mon (01/09) | 01 Sep 2025 | P43 |  | Concrete footing installed for crosshead faslework
Mon (01/09) | 01 Sep 2025 | P1 |  | Scaffold access shifting to continue excavation to FEL
Mon (01/09) | 01 Sep 2025 | P3 |  | Curing
Mon (01/09) | 01 Sep 2025 | P4 |  | Hard barricade installation for top bar installation
Mon (01/09) | 01 Sep 2025 | P1 |  | No activity
Mon (01/09) | 01 Sep 2025 | P7 |  | Column formwork support removal
Mon (01/09) | 01 Sep 2025 | BR18B |  | Struts installation in progress
Mon (01/09) | 01 Sep 2025 | BR20 |  | Rebar works in progress
Mon (01/09) | 01 Sep 2025 | N1 |  | Materials bring up and preparation for stressing work
Mon (01/09) | 01 Sep 2025 | P15-16 |  | Tonight plan to shift the lifter
Mon (01/09) | 01 Sep 2025 | BR19 |  | Continue rebar works and partial formwork
Mon (01/09) | 01 Sep 2025 | BR7A |  | Continue rebar works
Mon (01/09) | 01 Sep 2025 | BR27 |  | Continue exposing couplers at inner side
Mon (01/09) | 01 Sep 2025 | BR7A |  | Continue excavation and hacking of balance abandoned drain
Mon (01/09) | 01 Sep 2025 | CCE4 |  | Patching of tie rod holes
Mon (01/09) | 01 Sep 2025 | P50 |  | Formwork closing. Tomorrow plan for 2nd stage casting. By tomorrow will complete around 75%
Mon (01/09) | 01 Sep 2025 | P49 |  | Crane mobilized for platform casting
Mon (01/09) | 01 Sep 2025 | P48 |  | KTC no night shift activity
Mon (01/09) | 01 Sep 2025 | DR3& P45 |  | No night shift activity
Tue (02/09) | 02 Sep 2025 | 800mm PW |  | Trial Trench and ERSS for butterfly valve
Tue (02/09) | 02 Sep 2025 | P50 |  | Concrete casting for L5 caisson wall
Tue (02/09) | 02 Sep 2025 | P49 |  | Hacking JGP Grout and excavation on going
Tue (02/09) | 02 Sep 2025 | CCE4 |  | Rebar installation is in progress for retaining wall beside RS
Tue (02/09) | 02 Sep 2025 | B2-43 |  | Excavation has started @ GL E1- E4
Tue (02/09) | 02 Sep 2025 | P48 |  | Excavation to L2 caisson layer
Tue (02/09) | 02 Sep 2025 | P45 |  | Preparing access to excavation area
Tue (02/09) | 02 Sep 2025 | BR7A |  | Rebar works in progress
Tue (02/09) | 02 Sep 2025 | BR28&29 |  | Dismantling of formwork
Tue (02/09) | 02 Sep 2025 | GL E5-E8 |  | Ongoing rebar installation for Waler
Tue (02/09) | 02 Sep 2025 | BR27 |  | Continue exposing of couplers
Tue (02/09) | 02 Sep 2025 | BR27 |  | Dwall rectification work is in progress
Tue (02/09) | 02 Sep 2025 | Between BR8A and BR8B |  | Temporary support installation to facilitate balance decking installation & utility support works
Tue (02/09) | 02 Sep 2025 | BR7B |  | Excavation in progress. Today plan for LSS backfill at dwall side
Tue (02/09) | 02 Sep 2025 | Exit 1 |  | Rebar installation is in progress for BR34
Tue (02/09) | 02 Sep 2025 | Exit 1 |  | Current stockpile @ new ECM pond
Tue (02/09) | 02 Sep 2025 | P16 |  | Tonight plan for stressing cage installation
Tue (02/09) | 02 Sep 2025 | P14 |  | Permanent stressing work
Tue (02/09) | 02 Sep 2025 | N1 |  | Preparation for segment launching work. Tomorrow to launch
Tue (02/09) | 02 Sep 2025 | P1 |  | Today to complete excavation. Tomorrow handover for pile head hacking
Tue (02/09) | 02 Sep 2025 | P3 |  | Curing
Tue (02/09) | 02 Sep 2025 | P4 |  | Top rebar work for crosshead
Tue (02/09) | 02 Sep 2025 | Zone 4 near pumping station |  | Wee Guan and Ley Choon already end work
Tue (02/09) | 02 Sep 2025 | P50 |  | 2nd stage of last layer caisson casting
Tue (02/09) | 02 Sep 2025 | P49 |  | Continue removal of soft soil
Tue (02/09) | 02 Sep 2025 | P48 |  | Current status of excavation
Tue (02/09) | 02 Sep 2025 | DR3 |  | Preparing for utility support installation
Tue (02/09) | 02 Sep 2025 | P45 |  | Proper access installation
Tue (02/09) | 02 Sep 2025 | DR4 |  | Barricade installation and tidy up site
Wed (03/09) | 03 Sep 2025 | P19 |  | Netting installation and segment adjustment in progress
Wed (03/09) | 03 Sep 2025 | S1 |  | Column rebar cage fabrication
Wed (03/09) | 03 Sep 2025 | Exit 2 capping beam |  | Formwork installation in progress
Wed (03/09) | 03 Sep 2025 | CCE4 |  | Rebar installation in progress for retaining wall beside RS
Wed (03/09) | 03 Sep 2025 | B2-43 |  | Continues excavation
Wed (03/09) | 03 Sep 2025 | BR27 |  | Continues exposing of couplers & rectifying Dwall
Wed (03/09) | 03 Sep 2025 | GL E5-E8 |  | Rebar installation for waler
Wed (03/09) | 03 Sep 2025 | P4 |  | Crosshead rebar installation works
Wed (03/09) | 03 Sep 2025 | P1 |  | Excavation to FEL completed. Preparation for pile head hacking works
Wed (03/09) | 03 Sep 2025 | Exit 1 |  | Continues rebar installation for BR34
Wed (03/09) | 03 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Wed (03/09) | 03 Sep 2025 | P19 |  | Segment adjustment in progress
Wed (03/09) | 03 Sep 2025 | P16 |  | Lifting frame installation works for segment launching tmr
Wed (03/09) | 03 Sep 2025 | S1 |  | Column cage installation ongoing. Target to cast sat
Wed (03/09) | 03 Sep 2025 | BR8A |  | Excavation in progress
Wed (03/09) | 03 Sep 2025 | BR7A |  | Rebar works ongoing
Wed (03/09) | 03 Sep 2025 | BR7B |  | Continue excavation
Wed (03/09) | 03 Sep 2025 | BR10 transfer beam |  | Waterproofing membrane works ongoing
Wed (03/09) | 03 Sep 2025 | P4 |  | Crosshead top rebar installation ongoing
Wed (03/09) | 03 Sep 2025 | P1 |  | Pile head hacking
Wed (03/09) | 03 Sep 2025 | P49 |  | Hacking JGP grout
Wed (03/09) | 03 Sep 2025 | P48 |  | Excavation to L2 caisson layer
Wed (03/09) | 03 Sep 2025 | DR3 |  | Manual excavation and utility support installation
Wed (03/09) | 03 Sep 2025 | P45 |  | Excavation to L1 caisson layer
Wed (03/09) | 03 Sep 2025 | P50 |  | L5 caisson rebar installation, tonight formwork closing
Wed (03/09) | 03 Sep 2025 | P44 |  | Crosshead rebar installation ongoing
Wed (03/09) | 03 Sep 2025 | P43 |  | Crosshead falsework erection
Thu (04/09) | 04 Sep 2025 | P50 |  | Balance rebar work in progress for last layer caisson. Tonight to cast
Thu (04/09) | 04 Sep 2025 | P49 |  | Final layer excavation. Continue soft soil removal
Thu (04/09) | 04 Sep 2025 | BR7B |  | Continue excavation and disposal
Thu (04/09) | 04 Sep 2025 | BR8B |  | VIG welding ongoing. Tmr plan material delivery for balance area of decking (between BR8A-8B)
Thu (04/09) | 04 Sep 2025 | BR7A |  | Formwork and support installation in progress, Continue rebar works, RTO inspection ongoing
Thu (04/09) | 04 Sep 2025 | P16 |  | Preparation for load test at 4pm
Thu (04/09) | 04 Sep 2025 | S1 |  | Column rebar cage installation works
Thu (04/09) | 04 Sep 2025 | DR3 |  | Exposing services for support installation
Thu (04/09) | 04 Sep 2025 | P48 |  | 50% excavation done for 3rd layer. Continue excavation
Thu (04/09) | 04 Sep 2025 | P43 |  | Current status of falsework erection
Thu (04/09) | 04 Sep 2025 | N1 |  | : Scaffold erection
Thu (04/09) | 04 Sep 2025 | Zone 2 |  | Vibro demobilization
Thu (04/09) | 04 Sep 2025 | P4 |  | Crosshead rebar installation
Thu (04/09) | 04 Sep 2025 | P1 |  | HSL Pile head hacking ongoing
Thu (04/09) | 04 Sep 2025 | P44 |  | Side formwork closing and adjusting. Tentative cast on Monday
Thu (04/09) | 04 Sep 2025 | DR4 |  | Quarry dust cover at duct laid area
Thu (04/09) | 04 Sep 2025 | 800mm dia water pipe |  | Preparing ERSS installation for butter fly valve construction
Thu (04/09) | 04 Sep 2025 | BR7A |  | Continue rebar works and formwork installation
Thu (04/09) | 04 Sep 2025 | BR7B |  | Continue LSS backfilling at next portion & hacking at dwall side to expose couplers
Thu (04/09) | 04 Sep 2025 | BR10 transfer beam |  | Polyethylene sheet laid. Tonight plan for protective screeding
Thu (04/09) | 04 Sep 2025 | Balance BR10 retaining wall |  | 2nd lift formwork closing in progress Rebar connection. Tonight plan for casting
Thu (04/09) | 04 Sep 2025 | GL16-GL18.5 |  | Arranging EPS blocks prior to LSS backfilling works
Thu (04/09) | 04 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Thu (04/09) | 04 Sep 2025 | Exit 1 |  | Continues rebar installation for BR34
Thu (04/09) | 04 Sep 2025 | P50 |  | Balance caisson formwork closing. Tomorrow to cast
Thu (04/09) | 04 Sep 2025 | P49 |  | Woh hup handover 1st part to Wendyng. Starter bar bending to start caisson rebar work
Thu (04/09) | 04 Sep 2025 | P1 |  | Pile head hacking
Thu (04/09) | 04 Sep 2025 | P4 |  | Continue top rebar installation
Thu (04/09) | 04 Sep 2025 | B2-43 |  | Continues excavation and soil disposal
Thu (04/09) | 04 Sep 2025 | CCE4 |  | Ongoing rebar installation for retaining wall beside RS
Thu (04/09) | 04 Sep 2025 | BR27 |  | Will continue exposing of couplers & Dwall rectification work
Thu (04/09) | 04 Sep 2025 | GL E5-E8 |  | Continue rebar installation for waler, target to cast by end of this week
Thu (04/09) | 04 Sep 2025 | P49 |  | Preparation work L5 caisson RCwork
Thu (04/09) | 04 Sep 2025 | P48 |  | Excavator maintenance
Thu (04/09) | 04 Sep 2025 | DR3 |  | Manual excavation and utility support installation
Thu (04/09) | 04 Sep 2025 | S1 |  | Column Formwork closing
Thu (04/09) | 04 Sep 2025 | N1 |  | Scaffold erection
Thu (04/09) | 04 Sep 2025 | P16 |  | Load test completed. AE inspection ongoing
Thu (04/09) | 04 Sep 2025 | P17 |  | Strand installation and segment adjustment in progress
Thu (04/09) | 04 Sep 2025 | P44 |  | Tendom duct to complete today and wendyng to continue with shear link work
Thu (04/09) | 04 Sep 2025 | Exit 3 |  | S2 preloading in progress
Thu (04/09) | 04 Sep 2025 | BR20 |  | Continue excavation and exposing couplers
Thu (04/09) | 04 Sep 2025 | Balance BR10 retaining wall |  | 2nd lift formwork installation in progress. Plan for casting tonight
Thu (04/09) | 04 Sep 2025 | Exit 2 capping beam |  | Formwork closing. Plan for casting tonight
Thu (04/09) | 04 Sep 2025 | BR19 |  | Continue formwork installation. Plan for casting tmr
Thu (04/09) | 04 Sep 2025 | Outside BR10 |  | Temporary backfilling ongoing for access
Thu (04/09) | 04 Sep 2025 | BR10 transfer beam |  | BRC laying ongoing & housekeeping
Thu (04/09) | 04 Sep 2025 | GL E5-E8 |  | Rebar works for waler beam in progress
Thu (04/09) | 04 Sep 2025 | BR30 |  | Flood protection wall casting in progress
Thu (04/09) | 04 Sep 2025 | BR34 |  | Rebar works in progress
Thu (04/09) | 04 Sep 2025 | CCE4 |  | Hacking works ongoing
Thu (04/09) | 04 Sep 2025 | BR7A |  | Continue rebar works. Plan for casting on Saturday
Thu (04/09) | 04 Sep 2025 | 800mm dia water pipe |  | Preparing for butterfly valve ERSS work
Thu (04/09) | 04 Sep 2025 | Balance BR10 retaining wall |  | 2nd lift formwork installation in progress, Connection for bolt installation for decking also in progress. Working platform area will be backfilled to facilitate works
Thu (04/09) | 04 Sep 2025 | BR10 |  | Temporary backfilling ongoing for access. Have reminded WHDA to provide coupler protection
Fri (05/09) | 05 Sep 2025 | P50& P49 |  | Clearing rain water inside excavated area
Fri (05/09) | 05 Sep 2025 | P48 |  | Preparing to resume work
Fri (05/09) | 05 Sep 2025 | BR7A |  | Continue rebar tying and formwork support installation
Fri (05/09) | 05 Sep 2025 | DR3 |  | Now no activity. Continue clearing rain water
Fri (05/09) | 05 Sep 2025 | P1 |  | Pile head hacking current status
Fri (05/09) | 05 Sep 2025 | P4 |  | Crosshead rebar and tendon duct works
Fri (05/09) | 05 Sep 2025 | S1 |  | Column formwork closing ongoing. Tmr to cast
Fri (05/09) | 05 Sep 2025 | N1 |  | Tendon wires installation for stress works
Fri (05/09) | 05 Sep 2025 | N3 |  | Falsework dismantling
Fri (05/09) | 05 Sep 2025 | P16 |  | Tendon wire installation for stressing works
Fri (05/09) | 05 Sep 2025 | P19 |  | PVC pipe installation
Fri (05/09) | 05 Sep 2025 | 800mm PW |  | Excavation and ERSS for butterfly valve
Fri (05/09) | 05 Sep 2025 | PMH26-PMH28 |  | Pipe laying protection above DR3
Fri (05/09) | 05 Sep 2025 | P50 |  | L5 caisson, last section casting
Fri (05/09) | 05 Sep 2025 | P50 |  | Preparation work for PIT test
Fri (05/09) | 05 Sep 2025 | 22KV diversion |  | Backfilling and ERSS removal
Fri (05/09) | 05 Sep 2025 | P19 |  | Segment adjustment ongoing
Fri (05/09) | 05 Sep 2025 | P16 |  | Preparation for stressing NB U02/D02
Fri (05/09) | 05 Sep 2025 | N1 |  | Preparation for stressing for D02/U02
Fri (05/09) | 05 Sep 2025 | P49 |  | North side hacking JGP Grout, south side start preparation for L5 caisson rebar work
Fri (05/09) | 05 Sep 2025 | P48 |  | Excavation to L2 caisson layer
Fri (05/09) | 05 Sep 2025 | DR3 |  | Manual excavation and utility support installation
Fri (05/09) | 05 Sep 2025 | P44 |  | Side formwork installation
Fri (05/09) | 05 Sep 2025 | BR7A |  | Continue rebar works
Fri (05/09) | 05 Sep 2025 | BR3 transfer beam |  | Waterproofing membrane laying in progress
Fri (05/09) | 05 Sep 2025 | BR10 transfer beam |  | Protective screeding was cast
Fri (05/09) | 05 Sep 2025 | BR7B |  | Continue excavation and disposal works. Plan to finish excavation by this week
Fri (05/09) | 05 Sep 2025 | S1 |  | Continue Formwork closing for column
Fri (05/09) | 05 Sep 2025 | P4 |  | Rebar installation ongoing
Fri (05/09) | 05 Sep 2025 | P1 |  | Pile head hacking works
Fri (05/09) | 05 Sep 2025 | Outside BR10 |  | Temporary backfilling ongoing
Fri (05/09) | 05 Sep 2025 | Balance BR10 retaining wall |  | 2nd lift cast last night
Sat (06/09) | 06 Sep 2025 | P44 |  | Crosshead shear link rebar works ongoing
Sat (06/09) | 06 Sep 2025 | P43 |  | Falsework erection and assembly works in progress
Sat (06/09) | 06 Sep 2025 | BR7B |  | Excavation completed. LSS backfill was done last night. Today plan for partial lean concrete casting
Sat (06/09) | 06 Sep 2025 | BR8A |  | Excavation and hacking of rebars for disposal ongoing
Sat (06/09) | 06 Sep 2025 | BR27 |  | Dwall rectification in progress
Sat (06/09) | 06 Sep 2025 | CCE | GL E5-E8 | Waler rebar works in progress
Sat (06/09) | 06 Sep 2025 | BR34 |  | Rebar works and RTO inspection ongoing
Sat (06/09) | 06 Sep 2025 | P45 |  | KTC excavation works ongoing for 1st layer
Sat (06/09) | 06 Sep 2025 | DR-3 |  | LECE utility supports works
Sat (06/09) | 06 Sep 2025 | P48 |  | Access shifting ongoing
Sat (06/09) | 06 Sep 2025 | P49 |  | KTC Hacking works for JGP grout in progress for 5th layer
Sat (06/09) | 06 Sep 2025 | P50 |  | Formwork dismantling for 5th layer ongoing
Sat (06/09) | 06 Sep 2025 | P50 |  | PIT test for P50-8 in progress
Sat (06/09) | 06 Sep 2025 | CCE4 near P40 |  | Wall rebar works in progress
Sat (06/09) | 06 Sep 2025 | CCE4 near RS |  | 1st lift retaining wall formwork installation in progress. Plan for casting tmr
Sat (06/09) | 06 Sep 2025 | PMH26-PMH28 |  | Backfilling and levelling works
Sat (06/09) | 06 Sep 2025 | Zone 4 |  | 800mm water pipe excavation and shoring for BVC
Sat (06/09) | 06 Sep 2025 | BR7A |  | Casting postponed to tomorrow due to rebar comments by qps team. Rebar inspection and cleaning ongoing. Thereafter to install shearlinks and final inspection to be done tomorrow
Sat (06/09) | 06 Sep 2025 | P19 |  | Segment adjustment and inner Formwork installation for wet stitching in progress
Sat (06/09) | 06 Sep 2025 | P17 |  | Unloading of materials for SH assembly
Sat (06/09) | 06 Sep 2025 | P16 |  | Preparation for stressing works for SB D02/U02
Sat (06/09) | 06 Sep 2025 | S1 |  | Scaffold erection for column casting. To cast in the afternoon
Sat (06/09) | 06 Sep 2025 | P4 |  | Crosshead rebar current status
Sat (06/09) | 06 Sep 2025 | P3 |  | Tie rod removal for Formwork dismantling in progress
Sat (06/09) | 06 Sep 2025 | P1 |  | Pile head hacking
Sat (06/09) | 06 Sep 2025 | BR16B |  | Excavation in progress
Sat (06/09) | 06 Sep 2025 | Exit 3 |  | Post-drilling for struts ongoing
Sat (06/09) | 06 Sep 2025 | P44 |  | Preparation for Formwork closing. Cleaning ongoing
Sat (06/09) | 06 Sep 2025 | GL11-12 |  | Excavation and disposal in progress
Sat (06/09) | 06 Sep 2025 | Exit 2 capping beam |  | Formwork dismantled. Now preparing to cast the balance area near retaining wall
Sat (06/09) | 06 Sep 2025 | Outside BR10 |  | Temporary backfilling for access. Dewatering to be done at balance area then soil will be levelled the same as current access level
Sat (06/09) | 06 Sep 2025 | BR10 | GL16-18 | Preparation for LSS backfill. Steel plates temporarily placed as counterweight for the EPS blocks
Sat (06/09) | 06 Sep 2025 | BR8A |  | Balance abandoned drain exposed and Hirose preparing for remaining utility support works
Sat (06/09) | 06 Sep 2025 | BR27 |  | Formwork installation for Dwall rectification
Sat (06/09) | 06 Sep 2025 | BR34 |  | Continue rebar works
Sat (06/09) | 06 Sep 2025 | Exit 1 |  | Stockpile disposal ongoing
Sat (06/09) | 06 Sep 2025 | P43 |  | Crosshead Falsework current status
Sat (06/09) | 06 Sep 2025 | P45 |  | KTC continue excavation works for 1st layer
Sat (06/09) | 06 Sep 2025 | DR-3 |  | Utility supports works
Sat (06/09) | 06 Sep 2025 | P48 |  | Access making ongoing
Sat (06/09) | 06 Sep 2025 | P49 |  | BRC installation for 5th layer
Sat (06/09) | 06 Sep 2025 | P50 |  | Continue Formwork dismantling for 5th layer and housekeeping works
Sat (06/09) | 06 Sep 2025 | Zone 4 |  | ERSS installation completed for 800mm water pipe BVC. Excavation ongoing
Sat (06/09) | 06 Sep 2025 | Zone 4 |  | Preparation works for 300mm water pipe link up locations
Sat (06/09) | 06 Sep 2025 | CCE4 near RS |  | Continue formwork installation for 1st lift retaining wall
Sat (06/09) | 06 Sep 2025 | CCE4 near P40 |  | Wall rebar works in progress & excavation below BR30
Sat (06/09) | 06 Sep 2025 | BR7A |  | Reinspection was done as per rto comments. Now continue shearlinks installation and cleaning works. Casting planned for tmr
Sat (06/09) | 06 Sep 2025 | P4 |  | Tendon duct head installation ongoing
Sat (06/09) | 06 Sep 2025 | P3 |  | Continue tie rod dismantling
Sat (06/09) | 06 Sep 2025 | P1 |  | Pile head hacking in progress
Sat (06/09) | 06 Sep 2025 | S1 |  | 2nd lift column casting in progress
Sat (06/09) | 06 Sep 2025 | N1 |  | Scffold erection in progress for tonight segment launching
Sat (06/09) | 06 Sep 2025 | P16 |  | Stressing completed for SB D02/U02
Sat (06/09) | 06 Sep 2025 | P17 |  | Unloading of SH materials
Sat (06/09) | 06 Sep 2025 | P19 |  | Inner Formwork installation for 1st pair stitching
Sat (06/09) | 06 Sep 2025 | BR16B |  | Excavation in progress
Sat (06/09) | 06 Sep 2025 | BR20 |  | Continue exposing couplers
Sat (06/09) | 06 Sep 2025 | BR19 |  | Casting started last night and completed this morning at 6am. Now levelling and power floater works ongoing
Mon (08/09) | 08 Sep 2025 | 800mm dia water pipe |  | Excavation and ERSS installation for butterfly valve
Mon (08/09) | 08 Sep 2025 | CCE4 |  | Retaining wall (B2-46) formwork installation in progress, target to cast it today
Mon (08/09) | 08 Sep 2025 | CCE4 |  | Linkway wall (B2-44) rebar installation is in progress
Mon (08/09) | 08 Sep 2025 | P44 |  | Final inspection completed, pending minor comments. Target to cast today at 5pm
Mon (08/09) | 08 Sep 2025 | Exit 2 capping beam area |  | Currently no activity
Mon (08/09) | 08 Sep 2025 | P19 |  | Outer Formwork closing for wet stitching. Target to cast by Wed
Mon (08/09) | 08 Sep 2025 | P16 |  | Preparation for segment launching tonight
Mon (08/09) | 08 Sep 2025 | N1 |  | Stressing ongoing for 3rd pair segment and scaffold erection for 4th pair segment
Mon (08/09) | 08 Sep 2025 | BR7A |  | Casting was completed earlier this morning. Now levelling and power floater works ongoing
Mon (08/09) | 08 Sep 2025 | BR10 | GL16-18 | Continue LSS backfilling
Mon (08/09) | 08 Sep 2025 | S1 |  | Column curing works
Mon (08/09) | 08 Sep 2025 | P4 |  | Tendon duct head installation works
Mon (08/09) | 08 Sep 2025 | P3 |  | Crane setting up for Formwork dismantling
Mon (08/09) | 08 Sep 2025 | P1 |  | Pile head hacking works
Mon (08/09) | 08 Sep 2025 | BR7B |  | Soil disposal and Dongah measuring at dwall side for couplers
Mon (08/09) | 08 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Mon (08/09) | 08 Sep 2025 | GL E5-E8 |  | Ongoing rebar installation for waler
Mon (08/09) | 08 Sep 2025 | BR27 |  | Exposing of coupler for DWall ST78&ST79
Mon (08/09) | 08 Sep 2025 | BR8B |  | Hirose preparing for top plate welding for decking beam works
Mon (08/09) | 08 Sep 2025 | Exit 1 |  | Rebar work continues for BR34, target to cast it by 10 Sep
Mon (08/09) | 08 Sep 2025 | Exit 1 |  | Clearing of stockpile @ new ECM pond
Mon (08/09) | 08 Sep 2025 | P49 last layer caisson |  | Rebar work in progress. 50% completed
Mon (08/09) | 08 Sep 2025 | P50 |  | Clear debris and rubbish. Tonight plan for base lean concrete for pile cap
Mon (08/09) | 08 Sep 2025 | P48 |  | Excavation for 2nd layer caisson in progress
Mon (08/09) | 08 Sep 2025 | DR3 |  | Utility support installation and welding
Mon (08/09) | 08 Sep 2025 | P45 |  | Continue clearing cement grout for 1st layer caisson work
Mon (08/09) | 08 Sep 2025 | BR16B |  | Excavation in progress
Mon (08/09) | 08 Sep 2025 | BR20 |  | Continue exposing couplers
Mon (08/09) | 08 Sep 2025 | BR20 |  | Debonding sheet laying, BR19: Surface roughening ongoing
Mon (08/09) | 08 Sep 2025 | BR10 | GL16-18 | Continue LSS backfilling, 458/700m3
Mon (08/09) | 08 Sep 2025 | BR4 |  | Start to expose couplers
Mon (08/09) | 08 Sep 2025 | BR7A |  | Curing
Mon (08/09) | 08 Sep 2025 | GL E5-E8 |  | Waler beam rebar works in progress
Mon (08/09) | 08 Sep 2025 | CCE4 near P40 |  | Continue wall rebar works
Tue (09/09) | 09 Sep 2025 | Balance BR10 retaining wall |  | 2nd lift formwork dismantling
Tue (09/09) | 09 Sep 2025 | BR3 transfer beam |  | Protective screeding was done last evening
Tue (09/09) | 09 Sep 2025 | BR7B |  | Clearing soil and surveyor marking ongoing. Plan for lean con casting today, BR4: Preparing to continue CJ hacking
Tue (09/09) | 09 Sep 2025 | BR10 | GL16-18 | LSS backfill, 1st layer completed
Tue (09/09) | 09 Sep 2025 | 800mm dia water pipe |  | Levelling of the base. Today will lay 2.5m length of pipe and quarry laying at the base of butterfly valve
Tue (09/09) | 09 Sep 2025 | BR8A |  | Manual hacking near utility area and utility support works in progress
Tue (09/09) | 09 Sep 2025 | P50 |  | Lean concrete of pile cap base
Tue (09/09) | 09 Sep 2025 | P49 |  | Clearing debris. Rebar for last layer caisson completed around 90%
Tue (09/09) | 09 Sep 2025 | P49 |  | Covering protruding rebar. Today to cast around 25% of last layer caisson
Tue (09/09) | 09 Sep 2025 | P48 |  | Preparing to start rebar work for 2nd layer caisson
Tue (09/09) | 09 Sep 2025 | DR3 |  | Continue exposing services to support and utility support installation work
Tue (09/09) | 09 Sep 2025 | P45 |  | Continue excavation and disposal
Tue (09/09) | 09 Sep 2025 | P44 |  | Crosshead casting last night
Tue (09/09) | 09 Sep 2025 | P43 |  | Transfer beam installation
Tue (09/09) | 09 Sep 2025 | PMH26-PMH28 |  | Wee Guan clearing their materials to demob
Tue (09/09) | 09 Sep 2025 | 800mm dia water pipe |  | Short pipe laid. Temporary stop work due to rain. Will continue with butterfly valve base lean concrete
Tue (09/09) | 09 Sep 2025 | BR16B |  | Continue excavation
Tue (09/09) | 09 Sep 2025 | BR20 |  | Start bottom rebar works
Tue (09/09) | 09 Sep 2025 | Exit 3 |  | Currently no activity
Tue (09/09) | 09 Sep 2025 | BR7B |  | Exposing coupler & preparing for base lean con casting
Tue (09/09) | 09 Sep 2025 | GL29 |  | Temporary RCU drain works in progress. Plan for base slab casting today
Tue (09/09) | 09 Sep 2025 | CCE4 |  | Preparation work for waterproofing is in progress
Tue (09/09) | 09 Sep 2025 | P50 |  | Lean con casting completed
Tue (09/09) | 09 Sep 2025 | P49 |  | (South and mid) formwork closing, (north) excavation on going
Tue (09/09) | 09 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Tue (09/09) | 09 Sep 2025 | GL E5-E8 |  | Continues rebar installation for waler
Tue (09/09) | 09 Sep 2025 | BR34 |  | Rebar & formwork installation is in progress
Tue (09/09) | 09 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Tue (09/09) | 09 Sep 2025 | P48 |  | (north) excavation on going, (south) preparation for L2 caisson rebar work
Wed (10/09) | 10 Sep 2025 | P50 |  | Preparing for scaffold erection for S2 layer strut removal
Wed (10/09) | 10 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Wed (10/09) | 10 Sep 2025 | BR34 |  | Shear links & formwork installation in progress, will cast it today
Wed (10/09) | 10 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Wed (10/09) | 10 Sep 2025 | P49 |  | Platform erection for casting. Last layer 30% of caisson will cast today
Wed (10/09) | 10 Sep 2025 | P49 Changi bound |  | Today will handover for rebar work for balance area
Wed (10/09) | 10 Sep 2025 | S1-1 |  | BR16B, Excavation and disposal ongoing
Wed (10/09) | 10 Sep 2025 | BR27 |  | Cleaning in progress & will repair the damaged lean con today
Wed (10/09) | 10 Sep 2025 | GL E5-E8 |  | Rebar inspection is in progress for the waler
Wed (10/09) | 10 Sep 2025 | Near BR10 |  | Main beam preparation for balance decking works
Wed (10/09) | 10 Sep 2025 | BR7B |  | Lean con cast evening. Now continue surface roughening at BR4 and survey marking
Wed (10/09) | 10 Sep 2025 | Between BR8A and BR8B |  | Top plate welding for balance decking works
Wed (10/09) | 10 Sep 2025 | P48 |  | Excavation for 2nd layer caisson done around 70%
Wed (10/09) | 10 Sep 2025 | DR3 |  | Continue manual excavation to provide utility support
Wed (10/09) | 10 Sep 2025 | P45 |  | Modification of 3 secondary beam to facilitate excavation work. To complete today
Wed (10/09) | 10 Sep 2025 | S1-2 |  | BR20, Exposing coupler and rebar works ongoing
Wed (10/09) | 10 Sep 2025 | B2-44 |  | Linkway wall rebar installation is in progress
Wed (10/09) | 10 Sep 2025 | B2-45 |  | Preparation work for waterproofing, surface inspection arranged @ 2pm
Wed (10/09) | 10 Sep 2025 | B2-46 |  | Retaining wall formwork plan to remove today
Wed (10/09) | 10 Sep 2025 | P43 |  | Transfer beam installed. Today to continue main beam installation
Wed (10/09) | 10 Sep 2025 | GL16-18 |  | EPS blocks installation ongoing
Wed (10/09) | 10 Sep 2025 | P4 |  | Tendon duct installation
Wed (10/09) | 10 Sep 2025 | P3 |  | Formwork dismantling
Wed (10/09) | 10 Sep 2025 | P1 |  | Bored pile hacking
Wed (10/09) | 10 Sep 2025 | N1 |  | No activity
Wed (10/09) | 10 Sep 2025 | Between BR8A and BR8B |  | Beam installation in progress, balance 1 more beam. The starhub pipes will be locally shifted about 300mm to facilitate the installation
Wed (10/09) | 10 Sep 2025 | GL16-18 |  | Continue installation of EPS blocks
Wed (10/09) | 10 Sep 2025 | BR7B |  | Dwall surface cleaning and preparing area for balance lean con casting
Wed (10/09) | 10 Sep 2025 | BR7A |  | Formwork dismantling and CJ hacking at BR2 area
Wed (10/09) | 10 Sep 2025 | P19 |  | Stitching formwork completed. Ready for casting at 5pm
Wed (10/09) | 10 Sep 2025 | P50 |  | Moveable scaffold erection done. Wendyng straightening the pile rebar for lapping with pile cap
Wed (10/09) | 10 Sep 2025 | P49 |  | Tonight will handover the area for 2nd stage formwork closing. 1st stage casting in progress
Wed (10/09) | 10 Sep 2025 | P48 |  | Continue excavation for 2nd layer caisson
Wed (10/09) | 10 Sep 2025 | P45 |  | Modification of support done. KTC can resume excavation. Space open up for mini to lower down
Wed (10/09) | 10 Sep 2025 | DR3 |  | Continue utility support welding
Wed (10/09) | 10 Sep 2025 | BR16B |  | Continue excavation
Wed (10/09) | 10 Sep 2025 | BR20 |  | Rebar works in progress
Wed (10/09) | 10 Sep 2025 | B2-43 |  | Excavation in progress
Wed (10/09) | 10 Sep 2025 | BR27 |  | Preparing for lean con casting at skin wall area
Wed (10/09) | 10 Sep 2025 | BR7B |  | Formwork installation for lean con casting at skin wall area
Wed (10/09) | 10 Sep 2025 | BR34 |  | Cleaning and housekeeping ongoing. Plan for final inspection ard 8pm
Wed (10/09) | 10 Sep 2025 | BR34 |  | MPI test in progress. Final inspection will be conducted thereafter
Thu (11/09) | 11 Sep 2025 | P49 |  | North side levelling, afternoon will handover to WD for caisson work
Thu (11/09) | 11 Sep 2025 | P48 |  | Excavation to L2 caisson level
Thu (11/09) | 11 Sep 2025 | P47 |  | Clearing stockpile to expose UKP
Thu (11/09) | 11 Sep 2025 | DR3 |  | Utility support installation
Thu (11/09) | 11 Sep 2025 | P45 |  | Utility support rectification work
Thu (11/09) | 11 Sep 2025 | P45 |  | Excavation to L1 caisson level
Thu (11/09) | 11 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Thu (11/09) | 11 Sep 2025 | BR27 |  | Cleaning in progress, planning to lay debonding sheet today
Thu (11/09) | 11 Sep 2025 | BR7B |  | Surface levelling and exposing kingpost
Thu (11/09) | 11 Sep 2025 | Blk 4 |  | Temporary drain formwork installation in progress
Thu (11/09) | 11 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Thu (11/09) | 11 Sep 2025 | GL E5-E8 |  | Ongoing rebar & formwork installation for the waler
Thu (11/09) | 11 Sep 2025 | BR8B |  | Excavation in progress below decking
Thu (11/09) | 11 Sep 2025 | Between BR8A and BR8B |  | Starhub pipes have been locally shifted for installation for last beam for decking. Now preparing for installation
Thu (11/09) | 11 Sep 2025 | N1 |  | Scaffolding erection for stressing work
Thu (11/09) | 11 Sep 2025 | N4-N5 |  | Preparation for clamping beam installation
Thu (11/09) | 11 Sep 2025 | BR7B |  | Continue surface roughening at BR2 area
Thu (11/09) | 11 Sep 2025 | GL16-18 |  | EPS blocks laying completed. Today will continue for next layer LSS backfill, GL18-19: Soil backfilling in progress
Thu (11/09) | 11 Sep 2025 | P19 |  | No activity
Thu (11/09) | 11 Sep 2025 | P16 |  | Preparation for Segment stressing work in progress
Thu (11/09) | 11 Sep 2025 | P43 |  | Crosshead falsework main beam installation
Thu (11/09) | 11 Sep 2025 | B2-46 |  | Retaining wall formwork dismantling is in progress
Thu (11/09) | 11 Sep 2025 | B2-45 |  | Preparation work in progress for waterproofing
Thu (11/09) | 11 Sep 2025 | B2-44 |  | Linkway wall rebar installation is in progress
Thu (11/09) | 11 Sep 2025 | P4 |  | PT tendon duct installation
Thu (11/09) | 11 Sep 2025 | P3 |  | No activity
Thu (11/09) | 11 Sep 2025 | P1 |  | PIT test ongoing
Thu (11/09) | 11 Sep 2025 | Along blk 4/DR2 |  | So far no silty discharge observed
Thu (11/09) | 11 Sep 2025 | P4 |  | No activity
Thu (11/09) | 11 Sep 2025 | P16 |  | 4th segment SB stressing completed
Thu (11/09) | 11 Sep 2025 | 800mm PW |  | MPI test completed. Now preparing butterfly valve joint
Thu (11/09) | 11 Sep 2025 | BR8B |  | Continue excavation and disposal works
Thu (11/09) | 11 Sep 2025 | BR7B |  | Surface cleaning and continue roughening works
Thu (11/09) | 11 Sep 2025 | GL16-18 |  | Next layer LSS backfilling ongoing
Thu (11/09) | 11 Sep 2025 | BR7A |  | Formwork dismantling ongoing
Thu (11/09) | 11 Sep 2025 | P48 |  | Excavation to L2 caisson level
Thu (11/09) | 11 Sep 2025 | DR3 |  | No activity
Thu (11/09) | 11 Sep 2025 | P45 |  | No activity
Thu (11/09) | 11 Sep 2025 | 800mm PW |  | Ready for MPI test today
Fri (12/09) | 12 Sep 2025 | B2-46 |  | Continues dismantling of formwork for retaining wall
Fri (12/09) | 12 Sep 2025 | B2-45 |  | Ongoing preparation work for waterproofing
Fri (12/09) | 12 Sep 2025 | B2-44 |  | Linkway wall rebar&formwork installation is in progress, target to cast by next Wed
Fri (12/09) | 12 Sep 2025 | B2-43 |  | Current excavation status below BR31
Fri (12/09) | 12 Sep 2025 | GL E5-E8 |  | Continues rebar & formwork installation for waler beam, target to cast it by this week
Fri (12/09) | 12 Sep 2025 | BR27 |  | Debonding sheet laid yesterday, will start rebar installation today
Fri (12/09) | 12 Sep 2025 | Exit 1 |  | Correct stocpil stockpile status @ new ECM pond
Fri (12/09) | 12 Sep 2025 | P19 |  | Preparation of stressing work
Fri (12/09) | 12 Sep 2025 | P16 |  | Tie down bar stressing on going
Fri (12/09) | 12 Sep 2025 | N1 |  | No activity
Fri (12/09) | 12 Sep 2025 | P45 |  | Modification of support for loading point was done. Current status
Fri (12/09) | 12 Sep 2025 | P45 |  | Status of excavation done for 1st layer caisson. Now worker go for lunch
Fri (12/09) | 12 Sep 2025 | DR3 |  | Manual exposing for services support. Almost completed
Fri (12/09) | 12 Sep 2025 | P48 |  | Continue excavation toward changi bound. To complete by this week
Fri (12/09) | 12 Sep 2025 | P48 |  | Trial trench for 300mm dia water pipe link up point
Fri (12/09) | 12 Sep 2025 | P49 |  | Preparing to bring up mini. 2nd stage of caisson to cast at 1PM
Fri (12/09) | 12 Sep 2025 | PMH26 |  | Bracket installation for access ladder
Fri (12/09) | 12 Sep 2025 | DR4 |  | Barricaded duct laid area
Fri (12/09) | 12 Sep 2025 | P3 |  | No activity. Both wing formwork dismantled
Fri (12/09) | 12 Sep 2025 | P4 |  | Tendon duct installation
Fri (12/09) | 12 Sep 2025 | P43 |  | Current status, working platform erection ongoing
Fri (12/09) | 12 Sep 2025 | BR7B |  | Rebar works in progress, Dwall couplers exposing, KP U-bar welding works ongoing
Fri (12/09) | 12 Sep 2025 | BR8B |  | Excavation in progress
Fri (12/09) | 12 Sep 2025 | 22KV diversion |  | Pumping out water inside manhole for access ladder bracket installation
Fri (12/09) | 12 Sep 2025 | BR10 |  | LSS backfilling in progress
Fri (12/09) | 12 Sep 2025 | S1-1 |  | BR16B, Excavation completed, exposing coupler ongoing
Fri (12/09) | 12 Sep 2025 | P49 |  | Casting of 2nd part for last caisson
Fri (12/09) | 12 Sep 2025 | P48 |  | Preparing for 2nd layer 1st part of caisson formwork closing
Fri (12/09) | 12 Sep 2025 | P49 |  | Continue casting
Fri (12/09) | 12 Sep 2025 | P45 |  | Excavation done around 50% as of now for 1st layer caisson
Fri (12/09) | 12 Sep 2025 | DR3 |  | Continue exposing services for support
Fri (12/09) | 12 Sep 2025 | P43 |  | Current status of working platform installation. Netting installation in progress to prevent falling object
Fri (12/09) | 12 Sep 2025 | P19 |  | Preparation for stressing work
Fri (12/09) | 12 Sep 2025 | P16 SB |  | Preparation to launch two segment tonight
Fri (12/09) | 12 Sep 2025 | N1 |  | Preparation to launch one segment tonight
Fri (12/09) | 12 Sep 2025 | P4 |  | Rain water drain pipe installed. Now worker went for dinner break
Fri (12/09) | 12 Sep 2025 | P1 |  | Levelling for lean concrete tonight
Fri (12/09) | 12 Sep 2025 | P50 |  | No activity already
Fri (12/09) | 12 Sep 2025 | P49 |  | 2nd stage casting done. WH arranging Wendyng manpower to complete rebar work for last stage. Plan to complete all by this week
Fri (12/09) | 12 Sep 2025 | P48 |  | Excavation for 300mm dia water pipe link up point
Fri (12/09) | 12 Sep 2025 | P48 |  | Levelling for working platform erection
Sat (13/09) | 13 Sep 2025 | Zone 1 |  | No silty water flow to live road
Sat (13/09) | 13 Sep 2025 | N1 |  | 9 segments installed as of now
Sat (13/09) | 13 Sep 2025 | Zone 1 |  | No silty water go to live road
Sat (13/09) | 13 Sep 2025 | P4 |  | 4/12 U pipe installed. Will resume after rain
Sat (13/09) | 13 Sep 2025 | B2-44 |  | Linkway wall rebar&formwork installation is in progress
Sat (13/09) | 13 Sep 2025 | B2-43 |  | Current excavation status below BR31
Sat (13/09) | 13 Sep 2025 | B2-45 |  | Ongoing preparation work for waterproofing
Sat (13/09) | 13 Sep 2025 | P43 |  | Current status of working platform installation
Sat (13/09) | 13 Sep 2025 | P45 |  | Continue removal of grout block
Sat (13/09) | 13 Sep 2025 | DR3 |  | Continue manual excavation for utility support
Sat (13/09) | 13 Sep 2025 | P48 |  | Formwork closing for 2nd layer caisson
Sat (13/09) | 13 Sep 2025 | P48 |  | Exposing 300mm dia water pipe link up point
Sat (13/09) | 13 Sep 2025 | P50 |  | Set up crane for strut removal
Sat (13/09) | 13 Sep 2025 | P19 |  | Stitching formwork removal and preparing for stressing work
Sat (13/09) | 13 Sep 2025 | P16 |  | Stressing for segment installed last night
Sat (13/09) | 13 Sep 2025 | P15 |  | Access dismantling
Sat (13/09) | 13 Sep 2025 | S1-1 |  | BR16B, Excavation ongoing
Sat (13/09) | 13 Sep 2025 | S1-2 |  | BR20, rebar works ongoing
Sat (13/09) | 13 Sep 2025 | N1 |  | Scaffold erection for segment launching
Sat (13/09) | 13 Sep 2025 | P4 |  | Rain water pipe installation
Sat (13/09) | 13 Sep 2025 | P1 |  | Clearing soil and debris. Will start rebar work after that
Sat (13/09) | 13 Sep 2025 | B2-44 |  | Linkway wall rebar&formwork installation is in progress
Sat (13/09) | 13 Sep 2025 | P50 |  | Woh hup unloading rebar almost done. This crane will be use for S2 layer dismantling
Sat (13/09) | 13 Sep 2025 | P48 |  | Exposed the old pipe and new pipe for water pipe link up on Tuesday
Sat (13/09) | 13 Sep 2025 | DR3 |  | Clearing materials and hardcore to extend excavation
Sat (13/09) | 13 Sep 2025 | DR3 |  | Continue exposing services for support
Sat (13/09) | 13 Sep 2025 | P45 |  | Continue hacking and removal of grout
Sat (13/09) | 13 Sep 2025 | P44 |  | Formwork support loosening for removal
Sat (13/09) | 13 Sep 2025 | P43 |  | Barricade installation around crosshead platform
Sat (13/09) | 13 Sep 2025 | P19 |  | Woh hup started stitching formwork dismantling and Ultracon preparing for stessing work
Sat (13/09) | 13 Sep 2025 | Zone 2 |  | No silty water discharge to public road
Mon (15/09) | 15 Sep 2025 | P43 |  | Side wing fwk removal ongoing, P44: access erection ongoing
Mon (15/09) | 15 Sep 2025 | P20 |  | Preparation for starter hanger installation and shifting from p19 for 1st pair segment launching
Mon (15/09) | 15 Sep 2025 | P19 |  | Stitching Formwork dismantling
Mon (15/09) | 15 Sep 2025 | B2-44 |  | Linkway wall rebar/formwork installation in progress, target to cast it by Thu
Mon (15/09) | 15 Sep 2025 | CCE4 |  | Continues preparation work for waterproofing
Mon (15/09) | 15 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Mon (15/09) | 15 Sep 2025 | P16 |  | Preparation for stress for SB U06/D06
Mon (15/09) | 15 Sep 2025 | N1 |  | 5th pair Strand installation for stressing
Mon (15/09) | 15 Sep 2025 | BR27 |  | Bottom bar installation is in progress
Mon (15/09) | 15 Sep 2025 | Exit 1 |  | Current stockpile status
Mon (15/09) | 15 Sep 2025 | P50 |  | Wendyng started rebar placing. 8 workers. HSL already completed work
Mon (15/09) | 15 Sep 2025 | P49 |  | Last part of last layer caisson formwork closing in progress. To cast tomorrow
Mon (15/09) | 15 Sep 2025 | 300mm dia water pipe link up |  | Preparation all done for link up/ cap off work. Now checking of valves and installed meter on FH to check the water pressure
Mon (15/09) | 15 Sep 2025 | Near BR10 |  | Balance portion for decking - welding works ongoing
Mon (15/09) | 15 Sep 2025 | BR7B |  | Rebar works in progress, Dwall rectification in progress, BR7A:, Surface roughening ongoing
Mon (15/09) | 15 Sep 2025 | BR8A, BR8B |  | Excavation in progress
Mon (15/09) | 15 Sep 2025 | BR8B |  | Partial LSS backfill was done yesterday
Mon (15/09) | 15 Sep 2025 | BR10 |  | BRC laying works & preparing for casting for access diversion
Mon (15/09) | 15 Sep 2025 | GL16 |  | Manual excavation below services for steel plates utility protection
Mon (15/09) | 15 Sep 2025 | P45 |  | Continue excavation for 1st layer caisson
Mon (15/09) | 15 Sep 2025 | P45-46 |  | Area prepare for link up
Mon (15/09) | 15 Sep 2025 | DR3 |  | Clearing rain water. Continue utility support welding
Mon (15/09) | 15 Sep 2025 | DR3 old existing drain |  | TT for coring work
Mon (15/09) | 15 Sep 2025 | P48 |  | Formwork closing done for 1st part caisson
Mon (15/09) | 15 Sep 2025 | P20 |  | Starter hanger installation
Mon (15/09) | 15 Sep 2025 | P19 |  | Stitching formwork dismantling
Mon (15/09) | 15 Sep 2025 | P16 |  | Stressing for SB U06/D06 completed
Mon (15/09) | 15 Sep 2025 | N1 |  | 5th pair preparation for stressing
Mon (15/09) | 15 Sep 2025 | P4 |  | No activity
Mon (15/09) | 15 Sep 2025 | P1 |  | Slurry cleaning on going. Preparing for lean concrete
Mon (15/09) | 15 Sep 2025 | P50 |  | Pile cap rebar works ongoing
Mon (15/09) | 15 Sep 2025 | P49 |  | L5 caisson last section closing formwork..tomorrow casting
Mon (15/09) | 15 Sep 2025 | P48 |  | No activity
Mon (15/09) | 15 Sep 2025 | P45 |  | No activity
Mon (15/09) | 15 Sep 2025 | P43 |  | Scaffolding erection
Mon (15/09) | 15 Sep 2025 | P44 |  | No activity. Balance 1 side wing formwork to be dismantled
Tue (16/09) | 16 Sep 2025 | GL14-16 |  | Decking installation continues infront of BR10, target to complete by 18 Sep
Tue (16/09) | 16 Sep 2025 | GL18-21 |  | Backfilling in progress for access diversion @ BR3
Tue (16/09) | 16 Sep 2025 | BR7B |  | Rebar installation is in progress, target to cast it by end of this week
Tue (16/09) | 16 Sep 2025 | BR8A & BR8B |  | Ongoing excavation & soil disposal
Tue (16/09) | 16 Sep 2025 | CCE4 |  | Continues preparation work for waterproofing
Tue (16/09) | 16 Sep 2025 | B2-44 |  | Linkway wall rebar/formwork installation is in progres
Tue (16/09) | 16 Sep 2025 | B2-43 |  | Ongoing excavation & soil disposal
Tue (16/09) | 16 Sep 2025 | BR27 |  | Continue bottom bar installation & target to cast it by 25 Sep
Tue (16/09) | 16 Sep 2025 | Exit 1 |  | Current stockpile @ new ECM pond
Tue (16/09) | 16 Sep 2025 | P16 |  | Awaiting for 600T crane to shift at P17 area. Maintenance on going
Tue (16/09) | 16 Sep 2025 | N1 5th pair |  | Grouting cap installation
Tue (16/09) | 16 Sep 2025 | P44 |  | Balance 1 side wing fwk to remove, P43: access & working platform erection in progress
Tue (16/09) | 16 Sep 2025 | P14 |  | Preparation for crosshead tendon grouting works
Tue (16/09) | 16 Sep 2025 | P1 |  | Steel plate bracing welding in progress
Tue (16/09) | 16 Sep 2025 | S1-2 |  | BR20, Rebar works and shear links installation ongoing, Tmr to complete and to close formwork tmr as well, Thursday plan to cast
Tue (16/09) | 16 Sep 2025 | S1-2 |  | BR21, Excavation and disposal ongoi
Tue (16/09) | 16 Sep 2025 | 800mm PW |  | No activity
Tue (16/09) | 16 Sep 2025 | P50 |  | Pilecap rebar work ongoing
Tue (16/09) | 16 Sep 2025 | P49 |  | Preparation for casting platform. Today going to cast last section of L5 caisson
Tue (16/09) | 16 Sep 2025 | P48 |  | L2 caisson (south) casting completed. No excavation, due to preparation work for link up work
Tue (16/09) | 16 Sep 2025 | DR3 |  | Preparation to install UKP end plate
Tue (16/09) | 16 Sep 2025 | P45 |  | Grout hacking in progress
Wed (17/09) | 17 Sep 2025 | P43 |  | Soffit fwk & fwk support erection ongoing
Wed (17/09) | 17 Sep 2025 | P44 |  | Access erection ongoing for minor rectification work on surface & balance side wing fwk removal
Wed (17/09) | 17 Sep 2025 | P45 |  | Currently excavation on standby, will resume after lunch due to linkup water pressure
Wed (17/09) | 17 Sep 2025 | P47 / DR3 | remainder JGP | TT ongoing B-165
Wed (17/09) | 17 Sep 2025 | P16 downchainage |  | Now shifting, to be dismantled today and shift to P17
Wed (17/09) | 17 Sep 2025 | P14-15 segment 2nd stage PT |  | Strand pulling in progress
Wed (17/09) | 17 Sep 2025 | CCE4 |  | Continue preparation work for waterproof, target to handover the area to Maxbond by end of today
Wed (17/09) | 17 Sep 2025 | B2-44 |  | Linkway wall formwork installation, target to cast it tomorrow
Wed (17/09) | 17 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Wed (17/09) | 17 Sep 2025 | P48 | North | Continue additional support welding work ongoing by LE. Will handover to WH for thrust block fwk & casting in the evening
Wed (17/09) | 17 Sep 2025 | P49 | South Side | Hacking & removing debris, (North / East Side): caisson wall fwk removal ongoing
Wed (17/09) | 17 Sep 2025 | P50 |  | Pile cap rebar ongoing
Wed (17/09) | 17 Sep 2025 | GL14-16 |  | Some metro decks have delivered to site, will continue with installation for the decking
Wed (17/09) | 17 Sep 2025 | BR3 |  | Continues backfilling work for access diversion
Wed (17/09) | 17 Sep 2025 | BR7B |  | Continues with rebar installation
Wed (17/09) | 17 Sep 2025 | BR27 |  | Rebar installation is in progre
Wed (17/09) | 17 Sep 2025 | Exit 1 |  | Preparing access diversion for waler work
Wed (17/09) | 17 Sep 2025 | Exit 1 |  | Current stockpile @ new ECM pond
Wed (17/09) | 17 Sep 2025 | P20 downchainage NB |  | Initial alignment completed
Wed (17/09) | 17 Sep 2025 | P14 |  | Grouting machine inspection by LEW completed. Tonight can proceed with grouting PT duct
Wed (17/09) | 17 Sep 2025 | N1 |  | Falsework erection for last pair of segment launching
Wed (17/09) | 17 Sep 2025 | P4 |  | U-shape stressing tube anti crack reinforcement bars installation
Wed (17/09) | 17 Sep 2025 | P1 |  | Pilecap base rebar installation ongoing
Wed (17/09) | 17 Sep 2025 | P20 downchainage 1st pair |  | SB initial alignment completed. Today to adjust NB
Wed (17/09) | 17 Sep 2025 | P17 upchainage |  | Lifter installed last night. Today to install stressing cage
Thu (18/09) | 18 Sep 2025 | P50 |  | Bar chair installation in progress
Thu (18/09) | 18 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Thu (18/09) | 18 Sep 2025 | BR27 |  | B1 & B2 bottom rebar inspection is in progres
Thu (18/09) | 18 Sep 2025 | DR3 |  | Exposing services for pipe sleeves installation
Thu (18/09) | 18 Sep 2025 | P48 |  | KTC resume excavation
Thu (18/09) | 18 Sep 2025 | P48 |  | Haunching was done for water pipe. Now tidy up the area
Thu (18/09) | 18 Sep 2025 | P49 |  | Clearing rubissh and unused materials. Part of the preparation for base lean concrete
Thu (18/09) | 18 Sep 2025 | BR34 |  | Dismantling of formwork
Thu (18/09) | 18 Sep 2025 | Exit 1 |  | Current stockpile status
Thu (18/09) | 18 Sep 2025 | Exit 1 |  | Preparing for access diversion for waler work
Thu (18/09) | 18 Sep 2025 | N1 |  | Scaffolding erection
Thu (18/09) | 18 Sep 2025 | P14 |  | Tendon duct pulling ongoing
Thu (18/09) | 18 Sep 2025 | DR3/ P47 |  | Continue excavation for main beam installation
Thu (18/09) | 18 Sep 2025 | P4 |  | U-shape stressing tube anti crack reinforcement bars installation
Thu (18/09) | 18 Sep 2025 | P4 |  | Formwork ties installation in progress
Thu (18/09) | 18 Sep 2025 | P1 |  | Pilecap base rebar installation ongoing
Thu (18/09) | 18 Sep 2025 | P45 |  | Continue clearing debris
Thu (18/09) | 18 Sep 2025 | P43 |  | Spreader beam welding work
Thu (18/09) | 18 Sep 2025 | P44 |  | Lowering down unused materials
Thu (18/09) | 18 Sep 2025 | BR8B |  | Preparing formwork for lean con casting at skin wall area
Thu (18/09) | 18 Sep 2025 | BR7B |  | Rebar works in progress
Thu (18/09) | 18 Sep 2025 | P20 |  | Segment adjustment ongoing
Thu (18/09) | 18 Sep 2025 | P17 |  | Shifting of Lifter from p16 in progress. Today to complete shifting
Thu (18/09) | 18 Sep 2025 | GL19-20 |  | Soil levelling and arranging steel plates for the access diversion
Thu (18/09) | 18 Sep 2025 | BR8A |  | Excavation and hacking of balance abandoned drain in progress
Thu (18/09) | 18 Sep 2025 | 800mm PW |  | Butterfly valve internal welding work ongoing
Thu (18/09) | 18 Sep 2025 | P4 |  | Continue U-shape stressing tube anti crack reinforcement bars installation
Thu (18/09) | 18 Sep 2025 | N1 |  | Current Falsework erection status
Thu (18/09) | 18 Sep 2025 | P50 |  | Pile cap rebar (bar chair) installation
Thu (18/09) | 18 Sep 2025 | P49 |  | Clearing material and preparation for lean con
Thu (18/09) | 18 Sep 2025 | P48 | north | Excavation to L2 caisson level
Thu (18/09) | 18 Sep 2025 | P47 |  | Trial Trench for JGP at existing DR3
Thu (18/09) | 18 Sep 2025 | DR3 |  | Utility support installation
Thu (18/09) | 18 Sep 2025 | P1 |  | Pile cap rebar - bar chair installation ongoing
Thu (18/09) | 18 Sep 2025 | BR21 |  | Excavation in progress
Thu (18/09) | 18 Sep 2025 | P43 |  | Spreader beams stiffener plates rectification ongoing
Thu (18/09) | 18 Sep 2025 | Exit 2 | GL-6 | Waler welding works ongoing
Thu (18/09) | 18 Sep 2025 | BR16B |  | Rebar works in progress
Thu (18/09) | 18 Sep 2025 | Exit 3 |  | S2 strutting installation in progress
Thu (18/09) | 18 Sep 2025 | CCW S4 |  | Excavation in progress
Thu (18/09) | 18 Sep 2025 | BR7B |  | Continue rebar works
Thu (18/09) | 18 Sep 2025 | BR8B |  | Preparing formwork for lean con casting at skin wall area. Plan for casting tonight
Thu (18/09) | 18 Sep 2025 | BR8A |  | Continue excavation and balance drain hacking
Thu (18/09) | 18 Sep 2025 | GL16-19 |  | Preparing for access diversion. Arranging steel plates, concrete barriers installation and VIG welding ongoing
Thu (18/09) | 18 Sep 2025 | BR27 |  | Rebar works in progress
Thu (18/09) | 18 Sep 2025 | BR34 |  | Dismantling formwork
Thu (18/09) | 18 Sep 2025 | Zone 3 |  | Concrete barriers installation in progress for the access diversion
Thu (18/09) | 18 Sep 2025 | BR7B |  | Rebar works in progress
Thu (18/09) | 18 Sep 2025 | BR8B |  | Partial lean concrete completed. Today plan to expose couplers
Thu (18/09) | 18 Sep 2025 | BR8A |  | Continue excavation
Thu (18/09) | 18 Sep 2025 | B2-44 |  | Linkway wall formwork installation in progress
Thu (18/09) | 18 Sep 2025 | CCE4 |  | Continues preparation work for waterproofing, target to handover to maxbond this afternoon
Thu (18/09) | 18 Sep 2025 | P20 |  | Segment adjustment and alignment
Fri (19/09) | 19 Sep 2025 | P44 |  | Platform erection for stressing work & material shifting, P43: welding ongoing
Fri (19/09) | 19 Sep 2025 | BR21 |  | Excavation in progress
Fri (19/09) | 19 Sep 2025 | 800mm PW |  | Air test and MPI test ongoing
Fri (19/09) | 19 Sep 2025 | P50 |  | Pile cap rebar installation (top bar)
Fri (19/09) | 19 Sep 2025 | P48 |  | (South) L2 caisson formwork removal. (North) Excavator breakdown, temporary stop excavation, mechanic on way coming
Fri (19/09) | 19 Sep 2025 | DR3 |  | Utility support installation. P47 side exposing services
Fri (19/09) | 19 Sep 2025 | P1 |  | Pile cap top rebar installation
Fri (19/09) | 19 Sep 2025 | P3 |  | Pull through test for tendon duct in progress
Fri (19/09) | 19 Sep 2025 | P4 |  | Crosshead rebar & platform installation
Fri (19/09) | 19 Sep 2025 | P17 |  | Lifter installation works in progress
Fri (19/09) | 19 Sep 2025 | P20 |  | Segment adjustment works
Fri (19/09) | 19 Sep 2025 | S1-1 |  | BR16B, Rebar work ongoing, RGT installation ongoing
Fri (19/09) | 19 Sep 2025 | S1-2 |  | BR20, Curing ongoing, covering with waterproofing sheet, levelling ongoing
Fri (19/09) | 19 Sep 2025 | S1-2 |  | BR21, Excavation and disposal ongoing
Fri (19/09) | 19 Sep 2025 | CCE4 |  | Handover inspection for waterproof has arranged @ 5pm
Fri (19/09) | 19 Sep 2025 | B2-44 |  | Linkway wall final inspection has conducted, will cast it later
Fri (19/09) | 19 Sep 2025 | B2-43 |  | Continues excavation & soil disposal
Fri (19/09) | 19 Sep 2025 | BR8A |  | Continue excavation
Fri (19/09) | 19 Sep 2025 | BR8B |  | Coupler exposing and rectifying of dwall
Fri (19/09) | 19 Sep 2025 | Z3 access diversion |  | Decking panels installation completed, welding works ongoing, Continue concrete barriers installation
Fri (19/09) | 19 Sep 2025 | BR4 |  | Partial area backfilling works and plan for casting tonight. Platform will be used to facilitate BR7B casting works
Fri (19/09) | 19 Sep 2025 | BR7B |  | Continue rebar works, shearlinks and corrugated pipes installation. Plan for casting tmr night
Fri (19/09) | 19 Sep 2025 | 800mm PW |  | Ground preparation work butterfly valve chamber construction
Fri (19/09) | 19 Sep 2025 | P50 |  | Pile cap rebar installation (top bar)
Fri (19/09) | 19 Sep 2025 | P49 |  | No activity
Fri (19/09) | 19 Sep 2025 | BR27 |  | Continues rebar installation
Fri (19/09) | 19 Sep 2025 | P48 |  | Excavation to L2 caisson layer on going
Fri (19/09) | 19 Sep 2025 | JGP at DR3 |  | Trial Trench on going
Fri (19/09) | 19 Sep 2025 | DR3 |  | Utility support installation
Fri (19/09) | 19 Sep 2025 | P45 |  | Excavation to L1 caisson level
Fri (19/09) | 19 Sep 2025 | BR16B |  | Rebar works in progress
Fri (19/09) | 19 Sep 2025 | BR18B |  | Excavation in progress
Fri (19/09) | 19 Sep 2025 | BR21 |  | Excavation in progress
Fri (19/09) | 19 Sep 2025 | BR8B |  | Removing loose concrete for dwall rectification. Tmr Dongah plan for casting back
Fri (19/09) | 19 Sep 2025 | BR8A |  | Continue excavation and disposal works
Fri (19/09) | 19 Sep 2025 | Z3 access diversion |  | Welding works ongoing below decking. Once completed & housekeeping done, access will be be opened
Fri (19/09) | 19 Sep 2025 | BR7B |  | Continue rebar works, RTO inspection ongoing
Fri (19/09) | 19 Sep 2025 | BR27 |  | Rebar works in progress
Fri (19/09) | 19 Sep 2025 | BR34 |  | Housekeeping
Fri (19/09) | 19 Sep 2025 | B2-44 |  | Linkway wall pending for casting. Concrete otw & pump truck on site
Fri (19/09) | 19 Sep 2025 | Z3 access diversion |  | Balance decking panels installation in progress. Target to open up the access after lunchtime
Fri (19/09) | 19 Sep 2025 | BR7B |  | Rebars, hyrib and corrugated pipes installation in progress
Fri (19/09) | 19 Sep 2025 | BR8B |  | Exposing couplers
Fri (19/09) | 19 Sep 2025 | BR8A |  | Excavation & disposal in progress
Sat (20/09) | 20 Sep 2025 | 800mm PW |  | Excavation ongoing
Sat (20/09) | 20 Sep 2025 | S1-1 |  | BR16B, Rebar works ongoing
Sat (20/09) | 20 Sep 2025 | S1-2 |  | BR20, Curing ongoing
Sat (20/09) | 20 Sep 2025 | S2-1 |  | BR21, Excavation and disposal ongoing
Sat (20/09) | 20 Sep 2025 | P50 |  | Pile cap rebar installation (top bar)
Sat (20/09) | 20 Sep 2025 | P49 |  | Scaffolding erection, afternoon start s2 strut removal
Sat (20/09) | 20 Sep 2025 | P48 |  | Excavator changing bucket, excavation to L2 caisson level ongoing
Sat (20/09) | 20 Sep 2025 | P47 |  | Exposing utilities
Sat (20/09) | 20 Sep 2025 | Dr3 |  | No activity
Sat (20/09) | 20 Sep 2025 | P45 |  | Excavation to L1 caisson level
Sat (20/09) | 20 Sep 2025 | P43 |  | No activity
Sat (20/09) | 20 Sep 2025 | P45 |  | Falsework removal
Sat (20/09) | 20 Sep 2025 | P20 |  | Segment alignment
Sat (20/09) | 20 Sep 2025 | P17 |  | Load test completed. Now preparing for segment launching tonight
Sat (20/09) | 20 Sep 2025 | P15 |  | Scaffolding erection for stressing work
Sat (20/09) | 20 Sep 2025 | P1 |  | Pile cap rebar installation (top bar)
Sat (20/09) | 20 Sep 2025 | P3 |  | No activity
Sat (20/09) | 20 Sep 2025 | P4 |  | No activity
Sat (20/09) | 20 Sep 2025 | S1-1 |  | BR16B, Rebar works ongoing, partial formwork closing as well
Sat (20/09) | 20 Sep 2025 | S2-1 |  | BR21, Excavation ongoing
Sat (20/09) | 20 Sep 2025 | 800mm PW |  | Excavation and ERSS
Sat (20/09) | 20 Sep 2025 | P50 |  | Pile cap rebar installation (top bar)
Sat (20/09) | 20 Sep 2025 | P49 |  | Strut removal started. 2nd scaffolding erection
Sat (20/09) | 20 Sep 2025 | P48 |  | Excavation to L2 caisson layer on going
Sat (20/09) | 20 Sep 2025 | P47 |  | Current excavation status
Sat (20/09) | 20 Sep 2025 | P45 |  | Excavation to L1 caisson level
Sat (20/09) | 20 Sep 2025 | P44 |  | Tie rod area touch up work & removal of polyfoam at stressing end area
Sat (20/09) | 20 Sep 2025 | P1 |  | Pile cap rebar installation
Sat (20/09) | 20 Sep 2025 | P17 |  | Segment preparation for tonight launching
Sat (20/09) | 20 Sep 2025 | P20 |  | Preparation work for strand pulling
Sun (21/09) | 21 Sep 2025 | Exit 2 |  | Ongoing strut installation
Sun (21/09) | 21 Sep 2025 | BR20 |  | Formwork dismantling is in progres
Sun (21/09) | 21 Sep 2025 | BR21 |  | Excavation & soil disposal is in progress
Sun (21/09) | 21 Sep 2025 | BR7 |  | Casting is in progress
Sun (21/09) | 21 Sep 2025 | BR8A |  | Ongoing excavation & soil disposal
Sun (21/09) | 21 Sep 2025 | B2-43 |  | Current excavation status
Sun (21/09) | 21 Sep 2025 | CCE4-P42 |  | Membrane installation is in progress
Sun (21/09) | 21 Sep 2025 | CCE4 / B2-45 |  | Continues rectification work for waterproofing
Sun (21/09) | 21 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Sun (21/09) | 21 Sep 2025 | BR-7B GL |  | 23 TO 27 ROOF SLAB CASTING COMPLETED, Casting started at : 23:32 hrs, Casting Completed at 13:30hrs, G50 - 5m³/5m³, G40WP - 99m³/100m³, G40PBFC - 1549m³/1549m³, Total volume - 1653m³/1653m³
Sun (21/09) | 21 Sep 2025 | BR16B |  | Continues rebar installation
Sun (21/09) | 21 Sep 2025 | BR21B |  | Continues excavation & soil disposal
Sun (21/09) | 21 Sep 2025 | GL16-19 |  | Removing of steel plate to prepare for next BR excavation
Sun (21/09) | 21 Sep 2025 | BR7B |  | Power floating is in progress
Sun (21/09) | 21 Sep 2025 | BR8A |  | Continues excavation & soil disposal
Sun (21/09) | 21 Sep 2025 | BR27 |  | Continues rebar installation
Sun (21/09) | 21 Sep 2025 | Exit 1 |  | Clearing of stockpile from new ECm pond
Sun (21/09) | 21 Sep 2025 | CCE4 |  | Rectification work is in progress @ B2-46
Sun (21/09) | 21 Sep 2025 | CCE4 - P41 |  | Preparation work for waterproofing in progress
Sun (21/09) | 21 Sep 2025 | BR16B |  | Rebar installation is in progress
Mon (22/09) | 22 Sep 2025 | 800mm dia water pipe |  | Quarry dust backfilling at completed pipe laying area
Mon (22/09) | 22 Sep 2025 | P50 |  | Shear link installation. Tonight plan to cast this pile cap
Mon (22/09) | 22 Sep 2025 | P49 |  | Clearing unused materials and prepare to lower down rebar
Mon (22/09) | 22 Sep 2025 | P44 |  | Strand pulling in progress, target Wed to stress
Mon (22/09) | 22 Sep 2025 | P45 |  | Excavation in progress for 2nd layer. Reached to bored pile area. Wednesday will handover to Wendyng for rebar work
Mon (22/09) | 22 Sep 2025 | DR3 to P47 |  | Main beam installation. 2nos done as of now
Mon (22/09) | 22 Sep 2025 | DR3 |  | TT done and pipe sleeves installed
Mon (22/09) | 22 Sep 2025 | P17 SB |  | Lifter shifting for 3rd pair launching
Mon (22/09) | 22 Sep 2025 | N1 |  | 6th pair stressing in progress
Mon (22/09) | 22 Sep 2025 | Blk 4 |  | Temporary drain wall formwork dismantling ongoing
Mon (22/09) | 22 Sep 2025 | CCE4 |  | Waterproofing primer application ongoing at P41, Side surface grinding ongoing at P42 area. Waterproofing membrane done on top
Mon (22/09) | 22 Sep 2025 | B2-44 linkway wall |  | Formwork support removal ongoing
Mon (22/09) | 22 Sep 2025 | P45 |  | Excavation stopped for the day
Mon (22/09) | 22 Sep 2025 | P44 |  | Strand pulling continue for T1-4. Works until 9pm
Mon (22/09) | 22 Sep 2025 | Exit 1 |  | Stockpile status
Mon (22/09) | 22 Sep 2025 | BR34 |  | No activity
Mon (22/09) | 22 Sep 2025 | BR27 |  | Continue rebar works & partial formwork installation in progress
Mon (22/09) | 22 Sep 2025 | BR8A |  | Continue disposal works and preparing for lean con casting
Mon (22/09) | 22 Sep 2025 | BR7A |  | Temporary opening wall formwork installation in progress
Mon (22/09) | 22 Sep 2025 | BR21 |  | Continue levelling and excavation works
Mon (22/09) | 22 Sep 2025 | P17 |  | Strand pulling to stand by for 3rd pair segment. Tonight to lunch NB U03 and D03
Tue (23/09) | 23 Sep 2025 | B2-43 |  | No excavation work for now
Tue (23/09) | 23 Sep 2025 | B2-44 |  | Dismantling of formwork for linkway wall
Tue (23/09) | 23 Sep 2025 | S1-1 |  | BR16B, Rebar work ongoing
Tue (23/09) | 23 Sep 2025 | BR8A |  | Removing loose concrete for dwall rectification works, Exposing couplers
Tue (23/09) | 23 Sep 2025 | B2-45 |  | Started laying of membrane for waterproofing
Tue (23/09) | 23 Sep 2025 | B2-46 |  | Preparation work in progress for waterprrofing
Tue (23/09) | 23 Sep 2025 | BR8A |  | Partial LSS backfilling completed. This evening plan to lean concrete at this area and also at BR8B balance area
Tue (23/09) | 23 Sep 2025 | BR8B |  | Pending inspection for dwall rectification works, Continue exposing couplers and surface roughening at BR6 CJ
Tue (23/09) | 23 Sep 2025 | BR27 |  | Continues top bar installation
Tue (23/09) | 23 Sep 2025 | Exit 1 |  | Access diverted for waler work @ BR34
Tue (23/09) | 23 Sep 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Tue (23/09) | 23 Sep 2025 | Exit 2 Capping Beam Part 1 |  | Above ground 250mm wall rebar works in progress
Tue (23/09) | 23 Sep 2025 | BR7B |  | Formwork support removal and unloading rebars for BR8B
Tue (23/09) | 23 Sep 2025 | BR8B |  | Last portion of decking panels installation in progress
Tue (23/09) | 23 Sep 2025 | P44 |  | Wedge plate installation in progress
Tue (23/09) | 23 Sep 2025 | P43 |  | Excavation for 2nd layer to continue until 10pm
Tue (23/09) | 23 Sep 2025 | P49 |  | Pile cap bottom bar installation in progress at south side
Tue (23/09) | 23 Sep 2025 | P4 |  | Section 1-3 links completed. Section 3 partially closed by formwork. Tonight plan to closed formwork at section 1 and 2 and continue links at section 4 and 5
Tue (23/09) | 23 Sep 2025 | P17 |  | Strand pushing to stand by for SB 3rd pair tensioning
Wed (24/09) | 24 Sep 2025 | P43 |  | Side fwk erection / setting up ongoing
Wed (24/09) | 24 Sep 2025 | P44 |  | Preparation for stressing work ongoing - cutting & fixing of base plate in progress, target tmr to start stressing work
Wed (24/09) | 24 Sep 2025 | P50 |  | Pile cap curing
Wed (24/09) | 24 Sep 2025 | P49 |  | Pile cap rebar installation (bottom bar)
Wed (24/09) | 24 Sep 2025 | P48 |  | Excavation to L2 caisson level
Wed (24/09) | 24 Sep 2025 | P47 |  | Trial Trench for JGP at existing DR3
Wed (24/09) | 24 Sep 2025 | DR3 |  | Utility support installation
Wed (24/09) | 24 Sep 2025 | P45 |  | Current excavation status
Wed (24/09) | 24 Sep 2025 | P43 |  | Continue side fwk erection, P44: continue preparation for stressing work
Wed (24/09) | 24 Sep 2025 | BR21 |  | GL11-12: Started debonding sheet laying, GL13: Continue excavation and disposal/internal shifting works, Surveying works ongoing
Wed (24/09) | 24 Sep 2025 | P17 SB 3rd pair |  | Stressing in progress
Wed (24/09) | 24 Sep 2025 | BR10 |  | Formwork dismantling for balance retaining wall area. Thereafter to backfill
Wed (24/09) | 24 Sep 2025 | BR8A |  | Preparing for lean concrete works at remaining area, Exposing couplers, drilling ongoing for dwall rectification, RGT installation at BR7A
Wed (24/09) | 24 Sep 2025 | BR8B |  | Top plate welding ongoing for king posts, Bottom rebar works in progress, Surface roughening ongoing at BR7B
Wed (24/09) | 24 Sep 2025 | 800mm PW |  | Backfilling completed
Wed (24/09) | 24 Sep 2025 | 800mm PW |  | Excavation and ERSS
Wed (24/09) | 24 Sep 2025 | B2-45/P41 area |  | Waterpoofing membrane laying in progress
Wed (24/09) | 24 Sep 2025 | B2-46 |  | PU grouting ongoing by Dongah
Wed (24/09) | 24 Sep 2025 | B2-46/P42 area |  | Currently no activity
Wed (24/09) | 24 Sep 2025 | B2-44 linkway wall |  | Formwork dismantling ongoing
Wed (24/09) | 24 Sep 2025 | Exit 1 |  | Excavation in progress. 1 cluster of IM affected - 1 IW, 1 piezo & 1 water standpipe
Wed (24/09) | 24 Sep 2025 | P50 |  | Pile cap rebar installation (bottom rebar)
Wed (24/09) | 24 Sep 2025 | P48 |  | Excavation to L2 caisson level
Wed (24/09) | 24 Sep 2025 | P47 |  | Soil disposal
Wed (24/09) | 24 Sep 2025 | DR3 |  | No activity
Wed (24/09) | 24 Sep 2025 | P45 |  | Steel plate support installation
Wed (24/09) | 24 Sep 2025 | BR27 |  | Rebar works in progress
Wed (24/09) | 24 Sep 2025 | Exit 3 |  | Installation of steel plates for services protection
Wed (24/09) | 24 Sep 2025 | BR16B |  | Casting was completed in the afternoon. Now power float works ongoing
Wed (24/09) | 24 Sep 2025 | BR18B |  | Excavation in progress
Wed (24/09) | 24 Sep 2025 | Exit 2 | GL6-7 | 2nos struts installed
Wed (24/09) | 24 Sep 2025 | BR20 |  | Surface roughening ongoing
Wed (24/09) | 24 Sep 2025 | BR22 |  | Excavation in progress
Wed (24/09) | 24 Sep 2025 | BR21 |  | Excavation and disposal/internal shifting works ongoing
Wed (24/09) | 24 Sep 2025 | Exit 1 |  | Current excavation status
Wed (24/09) | 24 Sep 2025 | BR27 |  | Continue rebar works and formwork closing. Plan for casting tmr
Wed (24/09) | 24 Sep 2025 | BR8A |  | Levelling works in preparation for lean concrete
Wed (24/09) | 24 Sep 2025 | BR8B |  | Top plate welding ongoing for king posts. Tonight to complete and tmr do MPI test, Bottom rebar works in progress, Surface roughening ongoing at BR7B
Wed (24/09) | 24 Sep 2025 | P21 |  | Scaffold erection for segment launching
Wed (24/09) | 24 Sep 2025 | P17 SB |  | 3rd pair strand pushing for tensioning
Wed (24/09) | 24 Sep 2025 | 800mm PW |  | Excavation and ERSS
Wed (24/09) | 24 Sep 2025 | P17 NB |  | Preparation for stressing cage dismantling. Tonight to launch 4th pair
Thu (25/09) | 25 Sep 2025 | 800mm PW |  | Continue excavation and ERSS
Thu (25/09) | 25 Sep 2025 | P44 |  | Stage 1 stressing ongoing
Thu (25/09) | 25 Sep 2025 | BR8B |  | Dongah to complete the 2nos dwall rectification here today. Formwork closing done, Continue rebar works, Note: Manpower for rebar works here are from CGW while they await for BR21 to be fully ready for them - 9 men here at BR8B, Wendyng manpower: 6 (hacking and surface roughening)
Thu (25/09) | 25 Sep 2025 | BR8B |  | RGT installation ongoing
Thu (25/09) | 25 Sep 2025 | BR8B |  | Welding works ongoing for king posts
Thu (25/09) | 25 Sep 2025 | BR8A |  | Dongah installing formwork for dwall rectification
Thu (25/09) | 25 Sep 2025 | BR7B |  | Surface roughening in progress
Thu (25/09) | 25 Sep 2025 | P50 |  | Pile cap curing
Thu (25/09) | 25 Sep 2025 | P49 |  | Pile cap rebar installation (bottom bar)
Thu (25/09) | 25 Sep 2025 | P48 |  | Excavation in progress
Thu (25/09) | 25 Sep 2025 | P47 |  | Trial Trench for JGP in progress
Thu (25/09) | 25 Sep 2025 | DR3 |  | Utility support installation ongoing
Thu (25/09) | 25 Sep 2025 | P45 | south | Steel plate support installation completed..currently making access
Thu (25/09) | 25 Sep 2025 | P45 | north | Excavator changing bucket. Excavation ongoing
Thu (25/09) | 25 Sep 2025 | P4 crosshead |  | Balance formwork tie rod tightening. Good to go for casting. Pump car arranged tmr at 3pm
Thu (25/09) | 25 Sep 2025 | P1 |  | Surface roughening. Today to start stump rebar installation
Thu (25/09) | 25 Sep 2025 | P20 |  | Outer Formwork closing for wet stitching works ongoing
Thu (25/09) | 25 Sep 2025 | P17 |  | Preparation for stressing works for NB 4th pair segment
Thu (25/09) | 25 Sep 2025 | P15 |  | 2nd stage CH post tensioning works at SB ongoing
Thu (25/09) | 25 Sep 2025 | 800mm PW |  | Pending to install 3.2m straight + 45deg bend pipe
Thu (25/09) | 25 Sep 2025 | BR8A |  | Dwall rectification completed for 1 panel
Thu (25/09) | 25 Sep 2025 | BR8B |  | Continue exposing couplers, RGT installation, Dwall rectification in progress
Thu (25/09) | 25 Sep 2025 | BR8B |  | Continue welding works for kingposts. Now welders on break
Thu (25/09) | 25 Sep 2025 | BR8A |  | Preparing formwork for skin wall area lean con casting
Thu (25/09) | 25 Sep 2025 | BR27 |  | RTO inspection ongoing. Plan for casting tonight
Thu (25/09) | 25 Sep 2025 | P1 |  | Column stump rebar installation ongoing
Thu (25/09) | 25 Sep 2025 | P4 |  | Formwork tie rod tightening
Thu (25/09) | 25 Sep 2025 | BR21 |  | 4nos KPs exposed, Continue soil disposal/internal shifting works, Continue exposing couplers and preparing for partial bottom rebar works
Thu (25/09) | 25 Sep 2025 | 800mm PW |  | Lowering 3.2m water pipe in progress
Thu (25/09) | 25 Sep 2025 | P44 |  | Continue 1st stage stressing, P43: working platform erection ongoing
Thu (25/09) | 25 Sep 2025 | P20 stitching formwork closing |  | SB D01: 50% completed, SB U01: 100% completed, NB D01: 60% completed, NB U01: 80% completed, Plan to cast on Saturday
Thu (25/09) | 25 Sep 2025 | P17 |  | NB: strand pushing for 4th pair, SB: LF shifting for 4th pair installation tonight
Thu (25/09) | 25 Sep 2025 | P15 |  | Preparation for crosshead 2nd stage tensioning
Fri (26/09) | 26 Sep 2025 | Beside P24 |  | Excavation in progress
Fri (26/09) | 26 Sep 2025 | BR18B |  | Excavation in progress
Fri (26/09) | 26 Sep 2025 | BR21 |  | Kingposts exposed and pending top plate welding works, Balance lean con casting plan to complete by tmr, Exposing couplers, Bottom rebar works in progress, Continue soil disposal/internal shifting works
Fri (26/09) | 26 Sep 2025 | GL9 |  | Endplate installation to facilitate utility beam steel support works
Fri (26/09) | 26 Sep 2025 | BR19 |  | Clearing loose materials before installing steel plates for utility protection
Fri (26/09) | 26 Sep 2025 | P20 |  | Stitching formwork balance SB D01. To complete today
Fri (26/09) | 26 Sep 2025 | P17 |  | SB: 4th pair segment stressing, NB: lifter shifting for 5th pair launching tonight
Fri (26/09) | 26 Sep 2025 | P4 crosshead |  | Pump set up completed for casting. U-bar need to adjust, target final inspection at 7pm
Sat (27/09) | 27 Sep 2025 | P43 |  | Crosshead top rebar installation works ongoing
Sat (27/09) | 27 Sep 2025 | P44 |  | Stressing materials clearing and housekeeping ongoing
Sat (27/09) | 27 Sep 2025 | P44 |  | Bottom formwork and working platform dismantling in progress
Sat (27/09) | 27 Sep 2025 | Exit 3 |  | Currently no other activity
Sat (27/09) | 27 Sep 2025 | Old ECM pond at exit 2 |  | Mixing of sludge before disposal
Sat (27/09) | 27 Sep 2025 | P45 |  | Preparation for slope lean concrete works
Sat (27/09) | 27 Sep 2025 | DR3 |  | Utility support welding works
Sat (27/09) | 27 Sep 2025 | P48 |  | Rebar bending works for 2nd layer cassion wall
Sat (27/09) | 27 Sep 2025 | P49 |  | Pile cap rebar works ongoing
Sat (27/09) | 27 Sep 2025 | BR7A |  | Temporary opening wall formwork closing ongoing. Plan for casting today
Sat (27/09) | 27 Sep 2025 | P50 |  | No activity
Sat (27/09) | 27 Sep 2025 | Zone 4 |  | Manual excavation and ERSS works for 800 water pipe laying
Sat (27/09) | 27 Sep 2025 | Zone 4 |  | Preparation for pipe joint MPI and air test
Sat (27/09) | 27 Sep 2025 | BR8B |  | Rebar works in progress, Continue debonding sheet laying, Exposing couplers & surface roughening at BR5 and BR6
Sat (27/09) | 27 Sep 2025 | BR8A |  | Exposing couplers
Sat (27/09) | 27 Sep 2025 | Exit 1 |  | Continue soil disposal/internal shifting works, Hacking of overcast dwall ongoing by Dongah, Hacking to dwall rebar level ongoing by WH
Sat (27/09) | 27 Sep 2025 | P1 |  | Coloum 1st lift wall rebar works ongoing. Target to cast on Monday
Sat (27/09) | 27 Sep 2025 | P2 |  | Curing works for pad footing installation
Sat (27/09) | 27 Sep 2025 | P4 |  | Crosshead cast. Curing works in progress
Sat (27/09) | 27 Sep 2025 | P17 |  | Preparation for segment stressing works for NB U/D 05
Sat (27/09) | 27 Sep 2025 | P20 |  | Formwork for wet stitching completed. To cast at 3pm
Sat (27/09) | 27 Sep 2025 | CCE4 tunnel roof slab |  | Waterproofing works ongoing
Sat (27/09) | 27 Sep 2025 | Blk 4 temporary drain |  | Constructing cascading steps prior to benching works
Sat (27/09) | 27 Sep 2025 | Exit 3 |  | No activity
Sat (27/09) | 27 Sep 2025 | CCW1 S4 |  | No activity
Sat (27/09) | 27 Sep 2025 | Below P24 |  | Excavation in progress
Sat (27/09) | 27 Sep 2025 | BR18B |  | Exposing couplers at dwall side, Ground preparation for lean con casting. Plan for today
Sat (27/09) | 27 Sep 2025 | P43 |  | Continue top rebar installation works
Sat (27/09) | 27 Sep 2025 | P44 |  | Bottom formwork dismantling and materials clearing
Sat (27/09) | 27 Sep 2025 | BR21 |  | Rebar works in progress, KP welding works ongoing
Sat (27/09) | 27 Sep 2025 | GL9 |  | Steel post installation for utility beam
Sat (27/09) | 27 Sep 2025 | BR8B |  | Rebar works in progress, BR8A: Preparing for dwall rectification
Sat (27/09) | 27 Sep 2025 | CCE4 tunnel roof slab |  | Waterproofing membrane laying in progress. Plan for inspection thereafter and proceed for protective screeding
Sat (27/09) | 27 Sep 2025 | B2-46 |  | LSS backfilling in progress
Sat (27/09) | 27 Sep 2025 | DR3 |  | Utility protection, manual excavation and trial trench works
Sat (27/09) | 27 Sep 2025 | P48 |  | Continue rebar bending for 2nd layer cassion wall
Sat (27/09) | 27 Sep 2025 | P49 |  | Pile cap rebar works
Sat (27/09) | 27 Sep 2025 | Zone 4 |  | 800 water pipe joint MPI and air test completed
Sat (27/09) | 27 Sep 2025 | Exit 1 |  | Continue dwall hacking to COL
Sat (27/09) | 27 Sep 2025 | Outside gate 7 along Loyang Way |  | Road resurfacing works by Starhub
Sat (27/09) | 27 Sep 2025 | P1 |  | Formwork closing for 1st lift column
Sat (27/09) | 27 Sep 2025 | P20 |  | Wet stitch casting ongoing
Sat (27/09) | 27 Sep 2025 | P17 |  | Stressing completed for NB U/D 05
Sat (27/09) | 27 Sep 2025 | Exit 3 |  | Dismantling scaffold access which was used for utility services protection works
Sat (27/09) | 27 Sep 2025 | Near P24 |  | Excavation in progress
Sat (27/09) | 27 Sep 2025 | BR18B |  | Excavation in progress
Sat (27/09) | 27 Sep 2025 | BR18B |  | Hacking of abandoned sewer manhole
Sat (27/09) | 27 Sep 2025 | BR22 |  | Excavation ongoing
Sat (27/09) | 27 Sep 2025 | BR21 |  | Rebar works in progress, RGT installation, Top plate welding for kingposts ongoing
Mon (29/09) | 29 Sep 2025 | Z4 800PW |  | 4.5m pipe installed, welding ongoing
Mon (29/09) | 29 Sep 2025 | P20 |  | Preparation for strand installation
Mon (29/09) | 29 Sep 2025 | P17 |  | Stressing for NB D/U 06
Mon (29/09) | 29 Sep 2025 | P50 |  | Curing
Mon (29/09) | 29 Sep 2025 | P1 |  | Preparation for 1st lift column casting today
Mon (29/09) | 29 Sep 2025 | P49 |  | Top rebar inspection ongoing
Mon (29/09) | 29 Sep 2025 | P45 |  | Levelling work ongoing
Mon (29/09) | 29 Sep 2025 | 800mm dia water pipe |  | Welding in progress for 4.5m laid pipe
Mon (29/09) | 29 Sep 2025 | P20 |  | Stitching formwork removal and stressing work. Plan to lower down stressing cages tonight
Mon (29/09) | 29 Sep 2025 | P17 |  | Prepare for segment launching tonight
Mon (29/09) | 29 Sep 2025 | CCW1 S4 |  | No activity
Mon (29/09) | 29 Sep 2025 | Exit 3 |  | Rebar planting for S2 layer strut (DS2-1)
Mon (29/09) | 29 Sep 2025 | Below P24 |  | Excavation in progress
Mon (29/09) | 29 Sep 2025 | P1 |  | Stump casting
Mon (29/09) | 29 Sep 2025 | P50 |  | Pile cap curing
Mon (29/09) | 29 Sep 2025 | P49 |  | Column starter bar and shear link installation. Still on schedule to cast tomorrow
Mon (29/09) | 29 Sep 2025 | P48 |  | Formwork closing. Tomorrow will cast 12m length
Mon (29/09) | 29 Sep 2025 | DR3 |  | Status of excavation toward P46 for utility support
Mon (29/09) | 29 Sep 2025 | BR18B |  | Started partial debonding sheet laying & continue exposing couplers
Mon (29/09) | 29 Sep 2025 | BR22/Exit 2 |  | No activity
Mon (29/09) | 29 Sep 2025 | BR21 |  | Continue rebar works and partial formwork installation, KPs welding works completed, tmr MPI test. Partial portion lean concrete plan for tonight
Mon (29/09) | 29 Sep 2025 | P45 |  | LSS backfilling done. Tomorrow will do levelling for caisson work
Mon (29/09) | 29 Sep 2025 | BR8B |  | Continue rebar works. Night shift team will take over at 8pm, BR8A: Tmr plan for handover to Wendyng
Mon (29/09) | 29 Sep 2025 | P43 |  | Falsework dismantling. Side bar installation for P43
Mon (29/09) | 29 Sep 2025 | BR7A |  | Temporary opening wall casting ongoing
Mon (29/09) | 29 Sep 2025 | B2-45 |  | Protective screeding works in progress
Mon (29/09) | 29 Sep 2025 | Exit 1 |  | Slope protection casting ongoing & hacking dwall to COL. Have informed WH to install additional lighting
Tue (30/09) | 30 Sep 2025 | BR21 |  | Balance area lean con casting, Continue rebar works & RTO inspection
Tue (30/09) | 30 Sep 2025 | P21 |  | Starter hanger installation from P20 ongoing. Tonight to launch 2 segments
Tue (30/09) | 30 Sep 2025 | BR8A |  | Start partial rebar works, Continue drilling for couplers, BR8B:, Continue rebar works, RGT installation ongoing
Tue (30/09) | 30 Sep 2025 | P44 |  | Falsework dismantling in progress
Tue (30/09) | 30 Sep 2025 | P43 |  | Rebar work ongoing
Tue (30/09) | 30 Sep 2025 | P17 |  | SB D/U 06 Strand installation for stressing works
Tue (30/09) | 30 Sep 2025 | P15 |  | Scaffold dismantling to shift to P16 for crosshead 2nd stage post tensioning works
Tue (30/09) | 30 Sep 2025 | Bet. P6-P7 |  | KTC soil stockpile
Tue (30/09) | 30 Sep 2025 | S3 |  | Area leveling for falsework erection
Tue (30/09) | 30 Sep 2025 | 800mm dia water pipe |  | Continue excavation for ERSS installation for water pipe laying
Tue (30/09) | 30 Sep 2025 | P2 NB |  | Premix removal for pad footing completed. To lean concrete after peak hour
Tue (30/09) | 30 Sep 2025 | P49 pile cap |  | Rebar inspection done. Concrete ordered for casting
Tue (30/09) | 30 Sep 2025 | P48 |  | 2nd layer caisson wall casting
Tue (30/09) | 30 Sep 2025 | P50 |  | Pile cap curing
Tue (30/09) | 30 Sep 2025 | P49 |  | Pile cap rebar installation . Target tonight 8pm start pile cap casting
Tue (30/09) | 30 Sep 2025 | P48 |  | L2 caisson casting east and West side
Tue (30/09) | 30 Sep 2025 | P47 |  | Trial Trench for JGP
Tue (30/09) | 30 Sep 2025 | DR3 |  | Excavation towards P46
Tue (30/09) | 30 Sep 2025 | P45 |  | Lean concrete casting for working platform
Wed (01/10) | 01 Oct 2025 | Zone 2 between P6-P7 |  | Soil internal shifting from station. Total loads shifted as of now est 26 loads, Additional bundwall to cast this afternoon
Wed (01/10) | 01 Oct 2025 | Exit 1 |  | Hacking in progress for waler work
Wed (01/10) | 01 Oct 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Wed (01/10) | 01 Oct 2025 | B2-44 |  | Ongoing preparation work for waterproofing
Wed (01/10) | 01 Oct 2025 | BR27 |  | Continue dismantling of formwork
Wed (01/10) | 01 Oct 2025 | 800mm PW |  | Excavation and ERSS
Wed (01/10) | 01 Oct 2025 | P17 |  | Dismantling of lifter
Wed (01/10) | 01 Oct 2025 | P21 |  | SB D01 launching done last night. Today to launch SB D01
Wed (01/10) | 01 Oct 2025 | P50 |  | No activity
Wed (01/10) | 01 Oct 2025 | P49 |  | Pile cap casting completed. Now cleaning work ongoing
Wed (01/10) | 01 Oct 2025 | P48 |  | East and West formwork dismantling, north formwork closing
Wed (01/10) | 01 Oct 2025 | DR3 |  | Excavation to expose UKP and utilities on going
Wed (01/10) | 01 Oct 2025 | P45 |  | Preparation for L1 caisson work
Wed (01/10) | 01 Oct 2025 | P21 |  | Segment adjustment for SB D01
Wed (01/10) | 01 Oct 2025 | P20 |  | Wet stitch Formwork dismantling
Wed (01/10) | 01 Oct 2025 | P16 |  | Scaffold erection for 2nd stage Crosshead post tensioning
Wed (01/10) | 01 Oct 2025 | P43 |  | Working platform erection ongoing
Wed (01/10) | 01 Oct 2025 | N1 |  | Falsework dismantling
Wed (01/10) | 01 Oct 2025 | S2 |  | ECM pond shifting works to prepare for s3 segment launching
Wed (01/10) | 01 Oct 2025 | P4 |  | Crosshead Formwork dismantling ongoing
Wed (01/10) | 01 Oct 2025 | BR21 |  | Rebar works in progress
Wed (01/10) | 01 Oct 2025 | BR8A |  | Dwall rectification ongoing, Continue debonding sheet laying, BR8B:, Continue rebar works
Wed (01/10) | 01 Oct 2025 | P50 area |  | Plan to commence LSS backfilling for abandoned 500mm sewer pipeline, currently pumping out rain water
Wed (01/10) | 01 Oct 2025 | P21 |  | No activity. Tonight going to launch NB D01
Wed (01/10) | 01 Oct 2025 | P20 |  | No activity
Wed (01/10) | 01 Oct 2025 | P17 |  | Dismantling of lifter and bringing down materials
Wed (01/10) | 01 Oct 2025 | P14 |  | Strand cable pulling ongoing
Wed (01/10) | 01 Oct 2025 | N1 |  | No activity
Wed (01/10) | 01 Oct 2025 | S2 |  | ECM pond casting completed
Wed (01/10) | 01 Oct 2025 | CCW1 S4 |  | No activity
Wed (01/10) | 01 Oct 2025 | CCW north side S4 |  | Rebar works for waler beam ongoing, Continue drilling for rebar planting
Wed (01/10) | 01 Oct 2025 | Exit 3 |  | Bolt planting for struts installation
Wed (01/10) | 01 Oct 2025 | Below P24 |  | Current status of excavation
Wed (01/10) | 01 Oct 2025 | Exit 2/BR23 area |  | Unloading materials for bracing works
Wed (01/10) | 01 Oct 2025 | BR18B |  | Rebar works in progress
Wed (01/10) | 01 Oct 2025 | BR8 |  | Dayshift stop works for the day. Heavy downpour
Wed (01/10) | 01 Oct 2025 | BR21 |  | Night shift team continue rebar works —, 15 rebar workers
Wed (01/10) | 01 Oct 2025 | Exit 2 |  | WH removing pumping main pipes
Wed (01/10) | 01 Oct 2025 | BR8B |  | Night shift team continue rebar works —14 workers, BR8A:, Dongah night shift team continue dwall rectification. Tonight to cast STN-73 — 4 pax
Wed (01/10) | 01 Oct 2025 | P43 |  | Rebar installation ongoing
Wed (01/10) | 01 Oct 2025 | Zone 4 |  | P45-P50 no activity
Wed (01/10) | 01 Oct 2025 | CCE4 |  | No activity
Wed (01/10) | 01 Oct 2025 | CCE1-3 |  | No activity
Wed (01/10) | 01 Oct 2025 | P44 |  | Current status, P43: rebar work for crosshead ongoing
Thu (02/10) | 02 Oct 2025 | P18-19 |  | Crane platform prepared. Today to assemble 600T crane here for Lifter shifting to P19 from P17
Thu (02/10) | 02 Oct 2025 | P16 SB |  | Scaffold access completed for 2nd stage post tensioning
Thu (02/10) | 02 Oct 2025 | N1 |  | Working platform dismantling
Thu (02/10) | 02 Oct 2025 | P49 |  | Curing ongoing
Thu (02/10) | 02 Oct 2025 | DR3 | P46 | Soldier pile built up for main beam installation
Thu (02/10) | 02 Oct 2025 | DR3 |  | Setting out for preboring for soldier pile installation
Thu (02/10) | 02 Oct 2025 | B2-43 |  | No activity
Thu (02/10) | 02 Oct 2025 | B2-44 |  | Dewatering in progress & continue with preparation work for water proofing, target to handover to maxbond by today
Thu (02/10) | 02 Oct 2025 | PW800mm |  | Welding for 4.9m length short pipe ongoing
Thu (02/10) | 02 Oct 2025 | P45 |  | Caisson rebar work in progress
Thu (02/10) | 02 Oct 2025 | P45 |  | Soil levelling. MPI test for the waler bracket
Thu (02/10) | 02 Oct 2025 | P44/43 |  | Current status
Thu (02/10) | 02 Oct 2025 | P48 |  | Caisson formwork closing
Thu (02/10) | 02 Oct 2025 | DR3 soldier pile |  | Preparation work, ready for preboring
Thu (02/10) | 02 Oct 2025 | BR27 |  | Formwork has dismantle
Thu (02/10) | 02 Oct 2025 | Exit 1 |  | Continues hacking to prepare for waler work
Thu (02/10) | 02 Oct 2025 | Exit 1 |  | Clearing of stockpile from new ECM pond
Thu (02/10) | 02 Oct 2025 | P51 |  | Clearing materials and housekeeping
Thu (02/10) | 02 Oct 2025 | P50 |  | S1 strut removal
Thu (02/10) | 02 Oct 2025 | P48 |  | L2 caisson last part casting ongoing
Thu (02/10) | 02 Oct 2025 | DR3 soldier pile |  | Preboring ongoing
Thu (02/10) | 02 Oct 2025 | P45 |  | L1 caisson rebar installation
Thu (02/10) | 02 Oct 2025 | P20 |  | Continue stitching formwork dismantling
Thu (02/10) | 02 Oct 2025 | P21 |  | Stressing cage shifting works
Thu (02/10) | 02 Oct 2025 | P19 |  | Shifting of lifter from P17 to P19
Thu (02/10) | 02 Oct 2025 | N1 |  | Falsework dismantling
Thu (02/10) | 02 Oct 2025 | S3 |  | Falsework erection for segment launching
Thu (02/10) | 02 Oct 2025 | P1 |  | Formwork column stump dismantling
Thu (02/10) | 02 Oct 2025 | P2 |  | Slope lean concrete in progress
Thu (02/10) | 02 Oct 2025 | P4 |  | Preparation for working platform installation for stressing works
Thu (02/10) | 02 Oct 2025 | BR8 |  | Rebar works in progress
Thu (02/10) | 02 Oct 2025 | BR21 |  | Rebar works in progress
Thu (02/10) | 02 Oct 2025 | P19 SB up chainage |  | Lifter shifting completed. Nightshift to install at NB upchainage
Thu (02/10) | 02 Oct 2025 | P17 NB |  | Lifter dismantling now. To be shifted to P19
Thu (02/10) | 02 Oct 2025 | P43 crosshead |  | PT duct and RWDP installation in progress
Thu (02/10) | 02 Oct 2025 | P45 |  | 1st layer caison rebar works until 930pm
Thu (02/10) | 02 Oct 2025 | P21 NB D01 |  | Segment launched yesterday. Initial adjustment in progress
Fri (03/10) | 03 Oct 2025 | BR21 |  | Rebar works in progress. Target to cast 6 Oct
Fri (03/10) | 03 Oct 2025 | Zone 2 P6-7 stockpile area |  | Disposal to T03, 8 loads already disposed
Fri (03/10) | 03 Oct 2025 | 800mm PW |  | Preparation for MPI test
Fri (03/10) | 03 Oct 2025 | B2-44 |  | Preparation work in progress for waterproofing, will handover partial to maxbond today
Fri (03/10) | 03 Oct 2025 | B2-43 |  | No activity
Fri (03/10) | 03 Oct 2025 | BR8A |  | Rebar works in progress, Dongah rectification works ongoing. Today to complete, BR8B, Continue rebar works, Target to cast by end next week
Fri (03/10) | 03 Oct 2025 | P50 |  | S1 strut removal
Fri (03/10) | 03 Oct 2025 | P49 |  | No activity. Pile cap concrete curing
Fri (03/10) | 03 Oct 2025 | P48 |  | Formwork removal and housekeeping
Fri (03/10) | 03 Oct 2025 | DR3 soldier pile |  | Preboring for 3rd point (2/7 completed)
Fri (03/10) | 03 Oct 2025 | DR3 |  | Excavation towards P46 side
Fri (03/10) | 03 Oct 2025 | P4 |  | Recces foam removal in progress. Plan to push strand today for 1st tage tensioning
Fri (03/10) | 03 Oct 2025 | Exit 1 |  | Leaned concrete for the slope last night, will continue preparation work for waler beam
Fri (03/10) | 03 Oct 2025 | P45 |  | L1 caisson rebar installation ongoing
Fri (03/10) | 03 Oct 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Fri (03/10) | 03 Oct 2025 | S1-1 |  | BR18, KP welding completed, 1pm lean con, All Coupler exposed, Rebar work ongoing now
Fri (03/10) | 03 Oct 2025 | S2-1 | BR12 | Excavation in progress
Fri (03/10) | 03 Oct 2025 | BR21 |  | Rebar works and formwork closing ongoing
Fri (03/10) | 03 Oct 2025 | BR18B |  | Lean con casting in progress
Fri (03/10) | 03 Oct 2025 | 800mm PW |  | Internal welding works ongoing
Fri (03/10) | 03 Oct 2025 | BR8 |  | Rebar works in progress
Fri (03/10) | 03 Oct 2025 | Exit 1 |  | Levelling works ongoing. Plan for lean con casting tonight
Fri (03/10) | 03 Oct 2025 | BR26 |  | Excavation started
Fri (03/10) | 03 Oct 2025 | P45 |  | 1st layer caison formwork closing
Fri (03/10) | 03 Oct 2025 | BR26 |  | Excavation in progress. Works till 8pm. No night shift here
Fri (03/10) | 03 Oct 2025 | B2-43 |  | No activity
Fri (03/10) | 03 Oct 2025 | B2-44 |  | Linkway wall patching works, Groove lines cutting for waterproofing ongoing
Fri (03/10) | 03 Oct 2025 | Exit 1 |  | To lean con by tonight to facilitate waler beam works
Fri (03/10) | 03 Oct 2025 | P19 |  | All lifter shifting completed. Now connection of electrical components and testing
Fri (03/10) | 03 Oct 2025 | BR8 |  | Rebar works in progress
Fri (03/10) | 03 Oct 2025 | Exit 2 capping beam area |  | 1nos i-beam installed at water pipe area
Fri (03/10) | 03 Oct 2025 | BR21 |  | Shearlinks, formwork closing and cleaning in progress
Fri (03/10) | 03 Oct 2025 | GL9 |  | Continue hacking RC stump. 1nos completed, balance 1 more
Fri (03/10) | 03 Oct 2025 | P4 |  | Strand pushing for 1st tage tensioning
Fri (03/10) | 03 Oct 2025 | BR18B |  | Continue rebar works (8 men)
Fri (03/10) | 03 Oct 2025 | P24 area |  | Currently making access
Fri (03/10) | 03 Oct 2025 | Exit 3 |  | No activity
Fri (03/10) | 03 Oct 2025 | P1 |  | LSS backfilling to pile level completed
Fri (03/10) | 03 Oct 2025 | CCW1 S4 |  | No activity
Fri (03/10) | 03 Oct 2025 | Zone 1 NB |  | 1 lane closed for excavator shifting at P3 side (from P2)
Fri (03/10) | 03 Oct 2025 | P21 Up chainage |  | Crane platform preparation for segment launching. PLT arrange today
Fri (03/10) | 03 Oct 2025 | GL9 |  | Hacking of RC stump
Fri (03/10) | 03 Oct 2025 | S2-1 | BR22 | Continue bracing works for deck posts
Fri (03/10) | 03 Oct 2025 | P43 |  | Shear link installation for both north & south side
Sat (04/10) | 04 Oct 2025 | 800mm PW |  | Water pipe backfilling ongoing
Sat (04/10) | 04 Oct 2025 | P51 |  | Clearing materials
Sat (04/10) | 04 Oct 2025 | P50 |  | No activity. S1 strut cutting completed, pending lifting of strut
Sat (04/10) | 04 Oct 2025 | P49 |  | No activity. Pile cap concrete curing
Sat (04/10) | 04 Oct 2025 | P48 |  | Maintenance platform installation ongoing
Sat (04/10) | 04 Oct 2025 | P47 |  | Trial Trench for JGP on going. Total 8nos coring on DR3 top slab completed
Sat (04/10) | 04 Oct 2025 | DR3 soldier pile |  | Soldier pile installation completed, balance 5 nos steel plate to be installed. Target to complete by today
Sat (04/10) | 04 Oct 2025 | DR3 |  | Excavation towards P46
Sat (04/10) | 04 Oct 2025 | P45 |  | Formwork closing. Target to cast L1 first section today
Sat (04/10) | 04 Oct 2025 | P43 |  | Rebar inspection ongoing
Sat (04/10) | 04 Oct 2025 | P21 |  | Segment adjustment
Sat (04/10) | 04 Oct 2025 | P19 |  | Preparation work to install stressing cage
Sat (04/10) | 04 Oct 2025 | S3 |  | Working platform erection
Sat (04/10) | 04 Oct 2025 | P6-7 |  | Current stockpile status
Sat (04/10) | 04 Oct 2025 | P4 |  | Strand cutting on going
Sat (04/10) | 04 Oct 2025 | P1 |  | No activity
Sat (04/10) | 04 Oct 2025 | P20 |  | Segment adjustment
Sat (04/10) | 04 Oct 2025 | P19 |  | 2nd stressing cage installation ongoing
Sat (04/10) | 04 Oct 2025 | S3 |  | Current working platform erection status
Sat (04/10) | 04 Oct 2025 | P4 |  | Strand pulling ongoing
Sat (04/10) | 04 Oct 2025 | 800mm PW |  | Backfilling and ERSS removal
Sat (04/10) | 04 Oct 2025 | P48 |  | KTC preparation work before lowering down excavator
Sat (04/10) | 04 Oct 2025 | P48 |  | Installation of maintenance platform for water pipe ongoing
Sat (04/10) | 04 Oct 2025 | P47 |  | Coring through top slab of existing DR3
Sat (04/10) | 04 Oct 2025 | DR3 |  | Current excavation status
Sat (04/10) | 04 Oct 2025 | P45 |  | L1 caisson (east and west) casting in progress; (north) rebar work ongoing
Sat (04/10) | 04 Oct 2025 | P43 |  | Crosshead closing side formwork
Sun (05/10) | 05 Oct 2025 | GL9 |  | 2nos RC stumps hacking completed
Sun (05/10) | 05 Oct 2025 | BR18B |  | Rebar works in progress (9 men)
Sun (05/10) | 05 Oct 2025 | BR22, BR23, BR24 |  | No activity
Sun (05/10) | 05 Oct 2025 | BR21 |  | Formwork support installation and cleaning in progress. Target for casting tmr
Sun (05/10) | 05 Oct 2025 | BR11 | GL13-16 | Excavation in progress, BR9 (GL16-18.5): Continue soil disposal/internal shifting works and clearing materials
Sun (05/10) | 05 Oct 2025 | Exit 2 capping beam area | GL16 | Part 1 wall formwork removal. Wall was cast last Friday evening
Sun (05/10) | 05 Oct 2025 | BR8 |  | Wendyng continue rebar works (40 men). RTO inspection ongoing, Balance dwall rectification works by Dongah to completed by today (ST67-68 joint area and at ST71) - 7men, Target to cast roof slab by end of the upcoming week
Sun (05/10) | 05 Oct 2025 | Exit 1 |  | Currently no activity
Sun (05/10) | 05 Oct 2025 | B2-44 |  | Groove line cutting for waterproofing works
Sun (05/10) | 05 Oct 2025 | B2-45, B2-46 |  | No activity
Sun (05/10) | 05 Oct 2025 | B2-43 |  | No activity
Sun (05/10) | 05 Oct 2025 | BR26 |  | Excavation in progress
Sun (05/10) | 05 Oct 2025 | P24 area |  | Excavation ongoing (1 excavator working)
Sun (05/10) | 05 Oct 2025 | CCW north side S4 |  | Continue rebar planting
Sun (05/10) | 05 Oct 2025 | BR21 |  | RTO inspection, Continue corrugated pipes installation & cleaning
Sun (05/10) | 05 Oct 2025 | BR11 | GL13-16 | Excavation in progress, BR9 (GL16-18.5): Continue soil disposal/internal shifting works
Sun (05/10) | 05 Oct 2025 | Exit 2 | GL16 | No activity. Part 1 wall formwork dismantled
Sun (05/10) | 05 Oct 2025 | BR18B |  | Continue rebar works
Sun (05/10) | 05 Oct 2025 | BR8 |  | Continue rebar works
Sun (05/10) | 05 Oct 2025 | Exit 1 |  | Clearing hardcore and soil. Tmr plan to continue balance lean con casting & start rebar works
Sun (05/10) | 05 Oct 2025 | BR26 |  | Continue excavation
Sun (05/10) | 05 Oct 2025 | B2-44 |  | Surface patching works ongoing. Currently no other activity
Sun (05/10) | 05 Oct 2025 | CCW1 S4 |  | No activity
Sun (05/10) | 05 Oct 2025 | CCW north side S4 |  | Rebar planting works ongoing (6 men)
Sun (05/10) | 05 Oct 2025 | Exit 3 |  | No activity
Sun (05/10) | 05 Oct 2025 | P24 area |  | Excavation and installing access towards north side
Mon (06/10) | 06 Oct 2025 | BR11 |  | Base lean con casting in progress
Mon (06/10) | 06 Oct 2025 | P19 |  | Load test for lifter completed. Waiting for LM certificate to be issued then proceed for launching
Mon (06/10) | 06 Oct 2025 | 800mm dia water pipe laying |  | Reinstate the area. Tomorrow Ley Choon RC team will mobilize for butterfly valve RC work
Mon (06/10) | 06 Oct 2025 | P50 |  | S1 struts already cut. Left some for removal
Mon (06/10) | 06 Oct 2025 | P49 |  | Pile cap curing
Mon (06/10) | 06 Oct 2025 | P48 |  | Excavation for 3rd layer caisson work
Mon (06/10) | 06 Oct 2025 | S3 |  | Upchainage working platform completed. Downchainage to complete today. I beam installation target to start tonight
Mon (06/10) | 06 Oct 2025 | P45 |  | Last part of caisson casting
Mon (06/10) | 06 Oct 2025 | DR3 | P46 side | 3 main beams and 5 secondary beam installed
Mon (06/10) | 06 Oct 2025 | DR3 |  | LE preparing to demob boring rig to P51
Mon (06/10) | 06 Oct 2025 | P4 |  | Wedge plate installation in progress. Tmr only can start stressing
Mon (06/10) | 06 Oct 2025 | P43 |  | Fwk closure ongoing, target to cast tmr
Mon (06/10) | 06 Oct 2025 | CCE4 |  | Dismantling of strut is in progress
Mon (06/10) | 06 Oct 2025 | BR26 |  | Continues excavation & soil disposal
Mon (06/10) | 06 Oct 2025 | B2-43 |  | No activity
Mon (06/10) | 06 Oct 2025 | Exit 1 |  | Has started straightening of the rebar for the waler, now leaning of concrete for the slope
Mon (06/10) | 06 Oct 2025 | BR11 |  | Leaning of concrete is almost done
Mon (06/10) | 06 Oct 2025 | BR21 |  | Ready to cast
Mon (06/10) | 06 Oct 2025 | CCW1 S4 |  | No excavation activity
Mon (06/10) | 06 Oct 2025 | CCW north side S4 |  | Rebar planting works in progress (7 men)
Mon (06/10) | 06 Oct 2025 | P24 area |  | Excavation in progress
Mon (06/10) | 06 Oct 2025 | Exit 3 |  | No activity
Mon (06/10) | 06 Oct 2025 | P21 |  | Segment launching
Mon (06/10) | 06 Oct 2025 | P19 |  | Preparation work for segment launching tonight
Mon (06/10) | 06 Oct 2025 | BR22 |  | Continue soil clearing and levelling works to facilitate platform for deck posts’ bracing works
Mon (06/10) | 06 Oct 2025 | BR18B |  | Rebar works in progress (6 men)
Mon (06/10) | 06 Oct 2025 | Exit 2 |  | Currently no other activity
Mon (06/10) | 06 Oct 2025 | BR11 | GL13-16 | Partial lean concrete completed. Balance area at KP
Mon (06/10) | 06 Oct 2025 | BR9 | GL16-18.5 | Hacking works ongoing for old bored pile, Continue excavation and disposal/internal shifting works
Mon (06/10) | 06 Oct 2025 | S1 |  | No activity. Hardcore backfilling completed
Mon (06/10) | 06 Oct 2025 | S3 |  | No activity. Currently working platform installation status
Mon (06/10) | 06 Oct 2025 | P4 |  | Stressing preparation work ongoing. Tomorrow morning start stressing
Mon (06/10) | 06 Oct 2025 | BR21 |  | Rebar works in progress (54 men - dayshift)
Mon (06/10) | 06 Oct 2025 | Exit 1 |  | Currently no activity
Mon (06/10) | 06 Oct 2025 | B2-44 |  | Waterproofing primer application at linkway wall
Mon (06/10) | 06 Oct 2025 | BR26 |  | Excavation stop for the day. No night shift planned here. Night shift continue at BR9 loading point area
Mon (06/10) | 06 Oct 2025 | B2-43 |  | No activity
Mon (06/10) | 06 Oct 2025 | B2-46, B2-45 |  | No activity
Mon (06/10) | 06 Oct 2025 | BR21 |  | Casting in progress
Mon (06/10) | 06 Oct 2025 | 800mm PW |  | Backfilling in progress
Mon (06/10) | 06 Oct 2025 | P48 |  | Excavation to L3 caisson level ongoing
Mon (06/10) | 06 Oct 2025 | DR3 |  | Utility support installation on going
Mon (06/10) | 06 Oct 2025 | P43 |  | Formwork closing in progress
Mon (06/10) | 06 Oct 2025 | BR18B |  | Continue rebar works (6 men - nightshift)
Mon (06/10) | 06 Oct 2025 | BR22 |  | Steel plates laid and cleaning ongoing
Mon (06/10) | 06 Oct 2025 | BR21 |  | Casting in progress (9 men - nightshift)
Mon (06/10) | 06 Oct 2025 | BR11 |  | No activity
Mon (06/10) | 06 Oct 2025 | BR9 | GL17 | Excavation ongoing. No disposal works tonight as access is used for pump truck parking
Mon (06/10) | 06 Oct 2025 | BR8 |  | Continue rebar works. Dayshift men working till 930pm. Night shift team - 20 men
Tue (07/10) | 07 Oct 2025 | BR21 |  | Casting completed
Tue (07/10) | 07 Oct 2025 | BR22 |  | Currently no activity. Tonight plan for dwall hacking as currently KTC breaker broke down. Only 1 breaker working at BR9, Hirose team at CCE for the struts removal
Tue (07/10) | 07 Oct 2025 | BR23, BR24/Exit 2 |  | No activity
Tue (07/10) | 07 Oct 2025 | P43 |  | Crosshead casting ongoing, vol: 208m3
Tue (07/10) | 07 Oct 2025 | BR11 |  | Exposing couplers and kingpost welding works, BR9: Soil hacking and disposal/internal shifting works ongoing
Tue (07/10) | 07 Oct 2025 | DR3/P46 |  | Main beam and secondary beam installed. Left to cast footing and welding work
Tue (07/10) | 07 Oct 2025 | P48 |  | KTC continue excavation for next layer caisson
Tue (07/10) | 07 Oct 2025 | P49 |  | Pile cap curing. Strut removal will be after P50 complete removal
Tue (07/10) | 07 Oct 2025 | P43 |  | Crosshead casting in progress
Tue (07/10) | 07 Oct 2025 | BR8 |  | Continue rebar works and partial formwork closing. Plan for casting Thursday evening or Friday
Tue (07/10) | 07 Oct 2025 | P1 S2 strut |  | Diagonal bracing cutting started
Tue (07/10) | 07 Oct 2025 | S3 |  | Working platform adjusting for segment launching
Tue (07/10) | 07 Oct 2025 | P19 2nd pair |  | Stressing in progress
Tue (07/10) | 07 Oct 2025 | CCE4 |  | Dismantling of struts, today target to finish for 6 Nos
Tue (07/10) | 07 Oct 2025 | B2-44 |  | Waterproofing membrane laying in progress
Tue (07/10) | 07 Oct 2025 | BR26 |  | Continues excavation & soil disposal
Tue (07/10) | 07 Oct 2025 | Exit 1 |  | Started lowering down of rebar for waler beam
Tue (07/10) | 07 Oct 2025 | P50 |  | Formwork erection for LSS backfilling
Tue (07/10) | 07 Oct 2025 | P48 |  | Excavation to L3 caisson level
Tue (07/10) | 07 Oct 2025 | DR3 |  | No activity
Tue (07/10) | 07 Oct 2025 | P45 |  | Hacking of lean con, for diagonal strut installation tomorrow
Tue (07/10) | 07 Oct 2025 | P43 |  | Crosshead casting in progress
Tue (07/10) | 07 Oct 2025 | P4 |  | No activity
Tue (07/10) | 07 Oct 2025 | S1 |  | Excavation ongoing
Tue (07/10) | 07 Oct 2025 | P19 |  | 1st segment delivered onsite. Preparation work for segment launching
Wed (08/10) | 08 Oct 2025 | 800mm PW | butterfly valve | Setting up working space and equipment. Today going to start formwork installation
Wed (08/10) | 08 Oct 2025 | 800mm PW |  | Current excavation status. No activity, LC assisting in preparation work at butterfly valve
Wed (08/10) | 08 Oct 2025 | P1 |  | S2 strut removal ongoing
Wed (08/10) | 08 Oct 2025 | P4 |  | Stressing completed
Wed (08/10) | 08 Oct 2025 | Exit 1 |  | Ready to start rebar work for the waler
Wed (08/10) | 08 Oct 2025 | Exit 1 |  | New ECM stockpile status
Wed (08/10) | 08 Oct 2025 | P50 |  | Formwork erection for LSS backfilling
Wed (08/10) | 08 Oct 2025 | P49 |  | No activity
Wed (08/10) | 08 Oct 2025 | P48 |  | Grout hacking and excavation at south side
Wed (08/10) | 08 Oct 2025 | P47 |  | Trial Trench for JGP
Wed (08/10) | 08 Oct 2025 | DR3 |  | Manual excavation for utility support installation
Wed (08/10) | 08 Oct 2025 | P45 |  | S1 strut installation in progress
Wed (08/10) | 08 Oct 2025 | BR26 |  | Continues excavation & soil disposal
Wed (08/10) | 08 Oct 2025 | B2-44 |  | Plan to finish the waterproofing work today
Wed (08/10) | 08 Oct 2025 | CCE4 |  | Today will dismantle the walers
Wed (08/10) | 08 Oct 2025 | Zone 1 |  | Erection of hoarding for existing linkway dismantling to facilitate P1 crosshead construction
Wed (08/10) | 08 Oct 2025 | P19 |  | Segment stressing ongoing for NB D/U 03
Wed (08/10) | 08 Oct 2025 | S3 |  | Segment launching Falsework current status
Wed (08/10) | 08 Oct 2025 | S1 |  | Falsework erection for Crosshead
Wed (08/10) | 08 Oct 2025 | P1 |  | S2 waler dismantling
Wed (08/10) | 08 Oct 2025 | 800PW | BV | Welding work along pipe / preparing fwk erection / rebar delivery target tmr to arrive / continue water pumping
Wed (08/10) | 08 Oct 2025 | BR22 |  | Current status of dwall hacking. Breaker currently at BR9, Hirose no activity yet
Wed (08/10) | 08 Oct 2025 | BR12 |  | Excavation ongoing. Currently only 1 excavator working
Wed (08/10) | 08 Oct 2025 | BR18B |  | Shearlinks & formwork installation, RTO inspection ongoing, Plan for casting tmr
Wed (08/10) | 08 Oct 2025 | BR11 | GL13-16 | Exposing couplers and top plate welding ongoing for kingposts, BR9 (GL16-18.5):, Continue hacking works at dwall surface, Soil disposal/internal shifting works
Wed (08/10) | 08 Oct 2025 | N4-N5 midspan |  | Stitching formwork closing completed. To cast tmr tonight
Wed (08/10) | 08 Oct 2025 | BR8 |  | Continue rebar works, corrugated pipes, shearlinks installation and cleaning ongoing
Wed (08/10) | 08 Oct 2025 | DR3 | South | Excavation ongoing for utility support
Wed (08/10) | 08 Oct 2025 | P43 |  | Curing
Wed (08/10) | 08 Oct 2025 | S1 |  | Lean con completed, preparing for pad footing work
Wed (08/10) | 08 Oct 2025 | S3 |  | Working platform in progress
Wed (08/10) | 08 Oct 2025 | P19 |  | Continue preparing for stressing work
Thu (09/10) | 09 Oct 2025 | 800PW | BV | Continue welding work & preparing fwk closure
Thu (09/10) | 09 Oct 2025 | S1 |  | Secondary beam installation in progress
Thu (09/10) | 09 Oct 2025 | P1 |  | Backfilling works for ERSS removal
Thu (09/10) | 09 Oct 2025 | B2-44 |  | Dewatering is in progress prior to continue with waterprrofing work
Thu (09/10) | 09 Oct 2025 | BR26 |  | Partial lean concrete was done last night
Thu (09/10) | 09 Oct 2025 | BR26 |  | Has started exposing of couplers
Thu (09/10) | 09 Oct 2025 | Exit 1 |  | Waler rebar work in progress, target to cast it by end of the week, Manpower: 1Sup + 14 workers
Thu (09/10) | 09 Oct 2025 | P50 |  | LSS backfilling ongoing, 122/230m3
Thu (09/10) | 09 Oct 2025 | P48 |  | 1st layer north side excavation completed, handover to WH for lean con (target tonight) & KTC continue with south side excavation
Thu (09/10) | 09 Oct 2025 | DR3 |  | Continue manual excavation for utility support by ice till 7pm
Thu (09/10) | 09 Oct 2025 | P45 |  | S1 strut welding work continue
Thu (09/10) | 09 Oct 2025 | P19 SB 3rd pair |  | Stressing in progress
Thu (09/10) | 09 Oct 2025 | S1 |  | Working platform fabrication, to be installed tonight
Thu (09/10) | 09 Oct 2025 | BR22 |  | Hirose welding works ongoing till 10pm
Thu (09/10) | 09 Oct 2025 | BR11 |  | Rebar works in progress
Thu (09/10) | 09 Oct 2025 | BR21 |  | Formwork removal in progress
Thu (09/10) | 09 Oct 2025 | BR8 |  | No activity. Tmr to cast
Thu (09/10) | 09 Oct 2025 | BR1 |  | Started clearing soil stockpile
Thu (09/10) | 09 Oct 2025 | Exit 1 |  | Rebar works for waler beam in progress (5+1)
Thu (09/10) | 09 Oct 2025 | P42 |  | Column rebar works in progress (3+1), Receiving shaft: No activity
Thu (09/10) | 09 Oct 2025 | B2-44 |  | Dismantling platform. LSS backfill plan for tonight
Thu (09/10) | 09 Oct 2025 | B2-43 |  | No activity
Thu (09/10) | 09 Oct 2025 | BR26 |  | Hacking of excess concrete until 10pm by WH. Tonight wendyng plan to continue exposing couplers
Thu (09/10) | 09 Oct 2025 | Exit 3 |  | No activity
Thu (09/10) | 09 Oct 2025 | P24 area |  | No activity
Thu (09/10) | 09 Oct 2025 | CCW north side S4 |  | Waler rebar works in progress (4 men)
Thu (09/10) | 09 Oct 2025 | BR18B |  | Casting in progress
Fri (10/10) | 10 Oct 2025 | BR26 |  | Hacking of excess concrete & CJ roughening in progress
Fri (10/10) | 10 Oct 2025 | BR26 |  | WH mini excavator preparing to continue cutting down soil
Fri (10/10) | 10 Oct 2025 | P42 |  | 2nd stage column rebar installation in progress
Fri (10/10) | 10 Oct 2025 | Exit 1 |  | Ongoing rebar work for waler
Fri (10/10) | 10 Oct 2025 | P45 |  | S1 strut installation ongoing
Fri (10/10) | 10 Oct 2025 | P48 |  | Excavation to L3 caisson level
Fri (10/10) | 10 Oct 2025 | DR3 |  | No activity
Fri (10/10) | 10 Oct 2025 | P51 |  | Preparation work for probing
Fri (10/10) | 10 Oct 2025 | P50 |  | No activity. LSS backfilling completed
Fri (10/10) | 10 Oct 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Fri (10/10) | 10 Oct 2025 | BR18B |  | Casting in progress
Fri (10/10) | 10 Oct 2025 | BR11 |  | Rebar works in progress
Fri (10/10) | 10 Oct 2025 | BR9 |  | Continue exposing couplers
Fri (10/10) | 10 Oct 2025 | Exit 2 |  | Soil disposal works ongoing
Fri (10/10) | 10 Oct 2025 | BR8 |  | No activity
Fri (10/10) | 10 Oct 2025 | Exit 1 |  | Continue rebar works for waler
Fri (10/10) | 10 Oct 2025 | B2-44 |  | LSS backfilling in progress
Fri (10/10) | 10 Oct 2025 | P42 |  | Column rebar works in progress
Fri (10/10) | 10 Oct 2025 | BR26 |  | CJ roughening ongoing
Fri (10/10) | 10 Oct 2025 | P19 SB |  | Preparing to shift lifter for tonight's segment installation, NB: 4th pair tensioning in progress
Fri (10/10) | 10 Oct 2025 | N4-N5 midspan |  | Wet stitching casting completed last night
Fri (10/10) | 10 Oct 2025 | N4-N3 midspan |  | Clamping bar installation completed
Fri (10/10) | 10 Oct 2025 | 800mm PW |  | Excavation and ERSS
Fri (10/10) | 10 Oct 2025 | P45 |  | S1 strut installation at north side
Fri (10/10) | 10 Oct 2025 | DR3 | south | Excavation at expose utilities
Fri (10/10) | 10 Oct 2025 | DR3 | north | Manual excavation for utility support installation
Fri (10/10) | 10 Oct 2025 | P48 | north | Preparation for L3 caisson rebar work
Fri (10/10) | 10 Oct 2025 | P48 | south | Continue excavation to L3 caisson level
Fri (10/10) | 10 Oct 2025 | P51 |  | Boring rig set up completed
Fri (10/10) | 10 Oct 2025 | P51 |  | Trial Trench ongoing
Fri (10/10) | 10 Oct 2025 | BR18B |  | Casting in progress with only 1 pump truck now
Fri (10/10) | 10 Oct 2025 | BR11 |  | Current status of rebar works
Fri (10/10) | 10 Oct 2025 | B2-44 |  | LSS backfilling in progress
Fri (10/10) | 10 Oct 2025 | CCW north side S4 |  | Rebar works in progress (9+1)
Fri (10/10) | 10 Oct 2025 | Exit 3 |  | No activity
Fri (10/10) | 10 Oct 2025 | P24 area |  | No activity
Fri (10/10) | 10 Oct 2025 | BR12 |  | No activity
Fri (10/10) | 10 Oct 2025 | BR22 |  | No activity
Fri (10/10) | 10 Oct 2025 | BR11 |  | Continue rebar works (4 men)
Fri (10/10) | 10 Oct 2025 | BR9 |  | Partial debonding sheet laid
Fri (10/10) | 10 Oct 2025 | Exit 1 |  | Waler rebar works in progress (6+1)
Fri (10/10) | 10 Oct 2025 | P42 |  | No activity
Fri (10/10) | 10 Oct 2025 | B2-43 |  | No activity
Fri (10/10) | 10 Oct 2025 | B2-44 |  | Preparing to continue LSS backfilling
Sat (11/10) | 11 Oct 2025 | P42 |  | Scaffold erection for column rebar works
Sat (11/10) | 11 Oct 2025 | P44 & P43 |  | No activity
Sat (11/10) | 11 Oct 2025 | P45 |  | 1st layer strut welding works ongoing. Today to complete
Sat (11/10) | 11 Oct 2025 | DR3 |  | Manual excavation for utility support installation
Sat (11/10) | 11 Oct 2025 | P48 |  | KTC excavation ongoing for 3rd layer caisson wall
Sat (11/10) | 11 Oct 2025 | P51 |  | Trial trench and probing ongoing
Sat (11/10) | 11 Oct 2025 | Zone 4 opp SIA |  | Excavation and shoring in progress for PW800 pipe laying
Sat (11/10) | 11 Oct 2025 | P4 |  | Falsework dismantling ongoing
Sat (11/10) | 11 Oct 2025 | S1 |  | Working platform and barricade installation works
Sat (11/10) | 11 Oct 2025 | S3 |  | Segment adjustment ongoing
Sat (11/10) | 11 Oct 2025 | P19 |  | SB D/U04 Tendon strands installation for stressing works
Sat (11/10) | 11 Oct 2025 | P21 |  | Scaffold erection in progress
Sat (11/10) | 11 Oct 2025 | BR26 |  | Current status of excavation
Sat (11/10) | 11 Oct 2025 | B2-44 |  | Continue LSS backfilling
Sat (11/10) | 11 Oct 2025 | P42 |  | Continue 2nd stage column rebar installation
Sat (11/10) | 11 Oct 2025 | P45 |  | Welding for s1 struts completed. Concrete ordered for concrete packing
Sat (11/10) | 11 Oct 2025 | DR3 |  | Manual excavation & Utility supports ongoing
Sat (11/10) | 11 Oct 2025 | P48 |  | Excavation for 3rd layer completed. Levelling and soil clearing in progress
Sat (11/10) | 11 Oct 2025 | P51 |  | Trial trench and probing works
Sat (11/10) | 11 Oct 2025 | Zone 4 |  | PW800 continue excavation for water pipe laying
Sat (11/10) | 11 Oct 2025 | P1 |  | Backfilling and compaction for s1 struts and Walers removal completed. Pending NDT test
Sat (11/10) | 11 Oct 2025 | P4 |  | Continue Falsework dismantling works
Sat (11/10) | 11 Oct 2025 | S1 |  | Falsework current status
Sat (11/10) | 11 Oct 2025 | S3 |  | Segment adjustment in progress
Sat (11/10) | 11 Oct 2025 | P19 |  | Stressing completed for SB D/U 04
Sat (11/10) | 11 Oct 2025 | P21 |  | Continue scaffold erection
Sat (11/10) | 11 Oct 2025 | BR11 |  | Works done for the night (CGW)
Sat (11/10) | 11 Oct 2025 | BR9 |  | No activity
Sat (11/10) | 11 Oct 2025 | B2-44 |  | LSS backfilling in progress, 285/355m3
Mon (13/10) | 13 Oct 2025 | P21 |  | Scaffold dismantling at the NB side
Mon (13/10) | 13 Oct 2025 | P19 |  | Stressing works for NB/SB D/U05 segments
Mon (13/10) | 13 Oct 2025 | 800mm dia water pipe |  | 7.5m length was laid. Will continue excavation toward TPE side
Mon (13/10) | 13 Oct 2025 | BR11 |  | Rebar works in progress (CGW)
Mon (13/10) | 13 Oct 2025 | BR9 |  | Rebar works in progress (Wendyng)
Mon (13/10) | 13 Oct 2025 | Gate 5 |  | New cube house erection
Mon (13/10) | 13 Oct 2025 | BR12 |  | Excavation in progress
Mon (13/10) | 13 Oct 2025 | P48 |  | Strut end plate installation before caisson wall formwork closing. Housekeeping to be improve
Mon (13/10) | 13 Oct 2025 | P51 |  | Shifting hardcore stockpile to continue TT for ERSS work
Mon (13/10) | 13 Oct 2025 | CCE4 |  | Dismantling of remaining 6 struts
Mon (13/10) | 13 Oct 2025 | BR26 |  | Preparing to lean concrete @ loading point
Mon (13/10) | 13 Oct 2025 | BR26 |  | Continue exposing of couplers & target to start rebar work tomorrow
Mon (13/10) | 13 Oct 2025 | B2-43 |  | Continues excavation & soil disposal
Mon (13/10) | 13 Oct 2025 | P45 |  | MPI test done for struct. Next activity will be excavation for 2nd layer caisson
Mon (13/10) | 13 Oct 2025 | DR3 |  | Continue utility support welding
Mon (13/10) | 13 Oct 2025 | DR3 TPE bound side |  | Exposing services for utility support
Mon (13/10) | 13 Oct 2025 | Exit 1 |  | Rebar/formwork installation in progress for waler, target to cast it tomorrow
Mon (13/10) | 13 Oct 2025 | P43 |  | Preparation for crosshead side formwork removal
Mon (13/10) | 13 Oct 2025 | P19 |  | Preparation for 2 segments to launch tonight at NB
Mon (13/10) | 13 Oct 2025 | S1 |  | Current status of working platform installation. Wendyng already end work
Mon (13/10) | 13 Oct 2025 | S3 |  | Now no activity
Mon (13/10) | 13 Oct 2025 | P1 |  | Waler beam removal
Mon (13/10) | 13 Oct 2025 | P4 |  | After last bus then plan to dismantle the primary beam at SB
Tue (14/10) | 14 Oct 2025 | 800mm dia water pipe |  | Excavation and ERSS installation
Tue (14/10) | 14 Oct 2025 | S3 |  | 1st pair stitching formwork closing. Target to cast tmr evening, 2nd pair working platform erection
Tue (14/10) | 14 Oct 2025 | BR18A |  | Surface grinding ongoing
Tue (14/10) | 14 Oct 2025 | BR12 |  | Excavation and disposal in progress
Tue (14/10) | 14 Oct 2025 | BR21 |  | CJ roughening ongoing
Tue (14/10) | 14 Oct 2025 | BR11 |  | Continue rebar works, shearlinks and partial formwork installation, BR9: Rebar works in progress
Tue (14/10) | 14 Oct 2025 | Exit 2 |  | Currently no other activity. Welder is cutting rebars ar BR12 area. Plan to provide support for water pipe tmr
Tue (14/10) | 14 Oct 2025 | P45 |  | As of now no activity
Tue (14/10) | 14 Oct 2025 | D3 |  | LE continue welding work
Tue (14/10) | 14 Oct 2025 | DR3 TPE bound |  | Excavation for drain work
Tue (14/10) | 14 Oct 2025 | DR3 existing drain |  | TT for coring work
Tue (14/10) | 14 Oct 2025 | P48 |  | Rebar work in progress for caisson wall
Tue (14/10) | 14 Oct 2025 | P48 |  | Formwork closing for caisson wall at Changi bound. Today to cast
Tue (14/10) | 14 Oct 2025 | P49 |  | Strut cutting for removal
Tue (14/10) | 14 Oct 2025 | P51 |  | TT for pipe sleeves installation
Tue (14/10) | 14 Oct 2025 | P43 |  | Crosshead formwork removal
Tue (14/10) | 14 Oct 2025 | Exit 1 waler |  | Rebar and formwork installation in progress
Tue (14/10) | 14 Oct 2025 | B2-46, B2-45, B2-44 |  | Current status. Balance 2 struts on site
Tue (14/10) | 14 Oct 2025 | B2-43 |  | Currently no activity
Tue (14/10) | 14 Oct 2025 | BR26 |  | Continue wxposing couplers and u-bar welding works, Preparing formwork for lean con casting, Hacking works ongoing
Tue (14/10) | 14 Oct 2025 | B2-41 |  | Excavation started
Tue (14/10) | 14 Oct 2025 | P19 |  | Stressing completed for NB d/u 06 segment
Tue (14/10) | 14 Oct 2025 | BR11 |  | Shearlinks and formwork installation
Tue (14/10) | 14 Oct 2025 | BR12 |  | Excavation ongoing
Tue (14/10) | 14 Oct 2025 | BR22 |  | Hirose continue bracing welding works
Tue (14/10) | 14 Oct 2025 | Exit 1 |  | Continues rebar & formwork installation for waler, target to cast it tonight
Tue (14/10) | 14 Oct 2025 | BR9 |  | Rebar works in progress
Tue (14/10) | 14 Oct 2025 | Exit 1 |  | No activity at new ECM pond
Tue (14/10) | 14 Oct 2025 | 800mm dia water pipe laying |  | Continue excavation and ERSS
Tue (14/10) | 14 Oct 2025 | CCE4 |  | 10 out of 12 struts have been dismantled
Tue (14/10) | 14 Oct 2025 | B2-41 |  | Continues excavation & soil disposal
Tue (14/10) | 14 Oct 2025 | BR26 |  | Continue exposing of couplers, target to start rebar work later
Tue (14/10) | 14 Oct 2025 | P6 |  | Lean concrete in progress for drain connection
Tue (14/10) | 14 Oct 2025 | P1 |  | Backfilling completed. Tmr to start SP and LP extraction
Tue (14/10) | 14 Oct 2025 | P45 |  | No activity
Tue (14/10) | 14 Oct 2025 | DR3 |  | 2nd part top soil layer
Tue (14/10) | 14 Oct 2025 | DR3 existing drain |  | Coring for JGP
Tue (14/10) | 14 Oct 2025 | P48 |  | Materials lowering to continue rebar work for caisson
Tue (14/10) | 14 Oct 2025 | P51 |  | Pipe sleeves for JGP
Tue (14/10) | 14 Oct 2025 | P43 |  | Side formwork removal
Tue (14/10) | 14 Oct 2025 | P42 |  | Column formwork closing
Tue (14/10) | 14 Oct 2025 | P19 |  | Materials bring up for tonight segment launching. Tonight plan for 4 segments to launch. 2nos at P19 and 2nos at P21
Tue (14/10) | 14 Oct 2025 | S1 |  | Level checking for soffit plywood laying
Tue (14/10) | 14 Oct 2025 | S4 |  | Balance falsework to remove tonight
Tue (14/10) | 14 Oct 2025 | P2 |  | Erection of falsework base for crosshead
Tue (14/10) | 14 Oct 2025 | P1 |  | LE rig mobilizing
Tue (14/10) | 14 Oct 2025 | P21 |  | Prepare segment to launch tonight
Tue (14/10) | 14 Oct 2025 | P21 |  | Steel plate laying for crane platform, preparation for upchainage 1st pair installation
Tue (14/10) | 14 Oct 2025 | P19 NB 6th pair |  | Strand pushing for tensioning
Tue (14/10) | 14 Oct 2025 | P19 SB |  | Lifter shifting for 6th pair launching tonight
Tue (14/10) | 14 Oct 2025 | P17 |  | Scaffold access erected for 2nd stage crosshead tensioning
Tue (14/10) | 14 Oct 2025 | CCW1 S4 |  | No activity
Tue (14/10) | 14 Oct 2025 | Below P24 TB |  | Excavation in progress, 3 excavators, 1 telescopic working, 1 breaker op on standby
Wed (15/10) | 15 Oct 2025 | B2-41 |  | Continues excavation and soil disposal
Wed (15/10) | 15 Oct 2025 | BR26 |  | Preparing the surface prior to call for inspection, later to lay debonding sheet follow by rebar work
Wed (15/10) | 15 Oct 2025 | P21 upchainage |  | Installation of stressing cage and alignment in progress
Wed (15/10) | 15 Oct 2025 | P17 crosshead |  | Stressing on going
Wed (15/10) | 15 Oct 2025 | Zone 4 near pumping station |  | Preparing to secured back the site at water pipe already laid area
Wed (15/10) | 15 Oct 2025 | PMH28 |  | Clearing unused materials to give way for SPPG
Wed (15/10) | 15 Oct 2025 | P19 NB |  | Preparation to dismantle stressing cage
Wed (15/10) | 15 Oct 2025 | BR22 |  | Currently no activity. WH will prepare platform for Hirose to continue bracing works for decking at BR12
Wed (15/10) | 15 Oct 2025 | BR12 |  | Now preparing platform for Hirose bracing works
Wed (15/10) | 15 Oct 2025 | P43 |  | Side fwk removal ongoing
Wed (15/10) | 15 Oct 2025 | P42 |  | Column fwk closure ongoing
Wed (15/10) | 15 Oct 2025 | BR11 |  | Continue cleaning works & RTO inspection ongoing
Wed (15/10) | 15 Oct 2025 | BR9 |  | Rebar works in progress
Wed (15/10) | 15 Oct 2025 | S3 1st pair |  | Stitching formwork closing, Upchainage: 90% completed, Downchainage: 80% completed, To cast tmr
Wed (15/10) | 15 Oct 2025 | S1 |  | Bottom formwork completed. Preparation to install end and side formwork
Wed (15/10) | 15 Oct 2025 | BR8B, BR7B |  | Backfilling ongoing for soil ramp construction
Wed (15/10) | 15 Oct 2025 | Exit 1 |  | No activity at new ECM pond
Wed (15/10) | 15 Oct 2025 | Exit 1 waler |  | Reinspection to be called again prior to casting. Now Wendyng rectifying comments
Wed (15/10) | 15 Oct 2025 | CCE4 |  | Struts dismantling completed
Wed (15/10) | 15 Oct 2025 | 800mm dia water pipe |  | Today plan to lay 2 pipes
Wed (15/10) | 15 Oct 2025 | BR26 |  | Started laying debonding sheet
Wed (15/10) | 15 Oct 2025 | DR3 |  | Continue top soil removal of main beam installation
Wed (15/10) | 15 Oct 2025 | P48 |  | Lowering down materials for caisson formwork closing. This week to complete 3rd layer caisson
Wed (15/10) | 15 Oct 2025 | P49 |  | S1 strut removal
Wed (15/10) | 15 Oct 2025 | P43 |  | Crosshead formwork removal
Wed (15/10) | 15 Oct 2025 | P19 |  | Will launch one segment tonight
Wed (15/10) | 15 Oct 2025 | P21 |  | Stressing completed. Clearing materials
Wed (15/10) | 15 Oct 2025 | S1 |  | Wingform installation for crosshead
Wed (15/10) | 15 Oct 2025 | S3 |  | Status of stitching formwork closing
Wed (15/10) | 15 Oct 2025 | P7 |  | Clearing hardcore to reinstate the drain
Wed (15/10) | 15 Oct 2025 | P1 |  | Clearing steel plates and soldier pile
Wed (15/10) | 15 Oct 2025 | S1 |  | Current status of soffit formwork and wingform installation for crosshead
Wed (15/10) | 15 Oct 2025 | 800mm dia water pipe |  | Tomorrow can lay two pipes
Wed (15/10) | 15 Oct 2025 | P48 |  | Strut end cutting for removal
Wed (15/10) | 15 Oct 2025 | P48 |  | Caisson rebar work and formwork closing
Wed (15/10) | 15 Oct 2025 | DR3 |  | Tomorrow can install one row of main beam
Wed (15/10) | 15 Oct 2025 | P45 |  | KTC started excavation
Wed (15/10) | 15 Oct 2025 | BR12 |  | Continue excavation and hacking works
Wed (15/10) | 15 Oct 2025 | CCE4 |  | Dismantling of struts in progress
Wed (15/10) | 15 Oct 2025 | P17 |  | Wedge plate installation for 2nd stage tensioning
Wed (15/10) | 15 Oct 2025 | P1 |  | Preparation to start ERSS extraction
Wed (15/10) | 15 Oct 2025 | P2 |  | Falsework assembly works
Wed (15/10) | 15 Oct 2025 | Exit 1 |  | Formwork installation in progress for waler, to cast it today
Thu (16/10) | 16 Oct 2025 | Exit 1 waler |  | Cast last night
Thu (16/10) | 16 Oct 2025 | Exit 1 new ecm pond |  | Status quo
Thu (16/10) | 16 Oct 2025 | Near Selarang Camp/Gate 7 |  | WH start to remove hoarding panels to facilitate preparation works at RTSA land
Thu (16/10) | 16 Oct 2025 | S3 |  | Stitching to cast after lunch. Working platform for upchainage until 3rd pair completed
Thu (16/10) | 16 Oct 2025 | P6 |  | Drain reinstatement
Thu (16/10) | 16 Oct 2025 | BR7B/8B |  | Continue backfilling works for soil ramp
Thu (16/10) | 16 Oct 2025 | BR9 |  | Rebar works in progress
Thu (16/10) | 16 Oct 2025 | P45 |  | Continue excavation for next layer caisson
Thu (16/10) | 16 Oct 2025 | DR3 |  | Preparing to build up UKP for main beam
Thu (16/10) | 16 Oct 2025 | P48 |  | Caisson formwork closing and preparing platform for welding work
Thu (16/10) | 16 Oct 2025 | P49 |  | Strut cutting and removal
Thu (16/10) | 16 Oct 2025 | P51 |  | Pipe sleeves installation for JGP
Thu (16/10) | 16 Oct 2025 | 800mm dia water pipe |  | Preparing for lowering down water pipe
Thu (16/10) | 16 Oct 2025 | P2 |  | Preparation for crane shifting. Today to resume falsework erection
Thu (16/10) | 16 Oct 2025 | P43 |  | Continue prepare to remove side fwk
Thu (16/10) | 16 Oct 2025 | P42 |  | Prepare for fwk side support
Thu (16/10) | 16 Oct 2025 | Exit 1 new ECM |  | Status quo. Now temporary stockpile from exit 2 area
Thu (16/10) | 16 Oct 2025 | Exit 1 waler area |  | No activity
Thu (16/10) | 16 Oct 2025 | P45 |  | Continue excavation for 2nd layer caisson
Thu (16/10) | 16 Oct 2025 | DR3 |  | UKP built up for main beam installation
Thu (16/10) | 16 Oct 2025 | DR3 |  | Continue excavation
Thu (16/10) | 16 Oct 2025 | P48 |  | Preparing for casting
Thu (16/10) | 16 Oct 2025 | P48 |  | Clearing materials for casting
Thu (16/10) | 16 Oct 2025 | P49 |  | Left two diagonal strut to complete cutting
Thu (16/10) | 16 Oct 2025 | P51 |  | Pipe sleeves installation for JGP
Thu (16/10) | 16 Oct 2025 | B2-43 |  | No activity
Thu (16/10) | 16 Oct 2025 | B2-40 |  | Excavation in progress
Thu (16/10) | 16 Oct 2025 | BR26 |  | Bottom rebar works in progress, BR27: CJ roughening ongoing
Thu (16/10) | 16 Oct 2025 | BR9 |  | Rebar works in progress
Thu (16/10) | 16 Oct 2025 | P20 NB upchainage |  | Lifter shifted. Anchoring in progress
Thu (16/10) | 16 Oct 2025 | P19 SB |  | 6th pair stressing completed. Preparation to dismantle stressing cage
Thu (16/10) | 16 Oct 2025 | S3 1st pair |  | Wet stitching casting completed
Thu (16/10) | 16 Oct 2025 | S1 |  | Side formwork installation in progress
Thu (16/10) | 16 Oct 2025 | P2 |  | Falsework erection stopped for the day
Thu (16/10) | 16 Oct 2025 | DR4 |  | Install hoarding panels and secure back the site
Thu (16/10) | 16 Oct 2025 | P21 upchainage |  | Segment adjusting continue. 1030 pm surveyor to take reading for YWL confirmation
Thu (16/10) | 16 Oct 2025 | P20 |  | Preparation for crane assembly to shift lifter from P19, NB
Thu (16/10) | 16 Oct 2025 | P19 SB 6th pair |  | Strand pulling for tensioning
Thu (16/10) | 16 Oct 2025 | P16 |  | Scaffold access erection for segment 2nd stage tensioning
Thu (16/10) | 16 Oct 2025 | B2-40 |  | Excavation in progress
Thu (16/10) | 16 Oct 2025 | BR26 |  | Bottom rebar works & preparing for RGT installation
Thu (16/10) | 16 Oct 2025 | B2-43 |  | No activity
Fri (17/10) | 17 Oct 2025 | BR22 |  | Clearing soil at dwall side, BR12: Bracing for deckposts on progress. Target to complete by today
Fri (17/10) | 17 Oct 2025 | Exit 2 |  | Disposal works ongoing
Fri (17/10) | 17 Oct 2025 | BR11 | GL13-16 | Once bracing for deckposts at BR12 complete, BR11 can proceed for casting
Fri (17/10) | 17 Oct 2025 | BR9 | GL16-18.5 | Rebar works in progress
Fri (17/10) | 17 Oct 2025 | S3 |  | Falsework erection for segment launching ongoing
Fri (17/10) | 17 Oct 2025 | S1 |  | Preparation for Crosshead rebar installation. To start rebar works in the afternoon
Fri (17/10) | 17 Oct 2025 | B2-43 |  | No activity
Fri (17/10) | 17 Oct 2025 | B2-48 |  | Planning to start excavation later
Fri (17/10) | 17 Oct 2025 | P4 |  | Falsework fully dismantled
Fri (17/10) | 17 Oct 2025 | P2 |  | Falsework erection works
Fri (17/10) | 17 Oct 2025 | P1 |  | ERSS extraction works ongoing
Fri (17/10) | 17 Oct 2025 | BR7B/8B | Soil ramp | Partial casting done last night
Fri (17/10) | 17 Oct 2025 | Exit 1 waler |  | No activity
Fri (17/10) | 17 Oct 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Fri (17/10) | 17 Oct 2025 | BR11 |  | Final inspection in progress
Fri (17/10) | 17 Oct 2025 | BR22 |  | Currently no activity
Fri (17/10) | 17 Oct 2025 | BR9 |  | Rebar works and barricade installation in progress
Fri (17/10) | 17 Oct 2025 | Z4 LP107F |  | MPI completed, bitumen wrapping ongoing
Fri (17/10) | 17 Oct 2025 | 800mm BV |  | 1st lift wall rebar tying ongoing, pending inspection prior to fwk closure
Fri (17/10) | 17 Oct 2025 | P1 |  | ERSS extraction continue
Fri (17/10) | 17 Oct 2025 | BR7 |  | Continue casting for ramp access
Fri (17/10) | 17 Oct 2025 | P50 |  | No activity, P49: struts alr disconnected, preparing for lifting work
Fri (17/10) | 17 Oct 2025 | S1 crosshead |  | Bottom bar installation started
Fri (17/10) | 17 Oct 2025 | P47 |  | Utility support welding work ongoing
Fri (17/10) | 17 Oct 2025 | P45 |  | S2 excavation ongoing
Fri (17/10) | 17 Oct 2025 | P20 |  | SB downchainage lifter installation
Fri (17/10) | 17 Oct 2025 | P21 |  | 1st pair 2nd adjustment in progress
Fri (17/10) | 17 Oct 2025 | P43 |  | Side fwk removal ongoing
Fri (17/10) | 17 Oct 2025 | Exit 1 waler area |  | No activity
Fri (17/10) | 17 Oct 2025 | B2-48 |  | Excavation in progress (1 exc op)
Fri (17/10) | 17 Oct 2025 | P42 |  | 1st lift column casting ongoing, P41: 1st lift working platform done
Fri (17/10) | 17 Oct 2025 | B2-43 |  | No activity
Fri (17/10) | 17 Oct 2025 | B2-40 |  | Excavation in progress (1 excavator, 1 telescopic)
Fri (17/10) | 17 Oct 2025 | BR26 |  | Bottom rebar works in progress
Fri (17/10) | 17 Oct 2025 | BR27 |  | CJ roughening ongoing
Fri (17/10) | 17 Oct 2025 | P43 crosshead |  | Side formwork dismantling completed
Fri (17/10) | 17 Oct 2025 | P45 |  | S2 excavation no more activity
Fri (17/10) | 17 Oct 2025 | P48 |  | 3rd layer caison SB side to continue formwork closing after dinner break
Fri (17/10) | 17 Oct 2025 | P1 |  | ERSS extraction completed. Housekeeping in progress
Fri (17/10) | 17 Oct 2025 | P2 |  | Falsework leg frame unloading. Tonight to install balance leg frame at the middle
Fri (17/10) | 17 Oct 2025 | S1 crosshead |  | Scaffold support erection for top bars installation
Fri (17/10) | 17 Oct 2025 | P17 |  | Crosshead 2nd stage tensioning completed. Scaffold access dismantling
Fri (17/10) | 17 Oct 2025 | P20 |  | 3/4 lifter shifted
Fri (17/10) | 17 Oct 2025 | P21 |  | 1st pair Segment adjustment ongoing
Fri (17/10) | 17 Oct 2025 | P19 to P20 |  | Crane setting up for lifter shifting from P19 to P20
Fri (17/10) | 17 Oct 2025 | B2-40 |  | Continues excavation & soil disposal
Fri (17/10) | 17 Oct 2025 | BR26 |  | Bottom bar installation is in progress
Sat (18/10) | 18 Oct 2025 | BR19A |  | Continue clearing mixed soil hardcore and platform preparation prior to handover for CGW capping beam construction
Sat (18/10) | 18 Oct 2025 | BR22 |  | Rebar cutting ongoing, KTC no activity
Sat (18/10) | 18 Oct 2025 | Exit 2 |  | Soil trimming and clearing works. In the meantime, WH also preparing access near the hoarding and will link this access to the IW at exit 2 for monitoring works
Sat (18/10) | 18 Oct 2025 | BR11 | GL13-16 | Casting in progress
Sat (18/10) | 18 Oct 2025 | P1 |  | LE continue send out steel plates. Vibro will demob today
Sat (18/10) | 18 Oct 2025 | BR12 |  | Bracing for deckposts completed. Today plan to complete kingpost endplate welding works
Sat (18/10) | 18 Oct 2025 | BR9 | GL16-18.5 | Continue rebar works and shearlinks installation
Sat (18/10) | 18 Oct 2025 | Exit 1 new ecm pond area |  | No activity
Sat (18/10) | 18 Oct 2025 | Gate 7 | for TOL area | Side rebar & formwork works for water pipe protection to facilitate ramp construction
Sat (18/10) | 18 Oct 2025 | CCE4 |  | No other activity. P41 column works ongoing, RS: Soil disposal ongoing
Sat (18/10) | 18 Oct 2025 | B2-48 |  | No activity. Operator out in the morning for some matters, will come back afternoon
Sat (18/10) | 18 Oct 2025 | B2-43 |  | No activity
Sat (18/10) | 18 Oct 2025 | B2-41 |  | Excavation in progress (1 exc op, 1 telescopic)
Sat (18/10) | 18 Oct 2025 | BR26 |  | Rebar works in progress
Sat (18/10) | 18 Oct 2025 | P45 |  | Excavation for 2nd layer caisson
Sat (18/10) | 18 Oct 2025 | P48 |  | Caisson formwork closing. Tomorrow to cast
Sat (18/10) | 18 Oct 2025 | DR3 |  | Base plate installation and welding for UKP
Sat (18/10) | 18 Oct 2025 | P49 |  | Crane set up to remove all S1 struts
Sat (18/10) | 18 Oct 2025 | P51 |  | Prepare platform for JGP
Sat (18/10) | 18 Oct 2025 | 800mm dia water pipe laying |  | Backfilling. Premix on the way to reinstate the area
Sat (18/10) | 18 Oct 2025 | P43 |  | Formwork removal and materials clearing
Sat (18/10) | 18 Oct 2025 | P42 |  | Column first lift cast
Sat (18/10) | 18 Oct 2025 | P41 |  | Rebar work for column first lift
Sat (18/10) | 18 Oct 2025 | P1 |  | Continue send out steel plates
Sat (18/10) | 18 Oct 2025 | P2 |  | Bracing installation for falsework
Sat (18/10) | 18 Oct 2025 | CCW2 |  | Excavation in progress (4 excavators, 1 telescopic)
Sat (18/10) | 18 Oct 2025 | CCW1 |  | Excavation in progress (2 excavators, 1 telescopic)
Sat (18/10) | 18 Oct 2025 | Exit 3 |  | Endplate for struts completed. Tmr to complete strutting
Sat (18/10) | 18 Oct 2025 | Exit 3 |  | Continue exposing couplers at entrance slab
Sat (18/10) | 18 Oct 2025 | BR22 |  | Continue rebar cutting. Worker currently on teabreak
Sat (18/10) | 18 Oct 2025 | Exit 2 |  | Access installation to IW in progress
Sat (18/10) | 18 Oct 2025 | BR11 | GL13-16 | Casting completed. Total vol: 1193m3. Power float works ongoing
Sat (18/10) | 18 Oct 2025 | BR9 | GL16-18.5 | Continue rebar and shearlinks installation. Start to install partial formwork. Target to cast next week
Sat (18/10) | 18 Oct 2025 | S1 |  | Preparation for working platform and crosshead top rebar work
Sat (18/10) | 18 Oct 2025 | S3 |  | Tendom wire pulling and continue falsework for segment launching
Sat (18/10) | 18 Oct 2025 | BR19A |  | Lean con casting at capping beam area
Sat (18/10) | 18 Oct 2025 | 800mm dia water pipe |  | Premix reinstatement done. Ley Choon today end work early
Sat (18/10) | 18 Oct 2025 | Exit 1 waler |  | Formwork removal ongoing
Sat (18/10) | 18 Oct 2025 | B2-41 |  | Excavation in progress (2 exc, 1 telescopic)
Sat (18/10) | 18 Oct 2025 | BR26 |  | Rebar works in progress
Sat (18/10) | 18 Oct 2025 | B2-48 |  | No activity
Sat (18/10) | 18 Oct 2025 | B2-43 |  | No activity
Sat (18/10) | 18 Oct 2025 | P51 |  | JGP 1 point grouting done
Sat (18/10) | 18 Oct 2025 | P49 |  | S1 strut removal completed
Sat (18/10) | 18 Oct 2025 | P48 |  | Continue removal of materials for caisson casting
Sat (18/10) | 18 Oct 2025 | DR3 |  | Current status of base plate installation
Sat (18/10) | 18 Oct 2025 | P45 |  | Excavation done around 30%
Sat (18/10) | 18 Oct 2025 | P20 |  | Adjusting of lifting cage and P21: tendom pipe installation and prepare for segment adjustment
Sat (18/10) | 18 Oct 2025 | CCW2 B1-05 |  | Excavation in progress (3 excavators, 1 telescopic)
Sat (18/10) | 18 Oct 2025 | P17 |  | Scaffold access dismantling
Sat (18/10) | 18 Oct 2025 | CCW1 |  | Excavation in progress (2 exc)
Sat (18/10) | 18 Oct 2025 | Exit 3 |  | Entrance slab coupler exposing
Sat (18/10) | 18 Oct 2025 | Exit 3 |  | Hirose preparing endplate installation for struts
Sat (18/10) | 18 Oct 2025 | S1 |  | Current status of crosshead rebar work. Lifting of rebar work in progress
Sat (18/10) | 18 Oct 2025 | S3 |  | Scaffold erection for segment launching
Sat (18/10) | 18 Oct 2025 | P2 |  | Steel plate laying and falsework erection for crosshead
Tue (21/10) | 21 Oct 2025 | N6 |  | Bearing stump rebar and Formwork closing ongoing. Today to cast
Tue (21/10) | 21 Oct 2025 | S3 |  | Falsework installation for segment launching and Formwork dismantling for 1st pair wet stitching
Tue (21/10) | 21 Oct 2025 | S1 |  | Crosshead rebar works in progress. To cast this week
Tue (21/10) | 21 Oct 2025 | P2 |  | Falsework erection works
Tue (21/10) | 21 Oct 2025 | P1 |  | Preparation for column rebar cage fabrication
Tue (21/10) | 21 Oct 2025 | DR3 |  | Stage 1 utility support welding done
Tue (21/10) | 21 Oct 2025 | Stage 2 |  | Current status of excavation
Tue (21/10) | 21 Oct 2025 | P45 |  | Excavation for 2nd layer caisson. Left to trim around caisson
Tue (21/10) | 21 Oct 2025 | P41 |  | Column 1st stage rebar work
Tue (21/10) | 21 Oct 2025 | 800mm dia water pipe |  | Continue ERSS for pipe laying
Tue (21/10) | 21 Oct 2025 | 800mm Dia BV |  | Wall formwork closing work
Tue (21/10) | 21 Oct 2025 | DR4 |  | Preparing for pipe sleeves installation for instrumentation work
Tue (21/10) | 21 Oct 2025 | P20 |  | No activity
Tue (21/10) | 21 Oct 2025 | N6 |  | Concrete on site for stump casting
Tue (21/10) | 21 Oct 2025 | Zone 2 |  | Overall housekeeping and tidy up materials
Tue (21/10) | 21 Oct 2025 | S1 |  | Crosshead rebar work
Tue (21/10) | 21 Oct 2025 | P2 |  | Preparation for working platform installation
Tue (21/10) | 21 Oct 2025 | Near P3 |  | Prepare for noise balloon installatiom
Wed (22/10) | 22 Oct 2025 | 800mm dia BV |  | Working platform erection & wall fwk tightening ongoing, target for wall fwk inspection this afternoon
Wed (22/10) | 22 Oct 2025 | BR26 |  | Rebar installation in progress, target to cast it by this week
Wed (22/10) | 22 Oct 2025 | 800mm dia |  | Continue excavation work for water pipe installation
Wed (22/10) | 22 Oct 2025 | P49 |  | Fwk erection for LSS
Wed (22/10) | 22 Oct 2025 | P51 |  | JGP completed, machinery & soil disposal in progress prior to handover to LECE for soldier pile work
Wed (22/10) | 22 Oct 2025 | B2-41 |  | Ongoing excavation & soil disposal
Wed (22/10) | 22 Oct 2025 | P21 |  | Preparation for stitching formwork closing
Wed (22/10) | 22 Oct 2025 | B2-43 |  | No activity
Wed (22/10) | 22 Oct 2025 | P45 |  | Continue excavation for S2
Wed (22/10) | 22 Oct 2025 | N4-N5 |  | Segment 2nd stage tensioning
Wed (22/10) | 22 Oct 2025 | N2 |  | Scaffold erection for segment launching
Wed (22/10) | 22 Oct 2025 | B2-48 |  | Excavation & soil disposal is in progress
Wed (22/10) | 22 Oct 2025 | P43 |  | WH clearing materials
Wed (22/10) | 22 Oct 2025 | P42 |  | No activity as of now
Wed (22/10) | 22 Oct 2025 | P41 |  | Column 1st stage rebar will completed today. Friday to cast
Wed (22/10) | 22 Oct 2025 | Exit 1 / RTSA Land |  | Ongoing rebar & formwork installation for water pipe protection
Wed (22/10) | 22 Oct 2025 | BR9 |  | Planning to cast it later, final inspection has cleared
Wed (22/10) | 22 Oct 2025 | BR12 |  | Hacking of overcast Dwall is in progress
Wed (22/10) | 22 Oct 2025 | S1-1 / B1-03 |  | Excavation & soil disposal is in progress
Wed (22/10) | 22 Oct 2025 | Exit 3 |  | Ongoing installation of diagonal strut (DS2-1)
Wed (22/10) | 22 Oct 2025 | P2 |  | Working platform assembly. To install tonight
Wed (22/10) | 22 Oct 2025 | P2 |  | C-channel installation
Wed (22/10) | 22 Oct 2025 | P1 |  | Column rebar cage assembly
Wed (22/10) | 22 Oct 2025 | P49 |  | Formwork closing for LSS backfilling
Wed (22/10) | 22 Oct 2025 | P51 |  | JGP grouting completed
Wed (22/10) | 22 Oct 2025 | P48 |  | S2 layer strut installation by LE in progress
Wed (22/10) | 22 Oct 2025 | DR3 |  | 5 workers exposing services to provide support
Wed (22/10) | 22 Oct 2025 | S1 |  | Main rebar for crosshead done. Tomorrow to start shear link
Wed (22/10) | 22 Oct 2025 | P1 |  | Column rebar cage fabrication
Wed (22/10) | 22 Oct 2025 | Zone4 - PW800 pipe Laying Progress Update |  | Date : 22/10/2025 (D/S), Contractor : CHIN KUAN, Location:Near SIA, Chainage: CH302.7 - 293.4, Pipe laying today :, PW 800 ~ 9.3m (1 Full pipe(7.5m + 1.8m short pipe ), Total As of today / Overall:, PW 800: 97.4m / 478m
Thu (23/10) | 23 Oct 2025 | 800mm dia water pipe laying |  | Day shift no activity. Ley Choon will work night shift at SIA access. Approval received from SIA
Thu (23/10) | 23 Oct 2025 | BR22 |  | Welding ongoing for 2nd layer bracing
Thu (23/10) | 23 Oct 2025 | BR12 |  | Partial debonding sheet laid and preparing for rebar works, CJ roughening at BR10, Continue clearing some soil and materials
Thu (23/10) | 23 Oct 2025 | N4-N5 |  | Segment 2nd stage stressing
Thu (23/10) | 23 Oct 2025 | P6 |  | Drain wall rebar works
Thu (23/10) | 23 Oct 2025 | P45 |  | KTC continue excavation for 2nd layer caisson
Thu (23/10) | 23 Oct 2025 | DR3 |  | Exposing of service to install utility support. Plan to install main beam today
Thu (23/10) | 23 Oct 2025 | DR3 |  | Now high tide. No coring work
Thu (23/10) | 23 Oct 2025 | P48 |  | S2 strut installation
Thu (23/10) | 23 Oct 2025 | P49 |  | Plan for LSS backfilling tomorrow
Thu (23/10) | 23 Oct 2025 | P51 |  | Continue send out soil
Thu (23/10) | 23 Oct 2025 | P1 column rebar cage |  | Removal of scaffold support. Today to install corbel rebars
Thu (23/10) | 23 Oct 2025 | BR12 |  | Continue debonding sheet laying, CJ exposing
Thu (23/10) | 23 Oct 2025 | BR7 area |  | Rectifying access platform
Thu (23/10) | 23 Oct 2025 | Exit 1/ Gate 7 |  | Water pipe protection side wall cast
Thu (23/10) | 23 Oct 2025 | Near exit 1 | RTSA land | Preparing hoarding frame installation
Thu (23/10) | 23 Oct 2025 | P21 |  | Segment adjustment works ongoing
Thu (23/10) | 23 Oct 2025 | P1 |  | Column Rebar cage fabrication
Thu (23/10) | 23 Oct 2025 | B1-05/Below P24 |  | Currently only clearing soil
Thu (23/10) | 23 Oct 2025 | CCW1 |  | Continue excavation
Thu (23/10) | 23 Oct 2025 | B1-03 |  | Access installation in progress
Thu (23/10) | 23 Oct 2025 | P45 |  | Excavation for 2nd layer caison continue
Thu (23/10) | 23 Oct 2025 | BR19A |  | Currently no activity
Thu (23/10) | 23 Oct 2025 | BR12 |  | Continue rebar works & cast lean concrete at the next section
Thu (23/10) | 23 Oct 2025 | BR22 |  | Continue bracing works. Target to complete tonight
Thu (23/10) | 23 Oct 2025 | P48 |  | S2 strut installation until 9pm
Thu (23/10) | 23 Oct 2025 | Zone 1 |  | P1, P2 and P3 no more activity, P2: working platform installation to continue at Engineering hours
Thu (23/10) | 23 Oct 2025 | B2-48 |  | No activity
Thu (23/10) | 23 Oct 2025 | B2-43 |  | No activity
Thu (23/10) | 23 Oct 2025 | P18-19 |  | Stressing cage material for LG unloading
Thu (23/10) | 23 Oct 2025 | B2-41 |  | Current extent of excavation. No planned night shift here due to no operators
Thu (23/10) | 23 Oct 2025 | BR26 |  | Continue rebar works and partial formwork closing
Thu (23/10) | 23 Oct 2025 | P20 |  | Spreader beam lowering for unloading of segment tonight
Fri (24/10) | 24 Oct 2025 | BR12 |  | Continue rebar works. Now shifting rebars, Next half of area still clearing materials. Target finish clearing and lean concrete this week
Fri (24/10) | 24 Oct 2025 | BR7A opening |  | Start to excavate
Fri (24/10) | 24 Oct 2025 | P49 |  | Pump car on site for LSS backfilling
Fri (24/10) | 24 Oct 2025 | P51 |  | Exposing services to check on the corridor. Probing to be done also
Fri (24/10) | 24 Oct 2025 | P45 |  | Preparing to diver access to five way for excavation
Fri (24/10) | 24 Oct 2025 | DR3 |  | Today to complete exposing services
Fri (24/10) | 24 Oct 2025 | DR3 |  | Status of main beam installation and exposing the last UKP at P46 area
Fri (24/10) | 24 Oct 2025 | DR3 existing |  | High tide. So, GCE pause the work
Fri (24/10) | 24 Oct 2025 | P48 |  | All struts fit up done S2 level. To continue welding work
Fri (24/10) | 24 Oct 2025 | S3 |  | Waiting for cube test results to proceed with tensioning
Fri (24/10) | 24 Oct 2025 | P20 SB 2nd pair segmen |  | Installation of railing and preparation for load test
Sat (25/10) | 25 Oct 2025 | CCW1 |  | Continues excavation & soil disposal
Sat (25/10) | 25 Oct 2025 | P41 |  | Column 2nd lift to cast today
Sat (25/10) | 25 Oct 2025 | P43 |  | Crosshead Stressing preparation works ongoing
Sat (25/10) | 25 Oct 2025 | BR22 |  | Bracing installation completed, KTC will continue excavation after Hirose clearing of their materials
Sat (25/10) | 25 Oct 2025 | BR12 |  | Bottom bar installation is in progress
Sat (25/10) | 25 Oct 2025 | P45 |  | NB side preparation for 2nd layer cassion rebar works. Soil trimming ongoing
Sat (25/10) | 25 Oct 2025 | DR3-P47 |  | KTC levelling works ongoing
Sat (25/10) | 25 Oct 2025 | P48 |  | S2 struts welding works in progress
Sat (25/10) | 25 Oct 2025 | BR7A Opening |  | Excavation to concourse in progress
Sat (25/10) | 25 Oct 2025 | P51 |  | LE preparation for ERSS preboring works. Today to start preboring
Sat (25/10) | 25 Oct 2025 | Zone 4 |  | 800mm dia water pipe laying day shift no activity. Ley Choon will work night shift
Sat (25/10) | 25 Oct 2025 | BR26 |  | Continues shearlinks & formwork installation, target to cast today
Sat (25/10) | 25 Oct 2025 | B2-41 |  | Continues excavation & soil disposal
Sat (25/10) | 25 Oct 2025 | B2-48 |  | No activity due to no operator
Sat (25/10) | 25 Oct 2025 | B2-43 |  | No activity due to no operator
Sat (25/10) | 25 Oct 2025 | P1 |  | Column rebar works in progress
Sat (25/10) | 25 Oct 2025 | P3 crosshead |  | Concrete cover surface hacking ongoing
Sat (25/10) | 25 Oct 2025 | P2 |  | Preparation for jack and bottom Formwork installation works
Sat (25/10) | 25 Oct 2025 | RTSA land near gate 7 |  | Hoarding installation is in progress
Sat (25/10) | 25 Oct 2025 | P6 |  | Drain wall formworks installation ongoing
Sat (25/10) | 25 Oct 2025 | S1 |  | Crosshead cast yesterday
Sat (25/10) | 25 Oct 2025 | S3 D/U 02 |  | Tendon strands installation for stressing works
Sat (25/10) | 25 Oct 2025 | P20 D/U 02 |  | Tendon strands installation for stressing works
Sat (25/10) | 25 Oct 2025 | CCW1 |  | Continues excavation & soil disposal
Sat (25/10) | 25 Oct 2025 | S1-1 / B1-05 |  | Excavation is in progress
Sat (25/10) | 25 Oct 2025 | P41 |  | 1st lift column casting ongoing
Sat (25/10) | 25 Oct 2025 | P44 & P43 |  | No activity
Sat (25/10) | 25 Oct 2025 | P45 |  | KTC Preparation to lower down mini excavator for 2nd layer excavation at SB side. Rebar installation ongoing for completed 2nd layer NB side
Sat (25/10) | 25 Oct 2025 | BR22 |  | Resumed excavation and soil disposal
Sat (25/10) | 25 Oct 2025 | BR12 |  | Continues rebar installation
Sat (25/10) | 25 Oct 2025 | P47 |  | Coring for JGP pipe sleeve installation in progress
Sat (25/10) | 25 Oct 2025 | P48 |  | Continue welding for S2 strutting works
Sat (25/10) | 25 Oct 2025 | P51 |  | Preparation (surveying and marking) for ERSS preboring works
Sat (25/10) | 25 Oct 2025 | BR7A Opening |  | Continues excavation to concourse level
Sat (25/10) | 25 Oct 2025 | BR26 |  | Cleaning in progress, will call for final inspection once shearlink is done
Sat (25/10) | 25 Oct 2025 | B2-41 |  | Continue excavation and soil disposal
Sat (25/10) | 25 Oct 2025 | P1 |  | Continue column rebar securing works. Tmr to start Formwork closing
Sat (25/10) | 25 Oct 2025 | P2 |  | Jack installation for bottom Formwork ongoing
Sat (25/10) | 25 Oct 2025 | P3 |  | Concrete surface hacking works ongoing at SB side
Sat (25/10) | 25 Oct 2025 | P6 |  | Drain Wall formwork closing
Sat (25/10) | 25 Oct 2025 | S3 |  | Falsework erection for segment launching
Sat (25/10) | 25 Oct 2025 | S3 Segment D/U 02 |  | Stressing works ongoing
Sat (25/10) | 25 Oct 2025 | P20 D/U 02 |  | Stressing completed for SB side. Now stressing ongoing for NB side
Sat (25/10) | 25 Oct 2025 | B1-03 |  | Continues excavation
Mon (27/10) | 27 Oct 2025 | P51 |  | 1st soldier pile installed. 2nos preboring done
Mon (27/10) | 27 Oct 2025 | P3 crosshead |  | Hacking to expose main bars continue
Mon (27/10) | 27 Oct 2025 | S3 |  | Segment 3rd pair stressing completed, Scaffold erection for 4th pair launching
Mon (27/10) | 27 Oct 2025 | P48 |  | MPI test done. KTC will lower down excavator to continue excavation
Mon (27/10) | 27 Oct 2025 | P20 |  | Stressing cage dismantling, tonight to launch 4th pair segment at SB
Mon (27/10) | 27 Oct 2025 | P21 |  | 1st pair segment stitching formwork closing, Upchainage: 90% completed, Downchainage: 40% completed, Plan to cast tmr night
Mon (27/10) | 27 Oct 2025 | P48 |  | Concrete on site for 2nd layer caisson casting
Mon (27/10) | 27 Oct 2025 | DR3 |  | Current status of utility support installation
Mon (27/10) | 27 Oct 2025 | DR3 |  | Preparing for JGP work
Mon (27/10) | 27 Oct 2025 | BR7A opening | B2-29 | Excavation in progress (1 telescopic, 1 exc)
Mon (27/10) | 27 Oct 2025 | P43 |  | Preparing for stressing work. No crack observed on crosshead as of now
Mon (27/10) | 27 Oct 2025 | B2-48 |  | No activity
Mon (27/10) | 27 Oct 2025 | B2-43 |  | No activity
Mon (27/10) | 27 Oct 2025 | B2-41 |  | Excavation in progress (3 exc, 1 telescopic)
Mon (27/10) | 27 Oct 2025 | P20 |  | Preparation for tonight segment launching. Plan for 2nos here tonight
Mon (27/10) | 27 Oct 2025 | S3 |  | Crane set up. Tonight plan to launch two segments here. Total 4 segments tonight
Mon (27/10) | 27 Oct 2025 | CCW2 |  | B1-05, B1-06 excavation in progress
Mon (27/10) | 27 Oct 2025 | Exit 3 B1-03 |  | No activity
Mon (27/10) | 27 Oct 2025 | P4 |  | Cleaning at the side of crosshead
Mon (27/10) | 27 Oct 2025 | P1 |  | Cleaning of side formwork for closing
Mon (27/10) | 27 Oct 2025 | BR22 |  | Start to lay debonding sheet
Mon (27/10) | 27 Oct 2025 | BR12 |  | Continue rebar works, Have informed WH to provide additional lighting within the working area
Mon (27/10) | 27 Oct 2025 | P2 |  | Status of wingform and soffit plywood laying
Mon (27/10) | 27 Oct 2025 | P1 |  | Column formwork closing
Mon (27/10) | 27 Oct 2025 | BR7A |  | Activity stopped for the day
Mon (27/10) | 27 Oct 2025 | BR8B area |  | Balance decking panels installation
Mon (27/10) | 27 Oct 2025 | Exit 1 |  | No activity
Mon (27/10) | 27 Oct 2025 | B2-48 |  | No activity
Mon (27/10) | 27 Oct 2025 | B2-43 |  | No activity
Mon (27/10) | 27 Oct 2025 | B2-41, B2-40 |  | Excavation in progress
Mon (27/10) | 27 Oct 2025 | P45 |  | 2nd layer caisson casting
Mon (27/10) | 27 Oct 2025 | Receiving shaft/P42 area |  | Current status
Wed (29/10) | 29 Oct 2025 | P50 & P49 |  | No activity
Wed (29/10) | 29 Oct 2025 | P51 |  | One lane closure ongoing, last probing point pending GCE (2/3 done)
Wed (29/10) | 29 Oct 2025 | DR3 |  | Utility support welding work ongoing towards P46 side
Wed (29/10) | 29 Oct 2025 | P45 | South | Continue excavation work
Wed (29/10) | 29 Oct 2025 | P43 |  | Stressing completed, platform dismantling ongoing
Wed (29/10) | 29 Oct 2025 | P42 |  | Backfilling status
Wed (29/10) | 29 Oct 2025 | P41 |  | Current status
Wed (29/10) | 29 Oct 2025 | P21 |  | Formwork closing for 1st pair wet stitching. Today to cast
Wed (29/10) | 29 Oct 2025 | P21 |  | Premix hacking for cutting down of soil level ongoing
Wed (29/10) | 29 Oct 2025 | P20 |  | Tendon strand installation for stressing in progress
Wed (29/10) | 29 Oct 2025 | P20 |  | Stressing cage assembly works for P21
Wed (29/10) | 29 Oct 2025 | N2 |  | Falsework erection ongoing
Wed (29/10) | 29 Oct 2025 | P7 |  | Drain wall rebar installation
Wed (29/10) | 29 Oct 2025 | S3 |  | Scaffold erection for stressing preparation works
Wed (29/10) | 29 Oct 2025 | P3 |  | Concrete surface hacking works ongoing at both sides
Wed (29/10) | 29 Oct 2025 | P2 |  | Scaffold erection for Crosshead rebar works
Wed (29/10) | 29 Oct 2025 | P1 |  | Preparation for 2nd lift column casting. Today to cast
Wed (29/10) | 29 Oct 2025 | P1 column |  | Casting in progress
Wed (29/10) | 29 Oct 2025 | P51 |  | Preparing to start 1st point probing. Total 3nos balance to do. 3nos did previously
Wed (29/10) | 29 Oct 2025 | BR19A |  | Capping beam rebar works in progress (Wendyng)
Wed (29/10) | 29 Oct 2025 | P3 crosshead |  | Hacking to expose main bars continue. 45% completed
Wed (29/10) | 29 Oct 2025 | BR22 |  | Rebar works in progress, BR12: Continue rebar and shearlinks installation, Target to cast both roof slabs this Saturday
Wed (29/10) | 29 Oct 2025 | BR7A opening | B2-29 | Excavation in progress
Wed (29/10) | 29 Oct 2025 | Decking area at BR8 |  | Hirose replacing temporary barricades with VIG. Installation works ongoing
Wed (29/10) | 29 Oct 2025 | B2-42 |  | Excavation & soil disposal is in progress
Wed (29/10) | 29 Oct 2025 | B2-41 |  | Started exposing of couplers
Wed (29/10) | 29 Oct 2025 | S1 crosshead |  | Formwork dismantling
Wed (29/10) | 29 Oct 2025 | N2 |  | Scaffold platform installation for segment launching
Wed (29/10) | 29 Oct 2025 | P19 |  | Strand pushing for segment 2nd stage tensioning
Wed (29/10) | 29 Oct 2025 | P21 |  | Stressing cage assembly
Wed (29/10) | 29 Oct 2025 | P20 |  | Lifter shifting for 5th pair launching tonight at SB
Wed (29/10) | 29 Oct 2025 | P21 |  | Wet stitching preparation for casting
Wed (29/10) | 29 Oct 2025 | P45 |  | 2nd layer caisson excavation completed. Trimming below caisson for rebar work. Caisson casting done around 50% for this layer
Wed (29/10) | 29 Oct 2025 | DR3 |  | Utility support welding with 6 welders
Wed (29/10) | 29 Oct 2025 | DR3 existing drain |  | Now low tide. Bring down equipment for coring
Wed (29/10) | 29 Oct 2025 | B2-43 |  | No activity
Wed (29/10) | 29 Oct 2025 | CCE4 Linkway |  | Erecting of falsework is in progress
Wed (29/10) | 29 Oct 2025 | P43 |  | Lowering down materials for falsework dismantling
Wed (29/10) | 29 Oct 2025 | P21 |  | Stitching work
Wed (29/10) | 29 Oct 2025 | P20 |  | Tonight plan for two segments lauching. S3: 1 segment launching. Total 3nos
Wed (29/10) | 29 Oct 2025 | P24 TB |  | Hacking ongoing for downhang wall rebar works
Wed (29/10) | 29 Oct 2025 | S1 |  | Crosshead formwork removal
Wed (29/10) | 29 Oct 2025 | P1 |  | Column casting completed
Wed (29/10) | 29 Oct 2025 | P2 |  | Crosshead rebar work
Wed (29/10) | 29 Oct 2025 | BR19A capping beam area |  | Activity done for the day
Wed (29/10) | 29 Oct 2025 | BR22 |  | Continue rebar works, Hirose expediting additional welding works for decking area, BR12: Continue shearlinks installation
Wed (29/10) | 29 Oct 2025 | BR7A opening | B2-29 | Activity done for the day. No planned night shift here yet
Wed (29/10) | 29 Oct 2025 | CCE4 linkway area |  | Falsework installation in progress for BR32 works
Wed (29/10) | 29 Oct 2025 | B2-43 |  | No activity
Wed (29/10) | 29 Oct 2025 | B2-41 |  | Current status. No planned night shift here
Wed (29/10) | 29 Oct 2025 | B2-42 |  | Continue night shift excavation works here
Wed (29/10) | 29 Oct 2025 | DR3 |  | Exposing crossing utility for support
Wed (29/10) | 29 Oct 2025 | P48 |  | Tonight KTC arrange for excavation
Wed (29/10) | 29 Oct 2025 | P45 |  | Lean concrete done. This week to complete 100% of 2nd layer caisson
Wed (29/10) | 29 Oct 2025 | Receiving shaft/P42 area |  | Continue backfilling works
Wed (29/10) | 29 Oct 2025 | Exit 2 |  | Preparing access to capping beam area, Exposing guidewall and slope trimming. Tmr plan for lean con casting
Thu (30/10) | 30 Oct 2025 | P20 SB D/U 05 |  | Tendon Strand installation for stressing works ongoing
Thu (30/10) | 30 Oct 2025 | P21 |  | Premix removal ongoing for upcoming segment launching
Thu (30/10) | 30 Oct 2025 | P21 |  | Wet stitching cast yesterday
Thu (30/10) | 30 Oct 2025 | BR7A opening | B2-29 | Excavation in progress
Thu (30/10) | 30 Oct 2025 | P45 |  | Rebar lower down to complete balance rebar work for caisson
Thu (30/10) | 30 Oct 2025 | DR3 |  | Working platform erection for balance welding work
Thu (30/10) | 30 Oct 2025 | P48 |  | Continue excavation for caisson
Thu (30/10) | 30 Oct 2025 | P51 |  | Discussion before continue with ERSS work
Thu (30/10) | 30 Oct 2025 | S3 |  | Tendon strand installation for D/U 05
Thu (30/10) | 30 Oct 2025 | S1 |  | Crosshead Formwork dismantling
Thu (30/10) | 30 Oct 2025 | P3 |  | Surface hacking works ongoing for both sides of crosshead
Thu (30/10) | 30 Oct 2025 | P2 |  | Crosshead rebar installation
Thu (30/10) | 30 Oct 2025 | P1 |  | Column cast yesterday
Thu (30/10) | 30 Oct 2025 | BR22 |  | Continue rebar works, column starter bar installation and start installing partial formwork, Hirose to continue welding works at deckposts, BR12:, Continue shearlinks installation, column starter bar works and cleaning ongoing, Welding at deckposts completed
Thu (30/10) | 30 Oct 2025 | B2-42 |  | Excavation & soil disposal is in progress
Thu (30/10) | 30 Oct 2025 | B2-41 |  | Exposing of couplers almost complete, today target to lean con
Thu (30/10) | 30 Oct 2025 | P20 |  | Stressing completed for SB D/U 05
Thu (30/10) | 30 Oct 2025 | P20 |  | Stressing cage assembly ongoing
Thu (30/10) | 30 Oct 2025 | BR7A opening | B2-29 | Continue excavation
Thu (30/10) | 30 Oct 2025 | Exit 2 | GL16 capping beam area | Currently no activity. CGW manpower focus at BR12 and BR22
Thu (30/10) | 30 Oct 2025 | S3 |  | Stressing completed. Strand cutting ongoing
Thu (30/10) | 30 Oct 2025 | S1 |  | Side Formwork dismantled
Thu (30/10) | 30 Oct 2025 | B2-43 |  | No activity
Thu (30/10) | 30 Oct 2025 | CCE4 |  | Ongoing backfilling work between P42 and P41
Thu (30/10) | 30 Oct 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Thu (30/10) | 30 Oct 2025 | P3 |  | Continue surface hacking works at both sides
Thu (30/10) | 30 Oct 2025 | P2 |  | Crosshead rebar installation ongoing
Thu (30/10) | 30 Oct 2025 | BR32 |  | Straightening of the rebar & exposing of couplers
Thu (30/10) | 30 Oct 2025 | P51 |  | 10/17nos soldier piles installed as of now. Open back the road to public. Tomorrow to resume
Thu (30/10) | 30 Oct 2025 | P45 |  | Strut end welding and balance caisson rebar work
Thu (30/10) | 30 Oct 2025 | DR3 |  | Utility support welding work
Thu (30/10) | 30 Oct 2025 | P48 |  | Excavation for next layer caisson
Thu (30/10) | 30 Oct 2025 | BR22 |  | Continue rebar works, BR12:, Continue rebar and shearlinks installation, Cleaning works ongoing, Hirose continue welding works at deckposts
Fri (31/10) | 31 Oct 2025 | Exit 2 | GL15-GL14 | Slope trimming and hacking of guidewall, Exit 2 GL16: Capping beam area currently no activity
Fri (31/10) | 31 Oct 2025 | BR32B |  | Roughening of CJ & continue exposing of couples
Fri (31/10) | 31 Oct 2025 | B2-42 |  | Continue excavation & soil disposal
Fri (31/10) | 31 Oct 2025 | B2-41 |  | Leaned con last night & continue exposing of couplers
Fri (31/10) | 31 Oct 2025 | B2-43 |  | No activity
Fri (31/10) | 31 Oct 2025 | CCE4 |  | Continue backfilling btw P42 and P41
Fri (31/10) | 31 Oct 2025 | B2-29 |  | Continue excavation, (1 telescopic, inside only 1 ripper op, 1 exc currently not used)
Fri (31/10) | 31 Oct 2025 | BR12 |  | Shearlinks installation and cleaning ongoing, BR22:, Shearlinks and barricades installation, Cleaning in progress, Hirose continue welding works at deckposts. Only balance at this BR, Target to cast both roof slabs tmr evening
Fri (31/10) | 31 Oct 2025 | BR19A capping beam |  | Hyrib mesh & formwork installation. Plan for casting today
Fri (31/10) | 31 Oct 2025 | 800mm dia water pipe laying |  | Tonight to continue with exposing services and ERSS work
Fri (31/10) | 31 Oct 2025 | Exit 2 | GL15-14 | Guidewall hacking, Exit 2 GL16: No activity
Fri (31/10) | 31 Oct 2025 | B2-29 |  | Continue excavation
Fri (31/10) | 31 Oct 2025 | CCE4 |  | Continue backfilling works
Fri (31/10) | 31 Oct 2025 | B2-41 |  | Surface cleaning ongoing before laying debonding sheet
Fri (31/10) | 31 Oct 2025 | BR19A capping beam |  | Currently no activity
Fri (31/10) | 31 Oct 2025 | BR9 |  | Floodwall formwork installation in progress
Fri (31/10) | 31 Oct 2025 | BR22, BR12 |  | Shearlinks installation and cleaning ongoing
Fri (31/10) | 31 Oct 2025 | P51 |  | Continue soldier pile installation. Two watchman provided near live road
Fri (31/10) | 31 Oct 2025 | DR3 |  | LE continue welding of utility support. 4 welders
Fri (31/10) | 31 Oct 2025 | P48 |  | Continue excavation for 4th layer caisson
Fri (31/10) | 31 Oct 2025 | P45 |  | Balance caisson formwork closing. This week to complete
Fri (31/10) | 31 Oct 2025 | P43 |  | Now no activity. Will dismantle falsework once P42 is ready for crosshead work
Sat (01/11) | 01 Nov 2025 | BR22 |  | Shearlinks installation, BR12: Plan for final inspection with BR22 today
Sat (01/11) | 01 Nov 2025 | P51 |  | Ground levelling, preparing for steel plate installation. Target to complete all soldier pile works by Monday
Sat (01/11) | 01 Nov 2025 | P48 |  | Excavation to 4th layer caisson
Sat (01/11) | 01 Nov 2025 | DR3 |  | Utility support installation work completed, today MPI test..excavation on going
Sat (01/11) | 01 Nov 2025 | P45 |  | Caisson formwork closing completed. Concrete ordered, going to cast today
Sat (01/11) | 01 Nov 2025 | Exit 2 | GL15-14 | Clearing hardcore and preparing access for IW monitoring, GL16 capping beam: No activity
Sat (01/11) | 01 Nov 2025 | B2-29 |  | Excavation in progress (1exc, 1 telescopic)
Sat (01/11) | 01 Nov 2025 | P43 |  | Hoisting down scaffold material and housekeeping
Sat (01/11) | 01 Nov 2025 | P20 |  | PT strand pushing
Sat (01/11) | 01 Nov 2025 | N2 |  | Falsework installation in progress
Sat (01/11) | 01 Nov 2025 | Exit 1 |  | Platform preparation and reinstating access to IW
Sat (01/11) | 01 Nov 2025 | CCE4 |  | Backfilling in progress till P41 column area
Sat (01/11) | 01 Nov 2025 | BR32B |  | Rebar planting in progress
Sat (01/11) | 01 Nov 2025 | B2-43 |  | No activity
Sat (01/11) | 01 Nov 2025 | B2-41 |  | Rebar planting and drilling ongoing, Continue debonding sheet laying
Sat (01/11) | 01 Nov 2025 | B2-42 |  | Excavation in progress (currently 1 ripper op, 1 exc, 1 telescopic)
Sat (01/11) | 01 Nov 2025 | P12 |  | Scaffolding erection
Sat (01/11) | 01 Nov 2025 | S3 |  | No activity
Sat (01/11) | 01 Nov 2025 | S1 |  | Crosshead formwork dismantling
Sat (01/11) | 01 Nov 2025 | P3 |  | Continue surface hacking works at both sides
Sat (01/11) | 01 Nov 2025 | Exit 3 B1-03 |  | No activity
Sat (01/11) | 01 Nov 2025 | P2 |  | Crosshead rebar installation
Sat (01/11) | 01 Nov 2025 | P1 |  | No activity
Sat (01/11) | 01 Nov 2025 | CCW1 | south side | Continue S4 excavation (2 exc, 1 telescopic)
Sat (01/11) | 01 Nov 2025 | Beside P24 |  | Dwall surface hacking ongoing
Sat (01/11) | 01 Nov 2025 | B1-05, B1-06 |  | Continue excavation
Sat (01/11) | 01 Nov 2025 | P21 |  | Preparation work for stressing..pier post concrete surface grinding..Hacking and excavation near P21 areas for crane parking
Sat (01/11) | 01 Nov 2025 | P20 |  | Preparation for stressing work
Sat (01/11) | 01 Nov 2025 | N2 |  | Falsework installation in progress
Sat (01/11) | 01 Nov 2025 | S1 |  | Crosshead formwork dismantling
Sat (01/11) | 01 Nov 2025 | BR19A |  | Currently no activity. Pending casting
Sat (01/11) | 01 Nov 2025 | BR12, BR22 |  | Final inspection in progress
Sat (01/11) | 01 Nov 2025 | B2-29 |  | Continue excavation
Sat (01/11) | 01 Nov 2025 | CCE4 |  | Continue backfilling works
Sat (01/11) | 01 Nov 2025 | BR32B |  | Preparing to start bottom rebar works
Sat (01/11) | 01 Nov 2025 | B2-43 |  | No activity. Excavator hoist up
Sat (01/11) | 01 Nov 2025 | B2-41 |  | Continue rebar planting
Sat (01/11) | 01 Nov 2025 | B2-42 |  | Continue excavation (2 exc, 1 ripper working), Reminded WH to install ventilation fans at this side
Sat (01/11) | 01 Nov 2025 | P3 |  | Continue surface hacking works at both sides
Sat (01/11) | 01 Nov 2025 | P2 |  | Crosshead rebar installation
Sat (01/11) | 01 Nov 2025 | P51 |  | Soldier pile steel plate installation ongoing
Sat (01/11) | 01 Nov 2025 | P48 |  | Current excavation status
Sat (01/11) | 01 Nov 2025 | P47 |  | Pipe sleeve installation for JGP
Sat (01/11) | 01 Nov 2025 | P45 |  | Last section for L2 caisson casting on going
Sat (01/11) | 01 Nov 2025 | BR12, BR22 |  | 3nos pump trucks getting ready for casting
Sat (01/11) | 01 Nov 2025 | Exit 2 | GL15 | Continue guidewall hacking and clearing hardcore, GL16 capping beam: No activity
Sat (01/11) | 01 Nov 2025 | DR3 |  | Mini excavator maintenance work ongoing..utility support welding works ongoing
Sat (01/11) | 01 Nov 2025 | CCW1 |  | S4 excavation in progress (1 telescopic, 1 exc currently working)
Sat (01/11) | 01 Nov 2025 | P24 TB |  | Dwall surface roughening in progress for downhang wall
Sat (01/11) | 01 Nov 2025 | CCW2 B1-05, B1-06 |  | Excavation in progress (3 exc, 1 telescopic)
Sat (01/11) | 01 Nov 2025 | BR19A capping beam |  | Plan for casting today
Mon (03/11) | 03 Nov 2025 | P50 |  | Utility support ongoing
Mon (03/11) | 03 Nov 2025 | P48 |  | Excavated to 4th layer caisson ongoing
Mon (03/11) | 03 Nov 2025 | P47 |  | Coring work for JGP ongoing
Mon (03/11) | 03 Nov 2025 | DR3 |  | Continue utility support welding
Mon (03/11) | 03 Nov 2025 | P20 |  | Stressing cage dismantling in progress, P21: Stressing in progress. Tonight to dismantle SH and shift to P12
Mon (03/11) | 03 Nov 2025 | 800mm dia water pipe |  | Partially backfilling done
Mon (03/11) | 03 Nov 2025 | P12 |  | Scaffold access for SH installation and segment launching complete
Mon (03/11) | 03 Nov 2025 | P42 |  | Column prefab work ongoing
Mon (03/11) | 03 Nov 2025 | B1-05 & B1-06 |  | 3 excavators onsite, 2 operators working <This message was edited>
Mon (03/11) | 03 Nov 2025 | S2 |  | Excavation in progress for falsework foundation. To cast today
Mon (03/11) | 03 Nov 2025 | P51 |  | Utility support removal
Mon (03/11) | 03 Nov 2025 | P51 |  | Steel plate installed
Mon (03/11) | 03 Nov 2025 | P3 crosshead hacking |  | P2 side 70% completed
Mon (03/11) | 03 Nov 2025 | P3 crosshead hacking |  | P4 side, 95% completed.. today to complete
Mon (03/11) | 03 Nov 2025 | B2-29 |  | Excavation in progress (1 exc op, 1 telescopic)
Mon (03/11) | 03 Nov 2025 | P3 |  | Crosshead PT duct installation in progress. Steel anchors completed
Mon (03/11) | 03 Nov 2025 | P47 |  | JGP rig maintenance
Mon (03/11) | 03 Nov 2025 | P48 |  | Excavation and pile head hacking
Mon (03/11) | 03 Nov 2025 | Exit 1 |  | Excavation started yesterday for B2-49. Currently machine hydraulic hose damaged
Mon (03/11) | 03 Nov 2025 | BR32B |  | Rebar works in progress
Mon (03/11) | 03 Nov 2025 | P42 |  | Column rebar cage fabrication
Mon (03/11) | 03 Nov 2025 | B2-43 |  | No activity
Mon (03/11) | 03 Nov 2025 | B2-41 |  | Rebar works in progress
Mon (03/11) | 03 Nov 2025 | B2-42 |  | Preparing for lean concrete today, Exposing couplers, Installing lights along working area
Mon (03/11) | 03 Nov 2025 | B2-40 |  | Excavation in progress (2 exc ops)
Mon (03/11) | 03 Nov 2025 | P21 |  | Will remove stressing cage at down chainage tonight
Mon (03/11) | 03 Nov 2025 | S2 |  | Concrete ordered for lean concrete for crosshead falsework
Mon (03/11) | 03 Nov 2025 | CCW1 |  | North side: Clearing stockpile, South side: S4 preparing for lean concrete works
Mon (03/11) | 03 Nov 2025 | P24 TB |  | Downhang wall rebar works in progress
Mon (03/11) | 03 Nov 2025 | B1-05, B1-06 |  | Continue excavation. Informed WH electrician to install additional lighting below
Mon (03/11) | 03 Nov 2025 | BR19A capping beam |  | Formwork dismantled
Mon (03/11) | 03 Nov 2025 | B2-29 |  | Activity done for the day. No planned night shift here yet
Mon (03/11) | 03 Nov 2025 | Exit 1 |  | Tonight olan to continue excavation here (2 exc, 1 telescopic), 1 more operator at RS
Mon (03/11) | 03 Nov 2025 | BR32B |  | Rebar works in progress
Mon (03/11) | 03 Nov 2025 | B2-41 |  | Rebar works current status
Mon (03/11) | 03 Nov 2025 | B2-42 |  | Preparing for lean concrete works
Mon (03/11) | 03 Nov 2025 | B2-40 |  | No activity. Currently excavators hoist up
Mon (03/11) | 03 Nov 2025 | P21 |  | Preparing for stressing cages dismantling
Mon (03/11) | 03 Nov 2025 | S2 |  | BRC placing for lean concrete
Mon (03/11) | 03 Nov 2025 | S2 |  | Ducting work by WH
Mon (03/11) | 03 Nov 2025 | P1 |  | Cement patch up at tie rod holes
Tue (04/11) | 04 Nov 2025 | Exit 2 | GL13 | Continue hacking guidewall, GL16 capping beam: Today plan for as-built survey for couplers and straighten the coupler bars
Tue (04/11) | 04 Nov 2025 | B2-29 |  | Continue excavation (1 exc op, 1 telescopic)
Tue (04/11) | 04 Nov 2025 | B2-49 |  | Excavation in progress (1 exc op, 1 ripper)
Tue (04/11) | 04 Nov 2025 | BR32B |  | Rebar works in progress
Tue (04/11) | 04 Nov 2025 | P2 crosshead |  | PT duct installation continue
Tue (04/11) | 04 Nov 2025 | P50 |  | Continue utility support removal
Tue (04/11) | 04 Nov 2025 | B2-29 |  | Excavation in progress
Tue (04/11) | 04 Nov 2025 | DR3 |  | Continue balance welding for utility support
Tue (04/11) | 04 Nov 2025 | DR3 |  | Excavation at utility free area
Tue (04/11) | 04 Nov 2025 | P47 |  | Pipe sleeves installation for JGP work
Tue (04/11) | 04 Nov 2025 | P48 |  | Excavation done around 70%. Balance to hack bored pile and trimming
Tue (04/11) | 04 Nov 2025 | B2-49 |  | Excavation ongoing (1 ripper, 1 exc, 1 telescopic)
Tue (04/11) | 04 Nov 2025 | P12 |  | Shifting of stressing cage
Tue (04/11) | 04 Nov 2025 | CCE4 |  | Current access at +2
Tue (04/11) | 04 Nov 2025 | B2-43 |  | No activity
Tue (04/11) | 04 Nov 2025 | BR32B |  | Rebar works in progress
Tue (04/11) | 04 Nov 2025 | B2-41 |  | Rebar works in progress
Tue (04/11) | 04 Nov 2025 | B2-42 |  | Base lean con was done last night. Now continue exposing couplers
Tue (04/11) | 04 Nov 2025 | P45 |  | Will resume excavation after cube strength achieve
Tue (04/11) | 04 Nov 2025 | P42 |  | Rebar cage fabrication for column
Tue (04/11) | 04 Nov 2025 | P43& P44 |  | Current status
Tue (04/11) | 04 Nov 2025 | P18 |  | Installation of access for bearing stump casting
Tue (04/11) | 04 Nov 2025 | P21 |  | Starter hanger dismantling
Tue (04/11) | 04 Nov 2025 | S2 |  | Falsework erection for crosshead
Tue (04/11) | 04 Nov 2025 | P20 |  | Grinding and cleaning around crosshead
Tue (04/11) | 04 Nov 2025 | P1 |  | Now no activity
Tue (04/11) | 04 Nov 2025 | P2 |  | Painting around formwork support area. To continue ducting work
Tue (04/11) | 04 Nov 2025 | P45 |  | Will resume excavation once cube result achieve
Tue (04/11) | 04 Nov 2025 | DR3 |  | Continue welding of utility support
Tue (04/11) | 04 Nov 2025 | DR3 |  | Continue clearing hardcore
Tue (04/11) | 04 Nov 2025 | P48 |  | Pile head hacking
Tue (04/11) | 04 Nov 2025 | P51 |  | Soldier piles and steel plate installed
Wed (05/11) | 05 Nov 2025 | P21 |  | Preparation for PLT for crane parking to launch upchainage
Wed (05/11) | 05 Nov 2025 | P20 |  | Shifting of LF to P21
Wed (05/11) | 05 Nov 2025 | P50 |  | Current status of support removal
Wed (05/11) | 05 Nov 2025 | P51 |  | Balance 1 soldier pile and 2 UKP to complete. One lane closed
Wed (05/11) | 05 Nov 2025 | P45 |  | KTC resume excavation for next layer caisson
Wed (05/11) | 05 Nov 2025 | DR3 |  | Continue excavation at utility free area
Wed (05/11) | 05 Nov 2025 | P47 |  | Rig maintenance done. Settling paper work to resume JGP grouting
Wed (05/11) | 05 Nov 2025 | P48 |  | Pile head hacking at TPE bound. HSL mobilize mini for pile head hacking at Changi bound
Wed (05/11) | 05 Nov 2025 | DR3 |  | Rebar delivery for drain diversion work
Wed (05/11) | 05 Nov 2025 | B2-29 |  | Alternate access installation ongoing. Excavation temporarily stopped
Wed (05/11) | 05 Nov 2025 | B2-49 |  | Excavation in progress
Wed (05/11) | 05 Nov 2025 | BR32B |  | Rebar works in progress
Wed (05/11) | 05 Nov 2025 | B2-41 |  | Rebar works in progress
Wed (05/11) | 05 Nov 2025 | P42 |  | Continue column rebar cage fabrication
Wed (05/11) | 05 Nov 2025 | N2 |  | Bearing stump formwork closing
Wed (05/11) | 05 Nov 2025 | S2 |  | Falsework erection, working platform only balance plywood laying
Wed (05/11) | 05 Nov 2025 | P3 |  | Hacking to expose rebar remaining about 15% to complete at P2 side
Wed (05/11) | 05 Nov 2025 | P21 |  | 1 no. of LF shifting from P20 completed. Installation ongoing
Wed (05/11) | 05 Nov 2025 | N2 |  | Bearing stump formwork closing
Wed (05/11) | 05 Nov 2025 | S3 |  | Excavation for ecm pond extension ongoing
Wed (05/11) | 05 Nov 2025 | S2 Crosshead |  | Scaffold erection in progress
Wed (05/11) | 05 Nov 2025 | P3 |  | Continue hacking and rebar exposing at p2 side. P4 side - drilling works ongoing
Wed (05/11) | 05 Nov 2025 | P51 |  | Soldier pile and steel plates installation done as per latest ERSS drawing. Tomorrow to start UKP work. Next week start excavation
Wed (05/11) | 05 Nov 2025 | P2 |  | Crosshead tendon duct installation
Wed (05/11) | 05 Nov 2025 | B2-29 |  | New access installation still in progress
Wed (05/11) | 05 Nov 2025 | B2-49 |  | Excavation in progress (2 exc ops, 1 telescopic)
Wed (05/11) | 05 Nov 2025 | BR32B |  | Rebar works in progress
Wed (05/11) | 05 Nov 2025 | B2-43 |  | No activity
Wed (05/11) | 05 Nov 2025 | B2-41 |  | Rebar works in progress
Wed (05/11) | 05 Nov 2025 | B2-42 |  | Exposing dwall couplers, Dongah preparing for dwall rectification works. 4 locations to be done
Wed (05/11) | 05 Nov 2025 | Exit 2 |  | GL14: Hacking dwall to COL, GL16 capping beam area: Straightening coupler bars
Wed (05/11) | 05 Nov 2025 | P48 |  | Pile head hacking at TPE bounf almost done
Wed (05/11) | 05 Nov 2025 | P50 |  | Utility support removal
Wed (05/11) | 05 Nov 2025 | DR3 |  | All utility support welding done. Current status of excavation
Wed (05/11) | 05 Nov 2025 | P45 |  | Continue excavation for 3rd layer caisson
Wed (05/11) | 05 Nov 2025 | CCW1 | north side | Soil disposal ongoing
Wed (05/11) | 05 Nov 2025 | B1-05 |  | Currently no hacking works, B1-06: Continue excavation and disposal works
Wed (05/11) | 05 Nov 2025 | BR17 opening |  | Started excavation just now. Currently activity done for the day
Wed (05/11) | 05 Nov 2025 | S2 |  | Preparing for wingform closing
Wed (05/11) | 05 Nov 2025 | P17 |  | Cleaning and grinding around column
Wed (05/11) | 05 Nov 2025 | Exit 2 |  | Slope lean concreting ongoing
Wed (05/11) | 05 Nov 2025 | BR22 |  | CJ roughening. Now activity done for the day, housekeeping ongoing
Wed (05/11) | 05 Nov 2025 | B2-29 |  | No more activity for the day
Wed (05/11) | 05 Nov 2025 | P2 |  | Tomorrow WH will handover half of the area to Wendyng for formwork closing
Wed (05/11) | 05 Nov 2025 | B2-49 |  | Nightshift continue excavation (3 exc, 1 telescopic)
Wed (05/11) | 05 Nov 2025 | CCE4/P42 area |  | Platform preparation
Wed (05/11) | 05 Nov 2025 | BR32B |  | Activity done for the day. No planned night work here tonight
Wed (05/11) | 05 Nov 2025 | B2-41 |  | Nightshift to continue rebar works here. Dayshift team already ended work
Wed (05/11) | 05 Nov 2025 | B2-42 |  | Drop area casting ongoing
Wed (05/11) | 05 Nov 2025 | B2-43 |  | No activity
Thu (06/11) | 06 Nov 2025 | P51 |  | Shifting of materials to start UKP work
Thu (06/11) | 06 Nov 2025 | P51 |  | Start boring for UKP
Thu (06/11) | 06 Nov 2025 | B2-29 |  | Excavation in progress (1 exc, 1 telescopic working)
Thu (06/11) | 06 Nov 2025 | B2-42 |  | Dwall rectification work is in progress
Thu (06/11) | 06 Nov 2025 | B2-43 |  | No activity
Thu (06/11) | 06 Nov 2025 | BR32B |  | Continues rebar installation work
Thu (06/11) | 06 Nov 2025 | P21 |  | Soil clearing and preparation for crane parking for segment launching today
Thu (06/11) | 06 Nov 2025 | P19 |  | Scaffold access dismantling
Thu (06/11) | 06 Nov 2025 | B2-49 |  | Ongoing excavation & soil disposal by 3 Excavators + 1 Telescopic
Thu (06/11) | 06 Nov 2025 | N2 |  | Bearing stump formwork closing
Thu (06/11) | 06 Nov 2025 | P48 |  | HSL hacking pile head at Changi bound. WH trimming at TPE bound
Thu (06/11) | 06 Nov 2025 | P47 |  | JGP grouting resume
Thu (06/11) | 06 Nov 2025 | DR3 |  | Continue excavation
Thu (06/11) | 06 Nov 2025 | P45 |  | Plan to complete excavation and lean con for 3rd layer caisson by Saturday
Thu (06/11) | 06 Nov 2025 | P2 Crosshead |  | Platform preparation for Formwork installation
Thu (06/11) | 06 Nov 2025 | P3 |  | Hacking and rebar exposing at p2 side, today to complete. P4 side - drilling works ongoing
Thu (06/11) | 06 Nov 2025 | P2 |  | Tendon duct installation works at NB side
Thu (06/11) | 06 Nov 2025 | P42 |  | Continue column rebar cage fabrication
Thu (06/11) | 06 Nov 2025 | B2-29 |  | Excavation in progress
Thu (06/11) | 06 Nov 2025 | B2-49 |  | Excavation in progress
Thu (06/11) | 06 Nov 2025 | P47 |  | 1st point JGP grouting done
Thu (06/11) | 06 Nov 2025 | P48 |  | Continue pile head hacking
Thu (06/11) | 06 Nov 2025 | P51 |  | 1st UKP boring done. 2nd UKP boring in progress
Thu (06/11) | 06 Nov 2025 | P45 |  | Continue excavation at TPE bound
Thu (06/11) | 06 Nov 2025 | DR3 |  | Continue excavation at utility free area
Thu (06/11) | 06 Nov 2025 | B2-41 |  | Continues rebar installation work
Fri (07/11) | 07 Nov 2025 | BR32B |  | Continues rebar work & target to cast it tomorrow
Fri (07/11) | 07 Nov 2025 | B2-41 |  | Shearlink installation is in progress, target to cast it by this week
Fri (07/11) | 07 Nov 2025 | B2-42 |  | Dwall rectification in progress, plan to lay debonding sheet follow by rebar work today
Fri (07/11) | 07 Nov 2025 | P21 |  | Preparation for load test
Fri (07/11) | 07 Nov 2025 | B2-43 |  | No activity
Fri (07/11) | 07 Nov 2025 | B2-49 |  | Ongoing excavation & soil disposal by 3 excavators & 1 telescopic
Fri (07/11) | 07 Nov 2025 | P51 |  | 2nos UKP installed. Left one to complete
Fri (07/11) | 07 Nov 2025 | P50 |  | No activity
Fri (07/11) | 07 Nov 2025 | P49 |  | No activity
Fri (07/11) | 07 Nov 2025 | P48 |  | Shifting access and bored pile hacking at north side
Fri (07/11) | 07 Nov 2025 | DR3 |  | Excavation to FEL in progress
Fri (07/11) | 07 Nov 2025 | P14-P15 |  | Preparation for mid span Formwork closing
Fri (07/11) | 07 Nov 2025 | N2 |  | Bearing stump Formwork closing
Fri (07/11) | 07 Nov 2025 | S1 |  | Crosshead Surface grinding ongoing
Fri (07/11) | 07 Nov 2025 | S2 |  | Wingform Formwork installed yesterday
Fri (07/11) | 07 Nov 2025 | Exit 1 |  | Current stockpile @ new ECM pond
Fri (07/11) | 07 Nov 2025 | P3 |  | Hacking of concrete surface at P2 side ongoing
Fri (07/11) | 07 Nov 2025 | P3 |  | Top and bottom drilling in progress at p4 side
Fri (07/11) | 07 Nov 2025 | P2 |  | Shear links installation at NB side and tendon duct installation at SB side
Fri (07/11) | 07 Nov 2025 | GL16 capping beam |  | Part 3 CB start rebar works (4+1)
Fri (07/11) | 07 Nov 2025 | B2-29, B2-30 |  | Excavation in progress (1 exc, 1 telescopic), 1 more excavator inside currently not in used
Fri (07/11) | 07 Nov 2025 | BR8 |  | Temporary stockpile status
Fri (07/11) | 07 Nov 2025 | P21 |  | Load test completed. Now preparing to launch segment SB U02
Fri (07/11) | 07 Nov 2025 | S2 |  | Pier column hacking works
Fri (07/11) | 07 Nov 2025 | S1 |  | Surface grinding ongoing
Fri (07/11) | 07 Nov 2025 | P3 |  | P4 side - continue drilling works
Fri (07/11) | 07 Nov 2025 | P3 |  | P2 side - Concrete surface hacking in progress
Fri (07/11) | 07 Nov 2025 | P51 |  | Preboring for UKP (last point)
Fri (07/11) | 07 Nov 2025 | P50 |  | Removal of utility support
Fri (07/11) | 07 Nov 2025 | P48 |  | (North) excavation and bored pile hacking
Fri (07/11) | 07 Nov 2025 | P47 |  | JGP grouting
Fri (07/11) | 07 Nov 2025 | DR3 |  | Excavation to FEL
Fri (07/11) | 07 Nov 2025 | P45 |  | Excavation to L3 caisson layer
Fri (07/11) | 07 Nov 2025 | P2 |  | Continue rebar and tendon ducts installation
Sat (08/11) | 08 Nov 2025 | P42 |  | Column rebar cage fabrication ongoing
Sat (08/11) | 08 Nov 2025 | P43 & P44 |  | No activity
Sat (08/11) | 08 Nov 2025 | P45 |  | No activity. KTC manpower currently at DR3 & P48
Sat (08/11) | 08 Nov 2025 | DR3 |  | Excavation to FEL
Sat (08/11) | 08 Nov 2025 | P47 |  | JGP grouting for P47-22
Sat (08/11) | 08 Nov 2025 | P48 |  | (North) 4th layer excavation ongoing
Sat (08/11) | 08 Nov 2025 | P49-P51 |  | No activity
Sat (08/11) | 08 Nov 2025 | P4 |  | Crosshead rebar installation ongoing
Sat (08/11) | 08 Nov 2025 | P3 |  | Hacking and drilling current status. No activity due to WH safety campaign. Work to resume in the afternoon
Sat (08/11) | 08 Nov 2025 | S2 |  | No activity
Sat (08/11) | 08 Nov 2025 | P14-P15 |  | Mid span Formwork closing ongoing
Sat (08/11) | 08 Nov 2025 | P21 |  | Strands installation for SB D/U 2 and load test for NB D 02 completed
Sat (08/11) | 08 Nov 2025 | P42 |  | Column rebar cage installation and lapping ongoing
Sat (08/11) | 08 Nov 2025 | DR3 |  | Continue excavation to FEL
Sat (08/11) | 08 Nov 2025 | P47 |  | JGP grouting completed for P47-22
Sat (08/11) | 08 Nov 2025 | P48, 4th layer |  | Continue excavation at NB side, SB side rebar works ongoing
Sat (08/11) | 08 Nov 2025 | P3 |  | P2 side continue hacking works. Today to finish
Sat (08/11) | 08 Nov 2025 | P3 |  | P4 side drilling works ongoing
Sat (08/11) | 08 Nov 2025 | P2 |  | Continue rebar and tendon duct installation
Sat (08/11) | 08 Nov 2025 | P14-P15 |  | Continue Formwork closing for NB mid span
Sat (08/11) | 08 Nov 2025 | P19 |  | Scaffold erection ongoing
Sat (08/11) | 08 Nov 2025 | P21 |  | Stressing completed for SB D/U 02
Mon (10/11) | 10 Nov 2025 | P2 crosshead |  | PT duct inspection for section 2 and 3 scheduled at 6pm. Tonight to install links. Est cast by Friday night
Mon (10/11) | 10 Nov 2025 | P12 |  | Toe board installation. Dry pack cast for SH installation
Mon (10/11) | 10 Nov 2025 | P21 |  | NB: 3rd pair stressing in progress, SB: LF shifting for 4th pair installation tonight
Mon (10/11) | 10 Nov 2025 | P51 |  | Last point UKP preboring completed, going to cast today
Mon (10/11) | 10 Nov 2025 | P48 |  | (south) L4 caisson formwork closing
Mon (10/11) | 10 Nov 2025 | P45 |  | No activity
Mon (10/11) | 10 Nov 2025 | DR3 |  | Excavation to FEL
Mon (10/11) | 10 Nov 2025 | P21 |  | No activity. SB ready for 4th pair installation tonight
Mon (10/11) | 10 Nov 2025 | P12 |  | No activity. toe board installation complete
Mon (10/11) | 10 Nov 2025 | S2 |  | No activity
Mon (10/11) | 10 Nov 2025 | P2 |  | Crosshead rebar installation
Mon (10/11) | 10 Nov 2025 | P45 |  | Excavation to L3 caisson level
Mon (10/11) | 10 Nov 2025 | P49 |  | Utility support removal
Mon (10/11) | 10 Nov 2025 | P48 |  | L4 caisson casting at south side
Mon (10/11) | 10 Nov 2025 | DR3 |  | Excavation to FEL level
Mon (10/11) | 10 Nov 2025 | P42 |  | Tonight formwork closing
Mon (10/11) | 10 Nov 2025 | P41 |  | Column rebar fabrication
Tue (11/11) | 11 Nov 2025 | N3-N4 |  | Midspan Formwork closing for stitching works
Tue (11/11) | 11 Nov 2025 | S2 |  | Crosshead rebar to arrive today afternoon
Tue (11/11) | 11 Nov 2025 | P3 |  | Hacking @ SB side and drilling at p4 side in progress
Tue (11/11) | 11 Nov 2025 | P2 |  | Formwork closing and shear links installation at SB side
Tue (11/11) | 11 Nov 2025 | B2-42 |  | Rebar installation is in progress
Tue (11/11) | 11 Nov 2025 | P49 |  | Utility support removal
Tue (11/11) | 11 Nov 2025 | P48 |  | L4 caisson rebar works
Tue (11/11) | 11 Nov 2025 | P47 |  | No activity. Machinary maintenance
Tue (11/11) | 11 Nov 2025 | P45 |  | Excavation to L3 caisson level
Tue (11/11) | 11 Nov 2025 | DR3 |  | 2nd layer excavation
Tue (11/11) | 11 Nov 2025 | B2-43 |  | No activity
Tue (11/11) | 11 Nov 2025 | CCE4/P42 Area |  | Hacking of abandoned sewer manhole
Tue (11/11) | 11 Nov 2025 | B2-49 |  | Levelling in progress & continue soil disposal by 2 excavators & 1 telescopic
Tue (11/11) | 11 Nov 2025 | Exit 1 |  | Current stockpile @ new ECM pond
Tue (11/11) | 11 Nov 2025 | P1 | SB side | Top soil removal for pad footing installation
Tue (11/11) | 11 Nov 2025 | P2 crosshead |  | Section 2 formwork closed. Section 3 links installation in progress
Tue (11/11) | 11 Nov 2025 | P3 crosshead | P4 side | Drilling completed
Tue (11/11) | 11 Nov 2025 | P2 side |  | Drilling started
Tue (11/11) | 11 Nov 2025 | P21 |  | No activity
Tue (11/11) | 11 Nov 2025 | S02 |  | No activity
Tue (11/11) | 11 Nov 2025 | P2 |  | Crosshead links installation
Tue (11/11) | 11 Nov 2025 | P3 |  | No activity
Tue (11/11) | 11 Nov 2025 | P48 |  | No activity
Tue (11/11) | 11 Nov 2025 | P47 |  | JGP work in progress
Tue (11/11) | 11 Nov 2025 | DR3 |  | No activity
Tue (11/11) | 11 Nov 2025 | P45 |  | Excavation to L3 caisson level
Tue (11/11) | 11 Nov 2025 | P41 |  | Column rebar fabrication
Tue (11/11) | 11 Nov 2025 | P42 |  | Column formwork closing
Tue (11/11) | 11 Nov 2025 | Zone 3 today KTC night excavation and soil disposal |  | B1-06 (1 telescopic, 2 excavators), BR19A (1 excavator)
Tue (11/11) | 11 Nov 2025 | P21 |  | SB D/U 4 strands installation for stressing ongoing
Tue (11/11) | 11 Nov 2025 | P20 |  | Scaffold erection ongoing
Wed (12/11) | 12 Nov 2025 | P20 |  | Scaffold access erection fot 2nd stage grouting
Wed (12/11) | 12 Nov 2025 | P47 |  | JGP works ongoing
Wed (12/11) | 12 Nov 2025 | DR3 |  | Excavation to FEL
Wed (12/11) | 12 Nov 2025 | S2 |  | Scaffold working platform erection to start rebar works. Formworks to come in later after P2
Wed (12/11) | 12 Nov 2025 | P42 |  | Column formwork erection
Wed (12/11) | 12 Nov 2025 | B2-49 |  | Continue to dispose the remain soil, lean con. has done for B2-48
Wed (12/11) | 12 Nov 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Wed (12/11) | 12 Nov 2025 | B2-29, B2-30 |  | Excavation in progress
Wed (12/11) | 12 Nov 2025 | P3 crosshead |  | Drilling for starter bar
Wed (12/11) | 12 Nov 2025 | Exit 1 Linkway |  | Hacking of Dwall is in progress
Wed (12/11) | 12 Nov 2025 | P2 crosshead |  | Section 3 links just completed. Final inspection at 130pm. Formwork closing tonight
Wed (12/11) | 12 Nov 2025 | B2-43 |  | No activity
Wed (12/11) | 12 Nov 2025 | P1 |  | Levelling on going for pad footing installation
Wed (12/11) | 12 Nov 2025 | B2-42 |  | Will continue rebar work after dewatering at the access
Wed (12/11) | 12 Nov 2025 | B2-29, B2-30 |  | Excavation in progress. Now waiting for lorry for disposal, (2 ops inside, 1 telescopic)
Wed (12/11) | 12 Nov 2025 | BR8 area |  | Temporary soft clay stockpile status
Wed (12/11) | 12 Nov 2025 | B2-43 |  | No activity
Wed (12/11) | 12 Nov 2025 | P2 |  | Crosshead rebar inspection completed. Tonight to continue Formwork closing
Wed (12/11) | 12 Nov 2025 | P3 |  | Hacking at P4 side and Drilling at P2 side ongoing
Wed (12/11) | 12 Nov 2025 | P48 |  | L4 caisson rebar installation
Wed (12/11) | 12 Nov 2025 | P47 |  | JGP works ongoing
Wed (12/11) | 12 Nov 2025 | P45 |  | Excavation to L3 caisson level
Wed (12/11) | 12 Nov 2025 | DR3 |  | Barricade installation and excavation to FEL
Wed (12/11) | 12 Nov 2025 | P14-P15 |  | Continue Formwork closing for midspan
Wed (12/11) | 12 Nov 2025 | P21 |  | Stressing completed for D/U 04
Wed (12/11) | 12 Nov 2025 | P2 |  | Crosshead formwork closing
Wed (12/11) | 12 Nov 2025 | P3 |  | No activity
Wed (12/11) | 12 Nov 2025 | B2-49 |  | Excavation in progress
Wed (12/11) | 12 Nov 2025 | Exit 1 linkway |  | Dwall hacking ongoing
Wed (12/11) | 12 Nov 2025 | B2-41 |  | Formwork removal ongoing
Wed (12/11) | 12 Nov 2025 | B2-42 |  | Currently no activity
Wed (12/11) | 12 Nov 2025 | P19 |  | Strand cable pulling
Wed (12/11) | 12 Nov 2025 | P20 |  | Preparation for segment launching tonight P20 U05/D05
Wed (12/11) | 12 Nov 2025 | BR8 |  | Temporary soft clay stockpile status
Wed (12/11) | 12 Nov 2025 | B2-29, B2-30 |  | Excavation works till 8pm. No planned night shift here
Wed (12/11) | 12 Nov 2025 | Exit 2 |  | Lean concrete cast for working platform completed. Levelling ongoing, Tonight KTC plan for works here (1 exc, 1 telescopic)
Wed (12/11) | 12 Nov 2025 | B1-05, B1-06 |  | Excavation and disposal works ongoing till 8pm. No planned night work here tonight, Lighting provision provided is OK
Wed (12/11) | 12 Nov 2025 | CCW1 | south side | S4 rebar works for struts and walers in progress. Dayshift team working till 10pm. Nightshift team to takeover thereafter (9pax)
Wed (12/11) | 12 Nov 2025 | P48 |  | L4 caisson rebar work ongoing
Wed (12/11) | 12 Nov 2025 | P47 |  | JGP no activity
Wed (12/11) | 12 Nov 2025 | DR3 |  | Excavation to FEL in progress
Wed (12/11) | 12 Nov 2025 | P45 |  | Excavation to L3 caisson level
Wed (12/11) | 12 Nov 2025 | CCW2 |  | South side GL-W5: Waler beams installation in progress, Central: Waler beams installation in progress, North side: Unloaded waler beam, Currently Hirose has finished works for the day. No planned night work here tonight
Wed (12/11) | 12 Nov 2025 | Exit 3 |  | No activity
Wed (12/11) | 12 Nov 2025 | B2-48 |  | Current status
Wed (12/11) | 12 Nov 2025 | B2-29, B2-30 |  | Current status
Wed (12/11) | 12 Nov 2025 | P42 |  | Formwork closing. Tomorrow morning column casting
Wed (12/11) | 12 Nov 2025 | P41 |  | Column rebar fabrication
Wed (12/11) | 12 Nov 2025 | P21 SB 4th pair |  | Strand pushing and preparation for stressing
Thu (13/11) | 13 Nov 2025 | P21 |  | Strand installation for SB D/U 05 stressing works
Thu (13/11) | 13 Nov 2025 | P19 |  | Preparation for stage 2 Crosshead stressing in the afternoon
Thu (13/11) | 13 Nov 2025 | B2-43 |  | No activity
Thu (13/11) | 13 Nov 2025 | B2-41 |  | Dismantling of formwork in progress
Thu (13/11) | 13 Nov 2025 | S2 |  | Scaffold erection for rebar installation. Today to start bottom rebar installation
Thu (13/11) | 13 Nov 2025 | P47 |  | JGP work ongoing
Thu (13/11) | 13 Nov 2025 | DR3 |  | Excavation to FEL
Thu (13/11) | 13 Nov 2025 | P45 |  | Lowering 1 more excavator for bored pile hacking at south side
Thu (13/11) | 13 Nov 2025 | B2-42 |  | Planting for the missing couplers by Dongah
Thu (13/11) | 13 Nov 2025 | B2-42 |  | Continue installing of rebars
Thu (13/11) | 13 Nov 2025 | Exit 1 Linkway |  | Hacking of Dwall to SHD +2m is in progress
Thu (13/11) | 13 Nov 2025 | P3 |  | Continue hacking works at P4 side
Thu (13/11) | 13 Nov 2025 | P2 |  | Formwork closing ongoing. Tmr to cast Crosshead
Thu (13/11) | 13 Nov 2025 | P1 |  | Excavation for pad footing installation
Thu (13/11) | 13 Nov 2025 | B2-49 |  | Levelling and installing of access
Thu (13/11) | 13 Nov 2025 | Exit 1 new ECM pond |  | Current stockpile status
Thu (13/11) | 13 Nov 2025 | P42 |  | Rcolumn ready for casting today
Thu (13/11) | 13 Nov 2025 | P41 |  | Column rebar fabrication
Thu (13/11) | 13 Nov 2025 | B2-29 & B2-30 |  | Ongoing excavation & soil disposal
Fri (14/11) | 14 Nov 2025 | P21 |  | Preparation for stressing NB D/U 05
Fri (14/11) | 14 Nov 2025 | P19 |  | CH Stage 2 stressing completed. Dismantling and shifting materials to P20 for stressing
Fri (14/11) | 14 Nov 2025 | Exit 1 New ECM Pond |  | Exiting stockpile status
Fri (14/11) | 14 Nov 2025 | BR19A |  | Excavation in progress
Fri (14/11) | 14 Nov 2025 | B2-49 |  | Leaning of concrete for base slab
Fri (14/11) | 14 Nov 2025 | B2-42 |  | Continues with rebar installation, target to cast it by 20 Nov
Fri (14/11) | 14 Nov 2025 | B2-43 |  | No activity
Fri (14/11) | 14 Nov 2025 | N2 |  | Falsework installation in progress
Fri (14/11) | 14 Nov 2025 | S2 |  | Crosshead bottom rebar installation
Fri (14/11) | 14 Nov 2025 | P3 |  | Hacking all completed. Drilling at P2 side ongoing
Fri (14/11) | 14 Nov 2025 | P1 |  | Preparing for LSS backfilling
Fri (14/11) | 14 Nov 2025 | P2 |  | Final inspection completed. To cast Crosshead today
Fri (14/11) | 14 Nov 2025 | CCW GL-W5 & CCW middle area |  | Waler beams installed. Pending shear key installation
Fri (14/11) | 14 Nov 2025 | Exit 3 |  | No activity
Fri (14/11) | 14 Nov 2025 | P24 TB downhang wall |  | 2nd lift formwork installation in progress. Target to cast on Monday
Fri (14/11) | 14 Nov 2025 | Exit 2 |  | Continue dwall hacking to COL, Capping beam currently no activity
Fri (14/11) | 14 Nov 2025 | BR19A |  | Excavation in progress (2 exc, 1 telescopic)
Fri (14/11) | 14 Nov 2025 | P48 |  | Formwork closing
Fri (14/11) | 14 Nov 2025 | P47 |  | JGP no working..soil disposal & preparation for coring at existing DR3
Fri (14/11) | 14 Nov 2025 | DR3 |  | Excavation ongoing
Fri (14/11) | 14 Nov 2025 | P45 |  | Excavation ongoing at north, access making at south
Fri (14/11) | 14 Nov 2025 | P1 |  | LSS backfill completed
Fri (14/11) | 14 Nov 2025 | S2 |  | Continue Crosshead bottom rebar works
Fri (14/11) | 14 Nov 2025 | P21 |  | Stressing preparation for NB D/U 05
Fri (14/11) | 14 Nov 2025 | N2 |  | Falswork erection ongoing
Fri (14/11) | 14 Nov 2025 | B2-29, B2-30/31 |  | Excavation in progress (2 exc, 1 telescopic). Now unloading ripper into the opening
Fri (14/11) | 14 Nov 2025 | BR8 |  | Temporary soft clay stockpile status
Fri (14/11) | 14 Nov 2025 | BR5 opening |  | Partial top lean concrete and excavation status. Noted on site that the works started yesterday. Currently no machinery here
Fri (14/11) | 14 Nov 2025 | B2-42 |  | Rebar works in progress
Fri (14/11) | 14 Nov 2025 | CR106 |  | Safety Timeout on *Working at Height.*
Mon (17/11) | 17 Nov 2025 | BR19A |  | Current status of excavation, Rebar cutting in progress, Preparing barricades installation
Mon (17/11) | 17 Nov 2025 | B2-29, B2-30 |  | Excavation in progress (3 exc, 1 telescopic)
Mon (17/11) | 17 Nov 2025 | BR8 |  | Temporary soft clay stockpile status
Mon (17/11) | 17 Nov 2025 | BR25 |  | Excavation in progress (1 exc, 1 telescopic)
Mon (17/11) | 17 Nov 2025 | P50 |  | Good earth backfilling to ground level. Soil from station excavation
Mon (17/11) | 17 Nov 2025 | P21 |  | Shifting of stressing cage to NB D/U 06
Mon (17/11) | 17 Nov 2025 | Zone 2 |  | P14-P15 midspan and N3/N4 midspan to cast tonight
Mon (17/11) | 17 Nov 2025 | P12 |  | Preparation of platform for crane parking for SH installation
Mon (17/11) | 17 Nov 2025 | S2 |  | Continue Crosshead rebar installation
Mon (17/11) | 17 Nov 2025 | P49 |  | Preparing for water pipe cutting and removal. Now started heavy rain
Mon (17/11) | 17 Nov 2025 | BR5 opening |  | Currently no activity
Mon (17/11) | 17 Nov 2025 | DR3 |  | Slope protection casting
Mon (17/11) | 17 Nov 2025 | P45 |  | Base lean concrete
Mon (17/11) | 17 Nov 2025 | P21 |  | Stressing cage installed. Demobing the crane
Mon (17/11) | 17 Nov 2025 | P12 |  | Preparing to install starter hanger. Tonight to install. Tomorrow to launch two segments at NB. Wednesday SB
Mon (17/11) | 17 Nov 2025 | P1 |  | Hardcore laying for cross head falsework
Mon (17/11) | 17 Nov 2025 | P2 |  | Continue curing
Mon (17/11) | 17 Nov 2025 | S2 |  | No activity already
Mon (17/11) | 17 Nov 2025 | S2 |  | Rain water down pipe installation
Mon (17/11) | 17 Nov 2025 | N6 |  | Bearing installation at abudment wall
Tue (18/11) | 18 Nov 2025 | P45 |  | Bend down caisson starter bar for 3rd layer rebar work
Tue (18/11) | 18 Nov 2025 | P21 |  | Stressing completed for NB D/U 06
Tue (18/11) | 18 Nov 2025 | DR3 |  | Now low tide. Preparing for coring work
Tue (18/11) | 18 Nov 2025 | DR3 |  | Current status of excavation. Slower down excavation due to tidy space to store soil at site
Tue (18/11) | 18 Nov 2025 | P45 |  | Started excavation for 5th layer caisson
Tue (18/11) | 18 Nov 2025 | P49 & P50 |  | Quarry dust and soil backfilling at completed pile cap area
Tue (18/11) | 18 Nov 2025 | N6 |  | Bearing pad installation works
Tue (18/11) | 18 Nov 2025 | N2 |  | Falsework erection and bearing pad installation works
Tue (18/11) | 18 Nov 2025 | P12 |  | Starter hanger installation works
Tue (18/11) | 18 Nov 2025 | P12 |  | Premix hacking for levelling works
Tue (18/11) | 18 Nov 2025 | S2 |  | Tendon duct and rebar installation ongoing
Tue (18/11) | 18 Nov 2025 | P1 |  | Base lean concrete for pad footing installation
Tue (18/11) | 18 Nov 2025 | P43 |  | Status of working platform dismantling
Tue (18/11) | 18 Nov 2025 | P42 |  | Column casting was done. P41: column casting by Thursday
Tue (18/11) | 18 Nov 2025 | P40 |  | 1st lift column casting going to start
Tue (18/11) | 18 Nov 2025 | P39 |  | Column 1st stage rebar work. P38: scaffold erection for column 1st stage rebar work
Tue (18/11) | 18 Nov 2025 | P41 |  | Column last lift formwork closing. To cast on Thursday
Tue (18/11) | 18 Nov 2025 | P39 |  | Continue 1st lift column rebar work. To cast by this week
Tue (18/11) | 18 Nov 2025 | P45 |  | Unloading of rebar for 3rd layer caisson work
Tue (18/11) | 18 Nov 2025 | P45 |  | LSS on the way for backfilling at caisson area
Tue (18/11) | 18 Nov 2025 | DR3 |  | Currently no activity. Need to clear the stockpiles
Tue (18/11) | 18 Nov 2025 | P48 |  | Rain stopped. Preparing to resume excavation
Tue (18/11) | 18 Nov 2025 | S2 |  | Now no activity
Tue (18/11) | 18 Nov 2025 | N2 |  | Preparing the platform for segment launching
Tue (18/11) | 18 Nov 2025 | P21 |  | Lowering down materials from completed segments launch area
Tue (18/11) | 18 Nov 2025 | P21 |  | Soil bund making along P21 to prevent rain water flow to CCW
Tue (18/11) | 18 Nov 2025 | P45 |  | LSS backfilling and soil bund making below to prevent LSS flow out
Wed (19/11) | 19 Nov 2025 | DR3 |  | No activity
Wed (19/11) | 19 Nov 2025 | P45 |  | Lowering rebar, rebar works for L3 caisson wall ongoing
Wed (19/11) | 19 Nov 2025 | P47 |  | Soil disposal..JGP no activity
Wed (19/11) | 19 Nov 2025 | P48 |  | Excavation to FEL
Wed (19/11) | 19 Nov 2025 | N2 |  | Falsework erection and preparation for bearing pad installation
Wed (19/11) | 19 Nov 2025 | P12 |  | Segment adjustment for NB/SB U01
Wed (19/11) | 19 Nov 2025 | S2 |  | Shear links installation ongoing
Wed (19/11) | 19 Nov 2025 | P1 |  | LSS backfilling for pad footing completed
Wed (19/11) | 19 Nov 2025 | P3 |  | Post drilling works ongoing
Wed (19/11) | 19 Nov 2025 | P2 |  | Preparing for Formwork dismantling
Wed (19/11) | 19 Nov 2025 | P45 |  | Rebar works for L3 caisson wall
Wed (19/11) | 19 Nov 2025 | P47 |  | JGP works ongoing
Wed (19/11) | 19 Nov 2025 | P48 |  | Excavation to FEL
Wed (19/11) | 19 Nov 2025 | P50 |  | Backfilling in progress
Thu (20/11) | 20 Nov 2025 | N6 |  | Segment jack installation ongoing
Thu (20/11) | 20 Nov 2025 | N2 |  | Bearing pad and Falsework platform installation ongoing
Thu (20/11) | 20 Nov 2025 | P12 |  | Segment adjustment ongoing
Thu (20/11) | 20 Nov 2025 | S2 |  | Rebar and tendon duct installation completed. Pending Formwork closing
Thu (20/11) | 20 Nov 2025 | P3 |  | Drilling in progress at P2 side. Target to finish by this week
Thu (20/11) | 20 Nov 2025 | P2 |  | Preparation for Formwork dismantling
Thu (20/11) | 20 Nov 2025 | P45 |  | L3 caisson rebar works
Thu (20/11) | 20 Nov 2025 | DR3 |  | No activity
Thu (20/11) | 20 Nov 2025 | P47 |  | JGP work in progress
Thu (20/11) | 20 Nov 2025 | P48 |  | Excavation to FEL
Thu (20/11) | 20 Nov 2025 | P49 |  | Quarry dust backfilling
Thu (20/11) | 20 Nov 2025 | N2 |  | Continue bearing pad installation
Thu (20/11) | 20 Nov 2025 | P12 |  | Segment adjustment ongoing
Thu (20/11) | 20 Nov 2025 | P50 |  | Backfilling in progress
Thu (20/11) | 20 Nov 2025 | P48 |  | Excavation to FEL
Thu (20/11) | 20 Nov 2025 | P47 |  | Soil disposal
Thu (20/11) | 20 Nov 2025 | P45 |  | L3 caisson rebar works ongoing
Thu (20/11) | 20 Nov 2025 | P42 |  | Column formwork removal
Thu (20/11) | 20 Nov 2025 | P41 |  | Scaffolding installation in progress
Thu (20/11) | 20 Nov 2025 | P3 |  | Continue drilling works at p2 side
Thu (20/11) | 20 Nov 2025 | P2 |  | Formwork dismantling works ongoing
Fri (21/11) | 21 Nov 2025 | P51 |  | Top soil removal started for utility support installation
Fri (21/11) | 21 Nov 2025 | DR3/P47 |  | Bottom and top slab coring 100% completed. JGP grouting in progress. Balance 20nos to complete within 10 days
Fri (21/11) | 21 Nov 2025 | DR3 |  | Temporary stopped the work to settle disposal issue
Fri (21/11) | 21 Nov 2025 | P45 |  | Clear LSS and continue caisson rebar work. This week to cast around 60% of 3rd layer caisson
Fri (21/11) | 21 Nov 2025 | P49& P50 |  | Soil levelling and backfilling for materials storage
Fri (21/11) | 21 Nov 2025 | N6 |  | Bearing pad and jack installation for segment launching
Fri (21/11) | 21 Nov 2025 | N2 |  | Bearing pad and jack installation completed
Fri (21/11) | 21 Nov 2025 | N2 |  | Continue Falsework erection for segment launching
Fri (21/11) | 21 Nov 2025 | S2 |  | Preparation for side Formwork installation. Formwork shifting from P2 to S2 ongoing
Fri (21/11) | 21 Nov 2025 | P51 |  | Expose to utility support
Fri (21/11) | 21 Nov 2025 | P48 |  | Excavation to FEL. Soil shifting in progress to facilitate crane parking. Going to lower down HSL excavator for pile hacking
Fri (21/11) | 21 Nov 2025 | P47 |  | JGP works in progress
Fri (21/11) | 21 Nov 2025 | DR3 |  | No activity
Fri (21/11) | 21 Nov 2025 | P45 |  | L3 caisson east side formwork closing
Fri (21/11) | 21 Nov 2025 | P36 |  | Falsework erection for column rebar work
Fri (21/11) | 21 Nov 2025 | P37 |  | 1st stage column rebar work done. P37& P38 to cast next week
Fri (21/11) | 21 Nov 2025 | P38 |  | 1st stage column rebar done
Fri (21/11) | 21 Nov 2025 | P41&P42 |  | Both column cast
Fri (21/11) | 21 Nov 2025 | P39 |  | Column closing for column 1st stage. Tomorrow to cast
Fri (21/11) | 21 Nov 2025 | P2 |  | Formwork dismantling
Fri (21/11) | 21 Nov 2025 | Zone 1 |  | Temp footpath to cast tonight
Sat (22/11) | 22 Nov 2025 | P39, P38 |  | Scaffold erection in progress for P39 & P38. P39 1st lift column to cast today
Sat (22/11) | 22 Nov 2025 | P37 and P36 1st lift column |  | No activity
Sat (22/11) | 22 Nov 2025 | P41, P42, P44 |  | No activity
Sat (22/11) | 22 Nov 2025 | P40 |  | No activity
Sat (22/11) | 22 Nov 2025 | P43 |  | Crosshead Falsework dismantling in progress
Sat (22/11) | 22 Nov 2025 | P45 |  | 3rd layer caisson rebar works ongoing
Sat (22/11) | 22 Nov 2025 | DR3 |  | Excavation currently no activity waiting for soil disposal prior to resume
Sat (22/11) | 22 Nov 2025 | P48 |  | BP hacking in progress
Sat (22/11) | 22 Nov 2025 | Zone 4 | 800PW | Backfilling in progress
Sat (22/11) | 22 Nov 2025 | P49 and P50 |  | Backfilking and levelling works
Sat (22/11) | 22 Nov 2025 | P51 |  | Manual excavation to expose utility and utility support
Sat (22/11) | 22 Nov 2025 | N2 |  | Bearing pad and jack installation works for segment launching
Sat (22/11) | 22 Nov 2025 | P12 |  | SB Stressing cage installation works
Sat (22/11) | 22 Nov 2025 | S2 |  | Preparation for side Formwork installation. To start installation in the afternoon
Sat (22/11) | 22 Nov 2025 | P3 |  | Continue drilling works at P2 side
Sat (22/11) | 22 Nov 2025 | P2 |  | Formwork dismantling
Sat (22/11) | 22 Nov 2025 | Zone 1 |  | Temp footpath for Awwa cast yesterday
Sat (22/11) | 22 Nov 2025 | P39 |  | Preparation for 1st lift column casting
Sat (22/11) | 22 Nov 2025 | P43 |  | Materials shifting in progress
Sat (22/11) | 22 Nov 2025 | P45 |  | Continue rebar works for 3rd layer wall
Sat (22/11) | 22 Nov 2025 | DR3 |  | No activity
Sat (22/11) | 22 Nov 2025 | P48 |  | Continue BP hacking works
Sat (22/11) | 22 Nov 2025 | P51 |  | Continue excavation and exposing for utility support
Sat (22/11) | 22 Nov 2025 | P3 |  | Continue drilling at P2 side. Balance middle portion to compete
Sat (22/11) | 22 Nov 2025 | P2 |  | Formwork dismantling completed. Balance wing form Formwork at NB to remove tonight
Sat (22/11) | 22 Nov 2025 | N2 |  | Preparation for segment launching tonight
Sat (22/11) | 22 Nov 2025 | P12 |  | SB segment adjustment ongoing
Sat (22/11) | 22 Nov 2025 | S2 |  | Formwork closing for Crosshead in progress. To cast next week
Mon (24/11) | 24 Nov 2025 | P51 |  | Excavation to expose utilities
Mon (24/11) | 24 Nov 2025 | Dr4 |  | Trial Trench for soldier pile
Mon (24/11) | 24 Nov 2025 | P47 |  | JGP work ongoing
Mon (24/11) | 24 Nov 2025 | P45 |  | L3 caisson formwork closing
Mon (24/11) | 24 Nov 2025 | P39& P40 |  | 1st stage column cast
Mon (24/11) | 24 Nov 2025 | P36, P37 & P38 |  | 1st stage column rebar work completed
Mon (24/11) | 24 Nov 2025 | P47 |  | Current status of stockpile. 22/39nos grouting done
Mon (24/11) | 24 Nov 2025 | DR3 |  | Current status of excavation. Height limiter provided
Mon (24/11) | 24 Nov 2025 | P45 |  | Balance formwork closing for 3rd layer caisson
Mon (24/11) | 24 Nov 2025 | P18 |  | Scaffold erection in progress
Mon (24/11) | 24 Nov 2025 | P14-P15 |  | Mid span Formwork dismantling
Mon (24/11) | 24 Nov 2025 | P12 |  | SB D/U 01 segment adjustment ongoing
Mon (24/11) | 24 Nov 2025 | N2 |  | D/U 01 MJ segment adjustment in progress
Mon (24/11) | 24 Nov 2025 | P7 |  | Formwork closing for drain wall. To cast tmr
Mon (24/11) | 24 Nov 2025 | S2 Crosshead |  | Formwork closing. To cast tmr
Mon (24/11) | 24 Nov 2025 | P51 |  | Current status
Mon (24/11) | 24 Nov 2025 | Near P50 |  | Exposing the cable for repairing
Mon (24/11) | 24 Nov 2025 | P50& P49 |  | Backfilling and levelling
Mon (24/11) | 24 Nov 2025 | P3 |  | Continue drilling works at center portion @ P2 side
Mon (24/11) | 24 Nov 2025 | P2 |  | Removal of polyfoam for stressing works preparation
Mon (24/11) | 24 Nov 2025 | P14-P15 |  | No activity
Mon (24/11) | 24 Nov 2025 | N2 |  | D/U 01 MJ segment adjustment in progress
Mon (24/11) | 24 Nov 2025 | P12 |  | No activity
Mon (24/11) | 24 Nov 2025 | S2 |  | Crosshead formwork closing
Mon (24/11) | 24 Nov 2025 | P7 |  | No activity
Mon (24/11) | 24 Nov 2025 | P3 |  | No activity
Mon (24/11) | 24 Nov 2025 | P2 |  | Preparation for stressing work
Tue (25/11) | 25 Nov 2025 | DR4 |  | Materials clearing for DR4 work
Tue (25/11) | 25 Nov 2025 | N2 |  | Segment adjustment for D/U 01
Tue (25/11) | 25 Nov 2025 | P45 |  | 3rd layer caisson formwork removal in progress
Tue (25/11) | 25 Nov 2025 | DR3 |  | Started to send out stockpile. Tomorrow to resume DR3 excavation
Tue (25/11) | 25 Nov 2025 | P47 |  | 2nd point boring for JGP grouting. 14nos left to complete
Tue (25/11) | 25 Nov 2025 | P48 |  | Continue excavation and pile head hacking
Tue (25/11) | 25 Nov 2025 | B2-29, B2-30 |  | Excavation in progress
Tue (25/11) | 25 Nov 2025 | GL23 |  | Current stockpile status
Tue (25/11) | 25 Nov 2025 | BR8 area |  | Current stockpile status
Tue (25/11) | 25 Nov 2025 | BR5 opening |  | Currently no activity
Tue (25/11) | 25 Nov 2025 | P36 |  | Column rebar works in progress
Tue (25/11) | 25 Nov 2025 | P3 |  | Drilling works ongoing at p4 side center portion
Tue (25/11) | 25 Nov 2025 | P2 |  | Preparation for tendon strand installation
Tue (25/11) | 25 Nov 2025 | S2 |  | Today to cast Crosshead
Tue (25/11) | 25 Nov 2025 | BR25 |  | Coupler exposing at BR26 area
Tue (25/11) | 25 Nov 2025 | P38 |  | Column formwork installation in progress
Tue (25/11) | 25 Nov 2025 | P37 |  | Currently no activity
Tue (25/11) | 25 Nov 2025 | B2-40, B2-41, B2-42 |  | No activity
Tue (25/11) | 25 Nov 2025 | B2-43 |  | Excavation in progress (1 ripper, 1 exc, 1 telescopic)
Tue (25/11) | 25 Nov 2025 | B2-48 |  | Rebar works and drainage pipe installation in progress
Tue (25/11) | 25 Nov 2025 | BR32B |  | Partial primer application done yesterday. Now cleaning ongoing before continue applying primer
Tue (25/11) | 25 Nov 2025 | P41 |  | Falsework installation in progress
Tue (25/11) | 25 Nov 2025 | N2 |  | No activity
Tue (25/11) | 25 Nov 2025 | S2 |  | Crosshead casting ongoing
Tue (25/11) | 25 Nov 2025 | P3 |  | No activity
Tue (25/11) | 25 Nov 2025 | P2 |  | No activity
Tue (25/11) | 25 Nov 2025 | P51 |  | No activity
Tue (25/11) | 25 Nov 2025 | P49 |  | Quarry dust backfilling
Tue (25/11) | 25 Nov 2025 | P48 |  | Bored pile hacking ongoing
Tue (25/11) | 25 Nov 2025 | DR3 |  | No activity
Tue (25/11) | 25 Nov 2025 | P45 |  | Casting completed
Wed (26/11) | 26 Nov 2025 | P18 |  | CJ roughening for bearing stump construction
Wed (26/11) | 26 Nov 2025 | B2-43 |  | Excavation (2 Excavator & 1 Telescopic) & soil disposal in progress. Target to finish by today
Wed (26/11) | 26 Nov 2025 | B2-48 |  | Continues rebar installation & target to cast it by this week
Wed (26/11) | 26 Nov 2025 | B2-29, B2-30 |  | Excavation in progress
Wed (26/11) | 26 Nov 2025 | BR5 opening |  | Currently no activity
Wed (26/11) | 26 Nov 2025 | P36 |  | Column formwork installation in progress
Wed (26/11) | 26 Nov 2025 | N2 | MJ | Segment adjusting in progress
Wed (26/11) | 26 Nov 2025 | P12 |  | 1st pair segment adjustment
Wed (26/11) | 26 Nov 2025 | S2 crosshead |  | Casting completed last night
Wed (26/11) | 26 Nov 2025 | Exit 1 |  | Current stockpile @ new ECM pond
Wed (26/11) | 26 Nov 2025 | B2-41/B2-42 |  | Plan to deliver 4 no. of struts tomorrow for its installation
Wed (26/11) | 26 Nov 2025 | P2 crosshead |  | Strand pushing for tensioning, required length of strand were precut, watch men provided at the opposite end
Wed (26/11) | 26 Nov 2025 | P3 |  | Drilling works ongoing at p4 side center portion
Wed (26/11) | 26 Nov 2025 | P1 |  | Preparation for PLT
Wed (26/11) | 26 Nov 2025 | P12 1st pair |  | SB adjustment completed
Wed (26/11) | 26 Nov 2025 | P2 |  | Crosshead tendon strands installation in progress
Wed (26/11) | 26 Nov 2025 | P3 drilling status |  | Balance on the highlighted area
Wed (26/11) | 26 Nov 2025 | P1 |  | PLT in progresss
Wed (26/11) | 26 Nov 2025 | P49-P50 |  | Housekeeping on going
Wed (26/11) | 26 Nov 2025 | P49 |  | Backfilling with quarry dust
Wed (26/11) | 26 Nov 2025 | P48 |  | Bored pile hacking
Wed (26/11) | 26 Nov 2025 | P47 |  | Soil disposal and JGP works ongoing
Wed (26/11) | 26 Nov 2025 | P51 |  | Resume excavation work
Wed (26/11) | 26 Nov 2025 | DR3 |  | Excavation to FEL. Scaffolding access installation on going
Wed (26/11) | 26 Nov 2025 | P45 |  | Formwork removal completed. LE preparing for S2 installation
Wed (26/11) | 26 Nov 2025 | B2-29, B2-30 |  | Continue disposal works, Rectification ongoing for 1 excavator
Wed (26/11) | 26 Nov 2025 | BR8 |  | Current stockpile status
Wed (26/11) | 26 Nov 2025 | P36 |  | Column formwork installation in progress. Plan for casting today
Wed (26/11) | 26 Nov 2025 | BR5 opening |  | No activity
Wed (26/11) | 26 Nov 2025 | P37 |  | No activity
Wed (26/11) | 26 Nov 2025 | P38 column |  | Plan for casting today
Wed (26/11) | 26 Nov 2025 | BR25 |  | CJ roughening & post-drilling works ongoing
Wed (26/11) | 26 Nov 2025 | B2-43 |  | Excavation in progress
Wed (26/11) | 26 Nov 2025 | B2-48 |  | E&M piping installation works and rebar works ongoing
Wed (26/11) | 26 Nov 2025 | BR32B |  | Partial waterproofing membrane laid
Wed (26/11) | 26 Nov 2025 | P40 |  | 2nd lift rebar cage fabrication in progress
Wed (26/11) | 26 Nov 2025 | P42 |  | Crosshead working platform installation in progress
Wed (26/11) | 26 Nov 2025 | P18 |  | Bearing stump RC work in progress
Wed (26/11) | 26 Nov 2025 | N2 |  | No activity
Wed (26/11) | 26 Nov 2025 | CCW2 |  | Currently no excavation activity yet
Wed (26/11) | 26 Nov 2025 | P12 |  | No activity
Wed (26/11) | 26 Nov 2025 | Near B1-03 |  | Dwall hacking ongoing
Wed (26/11) | 26 Nov 2025 | P2 |  | Crosshead surface grinding in progress
Wed (26/11) | 26 Nov 2025 | P1 |  | No activity
Wed (26/11) | 26 Nov 2025 | P3 |  | No activity
Wed (26/11) | 26 Nov 2025 | Below BR19 slab |  | CJ roughening ongoing, BR19A:, KP endplate welding works ongoing for last KP (8/8nos), Hacking ongoing for excess concrete
Wed (26/11) | 26 Nov 2025 | B2-29, B2-30 |  | No activity
Wed (26/11) | 26 Nov 2025 | GL23 |  | Current stockpile status
Wed (26/11) | 26 Nov 2025 | P36 |  | Pending 1st lift column casting
Wed (26/11) | 26 Nov 2025 | P37 |  | No activity
Wed (26/11) | 26 Nov 2025 | BR25 |  | CJ roughening at BR26 side, Tmr to continue KP endplate welding works (4nos)
Wed (26/11) | 26 Nov 2025 | P38 |  | 1st lift column casting in progress
Wed (26/11) | 26 Nov 2025 | B2-43 |  | No activity
Wed (26/11) | 26 Nov 2025 | BR32B |  | Surface inspection for waterproofing membrane laying, Continue membrane laying
Wed (26/11) | 26 Nov 2025 | P51 |  | No activity
Wed (26/11) | 26 Nov 2025 | P49 |  | Housekeeping, material shifting
Wed (26/11) | 26 Nov 2025 | P48 |  | No activity
Wed (26/11) | 26 Nov 2025 | DR3 |  | Excavation to FEL in progress
Wed (26/11) | 26 Nov 2025 | B2-48 |  | Dayshift working till 8pm. Thereafter nightshift takeover
Wed (26/11) | 26 Nov 2025 | P40 |  | 2nd lift rebar cage fabrication in progress
Wed (26/11) | 26 Nov 2025 | P42 |  | Barricade installation for crosshead works
Wed (26/11) | 26 Nov 2025 | Exit 2 |  | 2nd lift formwork closing in progress. Plan for casting tmr
Wed (26/11) | 26 Nov 2025 | B1-05 |  | Pump truck already standby for lean concrete casting at remaining area
Wed (26/11) | 26 Nov 2025 | P45 |  | Preparation work S2 installation
Thu (27/11) | 27 Nov 2025 | BR32B |  | Installing of polyfoam is in progress
Thu (27/11) | 27 Nov 2025 | BR43 |  | Excavation has completed, clearing of balanced soil for disposal by 2 Excavators & 1 telescopic
Thu (27/11) | 27 Nov 2025 | B2-48 |  | Continues rebar installation & target to cast by this week
Thu (27/11) | 27 Nov 2025 | B2-41/B2-42 |  | 4 No. of struts will be delivered today
Thu (27/11) | 27 Nov 2025 | Exit 1 |  | Current stockpile status @ new ECM pond
Thu (27/11) | 27 Nov 2025 | P18 |  | Steel plates laying for crane parking
Thu (27/11) | 27 Nov 2025 | B2-29, B2-30 |  | Excavation in progress, 3 excavators (KTC) - 2 operators, 1 telescopic op, 1 mini exc (WH)
Thu (27/11) | 27 Nov 2025 | BR25 |  | Continue CJ roughening and exposing couplers, KP endplate welding works ongoing — 2/4nos completed, now ongoing next to BR26 CJ, Continue post-drilling works by Dongah
Thu (27/11) | 27 Nov 2025 | P35 |  | Column rebar works started
Thu (27/11) | 27 Nov 2025 | N2 |  | Continue segment adjustment for 1st pair
Thu (27/11) | 27 Nov 2025 | P3 |  | Driling works ongoing for P4 side
Thu (27/11) | 27 Nov 2025 | P2 |  | Tendon Strand installation ongoing
Thu (27/11) | 27 Nov 2025 | DR4 |  | 5nos probing done. Now preparing for shifting back the rig to P47
Thu (27/11) | 27 Nov 2025 | P22 |  | Scaffold material shifting for erection of platform access. 1st stage column installation plan to start tmr
Thu (27/11) | 27 Nov 2025 | P48 |  | Continue excavation
Thu (27/11) | 27 Nov 2025 | P49 |  | Backfilling and levelling
Thu (27/11) | 27 Nov 2025 | P51 |  | Top soil layer exposing
Thu (27/11) | 27 Nov 2025 | DR3 |  | Continue excavation with two mini
Thu (27/11) | 27 Nov 2025 | P45 |  | 2 waler and 3 struts installed at TPE bound. Next tuesday to complete
Thu (27/11) | 27 Nov 2025 | P42 |  | Status of working platform erection. To cast this crosshead in December
Thu (27/11) | 27 Nov 2025 | P41 |  | Preparing for tie rod holes patch up
Thu (27/11) | 27 Nov 2025 | P39& P39 |  | 1st lift cast
Thu (27/11) | 27 Nov 2025 | P35 |  | 1st lift rebar work in progress
Thu (27/11) | 27 Nov 2025 | P36 |  | 1st lift cast
Thu (27/11) | 27 Nov 2025 | P37 |  | 1st lift status of rebar work
Thu (27/11) | 27 Nov 2025 | P18 |  | Current status
Thu (27/11) | 27 Nov 2025 | P12 |  | Crane set up for segment lowering down
Thu (27/11) | 27 Nov 2025 | S2 |  | No activity already. Just curing
Thu (27/11) | 27 Nov 2025 | P48 |  | Pile head hacking and trimming of cement grout continue
Thu (27/11) | 27 Nov 2025 | DR3 |  | Abandoned water pipe removal and clearing soft soil for the base
Thu (27/11) | 27 Nov 2025 | B2-29, B2-30/31 |  | Continue excavation
Thu (27/11) | 27 Nov 2025 | P36 |  | 1st lift column cast last night
Thu (27/11) | 27 Nov 2025 | BR5 opening |  | No activity
Thu (27/11) | 27 Nov 2025 | P37 |  | Currently no activity
Thu (27/11) | 27 Nov 2025 | BR25 |  | Continue CJ roughening & exposing couplers (Wendyng), Dewatering & preparation works ongoing at KP area prior to welding endplates. Plan 2 welders at this area, Preparing to continue post-drilling works by Dongah, Formwork removal for drop slab area
Fri (28/11) | 28 Nov 2025 | P51 |  | Top soil removal and prepare bund wall for lean concrete
Fri (28/11) | 28 Nov 2025 | BR32B |  | Topping up of water to 150mm for water ponding test from its current level 110mm. Once ready will arrange for QPS re-inspection
Fri (28/11) | 28 Nov 2025 | B2-43 |  | Balanced soil have been cleared
Fri (28/11) | 28 Nov 2025 | B2-29, B2-30 |  | Excavation in progress. Current excavation ~GL23 to GL26
Fri (28/11) | 28 Nov 2025 | BR5 opening |  | Today plan to mobilise excavator and start excavation
Fri (28/11) | 28 Nov 2025 | BR25 |  | U-bar welding works, Continue CJ roughening, Post-drilling works ongoing
Fri (28/11) | 28 Nov 2025 | P49 |  | Backfilling and barricade installation
Fri (28/11) | 28 Nov 2025 | P48 |  | One side to complete pile head hacking today
Fri (28/11) | 28 Nov 2025 | DR3 |  | Continue excavation with 2 mini and one long arm. Around 70% done as of now
Fri (28/11) | 28 Nov 2025 | P45 |  | Strut installation done at TPE bound side
Fri (28/11) | 28 Nov 2025 | P47 |  | JGP left 11 points to complete
Fri (28/11) | 28 Nov 2025 | B2-48 |  | Continue installing of remaining shear links & cleaning is in progress, target to cast it today
Fri (28/11) | 28 Nov 2025 | B2-41/B2-42 |  | Started drilling and installing of N plates, understand that strut materials are otw to site
Fri (28/11) | 28 Nov 2025 | P42 |  | Preparing for soffit plywood laying for crosshead
Fri (28/11) | 28 Nov 2025 | Exit 1 ECM Pond |  | Current stockpile status
Fri (28/11) | 28 Nov 2025 | N2 1st pair | MJ | Adjustment completed. Awaiting for YWL confirmation. If all okay plan to launch U02 tonight
Fri (28/11) | 28 Nov 2025 | BR19A |  | Rebar works and RGT installation in progress
Fri (28/11) | 28 Nov 2025 | BR22B |  | Currently no activity
Fri (28/11) | 28 Nov 2025 | B2-29, B2-30 |  | Continue excavation
Fri (28/11) | 28 Nov 2025 | P35 |  | Currently no activity
Fri (28/11) | 28 Nov 2025 | P36 & BR5 opening |  | Currently no activity
Fri (28/11) | 28 Nov 2025 | P37 |  | No activity
Fri (28/11) | 28 Nov 2025 | P2 |  | Strand pushing for stage 1 tensioning
Fri (28/11) | 28 Nov 2025 | P3 |  | Drilling for starter bar status. Balance 1 layer at the middle
Fri (28/11) | 28 Nov 2025 | P1 |  | Lean concrete for pad footing cast
Fri (28/11) | 28 Nov 2025 | BR25 |  | Clearing debris at CJ area, U-bar welding works for 4nos kingposts completed. MPI test was also done. Now waiting for backfilling and plan to complete lean con today, Dongah continue post-drilling works
Fri (28/11) | 28 Nov 2025 | B2-41/B2-42 |  | Hirose start strutting works
Fri (28/11) | 28 Nov 2025 | B2-48 |  | Final inspection was done. Now ongoing cleaning and reinspection to be called before casting
Fri (28/11) | 28 Nov 2025 | BR32B |  | Water ponding test
Fri (28/11) | 28 Nov 2025 | P41 |  | Column formwork dismantled
Fri (28/11) | 28 Nov 2025 | B1-06 |  | Rebar works in progress
Fri (28/11) | 28 Nov 2025 | B1-04 |  | Continue clearing soil
Fri (28/11) | 28 Nov 2025 | BR19A |  | Rebar works in progress
Fri (28/11) | 28 Nov 2025 | BR22B |  | Continue hacking of overcast dwall
Fri (28/11) | 28 Nov 2025 | B2-29, B2-30 |  | No activity. Ventilation hoses replaced and adjusted
Fri (28/11) | 28 Nov 2025 | BR8 |  | 1 telescopic op on site for the soft clay disposal
Fri (28/11) | 28 Nov 2025 | BR5 opening |  | New access installation in progress. Once installed, excavation planned to resume here
Fri (28/11) | 28 Nov 2025 | P37 |  | Working platform scaffold erection in progress
Fri (28/11) | 28 Nov 2025 | BR25 |  | Preparing backfilling and lean concrete works
Fri (28/11) | 28 Nov 2025 | B2-41, B2-42 |  | 1nos strut installed. Tmr to resume
Fri (28/11) | 28 Nov 2025 | B2-48 |  | Continue cleaning works and rectifying comments. Once completed, reinspection to be called again ard 830pm, Concrete pump on site and pipes/hose joining done
Sat (29/11) | 29 Nov 2025 | BR19A |  | Rebar works in progress, Continue debonding sheet laying, U-bar welding works for balance 2nos
Sat (29/11) | 29 Nov 2025 | BR22B |  | Continue hacking works (1 operator), 1 KTC excavator currently not operating
Sat (29/11) | 29 Nov 2025 | P48 |  | Lifting of excavator
Sat (29/11) | 29 Nov 2025 | P47 |  | Soil disposal..JGP no activity
Sat (29/11) | 29 Nov 2025 | DR3 |  | Excavation to FEL
Sat (29/11) | 29 Nov 2025 | P45 |  | S2 strut installation
Sat (29/11) | 29 Nov 2025 | B2-29, B2-30 |  | Continue excavation, BR5 opening: Dismantling old access and preparation to bring down 1 excavator to resume excavation here, P36: No activity
Sat (29/11) | 29 Nov 2025 | P37 |  | Working platform installation in progress
Sat (29/11) | 29 Nov 2025 | BR25 |  | Surface cleaning ongoing prior to laying debonding sheet
Sat (29/11) | 29 Nov 2025 | B2-41, B2-42 |  | Resume strut installation works
Sat (29/11) | 29 Nov 2025 | P40 transfer beam soffit |  | Hacking ongoing for 800mm thick wall rebar works
Sat (29/11) | 29 Nov 2025 | B2-48 |  | Casting completed earlier this morning ard 6am, Casting started last night at 10pm, G40PBFC 193m³/193m³, G40PBFC WP 73m³/73m³
Sat (29/11) | 29 Nov 2025 | B2-43 |  | Currently no activity
Sat (29/11) | 29 Nov 2025 | P5 |  | PT duct pipe polyform removal works
Sat (29/11) | 29 Nov 2025 | P4 |  | Pier column concrete surface grinding works
Sat (29/11) | 29 Nov 2025 | P2 |  | Crosshead tendon pulling works
Sat (29/11) | 29 Nov 2025 | P3 |  | Drilling works for tendon duct rectification starter bar
Sat (29/11) | 29 Nov 2025 | P42 |  | Crosshead wing formwork installation ongoing
Sat (29/11) | 29 Nov 2025 | Exit 1 |  | Ground access works ongoing
Sat (29/11) | 29 Nov 2025 | P12 |  | Segment tendon pulling works
Sat (29/11) | 29 Nov 2025 | N2 |  | Segment adjustment works
Sat (29/11) | 29 Nov 2025 | P18 |  | Segment jacking support system falsework installation works
Sat (29/11) | 29 Nov 2025 | P18 |  | No activity
Sat (29/11) | 29 Nov 2025 | N2 |  | No activity
Sat (29/11) | 29 Nov 2025 | P13 |  | Ground preparation work for crane parking..for segment launching work at N2
Sat (29/11) | 29 Nov 2025 | P12 |  | Segment tendon pulling works
Sat (29/11) | 29 Nov 2025 | P7-1 |  | No activity
Sat (29/11) | 29 Nov 2025 | P7 |  | Soil disposal
Sat (29/11) | 29 Nov 2025 | P5 |  | PT duct pipe polyform removal works
Sat (29/11) | 29 Nov 2025 | P3 |  | No activity
Sat (29/11) | 29 Nov 2025 | P2 |  | Crosshead tendon pulling works
Sat (29/11) | 29 Nov 2025 | P51 |  | Excavation to expose utility services
Sat (29/11) | 29 Nov 2025 | P48 |  | Grout hacking and excavation work on going
Sat (29/11) | 29 Nov 2025 | P47 |  | Ground preparation work for JGP
Sat (29/11) | 29 Nov 2025 | DR3 |  | Excavation to FEL
Sat (29/11) | 29 Nov 2025 | P45 |  | No activity
Sat (29/11) | 29 Nov 2025 | CCW2 |  | S3 plan for preloading at 10am
Sat (29/11) | 29 Nov 2025 | B1-03 |  | Excavation and disposal work (3 exc below, 1 telescopic)
Sat (29/11) | 29 Nov 2025 | DR4 |  | No activity
Sat (29/11) | 29 Nov 2025 | B1-06, B1-05, B1-04 |  | Levelling access, Rebar works ongoing at B1-06
Sun (30/11) | 30 Nov 2025 | CCW1 | North Side | S5 excavation is in progress (3 excavators & 1 telescopic)
Sun (30/11) | 30 Nov 2025 | B1-06 |  | Pipe installation in progress by APP
Sun (30/11) | 30 Nov 2025 | B1-03 |  | Excavation & soil disposal by 1 excavator & 1 telescopic
Sun (30/11) | 30 Nov 2025 | BR19A |  | Ongoing rebar installation works (25 workers + 2 Sups), all CGW manpower are focusing this slab today
Sun (30/11) | 30 Nov 2025 | BR22B |  | No activity
Sun (30/11) | 30 Nov 2025 | B2-29 / B2-30 |  | No excavation from KTC today
Sun (30/11) | 30 Nov 2025 | BR5 Opening |  | Excavation in progress by 1 excavator & 1 telescopic
Sun (30/11) | 30 Nov 2025 | BR25 |  | Joining of couplers is in progress (9 workers + 1 Sup)
Sun (30/11) | 30 Nov 2025 | B2-41 / B2-42 |  | 3 struts have been installed, no activity today
Sun (30/11) | 30 Nov 2025 | B2-43 |  | No activity
Sun (30/11) | 30 Nov 2025 | Wall below P40 |  | Rebar work is in progress
Sun (30/11) | 30 Nov 2025 | B2-48 / B2-49 |  | No activity
Sun (30/11) | 30 Nov 2025 | Exit 1 |  | Access cutting down to SHD +2m
Sun (30/11) | 30 Nov 2025 | Exit 1 ECM pond |  | Current stockpile status
Sun (30/11) | 30 Nov 2025 | CCW1 | North Side | Continues S5 excavation & soil disposal
Sun (30/11) | 30 Nov 2025 | B1-03 |  | Continues excavation & soil disposal
Sun (30/11) | 30 Nov 2025 | B1-06 |  | No more activity for today
Sun (30/11) | 30 Nov 2025 | BR19A |  | Will continue rebar installation until 5pm today
Sun (30/11) | 30 Nov 2025 | Exit 2 |  | Dismantling of capping beam formwork
Sun (30/11) | 30 Nov 2025 | B2-29 / B2-30 |  | No excavation for the day
Sun (30/11) | 30 Nov 2025 | BR5 opening |  | Continues excavation & soil disposal
Sun (30/11) | 30 Nov 2025 | P37 |  | Formwork installation for 1st stage of column
Sun (30/11) | 30 Nov 2025 | BR25 |  | Day shift will continue rebar work until 5pm & understand that night shift plan to come @ 8pm
Sun (30/11) | 30 Nov 2025 | CCE4 |  | Continue rebar installation for RC wall below P40
Sun (30/11) | 30 Nov 2025 | BR32B |  | Laying of BRC to prepare for protection concrete
Sun (30/11) | 30 Nov 2025 | Exit 1 |  | Access continue cutting to SHD +2m
Mon (01/12) | 01 Dec 2025 | B2-29, B2-30 |  | Currently no activity by KTC (3 exc, 1 telescopic), Hacking works ongoing by WH (1 breaker)
Mon (01/12) | 01 Dec 2025 | P35 |  | Currently no activity
Mon (01/12) | 01 Dec 2025 | BR25 |  | Rebar works in progress
Mon (01/12) | 01 Dec 2025 | BR5 opening |  | Excavation and disposal in progress (1 telescopic, 1 exc)
Mon (01/12) | 01 Dec 2025 | P18 |  | Bearing stump casting
Mon (01/12) | 01 Dec 2025 | P19 |  | Crosshead tendon duct grouting
Mon (01/12) | 01 Dec 2025 | N2 |  | Currently no activity..segment delivered on site, tonight segment launching
Mon (01/12) | 01 Dec 2025 | GL23 |  | Clearing stockpile
Mon (01/12) | 01 Dec 2025 | BR32B |  | Backfilling ongoing
Mon (01/12) | 01 Dec 2025 | B2-49A |  | Currently no activity
Mon (01/12) | 01 Dec 2025 | B2-48 |  | No activity
Mon (01/12) | 01 Dec 2025 | CCE4 |  | Current status of rebar installation for RC wall below P40
Mon (01/12) | 01 Dec 2025 | B2-43 |  | No activity
Mon (01/12) | 01 Dec 2025 | Exit 1 |  | Current access status
Mon (01/12) | 01 Dec 2025 | Exit 1 |  | Current stockpile status
Mon (01/12) | 01 Dec 2025 | P2 |  | No activity
Mon (01/12) | 01 Dec 2025 | P3 |  | No activity
Mon (01/12) | 01 Dec 2025 | P1 |  | Slope casting
Mon (01/12) | 01 Dec 2025 | P42 |  | Crosshead rebar works in progress
Mon (01/12) | 01 Dec 2025 | B2-41, B2-42 |  | 4nos struts installed. Tmr plan for preloading
Mon (01/12) | 01 Dec 2025 | BR25 |  | Rebar works in progress
Mon (01/12) | 01 Dec 2025 | P37 column |  | 1st lift plan for casting tmr morning
Mon (01/12) | 01 Dec 2025 | BR5 opening |  | No activity now
Mon (01/12) | 01 Dec 2025 | GL23 |  | No activity now
Mon (01/12) | 01 Dec 2025 | BR22B |  | No activity now
Mon (01/12) | 01 Dec 2025 | BR19A |  | Rebar works in progress
Mon (01/12) | 01 Dec 2025 | P51 |  | Slope casting
Mon (01/12) | 01 Dec 2025 | P48 |  | Grout hacking in progress
Mon (01/12) | 01 Dec 2025 | B2-29, B2-30 |  | No activity. Dongah preparing to bring down excavator for barette pile hacking
Mon (01/12) | 01 Dec 2025 | Near B1-05 |  | Soil levelling works ongoing
Mon (01/12) | 01 Dec 2025 | B1-04 |  | No activity
Mon (01/12) | 01 Dec 2025 | B1-06 |  | Debonding sheet laying, WH installing pump for temporary sump pit
Mon (01/12) | 01 Dec 2025 | DR3 |  | Excavation to FEL
Mon (01/12) | 01 Dec 2025 | P45 |  | S2 strut installation
Tue (02/12) | 02 Dec 2025 | P48 North |  | 5th layer caisson wall casting
Tue (02/12) | 02 Dec 2025 | 800mm PW |  | 1lane closed..preparation for excavation and pipe laying
Tue (02/12) | 02 Dec 2025 | 800mm PW |  | DR4 area no activity
Tue (02/12) | 02 Dec 2025 | P3 crosshead |  | Drilling for starter bars in progress. P4 side drilling completed
Tue (02/12) | 02 Dec 2025 | GL23 |  | Current stockpile status
Tue (02/12) | 02 Dec 2025 | BR7 opening |  | Installation of new access in progress, Hacking works ongoing
Tue (02/12) | 02 Dec 2025 | P35 |  | No activity
Tue (02/12) | 02 Dec 2025 | BR25 |  | Rebar works and RGT installation in progress
Tue (02/12) | 02 Dec 2025 | BR5 opening |  | Excavation in progress
Tue (02/12) | 02 Dec 2025 | P37 column |  | 1st lift plan for casting today
Tue (02/12) | 02 Dec 2025 | P45 |  | S2 all Diagonal struts and horizontal strut installation done. Balance welding only
Tue (02/12) | 02 Dec 2025 | DR3 |  | Continue excavation. 2 mini and one long arm
Tue (02/12) | 02 Dec 2025 | P47 |  | Last point JGP grouting. Today to complete all
Tue (02/12) | 02 Dec 2025 | P48 |  | Last layer caisson area trimming. Base lean concrete yet to complete at this area
Tue (02/12) | 02 Dec 2025 | P51 |  | Completed top soil removal at SB. Exposing at NB in progress
Tue (02/12) | 02 Dec 2025 | B2-41, B2-42 |  | Struts preloading postponed to tmr due to pump issue encountered just now
Tue (02/12) | 02 Dec 2025 | BRP61 |  | Hacking ongoing for rectification works
Tue (02/12) | 02 Dec 2025 | BR32B |  | Current backfilling status
Tue (02/12) | 02 Dec 2025 | B2-49A |  | Lean concrete cement patching works in preparation for waterproofing membrane works
Tue (02/12) | 02 Dec 2025 | Below P40 |  | Formwork installation for RC wall. Plan for casting tmr
Tue (02/12) | 02 Dec 2025 | B2-43 |  | No activity
Tue (02/12) | 02 Dec 2025 | P18 SB upchainage |  | Scaffold platform erection for MJ segment launching status. Balance u-jack and Channel installation
Tue (02/12) | 02 Dec 2025 | P20 crosshead |  | Grouting completed yesterday
Tue (02/12) | 02 Dec 2025 | P42 |  | Crosshead rebar works in progress
Tue (02/12) | 02 Dec 2025 | Exit 1 |  | Stockpile status
Tue (02/12) | 02 Dec 2025 | P42 |  | Top rebar work for crosshead in progress
Tue (02/12) | 02 Dec 2025 | P41 |  | Falsework for crosshead to start after backfilling and clearing unused materials
Tue (02/12) | 02 Dec 2025 | P20 |  | Scaffolding dismantling
Tue (02/12) | 02 Dec 2025 | P18 |  | Bearing stump formwork removal
Tue (02/12) | 02 Dec 2025 | P12 |  | Installation of stitching formwork
Tue (02/12) | 02 Dec 2025 | S2 |  | Crosshead formwork dismantling
Tue (02/12) | 02 Dec 2025 | P7-2 |  | Drain casting
Tue (02/12) | 02 Dec 2025 | P1-P5 |  | No activity..near P1: Barricade installation along footpath
Tue (02/12) | 02 Dec 2025 | P45 |  | No activity
Tue (02/12) | 02 Dec 2025 | P51 |  | No activity
Tue (02/12) | 02 Dec 2025 | DR3 |  | Excavation to FEL ongoing
Wed (03/12) | 03 Dec 2025 | P21 |  | Crane platform preparation for P22 column 1st stage formwork closing
Wed (03/12) | 03 Dec 2025 | P51 |  | Access erection at TPE bound. This week should be able to settle the utility stump and handover to LE by next week
Wed (03/12) | 03 Dec 2025 | P51 |  | Top soil removal at Changi bound
Wed (03/12) | 03 Dec 2025 | P22 column 1st stage |  | Preparation for formwork closing
Wed (03/12) | 03 Dec 2025 | P18 |  | Bearing stump formwork dismantling
Wed (03/12) | 03 Dec 2025 | P48 |  | 5th layer caisson 50% casting done. Today to lean concrete the platform for the balance area. Pile head hacking done. Left trimming
Wed (03/12) | 03 Dec 2025 | B2-41/B2-42 |  | Strut preloading plan to carry out today
Wed (03/12) | 03 Dec 2025 | BRP61 |  | Rectification work is in progress
Wed (03/12) | 03 Dec 2025 | B2-43 |  | No activity
Wed (03/12) | 03 Dec 2025 | P47 |  | JGP grouting 100% completed. Completed for tunnel also
Wed (03/12) | 03 Dec 2025 | P3 crosshead |  | Drilling continue. To complete tomorrow
Wed (03/12) | 03 Dec 2025 | BR32B |  | Backfilling is in progress
Wed (03/12) | 03 Dec 2025 | CCE4 |  | Wall below P40 plan to cast today
Wed (03/12) | 03 Dec 2025 | B2-49A |  | Cleaning in progress, will start laying of membrane later
Wed (03/12) | 03 Dec 2025 | P42 |  | Continue crosshead rebar work
Wed (03/12) | 03 Dec 2025 | P48 |  | S2 strut welding to complete today
Wed (03/12) | 03 Dec 2025 | DR3 |  | Continue excavation with 2 mini and one long arm
Wed (03/12) | 03 Dec 2025 | P22 column 1st stage |  | Formwork closing in progress
Wed (03/12) | 03 Dec 2025 | P18 |  | Preparation for bearing pad installation @ SB
Wed (03/12) | 03 Dec 2025 | P51 |  | Current status of exposing UKP. No KTC go for tea break
Wed (03/12) | 03 Dec 2025 | B2-29, B2-30 |  | Excavation ongoing (1 KTC exc, 1 WH breaker)
Wed (03/12) | 03 Dec 2025 | P35 |  | No activity
Wed (03/12) | 03 Dec 2025 | N2 D03 |  | Adjustable jack installation for launching tonight
Wed (03/12) | 03 Dec 2025 | P12 SB |  | Wet stitching formwork installation completed
Wed (03/12) | 03 Dec 2025 | S2 |  | Formwork dismantled
Wed (03/12) | 03 Dec 2025 | P3 |  | Continue drilling works at p2 side
Wed (03/12) | 03 Dec 2025 | GL22-23 |  | Current stockpile status
Wed (03/12) | 03 Dec 2025 | BR25 |  | Rebar works in progress & start installing side formwork. Plan for casting this week
Wed (03/12) | 03 Dec 2025 | BR5 opening |  | Excavation ongoing
Wed (03/12) | 03 Dec 2025 | DR3 |  | Continue excavation and send out spoil to clear up the space
Wed (03/12) | 03 Dec 2025 | P48 |  | Crane parking for balance lean concrete for 5th layer caisson
Wed (03/12) | 03 Dec 2025 | P45 |  | S2 diagonal strut welding done. Continue welding horizontal struts
Wed (03/12) | 03 Dec 2025 | B2-49A |  | Waterproofing membrane works ongoing
Wed (03/12) | 03 Dec 2025 | B2-48 |  | No activity
Wed (03/12) | 03 Dec 2025 | B2-43 |  | No activity
Wed (03/12) | 03 Dec 2025 | BR32B |  | Current backfill status
Wed (03/12) | 03 Dec 2025 | Below P40 |  | Wall casting in progress
Wed (03/12) | 03 Dec 2025 | B2-41, B2-42 |  | 3/4nos preloading completed. For the other one, noted on site that qps has requested to verify the grout strength first
Wed (03/12) | 03 Dec 2025 | B2-40 |  | No activity
Wed (03/12) | 03 Dec 2025 | BR25 |  | Rebar works in progress
Wed (03/12) | 03 Dec 2025 | P37 column |  | 1st lift cast yesterday
Wed (03/12) | 03 Dec 2025 | BR5 opening | B2-35 | Excavation in progress (1 exc op inside, 1 telescopic)
Wed (03/12) | 03 Dec 2025 | P35 |  | No activity
Wed (03/12) | 03 Dec 2025 | B2-29, B2-30 |  | Soft clay disposal ongoing
Wed (03/12) | 03 Dec 2025 | GL20-23 |  | Stockpile clearing in progress
Wed (03/12) | 03 Dec 2025 | Exit 2 |  | No activity
Wed (03/12) | 03 Dec 2025 | BR19A |  | Rebar works in progress
Wed (03/12) | 03 Dec 2025 | CCW2 |  | S4 excavation in progress
Wed (03/12) | 03 Dec 2025 | B1-06 |  | No activity
Wed (03/12) | 03 Dec 2025 | B1-05 |  | No activity
Wed (03/12) | 03 Dec 2025 | B1-04 |  | Excavation in progress
Wed (03/12) | 03 Dec 2025 | P18 |  | System falsework installation in progress
Wed (03/12) | 03 Dec 2025 | N2 |  | No activity
Wed (03/12) | 03 Dec 2025 | P12 |  | No activity
Wed (03/12) | 03 Dec 2025 | S2 |  | Falsework dismantling in progress
Wed (03/12) | 03 Dec 2025 | P7 |  | Drain formwork removal
Wed (03/12) | 03 Dec 2025 | P1-P5 |  | No activity
Wed (03/12) | 03 Dec 2025 | P44-P45 |  | SPPG work in progress
Wed (03/12) | 03 Dec 2025 | P45 |  | No activity
Wed (03/12) | 03 Dec 2025 | DR3 |  | No activity
Wed (03/12) | 03 Dec 2025 | P48 |  | Working platform lean concrete casting completed
Wed (03/12) | 03 Dec 2025 | 800mm |  | Preparation for water pipe laying
Wed (03/12) | 03 Dec 2025 | P51 |  | No activity
Thu (04/12) | 04 Dec 2025 | P51 |  | Exposing UKP at changi bound
Thu (04/12) | 04 Dec 2025 | PMH26 |  | No movement/ disposal for stockpile here
Thu (04/12) | 04 Dec 2025 | P22 |  | 1st lift column target to cast tmr
Thu (04/12) | 04 Dec 2025 | P18 |  | Falsework erection for segment launching and bearing pad installation ongoing
Thu (04/12) | 04 Dec 2025 | BRP61 |  | Continues rectification work
Thu (04/12) | 04 Dec 2025 | B2-43 |  | No activity
Thu (04/12) | 04 Dec 2025 | N2 |  | D03 segment launched last night
Thu (04/12) | 04 Dec 2025 | P12 |  | SB stitching formwork closing. To cast in the afternoon
Thu (04/12) | 04 Dec 2025 | S2 |  | Falsework dismantled
Thu (04/12) | 04 Dec 2025 | CCE4 |  | Wall below P40 casted last night, no activity now
Thu (04/12) | 04 Dec 2025 | B2-48 |  | Hacking of overcast Dwall
Thu (04/12) | 04 Dec 2025 | B2-49 |  | Laying of membrane is in progress
Thu (04/12) | 04 Dec 2025 | P3 |  | Continue drilling works at p2 side
Thu (04/12) | 04 Dec 2025 | P2 |  | No activity
Thu (04/12) | 04 Dec 2025 | P1 |  | No activity
Thu (04/12) | 04 Dec 2025 | BR7 opening |  | Modular access installation still in progress, Observed no disposal works currently, Hacking works ongoing inside
Thu (04/12) | 04 Dec 2025 | P35 |  | No activity
Thu (04/12) | 04 Dec 2025 | GL20-23 |  | Stockpile disposal ongoing
Thu (04/12) | 04 Dec 2025 | BR25 |  | Rebar works and formwork installation in progress
Thu (04/12) | 04 Dec 2025 | BR5 opening |  | Excavation in progress
Thu (04/12) | 04 Dec 2025 | DR3 |  | Clearing soft and maintaining the slope
Thu (04/12) | 04 Dec 2025 | P47 |  | Rig maintenance
Thu (04/12) | 04 Dec 2025 | P48 |  | Lowering down rebar for last layer caisson
Thu (04/12) | 04 Dec 2025 | BR32B |  | Continues backfilling work
Thu (04/12) | 04 Dec 2025 | P42 |  | Crosshead main bar installation done. Handover to WH already. WH shifting materials to start ducting work
Thu (04/12) | 04 Dec 2025 | P18 |  | Continue Falsework erection and bearing pad installation
Thu (04/12) | 04 Dec 2025 | P12 |  | Preparation for casting for SB stitching. Concrete ordered
Thu (04/12) | 04 Dec 2025 | P51 |  | Current status of UKP exposing at Changi bound
Thu (04/12) | 04 Dec 2025 | BR5 opening |  | Continue excavation towards BR8 area (2 exc op below, 1 telescopic)
Thu (04/12) | 04 Dec 2025 | BR25 |  | Rebar works in progress. Plan for casting tomorrow
Thu (04/12) | 04 Dec 2025 | BR7 area |  | Modular access installation and roofing works in progress, Currently observed no disposal activity
Thu (04/12) | 04 Dec 2025 | P3 |  | Continue drilling works at the sides of crosshead. To complete by this week
Thu (04/12) | 04 Dec 2025 | GL20-23 |  | Soft soil disposal in progress (1 exc op)
Thu (04/12) | 04 Dec 2025 | P45 |  | Rest area dismantling and clearing materials to give way for 22KV diversion
Thu (04/12) | 04 Dec 2025 | P45 |  | MPI test done. KTC preparing to resume excavation
Thu (04/12) | 04 Dec 2025 | P47 |  | Continue clearing stockpile. Left a few loads only
Thu (04/12) | 04 Dec 2025 | DR3 |  | Continue soft soil removal
Thu (04/12) | 04 Dec 2025 | P48 |  | Rebar work done for center portion of caisson. Tomorrow to cast
Thu (04/12) | 04 Dec 2025 | P42 crosshead |  | Main bar inspection done. Handover to WH for ducting work
Thu (04/12) | 04 Dec 2025 | P18 SB downchainage |  | Falsework erection for Segment (MJ) installation
Thu (04/12) | 04 Dec 2025 | P14-P15 midspan |  | SB wet stitching formwork dismantled. Tonight to dismantle NB side after last bus
Thu (04/12) | 04 Dec 2025 | North ramp N2 |  | Tonight segment launching D04
Fri (05/12) | 05 Dec 2025 | P22 |  | 1st lift column to cast today in the afternoon
Fri (05/12) | 05 Dec 2025 | B2-49A |  | Membrane laying has completed, will start rebar work later
Fri (05/12) | 05 Dec 2025 | B2-48 |  | Will continue hacking of overcast Dwall
Fri (05/12) | 05 Dec 2025 | B2-43 |  | No activity
Fri (05/12) | 05 Dec 2025 | GL20-23 |  | Currently observed no disposal activity
Fri (05/12) | 05 Dec 2025 | P35 column |  | 1st lift formwork in progress
Fri (05/12) | 05 Dec 2025 | BR5 opening |  | Continue excavation works
Fri (05/12) | 05 Dec 2025 | BR25 |  | Formwork installation in progress. Plan for casting tonight
Fri (05/12) | 05 Dec 2025 | BR32B |  | Backfilling completed, NDT in progress
Fri (05/12) | 05 Dec 2025 | Exit 1 ECM Pond |  | Current stockpile status
Fri (05/12) | 05 Dec 2025 | P18 |  | Step access erection in progress
Fri (05/12) | 05 Dec 2025 | N2 |  | D04 launched last night. Preparation for tendon strand installation
Fri (05/12) | 05 Dec 2025 | P12 |  | SB preparation for tendon strand installation
Fri (05/12) | 05 Dec 2025 | P3 |  | Drilling works ongoing at p2 side
Fri (05/12) | 05 Dec 2025 | P1 & P2 |  | No activity
Fri (05/12) | 05 Dec 2025 | BRP61 |  | Continues rectification work
Fri (05/12) | 05 Dec 2025 | P51 |  | Hard barricade installation around pile cap excavation area
Fri (05/12) | 05 Dec 2025 | P51 |  | Continue exposing 700mm dia water pipe for supporting
Fri (05/12) | 05 Dec 2025 | P48 |  | Continue formwork closing for last layer caisson
Fri (05/12) | 05 Dec 2025 | DR3 |  | Current status of stockpile
Fri (05/12) | 05 Dec 2025 | P45 |  | No activity. Mini excavator yet to lower down
Fri (05/12) | 05 Dec 2025 | P42 |  | Continue ducting installation for crosshead
Fri (05/12) | 05 Dec 2025 | P40 |  | 2nd lift column rebar cage installation
Fri (05/12) | 05 Dec 2025 | Exit 2 |  | Currently no activity
Fri (05/12) | 05 Dec 2025 | P40 |  | 2nd lift column rebar cage installation in progress
Fri (05/12) | 05 Dec 2025 | B2-49A |  | Rebar works in progress, Installing access to working area
Fri (05/12) | 05 Dec 2025 | B2-48 |  | Current hacking status of overcast dwall. Now changing operator
Fri (05/12) | 05 Dec 2025 | B2-43 |  | No activity
Fri (05/12) | 05 Dec 2025 | BR25 |  | Cleaning ongoing prior to final inspection. Plan for casting tonight
Fri (05/12) | 05 Dec 2025 | BR5 opening | B2-35 | Currently no activity, Earlier photos of excavation for reference
Fri (05/12) | 05 Dec 2025 | P35 |  | Working platform erection ongoing
Fri (05/12) | 05 Dec 2025 | B2-29, B2-30 |  | Currently no disposal activity. Changing of operator and tonight plan for soil shifting, Earlier photos of activities inside for reference — hacking works and soil shifting
Fri (05/12) | 05 Dec 2025 | GL20-23 |  | Continue clearing stockpile
Fri (05/12) | 05 Dec 2025 | BR19A |  | Continue rebar works
Fri (05/12) | 05 Dec 2025 | CCW2 | South side | Hirose plan to complete the waler installation tonight. Works ongoing till 10pm today
Fri (05/12) | 05 Dec 2025 | CCW2 | North side | Waler bracket welding works in progress
Fri (05/12) | 05 Dec 2025 | CCW1 | North side | No activity
Fri (05/12) | 05 Dec 2025 | B1-05 |  | No activity
Fri (05/12) | 05 Dec 2025 | B1-06 |  | No activity
Fri (05/12) | 05 Dec 2025 | B1-04 |  | No activity
Sat (06/12) | 06 Dec 2025 | N2-N3 |  | Installation of duct and clamping beam installation
Sat (06/12) | 06 Dec 2025 | GL20-23 |  | Current stockpile status. Currently observed no activity
Sat (06/12) | 06 Dec 2025 | BR7A opening |  | Continue modular access erection
Sat (06/12) | 06 Dec 2025 | B2-29, B2-30 |  | Continue soil shifting and hacking works (3 KTC exc op,1 telescopic, 1 WH op), Dongah excavator currently no activity
Sat (06/12) | 06 Dec 2025 | P35 |  | Currently no activity
Sat (06/12) | 06 Dec 2025 | BR25 |  | Casting in progress
Sat (06/12) | 06 Dec 2025 | BR5 opening | B2-35 | Excavation in progress
Sat (06/12) | 06 Dec 2025 | Zone 1 |  | No activity this morning. Work arranged at P3 this afternoon
Sat (06/12) | 06 Dec 2025 | Exit 1 |  | Access continue cutting to SHD +2m
Sat (06/12) | 06 Dec 2025 | P40 |  | 2nd lift column shearlinks installation
Sat (06/12) | 06 Dec 2025 | B2-49A |  | Rebar works and RGT installation ongoing. Plan for casting next week
Sat (06/12) | 06 Dec 2025 | B2-48 |  | Clearing debonding sheets
Sat (06/12) | 06 Dec 2025 | Below P40 |  | Dismantling formwork for RC wall
Sat (06/12) | 06 Dec 2025 | B2-43 |  | No activity
Sat (06/12) | 06 Dec 2025 | P51 |  | Hard barricade installed. Continue exposing services
Sat (06/12) | 06 Dec 2025 | P51 |  | TPE bound: exposing services for support
Sat (06/12) | 06 Dec 2025 | P39 column |  | 2nd lift rebar works
Sat (06/12) | 06 Dec 2025 | BR32B |  | Internal dewatering pipe installation ongoing
Sat (06/12) | 06 Dec 2025 | B2-40 |  | No activity, BRP61: Dongah hacking works for barette pile rectification ongoing
Sat (06/12) | 06 Dec 2025 | B2-41, B2-42 |  | No activity
Sat (06/12) | 06 Dec 2025 | P45 |  | Mini yet to lower down
Sat (06/12) | 06 Dec 2025 | DR3 |  | Preparing to remove soil above services
Sat (06/12) | 06 Dec 2025 | DR3 |  | Now mini break down. Repairing on going
Sat (06/12) | 06 Dec 2025 | P47 |  | TT for JGP testing
Sat (06/12) | 06 Dec 2025 | P48 |  | Clearing LSS and preparing for caisson casting
Sat (06/12) | 06 Dec 2025 | CCW1/CCW2 |  | S5 excavation in progress (3 exc, 1 telescopic)
Sat (06/12) | 06 Dec 2025 | CCW2 | north side | Waler welding works and access installation in progress
Sat (06/12) | 06 Dec 2025 | CCW2 | south side | Waler welding works, Struts materials delivery
Sat (06/12) | 06 Dec 2025 | CCW1 | north side | No activity
Sat (06/12) | 06 Dec 2025 | B1-05 |  | No activity
Sat (06/12) | 06 Dec 2025 | B1-06 |  | No activity
Sat (06/12) | 06 Dec 2025 | B1-04 |  | Soil shifting and hacking works ongoing (2 ktc exc op, 1 WH op), Preparing platform for access shifting at this location. The current access at B1-03/B1-05 CJ will be shifted here, Currently observed no disposal activity. 2 telescopic at CCW area
Sat (06/12) | 06 Dec 2025 | P42 crosshead |  | Continue ducting work. P41: prepare platform for crosshead
Sat (06/12) | 06 Dec 2025 | CCW1/CCW2 |  | Continue excavation to S5 level (2 exc op, 1 telescopic)
Sat (06/12) | 06 Dec 2025 | CCW2 | south side | Continue welding works. Hirose today plan for waler concrete packing
Sat (06/12) | 06 Dec 2025 | B1-06 |  | No activity
Sat (06/12) | 06 Dec 2025 | B1-05 |  | No activity
Sat (06/12) | 06 Dec 2025 | B1-04 |  | Soil shifting for disposal works ongoing (2 exc op), Pending lean con casting for the access platform
Sat (06/12) | 06 Dec 2025 | N2-N3 |  | Duct already installed. Netting install back
Sat (06/12) | 06 Dec 2025 | N2-N3 |  | Tendom wire pulling
Sat (06/12) | 06 Dec 2025 | P1 near AWWA home |  | Preparing to lean concrete for falsework base
Sat (06/12) | 06 Dec 2025 | BR19A |  | Formwork installation ongoing at wall area, Continue rebar works, RTO inspection ongoing
Sat (06/12) | 06 Dec 2025 | Exit 2, BR22B |  | No activity
Sat (06/12) | 06 Dec 2025 | P40 |  | Continue 2nd lift works
Sat (06/12) | 06 Dec 2025 | B2-49A |  | Rebar works in progress
Sat (06/12) | 06 Dec 2025 | Below P40 |  | Continue dismantling wall formwork support
Sat (06/12) | 06 Dec 2025 | B2-43 |  | No activity
Sat (06/12) | 06 Dec 2025 | B2-48 |  | No activity
Sat (06/12) | 06 Dec 2025 | P39 |  | 2nd lift column rebar works ongoing
Sat (06/12) | 06 Dec 2025 | B2-40 |  | No activity, BRP61: Dongah continue hacking barrette pile for rectification works
Sat (06/12) | 06 Dec 2025 | B2-41, B2-42 |  | No activity
Sat (06/12) | 06 Dec 2025 | P51 |  | Exposing services at both bounds
Sat (06/12) | 06 Dec 2025 | P37 column |  | Preparing to dismantle 1st lift formwork
Sat (06/12) | 06 Dec 2025 | BR5 opening | B2-35 | Excavation and disposal ongoing
Sat (06/12) | 06 Dec 2025 | DR3 |  | Soft soil removal and replace with hardcore at the base
Sat (06/12) | 06 Dec 2025 | P48 |  | Caisson casting last truck to complete
Sat (06/12) | 06 Dec 2025 | P35 column |  | Waiting for first lift casting
Sat (06/12) | 06 Dec 2025 | BR7 opening |  | Soil disposal works ongoing
Sat (06/12) | 06 Dec 2025 | GL20-23 |  | Observed no activity
Sat (06/12) | 06 Dec 2025 | DR3 |  | Continue removal soil above services
Sat (06/12) | 06 Dec 2025 | P45 |  | No activity. Still arranging mini to lower down
Sat (06/12) | 06 Dec 2025 | BR19A |  | Continue rebar works & shearlinks installation, Started partial formwork installation at wall area, Manpower: 32
Sat (06/12) | 06 Dec 2025 | Exit 2, BR22B |  | No activity
Sat (06/12) | 06 Dec 2025 | P21 |  | Shifting of soil stockpile
Sat (06/12) | 06 Dec 2025 | Falsework erection for P18 |  | 7 workers. Target to complete latest by Monday
Mon (08/12) | 08 Dec 2025 | P18 SB downchainage |  | Falsework erection for segment launching
Mon (08/12) | 08 Dec 2025 | P51 |  | Rebar work in progress for utility stump. Total 8nos to do
Mon (08/12) | 08 Dec 2025 | P51 |  | Current status of exposing services for support. Need to clear stagnant water.Now tea break
Mon (08/12) | 08 Dec 2025 | P51 changi bound |  | Status of exposing 700mm dia water pipe
Mon (08/12) | 08 Dec 2025 | P18 |  | Continue falsework erection segment launching
Mon (08/12) | 08 Dec 2025 | P18 |  | Levelling works in progress for crane parking (for lifter shifting from P19 to P17)
Mon (08/12) | 08 Dec 2025 | N6 |  | Segment adjustment in progress
Mon (08/12) | 08 Dec 2025 | P47 |  | Already set up rig for P47
Mon (08/12) | 08 Dec 2025 | P48 |  | Now no activity. Balance 10% of caisson for 5th layer
Mon (08/12) | 08 Dec 2025 | DR3 |  | Now soil stockpile already less
Mon (08/12) | 08 Dec 2025 | P45 |  | Already lowered down mini and resume excavation
Mon (08/12) | 08 Dec 2025 | P41 |  | Prepare platform for P41 crosshead
Mon (08/12) | 08 Dec 2025 | P42 changi bound |  | Handover to Wendyng for shear link. WH working for ducting at TPE bound. Wednesday to full handover
Mon (08/12) | 08 Dec 2025 | P41 |  | Casting for falsework base done
Mon (08/12) | 08 Dec 2025 | P40 |  | Column last lift formwork closing in progress. Tomorrow to cast
Mon (08/12) | 08 Dec 2025 | P39 |  | Column last lift rebar work
Mon (08/12) | 08 Dec 2025 | BR7 opening |  | *B2-29, B2-30*: Continue excavation and disposal works. Can already see the opening area at BR5, 2 exc working inside + 1 telescopic, 1 WH mini & 1 Dongah exc currently no activity
Mon (08/12) | 08 Dec 2025 | P3 |  | No activity. Tmr to start formwork installation
Mon (08/12) | 08 Dec 2025 | BR25 |  | No activity
Mon (08/12) | 08 Dec 2025 | BR5 opening |  | *B2-35*: Excavation and disposal ongoing towards B2-31/32 area, 2 exc working inside + 1 telescopic
Mon (08/12) | 08 Dec 2025 | P19 |  | Preparation work for lifter shifting
Mon (08/12) | 08 Dec 2025 | BR19A |  | Continue formwork installation
Mon (08/12) | 08 Dec 2025 | Exit 2, BR22B |  | No activity
Mon (08/12) | 08 Dec 2025 | P8 |  | Preparing materials to shift to P3 for rectification work
Mon (08/12) | 08 Dec 2025 | B2-49A |  | Continue rebar works. Plan for casting tmr
Mon (08/12) | 08 Dec 2025 | B2-48 |  | No activity
Mon (08/12) | 08 Dec 2025 | Below P40 |  | Patching tie rod holes for RC wall
Mon (08/12) | 08 Dec 2025 | B2-43 |  | No activity
Mon (08/12) | 08 Dec 2025 | P40 |  | 2nd lift formwork installation in progress. Plan for casting tmr
Mon (08/12) | 08 Dec 2025 | P39 |  | 2nd lift column rebar works in progress
Mon (08/12) | 08 Dec 2025 | Exit 1 |  | Current stockpile status
Mon (08/12) | 08 Dec 2025 | BR25 |  | Housekeeping
Mon (08/12) | 08 Dec 2025 | BR5 opening |  | B2-35 excavation continue until 9:30pm. Tonight plan night works at B2-29/30
Mon (08/12) | 08 Dec 2025 | BR8 |  | Currently no activity
Mon (08/12) | 08 Dec 2025 | BR7 opening |  | B2-29/30 continue disposal works
Mon (08/12) | 08 Dec 2025 | GL20-23 |  | Levelling works. Observed no other activity, GL18-20: Observed no activity
Mon (08/12) | 08 Dec 2025 | P51 |  | Rebar fabrication for utility stump
Mon (08/12) | 08 Dec 2025 | P48 |  | WH clearing soft soil and preparation for lean concrete
Mon (08/12) | 08 Dec 2025 | P48 |  | Soft soil clearing for lean concrete
Mon (08/12) | 08 Dec 2025 | P47 |  | Preparing to shift JGP rig to DR4
Mon (08/12) | 08 Dec 2025 | P45 |  | Resume excavation. Long arm shifted
Mon (08/12) | 08 Dec 2025 | CCW2 |  | Continue struts installation, Working platform installation for bracing in progress
Mon (08/12) | 08 Dec 2025 | CCW1 | North side | Clearing loose soil
Mon (08/12) | 08 Dec 2025 | P43-44 |  | BRC laying for platform casting
Mon (08/12) | 08 Dec 2025 | P42 |  | Continue ducting work
Mon (08/12) | 08 Dec 2025 | P40 |  | Column formwork closing done. Tomorrow to cast
Mon (08/12) | 08 Dec 2025 | P39 |  | Tonight will continue column last lift rebar work
Mon (08/12) | 08 Dec 2025 | B1-04 |  | Continue excavation and disposal works (3 exc op, 1 telescopic)
Mon (08/12) | 08 Dec 2025 | B1-05 |  | No activity
Mon (08/12) | 08 Dec 2025 | B1-06 |  | Continue rebar works, Dayshift working till 10pm, Night shift already on site (13 workers + 1 sup)
Tue (09/12) | 09 Dec 2025 | N2 |  | Strand pushing for stressing works
Tue (09/12) | 09 Dec 2025 | BR19A |  | Continue shearlinks and formwork installation
Tue (09/12) | 09 Dec 2025 | Exit 2, BR22B |  | No activity
Tue (09/12) | 09 Dec 2025 | GL18-20 |  | Observed internal shifting of softclay from BR7 opening (B2-29) to this location
Tue (09/12) | 09 Dec 2025 | P12 SB |  | Strand pushing for stressing
Tue (09/12) | 09 Dec 2025 | DR4 |  | Preparing for probing at HDD and soldier pile location for 800mm dia water pipe laying
Tue (09/12) | 09 Dec 2025 | GL21-23 |  | Platform levelling
Tue (09/12) | 09 Dec 2025 | BR7 opening |  | Continue soft soil internal shifting to GL18 area
Tue (09/12) | 09 Dec 2025 | BR25 |  | Dismantling formwork
Tue (09/12) | 09 Dec 2025 | BR5 opening | B2-35 | Continue excavation below
Tue (09/12) | 09 Dec 2025 | P26 column |  | 1st stage shearlinks installation
Tue (09/12) | 09 Dec 2025 | DR3 |  | Continue soft soil removal
Tue (09/12) | 09 Dec 2025 | P47 |  | JGP testing started for SPT
Tue (09/12) | 09 Dec 2025 | P48 |  | Continue soft soil removal
Tue (09/12) | 09 Dec 2025 | P51 |  | Continue fabrication of utility stump
Tue (09/12) | 09 Dec 2025 | P51 |  | Manual excavation at south side
Tue (09/12) | 09 Dec 2025 | P51 |  | No activity at north side
Tue (09/12) | 09 Dec 2025 | P47 |  | JGP Testing in progress
Tue (09/12) | 09 Dec 2025 | P45 |  | Resume excavation
Tue (09/12) | 09 Dec 2025 | DR3 |  | Excavation to FEL in progress..only 1 mini excavator and long arm working here
Tue (09/12) | 09 Dec 2025 | P48 |  | Soil clearing at south side
Tue (09/12) | 09 Dec 2025 | B2-40 |  | No activity
Tue (09/12) | 09 Dec 2025 | B2-43 |  | No activity
Tue (09/12) | 09 Dec 2025 | B2-48 |  | Continues PU grouting (3 Workers) for Dwall
Tue (09/12) | 09 Dec 2025 | GL18-20 |  | Softclay disposal ongoing
Tue (09/12) | 09 Dec 2025 | BR8 area |  | Currently no activity
Tue (09/12) | 09 Dec 2025 | B2-35 |  | Excavation and disposal in progress
Tue (09/12) | 09 Dec 2025 | BR25 |  | Currently no activity
Tue (09/12) | 09 Dec 2025 | B2-49A |  | Shear links & formwork installation in progress, target to cast it tonight
Tue (09/12) | 09 Dec 2025 | Exit 1 |  | Current stockpile
Tue (09/12) | 09 Dec 2025 | P3 |  | Formwork installation for PT replacement continue
Tue (09/12) | 09 Dec 2025 | P39 |  | 2nd lift rebar work in progress
Tue (09/12) | 09 Dec 2025 | P40 |  | Scaffold erection for access
Tue (09/12) | 09 Dec 2025 | P42 |  | Continue with tendom duct laying. P41: falsework erection in progress
Tue (09/12) | 09 Dec 2025 | P18 |  | Falsework erection done. Left to continue hollow section installation
Tue (09/12) | 09 Dec 2025 | N6 |  | Platform preparation and segment adjusting work
Tue (09/12) | 09 Dec 2025 | N2 |  | Tendom wire pulling. Tomorrow plan to complete. Stressing work will be after casting done by WH
Tue (09/12) | 09 Dec 2025 | P51 |  | Continue utility stump fabrication
Tue (09/12) | 09 Dec 2025 | P48 |  | Lowering down rebars
Tue (09/12) | 09 Dec 2025 | P48 |  | Clearing soft soil and preparation for formwork closing
Tue (09/12) | 09 Dec 2025 | P47 |  | Today one number SPT done
Tue (09/12) | 09 Dec 2025 | DR3 |  | Continue removal of soft soil
Tue (09/12) | 09 Dec 2025 | DR3 |  | Continue excavation to FEL
Tue (09/12) | 09 Dec 2025 | P43&P44 |  | Platform prepared
Tue (09/12) | 09 Dec 2025 | P42 |  | Balance ducting at TPE bound to complete tomorrow. Shear link installation at Changi bound side
Tue (09/12) | 09 Dec 2025 | P41 |  | Status of falsework erection
Tue (09/12) | 09 Dec 2025 | P40 |  | Preparing for last lift casting
Tue (09/12) | 09 Dec 2025 | P39 |  | Status of column work
Wed (10/12) | 10 Dec 2025 | N2 |  | Top strand pushing completed yesterday. Today to start installation at the bottom part
Wed (10/12) | 10 Dec 2025 | DR4 |  | Probing for ERSS work for 800mm dia water pipe laying. 2nos done for today. Going until 11m depth
Wed (10/12) | 10 Dec 2025 | P51 North |  | Excavation in progress.. mini excavator will be delivered on site today afternoon
Wed (10/12) | 10 Dec 2025 | P47 |  | Trial Trench for JGP testing
Wed (10/12) | 10 Dec 2025 | Dr3 |  | Excavation to FEL in progress
Wed (10/12) | 10 Dec 2025 | P48 |  | Bored pile head hacking at north, caisson wall formwork closing at south
Wed (10/12) | 10 Dec 2025 | P45 |  | Excavation to L4 caisson layer
Wed (10/12) | 10 Dec 2025 | P42 |  | Crosshead shear link installation
Wed (10/12) | 10 Dec 2025 | P41 |  | Crosshead falsework installation
Wed (10/12) | 10 Dec 2025 | Exit 1 |  | Preparing for waler beam is in progress
Wed (10/12) | 10 Dec 2025 | Exit 1 |  | Soil disposal is progress
Wed (10/12) | 10 Dec 2025 | P3 |  | P2 side dismantling of scaffold. Formwork to start at this side today
Wed (10/12) | 10 Dec 2025 | P3 |  | P4 side, formwork installation continue
Wed (10/12) | 10 Dec 2025 | P39 |  | 2nd lift rebar work in progress
Wed (10/12) | 10 Dec 2025 | B2-49A |  | Casting has completed this morning abt 7.45am, total volume 206m3
Wed (10/12) | 10 Dec 2025 | BRP61 |  | Continues rectification work
Wed (10/12) | 10 Dec 2025 | B2-48 |  | Will continue hacking of overcast Dwall
Wed (10/12) | 10 Dec 2025 | P22 |  | Formwork dismantling in progress
Wed (10/12) | 10 Dec 2025 | P15-P16 |  | Mid span stitching to cast tonight
Wed (10/12) | 10 Dec 2025 | N2 |  | Continue tendon strand installation
Wed (10/12) | 10 Dec 2025 | P22 |  | 1st stage column formwork dismantling
Wed (10/12) | 10 Dec 2025 | DR4 |  | Two nos of probing done. 3rd point encountered obstruction at 4.95m depth. Need to varify further
Wed (10/12) | 10 Dec 2025 | P3 |  | Formwork installation and scaffold dismantling at P2 side
Wed (10/12) | 10 Dec 2025 | P3 |  | Current status of Formwork installation at P4 side
Wed (10/12) | 10 Dec 2025 | PMH26-28 |  | No silty discharge to live road during rain
Wed (10/12) | 10 Dec 2025 | P51 |  | All the 8nos of stump rebar done
Wed (10/12) | 10 Dec 2025 | P51 |  | No activity due to rain
Wed (10/12) | 10 Dec 2025 | P48 |  | Continue internal shifting of soil to clear up space
Wed (10/12) | 10 Dec 2025 | P19 |  | Preparing for lifter to lower down
Wed (10/12) | 10 Dec 2025 | P18 |  | Status of falsework erection for segment launching
Wed (10/12) | 10 Dec 2025 | P2-P3 |  | Tendom wire pulling done
Wed (10/12) | 10 Dec 2025 | CCW1 | North side | Witness rock sampling with RTO
Wed (10/12) | 10 Dec 2025 | P51 |  | Concrete on the way for protection bund casting
Wed (10/12) | 10 Dec 2025 | P48 |  | Casting of balance last layer caisson. Today will complete all
Wed (10/12) | 10 Dec 2025 | P47 |  | JGP test in progress. Coring test
Wed (10/12) | 10 Dec 2025 | DR3 |  | Continue excavation and levelling
Wed (10/12) | 10 Dec 2025 | P45 |  | Resume excavation for 4th layer caisson
Wed (10/12) | 10 Dec 2025 | P42 |  | To continue shear link installation
Wed (10/12) | 10 Dec 2025 | P41 |  | Continue secondary beam and preparation for platform installation
Wed (10/12) | 10 Dec 2025 | P39 |  | Night shift team continue with column last lift rebar work
Wed (10/12) | 10 Dec 2025 | CCW1 | North side | Rock samples collected. Total 17 bags
Wed (10/12) | 10 Dec 2025 | CCW2 |  | WH erecting scaffold tower for bracing works, No other activity
Wed (10/12) | 10 Dec 2025 | B1-06 |  | Night shift continue rebar works — 10 workers, 1 sup
Wed (10/12) | 10 Dec 2025 | B1-04 |  | Continue soil shifting and disposal works (1 exc + 1 telescopic working, 2 exc no activity, Access scaffold installation in progress by WH
Wed (10/12) | 10 Dec 2025 | BR19A |  | Continue shearlinks installation and cleaning works. Dayshift till 10pm, No planned night shift here. Night team at B1-06
Wed (10/12) | 10 Dec 2025 | P3 |  | Dismantling of scaffold
Wed (10/12) | 10 Dec 2025 | P18 |  | Placing hollow section for segment launching
Wed (10/12) | 10 Dec 2025 | GL18-20 |  | No activity
Wed (10/12) | 10 Dec 2025 | GL20-23 |  | Ground levelling & arranging steel plates
Wed (10/12) | 10 Dec 2025 | BR8 area |  | No activity
Wed (10/12) | 10 Dec 2025 | BR25 |  | No activity
Wed (10/12) | 10 Dec 2025 | BR5 opening |  | No planned night shift. Tonight nightshift continue at B1-04 area, exit 1 stockpile and BR7 opening
Wed (10/12) | 10 Dec 2025 | BR7 opening |  | Continue soil internal shifting to exit 1 area (1 telescopic, 2 exc)
Thu (11/12) | 11 Dec 2025 | DR4 |  | 1nos probing done until 12m (green). Encounter obstruction at 8.56m (red). Now preparing for yellow area probing. Suspect the obstruction is HDD cable
Thu (11/12) | 11 Dec 2025 | B2-31, B2-32 |  | Excavation and soil shifting in progress (3 exc working + 1 telescopic), Soft clay internal shifting to GL18-20 area (1 exc)
Thu (11/12) | 11 Dec 2025 | P45 |  | Removal of top soil to place utility stump
Thu (11/12) | 11 Dec 2025 | P51 |  | Tidy up the area before continue exposing the services
Thu (11/12) | 11 Dec 2025 | P51 changi bound |  | Exposing utility. Need to continue clear water
Thu (11/12) | 11 Dec 2025 | B2-43 |  | No activity
Thu (11/12) | 11 Dec 2025 | B2-48 |  | Continue hacking of overcast Dwall
Thu (11/12) | 11 Dec 2025 | BR8 area |  | No activity
Thu (11/12) | 11 Dec 2025 | B2-35 |  | Continue excavation and disposal works
Thu (11/12) | 11 Dec 2025 | BR7 opening |  | Continue excavation works
Thu (11/12) | 11 Dec 2025 | GL18-20 stockpile area |  | Currently observed no activity
Thu (11/12) | 11 Dec 2025 | B2-49A |  | No activity
Thu (11/12) | 11 Dec 2025 | B2-48 |  | Continue with 1st pass of PU grouting
Thu (11/12) | 11 Dec 2025 | BRP61 |  | Rectification work is in progress
Thu (11/12) | 11 Dec 2025 | P48 |  | Clearing materials for prop concrete
Thu (11/12) | 11 Dec 2025 | Exit 1 |  | Excavation in progress to prepare tor waler beam works
Thu (11/12) | 11 Dec 2025 | P45 |  | Continue excavation with mini and long arm
Thu (11/12) | 11 Dec 2025 | Exit 1 |  | Current stockpile status
Thu (11/12) | 11 Dec 2025 | P39 |  | Last lift column rebar work
Thu (11/12) | 11 Dec 2025 | P41 |  | Current status of work platform installation
Thu (11/12) | 11 Dec 2025 | P42 |  | Side formwork closing in progress
Thu (11/12) | 11 Dec 2025 | P26 |  | 1st stage column casting
Thu (11/12) | 11 Dec 2025 | N6 D01 |  | Alignment still not confirmed. A bit of adjustment required tmr during dayshift. Nightshift planned for D02 segment launching
Thu (11/12) | 11 Dec 2025 | P38, 39 and 40 |  | No activity
Thu (11/12) | 11 Dec 2025 | P42 crosshead |  | Section 1 and 2 formwork closed. Section 3 to complete links installation tonight
Thu (11/12) | 11 Dec 2025 | P45 |  | Excavation for 4th layer casion will continue until 9pm
Thu (11/12) | 11 Dec 2025 | P48 |  | Excavator shifting. Nightshift to cast concrete prop
Thu (11/12) | 11 Dec 2025 | P51 |  | Excavation for Utility stump, work until 930pm
Fri (12/12) | 12 Dec 2025 | B2-43 |  | No activity
Fri (12/12) | 12 Dec 2025 | B2-48 |  | Continues PU grouting for Dwall
Fri (12/12) | 12 Dec 2025 | B2-48 |  | Hacking of overcast Dwall is in progre
Fri (12/12) | 12 Dec 2025 | B2-49A |  | Dismantling of formwork
Fri (12/12) | 12 Dec 2025 | B2-40 |  | Continues excavation & soil disposal
Fri (12/12) | 12 Dec 2025 | Exit 1 |  | Waler Beam, Current excavation status & soil disposal
Fri (12/12) | 12 Dec 2025 | Exit 1 |  | Current stockpile status
Fri (12/12) | 12 Dec 2025 | P22 |  | 1st lift Column Formwork dismantled
Fri (12/12) | 12 Dec 2025 | N3-N2 |  | Formwork shifting for midspan stitching. Tmr to start
Fri (12/12) | 12 Dec 2025 | P3 Rectification |  | Plywood laying in progress for P2 side
Fri (12/12) | 12 Dec 2025 | DR4 |  | Preparation for footpath diversion..temporary stop due to heavy rain
Fri (12/12) | 12 Dec 2025 | 800mm PW ERSS probing |  | No activity
Fri (12/12) | 12 Dec 2025 | P51 north |  | Current excavation status. No activity due to heavy rain
Fri (12/12) | 12 Dec 2025 | P51 South |  | Stump construction ongoing..going to cast 2 nos stump today
Fri (12/12) | 12 Dec 2025 | P48 |  | Concrete plug casting completed last night. Today completed scaffolding erection. Tomorrow going to start S2 removal
Fri (12/12) | 12 Dec 2025 | P47 |  | Trial Trench for JGP Testing
Fri (12/12) | 12 Dec 2025 | P47 |  | JGP Testing work in progress
Fri (12/12) | 12 Dec 2025 | Dr3 |  | Excavation to FEL in progress
Fri (12/12) | 12 Dec 2025 | P45 |  | No activity
Fri (12/12) | 12 Dec 2025 | CCW2 |  | Continue erecting scaffold platform, Hirose continue bracing welding works & struts installation. Works till 10pm
Fri (12/12) | 12 Dec 2025 | CCW1 | north side | No activity
Fri (12/12) | 12 Dec 2025 | CCW1 | south side | No excavation activity
Fri (12/12) | 12 Dec 2025 | B1-05 |  | Rebar works in progress. Now both dayshift and nightshift on site. Night shift will continue here (10+1)
Fri (12/12) | 12 Dec 2025 | B1-06 |  | Shearlinks and hyrib installation ongoing
Fri (12/12) | 12 Dec 2025 | B1-04 |  | KTC dayshift till 10pm. Currently 3 excavators & 1 telescopic working. Nightshift continue excavation works here (1 exc, 1 telescopic), WH hacking excess concrete by mini breaker
Fri (12/12) | 12 Dec 2025 | Exit 2, BR22B |  | No activity
Fri (12/12) | 12 Dec 2025 | BR19A |  | Currently no activity. Pending WH/Alliance confirmation
Fri (12/12) | 12 Dec 2025 | B2-31 |  | Hacking works ongoing, B2-32: Continue excavation and internal shifting works to RTSA land tonight
Fri (12/12) | 12 Dec 2025 | B2-35 |  | No activity
Fri (12/12) | 12 Dec 2025 | P38 |  | 2nd lift column rebar works in progress
Fri (12/12) | 12 Dec 2025 | B2-43 |  | No activity
Fri (12/12) | 12 Dec 2025 | B2-49A |  | Preparing for CJ hacking works
Fri (12/12) | 12 Dec 2025 | B2-48 |  | Hacking of excess concrete till 10pm
Fri (12/12) | 12 Dec 2025 | B2-40 |  | No activity. No planned excavation activity tonight
Fri (12/12) | 12 Dec 2025 | Exit 1 stockpile area |  | Observed no activity
Sat (13/12) | 13 Dec 2025 | P26 |  | No activity. Curing ongoing
Sat (13/12) | 13 Dec 2025 | P35 |  | No activity
Sat (13/12) | 13 Dec 2025 | P37 |  | No activity
Sat (13/12) | 13 Dec 2025 | P38 |  | Column 2nd lift rebar installation, P39: Scaffold dismantling for Formwork closing
Sat (13/12) | 13 Dec 2025 | P40 |  | No activity. Curing in progress
Sat (13/12) | 13 Dec 2025 | P41 |  | Continue Falsework erection
Sat (13/12) | 13 Dec 2025 | P42 |  | Formwork closing in progress
Sat (13/12) | 13 Dec 2025 | P45 |  | Excavation for 4th layer
Sat (13/12) | 13 Dec 2025 | DR3 |  | Excavation works in progress
Sat (13/12) | 13 Dec 2025 | P47 |  | Preparation for SPT coring
Sat (13/12) | 13 Dec 2025 | P48 |  | Preparation for s2 struts removal
Sat (13/12) | 13 Dec 2025 | P51 |  | Manual excavation for utility bracket installation
Sat (13/12) | 13 Dec 2025 | Z4 |  | Holding down bolts installation at utility footings in progress
Sat (13/12) | 13 Dec 2025 | DR4 |  | Preparation for probing test for Z3: SP-06
Sat (13/12) | 13 Dec 2025 | N6 |  | Segment adjustment completed. Preparation for N6-D03 launching tonight
Sat (13/12) | 13 Dec 2025 | N2-N3 midspan |  | Preparation for Formwork closing for stitching works
Sat (13/12) | 13 Dec 2025 | P1 & P2 |  | No activity
Sat (13/12) | 13 Dec 2025 | P3 Rectification |  | Continue Formwork installation works
Sat (13/12) | 13 Dec 2025 | B1-04 |  | Excavation in progress (1 exc, 1 ripper, 1 telescopic), Soil internal shifting to exit 3 stockpile
Sat (13/12) | 13 Dec 2025 | B1-06 |  | Shearlinks installation
Sat (13/12) | 13 Dec 2025 | B1-05 |  | Rebar works in progress
Sat (13/12) | 13 Dec 2025 | BR19A |  | Casting postponed to today (Saturday)
Sat (13/12) | 13 Dec 2025 | P41 |  | Netting and base jack installation works in progress
Sat (13/12) | 13 Dec 2025 | P39 |  | Scaffold dismantling for Formwork closing completed, P38: 2nd lift column rebar installation in progress
Sat (13/12) | 13 Dec 2025 | P38 |  | 2nd lift column rebar works in progress
Sat (13/12) | 13 Dec 2025 | BR8 area |  | No activity
Sat (13/12) | 13 Dec 2025 | GL18-20 |  | Observed no activity for stockpile
Sat (13/12) | 13 Dec 2025 | P42 |  | Formwork closing completed. Tmr to cast Crosshead
Sat (13/12) | 13 Dec 2025 | B2-29/30, B2-31/32 |  | Continue soil shifting (2 exc)
Sat (13/12) | 13 Dec 2025 | P45 |  | Continue 4th layer excavation works
Sat (13/12) | 13 Dec 2025 | DR3 |  | Excavation and levelling ongoing
Sat (13/12) | 13 Dec 2025 | P47 |  | Continue SPT coring tests
Sat (13/12) | 13 Dec 2025 | P48 |  | S2 struts cutting and removal ongoing
Sat (13/12) | 13 Dec 2025 | P51 |  | Manual excavation for utility support ongoing
Sat (13/12) | 13 Dec 2025 | P51 |  | NB side slope lean concrete in progress
Sat (13/12) | 13 Dec 2025 | P3 |  | NB side continue c-channel and plywood laying works
Mon (15/12) | 15 Dec 2025 | B2-31 |  | Started exposing couplers (Wendyng) and preparing for lean con. Plan for lean con tonight, B2-32:, Continue excavation and soil shifting (4 exc, 1 telescopic), B2-33/34/35:, Continue excavation and hacking ongoing (1 exc, 1 breaker , 1 exc on standby)
Mon (15/12) | 15 Dec 2025 | DR4 |  | As of now no probing work. Manpower at P47 area
Mon (15/12) | 15 Dec 2025 | P51 |  | Exposing services for utility support
Mon (15/12) | 15 Dec 2025 | GL18-20 stockpile |  | Currently observed no activity. 1 exc on standby
Mon (15/12) | 15 Dec 2025 | BR25 |  | Wall rebar installation & erecting new access ongoing
Mon (15/12) | 15 Dec 2025 | BR8 stockpile area |  | Observed no activity
Mon (15/12) | 15 Dec 2025 | DR3 |  | Continue removal of soft soil to replace with hardcore
Mon (15/12) | 15 Dec 2025 | P47 |  | Pipe sleeves installation for JGP testing
Mon (15/12) | 15 Dec 2025 | P45 |  | Continue excavation for 4th layer caisson. Half handover for bored pile hacking
Mon (15/12) | 15 Dec 2025 | P39 |  | Column 2nd lift formwork closing. Rebar work in progress for P38
Mon (15/12) | 15 Dec 2025 | P41 |  | Preparing for side formwork closing. This will be next crosshead to cast
Mon (15/12) | 15 Dec 2025 | P43 |  | Assembling of starter hanger
Mon (15/12) | 15 Dec 2025 | P42 crosshead |  | Curing
Tue (16/12) | 16 Dec 2025 | B2-32 |  | Continue hacking works & soil shifting (1 breaker, 3 excavators), B2-29/30:, Continue disposal works (1 telescopic)
Tue (16/12) | 16 Dec 2025 | B2-333/34/35 |  | Excavation in progress (2 exc, 1 telescopic)
Tue (16/12) | 16 Dec 2025 | 800mm PW |  | Excavation on going near P49
Tue (16/12) | 16 Dec 2025 | N2-N3 midspan |  | Wet stitch formwork closed. To cast tonight after last bus
Tue (16/12) | 16 Dec 2025 | P48 |  | Pile cap bottom rebar work in progress
Tue (16/12) | 16 Dec 2025 | P47 |  | Continue JGP testing
Tue (16/12) | 16 Dec 2025 | P51 |  | Going to remove access for fully excavation of P51
Tue (16/12) | 16 Dec 2025 | DR3 |  | Excavation to FEL
Tue (16/12) | 16 Dec 2025 | P41 |  | Crosshead side formwork closing in progress
Tue (16/12) | 16 Dec 2025 | P39 |  | Column last lift formwork closing in progress. P38: column last lift rebar also going to complete
Tue (16/12) | 16 Dec 2025 | B2-49A |  | No activity
Tue (16/12) | 16 Dec 2025 | B2-48 |  | Currently observed no activity
Tue (16/12) | 16 Dec 2025 | B2-43 |  | No activity
Tue (16/12) | 16 Dec 2025 | B2-40 |  | Observed dasyhift excavation works done for the day & currently no activity
Tue (16/12) | 16 Dec 2025 | BR25 |  | Currently observed no activity
Tue (16/12) | 16 Dec 2025 | B2-35 |  | Excavation ongoing
Tue (16/12) | 16 Dec 2025 | Exit 1 waler beam area |  | Lean concrete levelling ongoing
Tue (16/12) | 16 Dec 2025 | Exit 1 |  | Current stockpile status
Tue (16/12) | 16 Dec 2025 | B2-33/34/35 |  | Continue excavation (3 exc)
Tue (16/12) | 16 Dec 2025 | N6 |  | Preparation for segment launching tonight N6-D6
Tue (16/12) | 16 Dec 2025 | B2-32 |  | Preparing for lean concrete casting tonight
Tue (16/12) | 16 Dec 2025 | B2-31 |  | Currently no activity
Tue (16/12) | 16 Dec 2025 | B2-29 |  | Continue soil shifitng (1 exc, 1 telescopic)
Tue (16/12) | 16 Dec 2025 | BR8 |  | Observed no activity
Tue (16/12) | 16 Dec 2025 | GL18-20 stockpile |  | Observed no activity
Tue (16/12) | 16 Dec 2025 | P12 |  | Dismantle stitching formwork
Tue (16/12) | 16 Dec 2025 | Exit 2, BR20A, BR22B |  | Observed no activity
Tue (16/12) | 16 Dec 2025 | Zone 1 |  | P1-P5 no activity
Tue (16/12) | 16 Dec 2025 | CCW2 |  | Hirose nightshift preparing for bracing welding works (2 welders, 1 sup)
Tue (16/12) | 16 Dec 2025 | CCW1 | south side | No activity
Tue (16/12) | 16 Dec 2025 | CCW1 | north side | No activity
Tue (16/12) | 16 Dec 2025 | B1-05 |  | Rebar works in progress
Tue (16/12) | 16 Dec 2025 | B1-04 |  | No activity
Tue (16/12) | 16 Dec 2025 | B1-03 |  | Excavation in progress (2 exc, 1 telescopic)
Tue (16/12) | 16 Dec 2025 | 800mm PW at DR4 |  | Preparation work for pipe sleeve installation
Tue (16/12) | 16 Dec 2025 | 800mm PW near P49 |  | Preparation joint welding work
Tue (16/12) | 16 Dec 2025 | P48 |  | Pile cap bottom rebar in progress
Tue (16/12) | 16 Dec 2025 | DR3 |  | Grout hacking work in progress
Tue (16/12) | 16 Dec 2025 | P47 |  | JGP Testing work in progress
Tue (16/12) | 16 Dec 2025 | P45 |  | No activity
Tue (16/12) | 16 Dec 2025 | B2-31 |  | Lean concrete cast last night
Wed (17/12) | 17 Dec 2025 | 800mm PW |  | Preparation work for pipe laying near P49
Wed (17/12) | 17 Dec 2025 | P51 |  | Temporary work stop for exposing utility due to continue rain
Wed (17/12) | 17 Dec 2025 | P51 |  | Continue removal of top soil at access area
Wed (17/12) | 17 Dec 2025 | B2-31 |  | Couplers exposing ongoing
Wed (17/12) | 17 Dec 2025 | B2-48 |  | No activity
Wed (17/12) | 17 Dec 2025 | B2-32 |  | Lean concrete in progress
Wed (17/12) | 17 Dec 2025 | B2-33/34/35 |  | Excavation in progress
Wed (17/12) | 17 Dec 2025 | DR3 |  | Grout hacking work in progress
Wed (17/12) | 17 Dec 2025 | P45 |  | No activity
Wed (17/12) | 17 Dec 2025 | P22 |  | Scaffold erected for column 2nd stage rebar works
Wed (17/12) | 17 Dec 2025 | Exit 1 / B2-49B |  | Continues preparing for waler beam construction
Wed (17/12) | 17 Dec 2025 | P18 |  | Stressing cage modification
Wed (17/12) | 17 Dec 2025 | Exit 1 |  | Current stockpile status
Wed (17/12) | 17 Dec 2025 | P48 |  | Continue base rebar for pile cap
Wed (17/12) | 17 Dec 2025 | P48 |  | Continue rebar work during rain. Temporary provided canvas sheet above
Wed (17/12) | 17 Dec 2025 | DR3 changi bound |  | Levelling done. Left pile to hack. Continue remove soft soil at TPE bound
Wed (17/12) | 17 Dec 2025 | P47 |  | JGP left two point to complete for tunnel. Next location will be junction
Wed (17/12) | 17 Dec 2025 | P45 |  | Now temporary no activity. HSL need to mobilize mini for pile head hacking
Wed (17/12) | 17 Dec 2025 | P41 |  | Formwork left one piece before can full swing rebar for crosshead. Rebar work started
Wed (17/12) | 17 Dec 2025 | B2-40 |  | Continues excavation & internal transfer by 1 excavator & 1 telescopic
Wed (17/12) | 17 Dec 2025 | P39 2nd lift column |  | Support installation in progress
Wed (17/12) | 17 Dec 2025 | P40 |  | Working platform removal to fully remove formwork
Wed (17/12) | 17 Dec 2025 | P45 |  | Mini mobilized. Now waiting for crane to lower down
Wed (17/12) | 17 Dec 2025 | P47 |  | 2nd last JGP grouting in progress
Wed (17/12) | 17 Dec 2025 | P48 |  | Bottom rebar work in progress
Wed (17/12) | 17 Dec 2025 | DR3 |  | Soft soil removal and replace with hardcore
Wed (17/12) | 17 Dec 2025 | P51 |  | Base plate placing for utility support
Wed (17/12) | 17 Dec 2025 | P51 |  | Fully removal of top soil
Wed (17/12) | 17 Dec 2025 | DR4 |  | Preparing for probing work at Zone 2
Wed (17/12) | 17 Dec 2025 | CCW2 |  | KP bracing welding & installation works ongoing. Dayshift till 10pm, nightshift will continue
Wed (17/12) | 17 Dec 2025 | CCW2 |  | Strut preloading in progress
Wed (17/12) | 17 Dec 2025 | CCW1 north & | south side | No activity
Wed (17/12) | 17 Dec 2025 | B1-05 |  | Rebar works in progress
Wed (17/12) | 17 Dec 2025 | B1-04 |  | No activity
Wed (17/12) | 17 Dec 2025 | B1-03 |  | Excavation in progress
Wed (17/12) | 17 Dec 2025 | BR20A |  | Hacking works stopped for the day
Wed (17/12) | 17 Dec 2025 | Exit 2, BR22B |  | No activity
Wed (17/12) | 17 Dec 2025 | GL18-20 stockpile |  | No activity observed
Wed (17/12) | 17 Dec 2025 | BR8 stockpile |  | No activity observed
Wed (17/12) | 17 Dec 2025 | BR25 |  | Partial formwork installation for wall
Wed (17/12) | 17 Dec 2025 | B2-40 |  | Excavation ongoing
Wed (17/12) | 17 Dec 2025 | B2-43 |  | No activity
Wed (17/12) | 17 Dec 2025 | Exit 1 waler area |  | CJ hacking ongoing
Wed (17/12) | 17 Dec 2025 | B2-33/34/35 |  | Excavation in progress. Tonight KTC arranged nightshift at this area
Wed (17/12) | 17 Dec 2025 | B2-40 |  | Nightshift arranged here tonight
Wed (17/12) | 17 Dec 2025 | B2-31 |  | Access installation & barricades in progress, B2-32: Lean concrete done, B2-29/30: Currently no activity
Wed (17/12) | 17 Dec 2025 | P22 |  | Scaffold erected for column 2nd stage rebar works
Wed (17/12) | 17 Dec 2025 | P18 |  | SB falsework erection status for downchainage
Wed (17/12) | 17 Dec 2025 | P48 |  | Pile cap bottom rebar work in progress
Thu (18/12) | 18 Dec 2025 | Exit 1/B2-49B |  | Going to start rebar work for waler beam & night shift plan to start today
Thu (18/12) | 18 Dec 2025 | Exit 1 |  | Current stockpile manage by 1 excavator operator
Thu (18/12) | 18 Dec 2025 | B2-48 |  | No activity
Thu (18/12) | 18 Dec 2025 | B2-40 |  | Continues excavation & disposal by 1 excavator & 1 telescopic
Thu (18/12) | 18 Dec 2025 | P18 SB downchainage |  | Platform installation for segment launching
Thu (18/12) | 18 Dec 2025 | P18 SB upchainage |  | Adjustable jack installation in progress. Launching this Saturday night
Thu (18/12) | 18 Dec 2025 | N6 downchainage segment |  | Steel blister dismantling and preparation for 2nd stage tensioning
Thu (18/12) | 18 Dec 2025 | P41 |  | Scaffold support installation for rebar works
Thu (18/12) | 18 Dec 2025 | P39 column |  | Casting platform erected. Tonight to cast
Thu (18/12) | 18 Dec 2025 | P45 |  | Hacking of pile head and 4th layer excavation status. Workers on dinner break. To resume later for nightshift work
Thu (18/12) | 18 Dec 2025 | DR3 |  | Levelling in progress. Tmr to lean con
Thu (18/12) | 18 Dec 2025 | P48 pile cap |  | Tob bar installation in progress
Thu (18/12) | 18 Dec 2025 | P51 |  | No more activity
Thu (18/12) | 18 Dec 2025 | P18 downchainage |  | Platform installation continue for segment launching. Work until 930pm
Thu (18/12) | 18 Dec 2025 | P45 |  | Preparing lower down excavator for bored pile hacking at North
Thu (18/12) | 18 Dec 2025 | DR3 |  | Excavation to FEL
Thu (18/12) | 18 Dec 2025 | P48 |  | Bar chair installation in progress
Thu (18/12) | 18 Dec 2025 | DR4 |  | Rig under maintenance
Thu (18/12) | 18 Dec 2025 | B2-33 |  | Hacking works ongoing, B2-35: Excavation in progress
Thu (18/12) | 18 Dec 2025 | B2-32 |  | Lean concrete completed
Thu (18/12) | 18 Dec 2025 | B2-29 |  | Lean con ground levelling ongoing
Thu (18/12) | 18 Dec 2025 | BR7 area |  | Steel plates cleaning ongoing
Fri (19/12) | 19 Dec 2025 | P26 |  | Scaffold erection for 2nd stage column construction
Fri (19/12) | 19 Dec 2025 | B2-49A |  | No activity
Fri (19/12) | 19 Dec 2025 | P45 |  | Bored pile hacking
Fri (19/12) | 19 Dec 2025 | DR3 |  | Excavation to FEL in progress. Today going to lean con at south side
Fri (19/12) | 19 Dec 2025 | P51 |  | Excavation to expose utilities at center portion
Fri (19/12) | 19 Dec 2025 | DR4 |  | No activity
Fri (19/12) | 19 Dec 2025 | P48 |  | Pile cap top bar installation. Target Saturday night casting
Fri (19/12) | 19 Dec 2025 | P18 |  | Platform level adjusting
Fri (19/12) | 19 Dec 2025 | P2-41 / B2-42 |  | Preloading test has arranged for the last strut
Fri (19/12) | 19 Dec 2025 | B2-40 |  | Continues excavations @ B2-40, partial lean concrete was done last night
Fri (19/12) | 19 Dec 2025 | CCE2 |  | Continues cutting down to +2 & soil disposal
Fri (19/12) | 19 Dec 2025 | Exit 1 |  | Rebar installation is in progress for waler beam
Fri (19/12) | 19 Dec 2025 | Exit 1 |  | Current stockpile status & managed by 1 excavator
Fri (19/12) | 19 Dec 2025 | North Ramp N6 |  | Tendom wite pulling
Fri (19/12) | 19 Dec 2025 | P18 |  | Preparing for segment launching tonight
Fri (19/12) | 19 Dec 2025 | P2 |  | No activity already. DE160 still have not open back the lane yet
Fri (19/12) | 19 Dec 2025 | P3 |  | Continue drilling for starter bar planting
Fri (19/12) | 19 Dec 2025 | DR4 |  | Day shift already end work. Night shift yet to report to woek
Fri (19/12) | 19 Dec 2025 | P51 |  | One main beam installed
Fri (19/12) | 19 Dec 2025 | DR3 |  | Base lean concrete in progress
Fri (19/12) | 19 Dec 2025 | P48 |  | Pile cap rebar on going. Tomorrow to cast
Fri (19/12) | 19 Dec 2025 | P45 |  | No activity of pile hacking already
Fri (19/12) | 19 Dec 2025 | P42 |  | Crosshead curing
Fri (19/12) | 19 Dec 2025 | P41 crosshead |  | Top bar in progress
Fri (19/12) | 19 Dec 2025 | P41 |  | Side formwork preparation
Fri (19/12) | 19 Dec 2025 | P39 |  | Column last lift cast. P38: column last lift rebar work in progress
Fri (19/12) | 19 Dec 2025 | P51 |  | Footing casting done. Footpath also done
Sat (20/12) | 20 Dec 2025 | DR4 |  | Pavement hacking in progress. Tonight to continue TT here for pipe sleeve installation
Sat (20/12) | 20 Dec 2025 | P51 |  | Utility support main beam welding works
Sat (20/12) | 20 Dec 2025 | P45 |  | Pile head hacking and clearing of debris
Sat (20/12) | 20 Dec 2025 | P44 |  | JGP coring and SPT
Sat (20/12) | 20 Dec 2025 | P43 |  | Crosshead rebar works
Sat (20/12) | 20 Dec 2025 | P51 |  | Manual excavation continue for Utility support installation
Sat (20/12) | 20 Dec 2025 | P44 |  | JGP testing continue. 2.d point for the day
Sat (20/12) | 20 Dec 2025 | P18 |  | Area preparation for crane parking. Tonight to launch P18 SB D01
Sun (21/12) | 21 Dec 2025 | B1-01 / B1-03 |  | Excavation in progress by 2 excavator operators
Sun (21/12) | 21 Dec 2025 | B1-03 / B1-04 |  | Partial B1-03 has leaned concrete tgt with B1-04 last night
Sun (21/12) | 21 Dec 2025 | B1-05 / B1-06 |  | Top bar and shear links installation is in progress
Sun (21/12) | 21 Dec 2025 | BR20A |  | Hacking of overcast Dwall has completed, today plan to do partial lean concrete today
Sun (21/12) | 21 Dec 2025 | Exit 2 |  | No activity, understand Hirose is off today
Sun (21/12) | 21 Dec 2025 | B2-31 / B2-32 |  | Ongoing bottom bar installation by Wendyng
Sun (21/12) | 21 Dec 2025 | B2-33 / B2-34 |  | Excavation in progress by 5 excavator operators
Sun (21/12) | 21 Dec 2025 | Vent shaft / BR25 |  | No activity
Sun (21/12) | 21 Dec 2025 | B2-40 |  | Continues excavation & soil disposal by 2 excavator & 1 telescopic
Sun (21/12) | 21 Dec 2025 | B2-43 |  | No activity
Sun (21/12) | 21 Dec 2025 | B2-48 / B2-49A |  | No activity
Sun (21/12) | 21 Dec 2025 | Exit 1 |  | Ongoing rebar & formwork installation for waler beam
Sun (21/12) | 21 Dec 2025 | Exit 1 |  | Current stockpile & no excavator arranged for today
Sun (21/12) | 21 Dec 2025 | B1-01 / B1-03 |  | Continues excavation by 1 excavator
Sun (21/12) | 21 Dec 2025 | B1-05 |  | Day shift will continue rebar work until 5pm, and night shift has arranged to continue from 8pm
Sun (21/12) | 21 Dec 2025 | BR20A |  | Concrete has just arrived site for lean concrete
Sun (21/12) | 21 Dec 2025 | BR9 |  | Waiting for concrete to start casting for flood barrier wall
Sun (21/12) | 21 Dec 2025 | B2-31 / B2-32 |  | Continues bottom bar installation, understand that night shift has also, been arranged
Sun (21/12) | 21 Dec 2025 | B2-33 / B2-34 |  | Continues excavation & soil disposal, night shift will come @ 8pm
Sun (21/12) | 21 Dec 2025 | B2-40 |  | Plan to finish the excavation for the slab today & will lean concrete tomorrow
Sun (21/12) | 21 Dec 2025 | Exit 1 |  | Waler Beam, Ongoing rebar & formwork installation will continue by night shift as well. Target to cast it tomorrow
Sun (21/12) | 21 Dec 2025 | CCW1 | South Side | Continues excavation by 2 excavators
Sun (21/12) | 21 Dec 2025 | CCW2 | North Side | Soil disposal by 1 excavator & 1 Telescopic
Mon (22/12) | 22 Dec 2025 | P18 SB 1st pair |  | Segment adjusting in progress
Mon (22/12) | 22 Dec 2025 | P51 |  | 4 main beams installed as of now
Mon (22/12) | 22 Dec 2025 | P51 |  | Continue exposing power duct for support
Mon (22/12) | 22 Dec 2025 | DR4 |  | Soldier pile location marked. Machinery inspection done. Will start installation once documentations are ready
Mon (22/12) | 22 Dec 2025 | DR3 |  | No PLT. Settlement just 0.8mm as of now. So no issue
Mon (22/12) | 22 Dec 2025 | P45 |  | HSL mini break down. WH already bring it up. Now hacking will be done by WH
Mon (22/12) | 22 Dec 2025 | P38 |  | Formwork closing yet to start
Mon (22/12) | 22 Dec 2025 | P42 |  | Crosshead formwork removal. P41: continue rebar work and WH doing ducting work at NB
Mon (22/12) | 22 Dec 2025 | P43-44 |  | Materials shifting for starter hanger assembling
Mon (22/12) | 22 Dec 2025 | P44 |  | All the 8nos of JGP testing done. Left at junction near P45
Tue (23/12) | 23 Dec 2025 | B2-33 |  | Rock coring & splitting ongoing
Tue (23/12) | 23 Dec 2025 | P18 NB |  | Stump for bearing formwork closing
Tue (23/12) | 23 Dec 2025 | B2-31 |  | Dongah continue rebar planting ongoing for last panel, Wendyng continue rebar works
Tue (23/12) | 23 Dec 2025 | B2-34 |  | Excavation and hacking in progress (1 exc, 1 breaker)
Tue (23/12) | 23 Dec 2025 | B2-32 |  | Rebar works in progress, Plan to cast B2-31 and B2-32 this week
Tue (23/12) | 23 Dec 2025 | B2-35 |  | Excavation in progress (2 exc working, 1 exc standby)
Tue (23/12) | 23 Dec 2025 | B2-29, B2-30 |  | Currently no activity
Tue (23/12) | 23 Dec 2025 | B2-49A |  | Continues excavations for the sum pit by 1 excavator
Tue (23/12) | 23 Dec 2025 | B2-48 |  | No activity
Tue (23/12) | 23 Dec 2025 | 800mm PW |  | 1 no Soldier pile installation completed. Preparation for 2nd Soldier pile
Tue (23/12) | 23 Dec 2025 | PMH 28 |  | Levelling in progress, preparing platform for cable pulling
Tue (23/12) | 23 Dec 2025 | P51 |  | Manual excavation, material clearance, barricade installation and access installation ongoing
Tue (23/12) | 23 Dec 2025 | P48 |  | No activity. Pile cap curing
Tue (23/12) | 23 Dec 2025 | DR3 |  | Preparation for lean con today
Tue (23/12) | 23 Dec 2025 | DR3 |  | Scaffolding erection for bracing installation
Tue (23/12) | 23 Dec 2025 | P45 |  | Bored pile hacking at North side
Tue (23/12) | 23 Dec 2025 | B2-43 |  | No activity
Tue (23/12) | 23 Dec 2025 | B2-40 |  | Lean concrete has completed last night, exposing of coupler is in progress
Tue (23/12) | 23 Dec 2025 | Exit 1 |  | Waler beam casted last night, no activity for now
Tue (23/12) | 23 Dec 2025 | Exit 1 |  | Current stockpile status
Tue (23/12) | 23 Dec 2025 | P38 |  | Column formwork closing
Tue (23/12) | 23 Dec 2025 | P41 crosshead |  | Top PT duct installation in progress
Tue (23/12) | 23 Dec 2025 | P43-44 |  | Unloading of LG materials
Tue (23/12) | 23 Dec 2025 | P48 |  | Hardcore disposal
Tue (23/12) | 23 Dec 2025 | P51 |  | 2 nos primary beam for Utility support installed today
Wed (24/12) | 24 Dec 2025 | P26 |  | Falsework erection for 2nd lift column
Wed (24/12) | 24 Dec 2025 | P27 |  | 1st lift column formwork closed
Wed (24/12) | 24 Dec 2025 | P35 |  | Falsework erection for 2nd lift column
Wed (24/12) | 24 Dec 2025 | PMH28 |  | Preparing platform for cable pulling
Wed (24/12) | 24 Dec 2025 | P51 |  | Utility support installation
Wed (24/12) | 24 Dec 2025 | PMH25 |  | Preparing platform for cable pulling
Wed (24/12) | 24 Dec 2025 | PMH24 |  | Preparing platform for cable pulling
Wed (24/12) | 24 Dec 2025 | P48 |  | No activity. Pile cap curing
Wed (24/12) | 24 Dec 2025 | DR3 |  | Lean con completed yesterday. No activity
Wed (24/12) | 24 Dec 2025 | P51 |  | Bored pile hacking and lean con completed at North last night. Access shifting in progress. After shifting Access, excavation will start at South side
Wed (24/12) | 24 Dec 2025 | P48 |  | 2nd lift formwork closing. Support installation for casting
Wed (24/12) | 24 Dec 2025 | P41 |  | Duct at Changi bound to complete today. To continue TPE bound tomorrow. Tentative casting date is next Tuesday or Wednesday
Wed (24/12) | 24 Dec 2025 | P43-44 |  | Unloading LG materials
Wed (24/12) | 24 Dec 2025 | B2-33 |  | Rock coring and splitting in progress, Yesterday managed to core 16 points, abt 6-27mins per coring
Wed (24/12) | 24 Dec 2025 | B2-34 |  | Continue excavation (2 exc)
Wed (24/12) | 24 Dec 2025 | B2-35 |  | Continue excavation (2 exc. 1 breaker on standby)
Wed (24/12) | 24 Dec 2025 | Zone 2 |  | 8nos soldier piles installed
Wed (24/12) | 24 Dec 2025 | Zone 1 |  | Already exposed services and pipe sleeves installed for probing. Preparing for backfilling. Chin Guan will work tomorrow and if area ready GCe also will work
Wed (24/12) | 24 Dec 2025 | CCW2 |  | Currently telescopic no activity due to access along CCW occupied by pump trucks for casting works, 1 excavator rectification ongoing
Wed (24/12) | 24 Dec 2025 | B1-05, B1-06 |  | Pending casting
Wed (24/12) | 24 Dec 2025 | B1-04 |  | Drilling ongoing for missing couplers
Wed (24/12) | 24 Dec 2025 | B1-01 |  | Hacking of temporary bored piles and clearing debonding sheets
Wed (24/12) | 24 Dec 2025 | Exit 2 | GL7-8 | Decking panels installation in progress
Wed (24/12) | 24 Dec 2025 | BR20A |  | Base lean concrete in progress
Wed (24/12) | 24 Dec 2025 | BR9 | construction opening 7 | Wall formwork dismantling ongoing
Wed (24/12) | 24 Dec 2025 | BR22B |  | No activity
Wed (24/12) | 24 Dec 2025 | GL18-20 stockpile area |  | No activity
Wed (24/12) | 24 Dec 2025 | BR8 stockpile area |  | No activity
Wed (24/12) | 24 Dec 2025 | BR25 |  | No activity. Wall cast last night
Wed (24/12) | 24 Dec 2025 | B2-40 |  | Start debonding sheet laying, RGT installation in progress, Exposing couplers & preparing bottom rebars installation
Wed (24/12) | 24 Dec 2025 | B2-49 |  | No activity
Wed (24/12) | 24 Dec 2025 | B2-48 |  | No activity
Wed (24/12) | 24 Dec 2025 | B2-43 |  | No activity
Wed (24/12) | 24 Dec 2025 | Exit 1 waler area |  | No activity
Wed (24/12) | 24 Dec 2025 | B2-33 |  | 2nd boulder coring works ongoing
Wed (24/12) | 24 Dec 2025 | B2-33 |  | 1st boulder partially completed. The current access to be dismantled to facilitate the works
Wed (24/12) | 24 Dec 2025 | B2-35, B2-34 |  | Excavation in progress (4 exc, 1 telescopic)
Wed (24/12) | 24 Dec 2025 | B2-31, B2-32 |  | Rebar works and partial side formwork installation in progress
Wed (24/12) | 24 Dec 2025 | P18 SB 1st Pair | MJ | 2nd adjustment in progress
Wed (24/12) | 24 Dec 2025 | 800mm PW |  | Preparation for soldier pile installation at DR4 area
Fri (26/12) | 26 Dec 2025 | P27 |  | 1st lift column cast yesterday, P26: No activity
Fri (26/12) | 26 Dec 2025 | Exit 1 |  | Dismantling of formwork for the waler beam
Fri (26/12) | 26 Dec 2025 | P38 |  | 2nd lift column Formwork inspection ongoing. To cast today
Fri (26/12) | 26 Dec 2025 | P41 |  | Crosshead rebar - sher links installation in progress
Fri (26/12) | 26 Dec 2025 | Exit 1 |  | Current stockpile status, no activity observed
Fri (26/12) | 26 Dec 2025 | Bet. P43 & P44 |  | Currently 3 containers on site as of now for LG. Another 1 container will deliver today
Fri (26/12) | 26 Dec 2025 | B2-35 |  | Hacking bulging concrete, Continue excavation works
Fri (26/12) | 26 Dec 2025 | B2-33 |  | Rock coring in progress
Fri (26/12) | 26 Dec 2025 | B2-31, B2-32 |  | Shearlinks installation in progress. Plan to cast this weekend
Fri (26/12) | 26 Dec 2025 | B2-29, B2-30 |  | Currently no activity
Fri (26/12) | 26 Dec 2025 | BR8 stockpile area |  | Currently observed no activity
Fri (26/12) | 26 Dec 2025 | BR25 |  | Currently observed no activity. Wall formwork dismantled
Fri (26/12) | 26 Dec 2025 | B2-43 |  | No activity
Fri (26/12) | 26 Dec 2025 | B2-49A |  | No activity
Fri (26/12) | 26 Dec 2025 | P45 |  | Excavation for 4th layer cassion wall
Fri (26/12) | 26 Dec 2025 | DR3 |  | No activity
Fri (26/12) | 26 Dec 2025 | P47 |  | Demob of GCE materials
Fri (26/12) | 26 Dec 2025 | P48 |  | No activity
Fri (26/12) | 26 Dec 2025 | B2-40 |  | Started bottom bar installation
Fri (26/12) | 26 Dec 2025 | P51 |  | Excavation works and utility support ongoing
Fri (26/12) | 26 Dec 2025 | DR4 |  | Manual trial trench in progress for soldier pile installation
Fri (26/12) | 26 Dec 2025 | N2-N3 |  | Stressing works ongoing
Fri (26/12) | 26 Dec 2025 | P38 |  | 2nd lift column casting in progress
Fri (26/12) | 26 Dec 2025 | P41 |  | Continue rebar and tendon duct works
Fri (26/12) | 26 Dec 2025 | P42 |  | Preparation for stressing works
Fri (26/12) | 26 Dec 2025 | Bet. P43 & P44 |  | Pending 1 no. container delivery around 4pm
Fri (26/12) | 26 Dec 2025 | P45 |  | North side - rebar works for 4th layer ongoing. South side - excavation for 4th layer
Fri (26/12) | 26 Dec 2025 | P47 |  | Continue demob of GCE materials
Fri (26/12) | 26 Dec 2025 | P51 |  | Utility supports and welding works ongoing
Fri (26/12) | 26 Dec 2025 | DR4 |  | Pending soldier pile materials delivery
Fri (26/12) | 26 Dec 2025 | N2-N3 |  | Continue stressing works
Fri (26/12) | 26 Dec 2025 | P15-P16 |  | Mid span Formwork dismantling
Fri (26/12) | 26 Dec 2025 | B2-31, B2-32 |  | Shearlinks and wall starter bar installation in progress
Fri (26/12) | 26 Dec 2025 | B2-35, B2-36 |  | Excavation in progress. Can see from B2-40 area already
Fri (26/12) | 26 Dec 2025 | B2-33 |  | Continue rock coring & splitting works
Fri (26/12) | 26 Dec 2025 | B2-34 |  | Lights installation in progress
Fri (26/12) | 26 Dec 2025 | BR8 stockpile |  | No activity
Fri (26/12) | 26 Dec 2025 | BR5 opening |  | WH preparing to hoist down 1 more excavator
Fri (26/12) | 26 Dec 2025 | B2-40 |  | Rebar works & RGT installation in progress
Fri (26/12) | 26 Dec 2025 | B2-49A |  | No activity
Fri (26/12) | 26 Dec 2025 | B2-48 |  | Housekeeping works
Fri (26/12) | 26 Dec 2025 | B2-43 |  | No activity
Fri (26/12) | 26 Dec 2025 | Exit 1 waler area |  | Formwork dismantled
Fri (26/12) | 26 Dec 2025 | BR22B |  | No activity observed
Fri (26/12) | 26 Dec 2025 | Exit 2 decking extension |  | Waiting for the 5th SB delivery
Fri (26/12) | 26 Dec 2025 | BR20A |  | Rebar works in progress
Fri (26/12) | 26 Dec 2025 | B1-05, B1-06 |  | Curing
Fri (26/12) | 26 Dec 2025 | B1-04 |  | Debonding sheet laying in progress
Fri (26/12) | 26 Dec 2025 | B1-03 |  | Currently observed no other activity. Soil disposal at loading point
Fri (26/12) | 26 Dec 2025 | CCW1 | North side | No activity
Fri (26/12) | 26 Dec 2025 | CCW1 | South side | No activity
Fri (26/12) | 26 Dec 2025 | Bet. P20 & P21 |  | Current status of temporary stockpile
Fri (26/12) | 26 Dec 2025 | CCW2 |  | S5 excavation in progress
Sat (27/12) | 27 Dec 2025 | P38 |  | 2nd lift column cast yesterday. Scaffold dismantling in progress
Sat (27/12) | 27 Dec 2025 | P39 |  | Column Formwork dismantling and removal completed
Sat (27/12) | 27 Dec 2025 | P41 Crosshead |  | Formwork closing and rebar installation in progress
Sat (27/12) | 27 Dec 2025 | P42 |  | Tendon strand installation in progress
Sat (27/12) | 27 Dec 2025 | Bet. P43 & P44 |  | Preparation for unloading of LG materials
Sat (27/12) | 27 Dec 2025 | P45 |  | North side - Rebar works ongoing for 4th layer cassion wall. South side - Excavation works for 4th layer
Sat (27/12) | 27 Dec 2025 | P45 |  | Preparation for coring test
Sat (27/12) | 27 Dec 2025 | DR3 |  | HSL BP hacking works ongoing
Sat (27/12) | 27 Dec 2025 | P48 |  | LE cutting and removal of struts in progress
Sat (27/12) | 27 Dec 2025 | P51 |  | Utility support and manual excavation works in progress
Sat (27/12) | 27 Dec 2025 | DR4 |  | Unloading of steel plates and soldier piles in progress. To resume SP installation in the afternoon
Sat (27/12) | 27 Dec 2025 | P12 |  | North bound - Segment adjustment in progress
Sat (27/12) | 27 Dec 2025 | N2-N3 |  | Stressing works ongoing
Sat (27/12) | 27 Dec 2025 | P35 |  | 2nd lift column rebar works started
Sat (27/12) | 27 Dec 2025 | P38 |  | Scaffold dismantled. Curing ongoing
Sat (27/12) | 27 Dec 2025 | P41 |  | Continue formwork closing and shear links installation at south side
Sat (27/12) | 27 Dec 2025 | P45 |  | J2-CP4 SPT/coring in progress
Sat (27/12) | 27 Dec 2025 | P45 |  | Continue 4th layer cassion excavation and rebar works
Sat (27/12) | 27 Dec 2025 | P48 |  | LE cutting and removal of struts ongoing
Sat (27/12) | 27 Dec 2025 | P51 |  | Continue utility support and manual excavation works
Sat (27/12) | 27 Dec 2025 | DR4 |  | 4 nos. of SP installed. Manual trial trench ongoing
Sat (27/12) | 27 Dec 2025 | N2-N3 |  | Continue stressing works
Sat (27/12) | 27 Dec 2025 | P12 |  | North bound Segment adjustment
Sun (28/12) | 28 Dec 2025 | BR19A |  | Surface roughening ongoing
Sun (28/12) | 28 Dec 2025 | Exit 2 decking extension |  | Tightening & welding works ongoing
Sun (28/12) | 28 Dec 2025 | BR20A |  | Shearlinks installation and preparing hyrib mesh
Sun (28/12) | 28 Dec 2025 | GL18-20 stockpile |  | No activity observed
Sun (28/12) | 28 Dec 2025 | BR22B |  | No activity observed
Sun (28/12) | 28 Dec 2025 | B2-31, B2-32 |  | Casting completed ard 345am this morning
Sun (28/12) | 28 Dec 2025 | B2-30, B2-29 |  | No activity
Sun (28/12) | 28 Dec 2025 | BR8 stockpile |  | Currently no activity
Sun (28/12) | 28 Dec 2025 | P35 |  | 2nd lift column rebar works in progress
Sun (28/12) | 28 Dec 2025 | BR25 |  | No activity
Sun (28/12) | 28 Dec 2025 | B2-35, B2-37 |  | Excavation in progress
Sun (28/12) | 28 Dec 2025 | B2-40 |  | Rebar works and drainage pipe installation in progress
Sun (28/12) | 28 Dec 2025 | B2-49A |  | Barricade and toeboard installation. Observed no other activity
Sun (28/12) | 28 Dec 2025 | B2-48 |  | No activity
Sun (28/12) | 28 Dec 2025 | B2-43 |  | No activity
Sun (28/12) | 28 Dec 2025 | Exit 1 waler area |  | Struts welding works ongoing
Sun (28/12) | 28 Dec 2025 | Exit 3 stockpile |  | Disposal works ongoing
Sun (28/12) | 28 Dec 2025 | B1-01 |  | Hacking ongoing to expose skin wall starter bars
Sun (28/12) | 28 Dec 2025 | B1-03 |  | Excavation in progress
Sun (28/12) | 28 Dec 2025 | B1-04 |  | Rebar works ongoing
Sun (28/12) | 28 Dec 2025 | BR20A |  | Shearlinks & formwork installation
Sun (28/12) | 28 Dec 2025 | Exit 1 waler area |  | Currently no activity
Sun (28/12) | 28 Dec 2025 | B2-35, B2-37 |  | Excavation in progress
Sun (28/12) | 28 Dec 2025 | B2-40 |  | Rebar works in progress
Sun (28/12) | 28 Dec 2025 | CCW1 | south side | No activity
Sun (28/12) | 28 Dec 2025 | CCW1 | North side | No activity
Sun (28/12) | 28 Dec 2025 | CCW2 |  | S5 excavation in progress (2 exc, 1 telescopic working. 1 exc standby)
Sun (28/12) | 28 Dec 2025 | B1-01 |  | Excavation in progress (1 exc), B1-03: Loading point (2 exc, 1 telescopic)
Sun (28/12) | 28 Dec 2025 | B1-04 |  | Preparing bottom bars installation, Drilling ongoing for missing couplers
Sun (28/12) | 28 Dec 2025 | Between P20 & P21 |  | Current temp stockpile status
Mon (29/12) | 29 Dec 2025 | P16-P17 South bound |  | Formwork closing for mid span stitching
Mon (29/12) | 29 Dec 2025 | P14 South bound |  | Shifting of LF towards P13
Mon (29/12) | 29 Dec 2025 | P12 |  | Tendon strand preparation for stressing works
Mon (29/12) | 29 Dec 2025 | P3 |  | Rebar unloading ongoing for rectification works
Mon (29/12) | 29 Dec 2025 | 800mm PW |  | Excavation for pipe laying works above existing DR4
Mon (29/12) | 29 Dec 2025 | 800mm PW |  | Current soldier pile installation status
Mon (29/12) | 29 Dec 2025 | P51 |  | Utility support installation
Mon (29/12) | 29 Dec 2025 | P48 |  | S1 strut removal completed. No activity
Mon (29/12) | 29 Dec 2025 | DR3 |  | No activity
Mon (29/12) | 29 Dec 2025 | P45 |  | L4 caisson part 1 casting
Mon (29/12) | 29 Dec 2025 | P16-P17 midspan |  | Continue Formwork closing for stitching
Mon (29/12) | 29 Dec 2025 | P15 |  | LF shifting towards P13
Mon (29/12) | 29 Dec 2025 | P12 NB |  | Tendon strand installation ongoing
Mon (29/12) | 29 Dec 2025 | 800mm PW |  | Trial trench for probing work
Mon (29/12) | 29 Dec 2025 | P51 |  | Manual excavation and utility support installation
Mon (29/12) | 29 Dec 2025 | P45 |  | Lowering excavator at south side
Mon (29/12) | 29 Dec 2025 | P41 |  | Formwork closing
Mon (29/12) | 29 Dec 2025 | P40 |  | Column surface rectification work
Mon (29/12) | 29 Dec 2025 | P3 |  | Continue rebar unloading works
Mon (29/12) | 29 Dec 2025 | P3 |  | P4 side - preparation for rebar installation
Mon (29/12) | 29 Dec 2025 | P35 |  | Column rebar work in progress
Tue (30/12) | 30 Dec 2025 | BR5 opening | Opening 9 | Disposal works ongoing (1 telescopic, 1 exc)
Tue (30/12) | 30 Dec 2025 | B2-35 |  | Continue excavation works
Tue (30/12) | 30 Dec 2025 | B2-33 |  | Current status
Tue (30/12) | 30 Dec 2025 | B2-34 |  | Partial lean con done
Tue (30/12) | 30 Dec 2025 | B2-31, B2-32 |  | Formwork removal
Tue (30/12) | 30 Dec 2025 | B2-29, B2-30 |  | No activity
Tue (30/12) | 30 Dec 2025 | BR8 stockpile |  | Currently no activity
Tue (30/12) | 30 Dec 2025 | BR25 |  | No activity
Tue (30/12) | 30 Dec 2025 | Exit 1 waler area |  | Backfilling ongoing outside the RC waler. Today plan to complete 1 more strut preloading
Tue (30/12) | 30 Dec 2025 | B2-49A |  | Currently no activity
Tue (30/12) | 30 Dec 2025 | B2-48/CCE linkway |  | Hacking at skin wall area ongoing
Tue (30/12) | 30 Dec 2025 | B2-43 |  | No activity
Tue (30/12) | 30 Dec 2025 | 800mm PW |  | Pipe laying works on going at part 3, trial trench work for probing at part 1
Tue (30/12) | 30 Dec 2025 | P20 |  | Falsework dismantling of 2nd lift column work
Tue (30/12) | 30 Dec 2025 | P51 |  | Utility support installation
Tue (30/12) | 30 Dec 2025 | P48 |  | No activity
Tue (30/12) | 30 Dec 2025 | Dr3 |  | Bracing installation ongoing..Manual bored pile trimming ongoing.. preparation for UKP hacking
Tue (30/12) | 30 Dec 2025 | P45 |  | Excavation to L4 caisson layer
Tue (30/12) | 30 Dec 2025 | P18 |  | Preparation work for segment launching. Now TBM at P19 area
Tue (30/12) | 30 Dec 2025 | P26 |  | Today no activity
Tue (30/12) | 30 Dec 2025 | P35 |  | 2nd lift column rebar work almost done
Tue (30/12) | 30 Dec 2025 | P41 |  | Tendom wire pulling
Tue (30/12) | 30 Dec 2025 | P12 | NB | Today target to start installing the formwork
Tue (30/12) | 30 Dec 2025 | DR4 soldier pile installation |  | Zone 3 (0/10 installed). Zone 2 ( 18/20 installed). Zone 1 (0/10 installed)
Tue (30/12) | 30 Dec 2025 | Zone 3 |  | Affected Starhub cable shifted
Tue (30/12) | 30 Dec 2025 | Zone 1 |  | Pipe sleeves installation for probing
Tue (30/12) | 30 Dec 2025 | P51 |  | Platform erection for support welding
Tue (30/12) | 30 Dec 2025 | DR3 |  | Bracing installation and pile head hacking work
Tue (30/12) | 30 Dec 2025 | P45 |  | Last two point JGP testing
Tue (30/12) | 30 Dec 2025 | P45 |  | Continue excavation work
Tue (30/12) | 30 Dec 2025 | P3 |  | Additional drilling as per QSS comments. Later will reinspect and cleared portion will start the rebar planting
Tue (30/12) | 30 Dec 2025 | DR4 |  | Last soldier pile for Zone 2 already installed
Tue (30/12) | 30 Dec 2025 | P18 |  | Jack set up and preparation for segment launching during night shift
Tue (30/12) | 30 Dec 2025 | P12 |  | As of now no activity
Tue (30/12) | 30 Dec 2025 | P3 |  | Starter bar planting work for rectification work
Tue (30/12) | 30 Dec 2025 | P2 |  | No activity already. Housekeeping and tidy up the work area
Tue (30/12) | 30 Dec 2025 | P51 |  | Platform erection and welding of utility support
Tue (30/12) | 30 Dec 2025 | P45 |  | Base lean concrete for caisson work
Tue (30/12) | 30 Dec 2025 | B2-40 |  | Top bar works in progress. Plan for casting tmr
Tue (30/12) | 30 Dec 2025 | B2-37 |  | Excavation and hacking works ongoing
Wed (31/12) | 31 Dec 2025 | P12 |  | WH started preparation for stitching formwork closing at NB side
Wed (31/12) | 31 Dec 2025 | P3 |  | Drilling for starter bar planting. Rebar work partially started
Wed (31/12) | 31 Dec 2025 | 800mm PW |  | Probing works at part 1
Wed (31/12) | 31 Dec 2025 | 800mm PW |  | Pipe laying works at part 3
Wed (31/12) | 31 Dec 2025 | P51 |  | Utility support installation ongoing.. preparing platform for welding works
Wed (31/12) | 31 Dec 2025 | 800mm PW |  | Joint installation near P49
Wed (31/12) | 31 Dec 2025 | DR3 |  | Preparation for UKP bracing installation
Wed (31/12) | 31 Dec 2025 | P45 |  | L4 caisson rebar work installation at South side
Wed (31/12) | 31 Dec 2025 | P18 down chainage |  | One segment launch last night . Cleaning exposy in progress
Wed (31/12) | 31 Dec 2025 | P18 movement joint area | NB | Housekeeping and preparing to continue formwork for plinth
Fri (02/01) | 02 Jan 2026 | Exit 1 |  | Current stockpile, no activity
Fri (02/01) | 02 Jan 2026 | B2-34 |  | Dwall rectification works ongoing, Lean concrete completed, Wendyng started to hoist down rebars
Fri (02/01) | 02 Jan 2026 | B2-33 |  | Partial lean concrete done. Tonight plan to do balance lean concrete
Fri (02/01) | 02 Jan 2026 | B2-35, B2-37 |  | Continue excavation
Fri (02/01) | 02 Jan 2026 | BR8 stockpile area |  | No activity
Fri (02/01) | 02 Jan 2026 | B2-48 |  | Understand that exposing of starter bar for skin wall will resume later
Fri (02/01) | 02 Jan 2026 | B2-49A |  | No activity
Fri (02/01) | 02 Jan 2026 | P35 |  | 2nd lift column formwork installation
Fri (02/01) | 02 Jan 2026 | B2-31, B2-32 |  | Clearing debonding sheets, Wendyng preparing rebars for next slab
Fri (02/01) | 02 Jan 2026 | B2-29, B2-30 |  | No activity
Fri (02/01) | 02 Jan 2026 | B2-43 |  | No activity
Fri (02/01) | 02 Jan 2026 | B2-40 |  | Casting was done on Wed night, no activity for now
Fri (02/01) | 02 Jan 2026 | P18 SB |  | 2 segments installed last week
Fri (02/01) | 02 Jan 2026 | P14 |  | Preparation for lifter frame shifting
Fri (02/01) | 02 Jan 2026 | P12 NB |  | Stitching Formwork closing
Fri (02/01) | 02 Jan 2026 | P3 Rectification |  | Rebar installation in progress at P2 side
Fri (02/01) | 02 Jan 2026 | P3 Rectification |  | Current status of rebar installation at P4 side
Fri (02/01) | 02 Jan 2026 | P45 |  | Formwork closing for L4 caisson wall
Fri (02/01) | 02 Jan 2026 | P47 |  | JGP Testing in progress
Fri (02/01) | 02 Jan 2026 | P51 |  | Utility support installation
Fri (02/01) | 02 Jan 2026 | 800mm PW |  | ERSS steel plate installation
Fri (02/01) | 02 Jan 2026 | BR2 roof slab thickening | rectification work | Drilling in progress by Wendyng
Fri (02/01) | 02 Jan 2026 | B2-33 |  | Continue excavation and levelling works prior to lean concrete casting
Fri (02/01) | 02 Jan 2026 | B2-34 |  | Exposing couplers, CJ roughening at B2-32 ongoing, Preparation works ongoing before laying debonding sheet
Fri (02/01) | 02 Jan 2026 | BR5 opening | Opening 9 | Continue excavation and disposal works
Fri (02/01) | 02 Jan 2026 | P35 |  | 2nd lift column installation
Fri (02/01) | 02 Jan 2026 | BR25 |  | Hacking of overcast dwall in progress
Fri (02/01) | 02 Jan 2026 | P31 |  | 1st lift column rebar installation ongoing
Fri (02/01) | 02 Jan 2026 | P29 |  | Preparation for 1st lift column rebar installation
Fri (02/01) | 02 Jan 2026 | P28 |  | Preparation for Formwork closing for 1st lift column
Fri (02/01) | 02 Jan 2026 | B2-49A |  | No activity
Fri (02/01) | 02 Jan 2026 | B2-48 |  | No activity observed
Fri (02/01) | 02 Jan 2026 | B2-43 |  | No activity
Fri (02/01) | 02 Jan 2026 | Exit 1 waler area |  | No activity
Fri (02/01) | 02 Jan 2026 | B2-34 |  | Continue exposing couplers
Fri (02/01) | 02 Jan 2026 | B2-33 |  | Ground levelling prior to casting balance lean concrete. Plan for lean concrete tonight
Fri (02/01) | 02 Jan 2026 | B2-35, B2-36 | Opening 9 | Continue excavation
Fri (02/01) | 02 Jan 2026 | B2-29, B2-30 |  | No activity
Fri (02/01) | 02 Jan 2026 | GL18-20 stockpile |  | No activity
Fri (02/01) | 02 Jan 2026 | BR22B |  | Currently observed no activity. Pump truck on site for LSS backfill behind capping beam
Fri (02/01) | 02 Jan 2026 | CCW1 | south side | Current excavation status. Tonight KTC will continue nightshift at CCW
Fri (02/01) | 02 Jan 2026 | CCW2 |  | ATC no more activity for the day. KTC night team to continue stockpile disposal works
Fri (02/01) | 02 Jan 2026 | B1-02 |  | Current excavation status. WH currently installing lights along this area & B1-01
Fri (02/01) | 02 Jan 2026 | B1-03 |  | Currently no activity, B1-01: WH installing lightings
Fri (02/01) | 02 Jan 2026 | B1-04 |  | Rebar works in progress. Dayshift working till 10pm. Night team already on site (12 pax)
Fri (02/01) | 02 Jan 2026 | 800mm PW |  | Preparation to continue erss steel plate installation
Fri (02/01) | 02 Jan 2026 | 800mm PW |  | Preparation for pipe laying works
Fri (02/01) | 02 Jan 2026 | P51 |  | Utility support installation
Fri (02/01) | 02 Jan 2026 | P48 |  | Formwork installation for LSS Backfilling
Fri (02/01) | 02 Jan 2026 | DR3 |  | Preparation for pile hacking and bracing installation work
Fri (02/01) | 02 Jan 2026 | P45 |  | Formwork closing for L4 caisson work
Sat (03/01) | 03 Jan 2026 | 800mm PW |  | Pipe laying at part 3
Sat (03/01) | 03 Jan 2026 | 800mm PW |  | Current excavation status at part 2
Sat (03/01) | 03 Jan 2026 | P51 |  | Utility support installation ongoing
Sat (03/01) | 03 Jan 2026 | P48 |  | No activity
Sat (03/01) | 03 Jan 2026 | DR3 |  | Ground levelling, bored pile trimming and access making
Sat (03/01) | 03 Jan 2026 | P45 |  | L4 caisson casting completed..formwork dismantling
Sat (03/01) | 03 Jan 2026 | P18 |  | Preparation work prior bearing stump casting at north side
Sat (03/01) | 03 Jan 2026 | P14 |  | Preparation for lifter frame shifting
Sat (03/01) | 03 Jan 2026 | P12 NB |  | Stitching Formwork closing
Sat (03/01) | 03 Jan 2026 | P3 |  | Rebar planting status at P2 side
Sat (03/01) | 03 Jan 2026 | P3 |  | Rebar planting status at p4 side
Sat (03/01) | 03 Jan 2026 | P3 |  | Rebar planting in progress
Sat (03/01) | 03 Jan 2026 | N1 to N2 |  | Stressing preparation work in progress
Sat (03/01) | 03 Jan 2026 | P12 |  | No activity
Sat (03/01) | 03 Jan 2026 | P14 |  | Preparation for lifter frame shifting
Sat (03/01) | 03 Jan 2026 | P18 |  | Bearing stump casting completed
Sat (03/01) | 03 Jan 2026 | P29 |  | Rebar installation for 1st lift column
Sat (03/01) | 03 Jan 2026 | P28 |  | Formwork closing for 1st lift column
Sat (03/01) | 03 Jan 2026 | P31 |  | Rebar installation work ongoing
Sat (03/01) | 03 Jan 2026 | P35 |  | 2nd lift column casting completed
Sat (03/01) | 03 Jan 2026 | P39 |  | Column patching work ongoing
Sat (03/01) | 03 Jan 2026 | P45 |  | Caisson formwork removal completed. Tomorrow start excavation
Sat (03/01) | 03 Jan 2026 | DR3 |  | UKP cross bracing installation in progress..completed 5/6 bay
Sat (03/01) | 03 Jan 2026 | 800mm PW |  | Pipe joint air test
Sat (03/01) | 03 Jan 2026 | 800mm PW |  | Excavation ongoing at part 2
Mon (05/01) | 05 Jan 2026 | P18 |  | Segment P18-SB-D04 launched yesterday. Tonight to launch P18-SB-U04
Mon (05/01) | 05 Jan 2026 | Near DR4 |  | 13m length of water pipe laid. Joint testing done
Mon (05/01) | 05 Jan 2026 | DR4 Zone 2 |  | Will be challenging to work due to services
Mon (05/01) | 05 Jan 2026 | P12 & N1-N2 midspan |  | Preparation for wet stitch casting tonight
Mon (05/01) | 05 Jan 2026 | B2-33 |  | Exposing couplers in progress, Partial debonding sheet laid
Mon (05/01) | 05 Jan 2026 | B2-34 |  | Partial bottom rebar installation in progress. Manpower now doing the column rebar works, Column rebar works in progress, Dwall rectification ongoing by Dongah
Mon (05/01) | 05 Jan 2026 | B2-37 |  | Hardcore clearing ongoing
Mon (05/01) | 05 Jan 2026 | B2-35, B2-38 |  | Excavation and disposal ongoing (2 exc, 1 telescopic)
Mon (05/01) | 05 Jan 2026 | B2-35 |  | Hardcore hacking works ongoing
Mon (05/01) | 05 Jan 2026 | B2-31, B2-32 |  | No activity
Mon (05/01) | 05 Jan 2026 | B2-29, B2-30 |  | No activity
Mon (05/01) | 05 Jan 2026 | BR2 roof slab thickening | rectification work | Rebar works in progress
Mon (05/01) | 05 Jan 2026 | P3 Rectification |  | Continue rebar installation works
Mon (05/01) | 05 Jan 2026 | GL18-20 stockpile |  | Soft clay internal shifting to exit 1 area
Mon (05/01) | 05 Jan 2026 | P51 NB |  | MPI test for for utility support. KTC started excavation
Mon (05/01) | 05 Jan 2026 | P51 SB |  | Exposing services and started utility supporting
Mon (05/01) | 05 Jan 2026 | P45 |  | Excavation for final layer caisson
Mon (05/01) | 05 Jan 2026 | DR3 |  | Base lean concrete
Mon (05/01) | 05 Jan 2026 | P47 |  | Last point JGP testing
Mon (05/01) | 05 Jan 2026 | P43-44 |  | LG assembling. 2nd batch delivery: 3 containers will delivered tomorrow
Mon (05/01) | 05 Jan 2026 | P42 |  | Tomorrow will complete stressing work
Mon (05/01) | 05 Jan 2026 | P29 |  | 1st lift column formwork closing done. P28: 1st lift column casting in progress
Mon (05/01) | 05 Jan 2026 | CCW1 | south side | Excavation ongoing (1 exc working, 2 standby)
Mon (05/01) | 05 Jan 2026 | CCW1 | north side | No activity
Mon (05/01) | 05 Jan 2026 | B1-05 |  | Current status of soffit hacking
Mon (05/01) | 05 Jan 2026 | B1-03 |  | Rebar works in progress
Mon (05/01) | 05 Jan 2026 | B1-02 |  | Excavation in progress, B1-04: Shearlinks and partial formwork installation in progress. Plan to cast B1-03 & B1-04 this week
Mon (05/01) | 05 Jan 2026 | P18 NB |  | Preparing for MJ bearing plate installation
Mon (05/01) | 05 Jan 2026 | P18 SB Up chainage |  | Left this segment to install tonight
Mon (05/01) | 05 Jan 2026 | N1-N2 |  | Mid joint formwork closing done. To cast together with P12 stiching after last bus
Mon (05/01) | 05 Jan 2026 | P12 NB |  | Stitching formwork done. To cast tonight
Mon (05/01) | 05 Jan 2026 | P3 |  | Continue rebar work for ducting
Mon (05/01) | 05 Jan 2026 | BR22B |  | Current status
Mon (05/01) | 05 Jan 2026 | GL18-20 stockpile |  | No activity observed now
Mon (05/01) | 05 Jan 2026 | BR2 roof slab thickening | rectification work | Rebar works in progress. Plan for casting tmr
Mon (05/01) | 05 Jan 2026 | B2-34, B2-33 |  | Column rebar works in progress. Manpower currently focusing here thereafter to continue for the slab area (same with B2-33)
Mon (05/01) | 05 Jan 2026 | B2-35 |  | Continue hacking and disposal works, B2-37, B2-38:, Excavation in progress
Mon (05/01) | 05 Jan 2026 | P51 |  | Reinstatement of barricade and continue excavation
Mon (05/01) | 05 Jan 2026 | DR3 |  | Base lean concrete casting done
Mon (05/01) | 05 Jan 2026 | B2-29, B2-30 |  | No activity
Mon (05/01) | 05 Jan 2026 | BR8 stockpile area |  | No activity
Mon (05/01) | 05 Jan 2026 | BR25 |  | Dongah clearing the hacking debris, WH slope levelling ongoing near VS. Tmr plan to cast lean con at slope area
Mon (05/01) | 05 Jan 2026 | Exit 1 waler area |  | No activity
Mon (05/01) | 05 Jan 2026 | P45 |  | Day shift team handover to night shift team for excavation
Mon (05/01) | 05 Jan 2026 | B2-49A |  | Just cast slope at sump pit area. Now preparing to reinstate the barricades
Mon (05/01) | 05 Jan 2026 | B2-48 |  | Current status. No activity observed
Mon (05/01) | 05 Jan 2026 | B2-43 |  | No activity
Tue (06/01) | 06 Jan 2026 | B2-40 |  | No activity
Tue (06/01) | 06 Jan 2026 | B2-48 |  | Current status for exposing of skin wall starter bar
Tue (06/01) | 06 Jan 2026 | Exit 1 |  | Stockpile and segregation works by 1 excavator
Tue (06/01) | 06 Jan 2026 | P18 |  | P18-SB-U04 launched last night. All southbound segments completed for P18
Tue (06/01) | 06 Jan 2026 | P12 NB & N1-N2 midspan |  | Wet stitch cast last night
Tue (06/01) | 06 Jan 2026 | P12 |  | NB tendon strand installation ongoing
Tue (06/01) | 06 Jan 2026 | 800mm PW | part 2 | Starhub cable diversion ongoing, meanwhile strut waler installation ongoing
Tue (06/01) | 06 Jan 2026 | P51 |  | South side excavation ongoing, north side utility support installation ongoing
Tue (06/01) | 06 Jan 2026 | DR3 |  | Preparation work for drain RC work
Tue (06/01) | 06 Jan 2026 | P45 |  | Excavation to L5 caisson layer
Tue (06/01) | 06 Jan 2026 | P3 Rectification |  | Continue rebar installation works. Target to complete today
Wed (07/01) | 07 Jan 2026 | B2-40 |  | No activity
Wed (07/01) | 07 Jan 2026 | B2-48 |  | General Housekeeping work
Wed (07/01) | 07 Jan 2026 | B2-49A |  | No activity
Wed (07/01) | 07 Jan 2026 | Exit 1 |  | Preparing for the ramp down
Wed (07/01) | 07 Jan 2026 | P45 |  | Excavation to L5 caisson layer on going
Wed (07/01) | 07 Jan 2026 | DR3 |  | Drain RC work ongoing
Wed (07/01) | 07 Jan 2026 | P51 |  | South side excavation ongoing..north side manual excavation and utility support installation ongoing
Wed (07/01) | 07 Jan 2026 | B2-33, B2-34 |  | Rebar works in progress, Cleaning ongoing for remaining portion for B2-34 prior to laying debonding sheet, Drilling ongoing for rebar planting at dwall side
Wed (07/01) | 07 Jan 2026 | B2-29, B2-30 |  | No activity
Wed (07/01) | 07 Jan 2026 | B2-37 |  | Levelling ongoing. Today plan for partial lean con casting
Wed (07/01) | 07 Jan 2026 | B2-35, B2-38 |  | Continue excavation
Wed (07/01) | 07 Jan 2026 | BR25 |  | Hacking ongoing for rectification for coupler misalignment for Dwall of CJ B2-39 (DW-078 & DW-079)
Wed (07/01) | 07 Jan 2026 | BR8 stockpile |  | No activity
Wed (07/01) | 07 Jan 2026 | GL18-20 stockpile |  | Partially cleared. No other activity observed here, P31: Column formwork installation in progress
Wed (07/01) | 07 Jan 2026 | Zone 2 down chainage |  | 3nos soldier piles installed
Wed (07/01) | 07 Jan 2026 | P51 |  | Manual excavation for utility support
Wed (07/01) | 07 Jan 2026 | P51 |  | Excavation at center portion
Wed (07/01) | 07 Jan 2026 | P47 |  | Started exposing UKP
Wed (07/01) | 07 Jan 2026 | DR3 |  | Base rebar work in progress
Wed (07/01) | 07 Jan 2026 | P45 |  | Excavation for last layer caisson
Wed (07/01) | 07 Jan 2026 | P43 |  | Scaffold erection for segment launching work
Wed (07/01) | 07 Jan 2026 | P42 |  | Stressing done. Wendyng to dismantle the working platform
Wed (07/01) | 07 Jan 2026 | P31 |  | Formwork closing for 1st lift
Wed (07/01) | 07 Jan 2026 | P26 |  | 2nd lift column rebar work
Wed (07/01) | 07 Jan 2026 | B2-49A sump pit |  | Tonight plan for base lean con casting
Wed (07/01) | 07 Jan 2026 | B2-48 |  | No activity
Wed (07/01) | 07 Jan 2026 | B2-43 |  | No activity
Wed (07/01) | 07 Jan 2026 | P12 SB |  | Formwork already take out for stitching work
Wed (07/01) | 07 Jan 2026 | B2-37 |  | Pending for lean con casting. Pump hose & pipe joining done
Wed (07/01) | 07 Jan 2026 | B2-38 |  | Excavation in progress, B2-35: Continue soil disposal
Wed (07/01) | 07 Jan 2026 | P3 |  | Wendyng rebar work completed. Ultracon installation of tendon box and duct by WH
Wed (07/01) | 07 Jan 2026 | P6 SB |  | TBM already over the junction
Wed (07/01) | 07 Jan 2026 | BR25 |  | Hacking ongoing for rectification for coupler misalignment for Dwall of CJ B2-39 (DW-078 & DW-079)
Wed (07/01) | 07 Jan 2026 | BR8 area |  | No activity
Wed (07/01) | 07 Jan 2026 | B2-34 |  | Debonding sheet laying in progress for remaining portion, Rebar works in progress, B2-33:, Rebar works in progress, Drilling ongoing for rebar planting at dwall side
Wed (07/01) | 07 Jan 2026 | B2-35 |  | Excavation and disposal works ongoing
Wed (07/01) | 07 Jan 2026 | B2-29, B2-30 |  | No activity
Wed (07/01) | 07 Jan 2026 | GL18-20 stockpile |  | No activity
Wed (07/01) | 07 Jan 2026 | BR22B |  | Tmr to continue excavation works. Plan to handover to CGW on Saturday
Wed (07/01) | 07 Jan 2026 | BR19 decking extension 10A |  | Activity done for the day
Wed (07/01) | 07 Jan 2026 | DR3 |  | Drain base slab rebar work
Wed (07/01) | 07 Jan 2026 | P45 |  | Excavation for last layer caisson
Wed (07/01) | 07 Jan 2026 | P48 |  | Lean concrete and bund wall making along the road
Wed (07/01) | 07 Jan 2026 | P51 |  | Current status of excavation
Wed (07/01) | 07 Jan 2026 | B1-05 |  | No activity for wall rebars. Workers shifted to Exit 3 focusing B1-03 rebar works
Wed (07/01) | 07 Jan 2026 | B1-07, B1-08 |  | Excavation in progress. 1 telescopic, 1 excavator; 1 excavator standby, Hacking temporary pile ongoing by WH breaker
Wed (07/01) | 07 Jan 2026 | B1-02 |  | Hardcores and soil disposal, KTC continue soil levelling ongoing, B1-04: Shearlinks installation in progress
Wed (07/01) | 07 Jan 2026 | B1-03 |  | Rebar works and corrugated pipes installation in progress
Wed (07/01) | 07 Jan 2026 | B1-01, B1-02 |  | Partial lean concrete casting ongoing
Thu (08/01) | 08 Jan 2026 | DR3 |  | Drain base rebar work
Thu (08/01) | 08 Jan 2026 | P45 |  | Excavation for final layer
Thu (08/01) | 08 Jan 2026 | P51 |  | Continue exposing services for support
Thu (08/01) | 08 Jan 2026 | B2-33, B2-34 |  | Rebar works in progress, B2-34: Drilling ongoing at dwall side for rebar planting
Thu (08/01) | 08 Jan 2026 | B2-29, B2-30 |  | No activity
Thu (08/01) | 08 Jan 2026 | B2-37 |  | Lean con completed 90% last night. Balance 10% still clearing soil and levelling, B2-35, B2-36, B2-38: Continue excavation and disposal works (Opening 9)
Thu (08/01) | 08 Jan 2026 | P14 |  | LF modification to be transferred to P12
Thu (08/01) | 08 Jan 2026 | P42 |  | Preparing to start dismantling of crosshead working platform
Thu (08/01) | 08 Jan 2026 | BR25 |  | Today to continue hacking ongoing for rectification for CJ B2-39 (DW-078 & DW-079) thereafter welding works. Target to cast this week
Thu (08/01) | 08 Jan 2026 | BR8 stockpile |  | No activity observed
Thu (08/01) | 08 Jan 2026 | GL18-20 stockpile |  | No activity observed
Thu (08/01) | 08 Jan 2026 | P7 |  | Area leveling for pad footing
Thu (08/01) | 08 Jan 2026 | P26 |  | 2nd lift column rebar work
Thu (08/01) | 08 Jan 2026 | P3 |  | Scaffold platforms erection for strand pulling at T2 and T3
Thu (08/01) | 08 Jan 2026 | P3 |  | Tie rod installation for formwork closing
Thu (08/01) | 08 Jan 2026 | B2-33, B2-34 |  | Continue drilling at dwall side (B2-33), Rebar works in progress and start to install hyrib mesh and formwork at CJ area of B2-35/36
Thu (08/01) | 08 Jan 2026 | B2-35, B2-36 |  | Continue excavation and disposal works
Thu (08/01) | 08 Jan 2026 | B2-29, B2-30 |  | No activity
Thu (08/01) | 08 Jan 2026 | Zone 2 |  | Stressing cage assembly works
Thu (08/01) | 08 Jan 2026 | B2-37 |  | Hacking ongoing at drop area. Also noted on site that plywood (12mm thk) will be used now instead of the debonding sheet
Thu (08/01) | 08 Jan 2026 | DR4 zone 2 |  | Soldier pile installation for edge
Thu (08/01) | 08 Jan 2026 | B2-49A |  | No other activity observed
Thu (08/01) | 08 Jan 2026 | B2-48 |  | No activity
Thu (08/01) | 08 Jan 2026 | B2-43 |  | No activity
Thu (08/01) | 08 Jan 2026 | Exit 1 soil ramp |  | Start excavation to +1 to expose dwall first
Thu (08/01) | 08 Jan 2026 | BR25 |  | Hacking ongoing for rectification Dwall of CJ B2-39 (DW-078 & DW-079)
Thu (08/01) | 08 Jan 2026 | P51 |  | Manual excavation for utility support and excavation for first layer caissom
Thu (08/01) | 08 Jan 2026 | P47 |  | Current status of exposing utility support
Thu (08/01) | 08 Jan 2026 | DR3 |  | Drain base rebar work done around 50%
Thu (08/01) | 08 Jan 2026 | P45 |  | Tomorrow plan to handover half of the area to Wendyng
Thu (08/01) | 08 Jan 2026 | P31 |  | 1st lift column casting in progress
Thu (08/01) | 08 Jan 2026 | P26 |  | 2nd lift column rebar work. Next week can cast
Thu (08/01) | 08 Jan 2026 | P31 |  | 1st stage column casting in progress
Thu (08/01) | 08 Jan 2026 | P45 |  | Excavation for final layer continue
Thu (08/01) | 08 Jan 2026 | DR3 |  | Bottom bar installation status
Thu (08/01) | 08 Jan 2026 | P12 SB |  | 1st pair stressing completed. Strand cutting in progress
Thu (08/01) | 08 Jan 2026 | DR4 Zone 2 |  | Fully enclosure ERSS done. Manual excavation to expose services
Thu (08/01) | 08 Jan 2026 | P18 NB |  | Grouting of Bearing stump in progress
Fri (09/01) | 09 Jan 2026 | PMH29 |  | GCE started TT for testing. Total 4 points to do
Fri (09/01) | 09 Jan 2026 | P18 |  | Shoring materials delivery for NB side
Fri (09/01) | 09 Jan 2026 | P12 NB |  | Preparation for 1st pair stressing
Fri (09/01) | 09 Jan 2026 | P12 NB |  | Stitching formwork dismantling. 1 lane closed
Fri (09/01) | 09 Jan 2026 | P12-13 |  | Area preparation for 600T platform
Fri (09/01) | 09 Jan 2026 | P45 |  | Half excavation for last layer done. Today plan for lean concrete
Fri (09/01) | 09 Jan 2026 | DR3 |  | Base rebar work almost complete. To cast tomorrow
Fri (09/01) | 09 Jan 2026 | P47 |  | Current status of exposing UKP
Fri (09/01) | 09 Jan 2026 | B2-43 |  | No activity
Fri (09/01) | 09 Jan 2026 | P12 NB |  | 1st pair stressing completed. Dismantling of stitching formwork continue
Fri (09/01) | 09 Jan 2026 | B2-49A |  | Preparing slope lean concrete for the sump pit
Fri (09/01) | 09 Jan 2026 | DR 4 Zone |  | Strut installed. Now Ryobi G survey the area to install Prism
Fri (09/01) | 09 Jan 2026 | DR4 |  | Bund wall installation and slope protection concrete casting
Fri (09/01) | 09 Jan 2026 | B2-37 |  | Exposing of couplers is in progress
Fri (09/01) | 09 Jan 2026 | B2-37 |  | Exposing couplers
Fri (09/01) | 09 Jan 2026 | B2-38 |  | Excavation in progress
Fri (09/01) | 09 Jan 2026 | B2-35 |  | Today plan for partial lean concrete
Fri (09/01) | 09 Jan 2026 | B2-33, B2-34 |  | Rebar works in progress, Drilling ongoing at dwall side for rebar planting, B2-36: Excavation in progress
Fri (09/01) | 09 Jan 2026 | B2-29, B2-30 |  | No activity
Fri (09/01) | 09 Jan 2026 | Exit 1 |  | Cutting down to prepare for the ramp down
Fri (09/01) | 09 Jan 2026 | Vent Shaft/BR25 |  | Wendyng continue hacking work to rectify CJ for B2-39
Fri (09/01) | 09 Jan 2026 | BR8 stockpile |  | Observed no activity
Fri (09/01) | 09 Jan 2026 | P51 |  | Tomorrow will handover to KTC for excavation
Fri (09/01) | 09 Jan 2026 | P45 SB |  | Will lean con today
Fri (09/01) | 09 Jan 2026 | DR3 |  | Rebar work almost completed. Lowering down formwork for casting
Fri (09/01) | 09 Jan 2026 | P47 |  | Continue excavation and disposal
Fri (09/01) | 09 Jan 2026 | P43 |  | Tomorrow will install both starter hanger
Fri (09/01) | 09 Jan 2026 | P26 |  | Rebar work for 2nd lift. P27: working platform erection for 2nd lift rebar work. Column work above station going quite smooth if space available
Fri (09/01) | 09 Jan 2026 | P3 |  | Strand pushing for T2 and T3
Fri (09/01) | 09 Jan 2026 | P2 |  | Strand pushing in progress. 8/22 installed
Fri (09/01) | 09 Jan 2026 | P26 |  | Column 2nd lift rebar installation continue
Fri (09/01) | 09 Jan 2026 | P43 |  | Dry pack casting for starter hanger
Fri (09/01) | 09 Jan 2026 | P45 |  | Concrete ordered for lean concrete casting
Fri (09/01) | 09 Jan 2026 | P9-10 |  | Stressing cage assembly for portal frame segment
Fri (09/01) | 09 Jan 2026 | P12 |  | Tonight to dismantle stressing cage
Sat (10/01) | 10 Jan 2026 | P26 |  | 2nd lift column rebar installation in progress
Sat (10/01) | 10 Jan 2026 | P28 to P29, P31 |  | 1st lift column all cast. No activity
Sat (10/01) | 10 Jan 2026 | P39 |  | Preparation for Falsework Installation
Sat (10/01) | 10 Jan 2026 | P41 |  | Base Formwork dismantling
Sat (10/01) | 10 Jan 2026 | P42 |  | Crosshead falsework dismantling
Sat (10/01) | 10 Jan 2026 | P43 |  | Crane setting up for starter hanger installation
Sat (10/01) | 10 Jan 2026 | BR22B |  | Excavation about 90% completed. Last night completed partial lean near BR20A, Cleaning and clearing soil in progress
Sat (10/01) | 10 Jan 2026 | GL18-20 stockpile |  | No activity
Sat (10/01) | 10 Jan 2026 | B2-33 |  | Drilling ongoing for missing couplers & grouting in progress, B2-34: Rebar works in progress
Sat (10/01) | 10 Jan 2026 | B2-29, B2-30 |  | No activity
Sat (10/01) | 10 Jan 2026 | BR8 stockpile |  | No activity
Sat (10/01) | 10 Jan 2026 | P45 NB |  | Preparation for excavation works for last layer
Sat (10/01) | 10 Jan 2026 | DR3 |  | Base slab formwork closing
Sat (10/01) | 10 Jan 2026 | P51 |  | Excavation works and utility support in progress
Sat (10/01) | 10 Jan 2026 | Zone 4 |  | Singtel contractor 1 lane closed for their pipe laying works
Sat (10/01) | 10 Jan 2026 | BR25 |  | Wendyng continue hacking work to rectify CJ for B2-39
Sat (10/01) | 10 Jan 2026 | Exit 1 |  | KTC continue excavation to prepare for the ramp down
Sat (10/01) | 10 Jan 2026 | Exit 1 stockpile |  | No activity
Sat (10/01) | 10 Jan 2026 | B2-49A sump pit |  | Previous access dismantled, now new access installation in progress, Formwork in progress for slope lean con, No other activity observed
Sat (10/01) | 10 Jan 2026 | B2-48 |  | No activity
Sat (10/01) | 10 Jan 2026 | B2-43 |  | No activity
Sat (10/01) | 10 Jan 2026 | B2-37 |  | Continue exposing couplers and started plywood installation
Sat (10/01) | 10 Jan 2026 | B2-35, B2-36 |  | Excavation in progress, B2-35: Partial lean con done yesterday
Sat (10/01) | 10 Jan 2026 | B2-38 |  | Excavation in progress (1 ripper)
Sat (10/01) | 10 Jan 2026 | P3 |  | Tendon strands installation works
Sat (10/01) | 10 Jan 2026 | P3 Rectification |  | Rebar and tendon duct installation completed. Pending inspection before Formwork closing
Sat (10/01) | 10 Jan 2026 | P2 |  | Preparation for stressing works
Sat (10/01) | 10 Jan 2026 | CCW2 |  | Rock sample collection for PLT
Sat (10/01) | 10 Jan 2026 | CCW1 | north side | ATC drilling ongoing for blasting holes (2-2.2m depth), 26/66nos, Drilling for relief holes (2.2-2.4m depth) completed 24nos
Sat (10/01) | 10 Jan 2026 | CCW1 | south side | Excavation in progress
Sat (10/01) | 10 Jan 2026 | B1-03, B1-04 |  | Preparing for casting
Sat (10/01) | 10 Jan 2026 | B1-05 |  | Wall rebar works in progress
Sat (10/01) | 10 Jan 2026 | B2-33 |  | Continue drilling for couplers & PU grouting works ongoing, B2-34: Rebar works in progress
Sat (10/01) | 10 Jan 2026 | B2-29, B2-30 |  | No activity
Sat (10/01) | 10 Jan 2026 | BR8 stockpile |  | No activity
Sat (10/01) | 10 Jan 2026 | BR25 |  | Wendyng continue hacking work to rectify CJ for B2-39
Sat (10/01) | 10 Jan 2026 | Exit 1 |  | KTC continue excavation to prepare for the ramp down
Sat (10/01) | 10 Jan 2026 | B2-35 |  | Partial lean concrete was done yesterday. Now preparing formwork for drop area, Continue excavation and disposal works
Sat (10/01) | 10 Jan 2026 | B2-37 |  | Continue exposing couplers
Sat (10/01) | 10 Jan 2026 | B2-38 |  | Hacking and excavation in progress (2 exc)
Sat (10/01) | 10 Jan 2026 | P26 |  | 2nd lift column rebar installation ongoing
Sat (10/01) | 10 Jan 2026 | P42 |  | Continue Falsework dismantling
Sat (10/01) | 10 Jan 2026 | P43 |  | Starter hanger installation in progress
Sat (10/01) | 10 Jan 2026 | P45 |  | Materials clearing and access shifting in progress
Sat (10/01) | 10 Jan 2026 | DR3 |  | Preparation for Base slab casting today
Sat (10/01) | 10 Jan 2026 | Zone 4 |  | Exposing utility for water pipe laying works
Sat (10/01) | 10 Jan 2026 | P51 |  | Continue excavation and utility support
Sat (10/01) | 10 Jan 2026 | DR4 |  | 2nd layer ERSS installation works
Sat (10/01) | 10 Jan 2026 | P3 |  | Tendon strands installation works
Sat (10/01) | 10 Jan 2026 | P3 Rectification |  | Tendon duct securing in progress. Preparation for Formwork closing
Sat (10/01) | 10 Jan 2026 | P2 |  | Setting up for stressing works
Sat (10/01) | 10 Jan 2026 | S4 |  | Bearing stump casting completed
Sat (10/01) | 10 Jan 2026 | CCW1 | north side | ATC preparing to mark out blasting and relief holes for 3rd blast. The next blast is scheduled for Monday, 9 Jan
Sat (10/01) | 10 Jan 2026 | CCW1 | south side | Excavation in progress
Sat (10/01) | 10 Jan 2026 | B1-07, B1-08 |  | Excavation in progress (3 exc, 1 telescopic)
Sat (10/01) | 10 Jan 2026 | B1-05 |  | Wall rebar works in progress & start partial formwork installation
Sat (10/01) | 10 Jan 2026 | B1-03, B1-04 |  | Cleaning in progress. Plan for casting today. Final inspection ard 10am
Sat (10/01) | 10 Jan 2026 | B1-01 |  | Preparing for bottom bar installation, Access installation in progress
Sat (10/01) | 10 Jan 2026 | B1-02 |  | Exposing couplers
Mon (12/01) | 12 Jan 2026 | P18 NB |  | Started Falsework erection for segment launching
Mon (12/01) | 12 Jan 2026 | P12 |  | Preparation for LF shifting. 2 nos. shifted last night at NB. Tonight to shift another 2 nos at SB
Mon (12/01) | 12 Jan 2026 | CCW1 | North side | Preparing for 4th blasting. Overburden soil and placing rubber mats/geotextile completed. Blasting at ard 4pm
Mon (12/01) | 12 Jan 2026 | B2-33, B2-34 |  | Rebar works in progress
Mon (12/01) | 12 Jan 2026 | B2-29, B2-30 |  | No activity
Mon (12/01) | 12 Jan 2026 | GL18-20 stockpile area |  | No activity observed
Mon (12/01) | 12 Jan 2026 | Opening 7 |  | Excavation started today (1 telescopic, 1 excavator)
Mon (12/01) | 12 Jan 2026 | P3 |  | Wedge plate installation on going for T2 and T3
Mon (12/01) | 12 Jan 2026 | P3 | east side | Formwork closing
Mon (12/01) | 12 Jan 2026 | BR22B |  | Hacking works & cleaning ongoing
Mon (12/01) | 12 Jan 2026 | B2-49A sump pit |  | Formwork support ongoing for slope lean con. No other activity observed
Mon (12/01) | 12 Jan 2026 | B2-48/Linkway |  | No activity observed
Mon (12/01) | 12 Jan 2026 | B2-43 |  | No activity
Mon (12/01) | 12 Jan 2026 | B2-33, B2-34 |  | Rebar works in progress
Mon (12/01) | 12 Jan 2026 | B2-35, B2-36 |  | Excavation in progress (3 exc, 1 telescopic)
Mon (12/01) | 12 Jan 2026 | B2-38 |  | Preparing for lean concrete
Mon (12/01) | 12 Jan 2026 | B2-37 |  | Plywood laying and CJ hacking at B2-40 side
Mon (12/01) | 12 Jan 2026 | P18 |  | No activity
Mon (12/01) | 12 Jan 2026 | P12 |  | Shifting lifting frame (SB)
Mon (12/01) | 12 Jan 2026 | P3 |  | Formwork closing
Mon (12/01) | 12 Jan 2026 | P2 |  | Stressing work in progress
Mon (12/01) | 12 Jan 2026 | Exit 1 ramp down |  | Current status. Currently no activity
Mon (12/01) | 12 Jan 2026 | Beside BR25 |  | LSS backfill was done last Sat, DW78, DW79: Rebar planting ongoing for the rectification works
Mon (12/01) | 12 Jan 2026 | Opening 7 |  | No planned night shift yet
Mon (12/01) | 12 Jan 2026 | CCW2 |  | Clearing rock stockpile (1 exc, 1 telescopic)
Mon (12/01) | 12 Jan 2026 | B1-07, B1-08 |  | Hacking ongoing by WH breaker, 4 exc and 1 telescopic no activity (KTC)
Mon (12/01) | 12 Jan 2026 | B1-02 |  | Exposing couplers
Mon (12/01) | 12 Jan 2026 | B1-01 |  | Continue laying debonding sheet and rebar works. Dayshift till 830pm, night team continue (13pax)
Mon (12/01) | 12 Jan 2026 | B1-05 wall rebar |  | Continue rebar works & partial formwork installation, RTO inspection ongoing
Mon (12/01) | 12 Jan 2026 | DR3 |  | RC work no activity. Making access at south side
Mon (12/01) | 12 Jan 2026 | P45 |  | Bored pile hacking in progress
Mon (12/01) | 12 Jan 2026 | 800mm PW |  | 2nd layer of strut installation ongoing
Tue (13/01) | 13 Jan 2026 | P18 NB |  | Falsework erection for segment launching. WAH PTW verified. All in order
Tue (13/01) | 13 Jan 2026 | B2-38 |  | Leaned concrete completed last night, today planing to lay plywood
Tue (13/01) | 13 Jan 2026 | B2-37 |  | Continue exposing of couplers
Tue (13/01) | 13 Jan 2026 | Current DR4 status |  | Waler bracket installation for S2
Tue (13/01) | 13 Jan 2026 | B2-36 |  | Continues excavation & soil disposal
Tue (13/01) | 13 Jan 2026 | P12 |  | 2 nos LF installed. Cabling works in progress
Tue (13/01) | 13 Jan 2026 | P7 |  | Material clearing for falsework foundation preparation
Tue (13/01) | 13 Jan 2026 | B2-33/B2-34 |  | Rebar installation is in progress, target to cast by this week
Tue (13/01) | 13 Jan 2026 | B2-43 |  | No activity
Tue (13/01) | 13 Jan 2026 | B2-49A |  | No activity observed
Tue (13/01) | 13 Jan 2026 | Exit 1 |  | Excavation in progress to prepare for the ramp down
Tue (13/01) | 13 Jan 2026 | DR3 |  | Access shifting. Wall rebar work started
Tue (13/01) | 13 Jan 2026 | P47 |  | Top soil removal and expose UKP
Tue (13/01) | 13 Jan 2026 | P49 |  | LE prepare to remove support for column stump work
Tue (13/01) | 13 Jan 2026 | P51 |  | Continue excavation for 1st layer caisson
Tue (13/01) | 13 Jan 2026 | P26 column 2nd lift |  | Tie rod installation for formwork closing
Tue (13/01) | 13 Jan 2026 | GL18-20 stockpile |  | No activity, (3 ktc exc, 1 hirose exc idle)
Tue (13/01) | 13 Jan 2026 | B2-33, B2-34 |  | Rebar works in progress
Tue (13/01) | 13 Jan 2026 | B2-29, B2-30 |  | No activity
Tue (13/01) | 13 Jan 2026 | BR8 stockpile |  | No activity
Tue (13/01) | 13 Jan 2026 | DW78, DW79 | rectification work | Rebar pull-out test was done
Tue (13/01) | 13 Jan 2026 | B2-35, B2-36 |  | B2-35: PU grouting ongoing for dwall, B2-35, B2-36: Continue excavation & soil disposal
Tue (13/01) | 13 Jan 2026 | B2-37 |  | Continue plywood installation
Tue (13/01) | 13 Jan 2026 | B2-38 |  | Partial lean con was done, Continue excavation, Exposing couplers
Tue (13/01) | 13 Jan 2026 | Opening 7 |  | Excavation in progress
Tue (13/01) | 13 Jan 2026 | P3 crosshead |  | 1st stage stressing continue
Tue (13/01) | 13 Jan 2026 | P18 NB |  | Current falsework erection status. No activity
Tue (13/01) | 13 Jan 2026 | P12 |  | 2nos Lifting frame installation in progress
Tue (13/01) | 13 Jan 2026 | BR22B |  | Continue hacking works & preparing to lean con at slope area
Tue (13/01) | 13 Jan 2026 | Exit 1 ramp down |  | Current status of excavation & hacking works
Tue (13/01) | 13 Jan 2026 | B2-49 |  | No activity
Tue (13/01) | 13 Jan 2026 | B2-48/Linkway |  | No activity
Tue (13/01) | 13 Jan 2026 | B2-43 |  | No activity
Tue (13/01) | 13 Jan 2026 | B2-35, B2-36 |  | B2-35: Plywood & debonding sheet laying ongoing, Continue excavation & disposal works
Tue (13/01) | 13 Jan 2026 | B2-33, B2-34 |  | Rebar installation in progress
Tue (13/01) | 13 Jan 2026 | B2-38, B2-36 |  | Continue excavation & disposal works, B2-38: Clearing hacking debris
Tue (13/01) | 13 Jan 2026 | DW78, DW79 | rectification work | Currently no activity observed
Tue (13/01) | 13 Jan 2026 | BR8 stockpile |  | No activity
Tue (13/01) | 13 Jan 2026 | GL18-20 stockpile |  | No activity
Tue (13/01) | 13 Jan 2026 | Opening 7 |  | Works done for the day. No night shift planned yet
Tue (13/01) | 13 Jan 2026 | B1-05 wall |  | Rebar & formwork installation in progress
Tue (13/01) | 13 Jan 2026 | B1-07, B1-08 |  | Hacking works ongoing by WH. KTC night team continue working here (3 exc, 1 telescopic)
Tue (13/01) | 13 Jan 2026 | B1-02 |  | Current status of works
Tue (13/01) | 13 Jan 2026 | B1-01 |  | Rebar works in progress
Tue (13/01) | 13 Jan 2026 | P51 |  | No activity
Tue (13/01) | 13 Jan 2026 | P45 |  | Bored pile hacking at north side, south side no activity
Tue (13/01) | 13 Jan 2026 | DR3 |  | No activity
Tue (13/01) | 13 Jan 2026 | P26 |  | 2nd lift rebar done. P27: falsework erection done for 2nd lift rebar work
Wed (14/01) | 14 Jan 2026 | B2-37 |  | Will continue to expose couplers
Wed (14/01) | 14 Jan 2026 | B2-38 |  | Will install plywood for the remaining area
Wed (14/01) | 14 Jan 2026 | Exit 1 |  | Continue ground preparation work for the ramp down
Wed (14/01) | 14 Jan 2026 | B2-48 |  | General Housekeeping work only
Wed (14/01) | 14 Jan 2026 | B2-49A |  | No activity at the sump pit today
Wed (14/01) | 14 Jan 2026 | P14 |  | Preparation for tower access installation
Wed (14/01) | 14 Jan 2026 | P12 |  | Stressing cage for up chainage installed last night. Today to install stressing cage for down chainage
Wed (14/01) | 14 Jan 2026 | P3 |  | Formwork closing in progress for P2 side
Wed (14/01) | 14 Jan 2026 | P2 |  | Strand cutting and grout cap installation. Stage 1 grouting to be done this Sat
Wed (14/01) | 14 Jan 2026 | P43-42 |  | LG material shifting for 600t crane access
Wed (14/01) | 14 Jan 2026 | B2-33, B2-34 |  | Shearlinks installation in progress, B2-33: Lifting hook inspection was done, Plan to cast B2-33 & B2-34 tmr
Wed (14/01) | 14 Jan 2026 | B2-29, B2-30 |  | No activity
Wed (14/01) | 14 Jan 2026 | B2-32 |  | Dwall PU grouting
Wed (14/01) | 14 Jan 2026 | BR8 stockpile area |  | No activity
Wed (14/01) | 14 Jan 2026 | BR25 | slab thickening | Today plan for casting
Wed (14/01) | 14 Jan 2026 | B2-38 |  | Clearing hacking debris, Excavation & just now lean concrete completed, B2-35, B2-36:, Excavation completed, Lean concrete 90% completed, Currently 4 excavators & 1 mini idle
Wed (14/01) | 14 Jan 2026 | B2-37 |  | Exposing couplers
Wed (14/01) | 14 Jan 2026 | P47 |  | Excavation to utility support on going
Wed (14/01) | 14 Jan 2026 | P49 |  | Area preparation for excavation tonight for 800mm water pipe
Wed (14/01) | 14 Jan 2026 | P51 |  | Excavation in progress
Wed (14/01) | 14 Jan 2026 | BR22B |  | Continue hacking Dwall overcast. Plan tomorrow partial handover to CGW and start rebar works
Wed (14/01) | 14 Jan 2026 | B2-33, B2-34 |  | Continue shearlinks installation. Plan for casting tmr
Wed (14/01) | 14 Jan 2026 | B2-35 |  | Preparing plywood
Wed (14/01) | 14 Jan 2026 | B2-36, B2-38 |  | 4 excavators have been demob. Balance mini excavator here, Currently no activity for coupler exposing yet for this area
Wed (14/01) | 14 Jan 2026 | B2-37 |  | Currently no activity
Wed (14/01) | 14 Jan 2026 | B2-49 |  | No activity
Wed (14/01) | 14 Jan 2026 | B2-48/Linkway |  | No activity
Wed (14/01) | 14 Jan 2026 | B2-43 |  | No activity
Wed (14/01) | 14 Jan 2026 | Exit 1 ramp down |  | Slope trimming ongoing
Wed (14/01) | 14 Jan 2026 | BR25 | slab thickening | Casting in progress
Wed (14/01) | 14 Jan 2026 | GL18-20 stockpile |  | No activty (7 ktc exc + 1 hirose exc parked here)
Wed (14/01) | 14 Jan 2026 | Opening 7 |  | Tonight will continue excavation (1 telescopic, 1 exc)
Wed (14/01) | 14 Jan 2026 | P12 downchainage |  | Stressing cage to install tonight
Wed (14/01) | 14 Jan 2026 | P2 |  | Grouting cap installation. Tmr plan to do 1st stage grouting
Wed (14/01) | 14 Jan 2026 | CCW2 |  | Tonight to continue rock disposal (1 exc, 1 crane operator), Currently 2 excavators working — dayshift till 10pm
Wed (14/01) | 14 Jan 2026 | CCW1 | south side | Excavation ongoing till 10pm (1 exc, 1 telescopic). No planned night shift here
Wed (14/01) | 14 Jan 2026 | B1-08 |  | Hacking ongoing by WH, B1-07: Continue excavation and disposal works (3 exc, 1 telescopic. 1 exc idle)
Wed (14/01) | 14 Jan 2026 | B1-02 |  | Clearing soil
Wed (14/01) | 14 Jan 2026 | B1-01 |  | Rebar works in progress
Wed (14/01) | 14 Jan 2026 | B1-05 |  | Formwork closing in progress
Thu (15/01) | 15 Jan 2026 | P39 |  | Crosshead falsework installation
Thu (15/01) | 15 Jan 2026 | BR25 | slab thickening | Casting done last evening
Thu (15/01) | 15 Jan 2026 | BR8 stockpile |  | No activity
Thu (15/01) | 15 Jan 2026 | Opening 7 |  | Excavation in progress (B2-19)
Thu (15/01) | 15 Jan 2026 | B2-43 |  | No activity
Thu (15/01) | 15 Jan 2026 | B2-49A |  | No activity for the sump pit
Thu (15/01) | 15 Jan 2026 | P12 NB 2nd pair |  | Segment delivery tonight for unloading. Dayshift to do load test
Thu (15/01) | 15 Jan 2026 | P51 |  | Excavation to 1st layer caisson in progress
Thu (15/01) | 15 Jan 2026 | P45 |  | Bored pile hacking at north side, formwork closing at south side
Thu (15/01) | 15 Jan 2026 | P47 |  | No activity
Thu (15/01) | 15 Jan 2026 | Exit 1 |  | Partial lean concrete was done yesterday, continue ground preparation work for the ramp down
Thu (15/01) | 15 Jan 2026 | P6 |  | Excavation for falsework foundation
Thu (15/01) | 15 Jan 2026 | Exit 1 |  | Current stockpile & segregation by 1 excavator operator
Thu (15/01) | 15 Jan 2026 | P3 | west side | Formwork closing completed. Balance propping
Thu (15/01) | 15 Jan 2026 | P2 |  | 1st stage grouting
Thu (15/01) | 15 Jan 2026 | DR4 |  | Road premix removal and clearing for DR4 work
Thu (15/01) | 15 Jan 2026 | B2-29, B2-30 |  | No activity, Observed 1 excavator has been lowered at B2-29, Plan to start excavation after the casting of B2-33 & B2-34 as the current Opening 8 is used for the casting
Thu (15/01) | 15 Jan 2026 | B2-33, B2-34 |  | Inspection ongoing for M&E opening thereafter final inspection will be done, Preparation works ongoing for casting, Pouring of concrete will be from Opening 8 & 9
Thu (15/01) | 15 Jan 2026 | B2-35, B2-36, B2-37 |  | Currently no activity. Wendyng manpower focusing at B2-33/34. Opening 9 will be used for concrete pouring for B2-33 & B2-34
Thu (15/01) | 15 Jan 2026 | B2-38 |  | Dongah clearing debris for the BRP58B rectification work, Plywood installation ongoing
Thu (15/01) | 15 Jan 2026 | BR25 |  | No activity, Along CCE access (near VS): Ground levelling ongoing
Thu (15/01) | 15 Jan 2026 | BR8 stockpile |  | No activity
Thu (15/01) | 15 Jan 2026 | GL18-20 stockpile |  | No activity
Thu (15/01) | 15 Jan 2026 | Opening 7 |  | Excavation in progress
Thu (15/01) | 15 Jan 2026 | P51 |  | Continue excavation for S2 layer. By this week, will complete
Thu (15/01) | 15 Jan 2026 | P47 |  | Continue removal of top soil and exposing services
Thu (15/01) | 15 Jan 2026 | DR3 |  | Wall rebar work continue
Thu (15/01) | 15 Jan 2026 | P45 changi bound |  | Trimming of pile head and prepare for last layer caisson
Thu (15/01) | 15 Jan 2026 | P43 |  | Current status of starter hanger
Thu (15/01) | 15 Jan 2026 | P49 |  | Current status of working platform for crosshead
Thu (15/01) | 15 Jan 2026 | P44 |  | Current status of access erection. Starter hanger will install next week
Thu (15/01) | 15 Jan 2026 | P3 |  | West side propping installation. Casting tmr after 7pm
Thu (15/01) | 15 Jan 2026 | P12 |  | Platform preparation for segment launching
Thu (15/01) | 15 Jan 2026 | P51 |  | Excavation left around 30% to complete
Thu (15/01) | 15 Jan 2026 | P47 |  | Current status of exposing servicez
Thu (15/01) | 15 Jan 2026 | DR3 |  | Continue wall rebar work
Thu (15/01) | 15 Jan 2026 | P45 |  | Last layer caisson. Today casting done 70%. Lean concrete done for the last 30%
Thu (15/01) | 15 Jan 2026 | P3 |  | Tomorrow to cast the tendon duct area
Thu (15/01) | 15 Jan 2026 | B2-38 |  | Rectification work is in progress for BRP58B
Thu (15/01) | 15 Jan 2026 | P43& P44 current status |  | Starter hanger installation for P43 in progress. P44 next week
Thu (15/01) | 15 Jan 2026 | P39 |  | Falsework erection for crosshead
Thu (15/01) | 15 Jan 2026 | B2-37 |  | No activity at the moment as all Wendyng workers are focusing at B2-33/B2-34 which plan to cast it today
Thu (15/01) | 15 Jan 2026 | B2-33, B2-34 |  | Shearlinks installation & cleaning ongoing. Final inspection ard 1130am. Plan for casting tonight
Thu (15/01) | 15 Jan 2026 | B2-29, B2-30 |  | No activity
Fri (16/01) | 16 Jan 2026 | B2-37 |  | Started rebar installation
Fri (16/01) | 16 Jan 2026 | DR4 Zone 1 |  | ERSS installation for short pipe laying before dive down to undercross new drain
Fri (16/01) | 16 Jan 2026 | B2-38 |  | Started rebar work as well
Fri (16/01) | 16 Jan 2026 | BR22B |  | WH continue hacking & cleaning works. (3 workers, 1 op), CGW started CJ cleaning (2 workers)
Fri (16/01) | 16 Jan 2026 | Opening 7 |  | Excavation in progress
Fri (16/01) | 16 Jan 2026 | B2-36 |  | Preparing to lean concrete for the remaining portion after casting of B2-33/B2-34
Fri (16/01) | 16 Jan 2026 | B2-43 |  | No activity
Fri (16/01) | 16 Jan 2026 | P51 |  | Excavation in progress. Now undercrossing new USD and 700mm dia water pipe
Fri (16/01) | 16 Jan 2026 | B2-49A |  | Plan to lean concrete for the slope of sump pit also after casting of B2-33/B2-34
Fri (16/01) | 16 Jan 2026 | Exit 1 |  | Continues ground preparation work for the ramp down, partial leaned concrete with BRC has done last night
Fri (16/01) | 16 Jan 2026 | P45 |  | Base lean concrete. Balance 30% caisson will complete by this week. Prop concrete by Monday. Pile cap casting will be around 23rd
Fri (16/01) | 16 Jan 2026 | P47 |  | Continue exposing top soil
Fri (16/01) | 16 Jan 2026 | P39 |  | Current status of falsework erection/ working platform
Fri (16/01) | 16 Jan 2026 | P43 |  | Current status of starter hanger
Fri (16/01) | 16 Jan 2026 | P44 |  | Access erection done. Netting installation
Fri (16/01) | 16 Jan 2026 | Exit 1 |  | Current stockpile managed by 1 excavator
Fri (16/01) | 16 Jan 2026 | P12 |  | LMRA prior to segment launching
Fri (16/01) | 16 Jan 2026 | DR4 Zone 1 |  | Preparation for ERSS work. Today will lay 3.5m short pipe
Fri (16/01) | 16 Jan 2026 | DR4 Zone 2 |  | Platform erection for S1 strut welding and inspection
Fri (16/01) | 16 Jan 2026 | BR8 stockpile |  | No activity
Fri (16/01) | 16 Jan 2026 | B2-35, B2-36 |  | Balance lean con casting and levelling (~97% completed). Remaining portion at drop areas, B2-36: Exposing couplers
Fri (16/01) | 16 Jan 2026 | B2-37, B2-38 |  | Rebar works in progress
Fri (16/01) | 16 Jan 2026 | Opening 7 | B2-19, B2-21 | Excavation in progress
Fri (16/01) | 16 Jan 2026 | P51 |  | Excavation below new USD and water pipe in progress
Fri (16/01) | 16 Jan 2026 | DR3 |  | Balance wall rebar work in progress. Tomorrow start formwork closing
Fri (16/01) | 16 Jan 2026 | DR3 existing drain |  | Drain top hacking for diversion work
Fri (16/01) | 16 Jan 2026 | P47 |  | Continue excavation for utility support
Fri (16/01) | 16 Jan 2026 | P39 |  | Continue working platform installation. WH to complete scaffold access tomorrow
Fri (16/01) | 16 Jan 2026 | P44 |  | Access erection done
Fri (16/01) | 16 Jan 2026 | P18 |  | Current status of falsework for both up chainage and down chainage at MJ area
Fri (16/01) | 16 Jan 2026 | P12 SB |  | Wire pulling for completed segment launched
Fri (16/01) | 16 Jan 2026 | DR4 |  | Provided barricade. Traffic light pipe laying done
Fri (16/01) | 16 Jan 2026 | DR4 Zone 1 |  | ERSS installed. Tonight will lay 4m
Fri (16/01) | 16 Jan 2026 | DR4 Zone 2 |  | Working platform installed. S2 layer bracket welding in progress
Fri (16/01) | 16 Jan 2026 | P51 |  | Lean concrete 50% done for 1st layer caisson
Fri (16/01) | 16 Jan 2026 | DR3 |  | Wall rebar work completed. Tomorrow started formwork closing
Fri (16/01) | 16 Jan 2026 | P45 |  | Balance caisson rebar to complete tomorrow
Fri (16/01) | 16 Jan 2026 | P43 |  | Plan to install first pair on 21st. Now focus on P12
Fri (16/01) | 16 Jan 2026 | P41 |  | Ultracon no activity now
Fri (16/01) | 16 Jan 2026 | P39 |  | Netting installation below platform to prevent falling object
Fri (16/01) | 16 Jan 2026 | P46& P47 |  | No activity. Need to arrange crane for installation of formwork
Fri (16/01) | 16 Jan 2026 | P18 NB up-chainage falsework |  | U-jack installation on going
Fri (16/01) | 16 Jan 2026 | DR4 within hoarded up area |  | 7 nos of pipes sleeves installed for JGP work as of today
Fri (16/01) | 16 Jan 2026 | P12 SB 2nd pair |  | Load test at 1030am
Fri (16/01) | 16 Jan 2026 | B2-29, B2-30 |  | Currently no activity
Fri (16/01) | 16 Jan 2026 | B2-33, B2-34 |  | Casting in progress. Casting started last night at 10pm
Sat (17/01) | 17 Jan 2026 | P6 |  | PLT on going. Settlement recorded 1.84mm
Sat (17/01) | 17 Jan 2026 | P12 |  | 2nd pair, *SB*: stressing in progress, *NB*: Segment launched last night, preparation for strand pushing
Sat (17/01) | 17 Jan 2026 | P42 area |  | Spreader beam shifting to free up space at P43 for 1st pair launching
Sat (17/01) | 17 Jan 2026 | P12 2nd pair |  | SB: stressing continue. Tonight to launch 3rd pair here, NB: strand pushing continue
Sat (17/01) | 17 Jan 2026 | P39 |  | C-channel completed. Tonight to lay plywood
Sat (17/01) | 17 Jan 2026 | P2 NB |  | Bottom formwork and working platform dismantled. Tonight to dismantle at SB side
Mon (19/01) | 19 Jan 2026 | N6-N5 midspan wet stitching |  | Rebar planting in progress
Mon (19/01) | 19 Jan 2026 | P12 |  | 3rd pair, SB: stressing completed. To launch 4th pair tonight, NB: strand pushing. To complete stressing tonight
Mon (19/01) | 19 Jan 2026 | P10 |  | Material shifting to P19 to free up space for LG material delivery
Mon (19/01) | 19 Jan 2026 | B2-35 |  | Exposing couplers, Preparing plywood prior to rebar works
Mon (19/01) | 19 Jan 2026 | B2-36 |  | Exposing couplers
Mon (19/01) | 19 Jan 2026 | B2-37, B2-38 |  | Rebar works in progress
Mon (19/01) | 19 Jan 2026 | Dwall STN 64/65 joint area | B2-31 area | 2nd pass PU grouting works ongoing
Mon (19/01) | 19 Jan 2026 | Opening 8 |  | Preparing base for lean concrete works. Plan for casting today. This is to facilitate the shifting of the modular access for the excavation of B2-29/30, 3 excavators + 1 telescopic
Mon (19/01) | 19 Jan 2026 | Exit 1 ramp down area |  | Lean concrete works ongoing (1 exc)
Mon (19/01) | 19 Jan 2026 | BR22B |  | Soil clearing and cleaning works ongoing. Also continue to expose couplers. Plan for debonding sheet laying today
Mon (19/01) | 19 Jan 2026 | P37 |  | Scaffold erection started for 2nd lift column construction
Mon (19/01) | 19 Jan 2026 | B2-19, B2-21 | Opening 7 | Excavation in progress (3 exc, 1 telescopic)
Mon (19/01) | 19 Jan 2026 | P39 crosshead |  | Working platform plywood laying
Mon (19/01) | 19 Jan 2026 | GL18-20 stockpile |  | Currently no activity
Mon (19/01) | 19 Jan 2026 | P43-44 |  | Area casting for 600T crane parking
Mon (19/01) | 19 Jan 2026 | Opening 9 |  | Unloading of rebars to B2-35/36 area, B2-35: Continue exposing couples, B2-36: Currently no activity
Mon (19/01) | 19 Jan 2026 | B2-37 |  | RGT installation & continue rebar works, B2-38: Continue rebar works
Mon (19/01) | 19 Jan 2026 | B2-29 |  | Partial area waiting for lean concrete for the shifting of modular access (Opening 8), B2-29, B2-30: Currently no other activity observed (3 exc on standby)
Mon (19/01) | 19 Jan 2026 | BR8 stockpile |  | No activity
Mon (19/01) | 19 Jan 2026 | Exit 1 ramp down area |  | Lean concrete casting and levelling ongoing
Mon (19/01) | 19 Jan 2026 | B2-43 |  | Hacking of excess concrete at TDP
Mon (19/01) | 19 Jan 2026 | B2-49A water seepage tank area |  | Observed slope lean con done as of last weekend. Currently no activity
Mon (19/01) | 19 Jan 2026 | B2-48/Linkway |  | No activity
Mon (19/01) | 19 Jan 2026 | P18 NB 3rd pair |  | Strand pushing continue
Mon (19/01) | 19 Jan 2026 | CCW1 | south side | No activity
Mon (19/01) | 19 Jan 2026 | CCW2 |  | No activity. Blast #7 to be done tmr, CCW1 North side: Continue rock disposal works (1 exc, 1 crane)
Mon (19/01) | 19 Jan 2026 | B1-01, B1-02 |  | Rebar works in progress
Mon (19/01) | 19 Jan 2026 | B1-07, B1-08 |  | Preparing for partial lean concrete. Excavation and hacking ongoing at CJ area (WH breaker continue till midnight. KTC night: 2 exc + 1 telescopic), B1-09, B1-10: Excavation in progress
Tue (20/01) | 20 Jan 2026 | B2-37 |  | Bottom bar installation is in progress
Tue (20/01) | 20 Jan 2026 | B2-38 |  | Rebar work is in progress
Tue (20/01) | 20 Jan 2026 | B2-29 |  | Partial area was cast with lean con last night. Modular access to be shifted here to facilitate the excavation (B2-29, B2-30) (3 exc standby)
Tue (20/01) | 20 Jan 2026 | Opening 9 |  | Rebar unloading area
Tue (20/01) | 20 Jan 2026 | Exit 1 |  | Continue leaning of concrete & ground preparation work for the ramp down access
Tue (20/01) | 20 Jan 2026 | B2-36 |  | Exposing couplers and clearing hacking debris
Tue (20/01) | 20 Jan 2026 | B2-35 |  | Preparing for dwall rectification works
Tue (20/01) | 20 Jan 2026 | Exit 1 stockpile |  | Segregation & soil (soft clay) disposal by 1 excavator
Tue (20/01) | 20 Jan 2026 | B2-43 |  | No activity
Tue (20/01) | 20 Jan 2026 | B2-49A |  | No activity
Tue (20/01) | 20 Jan 2026 | Blasting no.7 completed at 3 |  | 04pm
Tue (20/01) | 20 Jan 2026 | P2 SB |  | Working platform dismantled. To continue removal of primary beams tonight
Tue (20/01) | 20 Jan 2026 | DR4 |  | Removing unused materials for DR4 JGP work
Tue (20/01) | 20 Jan 2026 | DR4 Zone 2 |  | 2nd layer waler installed. Preparing for strut installation work
Tue (20/01) | 20 Jan 2026 | Opening 7 | B2-19, B2-21 | Excavation in progress
Tue (20/01) | 20 Jan 2026 | B2-37, B2-38 |  | Rebar works in progress, CJ side formwork installation at B2-38
Tue (20/01) | 20 Jan 2026 | Opening 8 |  | Shifting of modular access in progress, B2-29: Excavation ongoing (2 exc operators, 1 exc standby)
Tue (20/01) | 20 Jan 2026 | S4 |  | Surveyor marking for positioning of bearing
Tue (20/01) | 20 Jan 2026 | B2-35 |  | Plywood installation and survey marking ongoing, Dwall 1st PU grouting in progress
Tue (20/01) | 20 Jan 2026 | P12 |  | NB shifting or lifter and stressing cage for tonight's launching of 4th pair, 4th pair SB strand pushing for stressing
Tue (20/01) | 20 Jan 2026 | BR8 stockpile area |  | No activity
Tue (20/01) | 20 Jan 2026 | P51 |  | Levelling of lean concrete of balance 50%
Tue (20/01) | 20 Jan 2026 | P51 SB |  | 1st layer caisson rebar work done. LE preparing for base plates installation
Tue (20/01) | 20 Jan 2026 | P47 |  | Current status
Tue (20/01) | 20 Jan 2026 | DR3 |  | Formwork closing for the wall and tidy up the area
Tue (20/01) | 20 Jan 2026 | P45 |  | Working platform erection for S2 strut removal
Tue (20/01) | 20 Jan 2026 | P26 |  | Resume 2nd lift work
Tue (20/01) | 20 Jan 2026 | P39 |  | Soffit plywood laying
Tue (20/01) | 20 Jan 2026 | P12 |  | Prepare for segment launching tonight at NB
Tue (20/01) | 20 Jan 2026 | P12 |  | Tendon wire pulling
Tue (20/01) | 20 Jan 2026 | DR4 |  | Cleared materials. Tomorrow GCE to resume work for JGP
Tue (20/01) | 20 Jan 2026 | DR4 |  | Continue welding work for S2 layer strut
Tue (20/01) | 20 Jan 2026 | P51 |  | Levelling for tomorrow lean concrete
Tue (20/01) | 20 Jan 2026 | P47 |  | Current status of excavation
Tue (20/01) | 20 Jan 2026 | DR3 |  | Wall formwork closing
Tue (20/01) | 20 Jan 2026 | P45 |  | Platform erection for strut removal
Tue (20/01) | 20 Jan 2026 | P43-44 |  | Stressing cage parts delivery. Tonight plan for segment delivery
Wed (21/01) | 21 Jan 2026 | Opening 7 | B2-19, B2-21 | Excavation in progress (3 exc op, 1 telescopic)
Wed (21/01) | 21 Jan 2026 | 800mm PW | zone 2 | S2 strut installation
Wed (21/01) | 21 Jan 2026 | P51 |  | (North & mid) ground levelling, (South) caisson wall formwork closing
Wed (21/01) | 21 Jan 2026 | B2-37, B2-38 |  | Rebar works in progress, CJ side formwork at B2-38
Wed (21/01) | 21 Jan 2026 | B2-35 |  | Welding of KP shear studs ongoing & CJ roughening works, B2-36: Exposing dwall couplers for rectification works ongoing
Wed (21/01) | 21 Jan 2026 | Dwall joint ST75 & ST76 |  | Preparing for PU grouting works
Wed (21/01) | 21 Jan 2026 | Opening 8 |  | B2-29 & B2-30 excavation in progress (3 exc op, 1 telescopic), Currently modular access temporarily blocked
Wed (21/01) | 21 Jan 2026 | P45 |  | Preparation for S2 removal. Afternoon going to start s2 removal
Wed (21/01) | 21 Jan 2026 | DR3 |  | Formwork closing for mid and right wall. Target to cast today
Wed (21/01) | 21 Jan 2026 | B2-38 |  | Top bar (T1) inspection by QP(S) is in progress
Wed (21/01) | 21 Jan 2026 | B2-37 |  | Continuing with rebar installation
Wed (21/01) | 21 Jan 2026 | B2-35 |  | First stage of grouting work for DWall is in progress besides exposing of couplers
Wed (21/01) | 21 Jan 2026 | B2-36 |  | Laying of plywood is progress
Wed (21/01) | 21 Jan 2026 | B2-43 |  | Finished hacking of temporary pile & materials has shifted to the loading point
Wed (21/01) | 21 Jan 2026 | B2-49A |  | No activity observed
Wed (21/01) | 21 Jan 2026 | Exit 1 |  | Ground preparation work current status for the ramp down access
Wed (21/01) | 21 Jan 2026 | Exit 1 Stockpile |  | Continue soil (soft clay) disposal to TSSG, 23 loads so far for today
Wed (21/01) | 21 Jan 2026 | DR4 |  | Ground preparation work on going
Wed (21/01) | 21 Jan 2026 | P51 |  | (north & mid) ground levelling, (South) L1 caisson formwork closing
Wed (21/01) | 21 Jan 2026 | DR3 |  | Centre and right wall formwork closing, target to cast tonight.. Existing DR3 hacking in progress
Wed (21/01) | 21 Jan 2026 | P45 |  | S2 strut removal
Wed (21/01) | 21 Jan 2026 | BR22B |  | Debonding sheet laying and RGT installation
Wed (21/01) | 21 Jan 2026 | B2-19, B2-21 | Opening 7 | Excavation in progress (3 exc, 1 telescopic). Night shift will continue here as well
Wed (21/01) | 21 Jan 2026 | Exit 1 ramp down |  | Currently no activity observed here
Wed (21/01) | 21 Jan 2026 | Exit 1 stockpile |  | Soft clay disposal in progress
Wed (21/01) | 21 Jan 2026 | B2-49A |  | No activity
Wed (21/01) | 21 Jan 2026 | B2-48/Linkway |  | No activity
Wed (21/01) | 21 Jan 2026 | B2-43 |  | No activity
Wed (21/01) | 21 Jan 2026 | B2-37, B2-38 |  | Rebar works in progress (Dayshift: 32 men, nightshift: 13 men), B2-35: Partial plywood laid, B2-36: Currently no activity
Wed (21/01) | 21 Jan 2026 | B2-29, B2-30 | Opening 8 | Excavation in progress, Modular access is temporarily blocked. Alternative access at P40 area
Wed (21/01) | 21 Jan 2026 | B1-07 to B1-10 |  | Continue hacking of dwall to expose skin wall starter bars, Excavation in progress, CJ hacking at B1-06 area
Wed (21/01) | 21 Jan 2026 | B1-05 |  | Wall formwork dismantling
Wed (21/01) | 21 Jan 2026 | B1-01 |  | Continue rebar works and construction opening formwork installation in progress, B1-02: Currently no activity
Thu (22/01) | 22 Jan 2026 | Opening 8 | B2-29, B2-30 | Excavation in progress
Thu (22/01) | 22 Jan 2026 | BR8 stockpile area |  | No activity
Thu (22/01) | 22 Jan 2026 | Opening 7 | B2-21, B2-22 | Continue excavation
Thu (22/01) | 22 Jan 2026 | P18 |  | Falsework erection for NB segment launching
Thu (22/01) | 22 Jan 2026 | N5-N6 |  | Mid span Formwork closing in progress
Thu (22/01) | 22 Jan 2026 | P12 |  | Preparation for segment stressing works. Safety briefing ongoing
Thu (22/01) | 22 Jan 2026 | P2 |  | Crosshead Falsework dismantling
Thu (22/01) | 22 Jan 2026 | P1 |  | Preparation for pad footing installation
Thu (22/01) | 22 Jan 2026 | B2-37/B2-38 |  | Top bar inspection is in progress by QP(S) team
Thu (22/01) | 22 Jan 2026 | P18 |  | NB Falsework erection current status
Thu (22/01) | 22 Jan 2026 | N5-N6 |  | Mid span outer formwork closing in progress
Thu (22/01) | 22 Jan 2026 | B2-35 |  | Started bottom rebar installation
Thu (22/01) | 22 Jan 2026 | B2-36 |  | Continues exposing of couplers & laying of plywood for the remaining area
Thu (22/01) | 22 Jan 2026 | B2-21, B2-22 | Opening 7 | Excavation in progress, 3 excavators working, 1 standby, 1 telescopic
Thu (22/01) | 22 Jan 2026 | BR22B |  | Plywood laying ongoing
Thu (22/01) | 22 Jan 2026 | B2-43 |  | No activity
Thu (22/01) | 22 Jan 2026 | Exit 1 |  | Continue ground preparation for the ramp down by 1 excavator
Thu (22/01) | 22 Jan 2026 | P12 |  | SB tendon strands installation ongoing
Thu (22/01) | 22 Jan 2026 | P6 |  | Preparation works for pad footing installation
Thu (22/01) | 22 Jan 2026 | P3 Rectification |  | Formwork dismantling in progress
Thu (22/01) | 22 Jan 2026 | P2 |  | Falsework dismantling
Thu (22/01) | 22 Jan 2026 | P1 |  | Pad footings near column installed
Thu (22/01) | 22 Jan 2026 | B2-29, B2-30 | Opening 8 | Excavation in progress (3 excavators, 1 telescopic)
Thu (22/01) | 22 Jan 2026 | B2-35 |  | Dwall PU grouting works and RGT installation in progress
Thu (22/01) | 22 Jan 2026 | Exit 1 Stockpile |  | Continue soil (soft clay) disposal to TSSG, 14 loads so far for today
Thu (22/01) | 22 Jan 2026 | 800mm PW | zone 2 | S3 strut installation and Manual excavation ongoing
Thu (22/01) | 22 Jan 2026 | P51 |  | (North) Manual excavation, (Mid) L1 rebar installation, (South) formwork closing
Thu (22/01) | 22 Jan 2026 | DR3 |  | Centre and right wall casting completed,currently concrete curing, no hacking activity on DE143 drain..left wall formwork closing in progress
Thu (22/01) | 22 Jan 2026 | P45 |  | S2 strut removal
Fri (23/01) | 23 Jan 2026 | B2-38 |  | Shear link installation is in progress
Fri (23/01) | 23 Jan 2026 | B2-37 |  | Ongoing sanitary pipe installation
Fri (23/01) | 23 Jan 2026 | B2-35 |  | Rebar works in progress, PU grouting ongoing. Target to complete today
Fri (23/01) | 23 Jan 2026 | B2-36 |  | Coupler exposing ongoing, Rebar works in progress
Fri (23/01) | 23 Jan 2026 | B2-27 to B2-30 |  | Excavation in progress (3 excavators, 1 telescopic)
Fri (23/01) | 23 Jan 2026 | BR8 stockpile |  | Soil shifting within the area to facilitate temporary material storage. Currently no disposal activity, Now concrete barriers shifting and cleaning works ongoing
Fri (23/01) | 23 Jan 2026 | B2-43 |  | No activity
Fri (23/01) | 23 Jan 2026 | B2-49 | A | Plan to finish up the remaining slope lean concrete for the sump pit
Fri (23/01) | 23 Jan 2026 | Exit 1 |  | Continue excavation & ground preparation for the ramp down by 1 excavator
Fri (23/01) | 23 Jan 2026 | P45 |  | S2 strut removal
Fri (23/01) | 23 Jan 2026 | DR3 |  | Mid and right wall formwork removal, left wall formwork closing
Fri (23/01) | 23 Jan 2026 | P47 |  | Resume excavation, expose utilities
Fri (23/01) | 23 Jan 2026 | P51 |  | L1 caisson rebar works on going
Fri (23/01) | 23 Jan 2026 | Exit 1 |  | Almost clear the stockpile, remaining 2-3 loads needs to segregate prior sending to TSSG
Fri (23/01) | 23 Jan 2026 | B2-21, B2-22 | Opening 7 | Excavation in progress (4 exc, 1 telescopic)
Fri (23/01) | 23 Jan 2026 | B2-27 to B2-30 |  | Excavation in progress (3 exc & 1 telescopic working, 1 exc standby)
Fri (23/01) | 23 Jan 2026 | B2-35 |  | PU grouting works and rebar planting in progress, B2-36: Continue exposing couplers and lean concrete at drop area
Fri (23/01) | 23 Jan 2026 | Exit 1 ramp down |  | Excavation and disposal in progress. Works till 10pm
Fri (23/01) | 23 Jan 2026 | Exit 1 stockpile |  | Continue disposal works till 10pm
Fri (23/01) | 23 Jan 2026 | B2-43 |  | No activity
Fri (23/01) | 23 Jan 2026 | B2-37, B2-38 |  | Shearlinks installation ongoing
Fri (23/01) | 23 Jan 2026 | B2-35, B2-36 |  | Rebar works in progres & preparing to continue plywood laying at B2-36
Fri (23/01) | 23 Jan 2026 | B2-27 to B2-30 |  | Excavation in progress (4 exc, 1 telescopic). No planned night shift here yet
Fri (23/01) | 23 Jan 2026 | B2-21, B2-22 | Opening 7 | Excavation to continue for night shift. Now preparing to handover to night team
Fri (23/01) | 23 Jan 2026 | CCW1 | south side | No activity. 1 excavator preparing for rock disposal works tonight at CCW2
Fri (23/01) | 23 Jan 2026 | CCW2 |  | Tonight to continue rock disposal
Fri (23/01) | 23 Jan 2026 | B1-08 to B1-10 |  | Excavation in progress
Fri (23/01) | 23 Jan 2026 | B1-07 |  | Skin wall area currently no activity. CJ roughening at B1-04 side
Fri (23/01) | 23 Jan 2026 | B1-05 |  | Grinding wall surface
Fri (23/01) | 23 Jan 2026 | B1-01, B1-02 |  | Continue top bar installation
Fri (23/01) | 23 Jan 2026 | B2-21, B2-22 | Opening 7 | Excavation in progress
Sat (24/01) | 24 Jan 2026 | 800mm PW | zone 2 | S3 strut installation
Sat (24/01) | 24 Jan 2026 | P51 |  | L1 caisson rebar work
Sat (24/01) | 24 Jan 2026 | P47 |  | Excavation to expose utilities
Sat (24/01) | 24 Jan 2026 | P45 |  | Yesterday completed S2 removal, today morning housekeeping and scaffold dismantling, later afternoon start pile cap rebar work
Sat (24/01) | 24 Jan 2026 | DR3 |  | Ready for left wall casting
Sat (24/01) | 24 Jan 2026 | P43 |  | Preparation work for segment launching tomorrow
Sat (24/01) | 24 Jan 2026 | P39 |  | No activity
Sat (24/01) | 24 Jan 2026 | P41 |  | No activity
Sat (24/01) | 24 Jan 2026 | P26 |  | Column formwork closing
Sat (24/01) | 24 Jan 2026 | P18 |  | Falsework erection on going
Sat (24/01) | 24 Jan 2026 | P15-P16 |  | Mid span stitching formwork dismantling work at north bound
Sat (24/01) | 24 Jan 2026 | P12 |  | U6/D6 Tendon pulling works
Sat (24/01) | 24 Jan 2026 | P1 |  | Crosshead falsework erection
Sat (24/01) | 24 Jan 2026 | P3 |  | Formwork removal in progress
Sat (24/01) | 24 Jan 2026 | P18 |  | Falsework erection on going
Sat (24/01) | 24 Jan 2026 | P12 |  | Stressing completed. No activity
Sat (24/01) | 24 Jan 2026 | P1 |  | Falsework erection ongoing
Sat (24/01) | 24 Jan 2026 | Blasting no.9 completed at 3 |  | 26pm
Sat (24/01) | 24 Jan 2026 | P3 |  | Formwork removal completed. Now housekeeping only. Pending cube test result before stressing
Sat (24/01) | 24 Jan 2026 | P51 |  | L1 caisson rebar work
Sat (24/01) | 24 Jan 2026 | P48 |  | LSS backfilling ongoing
Sat (24/01) | 24 Jan 2026 | DR3 |  | Mid and right wall formwork removal
Sat (24/01) | 24 Jan 2026 | P45 |  | Housekeeping
Sun (25/01) | 25 Jan 2026 | Exit 1 ramp down |  | Excavation in progress (2 exc)
Sun (25/01) | 25 Jan 2026 | B2-31 |  | Hacking ongoing to expose skin wall starter bars
Sun (25/01) | 25 Jan 2026 | B2-35, B2-36 |  | PU grouting ongoing, Rebar works in progress (Wendyng - 20 men), B2-37, B2-38: Currently no activity
Sun (25/01) | 25 Jan 2026 | Exit 1 ramp down |  | Excavation in progress (2 excavators)
Sun (25/01) | 25 Jan 2026 | B2-49A |  | No activity
Sun (25/01) | 25 Jan 2026 | B2-48/Linkway |  | No activity
Sun (25/01) | 25 Jan 2026 | B2-43 |  | No activity
Sun (25/01) | 25 Jan 2026 | BR22B |  | Current status of waterproofing membrane laying. No other activity observed
Sun (25/01) | 25 Jan 2026 | CCW2 |  | Stockpile shifting works (1 exc operator), CCW1 North side: No other activity observed
Sun (25/01) | 25 Jan 2026 | B1-05 |  | Scaffold installation ongoing by WH (2 pax)
Sun (25/01) | 25 Jan 2026 | B1-07 to B1-10 |  | Excavation ongoing by KTC (3 exc, 1 telescopic working), Hacking ongoing to expose skin wall starter bars by WH (1 exc), General housekeeping by WH (2 pax), No other activity observed here
Sun (25/01) | 25 Jan 2026 | B1-01, B1-02 |  | No rebar works today. CGW off day due to company event, WH preparing pipes at escalator pit area (3 pax)
Mon (26/01) | 26 Jan 2026 | P18 NB upchainage |  | Hollow section installation for 3rd and 4th pair. Tonight and tmr night to launch 1st pair
Mon (26/01) | 26 Jan 2026 | DR4 |  | Changing to breaker for old footpath hacking
Mon (26/01) | 26 Jan 2026 | DR4 |  | Marking of services location for TT
Mon (26/01) | 26 Jan 2026 | P51 |  | Caisson casting. Tomorrow to complete 100% for 1st layer
Mon (26/01) | 26 Jan 2026 | BR22B |  | Started bottom rebar works (4 men)
Mon (26/01) | 26 Jan 2026 | Opening 7 |  | B2-21 to B2-24: Excavation in progress (4 exc, 1 telescopic + 1 WH exc)
Mon (26/01) | 26 Jan 2026 | P3 crosshead T4 |  | Preparation for stressing
Mon (26/01) | 26 Jan 2026 | B2-31 area |  | Continue hacking works to expose skin wall starter bars
Mon (26/01) | 26 Jan 2026 | B2-35, B2-36 |  | Rebar works in progress, Plan to cast B2-35, B2-36, B2-37 & B2-38 this Saturday
Mon (26/01) | 26 Jan 2026 | Opening 8 |  | B2-25 to B2-30: Excavation in progress (3 exc + 1 telescopic working. 1 exc under repair)
Mon (26/01) | 26 Jan 2026 | P47 |  | Safety time out for AC cable damaged
Mon (26/01) | 26 Jan 2026 | P45 |  | Pile cap rebar started. To cast this week
Mon (26/01) | 26 Jan 2026 | Exit 1 stockpile |  | Continue clearing (2 exc)
Mon (26/01) | 26 Jan 2026 | B2-49A sump pit |  | Groove line cutting ongoing. Plan to complete today
Mon (26/01) | 26 Jan 2026 | Exit 1 ramp down |  | Levelling works and partial hardcore laying. This evening plan for partial lean concrete casting
Mon (26/01) | 26 Jan 2026 | B2-48/Linkway |  | No activity
Mon (26/01) | 26 Jan 2026 | B2-43 |  | No activity
Mon (26/01) | 26 Jan 2026 | P26 |  | Access scaffold erection for casting
Mon (26/01) | 26 Jan 2026 | P37 |  | 2nd lift falsework erection for rebar work
Mon (26/01) | 26 Jan 2026 | P39 |  | Scaffold erection for rebar work
Mon (26/01) | 26 Jan 2026 | P43-P44 |  | Platform casting for segment launching
Mon (26/01) | 26 Jan 2026 | CCW1 North side S5 |  | Hirose continue drilling and bolt planting for waler brackets. Works till 8pm
Mon (26/01) | 26 Jan 2026 | CCW2 |  | No activity. Blasting #10 to be done tmr
Mon (26/01) | 26 Jan 2026 | CCW1 | South side | Continue soil shifting
Mon (26/01) | 26 Jan 2026 | B1-07, B1-08 |  | Hacking Dwall to expose couplers. Currently no other activity
Mon (26/01) | 26 Jan 2026 | B1-01, B1-02 |  | Shearlinks and wall starter bars installation in progress
Mon (26/01) | 26 Jan 2026 | BR22B |  | Bottom rebar works in progress. No planned night shift here yet
Mon (26/01) | 26 Jan 2026 | P43 |  | 1st pair segment adjusting
Mon (26/01) | 26 Jan 2026 | Opening 7 |  | Excavation in progress. Tonight to continue here and Opening 8
Mon (26/01) | 26 Jan 2026 | B2-35, B2-36 |  | Top bar installation in progress
Mon (26/01) | 26 Jan 2026 | B2-37, B2-38 |  | Currently no activity. Plan for casting together with B2-35 and B2-36 this Saturday
Mon (26/01) | 26 Jan 2026 | B2-48, B2-43 |  | No activity
Mon (26/01) | 26 Jan 2026 | Exit 1 ramp down |  | Partial BRC laying ongoing prior to lean con casting. Steel plates laying along access along ongoing
Mon (26/01) | 26 Jan 2026 | P10 |  | LG materials unloading continue
Tue (27/01) | 27 Jan 2026 | B2-37 |  | Continues 1st stage of grouting work for the Dwall
Tue (27/01) | 27 Jan 2026 | B2-35/B2-36 |  | Continues top bar installation, target to cast tgt with B2-37&B2-38 this Sat
Tue (27/01) | 27 Jan 2026 | B2-40 |  | Rectification work for BRP61 is in progress
Tue (27/01) | 27 Jan 2026 | P18 |  | Falsework installation for NB segment launching and segment adjustment for NB-D01
Tue (27/01) | 27 Jan 2026 | P12 |  | Stressing works ongoing for NB segment
Tue (27/01) | 27 Jan 2026 | B2-43 |  | No activity
Tue (27/01) | 27 Jan 2026 | DR4 Zone 2 |  | Manual excavation for S4 layer waler and strut
Tue (27/01) | 27 Jan 2026 | Opening 7 |  | B2-21 to B2-24: Excavation and soil disposal in progress (3 exc op + 1 telescopic)
Tue (27/01) | 27 Jan 2026 | B2-49A |  | No activity observed
Tue (27/01) | 27 Jan 2026 | Exit 1 |  | Partial lean concrete was done just now, will continue ground preparation work for the ramp down
Tue (27/01) | 27 Jan 2026 | P51 |  | 1st layer caisson casting. LE started struting work
Tue (27/01) | 27 Jan 2026 | DR4 |  | TT for JGP work
Tue (27/01) | 27 Jan 2026 | Opening 8 |  | B2-25 to B2-30: Excavation in progress (4 exc op + 1 telescopic, 1 WH exc standby)
Tue (27/01) | 27 Jan 2026 | B2-31 |  | Current status of hacking of skin wall
Tue (27/01) | 27 Jan 2026 | Exit 1 |  | Current stockpile status
Tue (27/01) | 27 Jan 2026 | B2-35, B2-36 |  | Rebar works in progress
Tue (27/01) | 27 Jan 2026 | P3 |  | Preparation for stressing works. Target to complete by tmr
Tue (27/01) | 27 Jan 2026 | P1 |  | Falsework assembly works ongoing
Tue (27/01) | 27 Jan 2026 | P47 |  | Barricaded 1m distance from services
Tue (27/01) | 27 Jan 2026 | P45 |  | Bottom rebar work for pile cap
Tue (27/01) | 27 Jan 2026 | P44 |  | Assembling starter hangers for segment launching work
Wed (28/01) | 28 Jan 2026 | DR4 |  | Left 4nos of bracket install for S4 layer. Today to complete
Wed (28/01) | 28 Jan 2026 | B2-35/B2-36 |  | Continues top bar installation
Wed (28/01) | 28 Jan 2026 | B2-38 |  | Providing rebar protection to the vertical bars
Wed (28/01) | 28 Jan 2026 | B2-40 |  | Will continue rectification work for BRP61
Wed (28/01) | 28 Jan 2026 | P51 |  | Formwork removal and strutting works
Wed (28/01) | 28 Jan 2026 | B2-43 |  | No activity
Wed (28/01) | 28 Jan 2026 | B2-49 |  | No activity
Wed (28/01) | 28 Jan 2026 | P45 |  | Pile cap bottom rebar work
Wed (28/01) | 28 Jan 2026 | Exit 1 |  | Continue ground preparation work for the ramp down by 1 excavator
Wed (28/01) | 28 Jan 2026 | P39 |  | Crosshead top rebar work
Wed (28/01) | 28 Jan 2026 | P41 |  | Tendon wire pulling
Wed (28/01) | 28 Jan 2026 | P44 |  | Preparing to install starter hanger
Wed (28/01) | 28 Jan 2026 | P1 |  | Material shifting and working platform assembly
Wed (28/01) | 28 Jan 2026 | Exit 1 |  | Current stockpile status
Wed (28/01) | 28 Jan 2026 | P26 |  | 2nd lift column cast yesterday. Scaffold dismantled
Wed (28/01) | 28 Jan 2026 | Opening 7 & 8 |  | B2-21 to B2-30: Excavation in progress (9 exc, 1 telescopic), B2-30: Exposing rock
Wed (28/01) | 28 Jan 2026 | B2-32 |  | Continue exposing skin wall starter bars
Wed (28/01) | 28 Jan 2026 | B2-35, B2-36 |  | PU grouting in progress, Shearlinks and wall starter bars installation in progress, B2-37, B2-38: Currently no activity, Plan to cast these 4 slabs this Saturday
Wed (28/01) | 28 Jan 2026 | P18 1st pair NB |  | Segement adjustment in progress
Wed (28/01) | 28 Jan 2026 | Zone 2 |  | LG materials unloading in progress
Wed (28/01) | 28 Jan 2026 | P1 |  | Falsework platform assembly works ongoing
Wed (28/01) | 28 Jan 2026 | P3 |  | Continue stressing works at SB. Today to complete stressing
Wed (28/01) | 28 Jan 2026 | P47 |  | Preparation for utility support installation
Wed (28/01) | 28 Jan 2026 | DR4 |  | TT in progress for JGP
Wed (28/01) | 28 Jan 2026 | P51 |  | Formwork removal and strutting work
Wed (28/01) | 28 Jan 2026 | P44 |  | Assembling of starter hangers
Thu (29/01) | 29 Jan 2026 | B2-35/B2-36 |  | Continues rebar installation, now working @ CD door area
Thu (29/01) | 29 Jan 2026 | B2-30 |  | Barricade installation around boulder area
Thu (29/01) | 29 Jan 2026 | Opening 8 & 7 |  | B2-21 to B2-29: Excavation & disposal ongoing, B2-27 to B2-29: Hacking skin wall in progress to expose starter bars
Thu (29/01) | 29 Jan 2026 | B2-38 |  | Rebar & formwork installation has completed
Thu (29/01) | 29 Jan 2026 | GL18-20 | BR9 area | Soil clearing ongoing
Thu (29/01) | 29 Jan 2026 | B2-40 |  | No activity
Thu (29/01) | 29 Jan 2026 | B2-43 |  | No activity
Thu (29/01) | 29 Jan 2026 | B2-48 |  | Observed more barricade have been installed along the wall
Thu (29/01) | 29 Jan 2026 | B2-49A |  | Continue to finish up the slope lean concrete for the sump pit, concrete barriers have placed around the area
Thu (29/01) | 29 Jan 2026 | P39 |  | Crosshead rebar installation in progress
Thu (29/01) | 29 Jan 2026 | Exit 1 |  | Partial lean concrete was done last night, will continue ground preparation work for the ramp down
Thu (29/01) | 29 Jan 2026 | Exit 1 |  | Current stockpile status, will continue disposal soft clay to TSSG by 1 excavator
Thu (29/01) | 29 Jan 2026 | P47 |  | Protection of services
Thu (29/01) | 29 Jan 2026 | P45 |  | Pile cap rebar work
Thu (29/01) | 29 Jan 2026 | P45 |  | Pile cap top rebar installation
Thu (29/01) | 29 Jan 2026 | P47 |  | Current excavation status
Thu (29/01) | 29 Jan 2026 | P51 |  | S1 strut installation
Thu (29/01) | 29 Jan 2026 | 800mm PW |  | S4 strut waler installation in progress
Thu (29/01) | 29 Jan 2026 | P18 |  | No activity
Thu (29/01) | 29 Jan 2026 | P1 |  | No activity
Thu (29/01) | 29 Jan 2026 | P11 |  | Unloading LG material
Thu (29/01) | 29 Jan 2026 | B2-30 | South side-GL25 | Rock surface inspection with RTO & WH
Thu (29/01) | 29 Jan 2026 | P3 |  | Base formwork removal
Thu (29/01) | 29 Jan 2026 | Opening 8 |  | B2-25 to B2-30: Excavation & disposal in progress (3 exc, 1 telescopic), Tonight to continue works here
Thu (29/01) | 29 Jan 2026 | Opening 7 |  | B2-21 to B2-24: Excavation & disposal in progress (4 exc, 1 telescopic), Tonight to continue works here
Thu (29/01) | 29 Jan 2026 | B2-35, B2-36 |  | Formwork, shearlinks and Hyrib installation ongoing, B2-37: Shearlinks and cleaning ongoing, Plan to cast B2-35 to B2-38 this Saturday
Thu (29/01) | 29 Jan 2026 | B2-43 |  | No activity, Observed 2 excavators here currently
Thu (29/01) | 29 Jan 2026 | Exit 1 ramp down |  | No activity, Exit 1 stockpile levelling
Thu (29/01) | 29 Jan 2026 | BR22B |  | No activity
Thu (29/01) | 29 Jan 2026 | Dr4 |  | No activity
Thu (29/01) | 29 Jan 2026 | P51 |  | No activity
Thu (29/01) | 29 Jan 2026 | P47 |  | No activity
Thu (29/01) | 29 Jan 2026 | P45 |  | Pile cap top rebar installation
Thu (29/01) | 29 Jan 2026 | DR3 |  | No activity
Thu (29/01) | 29 Jan 2026 | CCW2 |  | No activity. Blast #11 to be done tmr, Tonight to resume rock disposal after Hirose ends ard 930pm (1 exc, 1 crane)
Thu (29/01) | 29 Jan 2026 | CCW1 | North side | Hirose continue waler installation. Works till 930pm
Thu (29/01) | 29 Jan 2026 | B1-09/10 |  | Preparing concrete pump connections for lean concrete casting
Thu (29/01) | 29 Jan 2026 | B1-11 |  | Continue excavation and disposal till 10pm
Thu (29/01) | 29 Jan 2026 | B1-08 |  | Exposing couplers
Thu (29/01) | 29 Jan 2026 | B1-07, B1-08 RC Column |  | Night team continue rebar works (8 men)
Thu (29/01) | 29 Jan 2026 | B1-07 |  | No activity
Thu (29/01) | 29 Jan 2026 | B2-37 |  | Continues first stage of grouting work for the Dwall
Fri (30/01) | 30 Jan 2026 | P51 |  | S1 strut installation in progress. To complete by Monday including MPI test
Fri (30/01) | 30 Jan 2026 | P47 |  | Manual excavation for utility support
Fri (30/01) | 30 Jan 2026 | P45 |  | Top bar work in progress. Shifting of access on going. To cast by this week
Fri (30/01) | 30 Jan 2026 | P44 |  | Start hanger already lift up. This week to complete first pair installation
Fri (30/01) | 30 Jan 2026 | P40 |  | Current status of platform preparation
Fri (30/01) | 30 Jan 2026 | Zone 4 DR2 |  | MPI test for waler and preparing for S4 strut installation
Fri (30/01) | 30 Jan 2026 | Opening 8 |  | Soil disposl ongoing, B2-25 to B2-28: Excavation in progress, B2-29 to B2-27 (North side): Hacking ongoing to expose skin wall starter bars
Fri (30/01) | 30 Jan 2026 | B2-32, B2-34 | South side | Hacking ongoing to expose skin wall starter bars
Fri (30/01) | 30 Jan 2026 | B2-35, B2-36 |  | RTO inspection ongoing, Formwork installation & preparing corrugated pipes, Wall starter bars & cleaning ongoing, B2-37, B2-38: Currently only cleaning works
Fri (30/01) | 30 Jan 2026 | P45 |  | Pile cap top rebar work in progress
Fri (30/01) | 30 Jan 2026 | P47 |  | Manual excavation for utility support installation
Fri (30/01) | 30 Jan 2026 | P51 |  | LE continue strut installation for S1
Fri (30/01) | 30 Jan 2026 | P44 |  | Tonight will launch two segments. Crane set up in progress
Fri (30/01) | 30 Jan 2026 | P39 |  | Crosshead top rebar work in progress
Fri (30/01) | 30 Jan 2026 | P10 |  | Unloading LG materials
Fri (30/01) | 30 Jan 2026 | P18 |  | Preparation work for 2nd segment launching
Fri (30/01) | 30 Jan 2026 | P3 |  | Base formwork removal
Fri (30/01) | 30 Jan 2026 | P1 |  | Working platform plywood laying
Fri (30/01) | 30 Jan 2026 | 800mm PW | zone 2 | S4 strut installation in progress
Fri (30/01) | 30 Jan 2026 | P51 |  | S1 strut installation ongoing
Fri (30/01) | 30 Jan 2026 | P47 |  | No activity
Fri (30/01) | 30 Jan 2026 | P45 |  | Pile cap top rebar work ongoing
Fri (30/01) | 30 Jan 2026 | P44 |  | Crane parking ready for segment launching tonight
Fri (30/01) | 30 Jan 2026 | P39 |  | No activity
Fri (30/01) | 30 Jan 2026 | Opening 8 |  | B2-25 to B2-30: Excavation and rock shifting in progress
Fri (30/01) | 30 Jan 2026 | B2-33 |  | Scaffold installation in progress for column works
Fri (30/01) | 30 Jan 2026 | B2-32 | south side | Hacking ongoing to expose skin wall starter bars
Fri (30/01) | 30 Jan 2026 | B2-35 to B2-38 |  | Corrugated pipe, shearlinks and hyrib installation ongoing, Cleaning in progress, Preparing pipe connections for casting, Plan for casting B2-35, B2-36, B2-37 & B2-38 tomorrow
Fri (30/01) | 30 Jan 2026 | BR22B |  | Resumed replacing damaged couplers with new coupler bars
Fri (30/01) | 30 Jan 2026 | Opening 7 |  | B2-21 to B2-24: Continue excavation and disposal works
Fri (30/01) | 30 Jan 2026 | DR4 Zone 2 |  | S4 waler and strut welding work
Fri (30/01) | 30 Jan 2026 | P18 NB |  | 1st pair adjustment completed. Installation of U jack and shimming for 2nd pair launching. Schedule to launched by 2nd Feb
Sat (31/01) | 31 Jan 2026 | P51 |  | Today to continue installation of 1st layer strut. No incompatible works observed
Sat (31/01) | 31 Jan 2026 | P46 |  | Manual excavation for Utility support installation
Sat (31/01) | 31 Jan 2026 | P45 pile cap |  | Balance links and starter bar installation. Casting tonight at 8pm
Sat (31/01) | 31 Jan 2026 | P44 upchainage D01 |  | Segment launched last night. Tonight to launched downchainage to complete 1st pair
Sat (31/01) | 31 Jan 2026 | Opening 8 |  | B2-25 to B2-30: Excavation & disposal in progress (4 exc + 1 telescopic working, 1 exc standby), B2-27: Hacking ongoing to expose skin wall starter bars (1 mini)
Sat (31/01) | 31 Jan 2026 | Opening 7 |  | B2-21 to B2-24: Excavation and disposal in progress (6 exc, 1 telescopic)
Sat (31/01) | 31 Jan 2026 | B2-32 |  | Skin wall hacking ongoing (1 mini)
Sat (31/01) | 31 Jan 2026 | B2-35, B2-36, B2-37, B2-38 |  | Final inspection was done, only minor comments. Target to cast this afternoon
Sat (31/01) | 31 Jan 2026 | B2-43 |  | No activity, B2-48: No activity, Today afternoon plan to do trial run for the exit 1 soil ramp here
Sat (31/01) | 31 Jan 2026 | BR22B |  | Rebar works in progress
Sat (31/01) | 31 Jan 2026 | P10 |  | Unloading of LG materials continue. 18 containers delivered so far
Sat (31/01) | 31 Jan 2026 | P1 |  | Bottom formwork installation started
Sat (31/01) | 31 Jan 2026 | Exit 1 soil ramp |  | Trial run for truck access done. Some comments such as ‘hump ahead’ signages, interlocking of concrete barriers to be followed up by WH. About 15mins turnaround time for 1 truck including loading time
Sat (31/01) | 31 Jan 2026 | CCW2 |  | Clearing blasting rocks to facilitate ATC machine for drilling works for blast #12. Next blast is scheduled for 03 Feb
Sat (31/01) | 31 Jan 2026 | CCW1 | south side | Excavation and disposal ongoing
Sat (31/01) | 31 Jan 2026 | CCW1 | North side | Waler welding works in progress
Sat (31/01) | 31 Jan 2026 | B1-06, B1-04 |  | Wall formwork installation in progress
Sat (31/01) | 31 Jan 2026 | B1-07, B1-08 |  | PU grouting ongoing, Exposing couplers and clearing debris from drop areas, RGT installation and preparing for water flushing, Partial debonding sheet laid
Sat (31/01) | 31 Jan 2026 | B1-08 |  | Column C01-3 rebar works and coupler tightening ongoing
Sat (31/01) | 31 Jan 2026 | B1-09, B1-10 |  | Lean concrete cast for remaining areas except for the soil disposal opening and drop areas, Soil disposal ongoing and plan to complete today, Scaffold installation ongoing for column works
Sat (31/01) | 31 Jan 2026 | Zone 4 near PMH28 |  | Preparation for TT to install pipe sleeve for JGP. WH supervisor here and RES in full time supervision. Nearest utility as per TT record is gas pipe at 2m O.C of TT
Mon (02/02) | 02 Feb 2026 | P27 |  | 2nd lift column rebar work
Mon (02/02) | 02 Feb 2026 | P36 |  | Falsework erection for 2nd lift. P37: started rebar work for 2nd lift
Mon (02/02) | 02 Feb 2026 | Exit 1 |  | Current stockpile status, 1 excavator idling
Mon (02/02) | 02 Feb 2026 | P18 |  | Gap closing at platform. Scheduled to launch U02 tonight
Mon (02/02) | 02 Feb 2026 | P39 |  | Preparing for main bar inspection. Ducting installation in progress
Mon (02/02) | 02 Feb 2026 | P43& P44 |  | Stitching formwork delivery. Stressing cages start to shift to the area by Ultracon
Mon (02/02) | 02 Feb 2026 | B2-43 |  | Excavation in progress by 1 excavator, another excavator is idling
Mon (02/02) | 02 Feb 2026 | B2-29 |  | Exposing of couplers
Mon (02/02) | 02 Feb 2026 | P45 |  | MPI test done. Repairing of damaged duct. Tomorrow plan to start excavation
Mon (02/02) | 02 Feb 2026 | P49 |  | Wendyng prepare rebar cage for column. On site cable still clashing
Mon (02/02) | 02 Feb 2026 | P47 |  | As of now no activity
Mon (02/02) | 02 Feb 2026 | P46 |  | Utility marking to start excavation
Mon (02/02) | 02 Feb 2026 | P45 |  | Pile cap curing
Mon (02/02) | 02 Feb 2026 | DR4 |  | Lean concrete at the base done. Welding on going to rectify the comment. Two pipes target to lower down tonight. Waiting for QP amended drawing
Mon (02/02) | 02 Feb 2026 | P18 |  | Tendon wire pulling
Mon (02/02) | 02 Feb 2026 | N5-N6 |  | Preparation for stressing work
Mon (02/02) | 02 Feb 2026 | P1 |  | Current status of soffit plywood laying
Mon (02/02) | 02 Feb 2026 | P3 |  | Soffit formwork removal
Mon (02/02) | 02 Feb 2026 | DR4 |  | Welding of waler joint. Tonight plan to lay the pipes
Mon (02/02) | 02 Feb 2026 | P51 |  | Packing concrete casting. Tomorrow to excavate to s3 layer
Mon (02/02) | 02 Feb 2026 | P49 |  | Current status of column rebar fabrication
Mon (02/02) | 02 Feb 2026 | P48 |  | Access removal to continue backfilling
Mon (02/02) | 02 Feb 2026 | P47 |  | Status of base plate installation
Mon (02/02) | 02 Feb 2026 | P41 |  | No activity
Mon (02/02) | 02 Feb 2026 | P39 |  | Ducting installation by WH
Tue (03/02) | 03 Feb 2026 | B2-27, B2-28 |  | Continue excavation and drilling ongoing to expose couplers. Today plan for lean concrete here
Tue (03/02) | 03 Feb 2026 | B2-29, B2-30 |  | Partial lean concrete done last night, Opening 8 continue disposal works
Tue (03/02) | 03 Feb 2026 | BR8 area |  | Storage for skin wall materials
Tue (03/02) | 03 Feb 2026 | P43& P44 |  | Stressing cage assembling
Tue (03/02) | 03 Feb 2026 | P45 |  | Clearing materials. Preparing to lower down mini for drain hacking
Tue (03/02) | 03 Feb 2026 | P47 |  | No activity. Just barricade installation only
Tue (03/02) | 03 Feb 2026 | B2-37 |  | Dwall PU grouting at top side ongoing
Tue (03/02) | 03 Feb 2026 | B2-34 |  | Hacking of skin wall in progress
Tue (03/02) | 03 Feb 2026 | P49 |  | Column rebar cage fabrication
Tue (03/02) | 03 Feb 2026 | P51 |  | Shifting out unused materials
Tue (03/02) | 03 Feb 2026 | DR4 |  | Platform preparation for silo and materials storage are for JGP grouting work
Tue (03/02) | 03 Feb 2026 | CCE3/B2-43 |  | Ongoing excavation & internal shifting by 3 excavators
Tue (03/02) | 03 Feb 2026 | B2-37 |  | Continues grouting work for the Dwall
Tue (03/02) | 03 Feb 2026 | Exit 1 |  | Current stockpile status & soil disposal to MESG by 1 excavator
Tue (03/02) | 03 Feb 2026 | P51 |  | Preparing Annex C&D. Will start excavation today
Tue (03/02) | 03 Feb 2026 | DR4 |  | GCE mobilizing of grouting machine and tanks
Tue (03/02) | 03 Feb 2026 | Opening 8 |  | Excavation completed, B2-29, B2-30: Exposing couplers, B2-27, B2-28: Surveyor marking and KTC levelling works ongoing. Today plan to cast lean con
Tue (03/02) | 03 Feb 2026 | Opening 7 |  | B2-26 to B2-21: Continue excavation and disposal works (8 operators)
Tue (03/02) | 03 Feb 2026 | B2-31 | GL27-28 | Scaffold installation in progress to facilitate skin wall rebar works
Tue (03/02) | 03 Feb 2026 | P46 |  | Start excavation to expose utilities
Tue (03/02) | 03 Feb 2026 | DR3 |  | DE143 drain hacking at left channel
Tue (03/02) | 03 Feb 2026 | P49 |  | Rebar cage fabrication
Tue (03/02) | 03 Feb 2026 | P49 |  | Clearing slurry
Tue (03/02) | 03 Feb 2026 | P51 |  | Clearing unused materials
Tue (03/02) | 03 Feb 2026 | P47 |  | No activity
Tue (03/02) | 03 Feb 2026 | P43&44 |  | Stressing cage assembling and netting installation to prevent falling object
Tue (03/02) | 03 Feb 2026 | P39 |  | Current status of ducting installation work
Tue (03/02) | 03 Feb 2026 | P37 |  | Current status of 2nd lift rebar work
Tue (03/02) | 03 Feb 2026 | P29 |  | Working platform erection for 2nd lift
Tue (03/02) | 03 Feb 2026 | P27 |  | Shear link installation for 2nd lift
Tue (03/02) | 03 Feb 2026 | P18 |  | Preparation for segment launching tonight
Tue (03/02) | 03 Feb 2026 | P12 |  | Prepare barricade for segment launching at P18 tonight
Tue (03/02) | 03 Feb 2026 | P1 |  | Crosshead soffit plywood installation
Tue (03/02) | 03 Feb 2026 | DR4 |  | Unloading of silo and tanks by GCE
Tue (03/02) | 03 Feb 2026 | P51 |  | KTC started excavation for 2nd layer caisson
Tue (03/02) | 03 Feb 2026 | DR4 |  | Backfilling and strut dismantling
Tue (03/02) | 03 Feb 2026 | P49 |  | Continue 2nd lift rebar cage fabrication
Tue (03/02) | 03 Feb 2026 | P47 |  | Platform preparation for crane for utility support installation
Tue (03/02) | 03 Feb 2026 | DR3 |  | Hacking of drain to divert the flow
Tue (03/02) | 03 Feb 2026 | P43&44 |  | Continue assembling of stressing cage
Tue (03/02) | 03 Feb 2026 | P39 |  | Ducting work by WH
Tue (03/02) | 03 Feb 2026 | P37 to P27 |  | No night work for column already
Tue (03/02) | 03 Feb 2026 | P26 |  | Working platform dismantling. P27: 2nd lift column rebar work
Tue (03/02) | 03 Feb 2026 | P29 |  | Duct installation work at NB side. This week to complete all
Tue (03/02) | 03 Feb 2026 | P36 |  | Working platform erection done for 2nd lift. P37: Rebar work for 2nd lift
Wed (04/02) | 04 Feb 2026 | N5-N6 |  | 2nd stage stressing completed. Tendon duct cutting in progress
Wed (04/02) | 04 Feb 2026 | B2-48 |  | Installing of bund wall along the linkway access
Wed (04/02) | 04 Feb 2026 | CCE3/B2-43 |  | Continues excavation & internal shifting of soil by 2 excavators
Wed (04/02) | 04 Feb 2026 | P3 |  | Crane working platform preparation for dismantling of falsework tonight
Wed (04/02) | 04 Feb 2026 | P1 crosshead |  | Rebars unloading
Wed (04/02) | 04 Feb 2026 | Exit 1 |  | Current stockpile status & soil disposal to MESG by 1 excavator
Wed (04/02) | 04 Feb 2026 | B2-40 |  | No activity
Wed (04/02) | 04 Feb 2026 | B2-37/B2-35/B2-33 |  | Beside grouting work for the Dwall, erecting of scaffold for skin wall work is also in progress
Wed (04/02) | 04 Feb 2026 | B2-33/B2-34 |  | Ongoing rebar/formwork installation for columns
Wed (04/02) | 04 Feb 2026 | B2-30 |  | Exposing of couplers is in progress
Wed (04/02) | 04 Feb 2026 | B2-27/B2-28 |  | Today plan to lean concrete for B2-28 & remaining portion for B2-27
Wed (04/02) | 04 Feb 2026 | Opening 7 |  | B2-26 to B2-21: Continue excavation and disposal works (9 operators)
Wed (04/02) | 04 Feb 2026 | BR22B |  | Rebar works and partial formwork installation in progress
Wed (04/02) | 04 Feb 2026 | B2-43 |  | Continue excavation and internal soil shifting
Wed (04/02) | 04 Feb 2026 | B2-31, B2-33, B2-37 | GL26-32 | Scaffold erection in progress for skin wall works
Wed (04/02) | 04 Feb 2026 | B2-29 | GL25 | Dongah drilling ongoing for PU grouting works
Wed (04/02) | 04 Feb 2026 | B2-33/B2-34 |  | Column formwork installation in progress
Wed (04/02) | 04 Feb 2026 | B2-29 |  | Started partial plywood/debonding sheet installation
Wed (04/02) | 04 Feb 2026 | B2-30 |  | Surface cleaning ongoing
Wed (04/02) | 04 Feb 2026 | B2-27, B2-28 |  | Preparing balance area for lean concrete works, B2-28: Hacking ongoing to expose skin wall starter bars
Wed (04/02) | 04 Feb 2026 | B2-27 | GL23-North side | Exposing couplers
Wed (04/02) | 04 Feb 2026 | Opening 7 |  | B2-21 to B2-26: Continue excavation and disposal works
Wed (04/02) | 04 Feb 2026 | P47 |  | Hacking existing Dr3 drain, LE unloading materials
Wed (04/02) | 04 Feb 2026 | P46 |  | Current excavation status
Wed (04/02) | 04 Feb 2026 | P45 |  | Pile cap concrete curing. No activity
Wed (04/02) | 04 Feb 2026 | P48 |  | Utility support removal
Wed (04/02) | 04 Feb 2026 | P49 |  | Column rebar cage fabrication in progress
Wed (04/02) | 04 Feb 2026 | P51 |  | Excavation to L2 caisson level in progress
Wed (04/02) | 04 Feb 2026 | 800mm PW | zone 2 | Backfilling in progress
Wed (04/02) | 04 Feb 2026 | B2-43 |  | Continue excavation and soil internal shifting to exit 1 stockpile (2 exc). Tonight to continue night shift here
Wed (04/02) | 04 Feb 2026 | Between GL32 to GL-E9 & | North side, GL26 onwards | Scaffold installation in progress for skin wall works
Wed (04/02) | 04 Feb 2026 | B2-34 | South side | Hacking of skin wall to expose starter bars is progressing towards B2-36 area
Wed (04/02) | 04 Feb 2026 | B2-29, B2-30 |  | Plywood installation in progress
Wed (04/02) | 04 Feb 2026 | B2-26 & balance area for B2-27, B2-28 |  | Joining of casting pipes ongoing for lean concrete works
Wed (04/02) | 04 Feb 2026 | B2-27 | south side | Continue exposing couplers
Wed (04/02) | 04 Feb 2026 | Opening 7 |  | B2-24 to B2-21: Continue excavation and disposal works
Wed (04/02) | 04 Feb 2026 | BR22B |  | Continue rebar works and formwork closing, Started planting bottom bars at corner area (CJ BR22B/B1-11)
Wed (04/02) | 04 Feb 2026 | B1-06, B1-04 |  | Removing formwork for RC wall
Wed (04/02) | 04 Feb 2026 | B1-07, B1-08 |  | Rebar works in progress
Wed (04/02) | 04 Feb 2026 | B1-01 |  | Dismantling formwork for opening, Mini breaker start hacking slab lean concrete below RC beams for RC wall connection
Wed (04/02) | 04 Feb 2026 | P18 NB D02 |  | Segment launched last night. Barricade and netting installation in progress
Thu (05/02) | 05 Feb 2026 | GL26 to | north side, GL32 | Currently no activity for scaffold installation. Manpower at B2-29 scaffold erection for column works
Thu (05/02) | 05 Feb 2026 | B2-36 | South side | Currently waiting operator to resume hacking at skin wall area
Thu (05/02) | 05 Feb 2026 | CCE3 | GL-E4 | Excavation in progress (3 exc operators)
Thu (05/02) | 05 Feb 2026 | Zone 3 |  | CAAS on site for crane inspection
Thu (05/02) | 05 Feb 2026 | N5-N6 |  | Clamping beam dismantling
Thu (05/02) | 05 Feb 2026 | N6 |  | Bearing grouting in progress
Thu (05/02) | 05 Feb 2026 | P18 |  | NB-D03 launched yesterday
Thu (05/02) | 05 Feb 2026 | P1 |  | Scaffold erection and access making for rebar installation works
Thu (05/02) | 05 Feb 2026 | P3 |  | Falsework dismantling in progress
Thu (05/02) | 05 Feb 2026 | Blasting no.13 completed at 4 |  | 44pm
Fri (06/02) | 06 Feb 2026 | B1-01 |  | Current status of lean concrete hacking. Mini breaker plan to shift out to next hacking works at skin wall area
Fri (06/02) | 06 Feb 2026 | DR4 |  | Rig maintenance and silo set up
Fri (06/02) | 06 Feb 2026 | DR4 |  | NDT test in progress. Will continue with backfilling to S2 layer
Fri (06/02) | 06 Feb 2026 | B1-02 |  | Hacking ongoing to expose skin wall starter bars
Fri (06/02) | 06 Feb 2026 | B1-07, B1-08 |  | Continue rebar works for slabs and RC column, B1-07: Dongah drilling ongoing for rebar planting
Fri (06/02) | 06 Feb 2026 | P27 |  | Preparing for scaffold dismantling for Formwork installation
Fri (06/02) | 06 Feb 2026 | P18 |  | NB-U03 segment launched yesterday. Balance 2 nos. To complete by this week
Fri (06/02) | 06 Feb 2026 | P16-P17 |  | Preparation for NB midspan formwork closing
Fri (06/02) | 06 Feb 2026 | DR3 |  | Drain wall hacking and removal of debris
Fri (06/02) | 06 Feb 2026 | P47 |  | UKP plate welding and drain hacking
Fri (06/02) | 06 Feb 2026 | P49 |  | Clearing slurry and mud for stump
Fri (06/02) | 06 Feb 2026 | P51 |  | Hacking of cement grout for 2nd layer caisson
Fri (06/02) | 06 Feb 2026 | P43 |  | Stressing cage installation
Fri (06/02) | 06 Feb 2026 | P46 |  | Levelling for parking platform
Fri (06/02) | 06 Feb 2026 | Opening 7 |  | B2-21 to B2-24: Excavation and disposal in progress (3 exc operators, 1 telescopic)
Fri (06/02) | 06 Feb 2026 | P41 |  | Tendon wire pulling done. Tomorrow to complete stressing
Fri (06/02) | 06 Feb 2026 | B2-30 | south side | Coupler exposing and Dongah drilling for PU grouting works ongoing, Scaffold erection in progress for column works, Bottom rebar installation in progress
Fri (06/02) | 06 Feb 2026 | B2-27, B2-25 | South side | Hacking ongoing to expose skin wall starter bars
Fri (06/02) | 06 Feb 2026 | B2-29 |  | PU grouting and debonding sheet laying in progress, Column rebar works ongoing
Fri (06/02) | 06 Feb 2026 | B2-34, B2-36 | South side | Hacking continue to expose skin wall starter bars
Fri (06/02) | 06 Feb 2026 | P37 |  | 2nd lift column rebar work
Fri (06/02) | 06 Feb 2026 | CCE3 |  | Excavation in progress (3 exc op)
Fri (06/02) | 06 Feb 2026 | Exit 1 stockpile |  | Soil disposal in progress
Fri (06/02) | 06 Feb 2026 | P1 |  | Access making and rebar installation in progress
Fri (06/02) | 06 Feb 2026 | P3 |  | Current Falsework dismantling status. Crane demob to P44
Fri (06/02) | 06 Feb 2026 | DR4 |  | Prepare the area to start TT for JGP work
Fri (06/02) | 06 Feb 2026 | DR4 |  | Backfilling to S2 level for strut removal
Fri (06/02) | 06 Feb 2026 | P27 |  | 2nd lift column tie rod installation for formwork closing
Fri (06/02) | 06 Feb 2026 | CCE3 |  | Excavation is progressing between B2-41 and B2-42
Fri (06/02) | 06 Feb 2026 | P16-P17 |  | NB midspan continue inner formwork closing
Fri (06/02) | 06 Feb 2026 | CCW2 |  | Continue disposal rocks. From morning till now, about 10 buckets cleared
Fri (06/02) | 06 Feb 2026 | CCW2 P24 TB |  | Downhang wall 2nd stage excavation in progress. 1 more excavator was brought down just now (3 exc, 1 telescopic)
Fri (06/02) | 06 Feb 2026 | CCW1 | south side | No activity, CCW2: Exposing area for inspection for rock surface and rock sampling collection for the next blasting work
Fri (06/02) | 06 Feb 2026 | P45 |  | 1st main beam installed
Fri (06/02) | 06 Feb 2026 | P51 |  | Excavation for 2nd layer caisson
Fri (06/02) | 06 Feb 2026 | P1 |  | Continue top rebar installation and access platform making
Fri (06/02) | 06 Feb 2026 | P3 |  | Current Falsework dismantling status
Fri (06/02) | 06 Feb 2026 | DR3 |  | Now high tide. No activity
Fri (06/02) | 06 Feb 2026 | P44 |  | Preparing to install man cage
Fri (06/02) | 06 Feb 2026 | P43 |  | Both man cage installed. The other two sides will use boom lift
Fri (06/02) | 06 Feb 2026 | P39 |  | Continue ducting work
Fri (06/02) | 06 Feb 2026 | CCW1 | North side | No activity
Fri (06/02) | 06 Feb 2026 | BR22B |  | Final inspection in progress. Minor comments to be rectified. Now continue cleaning works and rebar tying. Casting to proceed tonight
Fri (06/02) | 06 Feb 2026 | B1-09, B1-10 |  | Continue coupler exposing, B1-10: Bottom rebar planting in progress
Fri (06/02) | 06 Feb 2026 | B1-07, B1-08 |  | Rebar installation in progress
Fri (06/02) | 06 Feb 2026 | Opening 7 |  | B2-21 to B2-24: No activity. No night shift here
Fri (06/02) | 06 Feb 2026 | B2-26, B2-25 |  | No activity, B2-27: Hacking dwall to expose skin wall starter bars to continue until 10pm
Fri (06/02) | 06 Feb 2026 | B2-28 |  | Continue exposing couplers
Fri (06/02) | 06 Feb 2026 | B2-30 |  | Bottom rebar works in progress, B2-29: Started bottom rebar planting and continue column rebar installation
Fri (06/02) | 06 Feb 2026 | GL26 to | north side, GL32 | No activity
Fri (06/02) | 06 Feb 2026 | CCE3 |  | Night shift team to continue the excavation here (3 exc). Excavation is progressing between B2-41 & B2-42
Fri (06/02) | 06 Feb 2026 | CCW2 P24 TB |  | Night shift team continue excavation for downhang wall 2nd stage (3 exc, 1 telescopic)
Fri (06/02) | 06 Feb 2026 | B1-01 |  | No activity
Fri (06/02) | 06 Feb 2026 | B1-02 |  | Continue hacking dwall to expose skin wall starter bars & clearing hacking debris (2 mini)
Fri (06/02) | 06 Feb 2026 | CCW2 |  | Disposal works in progress
Fri (06/02) | 06 Feb 2026 | CCW2 |  | Disposing blasted rocks, CCW1 North side: No activity
Fri (06/02) | 06 Feb 2026 | CCW2 P24 TB |  | Downhang wall 2nd stage excavation in progress (2 exc, 1 telescopic)
Fri (06/02) | 06 Feb 2026 | CCW1 | south side | No other activity, CCW2: KTC preparing excavation to expose rock level
Sat (07/02) | 07 Feb 2026 | P27 |  | 2nd lift column formwork closing. 1/4 nos. completed
Sat (07/02) | 07 Feb 2026 | P37 |  | 2nd lift column rebar installation in progress
Sat (07/02) | 07 Feb 2026 | P39 |  | Crosshead tendon duct and rebar - shear links installation ongoing
Sat (07/02) | 07 Feb 2026 | P43 |  | Stressing cage adjustment and stitching formwork materials shifting
Sat (07/02) | 07 Feb 2026 | P44 |  | Stressing cage assembly in progress
Sat (07/02) | 07 Feb 2026 | P46 |  | KTC excavation works for 1st layer in progress
Sat (07/02) | 07 Feb 2026 | P47 |  | Preparation for utility supports works
Sat (07/02) | 07 Feb 2026 | P51 |  | 2nd layer manual excavation and levelling in progress
Sat (07/02) | 07 Feb 2026 | DR4 |  | Backfilling and levelling to S2 level for strut removal
Sat (07/02) | 07 Feb 2026 | P41 |  | Tendon stressing in progress
Sat (07/02) | 07 Feb 2026 | P1 |  | Crosshead top rebar installation works
Sat (07/02) | 07 Feb 2026 | P3 |  | No activity. Falsework dismantling current status
Sat (07/02) | 07 Feb 2026 | P27 |  | Continue formwork closing for 2nd lift column
Sat (07/02) | 07 Feb 2026 | P37 |  | 2nd lift column rebar inspection
Sat (07/02) | 07 Feb 2026 | P39 |  | Continue Crosshead rebar installation. Target to cast next week
Sat (07/02) | 07 Feb 2026 | P41 |  | Crosshead tendon stressing in progress
Sat (07/02) | 07 Feb 2026 | P43 |  | SB stitching formwork installation
Sat (07/02) | 07 Feb 2026 | P44 |  | Stressing cage assembly ongoing
Sat (07/02) | 07 Feb 2026 | P46 |  | KTC 1st layer excavation
Sat (07/02) | 07 Feb 2026 | P47 |  | No activity. LE stopped for the day due to company dinner
Sat (07/02) | 07 Feb 2026 | P51 |  | Continue excavation for for 2nd layer caisson
Sat (07/02) | 07 Feb 2026 | DR4 |  | Continue backfilling and compaction for struts removal
Sat (07/02) | 07 Feb 2026 | Zone 2 |  | LG materials unloading
Sat (07/02) | 07 Feb 2026 | P1 |  | Continue Crosshead rebar installation
Sun (08/02) | 08 Feb 2026 | B1-11 |  | Started hacking to expose couplers
Sun (08/02) | 08 Feb 2026 | B1-10 |  | Continue exposing couplers
Sun (08/02) | 08 Feb 2026 | B1-09 |  | RGT installation in progress & general houskeeping
Sun (08/02) | 08 Feb 2026 | BR22B |  | No activity
Sun (08/02) | 08 Feb 2026 | Exit 2 capping beam area |  | Current status of cutting down level for erecting scaffolding work platform for Hirose
Sun (08/02) | 08 Feb 2026 | Zone 3 access |  | Dust control in progress. KTC water truck deployed
Sun (08/02) | 08 Feb 2026 | Opening 7 |  | B2-21, B2-22: No excavation and disposal activity, (GL19.5-18), B2-23, B2-24: Lean concrete was cast last night
Sun (08/02) | 08 Feb 2026 | B2-28 | South side | Hacking ongoing to expose skin wall starter bars
Sun (08/02) | 08 Feb 2026 | B2-27 | North side | Dwall PU grouting in progress, Plywood installation in progress
Sun (08/02) | 08 Feb 2026 | B2-29, B2-30 |  | Rebar works in progress (Wendyng 1 sup, 18 workers)
Sun (08/02) | 08 Feb 2026 | B2-34 | South side | Column formwork installation in progress
Sun (08/02) | 08 Feb 2026 | B2-33 | North side | Hacking ongoing to expose skin wall starter bars
Sun (08/02) | 08 Feb 2026 | Exit 1 stockpile |  | Soil internal shifting from B2-48 segregation and disposal ongoing (1 exc)
Sun (08/02) | 08 Feb 2026 | CCE3 |  | Excavation in progress (3 exc), B2-48: Observed walking platform installation is in progress
Sun (08/02) | 08 Feb 2026 | LVC drain diversion | btw P20 to P21 | No activity
Sun (08/02) | 08 Feb 2026 | CCW2 |  | Downhang wall 2nd stage, Excavation and soil disposa in progress (1 telescopic, 2 excavators), Partial base lean con was done
Sun (08/02) | 08 Feb 2026 | CCW1 | North side | No activity, CCW2: Rock disposal works in progress (1 exc, 1 crane)
Sun (08/02) | 08 Feb 2026 | B1-01 |  | No activity
Sun (08/02) | 08 Feb 2026 | B1-02 |  | Hacking ongoing to expose skin wall starter bars (1 mini), No other activity observed
Sun (08/02) | 08 Feb 2026 | B1-07, B1-08 |  | Rebar works in progress (CGW 1 sup, 68 workers). Plan for casting next week, APP piping installation in progress
Sun (08/02) | 08 Feb 2026 | B1-04, B1-06 |  | RC wall formwork removal ongoing
Tue (10/02) | 10 Feb 2026 | CCE3/B2-43 |  | Continues excavation & internal shifting of soil by 3 excavators
Tue (10/02) | 10 Feb 2026 | P1 crosshead |  | Steel anchor installation in progress
Tue (10/02) | 10 Feb 2026 | B2-40 |  | No activity
Tue (10/02) | 10 Feb 2026 | B2-23 |  | Coupler exposing in progress, B2-24: No activity, Opening 7:, B2-21, B2-22 no activity
Tue (10/02) | 10 Feb 2026 | B2-25, B2-26 |  | No activity
Tue (10/02) | 10 Feb 2026 | B2-28 | South side | Hacking ongoing to expose skin wall starter bars
Tue (10/02) | 10 Feb 2026 | B2-27 | North side | PU grouting in progress
Tue (10/02) | 10 Feb 2026 | B2-30, B2-29 |  | Rebar works in progress
Tue (10/02) | 10 Feb 2026 | B2-31, B2-33 | North side | Dwall PU grouting and straightening of starter bars ongoing
Tue (10/02) | 10 Feb 2026 | B2-34 | South side | Column formwork installation in progress
Tue (10/02) | 10 Feb 2026 | B2-35, B2-37 | North side | No activity
Tue (10/02) | 10 Feb 2026 | B2-48 |  | Designated pedestrian walkway has implemented along the linkway
Tue (10/02) | 10 Feb 2026 | P51 |  | Rebar work done around 40% for 2nd layer
Tue (10/02) | 10 Feb 2026 | P51 |  | Pump car set up and prepare for LSS backfilling of sewer pipe
Tue (10/02) | 10 Feb 2026 | Vent shaft S1b strut |  | 6/6nos struts installed. Now ongoing welding and bolt tightening. Today plan for preloading
Tue (10/02) | 10 Feb 2026 | Exit 1 |  | Current stockpile status & soil disposal to MESG by 1 excavator
Tue (10/02) | 10 Feb 2026 | P7-P8 |  | LG materials unloading
Tue (10/02) | 10 Feb 2026 | P46 |  | Continue removal of top soil for utility support
Tue (10/02) | 10 Feb 2026 | P47 |  | Hard barricate installation around excavation area
Tue (10/02) | 10 Feb 2026 | P48 |  | Utility support removal
Tue (10/02) | 10 Feb 2026 | P39 |  | Shear link installation for balance area
Tue (10/02) | 10 Feb 2026 | P43 |  | Stitching formwork closing
Tue (10/02) | 10 Feb 2026 | P44 |  | Segment adjusting done. Serveyor will take reading before continue with stitching formwork
Tue (10/02) | 10 Feb 2026 | P37 |  | 2nd lift column formwork closing work
Tue (10/02) | 10 Feb 2026 | P27 |  | 2nd lift column casting
Tue (10/02) | 10 Feb 2026 | P27 pier 2nd lift |  | 36/76 m3. Waiting for concrete lorry
Tue (10/02) | 10 Feb 2026 | P43 |  | 1/4 wet stitch formwork closed. No activity observed
Tue (10/02) | 10 Feb 2026 | Zone 2 |  | LG materials continue unloading
Tue (10/02) | 10 Feb 2026 | N5-N6 |  | Clamping beam dismantling
Tue (10/02) | 10 Feb 2026 | P3 |  | Rail beam installation in progress for dismantling of primary beams at NB tonight after last bus
Wed (11/02) | 11 Feb 2026 | Opening 7 |  | B2-21, B2-22: No activity
Wed (11/02) | 11 Feb 2026 | B2-23 | North side | Exposing couplers
Wed (11/02) | 11 Feb 2026 | B2-24 | South side | No activity
Wed (11/02) | 11 Feb 2026 | B2-28 to B2-26 | South side | Soil levelling ongoing at drop area prior to casting lean concrete. Casting pipe joining in progress
Wed (11/02) | 11 Feb 2026 | B2-30, B2-29 |  | Rebar works and APP piping installation in progress. Plan for slab casting this Saturday
Wed (11/02) | 11 Feb 2026 | B2-31 | North side | Dongah continue PU grouting and Maxbond RGT installation in progress
Wed (11/02) | 11 Feb 2026 | B2-33, B2-35, B2-37 | North side | No activity
Wed (11/02) | 11 Feb 2026 | B2-33, B2-34 |  | Columns cast yesterday
Wed (11/02) | 11 Feb 2026 | B2-38, Opening 9 |  | No activity
Wed (11/02) | 11 Feb 2026 | CCE2 ramp down |  | Excavation in progress (3 exc)
Wed (11/02) | 11 Feb 2026 | B2-43 ramp down |  | Partial lean concrete (with BRC) was cast last night at south side (1 WH exc standby)
Wed (11/02) | 11 Feb 2026 | 800mm PW |  | Expose utilities at Zone 3
Wed (11/02) | 11 Feb 2026 | DR4 |  | JGP trial trench ongoing
Wed (11/02) | 11 Feb 2026 | P51 |  | (north) formwork closing, today casting..(south) sewer pipe LSS backfilling completed, today afternoon continue excavation
Wed (11/02) | 11 Feb 2026 | Exit 1 stockpile |  | Soil disposal in progress (1 exc)
Wed (11/02) | 11 Feb 2026 | P46 |  | Excavation to expose utilities. Target to complete by tomorrow
Wed (11/02) | 11 Feb 2026 | P47 |  | Hacking existing DR3
Wed (11/02) | 11 Feb 2026 | P48 |  | Utility support removal
Wed (11/02) | 11 Feb 2026 | P39 |  | Formwork closing done. Tightening of support and housekeeping. Preparation for casting tomorrow
Wed (11/02) | 11 Feb 2026 | P37 |  | 2nd lift formwork closing
Wed (11/02) | 11 Feb 2026 | P43 |  | Stitching formwork closing. P44: adjusting of segment done. Surveyor to confirm again
Wed (11/02) | 11 Feb 2026 | P51 |  | Formwork closing for 2nd layer caisson. Today will cast around 40%
Wed (11/02) | 11 Feb 2026 | P51 |  | Continue excavation for 2nd layer balance area
Wed (11/02) | 11 Feb 2026 | P47 |  | Continue hacking and removal of abandoned drain
Wed (11/02) | 11 Feb 2026 | P46 |  | Continue top soil removal
Wed (11/02) | 11 Feb 2026 | DR4 |  | TT for JGP work. Tomorrow plan to start JGP grouting
Wed (11/02) | 11 Feb 2026 | Exit 2 |  | Struts assembly in progress prior to installation. Today plan to install 2/12nos. Hirose working till 10pm
Wed (11/02) | 11 Feb 2026 | B1-10, B1-09 |  | No activity
Wed (11/02) | 11 Feb 2026 | B1-07, B1-08 |  | Continue rebar works and corrugated pipes installation, Shearlinks and formwork installation also ongoing, Plan for casting this Friday
Wed (11/02) | 11 Feb 2026 | B1-11 |  | Overcast dwall hacking in progress. Currently operator on dinner break. Target to complete hacking today
Wed (11/02) | 11 Feb 2026 | P39 |  | Barricade installation for casting works tmr
Wed (11/02) | 11 Feb 2026 | B2-25 | North side | Exposing couplers
Wed (11/02) | 11 Feb 2026 | P43-44 |  | Unloading of LG materials
Wed (11/02) | 11 Feb 2026 | B2-23 | North side | Preparing to cast lean concrete for drop areas. Casting pipes joining ongoing
Wed (11/02) | 11 Feb 2026 | Opening 7 |  | Casting point for B2-23 area, B2-21, B2-22: No activity
Wed (11/02) | 11 Feb 2026 | B2-24, B2-26, B2-28 | South side | Lean concrete casting for drop areas completed just now. Now levelling ongoing
Wed (11/02) | 11 Feb 2026 | B2-30, B2-29 |  | Continue rebar works and partial side formwork installation, Plan for casting this Saturday
Wed (11/02) | 11 Feb 2026 | B2-31, B2-33, B2-35, B2-37 | North side | Currently no activity
Wed (11/02) | 11 Feb 2026 | B2-34, B2-36, B2-38 | South side | No activity
Wed (11/02) | 11 Feb 2026 | B2-40 opening area |  | Observed 1 KTC excavator was just mobbed here and top lean con was partially clearing. Currently no activity
Wed (11/02) | 11 Feb 2026 | P51 |  | Preparation for 2nd layer NB side caison casting
Wed (11/02) | 11 Feb 2026 | CCE2 ramp down |  | Continue excavation and disposal works (3 exc)
Wed (11/02) | 11 Feb 2026 | P1 |  | PT duct support bar installation, until 9pm only
Wed (11/02) | 11 Feb 2026 | Exit 2 |  | Raker strut installation in progress
Wed (11/02) | 11 Feb 2026 | P24 TB downhang wall |  | Soffit roughening for RC wall rebar works
Wed (11/02) | 11 Feb 2026 | Opening 3 |  | B2-04: Night shift excavation in progress (2 exc, 1 telescopic)
Thu (12/02) | 12 Feb 2026 | N2-N4 |  | Preparation for grouting works
Thu (12/02) | 12 Feb 2026 | Zone 2 |  | Preparation for LG materials unloading
Thu (12/02) | 12 Feb 2026 | P1 |  | Tendon ducts installation works
Thu (12/02) | 12 Feb 2026 | P3 |  | Falsework dismantling current status
Thu (12/02) | 12 Feb 2026 | DR4 Zone 1 |  | Services exposed for ERSS work
Thu (12/02) | 12 Feb 2026 | DR4 Zone 3 |  | Soldier pile for sides installation done. Left to install at closing area
Thu (12/02) | 12 Feb 2026 | DR4 Changi Bound |  | Pipe sleeves installation for JGP
Thu (12/02) | 12 Feb 2026 | N2-N4 |  | PT grouting in progress
Thu (12/02) | 12 Feb 2026 | Zone 2 |  | Continue LG materials unloading
Thu (12/02) | 12 Feb 2026 | P1 |  | Tendon ducts installation
Thu (12/02) | 12 Feb 2026 | P46 |  | Manual exposing of services for support
Thu (12/02) | 12 Feb 2026 | P47 |  | Current status of utility support
Thu (12/02) | 12 Feb 2026 | P51 |  | Formwork removal for caisson and excavation for balance caisson
Thu (12/02) | 12 Feb 2026 | P43 |  | Stitching formwork closing. Saturday to cast. P44: final adjustment done
Thu (12/02) | 12 Feb 2026 | P45 |  | S1 strut removal
Thu (12/02) | 12 Feb 2026 | P39 |  | Water hose installation inside duct
Thu (12/02) | 12 Feb 2026 | N2-N3 |  | Top tendon grouting work
Thu (12/02) | 12 Feb 2026 | Zone 1 |  | P1 to P3 no activity already. Workers at P39 for tomorrow casting
Thu (12/02) | 12 Feb 2026 | DR4 Zone 3 |  | Left 2 soldier to complete. Today will expose the utility for the 2nos installation
Thu (12/02) | 12 Feb 2026 | P51 |  | The excavator break down. Tomorrow will deliver spare part and repair
Thu (12/02) | 12 Feb 2026 | P48 |  | Current status of utility support removal
Thu (12/02) | 12 Feb 2026 | P47 |  | Main beam left two number to install
Thu (12/02) | 12 Feb 2026 | P45 |  | S1 strut removal until 9PM
Thu (12/02) | 12 Feb 2026 | P43&44 |  | Stressing cage dismantling go shift to Zone 2
Thu (12/02) | 12 Feb 2026 | P37 |  | Formwork support installation. To cast on Saturday. Tomorrow casting will priority for P39
Thu (12/02) | 12 Feb 2026 | P39 |  | Hose pushing inside tendon duct. Tomorrow final inspection and casting
Fri (13/02) | 13 Feb 2026 | P1 |  | Tendon duct installation
Fri (13/02) | 13 Feb 2026 | P3 |  | Falsework materials shifting to p6
Fri (13/02) | 13 Feb 2026 | P39 crosshead |  | Now final inspection. Bottom ducts are already covered with water hoses
Fri (13/02) | 13 Feb 2026 | CCE3 |  | Continue excavation & soil disposal/internal transfer by 3 excavators, plan to lean concrete with BRC up to GL E4 by this week
Fri (13/02) | 13 Feb 2026 | B2-49A |  | Plan to continue hacking of CJ today
Fri (13/02) | 13 Feb 2026 | Exit 1 stockpile |  | Continues soil disposal to MESG by 1 excavator
Fri (13/02) | 13 Feb 2026 | Opening 7 |  | B2-21, B2-22: No activity
Fri (13/02) | 13 Feb 2026 | B2-23, B2-24 |  | No activity
Fri (13/02) | 13 Feb 2026 | B2-25 | North side | Scaffold installation in progress for column C01-4, B2-26 (South side): No activity
Fri (13/02) | 13 Feb 2026 | B2-27 | North side | No activity, Surveying works ongoing, B2-28 (South side): Hacking ongoing at skin wall area
Fri (13/02) | 13 Feb 2026 | B2-29, B2-30 |  | Shearlinks installation in progress. Plan for casting tmr
Fri (13/02) | 13 Feb 2026 | B2-31 | North side | Preparing for skin wall rebar works
Fri (13/02) | 13 Feb 2026 | B2-33, B2-34 |  | No activity
Fri (13/02) | 13 Feb 2026 | B2-33, B2-35 | North side | Preparing for PU grouting works
Fri (13/02) | 13 Feb 2026 | Opening 9, B2-37, B2-38 |  | No activity
Fri (13/02) | 13 Feb 2026 | P43 |  | Stitching formwork closing. Tomorrow can cast
Fri (13/02) | 13 Feb 2026 | P45 |  | Balance S1 diagonal strut removal
Fri (13/02) | 13 Feb 2026 | P46 |  | Manual excavation for services support
Fri (13/02) | 13 Feb 2026 | P47 |  | Current status of utility support
Fri (13/02) | 13 Feb 2026 | P51 |  | Current status of excavation and caisson work for 2nd layer
Fri (13/02) | 13 Feb 2026 | P12 |  | Unloading of LG materials
Fri (13/02) | 13 Feb 2026 | DR4 |  | 1st point JGP done. Preparing for 2nd point JGP boring and grouting
Fri (13/02) | 13 Feb 2026 | CCW2 |  | Preparing for 14th blast. Geotextiles covering ongoing
Fri (13/02) | 13 Feb 2026 | CCW1 | North side | No activity
Fri (13/02) | 13 Feb 2026 | P24 TB downhang wall |  | Soffit roughening ongoing for RC wall rebar works
Fri (13/02) | 13 Feb 2026 | Opening 3 |  | B2-04: Excavation in progress (2 exc, 1 telescopic)
Fri (13/02) | 13 Feb 2026 | P1 |  | PT duct installation in progress
Fri (13/02) | 13 Feb 2026 | Exit 2 |  | 5th strut installation in progress
Fri (13/02) | 13 Feb 2026 | B1-01 |  | Formwork installation in progress for RC wall connection
Fri (13/02) | 13 Feb 2026 | B1-07, B1-08 |  | Final inspection still in progress, CGW continue shearlinks installation, Surveyor marking ongoing
Fri (13/02) | 13 Feb 2026 | Exit 3 |  | 2nos additional struts installation in progress
Fri (13/02) | 13 Feb 2026 | CCW2 |  | 14th blast completed at 1620hrs
Fri (13/02) | 13 Feb 2026 | CCW2 |  | 14th blast done
Fri (13/02) | 13 Feb 2026 | P46 |  | Manual expose services for support
Fri (13/02) | 13 Feb 2026 | P59 |  | Clearing unused materials
Fri (13/02) | 13 Feb 2026 | P51 |  | Shifting of soil and disposal
Fri (13/02) | 13 Feb 2026 | P39 crosshead |  | Casting in progress
Fri (13/02) | 13 Feb 2026 | P43 |  | Continue stitching formwork closing
Fri (13/02) | 13 Feb 2026 | P6 |  | Pad footing installation in progress
Fri (13/02) | 13 Feb 2026 | P36 |  | 2nd lift column rebar work
Fri (13/02) | 13 Feb 2026 | N4 to N5 |  | Grouting of tendon duct
Fri (13/02) | 13 Feb 2026 | DR4 Changi bound |  | 2nos JGP point grouting done. Tidy up the area and prepare for the next point
Fri (13/02) | 13 Feb 2026 | DR4 Zone 3 |  | Soldier pile and steel plates installation completed. To continue with with excavation and lagging plates
Fri (13/02) | 13 Feb 2026 | DR4 Zone 1 |  | Tonight to continue exposing services for soldier pile installation
Fri (13/02) | 13 Feb 2026 | P51 |  | Lagging plate installation by LE until 9PM
Fri (13/02) | 13 Feb 2026 | P50 |  | Unloading of rebar for P51
Fri (13/02) | 13 Feb 2026 | P45 |  | S1 strut removal done
Fri (13/02) | 13 Feb 2026 | P43 |  | Stitching formwork closing. Tomorrow to cast
Fri (13/02) | 13 Feb 2026 | P41 |  | Dismantling of working platform
Fri (13/02) | 13 Feb 2026 | P39 |  | Crosshead casting in progress
Fri (13/02) | 13 Feb 2026 | P36 |  | Status of 2nd lift column rebar work
Sat (14/02) | 14 Feb 2026 | P43 |  | 1st pair stitching formwork closed. Filler plate installation in progress. Target to cast today
Sat (14/02) | 14 Feb 2026 | B1-10 |  | Dwall rectification in progress (STN212), Drilling ongoing for missing couplers
Sat (14/02) | 14 Feb 2026 | B1-09 |  | No activity. Opening currently used for casting pump
Sat (14/02) | 14 Feb 2026 | B1-11 |  | No activity
Sat (14/02) | 14 Feb 2026 | P45 |  | 1st layer waler dismantled. Material shifting
Sat (14/02) | 14 Feb 2026 | P46 |  | Establishing slope for lean concrete casting tonight and manual excavation for Utility support installation
Sat (14/02) | 14 Feb 2026 | P47 |  | Abandoned drain hacking. No other activity
Sat (14/02) | 14 Feb 2026 | P51 |  | 2nd layer caison SB side excavation works
Sat (14/02) | 14 Feb 2026 | Exit 2 |  | 6/11nos struts installed
Sat (14/02) | 14 Feb 2026 | P1 |  | PT duct installation
Sat (14/02) | 14 Feb 2026 | P3 |  | Pad footing removal to be shifted to P6
Sat (14/02) | 14 Feb 2026 | P6 |  | Falsework leg frame installation started
Sat (14/02) | 14 Feb 2026 | P6 |  | Leg frame installation status. SB side pad footing installed
Sat (14/02) | 14 Feb 2026 | P1 |  | PT duct installation continue
Sat (14/02) | 14 Feb 2026 | Opening 7 |  | B2-21, B2-22: No activity
Sat (14/02) | 14 Feb 2026 | B2-23, B2-24 |  | No activity
Sat (14/02) | 14 Feb 2026 | B2-25, B2-26 |  | Start laying plywood, B2-26 (South side): Hacking ongoing to expose skin wall starter bars
Sat (14/02) | 14 Feb 2026 | B2-28 | South side | No activity, B2-27 (North side): Plywood laying in progress
Sat (14/02) | 14 Feb 2026 | B2-29, B2-30 |  | Final inspection was done. Now preparing for casting (plan later afternoon or evening)
Sat (14/02) | 14 Feb 2026 | B2-31 | North side | Skin wall rebar works and RGT works ongoing
Sat (14/02) | 14 Feb 2026 | B2-33 | North side | PU grouting and skin wall rebar straightening ongoing
Sat (14/02) | 14 Feb 2026 | B2-35, B2-37 | North side | No activity
Sat (14/02) | 14 Feb 2026 | B2-34, B2-36 | South side | Hacking ongoing to expose skin wall rebar
Sat (14/02) | 14 Feb 2026 | Opening 9 |  | No activity, B2-38: Scaffold erection in progress for TDP H-beam cutting
Sat (14/02) | 14 Feb 2026 | B2-40 opening |  | Observed ramp excavation is progressing here
Sat (14/02) | 14 Feb 2026 | B2-43 | North side | Ramp lean concrete casting and levelling ongoing
Sat (14/02) | 14 Feb 2026 | Exit 1 stockpile |  | Soil disposal in progress
Sat (14/02) | 14 Feb 2026 | DR4 |  | JGP works
Sat (14/02) | 14 Feb 2026 | P51 |  | Excavation for 2nd layer caison continue
Sat (14/02) | 14 Feb 2026 | P46 |  | Manual excavation for Utility support installation continue
Sat (14/02) | 14 Feb 2026 | P44 |  | Stressing cage assembly
Sat (14/02) | 14 Feb 2026 | P43 |  | Wet stitching to cast tonight
Sat (14/02) | 14 Feb 2026 | P37 |  | Concrete pump set up for casting. Concrete supply only available after 7pm
Sat (14/02) | 14 Feb 2026 | Exit 2 |  | 8/11nos struts installed. Now ongoing diagonal strut installation
Sat (14/02) | 14 Feb 2026 | CCW1 | South side | Hirose drilling works ongoing for S5 layer, (2 ktc excavator no activity)
Sat (14/02) | 14 Feb 2026 | CCW2 |  | Ground levelling ongoing by 1 ktc excavator, Observed ATC machines (2nos) have been demob from here. Now continue clearing materials & houskeeping works
Sat (14/02) | 14 Feb 2026 | CCW1 | North side | No activity
Sat (14/02) | 14 Feb 2026 | P24 TB Donwhang wall |  | 2nd stage rebar works started and continue surface roughening, CGW: 7men
Sat (14/02) | 14 Feb 2026 | Opening 3 |  | B2-05: Excavation and disposal in progress (2 exc, 1 telescopic)
Sat (14/02) | 14 Feb 2026 | P28 |  | Scaffold erection for 2nd stage rebar works
Sat (14/02) | 14 Feb 2026 | B1-01 |  | RC wall connection currently not yet cast. Plan for casting today, WH mini preparing platform for skin wall hacking works
Sat (14/02) | 14 Feb 2026 | B1-02 |  | No activity
Sat (14/02) | 14 Feb 2026 | Exit 3 |  | 2nos additional struts installed. MPI test planned in the afternoon
Sat (14/02) | 14 Feb 2026 | P36 |  | 2nd stage pier rebar works
Sat (14/02) | 14 Feb 2026 | P37 |  | Formwork final inspection. Target to cast tonight
Mon (16/02) | 16 Feb 2026 | P51 |  | Backfilling before caisson
Mon (16/02) | 16 Feb 2026 | P47 |  | Drain hacking
Mon (16/02) | 16 Feb 2026 | P44 |  | Prepare for pipe installation around tendom wire for stitching work
Mon (16/02) | 16 Feb 2026 | P46 |  | Manual excavation for services support
Mon (16/02) | 16 Feb 2026 | DR4 Zone 3 |  | Waler welding for S1 strut installation. Housekeeping and preparing for proper access erection
Mon (16/02) | 16 Feb 2026 | Exit 1 |  | Wendyng housekeeping
Mon (16/02) | 16 Feb 2026 | B2-29 to B2-38 |  | No activity
Mon (16/02) | 16 Feb 2026 | Opening 7 |  | B2-21, B2-22 no activity, B2-23 to B2-28: No activity
Mon (16/02) | 16 Feb 2026 | Exit 2 |  | Raker struts welding & corbel drilling works in progress. Hirose continue works till 5pm
Mon (16/02) | 16 Feb 2026 | P24 TB donwhang wall |  | No activity, CGW off
Mon (16/02) | 16 Feb 2026 | Opening 3 |  | B2-05: KTC continue excavation works
Mon (16/02) | 16 Feb 2026 | B1-01, B1-02, B1-07 to B1-11 |  | No activity
Mon (16/02) | 16 Feb 2026 | Zone 3 |  | Only Hirose and KTC will work till 5pm & 7pm respectively today, All subcon will not be working during CNY. Only WH essential workers will be on standby
Thu (19/02) | 19 Feb 2026 | P36 |  | 2nd lift column rebar work
Thu (19/02) | 19 Feb 2026 | P43 |  | Removal of stitching formwork and prepare to install at P44
Thu (19/02) | 19 Feb 2026 | P6 |  | Falsework assembly in progress
Thu (19/02) | 19 Feb 2026 | P46 |  | Manual exposing services for support
Thu (19/02) | 19 Feb 2026 | P47 |  | Hacking and removal of abandoned drain
Thu (19/02) | 19 Feb 2026 | P51 |  | Resume excavation for 2nd layer caisson
Thu (19/02) | 19 Feb 2026 | DR4 Zone 1 |  | Services exposed
Thu (19/02) | 19 Feb 2026 | DR4 Zone 3 |  | S2 strut installed. Preparing for excavation for S3
Fri (20/02) | 20 Feb 2026 | B2-27 | North side | Drilling ongoing for PU grouting works
Fri (20/02) | 20 Feb 2026 | B2-26 | South side | Rebar works in progress, B2-25 (North side): Preparing to start bottom rebar works
Fri (20/02) | 20 Feb 2026 | Opening 7 |  | Excavation in progress towards B2-19 area (4 exc, 1 telescopic)
Fri (20/02) | 20 Feb 2026 | B2-23 | North side | Currently no activity
Fri (20/02) | 20 Feb 2026 | B2-24 | South side | Hacking dwall to expose skin wall starter bars
Fri (20/02) | 20 Feb 2026 | B2-28 | South side | Surveyor works ongoing, Plywood installation in progress
Fri (20/02) | 20 Feb 2026 | B2-30 | South side | Maxbond preparing for RGT works
Fri (20/02) | 20 Feb 2026 | B2-31 | North side | Skin wall rebar works and inspection in progress
Fri (20/02) | 20 Feb 2026 | B2-33 |  | Column C01-7 formwork dismantling
Fri (20/02) | 20 Feb 2026 | B2-32 | North side | Drilling ongoing for skin wall PU grouting works
Fri (20/02) | 20 Feb 2026 | B2-36 | South side | Hacking ongoing to expose skin wall starter bars, Scaffold erection in progress for TDP H-beam cutting
Fri (20/02) | 20 Feb 2026 | B2-35, B2-37 | North side | No activity
Fri (20/02) | 20 Feb 2026 | P6 |  | Crosshead Falsework installation in progress
Fri (20/02) | 20 Feb 2026 | P1 |  | Crosshead tendon ducts installation in progress
Fri (20/02) | 20 Feb 2026 | Exit 1 stockpile |  | Currently no activity
Fri (20/02) | 20 Feb 2026 | P36 |  | 2nd lift column rebar work. This is the last 2nd lift to cast from P35 to P44
Fri (20/02) | 20 Feb 2026 | P41 |  | Working platform dismantling
Fri (20/02) | 20 Feb 2026 | P46 |  | Manual excavation for services support
Fri (20/02) | 20 Feb 2026 | P51 |  | Backfilling at the base for lean concrete. Tomorrow KTC will handover to Wendyng for balance 2nd layer caisson work
Fri (20/02) | 20 Feb 2026 | P6 |  | Crane breakdown. Mechanic on site to repair now
Fri (20/02) | 20 Feb 2026 | P1 |  | Continue PT ducts installation and adjustment
Fri (20/02) | 20 Feb 2026 | B2-35, B2-37 | North side | No activity
Fri (20/02) | 20 Feb 2026 | Opening 9 |  | No activity
Fri (20/02) | 20 Feb 2026 | B2-38 | South side | Hacking dwall surface to expose skin wall starter bars
Fri (20/02) | 20 Feb 2026 | B2-31 | North side | Skin wall rebar works ongoing
Fri (20/02) | 20 Feb 2026 | B2-30 | South side | PU grouting in progress
Fri (20/02) | 20 Feb 2026 | B2-27 | North side | PU grouting in progress
Fri (20/02) | 20 Feb 2026 | B2-25, B2-26 |  | Rebar works in progress
Fri (20/02) | 20 Feb 2026 | B2-26 | South side | Hacking ongoing to expose couplers
Fri (20/02) | 20 Feb 2026 | B2-24 | South side | Hacking dwall sueface to expose skin wall starter bars
Fri (20/02) | 20 Feb 2026 | B2-28 | South side | Currently no activity
Fri (20/02) | 20 Feb 2026 | Opening 7 |  | B2-21 (North side): Excavation in progress towards B2-19 side, B2-22 (South side): No activity
Fri (20/02) | 20 Feb 2026 | DR4 |  | Continue JGP grouting and spoil disposal
Fri (20/02) | 20 Feb 2026 | P51 |  | Levelling for base lean concrete
Fri (20/02) | 20 Feb 2026 | P47 |  | Continue hacking of drain and debris removal
Fri (20/02) | 20 Feb 2026 | P46 |  | Exposing services for support
Fri (20/02) | 20 Feb 2026 | P43 |  | Stressing done. By Sunday will shift starter hanger to P42. WH preparing for stitching formwork closing at P44
Fri (20/02) | 20 Feb 2026 | P41 |  | Working platform dismantling
Fri (20/02) | 20 Feb 2026 | P6 |  | Falsework erection in progress. Now crane breakdown. Tomorrow to repair the crane
Fri (20/02) | 20 Feb 2026 | DR4 Zone 3 |  | Prism installed and reading taken
Fri (20/02) | 20 Feb 2026 | P51 |  | Base lean concrete
Fri (20/02) | 20 Feb 2026 | P47 |  | Removing rebars from hacked drain
Fri (20/02) | 20 Feb 2026 | P46 |  | Housekeeping
Fri (20/02) | 20 Feb 2026 | MH3-5 |  | Clean up at DICs area done
Fri (20/02) | 20 Feb 2026 | P1 |  | Ducting installation
Sat (21/02) | 21 Feb 2026 | P36 2nd lift column |  | Preparing for RWDP installation
Sat (21/02) | 21 Feb 2026 | P37 |  | 2nd lift column Formwork dismantling ongoing
Sat (21/02) | 21 Feb 2026 | P41 |  | Crosshead Falsework and scaffold dismantling in progress
Sat (21/02) | 21 Feb 2026 | P43 |  | Preparation for starter hanger shifting to P42. Materials shifting ongoing
Sat (21/02) | 21 Feb 2026 | P43 |  | 1st pair stitching formwork dismantling
Sat (21/02) | 21 Feb 2026 | P46 |  | Manual excavation to expose utilities for support works
Sat (21/02) | 21 Feb 2026 | P47 |  | Hacking of drain and debris removal
Sat (21/02) | 21 Feb 2026 | P51 |  | 2nd layer cassion rebar works ongoing
Sat (21/02) | 21 Feb 2026 | DR4 |  | JGP works ongoing
Sat (21/02) | 21 Feb 2026 | DR4-Zone 3 |  | Excavation works ongoing for S3 layer ERSS installation
Sat (21/02) | 21 Feb 2026 | P1 |  | Tendon ducts and RWDP installed. Now ducts and RWDP rebar supports installation in progress
Sat (21/02) | 21 Feb 2026 | P6 |  | Falsework - Primary beam installation in progress
Sat (21/02) | 21 Feb 2026 | P36 |  | RWDP installed. Preparation for Formwork closing for 2nd lift column
Sat (21/02) | 21 Feb 2026 | P37 |  | 2nd lift column Formwork dismantled
Sat (21/02) | 21 Feb 2026 | P41 |  | Continue Falsework dismantling
Sat (21/02) | 21 Feb 2026 | P42 |  | Netting installation ongoing
Sat (21/02) | 21 Feb 2026 | P43 |  | Preparation for stressing cage lowering
Sat (21/02) | 21 Feb 2026 | P46 |  | Continue manual excavation to expose utilities for support works
Sat (21/02) | 21 Feb 2026 | P47 |  | Continue hacking of drain and removal of debris
Sat (21/02) | 21 Feb 2026 | P51 |  | 2nd layer cassion wall rebar works
Sat (21/02) | 21 Feb 2026 | DR4 |  | Continue JGP works. Preparation for 3rd JGP point
Sat (21/02) | 21 Feb 2026 | DR4-Zone 3 |  | Continue excavation for S3 layer ERSS
Sat (21/02) | 21 Feb 2026 | P1 |  | Continue rebar support for tendon ducts
Sat (21/02) | 21 Feb 2026 | P6 |  | Falsework - platform installation ongoing
Sat (21/02) | 21 Feb 2026 | P12 |  | Scaffold installation for CH stage 2 tension works
Mon (23/02) | 23 Feb 2026 | B2-27 | North side | PU grouting in progress
Mon (23/02) | 23 Feb 2026 | B2-25, B2-26, B2-27, B2-28 |  | Bottom bar installation in progress, B2-28 (South side): PU grouting in progress
Mon (23/02) | 23 Feb 2026 | B2-23 | North side | Current status of hacking to expose skin wall starter bars
Mon (23/02) | 23 Feb 2026 | B2-31, B2-33, B2-35, B2-37 | North side | Currently no activity at skin wall area
Mon (23/02) | 23 Feb 2026 | B2-29 |  | Column C01-6 bottom surface hacking ongoing
Mon (23/02) | 23 Feb 2026 | B2-33, B2-34 |  | Columns no activity
Mon (23/02) | 23 Feb 2026 | B2-35 | North side | Column C02-2 soffit roughening in progress for rebar works
Mon (23/02) | 23 Feb 2026 | B2-36 | South side | Column C02-2 soffit roughening in progress for rebar works
Mon (23/02) | 23 Feb 2026 | Opening 7 |  | B2-19, B2-21 (North side): Excavation in progress (3 exc, 1 telescopic), B2-22 (South side): Currently no activity
Mon (23/02) | 23 Feb 2026 | B2-36 | South side | Current status of hacking skin wall to expose starter bars
Mon (23/02) | 23 Feb 2026 | Exit 1 stockpile |  | Soil disposal ongoing
Mon (23/02) | 23 Feb 2026 | Vent shaft S1a layer |  | Drilling ongoing for anchor bolts. Waler and strutting materials target to arrive on Wed
Mon (23/02) | 23 Feb 2026 | Exit 2 raker strut |  | Rectifying comments to jacking connection prior to preloading
Mon (23/02) | 23 Feb 2026 | B1-10 |  | Drilling ongoing for missing couplers
Mon (23/02) | 23 Feb 2026 | B1-09 |  | APP piping installation, Rebar works in progress (CGW: 22 men), Partial formwork installation in progress
Mon (23/02) | 23 Feb 2026 | B1-02 |  | Houskeeping
Mon (23/02) | 23 Feb 2026 | B1-01 |  | Hacking ongoing to expose skin wall starter bars
Mon (23/02) | 23 Feb 2026 | B1-01 | Opening construction 3B | CJ roughening ongoing
Mon (23/02) | 23 Feb 2026 | Opening 3 |  | B2-05, B2-06: Excavation in progress
Mon (23/02) | 23 Feb 2026 | P24 TB downhang wall |  | Partial formwork closing. Plan for casting on 26 Feb
Tue (24/02) | 24 Feb 2026 | P36 |  | 2nd lift formwork closing for column
Tue (24/02) | 24 Feb 2026 | P28&P29 |  | Current status of working platform erection
Tue (24/02) | 24 Feb 2026 | P41 |  | Current status of starter hanger installation
Tue (24/02) | 24 Feb 2026 | P43 |  | Stitching formwork removal
Tue (24/02) | 24 Feb 2026 | P44 |  | Formwork closing for stitching. Plan to cast on Saturday
Tue (24/02) | 24 Feb 2026 | Opening 7 |  | B2-19, B2-21, B2-22: Excavation in progress (3 exc, 1 telescopic)
Tue (24/02) | 24 Feb 2026 | B2-26 | South side | Drilling ongoing for missing couplers
Tue (24/02) | 24 Feb 2026 | B2-27 | North side | PU grouting in progress
Tue (24/02) | 24 Feb 2026 | B2-28, B2-26 | South side | PU grouting and bottom rebar planting in progress, RGT installation ongoing
Tue (24/02) | 24 Feb 2026 | B2-27, B2-28, B2-26, B2-25 |  | Rebar works in progress
Tue (24/02) | 24 Feb 2026 | B2-29, B2-30 |  | Columns no activity
Tue (24/02) | 24 Feb 2026 | B2-33, B2-34 |  | Columns no activity
Tue (24/02) | 24 Feb 2026 | B2-31, B2-33 | North side | Skin wall area no activity
Tue (24/02) | 24 Feb 2026 | B2-35, B2-37 | North side | Bottom hacking ongoing for skin wall area
Tue (24/02) | 24 Feb 2026 | B2-35, B2-36 |  | Columns area no other activity. Only clearing debris
Tue (24/02) | 24 Feb 2026 | B2-36 / Vent shaft | South side | Hacking ongoing to expose skin wall starter bars
Tue (24/02) | 24 Feb 2026 | B2-49A sump area |  | Drilling and rebar planting in progress
Tue (24/02) | 24 Feb 2026 | Vent shaft | S1a layer | Drilling ongoing for anchor bolts. Currently workers taking a break, This evening plan delivery for some materials and also tmr
Tue (24/02) | 24 Feb 2026 | Zone 3 |  | SHE inspection
Tue (24/02) | 24 Feb 2026 | P1 SB |  | Stump rebar work and U bar support installation
Tue (24/02) | 24 Feb 2026 | P6 |  | C channel placing and preparation for platform installation
Tue (24/02) | 24 Feb 2026 | P12 |  | Lowering down materials
Tue (24/02) | 24 Feb 2026 | DR4 |  | JGP grouting in progress. 2nos finish today. Total completed 23nos
Tue (24/02) | 24 Feb 2026 | DR4 |  | Platform rectification done
Tue (24/02) | 24 Feb 2026 | DR4 Zone 3 |  | Manual excavation for S4 layer struts
Tue (24/02) | 24 Feb 2026 | P51 |  | Continue casting of caisson for 2nd layer
Tue (24/02) | 24 Feb 2026 | P47 |  | Protruding rebar cutting and clearing
Tue (24/02) | 24 Feb 2026 | P46 |  | Current status
Tue (24/02) | 24 Feb 2026 | P43 |  | Assembling stressing cage to install at P42
Tue (24/02) | 24 Feb 2026 | P42 |  | Preparing for 2 segments to install tonight
Tue (24/02) | 24 Feb 2026 | MH3-5 |  | 1/2nos DIC installed. Tomorrow to complete the 2nd one
Wed (25/02) | 25 Feb 2026 | B2-27 | North side | PU grouting and bottom rebar planting ongoing
Wed (25/02) | 25 Feb 2026 | B2-21 | North side | Hacking ongoing to expose skin wall starter bars
Wed (25/02) | 25 Feb 2026 | B2-27, B2-28, B2-25, B2-26 |  | Rebar works in progress
Wed (25/02) | 25 Feb 2026 | P6 |  | Scaffold erection for bottom formwork installation. Start tmr
Wed (25/02) | 25 Feb 2026 | B2-31 | North side | PU grouting in progress for the bottom seepage
Wed (25/02) | 25 Feb 2026 | B2-35, B2-37 | North side | No activity
Wed (25/02) | 25 Feb 2026 | Zone 4 |  | PGI and drain inspection
Wed (25/02) | 25 Feb 2026 | P1 |  | Links installation in progress
Wed (25/02) | 25 Feb 2026 | Exit 2 |  | Strain gauge readings obtained and now ok to proceed excavation, 1 excavator hoisted down to facilitate B1-11 excavation. Awaiting telescopic parking
Wed (25/02) | 25 Feb 2026 | B2-27 | North side | Bottom rebar planting and PU grouting in progress, RTO inspection ongoing for post drilling depth
Wed (25/02) | 25 Feb 2026 | B2-25 | North side | RGT installation in progress
Wed (25/02) | 25 Feb 2026 | Opening 7 |  | B2-19, B2-20, B2-21: Excavation in progress (3 exc, 1 telescopic), B2-22: Currently no activity
Wed (25/02) | 25 Feb 2026 | B2-33 | North side | Preparing for PU grouting at bottom seepage area
Wed (25/02) | 25 Feb 2026 | B2-34, B2-36 | South side | No activity
Wed (25/02) | 25 Feb 2026 | B2-35, B2-37 | North side | No activity
Wed (25/02) | 25 Feb 2026 | DR4 |  | JGP grouting work. 2nos done as of now. Today target 4nos
Wed (25/02) | 25 Feb 2026 | DR4 Zone 3 |  | S4 waler bracket installed. Preparing for waler installation
Wed (25/02) | 25 Feb 2026 | B2-35, B2-36 & Opening 9 |  | No activity
Wed (25/02) | 25 Feb 2026 | Vent shaft - S1a layer |  | Hirose continue drilling works. Today plan for material delivery
Wed (25/02) | 25 Feb 2026 | P28-29 |  | No activity
Wed (25/02) | 25 Feb 2026 | B2-49A sump area |  | Wendyng housekeeping for Maxbond works. Wendyng will continue once Maxbond complete their works
Wed (25/02) | 25 Feb 2026 | Exit 2 |  | B1-11 excavation started
Wed (25/02) | 25 Feb 2026 | P43-P42 |  | Assembling of main beam for LG
Wed (25/02) | 25 Feb 2026 | P44 |  | Formwork closing for stitching work
Wed (25/02) | 25 Feb 2026 | P46 |  | Current status. Now no activity due to rain
Wed (25/02) | 25 Feb 2026 | P47 |  | Main beam installation for utility support
Wed (25/02) | 25 Feb 2026 | P51 |  | Formwork removal
Wed (25/02) | 25 Feb 2026 | P36 |  | Access erection. Tomorrow to cast
Wed (25/02) | 25 Feb 2026 | P6 TPE bound |  | Soffit plywood laying. Changi bound: will continue after last bus
Wed (25/02) | 25 Feb 2026 | DR4 Zone 3 |  | Preparing for waler installation
Wed (25/02) | 25 Feb 2026 | DR4 |  | JGP grouting in progress
Wed (25/02) | 25 Feb 2026 | P51 |  | Formwork removal for caisson
Wed (25/02) | 25 Feb 2026 | P47 |  | Hard barricade installation for completed drain hacking
Wed (25/02) | 25 Feb 2026 | P46 |  | No activity already due to rain
Wed (25/02) | 25 Feb 2026 | P44 and P42 |  | No working at height activity due to rain
Wed (25/02) | 25 Feb 2026 | P1 |  | Rebar installation around U pipes
Wed (25/02) | 25 Feb 2026 | P12 |  | Crosshead 2nd stage stressing in progress
Wed (25/02) | 25 Feb 2026 | North ramp P10-11 |  | Hardcore laying for crane parking to unload segments
Thu (26/02) | 26 Feb 2026 | Zone 2 |  | Unloading of PT ducts for station crossheads
Thu (26/02) | 26 Feb 2026 | N2 |  | Falsework dismantling
Thu (26/02) | 26 Feb 2026 | 800mm PW |  | S4 strut installation ongoing
Thu (26/02) | 26 Feb 2026 | DR4 |  | Soil disposal
Thu (26/02) | 26 Feb 2026 | P51 |  | Remove material and clearing for excavation
Thu (26/02) | 26 Feb 2026 | P48 |  | No activity
Thu (26/02) | 26 Feb 2026 | P47 | south | Utility support installation
Thu (26/02) | 26 Feb 2026 | P47 | north | DSTA cable protection in progress
Thu (26/02) | 26 Feb 2026 | P6 |  | Bottom formwork installation started
Thu (26/02) | 26 Feb 2026 | Opening 7 |  | B2-19, B2-20, B2-21: Excavation in progress (3 exc, 1 telescopic), B2-22: Currently no activity
Thu (26/02) | 26 Feb 2026 | P1 crosshead |  | Section 3 links installation. Inspection at 5pm. To close balance formwork tonight
Thu (26/02) | 26 Feb 2026 | Opening 7 |  | B2-19, B2-20, B2-21, B2-22: Excavation in progress (3 exc, 1 telescopic)
Thu (26/02) | 26 Feb 2026 | B2-25 , B2-26 (South side) | North side | PU grouting and drilling for missing couplers ongoing
Thu (26/02) | 26 Feb 2026 | B2-27, B2-28 |  | Continue rebar works and RTO inspection for wall starter bars, B2-25, B2-26: Also continue rebar works
Thu (26/02) | 26 Feb 2026 | B2-31 | North side | Cleaning works ongoing
Thu (26/02) | 26 Feb 2026 | Vent shaft | S1a layer | Hirose continue drilling works. Today plan to complete and tmr to start installing waler bracket
Thu (26/02) | 26 Feb 2026 | B2-49A seepage tank area |  | Waterproofing membrane laying in progress
Thu (26/02) | 26 Feb 2026 | B1-11 |  | Excavation in progress
Thu (26/02) | 26 Feb 2026 | DR4 |  | JGP rig breakdown, no activity
Thu (26/02) | 26 Feb 2026 | P51 |  | Lowering excavator for 3rd layer excavation
Thu (26/02) | 26 Feb 2026 | P49 |  | Exposing further SPPG cable
Thu (26/02) | 26 Feb 2026 | P46 |  | No activity
Thu (26/02) | 26 Feb 2026 | P47 |  | Steel box protection for DSTA Cable completed..stump construction in progress
Thu (26/02) | 26 Feb 2026 | North ramp P10-11 |  | Steel plate laying. Tonight to deliver segment
Thu (26/02) | 26 Feb 2026 | P1 crosshead |  | Section 3 links inspection completed
Thu (26/02) | 26 Feb 2026 | P51 |  | Excavator hoist down for 3rd layer caison excavation
Thu (26/02) | 26 Feb 2026 | P40 |  | Falsework erection started
Thu (26/02) | 26 Feb 2026 | P36 |  | Column 2nd stage casting
Fri (27/02) | 27 Feb 2026 | P36 |  | Casting completed for 2nd lift. As of today P35 to P40 is available to do crosshead
Fri (27/02) | 27 Feb 2026 | P39 |  | Crosshead formwork removal
Fri (27/02) | 27 Feb 2026 | P40 |  | Continue preparation for falsework erection
Fri (27/02) | 27 Feb 2026 | Vent shaft | S1a layer | Drilling and bolt planting ongoing. Also hoisting down materials for waler bracket installation
Fri (27/02) | 27 Feb 2026 | B2-49A sump pit area |  | Post drilling inspection for rebar planting
Fri (27/02) | 27 Feb 2026 | Beside B2-38 |  | Clearing debonding sheets. No other activity
Fri (27/02) | 27 Feb 2026 | B-29 to B2-37 |  | No activity
Fri (27/02) | 27 Feb 2026 | B2-25 to B2-28 |  | Rebar works in progress, B2-25, B2-26: Dongah continue PU grouting and drilling for missing couplers
Fri (27/02) | 27 Feb 2026 | Opening 7 |  | B2-19, B2-20, B2-21: Excavation in progress (3 exc, 1 telescopic)
Fri (27/02) | 27 Feb 2026 | P46 |  | Preparing stump rebar for casting
Fri (27/02) | 27 Feb 2026 | P47 |  | Utility support installation and continue exposing utility
Fri (27/02) | 27 Feb 2026 | P49 |  | Exposing 22KV to check for localize shifting
Fri (27/02) | 27 Feb 2026 | P51 |  | Continue excavation for 3rd layer caisson
Fri (27/02) | 27 Feb 2026 | B1-11 |  | Partial lean concrete cast last night, Continue excavation. Thereafter, lean concrete will be progressively cast
Fri (27/02) | 27 Feb 2026 | P12 |  | Lifting appliance for stressing cage replacement
Fri (27/02) | 27 Feb 2026 | DR4 Zone 3 |  | Excavation to FEL done. Now quarry dust laying at the base and prepare for base lean concrete. Tonight plan to lay the pipe
Fri (27/02) | 27 Feb 2026 | P51 |  | Excavation to L3 caisson level ongoing
Fri (27/02) | 27 Feb 2026 | P48 |  | Utility support removal ongoing
Fri (27/02) | 27 Feb 2026 | P46 |  | Utility support installation in progress
Fri (27/02) | 27 Feb 2026 | P47 |  | Manual excavation in progress
Fri (27/02) | 27 Feb 2026 | P6 |  | Bottom formwork adjustable jack installation status
Fri (27/02) | 27 Feb 2026 | P1 |  | Tie back on railing installation for casting
Fri (27/02) | 27 Feb 2026 | P27 |  | Tie rod formwork dismantling
Fri (27/02) | 27 Feb 2026 | P39 |  | Crosshead formwork dismantling status
Fri (27/02) | 27 Feb 2026 | P40 |  | Falsework leg frame level adjusted. Tmr to start primary beam installation
Fri (27/02) | 27 Feb 2026 | P42 |  | Preparation to install stressing cage at downchainage
Fri (27/02) | 27 Feb 2026 | P46 |  | Column rebar delivery
Fri (27/02) | 27 Feb 2026 | P46 |  | Primary beam installation for Utility support
Fri (27/02) | 27 Feb 2026 | P47 |  | No more activity
Fri (27/02) | 27 Feb 2026 | P51 |  | Excavation for 3rd layer caison
Fri (27/02) | 27 Feb 2026 | P28&29 |  | Current status
Fri (27/02) | 27 Feb 2026 | P27 |  | Column formwork removal
Sat (28/02) | 28 Feb 2026 | 800mm PW |  | Welding pipe joint
Sat (28/02) | 28 Feb 2026 | DR4 |  | JGP Grouting works in progress
Sat (28/02) | 28 Feb 2026 | P51 |  | Excavation to L3 caisson level
Sat (28/02) | 28 Feb 2026 | P48 |  | Utility support removal
Sat (28/02) | 28 Feb 2026 | P47 |  | Manual excavation for utility support
Sat (28/02) | 28 Feb 2026 | P47 |  | Utility support installation
Sat (28/02) | 28 Feb 2026 | P45 |  | 1st lift column rebar delivery
Sat (28/02) | 28 Feb 2026 | P44 |  | Formwork closing for stitching. Target to cast on today
Sat (28/02) | 28 Feb 2026 | P43 |  | No activity
Sat (28/02) | 28 Feb 2026 | P42 |  | Stressing cage installation ongoing
Sat (28/02) | 28 Feb 2026 | P40 |  | Falsework installation in progress
Sat (28/02) | 28 Feb 2026 | P39 |  | Crosshead formwork dismantling status
Sat (28/02) | 28 Feb 2026 | N1 |  | Falsework dismantling
Sat (28/02) | 28 Feb 2026 | P6 |  | Side formwork assembly and landing platform leveling work in progress
Sat (28/02) | 28 Feb 2026 | P1 |  | Crosshead tie rod installation work in progress
Sat (28/02) | 28 Feb 2026 | P44 |  | Ready for stitch casting
Sat (28/02) | 28 Feb 2026 | P42 |  | Cable pulling for stressing
Sat (28/02) | 28 Feb 2026 | 800mm PW |  | Water pipe joint welding in progree
Sat (28/02) | 28 Feb 2026 | P51 |  | Excavation to L3 caisson level
Sat (28/02) | 28 Feb 2026 | P47 |  | Utility support installation
Sat (28/02) | 28 Feb 2026 | P46 |  | Utility support installation and preparing working platform for welding works
Sat (28/02) | 28 Feb 2026 | DR4 |  | JGP works ongoing
Sat (28/02) | 28 Feb 2026 | P42 |  | Platform casting in progress
Sat (28/02) | 28 Feb 2026 | P40 |  | Falsework installation in progress
Sat (28/02) | 28 Feb 2026 | P39 |  | Current crosshead formwork dismantling status
Mon (02/03) | 02 Mar 2026 | P6 |  | Currently no activity
Mon (02/03) | 02 Mar 2026 | P27 |  | Column formwork dismantling
Mon (02/03) | 02 Mar 2026 | P39 |  | Bottom formwork dismantling
Mon (02/03) | 02 Mar 2026 | P40 |  | Working platform installation
Mon (02/03) | 02 Mar 2026 | P47 |  | Stump rebar works and preparation for formwork closing
Mon (02/03) | 02 Mar 2026 | P51 |  | Pile head hacking
Mon (02/03) | 02 Mar 2026 | P6 |  | Tonight to continue installation of side formwork
Tue (03/03) | 03 Mar 2026 | B2-49A sump pit |  | Rebar works and drainage pipe installation in progress
Tue (03/03) | 03 Mar 2026 | Vent shaft | S1a layer | Continue waler beam installation - 1/7nos struts installed, Currently no excavation to B2-39. Plan to commence once S1a layer complete this week
Tue (03/03) | 03 Mar 2026 | P6 |  | Sideformwork assembly
Tue (03/03) | 03 Mar 2026 | 800mm PW |  | Preparation of short vertical pipe installation
Tue (03/03) | 03 Mar 2026 | DR4 |  | JGP works ongoing and soil disposal
Tue (03/03) | 03 Mar 2026 | P51 |  | Working platform levelling. Target today lean con casting and tomorrow wendyng start L3 caisson rebar work
Tue (03/03) | 03 Mar 2026 | P48 |  | Utility support removal completed. Backfilling to ground level on going
Tue (03/03) | 03 Mar 2026 | P47 |  | Stump construction ongoing
Tue (03/03) | 03 Mar 2026 | P46 |  | Utility support installation ongoing
Tue (03/03) | 03 Mar 2026 | P45 |  | Preparation work to start 1st lift of column
Tue (03/03) | 03 Mar 2026 | P30 |  | Drilling for start bar installation
Tue (03/03) | 03 Mar 2026 | P43 |  | 2/3 parts of LCB installation
Tue (03/03) | 03 Mar 2026 | P39 |  | Grouting cap installation
Tue (03/03) | 03 Mar 2026 | Opening 7 |  | Soil disposal in progress, B2-21, B2-22: Soil levelling ongoing. Today plan for lean concrete works
Tue (03/03) | 03 Mar 2026 | B2-26, B2-28 |  | Rebar works in progress, B2-25 (North side): PU grouting ongoing, This week plan to cast B2-25 to B2-28
Tue (03/03) | 03 Mar 2026 | B2-33 | North side | Preparing for PU grouting
Tue (03/03) | 03 Mar 2026 | B2-35 | North side | Column C02-2 rebar planting in progress
Tue (03/03) | 03 Mar 2026 | B2-37 | North side | Exposing dwall for rectification works
Tue (03/03) | 03 Mar 2026 | B2-36 | South side | Continue hacking to expose skin wall starter bars
Wed (04/03) | 04 Mar 2026 | P12 |  | Scaffold access for grouting dismantling. Grouting works completed
Wed (04/03) | 04 Mar 2026 | P6 |  | Continue assembly of side formwork
Wed (04/03) | 04 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Wed (04/03) | 04 Mar 2026 | B2-49A |  | Current rebar status for the sump pit
Wed (04/03) | 04 Mar 2026 | P6 |  | Side formwork assembly continue
Wed (04/03) | 04 Mar 2026 | B1-11 |  | Excavation in progress. Currently ard GL15 (2 exc, 1 telescopic)
Wed (04/03) | 04 Mar 2026 | Vent shaft | S1a layer | Welding works & preparing for 3rd strut installation
Wed (04/03) | 04 Mar 2026 | Vent shaft | S3 layer | Hacking dwall to COL
Wed (04/03) | 04 Mar 2026 | B2-37 | North side | Hacking ongoing to expose dwall STN79 for rectification works
Wed (04/03) | 04 Mar 2026 | B2-33 | North side | PU grouting ongoing
Wed (04/03) | 04 Mar 2026 | GL22 |  | PU grouting ongoing at STN57
Wed (04/03) | 04 Mar 2026 | B2-21, B2-22 | GL18-16 | Yesterday cast lean con. Now formwork closing at drop area and exposing couplers
Wed (04/03) | 04 Mar 2026 | B2-17 to B2-20 | GL16-12 | Excavation in progress (3 exc, 1 telescopic)
Wed (04/03) | 04 Mar 2026 | B2-25 to B2-28 |  | Top bar works and E&M pipe installation in progress, Surveyor marking in progress, Balance to install shearlinks, starter bars, Dongah PU grouting ongoing, Plan for casting this Friday
Wed (04/03) | 04 Mar 2026 | P36 |  | Tie rod removal in progress. Preparation for Formwork dismantling
Wed (04/03) | 04 Mar 2026 | P39 |  | PT strands installation ongoing
Wed (04/03) | 04 Mar 2026 | P1 |  | Polyfoam installation around bearing stump. Final inspection at 530pm
Wed (04/03) | 04 Mar 2026 | P40 |  | CH Falsework installation ongoing
Wed (04/03) | 04 Mar 2026 | P43 |  | LG (wagon) installation in progress
Wed (04/03) | 04 Mar 2026 | P44 |  | Stitiching Formwork dismantling
Wed (04/03) | 04 Mar 2026 | 800mm PW |  | Air test for water pipe joint
Wed (04/03) | 04 Mar 2026 | DR4 |  | JGP works ongoing
Wed (04/03) | 04 Mar 2026 | P51 |  | Excavation to L3 caisson level ongoing at south side.. Lean con casting completed at north side
Wed (04/03) | 04 Mar 2026 | P47 |  | Utility support installation ongoing
Wed (04/03) | 04 Mar 2026 | P46 |  | No activity
Wed (04/03) | 04 Mar 2026 | P45 |  | 1st lift column rebar installation
Wed (04/03) | 04 Mar 2026 | DR4 |  | JGP to continue until 10pm. 3rd point drilling in progress
Wed (04/03) | 04 Mar 2026 | P44 |  | SB side to stress tonight. NB side stitching formwork dismantling
Thu (05/03) | 05 Mar 2026 | P17-P18 |  | Materials shifting for midspan formwork stitching
Thu (05/03) | 05 Mar 2026 | P11 |  | Scaffold erection in progress
Thu (05/03) | 05 Mar 2026 | P10 |  | Barricade netting installation ongoing
Thu (05/03) | 05 Mar 2026 | P6 |  | Crosshead formwork installation
Thu (05/03) | 05 Mar 2026 | 800mm Pw |  | Preparation for pipe joint test
Thu (05/03) | 05 Mar 2026 | DR4 |  | JGP works ongoing
Thu (05/03) | 05 Mar 2026 | P51 | North | Preparation for L3 caisson rebar work
Thu (05/03) | 05 Mar 2026 | P51 | South | Bored pile hacking completed, currently excavation status
Thu (05/03) | 05 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Thu (05/03) | 05 Mar 2026 | P30 |  | Drilling for start bars completed
Thu (05/03) | 05 Mar 2026 | Vent shaft S3 layer |  | Dwall hacking to COL in progress
Thu (05/03) | 05 Mar 2026 | Vent shaft S1a layer |  | Struts installation and welding works ongoing - 3/7nos struts installed
Thu (05/03) | 05 Mar 2026 | B2-37 | North side | Dwall rectification works ongoing at STN79
Thu (05/03) | 05 Mar 2026 | B2-25 to B2-28 |  | Shearlinks installation ongoing, Top bar inspection, Joining of casting pipes in progress, Surveyor works ongoing, PU grouting ongoing at B2-27 (North side) for STN58, Plan for casting tomorrow
Thu (05/03) | 05 Mar 2026 | B2-23 | North side | Hacking and debris clearing ongoing for PU grouting works
Thu (05/03) | 05 Mar 2026 | B2-24 | South side | Exposing couplers ongoing
Thu (05/03) | 05 Mar 2026 | P45 |  | Preparation for column formwork closing
Thu (05/03) | 05 Mar 2026 | P46 |  | No activity
Thu (05/03) | 05 Mar 2026 | P47 |  | Concrete stump formwork removal ongoing..utility support installation ongoing
Thu (05/03) | 05 Mar 2026 | P43 |  | MS main frame and wagon installation in progress at SB side
Thu (05/03) | 05 Mar 2026 | P1 |  | Crosshead cast last night
Thu (05/03) | 05 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator, 8 loads have been sent to MESG for today
Thu (05/03) | 05 Mar 2026 | B2-49A |  | Continues rebar installation for the sump pit
Thu (05/03) | 05 Mar 2026 | CCE | GL E9 - GL32 | Continues north side excavation & soil internal shifting by 2 excavators
Thu (05/03) | 05 Mar 2026 | P6 |  | Column CJ roughening
Thu (05/03) | 05 Mar 2026 | P6 |  | Scaffold support for rebar works. Tmr to start rebar installation
Thu (05/03) | 05 Mar 2026 | B2-25 to B2-28 |  | Started cleaning works, Continue top bar inspection and shearlinks installation
Thu (05/03) | 05 Mar 2026 | Opening 7 |  | B2-17 to B2-20: Excavation and disposal in progress
Thu (05/03) | 05 Mar 2026 | B2-34 | South side | Drilling ongoing for PU grouting at STN167
Thu (05/03) | 05 Mar 2026 | Vent shaft S1a layer |  | Preparing to install 4th strut, Welding works ongoing, This evening ard 7pm to cast waler concrete packing
Thu (05/03) | 05 Mar 2026 | Vent shaft S3 layer |  | Dwall hacking to COL ongoing
Thu (05/03) | 05 Mar 2026 | P51 |  | Utility gap welding work in progress
Thu (05/03) | 05 Mar 2026 | 800mm PW |  | Preparation work for access manhole installation
Thu (05/03) | 05 Mar 2026 | P45 |  | Crane parking, ready for formwork erection
Fri (06/03) | 06 Mar 2026 | B2-37 | North side | Dwall rectification works is in progress
Fri (06/03) | 06 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Fri (06/03) | 06 Mar 2026 | B2-25 to B2-28 |  | Wall starter bar & shearlinks installation, Cleaning ongoing, corrugated pipes & hyrib installation, Joining of casting pipes, Plan for final inspection this afternoon and cast at night
Fri (06/03) | 06 Mar 2026 | B2-23 | North side | Drilling ongoing for PU grouting works, Currently no other activity at B2-23 and B2-24
Fri (06/03) | 06 Mar 2026 | B2-34 | South side | Demo for dwall (joint between STN167 & 168) repair using Greenflex 200, Attended by PJT, SRE, WHDA
Fri (06/03) | 06 Mar 2026 | Vent shaft S1a layer |  | 4/7nos struts installed, Now ongoing welding works and preparing for subsequent installation, Waler concrete packing cast last night
Fri (06/03) | 06 Mar 2026 | Vent shaft S3 |  | Dwall hacking ongoing to COL
Fri (06/03) | 06 Mar 2026 | B2-49A |  | Continues top bar installation for the e sump pit & plan to cast tomorro
Fri (06/03) | 06 Mar 2026 | CCE Ramp/GL E9-GL32 |  | Continues excavation & soil internal shifting by 2 excavators
Fri (06/03) | 06 Mar 2026 | P4 |  | Preparation for lean concrete casting
Fri (06/03) | 06 Mar 2026 | 800mm PW |  | 1st part access manhole installation completed, currently removing s3 strut
Fri (06/03) | 06 Mar 2026 | P51 |  | Current levelling status, target to lean con today for working platform
Fri (06/03) | 06 Mar 2026 | P51 |  | Preparation work for L3 caisson rebar works
Fri (06/03) | 06 Mar 2026 | P46 |  | No activity
Fri (06/03) | 06 Mar 2026 | P45 |  | 1st lift rebar formwork closing, target to cast tomorrow
Fri (06/03) | 06 Mar 2026 | P47 |  | Utility support installation ongoing
Fri (06/03) | 06 Mar 2026 | 800mm water pipe laying area |  | S3 waler dismantling and backfilling works
Fri (06/03) | 06 Mar 2026 | P51 3rd layer caison |  | SB side excavation completed
Fri (06/03) | 06 Mar 2026 | P47 |  | Secondary beam for Utility support installation
Fri (06/03) | 06 Mar 2026 | P44 |  | SB side SH dismantled
Fri (06/03) | 06 Mar 2026 | P43 |  | 1 side wagon and MS LC frame installed
Fri (06/03) | 06 Mar 2026 | P6 |  | Wendyng no rebar works tonight
Sat (07/03) | 07 Mar 2026 | P30 |  | Rectification/drilling works for rebar installation
Sat (07/03) | 07 Mar 2026 | P39 |  | Crosshead PT strand stressing works in progress
Sat (07/03) | 07 Mar 2026 | P40 |  | Crosshead Falsework installation
Sat (07/03) | 07 Mar 2026 | P42 |  | 1st pair stitching - inner formwork installation
Sat (07/03) | 07 Mar 2026 | P43 |  | Currently no activity. Materials shifting in progress
Sat (07/03) | 07 Mar 2026 | P43 |  | Preparation to shift starter hanger to Zone 2 - P10/P11 area
Sat (07/03) | 07 Mar 2026 | P44 |  | 1st pair stitching - formwork dismantling
Sat (07/03) | 07 Mar 2026 | P45 |  | Scaffold erection for 1st lift column casting today
Sat (07/03) | 07 Mar 2026 | P47 |  | Utility support welding works in progress
Sat (07/03) | 07 Mar 2026 | 800mm water pipe laying area |  | S3 waler dismantling and backfilling works for AMH installation
Sat (07/03) | 07 Mar 2026 | P51 |  | 3rd layer caisson wall rebar works
Sat (07/03) | 07 Mar 2026 | DR4 |  | Soil clearing and platform preparation for JGP works
Sat (07/03) | 07 Mar 2026 | Zone 1 |  | Housekeeping and area preparation for segment launching works
Sat (07/03) | 07 Mar 2026 | P6 |  | Crosshead base rebars installation
Sat (07/03) | 07 Mar 2026 | P30 |  | Drilling works completed. Suverying check ongoing
Sat (07/03) | 07 Mar 2026 | P39 |  | Stressing completed. Strand cutting ongoing
Sat (07/03) | 07 Mar 2026 | P40 |  | CH bottom Falsework installation
Sat (07/03) | 07 Mar 2026 | P42 |  | 1st pair stitching formwork installation
Sat (07/03) | 07 Mar 2026 | Bet. P43-P44 |  | Stater hanger materials shifting to zone 2
Sat (07/03) | 07 Mar 2026 | P45 |  | Preparation for 1st lift column casting. Concrete ordered
Sat (07/03) | 07 Mar 2026 | P47 |  | Utility support welding works
Sat (07/03) | 07 Mar 2026 | P51 |  | 3rd layer caisson wall rebar works
Sat (07/03) | 07 Mar 2026 | DR4 |  | Preparation for next JGP location
Sat (07/03) | 07 Mar 2026 | P2 |  | Area preparation for segment launching - Hardcores laying ongoing
Sat (07/03) | 07 Mar 2026 | P6 |  | Continue Crosshead base rebar installation works
Sat (07/03) | 07 Mar 2026 | P10-P11 |  | Starter hanger assembly works
Mon (09/03) | 09 Mar 2026 | P6 |  | Crosshead rebar installation and platform laying works
Mon (09/03) | 09 Mar 2026 | P1 |  | Inspection with PE on Crosshead Falsework
Mon (09/03) | 09 Mar 2026 | B2-25 to B2-28 |  | Cast last Saturday
Mon (09/03) | 09 Mar 2026 | B2-23/21 | North side | Post-drilling ongoing
Mon (09/03) | 09 Mar 2026 | B2-21, B2-20 |  | Plywood laying in progress
Mon (09/03) | 09 Mar 2026 | B2-24 | South side | PU grouting ongoing
Mon (09/03) | 09 Mar 2026 | B2-25, B2-26 |  | CJ roughening in progress
Mon (09/03) | 09 Mar 2026 | B2-29 | North side | Column C01-6 rebar works ongoing
Mon (09/03) | 09 Mar 2026 | B2-32 | South side | PU grouting ongoing
Mon (09/03) | 09 Mar 2026 | Vent shaft | S1a layer | Preloading in progress (DS3-3), Bolt tightening
Mon (09/03) | 09 Mar 2026 | B2-35 | North side | Column 02-2 rebar planting in progress
Mon (09/03) | 09 Mar 2026 | B2-37 | North side | Debris clearing ongoing prior to PU grouting works
Mon (09/03) | 09 Mar 2026 | P30 |  | No activity
Mon (09/03) | 09 Mar 2026 | P39 |  | Base formwork dismantling in progress
Mon (09/03) | 09 Mar 2026 | P40 |  | Base formwork installation on going
Mon (09/03) | 09 Mar 2026 | P42 |  | No activity
Mon (09/03) | 09 Mar 2026 | P43 & P44 |  | No activity
Mon (09/03) | 09 Mar 2026 | P45 |  | No activity. Pier stump concrete curing
Mon (09/03) | 09 Mar 2026 | P46 |  | No activity
Mon (09/03) | 09 Mar 2026 | P47 |  | LSS casting below existing DR3 slab
Mon (09/03) | 09 Mar 2026 | P48 |  | No activity. Currently backfilling status
Mon (09/03) | 09 Mar 2026 | P51 |  | L3 caisson rebar works
Mon (09/03) | 09 Mar 2026 | 800mm PW |  | (Zone 3) Soldier pile and lagging plate extraction ongoing
Mon (09/03) | 09 Mar 2026 | P6 |  | Crosshead rebar installation work ongoing
Tue (10/03) | 10 Mar 2026 | B1-10 |  | Hacking dwall surface to expose skin wall starter bars
Tue (10/03) | 10 Mar 2026 | B1-11 | part 1 | Rebar works and RGT installation in progress, Pipe installation ongoing by APP
Tue (10/03) | 10 Mar 2026 | P10 |  | Steel blister and spreader beam clamp installation
Tue (10/03) | 10 Mar 2026 | P11 |  | Raling installation. Plan to install SH tmr
Tue (10/03) | 10 Mar 2026 | B2-24 | South side | PU grouting in progress
Tue (10/03) | 10 Mar 2026 | B2-21 | North side | Column C01-3 rebar planting in progress
Tue (10/03) | 10 Mar 2026 | B2-19 | North side | Hacking dwall surface to expose skin wall starter bars
Tue (10/03) | 10 Mar 2026 | B2-23/21 | North side | Post-drilling ongoing
Tue (10/03) | 10 Mar 2026 | B2-22 | South side | Exposing couplers in progress
Tue (10/03) | 10 Mar 2026 | B2-24/B2-23 |  | Continue cleaning & laying plywood
Tue (10/03) | 10 Mar 2026 | B2-35 | North side | Column C02-2 rebar works in progress
Tue (10/03) | 10 Mar 2026 | B2-37 | North side | PU grouting ongoing
Tue (10/03) | 10 Mar 2026 | Vent shaft S3 layer |  | Continue exposing dwall to facilitate hacking to COL
Tue (10/03) | 10 Mar 2026 | Vent shaft s1a layer |  | Struts preloading completed yesterday. Now Hirose ongoing housekeeping, B2-39 excavation plan to start tmr
Tue (10/03) | 10 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Tue (10/03) | 10 Mar 2026 | P1 crosshead |  | Tie rod loosening
Tue (10/03) | 10 Mar 2026 | CCE Ramp / | GL32-30 | Excavation and soil internal shifting is in progress by 2 excavators
Tue (10/03) | 10 Mar 2026 | P6 crosshead |  | Main bar installation continue. Thursday to start installation of PT duct. Ultracon shifting steel anchor for progressive installation
Tue (10/03) | 10 Mar 2026 | P30 |  | No activity. Pending design clearance before resume rebar planting works
Tue (10/03) | 10 Mar 2026 | 800mm PW |  | ERSS installation at zone 1
Tue (10/03) | 10 Mar 2026 | DR4 |  | Shifting machine to South DR4 for probing works
Tue (10/03) | 10 Mar 2026 | P39 |  | Preparation for Falsework removal
Tue (10/03) | 10 Mar 2026 | P42 |  | 1st pair stitching formwork closing
Tue (10/03) | 10 Mar 2026 | P44 |  | Stressing cage assembly for upcoming segment launching
Tue (10/03) | 10 Mar 2026 | P43 |  | Surveying and marking works
Tue (10/03) | 10 Mar 2026 | P12 |  | Area preparation for crosshead grouting. Tonight to do grouting after last bus
Tue (10/03) | 10 Mar 2026 | Vent shaft S3 |  | Continue hacking dwall to COL. Currently rectifying excavator
Tue (10/03) | 10 Mar 2026 | B2-35 | North side | Column C02-2 rebar works in progress
Tue (10/03) | 10 Mar 2026 | B2-33 | North side | PU grouting ongoing and bottom cleaning works
Tue (10/03) | 10 Mar 2026 | B2-22 | South side | Continue exposing couplers
Tue (10/03) | 10 Mar 2026 | B2-22 |  | Levelling ongoing prior to casting lean con for balance area below Opening 7
Tue (10/03) | 10 Mar 2026 | P51 |  | L3 caisson formwork closing at north side
Tue (10/03) | 10 Mar 2026 | P47 |  | Utility support installation ongoing
Tue (10/03) | 10 Mar 2026 | P46 |  | No activity
Tue (10/03) | 10 Mar 2026 | P45 |  | No activity. Stump concrete curing
Tue (10/03) | 10 Mar 2026 | B2-21 | North side | Column C01-3 rebar works in progress, Bottom rebar plan to start tmr from B2-23
Tue (10/03) | 10 Mar 2026 | P39 |  | Crosshead falsework dismantling
Tue (10/03) | 10 Mar 2026 | P42 |  | 1st pair stitching formwork closing
Tue (10/03) | 10 Mar 2026 | P44 |  | Stressing cage assembly for upcoming segment launching
Tue (10/03) | 10 Mar 2026 | P47 |  | No activity
Tue (10/03) | 10 Mar 2026 | P51 |  | (north) L3 caisson 1st casting
Tue (10/03) | 10 Mar 2026 | 800mm PW |  | (Zone 1) tomorrow start probing for ERSS. Tonight going to do trial trench
Tue (10/03) | 10 Mar 2026 | P6 |  | Crosshead rebar works
Tue (10/03) | 10 Mar 2026 | P10 |  | Preparation work for starter hanger installation
Tue (10/03) | 10 Mar 2026 | P11 |  | Material shifting from zone 3
Tue (10/03) | 10 Mar 2026 | P12 |  | No activity. Tonight grouting @1:30am
Wed (11/03) | 11 Mar 2026 | B2-23 | North side | Start to prepare for bottom rebar works, CJ hacking ongoing at B2-25 area, Post-drilling ongoing
Wed (11/03) | 11 Mar 2026 | B2-21 | North side | Column C01-3 rebar works in progress, Preparing for PU grouting at dwall side
Wed (11/03) | 11 Mar 2026 | Opening 7 |  | Currently no excavation & disposal. Opening is used for hoisting down materials
Wed (11/03) | 11 Mar 2026 | B2-22 | South side | Preparing for PU grouting works
Wed (11/03) | 11 Mar 2026 | B2-24 | South side | Drilling ongoing for PU grouting and continuelaying debonding sheet
Wed (11/03) | 11 Mar 2026 | B2-26 |  | RGT installation in progress
Wed (11/03) | 11 Mar 2026 | B2-29 | North side | Column C01-6 rebar works in progress
Wed (11/03) | 11 Mar 2026 | B2-31 | North side | Cleaning ongoing at skin wall bottom side
Wed (11/03) | 11 Mar 2026 | B2-35 | North side | PU grouting ongoing
Wed (11/03) | 11 Mar 2026 | Opening 9/B2-39 |  | Observed telescopic has parked here for B2-39 excavation works, B2-39 excavation & hacking of dwall to COL ongoing
Wed (11/03) | 11 Mar 2026 | B2-30 | South side | Column C01-6 formwork installation in progress
Wed (11/03) | 11 Mar 2026 | P18 |  | Dismantling of adjustable jack and progressive installation of stitching formwork
Wed (11/03) | 11 Mar 2026 | P10 and P11 ramp |  | SH installation completed last night. Tonight to install P11 U01
Wed (11/03) | 11 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Wed (11/03) | 11 Mar 2026 | CCE Ramp / | GL31-29 | Excavation and soil internal shifting is in progress by 2 excavators
Wed (11/03) | 11 Mar 2026 | 800mm PW |  | Probing works for ERSS
Wed (11/03) | 11 Mar 2026 | P51 |  | East and west rebar installation
Wed (11/03) | 11 Mar 2026 | P47 |  | Utility support installation
Wed (11/03) | 11 Mar 2026 | P46 |  | No activity
Wed (11/03) | 11 Mar 2026 | P45 |  | No activity. Concrete curing
Wed (11/03) | 11 Mar 2026 | P1 crosshead |  | Section 2 and 3 formwork dismantled last night for east side
Wed (11/03) | 11 Mar 2026 | P39 |  | Falsework dismantling
Wed (11/03) | 11 Mar 2026 | P42 |  | Wet stitching formwork installation
Wed (11/03) | 11 Mar 2026 | P44 |  | Stressing cage modification for 2nd-3rd pair launching. Plan next week
Wed (11/03) | 11 Mar 2026 | P39 |  | Falsework dismantling
Wed (11/03) | 11 Mar 2026 | P42 |  | No activity
Wed (11/03) | 11 Mar 2026 | P44 |  | Stressing cage assembly ongoing
Wed (11/03) | 11 Mar 2026 | P47 |  | Utility support installation
Wed (11/03) | 11 Mar 2026 | P51 |  | East and west L3 caisson rebar work
Wed (11/03) | 11 Mar 2026 | 800mm PW |  | Probing for ERSS completed. Tonight expose utilities. Tomorrow start installation of soldier pile
Wed (11/03) | 11 Mar 2026 | P10 |  | No activity. Ready for tonight segment launching at 1:30am
Wed (11/03) | 11 Mar 2026 | P6 |  | Crosshead rebar installation
Wed (11/03) | 11 Mar 2026 | P1 |  | Tonight formwork dismantling
Wed (11/03) | 11 Mar 2026 | P18 |  | Installation of stitching formwork
Thu (12/03) | 12 Mar 2026 | B2-24, B2-22 dwall side | South | Drilling ongoing for RGT installation, PU grouting in progress, Working platform erection for PU grouting in progress
Thu (12/03) | 12 Mar 2026 | B2-22 | South side | Column C01-3 rebar planting in progress
Thu (12/03) | 12 Mar 2026 | B2-21 | North side | Post-drilling and preparing for PU grouting works, Column C01-3 working platform dismantling
Thu (12/03) | 12 Mar 2026 | B2-24, B2-23 |  | Bottom rebar installation in progress
Thu (12/03) | 12 Mar 2026 | B2-29 | North side | Column C01-6 formwork installation ongoing
Thu (12/03) | 12 Mar 2026 | B2-31 | North side | Skin wall surface cleaning ongoing
Thu (12/03) | 12 Mar 2026 | B2-35 | North side | PU grouting works ongoing
Thu (12/03) | 12 Mar 2026 | 800mm PW |  | Preparation for ERSS installation
Thu (12/03) | 12 Mar 2026 | DR4 |  | JGP works in progress
Thu (12/03) | 12 Mar 2026 | P51 |  | L3 caisson east and west formwork closing
Thu (12/03) | 12 Mar 2026 | P47 |  | Manual excavation for utility support
Thu (12/03) | 12 Mar 2026 | P45 |  | Formwork dismantling
Thu (12/03) | 12 Mar 2026 | P46 |  | Preparation work for concrete stump
Thu (12/03) | 12 Mar 2026 | Opening 9 |  | B2-39: Continue hacking dwall to COL and excavation in progress (2 exc, 1 telescopic, 1 mini)
Thu (12/03) | 12 Mar 2026 | P44 |  | Stressing cage modification for 2nd-3rd pair launching
Thu (12/03) | 12 Mar 2026 | P42 |  | Preparation for stressing work
Thu (12/03) | 12 Mar 2026 | P39 |  | Falsework dismantling
Thu (12/03) | 12 Mar 2026 | Soil mix ratio (1 |  | 1) inspection has conducted @ RTSA land stockpile
Thu (12/03) | 12 Mar 2026 | P10 |  | NBR-P10-D01 Segment launching work completed last night. Currently segment adjustment
Thu (12/03) | 12 Mar 2026 | P6 |  | Crosshead rebar installation work
Thu (12/03) | 12 Mar 2026 | P1 |  | Crosshead formwork removal completed last night. Currently working platform erection at both side for stressing work
Thu (12/03) | 12 Mar 2026 | Exit 1 stockpile |  | Continues soil internal shifting & disposal by 1 excavator
Thu (12/03) | 12 Mar 2026 | CCE Ramp / | GL31-29 | Excavation and soil internal shifting is in progress by 3 excavators
Thu (12/03) | 12 Mar 2026 | B2-23, B2-24 |  | Bottom rebar works in progress, PU grouting ongoing at B2-24, Column C01-3 (south side) rebar installation ongoing, B2-22: PU grouting in progress
Thu (12/03) | 12 Mar 2026 | B2-29 | North side | Column C01-6 formwork installation ongoing
Thu (12/03) | 12 Mar 2026 | B2-31 | North side | Skinwall kicker cast yesterday
Thu (12/03) | 12 Mar 2026 | B2-35, B2-37 | North side | PU grouting in progress
Thu (12/03) | 12 Mar 2026 | B2-39 |  | Excavation & disposal at Opening 9 in progress
Thu (12/03) | 12 Mar 2026 | DR4 |  | JGP work ongoing. Coring machine shifting to P45
Thu (12/03) | 12 Mar 2026 | 800mm PW |  | ERSS installation completed. Pending Annex C to start excavation
Thu (12/03) | 12 Mar 2026 | P51 |  | L3 caisson east and west formwork closing
Thu (12/03) | 12 Mar 2026 | P47 |  | Manual excavation for utility support works
Thu (12/03) | 12 Mar 2026 | P46 |  | Concrete stump preparation work
Thu (12/03) | 12 Mar 2026 | P46 |  | Concrete stump preparation work
Thu (12/03) | 12 Mar 2026 | P43 |  | Lifting frame installation ongoing
Thu (12/03) | 12 Mar 2026 | P39 |  | Falsework dismantling
Thu (12/03) | 12 Mar 2026 | P41 |  | Scaffolding erection ongoing
Fri (13/03) | 13 Mar 2026 | P39 |  | Falsework dismantling
Fri (13/03) | 13 Mar 2026 | P42 |  | Dismantling stitching formwork
Fri (13/03) | 13 Mar 2026 | P43 |  | Installation of lifting frame
Fri (13/03) | 13 Mar 2026 | P45 |  | Formwork dismantling completed
Fri (13/03) | 13 Mar 2026 | P46 |  | Preparation of concrete stump
Fri (13/03) | 13 Mar 2026 | P47 |  | Prism installation completed. Today MPI test for utility support
Fri (13/03) | 13 Mar 2026 | P51 |  | North side, S2 strut installation. South side, L3 caisson ready for casting today
Fri (13/03) | 13 Mar 2026 | 800mm PW |  | 1st layer manual excavation and S1 strut installation ongoing
Fri (13/03) | 13 Mar 2026 | CCE Ramp / | GL30-28 | Excavation and soil internal shifting is in progress by 3 excavators
Fri (13/03) | 13 Mar 2026 | Exit 1 stockpile |  | Continues soil internal shifting & disposal by 1 excavator
Fri (13/03) | 13 Mar 2026 | B2-22 | South side | PU grouting in progress, Column C01-3 rebar works ongoing
Fri (13/03) | 13 Mar 2026 | B2-23, B2-24 |  | Rebar works in progress, PU grouting in progress at B2-24
Fri (13/03) | 13 Mar 2026 | B2-32 | South side | PU grouting in progress
Fri (13/03) | 13 Mar 2026 | B2-35, B2-37 | North side | PU grouting in progress
Fri (13/03) | 13 Mar 2026 | 800mm PW |  | S1 waler preparation work
Fri (13/03) | 13 Mar 2026 | P51 |  | Final L3 caison casting at east and west side
Fri (13/03) | 13 Mar 2026 | P47 |  | Today going to do MPI test
Fri (13/03) | 13 Mar 2026 | P46 |  | Concrete stump preparation
Fri (13/03) | 13 Mar 2026 | P45 |  | No activity
Fri (13/03) | 13 Mar 2026 | P43 |  | Lifting frame installation ongoing
Fri (13/03) | 13 Mar 2026 | P40 |  | Crosshead side formwork installation
Fri (13/03) | 13 Mar 2026 | P39 |  | Falsework dismantling
Fri (13/03) | 13 Mar 2026 | P41 |  | Installing railing and netting
Fri (13/03) | 13 Mar 2026 | Vent shaft, B2-39 |  | Hacking ongoing to expose skin wall starter bars, Excavation in progress (2 exc, 1 telescopic)
Fri (13/03) | 13 Mar 2026 | P11 |  | NBR D01 segment adjustment
Fri (13/03) | 13 Mar 2026 | P6 |  | Tendon duct installation in progress
Fri (13/03) | 13 Mar 2026 | P1 |  | Strand pulling in progress
Fri (13/03) | 13 Mar 2026 | Blasting no.15 at B2-05 completed at 6 | S-1-1 | 26pm
Sat (14/03) | 14 Mar 2026 | P47 |  | Utility support
Sat (14/03) | 14 Mar 2026 | P46 |  | No activity
Sat (14/03) | 14 Mar 2026 | P45 |  | Waiting for pump truck, going to LSS backfill
Sat (14/03) | 14 Mar 2026 | P42 |  | 1st pair segment TPT stressing
Sat (14/03) | 14 Mar 2026 | P39 |  | Current falsework dismantling status
Sat (14/03) | 14 Mar 2026 | P40 |  | Crosshead formwork installation
Sat (14/03) | 14 Mar 2026 | P43 |  | Lifting frame installation
Sat (14/03) | 14 Mar 2026 | P11 |  | Segment adjustment. One lane closed
Sat (14/03) | 14 Mar 2026 | P6 |  | Cross head duct pipe installation and rebar laying work in progress
Sat (14/03) | 14 Mar 2026 | P1 |  | Strand cable pulling
Sat (14/03) | 14 Mar 2026 | 800mm PW |  | S1 strut installation
Sat (14/03) | 14 Mar 2026 | P51 |  | S2 strut installation at north, formwork dismantling at south
Sat (14/03) | 14 Mar 2026 | P47 |  | 2nd layer excavation started
Sat (14/03) | 14 Mar 2026 | P46 |  | LSS backfilling for stump footing
Sat (14/03) | 14 Mar 2026 | P45 |  | Ready for LSS backfilling after P46
Sat (14/03) | 14 Mar 2026 | P43 |  | Lifting frame installation
Sat (14/03) | 14 Mar 2026 | P42 |  | 1st pair segment tendon stressing
Sat (14/03) | 14 Mar 2026 | P40 |  | Crosshead formwork installation
Sat (14/03) | 14 Mar 2026 | P11 |  | Segment adjustment
Sat (14/03) | 14 Mar 2026 | P6 |  | Cross head duct pipe installation and rebar laying work in progress
Sat (14/03) | 14 Mar 2026 | P1 |  | Strand cable pulling
Sat (14/03) | 14 Mar 2026 | P51 |  | S2 strut installation at north, caisson formwork dismantling at south
Mon (16/03) | 16 Mar 2026 | P6 |  | PT duct installation, 40% completed
Mon (16/03) | 16 Mar 2026 | Blasting no.A2 completed at 3 |  | 54pm
Mon (16/03) | 16 Mar 2026 | P11 NBR 1st pair |  | Initial adjustment completed. Waiting YWL to confirm
Mon (16/03) | 16 Mar 2026 | 800mm PW |  | S2 strut installation
Mon (16/03) | 16 Mar 2026 | P51 |  | S2 strut installation
Mon (16/03) | 16 Mar 2026 | P47 |  | 2nd layer ongoing
Mon (16/03) | 16 Mar 2026 | P45 |  | LSS backfilling completed. No activity
Mon (16/03) | 16 Mar 2026 | P33 |  | 1st lift column rebar started
Mon (16/03) | 16 Mar 2026 | P38 |  | Crosshead falsework erection
Mon (16/03) | 16 Mar 2026 | P40 |  | Crosshead rebar installation
Mon (16/03) | 16 Mar 2026 | P42 |  | Dismantling of starter hanger
Mon (16/03) | 16 Mar 2026 | P43 |  | No activity
Mon (16/03) | 16 Mar 2026 | P45 |  | No activity
Mon (16/03) | 16 Mar 2026 | P46 |  | Concrete stump casted 6/7. Target to complete balance 1 no tomorrow
Mon (16/03) | 16 Mar 2026 | P47 |  | 2nd layer excavation
Mon (16/03) | 16 Mar 2026 | P51 |  | S2 strut installation ongoing
Mon (16/03) | 16 Mar 2026 | 800mm PW |  | S2 strut installation
Mon (16/03) | 16 Mar 2026 | P11 |  | No activity
Mon (16/03) | 16 Mar 2026 | P6 |  | Crosshead tendon duct installation
Mon (16/03) | 16 Mar 2026 | P1 |  | No activity
Tue (17/03) | 17 Mar 2026 | P41 |  | SH ready for 1st pair launching tonight
Tue (17/03) | 17 Mar 2026 | P40 crosshead |  | Bottom bar installation completed. Preparing for top bar installation
Tue (17/03) | 17 Mar 2026 | DR4 NB |  | GCE has done all JGP whichever can be done now. Preparing to shift materials and rig to P45 area
Tue (17/03) | 17 Mar 2026 | DR4 Zone 1 |  | Tidy up cable for S2 struts welding work
Tue (17/03) | 17 Mar 2026 | P45 |  | Tomorrow plan to start removal of utility support
Tue (17/03) | 17 Mar 2026 | P46 |  | Balance 1nos footing to cast today
Tue (17/03) | 17 Mar 2026 | P47 |  | Current status
Tue (17/03) | 17 Mar 2026 | P51 |  | Tomorrow to complete S2 Strut MPI test
Tue (17/03) | 17 Mar 2026 | CCE ramp / | GL30-28 | Continues excavation and internal shifting by 3 excavators
Tue (17/03) | 17 Mar 2026 | CCE ramp / | GL29-28 | Rock splitting is in progress
Tue (17/03) | 17 Mar 2026 | Vent shaft / B2-39 |  | Excavation & internal transfer by 3 excavator & 1 telescopic
Tue (17/03) | 17 Mar 2026 | Vent shaft / B2-39 |  | Hacking work in progress by 1 mini breaker
Tue (17/03) | 17 Mar 2026 | P34 |  | Scaffold erection for 1st lift column works
Tue (17/03) | 17 Mar 2026 | P29 |  | Column 2nd lift rebar works
Tue (17/03) | 17 Mar 2026 | B2-21 to B2-24 |  | Rebar work is in progress & target to cast by 23 Mar (Manpower - 23)
Tue (17/03) | 17 Mar 2026 | B2-33 & B2-35 |  | Drilling for tie rod formwork support is in progress
Tue (17/03) | 17 Mar 2026 | B2-35 |  | Formwork installation is in progress for column C02-2
Wed (18/03) | 18 Mar 2026 | DR4 Zone 1 |  | S2 waler MPI done. Now preparing for excavation for S3
Wed (18/03) | 18 Mar 2026 | P11 NBR 1st pair |  | 2nd adjustment in progress
Wed (18/03) | 18 Mar 2026 | CCE ramp / | GL30-28 | Continues excavation and internal shifting by 3 excavators
Wed (18/03) | 18 Mar 2026 | CCE ramp / | GL29-28 | Continues rock splitting work
Wed (18/03) | 18 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Wed (18/03) | 18 Mar 2026 | P6 |  | PT duct installation. Inspection for section 1 scheduled tmr
Wed (18/03) | 18 Mar 2026 | DR4 Changi bound |  | GCE clearing soil. Preparing to mobilize to TPE bound
Wed (18/03) | 18 Mar 2026 | P51 |  | Doing some balance welding for S2
Wed (18/03) | 18 Mar 2026 | P47 |  | Drain slab hacking
Wed (18/03) | 18 Mar 2026 | P47 |  | Preparing to provide protection for gas pipe
Wed (18/03) | 18 Mar 2026 | P46 |  | Currently no work
Wed (18/03) | 18 Mar 2026 | P45 |  | Backfilling to utility level
Wed (18/03) | 18 Mar 2026 | P43-44 |  | Stressing cage assembling
Wed (18/03) | 18 Mar 2026 | Vent Shaft / B2-39 |  | Erecting of working platforms for bracing work
Wed (18/03) | 18 Mar 2026 | Vent shaft / B2-39 |  | Continue hacking of Dwall, excavation & internal transfer by 1 mini breaker, 3 excavator s& 1 telescopic
Wed (18/03) | 18 Mar 2026 | P41 |  | Two numbers of segment at down chainage already installed. Tonight will be up chainage
Wed (18/03) | 18 Mar 2026 | P40 |  | Top rebar work for crosshead
Wed (18/03) | 18 Mar 2026 | P1 |  | 1st stage stressing completed yesterday. Today grouting cap installation only
Wed (18/03) | 18 Mar 2026 | P38 |  | Preparation for falsework erection
Wed (18/03) | 18 Mar 2026 | P34 |  | Today will start first lift rebar work
Wed (18/03) | 18 Mar 2026 | P33 |  | Preparing for 1st lift formwork closing. Tomorrow to cast
Wed (18/03) | 18 Mar 2026 | P29 |  | 2nd lift rebar work
Wed (18/03) | 18 Mar 2026 | Blasting no.17 completed at 3 |  | 18pm
Wed (18/03) | 18 Mar 2026 | P41 |  | Stressing cage installation
Wed (18/03) | 18 Mar 2026 | P40 |  | Crosshead rebar installation continue
Wed (18/03) | 18 Mar 2026 | P45 |  | Current status of backfilling
Wed (18/03) | 18 Mar 2026 | P46 |  | Last footing cast. Tomorrow balance main beam delivery
Wed (18/03) | 18 Mar 2026 | P47 |  | Protection provided for gas pipe
Wed (18/03) | 18 Mar 2026 | P47 |  | Current status of base slab hacking
Wed (18/03) | 18 Mar 2026 | P51 |  | MPI test done. Preparing for next layer excavation
Wed (18/03) | 18 Mar 2026 | DR4 Zone 1 |  | Excavation for S3 layer
Wed (18/03) | 18 Mar 2026 | P15-16 |  | LG materials shifting
Thu (19/03) | 19 Mar 2026 | 800mm PW |  | Preparing to install S3 waler
Thu (19/03) | 19 Mar 2026 | P51 |  | Preparation to start excavation to L4 caisson level
Thu (19/03) | 19 Mar 2026 | P47 |  | Continue hacking existing DR3
Thu (19/03) | 19 Mar 2026 | P46 |  | Waiting for main beam delivery, going to resume utility support installation today
Thu (19/03) | 19 Mar 2026 | P45 |  | No activity
Thu (19/03) | 19 Mar 2026 | B2-26 |  | Column C01-4 base cleaning ongoing
Thu (19/03) | 19 Mar 2026 | B2-21 to B2-24 |  | Continue rebar works and side formwork installation, Balance some M&E works and shearlinks installation, Plan for casting on Monday
Thu (19/03) | 19 Mar 2026 | B2-29 | North side | Preparing for PU grouting
Thu (19/03) | 19 Mar 2026 | B2-31 | North side | Skinwall formwork installed. Currently no activity
Thu (19/03) | 19 Mar 2026 | B2-33 | North side | Skin wall rebar works in progress
Thu (19/03) | 19 Mar 2026 | Vent shaft, B2-39 |  | Continue excavation, KP bracing installation in progress, Hacking dwall to expose skin wall starter bars ongoing
Thu (19/03) | 19 Mar 2026 | CCE ramp / | GL30-28 | Continues excavation and internal shifting by 2 excavators
Thu (19/03) | 19 Mar 2026 | CCE ramp / | GL29-28 | Rock splitting work by machine #1
Thu (19/03) | 19 Mar 2026 | P7 |  | Area preparation for pad footing works
Thu (19/03) | 19 Mar 2026 | P44 |  | Continue assembling of stressing cage
Thu (19/03) | 19 Mar 2026 | P41 |  | Segment adjustment
Thu (19/03) | 19 Mar 2026 | P40 |  | Continue side bar installation for crosshead
Thu (19/03) | 19 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Thu (19/03) | 19 Mar 2026 | P13 |  | Scaffold access erection started
Thu (19/03) | 19 Mar 2026 | P1 |  | Tonight to dismantle working platform at SB side
Thu (19/03) | 19 Mar 2026 | Zone 4 800mm water pipe |  | S3 layer installation in progress
Thu (19/03) | 19 Mar 2026 | P41 |  | Stressing cage for upchainage installed
Thu (19/03) | 19 Mar 2026 | P40 |  | Main bars installation completed. Steel anchor shifting in progress. To start installation tmr
Thu (19/03) | 19 Mar 2026 | P38 |  | Falsework erected until primary beam
Thu (19/03) | 19 Mar 2026 | P34 |  | 1st stage column formwork closed. To cast tmr
Thu (19/03) | 19 Mar 2026 | P29 |  | Column 2nd stage links installation
Fri (20/03) | 20 Mar 2026 | CCE ramp / | GL30-28 | Continues excavation and internal shifting by 2 excavators
Fri (20/03) | 20 Mar 2026 | CCE Ramp / | GL30-29 | Rock inspection arranged for these 2 rocks, machine ready to carry out coring & splitting afterward
Fri (20/03) | 20 Mar 2026 | CCE Ramp / | GL29-30 | Witnessed rock inspection with QPS rep
Fri (20/03) | 20 Mar 2026 | CCE Ramp / | North side, GL29-30 | Rock splitting sample collected for PLT
Fri (20/03) | 20 Mar 2026 | P45 |  | Utility support removal
Fri (20/03) | 20 Mar 2026 | P46 |  | Going to start utility support
Fri (20/03) | 20 Mar 2026 | P47 |  | Hacking existing DR3 base slab
Fri (20/03) | 20 Mar 2026 | P51 |  | Excavation to L4 caisson layer
Fri (20/03) | 20 Mar 2026 | 800mm PW |  | S3 strut installation in progress
Fri (20/03) | 20 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Fri (20/03) | 20 Mar 2026 | Vent Shaft / B2-39 |  | Levelling by 1 excavator, Exposing of couplers
Fri (20/03) | 20 Mar 2026 | Vent shaft / B2-39 |  | Continue hacking of Dwall & internal transfer by 1 mini breaker, 1 excavator & telescopic
Fri (20/03) | 20 Mar 2026 | B2-35 |  | Rebar installation in progress for skin wall
Fri (20/03) | 20 Mar 2026 | B2-21 to B2-24 |  | Top bar, Shearlinks & side formwork installation is in progress
Fri (20/03) | 20 Mar 2026 | P13 |  | Scaffold access erection. Tmr to start stump construction
Fri (20/03) | 20 Mar 2026 | DR4 |  | GCE checking sample and preparing to resume TT for JGP
Fri (20/03) | 20 Mar 2026 | DR4 Zone 1 |  | S3 layer installation. To complete today including welding
Fri (20/03) | 20 Mar 2026 | DR4 |  | Preparing to divert footpath
Fri (20/03) | 20 Mar 2026 | P11 no work |  | Waiting for stitching formwork materials
Fri (20/03) | 20 Mar 2026 | P10 coring |  | 1/2 in progress. 1st coring 1.5/3m done
Fri (20/03) | 20 Mar 2026 | P6 crosshead |  | PT duct inspection, SB to center
Fri (20/03) | 20 Mar 2026 | P1 |  | Working platform dismantling
Mon (23/03) | 23 Mar 2026 | DR4 Zone 1 |  | Last layer waler and strut welding. This week can lay the balance water pipe
Mon (23/03) | 23 Mar 2026 | P51 |  | Tomorrow HSL will mobilize for hacking at NB. KTC continue excavation at SB
Mon (23/03) | 23 Mar 2026 | P47 |  | Current status of drain hacking
Mon (23/03) | 23 Mar 2026 | P46 |  | LE continue prepating main beam for installation
Mon (23/03) | 23 Mar 2026 | P51 |  | GCE TT for JGP testing. Stump cast
Mon (23/03) | 23 Mar 2026 | P44 |  | All the 4nos stressing cages assembling done
Mon (23/03) | 23 Mar 2026 | P42 |  | Assembling of LCB can complete by Wednesday and Thursday
Mon (23/03) | 23 Mar 2026 | P39 |  | Continue platform installation
Mon (23/03) | 23 Mar 2026 | P34 |  | Falsework erected for 1st lift
Mon (23/03) | 23 Mar 2026 | P39 |  | WH installation of RWDP and P38: 2nd lift rebar work
Tue (24/03) | 24 Mar 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Tue (24/03) | 24 Mar 2026 | CCE Ramp / | GL E6-E8 | *CD3* - Rock splitting is in progress
Tue (24/03) | 24 Mar 2026 | CCE ramp / | GL29-27 | Continues excavation and internal shifting by 3 excavators
Tue (24/03) | 24 Mar 2026 | CCE Ramp / | GL30-29 | *CD2* - Rock splitting is in progress
Tue (24/03) | 24 Mar 2026 | CCE Ramp / | GL28-30 | Witnessed rock (14 Numbers) inspection with QPS rep
Tue (24/03) | 24 Mar 2026 | DR4 |  | MPI test for last layer done. Preparing to resume excavation. This week can complete balance pipe laying
Tue (24/03) | 24 Mar 2026 | DR4 |  | TT for pipe sleeves installation. Found LV
Tue (24/03) | 24 Mar 2026 | B2-33 | North side | Skinwall kicker formwork installation in progress
Tue (24/03) | 24 Mar 2026 | B2-36 | North side | Column C02-2 rebar installation in progress
Tue (24/03) | 24 Mar 2026 | Opening 9 |  | Soil clearing and internal shifting to exit 3 stockpile
Tue (24/03) | 24 Mar 2026 | Vent shaft/ B2-39 |  | Dwall hacking to COL (2 mini), Coupler exposing ongoing & drilling ongoing for PU grouting works
Tue (24/03) | 24 Mar 2026 | P51 |  | Mini lowered down for BP hacking at NB and continue excavation at SB
Tue (24/03) | 24 Mar 2026 | P47 |  | Drain hacking done around 30%
Tue (24/03) | 24 Mar 2026 | P45 |  | LSS backfilling for water pipe support removal
Tue (24/03) | 24 Mar 2026 | P46 |  | Utility support base plate installation
Tue (24/03) | 24 Mar 2026 | B1-11 | part 2 | Waterproofing membrane laying in progress. Tmr plan to start rebar works
Tue (24/03) | 24 Mar 2026 | P13 |  | Concrete block fabrication for FBCM set up
Tue (24/03) | 24 Mar 2026 | P13 |  | Stump preparation for formwork closing
Tue (24/03) | 24 Mar 2026 | P44 NB down chaingage |  | One segment installed. Tonight to install at live road side
Tue (24/03) | 24 Mar 2026 | P41 |  | Today can complete this LCB assembling. Tomorrow can install
Tue (24/03) | 24 Mar 2026 | P39 |  | Continue access erection and working platform for crosshead
Tue (24/03) | 24 Mar 2026 | CCW | GLW6-W8/A-B | Blasting completed at 5:25pm
Tue (24/03) | 24 Mar 2026 | B1-01 |  | Skinwall rebar works in progress
Tue (24/03) | 24 Mar 2026 | GL W6 |  | Drilling ongoing for next blasting works
Tue (24/03) | 24 Mar 2026 | B2-04, B2-05 |  | Rebar works in progress (CGW day manpower: 26, night: 12), Pipe installation in progress by APP
Tue (24/03) | 24 Mar 2026 | B2-08 to B2-10 |  | Excavation and hacking works in progress, Levelling ongoing at B2-08, B2-09. Tonight plan for lean con casting
Tue (24/03) | 24 Mar 2026 | B1-05 |  | Skinwall formwork installation in progress
Tue (24/03) | 24 Mar 2026 | B1-11 part 2 |  | RGT installation in progress. Tmr plan to start rebar works at this section, WH continue cleaning works at the bottom area and plan to continue waterproofing membrane laying tmr
Tue (24/03) | 24 Mar 2026 | B2-21 to B2-35 |  | Currently no activity
Tue (24/03) | 24 Mar 2026 | B2-36 | South side | Column C02-2 rebar works in progress
Tue (24/03) | 24 Mar 2026 | Opening 9 |  | Currently no activity. Area has been levelled
Tue (24/03) | 24 Mar 2026 | B2-39 |  | Continue hacking dwall to COL
Tue (24/03) | 24 Mar 2026 | P51 |  | No activity
Tue (24/03) | 24 Mar 2026 | P47 |  | Excavation on going
Tue (24/03) | 24 Mar 2026 | P46 |  | No activity
Tue (24/03) | 24 Mar 2026 | P45 |  | Backfilling works ongoing
Tue (24/03) | 24 Mar 2026 | CCE Ramp/GL E6-E8 |  | Rock splitting in progress till 10pm
Tue (24/03) | 24 Mar 2026 | CCE Ramp/GL30-29 |  | Rock splitting in progress till 10pm
Tue (24/03) | 24 Mar 2026 | CCE ramp/GL29-27 |  | Continue excavation and internal shifting (3 exc)
Tue (24/03) | 24 Mar 2026 | P40 |  | No activity
Tue (24/03) | 24 Mar 2026 | P38 |  | No activity
Tue (24/03) | 24 Mar 2026 | P11 |  | No activity
Tue (24/03) | 24 Mar 2026 | P10 |  | No activity
Tue (24/03) | 24 Mar 2026 | P7 |  | No activity
Tue (24/03) | 24 Mar 2026 | P6 |  | No activity
Tue (24/03) | 24 Mar 2026 | P1 |  | Falsework dismantling ongoing
Wed (25/03) | 25 Mar 2026 | B2-39 |  | Hacking of overcast dwal. No other activity
Wed (25/03) | 25 Mar 2026 | P47 |  | Continue hacking existing DR3
Wed (25/03) | 25 Mar 2026 | P46 |  | Utility support installation
Wed (25/03) | 25 Mar 2026 | P45 |  | GCE trial trench for JGP testing
Wed (25/03) | 25 Mar 2026 | P44 |  | Segment launching completed last night. Now cable pushing at downchainage side
Wed (25/03) | 25 Mar 2026 | B2-04 to B2-07 |  | Rebar installation is in progress & target to cast by end of the month
Wed (25/03) | 25 Mar 2026 | B2-39 |  | Will continue to hack the Dwall by 1 breaker
Wed (25/03) | 25 Mar 2026 | B2-39 |  | Continues exposing of couplers
Wed (25/03) | 25 Mar 2026 | CCE / | GL E6-E8 | *CD3 * - Continue rock splitting
Wed (25/03) | 25 Mar 2026 | CCE Ramp/ | GL29-27 | Continue excavation & internal transfer by 3 excavators
Wed (25/03) | 25 Mar 2026 | Exit 1 stockpile |  | Continues internal transfer & soil disposal by 1 excavator
Wed (25/03) | 25 Mar 2026 | CCW2 |  | 2nd blasting (blast no. 19& 20) for this week completed today at around 4pm
Wed (25/03) | 25 Mar 2026 | CCW1 NB |  | Rock fragment disposal until 10pm only. Nightshift is arrange from tmr
Wed (25/03) | 25 Mar 2026 | S1-1 |  | Concourse, B2-04 & 05: rebar works in progress. 60% completed, B2-06 & 07: rebar installation completed, All 4 panels still target to cast by end of this month, CGW manpower:, Nightshift: 18 pax
Wed (25/03) | 25 Mar 2026 | P28 column 2nd lift |  | Rebar installation for nightshift
Wed (25/03) | 25 Mar 2026 | P29 column 2nd lift |  | Formwork closing no activity for nightshift. 1 face completed
Wed (25/03) | 25 Mar 2026 | P34 |  | Column 1st lift main bar installation completed. No activity for nightshift
Wed (25/03) | 25 Mar 2026 | 800mm PW |  | Manual excavation to FEL
Wed (25/03) | 25 Mar 2026 | P51 |  | Preparation to start excavation work
Thu (26/03) | 26 Mar 2026 | P28 |  | 2nd lift rebar works in progress, P29: 2nd lift formwork installation in progress
Thu (26/03) | 26 Mar 2026 | B1-11 part 2 |  | PU grouting in progress, Bottom rebar installation ongoing, GL15-16: CJ roughening & exposing couplers
Thu (26/03) | 26 Mar 2026 | Opening 7 |  | B2-17 to B2-20: Excavation in progress (3 exc, 1 telescopic)
Thu (26/03) | 26 Mar 2026 | B2-25, B2-26 |  | Columns C01-4 formwork installation in progress
Thu (26/03) | 26 Mar 2026 | B2-27 | North side | Preparation for PU grouting ongoing
Thu (26/03) | 26 Mar 2026 | B2-31 | GL26-28 | Wall rebar works in progress
Thu (26/03) | 26 Mar 2026 | Vent shaft/B2-39 |  | Continue hacking overcast dwall, Hacking ongoing at drop area, CJ roughening and exposing couplers, Post-drilling works ongoing
Thu (26/03) | 26 Mar 2026 | Exit 1 stockpile |  | Continue internal transfer & soil disposal
Thu (26/03) | 26 Mar 2026 | CCE | GL E6-E8 | Continue rock coring and splitting
Thu (26/03) | 26 Mar 2026 | CCE | GL30-29 | Continue rock coring and splitting
Thu (26/03) | 26 Mar 2026 | CCE Ramp | GL29-27 | Continue excavation & internal transfer
Thu (26/03) | 26 Mar 2026 | CCW2 |  | Drilling of blast holes completed for the day, 80/80 holes. Tmr to prepare area for blasting
Thu (26/03) | 26 Mar 2026 | B2-08 |  | Continue levelling works for balance area. Tmr to cast lean con together with B2-10 & B2-11, Debonding sheet and plywood laying at column areas
Thu (26/03) | 26 Mar 2026 | B2-10, B2-11 |  | Continue excavation works and levelling. Tmr to cast lean con
Thu (26/03) | 26 Mar 2026 | B2-04 to B2-07 |  | Continue rebar works at slab areas, P24 downhang wall, Preparing corrugated pipes
Thu (26/03) | 26 Mar 2026 | B1-01 |  | Skin wall rebar works in progress
Thu (26/03) | 26 Mar 2026 | B1-05, B1-06 |  | Skin wall cast yesterday
Thu (26/03) | 26 Mar 2026 | B1-08 |  | Partial skin wall formwork installation ongoing
Thu (26/03) | 26 Mar 2026 | Opening 3A |  | Excavation and disposal works ongoing
Thu (26/03) | 26 Mar 2026 | B1-11 | Part 2 | Bottom rebar works in progress. No nightshift plan here currently as manpower focusing at B2-04, B2-05 area. Dayshift working till 930pm, GL15-16: Continue exposing couplers
Thu (26/03) | 26 Mar 2026 | B2-33 |  | Skin wall kicker casting ongoing
Thu (26/03) | 26 Mar 2026 | Opening 7 |  | B2-17 to B2-20: Night shift continue excavation
Thu (26/03) | 26 Mar 2026 | B2-31 | GL26-28 | Wall rebar works currently no activity
Thu (26/03) | 26 Mar 2026 | B2-32/34/36 | South side | Working platform erection ongoing
Thu (26/03) | 26 Mar 2026 | B2-39 |  | Continue hacking overcast dwall. Currently no other activity
Thu (26/03) | 26 Mar 2026 | P44 |  | Segment launching for NB-D3. Tonight to continue launching facing road side
Thu (26/03) | 26 Mar 2026 | CCE | GL E6-E8 | Hacking of split rocks. Coring machine shifting to next location
Thu (26/03) | 26 Mar 2026 | CCE | GL30-29 | Continue rock coring and splitting. Works till 10pm
Thu (26/03) | 26 Mar 2026 | CCE Ramp | GL29-27 | Continue excavation & internal transfer
Thu (26/03) | 26 Mar 2026 | B1-01 |  | Working platform erection for next section of skin wall rebar works, North side: Pending skin wall rebar inspection
Thu (26/03) | 26 Mar 2026 | Opening 3 |  | B2-04, B2-05:, Rebars and pipes installation in progress, B2-06, B2-07:, Corrugated pipes and shearlinks installation ongoing, Plan to cast these 4 slabs by next Mon/Tues
Thu (26/03) | 26 Mar 2026 | B2-03 |  | Continue clearing soil and hacking ongoing to expose skin wall starter bars
Thu (26/03) | 26 Mar 2026 | Opening 3A |  | B2-08, B2-09: Lean concrete cast. Currently no activity, B2-10, B2-11: Excavation, levelling and hacking works in progress
Fri (27/03) | 27 Mar 2026 | CCE | GL E6-E8 | Hacking of split rocks done & preparing for disposal
Fri (27/03) | 27 Mar 2026 | CCE | GL30-29 | Continue rock coring and splitting — 2 machines here
Fri (27/03) | 27 Mar 2026 | Zone 4 |  | Tonight to continue welding works for 800mm water pipe only. Balance around 6m to lay
Fri (27/03) | 27 Mar 2026 | Vent shaft/ B2-39 |  | Post-drilling ongoing, Continue exposing couplers, Start to lay waterproofing membrane, Continue hacking overcast dwall. Try to complete hacking today
Fri (27/03) | 27 Mar 2026 | B2-36 | South side | Column C02-2 formwork installation ongoing, Straightening of bottom skin wall starter bars
Fri (27/03) | 27 Mar 2026 | B2-34 | South side | Dongah continue PU grouting
Fri (27/03) | 27 Mar 2026 | Along B2-31, B2-33 area |  | Wendyng continue bottom surface roughening for wall rebar works, rebar straightening and cleaning ongoing
Fri (27/03) | 27 Mar 2026 | GL22 | South side | Dongah continue PU grouting
Fri (27/03) | 27 Mar 2026 | CCW2 blasting #21 completed at 5 |  | 18pm
Fri (27/03) | 27 Mar 2026 | Zone 1 |  | Shifting of 100T crane for tonight's PB dismantling work. Noise ballon to be Progressively set up
Fri (27/03) | 27 Mar 2026 | S1-1 |  | B2-05 & 05, rebar installation continue, 15 pax for nightshift
Fri (27/03) | 27 Mar 2026 | CCW2 |  | Rock fragment disposal for nightshift
Fri (27/03) | 27 Mar 2026 | B2-08 |  | Preparation for lean concrete. Tonight to complete
Fri (27/03) | 27 Mar 2026 | B2-10 & 11 |  | Partial lean concrete tonight
Fri (27/03) | 27 Mar 2026 | B2-12 &13 |  | Excavation continue tonight thru opening 3A
Fri (27/03) | 27 Mar 2026 | B1-11 part 2 |  | No more activity for rebar works. Focuse at Concourse level
Fri (27/03) | 27 Mar 2026 | S2-2 |  | Excavation and internal soil disposal continue for nightshift. 2 excavator
Fri (27/03) | 27 Mar 2026 | P38 |  | 1 side formwork closing
Fri (27/03) | 27 Mar 2026 | P44 NB |  | Stressing cage dismantling, P44 SB D03 launching completed. Tonight to launch SB U03 after last bus
Sat (28/03) | 28 Mar 2026 | B2-04, B2-05 |  | Partial bottom formwork installation in progress at downhang wall, Top bar installation ongoing at B2-04, Shearlinks installation at B2-05, Manpower: 36
Sat (28/03) | 28 Mar 2026 | B2-09 |  | Coupler exposing ongoing
Sat (28/03) | 28 Mar 2026 | B2-11/13 |  | Dwall surface hacking to expose skin wall starter bars
Sat (28/03) | 28 Mar 2026 | B2-10, B2-11 |  | Partial lean concrete cast last night. Now onging surveyor marking
Sat (28/03) | 28 Mar 2026 | B2-09 | South side | Column C03-1 soffit roughening ongoing
Sat (28/03) | 28 Mar 2026 | Opening 3A |  | B2-12, B2-13 (GL8-10): Excavation and disposal ongoing (3 exc, 1 telescopic)
Sat (28/03) | 28 Mar 2026 | B1-06, B1-08 |  | Skin wall formwork support installation ongoing. Plan for casting today
Sat (28/03) | 28 Mar 2026 | B1-11 part 2 |  | GL15-16: Surveyor marking ongoing, Dongah preparing for PU grouting and post-drilling works, Today plan to continue laying waterproofing membrane, APP preparing drainage pipes
Sat (28/03) | 28 Mar 2026 | CCE | GL-E6 | Rocks cleared. Area plan to use for access erection
Sat (28/03) | 28 Mar 2026 | CCE | GL30-29 | Continue rock coring and splitting works, 2 machines
Sat (28/03) | 28 Mar 2026 | CCE ramp | GL28-26 | Continue excavation and internal shifting
Sat (28/03) | 28 Mar 2026 | Vent shaft/ B2-39 |  | Continue waterproofing membrane laying, PU grouting ongoing, Hacking dwall to COL ongoing
Sat (28/03) | 28 Mar 2026 | B2-36 | south side | Column C02-2 plan for casting today
Sat (28/03) | 28 Mar 2026 | Concourse | GL26-28 | RC wall rebar and formwork installation
Sat (28/03) | 28 Mar 2026 | Concourse | GL22 | PU grouting in progress
Sat (28/03) | 28 Mar 2026 | B2-25, B2-26 |  | Columns C01-4 plan for casting today
Sat (28/03) | 28 Mar 2026 | B2-19 | North side | Dwall surface hacking to expose skin wall starter bars, *Opening 7*, B2-17, B2-18: Excavation in progress (3 exc, 1 telescopic), B2-20 (South side): Dwall surface hacking to expose skin wall starter bars
Sat (28/03) | 28 Mar 2026 | CCW2 |  | KTC clearing blasted rocks. Blasting #21 was done yesterday afternoon, ATC preparing drilling rigs before continuing for next blast hole drilling works. Next planned blasting (#22) scheduled for Monday
Sat (28/03) | 28 Mar 2026 | CCW1 North |  | KTC continue excavation and rock fragments disposal works. Next blasting (#23) planned for next week
Sat (28/03) | 28 Mar 2026 | Exit 3 |  | No activity. Manpower focusing at concourse area
Mon (30/03) | 30 Mar 2026 | P6 |  | Crosshead casting start
Mon (30/03) | 30 Mar 2026 | N6 |  | Abutment wall formwork closing
Mon (30/03) | 30 Mar 2026 | P11 |  | 1st pair stitching formwork closing
Mon (30/03) | 30 Mar 2026 | CCW1 | North side | Continue excavation and disposal below S5 prior to blasting works here (2 excavators). Blasting #23 planned here this week, Continue rock fragments disposal (1 exc), Night shift to continue
Mon (30/03) | 30 Mar 2026 | CCW2 |  | Drilling for blasting holes completed for the day, 72/72nos & relief holes 18/18nos. Tmr to expedite blasting #22
Mon (30/03) | 30 Mar 2026 | B2-04 to B2-07 & P24 downhang wall |  | Formwork installation & inspection ongoing at downhang wall area, Shearlinks installation, Plan for casting tmr, Manpower: 50 (Day), 17 (Night)
Mon (30/03) | 30 Mar 2026 | B2-08 to B2-11 |  | Lean con casting for drop areas at B2-08 & B2-09, Continue disposal and levelling works at B2-10 & B2-11. Tmr plan to cast lean con for balance areas, KTC to continue night shift here
Mon (30/03) | 30 Mar 2026 | Exit 3 skinwall area |  | No activity currently
Mon (30/03) | 30 Mar 2026 | Opening 3A |  | Continue excavation and disposal works. Currently observed excavation at north side is between GL10-11
Mon (30/03) | 30 Mar 2026 | Opening 7 |  | B2-17, B2-18: Nightshift continue excavation & disposal works, B2-20, B2-18 (South side): Hacking ongoing to expose skin wall starter bars
Mon (30/03) | 30 Mar 2026 | B2-25, B2-26 |  | Columns C01-4 cast last Saturday
Mon (30/03) | 30 Mar 2026 | B2-31 skinwall |  | Formwork removal. Currently no activity
Mon (30/03) | 30 Mar 2026 | B2-31, B2-33 | GL26-28 North side | Exit staircase corridor partial formwork installation, Tonight to continue RC wall rebar works along B2-33
Mon (30/03) | 30 Mar 2026 | Vent shaft/ B2-39 |  | Dwall hacking to COL. Now levelling ongoing and preparing for base lean con casting at B2-39, Access erection ongoing at VS area
Mon (30/03) | 30 Mar 2026 | P51 |  | North side working platform lean con casting completed..currently making access scaffolding
Mon (30/03) | 30 Mar 2026 | P47 |  | Existing DR3 hacking works
Mon (30/03) | 30 Mar 2026 | P46 |  | No activity
Mon (30/03) | 30 Mar 2026 | P45 |  | No activity
Mon (30/03) | 30 Mar 2026 | P41 |  | No activity
Mon (30/03) | 30 Mar 2026 | P40 |  | No activity
Mon (30/03) | 30 Mar 2026 | CCE ramp | GL26 | Excavation and internal shifting in progress
Mon (30/03) | 30 Mar 2026 | P44 |  | Dismantling stressing cage
Mon (30/03) | 30 Mar 2026 | CCE | GL30-29 | Rock coring and splitting in progress till 10pm — 3 machines
Mon (30/03) | 30 Mar 2026 | P38 |  | Preparation for crosshead rebar works
Mon (30/03) | 30 Mar 2026 | P34 |  | 1st lift column casting completed
Mon (30/03) | 30 Mar 2026 | P29 |  | 2nd lifter column casting completed
Mon (30/03) | 30 Mar 2026 | P28 |  | No activity
Mon (30/03) | 30 Mar 2026 | P7 |  | Crosshead falsework installation
Tue (31/03) | 31 Mar 2026 | CCE Ramp/ | GL27-25 | Continue excavation & internal transfer by 3 excavators
Tue (31/03) | 31 Mar 2026 | CCE Ramp / | GL30-28 | Rock splitting is in progress by *CD2*
Tue (31/03) | 31 Mar 2026 | CCE Ramp / | GL30-28 | Rock coring is in progress by *CD4*
Tue (31/03) | 31 Mar 2026 | P41 |  | Wet stitching formwork closing
Tue (31/03) | 31 Mar 2026 | P44-43 |  | Ground levelling started for main truss assembly
Tue (31/03) | 31 Mar 2026 | B2-39 |  | Exposing couplers and CJ roughening at B2-38 area
Tue (31/03) | 31 Mar 2026 | B2-37 |  | Preparing to start skin wall rebar works
Tue (31/03) | 31 Mar 2026 | GL26-30 | North side | Continue wall rebar works for exit staircase corridor
Tue (31/03) | 31 Mar 2026 | B2-35 |  | Skin wall rebar works in progress
Tue (31/03) | 31 Mar 2026 | B2-33 |  | Scaffold dismantling ongoing prior to shifting the skin wall formwork here
Tue (31/03) | 31 Mar 2026 | Exit 1 stockpile |  | Continues internal transfer & soil disposal by 1 excavator
Tue (31/03) | 31 Mar 2026 | P28 |  | No activity
Tue (31/03) | 31 Mar 2026 | P38 |  | No activity
Tue (31/03) | 31 Mar 2026 | CCW1 North |  | Continue disposal works. ATC drilling rigs have shifted at North side
Tue (31/03) | 31 Mar 2026 | CCW2 |  | Blasting #22 completed this afternoon. Rigs shifted to CCW1 North
Tue (31/03) | 31 Mar 2026 | P40 |  | PT duct installation in progress
Tue (31/03) | 31 Mar 2026 | P41 |  | No activity
Tue (31/03) | 31 Mar 2026 | P44 |  | Housekeeping and material clearance
Tue (31/03) | 31 Mar 2026 | P43-P44 |  | Current ground levelling status.. platform preparation for LG assembly
Tue (31/03) | 31 Mar 2026 | P45 |  | Completed 1 no compaction grouting. Now no activity
Tue (31/03) | 31 Mar 2026 | P46 |  | Utility support installation in progress
Tue (31/03) | 31 Mar 2026 | B2-10, B2-11 |  | Base lean con casting in progress. Opening 3A currently using for pump hose
Tue (31/03) | 31 Mar 2026 | B2-08, B2-09 |  | Currently no activity
Tue (31/03) | 31 Mar 2026 | B2-04 to B2-07 |  | Tying works, downhang wall formwork support installation. Final inspection at 8pm
Tue (31/03) | 31 Mar 2026 | Exit 3 |  | No activity
Tue (31/03) | 31 Mar 2026 | DR3 |  | Benching work status..now no activity
Tue (31/03) | 31 Mar 2026 | P47 |  | Existing DR3 drain hacking status
Tue (31/03) | 31 Mar 2026 | P51 |  | L4 caisson rebar work start
Tue (31/03) | 31 Mar 2026 | 800mm PW |  | Preparation work for access manhole chamber installation
Tue (31/03) | 31 Mar 2026 | Opening 7 |  | B2-19, B2-20: Tmr to cast lean con. WH continue hacking to expose skin wall starter bars
Tue (31/03) | 31 Mar 2026 | P11 |  | Shifting LG material to P43-P44 for assembly
Tue (31/03) | 31 Mar 2026 | P10 |  | Tendon duct hacking work in progress
Tue (31/03) | 31 Mar 2026 | P7 |  | Crosshead falsework installation
Tue (31/03) | 31 Mar 2026 | P6 |  | Concrete curing
Tue (31/03) | 31 Mar 2026 | P1 |  | Falsework dismantling in progress
Tue (31/03) | 31 Mar 2026 | CCE | GL27 | WH exposing rock surface. Tmr plan for 20T excavator mobilisation to facilitate the hacking works here
Tue (31/03) | 31 Mar 2026 | CCE ramp | GL26 | Continue excavation and internal shifting
Tue (31/03) | 31 Mar 2026 | CCE | GL29-30 | Continue boulder coring and splitting works till 10pm (3 machines)
Wed (01/04) | 01 Apr 2026 | B1-11 part 2 |  | Continue bottom rebar installation, Waterproofing membrane works, Surveying ongoing
Wed (01/04) | 01 Apr 2026 | B2-31 skin wall |  | Formwork dismantled & shifting to B2-33 skin wall area
Wed (01/04) | 01 Apr 2026 | B2-33, B2-35, B2-37 | North side | Skin wall rebar works in progress
Wed (01/04) | 01 Apr 2026 | P13 |  | Concrete block completed for FBCM
Wed (01/04) | 01 Apr 2026 | P11 |  | 1st pair wet stitch cast last night
Wed (01/04) | 01 Apr 2026 | B2-39 |  | Bottom rebar planting in progress, Today plan to lean con at balance dwall area
Wed (01/04) | 01 Apr 2026 | P7 |  | Falsework leg frame installation
Wed (01/04) | 01 Apr 2026 | CCE Ramp / | GL27-28 | Witnessed rock (4 numbers) inspection with QPS rep
Wed (01/04) | 01 Apr 2026 | CCE Ramp/ | GL27-25 | Continue excavation & internal transfer by 2 excavators
Wed (01/04) | 01 Apr 2026 | CCE Ramp / | GL30-28 | Rock coring is in progress by 3 machines *CD2/CD3/CD4*
Wed (01/04) | 01 Apr 2026 | CCE Ramp/ | GL30-28 | Rock disposal by 1 excavator
Wed (01/04) | 01 Apr 2026 | 800mm PW |  | Preparation for chamber installation
Wed (01/04) | 01 Apr 2026 | DR4 |  | JGP trial trench ongoing
Wed (01/04) | 01 Apr 2026 | P51 |  | Preparation for formwork closing at north side, continue bored pile hacking at south side
Wed (01/04) | 01 Apr 2026 | P47 |  | Hacking existing DR3
Wed (01/04) | 01 Apr 2026 | DR3 |  | Benching work formwork installation
Wed (01/04) | 01 Apr 2026 | P46 |  | Utility support installation
Wed (01/04) | 01 Apr 2026 | P45 |  | Preparation for compaction grouting
Wed (01/04) | 01 Apr 2026 | Exit 1 stockpile |  | Continues internal transfer & soil disposal by 1 excavator
Wed (01/04) | 01 Apr 2026 | B1-01 |  | Straightening of skin wall starter bars & surveyor works ongoing
Wed (01/04) | 01 Apr 2026 | B1-02 |  | RGT installation ongoing
Wed (01/04) | 01 Apr 2026 | 800mm PW |  | Chamber installation ongoing
Wed (01/04) | 01 Apr 2026 | P51 |  | Preparation for formwork closing at north side, bored pile hacking at south side
Wed (01/04) | 01 Apr 2026 | P47 |  | Hacking existing DR3
Wed (01/04) | 01 Apr 2026 | P45 |  | Compaction grouting in progress
Wed (01/04) | 01 Apr 2026 | P46 |  | Utility support welding works ongoing
Wed (01/04) | 01 Apr 2026 | P45 |  | Quarry dust backfilling at north side
Wed (01/04) | 01 Apr 2026 | Opening 3A |  | B2-12 to B2-15: Excavation in progress (4 exc, 1 telescopic)
Wed (01/04) | 01 Apr 2026 | B1-11 part 2 |  | Bottom rebar installation in progress (CGW manpower: 9)
Wed (01/04) | 01 Apr 2026 | P33 |  | Column rebar installation work
Wed (01/04) | 01 Apr 2026 | P38 |  | No activity
Wed (01/04) | 01 Apr 2026 | P40 |  | Tendon duct installation status
Wed (01/04) | 01 Apr 2026 | P41 |  | No activity
Wed (01/04) | 01 Apr 2026 | P42-P43 |  | Current ground levelling status
Wed (01/04) | 01 Apr 2026 | P44 |  | Stressing cage dismantle completed
Wed (01/04) | 01 Apr 2026 | P45 |  | Compaction grouting completed
Wed (01/04) | 01 Apr 2026 | P45 |  | Utility support removal status at north side
Wed (01/04) | 01 Apr 2026 | P46 |  | No activity
Wed (01/04) | 01 Apr 2026 | P51 |  | No activity
Wed (01/04) | 01 Apr 2026 | P47 |  | No activity
Wed (01/04) | 01 Apr 2026 | CCW1 North |  | ATC drilling works done for the day. Tmr plan for blasting #23
Wed (01/04) | 01 Apr 2026 | CCW1 South |  | No activity
Wed (01/04) | 01 Apr 2026 | B1-05, B1-06, B1-08 |  | Skin wall formwork removal
Wed (01/04) | 01 Apr 2026 | Opening 3A |  | B2-12 to B2-15: Excavation in progress
Wed (01/04) | 01 Apr 2026 | P10 |  | Tendon duct hacking work in progress
Wed (01/04) | 01 Apr 2026 | P11 |  | No activity
Wed (01/04) | 01 Apr 2026 | P7 |  | Crosshead falsework installation
Wed (01/04) | 01 Apr 2026 | B1-11 part 2 |  | Bottom rebar works in progress
Wed (01/04) | 01 Apr 2026 | B2-17 to B2-20 |  | Preparing for lean con casting
Wed (01/04) | 01 Apr 2026 | Opening 7 |  | Access erection in progress
Wed (01/04) | 01 Apr 2026 | Station B2 area |  | Currently no activity for exit staircase wall & double slab rebar and skinwall
Wed (01/04) | 01 Apr 2026 | B2-39 |  | Dwall hacking ongoing at this last portion (near B2-36), Wendyng night team continue bottom rebar works
Wed (01/04) | 01 Apr 2026 | P1 |  | No activity
Wed (01/04) | 01 Apr 2026 | CCE ramp | GL27-25 | Excavation and internal transfer in progress
Wed (01/04) | 01 Apr 2026 | CCE ramp | GL27-28 | Rock surface hacking ongoing
Wed (01/04) | 01 Apr 2026 | CCE | GL30-28 | Coring and splitting works ongoing till 10pm (3 machines)
Thu (02/04) | 02 Apr 2026 | P18 |  | Scaffold erection for stage 2 Crosshead stressing
Thu (02/04) | 02 Apr 2026 | P11 |  | Material shifting ongoing
Thu (02/04) | 02 Apr 2026 | P10 |  | Tendon duct hacking rectification works
Thu (02/04) | 02 Apr 2026 | P7 |  | Pad footing and Falsework installation
Thu (02/04) | 02 Apr 2026 | P46 & P49 |  | SPPG cable spiking works ongoing
Thu (02/04) | 02 Apr 2026 | P1 |  | Falsework material shifting
Thu (02/04) | 02 Apr 2026 | B2-17 to B2-20 |  | Lean con was cast at KPs area and skinwall side, Excavation in progress at breakthrough area
Thu (02/04) | 02 Apr 2026 | CCE Ramp/ | GL27-25 | Continue excavation & internal transfer by 2 excavators & 1 breaker activated today
Thu (02/04) | 02 Apr 2026 | CCE Ramp / | GL30-28 | Rock coring/splitting is in progress by 3 machines *CD2/CD3/CD4*
Thu (02/04) | 02 Apr 2026 | CCE Ramp/ | GL30-28 | Continue rock disposal by 1 excavator
Thu (02/04) | 02 Apr 2026 | Opening 7 |  | Access erection in progress
Thu (02/04) | 02 Apr 2026 | B2-27 | North side | Column C01-5 formwork installation ongoing
Thu (02/04) | 02 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Thu (02/04) | 02 Apr 2026 | P51 |  | Formwork casting at north side, bored pile hacking at south side
Thu (02/04) | 02 Apr 2026 | P47 |  | Hacking existing DR3
Thu (02/04) | 02 Apr 2026 | DR3 |  | No activity
Thu (02/04) | 02 Apr 2026 | P45 |  | Compaction grouting
Thu (02/04) | 02 Apr 2026 | P45 |  | Utility support removal at north
Thu (02/04) | 02 Apr 2026 | P28 |  | No activity. Pending scaffold dismantling
Thu (02/04) | 02 Apr 2026 | P40 |  | Tendon duct installation
Thu (02/04) | 02 Apr 2026 | P42 |  | Stitching formwork dismantling
Thu (02/04) | 02 Apr 2026 | CCW1 North |  | Unloading of blasting materials and preparation works, Pending inspection for blast holes, Blasting #23 to be done this afternoon
Thu (02/04) | 02 Apr 2026 | B2-04 to 07 slab cast. Total vol |  | 1651m3, 01 Apr: Casting started at 1:56am, 02 Apr: Casting completed at 2:20am
Thu (02/04) | 02 Apr 2026 | P42-P43 |  | Soil cutting down for LG preparation works
Thu (02/04) | 02 Apr 2026 | P44 |  | Shifting & unloading of materials
Thu (02/04) | 02 Apr 2026 | Blasting no.23 completed at 4 |  | 01pm
Thu (02/04) | 02 Apr 2026 | P7 |  | Continue Falsework installation
Thu (02/04) | 02 Apr 2026 | P10 |  | Tendon duct hacking rectification works
Thu (02/04) | 02 Apr 2026 | P10-P11 |  | Ground leveling works
Thu (02/04) | 02 Apr 2026 | P18 |  | Scaffold installation completed
Thu (02/04) | 02 Apr 2026 | 800mm PW |  | S3 strut removal
Thu (02/04) | 02 Apr 2026 | P51 |  | L4 caisson casting at north side
Thu (02/04) | 02 Apr 2026 | P47 |  | Hacking existing DR3
Thu (02/04) | 02 Apr 2026 | 800mm PW |  | Air valve installation near DR3
Thu (02/04) | 02 Apr 2026 | P46 |  | Utility support installation
Thu (02/04) | 02 Apr 2026 | P45 |  | 1 nos packer grouting completed at south side..current utility support removal status at north side
Thu (02/04) | 02 Apr 2026 | P51 |  | L4 caisson casting in progress
Thu (02/04) | 02 Apr 2026 | P47 |  | No activity
Thu (02/04) | 02 Apr 2026 | P46 |  | No activity
Thu (02/04) | 02 Apr 2026 | P45 |  | No activity
Thu (02/04) | 02 Apr 2026 | P44 |  | No activity
Thu (02/04) | 02 Apr 2026 | P42-P43 |  | Soil cutting down for LG preparation works
Thu (02/04) | 02 Apr 2026 | P42 |  | Stitching formwork dismantled 2/4 nos
Thu (02/04) | 02 Apr 2026 | P40 |  | Tendon duct installation status
Thu (02/04) | 02 Apr 2026 | P10-P11 |  | Ground levelling works
Thu (02/04) | 02 Apr 2026 | P10 |  | Tendon duct hacking work
Thu (02/04) | 02 Apr 2026 | P7 |  | Crosshead falsework installation
Thu (02/04) | 02 Apr 2026 | P7 |  | Crosshead falsework installation
Thu (02/04) | 02 Apr 2026 | P1 |  | No activity
Thu (02/04) | 02 Apr 2026 | 800mm PW |  | Backfilling to S3 strut level
Sat (04/04) | 04 Apr 2026 | P51 |  | Formwork removal at north, bored pile hacking and ground levelling at south
Sat (04/04) | 04 Apr 2026 | P49 |  | Start stump rebar installation work
Sat (04/04) | 04 Apr 2026 | P47 |  | Continue hacking existing DR3
Sat (04/04) | 04 Apr 2026 | 800mm |  | Air valve testing near DR3
Sat (04/04) | 04 Apr 2026 | DR3 |  | No activity
Sat (04/04) | 04 Apr 2026 | P42-P43 |  | Soil cutting down for LG preparation works
Sat (04/04) | 04 Apr 2026 | P42-P41 |  | LG assembly work ongoing
Sat (04/04) | 04 Apr 2026 | P40 |  | Tendon duct and U pipe installation
Sat (04/04) | 04 Apr 2026 | P38 |  | Crosshead rebar installation work
Sat (04/04) | 04 Apr 2026 | P33 |  | 2nd lifter column rebar installation work ongoing
Sat (04/04) | 04 Apr 2026 | P30 |  | Scaffolding erection
Sat (04/04) | 04 Apr 2026 | CCE ramp to Station | GL24-30 | Excavation to -12.5mSHD at GL24-26. (3 KTC excavators), Loading rocks to trucks. (1 KTC excavator), Rocks coring and splitting. (3 machines), Shifting rocks to loading point. (1 WH excavator), Hacking rocks and temporary piles. (1 WH breaker)
Sat (04/04) | 04 Apr 2026 | P28 |  | Preparation work for formwork closing
Sat (04/04) | 04 Apr 2026 | P18 |  | Preparation for stressing work
Sat (04/04) | 04 Apr 2026 | P11 |  | Preparing for TPT and PT stressing
Sat (04/04) | 04 Apr 2026 | P10 |  | Tendon duct hacking work
Sat (04/04) | 04 Apr 2026 | P7 |  | Crosshead falsework installation in progresss
Sat (04/04) | 04 Apr 2026 | P2 |  | Shifting material, preparation for starter hanger installation
Sat (04/04) | 04 Apr 2026 | P1 |  | No activity
Sat (04/04) | 04 Apr 2026 | 800mm PW |  | S3 strut removal completed..backfilling works ongoing
Sat (04/04) | 04 Apr 2026 | DR4 |  | Preparation for JGP trial trench work
Mon (06/04) | 06 Apr 2026 | B2-39 |  | Bottom rebar works in progress, Continue dwall hacking to COL at the last portion
Mon (06/04) | 06 Apr 2026 | B2-35, B2-37 | North side | PU grouting and cleaning ongoing for skinwall area
Mon (06/04) | 06 Apr 2026 | GL26-30 |  | Exit staircase rebar and formwork currently no activity
Mon (06/04) | 06 Apr 2026 | GL28-30 | North side | Skin wall cast last Saturday. As to date, 40m skin wall cast
Mon (06/04) | 06 Apr 2026 | GL26-28 | North side | Skin wall cast the week before. Currently no activity
Mon (06/04) | 06 Apr 2026 | B2-28 | South side | Column C01-5 formwork installation in progress
Mon (06/04) | 06 Apr 2026 | B2-32, B2-34 | South side | Skin wall PU grouting ongoing
Mon (06/04) | 06 Apr 2026 | B2-19, B2-20 |  | Currently no activity
Mon (06/04) | 06 Apr 2026 | B2-14, B2-17 | North side | Hacking dwall surface to expose skin wall starter bars, B2-13, B2-15 (South side): Continue hacking and excavation. Loading point at Opening 3A
Mon (06/04) | 06 Apr 2026 | Blasting no.24 and 25 completed at 4 |  | 43pm
Mon (06/04) | 06 Apr 2026 | CCE | GL30-29 | Coring and splitting works ongoing — 3 machines
Mon (06/04) | 06 Apr 2026 | B2-39 |  | Rebar works in progress, Dwall hacking to COL completed. Now ongoing hacking at CJ side
Mon (06/04) | 06 Apr 2026 | B2-19, B2-20 |  | Currently no activity
Mon (06/04) | 06 Apr 2026 | B2-17 | North side | Now preparing to cast lean con. Joining of casting pipes in progress
Mon (06/04) | 06 Apr 2026 | B2-14, B2-15, B2-18 |  | Excavation in progress. Loading point at Opening 3A, Night team: 4 exc, 1 telescopic
Mon (06/04) | 06 Apr 2026 | Opening 3A |  | B2-12, B2-13: Excavation and internal soil transfer in progress
Mon (06/04) | 06 Apr 2026 | B1-01 |  | Skin wall formwork installation in progress
Mon (06/04) | 06 Apr 2026 | B1-11 part 2 |  | Rebar works in progress. Night team: 17 pax
Mon (06/04) | 06 Apr 2026 | B2-08, B2-09 |  | Unloading rebars. Dayshift until 9pm. No plan nightshift here tonight as manpower focus at B1-11 part 2
Mon (06/04) | 06 Apr 2026 | B2-02, B2-03 |  | Currently no activity yet
Tue (07/04) | 07 Apr 2026 | CCE Ramp/ | GL27-24 | Continue excavation & internal transfer by 4 excavators & 1 breaker
Tue (07/04) | 07 Apr 2026 | CCE Ramp / | GL29-27 | Rock coring/splitting is in progress by 3 machines *CD2/CD3/CD4*
Tue (07/04) | 07 Apr 2026 | CCE Ramp/ | GL30-29 | Continue rock disposal by 1 excavator
Tue (07/04) | 07 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Tue (07/04) | 07 Apr 2026 | CCE Ramp/ | GL27-24 | Continue excavation & internal transfer, Manpower: 2 excavator ktc, 2 excavator WHDA 1 breaker, Rock coring/splitting is in progress by 3 machines until 9 30
Wed (08/04) | 08 Apr 2026 | CCE Ramp/ | GL27-24 | Continue excavation & internal transfer by 3 excavators
Wed (08/04) | 08 Apr 2026 | CCE Ramp / | GL29-27 | Rock breaking & shifting of rock by 1 breaker & 1 excavator
Wed (08/04) | 08 Apr 2026 | CCE Ramp / | GL30-28 | Rock coring/splitting is in progress by 3 machines *CD2/CD3/CD4*
Wed (08/04) | 08 Apr 2026 | CCE Ramp / | GL26-25 | Witnessed rock (14 numbers) inspection with QPS rep
Wed (08/04) | 08 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Wed (08/04) | 08 Apr 2026 | P10 |  | Hacking to re-align PT duct. Balance 2 nos. To complete this week
Wed (08/04) | 08 Apr 2026 | P7 crosshead |  | Plywood laying in progress for working platform
Wed (08/04) | 08 Apr 2026 | P1 |  | SH and accessories shifting
Wed (08/04) | 08 Apr 2026 | P29 |  | Column Formwork dismantling ongoing
Wed (08/04) | 08 Apr 2026 | P30 |  | 1st lift column rebar installation
Wed (08/04) | 08 Apr 2026 | P33 |  | No activity
Wed (08/04) | 08 Apr 2026 | P38 |  | Crosshead no activity
Wed (08/04) | 08 Apr 2026 | P40 |  | Crosshead rebar installation
Wed (08/04) | 08 Apr 2026 | P41 |  | LG materials unloading and preparation for main truss assembly works
Wed (08/04) | 08 Apr 2026 | P43-P42 |  | Ground levelling works ongoing. Tmr to start LG main truss assembly works
Wed (08/04) | 08 Apr 2026 | P46 |  | LE utility supports works
Wed (08/04) | 08 Apr 2026 | P47 |  | Excavation and hacking works for 1st layer
Wed (08/04) | 08 Apr 2026 | P48 |  | 1st lift column rebar installation works
Wed (08/04) | 08 Apr 2026 | P51 |  | 4th layer cassion wall casting ongoing
Wed (08/04) | 08 Apr 2026 | Zone 4 |  | ERSS extraction for 800mm waterpipe
Thu (09/04) | 09 Apr 2026 | P11 |  | Preparation for segment launching works
Thu (09/04) | 09 Apr 2026 | P10 |  | Continue tendon duct rectification works
Thu (09/04) | 09 Apr 2026 | P7 |  | Base jack installation in progress
Thu (09/04) | 09 Apr 2026 | P6 |  | Crosshead formwork dismantling in progress
Thu (09/04) | 09 Apr 2026 | 800mm PW |  | Demob materials at DR4
Thu (09/04) | 09 Apr 2026 | P51 |  | Completed L4 caisson casting last night, currently concrete curing
Thu (09/04) | 09 Apr 2026 | P49 |  | No activity
Thu (09/04) | 09 Apr 2026 | P48 |  | Stump rebar work installation
Thu (09/04) | 09 Apr 2026 | P47 |  | Hacking grout at south side, excavation at north side
Thu (09/04) | 09 Apr 2026 | 800mm PW |  | Excavation to install chamber
Thu (09/04) | 09 Apr 2026 | P45 |  | Soldier pile removal
Thu (09/04) | 09 Apr 2026 | P46 |  | No activity
Thu (09/04) | 09 Apr 2026 | P42-P43 |  | Ground levelling for LG assembly platform
Thu (09/04) | 09 Apr 2026 | P42-P43 |  | Shifting LG material
Thu (09/04) | 09 Apr 2026 | P41 |  | Current status of LG assembly
Thu (09/04) | 09 Apr 2026 | P40 |  | Crosshead rebar installation
Thu (09/04) | 09 Apr 2026 | CCE Ramp / | GL30-28 | WH started to activate 4th (CD5) splitting machines today, continue rock coring/splitting by 4 machines *CD2/CD3/CD4/CD5*. FYI that last night they’ve also started night shift 1 team for coring/splitting work & understand that they will increase to 2 teams for tonight
Thu (09/04) | 09 Apr 2026 | CCE Ramp / | GL28-26 | Rock breaking & shifting of rock by 1 breaker & 1 excavator
Thu (09/04) | 09 Apr 2026 | CCE Ramp/ | GL26-24 | Continue excavation & internal transfer by 3 excavators
Thu (09/04) | 09 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Fri (10/04) | 10 Apr 2026 | B2-39 |  | Clearing hardcores and laying plywood at corner area (near B2-36), Rebar works ongoing, Dongah PU grouting
Fri (10/04) | 10 Apr 2026 | P51 |  | Formwork removal
Fri (10/04) | 10 Apr 2026 | P49 |  | Scaffolding erection, target to cast today
Fri (10/04) | 10 Apr 2026 | P48 |  | Preparation for formwork closing
Fri (10/04) | 10 Apr 2026 | P47 |  | Excavation at north side, grout hacking at south side
Fri (10/04) | 10 Apr 2026 | P46 |  | 2nd layer excavation
Fri (10/04) | 10 Apr 2026 | P45 |  | ERSS removal
Fri (10/04) | 10 Apr 2026 | CCE Ramp / | GL30-29 | Rock coring/splitting in progress by *CD3*
Fri (10/04) | 10 Apr 2026 | CCE Ramp / | GL29-26 | Rock coring/splitting in progress by 2 machines *CD2/CD5* & rock disposal by 1 excavator
Fri (10/04) | 10 Apr 2026 | CCE Ramp/ | GL26-23 | Continue excavation & internal transfer by 3 excavators & hacking of rock by 1 breaker
Fri (10/04) | 10 Apr 2026 | Zone 1 |  | Lane closed for access preparation and materials clearing to P2
Fri (10/04) | 10 Apr 2026 | P6 |  | Side Formwork dismantling completed
Fri (10/04) | 10 Apr 2026 | P7 |  | Side Formwork assembly works
Fri (10/04) | 10 Apr 2026 | P7 |  | Column hacking to correct level ongoing
Fri (10/04) | 10 Apr 2026 | Zone 2 |  | LG materials shifting works
Fri (10/04) | 10 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Fri (10/04) | 10 Apr 2026 | B1-11 part 2 |  | Shearlinks and formwork installation in progress. Plan for casting tmr
Fri (10/04) | 10 Apr 2026 | CCE ramp | GL30-29 | Coring works ongoing
Fri (10/04) | 10 Apr 2026 | CCE ramp | GL29-26 | Coring and splitting ongoing (3 machines), Tonight WH to continue coring/splitting works with 2 machines
Fri (10/04) | 10 Apr 2026 | CCE ramp | GL26-23 | Continue excavation & internal transfer and hacking works ongoing
Fri (10/04) | 10 Apr 2026 | B2-39 |  | Rebar works and cutting dwall hanging bars ongoing
Fri (10/04) | 10 Apr 2026 | B2-28, B2-30 | South side | Hacking ongoing to expose skin wall starter bars
Fri (10/04) | 10 Apr 2026 | B2-22 | South side | Column C01-3 rebar works in progress
Fri (10/04) | 10 Apr 2026 | B2-19, B2-20 |  | Plywood installation ongoing
Fri (10/04) | 10 Apr 2026 | B2-15 | South side | Hacking ongoing at dwall side
Fri (10/04) | 10 Apr 2026 | Opening 3A |  | B2-12 to B2-15: Nightshift continue excavation and disposal works (3 exc, 1 telescopic)
Fri (10/04) | 10 Apr 2026 | B2-08, B2-09 |  | Rebar works in progress. Plan for casting next week, Night team here: 10pax, At B1-11, 7pax tonight
Fri (10/04) | 10 Apr 2026 | B2-02, B2-03 |  | No activity
Fri (10/04) | 10 Apr 2026 | Exit 3 |  | No activity
Fri (10/04) | 10 Apr 2026 | CCW2 |  | Internal shifting. No other activty
Fri (10/04) | 10 Apr 2026 | B2-14, B2-15 |  | Partial base lean concrete done last night, Continue excavation and hardcores/soil clearing. Plan to complete tmr
Fri (10/04) | 10 Apr 2026 | B2-18 | South side | Base lean concrete completed. Levelling ongoing
Fri (10/04) | 10 Apr 2026 | B2-19 | North side | Soffit roughening and coupler exposing for Column C01-2, Dongah preparing for PU grouting at skinwall area
Fri (10/04) | 10 Apr 2026 | B2-30 | South side | PU grouting in progress
Fri (10/04) | 10 Apr 2026 | B2-26 | South side | PU grouting in progress
Fri (10/04) | 10 Apr 2026 | GL28-30 | North side | Skinwall formwork removal ongoing
Sat (11/04) | 11 Apr 2026 | CCW1 | South side | Currently no activity
Sat (11/04) | 11 Apr 2026 | CCW2 |  | Excavation and hacking ongoing (2 exc, 1 telescopic)
Sat (11/04) | 11 Apr 2026 | B2-02, B2-03 |  | Currently no activity
Sat (11/04) | 11 Apr 2026 | B1 area |  | No activity
Sat (11/04) | 11 Apr 2026 | Opening 3A |  | B2-12 to B2-15: Continue disposal works. Plan to complete today/tmr
Sat (11/04) | 11 Apr 2026 | B1-11 part 2 |  | Shearlinks and formwork installation in progress, Cleaning ongoing, Final inspection plan in the afternoon and target to cast today
Sat (11/04) | 11 Apr 2026 | P28 |  | 2nd lift column final inspection completed. To cast tmr
Sat (11/04) | 11 Apr 2026 | P30 |  | 1st lift column rebar works in progress
Sat (11/04) | 11 Apr 2026 | P33 2nd lift column |  | Preparation for tie rod and formwork closing
Sat (11/04) | 11 Apr 2026 | P38 |  | Crosshead no activity. Manpower all at P40 now
Sat (11/04) | 11 Apr 2026 | P40 |  | U loop pipe, tendon ducts and rebar adjustment works
Sat (11/04) | 11 Apr 2026 | P41 |  | 1st pair stitching formwork installation. Today to cast
Sat (11/04) | 11 Apr 2026 | P42 |  | LG Main truss assembly works
Sat (11/04) | 11 Apr 2026 | P43 |  | Continue excavation and ground levelling for LG assembly works
Sat (11/04) | 11 Apr 2026 | B2-19 | North side | Exposing couplers and preparing for PU grouting works, Column C01-2 rebar planting in progress
Sat (11/04) | 11 Apr 2026 | B2-20 | South side | Drilling ongoing for RGT installation
Sat (11/04) | 11 Apr 2026 | B2-15 | South side | Hacking works ongoing at dwall side
Sat (11/04) | 11 Apr 2026 | B2-22 | South side | Column C01-3 shearlinks installation ongoing
Sat (11/04) | 11 Apr 2026 | B2-24 | South side | PU grouting ongoing
Sat (11/04) | 11 Apr 2026 | B2-28 | South side | Hacking ongoing to expose skinwall starter bars
Sat (11/04) | 11 Apr 2026 | GL30-32 |  | Wall formwork installation for exit staircase
Sat (11/04) | 11 Apr 2026 | B2-39 |  | RGT water flushing inspection ongoing, Rebar works & drainage pipes installation in progress
Sat (11/04) | 11 Apr 2026 | P45 |  | LE dismantling and removal of strutting in progress
Sat (11/04) | 11 Apr 2026 | P46 |  | Preparation for washout pipe installation works
Sat (11/04) | 11 Apr 2026 | P47 |  | Hacking and excavation works for 1st layer cassion wall
Sat (11/04) | 11 Apr 2026 | P48 |  | 1st lift column preparation for Formwork closing
Sat (11/04) | 11 Apr 2026 | P50 |  | Removal of abandoned cables
Sat (11/04) | 11 Apr 2026 | DR4 |  | JGP trial trench in progress
Sat (11/04) | 11 Apr 2026 | DR4 |  | Removal of ERSS materials
Sat (11/04) | 11 Apr 2026 | CCE ramp | GL30-29 | Coring works ongoing
Sat (11/04) | 11 Apr 2026 | CCE ramp | GL29-26 | Coring and splitting ongoing (3 machines)
Sat (11/04) | 11 Apr 2026 | CCE ramp | GL26-23 | Continue excavation & internal transfer and hacking works ongoing
Sat (11/04) | 11 Apr 2026 | N6 |  | Abutment wall casting in progress
Sat (11/04) | 11 Apr 2026 | P11 |  | 3rd pair segment installed yesterday. Strands installation for stressing ongoing
Sat (11/04) | 11 Apr 2026 | P10 |  | Tendon duct rectification works
Sat (11/04) | 11 Apr 2026 | P7 Crosshead |  | Column hacking, formwork assembly and formwork installation in progress
Sat (11/04) | 11 Apr 2026 | CCW2 |  | Continue excavation and hacking (2 exc, 1 mini, 1 telescopic)
Sat (11/04) | 11 Apr 2026 | CCW W5 |  | Drilling ongoing by ATC for next blasting works
Sat (11/04) | 11 Apr 2026 | B2-02, B2-03 |  | No excavation activity yet, B2-03: Post-drilling ongoing
Sat (11/04) | 11 Apr 2026 | B2-08, B2-09 |  | Rebar works in progress
Sat (11/04) | 11 Apr 2026 | B1-11 part 2 |  | Shearlinks, balance rebar works and cleaning ongoing. Final inspection plan late afternoon
Sat (11/04) | 11 Apr 2026 | P28 |  | 2nd lift column to cast tmr
Sat (11/04) | 11 Apr 2026 | P33 |  | 2nd lift column tie rod installation and preparation for formwork closing
Sat (11/04) | 11 Apr 2026 | B2-19 | North side | PU grouting ongoing, Continue exposing couplers, Column C01-2 rebar planting in progress
Sat (11/04) | 11 Apr 2026 | B2-12 to B2-15 |  | Continue clearing soil and hardcores
Sat (11/04) | 11 Apr 2026 | B2-22 | South side | Column C01-3 shearlinks installation ongoing
Sat (11/04) | 11 Apr 2026 | B2-39 |  | Rebar installation in progress. Plan for casting next week
Sat (11/04) | 11 Apr 2026 | P40 |  | Shear links installation in progress
Sat (11/04) | 11 Apr 2026 | P41 |  | 1st pair stitching to cast tonight
Sat (11/04) | 11 Apr 2026 | P42 |  | Current LG main truss asssembly status
Sat (11/04) | 11 Apr 2026 | P43 |  | Excavation for LG assembly
Sat (11/04) | 11 Apr 2026 | P45 |  | Current status for backfilling & strut removal
Sat (11/04) | 11 Apr 2026 | P46 |  | Washout pipe installed
Sat (11/04) | 11 Apr 2026 | P48 |  | 1st lift column preparation for Formwork closing
Sat (11/04) | 11 Apr 2026 | DR4 |  | Continue trial trench for JGP works
Sat (11/04) | 11 Apr 2026 | DR4 |  | Preparation for chamber installation and backfilling
Sat (11/04) | 11 Apr 2026 | P11 |  | Strands installation completed
Sat (11/04) | 11 Apr 2026 | P7 |  | Crosshead formwork assembly & installation
Sat (11/04) | 11 Apr 2026 | Zone 1 |  | Preparation for noise balloon set up
Sat (11/04) | 11 Apr 2026 | CCW1 | North side | Currently no activity. Blast #27 was done yesterday
Sat (11/04) | 11 Apr 2026 | CCW W5 |  | ATC preparing for next drilling works. Next blasting scheduled for Monday
Mon (13/04) | 13 Apr 2026 | P13 |  | Preparation for Formwork closing for bearing stump
Mon (13/04) | 13 Apr 2026 | P38 |  | Main bar for crosshead done. Handover to WH. WH preparing for ducting work
Mon (13/04) | 13 Apr 2026 | P40 crosshead |  | Shear link installation. Tentatively cast on Friday
Mon (13/04) | 13 Apr 2026 | P41 |  | Jack installation and preparation for stressing work
Mon (13/04) | 13 Apr 2026 | P43-42 |  | Shifting of stressing cage to clear up space for main truss assembling
Mon (13/04) | 13 Apr 2026 | P11 |  | 4th pair segment stressing & stitching formwork dismantling in progress
Mon (13/04) | 13 Apr 2026 | P7 |  | Crosshead Side Formwork assembly and installation ongoing
Mon (13/04) | 13 Apr 2026 | P2 |  | Noise balloon setting up
Mon (13/04) | 13 Apr 2026 | P48 |  | Platform erection for casting of 1st lift tomorrow
Mon (13/04) | 13 Apr 2026 | P49 |  | 1st lift cast
Mon (13/04) | 13 Apr 2026 | P51 |  | Pile head exposed at TPE bound. Continue excavation at changi bound
Mon (13/04) | 13 Apr 2026 | B2-39 |  | Rebar works in progress and start to install partial formwork. Target to cast on Wednesday
Mon (13/04) | 13 Apr 2026 | GL26-28 |  | RC wall formwork removal ongoing
Mon (13/04) | 13 Apr 2026 | CCE ramp | GL25 | Rock hacking in progress
Mon (13/04) | 13 Apr 2026 | Column C01-3 | North side | Column formwork installation ongoing
Mon (13/04) | 13 Apr 2026 | B2-20, B2-19 |  | Currently rebar works not yet started, Column C01-2 rebar works in progress
Mon (13/04) | 13 Apr 2026 | B2-17, B2-18 |  | Plywood installation in progress
Mon (13/04) | 13 Apr 2026 | B2-15 | South side | Current status of hacking works. Excavation completed
Mon (13/04) | 13 Apr 2026 | B2-14 | North side | Tonight to partial lean con at drop areas
Mon (13/04) | 13 Apr 2026 | Opening 3A |  | Continue clearing hardcores and soil. Tonight or by tmr to complete
Mon (13/04) | 13 Apr 2026 | B2-08, B2-09 |  | Continue rebar installation, side formwork closing and corrugated pipes installation, Target to cast on Wednesday
Mon (13/04) | 13 Apr 2026 | B2-02, B2-03 |  | Currently no activity
Mon (13/04) | 13 Apr 2026 | Column C01-1 |  | Pressure grout for tie rod holes ongoing
Mon (13/04) | 13 Apr 2026 | B1 area |  | No activity
Mon (13/04) | 13 Apr 2026 | CCW W4-W5 |  | Rock blasting #28 was completed this afternoon. KTC continue clearing & internal shifting (2 exc op)
Mon (13/04) | 13 Apr 2026 | CCW2 | North side | Temp pile hacking ongoing
Tue (14/04) | 14 Apr 2026 | P7 |  | Crosshead formwork installation
Tue (14/04) | 14 Apr 2026 | P11 |  | Preparation for stressing work
Tue (14/04) | 14 Apr 2026 | P10 |  | Tendon duct rectification works
Tue (14/04) | 14 Apr 2026 | P18 |  | Falsework dismantling
Tue (14/04) | 14 Apr 2026 | B2-08, B2-09 |  | Corrugated pipes, shearlinks and formwork installation in progress. Plan for casting tmr
Tue (14/04) | 14 Apr 2026 | Opening 3A |  | B2-12, B2-13: Disposal works ongoing, B2-14 (North side): Drop areas cast last night. Now preparing formwork for balance lean con areas
Tue (14/04) | 14 Apr 2026 | B2-18 | South side | Exposing couplers
Tue (14/04) | 14 Apr 2026 | B2-19 | North side | Bottom rebar planting at dwall side, Columns C01-2 currently no activity
Tue (14/04) | 14 Apr 2026 | CCE Ramp/ | GL26-23 | Continue excavation & internal transfer by 3 excavators
Tue (14/04) | 14 Apr 2026 | CCE Ramp / | GL28-26 | Rock coring/splitting is in progress by 4 machines *CD2/CD3/CD4/CD5*
Tue (14/04) | 14 Apr 2026 | Column C01-3 | North side | Formwork closing ongoing
Tue (14/04) | 14 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Tue (14/04) | 14 Apr 2026 | DR4 |  | TT for JGP
Tue (14/04) | 14 Apr 2026 | DR4 |  | Cleaning of completed water pipe laid and chambering work
Tue (14/04) | 14 Apr 2026 | P33 |  | Formwork closing
Tue (14/04) | 14 Apr 2026 | P34 |  | 2nd lift column rebar installation
Tue (14/04) | 14 Apr 2026 | P38 |  | No activity
Tue (14/04) | 14 Apr 2026 | P40 |  | Crosshead formwork closing
Tue (14/04) | 14 Apr 2026 | P41 |  | No activity
Tue (14/04) | 14 Apr 2026 | P43-P44 |  | Ground levelling in progress
Tue (14/04) | 14 Apr 2026 | CCW2 W5-W7 |  | Excavation and disposal in progress
Tue (14/04) | 14 Apr 2026 | CCW1 | North side | Soil shifting to CCW2 side for disposal works
Tue (14/04) | 14 Apr 2026 | CCW1 | South side | ATC drilling works done for the day. Tmr plan for blasting #29
Tue (14/04) | 14 Apr 2026 | Exit 3 B1 area |  | No activity
Tue (14/04) | 14 Apr 2026 | B1-07 column C03-1 |  | Pressure grout for tie rod holes
Tue (14/04) | 14 Apr 2026 | P45 |  | Current ground levelling status. No activity
Tue (14/04) | 14 Apr 2026 | P46 |  | Current excavation status. No activity
Tue (14/04) | 14 Apr 2026 | P47 |  | L1 caisson rebar installation work
Tue (14/04) | 14 Apr 2026 | P48 |  | 1st lift column casting
Tue (14/04) | 14 Apr 2026 | P51 |  | No activity
Tue (14/04) | 14 Apr 2026 | Opening 3 |  | Observed KTC has started clearing lean con for excavation to underplatform U3-37 and U3-38
Tue (14/04) | 14 Apr 2026 | B2-02, B2-03 |  | Currently no excavation activity
Tue (14/04) | 14 Apr 2026 | B2-03 | GL5-6 | Waterproofing membrane installation ongoing
Tue (14/04) | 14 Apr 2026 | B2-08, B2-09 |  | Continue rebar works, shearlinks and formwork installation
Tue (14/04) | 14 Apr 2026 | B2-10 | North side | Column C01-1 rebar works in progress
Tue (14/04) | 14 Apr 2026 | Opening 3A |  | B2-12 (North side): Preparing for partial lean con casting, B2-14 (North side): Plan to continue lean con casting also
Tue (14/04) | 14 Apr 2026 | B2-15 | South side | Observed hacking ongoing towards B2-16 side
Tue (14/04) | 14 Apr 2026 | B2-17, B2-18 |  | Platform erection ongoing for Column works
Tue (14/04) | 14 Apr 2026 | B2-19 | North side | Bottom rebar works in progress
Tue (14/04) | 14 Apr 2026 | Column C01-3 | North side | Formwork closing ongoing
Tue (14/04) | 14 Apr 2026 | B2-39 |  | Rebar and welding works ongoing
Tue (14/04) | 14 Apr 2026 | P7 |  | No activity
Tue (14/04) | 14 Apr 2026 | P6 |  | Tendon cable pulling in progress
Tue (14/04) | 14 Apr 2026 | P11 |  | Stressing completed. Dismantling work in progress
Tue (14/04) | 14 Apr 2026 | P2 |  | Noise balloon erection
Tue (14/04) | 14 Apr 2026 | CCE ramp | GL26-22 | Continue excavation & internal transfer (3 exc)
Wed (15/04) | 15 Apr 2026 | CCE Ramp / G30-28 |  | Rock hacking & internal shifting of rock by 1 breaker & 1 excavator
Wed (15/04) | 15 Apr 2026 | CCE Ramp / | GL28-26 | Rock coring/splitting is in progress by 4 machines *CD2/CD3/CD4/CD5*
Wed (15/04) | 15 Apr 2026 | CCE Ramp/ | GL26-23 | Continue excavation & internal transfer by 3 excavators
Wed (15/04) | 15 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Wed (15/04) | 15 Apr 2026 | P13 |  | Continue bearing stump Formwork closing. 7/8 nos. completed
Wed (15/04) | 15 Apr 2026 | P7 crosshead |  | End formwork installation
Wed (15/04) | 15 Apr 2026 | P6 crosshead |  | Strand pushing for 1st stage stressing
Wed (15/04) | 15 Apr 2026 | P2 SB |  | 1st pair initial adjustment completed last night. Survey taken for YWL confirmation
Wed (15/04) | 15 Apr 2026 | B2-39 |  | Rebar installation in progress. Plan for casting on Friday
Wed (15/04) | 15 Apr 2026 | 800mm PW |  | Butterfly valve top slab installation done, now backfilling ongoing
Wed (15/04) | 15 Apr 2026 | P51 TPE bound |  | Pile head hacking
Wed (15/04) | 15 Apr 2026 | P48 |  | To complete 100% of 1st layer caisson rebar by Tuesday. WH preparing additional steel plate protection for services
Wed (15/04) | 15 Apr 2026 | P46 |  | Excavation for 1st layer caisson
Wed (15/04) | 15 Apr 2026 | P45 |  | Backfilling done. Compaction in progress
Wed (15/04) | 15 Apr 2026 | P41 |  | Preparation for stressing work
Wed (15/04) | 15 Apr 2026 | P40 |  | Formwork closing and inspection. Target tomorrow casting
Wed (15/04) | 15 Apr 2026 | P33 |  | 2nd lift column formwork closing
Wed (15/04) | 15 Apr 2026 | P34 |  | 2nd lift column rebar works
Wed (15/04) | 15 Apr 2026 | P38 |  | No activity
Wed (15/04) | 15 Apr 2026 | P40 |  | No activity
Wed (15/04) | 15 Apr 2026 | P41 |  | No activity
Wed (15/04) | 15 Apr 2026 | P43-P44 |  | Current ground levelling status. No activity
Wed (15/04) | 15 Apr 2026 | P45 |  | No activity
Wed (15/04) | 15 Apr 2026 | P46 |  | Excavation for 1st layer caisson
Wed (15/04) | 15 Apr 2026 | CCW2 |  | Continue excavation
Wed (15/04) | 15 Apr 2026 | B1-01 |  | Skinwall formwork removal and housekeeping
Wed (15/04) | 15 Apr 2026 | P47 |  | L1 caisson rebar installation and S1 strut end plate installation
Wed (15/04) | 15 Apr 2026 | P51 |  | No activity
Wed (15/04) | 15 Apr 2026 | 800mm PW |  | Air valve 2 backfilling in progress
Wed (15/04) | 15 Apr 2026 | B2-04 opening | Opening 3 | U3-37: Nightshift continue excavation and internal shifting (1 exc, 1 telescopic)
Wed (15/04) | 15 Apr 2026 | B2-02, B2-03 |  | Currently no activity
Wed (15/04) | 15 Apr 2026 | B2-08, B2-09 |  | Shearlinks, corrugated pipes installation & cleaning ongoing. Tmr plan for casting, Nightshift: 16pax
Wed (15/04) | 15 Apr 2026 | B2-12 to B2-15 |  | Currently no activity
Wed (15/04) | 15 Apr 2026 | B2-18 | South side | Coupler exposing, B2-17, B2-18: Continue plywood installation
Wed (15/04) | 15 Apr 2026 | B2-19, B2-20 |  | Bottom rebar works ongoing till 830pm, Dayshift: 3+1 pax, No nightshift here as manpower focus at B2-08/09
Wed (15/04) | 15 Apr 2026 | Column C01-3 | South side | Formwork installation in progress
Wed (15/04) | 15 Apr 2026 | B2-29, B2-27 | North side | Scaffold erection ongoing for skinwall works
Wed (15/04) | 15 Apr 2026 | B2-39 |  | Rebar works ongoing near CJ at B2-36. Slab plan to cast on Friday
Wed (15/04) | 15 Apr 2026 | B2-35, B2-37 | North side | Skinwall area no activity
Wed (15/04) | 15 Apr 2026 | P13 |  | Continue bearing formwork closing, tie rod installation
Wed (15/04) | 15 Apr 2026 | P10 |  | No activity
Wed (15/04) | 15 Apr 2026 | P11 |  | No activity
Wed (15/04) | 15 Apr 2026 | P7 |  | Crosshead formwork installation
Wed (15/04) | 15 Apr 2026 | P6 |  | Strand cable pulling
Wed (15/04) | 15 Apr 2026 | P2 |  | Preparation work for tonight stressing cage installation
Thu (16/04) | 16 Apr 2026 | CCW2 |  | KTC and WH continue to hack and clear rocks near P24 before preparing platform for ATC works
Thu (16/04) | 16 Apr 2026 | CCW1 South |  | Excavation ongoing
Thu (16/04) | 16 Apr 2026 | DR4 |  | Pipe laying for traffic light cable
Thu (16/04) | 16 Apr 2026 | DR4 |  | JGP trial trench ongoing
Thu (16/04) | 16 Apr 2026 | P51 |  | Excavator maintenance
Thu (16/04) | 16 Apr 2026 | P13 |  | Stump formwork closing. Plan to cast tmr
Thu (16/04) | 16 Apr 2026 | P10 |  | 1st pair wet stitch, today to start rebar installation. Gap at 275-300mm
Thu (16/04) | 16 Apr 2026 | B2-04 opening | Opening 3 | Excavation ongoing for U3-37
Thu (16/04) | 16 Apr 2026 | B2-02, B2-03 |  | Currently no excavation activity
Thu (16/04) | 16 Apr 2026 | B2-08, B2-09 |  | Some cleaning and tying works ongoing. Final inspection ard 2pm
Thu (16/04) | 16 Apr 2026 | B2-03 | GL5-6 | Post drilling and inspection ongoing
Thu (16/04) | 16 Apr 2026 | B2-13 | South side | Currently no activity
Thu (16/04) | 16 Apr 2026 | B2-12 | North side | Exposing couplers, B2-14 (North side): Preparing for PU grouting works
Thu (16/04) | 16 Apr 2026 | B2-18 | South side | Hacking dwall surface to expose skin wall starter bars
Thu (16/04) | 16 Apr 2026 | B2-18, B2-20 | South side | Exposing couplers
Thu (16/04) | 16 Apr 2026 | B2-18 | South side | Column C04 rebar planting ongoing
Thu (16/04) | 16 Apr 2026 | B2-17 | North side | Column C04 rebar planting ongoing
Thu (16/04) | 16 Apr 2026 | B2-19, B2-20 |  | Bottom rebar works in progress, RGT installation at B2-20 side (South)
Thu (16/04) | 16 Apr 2026 | B2-22 | South side | PU grouting ongoing at skinwall area, Column C01-3 formwork installation in progress
Thu (16/04) | 16 Apr 2026 | P50 |  | Cleaning slurry to prepare for stump RC work
Thu (16/04) | 16 Apr 2026 | P49 |  | Preparation to backfilling
Thu (16/04) | 16 Apr 2026 | P48 |  | Concrete curing. No activity
Thu (16/04) | 16 Apr 2026 | P47 |  | L1 caisson rebar work at south, formwork closing at north
Thu (16/04) | 16 Apr 2026 | P46 |  | Excavation to L1 caisson level
Thu (16/04) | 16 Apr 2026 | P6 crosshead |  | Formwork adjusting
Thu (16/04) | 16 Apr 2026 | P6 |  | Strand pushing for 1st stage tensioning
Thu (16/04) | 16 Apr 2026 | P2 SB |  | Stressing cage installed last night. Tonight to continue segment adjusting
Thu (16/04) | 16 Apr 2026 | P13 |  | Formwork closing for bearing stump. Tonight to cast
Thu (16/04) | 16 Apr 2026 | Zone 2 |  | LG materials shifting to Zone 3 for assembly works
Thu (16/04) | 16 Apr 2026 | P10 |  | Stitching materials shifting for Formwork closing ongoing
Thu (16/04) | 16 Apr 2026 | P7 |  | Crosshead formwork adjusting and barricades installation
Thu (16/04) | 16 Apr 2026 | P6 |  | Continue tendon strands installation
Thu (16/04) | 16 Apr 2026 | DR4 |  | Cleaning inside water pipe and preparation for inspection
Thu (16/04) | 16 Apr 2026 | P40 |  | Crosshead casting
Thu (16/04) | 16 Apr 2026 | CCE ramp | GL28-25 | Hacking ongoing (1 breaker), Coring and splitting works ongoing (4 machines)
Thu (16/04) | 16 Apr 2026 | CCE ramp | GL22 | Excavation and internal shifting ongoing (3 exc)
Thu (16/04) | 16 Apr 2026 | CCE ramp | GL30-29 | Rock disposal ongoing (1 exc)
Thu (16/04) | 16 Apr 2026 | P33 |  | Scaffold access and casting platform erection
Thu (16/04) | 16 Apr 2026 | B2-39 |  | Top bars, shearlinks, wall starter bars and formwork installation in progress, Target to cast tmr evening
Thu (16/04) | 16 Apr 2026 | B2 area | North side | GL28-32 RC wall formwork installation in progress
Thu (16/04) | 16 Apr 2026 | Column C01-3 | South side | Continue formwork installation
Thu (16/04) | 16 Apr 2026 | B2-19, B2-20 |  | Bottom rebar installation in progress
Thu (16/04) | 16 Apr 2026 | B2-17 | North side | PU grouting ongoing, Column C04 rebar planting in progress
Thu (16/04) | 16 Apr 2026 | B2-20 | South side | PU grouting ongoing
Thu (16/04) | 16 Apr 2026 | B2-18 | South side | Continue plywood installation
Thu (16/04) | 16 Apr 2026 | B2-18/B2-15 | South side | Continue hacking dwall surface to expose skin wall starter bars
Thu (16/04) | 16 Apr 2026 | B2-12 | GL8-11 | Soil resistivity test for earth mat installation
Thu (16/04) | 16 Apr 2026 | B2-03 | GL5-6 | Rebar planting at dwall coupler side
Thu (16/04) | 16 Apr 2026 | B2-08, B2-09 |  | Final inspection completed. Now preparing for casting
Thu (16/04) | 16 Apr 2026 | B2-02, B2-03 |  | Currently no excavation activity yet
Thu (16/04) | 16 Apr 2026 | B2-04 | Opening 3 | Excavation in progress for U3-37
Thu (16/04) | 16 Apr 2026 | P45 |  | Current status of backfilling done. Tomorrow NDT test
Thu (16/04) | 16 Apr 2026 | P46 |  | Continue excavation for 1st layer caisson
Thu (16/04) | 16 Apr 2026 | P47 |  | 1st layer caisson rebar work anf maintenance platform erection
Thu (16/04) | 16 Apr 2026 | P50 |  | Cleaning for 1st lift rebar work
Thu (16/04) | 16 Apr 2026 | P51 |  | Pile head hacking at TPE bound
Thu (16/04) | 16 Apr 2026 | P40 |  | Crosshead casting in progress
Thu (16/04) | 16 Apr 2026 | P33 |  | 2nd lift formwork closed. Support installation for casting. P34: 2nd lift rebar work in progress
Thu (16/04) | 16 Apr 2026 | P38 |  | Preparation for duct pipe installation
Thu (16/04) | 16 Apr 2026 | P40 crosshead |  | Today to cast
Fri (17/04) | 17 Apr 2026 | CCE Ramp / | GL28-25 | Rock coring/splitting is in progress by 4 machines *CD2/CD4/CD5*
Fri (17/04) | 17 Apr 2026 | CCE Ramp/ | GL25-22 | Continue excavation & internal transfer by 1 breaker & 4 excavators
Fri (17/04) | 17 Apr 2026 | B2-04 |  | Excavation ongoing for U3-37
Fri (17/04) | 17 Apr 2026 | B2-02, B2-03 |  | Currently no activity
Fri (17/04) | 17 Apr 2026 | B1-06, B1-08 |  | Scaffold platform dismantled, B1-10: Scaffold erection ongoing for skinwall works
Fri (17/04) | 17 Apr 2026 | B2-19, B2-20 |  | Rebar works in progress, B2-17: Column C04 rebar planting ongoing
Fri (17/04) | 17 Apr 2026 | B2-39 |  | Balance wall starter bars & shearlinks installation, Final inspection plan this evening thereafter to cast
Fri (17/04) | 17 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and will continue disposal later as now the excavator is working at RTSA
Fri (17/04) | 17 Apr 2026 | P40 |  | Status of LG assembling
Fri (17/04) | 17 Apr 2026 | P41 |  | Preparing for stressing work
Fri (17/04) | 17 Apr 2026 | P13 |  | Concrete packing casting and preparation for bearing installation
Fri (17/04) | 17 Apr 2026 | DR4 |  | Current status of leychoon demob materials and machinery from site
Fri (17/04) | 17 Apr 2026 | P10 |  | 1st pair segment alignment finalised. To proceed with rebar installation. WH manpower currently at P41 wet stitch formwork dismantling
Fri (17/04) | 17 Apr 2026 | P7 |  | Scaffold support installation for rebar works. Tmr to start rebar
Fri (17/04) | 17 Apr 2026 | P6 crosshead |  | 1st stage stressing in progress
Fri (17/04) | 17 Apr 2026 | P47 |  | Formwork closing done for 1st layer west side. Today casting
Fri (17/04) | 17 Apr 2026 | P51 |  | Bund wall making for 1st lift rebar work
Fri (17/04) | 17 Apr 2026 | P51 TPE bound |  | Pile head hacking. Changi bound: excavation
Fri (17/04) | 17 Apr 2026 | P46 |  | Continue excavation for 1st layer caisson
Fri (17/04) | 17 Apr 2026 | P41 |  | Current status
Fri (17/04) | 17 Apr 2026 | P40 crosshead |  | Casting done and curing
Fri (17/04) | 17 Apr 2026 | P38 |  | Today no activity of duct work. WH manpower supporting at Zone 2
Fri (17/04) | 17 Apr 2026 | P33 |  | 2nd lift casting. P34: 2nd lift rebar work
Sat (18/04) | 18 Apr 2026 | P13 |  | Surveyor marking for bearing installation
Sat (18/04) | 18 Apr 2026 | P10 |  | 1st pair rebar works for wet stitch. 4pax
Sat (18/04) | 18 Apr 2026 | P7 crosshead |  | Rebar installation to start installation this afternoon
Sat (18/04) | 18 Apr 2026 | P2 SB |  | 1st pair 2nd alignment completed last night. Surveyor reading taken, pending YWL confirmation
Sat (18/04) | 18 Apr 2026 | P51 |  | 5th layer casion excavation works
Sat (18/04) | 18 Apr 2026 | P46 |  | Excavation in progress
Sat (18/04) | 18 Apr 2026 | P41 |  | Stressing cage and SH dismantled at SB. Dismantling now at NB
Sat (18/04) | 18 Apr 2026 | P13 |  | Bearing installation in progress
Sat (18/04) | 18 Apr 2026 | P10 |  | Wet stitch rebar works no activity
Sat (18/04) | 18 Apr 2026 | P7 |  | Continue assembly of side formwork
Mon (20/04) | 20 Apr 2026 | B1-11 part 2 |  | Preparing for formwork removal
Mon (20/04) | 20 Apr 2026 | B2-39 |  | Cast last Saturday
Mon (20/04) | 20 Apr 2026 | B2-36 | South side | Drilling ongoing for skin wall works
Mon (20/04) | 20 Apr 2026 | B2 | GL28-32 | Double slab and wall formwork installation ongoing
Mon (20/04) | 20 Apr 2026 | B2-19, B2-20 |  | Shearlinks, wall starter bars and corrugated pipes installation, Cleaning ongoing, Plan for casting tmr
Mon (20/04) | 20 Apr 2026 | B2-17 | North side | Column C04 scaffold dismantling ongoing
Mon (20/04) | 20 Apr 2026 | B2-18 | South side | Rebar planting ongoing at coupler areas
Mon (20/04) | 20 Apr 2026 | B2-10, B2-11 |  | Started to unload rebars and lay bottom rebars
Mon (20/04) | 20 Apr 2026 | B2-09, B2-08 |  | CJ roughening ongoing
Mon (20/04) | 20 Apr 2026 | B2-02, B2-03 |  | Currently no activity
Mon (20/04) | 20 Apr 2026 | B2-04 |  | Excavation in progress for U3-37, U3-38
Mon (20/04) | 20 Apr 2026 | P46 |  | Continue excavation. Reaching near water pipe
Mon (20/04) | 20 Apr 2026 | P47 |  | Continue caison casting
Mon (20/04) | 20 Apr 2026 | P48 |  | Rebar cage fabrication
Mon (20/04) | 20 Apr 2026 | P49 |  | Backfilling and levelling
Mon (20/04) | 20 Apr 2026 | P51 |  | Wendyng prepare for rebar work
Mon (20/04) | 20 Apr 2026 | P33 |  | Formwork removal. P34: 2nd lift rebar work
Mon (20/04) | 20 Apr 2026 | P36 |  | Decking removal to prepare platform for falsework erection
Mon (20/04) | 20 Apr 2026 | B2-08, B2-09 |  | Removing formwork, Clearing hacking debris at CJ area
Mon (20/04) | 20 Apr 2026 | B2-10, B2-11 |  | Bottom rebar works in progress
Mon (20/04) | 20 Apr 2026 | B2-19, B2-20 |  | Wall starter bar, shearlinks installation in progress
Tue (21/04) | 21 Apr 2026 | DR4 |  | No silty water discharge to public drain during rain
Tue (21/04) | 21 Apr 2026 | DR4 SB |  | TT for JGP. One number done today
Tue (21/04) | 21 Apr 2026 | GL28-32 | North side | Formwork installation in progress for 1st lift RC wall and double slab
Tue (21/04) | 21 Apr 2026 | B2-27, B2-29 | North side | PU grouting ongoing
Tue (21/04) | 21 Apr 2026 | B2-19, B2-20 |  | Preparing for casting
Tue (21/04) | 21 Apr 2026 | B2-10, B2-11 |  | Bottom rebar works & PU grouting ongoing
Tue (21/04) | 21 Apr 2026 | B2-04 |  | Excavation and hacking ongoing for U3-37 & U3-38
Tue (21/04) | 21 Apr 2026 | P10 |  | Stitching rebar installation in progress
Tue (21/04) | 21 Apr 2026 | P7 |  | Crosshead rebar installation
Tue (21/04) | 21 Apr 2026 | P45 |  | Levelling around column area
Tue (21/04) | 21 Apr 2026 | P46 |  | Continue excavation work
Tue (21/04) | 21 Apr 2026 | P47 |  | Caisson casting at east side
Tue (21/04) | 21 Apr 2026 | P48 |  | 2nd lift column rebar work
Tue (21/04) | 21 Apr 2026 | P51 | west side | Caisson rebar installed
Tue (21/04) | 21 Apr 2026 | P33 |  | 2nd lift formwork removal. P34: 2nd rebar work almost completed
Tue (21/04) | 21 Apr 2026 | P13 |  | 4nos of bearing plates installed at SB side. Tonight target to cast 4nod at NB side
Tue (21/04) | 21 Apr 2026 | P11NB |  | Steel blaster bar removal and clearing materials from segments
Tue (21/04) | 21 Apr 2026 | P7 crosshead |  | Bottom bar and top bar completed. Now working for side bar installation
Tue (21/04) | 21 Apr 2026 | P7 |  | Continue assembling of side formwork
Tue (21/04) | 21 Apr 2026 | P6 |  | Tomorrow will continue with working platform removal
Tue (21/04) | 21 Apr 2026 | P47 |  | Continue caisson casting work
Tue (21/04) | 21 Apr 2026 | P45 |  | Current status of backfilling
Tue (21/04) | 21 Apr 2026 | P51 |  | Continue excavation work
Tue (21/04) | 21 Apr 2026 | P48, P49 |  | No activity already
Wed (22/04) | 22 Apr 2026 | Zone 2 |  | Fire drill exercise
Wed (22/04) | 22 Apr 2026 | P13 |  | Working platform installation for segment launching
Wed (22/04) | 22 Apr 2026 | P10 NR |  | Rebar installation for 1st pair stitching
Wed (22/04) | 22 Apr 2026 | P6 |  | Preparation for working platform and Falsework removal
Wed (22/04) | 22 Apr 2026 | P7 |  | Crosshead rebar installation in progress
Wed (22/04) | 22 Apr 2026 | Zone 3 |  | Emergency rescue drill done
Wed (22/04) | 22 Apr 2026 | P51 |  | Hacking of balance pile and provide protection plywood for rebar work
Wed (22/04) | 22 Apr 2026 | P49 |  | CJ roughening
Wed (22/04) | 22 Apr 2026 | P49 |  | Prepare rain water down pipe
Wed (22/04) | 22 Apr 2026 | P49 |  | 2nd lift rebar cage fabrication
Wed (22/04) | 22 Apr 2026 | P47 |  | 1st caisson casting was done. Now formwork removal. LE preparing for strut installation
Wed (22/04) | 22 Apr 2026 | P46 |  | WH erection of access and KTC continue excavation at NB
Wed (22/04) | 22 Apr 2026 | P45 |  | Platform preparation for 2nd rebar cage fabrication
Wed (22/04) | 22 Apr 2026 | P38 |  | No activity by WH yet. Rafiqual at Zone 4
Wed (22/04) | 22 Apr 2026 | B2-19, B2-20 |  | Casting completed
Wed (22/04) | 22 Apr 2026 | GL22-26 | North side | Straightening of skin wall starter bars
Wed (22/04) | 22 Apr 2026 | GL28-32 | North side | Double slab and first lift wall plan for casting today
Wed (22/04) | 22 Apr 2026 | GL32-E9 |  | Rebar works ongoing for RC wall
Wed (22/04) | 22 Apr 2026 | P13 |  | Working platform installation for tonight segment launching
Wed (22/04) | 22 Apr 2026 | P10 |  | Continue 1st pair stitching rebar installation
Wed (22/04) | 22 Apr 2026 | P7 |  | CH Rebar installation in progress
Wed (22/04) | 22 Apr 2026 | P6 |  | Materials unloading and preparation for Falsework removal
Wed (22/04) | 22 Apr 2026 | P45 |  | No activity
Wed (22/04) | 22 Apr 2026 | P46 |  | Excavation to L1 caisson layer
Wed (22/04) | 22 Apr 2026 | P48 |  | 2nd lift rebar cage fabrication
Wed (22/04) | 22 Apr 2026 | P47 |  | S1 strut installation
Wed (22/04) | 22 Apr 2026 | P49 |  | Preparation for 2nd lift column work
Wed (22/04) | 22 Apr 2026 | DR2 |  | No silty discharge observed
Wed (22/04) | 22 Apr 2026 | Loyang way footpath/Gate 7 |  | No silty discharge observed
Wed (22/04) | 22 Apr 2026 | P13 MJ |  | Tonight will launch one segment at SB. And tomorrow one segment also
Wed (22/04) | 22 Apr 2026 | P7 |  | Lighting provided. Continue balance rebar work
Wed (22/04) | 22 Apr 2026 | GL32-E9 |  | Rebar works ongoing for RC wall
Wed (22/04) | 22 Apr 2026 | GL28-32 |  | Preparing to cast double slab and first lift wall
Wed (22/04) | 22 Apr 2026 | B2-17, B2-18 |  | Bottom rebar installation ongoing
Wed (22/04) | 22 Apr 2026 | P7 |  | Assembling of formwork for crosshead
Wed (22/04) | 22 Apr 2026 | Zone 1 |  | No silty water discharge to live road during rain
Wed (22/04) | 22 Apr 2026 | P12 |  | Tonight plan to complete joining of duct and handover to WH
Wed (22/04) | 22 Apr 2026 | P51 |  | No activity due to rain
Wed (22/04) | 22 Apr 2026 | P49 |  | Current status of 2nd lift
Wed (22/04) | 22 Apr 2026 | P47 |  | Preparing i beam for S1 layer strut. This week target to complete installation. Monday MPI test
Wed (22/04) | 22 Apr 2026 | P46 |  | Erection of access scaffold by WH
Thu (23/04) | 23 Apr 2026 | P42/41 |  | Current status
Thu (23/04) | 23 Apr 2026 | P40 |  | Current status
Thu (23/04) | 23 Apr 2026 | P13 1st pair wet stitch |  | Rebar works to complete today. Manpower 7+ 1
Thu (23/04) | 23 Apr 2026 | GL32-E9 |  | RC wall rebar works in progress
Thu (23/04) | 23 Apr 2026 | B2-36 | South side | Preparing for skinwall works
Thu (23/04) | 23 Apr 2026 | B2-29 | South side | Skin wall rebar works ongoing
Thu (23/04) | 23 Apr 2026 | P7 crosshead |  | Top bars installation in progress
Thu (23/04) | 23 Apr 2026 | P6 |  | Falsework dismantling in progress
Thu (23/04) | 23 Apr 2026 | B2-17, B2-18 |  | Rebar and RGT installation in progress
Thu (23/04) | 23 Apr 2026 | P30 |  | Status quo
Thu (23/04) | 23 Apr 2026 | CCE Ramp/ | GL29-27 | Continue rock hacking & internal transfer by 2 breakers & 1 excavator
Thu (23/04) | 23 Apr 2026 | CCE Ramp / | GL27-23 | Rock coring/splitting is in progress by 4 machines *CD2/CD3/CD4/CD5*
Thu (23/04) | 23 Apr 2026 | P48 |  | 2nd lift rebar cage fabrication
Thu (23/04) | 23 Apr 2026 | P47 |  | 5/14 nos strut installed
Thu (23/04) | 23 Apr 2026 | P51 |  | Access erection
Thu (23/04) | 23 Apr 2026 | P51 |  | Continue pile head hacking and rebar work
Thu (23/04) | 23 Apr 2026 | CCE Ramp/ | GL23-20 | Continue excavation & internal transfer by 3 excavators
Thu (23/04) | 23 Apr 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Thu (23/04) | 23 Apr 2026 | CCW2 W6-W8 | North side | Blast 33 completed at 1607hrs
Thu (23/04) | 23 Apr 2026 | P13 NB |  | Bearing installation in progress. Plan to launch 3 nos tonight
Thu (23/04) | 23 Apr 2026 | P10 NBR wet stitch |  | Rebar 80% completed
Thu (23/04) | 23 Apr 2026 | P7 crosshead |  | Main bar installation completed. Stirrups installation in progress
Thu (23/04) | 23 Apr 2026 | P30 |  | No activity
Thu (23/04) | 23 Apr 2026 | P34 |  | Spacer block installation in progress in preparation for formwork closing
Thu (23/04) | 23 Apr 2026 | P38 |  | PT duct installation no activity observed
Thu (23/04) | 23 Apr 2026 | P44 |  | Telstra cable recovery
Thu (23/04) | 23 Apr 2026 | P43-44 |  | LG assembly stopped for the day
Thu (23/04) | 23 Apr 2026 | P46 |  | Excavator spoiled. Waiting for crane to mobilize to retrieve excavator
Thu (23/04) | 23 Apr 2026 | P47 |  | S1 strut installation until 9pm
Thu (23/04) | 23 Apr 2026 | P51 |  | Excavation to expose pile head to continue hacking tmr
Thu (23/04) | 23 Apr 2026 | P13 |  | Preparation for segment launching at NB, U01. To launch at 1030 pm
Thu (23/04) | 23 Apr 2026 | P10 NBR |  | 1st pair wet stitch rebar installation completed. Formwork closing to start tmr. Plan to cast on Saturday
Thu (23/04) | 23 Apr 2026 | P7 |  | Steel anchor shifting. Tmr to start installation
Thu (23/04) | 23 Apr 2026 | P6 |  | Falsework dismantling to continue tonight m
Thu (23/04) | 23 Apr 2026 | P13 |  | Scaffold access erection, SB U01 launched last night
Thu (23/04) | 23 Apr 2026 | DR4 |  | Dewatering before continue with cement lining work
Thu (23/04) | 23 Apr 2026 | DR4 |  | TT in progress for pipe sleeves. Today target 3nos
Fri (24/04) | 24 Apr 2026 | P34 |  | Scaffold removal in progress, prior to fwk closing
Fri (24/04) | 24 Apr 2026 | P6 |  | Falsework removal in progress
Fri (24/04) | 24 Apr 2026 | P7 |  | Crosshead rebar installation
Fri (24/04) | 24 Apr 2026 | P38 |  | Duct installation ongoing
Fri (24/04) | 24 Apr 2026 | Exit 1 stockpile |  | Current stockpile
Fri (24/04) | 24 Apr 2026 | GL32-E9 |  | Rebar and inner formwork installation in progress for RC wall
Fri (24/04) | 24 Apr 2026 | B2-36, B2-38 | South side | Drilling ongoing for tie rod holes and preparing for skin wall rebar works
Fri (24/04) | 24 Apr 2026 | B2-29 | North side | Skin wall rebar works ongoing
Fri (24/04) | 24 Apr 2026 | B2-17, B2-18 |  | Bar chair and bottom rebar planting in progress
Fri (24/04) | 24 Apr 2026 | P10 NR |  | 1st pair stitching Formwork installation
Fri (24/04) | 24 Apr 2026 | P13 |  | 1 segment launched yesterday. Segment adjustment in progress
Fri (24/04) | 24 Apr 2026 | CCE Ramp/ | GL29-27 | Continue rock hacking & internal transfer by 2 breakers & 1 excavator
Fri (24/04) | 24 Apr 2026 | CCE Ramp / | GL27-23 | Rock coring/splitting is in progress by 4 machines *CD2/CD3/CD4/CD5*
Fri (24/04) | 24 Apr 2026 | CCE Ramp/ | GL22-19 | Continue excavation & internal transfer by 3 excavators
Fri (24/04) | 24 Apr 2026 | P2 SB |  | No activity. Stitching team still at P10
Fri (24/04) | 24 Apr 2026 | P10 NBR |  | Wet stitch formwork closing in progress
Fri (24/04) | 24 Apr 2026 | P7 crosshead |  | Box girder rebar works in progress
Fri (24/04) | 24 Apr 2026 | P48 |  | Backfilling ongoing. Rebar fabrication works for 2nd lift column ongoing
Fri (24/04) | 24 Apr 2026 | P46 |  | Excavation to L1 caisson level
Fri (24/04) | 24 Apr 2026 | P47 |  | Raining. To continue S1 strut installation
Fri (24/04) | 24 Apr 2026 | P34 |  | RWDP installed. Tmr to start formwork closing
Fri (24/04) | 24 Apr 2026 | P38 crosshead |  | No activity observed
Fri (24/04) | 24 Apr 2026 | P43-44 |  | Slope cutting for LG installation status. No more activity
Fri (24/04) | 24 Apr 2026 | CCW1 |  | Continue disposal works
Fri (24/04) | 24 Apr 2026 | CCW2 |  | Blast #34 was done this afternoon
Fri (24/04) | 24 Apr 2026 | CCW1 North |  | Hacking ongoing at drop area
Fri (24/04) | 24 Apr 2026 | U3-37, U3-38 |  | Excavation in progress (2 exc, 1 telescopic), Access erection ongoing
Fri (24/04) | 24 Apr 2026 | B1 area |  | No activity
Fri (24/04) | 24 Apr 2026 | B2-02, B2-03 |  | Currently no activity
Fri (24/04) | 24 Apr 2026 | B2-10, B2-11 |  | Rebar works in progress. Plan for casting early next week
Fri (24/04) | 24 Apr 2026 | P49 |  | 2nd lift column rebar cage installed. Propping installation in progress
Fri (24/04) | 24 Apr 2026 | P51 |  | 5th layer caison formwork closing. Plan to cast tonight
Fri (24/04) | 24 Apr 2026 | B2-17, B2-18 |  | Rebar works in progress
Fri (24/04) | 24 Apr 2026 | B2-36 | South side | Straightening of skinwall starter bars
Fri (24/04) | 24 Apr 2026 | CCE ramp | South side, GL-E6 | Excavation here tonight (2 exc)
Fri (24/04) | 24 Apr 2026 | P7 crosshead |  | Steel anchor installation until 9pm. Rebar works will continue by nightshift team
Fri (24/04) | 24 Apr 2026 | P6 |  | Falsework dismantling to continue by nightshift team
Sat (25/04) | 25 Apr 2026 | P7 crosshead |  | Rebar work in progress at opening area. By today will complete all rebar work and handover to WH for ducting work. Currently no WH manpower can allocate for this work
Sat (25/04) | 25 Apr 2026 | P6 |  | Today should be able to complete dismantling of 2 runner beams and two legs
Sat (25/04) | 25 Apr 2026 | B1-04 |  | Preparing for PU grouting at skinwall side
Sat (25/04) | 25 Apr 2026 | U3-37, U3-38 |  | Excavation in progress (3 exc, 1 telescopic), U3-38: Hacking ongoing at skin wall side (2 breakers)
Sat (25/04) | 25 Apr 2026 | CCW1 | North side | Exposing couplers in progress (4 men)
Sat (25/04) | 25 Apr 2026 | CCW1 South |  | Excavation in progress to FEL (2 exc)
Sat (25/04) | 25 Apr 2026 | Zone 1 |  | No activity today. Monday to start stitching formwork closing for P2
Sat (25/04) | 25 Apr 2026 | Zone 2 |  | Shifting of LG materials to P43
Sat (25/04) | 25 Apr 2026 | DR4 |  | Preparing for JGP trial trench
Sat (25/04) | 25 Apr 2026 | DR4 |  | Lean concrete done for footpath diversion
Sat (25/04) | 25 Apr 2026 | B2-10, B2-11 |  | Rebar works in progress at GL5.5-6, Corrugated pipes and partial formwork installation ongoing
Sat (25/04) | 25 Apr 2026 | B2-17, B2-18 |  | Rebar works in progress
Sat (25/04) | 25 Apr 2026 | B2-20 |  | Formwork dismantling ongoing
Sat (25/04) | 25 Apr 2026 | B2-29 | North side | Skin wall rebar works, kicker formwork installation & PU grouting ongoing
Sat (25/04) | 25 Apr 2026 | B2-35 | North side | PU grouting ongoing
Sat (25/04) | 25 Apr 2026 | GL32-E9 |  | Partial formwork installation in progress for RC wall
Sat (25/04) | 25 Apr 2026 | P46 |  | Continue excavation for 1st layer caisson
Sat (25/04) | 25 Apr 2026 | P47 |  | Tomorrow to complete S1 strut welding
Sat (25/04) | 25 Apr 2026 | P48 |  | Backfilling and compaction in progress
Sat (25/04) | 25 Apr 2026 | P48 |  | Continue fabrication of rebar cage
Sat (25/04) | 25 Apr 2026 | P49 |  | Prepare to lean concrete the base for column work
Sat (25/04) | 25 Apr 2026 | P51 |  | Formwork closing for caisson
Sat (25/04) | 25 Apr 2026 | CCE ramp | South side, GL E6-7 | Excavation in progress (2 exc)
Sat (25/04) | 25 Apr 2026 | CCE ramp | GL30-18 | Hacking works ongoing (2 breakers), Coring and splitting (2 machines). 1 mini breaker preparing next locations for other 2 machines, Excavation and internal shifting ongoing (3 exc)
Sat (25/04) | 25 Apr 2026 | P38 |  | WH continue ducting work. Plan to complete by Wednesday. Casting tentatively on 3rd May
Sat (25/04) | 25 Apr 2026 | P34 |  | Preparing for 2nd lift formwork closing
Sat (25/04) | 25 Apr 2026 | S3 |  | Column painting mock up
Sat (25/04) | 25 Apr 2026 | P10 |  | Stitching formwork closing
Sat (25/04) | 25 Apr 2026 | U3-37, U3-38 |  | Continue excavation
Sat (25/04) | 25 Apr 2026 | B2-10, B2-11 |  | Continue rebar works, formwork installation, RTO inspection ongoing
Sat (25/04) | 25 Apr 2026 | B2-12 to B2-16 |  | Currently no activity
Sat (25/04) | 25 Apr 2026 | B2-17, B2-18 |  | Rebar installation in progress
Sat (25/04) | 25 Apr 2026 | P7 crosshead |  | Balance rebar work in progress. Ultracon installation of tendon box
Sat (25/04) | 25 Apr 2026 | P6 |  | Continue removal of falsework
Sat (25/04) | 25 Apr 2026 | DE160 current status |  | Two crosshead (part of crosshead) and 3 columns already come out
Sat (25/04) | 25 Apr 2026 | B2-19, B2-20 |  | Formwork dismantling
Sat (25/04) | 25 Apr 2026 | GL26-25 | North side | Bottom surface roughening ongoing for RC wall rebar works
Sat (25/04) | 25 Apr 2026 | B2-29 | North side | PU grouting ongoing
Sat (25/04) | 25 Apr 2026 | B2-35 | North side | PU grouting ongoing
Sat (25/04) | 25 Apr 2026 | GL32-E9 |  | RC wall rebar works and formwork installation ongoing. Plan for casting next week
Sat (25/04) | 25 Apr 2026 | DR4 |  | Current status of preparation for footpath diversion and TT for JGP. Now worker go for tea break
Sat (25/04) | 25 Apr 2026 | P45 |  | Platform prepared for column rebar fabrication
Sat (25/04) | 25 Apr 2026 | P46 |  | Continue excavation for caisson. Will backfill at the base for platform
Sat (25/04) | 25 Apr 2026 | P47 |  | Continue welding of strut
Sat (25/04) | 25 Apr 2026 | P48 |  | Column rebar cage fabrication done
Sat (25/04) | 25 Apr 2026 | P49 |  | Lean concrete around column
Sat (25/04) | 25 Apr 2026 | P51 |  | Continue caisson casting
Sat (25/04) | 25 Apr 2026 | P34 |  | 2nd lift formwork closing
Sat (25/04) | 25 Apr 2026 | P38 |  | Continue ducting work. Wednesday to complete
Sat (25/04) | 25 Apr 2026 | P13 |  | 3/4 segements for 1st pair installed at MJ area
Sat (25/04) | 25 Apr 2026 | P10 |  | Today will complete formwork closing for stitching. Tonight after last bus will cast
Sat (25/04) | 25 Apr 2026 | CCW2 | North side | ATC preparation works for drilling of blast holes. Blast #35 plan for Monday
Mon (27/04) | 27 Apr 2026 | P32 |  | 1st lift rebar ongoing
Mon (27/04) | 27 Apr 2026 | P34 |  | 2nd lift fwk working platform erection ongoing
Mon (27/04) | 27 Apr 2026 | P36 |  | Preparing for crosshead falsework erection
Mon (27/04) | 27 Apr 2026 | P38 |  | Duct installation ongoing
Mon (27/04) | 27 Apr 2026 | P2 SB |  | Tonight to start wet stitch rebar works
Mon (27/04) | 27 Apr 2026 | P47 |  | MPI test for S1 strut done
Mon (27/04) | 27 Apr 2026 | P48 |  | Current status of backfilling
Mon (27/04) | 27 Apr 2026 | P49 |  | Lifting point installation for 2nd lift
Mon (27/04) | 27 Apr 2026 | P48 |  | Shear link installation for 2nd lift
Mon (27/04) | 27 Apr 2026 | P51 |  | Excavation at NB side for caisson
Mon (27/04) | 27 Apr 2026 | P46 SB |  | Lean concrete today. NB: tomorrow lean concrete
Mon (27/04) | 27 Apr 2026 | P32 |  | Resume 1st lift rebar work
Mon (27/04) | 27 Apr 2026 | B2-17, B2-18 |  | Drainage pipes & top bar installation in progress, Night shift: 15pax
Mon (27/04) | 27 Apr 2026 | Exit 2 |  | Excavation in progress to B2-16
Mon (27/04) | 27 Apr 2026 | B2-10, B2-11 |  | Final inspection in progress
Mon (27/04) | 27 Apr 2026 | B2-29 | North side | Shifting formwork for skinwall
Mon (27/04) | 27 Apr 2026 | GL32-E9 |  | Rebar works and formwork installation for double slab and RC wall
Mon (27/04) | 27 Apr 2026 | P13 |  | Adjusting of segment
Mon (27/04) | 27 Apr 2026 | P12 |  | Lowering down materials from segment already launched area
Mon (27/04) | 27 Apr 2026 | P7 crosshead |  | Now no activity. Need to get ducting manpower from P38
Mon (27/04) | 27 Apr 2026 | P51 |  | Continue caisson casting work
Mon (27/04) | 27 Apr 2026 | P49 |  | Continue shear link installation
Mon (27/04) | 27 Apr 2026 | P48 |  | Lifting hook installed for rebar cage
Mon (27/04) | 27 Apr 2026 | P46 |  | Base lean concrete to handover to Wendyng
Mon (27/04) | 27 Apr 2026 | B2-10, B2-11 |  | Pump trucks parked. Concrete ordered
Tue (28/04) | 28 Apr 2026 | P13 NB 1st pair |  | Final adjustment in progress
Tue (28/04) | 28 Apr 2026 | P2 SB 1st Pair |  | Wet stitch formwork installation started last night
Tue (28/04) | 28 Apr 2026 | P51 |  | Continue north side hacking for L5 caisson
Tue (28/04) | 28 Apr 2026 | P50 | 1st lift | Preparation work for column rebar
Tue (28/04) | 28 Apr 2026 | P49 |  | Tie rod installation / preparation for fwk closure
Tue (28/04) | 28 Apr 2026 | P46 |  | Starting cassion wall rebar work
Tue (28/04) | 28 Apr 2026 | P45 | 1st lift | Preparing for column rebar work ongoing
Tue (28/04) | 28 Apr 2026 | P38 crosshead |  | Fwk closure ongoing
Tue (28/04) | 28 Apr 2026 | CCE Ramp/ | GL E6-E8 | Continue excavation & internal transfer by 3 excavators
Tue (28/04) | 28 Apr 2026 | CCE Ramp/ | GL29-26 | Continue rock hacking & internal transfer by 2 breakers & 1 excavator
Tue (28/04) | 28 Apr 2026 | P13 |  | Continue adjusting of segment at NB side
Tue (28/04) | 28 Apr 2026 | CCE Ramp / | GL28-23 | Rock coring/splitting is in progress by 4 machines
Tue (28/04) | 28 Apr 2026 | CCE Ramp/ | GL21-18 | Continue excavation & internal transfer by 3 excavators
Tue (28/04) | 28 Apr 2026 | P7 |  | PT duct support bar installation started. 2 pax
Tue (28/04) | 28 Apr 2026 | Vent shaft / B2-39 |  | CJ hacking & cleaning work is in progress
Tue (28/04) | 28 Apr 2026 | B2-36 |  | Rebar installation for the skin wall is in progress, B2-34:, Grouting work is in progress
Tue (28/04) | 28 Apr 2026 | B2-29 |  | Formwork closing in progress for skin wall
Tue (28/04) | 28 Apr 2026 | B2-17 & B2-18 |  | Top bar & shear links installation in progress, target to cast on Thu
Tue (28/04) | 28 Apr 2026 | B2-10 & B2-11 |  | Casting has completed around 2.15pm
Wed (29/04) | 29 Apr 2026 | B2-29 | North side | Skinwall formwork installation in progress
Wed (29/04) | 29 Apr 2026 | GL32-E9 |  | Double slab and 1st lift RC wall cast yesterday, GL-E9 to VS: Ongoing rebar works for RC wall
Wed (29/04) | 29 Apr 2026 | CCE Ramp/ | GL E6-E9 | Continue excavation & internal transfer by 4 excavators
Wed (29/04) | 29 Apr 2026 | CCE Ramp / | GL28-23 | Rock coring/splitting is in progress by 4 machines
Wed (29/04) | 29 Apr 2026 | CCE Ramp/ | GL29-26 | Continue rock hacking & internal transfer by 2 breakers & 1 excavator
Wed (29/04) | 29 Apr 2026 | CCE Ramp/ | GL20-17 | Continue excavation & internal transfer by 3 excavators
Wed (29/04) | 29 Apr 2026 | Column C01-2 |  | North side: Formwork installation, South side: Rebar works ongoing
Wed (29/04) | 29 Apr 2026 | P13 NB |  | 1st final adjustment ~9mm at gradient side completed. Pending YWL confirmation
Wed (29/04) | 29 Apr 2026 | P10 |  | Stressing cage and SH dismantling completed. Tonight to install LF
Wed (29/04) | 29 Apr 2026 | P36 |  | Current status
Wed (29/04) | 29 Apr 2026 | P7 crosshead |  | Rectification of main bars at the drop for steel anchor installation, Anti burst reinforcement installation
Wed (29/04) | 29 Apr 2026 | P6 |  | Material shifting to zone 3
Wed (29/04) | 29 Apr 2026 | DR4 |  | Ley Choon clear all their materials. GCE can do their balance JGP
Wed (29/04) | 29 Apr 2026 | DR4 |  | Preparing for balance traffic light pipe laying at footpath diverted area
Wed (29/04) | 29 Apr 2026 | B1-10 |  | Straightening of skinwall starter bars
Wed (29/04) | 29 Apr 2026 | CCW1 | south side | Coupler exposing ongoing, WH to also continue hacking of dwall surface to expose skinwall starter bars, Plan for lean concrete casting this Saturday
Wed (29/04) | 29 Apr 2026 | CCW1 | North side | Lean concrete was cast last night
Wed (29/04) | 29 Apr 2026 | CCW2 South side | GL W6-8 | Area preparation for drilling blast holes for blast #37
Wed (29/04) | 29 Apr 2026 | P38 |  | Current status
Wed (29/04) | 29 Apr 2026 | U3-35 to U3-38 |  | Excavation in progress. Currently workers on tea break
Wed (29/04) | 29 Apr 2026 | CCW2 North side | GL W6-8 | Blast #36 was done at 1520hrs
Wed (29/04) | 29 Apr 2026 | B2-03 | GL4-5.5 | Bottom rebar works ongoing
Wed (29/04) | 29 Apr 2026 | B2-16 |  | Excavation in progress. Soil loading point at Opening 3A
Wed (29/04) | 29 Apr 2026 | B2-17, B2-18 |  | Shearlinks & corrugated pipes installation, preparing casting pipes, RTO inspection ongoing, Plan for casting tmr
Wed (29/04) | 29 Apr 2026 | Column C01-2 |  | North side: Formwork installation, South side: Rebar works ongoing
Wed (29/04) | 29 Apr 2026 | B2-25, B2-27 | North side | Straightening of skinwall starter bars & bottom CJ roughening
Wed (29/04) | 29 Apr 2026 | B2-29 | North side, GL24-26 | Skinwall formwork inspection. Plan for casting tonight
Wed (29/04) | 29 Apr 2026 | GL-E9 to VS |  | Ongoing rebar works for RC wall
Wed (29/04) | 29 Apr 2026 | P2 SB downchainage |  | Wet stitch formwork installation 90% completed. Balance filler plate
Wed (29/04) | 29 Apr 2026 | P51 |  | Hacking of pile head at NB side
Wed (29/04) | 29 Apr 2026 | P49 |  | 2nd lift formwork closing. Tomorrow to cast
Wed (29/04) | 29 Apr 2026 | P48 |  | 2nd lift rebar cage fabricated
Wed (29/04) | 29 Apr 2026 | P48 |  | Prepare concrete footing tomorrow to install rebar cage
Wed (29/04) | 29 Apr 2026 | P47 |  | Started excavation for 2nd layer
Wed (29/04) | 29 Apr 2026 | P46 |  | 1st layer caisson rebar work
Wed (29/04) | 29 Apr 2026 | P45 |  | TT for JGP testing
Wed (29/04) | 29 Apr 2026 | P45 |  | Rebar cage fabrication for 2nd lift
Wed (29/04) | 29 Apr 2026 | P17-18 |  | Grouting of tendon pipe done. Now housekeeping
Wed (29/04) | 29 Apr 2026 | P13 |  | No activity as of now
Wed (29/04) | 29 Apr 2026 | P10 |  | Preparing to shift lifter frame tonight after last bus
Wed (29/04) | 29 Apr 2026 | CCE ramp | GL29-25 | Hacking, coring and splitting works in progress (2 breakers, 4 coring machines), Dayshift team just came back from dinner, Night team will take over from 9:30pm (1 breaker, 2 coring machines)
Wed (29/04) | 29 Apr 2026 | CCE ramp | GL18 | Excavation ongoing (1 excavator)
Wed (29/04) | 29 Apr 2026 | CCE ramp | GL E6-9 | Nightshift continue excavation here (3 operators)
Wed (29/04) | 29 Apr 2026 | P7 |  | Tendon box installation by Ultracon
Wed (29/04) | 29 Apr 2026 | P2 |  | Starter hanger assembling for 1st pair work at NB
Wed (29/04) | 29 Apr 2026 | P3 |  | Current status of access erection
Wed (29/04) | 29 Apr 2026 | B2-17, B2-18 |  | Shearlinks installation, joining of casting pipes & cleaning ongoing. Casting tmr
Wed (29/04) | 29 Apr 2026 | B2-16 |  | Nightshift continue excavation (2 exc, 1 telescopic), Loading point at Opening 3A
Wed (29/04) | 29 Apr 2026 | B2-03 | GL4-5.5 | Rebar works in progress
Wed (29/04) | 29 Apr 2026 | CCW2 |  | KTC continue excavation for area preparation for ATC’s next drilling/blasting location (#38), South side: ATC drilling ongoing. To complete drilling by tonight. (blast holes: 75nos, relief holes: 27). Blast #37 scheduled for tmr
Wed (29/04) | 29 Apr 2026 | B1-10 |  | Skinwall rebar works ongoing
Wed (29/04) | 29 Apr 2026 | P45 |  | Current status of 2nd lift rebar fabrication
Wed (29/04) | 29 Apr 2026 | P47 |  | No activity of excavation already. Will chase for night shift excavation
Wed (29/04) | 29 Apr 2026 | P48 |  | Backfilling and installation of footing for 2nd lift column rebar cage installation tomorrow
Wed (29/04) | 29 Apr 2026 | P49 |  | 2nd lift formwork closed. Target to cast tomorrow
Wed (29/04) | 29 Apr 2026 | P32 |  | 1st lift column rebar work
Wed (29/04) | 29 Apr 2026 | P36 |  | Current status of falsework installation. To cast this crosshead in May
Wed (29/04) | 29 Apr 2026 | P38 |  | One side formwork closed
Wed (29/04) | 29 Apr 2026 | P40 |  | Crosshead formwork removal
Wed (29/04) | 29 Apr 2026 | P25 |  | 1st lift column formwork closing
Thu (30/04) | 30 Apr 2026 | P10 NBR downchainage |  | LF installed last night. Tonight to install upchainage
Thu (30/04) | 30 Apr 2026 | P7 SB |  | Steel anchor installation in progress. Balance 8 nos
Thu (30/04) | 30 Apr 2026 | P32 |  | 2nd lift column rebar installed
Thu (30/04) | 30 Apr 2026 | P36 |  | Current status of working platform erection for crosshead
Thu (30/04) | 30 Apr 2026 | P38 |  | Current status of formwork closing. WH installation of support for tendon pipes
Thu (30/04) | 30 Apr 2026 | P40 |  | Continue removal of materials on crosshead. Today to erect platform for stressing work
Thu (30/04) | 30 Apr 2026 | B2 | North side | B2-14: Bottom rebar planting ongoing at dwall side, B2-12: Dongah post-drilling ongoing
Thu (30/04) | 30 Apr 2026 | B2-16 |  | Excavation in progress
Thu (30/04) | 30 Apr 2026 | B2-17, B2-18 |  | Continue balance shearlinks installation & cleaning, Preparing for final inspection. To cast slab today
Thu (30/04) | 30 Apr 2026 | Column C01-2 |  | Formwork installation ongoing
Thu (30/04) | 30 Apr 2026 | P45 |  | Preparing to start JGP testing. Total 8nos of spt
Thu (30/04) | 30 Apr 2026 | P46 |  | Inspection of rebar and base plate for caisson work
Thu (30/04) | 30 Apr 2026 | GL20-24 | North side | CJ hacking ongoing for skinwall works, Straightening of starter bars & PU grouting ongoing at GL22-24
Thu (30/04) | 30 Apr 2026 | GL24-26 | North side | Skinwall cast yesterday evening (18.6m length)
Thu (30/04) | 30 Apr 2026 | GL24-26 | South side | PU grouting ongoing
Thu (30/04) | 30 Apr 2026 | GL-E9 to VS |  | RC wall rebar & plywood installation in progress
Thu (30/04) | 30 Apr 2026 | CCE ramp | GL E6-9 | Excavation in progress (3 exc)
Thu (30/04) | 30 Apr 2026 | P2 |  | SH shifting. Assembly to start this afternoon
Thu (30/04) | 30 Apr 2026 | CCE | South side, GL29-27 | Hacking ongoing at skin wall area (1 mini breaker), Coring & splitting in progress (2 machines), Excavation and shifting rocks (1 exc)
Thu (30/04) | 30 Apr 2026 | CCE | GL24-22 | Coring and splitting ongoing (2 machines)
Thu (30/04) | 30 Apr 2026 | CCE | GL18 | Excavation in progress (2 exc)
Thu (30/04) | 30 Apr 2026 | CCE | GL22-21 | Boulder inspection with RTO
Thu (30/04) | 30 Apr 2026 | DR4 |  | Continue TT for JGP work
Thu (30/04) | 30 Apr 2026 | DR4 |  | Traffic light pipe laying done. Preparing to cast protection concrete
Thu (30/04) | 30 Apr 2026 | GL20-24 | North side | CJ hacking ongoing for skinwall works, Straightening of starter bars & PU grouting ongoing at GL22-24, RTO inspection for tie rod holes drilling depth
Thu (30/04) | 30 Apr 2026 | GL32-E9 |  | RC wall formwork dismantling ongoing, GL E9 to VS: RC wall rebar and plywood installation in progress
Thu (30/04) | 30 Apr 2026 | P51 |  | Caisson formwork removal and hacking of bored pile at NB side
Thu (30/04) | 30 Apr 2026 | P49 |  | Preparing for 2nd lift casting. Pump car on site
Thu (30/04) | 30 Apr 2026 | P48 |  | 2nd lift rebar cage installation
Thu (30/04) | 30 Apr 2026 | P47 |  | Continue excavation for 2nd layer. 6 loads already send out as of now
Thu (30/04) | 30 Apr 2026 | P46 |  | Base plate welding for strut
Thu (30/04) | 30 Apr 2026 | P45 |  | 2nd SPT point testing in progress
Thu (30/04) | 30 Apr 2026 | P40 |  | Prepare tendon wire for pulling
Thu (30/04) | 30 Apr 2026 | P38 |  | Shear link installation
Thu (30/04) | 30 Apr 2026 | P36 |  | Working platform assembling
Thu (30/04) | 30 Apr 2026 | P36 |  | Secondary beam installation now no activity
Thu (30/04) | 30 Apr 2026 | P38 crosshead |  | Links installation for section 3 continue
Thu (30/04) | 30 Apr 2026 | P45 |  | SPT completed
Thu (30/04) | 30 Apr 2026 | P46 |  | Baseplate installation for s1 layer strut until 9pm
Thu (30/04) | 30 Apr 2026 | P48 |  | Column rebar cage installed. Stirrups installation at lapping area in progress
Thu (30/04) | 30 Apr 2026 | P11 |  | LF shifting
Thu (30/04) | 30 Apr 2026 | P10 |  | Upchainage to install LF here tonight after last bus
Thu (30/04) | 30 Apr 2026 | P7 |  | No more activity
Thu (30/04) | 30 Apr 2026 | P2 NB |  | Assembly of SH until 10pm
Sat (02/05) | 02 May 2026 | B2-03 | GL4-5.5 | Top bar installation in progress
Sat (02/05) | 02 May 2026 | B2-12, B2-14 | North side | PU grouting & bottom bar installation ongoing
Sat (02/05) | 02 May 2026 | Opening 3A |  | Unloading of rebars, B2-13, B2-15: Preparation works for lean concrete casting, B2-16: Currently no activity
Sat (02/05) | 02 May 2026 | B2-17, B2-18 |  | No activity. Was cast on Thursday
Sat (02/05) | 02 May 2026 | P25 |  | 1st lift column cast on last Thurs
Sat (02/05) | 02 May 2026 | P34 |  | 2nd lift column cast on last Tues
Sat (02/05) | 02 May 2026 | P36 |  | Crosshead Falsework - working platform installation
Sat (02/05) | 02 May 2026 | GL19-22 | North side | Drilling ongoing for skinwall rebar works, WH clearing loose plywod from roof soffit
Sat (02/05) | 02 May 2026 | GL22-24 | North side | PU grouting and skinwall rebar works ongoing
Sat (02/05) | 02 May 2026 | P38 |  | Crosshead formwork closing ongoing, target to cast tmr
Sat (02/05) | 02 May 2026 | P40 |  | Stressing completed. Base formwork dismantling in progress
Sat (02/05) | 02 May 2026 | CCE ramp | GL E8-GL32 | Excavation in progress (3 exc)
Sat (02/05) | 02 May 2026 | P42 |  | Preparation for PLT for crane parking location for upcoming LG installation works
Sat (02/05) | 02 May 2026 | P43 |  | Soil cut down for LG crane parking
Sat (02/05) | 02 May 2026 | CCE | South side, GL30-27 | Clearing hardcore and hacking works ongoing (4 exc), GL27-25: Continue coring and splitting works (4 machines)
Sat (02/05) | 02 May 2026 | CCE ramp GL18-17.5 |  | Currently no activity
Sat (02/05) | 02 May 2026 | P45 |  | 2nd lift column rebar fabrication works
Sat (02/05) | 02 May 2026 | P45 |  | SPT works in progress
Sat (02/05) | 02 May 2026 | P46 |  | Baseplate installation for s1 layer strut
Sat (02/05) | 02 May 2026 | P47 |  | 2nd layer excavation works
Sat (02/05) | 02 May 2026 | P48 |  | 2nd lift column RWDP installation
Sat (02/05) | 02 May 2026 | P51 |  | Excavation and soil clearing works ongoing
Sat (02/05) | 02 May 2026 | DR4 |  | Hoarding installation
Sat (02/05) | 02 May 2026 | P13 |  | No activity
Sat (02/05) | 02 May 2026 | P10 NR |  | Tonight 2 nos. of segments delivery
Sat (02/05) | 02 May 2026 | P7 |  | Tendon ducts preparation works
Sat (02/05) | 02 May 2026 | P2 |  | SH assembly works. Tonight to install at NB
Sat (02/05) | 02 May 2026 | B1-02 |  | Rebar works ongoing at corner area near B1-01 & formwork installation
Sat (02/05) | 02 May 2026 | B1-10 |  | PU grouting ongoing
Sat (02/05) | 02 May 2026 | CCW2 | North side | S5 waler beam installation in progress
Sat (02/05) | 02 May 2026 | CCW2 centre area |  | Drilling ongoing for blasting/relief holes
Sat (02/05) | 02 May 2026 | U3-35 to U3-38 |  | Continue excavation
Sat (02/05) | 02 May 2026 | B2-03 | GL4-5.5 | Top bar installation in progress
Sat (02/05) | 02 May 2026 | B2-12, B2-14 | North side | Bar chairs, drainage pipes installation ongoing
Sat (02/05) | 02 May 2026 | B2-13 | South side | Exposing couplers and preparing formwork for drop areas for lean con casting
Sat (02/05) | 02 May 2026 | B2-15 |  | Today to cast balance lean con, B2-16: Currently no activity
Sat (02/05) | 02 May 2026 | GL22-24 | North side | Skinwall rebar works in progress
Sat (02/05) | 02 May 2026 | P36 |  | Crosshead Falsework installation ongoing
Sat (02/05) | 02 May 2026 | P38 Crosshead |  | Preparation for final inspection
Sat (02/05) | 02 May 2026 | GL E9-VS |  | Continue RC wall rebar works and cleaning ongoing
Sat (02/05) | 02 May 2026 | CCE ramp | South side, GL32-30 | Excavation in progress (4 exc)
Sat (02/05) | 02 May 2026 | P40 |  | Continue base formwork dismantling
Sat (02/05) | 02 May 2026 | P42 |  | PLT ongoing for crane parking location
Sat (02/05) | 02 May 2026 | Zone 3 |  | LG truss connection works
Sat (02/05) | 02 May 2026 | CCE | South side, GL30-27 | Clearing hardcore and hacking works ongoing (4 exc), GL27-25: Continue coring and splitting works (4 machines). Currently workers on break
Sat (02/05) | 02 May 2026 | CCE ramp GL18-17.5 |  | Currently no activity
Sat (02/05) | 02 May 2026 | P45 |  | 2nd lift column rebar fabrication works
Sat (02/05) | 02 May 2026 | P45 |  | Continue SPT works
Sat (02/05) | 02 May 2026 | P46 |  | 1st layer cassion rebar and base plate installation works
Sat (02/05) | 02 May 2026 | P47 |  | Continue 2nd layer excavation works
Sat (02/05) | 02 May 2026 | P48 |  | RWDP installation
Sat (02/05) | 02 May 2026 | P51 |  | 5th layer NB hacking & excavation works
Sat (02/05) | 02 May 2026 | DR4 |  | Current hoarding installation status
Sat (02/05) | 02 May 2026 | P2 |  | SH for NB assembly completed. Tonight to install
Sat (02/05) | 02 May 2026 | P7 |  | Crosshead tendon duct preparation works ongoing. No activity for tendon duct installation
Sat (02/05) | 02 May 2026 | P16-P18 |  | Tendon grouting in progress
Sat (02/05) | 02 May 2026 | CCW1 | South side | Exposing couplers and hacking dwall surface to expose skin wall starter bars
Sat (02/05) | 02 May 2026 | CCW1 | North side | Formwork removal and today plan to continue waterproofing works
Sat (02/05) | 02 May 2026 | CCW2 | North side | Waler brackets installed. Currently no activity
Sat (02/05) | 02 May 2026 | CCW2 | South side | Drilling in progress for waler bracket works
Sat (02/05) | 02 May 2026 | U3-35 to U3-38 |  | Excavation and disposal in progress (2 exc, 1 telescopic)
Sat (02/05) | 02 May 2026 | B1-02 |  | Formwork installation in progress for skin wall
Sat (02/05) | 02 May 2026 | CCW2 centre area |  | ATC preparation works for blast/relief holes drilling. Blast #38 plan for next week
Sat (02/05) | 02 May 2026 | Exit 3 |  | Currently no activity
Mon (04/05) | 04 May 2026 | P31 |  | Working platform erection for 2nd lift
Mon (04/05) | 04 May 2026 | P10 NBR |  | 2nd pair stressing in progress
Mon (04/05) | 04 May 2026 | P7 crosshead |  | Preparation for PT duct installation
Mon (04/05) | 04 May 2026 | P51 | 5th layer caisson | Preparing for north side rebar works
Mon (04/05) | 04 May 2026 | P50 | 1st lift | Column rebar work ongoing
Mon (04/05) | 04 May 2026 | P49 |  | Working platform dismantling ongoing
Mon (04/05) | 04 May 2026 | P48 |  | Preparation for lean concrete prior to fwk closure
Mon (04/05) | 04 May 2026 | P47 |  | Excavation ongoing
Mon (04/05) | 04 May 2026 | Next to P45 |  | ASPT-03 ongoing, SPT 4 in progress
Mon (04/05) | 04 May 2026 | P45 | 1st lift | Column rebar ongoing
Mon (04/05) | 04 May 2026 | B1-02 |  | Skinwall formwork installation in progress
Mon (04/05) | 04 May 2026 | B1 area |  | Wall rebar planting and soffit roughening ongoing for wall rebar works
Mon (04/05) | 04 May 2026 | B2-02, B2-03 |  | Excavation in progress (2 exc)
Mon (04/05) | 04 May 2026 | CCW1 | North side | Currently no activity, CCW2 North side: Waler welding works ongoing
Mon (04/05) | 04 May 2026 | CCW2 |  | Blast #38 was done at 3pm. Now clearing rubber mats
Mon (04/05) | 04 May 2026 | CCW1 | South side | Exposing couplers
Mon (04/05) | 04 May 2026 | CCW2 | South side | Waler welding works ongoing
Mon (04/05) | 04 May 2026 | U3-38 |  | Excavation in progress (2 exc)
Mon (04/05) | 04 May 2026 | U3-37 |  | Currently no activity (2 exc, 1 mini standby)
Mon (04/05) | 04 May 2026 | B2-03 | GL4-5.5 | Welding works and cleaning ongoing. Plan for casting tmr
Mon (04/05) | 04 May 2026 | B2-12, B2-14 | North side | Rebar installation in progress
Mon (04/05) | 04 May 2026 | B2 | South side | B2-13: Coupler exposing and plywood installation in progress, B2-15: Plywood installation in progress, B2-16: Currently no activity
Mon (04/05) | 04 May 2026 | GL20 | North side | Skinwall rebar works in progress
Mon (04/05) | 04 May 2026 | GL22-24 | North side | RGT installation
Mon (04/05) | 04 May 2026 | GL24-26 | North side | Preparing to dismantle skinwall formwork
Mon (04/05) | 04 May 2026 | GL24-26 | near P34 | RC wall rebar works ongoing
Mon (04/05) | 04 May 2026 | GL32-Vent shaft |  | Centre section: Roof slab soffit roughening ongoing for wall rebar works, North side: Formwork installation in progress for RC wall
Mon (04/05) | 04 May 2026 | P2 |  | NB: to launch D01 tonight, SB: Upchainage rebar installation completed. Tonight to start formwork closing
Mon (04/05) | 04 May 2026 | CCE ramp | GL32 | Excavation in progress (3 exc)
Mon (04/05) | 04 May 2026 | CCE | South side, GL30-25 | Hacking & surveyor works ongoing at -16 (3 exc, 1 mini), Disposal works ongoing (1 exc), Coring and splitting ongoing (1 machine)
Mon (04/05) | 04 May 2026 | CCE | GL22-18 | Currently no excavation activity, 1 coring machine standby while waiting for next location, 2 coring machines working in progress (South side)
Mon (04/05) | 04 May 2026 | P38 crosshead |  | Casting in progress
Mon (04/05) | 04 May 2026 | B1-02 |  | Continue skinwall formwork installation
Mon (04/05) | 04 May 2026 | P7 |  | Continue PT duct installation
Mon (04/05) | 04 May 2026 | P10 |  | Continue stressing works
Mon (04/05) | 04 May 2026 | B1 area |  | Continue rebar planting for RC wall & soffit roughening for rebar works
Mon (04/05) | 04 May 2026 | CCW2 North & | South side | Waiting for waler concrete packing
Mon (04/05) | 04 May 2026 | CCW1 North |  | Currently no activity. Today WH did prep works prior to handing over to Maxbond for waterproofing works. Plan for Maxbond to start tmr
Mon (04/05) | 04 May 2026 | U3-38 |  | Continue excavation. Tonight no plan night shift here
Mon (04/05) | 04 May 2026 | CCW1 South |  | Continue exposing couplers
Mon (04/05) | 04 May 2026 | P02 |  | Segment lifter on site, preparation work ongoing for night work
Mon (04/05) | 04 May 2026 | B2-12, B2-14 | North side | Bottom rebar works & partial top bar installation in progress
Mon (04/05) | 04 May 2026 | B2-13 | South side | Partial bottom rebar works & continue plywood installation ongoing
Mon (04/05) | 04 May 2026 | B2-15 | South side | RGT installation & bottom rebar works ongoing
Mon (04/05) | 04 May 2026 | B2-16 |  | Currently no activity
Mon (04/05) | 04 May 2026 | GL20 | North side | Skinwall rebar works in progress
Mon (04/05) | 04 May 2026 | GL24-26 | near P34 | RC wall rebar works ongoing
Mon (04/05) | 04 May 2026 | GL32-Vent shaft |  | Centre section: Rebar planting in progress for wall rebar works, North side: Formwork installation in progress for RC wall and double slab
Mon (04/05) | 04 May 2026 | CCE ramp | South side, GL32-31 | Excavation in progress (3 exc)
Mon (04/05) | 04 May 2026 | CCE | South side, GL30-22 | Hacking ongoing at -16 (3 exc), 1 mini hacking to expose skinwall starter bars, Disposal works ongoing (2 exc), Coring and splitting ongoing (4 machines), Night shift: 4 operators (KTC), coring & splitting 2 machines
Mon (04/05) | 04 May 2026 | P36 |  | Falsework erection status
Tue (05/05) | 05 May 2026 | GL19.5-21 | North side | Skinwall rebar works and PU grouting ongoing
Tue (05/05) | 05 May 2026 | GL24-26 | North side | Skinwall formwork dismantling thereafter to shift to GL22-24, GL22-24: Scaffold platform dismantling ongoing
Tue (05/05) | 05 May 2026 | GL26-21 | near Opening 8 | RC wall rebar works ongoing
Tue (05/05) | 05 May 2026 | GL32 to VS |  | North side: RC wall & double slab formwork installation in progress, Centre & south side: Rebar planting in progress
Tue (05/05) | 05 May 2026 | CCE ramp | South side, GL32-31 | Excavation in progress (3 exc)
Tue (05/05) | 05 May 2026 | CCE | GL30-25 | Hacking ongoing at -16 and dwall surface hacking to expose skinwall starter bars (3 exc, 1 mini), Currently workers on break
Tue (05/05) | 05 May 2026 | CCE | GL24-22 | Sieving and internal shifting ongoing (1 exc), Coring and splitting works in progress (4 machines). Currently workers on break
Tue (05/05) | 05 May 2026 | CCE GL17.5 |  | Excavation ongoing (1 exc)
Tue (05/05) | 05 May 2026 | P32 |  | 1st lift formwork closing done
Tue (05/05) | 05 May 2026 | P13 |  | Currently no activity. Nightshift to adjust SB 1st pair
Tue (05/05) | 05 May 2026 | P10 NBR |  | 3rd pair stressing completed. Tendon wire cutting in progress. Tonight to launch 4th pair
Tue (05/05) | 05 May 2026 | P36 |  | Current status of working platform installation. WH installation of access for crosshead work
Tue (05/05) | 05 May 2026 | P45 |  | 2nd lift rebar cage fabrication. Friday will install the rebar cage
Tue (05/05) | 05 May 2026 | P45 |  | 2/8nos SPT test done
Tue (05/05) | 05 May 2026 | P46 |  | Current status of 1st layer caisson installation. LE preparing for strut installation also
Tue (05/05) | 05 May 2026 | P47 |  | Continue excavation for 2nd layer caisson
Tue (05/05) | 05 May 2026 | P2 SB upchainage |  | Stitching formwork 70% completed. To cast on Thursday night
Tue (05/05) | 05 May 2026 | P2 SB D01 |  | Segment launched last night
Tue (05/05) | 05 May 2026 | P48 |  | Preparing for formwork installation
Tue (05/05) | 05 May 2026 | P51 |  | Continue rebar work for balance caisson. To cast on Thursday
Tue (05/05) | 05 May 2026 | GL32 to VS |  | North side, RC wall & double slab formwork installation in progress, Centre & south side: Rebar planting in progress
Tue (05/05) | 05 May 2026 | P48 |  | Current status. no activity
Wed (06/05) | 06 May 2026 | GL32 to VS |  | North side: RC wall & double slab formwork installation in progress, Centre & south side: Rebar planting in progress
Wed (06/05) | 06 May 2026 | CCE Ramp / | GL22-28 | Rock coring/splitting by 4 machines & internal transfer by 2 excavators
Wed (06/05) | 06 May 2026 | CCE Ramp/ | GL25-30 | Continue rock hacking & internal transfer by 3 breakers & 2 excavators
Wed (06/05) | 06 May 2026 | CCE Ramp/ | GL30-32 | Continue excavation & internal transfer by 4 excavators
Wed (06/05) | 06 May 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Wed (06/05) | 06 May 2026 | P34 |  | 2nd lift formwork removal
Wed (06/05) | 06 May 2026 | P36 |  | Current status of working platform erection for crosshead work
Wed (06/05) | 06 May 2026 | P7 |  | Tendon duct installation in progress
Wed (06/05) | 06 May 2026 | P10 4th pair |  | Stressing completed. Strand cutting in progress
Wed (06/05) | 06 May 2026 | P51 |  | Balance area formwork closing
Wed (06/05) | 06 May 2026 | P48 |  | 2nd lift formwork closing
Wed (06/05) | 06 May 2026 | P47 SB |  | 2nd layer rebar work. NB: continue excavation
Wed (06/05) | 06 May 2026 | P46 |  | Preparing to extend excavation for caisson work
Wed (06/05) | 06 May 2026 | P47 |  | Current status of rebar cage fabrication
Thu (07/05) | 07 May 2026 | P18 |  | Grouting tube flushing
Thu (07/05) | 07 May 2026 | P31 |  | 2nd lift column rebar work started
Thu (07/05) | 07 May 2026 | P36 |  | Working platform installation for crosshead
Thu (07/05) | 07 May 2026 | P10 |  | Strand pushing for 5th pair stressing
Thu (07/05) | 07 May 2026 | P7 crosshead |  | PT duct installation, 5pax. Target to complete PT duct this week. Cast in items by next week
Thu (07/05) | 07 May 2026 | P51 |  | L5 caisson formwork closing at north side
Thu (07/05) | 07 May 2026 | P50 |  | No activity
Thu (07/05) | 07 May 2026 | P48 |  | 2nd lift column formwork closing
Thu (07/05) | 07 May 2026 | P47 |  | Excavation to L2 caisson level at north side
Thu (07/05) | 07 May 2026 | P46 |  | Excavation at north side
Thu (07/05) | 07 May 2026 | P31 |  | Continue 2nd lift rebar work
Thu (07/05) | 07 May 2026 | P36 |  | Working platform erection in progress. This week should be able to handover for rebar work
Thu (07/05) | 07 May 2026 | B2-14 & B2-15 |  | Continues top bar & formwork installation, target to cast on Sat
Thu (07/05) | 07 May 2026 | B2-27 |  | Continues formwork installation for skin wall
Thu (07/05) | 07 May 2026 | B2-38 / B2-39 |  | Rebar & formwork installation is in progress
Thu (07/05) | 07 May 2026 | P51 |  | Preparation for L5 caisson casting
Thu (07/05) | 07 May 2026 | P48 |  | 2nd lift column formwork closing
Thu (07/05) | 07 May 2026 | P47 |  | Excavation to L2 caisson level
Thu (07/05) | 07 May 2026 | P45 |  | 2nd lift column rebarwork completed
Thu (07/05) | 07 May 2026 | 800mm PW |  | Preparation work for pipe cleaning works
Thu (07/05) | 07 May 2026 | CCE Ramp/ | GL30-32 | Continue excavation & internal transfer by 4 excavators
Thu (07/05) | 07 May 2026 | CCE Ramp/ | GL25-30 | Continue rock hacking & internal transfer by 3 breakers & 1 excavator
Thu (07/05) | 07 May 2026 | CCE Ramp / | GL22-28 | Rock coring/splitting by 4 machines & internal transfer by 1 excavator
Thu (07/05) | 07 May 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Thu (07/05) | 07 May 2026 | P31 column 2nd lift |  | Main bar installation to continue until 10pm
Thu (07/05) | 07 May 2026 | P44 |  | Slope and barricade preparation for LG lifting tmr
Thu (07/05) | 07 May 2026 | P46 |  | 1st layer strut installation until 9pm
Thu (07/05) | 07 May 2026 | P51 |  | L5 caison casting
Thu (07/05) | 07 May 2026 | GL32 to VS |  | North side, Centre & south side: Rebar planting in progress, Manpower: 8 men
Thu (07/05) | 07 May 2026 | P2 |  | No activity yet. Tonight to cast SB wet stitch and install stressing cage at NB
Fri (08/05) | 08 May 2026 | CCE Ramp/ | GL E8 - 32 | Continue excavation & internal transfer by 3 excavators
Fri (08/05) | 08 May 2026 | CCE Ramp/ | GL30-24 | Continue rock hacking & internal transfer by 3 breakers & 3 excavators
Fri (08/05) | 08 May 2026 | CCE Ramp / | GL28-22 | Rock coring/splitting by 4 machines
Fri (08/05) | 08 May 2026 | CCE Ramp/ | GL19-17 | Continue excavation & internal transfer by 2 excavators
Fri (08/05) | 08 May 2026 | P51 |  | L5 caisson complete casting..no activity, concrete curing
Fri (08/05) | 08 May 2026 | P50 |  | 1st lift column formwork closing
Fri (08/05) | 08 May 2026 | P48 |  | Preparing casting platform and scaffolding
Fri (08/05) | 08 May 2026 | P47 |  | Excavation to L2 caisson level
Fri (08/05) | 08 May 2026 | P46 |  | S1 strut installation at south side
Fri (08/05) | 08 May 2026 | P45 |  | 4th number testing ongoing
Fri (08/05) | 08 May 2026 | Exit 1 stockpile |  | Soil internal shifting and disposal by 1 excavator
Fri (08/05) | 08 May 2026 | P51 |  | No activity
Fri (08/05) | 08 May 2026 | P50 |  | 1st lift column formwork closing
Fri (08/05) | 08 May 2026 | P48 |  | Scaffolding erection ongoing
Fri (08/05) | 08 May 2026 | P47 |  | Ground levelling
Fri (08/05) | 08 May 2026 | P45 |  | JGP Testing ongoing
Fri (08/05) | 08 May 2026 | P46 |  | No activity
Fri (08/05) | 08 May 2026 | P31 |  | 2nd lift rebar work in progress
Fri (08/05) | 08 May 2026 | P36 |  | Current status of working platform erection
Fri (08/05) | 08 May 2026 | P40 |  | Shifting of formwork materials
Fri (08/05) | 08 May 2026 | GL E9 to VS | North side | Formwork installation ongoing for RC wall
Fri (08/05) | 08 May 2026 | GL32-VS | Centre area | Soffit roughening ongoing for RC wall works
Fri (08/05) | 08 May 2026 | GL32-E9 |  | 2nd lift rebar works ongoing for RC wall
Fri (08/05) | 08 May 2026 | B2-12, B2-14 | North side | Cleaning and balance formwork installation ongoing
Fri (08/05) | 08 May 2026 | Exit 3 | B2-01 to B2-03 | Excavation in progress
Fri (08/05) | 08 May 2026 | CCW2 |  | Bracing installation in progress. Tmr plan for MPI test
Fri (08/05) | 08 May 2026 | CCW1 | North side | U3-39A rebar works in progress
Fri (08/05) | 08 May 2026 | CCW1 | South side | U3-39B, groove line cutting ongoing by WH, Survey works ongoing by Dongah for ventilation coring works
Tue (12/05) | 12 May 2026 | Exit 3 |  | B2-01 to B2-03 excavation & hacking in progress
Tue (12/05) | 12 May 2026 | S1-1 |  | Drilling ongoing for blast #42. Yesterday afternoon completed blast 41 at 3:20pm
Tue (12/05) | 12 May 2026 | P7 crosshead |  | NB side: links installation. Inspection at 6pm for formwork closing tonight, SB side: continue PT duct installation
Tue (12/05) | 12 May 2026 | U3-35 to U3-37 |  | Currently no activity
Tue (12/05) | 12 May 2026 | CCW2 |  | S5 struts installation in progress
Tue (12/05) | 12 May 2026 | CCW1 North |  | U3-39A rebar works in progress (14 men)
Tue (12/05) | 12 May 2026 | CCW1 South | U3-39B | PU grouting ongoing by Maxbond, Ventilation coring ongoing by Dongah
Tue (12/05) | 12 May 2026 | P48 |  | Curing & working platform removal
Tue (12/05) | 12 May 2026 | P51 |  | Cleaning & patching up caisson walls ongoing
Tue (12/05) | 12 May 2026 | B2-13, B2-15 |  | Bottom rebar works in progress, CJ roughening ongoing at B2-14
Tue (12/05) | 12 May 2026 | PW800 CH06-CH40 |  | Pipe cleaning works on going
Tue (12/05) | 12 May 2026 | P45 |  | Continue rebar cage for 2nd lift column, preparation work to install on Wednesday
Tue (12/05) | 12 May 2026 | GL16 | North side | PU grouting ongoing by Dongah
Tue (12/05) | 12 May 2026 | GL18-21 | North side | Hacking for skinwall ongoing
Tue (12/05) | 12 May 2026 | P36 |  | Continue working platform erection / rebar work
Tue (12/05) | 12 May 2026 | P32 |  | RWDP installation
Tue (12/05) | 12 May 2026 | GL E9 to VS |  | Internal rebar works ongoing for RC wall
Tue (12/05) | 12 May 2026 | GL E8 to | U3-06, GL32 | Hacking of bulging concrete ongoing. Today plan to lean con
Tue (12/05) | 12 May 2026 | U3-12 | South side, GL27 | Area preparation for earth mat works, Rock splitting ongoing
Tue (12/05) | 12 May 2026 | GL17 |  | Excavation ongoing
Tue (12/05) | 12 May 2026 | GL20-19 |  | Continue coring and splitting works
Tue (12/05) | 12 May 2026 | B1-02 |  | Dismantling skinwall formwork
Tue (12/05) | 12 May 2026 | B1-10 |  | Formwork installation for skinwall, Near B1-10/B1-08: Internal wall rebar works for RC wall
Tue (12/05) | 12 May 2026 | 800mm dia water pipe |  | 20% cleaning done. Tomorrow will have additional one team
Tue (12/05) | 12 May 2026 | Exit 3 |  | Excavation in progress
Tue (12/05) | 12 May 2026 | S1-1 |  | Area preparation for blast/relief holes drilling for blast #43. Blasting is scheduled for this Friday
Tue (12/05) | 12 May 2026 | S1-1 |  | Blast #42 scheduled for tmr
Tue (12/05) | 12 May 2026 | P7 |  | NB side section 1 links completed. Tonight to close formwork, SB side PT duct installation continue
Tue (12/05) | 12 May 2026 | P38 |  | Preparing to remove wing fwk
Tue (12/05) | 12 May 2026 | P13 SB |  | DC side need to adjust 4mm
Tue (12/05) | 12 May 2026 | P36 |  | Current status
Tue (12/05) | 12 May 2026 | P31 |  | RWDP installed
Tue (12/05) | 12 May 2026 | B2-13, B2-15 |  | Bottom rebar installation in progress, Continue CJ roughening at B2-12 & B2-14
Tue (12/05) | 12 May 2026 | Underplatform | GL17 | Excavation and soil internal shifting ongoing
Tue (12/05) | 12 May 2026 | GL18-21 | North side | Skinwall rebar works ongoing
Tue (12/05) | 12 May 2026 | GL29-27 | South side | Preparation ongoing for skinwall works
Tue (12/05) | 12 May 2026 | GL32-29 | South side | Skinwall rebar works ongoing
Tue (12/05) | 12 May 2026 | B2-39 to VS |  | Internal RC wall formwork installation in progress
Tue (12/05) | 12 May 2026 | Underplatform | GL32 | Hacking works ongoing
Tue (12/05) | 12 May 2026 | GL E9 to VS |  | Internal rebar works ongoing for RC wall
Tue (12/05) | 12 May 2026 | P50 |  | Curing
Tue (12/05) | 12 May 2026 | P47 |  | Concrete ordered for 2nd layer caisson casting
Tue (12/05) | 12 May 2026 | P45 |  | Preparing to install 2nd lift rebar cage
Tue (12/05) | 12 May 2026 | P46 |  | Manual excavation for balance 2nd layer caisson
Tue (12/05) | 12 May 2026 | P31 |  | No activity
Tue (12/05) | 12 May 2026 | P36 |  | Current status of crosshead formwork installation
Tue (12/05) | 12 May 2026 | P38 |  | No activity
Tue (12/05) | 12 May 2026 | P42 |  | LG main truss adjustment work
Tue (12/05) | 12 May 2026 | B1-10 |  | Formwork installation for skinwall, Near B1-10/B1-08: Internal wall rebar works for RC wall
Tue (12/05) | 12 May 2026 | CCW2 |  | S5 struts installation and clearing of materials. Target to preload this layer on Friday
Tue (12/05) | 12 May 2026 | CCW1 North | U3-39A | Continue rebar installation. Nightshift: 12 men + 1 sup
Tue (12/05) | 12 May 2026 | CCW1 South | U3-39B | Continue PU grouting and RGT installation, Currently no activity for ventilation coring works
Tue (12/05) | 12 May 2026 | P45 |  | Lifting of 2nd lift column rebar
Tue (12/05) | 12 May 2026 | P46 |  | Current excavation status at north side
Tue (12/05) | 12 May 2026 | P47 |  | L2 caisson formwork closing at south side. Tomorrow morning casting
Tue (12/05) | 12 May 2026 | P48 |  | No activity
Tue (12/05) | 12 May 2026 | P50 |  | No activity
Tue (12/05) | 12 May 2026 | P51 |  | No activity
Tue (12/05) | 12 May 2026 | P51 |  | Shifting of drilling rig for probing works at P51
Tue (12/05) | 12 May 2026 | S1-1 |  | No more activity. Tmr ATC to blast #42
Tue (12/05) | 12 May 2026 | Exit 3 |  | Night shift to continue disposal works (1 exc, 1 telescopic)
Tue (12/05) | 12 May 2026 | B2-13, B2-15 |  | Bottom rebar installation in progress, Continue CJ roughening at B2-12 & B2-14, 13 men
Tue (12/05) | 12 May 2026 | B2-39 to VS |  | Internal RC wall formwork installation currently no activity. Light power trip, WH electrician currently checking
Tue (12/05) | 12 May 2026 | P13 |  | No activity
Tue (12/05) | 12 May 2026 | P7 |  | Tendon duct installation at south side
Tue (12/05) | 12 May 2026 | P2 |  | Preparation work for starter hanger dismantling at south bound
Tue (12/05) | 12 May 2026 | U3-12 | GL27 | Area preparation for earth mat works & rock splitting ongoing
Tue (12/05) | 12 May 2026 | Underplatform | GL20-19 | Hacking ongoing (1 breaker)
Tue (12/05) | 12 May 2026 | GL17 |  | Excavation in progress (2 exc)
Tue (12/05) | 12 May 2026 | Underplatform | GL28-29 | Hacking and coring works ongoing (2 breakers, 1 coring machine, 1 exc)
Tue (12/05) | 12 May 2026 | P13 |  | NB required adjustment again. Around 10mm to match p14 alignment, SB: nth adjustment done last night. Pending surveyor to take reading for YWL confirmation
Wed (13/05) | 13 May 2026 | P35 |  | Preparing to install falsework
Wed (13/05) | 13 May 2026 | P36 |  | Pending rebar delivery tmr
Wed (13/05) | 13 May 2026 | P13 MJ 1st pair |  | Final adjustment completed for both bounds, NB Upchainage 5mm adjustment, SB downchainage 4mm adjustment, Now pending YWL confirmation
Wed (13/05) | 13 May 2026 | P38 |  | Formwork removal ongoing, shifting to P7
Wed (13/05) | 13 May 2026 | P3 SB |  | SH installation completed last night
Wed (13/05) | 13 May 2026 | P2 NB |  | Wet stitch formwork closing
Wed (13/05) | 13 May 2026 | P51 |  | Preparation work for Probing at West side
Wed (13/05) | 13 May 2026 | P50 |  | No activity
Wed (13/05) | 13 May 2026 | P49 |  | Platform casting
Wed (13/05) | 13 May 2026 | P48 |  | No activity
Wed (13/05) | 13 May 2026 | P47 |  | South side ready for concrete casting, north side formwork closing.. stagnant water pumping ongoing
Wed (13/05) | 13 May 2026 | P45 |  | 2nd lift column rebar works ongoing
Wed (13/05) | 13 May 2026 | 800mm PW |  | Pipe cleaning work in progress
Wed (13/05) | 13 May 2026 | P46 |  | Manual excavation at north side
Wed (13/05) | 13 May 2026 | P13 |  | Rubber seal install between segment and bearing plate
Wed (13/05) | 13 May 2026 | P7 | SB side | Continue Pt duct installation
Wed (13/05) | 13 May 2026 | P2 | NB side | Continue wet stitch formwork closing
Wed (13/05) | 13 May 2026 | P51 |  | Preparation work for probing
Wed (13/05) | 13 May 2026 | P49 |  | Platform casting completed
Wed (13/05) | 13 May 2026 | P47 |  | L2 caisson casting, at south and west side
Wed (13/05) | 13 May 2026 | P46 |  | Excavation for L1 caisson at north side
Wed (13/05) | 13 May 2026 | P45 |  | 2nd lift column rebar works
Wed (13/05) | 13 May 2026 | P31 |  | No activity
Wed (13/05) | 13 May 2026 | P32 |  | No activity
Wed (13/05) | 13 May 2026 | P35 |  | Column falsework erection ongoing
Wed (13/05) | 13 May 2026 | P36 |  | No activity
Wed (13/05) | 13 May 2026 | P38 |  | Crosshead formwork dismantling
Wed (13/05) | 13 May 2026 | B1-02-B1-04 |  | Skinwall formwork installation in progress
Wed (13/05) | 13 May 2026 | Near B1-08 |  | Formwork installation ongoing for internal RC wall
Wed (13/05) | 13 May 2026 | P45 |  | No activity
Wed (13/05) | 13 May 2026 | P46 |  | Current excavation status. No activity
Wed (13/05) | 13 May 2026 | P47 |  | L2 caisson casting on going
Wed (13/05) | 13 May 2026 | P51 |  | 3 nos probing completed. Balanxe 4nos at West side to be completed by tomorrow morning
Wed (13/05) | 13 May 2026 | Exit 3 |  | Nightshift continue excavation & disposal works (1 exc, 1 telescopic)
Wed (13/05) | 13 May 2026 | CCW2 |  | Last strut installation in progress (4/4). Target to complete works by tmr and preload on Friday
Wed (13/05) | 13 May 2026 | CCW1 North | U3-39A | Top bar and shearlinks installation in progress
Wed (13/05) | 13 May 2026 | CCW1 South | U3-39B | Right side: Maxbond started laying waterproofing membrane, Left side: Continue PU grouting by Maxbond, Currently no activity by Dongah for ventilation coring works
Wed (13/05) | 13 May 2026 | P13 |  | Steel plate installation as support for jack
Wed (13/05) | 13 May 2026 | P7 | SB side | Continue Pt duct installation
Wed (13/05) | 13 May 2026 | B2-13, B2-15 |  | Rebar installation in progress
Wed (13/05) | 13 May 2026 | GL16-18 | North side | Scaffold installation ongoing for skinwall works
Wed (13/05) | 13 May 2026 | GL20-22 | North side | Skinwall formwork installation in progress. Formwork moving from GL22-24
Wed (13/05) | 13 May 2026 | B2 | south side | Currently skinwall rebar works progressing ard GL28
Wed (13/05) | 13 May 2026 | P3 |  | Waiting crane to arrive for tonight starter hanger installation work
Wed (13/05) | 13 May 2026 | U3 | GL30-29 | Hacking ongoing
Wed (13/05) | 13 May 2026 | U3 | GL27 | Area preparation for earth mat works. Drilling rig currently on site, WH continue coring works
Wed (13/05) | 13 May 2026 | U3 | GL20-19 | WH continue boulder coring works (2 machines)
Wed (13/05) | 13 May 2026 | U3 GL17.5-17 |  | Nightshift continue excavation (2 exc)
Wed (13/05) | 13 May 2026 | U3-06 |  | Last night cast lean con. Currently exposing dwall couplers
Wed (13/05) | 13 May 2026 | P32 |  | Erection of working platform for 2nd lift rebar work
Wed (13/05) | 13 May 2026 | P31 |  | 2nd lift rebar work done. To continue with formwork closing
Thu (14/05) | 14 May 2026 | B2 | North side, GL16-18 | Scaffold erection in progress for skinwall works
Thu (14/05) | 14 May 2026 | B2 | North side, GL20-22 | Skinwall formwork installation in progress
Thu (14/05) | 14 May 2026 | B2 | North side, GL24-22 | Internal wall 1st lift rebar works in progress
Thu (14/05) | 14 May 2026 | B2 | North side, GL24-26 | Internal wall 1st lift formwork installation in progress
Thu (14/05) | 14 May 2026 | B2-39 to VS |  | Internal wall was cast last night at south side
Thu (14/05) | 14 May 2026 | B2-39 to VS |  | Continue internal wall rebar works at centre area
Thu (14/05) | 14 May 2026 | U3 | GL32-30 | Hacking, disposal works and lean con casting for sump pit in progress
Thu (14/05) | 14 May 2026 | U3-06 |  | Preparing formwork for drop areas & continue exposing couplers
Thu (14/05) | 14 May 2026 | U3 | GL27 | Drilling in progress by ATC for earth mat rod installation
Thu (14/05) | 14 May 2026 | U3 | GL20-29 | Coring and splitting in progress (3 machines)
Thu (14/05) | 14 May 2026 | U3 | GL17 | Excavation in progress (3 exc)
Thu (14/05) | 14 May 2026 | P45 |  | RWDP installation ongoing
Thu (14/05) | 14 May 2026 | P46 |  | Excavation completed and done lifting up excavator. Today afternoon lean con casting working platform, tomorrow wendyng will continue with caisson rebar work
Thu (14/05) | 14 May 2026 | P48 |  | Removing casting platform
Thu (14/05) | 14 May 2026 | P51 |  | Completed probing 5/7 nos at west side. Balance 2 nos probing to be completed before lunch. Today afternoon start strut removal
Thu (14/05) | 14 May 2026 | P13 1st pair |  | Filler plate installation in progress
Thu (14/05) | 14 May 2026 | P38 |  | Left with wing & bottom fwk removal
Thu (14/05) | 14 May 2026 | P36 |  | Crosshead bottom rebar ongoing
Thu (14/05) | 14 May 2026 | CCW1 South | U3-39B | Exposing couplers by CGW, Maxbond will continue waterproofing membrane laying & PU grouting once WH mini has cleared materials this afternoon. Currently mini is accessing on the area, Dongah coring machine currently breakdown. Will resume ventilation coring works once machine rectified today
Thu (14/05) | 14 May 2026 | CCW1 North | U3-39A | Shearlinks and formwork installation in progress, Cleaning ongoing. Plan for casting tmr
Thu (14/05) | 14 May 2026 | CCW2 |  | S5 struts lacing welding works. Plan for preloading tmr morning
Thu (14/05) | 14 May 2026 | S1-1 |  | Currently no activity. Blast #43 scheduled for tmr. ATC team is now at underplatform area for earth mat drilling works
Thu (14/05) | 14 May 2026 | Opening 3 |  | KTC continue disposal works
Thu (14/05) | 14 May 2026 | B2-03 | GL2-4 | Soil levelling ongoing in preparation for lean con casting today
Thu (14/05) | 14 May 2026 | P7 | SB side | PT duct installation continue. To complete today. Tmr to start cast in anchor installation, Saturday night to handover to Wendyng for links installation
Thu (14/05) | 14 May 2026 | P31 |  | 2nd lift current status
Thu (14/05) | 14 May 2026 | B2-13, B2-15 |  | Slab rebar works in progress
Thu (14/05) | 14 May 2026 | B2 | North side, GL18-20 | Skinwall rebar works in progress
Thu (14/05) | 14 May 2026 | B2 | North side, GL20-22 | Skinwall formwork installation ongoing
Thu (14/05) | 14 May 2026 | B2 | South side, GL28-27 | Skinwall rebar works ongoing
Thu (14/05) | 14 May 2026 | P2 NB |  | Wet stitch formwork closing continue. Est 40% completed
Thu (14/05) | 14 May 2026 | B2-39 to VS |  | Soffit roughening ongoing for 2nd lift rebar works
Thu (14/05) | 14 May 2026 | U3 | North side, GL32-31 | Start to excavate. Access is temporarily blocked
Thu (14/05) | 14 May 2026 | U3 | South side, GL32-31 | Continue hacking works
Thu (14/05) | 14 May 2026 | U3-06 |  | Continue exposing couplers, Formwork installation for drop areas. Plan for lean con casting today, Hacking dwall surface to expose skinwall starter bars
Thu (14/05) | 14 May 2026 | P48 |  | Column formwork dismantling
Thu (14/05) | 14 May 2026 | P47 |  | L2 caisson rebar works at north side ongoing
Thu (14/05) | 14 May 2026 | P46 |  | Lean con casting completed for working platform
Thu (14/05) | 14 May 2026 | P45 |  | RWDP installation ongoing
Thu (14/05) | 14 May 2026 | B2 | North side, GL24-26 | Internal wall 1st lift formwork installation in progress
Thu (14/05) | 14 May 2026 | B2 | North side, GL24-26 | Internal wall 1st lift formwork installation in progress
Thu (14/05) | 14 May 2026 | B2-13, B2-15 |  | Slab rebar works and RTO inspection ongoing, Dongah installing post-drill rebars at B2-15
Fri (15/05) | 15 May 2026 | P38 |  | Bottom fwk removal ongoing
Fri (15/05) | 15 May 2026 | P36 |  | Crosshead rebar work in progress
Fri (15/05) | 15 May 2026 | P32 |  | 2nd lift column rebar work ongoing
Fri (15/05) | 15 May 2026 | P13 |  | NB: strand Pushing for temporary stressing, SB: still need to adjust as per YWL requirement
Fri (15/05) | 15 May 2026 | P7 SB |  | PT duct installation completed. Support bar installation in progress. Tmr to install cast in anchor
Fri (15/05) | 15 May 2026 | P2 NB |  | Stitching formwork closing continue
Fri (15/05) | 15 May 2026 | P3-P4 side |  | Material clearing for crane parking tonight to launch P3 SB U01
Fri (15/05) | 15 May 2026 | S1-1 |  | Blast #43 done at 1550hrs
Fri (15/05) | 15 May 2026 | B2-03 | GL2-4 | Lean con was cast yesterday
Fri (15/05) | 15 May 2026 | CCW2 |  | MPI test was just completed for S5 struts. Preloading will be done soon. Delayed due to heavy downpour this morning
Fri (15/05) | 15 May 2026 | CCW1 North | U3-39A | To cast today
Fri (15/05) | 15 May 2026 | CCW1 South | U3-39B | Ventilation coring works by Dongah completed, Waterproofing works by Maxbond ongoing
Fri (15/05) | 15 May 2026 | P35 |  | Current status of falsework installation
Fri (15/05) | 15 May 2026 | B2-13, B2-15 |  | Rebar works in progress
Fri (15/05) | 15 May 2026 | B2 | North side, GL20-22 | Skinwall formwork installation in progress
Fri (15/05) | 15 May 2026 | B2 | North side, GL24-26 | Internal wall formwork installation ongoing
Fri (15/05) | 15 May 2026 | B2-39 to VS |  | Centre: Formwork installation ongoing for RC wall, North side: 2nd lift wall rebar works
Fri (15/05) | 15 May 2026 | U3 | GL17 | Excavation in progress, GL20-18: Disposal and coring/splitting works ongoing
Fri (15/05) | 15 May 2026 | U3 | GL27 - Earth Mat | Copper rod installation completed for 14 boreholes, Now preparing for earth enhancement material filling, Tomorrow plan to take individual borehole earth test value
Fri (15/05) | 15 May 2026 | U3-06 |  | Continue exposing couplers. Yesterday cast drop areas, now removing formwork support
Fri (15/05) | 15 May 2026 | P51 |  | S2 strut removal ongoing
Fri (15/05) | 15 May 2026 | P48 |  | 2nd lift column formwork removal
Fri (15/05) | 15 May 2026 | P47 |  | L2caisson formwork installation at north side, target tomorrow casting
Fri (15/05) | 15 May 2026 | P45 |  | 2nd lift column rebar works ongoing
Fri (15/05) | 15 May 2026 | P46 |  | L1 caisson rebar work at north side
Sat (16/05) | 16 May 2026 | P7 crosshead SB |  | PT duct inspection at 11 am. This afternoon links installation can start
Sat (16/05) | 16 May 2026 | CCW1 South | U3-39B | Waterpoofing works ongoing & to complete today. Area plan be handed over to CGW today
Sat (16/05) | 16 May 2026 | CCW1 North | U3-39A | Casting completed
Sat (16/05) | 16 May 2026 | CCW2 |  | S5 struts preloaded yesterday. Only balance welding works now ongoing
Sat (16/05) | 16 May 2026 | B2 column C02-1 |  | Scaffold platform installation ongoing
Sat (16/05) | 16 May 2026 | B2-13, B2-15 |  | Top bar installation in progress. Plan for casting on Tuesday
Sat (16/05) | 16 May 2026 | P2 NB |  | Formwork closing continue. Est 70% completed
Sat (16/05) | 16 May 2026 | B2 | North side, GL16-18 | Skinwall rebar works ongoing and preparing drilling for tie rod holes
Sat (16/05) | 16 May 2026 | B2 | North side, GL20-22 | Skinwall formwork installation in progress
Sat (16/05) | 16 May 2026 | B2 | North side, GL24-26 | Formwork installation ongoing for RC wall and double slab
Sat (16/05) | 16 May 2026 | B2-39 to VS |  | 2nd lift wall rebar installation in progress
Sat (16/05) | 16 May 2026 | U3-06 |  | Continue exposing couplers & hacking at barette pile area, Dongah preparing for PU grouting at dwall side
Sat (16/05) | 16 May 2026 | U3-08 |  | Continue excavation. Today plan to partial lean con the area
Sat (16/05) | 16 May 2026 | Zone 4 |  | Sheltered linkway construction status
Sat (16/05) | 16 May 2026 | U3 | GL27 | APP preparing mixture for earth enhancement material filling for rod boreholes, U3 GL26-25:, ATC and WH preparing to continue drilling works and ground respectively for earth mat works
Sat (16/05) | 16 May 2026 | U3 | GL17 | Continue excavation, U3 GL20-19: Continue coring/splitting and hacking works
Sat (16/05) | 16 May 2026 | P31 |  | Column 2nd lift formwork closing
Sat (16/05) | 16 May 2026 | P35 |  | Crosshead falsework primary beam installation
Sat (16/05) | 16 May 2026 | P36 |  | Crosshead rebar installation in progress
Sat (16/05) | 16 May 2026 | P38 |  | Strand pushing for stressing work
Sat (16/05) | 16 May 2026 | CCW1 South | U3-39B | RGT installation ongoing, Remaining waterproofing membrane to be installed at drop area. Currently CGW is exposing the couplers and some cleaning works
Sat (16/05) | 16 May 2026 | CCW1 North | U3-39A | Curing
Sat (16/05) | 16 May 2026 | B2 Column C02-1 |  | Formwork installation in progress
Sat (16/05) | 16 May 2026 | S1-1 |  | Drilling ongoing for blast/relief holes. Blast #44 scheduled for Monday
Sat (16/05) | 16 May 2026 | B2 Column C01-1 |  | Formwork installation in progress
Sat (16/05) | 16 May 2026 | B2-13, B2-15 |  | Continue top bars installation
Sat (16/05) | 16 May 2026 | B2 | North side, GL16-18 | Skinwall works ongoing
Sat (16/05) | 16 May 2026 | B2 | North side, GL20-22 | Preparation ongoing for skinwall casting
Sat (16/05) | 16 May 2026 | B2 | North side, GL24-26 | Internal wall formwork installation ongoing for 1st lift
Sat (16/05) | 16 May 2026 | B2 | south side | No activity
Sat (16/05) | 16 May 2026 | B2-39 to VS |  | Formwork removal for inner RC wall, Continue 2nd lift wall rebar works at outer side
Sat (16/05) | 16 May 2026 | P13 |  | TPT installation. Target to install concrete blocks on Monday for FBCM
Sat (16/05) | 16 May 2026 | P7 SB |  | PT duct inspection completed. Tonight to start links installation
Sat (16/05) | 16 May 2026 | P2 NB |  | Wet stitching formwork balance at the wing form. To complete tonight
Sat (16/05) | 16 May 2026 | U3-06 |  | Continue exposing couplers
Sat (16/05) | 16 May 2026 | U3-08 |  | Continue clearing soil and hacking works
Sat (16/05) | 16 May 2026 | U3 | Earth Mat, GL27-25 | WH continue hacking and preparing area for ATC to continue drilling works, WH continue coring/splitting works, APP continue filling rod boreholes with earth enhancement mixture
Sat (16/05) | 16 May 2026 | U3 | GL20-19 | Continue coring/splitting and rock disposal
Sat (16/05) | 16 May 2026 | U3 | GL17 | Excavation progressing towards GL16
Sat (16/05) | 16 May 2026 | Exit 2 |  | Hirose start strut removal
Sat (16/05) | 16 May 2026 | B1-09 |  | Skinwall rebar works ongoing
Mon (18/05) | 18 May 2026 | P18 |  | Working platform dismantling
Mon (18/05) | 18 May 2026 | P35 |  | Pending netting for working platform
Mon (18/05) | 18 May 2026 | P36 |  | Current status for crosshead rebar
Mon (18/05) | 18 May 2026 | P51 |  | Clearing stagnant water. Today to start pile cap rebar work
Mon (18/05) | 18 May 2026 | DR4 |  | Removal of hardcore and levelling
Mon (18/05) | 18 May 2026 | P47 |  | Formwork removal at NB side. Tomorrow will start day and night excavation work
Mon (18/05) | 18 May 2026 | P46 |  | Balance 1st layer caisson can finish by tomorrow
Mon (18/05) | 18 May 2026 | P45 |  | Shear link installation for 2nd lift
Mon (18/05) | 18 May 2026 | P7 |  | Formwork closing
Mon (18/05) | 18 May 2026 | P2 SB |  | LF modification in progress
Mon (18/05) | 18 May 2026 | P2 NB |  | Wet stitching formwork final inspection completed. Casting tonight
Mon (18/05) | 18 May 2026 | B1-09 |  | RGT installation ongoing at skinwall area
Mon (18/05) | 18 May 2026 | S1-1 |  | Blast #44 was done this afternoon ard 3:40pm, KTC is now clearing the area (2 exc, 1 telescopic), Currently no access to CCW as the soil from the blasting works need to cut down
Mon (18/05) | 18 May 2026 | P31 |  | 2nd lift column formwork closing continue until 930pm
Mon (18/05) | 18 May 2026 | CCW1 South | U3-39B | Bottom rebar works in progress
Mon (18/05) | 18 May 2026 | B2-03 |  | Currently no activity. KTC is hoisting up excavator from the area
Mon (18/05) | 18 May 2026 | P35 falsework |  | Lip channel installation in progress, until 930 pm
Mon (18/05) | 18 May 2026 | P36 crosshead |  | Main bar installation to complete tonight. Tmr steel anchor can start installation
Mon (18/05) | 18 May 2026 | B2-13, B2-15 |  | Shearlinks installation & cleaning ongoing. Plan for casting tmr
Mon (18/05) | 18 May 2026 | B2 | GL18 | Skinwall rebar works ongoing
Mon (18/05) | 18 May 2026 | B2 | North side, GL22-26 | Formwork installation in progress for 1st lift wall and double slab
Mon (18/05) | 18 May 2026 | B2-39 to VS |  | Houskeeping ongoing
Mon (18/05) | 18 May 2026 | B2 | south side | Currently no activity
Mon (18/05) | 18 May 2026 | P46 |  | 1st layer caison formwork closing
Mon (18/05) | 18 May 2026 | P47 |  | 2nd layer caison formwork dismantling
Mon (18/05) | 18 May 2026 | P51 |  | Water pumping. No other activity
Mon (18/05) | 18 May 2026 | U3-08 |  | Continue clearing hardcores/rocks. Tonight plan for partial lean con casting
Mon (18/05) | 18 May 2026 | U3-06 |  | Slab patch up works & surface inspection were done. Tonight plan preparation for dwall ST160 rectification and tmr plan for waterproofing membrane laying
Mon (18/05) | 18 May 2026 | U3 | Earth mat, GL27-26 | APP continue cable laying for rod boreholes and target to complete today. Tmr plan for inspection & combined earth resistance test for 16 boreholes
Mon (18/05) | 18 May 2026 | U3 | GL16 | Excavation in progress
Mon (18/05) | 18 May 2026 | P7 crosshead |  | Formwork closing and cast in anchor installation. Tonight plan to complete formwork closing
Mon (18/05) | 18 May 2026 | P2 SB |  | LF assembly to continue until 10pm
Mon (18/05) | 18 May 2026 | P2 NB wet stitch |  | To cast tonight after last bus
Tue (19/05) | 19 May 2026 | P32 |  | 2nd lift rebar work
Tue (19/05) | 19 May 2026 | P31 |  | Working platform erection for 2nd lift casting
Tue (19/05) | 19 May 2026 | P35 |  | Current status of working platform erection. P36: WH team started ducting work
Tue (19/05) | 19 May 2026 | DR4 |  | No activity
Tue (19/05) | 19 May 2026 | P51 |  | Pile cap rebar work start..straighten bored pile rebar
Tue (19/05) | 19 May 2026 | P2 NB |  | Wet stitch cast last night
Tue (19/05) | 19 May 2026 | P45 |  | Preparation platform for column works
Tue (19/05) | 19 May 2026 | P46 |  | L1 caisson rebar works at north side
Tue (19/05) | 19 May 2026 | P47 |  | Excavation to L3 caisson start
Tue (19/05) | 19 May 2026 | P36 |  | Anchor installation ongoing
Tue (19/05) | 19 May 2026 | P38 |  | 1st stage stressing done
Tue (19/05) | 19 May 2026 | CCW1 South |  | U3-39B bottom rebar installation in progress
Tue (19/05) | 19 May 2026 | S1-1 |  | Disposal ongoing, ATC works done for the day. Tmr plan for blast #45
Tue (19/05) | 19 May 2026 | CCW | GL-W5 | Excavation ongoing to -13.5
Tue (19/05) | 19 May 2026 | U3-35 |  | Excavation in progress at ard GL3
Tue (19/05) | 19 May 2026 | B2-13, B2-15 |  | Preparing for casting. Concrete otw
Tue (19/05) | 19 May 2026 | B2 | North side, GL17-20 | Skinwall rebar works in progress
Tue (19/05) | 19 May 2026 | U3-06 |  | Today started waterproofing membrane laying, Patch up works at drop areas, RGT installation
Tue (19/05) | 19 May 2026 | U3-08 |  | Preparing formwork for drop areas. Plan to lean con tmr, Hacking ongoing at dwall surface to expose skinwall starter bars
Tue (19/05) | 19 May 2026 | U3 | Earth mat, GL27 | Combined earth resistance test for 16 points was done earlier today and achieved less than 1 ohm
Tue (19/05) | 19 May 2026 | U3 | GL26-25 | Continue hacking & coring/splitting works
Tue (19/05) | 19 May 2026 | U3 | GL16 | Continue excavation
Wed (20/05) | 20 May 2026 | B2 | North side, GL17-19 | Skinwall rebar works and PU grouting ongoing
Wed (20/05) | 20 May 2026 | B2 | North side, GL22-26 | Today plan to cast internal 1st lift wall and double slab
Wed (20/05) | 20 May 2026 | U3-06 |  | Continue waterproofing membrane laying & PU grouting works
Wed (20/05) | 20 May 2026 | U3-08 |  | Formwork installation in progress for drop areas. Plan for lean con today, Coupler exposing ongoing and ground levelling
Wed (20/05) | 20 May 2026 | U3 | Earth mat, GL26-25 | Today plan to complete individual borehole earth resistance test for 10 points, U3 GL27-26 (Earth mat):, Yesterday completed combined earth resistance test for 16 points. Today to continue soil backfill
Wed (20/05) | 20 May 2026 | Exit 2 |  | Last strut removal ongoing (12/12)
Wed (20/05) | 20 May 2026 | P16-17 |  | 2nd stage PT duct pipe grouting
Wed (20/05) | 20 May 2026 | P13 SB |  | Working platform for concrete block installation completed, 4pm to start erection at NB
Wed (20/05) | 20 May 2026 | P7 crosshead |  | 28/32 cast in anchor installed, scheduled for casting tmr
Wed (20/05) | 20 May 2026 | P2 SB |  | LF 1/2 assembly completed
Wed (20/05) | 20 May 2026 | P31 2nd lift started, total vol |  | 73m3
Wed (20/05) | 20 May 2026 | P35 |  | Working platform erection ongoing
Wed (20/05) | 20 May 2026 | P32 |  | 2nd lift rebar work ongoing
Wed (20/05) | 20 May 2026 | P35 |  | Scaffold access erection status. No activity observed
Wed (20/05) | 20 May 2026 | P36 |  | No activity for PT duct installation
Wed (20/05) | 20 May 2026 | S1-1 |  | Blast #45 completed at 1423hrs just now. Currently KTC clearing rocks and prepare area for next blasting location (3 exc, 1 telescopic)
Wed (20/05) | 20 May 2026 | CCW1 South |  | U3-39B bottom rebar works ongoing, Day: 15 men, Night: 8 men
Wed (20/05) | 20 May 2026 | CCW2 | GL-W5 | Excavation ongoing to -13.5
Wed (20/05) | 20 May 2026 | U3-35 |  | Excavation in progress (2 exc)
Wed (20/05) | 20 May 2026 | B2-13, B2-15 |  | Curing
Wed (20/05) | 20 May 2026 | P51 |  | Pile cap rebars continue, Nightshift: 7 pax
Wed (20/05) | 20 May 2026 | B2 | GL16-18 | Skinwall PU grouting ongoing
Wed (20/05) | 20 May 2026 | U3-06 |  | Started coupler bar & bottom rebar installation this afternoon, Maxbond continue waterproofing membrane laying
Wed (20/05) | 20 May 2026 | U3 | Earth mat, GL27-26 | Soil backfill done for 16 points, U3 GL26-25 (Earth mat):, Individual earth resistance test was done for 10 points today, Currently WH is doing hacking works here
Wed (20/05) | 20 May 2026 | U3-08 |  | Hacking dwall surface to expose skinwall starter bars, Formwork installation ongoing at KPs drop areas. Tonight to cast lean con
Wed (20/05) | 20 May 2026 | U3 | GL16 | Excavation to continue nightshift (3 exc)
Wed (20/05) | 20 May 2026 | P7 |  | Cast in anchor installation continue. Balance 2 nos
Thu (21/05) | 21 May 2026 | U3-08 |  | Lean con cast at drop slab area & continue hacking dwall surface to expose skinwall starter bars
Thu (21/05) | 21 May 2026 | U3-06 |  | Continue unloading and installing bottom rebar, RGT installation & PU grouting ongoing
Thu (21/05) | 21 May 2026 | U3 | GL25 | Continue hacking and area preparation for earth mat works
Thu (21/05) | 21 May 2026 | U3 | GL19-16 | Continue excavation and hacking works
Thu (21/05) | 21 May 2026 | P13 NB |  | Scaffold erection continue. Today to complete
Thu (21/05) | 21 May 2026 | P7 crosshead |  | Final inspection completed. Awaiting for surveyor report on the alignment. Target to cast at 2pm
Thu (21/05) | 21 May 2026 | P35 |  | Netting & access erection ongoing
Thu (21/05) | 21 May 2026 | P36 |  | Ducting work ongoing, manpower: 6
Thu (21/05) | 21 May 2026 | P51 |  | Bottom rebar for pile cap
Thu (21/05) | 21 May 2026 | P45 |  | No activity
Thu (21/05) | 21 May 2026 | P47 |  | Excavation to L3 caisson level
Thu (21/05) | 21 May 2026 | P49 |  | Concrete block preparation for DR4
Thu (21/05) | 21 May 2026 | P32 |  | 2nd lift shear link installation. P31: 2nd lift already cast
Thu (21/05) | 21 May 2026 | P35 |  | Working platform installation done. Surveyor marking and will continue with jack installation for crosshead rebar work
Thu (21/05) | 21 May 2026 | P16 |  | Preparation for segment 2nd stage grouting works
Thu (21/05) | 21 May 2026 | P36 |  | Continue ducting work
Thu (21/05) | 21 May 2026 | P7 |  | Pump car setting up for casting. 1st lorry est to arrive by 4pm
Thu (21/05) | 21 May 2026 | Zone 4 near junction |  | Lane closure for road rectification. Will open back before peak hour
Thu (21/05) | 21 May 2026 | P46 |  | Last part formwork closing for caisson
Thu (21/05) | 21 May 2026 | P47 |  | Continue excavation for 3rd layer caisson
Thu (21/05) | 21 May 2026 | P51 |  | Pile cap bottom rebar installation ongoing
Thu (21/05) | 21 May 2026 | P2 |  | 2nd LF completed
Thu (21/05) | 21 May 2026 | P7 crosshead |  | 1st truck on site for casting
Fri (22/05) | 22 May 2026 | B2 | North side, GL18 | Skinwall PU grouting
Fri (22/05) | 22 May 2026 | U3-06 |  | Continue coupler bar and bottom bar installation
Fri (22/05) | 22 May 2026 | U3 | GL30-28 | Currently no activity, U3 GL28-26: Lean con cast, U3 GL26-24: Continue coring and hacking works
Fri (22/05) | 22 May 2026 | U3 | GL15 | Excavation and disposal in progress
Fri (22/05) | 22 May 2026 | P16-17 |  | Segment 2nd stage grouting
Fri (22/05) | 22 May 2026 | P46 |  | Today will cast balance 2nd layer caisson
Fri (22/05) | 22 May 2026 | P47 |  | Excavator break down. Will replace with mini. Tonight plan to lean concrete 50% for 3rd layer caisson
Fri (22/05) | 22 May 2026 | P51 |  | Bottom bar for pile cap almost done. Lowering down bar chair for top bar work
Fri (22/05) | 22 May 2026 | P36 |  | Bottom rebar tying by wendyng & continue sealing anchor gaps by wh
Fri (22/05) | 22 May 2026 | P35 |  | Preparing for bottom fwk installation
Fri (22/05) | 22 May 2026 | P31 |  | Curing, P32: rebar done, arranging & preparing to install RWDP
Fri (22/05) | 22 May 2026 | CCW1 South |  | U3-39B rebar installation in progress
Fri (22/05) | 22 May 2026 | CCW2 W5-6 |  | Excavation in progress to -13.5, Hacking works ongoing
Fri (22/05) | 22 May 2026 | CCW1 North |  | Preparation ongoing for S5 strut removal. Hirose just mobilised their excavator. Plywood laid for excavator to facilitate the removal works
Fri (22/05) | 22 May 2026 | S1-1 |  | Blast #46 was completed at 1520hrs, KTC continue soil disposal works at Opening 3, U3-35 excavation ongoing ard GL4
Fri (22/05) | 22 May 2026 | DR4 |  | Now no activity of probing. WH pulling cables for internal lighting
Fri (22/05) | 22 May 2026 | P51 |  | Bottom bar completed. Bar chair installation for top bar work
Fri (22/05) | 22 May 2026 | B1-09 |  | Skinwall formwork installation
Fri (22/05) | 22 May 2026 | U3-06 |  | Rebar works & PU grouting in progress
Fri (22/05) | 22 May 2026 | U3-10 | GL30-28 | Lean con was done for slab area, Survey works ongoing for sump pit prior to lean con casting
Fri (22/05) | 22 May 2026 | U3 | GL15 | Excavation in progress towards GL14
Sat (23/05) | 23 May 2026 | P45 |  | Concrete spacer installation for column formwork
Sat (23/05) | 23 May 2026 | P46 |  | L1 caisson casting completed. Curing, no activity
Sat (23/05) | 23 May 2026 | P47 |  | Manual hacking at north side. Preparation to lift up mini excavator
Sat (23/05) | 23 May 2026 | P49 |  | Concrete block completed 3nos for DR4
Sat (23/05) | 23 May 2026 | P51 |  | Pile cap top bar installation
Sat (23/05) | 23 May 2026 | DR4 |  | Probing works paused due to air compressor problem
Sat (23/05) | 23 May 2026 | P13 |  | Platform installation for precast concrete packer
Sat (23/05) | 23 May 2026 | P10 |  | LF dismantling in progress..to be shifted to zone 1
Sat (23/05) | 23 May 2026 | P7 |  | Curing, no activity
Sat (23/05) | 23 May 2026 | P6 |  | Material shifting and housekeeping
Sat (23/05) | 23 May 2026 | P2 |  | LF installation completed at SB
Sat (23/05) | 23 May 2026 | P3 |  | No activity
Sat (23/05) | 23 May 2026 | P13 |  | Platform installation for precast concrete packer
Sat (23/05) | 23 May 2026 | P32 |  | Preparation for column formwork
Sat (23/05) | 23 May 2026 | P35 |  | Crosshead wing formwork installation
Sat (23/05) | 23 May 2026 | P36 |  | Tendon duct installation
Sat (23/05) | 23 May 2026 | P40 |  | Scaffolding erection
Sat (23/05) | 23 May 2026 | P45 |  | Preparation for formwork closing
Sat (23/05) | 23 May 2026 | P47 |  | Ready for working platform lean con at North side
Sat (23/05) | 23 May 2026 | P51 |  | Pile cap top rebar installation work
Sat (23/05) | 23 May 2026 | P31 |  | Curing. No activity
Sat (23/05) | 23 May 2026 | P32 |  | Preparation for formwork closing
Sat (23/05) | 23 May 2026 | P35 |  | Crosshead bottom formwork installation
Sat (23/05) | 23 May 2026 | P36 |  | Tendon duct installation
Mon (25/05) | 25 May 2026 | P51 |  | Shear link and column starter bar installation. Target tomorrow casting
Mon (25/05) | 25 May 2026 | DR4 |  | Pumping out water for CCTV inspection
Mon (25/05) | 25 May 2026 | DR4 |  | Probing 15 points done. 4 points found obstruction
Mon (25/05) | 25 May 2026 | P50 |  | Soil compaction. Arranged for NDT test
Mon (25/05) | 25 May 2026 | P36 |  | Continue tendon duct installation by ICE, 6 workers
Mon (25/05) | 25 May 2026 | P35 |  | Fwk installation status
Mon (25/05) | 25 May 2026 | P2 |  | No activity
Mon (25/05) | 25 May 2026 | P13 |  | Preparation for concrete block hoisting works
Mon (25/05) | 25 May 2026 | P47 |  | Access erection for 3rd layer caisson rebar work
Mon (25/05) | 25 May 2026 | P46 |  | S1 layer horizontal strut installation
Mon (25/05) | 25 May 2026 | P30 |  | No activity
Mon (25/05) | 25 May 2026 | P31 |  | Current casting platform dismantling status. No activity
Mon (25/05) | 25 May 2026 | P32 |  | No activity
Mon (25/05) | 25 May 2026 | P35 |  | Preparation for crosshead rebar work
Mon (25/05) | 25 May 2026 | P36 |  | Tendon duct installation
Mon (25/05) | 25 May 2026 | P40 |  | Scaffolding erection completed. No activity
Mon (25/05) | 25 May 2026 | U3-06 |  | Rebar works in progress
Mon (25/05) | 25 May 2026 | U3-10 |  | Sump pit formwork installation in progress
Mon (25/05) | 25 May 2026 | U3 | GL15 | Excavation in progress
Mon (25/05) | 25 May 2026 | U3 | GL26-25 | Currently no activity. Workers on dinner break
Mon (25/05) | 25 May 2026 | P46 |  | S1 strut installation ongoing
Mon (25/05) | 25 May 2026 | P50 |  | Current backfilling status
Mon (25/05) | 25 May 2026 | P51 |  | Pile cap shear links installation. Target tomorrow casting
Mon (25/05) | 25 May 2026 | B2 | GL-E9 | Soffit roughening ongoing for internal wall rebar planting
Mon (25/05) | 25 May 2026 | B2 GL18-20.5 | North side | Skinwall formwork shifting & installation in progress
Mon (25/05) | 25 May 2026 | B2-16 |  | Excavation in progress (3 exc, 1 telescopic), about 80% completed
Mon (25/05) | 25 May 2026 | B2 Column C03-2 |  | Formwork installation in progress
Mon (25/05) | 25 May 2026 | B2 Column C02-1 |  | Formwork removal ongoing
Mon (25/05) | 25 May 2026 | B2-03 |  | Drainage pipe installation & rebar works ongoing, CGW night manpower: 6 men
Mon (25/05) | 25 May 2026 | B2-01 |  | Clearing debris, B2-02: Partial waterproofing membrane installation
Mon (25/05) | 25 May 2026 | P13 |  | Preparation for precast concrete packer installation
Mon (25/05) | 25 May 2026 | P13 |  | Shifting stressing cage to zone 1
Mon (25/05) | 25 May 2026 | P09 |  | Scaffolding erection
Mon (25/05) | 25 May 2026 | P7 |  | No activity
Mon (25/05) | 25 May 2026 | P6 |  | Platform lean con casting
Mon (25/05) | 25 May 2026 | P3 |  | Preparation for segment launching tonight at north bound
Mon (25/05) | 25 May 2026 | S1-1 |  | Blast #47 was completed at 1603hrs. No activity now
Mon (25/05) | 25 May 2026 | CCW1 South |  | U3-39B final inspection was done. Now waiting for casting
Mon (25/05) | 25 May 2026 | CCW1 North |  | No activity
Mon (25/05) | 25 May 2026 | B1 level |  | Internal wall rebar planting in progress
Tue (26/05) | 26 May 2026 | P51 |  | Already set up pump car for pile cap casting
Tue (26/05) | 26 May 2026 | DR4 |  | Probing work in progress, 3nos finished today. Total completed is 22nos
Tue (26/05) | 26 May 2026 | P13 FBCM |  | Concrete blocks hoisting for SB side. 3/16 nos. installed
Tue (26/05) | 26 May 2026 | U3-06 |  | Rebar works and side formwork installation in progress
Tue (26/05) | 26 May 2026 | U3-08 |  | Waterproofing membrane installation in progress
Tue (26/05) | 26 May 2026 | U3-10 |  | Partial lean concrete was cast
Tue (26/05) | 26 May 2026 | U3 | GL26-24 | Ground levelling for earth mat drilling works
Tue (26/05) | 26 May 2026 | U3 | GL22-19 | Hacking dwall surface to expose skinwall starter bars (1 mini), Rock hacking ongoing (2 breakers), Coring and splitting ongoing (4 machines)
Tue (26/05) | 26 May 2026 | P9 |  | Scaffold erection ongoing
Tue (26/05) | 26 May 2026 | U3 | GL18-16 | Excavation and disposal ongoing (2 exc), Hacking works ongoing to -16. (1 breaker). Balance about 700mm to reach FEL
Tue (26/05) | 26 May 2026 | U3 | GL15-14 | Excavation in progress (3 exc)
Tue (26/05) | 26 May 2026 | P3 |  | NB-D01 segment launched last night
Tue (26/05) | 26 May 2026 | B2 GL18-20.5 |  | Skinwall formwork installation in progress
Tue (26/05) | 26 May 2026 | B2 | GL14-17 | Straightening of skinwall starter bars & continue scaffold erection in progress for skinwall works
Tue (26/05) | 26 May 2026 | P48 |  | Levelling for hardcore laying. PTD provided and RES supervising this activity
Tue (26/05) | 26 May 2026 | P47 |  | Lowering down rebar for caisson work
Tue (26/05) | 26 May 2026 | P46 |  | Continue welding of strut end
Tue (26/05) | 26 May 2026 | P35 |  | Rebar work started for crosshead
Tue (26/05) | 26 May 2026 | P36 |  | Shear link installation at NB and ducting work at SB
Tue (26/05) | 26 May 2026 | U3 | GL22-19 | Rock hacking ongoing (1 breakers), Coring and splitting ongoing (2 machines)
Tue (26/05) | 26 May 2026 | U3 | GL22-19 | Rock hacking ongoing (1 breakers), Coring and splitting ongoing (2 machines)
Tue (26/05) | 26 May 2026 | P35 |  | Crosshead rebar installation
Tue (26/05) | 26 May 2026 | P36 |  | Shear link installation ongoing
Tue (26/05) | 26 May 2026 | P45 |  | No activity
Tue (26/05) | 26 May 2026 | P46 |  | No activity
Tue (26/05) | 26 May 2026 | P47 |  | No activity
Tue (26/05) | 26 May 2026 | P51 |  | Pile cap rebar casting ongoing
Tue (26/05) | 26 May 2026 | Zone 2 |  | No activity
Tue (26/05) | 26 May 2026 | P3 |  | Preparation for segment launching
Thu (28/05) | 28 May 2026 | P36 |  | Northbound installing fwk,, southbound continue ducting work, tmr to handover to Wendyng, Manpower: 6 ICE workers
Thu (28/05) | 28 May 2026 | P35 |  | Prepare for top bar installation
Thu (28/05) | 28 May 2026 | P13 |  | 7/16 concrete blocks installed. NB side platform preparation for concrete block installation. Tmr to start NB side
Thu (28/05) | 28 May 2026 | P7 |  | Crosshead formwork dismantling ongoing
Thu (28/05) | 28 May 2026 | P2 |  | LF materials for NB unloading in progress
Thu (28/05) | 28 May 2026 | P3 |  | NB 1st pair segment adjustment in progress
Thu (28/05) | 28 May 2026 | DR4 |  | Preparation for probing works
Thu (28/05) | 28 May 2026 | P51 |  | Pile cap casting completed. Clearing materials
Thu (28/05) | 28 May 2026 | P50 |  | Current backfilling status
Thu (28/05) | 28 May 2026 | P48 |  | NDT test for crosshead falsework platform
Thu (28/05) | 28 May 2026 | P47 |  | L3 caisson rebar work start
Thu (28/05) | 28 May 2026 | P45 |  | No activity
Thu (28/05) | 28 May 2026 | 800mm dia water pipe |  | Painting of barricade for the manholes
Thu (28/05) | 28 May 2026 | P13 |  | Continue platform preparation for NB concrete blocks installation
Thu (28/05) | 28 May 2026 | P9 |  | Barricades netting installation
Thu (28/05) | 28 May 2026 | P7 |  | Crosshead Formwork dismantling
Thu (28/05) | 28 May 2026 | P3 |  | NB segment adjustment
Thu (28/05) | 28 May 2026 | P2 |  | LF assembly works for NB side
Thu (28/05) | 28 May 2026 | P46 |  | Continue welding of 1st layer struts. Plan for MPI test this Saturday
Thu (28/05) | 28 May 2026 | P47 NB |  | Rebar work for 3rd layer caisson
Thu (28/05) | 28 May 2026 | P48 |  | PLT for falsework platform. Plan to handover the area to Wendyng on Monday
Thu (28/05) | 28 May 2026 | P51 |  | Pile cap curing
Thu (28/05) | 28 May 2026 | P36 |  | Current status
Thu (28/05) | 28 May 2026 | P35 |  | Rebar work ongoing
Thu (28/05) | 28 May 2026 | P51 |  | Curing ongoing
Thu (28/05) | 28 May 2026 | P50 |  | Current status, no activity
Thu (28/05) | 28 May 2026 | P13 |  | Current status
Thu (28/05) | 28 May 2026 | P9 |  | Current status, no activity
Thu (28/05) | 28 May 2026 | P3 |  | Status quo
Thu (28/05) | 28 May 2026 | P2 |  | To install stressing cage during night shift at SB
Fri (29/05) | 29 May 2026 | P7 |  | Removal of unused materials and prepare for formwork removal
Fri (29/05) | 29 May 2026 | P5 |  | Formwork closing for lamppost footing casting
Fri (29/05) | 29 May 2026 | P3 |  | Trimming of overcast area for segment adjustment
Fri (29/05) | 29 May 2026 | P3 SB |  | Tonight will launch two segments
Fri (29/05) | 29 May 2026 | P2 down chainage |  | Lifter assembling
Fri (29/05) | 29 May 2026 | P32 |  | 2nd lift column formwork closing
Fri (29/05) | 29 May 2026 | P35 |  | Crosshead rebar installation work
Fri (29/05) | 29 May 2026 | B2 | North side, GL16-18 | Skinwall rebar works and PU grouting ongoing
Fri (29/05) | 29 May 2026 | U3-06 |  | Top bar and shearlinks installation and welding works ongoing, U3-08: Waterproofing membrane laying and PU grouting ongoing
Fri (29/05) | 29 May 2026 | U3-10 |  | Ejector/drainage pit formwork installation in progress
Fri (29/05) | 29 May 2026 | U3 | GL24-26 | Earth mat cable laying installation in progress
Fri (29/05) | 29 May 2026 | P36 |  | Crosshead tendon duct installation ongoing, will finish tonight and handover for shearlinks
Fri (29/05) | 29 May 2026 | P38 |  | Falsework dismantling ongoing
Fri (29/05) | 29 May 2026 | P43 |  | Preparation for load test
Fri (29/05) | 29 May 2026 | P42 |  | Preparation for load test
Fri (29/05) | 29 May 2026 | P45 |  | No activity
Fri (29/05) | 29 May 2026 | P46 |  | S1 strut installation
Fri (29/05) | 29 May 2026 | P48 |  | Ground preparation for crosshead falsework
Fri (29/05) | 29 May 2026 | P47 |  | L3 caisson rebar works ongoing at north side
Fri (29/05) | 29 May 2026 | P50 |  | Backfilling and NDT test completed
Fri (29/05) | 29 May 2026 | DR4 |  | 28nos of probing done. Balance 3nos can complete tomorrow. Next week plan to start JGP grouting work
Fri (29/05) | 29 May 2026 | B2-02 |  | Rebar works & PU grouting in progress, B2-01: Hacking dwall surface to expose skinwall starter bars
Fri (29/05) | 29 May 2026 | S1-1 |  | Blast #49 completed at 1500hrs
Fri (29/05) | 29 May 2026 | B2-16 |  | Excavation completed. Partial lean con was cast last night. Today to lean con balance area
Fri (29/05) | 29 May 2026 | B2 | North side, GL14-16 | PU grouting, RGT installation and drilling tie rod holes ongoing
Fri (29/05) | 29 May 2026 | B2 | North side, GL22-24 | Dismantling formwork for internal wall
Fri (29/05) | 29 May 2026 | P15-P16 |  | Tendon duct grouting works
Fri (29/05) | 29 May 2026 | P13 |  | Concrete packing installation
Fri (29/05) | 29 May 2026 | U3-06 |  | Shearlinks installation in progress
Fri (29/05) | 29 May 2026 | U3-08 |  | PU grouting in progress. Tmr plan to start rebar works
Fri (29/05) | 29 May 2026 | U3 | GL26-24 | Continue cable laying for earth mat
Fri (29/05) | 29 May 2026 | U3 | GL24-20 | Continue coring/splitting works, hacking and disposal
Fri (29/05) | 29 May 2026 | U3 | GL17 | Hacking dwall surface to expose skinwall starter bars
Fri (29/05) | 29 May 2026 | U3 | GL15-13 | Excavation in progress
Fri (29/05) | 29 May 2026 | P7 |  | Preparation for formwork dismantling
Fri (29/05) | 29 May 2026 | P5 |  | Fabrication of lamp post footing
Fri (29/05) | 29 May 2026 | P2 |  | Preparation for strand pushing
Fri (29/05) | 29 May 2026 | P2 |  | LF3 assembly in progress
Fri (29/05) | 29 May 2026 | P48 |  | Hardcore laying for falsework platform
Fri (29/05) | 29 May 2026 | P47 |  | 3rd layer caisson work
Fri (29/05) | 29 May 2026 | P46 |  | Strut welding done. Tomorrow MPI
Fri (29/05) | 29 May 2026 | P15 to 16 |  | Tendom duct grouting work
Sat (30/05) | 30 May 2026 | P7 |  | Preparation to start formwork removal
Sat (30/05) | 30 May 2026 | P5 |  | Prepare rebar and formwork for lamp post footing casting. Plan to cast today
Sat (30/05) | 30 May 2026 | P3 |  | Trimming of crosshead will complete today. Can continue with segment adjustment after this
Sat (30/05) | 30 May 2026 | P2 |  | 1/2 nos lifter assembled. Preparing for 2nd lifter assembling. Plan to install by Monday
Sat (30/05) | 30 May 2026 | DR4 |  | 1/5 nos 800mm dia water pipe manhole rectification will complete today
Sat (30/05) | 30 May 2026 | DR4 |  | 30/31nos probing done. GCE plan for additional 20nos to be done near existing drain
Sat (30/05) | 30 May 2026 | P48 |  | Now no work. Need to continue hardcore backfilling for crosshead
Sat (30/05) | 30 May 2026 | P47 |  | 3rd layer caisson work
Sat (30/05) | 30 May 2026 | P46 |  | MPI test done. Next stage of work will be excavation
Sat (30/05) | 30 May 2026 | P36 Crosshead |  | Ducting completed. Wendyng will come for shear link installation after lunch. Plan to cast on Monday
Sat (30/05) | 30 May 2026 | P35 crosshead |  | Main bar completed. ICE will come on Monday for ducting work
Sat (30/05) | 30 May 2026 | P32 |  | 2nd lift formwork closed. Support installation
Sat (30/05) | 30 May 2026 | B1 level |  | Scaffold erection ongoing for internal wall rebar planting
Sat (30/05) | 30 May 2026 | B2-01 |  | Hacking ongoing to expose skinwall starter bars and couplers, B2-02, B2-03: Rebar works in progress. Plan for casting next week
Sat (30/05) | 30 May 2026 | S1-1 |  | Drilling ongoing for blast #50. Blast is scheduled for Tuesday
Sat (30/05) | 30 May 2026 | U3-35 |  | Excavation in progress ard GL4
Sat (30/05) | 30 May 2026 | P3 |  | Continue trimming for segment adjustment
Sat (30/05) | 30 May 2026 | P2 |  | 2nd lifter assembling
Sat (30/05) | 30 May 2026 | P5 |  | 5 footings reading to cast for lamp post
Sat (30/05) | 30 May 2026 | B2-16 |  | Currently no activity. Lean con was just partially cast. Tonight to complete balance lean con casting. Tmr plan to strt coupler exposing
Sat (30/05) | 30 May 2026 | CCW1 North |  | Currently no activity, CCW2: Excavation in progress to -13.5
Sat (30/05) | 30 May 2026 | B2 | North side, GL14-16 | PU grouting & skinwall rebar works in progress
Sat (30/05) | 30 May 2026 | U3-06 |  | Starter bars and shearlinks installation
Sat (30/05) | 30 May 2026 | U3-08 |  | Started coupler bar installation and continue waterproofing membrane laying at KP drop area
Sat (30/05) | 30 May 2026 | U3-10 |  | Lean con was cast at ejector/drainage pit area, PU grouting ongoing at skinwall
Sat (30/05) | 30 May 2026 | U3 | GL25-24 | ATC continue drilling for earth mat works
Sat (30/05) | 30 May 2026 | U3 | GL14-13 | Excavation in progress
Sat (30/05) | 30 May 2026 | U3 | GL19-17 | Hacking dwall surface to expose skinwall starter bars & survey works ongoing
Sat (30/05) | 30 May 2026 | P13 |  | Formwork making for grouting to seal the gap between crosshead and segment
Tue (02/06) | 02 Jun 2026 | S1-1 |  | Blast #50 completed at 1501hrs
Tue (02/06) | 02 Jun 2026 | P36 |  | Preparing for casting of crosshead, fwk support erection ongoing
Tue (02/06) | 02 Jun 2026 | CCW1 South |  | Currently no activity
Tue (02/06) | 02 Jun 2026 | U3-39C |  | WH constructing bundwall and cleaning works
Tue (02/06) | 02 Jun 2026 | CCW1 North |  | Scaffold erection ongoing
Tue (02/06) | 02 Jun 2026 | CCW2 |  | Current status of excavation
Tue (02/06) | 02 Jun 2026 | B2-02, B2-03 |  | Top bar installation in progress
Tue (02/06) | 02 Jun 2026 | B2-16 |  | PU grouting and coupler exposing ongoing
Tue (02/06) | 02 Jun 2026 | P32 |  | 2nd lift curing
Tue (02/06) | 02 Jun 2026 | P51 |  | LSS backfill done, up till 1.5m
Tue (02/06) | 02 Jun 2026 | P50 |  | 2nd lift rebar work started
Tue (02/06) | 02 Jun 2026 | P46 |  | Excavation ongoing
Tue (02/06) | 02 Jun 2026 | P45 |  | No activity currently
Tue (02/06) | 02 Jun 2026 | U3-06 |  | Rebar works completed. Partial formwork installed, U3-08: Rebar works in progress, Plan to cast both slabs this week
Tue (02/06) | 02 Jun 2026 | U3 | GL24-23 | Cable laying & exothermic welding works for earth mat
Tue (02/06) | 02 Jun 2026 | U3 | GL26-25 | Partial formwork installation for U3-14 lean con works
Tue (02/06) | 02 Jun 2026 | U3-10 |  | Formwork removal for ejector/drainage pits
Tue (02/06) | 02 Jun 2026 | U3 | GL22-20 | Coring/splitting & disposal works ongoing
Tue (02/06) | 02 Jun 2026 | U3 | GL17-14 | Hacking dwall surface to expose skinwall starter bars ongoing
Tue (02/06) | 02 Jun 2026 | U3 | GL13 | Excavation in progress
Tue (02/06) | 02 Jun 2026 | P3 |  | NB Segment adjustment works
Tue (02/06) | 02 Jun 2026 | P2 |  | Lifter assembly and preparation for NB lifter installation
Tue (02/06) | 02 Jun 2026 | P7 |  | Crosshead formwork dismantling
Tue (02/06) | 02 Jun 2026 | Zone 2 |  | LF materials shifting to P2
Tue (02/06) | 02 Jun 2026 | P13 |  | Formwork closing for concrete block gap casting. 14/16 concrete block installed
Tue (02/06) | 02 Jun 2026 | P50 |  | Current status
Tue (02/06) | 02 Jun 2026 | P48 |  | Lean con for falsework footing completed
Tue (02/06) | 02 Jun 2026 | P46 |  | Continue excavation work
Tue (02/06) | 02 Jun 2026 | P31 |  | Fwk removal ongoing
Tue (02/06) | 02 Jun 2026 | P2/3 |  | Handover to night shift, currently no activity
Tue (02/06) | 02 Jun 2026 | U3-06 |  | Rebar works completed. Partial formwork installed, U3-08: Rebar works in progress, Plan to cast both slabs this week
Tue (02/06) | 02 Jun 2026 | U3-06 |  | Rebar works completed. Partial formwork installed, U3-08: Rebar works in progress, Plan to cast both slabs this week
Tue (02/06) | 02 Jun 2026 | U3 | GL22-20 | Coring/splitting & disposal works ongoing, U3 GL17-14: Hacking dwall surface to expose skinwall starter bars ongoing
Tue (02/06) | 02 Jun 2026 | U3 | GL22-20 | Coring/splitting & disposal works ongoing, U3 GL17-14: Hacking dwall surface to expose skinwall starter bars ongoing
Tue (02/06) | 02 Jun 2026 | U3 | GL13 | Excavation in progress, Manpower: 3 excavator
Tue (02/06) | 02 Jun 2026 | U3 | GL13 | Excavation in progress, Manpower: 3 excavator
Wed (03/06) | 03 Jun 2026 | P13 |  | Formwork closing for concrete block gap grouting
Wed (03/06) | 03 Jun 2026 | P7 |  | Side Formwork dismantling completed
Wed (03/06) | 03 Jun 2026 | P4 |  | Scaffold erection ongoing
Wed (03/06) | 03 Jun 2026 | P3 |  | Segment adjustment for NB side
Wed (03/06) | 03 Jun 2026 | P2 |  | Stressing cage assembly and installation for NB side
Wed (03/06) | 03 Jun 2026 | P36 |  | Crosshead cast and curing
Wed (03/06) | 03 Jun 2026 | P35 |  | Target to complete half of ducting by tomorrow for Wendyng to install shear link
Wed (03/06) | 03 Jun 2026 | P43 |  | Stressing at SB side for segment launching tonight
Wed (03/06) | 03 Jun 2026 | P46 |  | Excavation for 2nd layer caisson
Wed (03/06) | 03 Jun 2026 | P47 |  | 2nd part of 3rd layer excavation will be after lunch
Wed (03/06) | 03 Jun 2026 | P48 |  | Falsework platform lean con done. Tomorrow will start falsework erection
Wed (03/06) | 03 Jun 2026 | DR4 Probing |  | 46/49 done. 3nos balance can complete today. Outside hoarding got 23 points to do
Wed (03/06) | 03 Jun 2026 | P13 |  | Continue Formwork closing for concrete block gap grouting
Wed (03/06) | 03 Jun 2026 | P9 |  | Lifter Materials shifting to zone 1
Wed (03/06) | 03 Jun 2026 | P7 |  | Scaffold erection for strands installation
Wed (03/06) | 03 Jun 2026 | P4 |  | Scaffold erection ongoing
Wed (03/06) | 03 Jun 2026 | CCW2 |  | ATC has parked 1 drilling machine for blasting works here. Currently no activity
Wed (03/06) | 03 Jun 2026 | U3-39C |  | Waterproofing membrane laying in progress
Wed (03/06) | 03 Jun 2026 | S1-1 |  | ATC drilling works for blast #51 (2 rigs). Currently no activity
Wed (03/06) | 03 Jun 2026 | B2-02, B2-03 |  | Top bar installation in progress
Wed (03/06) | 03 Jun 2026 | B2 | South side, GL26 | Skinwall rebar works & drilling for tie rod holes ongoing
Wed (03/06) | 03 Jun 2026 | U3-10 |  | Surface cleaning ongoing
Wed (03/06) | 03 Jun 2026 | Partial U3-14 | KP area | Waterproofing membrane laying. Tmr plan to start rebar works
Wed (03/06) | 03 Jun 2026 | U3 | GL13 | Excavation in progress
Wed (03/06) | 03 Jun 2026 | U3 | GL23-20 | Coring/splitting works ongoing, Hacking and disposal activity ongoing
Wed (03/06) | 03 Jun 2026 | U3-08 |  | Top bar and partial side formwork installation in progress
Wed (03/06) | 03 Jun 2026 | Blast #51 |  | Blast holes: 96/96, Relief holes: 18/18
Wed (03/06) | 03 Jun 2026 | Blast #52 |  | Blast holes: 20/75, Relief holes: 7/20
Thu (04/06) | 04 Jun 2026 | Partial U3-14 |  | Continue laying waterproofing membrane and cleaning works. Today plan to start rebar works
Thu (04/06) | 04 Jun 2026 | U3-10 |  | Continue PU grouting
Thu (04/06) | 04 Jun 2026 | U3 | GL24 | APP continue earth mat cable laying & welding works
Thu (04/06) | 04 Jun 2026 | U3 | GL13 | Excavation in progress
Thu (04/06) | 04 Jun 2026 | U3 | GL15 | Hacking works ongoing to expose skinwall starter bars at dwall and excess concrete at KP area
Thu (04/06) | 04 Jun 2026 | U3 | GL17-16 | Ground preparation ongoing by WH to facilitate earth mat works
Thu (04/06) | 04 Jun 2026 | U3 | GL23-18 | Continue coring/splitting, hacking and disposal works
Thu (04/06) | 04 Jun 2026 | U3-08 |  | Continue top bar and side formwork installation
Thu (04/06) | 04 Jun 2026 | B2 | GL32-E9 | Preparing to continue rebar planting for internal wall
Thu (04/06) | 04 Jun 2026 | B2 | South side, GL32-30 | Skinwall formwork installation in progress
Thu (04/06) | 04 Jun 2026 | B2 | North side, GL12 | PU grouting ongoing
Thu (04/06) | 04 Jun 2026 | B2-16 |  | Continue coupler exposing and PU grouting. Today plan for Maxbond to lay waterproofing membrane
Thu (04/06) | 04 Jun 2026 | B2-02 |  | Continue top bar installation
Thu (04/06) | 04 Jun 2026 | B1 level |  | Working platform erection ongoing for internal wall works
Thu (04/06) | 04 Jun 2026 | U3-39C |  | Waterproofing membrane installed. Maxbond continue PU grouting works
Thu (04/06) | 04 Jun 2026 | CCW1 North |  | Current status of scaffold erection
Thu (04/06) | 04 Jun 2026 | CCW2 |  | ATC drilling blast/relief holes in progress. Currently workers on tea break
Thu (04/06) | 04 Jun 2026 | CCW2 | GL W7 | Hirose preparing to install balance 1no. bracing, S1-1 Opening 3: KTC continue soil and rock disposal
Thu (04/06) | 04 Jun 2026 | S1-1 |  | Blast #51 completed at 1504hrs
Thu (04/06) | 04 Jun 2026 | U3-35 |  | Excavation in progress
Thu (04/06) | 04 Jun 2026 | P13 |  | Preparation for grouting works for concrete block gaps
Thu (04/06) | 04 Jun 2026 | P7 |  | Strands installation for stressing in progress
Thu (04/06) | 04 Jun 2026 | B2-02, B2-03 |  | Continue top bar installation
Thu (04/06) | 04 Jun 2026 | B2-16 |  | Currently workers on tea break. Thereafter WH to proceed surface cleaning prior to waterproofing membrane installation
Thu (04/06) | 04 Jun 2026 | B2 | GL32-VS | Internal wall rebar installation in progress
Thu (04/06) | 04 Jun 2026 | U3-08 |  | Continue top bar installation
Thu (04/06) | 04 Jun 2026 | P35 |  | Half of ducting completed
Thu (04/06) | 04 Jun 2026 | P36 |  | Crosshead cast and curing. No activity
Thu (04/06) | 04 Jun 2026 | P46 |  | Excavation for Layer 2 of caisson
Thu (04/06) | 04 Jun 2026 | P48 |  | Falsework erection starting
Thu (04/06) | 04 Jun 2026 | P50 |  | Rebar works ongoing
Thu (04/06) | 04 Jun 2026 | P51 |  | LSS backfill completed
Thu (04/06) | 04 Jun 2026 | P2 |  | Tonight to resume 2nd pair segment launching at NB
Fri (05/06) | 05 Jun 2026 | P13 SB | MJ | Preparation for grouting between concrete blocks and 1st pair segment
Fri (05/06) | 05 Jun 2026 | U3-08 |  | Shearlinks & formwork installation in progress, Tmr plan to cast U3-06 & U3-08
Fri (05/06) | 05 Jun 2026 | U3-10 |  | Sump pit drop area hacking and cleaning ongoing, Continue PU grouting at skinwall
Fri (05/06) | 05 Jun 2026 | Partial U3-14 |  | Started rebar works
Fri (05/06) | 05 Jun 2026 | U3 | GL13 | Slope levelling ongoing
Fri (05/06) | 05 Jun 2026 | U3 | GL16 | APP preparation works for earth mat
Fri (05/06) | 05 Jun 2026 | U3 | GL24-19 | Continue coring/splitting, hacking and disposal works
Fri (05/06) | 05 Jun 2026 | B2-16 |  | Continue waterproofing membrane installation & PU grouting works
Fri (05/06) | 05 Jun 2026 | B2-02, B2-03 |  | Continue top bar installation. Plan for casting on Monday
Fri (05/06) | 05 Jun 2026 | P2 |  | NB 2nd pair strand pushing for stressing, SB 3rd pair to launch tonight
Fri (05/06) | 05 Jun 2026 | Partial U3-14 |  | Rebar works in progress
Fri (05/06) | 05 Jun 2026 | U3-08 |  | Continue top bar and shearlinks installation. Plan to casting U3-06 & U3-08 tmr
Fri (05/06) | 05 Jun 2026 | U3-10 sump pit |  | Patching up below for waterproofing and preparing balance area lean con works at the right side
Fri (05/06) | 05 Jun 2026 | U3 | GL17-15 | Continue hacking at skinwall area to expose starter bars, Exposing couplers, ATC drilling ongoing for earth mat works
Fri (05/06) | 05 Jun 2026 | U3 | GL24-20 | Continue hacking, coring/splitting and disposal works
Fri (05/06) | 05 Jun 2026 | U3 | GL13 | Continue excavation/disposal and slope levelling
Fri (05/06) | 05 Jun 2026 | B2-16 |  | Continue waterproofing membrane installation & PU grouting
Fri (05/06) | 05 Jun 2026 | P35 |  | Lifting and installation of U tendon ongoing
Fri (05/06) | 05 Jun 2026 | P36 |  | No activity
Fri (05/06) | 05 Jun 2026 | P45 |  | Rebar works ongoing
Fri (05/06) | 05 Jun 2026 | P46 |  | Excavation works for layer 2 of caisson continue
Fri (05/06) | 05 Jun 2026 | P47 |  | Falsweork erection ongoing
Fri (05/06) | 05 Jun 2026 | P49 |  | Rebar works ongoing
Fri (05/06) | 05 Jun 2026 | DR4 |  | Probing has not begun since lunch
Fri (05/06) | 05 Jun 2026 | B2-02, B2-03 |  | Continue top bar installation and partial shearlinks installation
Fri (05/06) | 05 Jun 2026 | S1-1 |  | U3-35 excavation in progress
Fri (05/06) | 05 Jun 2026 | CCW2 W7-8 |  | Excavation in progress, Loading point at Opening 3
Fri (05/06) | 05 Jun 2026 | B1 level |  | No activity
Fri (05/06) | 05 Jun 2026 | CCW2 W5-6 |  | Blast #52 was done at 1543hrs
Sat (06/06) | 06 Jun 2026 | B2-16 |  | Continue PU grouting and some patch up works for waterproofing membrane, Preparing to start bottom rebar works
Sat (06/06) | 06 Jun 2026 | P43 NB 4th pair |  | Strand cutting and grouting cap installation
Sat (06/06) | 06 Jun 2026 | CCE | GL-E6 | Preparing platform for pump truck parking to facilitate casting
Sat (06/06) | 06 Jun 2026 | U3-06, U3-08 |  | Cleaning, balance tying and welding works ongoing. Final inspection ard 11am
Sat (06/06) | 06 Jun 2026 | U3-10 sump pit |  | Balance lean con casting done
Sat (06/06) | 06 Jun 2026 | U3-10 |  | RGT installation in progress
Sat (06/06) | 06 Jun 2026 | U3-10, U3-12 |  | Partial waterproofing membrane installation, U3-12: Preparing PU grouting works
Sat (06/06) | 06 Jun 2026 | U3-14 |  | Part 1: Continue rebar works, Part 2: Lean con casting done last night. Now ongoing coupler exposing
Sat (06/06) | 06 Jun 2026 | P45 |  | Today to start column formwork closing
Sat (06/06) | 06 Jun 2026 | P46 |  | 2nd layer caison works
Sat (06/06) | 06 Jun 2026 | P50 |  | RWDP installation
Sat (06/06) | 06 Jun 2026 | U3 | GL16-15 | Earth mat: APP preparing for rod installation & ATC preparing to continue drilling works, WH continue exposing skin wall starter bars
Sat (06/06) | 06 Jun 2026 | U3 | GL13 | Currently no excavation/levelling. Only disposing soil
Sat (06/06) | 06 Jun 2026 | U3 | GL17 | Rock hacking ongoing
Sat (06/06) | 06 Jun 2026 | U3 | GL23-20 | Continue coring/splitting, hacking & disposal works
Sat (06/06) | 06 Jun 2026 | P2 SB 2nd pair |  | Segment launching completed last night. Tonight to do stressing
Sat (06/06) | 06 Jun 2026 | P3 SB |  | Wet stitching to cast tonight
Sat (06/06) | 06 Jun 2026 | P7 crosshead |  | Strand pushing for 1st stage stressing
Sat (06/06) | 06 Jun 2026 | P13 NB |  | Grouting in progress for FBCM. Today to complete
Sat (06/06) | 06 Jun 2026 | P13 NB |  | Grouting completed
Sat (06/06) | 06 Jun 2026 | U3-06, U3-08 |  | Continue cleaning. Final inspection change to 3pm
Sat (06/06) | 06 Jun 2026 | U3-10, U3-12 |  | Continue waterproofing membrane installation, RGT installation and PU grouting
Sat (06/06) | 06 Jun 2026 | U3-14 part 1 |  | Continue rebar works
Sat (06/06) | 06 Jun 2026 | U3 | GL23 | Continue hacking at KP area, Ground preparation for earth mat works
Sat (06/06) | 06 Jun 2026 | U3 | GL22-18 | Continue hacking and disposal works
Sat (06/06) | 06 Jun 2026 | U3 | GL16 | Continue hacking to expose skinwall starter bars, Earth mat works ongoing, Continue disposing soil. Currently no excavation at GL13
Sat (06/06) | 06 Jun 2026 | P40 |  | RWDP cover removal
Sat (06/06) | 06 Jun 2026 | P43 |  | Clamping beam shifting
Sat (06/06) | 06 Jun 2026 | P47 | NB side | 2nd layer strut installation
Sat (06/06) | 06 Jun 2026 | B2-02, B2-03 |  | Shearlinks installation in progress
Sat (06/06) | 06 Jun 2026 | CCW1 South |  | S5 struts 10/10 completed. Now preparing for waler cutting and working platform erection
Sat (06/06) | 06 Jun 2026 | CCW1 North |  | Currently no activity
Sat (06/06) | 06 Jun 2026 | CCW2 | GL W5-6 | Blast #52 was done yesterday afternoon. Now clearing the rocks
Sat (06/06) | 06 Jun 2026 | CCW2 |  | Current status of excavation to -13.5. KTC continue disposal works at Opening 3
Sat (06/06) | 06 Jun 2026 | S1-1 |  | ATC preparation works for drilling blast #53
Sat (06/06) | 06 Jun 2026 | P33 |  | Falsework erection in progress
Sat (06/06) | 06 Jun 2026 | U3-35 |  | Excavation in progress. Soil loading point at Opening 2B
Sat (06/06) | 06 Jun 2026 | P35 crosshead |  | Anti burst link installation for U-pipe, 4 pax by ICE
Mon (08/06) | 08 Jun 2026 | P35 |  | Ducting by ICE and assessories installation by WH. This Wednesday will handover half for shear link and by Saturday will fully handover. Next week to cast the crosshea
Mon (08/06) | 08 Jun 2026 | P33 |  | Secondary beam installation for crosshead work
Mon (08/06) | 08 Jun 2026 | P13 |  | Grout curing, once cube test result pass, temporary stressing can proceed for FBCM set up
Mon (08/06) | 08 Jun 2026 | P42 SB |  | Stitching formwork removal
Mon (08/06) | 08 Jun 2026 | P3 NB |  | Wet stitch formwork closing started. 6 pax
Mon (08/06) | 08 Jun 2026 | P2 NB 3rd pair |  | Pending confirmation from the transporter for delivery and launching tonight
Mon (08/06) | 08 Jun 2026 | P45 |  | Installation for formwork for casting of 2nd lift in progress
Mon (08/06) | 08 Jun 2026 | P46 |  | Rebar works for 2nd layer caisson in progress
Mon (08/06) | 08 Jun 2026 | P47 |  | Layer 3 caisson strutting works in progress
Mon (08/06) | 08 Jun 2026 | P48 |  | Falsework erection no activity
Mon (08/06) | 08 Jun 2026 | P50 |  | No activity
Mon (08/06) | 08 Jun 2026 | P51 |  | No activity
Mon (08/06) | 08 Jun 2026 | DR4 |  | No probing works started yet due to some obstructions. 12 more probing points to be completed
Mon (08/06) | 08 Jun 2026 | U3-10 & U3-12 |  | Started rebar installatio
Mon (08/06) | 08 Jun 2026 | U3-14 |  | Exposing of coupler is in progress
Mon (08/06) | 08 Jun 2026 | U3-16 & U3-18 |  | Hacking, excavation & internal transfer in progress
Mon (08/06) | 08 Jun 2026 | U3-21 & U3-23 |  | Excavation & internal transfer in progress
Mon (08/06) | 08 Jun 2026 | P33 |  | Falsework secondary beam installation
Mon (08/06) | 08 Jun 2026 | S1-1 |  | Blast #54 was completed at 1820hrs, CCW2: Blast #53 was completed at the same timing
Mon (08/06) | 08 Jun 2026 | CCW1 North |  | Continue falsework erection
Mon (08/06) | 08 Jun 2026 | B2-02, B2-03 |  | Pending for casting
Mon (08/06) | 08 Jun 2026 | P45 |  | Column 2nd lift formwork closing completed. Propping installation in progress
Mon (08/06) | 08 Jun 2026 | B2-16 |  | Rebar works in progress, Nightshift - 14 men
Mon (08/06) | 08 Jun 2026 | U3 | North side, GL14 | Hacking ongoing to expose skinwall starter bars
Mon (08/06) | 08 Jun 2026 | U3 | Earth mat, GL16-14 | Cable laying & exothermic welding works was done just now. Currently no activity
Mon (08/06) | 08 Jun 2026 | B2 | GL23-24 | Preparing formwork for Skinwall rectification works
Mon (08/06) | 08 Jun 2026 | B2 | GL-E9 to VS | Preparing materials for working platform erection for 2nd lift internal wall
Mon (08/06) | 08 Jun 2026 | U3 | North side, GL16-14 | Excavation & disposal ongoing to -15
Mon (08/06) | 08 Jun 2026 | U3-06, U3-08 |  | Curing
Mon (08/06) | 08 Jun 2026 | U3-10, U3-12 |  | Coupler bar planting in progress
Mon (08/06) | 08 Jun 2026 | U3 | GL23-20 | Hacking, coring/splitting and disposal works ongoing
Mon (08/06) | 08 Jun 2026 | U3-14 | Part 1-KP area | Rebar works and formwork installation in progress. Plan for casting on Wednesday
Mon (08/06) | 08 Jun 2026 | U3 | GL17 | Ground preparation for earth mat works
Tue (09/06) | 09 Jun 2026 | P13 |  | Cube test result came out yesterday with satisfactory result. Preparation now to temporary stressing
Tue (09/06) | 09 Jun 2026 | CCW2 | GL W6-7 | ATC preparing drilling holes for next blasting, KTC shifting materials to facilitate works
Tue (09/06) | 09 Jun 2026 | CCW1 North |  | Falsework installation in progress for roof slab works
Tue (09/06) | 09 Jun 2026 | Opening 3 |  | Continue disposal of rock fragments/soil
Tue (09/06) | 09 Jun 2026 | DR4 |  | 11nos of probing encountered obstruction. GCE relocade the point to do probing again
Tue (09/06) | 09 Jun 2026 | 800mm dia water pipe |  | PU grouting manhole dampness area
Tue (09/06) | 09 Jun 2026 | B2-16 |  | Rebar installation in progress
Tue (09/06) | 09 Jun 2026 | B2 | GL E9 | Column C01-1 rebar planting in progress
Tue (09/06) | 09 Jun 2026 | B2 | GL E9 to VS | Working platform installation in progress for 2nd lift internal wall
Tue (09/06) | 09 Jun 2026 | U3-10 |  | Continue PU grouting works
Tue (09/06) | 09 Jun 2026 | U3-14 |  | PU grouting ongoing at skinwall area, Part 1: Continue rebar and formwork installation. Plan for casting tonight or tmr, Part 2: Formwork installation for balance lean con
Tue (09/06) | 09 Jun 2026 | U3 | GL23 | Continue exposing couplers, U3 GL22-19Continue hacking & disposal works
Tue (09/06) | 09 Jun 2026 | U3 | GL17 | ATC preparing drilling works for earth mat
Tue (09/06) | 09 Jun 2026 | U3-08 |  | Formwork dismantling ongoing
Tue (09/06) | 09 Jun 2026 | P45 |  | Formwork closing for 2nd lift. Tomorrow can cast
Tue (09/06) | 09 Jun 2026 | P46 |  | Formwork closing for 2nd layer caisson
Tue (09/06) | 09 Jun 2026 | P47 |  | Started rebar work for 3rd layer caisson
Tue (09/06) | 09 Jun 2026 | P48 |  | Currently no activity. Materials to shift from P7
Tue (09/06) | 09 Jun 2026 | P50 |  | Working platform removal for formwork closing
Tue (09/06) | 09 Jun 2026 | P42 |  | Tendon wire pulling for stressing work
Tue (09/06) | 09 Jun 2026 | P3 |  | SB: dismantling of stitching formwork, NB: stitching formwork closing
Tue (09/06) | 09 Jun 2026 | P2 |  | NB: 3rd pair strand pushing for stressing, SB: to launch 4th pair tonight
Tue (09/06) | 09 Jun 2026 | P35 |  | Ducting and cast in accessories installation
Tue (09/06) | 09 Jun 2026 | P33 |  | Current status of platform erection. End of next week should be able to start crosshead rebar work
Tue (09/06) | 09 Jun 2026 | U3-14 | A | Continues rebar/formwork installation & target to cast it tonight
Tue (09/06) | 09 Jun 2026 | GL23-19 |  | Continue hacking & internal transfer
Tue (09/06) | 09 Jun 2026 | U3-22 |  | Drilling in progress for earth Matt work
Tue (09/06) | 09 Jun 2026 | U3-24 |  | Done installing earth rod and inspection arranged at 5pm
Tue (09/06) | 09 Jun 2026 | GL15-13 |  | Excavation in progress& internal transfer
Tue (09/06) | 09 Jun 2026 | U3-14 | A | Continues rebar/formwork installation & target to cast it tonight
Tue (09/06) | 09 Jun 2026 | U3-14 | A | Continues rebar/formwork installation & target to cast it tonight
Tue (09/06) | 09 Jun 2026 | GL23-19 |  | Continue hacking & internal transfer
Tue (09/06) | 09 Jun 2026 | GL23-19 |  | Continue hacking & internal transfer
Tue (09/06) | 09 Jun 2026 | P50 |  | No activity. Currently status of 2nd lift column work
Tue (09/06) | 09 Jun 2026 | P48 |  | No activity
Tue (09/06) | 09 Jun 2026 | P47 |  | No activity
Tue (09/06) | 09 Jun 2026 | P46 |  | L2 caisson casting ongoing
Tue (09/06) | 09 Jun 2026 | P45 |  | Preparing platform for scaffolding erection tomorrow. Target to cast P45 2nd lift column tomorrow
Tue (09/06) | 09 Jun 2026 | GL15-13 |  | Excavation in progress& internal transfer
Tue (09/06) | 09 Jun 2026 | GL15-13 |  | Excavation in progress& internal transfer
Tue (09/06) | 09 Jun 2026 | P42 |  | Preparation for segment launching tonight
Tue (09/06) | 09 Jun 2026 | P13 |  | NB TPT stressing completed. SB preparation for stressing complete, tomorrow morning can proceed with stressing work
Tue (09/06) | 09 Jun 2026 | P3 |  | No activity
Tue (09/06) | 09 Jun 2026 | P2 |  | Strand pushing at NB
Tue (09/06) | 09 Jun 2026 | B1 level |  | Currently no activity
Wed (10/06) | 10 Jun 2026 | P35 NB |  | Today to complete ducting work and handover for shear link installation. SB: will handover by this week. Next week casting of crosshead
Wed (10/06) | 10 Jun 2026 | P36 |  | Started support dismantling for formwork
Wed (10/06) | 10 Jun 2026 | P33 |  | Prepare to continue installation of working platform for crosshead
Wed (10/06) | 10 Jun 2026 | P45 |  | Access scaffold erection. Target today casting
Wed (10/06) | 10 Jun 2026 | P46 |  | Removal of stagnant water and prepare to continue excavation at SB
Wed (10/06) | 10 Jun 2026 | P47 |  | Caisson rebar work for 3rd layer at SB
Wed (10/06) | 10 Jun 2026 | P48 |  | No activity. Materials to come from Zone 2
Wed (10/06) | 10 Jun 2026 | P51 |  | Removal of stagnant water. Today to start removal of struts
Wed (10/06) | 10 Jun 2026 | DR4 |  | Relocation of pipe sleeves to avoid obstruction
Wed (10/06) | 10 Jun 2026 | P45 |  | Access erected for column casting
Wed (10/06) | 10 Jun 2026 | B2-01 |  | Clearing debris
Wed (10/06) | 10 Jun 2026 | CCW2 | GL W5-7 | Blast #55 was done this afternoon at 3pm. Now clearing rubber mats and continue excavation
Wed (10/06) | 10 Jun 2026 | CCW1 North |  | Falsework installation in progress. Plan to complete this week
Wed (10/06) | 10 Jun 2026 | CCW2 | North side, GL W5-6 | Excavation and levelling ongoing at -13.5
Wed (10/06) | 10 Jun 2026 | CCW1 South |  | Walers removal completed. Now Hirose housekeeping
Wed (10/06) | 10 Jun 2026 | CCW2 | South side, GL W5-6 | Excavation ongoing to -13.5
Wed (10/06) | 10 Jun 2026 | U3-39C |  | Bottom rebar works started today
Wed (10/06) | 10 Jun 2026 | S1-1 |  | Continue excavation works
Wed (10/06) | 10 Jun 2026 | U3-35, U3-33 |  | Excavation. Soil loading point at Opening 2B
Wed (10/06) | 10 Jun 2026 | B2-16 |  | Continue rebar works and preparing shearlinks. Plan to cast Friday
Wed (10/06) | 10 Jun 2026 | B2 | GL E9 | Column C01-1 rebar works in progress
Wed (10/06) | 10 Jun 2026 | U3-24 |  | Lean con was cast last night. Now ongoing formwork installation for drop area
Wed (10/06) | 10 Jun 2026 | U3 | North side, GL18-19 | Excavation ongoing to -15
Wed (10/06) | 10 Jun 2026 | U3 | South side, GL20-23 | Continue coring/splitting, hacking and disposal works
Wed (10/06) | 10 Jun 2026 | U3 | U3-22, South side, GL17-18 | Rod installation ongoing for earth mat
Wed (10/06) | 10 Jun 2026 | U3-14 part 1 |  | Casting in progress
Wed (10/06) | 10 Jun 2026 | U3-10 |  | Rebar works in progress
Wed (10/06) | 10 Jun 2026 | P30 |  | No activity
Wed (10/06) | 10 Jun 2026 | P33 |  | No activity
Wed (10/06) | 10 Jun 2026 | P35 |  | Tendon duct installation in progress
Wed (10/06) | 10 Jun 2026 | P42 |  | Strand pulling on going
Wed (10/06) | 10 Jun 2026 | P43 |  | Scaffolding dismantling
Wed (10/06) | 10 Jun 2026 | P45 |  | Preparation for 2nd lift column casting tonight
Wed (10/06) | 10 Jun 2026 | P47 |  | No activity
Wed (10/06) | 10 Jun 2026 | P48 |  | No activity
Wed (10/06) | 10 Jun 2026 | P50 |  | No activity
Wed (10/06) | 10 Jun 2026 | P46 |  | No activity
Wed (10/06) | 10 Jun 2026 | P13 |  | No activity
Wed (10/06) | 10 Jun 2026 | P2 |  | Strand pulling for SB
Wed (10/06) | 10 Jun 2026 | P3 |  | No activity
Thu (11/06) | 11 Jun 2026 | P43 |  | Midspan stitching fwk ongoing
Thu (11/06) | 11 Jun 2026 | P49 |  | Concrete block fwk erection ongoing
Thu (11/06) | 11 Jun 2026 | P48 |  | Current status of falsework erection
Thu (11/06) | 11 Jun 2026 | P13 | MJ | Temporary stressing for horizontal bar completed. Grouting for bearing plate in progress
Thu (11/06) | 11 Jun 2026 | P30 |  | 1st lift rebar work ongoing
Thu (11/06) | 11 Jun 2026 | P33 |  | Current status of falsework erection
Thu (11/06) | 11 Jun 2026 | P32 |  | Preparing to remove working platform
Thu (11/06) | 11 Jun 2026 | P36 |  | Side fwk removal ongoing
Thu (11/06) | 11 Jun 2026 | P3 NB |  | Formwork closing for stitching in progress. To cast 1st pair stitching tmr
Fri (12/06) | 12 Jun 2026 | P33 |  | Access erection ongoing
Fri (12/06) | 12 Jun 2026 | B2-16 |  | Pumping out water and cleaning ongoing. Final inspection to be done ard 11am. To cast today
Fri (12/06) | 12 Jun 2026 | B2 | North side, GL12-11 | Skinwall rebar works ongoing
Fri (12/06) | 12 Jun 2026 | U3-24 |  | PU grouting ongoing
Fri (12/06) | 12 Jun 2026 | P38 decking reinstatement |  | To start reinstating 40 pieces decking, target to handover tmr
Fri (12/06) | 12 Jun 2026 | U3 | U3-23, North side, GL14-16 | Hacking ongoing to expose skinwall starter bars
Fri (12/06) | 12 Jun 2026 | U3-22, U3-20 |  | Earth mat works ongoing
Fri (12/06) | 12 Jun 2026 | B2 | South side, GL26-24 | Drilling and hacking ongoing for skinwall works
Fri (12/06) | 12 Jun 2026 | P35 |  | Bearing stump rebar work ongoing by Wendyng
Fri (12/06) | 12 Jun 2026 | U3-10, U3-12 |  | Rebar works ongoing
Fri (12/06) | 12 Jun 2026 | P43/44 |  | Midspan fwk stitching ongoing
Fri (12/06) | 12 Jun 2026 | P50 |  | Preparing for column fwk closure
Fri (12/06) | 12 Jun 2026 | P48 |  | Current status for falsework installation
Fri (12/06) | 12 Jun 2026 | P46 |  | Excavation ongoing
Fri (12/06) | 12 Jun 2026 | P47 |  | Rebar work for caisson wall ongoing
Fri (12/06) | 12 Jun 2026 | P45 |  | 2nd lift curing
Fri (12/06) | 12 Jun 2026 | P13 |  | Grout curing, vertical stressing est to be done on Sunday
Fri (12/06) | 12 Jun 2026 | S1-1, CCW2 |  | Covering blasting area with soil. Plan for blasting ard 430pm
Fri (12/06) | 12 Jun 2026 | U3-39C |  | Rebar works and partial formwork installation in progress
Fri (12/06) | 12 Jun 2026 | U3-37 to U3-33 |  | Continue excavation
Fri (12/06) | 12 Jun 2026 | P9 NBR |  | SH assembly. Target to install tmr night
Fri (12/06) | 12 Jun 2026 | P33 |  | Status of barricade / access
Fri (12/06) | 12 Jun 2026 | B2-16 |  | Final inspection was completed. Now preparing for casting
Fri (12/06) | 12 Jun 2026 | B2 | North side, GL12-11 | Skinwall works ongoing
Fri (12/06) | 12 Jun 2026 | B2 | North side, GL16-14 | Formwork installation for skinwall
Fri (12/06) | 12 Jun 2026 | U3-22, U3-20 |  | Earth mat works ongoing
Fri (12/06) | 12 Jun 2026 | B2 | South side, GL26-24 | Continue drilling to facilitate skinwall works
Fri (12/06) | 12 Jun 2026 | P50 |  | Status of fwk closure (3/4)
Fri (12/06) | 12 Jun 2026 | Zone 1 |  | Shifting of spreader beam and stressing cage to zone 2
Fri (12/06) | 12 Jun 2026 | U3-10, U3-12 |  | Bottom rebar works in progress
Fri (12/06) | 12 Jun 2026 | U3-14 part 1 |  | Dismantling formwork
Fri (12/06) | 12 Jun 2026 | P38 |  | Status of decking reinstatement
Fri (12/06) | 12 Jun 2026 | P2 NB |  | Stressing in progress. To continue at 8pm after rush hour, SB: to launch segment tonight
Fri (12/06) | 12 Jun 2026 | S1-1, CCW2 |  | Blast 56 & 57 completed at 1656hrs
Fri (12/06) | 12 Jun 2026 | B2-01 |  | Clearing debris
Fri (12/06) | 12 Jun 2026 | Exit 3 |  | CGW preparing hacking for rectification works
Fri (12/06) | 12 Jun 2026 | U3-37 to U3-33 |  | Excavation ongoing. Soil loading point at Opening 3 and 2B respectively
Fri (12/06) | 12 Jun 2026 | CCW1 North |  | Falsework erection for tunnel roof slab completed. Pending PE inspection
Fri (12/06) | 12 Jun 2026 | U3-39C |  | Rebar works in progress
Fri (12/06) | 12 Jun 2026 | S1-1 & CCW2 | South side | Today plan for blast #57 & #56 respectively
Fri (12/06) | 12 Jun 2026 | P30 |  | Current status for 1st lift
Mon (15/06) | 15 Jun 2026 | P35 |  | Cast in items installation by WH
Mon (15/06) | 15 Jun 2026 | P30 |  | 1st lift formwork closing. Tomorrow to cast
Mon (15/06) | 15 Jun 2026 | P13 |  | Vertical stressing in progress
Mon (15/06) | 15 Jun 2026 | P43-44 |  | No activity as of now. Stitching curing
Mon (15/06) | 15 Jun 2026 | P45 |  | Formwork support removal
Mon (15/06) | 15 Jun 2026 | P46 |  | Tie rod installation for formwork closing
Mon (15/06) | 15 Jun 2026 | P47 |  | Formwork and support removal
Mon (15/06) | 15 Jun 2026 | P50 |  | 2nd lift curing
Mon (15/06) | 15 Jun 2026 | P9 NBR |  | Stressing cage modification
Mon (15/06) | 15 Jun 2026 | P3 NB |  | Waiting for wet stitch cube test result. If satisfactory, can proceed to stress tonight
Mon (15/06) | 15 Jun 2026 | P2 |  | Preparation for 6th pair segment launching tonight
Tue (16/06) | 16 Jun 2026 | Bet P10-P11 |  | Materials shifting ongoing
Tue (16/06) | 16 Jun 2026 | P9 |  | NB-D01 segment launched yesterday
Tue (16/06) | 16 Jun 2026 | P7 |  | Water jet - tendon duct rectification works commenced
Tue (16/06) | 16 Jun 2026 | P2 |  | Strands pushing for NB 6th pair segment
Tue (16/06) | 16 Jun 2026 | DR4 |  | Preparation for footpath diversion casting
Tue (16/06) | 16 Jun 2026 | DR4 |  | GCE rig maintenace and preparation for JGP grouting work
Tue (16/06) | 16 Jun 2026 | 800mm dia water pipe |  | Manhole PU grouting work
Tue (16/06) | 16 Jun 2026 | U3 | North side, GL-E9 to E7 | Excavation in progress to -14
Tue (16/06) | 16 Jun 2026 | U3-10, U3-12 |  | Rebar works in progress
Tue (16/06) | 16 Jun 2026 | U3-20 |  | Earth mat works in progress
Tue (16/06) | 16 Jun 2026 | U3 | GL12 | Excavation in progress
Tue (16/06) | 16 Jun 2026 | U3-24 |  | Rebar works and partial side formwork installation ongoing
Tue (16/06) | 16 Jun 2026 | U3-16 |  | Partial lean con was cast this morning
Tue (16/06) | 16 Jun 2026 | B2 | GL32 towards VS | Formwork installation in progress for internal wall
Tue (16/06) | 16 Jun 2026 | P45 |  | Formwork removal
Tue (16/06) | 16 Jun 2026 | P46 |  | 2nd layer caisson formwork closing
Tue (16/06) | 16 Jun 2026 | P47 |  | 2nd layer strut installation
Tue (16/06) | 16 Jun 2026 | P48 |  | Crane parking platform casting
Tue (16/06) | 16 Jun 2026 | P30 |  | Formwork closed. Casting platform erection. Tomorrow to cast
Tue (16/06) | 16 Jun 2026 | P33 |  | Side formwork closed. Can start rebar work after GI pipe support installation done
Tue (16/06) | 16 Jun 2026 | P35 |  | Formwork closing and balance shear link installation
Tue (16/06) | 16 Jun 2026 | P36 |  | Preparing for stressing work, P35: fwk closure
Tue (16/06) | 16 Jun 2026 | P46 |  | Continue 2nd layer caisson wall fwk closure
Wed (17/06) | 17 Jun 2026 | P13 |  | Vertical stressing completed. Tonight to launch NB U02
Wed (17/06) | 17 Jun 2026 | P7 |  | Water jet preparation works, CCTV inspection completed
Wed (17/06) | 17 Jun 2026 | P33 |  | Crosshead side formwork and platform completed. Now continue additional support installation
Wed (17/06) | 17 Jun 2026 | P35 |  | WH almost completed cast in items installation. Saturday can cast this crosshead
Wed (17/06) | 17 Jun 2026 | P3 |  | SH dismantling to be shifted to zone 2
Wed (17/06) | 17 Jun 2026 | P45 |  | No activity
Wed (17/06) | 17 Jun 2026 | P46 |  | 2nd layer caisson formwork closure ongoing
Wed (17/06) | 17 Jun 2026 | P47 |  | 2nd layer strutting works ongoing
Wed (17/06) | 17 Jun 2026 | P48 |  | No activity
Wed (17/06) | 17 Jun 2026 | P50 |  | Trenching for DSTA cable laying still ongoing
Wed (17/06) | 17 Jun 2026 | P7 |  | Water jet continue
Wed (17/06) | 17 Jun 2026 | P11 SB |  | SH assembly
Wed (17/06) | 17 Jun 2026 | P9 NBR |  | Initial adjustment completed. Survey reading taken for YWL confirmation
Wed (17/06) | 17 Jun 2026 | CCW1 North |  | Continue exposing couplers for tunnel roof slab
Wed (17/06) | 17 Jun 2026 | B1 level |  | Internal wall rebar works and housekeeping
Wed (17/06) | 17 Jun 2026 | Exit 3 |  | Hoisting down walers
Wed (17/06) | 17 Jun 2026 | CCW2 |  | Excavation to FEL in progress
Wed (17/06) | 17 Jun 2026 | S1-1 |  | Blast #60 was done this afternoon ard 1521hrs. Now continue to clear the rocks, Soil loading point at Opening 3 for CCW2 as well
Wed (17/06) | 17 Jun 2026 | U3-36 to U3-33 |  | Excavation in progress. Loading point at Opening 2B
Wed (17/06) | 17 Jun 2026 | B2-16 |  | Continue scaffold erection for RC wall. Informed the team to provide more lighting to face the inner side
Wed (17/06) | 17 Jun 2026 | U3-24 |  | Continue rebar works. Plan for casting this week
Wed (17/06) | 17 Jun 2026 | U3 | GL E8-E6 | Excavation ongoing to -14
Wed (17/06) | 17 Jun 2026 | U3 | GL12-11 | Nightshift to continue excavation here
Wed (17/06) | 17 Jun 2026 | U3-20 |  | Tonight plan for lean con casting
Wed (17/06) | 17 Jun 2026 | U3-14 part 2 |  | Waterproofing membrane installation in progress, U3-16: Preparing formwork for drop area lean con casting tonight
Wed (17/06) | 17 Jun 2026 | U3-10, U3-12 |  | Top bar installation in progress
Wed (17/06) | 17 Jun 2026 | P35 |  | Shear link installation ongoing
Wed (17/06) | 17 Jun 2026 | P18 |  | Falsework dismantling in progress
Thu (18/06) | 18 Jun 2026 | B2-16 |  | Scaffold erection completed for RC wall. CGW now preparing to expose couplers, WH hacking ongoing for skinwall area
Thu (18/06) | 18 Jun 2026 | B2 | GL16-13 | Skinwall formwork installation
Thu (18/06) | 18 Jun 2026 | U3-20 |  | Lean con cast last night. Now coupelr exposing ongoing
Thu (18/06) | 18 Jun 2026 | U3-24 |  | Shearlinks installation and cleaning ongoing
Thu (18/06) | 18 Jun 2026 | P33 |  | Arranging materials to start crosshead rebar work
Thu (18/06) | 18 Jun 2026 | P34 |  | Balance shear link installation. Today will continue with balance formwork closing. Tomorrow can cast the crosshead
Thu (18/06) | 18 Jun 2026 | P7 |  | Water jet preparation works
Thu (18/06) | 18 Jun 2026 | Bet. P8 & P9 |  | SH dismantling and modification before shifting to p11
Thu (18/06) | 18 Jun 2026 | P13 |  | NB D02 segment launched last night
Thu (18/06) | 18 Jun 2026 | P9 NR |  | Preparation for segment adjustment works
Thu (18/06) | 18 Jun 2026 | P45 |  | Cement touch up works ongoing
Thu (18/06) | 18 Jun 2026 | P46 |  | No activity
Thu (18/06) | 18 Jun 2026 | P47 |  | 2nd layer caisson strutting works ongoing
Thu (18/06) | 18 Jun 2026 | P48 |  | No activity
Thu (18/06) | 18 Jun 2026 | P50 |  | No activity
Thu (18/06) | 18 Jun 2026 | P43-44 |  | Stitching formwork removal. Materials to shift to P9
Thu (18/06) | 18 Jun 2026 | P2 |  | Stressing material shifting to P3
Thu (18/06) | 18 Jun 2026 | P3 |  | 1/4 lifter shifted
Thu (18/06) | 18 Jun 2026 | U3 | North side, GL-E8 to E6 | Excavation in progress between -14 and -15
Thu (18/06) | 18 Jun 2026 | U3 | South side, GL13 | Drilling ongoing for earth mat works
Thu (18/06) | 18 Jun 2026 | U3 | GL12-11 | Excavation ongoing between -14 to -15
Thu (18/06) | 18 Jun 2026 | U3-16 |  | Lean con casting for drop area in progress
Thu (18/06) | 18 Jun 2026 | U3-14 part 2 |  | Preparing to start partial bottom rebar works, U3-10, U3-12: Top bar installation in progress. Plan for casting next week
Thu (18/06) | 18 Jun 2026 | U3-18 |  | Earth mat completed and inspected by RTO. Today plan for soil backfilling
Thu (18/06) | 18 Jun 2026 | DR4 |  | JGP silo setup in progress
Thu (18/06) | 18 Jun 2026 | P18 |  | Rebar preparation and bending for P19-P20 mid span stitching works
Thu (18/06) | 18 Jun 2026 | P7 |  | Tendon ducts rectification - Water jet continue
Thu (18/06) | 18 Jun 2026 | Zone 2 |  | Vsk Telco MH rectification works
Thu (18/06) | 18 Jun 2026 | P9 |  | NR 1st pair segment adjustment ongoing
Thu (18/06) | 18 Jun 2026 | P10 |  | Continue modification for starter hanger works
Thu (18/06) | 18 Jun 2026 | B2 | GL10-8 | Scaffold erection in progress for skinwall works
Thu (18/06) | 18 Jun 2026 | B2-16 |  | CGW: Coupler exposing and soffit roughening ongoing for RC wall works, WH: Continue hacking at skinwall area
Thu (18/06) | 18 Jun 2026 | U3-24 |  | Continue shearlinks installation and cleaning
Thu (18/06) | 18 Jun 2026 | U3-18 |  | Earth mat works completed. Soil backfilling ongoing prior to lean con casting
Thu (18/06) | 18 Jun 2026 | P33 |  | No activity
Thu (18/06) | 18 Jun 2026 | P34 |  | Balance shear link installation still ongoing
Thu (18/06) | 18 Jun 2026 | P43-44 |  | Stitching formwork removal still ongoing
Thu (18/06) | 18 Jun 2026 | GLE6-E9 |  | Ongoing under platform excavation & soil disposal
Thu (18/06) | 18 Jun 2026 | U3-10 & U3-12 |  | Top bar installation is in progress, target to cast next Monday
Thu (18/06) | 18 Jun 2026 | U3-24 |  | Rebar & formwork installation is in progress, target to cast tomorrow
Thu (18/06) | 18 Jun 2026 | GL11-13 |  | Ongoing under platform excavation & soil disposal
Thu (18/06) | 18 Jun 2026 | P45 |  | Cement touch up works still ongoing
Thu (18/06) | 18 Jun 2026 | P46 |  | 2nd layer caisson formwork closure works ongoing
Thu (18/06) | 18 Jun 2026 | P47 |  | 2nd layer caisson strutting works still ongoing
Thu (18/06) | 18 Jun 2026 | P48 |  | No activity
Thu (18/06) | 18 Jun 2026 | P50 |  | No activity
Thu (18/06) | 18 Jun 2026 | DR4 |  | Silo pump delivery just arrived, setup to begin now
Thu (18/06) | 18 Jun 2026 | Zone 1 |  | Tendon strands preparation
Thu (18/06) | 18 Jun 2026 | GLE6-E9 |  | Ongoing under platform excavation and soil disposal, 1 excavator
Thu (18/06) | 18 Jun 2026 | GLE6-E9 |  | Ongoing under platform excavation and soil disposal, 1 excavator
Thu (18/06) | 18 Jun 2026 | S1-1 GL |  | 2-4 under platform excavation area, Soil sampling ongoing
Thu (18/06) | 18 Jun 2026 | S1-1 GL |  | 2-4 under platform excavation area, Soil sampling ongoing
Fri (19/06) | 19 Jun 2026 | P19-P20 |  | Rebar installation and bending for mid span stitching
Fri (19/06) | 19 Jun 2026 | U3 | North side, GL 32-E8 | Hacking and access levelling ongoing at -15
Fri (19/06) | 19 Jun 2026 | U3 Column C02-2a |  | Rebar planting in progress
Fri (19/06) | 19 Jun 2026 | U3 | GL12-11 | Excavation in progress
Fri (19/06) | 19 Jun 2026 | U3-18 |  | Lean con cast. Balance lean con to be cast at drop area
Fri (19/06) | 19 Jun 2026 | U3-14 part 2 |  | Rebar works in progress, PU grouting ongoing
Fri (19/06) | 19 Jun 2026 | U3-10, U3-12 |  | Top bar installation & RTO inspection in progress
Fri (19/06) | 19 Jun 2026 | P9 NR |  | Segment adjustment in progress
Fri (19/06) | 19 Jun 2026 | P7 |  | Continue water jet works
Fri (19/06) | 19 Jun 2026 | U3-24 |  | Final inspection. To cast slab today
Fri (19/06) | 19 Jun 2026 | Exit 2 |  | Continue coupler exposing for RC wall works
Fri (19/06) | 19 Jun 2026 | B2 | GL7-8 | Scaffold erection ongoing for skinwall works
Fri (19/06) | 19 Jun 2026 | Exit 3 |  | Continue coupler exposing and roughening works for RC wall, Waler installation in progress
Fri (19/06) | 19 Jun 2026 | U3-10, U3-12 |  | Top bar installation & RTO inspection in progress
Fri (19/06) | 19 Jun 2026 | U3-10, U3-12 |  | Top bar installation & RTO inspection ongoing
Fri (19/06) | 19 Jun 2026 | P2 |  | Generators shifting from p2 to p3
Fri (19/06) | 19 Jun 2026 | GL E9 - 32 |  | Hacking of bulging Dwall in progress
Fri (19/06) | 19 Jun 2026 | U3-10 & U3-12 |  | Continues rebar installation & target to cast next Monday
Fri (19/06) | 19 Jun 2026 | U3-24 |  | Final inspection cleared & gonna cast later
Fri (19/06) | 19 Jun 2026 | U3 | GL13-11 | Continue excavation & soil disposal
Sat (20/06) | 20 Jun 2026 | P2 |  | Manhole opening barricade installation work
Sat (20/06) | 20 Jun 2026 | Exit 3 RC wall |  | Extending the access to working area & continue exposing couplers
Sat (20/06) | 20 Jun 2026 | B2 | North side, GL7-5 | Continue working platform erection for skinwall works
Sat (20/06) | 20 Jun 2026 | Exit 2 |  | CGW has started RC wall rebar planting, WH continue hacking at skinwall area
Sat (20/06) | 20 Jun 2026 | B2 | North side, GL27-26 | CJ roughening ongoing for 2nd lift internal wall
Sat (20/06) | 20 Jun 2026 | DR4 |  | Platform prepare for probing
Sat (20/06) | 20 Jun 2026 | P47 |  | MPI test for S2 strut was done. Next step to continue excavation
Sat (20/06) | 20 Jun 2026 | P46 |  | Continue excavation for 3rd layer
Sat (20/06) | 20 Jun 2026 | U3 | North, GL E9-E7 | Hacking ongoing
Sat (20/06) | 20 Jun 2026 | U3 Column C02-2a |  | Rebar works in progress
Sat (20/06) | 20 Jun 2026 | U3-26 |  | Earth mat cable laying and welding works ongoing
Sat (20/06) | 20 Jun 2026 | U3 | GL12-10 | Excavation in progress
Sat (20/06) | 20 Jun 2026 | U3-16 |  | Partial waterproofing membrane installation
Sat (20/06) | 20 Jun 2026 | U3-14 part 2 |  | PU grouting and bottom rebar works in progress
Sat (20/06) | 20 Jun 2026 | U3-18 |  | Coupler exposing
Sat (20/06) | 20 Jun 2026 | U3-10, U3-12 |  | Top bar installation. Plan for casting on Monday
Sat (20/06) | 20 Jun 2026 | CCW1 North |  | Continue rebar works for BR36
Sat (20/06) | 20 Jun 2026 | Exit 3 B2-01 |  | Hirose struts preparation $ continue waler welding works.Concrete packing casting plan ard 5pm
Sat (20/06) | 20 Jun 2026 | CCW1 South |  | Falsework erection in progress
Sat (20/06) | 20 Jun 2026 | CCW2 | South side, GL W5-6 | Exposing couplers and pile hacking
Sat (20/06) | 20 Jun 2026 | Exit 3 RC wall |  | Continue soffit roughening for rebar planting
Sat (20/06) | 20 Jun 2026 | B2 | North side, GL7-9 | Drilling and starter bar straightening for skinwall works
Sat (20/06) | 20 Jun 2026 | Exit 2 RC wall |  | Dongah post-drilling ongoing, CGW continue rebar planting
Sat (20/06) | 20 Jun 2026 | B2 | South side, GL10-12 | Scaffold erection started for skinwall works
Sat (20/06) | 20 Jun 2026 | U3-24 |  | Curing
Sat (20/06) | 20 Jun 2026 | P33 |  | Unloading of rebar for crosshead
Sat (20/06) | 20 Jun 2026 | P33 |  | Current status of crosshead rebar work
Sat (20/06) | 20 Jun 2026 | P36 |  | Tendon wire pulling
Sat (20/06) | 20 Jun 2026 | P35 |  | Casting will be a bit delay due to access blocking by rebar unloading for P33
Sat (20/06) | 20 Jun 2026 | P40 |  | Formwork installation for stump
Sat (20/06) | 20 Jun 2026 | P47 |  | Now no activity
Sat (20/06) | 20 Jun 2026 | P46 |  | Excavation done for NB. Left to do hacking below caisson for rebar work
Sat (20/06) | 20 Jun 2026 | U3-18 |  | Lean con casting at drop area
Sat (20/06) | 20 Jun 2026 | U3-10, U3-12 |  | Continue top bar installation
Sat (20/06) | 20 Jun 2026 | U3 Column C02-2a |  | Continue rebar installation
Sat (20/06) | 20 Jun 2026 | U3-14 part 2 |  | Currently no activity. Manpower focus at U3-10/12
Sat (20/06) | 20 Jun 2026 | U3-26 |  | Continue earth mat cable laying
Sat (20/06) | 20 Jun 2026 | U3 | GL11 | Excavation in progress
Sat (20/06) | 20 Jun 2026 | P7 |  | Water jet work done. Now cleaning and housekeeping
Sat (20/06) | 20 Jun 2026 | P8 |  | SH materials unloading
Sat (20/06) | 20 Jun 2026 | P9 |  | Segment adjustment work
Sat (20/06) | 20 Jun 2026 | P11 |  | Stressing cage assembling
Sat (20/06) | 20 Jun 2026 | P19-20 |  | Mid stitch formwork closing preparation
Sat (20/06) | 20 Jun 2026 | P19 to P20 |  | Rebar installation for mid stitching work
Sat (20/06) | 20 Jun 2026 | P9 NB |  | Tendon wire pulling
Sat (20/06) | 20 Jun 2026 | CCW1 North |  | BR36 roof slab rebar works in progress
Sat (20/06) | 20 Jun 2026 | B1 level |  | Currently no activity
Sat (20/06) | 20 Jun 2026 | Exit 3 B2-01 |  | Waler welding works ongoing and preparing hyrib for concrete packing casting today
Sat (20/06) | 20 Jun 2026 | CCW1 | South side | Falsework erection in progress
Sun (21/06) | 21 Jun 2026 | P30 1st lift |  | Fwk removal ongoing
Sun (21/06) | 21 Jun 2026 | P33 |  | Bottom rebar work ongoing, access preparation & rebar unloading
Sun (21/06) | 21 Jun 2026 | P36 |  | First stage stressing done
Sun (21/06) | 21 Jun 2026 | P35 |  | Curing
Sun (21/06) | 21 Jun 2026 | P43-44 |  | Strand pulling ongoing
Sun (21/06) | 21 Jun 2026 | P46 |  | 3rd layer excavation ongoing
Sun (21/06) | 21 Jun 2026 | P3 |  | LF stressing cage shifting & assembly preparation works ongoing
Sun (21/06) | 21 Jun 2026 | P10 |  | Assembly work ongoing
Mon (22/06) | 22 Jun 2026 | P33 |  | Top rebar work ongoing
Mon (22/06) | 22 Jun 2026 | Zone 2 |  | Stressing cage assembly for P11 MV
Mon (22/06) | 22 Jun 2026 | DR4 |  | Probing done. Now prepare platform for grouting work
Mon (22/06) | 22 Jun 2026 | P9 NBR |  | Stitch rebar works in progress
Mon (22/06) | 22 Jun 2026 | P7 |  | PT duct opening enlargement in progress
Mon (22/06) | 22 Jun 2026 | P36 |  | Stressing work ongoing, P35: curing
Mon (22/06) | 22 Jun 2026 | P48 |  | To continue falsework after materials delivery from P7
Mon (22/06) | 22 Jun 2026 | P47 |  | Started excavation for 4th layer
Mon (22/06) | 22 Jun 2026 | P36 |  | Hacking of grout for 3rd layer caisson. Tomorrow can start rebar work
Mon (22/06) | 22 Jun 2026 | U3-10 & U3-12 |  | Continues shear links & formwork installation, will cast it tonight
Mon (22/06) | 22 Jun 2026 | U3-24 |  | Dismantling of formwork in progress
Mon (22/06) | 22 Jun 2026 | GL11-13 |  | Continues excavation & soil disposal
Mon (22/06) | 22 Jun 2026 | GL32 - E8 |  | Roughening of CJ in progress
Mon (22/06) | 22 Jun 2026 | P33 |  | Top rebar work ongoing
Mon (22/06) | 22 Jun 2026 | P36 |  | Stressing work ongoing
Mon (22/06) | 22 Jun 2026 | CCW1 North |  | BR36 shearlinks installation and cleaning ongoing. Plan for casting tmr
Mon (22/06) | 22 Jun 2026 | Exit 3 RC wall |  | Rebar planting in progress
Mon (22/06) | 22 Jun 2026 | CCW1 South |  | Falsework installation in progress
Mon (22/06) | 22 Jun 2026 | S1-1, S1-2 |  | Blast 62 & 63 was done this afternoon at 1609hrs. Now clearing rocks
Mon (22/06) | 22 Jun 2026 | U3-35 to U3-33 |  | Excavation ongoing
Mon (22/06) | 22 Jun 2026 | P46 |  | No activity
Mon (22/06) | 22 Jun 2026 | P47 |  | Excavation to L4 caisson layer
Mon (22/06) | 22 Jun 2026 | DR4 |  | Concrete block construction on going
Mon (22/06) | 22 Jun 2026 | P7 |  | PT duct opening enlargement in progress
Mon (22/06) | 22 Jun 2026 | B2 | North side, GL7-5 | Straightening of skinwall rebar ongoing
Mon (22/06) | 22 Jun 2026 | B2 | North side, GL10-7 | Skinwall rebar works ongoing
Mon (22/06) | 22 Jun 2026 | Exit 2 RC wall |  | Inner formwork installation in progress
Mon (22/06) | 22 Jun 2026 | Exit 2 skinwall area |  | Scaffold erection in progress
Mon (22/06) | 22 Jun 2026 | B2 | South side, GL11-14 | Scaffold erection ongoing for skinwall works
Mon (22/06) | 22 Jun 2026 | P11 |  | Starter hanger assemble
Mon (22/06) | 22 Jun 2026 | P11 |  | Stressing cage assembly
Mon (22/06) | 22 Jun 2026 | U3-24 |  | Formwork dismantled. Scaffold erection for access ongoing
Mon (22/06) | 22 Jun 2026 | U3-22 to U3-18 |  | No activity
Mon (22/06) | 22 Jun 2026 | U3-10, U3-12 |  | Preparing for final inspection
Mon (22/06) | 22 Jun 2026 | U3-16, U3-18 |  | Partial waterproofing installation. Patching up works at U3-16 drop area and formwork removal at U3-18 drop area
Mon (22/06) | 22 Jun 2026 | U3 | South side, GL31 to E6 | No activity
Mon (22/06) | 22 Jun 2026 | U3 | GL11-10 | Excavation in progress (4 exc)
Mon (22/06) | 22 Jun 2026 | P3 |  | Preparation work for segment launching work tonight..NB 2nd pair
Tue (23/06) | 23 Jun 2026 | P33 |  | Top bar tying / installation ongoing
Tue (23/06) | 23 Jun 2026 | P36 |  | Strands cutting work ongoing & side wing fwk hacking & polyfoam removal
Tue (23/06) | 23 Jun 2026 | P43 to 44 | NB side | Strands pushing ongoing
Tue (23/06) | 23 Jun 2026 | U3-10, U3-12 |  | Casting in progress
Tue (23/06) | 23 Jun 2026 | U3 | GL11 | Excavation and hacking at skinwall area in progress
Tue (23/06) | 23 Jun 2026 | U3-24 |  | CJ hacking ongoing
Tue (23/06) | 23 Jun 2026 | U3-16 |  | Surface cleaning ongoing at drop area, Adjusting working platform for PU grouting works & preparation for bottom rebar works
Tue (23/06) | 23 Jun 2026 | U3-14 part 2 |  | Bottom rebar works ongoing
Tue (23/06) | 23 Jun 2026 | U3-18, U3-20 |  | Clearing debris from KP area, U3-22: Currently no activity
Tue (23/06) | 23 Jun 2026 | P19-20 midspan |  | Wet stitch formwork closing
Tue (23/06) | 23 Jun 2026 | P18 |  | Falsework dismantling
Tue (23/06) | 23 Jun 2026 | P13 |  | Stressing cage assembly
Tue (23/06) | 23 Jun 2026 | P11 MV SB |  | SH installed. Plan for 1st pair launching tmr night
Tue (23/06) | 23 Jun 2026 | P8 NBR |  | UC rebar for stitching to complete today
Tue (23/06) | 23 Jun 2026 | P7 |  | Strand pushing in progress. Balance 3 strand. To complete today
Tue (23/06) | 23 Jun 2026 | B2 | South side, GL32-31 | Skinwall formwork removal
Tue (23/06) | 23 Jun 2026 | B2 | South side, GL29-26 | Skinwall rebar works ongoing
Tue (23/06) | 23 Jun 2026 | Exit 2 RC wall |  | Inner formwork installation in progress
Tue (23/06) | 23 Jun 2026 | Exit 3 RC wall |  | Rebar installation ongoing
Tue (23/06) | 23 Jun 2026 | Exit 3 |  | Struts installation in progress
Tue (23/06) | 23 Jun 2026 | S1-1 B2 level |  | Clearing the loose hanging debonding sheets
Tue (23/06) | 23 Jun 2026 | B1 level |  | No activity
Wed (24/06) | 24 Jun 2026 | P36 |  | Side wing, polyfoam removal ongoing
Wed (24/06) | 24 Jun 2026 | P43-44 | SB side | Strands pushing ongoing
Wed (24/06) | 24 Jun 2026 | P9 NR |  | 1st pair stitching in progress. Target to cast this week
Wed (24/06) | 24 Jun 2026 | P7 |  | Preparation for stressing
Wed (24/06) | 24 Jun 2026 | P49 |  | Formwork closing for footing
Wed (24/06) | 24 Jun 2026 | P51 |  | Tomorrow SPPG will come for cable spiking. This will be the last services affect column work
Wed (24/06) | 24 Jun 2026 | P48 |  | Current status of falsework
Wed (24/06) | 24 Jun 2026 | P46 3rd layer |  | KTC handover half of the area. rebar work in progress
Wed (24/06) | 24 Jun 2026 | P47 4th layer |  | Today can complete excavation 50%. Tomorrow lean con
Wed (24/06) | 24 Jun 2026 | U3 Column C02-2a |  | Rebar works in progress
Wed (24/06) | 24 Jun 2026 | U3-10, U3-12 |  | Casting completed last night
Wed (24/06) | 24 Jun 2026 | U3 | South side, GL13 | Hacking ongoing at skinwall area
Wed (24/06) | 24 Jun 2026 | U3 | GL12-10 | Excavation in progress
Wed (24/06) | 24 Jun 2026 | U3-22 |  | Clearing debris at KP area, U3-20, U3-18: Currently no activity, U3-16: Partial bottom rebar installation in progress, U3-14 part 2: Rebar works in progress
Wed (24/06) | 24 Jun 2026 | P3 SB 2nd pair |  | Strand pushing for stressing work
Wed (24/06) | 24 Jun 2026 | P18 SB |  | Falsework dismantling completed
Wed (24/06) | 24 Jun 2026 | P13 |  | Stressing cage assembly continue
Wed (24/06) | 24 Jun 2026 | DR4 |  | Soil bund making for JGP work
Wed (24/06) | 24 Jun 2026 | P11 SB |  | 1st pair launching tonight
Wed (24/06) | 24 Jun 2026 | P9 NBR UC |  | Wet stitch formwork closing
Wed (24/06) | 24 Jun 2026 | P46 3rd layer caisson |  | Rebar work at changi bound
Wed (24/06) | 24 Jun 2026 | P47 4th layer caisson |  | Bored pile hacking at TPE bound. Excavation done for half of the area
Wed (24/06) | 24 Jun 2026 | CCW1 North |  | BR36 casting in progress
Wed (24/06) | 24 Jun 2026 | CCW1 South |  | Coupler exposing ongoing
Wed (24/06) | 24 Jun 2026 | CCW2 |  | Currently no activity
Wed (24/06) | 24 Jun 2026 | S1-1 |  | Blast #64 was done this afternoon ard 1530hrs, U3-36 to U3-33: Nightshift continue excavation
Wed (24/06) | 24 Jun 2026 | B2 | South side, GL10-8 | Scaffold erection ongoing for skinwall works
Wed (24/06) | 24 Jun 2026 | B2 | South side, GL11-16 | Scaffold erection ongoing for skinwall works
Wed (24/06) | 24 Jun 2026 | B2 | North side, GL12-14 | Skinwall formwork dismantling ongoing
Wed (24/06) | 24 Jun 2026 | U3 | GL11 | Excavation in progress
Wed (24/06) | 24 Jun 2026 | U3-22 |  | Currently no activity, U3-18: Hacking ongoing at KP area
Wed (24/06) | 24 Jun 2026 | U3-14 , U3-16 | part 2 | Dayshift team done for the day. Nightshift to continue rebar works here
Wed (24/06) | 24 Jun 2026 | U3-10, U3-12 |  | Curing
Wed (24/06) | 24 Jun 2026 | U3 | North side, GL31-E6 | Currently no activity
Wed (24/06) | 24 Jun 2026 | P33 |  | No activity
Wed (24/06) | 24 Jun 2026 | P36 |  | Side wing, polyfoam removal ongoing
Wed (24/06) | 24 Jun 2026 | P40 |  | Bearing stump construction in progress
Wed (24/06) | 24 Jun 2026 | P43-P44 |  | SB U5-D6 segment stressing in progress
Wed (24/06) | 24 Jun 2026 | P46 |  | No activity
Wed (24/06) | 24 Jun 2026 | P47 |  | No activity
Wed (24/06) | 24 Jun 2026 | P30 | 1st lift 2nd part | Access & platform extension ongoing
Wed (24/06) | 24 Jun 2026 | P33 |  | Wendyng continue rebar work, 4 workers. Tmr target to start duct installation
Wed (24/06) | 24 Jun 2026 | DR4 |  | Briefing to start work for JGP grouting
Thu (25/06) | 25 Jun 2026 | P36 |  | Current status for falsework removal, polyfoam removal ongoing on NB side
Thu (25/06) | 25 Jun 2026 | P30 1st lift Part 2 |  | Working platform extension ongoing
Thu (25/06) | 25 Jun 2026 | P33 |  | Utracon: anchor body installation, Wendyng: Opening rebar installation
Thu (25/06) | 25 Jun 2026 | P43-44 |  | SB strand pushing ongoing
Thu (25/06) | 25 Jun 2026 | DR4 |  | Machine spoil, fixing ongoing mechanic here
Thu (25/06) | 25 Jun 2026 | U3-22 |  | Waterproofing membrane installation ongoing
Thu (25/06) | 25 Jun 2026 | U3-14 , U3-16 | part 2 | Rebar works ongoing, U3-16: Surveyor checking and marking out point for the delayed pour strip location
Thu (25/06) | 25 Jun 2026 | U3-18, U3-20 |  | Hacking and debris disposal ongoing at KP area, U3-18: PU grouting ongoing at dwall side
Thu (25/06) | 25 Jun 2026 | U3 | South side, GL14-12 | Hacking ongoing at KP area & levelling works, U3 GL12-10: Continue excavation (5 exc)
Thu (25/06) | 25 Jun 2026 | P47 4th layer caisson |  | Bored pile hacking ongoing
Thu (25/06) | 25 Jun 2026 | B2 | South side, GL11-14 | Straightening skinwall starter bars
Thu (25/06) | 25 Jun 2026 | Exit 2 RC wall |  | Formwork installation in progress
Thu (25/06) | 25 Jun 2026 | B2 | South side, GL9-8 | Scaffold erection ongoing for skinwall works
Thu (25/06) | 25 Jun 2026 | B2 | North side, GL7-6 | PU grouting ongoing
Thu (25/06) | 25 Jun 2026 | Exit 3 RC wall |  | Rebar works ongoing
Thu (25/06) | 25 Jun 2026 | CCW2 |  | BP hacking ongoing
Thu (25/06) | 25 Jun 2026 | B1 level |  | No activity
Thu (25/06) | 25 Jun 2026 | CCW1 South |  | Coupler exposing
Thu (25/06) | 25 Jun 2026 | CCW1 North |  | BR36 cast ☑️
Thu (25/06) | 25 Jun 2026 | P14 |  | Barricades installation for materials storage area
Thu (25/06) | 25 Jun 2026 | P13 |  | Assembly of stressing cage for 2nd pair strand installation and stressing works
Thu (25/06) | 25 Jun 2026 | P11 |  | No segment launched last night due to crane breakdown. Pending mechanic to arrive
Thu (25/06) | 25 Jun 2026 | P9NR |  | 1st pair stitching formwork closing at upchainage and rebar installation at downchainage in progress. Target to cast this week
Thu (25/06) | 25 Jun 2026 | P7 |  | Crosshead tendon strands stressing in progress
Thu (25/06) | 25 Jun 2026 | Zone 1 |  | Housekeeping ongoing
Fri (26/06) | 26 Jun 2026 | P30 | 1st lift part 2 | Rebar work ongoing
Fri (26/06) | 26 Jun 2026 | P33 |  | Preparing for duct installation, lifting of ducting materials ongoing
Fri (26/06) | 26 Jun 2026 | P36 |  | Falsework dismantling status
Fri (26/06) | 26 Jun 2026 | P37 |  | No hirose crane, pending decking removal
Fri (26/06) | 26 Jun 2026 | U3 Column C02-2a |  | 1st lift formwork installation in progress
Fri (26/06) | 26 Jun 2026 | U3 Column C01-7 |  | Scaffold erection in progress for column works
Fri (26/06) | 26 Jun 2026 | U3-16 |  | Continue to pump put water and cleaning works at drop area prior to rebar installation, Rebar works in progress. The location for delayed pour strip has been provided yesterday
Fri (26/06) | 26 Jun 2026 | U3-14 part 2 |  | Bar chair installation in progress
Fri (26/06) | 26 Jun 2026 | U3-18 |  | Continue clearing debris around KP area
Fri (26/06) | 26 Jun 2026 | U3-22 |  | Waterproofing membrane installation and patch up works ongoing. Maxbond also preparing for RGT installation, Cleaning ongoing at KP area. Water pump also on standby nearby
Fri (26/06) | 26 Jun 2026 | P46 |  | Cable management and tidy up the area. Half of the 3rd layer caisson will cast tomorrow
Fri (26/06) | 26 Jun 2026 | P45 |  | Removal of unused materials
Fri (26/06) | 26 Jun 2026 | P43-44 |  | Strand pushing at NB side ongoing
Fri (26/06) | 26 Jun 2026 | U3-26 |  | Area preparation for earth mat works
Fri (26/06) | 26 Jun 2026 | U3 | North side, GL12-10 | Continue excavation
Fri (26/06) | 26 Jun 2026 | B2 | North side, GL11 | Skinwall formwork installation ongoing
Fri (26/06) | 26 Jun 2026 | B2 | South side, GL11-12 | Skinwall rebar works ongoing
Fri (26/06) | 26 Jun 2026 | Exit 2 RC wall |  | Formwork installed. Final inspection in the afternoon
Fri (26/06) | 26 Jun 2026 | B2 | North side, GL7-5 | Skinwall rebar works ongoing
Fri (26/06) | 26 Jun 2026 | B2 | South side, GL7-5 | Scaffold erection ongoing for skinwall works
Fri (26/06) | 26 Jun 2026 | Exit 3 RC wall |  | Formwork installation in progress
Fri (26/06) | 26 Jun 2026 | P47 |  | Half of 4th layer excavation to complete today and arrange for lean con
Fri (26/06) | 26 Jun 2026 | P13 |  | Stressing cage assembly in progress
Fri (26/06) | 26 Jun 2026 | P11 |  | SB U01 launched last night
Fri (26/06) | 26 Jun 2026 | P9NR |  | Continue rebar and formworks closing for 1st pair stitching at downchainage
Fri (26/06) | 26 Jun 2026 | P7 |  | Crosshead stressing in progress
Sat (27/06) | 27 Jun 2026 | DR4 |  | Preparing to commence 3 points today, the hosing at silo plant have some issue mechanic on site
Sat (27/06) | 27 Jun 2026 | DR4 |  | Footpath diversion preparation ongoing
Sat (27/06) | 27 Jun 2026 | P46 |  | 3rd layer caisson rebar work ongoing
Sat (27/06) | 27 Jun 2026 | U3 Column C02-2a | South side | Currently no activity
Sat (27/06) | 27 Jun 2026 | U3 Column C01-7 | South side | Working platform installation in progress
Sat (27/06) | 27 Jun 2026 | U3-14 , U3-16 | part 2 | Rebar works in progress
Sat (27/06) | 27 Jun 2026 | U3-22 |  | Rebar works in progress. Started yesterday, RGT installation ongoing, U3-18, U3-20:, Waterproofing membrane installation ongoing, PU grouting ongoing, Continue hacking & clearing debris at U3-18 side
Sat (27/06) | 27 Jun 2026 | U3-26 |  | Earth mat works ongoing between GL14-13, Area preparation for earth mat works continue between GL13-12
Sat (27/06) | 27 Jun 2026 | U3 | GL11-10 | Continue excavation
Sat (27/06) | 27 Jun 2026 | B2 | South side, GL30-26 | Skinwall rebar works and PU grouting ongoing
Sat (27/06) | 27 Jun 2026 | B2 | North side, GL28-26 | Internal wall 2nd lift rebar installation
Sat (27/06) | 27 Jun 2026 | B2 | North side, GL13-11 | Skinwall formwork installation in progress
Sat (27/06) | 27 Jun 2026 | B2 | South side, GL11-14 | Drilling ongoing for skinwall works
Sat (27/06) | 27 Jun 2026 | Exit 2 RC wall | GL11-12 | Cast yesterday, Exit 2 GL11-10: Skinwall rebar works and wall rebar installation ongoing
Sat (27/06) | 27 Jun 2026 | P13 |  | Stressing cage assembly ongoing
Sat (27/06) | 27 Jun 2026 | P9 NBR |  | Stitching formwork closing work, with one partial lane closure, tonight casting
Sat (27/06) | 27 Jun 2026 | P7 |  | Polyfoam removal work & tendon strand cutting & grouting gap fixing work
Sat (27/06) | 27 Jun 2026 | B2 | South side, GL10-5 | Scaffold erection ongoing for skinwall works
Sat (27/06) | 27 Jun 2026 | B2 | North side, GL7-5 | PU grouting ongoing
Sat (27/06) | 27 Jun 2026 | B2 level |  | Clearing debonding sheets, Exit 3 RC wall: Formwork installation in progress
Sat (27/06) | 27 Jun 2026 | P3 NB-U/D03 |  | Strand pulling work ongoing
Sat (27/06) | 27 Jun 2026 | CCW2 |  | Clearing debris
Sat (27/06) | 27 Jun 2026 | S1-1 | North side | Drilling ongoing for next blast location, U3-36 to U3-33: Continue excavation and hacking at skinwall area
Sat (27/06) | 27 Jun 2026 | B1 level |  | CJ hacking for internal wall works ongoing at B1-02 area, No other activity
Sat (27/06) | 27 Jun 2026 | CCW1 South | BR37 | Post-drilling ongoing for missing couplers & continue exposing couplers
Sat (27/06) | 27 Jun 2026 | CCW1 North |  | BR36 no activity
Sat (27/06) | 27 Jun 2026 | P30 1st lift Part 2 |  | Preparing for rebar work
Sat (27/06) | 27 Jun 2026 | P33 |  | Duct installation ongoing
Sat (27/06) | 27 Jun 2026 | P37 |  | Pending hirose crane for decking removal
Sat (27/06) | 27 Jun 2026 | P43-44 SB |  | Strand pushing ongoing
Mon (29/06) | 29 Jun 2026 | P30 | 1st lift Part 2 | Pending to cast today
Mon (29/06) | 29 Jun 2026 | P19-20 midspan |  | NB wet stitch formwork closing
Mon (29/06) | 29 Jun 2026 | P33 |  | Duct installation ongoing
Mon (29/06) | 29 Jun 2026 | P37 |  | Pending 5 nos decking removal
Mon (29/06) | 29 Jun 2026 | P37 |  | Falsework preparation work ongoing
Mon (29/06) | 29 Jun 2026 | P11 SB |  | Initial adjustment completed. Surveyor reading taken and sent to YWL for confirmation
Mon (29/06) | 29 Jun 2026 | P7 |  | Grouting cap installation and housekeeping
Mon (29/06) | 29 Jun 2026 | P40 |  | Preparation for MJ work
Mon (29/06) | 29 Jun 2026 | P42 NB |  | Strand pushing work ongoing
Mon (29/06) | 29 Jun 2026 | DR4 |  | 8nos JGP grouting done. 9th point boring in progress
Mon (29/06) | 29 Jun 2026 | P48 |  | Will resume after materials delivered from P7
Mon (29/06) | 29 Jun 2026 | P47 |  | 4th layer caisson rebar work started
Mon (29/06) | 29 Jun 2026 | P46 |  | New access erection and shifting of materials to resume excavation at SB
Mon (29/06) | 29 Jun 2026 | Zone 1 |  | P3 NB 4th pair segment launching tonight
Mon (29/06) | 29 Jun 2026 | DR4 |  | Tightening of all valves for water charging
Mon (29/06) | 29 Jun 2026 | DR4 |  | Bund wall making to contain the slurry
Mon (29/06) | 29 Jun 2026 | DR4 |  | JGP grouting in progress for No-10
Mon (29/06) | 29 Jun 2026 | P47 |  | 4th layer caisson rebar work and cleaning of debris
Mon (29/06) | 29 Jun 2026 | P46 |  | Resume excavation for TPE bound
Mon (29/06) | 29 Jun 2026 | P30 |  | Column casting completed
Mon (29/06) | 29 Jun 2026 | P33 |  | Tendon duct installation ongoing
Mon (29/06) | 29 Jun 2026 | P42 |  | NB U5/D5 stresssing complete. Shifting stressing cage ongoing
Mon (29/06) | 29 Jun 2026 | U3 | North side, GL31-32 | Excavation in progress, The access at North side has been diverted to facilitate the works from GL28 to CCE onwards
Mon (29/06) | 29 Jun 2026 | U3 | North side, GL28-30 | Hacking works ongoing. Currently workers on dinner break
Mon (29/06) | 29 Jun 2026 | U3 Column C02-2a | South side | Currently no activity
Mon (29/06) | 29 Jun 2026 | U3 Column C01-7 | South side | Currently no activity
Mon (29/06) | 29 Jun 2026 | U3-14 part 2 & U3-16 |  | Rebar works & cast-in pipes installation in progress, U3-18: Balance lean concrete levelling
Mon (29/06) | 29 Jun 2026 | U3-20 |  | Currently no activity, U3-22: Formwork installation & top bar installation in progress. Location for delayed pour strip has been provided
Mon (29/06) | 29 Jun 2026 | U3-26 |  | Earth mat works, U3 GL11-10: Excavation in progress
Mon (29/06) | 29 Jun 2026 | B2 | North side, GL13-11 | Skinwall formwork installation. Plan for casting tmr
Mon (29/06) | 29 Jun 2026 | Exit 2 | GL11-10 | RC wall rebar works & skinwall rebar in progress
Mon (29/06) | 29 Jun 2026 | P46 |  | Excavation ongoing at south side
Mon (29/06) | 29 Jun 2026 | P47 |  | Caisson rebar work at south side
Mon (29/06) | 29 Jun 2026 | DR4 |  | JGP Work in progress
Mon (29/06) | 29 Jun 2026 | B2 S1-1 | South side | Scaffold erection ongoing for skinwall works
Mon (29/06) | 29 Jun 2026 | Exit 3 RC wall |  | Waiting for RTO inspection. Plan for casting tonight
Mon (29/06) | 29 Jun 2026 | U3-36 to U3-31 |  | Excavation in progress
Mon (29/06) | 29 Jun 2026 | P13 |  | No activity
Mon (29/06) | 29 Jun 2026 | P11 |  | Preparation for stitching formwork closing
Mon (29/06) | 29 Jun 2026 | P9 |  | No activity
Mon (29/06) | 29 Jun 2026 | P7 |  | Scaffolding(top) dismantling and material shifting
Mon (29/06) | 29 Jun 2026 | P3 |  | Strand pushing at south..tonight segment launching for NB U/D04
Mon (29/06) | 29 Jun 2026 | CCW2 |  | Gravel drainage works ongoing
Mon (29/06) | 29 Jun 2026 | B1 level |  | No activity
Mon (29/06) | 29 Jun 2026 | CCW1 North |  | No activity
Mon (29/06) | 29 Jun 2026 | CCW1 South |  | BR37 bottom rebar works in progress
Tue (30/06) | 30 Jun 2026 | P33 NB |  | Tomorrow will handover for shear link. SB: to complete ducting this week
Tue (30/06) | 30 Jun 2026 | P40 |  | Bracket delivery for MJ segment working platform
Tue (30/06) | 30 Jun 2026 | P3 NB |  | 4th pair strand pushing for stressing work
Tue (30/06) | 30 Jun 2026 | P11 SB |  | Stitch formwork closing
Tue (30/06) | 30 Jun 2026 | P47 |  | 4th caisson fwk closure ongoing
Tue (30/06) | 30 Jun 2026 | P46 |  | BP removal ongoing
Tue (30/06) | 30 Jun 2026 | U3 | GL30-E8 | Hacking of rock is in progress
Tue (30/06) | 30 Jun 2026 | U3-14 & U3-16 |  | Continues rebar inatallation work
Tue (30/06) | 30 Jun 2026 | U3-22 |  | Rebar installation in progress
Tue (30/06) | 30 Jun 2026 | U3 | GL12-10 | Continues excavation & soil disposal
Tue (30/06) | 30 Jun 2026 | P33 |  | PT duct installation
Tue (30/06) | 30 Jun 2026 | P35 |  | No activity
Tue (30/06) | 30 Jun 2026 | U3 | GL30-E8 | Hacking of rock is in progress, Excavation in progress, Disposal in progress, 5 excavator
Tue (30/06) | 30 Jun 2026 | U3 | GL30-E8 | Hacking of rock is in progress, Excavation in progress, Disposal in progress, 5 excavator
Tue (30/06) | 30 Jun 2026 | P41 |  | Stressing cage installation
Tue (30/06) | 30 Jun 2026 | U3-14 & U3-16 |  | Continues rebar inatallation work
Tue (30/06) | 30 Jun 2026 | U3-14 & U3-16 |  | Continues rebar inatallation work
Tue (30/06) | 30 Jun 2026 | U3-22 |  | Rebar installation in progress
Tue (30/06) | 30 Jun 2026 | U3-22 |  | Rebar installation in progress
Tue (30/06) | 30 Jun 2026 | U3 | GL12-10 | Continues excavation & soil disposal
Tue (30/06) | 30 Jun 2026 | U3 | GL12-10 | Continues excavation & soil disposal
Tue (30/06) | 30 Jun 2026 | P46 |  | No activity
Tue (30/06) | 30 Jun 2026 | P47 |  | Caisson formwork closing at south side
Tue (30/06) | 30 Jun 2026 | P11 |  | No activity
Tue (30/06) | 30 Jun 2026 | P7 |  | Bottom formwork dismantling
Tue (30/06) | 30 Jun 2026 | P3 |  | NB U/D04 strand pushing on going
Wed (01/07) | 01 Jul 2026 | P11 SB |  | Wet stitch formwork closing. To complete today, cast tomorrow
Wed (01/07) | 01 Jul 2026 | P9 NBR |  | 1st pair stressing
Wed (01/07) | 01 Jul 2026 | P33 |  | Duct installation ongoing
Wed (01/07) | 01 Jul 2026 | P37 |  | Falsework erection
Wed (01/07) | 01 Jul 2026 | P40 MJ |  | Current status
Wed (01/07) | 01 Jul 2026 | P7 |  | Bottom formwork dismantling. Loosening for platform dismantling
Wed (01/07) | 01 Jul 2026 | U3 | GL E9-8 | Excavation ongoing to expose U3-06 CJ area
Wed (01/07) | 01 Jul 2026 | U3 | North side, GL28-32 | Excavation & hacking works ongoing
Wed (01/07) | 01 Jul 2026 | U3 Column C02-2a | South side | Currently no activity
Wed (01/07) | 01 Jul 2026 | U3 Column C01-7 | South side | Currently no activity
Wed (01/07) | 01 Jul 2026 | U3-14 part 2 |  | Top bar rebar currently no activity, U3-16: Bar chair installation in progress
Wed (01/07) | 01 Jul 2026 | U3-18, U3-20 |  | Currently no activity
Wed (01/07) | 01 Jul 2026 | U3-22 |  | Shearlinks installation and welding ongoing. Plan for casting tmr
Wed (01/07) | 01 Jul 2026 | U3-26 |  | Levelling ongoing. Plan for lean con casting tonight, U3 GL11-9: Excavation ongoing. Already breakthrough to the other side
Wed (01/07) | 01 Jul 2026 | B2-38 internal wall |  | Plan for casting tonight
Wed (01/07) | 01 Jul 2026 | B2 | South side, GL5-6 | Skinwall starter straightening ongoing
Wed (01/07) | 01 Jul 2026 | Exit 3 |  | No activity
Wed (01/07) | 01 Jul 2026 | B1 level | B1-08 area | Internal wall rebar works & partial formwork installation in progress, B1 level (B1-07 area): Scaffold erection ongoing for internal wall works
Wed (01/07) | 01 Jul 2026 | B1 level | B1-04 area | Internal wall rebar works ongoing
Wed (01/07) | 01 Jul 2026 | CCW1 South |  | BR37 rebar works ongoing
Wed (01/07) | 01 Jul 2026 | S1-2 |  | Blast 68 was completed this afternoon. Now continue excavation and disposal
Wed (01/07) | 01 Jul 2026 | CCW2 |  | Subsoil drain works ongoing and pile hacking, Note: S1-1 access from B2 level to underplatform is currently being dismantled. Access is now from CCW South
Wed (01/07) | 01 Jul 2026 | CCW1 North |  | Falsework dismantling in progress
Thu (02/07) | 02 Jul 2026 | P3 NB 5th pair |  | Strand pushing for stressing work
Thu (02/07) | 02 Jul 2026 | P33 |  | Duct installation ongoing
Thu (02/07) | 02 Jul 2026 | DR4 |  | Preparation work for JGP
Thu (02/07) | 02 Jul 2026 | P47 |  | Caisson formwork removal at south
Thu (02/07) | 02 Jul 2026 | P46 |  | Preparation work for L3 caisson RC work and also S2 strut installation
Thu (02/07) | 02 Jul 2026 | DR3 |  | Coring works for weep hole
Thu (02/07) | 02 Jul 2026 | P7 NB |  | 1st part of working platform dismantled last night
Thu (02/07) | 02 Jul 2026 | P9 NBR |  | SH dismantled last night
Thu (02/07) | 02 Jul 2026 | P11 SB |  | 1st pair wet stitch to cast at 2pm
Thu (02/07) | 02 Jul 2026 | P37 |  | Falsework erection ongoing
Thu (02/07) | 02 Jul 2026 | P40 MJ |  | Bracket installation for FBCM
Thu (02/07) | 02 Jul 2026 | P35 |  | Pending wing fwk removal to proceed with post tensioning works this weekend
Thu (02/07) | 02 Jul 2026 | P41-44 |  | Strand pushing ongoing
Fri (03/07) | 03 Jul 2026 | P19-20 midspan |  | Wet stitch NB rebar installation
Fri (03/07) | 03 Jul 2026 | P9 NBR |  | Wet stitch formwork dismantling
Fri (03/07) | 03 Jul 2026 | P7 |  | Continue falsework dismantling
Fri (03/07) | 03 Jul 2026 | P40 |  | Bearing plates installation ongoing
Fri (03/07) | 03 Jul 2026 | P33 |  | Duct installation & shear links ongoing
Fri (03/07) | 03 Jul 2026 | P35 |  | Pending wing fwk removal for post tensioning
Fri (03/07) | 03 Jul 2026 | P37 |  | Channel, barricade & working platform installation ongoing
Fri (03/07) | 03 Jul 2026 | P46 |  | Rebar caisson & preparing for strut installation ongoing
Fri (03/07) | 03 Jul 2026 | P47 |  | Excavation ongoing
Sat (04/07) | 04 Jul 2026 | P40 |  | Bearing installation completed (8/8nos), today afternoon casting
Sat (04/07) | 04 Jul 2026 | P46 |  | L3 caisson rebar works at south side, s2 strut installation at north side
Sat (04/07) | 04 Jul 2026 | DR3 |  | Coring works for weep hole ongoing
Sat (04/07) | 04 Jul 2026 | P47 |  | Excavation and bored pile hacking ongoing
Sat (04/07) | 04 Jul 2026 | 800mm PW |  | Internal pressure test ongoing
Sat (04/07) | 04 Jul 2026 | DR4 |  | JGP Works ongoing
Sat (04/07) | 04 Jul 2026 | P13 |  | Preparation for stressing work
Sat (04/07) | 04 Jul 2026 | P11 |  | Segment adjustment at north side, stitching formwork dismantling at south side
Sat (04/07) | 04 Jul 2026 | P7 |  | Crosshead falsework dismantling status
Sat (04/07) | 04 Jul 2026 | P3 |  | Preparation of stressing work, and material shifting
Sat (04/07) | 04 Jul 2026 | P30 |  | Column formwork dismantling
Sat (04/07) | 04 Jul 2026 | P33 |  | Duct installation & shear links ongoing
Sat (04/07) | 04 Jul 2026 | P37 |  | Crosshead working platform installation
Sat (04/07) | 04 Jul 2026 | P40 |  | Current status of bracket installation and working platform installation..Bearing: waiting for inspection before grouting
Sat (04/07) | 04 Jul 2026 | P46 |  | S2 strut installation completed at north side, caisson rebar work at south side
Sat (04/07) | 04 Jul 2026 | P47 |  | Excavation and bored pile hacking
Sat (04/07) | 04 Jul 2026 | DR4 |  | Slurry disposal and JGP works ongoing
Sat (04/07) | 04 Jul 2026 | P13 |  | Side stressing completed. Now no activity
Sat (04/07) | 04 Jul 2026 | P11 |  | Stitching formwork dismantling
Sat (04/07) | 04 Jul 2026 | P7 |  | Crosshead working platform dismantling
Sat (04/07) | 04 Jul 2026 | P3 |  | Strand pushing for stressing
Sat (04/07) | 04 Jul 2026 | P33 |  | Duct installation & shear links ongoing
Sat (04/07) | 04 Jul 2026 | P35 |  | No activity
Sat (04/07) | 04 Jul 2026 | P37 |  | Working platform installation ongoing
Mon (06/07) | 06 Jul 2026 | P19-20 NB midspan |  | Wet stitch formwork closing. Wednesday to cast
Mon (06/07) | 06 Jul 2026 | P11 | MV | SB wet stitch formwork dismantling, NB: Segment adjusting
Mon (06/07) | 06 Jul 2026 | P7 |  | Left primary beam and leg frame at SB side. Continue material shifting to zone 4
Mon (06/07) | 06 Jul 2026 | P30 |  | No activity
Mon (06/07) | 06 Jul 2026 | P33 |  | Crosshead formwork closure ongoing
Mon (06/07) | 06 Jul 2026 | P35 |  | No activity
Mon (06/07) | 06 Jul 2026 | P37 |  | Crosshead working platform installation in progress
Mon (06/07) | 06 Jul 2026 | P40 |  | Bracket installation and working platform installation in progress
Mon (06/07) | 06 Jul 2026 | P46 |  | 3rd layer caisson formwork closure in progress
Mon (06/07) | 06 Jul 2026 | P47 |  | 4th layer caisson excavation in progress
Mon (06/07) | 06 Jul 2026 | P48 |  | Moving of Falsework from P7 in progress
Mon (06/07) | 06 Jul 2026 | DR4 |  | No JGP activity for today
Mon (06/07) | 06 Jul 2026 | CCW1 South |  | BR37 awaiting COS & PE declaration prior to casting
Mon (06/07) | 06 Jul 2026 | U3-39 | South side GL W5-7 | Lean concrete done last week. Currently no activity
Mon (06/07) | 06 Jul 2026 | U3-37 |  | Excavation and disposal ongoing at Opening 3, Levelling ongoing at BP area
Mon (06/07) | 06 Jul 2026 | U3-38 |  | Coupler exposing ongoing, Blast 70 & 71 were done this afternoon at 4pm
Mon (06/07) | 06 Jul 2026 | CCW1 North |  | Multibase has started preparation for coring works
Mon (06/07) | 06 Jul 2026 | P33 |  | Crosshead side formwork closing
Mon (06/07) | 06 Jul 2026 | P35 |  | Scaffold erection for stressing work
Mon (06/07) | 06 Jul 2026 | P37 |  | Working platform installation
Mon (06/07) | 06 Jul 2026 | B1 level | along B1-02, B1-04 | Internal wall rebar works in progress
Mon (06/07) | 06 Jul 2026 | P40 |  | Bearing installation
Mon (06/07) | 06 Jul 2026 | B1 level | along B1-04, B1-06, B1-08 | Internal wall formwork installation in progress
Mon (06/07) | 06 Jul 2026 | Exit 3 |  | No activity. RC wall formwork has been dismantled
Mon (06/07) | 06 Jul 2026 | B2 | North side, GL9-8 | Skinwall formwork installation in progress
Mon (06/07) | 06 Jul 2026 | Exit 2 | GL11-10 | Skinwall & RC wall casting
Mon (06/07) | 06 Jul 2026 | U3-26 |  | Bottom bar installation in progress
Mon (06/07) | 06 Jul 2026 | U3-18, U3-20 |  | Currently no activity
Mon (06/07) | 06 Jul 2026 | U3-28 |  | Earth mat works ongoing
Mon (06/07) | 06 Jul 2026 | U3-31 to U3-34 |  | Excavation in progress
Mon (06/07) | 06 Jul 2026 | U3-22 |  | Cast last Thursday. Now removing formwork supports
Mon (06/07) | 06 Jul 2026 | U3-14 & U3-16 | part 2 | Joining of casting pipes and preparing for final inspection
Mon (06/07) | 06 Jul 2026 | U3 Column C01-7 | South side | No activity
Mon (06/07) | 06 Jul 2026 | U3 Column C02-2a | South side | No activity
Mon (06/07) | 06 Jul 2026 | U3 | North side, GL27-30 | Current status of excavation and hacking works
Mon (06/07) | 06 Jul 2026 | U3 | U3-07, GL31 | Hacking works ongoing at KP area
Mon (06/07) | 06 Jul 2026 | U3 | U3-05, U3-04, GL32-E8 | Subsoil drain works ongoing
Mon (06/07) | 06 Jul 2026 | P13 |  | Tonight to continue stressing at SB side
Mon (06/07) | 06 Jul 2026 | P11 1st pair |  | SB stressing work completed. Strand cutting in progress, NB to continue segment alignment
Mon (06/07) | 06 Jul 2026 | P9 NBR |  | Segment U02 to launch tonight
Mon (06/07) | 06 Jul 2026 | P7 |  | To complete falsework dismantling for the balance item
Mon (06/07) | 06 Jul 2026 | P1 NB |  | Lean concrete for pad footing, hacking until 7pm. Debris clearing only
Tue (07/07) | 07 Jul 2026 | P11 NB |  | Segment adjusting
Tue (07/07) | 07 Jul 2026 | P9 NBR U02 |  | Segment launched last night. Tonight to launch D02
Tue (07/07) | 07 Jul 2026 | P30 |  | No activity
Tue (07/07) | 07 Jul 2026 | P33 |  | Crosshead formwork closure in progress
Tue (07/07) | 07 Jul 2026 | B2 | North side, GL9-7 | Skinwall formwork installation in progress
Tue (07/07) | 07 Jul 2026 | Exit 2 |  | Skinwall and RC wall (RHS) cast yesterday
Tue (07/07) | 07 Jul 2026 | P35 |  | Strand pushing for stressing work in progress
Tue (07/07) | 07 Jul 2026 | P35 |  | Strand pushing for stressing work in progress
Tue (07/07) | 07 Jul 2026 | P40 |  | Bracket installation and working platform installation in progress
Tue (07/07) | 07 Jul 2026 | U3-28 |  | Earth mat cable laying ongoing
Tue (07/07) | 07 Jul 2026 | U3-26 |  | Rebar works in progress
Tue (07/07) | 07 Jul 2026 | P46 |  | 3rd layer caisson formwork closure in progress
Tue (07/07) | 07 Jul 2026 | P47 |  | Rebar works for 4th layer caisson formwork in progress
Tue (07/07) | 07 Jul 2026 | P48 |  | No activity
Tue (07/07) | 07 Jul 2026 | DR4 |  | Total 25 points done, today planning to do 4 to 5 points
Tue (07/07) | 07 Jul 2026 | U3-20, U3-18 |  | Coupler bar installation ongoing
Tue (07/07) | 07 Jul 2026 | U3-14 & U3-16 | part 2 | Casting in progress
Tue (07/07) | 07 Jul 2026 | U3-05 |  | Sub soil drain work by 2 excavators
Tue (07/07) | 07 Jul 2026 | U3-07 |  | Excavation & internal transfer by 1 excavator
Wed (08/07) | 08 Jul 2026 | P33 |  | Shear link installation and WH installation of cast in items. To cast on Friday
Wed (08/07) | 08 Jul 2026 | P35 |  | Tendon wire pulling
Wed (08/07) | 08 Jul 2026 | P37 |  | Jacking installation for crosshead platform. 5 workers
Wed (08/07) | 08 Jul 2026 | P40 |  | Current status of jack base installation
Wed (08/07) | 08 Jul 2026 | P46 |  | 3rd layer caisson formwork closure in progress
Wed (08/07) | 08 Jul 2026 | P47 |  | Rebar works for 4th layer caisson formwork closure ongoing
Wed (08/07) | 08 Jul 2026 | P48 |  | Falsework column jack installation in progress
Wed (08/07) | 08 Jul 2026 | DR4 |  | JGP works ongoing, one point completed, JGP works ongoing for P89 and P104
Wed (08/07) | 08 Jul 2026 | P11 NB |  | 1st pair alignment waiting for YWL confirmation
Wed (08/07) | 08 Jul 2026 | P11 SB |  | 600T crane setting up for Stressing cage dismantling and shifting of SH to P10 SB
Wed (08/07) | 08 Jul 2026 | P7 |  | Leg frame modification for P48
Wed (08/07) | 08 Jul 2026 | P48 |  | Assembling of falsework for erection
Wed (08/07) | 08 Jul 2026 | P47 |  | Center portion rebar work done. Will shift formwork from P46
Wed (08/07) | 08 Jul 2026 | P11 SB |  | SH dismantling
Wed (08/07) | 08 Jul 2026 | P30 |  | Working platform installation for 2nd lift in progress
Wed (08/07) | 08 Jul 2026 | P33 |  | Shear link installation and formwork closure in progress
Wed (08/07) | 08 Jul 2026 | P35 |  | Strand pulling for stressing work in progress
Wed (08/07) | 08 Jul 2026 | P37 |  | Crosshead wing form formwork installation in progress
Wed (08/07) | 08 Jul 2026 | P19-20 midspan |  | Pump car setting up for wet stitch casting
Wed (08/07) | 08 Jul 2026 | P40 |  | Current status of jack base installation
Thu (09/07) | 09 Jul 2026 | P19-P20 |  | Mid stitch cast yesterday
Thu (09/07) | 09 Jul 2026 | P13 |  | Preparation for stressing works for NB
Thu (09/07) | 09 Jul 2026 | P12 |  | Scaffold dismantling for LF shifting works from Zone 1 to P13
Thu (09/07) | 09 Jul 2026 | P11 |  | Segment adjustment for NB segment and 1st pair stitching materials shifting
Thu (09/07) | 09 Jul 2026 | P10 |  | Starter hanger installation works at SB
Thu (09/07) | 09 Jul 2026 | P8 |  | Stressing cage dismantling and modification for P9 NBR
Thu (09/07) | 09 Jul 2026 | DR4 |  | JGP preparation work
Thu (09/07) | 09 Jul 2026 | P48 |  | Assembly of column falsework
Thu (09/07) | 09 Jul 2026 | P47 |  | L4 caisson rebar works
Thu (09/07) | 09 Jul 2026 | P46 |  | No activity
Thu (09/07) | 09 Jul 2026 | 800mm PW |  | Pressure test ongoing
Thu (09/07) | 09 Jul 2026 | P40 |  | Working platform installation
Thu (09/07) | 09 Jul 2026 | P37 |  | Crosshead side formwork installation
Thu (09/07) | 09 Jul 2026 | Zone 1 |  | Housekeeping works
Thu (09/07) | 09 Jul 2026 | P30 |  | Current status of working platform installation for 2nd lift
Thu (09/07) | 09 Jul 2026 | P33 |  | Formwork closure in progress
Thu (09/07) | 09 Jul 2026 | P35 |  | No activity
Thu (09/07) | 09 Jul 2026 | P37 |  | Crosshead wing formwork installation in progress
Thu (09/07) | 09 Jul 2026 | P40 |  | No activity in the day, yesterday night preparation works for jack base installation tonight begin installation
Thu (09/07) | 09 Jul 2026 | 800mm PW |  | Pressure test witnessed by PUB. Leakage test was successful
Thu (09/07) | 09 Jul 2026 | P46 |  | S2 strut installation
Thu (09/07) | 09 Jul 2026 | P47 |  | L4 caisson rebar installation
Thu (09/07) | 09 Jul 2026 | DR4 |  | 3probing point coming, preparation for JGP work
Fri (10/07) | 10 Jul 2026 | P30 2nd lift |  | Working platform erection ongoing
Fri (10/07) | 10 Jul 2026 | P33 |  | Preparing for casting tmr
Fri (10/07) | 10 Jul 2026 | P35 |  | Post tensioning work ongoing
Fri (10/07) | 10 Jul 2026 | P37 |  | Preparing for bottom rebar work
Fri (10/07) | 10 Jul 2026 | P40 MJ |  | 1 pair launched last night
Fri (10/07) | 10 Jul 2026 | P33 |  | Balance formwork closing and final inspection. Tomorrow to cast
Fri (10/07) | 10 Jul 2026 | P35 |  | Polyform removal. Tomorrow to start falsework dismantling
Fri (10/07) | 10 Jul 2026 | P37 |  | GI pipe support installation for crosshead rebar work
Fri (10/07) | 10 Jul 2026 | P46 |  | 3rd layer caisson S2 strut works in progress
Fri (10/07) | 10 Jul 2026 | P47 |  | 4th layer caisson formwork closure in progress
Fri (10/07) | 10 Jul 2026 | P48 |  | Falsework erection for north column in progress
Fri (10/07) | 10 Jul 2026 | P51 |  | Lowering of rebars for rebar tying works
Fri (10/07) | 10 Jul 2026 | DR4 |  | Finished JGP works for P104, next point will be P87, target to do 5 points by today
Sat (11/07) | 11 Jul 2026 | P3 |  | Preparing for lifter shifting
Sat (11/07) | 11 Jul 2026 | Exit 3 |  | Excavation in progress
Sat (11/07) | 11 Jul 2026 | B2 | North side, GL5-7 | Skinwall formwork installation in progress, B2 GL7-9 (North side): Skinwall currently no activity yet
Sat (11/07) | 11 Jul 2026 | 800mm dia water pipe |  | Preparing for ladder installation for butterfly valve
Sat (11/07) | 11 Jul 2026 | DR4 |  | Platform preparation for JGP grouting. 31nos done. Today plan to complete 5nos
Sat (11/07) | 11 Jul 2026 | U3-30 |  | Earth mat cable laying completed, Subsoil drain works ongoing, U3-32: Hacking ongoing at KP area
Sat (11/07) | 11 Jul 2026 | B2 | North side, GL9 | Skinwall patching ongoing at previous bulging part
Sat (11/07) | 11 Jul 2026 | Exit 2 |  | Houskeeping. No other activity yet
Sat (11/07) | 11 Jul 2026 | U3-20 |  | Rebar works ongoing, RG to drill for piezo installation here once finish at U3-18 area
Sat (11/07) | 11 Jul 2026 | B2 | South side, GL17 | Skinwall rebar works ongoing
Sat (11/07) | 11 Jul 2026 | U3-26 |  | Top bar installation on progress
Sat (11/07) | 11 Jul 2026 | U3-28 |  | Rebar works in progress
Sat (11/07) | 11 Jul 2026 | Column C01-3 | South side | Scaffold erection ongoing for column works
Sat (11/07) | 11 Jul 2026 | U3-18 |  | RG drilling ongoing for piezo installation
Sat (11/07) | 11 Jul 2026 | U3 | North side, GL28-30 | Exposing rock
Sat (11/07) | 11 Jul 2026 | Column C01-7 | South side | Rebar works ongoing
Sat (11/07) | 11 Jul 2026 | Column C02-2a |  | 1st lift just cast. Bonding agent will be applied this afternoon
Sat (11/07) | 11 Jul 2026 | U3-07 |  | Formwork installation for drop area lean con casting, Hacking ongoing at KP area
Sat (11/07) | 11 Jul 2026 | U3-05 |  | Hacking ongoing to expose couplers at barrette pile area, No other activity yet
Sat (11/07) | 11 Jul 2026 | P51 |  | Lowering down rebar for abudment wall
Sat (11/07) | 11 Jul 2026 | P48 |  | Falsework erection for crosshead
Sat (11/07) | 11 Jul 2026 | P47 |  | Formwork closing for caisson. Today to cast all
Sat (11/07) | 11 Jul 2026 | P46 |  | 2nd layer strut installation and welding. Monday planned for MPI test
Sat (11/07) | 11 Jul 2026 | P37 |  | GI pipe support installation and crosshead rebar work
Sat (11/07) | 11 Jul 2026 | P33 crosshead |  | Will cast today
Sat (11/07) | 11 Jul 2026 | CCW1 South |  | No activity
Sat (11/07) | 11 Jul 2026 | U3-39 | South side | Currently no activity, U3-39 (North side): Preparing for subsoil drain works
Sat (11/07) | 11 Jul 2026 | U3-38 |  | Drilling ongoing for earth mat works
Sat (11/07) | 11 Jul 2026 | Between U3-37/U3-38 |  | Hacking ongoing at BP area and clearing debris, U3-35 to U3-31: Excavation and disposal ongoing
Sat (11/07) | 11 Jul 2026 | U3-37 |  | Hacking ongoing to expose couplers
Sat (11/07) | 11 Jul 2026 | CCW1 North |  | Tunnel eye hacking ongoing
Sat (11/07) | 11 Jul 2026 | P13 |  | 1/3 lifter installed. Now Ultracon clearing materials for segment launching area
Sat (11/07) | 11 Jul 2026 | B1-04, B1-06, B1-08 |  | Internal wall casting just completed today
Sat (11/07) | 11 Jul 2026 | B1 level |  | No other activity
Sat (11/07) | 11 Jul 2026 | P9 |  | Tendon wire pulling. Watch man provided
Sat (11/07) | 11 Jul 2026 | Exit 3 bomb pit |  | Excavation ongoing. Currently rectifying 1 excavator
Sat (11/07) | 11 Jul 2026 | Exit 3 RC wall |  | Waterproofing works ongoing
Sat (11/07) | 11 Jul 2026 | B2 | North side, GL4-7 | Skinwall formwork installation ongoing, Tonight plan for GL4-9 skinwall casting
Sat (11/07) | 11 Jul 2026 | B2 | North side, GL9 | Continue patching works
Sat (11/07) | 11 Jul 2026 | U3-30 |  | Earth mat completed & subsoil drain works ongoing. Plan for lean con casting tonight
Sat (11/07) | 11 Jul 2026 | B2 | South side, GL25-26 | Skinwall rebar works in progress
Sat (11/07) | 11 Jul 2026 | U3-26 |  | Shearlinks installation, U3-28: Top bar installation in progress
Sat (11/07) | 11 Jul 2026 | U3-18, U3-20 |  | Rebar works in progress
Sat (11/07) | 11 Jul 2026 | U3-18 |  | RG continue drilling for piezo installation. About 300mm more to drill
Sat (11/07) | 11 Jul 2026 | U3-09 |  | Hacking and excavation ongoing
Sat (11/07) | 11 Jul 2026 | Column C01-7 | South side | Continue rebar installation
Sat (11/07) | 11 Jul 2026 | U3-07, U3-09 |  | Subsoil drain works ongoing
Sat (11/07) | 11 Jul 2026 | U3-07 |  | Formwork installation for drop area. Tonight plan for lean con casting
Sat (11/07) | 11 Jul 2026 | U3-05 |  | Hacking ongoing to expose couplers
Sat (11/07) | 11 Jul 2026 | DR4 |  | JGP grouting 2 points done as of today
Sat (11/07) | 11 Jul 2026 | P47 |  | Concrete on site for caisson casting
Sat (11/07) | 11 Jul 2026 | P48 |  | Continue falsework assembling
Sat (11/07) | 11 Jul 2026 | P46 |  | Continue strut welding
Sat (11/07) | 11 Jul 2026 | P40 |  | Precast block casting. 4nos
Sat (11/07) | 11 Jul 2026 | P37 |  | Crosshead bottom rebar work
Sat (11/07) | 11 Jul 2026 | P33 |  | Preparing for casting
Sat (11/07) | 11 Jul 2026 | CCW1 South |  | Only survey works. No other activity
Sat (11/07) | 11 Jul 2026 | CCW1 North |  | Multibase preparation works ongoing for tunnel eye hacking works
Sat (11/07) | 11 Jul 2026 | U3-39 | North side | Subsoil drain works ongoing, U3-37: Coupler exposing & skinwall hacking ongoing
Sat (11/07) | 11 Jul 2026 | U3-37 |  | Coupler exposing & skinwall hacking ongoing, U3-38:, Earthmat trenching works ongoing, ATC preparing for earth mat drilling works, HSL hacking ongoing for 6nos BP (between U3-37/U3-38)
Sat (11/07) | 11 Jul 2026 | U3-39 | South side | Partial waterproofing membrane laying & preparing welding works at KP area
Sat (11/07) | 11 Jul 2026 | P13 |  | Now ultracon cutting of tendon wire for capping. One side lifter up
Sat (11/07) | 11 Jul 2026 | P11 |  | Up chainage stitching rebar work. Down chaingage stitching formwork closing
Sun (12/07) | 12 Jul 2026 | DR4 |  | JGP works ongoing
Sun (12/07) | 12 Jul 2026 | P48 |  | Falsework erection status
Sun (12/07) | 12 Jul 2026 | P47 |  | Caisson wall curing, no activity
Sun (12/07) | 12 Jul 2026 | P46 |  | Strut welding work ongoing
Sun (12/07) | 12 Jul 2026 | N2 to N1 |  | Painting works ongoing
Sun (12/07) | 12 Jul 2026 | P13 |  | LF installation ongoing
Sun (12/07) | 12 Jul 2026 | Column C01-7 | South side | Continue rebar installation
Sun (12/07) | 12 Jul 2026 | Column C01-7 | South side | Continue rebar installation
Sun (12/07) | 12 Jul 2026 | P3 |  | Rail adjustment ongoing for LF shifting
Sun (12/07) | 12 Jul 2026 | P7-8 |  | Material shifting ongoing
Sun (12/07) | 12 Jul 2026 | U3-18, U3-20 |  | Rebar works in progress
Sun (12/07) | 12 Jul 2026 | U3-18, U3-20 |  | Rebar works in progress
Sun (12/07) | 12 Jul 2026 | P30 | 2nd lift | No activity
Sun (12/07) | 12 Jul 2026 | P33 |  | Curing
Sun (12/07) | 12 Jul 2026 | P35 |  | No activity
Sun (12/07) | 12 Jul 2026 | P37 |  | Bottom rebar work ongoing
Mon (13/07) | 13 Jul 2026 | 800mm dia water pipe |  | Flushing of pipe and putting chlorine
Mon (13/07) | 13 Jul 2026 | DR4 |  | 37 points grouting done as of now. Today plan to complete around 4 points
Mon (13/07) | 13 Jul 2026 | P30 |  | No activity
Mon (13/07) | 13 Jul 2026 | P33 |  | Curing for crosshead in progress
Mon (13/07) | 13 Jul 2026 | P35 |  | No activity
Mon (13/07) | 13 Jul 2026 | P37 |  | Top rebar works in progress
Mon (13/07) | 13 Jul 2026 | P40 |  | Access erection in progress
Mon (13/07) | 13 Jul 2026 | P46 |  | Today to resume excavation
Mon (13/07) | 13 Jul 2026 | P47 |  | Formwork removal
Mon (13/07) | 13 Jul 2026 | P48 |  | Current status of platform erection for crosshead
Mon (13/07) | 13 Jul 2026 | P51 |  | Cleaning before resume rebar work
Mon (13/07) | 13 Jul 2026 | P11 NB |  | 1st pair wet stitch
Mon (13/07) | 13 Jul 2026 | P30 | 2nd lift | No activity
Mon (13/07) | 13 Jul 2026 | P37 |  | Top bar ongoing
Mon (13/07) | 13 Jul 2026 | P33 |  | Curing
Mon (13/07) | 13 Jul 2026 | P35 |  | Pending falsework removal to shift to P29
Mon (13/07) | 13 Jul 2026 | P40 MJ |  | 1 nos launched last night, pending 1 more before they can proceed with segment adjustment works
Mon (13/07) | 13 Jul 2026 | P3 |  | LF shifting, tonight to dismantle LF3 and install at P13 NB downchainage
Mon (13/07) | 13 Jul 2026 | CCW1 South |  | No activity
Mon (13/07) | 13 Jul 2026 | U3-38 |  | Filling in progress for earth mat drilling holes. Currently no other activity
Mon (13/07) | 13 Jul 2026 | CCW1 North |  | Currently no activity
Mon (13/07) | 13 Jul 2026 | B1 level | along B1-02, B1-04 | Internal wall formwork installation in progress
Mon (13/07) | 13 Jul 2026 | B1 level | along B1-04, B1-06, B1-08 | Internal wall cast last Saturday
Mon (13/07) | 13 Jul 2026 | U3-30 |  | Lean con cast last weekend. Currently no activity, U3-28: Side formwork installation in progress
Mon (13/07) | 13 Jul 2026 | Exit 2 | B2-16 area | No activity. All formwork for skinwall and RC wall dismantled
Mon (13/07) | 13 Jul 2026 | P30 | 2nd lift | No activity
Mon (13/07) | 13 Jul 2026 | P33 |  | Curing
Mon (13/07) | 13 Jul 2026 | P35 |  | No activity
Mon (13/07) | 13 Jul 2026 | P37 |  | Top rebar work ongoing
Mon (13/07) | 13 Jul 2026 | P40 MJ |  | Status quo
Mon (13/07) | 13 Jul 2026 | P47 |  | Pending fwk striking & removal, till 10pm
Mon (13/07) | 13 Jul 2026 | P48 |  | Secondary beam / barricade & working platform erection status, to continue night shift
Mon (13/07) | 13 Jul 2026 | P46 |  | Excavation ongoing, till 10pm
Mon (13/07) | 13 Jul 2026 | B2 level |  | Currently no activity
Mon (13/07) | 13 Jul 2026 | Column C02-2a | South side | 1st lift formwork dismantling ongoing
Mon (13/07) | 13 Jul 2026 | Column C01-7 | South side | Currently no activity
Mon (13/07) | 13 Jul 2026 | U3 | North side, GL27-28 | Hacking and disposal ongoing
Mon (13/07) | 13 Jul 2026 | U3-09 |  | 1 piezo was installed just now. Currently no activity
Mon (13/07) | 13 Jul 2026 | U3-18 |  | Bottom bar installation in progress, U3-20: Top bar installation and side formwork in progress
Mon (13/07) | 13 Jul 2026 | P11 NB |  | 1st pair wet stitch fwk closure ongoing
Mon (13/07) | 13 Jul 2026 | U3-32 |  | Lean con casting at KP area
Mon (13/07) | 13 Jul 2026 | U3-26, U3-28 |  | Wall starter bar installation and shearlinks ongoing
Mon (13/07) | 13 Jul 2026 | Column C01-3 | South side | Currently no activity
Mon (13/07) | 13 Jul 2026 | U3-05 |  | CJ hacking at U3-06 side
Mon (13/07) | 13 Jul 2026 | P1 | near to AWWA | Removal of lean concrete previously used for falsework
Tue (14/07) | 14 Jul 2026 | P18 |  | Falsework dismantling
Tue (14/07) | 14 Jul 2026 | P13 |  | 3/4 nos. LF installed. Tonight to finish shifting last LF from P3 to P13
Tue (14/07) | 14 Jul 2026 | Bet P11 NR-P10 NR |  | Segment painting works ongoing
Tue (14/07) | 14 Jul 2026 | P11 NB |  | 1st pair stitching Formwork and rebar installation. Target to cast this sat
Tue (14/07) | 14 Jul 2026 | Zone 1 |  | Tendon strand preparation works
Wed (15/07) | 15 Jul 2026 | 800mm PW |  | Water sampling with PUB
Wed (15/07) | 15 Jul 2026 | P18 |  | Falsework dismantling in progress
Wed (15/07) | 15 Jul 2026 | P13 |  | Stressing cage dismantling
Wed (15/07) | 15 Jul 2026 | P13 |  | 4/4 LF shifted from P3 and installed
Wed (15/07) | 15 Jul 2026 | P11 NB |  | 1st pair segment stitching rebar and Formwork installation
Wed (15/07) | 15 Jul 2026 | P51 |  | Current stump rebar status..no activity
Wed (15/07) | 15 Jul 2026 | P48 |  | Falsework assembly
Wed (15/07) | 15 Jul 2026 | P47 |  | Excavation to L5 caisson level
Wed (15/07) | 15 Jul 2026 | P46 |  | Excavation to L4 caisson layer
Wed (15/07) | 15 Jul 2026 | P30 |  | No activity
Wed (15/07) | 15 Jul 2026 | P33 |  | No activity. Curing
Wed (15/07) | 15 Jul 2026 | P35 |  | Crosshead bottom formwork dismantling
Wed (15/07) | 15 Jul 2026 | P37 |  | Crosshead rebar installation ongoing
Wed (15/07) | 15 Jul 2026 | P40 |  | Segment adjustment ongoing
Wed (15/07) | 15 Jul 2026 | P41 |  | Strand pulling in progress
Wed (15/07) | 15 Jul 2026 | P40 |  | Concrete block casting
Wed (15/07) | 15 Jul 2026 | P46 |  | No activity
Wed (15/07) | 15 Jul 2026 | P47 |  | Excavation to L5 caisson layer..soil disposal ongoing
Wed (15/07) | 15 Jul 2026 | P48 |  | Material delivery and formwork assembly
Wed (15/07) | 15 Jul 2026 | DR4 |  | Preparation for next JGP point
Wed (15/07) | 15 Jul 2026 | P13 |  | LF installation ongoing
Wed (15/07) | 15 Jul 2026 | P11 NB |  | Stitching formwork installation
Thu (16/07) | 16 Jul 2026 | 800mm PW |  | Water sampling with PUB
Thu (16/07) | 16 Jul 2026 | P30 |  | No activity
Thu (16/07) | 16 Jul 2026 | P33 |  | Preparation for formwork dismantling
Thu (16/07) | 16 Jul 2026 | P35 |  | Bottom formwork dismantling
Thu (16/07) | 16 Jul 2026 | P37 |  | Crosshead rebar installation
Thu (16/07) | 16 Jul 2026 | P40 |  | Segment adjustment ongoing
Thu (16/07) | 16 Jul 2026 | P46 |  | Excavation to L4 caisson in progress
Thu (16/07) | 16 Jul 2026 | P47 |  | No activity
Thu (16/07) | 16 Jul 2026 | P48 |  | Working platform and barricade installation
Thu (16/07) | 16 Jul 2026 | DR4 |  | JGP works ongoing
Fri (17/07) | 17 Jul 2026 | U3-05 |  | Started rebar installation work
Fri (17/07) | 17 Jul 2026 | U3 | GL29-27 | Continue hacking work by 1 breaker
Fri (17/07) | 17 Jul 2026 | U3-18 & U3-20 |  | Cleaning in progress, target to cast tomorrow
Fri (17/07) | 17 Jul 2026 | P33 |  | No activity
Fri (17/07) | 17 Jul 2026 | P35 |  | Falsework dismantling ongoing
Fri (17/07) | 17 Jul 2026 | P37 |  | Crosshead rebar installation work
Fri (17/07) | 17 Jul 2026 | P40 |  | Segment adjustment ongoing
Fri (17/07) | 17 Jul 2026 | P46 |  | Excavation to L4 caisson level
Fri (17/07) | 17 Jul 2026 | P47 |  | Bored pile hacking ongoing
Fri (17/07) | 17 Jul 2026 | P48 |  | Crosshead formwork assembly work
Fri (17/07) | 17 Jul 2026 | DR4 |  | JGP works ongoing
Mon (20/07) | 20 Jul 2026 | P18 |  | Falsework dismantling
Mon (20/07) | 20 Jul 2026 | P16-17 |  | Segment painting works
Mon (20/07) | 20 Jul 2026 | P13 |  | Crane parking location preparation for PLT
Mon (20/07) | 20 Jul 2026 | P11 NB |  | Wet stitch formwork dismantling
Mon (20/07) | 20 Jul 2026 | P10 SB |  | Segment alignment completed. Wet stitch formwork closing start tmr
Mon (20/07) | 20 Jul 2026 | P4 |  | Hacking for stump construction
Mon (20/07) | 20 Jul 2026 | CCW1 South |  | Currently no activity
Mon (20/07) | 20 Jul 2026 | U3-38, U3-37 |  | Tonight plan for lean con casting
Mon (20/07) | 20 Jul 2026 | CCW1 North | Tunnel eye | Current status
Mon (20/07) | 20 Jul 2026 | P29-P30 |  | Current falsework material delivery status
Mon (20/07) | 20 Jul 2026 | P29 |  | No activity. Not yet start falsework installation
Mon (20/07) | 20 Jul 2026 | P30 |  | No activity
Mon (20/07) | 20 Jul 2026 | P33 |  | Formwork dismantling ongoing
Mon (20/07) | 20 Jul 2026 | P37 |  | PT duct installation ongoing
Mon (20/07) | 20 Jul 2026 | P40 |  | Segment adjustment and removal of working platform
Mon (20/07) | 20 Jul 2026 | P46 |  | Bored pile hacking ongoing
Mon (20/07) | 20 Jul 2026 | P47 |  | No activity
Mon (20/07) | 20 Jul 2026 | P48 |  | Crosshead base and side formwork installation
Mon (20/07) | 20 Jul 2026 | DR4 |  | Balance 1 last point, going to complete all available JGP point at south side by tonight
Mon (20/07) | 20 Jul 2026 | B1 level | along B1-02, B1-04 | Internal wall formwork installation in progress
Mon (20/07) | 20 Jul 2026 | B1 level |  | Currently no other activity
Mon (20/07) | 20 Jul 2026 | B2 level | South side, GL-W8 to GL4 | Skinwall rebar works ongoing
Mon (20/07) | 20 Jul 2026 | B2 level | North side, GL9-5 | Skinwall formwork dismantled
Mon (20/07) | 20 Jul 2026 | Exit 2 B2-16 area |  | Currently no activity
Mon (20/07) | 20 Jul 2026 | B2 | South side, GL17-19 | Skinwall formwork installation in progress
Mon (20/07) | 20 Jul 2026 | B2 | North side, GL28 | 2nd lift internal wall CJ hacking ongoing
Mon (20/07) | 20 Jul 2026 | B2 | North side, GL30-32 | 2nd lift internal wall formwork installation in progress
Mon (20/07) | 20 Jul 2026 | P15-P16 |  | Material shifting and housekeeping
Mon (20/07) | 20 Jul 2026 | P13 |  | Preparation for segment D/U04 launching tonight
Mon (20/07) | 20 Jul 2026 | P11 |  | Strand pulling and preparation for stressing at NB
Mon (20/07) | 20 Jul 2026 | P10 |  | No activity
Mon (20/07) | 20 Jul 2026 | P4 |  | Bearing stump construction works ongoing
Mon (20/07) | 20 Jul 2026 | U3-26, U3-28 |  | Rebar completed, U3-30: Rebar works in progress
Mon (20/07) | 20 Jul 2026 | U3-05 |  | Bar chair installation in progress. Awaiting for night shift to takeover
Mon (20/07) | 20 Jul 2026 | U3-07 |  | Currently only waterproofing membrane cleaning. No other activity
Mon (20/07) | 20 Jul 2026 | Column C02-2a | South side | 2nd lift formwork installation in progress
Mon (20/07) | 20 Jul 2026 | Column C01-7 | South side | Currently no activity yet for 2nd lift
Mon (20/07) | 20 Jul 2026 | Column C01-6 | South side | Currently no activity yet
Mon (20/07) | 20 Jul 2026 | U3 | North side, GL23 | Hacking works ongoing
Mon (20/07) | 20 Jul 2026 | U3-09 |  | Currently no activity yet
Tue (21/07) | 21 Jul 2026 | P4 |  | No activity observed
Tue (21/07) | 21 Jul 2026 | P29 |  | No activity observed
Tue (21/07) | 21 Jul 2026 | P30 | 2nd lift | No activity observed
Tue (21/07) | 21 Jul 2026 | P33 |  | Fwk removal status, pending to shift to P34
Tue (21/07) | 21 Jul 2026 | P34 |  | No activity observed
Tue (21/07) | 21 Jul 2026 | P37 |  | Duct installation ongoing
Tue (21/07) | 21 Jul 2026 | P40 MJ |  | Segment adjustment ongoing
Tue (21/07) | 21 Jul 2026 | P10 SB |  | Strand pushing
Tue (21/07) | 21 Jul 2026 | P11 NB |  | Wet stitch formwork dismantling
Tue (21/07) | 21 Jul 2026 | P12-13 midspan |  | Preparation for clamping beam installation
Tue (21/07) | 21 Jul 2026 | U3-38, U3-37 |  | Lean con completed last night, U3-37: Hacking ongoing at drainage pit area
Tue (21/07) | 21 Jul 2026 | CCW1 South |  | Tunnel roof falsework dismantling ongoing
Tue (21/07) | 21 Jul 2026 | P15-16 |  | Segment painting, 2nd coat
Tue (21/07) | 21 Jul 2026 | B1 level | B1-02 area | Internal wall formwork installation in progress
Tue (21/07) | 21 Jul 2026 | B1 level |  | Currently no other activity yet
Tue (21/07) | 21 Jul 2026 | Exit 3 Bomb Pit |  | WH to continue skinwall hacking. Currently on tea break
Tue (21/07) | 21 Jul 2026 | Exit 3 RC wall area |  | Waterproofing primer coat ongoing
Tue (21/07) | 21 Jul 2026 | B2 | South side, GL5-6 | Skinwall rebar works ongoing
Tue (21/07) | 21 Jul 2026 | U3-30 |  | Top bar and side formwork installation in progress
Tue (21/07) | 21 Jul 2026 | U3-31 |  | Trenching ongoing for subsoil drain works
Tue (21/07) | 21 Jul 2026 | B2 | South side, GL16-18 | Working platform dismantling ongoing to facilitate shifting of the moveable skinwall formwork installation
Tue (21/07) | 21 Jul 2026 | B2 | North side, GL22-24 | 2nd lift internal wall CJ hacking & soffit roughening ongoing
Tue (21/07) | 21 Jul 2026 | B2 | North side, GL27-29 | 2nd lift internal wall formwork installation in progress
Tue (21/07) | 21 Jul 2026 | U3-05 |  | Rebar installation in progres
Tue (21/07) | 21 Jul 2026 | U3-07 |  | Waterproofing status
Tue (21/07) | 21 Jul 2026 | U3-09 |  | Leaned con. & starting hacking of CJ
Tue (21/07) | 21 Jul 2026 | U3 | GL27 | Permeability test ongoing
Tue (21/07) | 21 Jul 2026 | U3-18, U3-20 |  | Currently no activity
Tue (21/07) | 21 Jul 2026 | Column C01-7 | South side | 2nd lift currently no activity
Tue (21/07) | 21 Jul 2026 | P33 |  | Crosshead formwork dismantling
Tue (21/07) | 21 Jul 2026 | P37 |  | PT duct installation ongoing
Tue (21/07) | 21 Jul 2026 | P40 |  | Segment adjustment ongoing
Tue (21/07) | 21 Jul 2026 | P46 |  | No activity
Tue (21/07) | 21 Jul 2026 | P47 |  | Slurry disposal
Tue (21/07) | 21 Jul 2026 | P48 |  | Crosshead side formwork installation
Tue (21/07) | 21 Jul 2026 | DR4 |  | No activity
Tue (21/07) | 21 Jul 2026 | P4 |  | Bearing stump construction ongoing
Tue (21/07) | 21 Jul 2026 | P11 |  | Preparation to shift the starter hanger to P10
Tue (21/07) | 21 Jul 2026 | P10 |  | Preparation work for starter hanger installation tonight
Tue (21/07) | 21 Jul 2026 | P13 |  | Preparation work for LF shifting
Tue (21/07) | 21 Jul 2026 | P18 |  | Scaffolding dismantling
Tue (21/07) | 21 Jul 2026 | P13-P14 |  | Strand pulling works ongoing
Wed (22/07) | 22 Jul 2026 | P13 |  | 3/4 clamping beam installed. Balance 1 nos to install today. LF to start dismantling and shifting tonight
Wed (22/07) | 22 Jul 2026 | P10 NB |  | SH installed last night. Tomorrow night to launch NB D01
Wed (22/07) | 22 Jul 2026 | P40 |  | Adjustment done, waiting for confirmation from YWL
Wed (22/07) | 22 Jul 2026 | P40 |  | Ground level assembly for LG FAS items
Wed (22/07) | 22 Jul 2026 | DR4 |  | JGP completed, area housekeeping to handover to LE
Wed (22/07) | 22 Jul 2026 | P48 |  | Working platform balance work ongoing
Wed (22/07) | 22 Jul 2026 | P46 | 4th layer caisson | Excavation ongoing
Wed (22/07) | 22 Jul 2026 | P47 | 5th caisson | Excavator breakdown, mechanic otw
Wed (22/07) | 22 Jul 2026 | Zone 1 |  | Stressing cage dismantling, to shift to zone 2
Wed (22/07) | 22 Jul 2026 | CCW2 |  | U3-39 bottom bar works in progress (18 men). Tonight CGW plan to start night shift here (14 men), S1-1: U3-37 & U3-38 currently no activity
Wed (22/07) | 22 Jul 2026 | CCW1 North |  | Tunnel eye status. Currently no activity here
Wed (22/07) | 22 Jul 2026 | CCW1 South |  | Tunnel roof falsework dismantling
Wed (22/07) | 22 Jul 2026 | P29 |  | No activity
Wed (22/07) | 22 Jul 2026 | P30 |  | No activity
Wed (22/07) | 22 Jul 2026 | P33 |  | Preparing for post tensioning works
Wed (22/07) | 22 Jul 2026 | P37 |  | PT duct and shear links installation
Wed (22/07) | 22 Jul 2026 | Exit 3 RC wall |  | Preparation ongoing for last layer of LSS backfilling. Plan for backfilling tonight, Soffit waterproofing done
Wed (22/07) | 22 Jul 2026 | Exit 3 Bomb Pit |  | Skinwall hacking currently no activity. Plan for lean con casting Friday
Wed (22/07) | 22 Jul 2026 | B2 level | B2-02 area | Scaffold erection ongoing for skinwall works
Wed (22/07) | 22 Jul 2026 | P40 |  | Preparation for strand pulling works
Wed (22/07) | 22 Jul 2026 | P46 |  | No activity
Wed (22/07) | 22 Jul 2026 | P47 |  | Bored pile at north side finish hacking, now levelling. Tomorrow going to lean con for working platform
Wed (22/07) | 22 Jul 2026 | P48 |  | Crosshead side formwork installation
Wed (22/07) | 22 Jul 2026 | DR4 |  | No activity
Wed (22/07) | 22 Jul 2026 | U3-30 |  | Top bar & shearlinks installation in progress
Wed (22/07) | 22 Jul 2026 | U3-05 |  | Top bar installation in progress
Wed (22/07) | 22 Jul 2026 | U3-07 |  | Currently no activity
Wed (22/07) | 22 Jul 2026 | U3-09 |  | Currently no activity
Wed (22/07) | 22 Jul 2026 | Column C02-2a | South side | 2nd lift casting in progress
Wed (22/07) | 22 Jul 2026 | Column C01-7 | South side | 2nd lift currently no activity
Wed (22/07) | 22 Jul 2026 | U3 | North side, GL27 | Coring for permeability test (BH-P11) completed today. Tmr to do testing, KTC & WH continue excavation and hacking works
Wed (22/07) | 22 Jul 2026 | Column C01-6 | South side | Rebar works in progress
Wed (22/07) | 22 Jul 2026 | U3-18, U3-20 |  | Currently no activity. Plan for casting Friday
Wed (22/07) | 22 Jul 2026 | U3-31, U3-32 |  | Levelling ongoing. Plan for lean con casting tonight
Wed (22/07) | 22 Jul 2026 | P13 |  | Preparation for bringing down LF to ground tonight
Wed (22/07) | 22 Jul 2026 | P10 |  | No activity
Wed (22/07) | 22 Jul 2026 | U3-33 |  | Excavation in progress
Wed (22/07) | 22 Jul 2026 | U3-34 |  | Earth mat works was done earlier today. Currently no activity
Wed (22/07) | 22 Jul 2026 | U3 | North side, GL23-11 | Currently no activity
Wed (22/07) | 22 Jul 2026 | P4 |  | Bearing stumo formwork closing
Wed (22/07) | 22 Jul 2026 | P29 |  | Crane operator SIC, after lunch will commence falsework erection
Wed (22/07) | 22 Jul 2026 | P35 |  | Preparing for post tensioning works
Wed (22/07) | 22 Jul 2026 | P37 |  | Duct installation ongoing
Thu (23/07) | 23 Jul 2026 | P13 |  | All clamping beam installed. 1 LF dismantled last night
Thu (23/07) | 23 Jul 2026 | P4 |  | Bearing stump preparation. Target to cast this week
Thu (23/07) | 23 Jul 2026 | P48 |  | No activity observed
Thu (23/07) | 23 Jul 2026 | P47 |  | Continue excavation to 4th caisson
Thu (23/07) | 23 Jul 2026 | P46 |  | Continue excavation to 5th caisson
Thu (23/07) | 23 Jul 2026 | Exit 1 |  | Current stockpile & internal transfer via gate 5 for seiging by 1 excavator
Thu (23/07) | 23 Jul 2026 | U3-05 |  | Shearlink installation & cleaning in progress
Thu (23/07) | 23 Jul 2026 | U3-07 |  | Waterproofing work in progress
Thu (23/07) | 23 Jul 2026 | DR4 |  | Preparation for trial trench work for soldier pile
Thu (23/07) | 23 Jul 2026 | P29 |  | Current falsework installation status
Thu (23/07) | 23 Jul 2026 | P34 |  | Preparation for post tensioning work
Thu (23/07) | 23 Jul 2026 | P37 |  | Shear links installation
Thu (23/07) | 23 Jul 2026 | P40 |  | Preparation for concrete packing works
Thu (23/07) | 23 Jul 2026 | P46 |  | Currently no activity, workers focus on P47
Thu (23/07) | 23 Jul 2026 | P47 |  | Ground levelling, tonight going to lean con casting working platform
Thu (23/07) | 23 Jul 2026 | P48 |  | Scaffolding installation and side formwork assembly ongoing
Thu (23/07) | 23 Jul 2026 | P4 |  | Stump formwork closing, 5/8 closing completed
Thu (23/07) | 23 Jul 2026 | P13 |  | USS nightshift team on site. Tonight to continue LF Dismantling
Thu (23/07) | 23 Jul 2026 | P18 |  | Falsework dismantling status
Thu (23/07) | 23 Jul 2026 | P37 |  | Links installation continue
Thu (23/07) | 23 Jul 2026 | P40 |  | Locking of segment for installation of concrete packing
Thu (23/07) | 23 Jul 2026 | P47 |  | Working platform casting in progress
Thu (23/07) | 23 Jul 2026 | P48 |  | Scaffold support for rebar installation no more activity. No nightshift activity here tonight
Thu (23/07) | 23 Jul 2026 | P13 SB UC |  | Preparation for PF dismantling
Thu (23/07) | 23 Jul 2026 | P18 NB upchainage |  | Falsework dismantling
Thu (23/07) | 23 Jul 2026 | P16-17 NB |  | Segment painting, 1st coat
Thu (23/07) | 23 Jul 2026 | P29 |  | Falsework erection started
Thu (23/07) | 23 Jul 2026 | P30 | 2nd lift | No activity
Thu (23/07) | 23 Jul 2026 | P35 |  | Preparing for post tensioning work
Thu (23/07) | 23 Jul 2026 | P37 |  | Shear link installation ongoing
Fri (24/07) | 24 Jul 2026 | P37 |  | Current status
Fri (24/07) | 24 Jul 2026 | P35 |  | Stressing work ongoing
Fri (24/07) | 24 Jul 2026 | P29 |  | Falsework erection status, P30: no activity
Fri (24/07) | 24 Jul 2026 | Exit 1 |  | Current stockpile & continues internal transfer by 1 excavator
Fri (24/07) | 24 Jul 2026 | U3-5 |  | Current rebar status
Fri (24/07) | 24 Jul 2026 | U3-07 |  | Lowering rebar for installation, U3-09:, Started waterproofing works
Fri (24/07) | 24 Jul 2026 | C01-7 |  | Installing formwork for 2nd lift
Fri (24/07) | 24 Jul 2026 | C01-6 |  | Preparing to install formwork for 1st lift
Fri (24/07) | 24 Jul 2026 | U3 | GL25-24 | Hacking by 1 breaker is in progress
Fri (24/07) | 24 Jul 2026 | U3-18 & U3-20 |  | Cleaning & inspection in progress, target to cast today
Fri (24/07) | 24 Jul 2026 | P48 |  | Preparation for crosshead rebar works
Fri (24/07) | 24 Jul 2026 | P47 |  | Working platform lean con casting complete..preparing for L5 caisson rebar works
Fri (24/07) | 24 Jul 2026 | P18 |  | Today to complete falsework dismantling
Fri (24/07) | 24 Jul 2026 | P17-18 |  | Segment painting started
Fri (24/07) | 24 Jul 2026 | P13 |  | Midspan wet stitch formwork closing in progress
Fri (24/07) | 24 Jul 2026 | P11 SB |  | LF1 and 2 installed last night
Sat (25/07) | 25 Jul 2026 | Exit 3 bomb pit |  | Skinwall hacking ongoing
Sat (25/07) | 25 Jul 2026 | Exit 3 RC wall area |  | Currently no activity. LSS backfill was done on Wed
Sat (25/07) | 25 Jul 2026 | P29 |  | Crosshead working platform installation in progress
Sat (25/07) | 25 Jul 2026 | B2 level | B2-02 area | Currently no activity for skinwall
Sat (25/07) | 25 Jul 2026 | B2 | South side, GL3-4 | Skinwall works ongoing
Sat (25/07) | 25 Jul 2026 | U3-34 |  | Drilling ongoing for earth mat works
Sat (25/07) | 25 Jul 2026 | B2 | South side, GL10-9 | RGT installation in progress
Sat (25/07) | 25 Jul 2026 | B2 | South side, GL20 | Drilling ongoing for PU grouting
Sat (25/07) | 25 Jul 2026 | B2 | North side, GL26-25 | Internal wall rebar works in progress
Sat (25/07) | 25 Jul 2026 | B2 | South side, GL27 | Skinwall formwork installation ongoing
Sat (25/07) | 25 Jul 2026 | B2 | South side, GL30 | Internal wall rebar works ongoing
Sat (25/07) | 25 Jul 2026 | P33 |  | Preparation for stressing works
Sat (25/07) | 25 Jul 2026 | P37 |  | Shear links installation at SB side
Sat (25/07) | 25 Jul 2026 | P40 |  | FBCM concrete blocks preparation and concrete packing grouting works ongoing
Sat (25/07) | 25 Jul 2026 | U3-05 |  | Welding works ongoing
Sat (25/07) | 25 Jul 2026 | U3-07 |  | Rebar works in progress
Sat (25/07) | 25 Jul 2026 | U3 | North side, GL27 | Continue soil disposal works
Sat (25/07) | 25 Jul 2026 | P46 |  | 4th layer excavation and hacking in progress at NB side
Sat (25/07) | 25 Jul 2026 | P47 |  | Access shifting and hacking works ongoing for 5th layer
Sat (25/07) | 25 Jul 2026 | Column C01-6 | South side | 1st lift column installation ongoing
Sat (25/07) | 25 Jul 2026 | U3 | North side, GL24 | Hacking and survey levelling ongoing
Sat (25/07) | 25 Jul 2026 | U3-18, U3-20 |  | 24 Jul: Casting started at 730pm, 25 Jul: Casting completed at 1030am, Total vol: 1923m3
Sat (25/07) | 25 Jul 2026 | U3 | North side, GL21 | Rock splitting ongoing (1 machine)
Sat (25/07) | 25 Jul 2026 | U3 | North side, GL13 | Coupler exposing
Sat (25/07) | 25 Jul 2026 | U3-32 |  | Formwork removal at drop area, Drilling ongoing for permeability test (BH-P6)
Sat (25/07) | 25 Jul 2026 | U3 | GL6-4 | Continue BP hacking, Earth mat works at South side, Excavation ongoing at North side
Sat (25/07) | 25 Jul 2026 | Column C01-2 | South side | Rebar planting in progress
Sat (25/07) | 25 Jul 2026 | U3-26, U3-28, U3-30 |  | Cleaning ongoing and preparing to join casting pipes. Plan for final inspection & casting today
Sat (25/07) | 25 Jul 2026 | P48 |  | Currently no activity
Sat (25/07) | 25 Jul 2026 | DR4 |  | LE trial trench works for solider piles installation
Sat (25/07) | 25 Jul 2026 | P4 |  | Bearing stump preparation works
Sat (25/07) | 25 Jul 2026 | P11 |  | 4/4 LF shifted and installed
Sat (25/07) | 25 Jul 2026 | Bet P12-P13 |  | Mid span stitching Formwork installation
Sat (25/07) | 25 Jul 2026 | Bet. P17 & P18 |  | Segment painting works
Sat (25/07) | 25 Jul 2026 | Receiving shaft & CCE4 |  | Excavation in progress
Sat (25/07) | 25 Jul 2026 | U3-07 |  | Bottom rebar works and PU grouting at skinwall area ongoing
Sat (25/07) | 25 Jul 2026 | U3 between | North side, GL27-28 | Hacking ongoing at skinwall area
Sat (25/07) | 25 Jul 2026 | U3 | North side, GL24-25 | Excavation ongoing
Sat (25/07) | 25 Jul 2026 | U3-18, U3-20 |  | Casting completed this morning. Power float works ongoing
Sat (25/07) | 25 Jul 2026 | U3 | GL6-4 | Continue excavation and disposal (North side), U3-34: Trenching ongoing for subsoil drain & continue earth mat drilling and cable laying works, Hacking ongoing
Sat (25/07) | 25 Jul 2026 | U3-26, U3-28, U3-30 |  | Joining of casting pipes and waiting to cast
Sat (25/07) | 25 Jul 2026 | Column C01-2 | South side | Rebar works ongoing
Sat (25/07) | 25 Jul 2026 | Column C01-3 | South side | Bottom CJ roughening
Sat (25/07) | 25 Jul 2026 | B2 | North side, GL8 | Preparing formwork for skinwall rectification
Sat (25/07) | 25 Jul 2026 | Exit 3 bomb pit |  | Currently no activity
Sat (25/07) | 25 Jul 2026 | Exit 3 RC wall area |  | No activity
Sat (25/07) | 25 Jul 2026 | P29 |  | Netting installation in progress
Sat (25/07) | 25 Jul 2026 | P33 |  | Preparation for stressing works
Sat (25/07) | 25 Jul 2026 | P37 |  | Crosshead Formwork closing
Sat (25/07) | 25 Jul 2026 | U3-38 |  | Rig for permeability test drilling has shifted here for BH-P2
Sat (25/07) | 25 Jul 2026 | CCW2 |  | U3-39 top bar and side formwork installation. Plan for casting next week
Sat (25/07) | 25 Jul 2026 | P40 FBCM |  | Continue preparation works for concrete blocks installation
Sat (25/07) | 25 Jul 2026 | P46 |  | Continue excavation works for 4th layer
Sat (25/07) | 25 Jul 2026 | P47 |  | Access making in progress for NB side
Sat (25/07) | 25 Jul 2026 | P48 |  | Base jack plates installation works. Next week to start rebar works
Sat (25/07) | 25 Jul 2026 | DR4 |  | LE trial trench works ongoing
Sat (25/07) | 25 Jul 2026 | P4 |  | Bearing stump works ongoing
Sat (25/07) | 25 Jul 2026 | P11 |  | Stressing materials shifting ongoing
Sat (25/07) | 25 Jul 2026 | P12-P13-P14 |  | Mid span stitching Formwork closing for SB side
Sat (25/07) | 25 Jul 2026 | CCW1 South |  | Tunnel roof falsework dismantled. Currently no activity
Sat (25/07) | 25 Jul 2026 | CCW2 |  | U3-39 top bar installation & RGT installation at CJ area. Plan for casting next week
Sat (25/07) | 25 Jul 2026 | U3-37 |  | Currently no activity
Sat (25/07) | 25 Jul 2026 | U3-38 |  | PU grouting ongoing
Sat (25/07) | 25 Jul 2026 | CCW1 North |  | Current status for tunnel eye. No activity observed
Sat (25/07) | 25 Jul 2026 | B1 level | Along B1-02 | Scaffold erection ongoing for i-beam removal
Sat (25/07) | 25 Jul 2026 | B1 level |  | Currently no other activity
Sun (26/07) | 26 Jul 2026 | DR4 |  | LE doing TT along soldier pile alignment. 19 to 20m length
Sun (26/07) | 26 Jul 2026 | P48 |  | Support installation done for crosshead. Tomorrow can start rebar work
Sun (26/07) | 26 Jul 2026 | P47 |  | New access erected and old access removal
Sun (26/07) | 26 Jul 2026 | P47 |  | Hacking of concrete around UKP for caisson work
Sun (26/07) | 26 Jul 2026 | P46 |  | Today no activity
Sun (26/07) | 26 Jul 2026 | P44 |  | Preparation for grouting work
Sun (26/07) | 26 Jul 2026 | P40 |  | Support installation for grouting of temporary jack
Sun (26/07) | 26 Jul 2026 | P47 |  | Shear link installation. To cast next week
Sun (26/07) | 26 Jul 2026 | P33 |  | Polyfoam removal. To continue tendon wire pulling and preparation for stressing work tomorrow
Sun (26/07) | 26 Jul 2026 | P29 |  | Current status. Today less Wendyng manpower for crosshead work
Sun (26/07) | 26 Jul 2026 | P12-P13 |  | Tendon wire cutting and installation
Sun (26/07) | 26 Jul 2026 | P11 |  | Two numbers of stressing cage shifted. Tonight to install
Sun (26/07) | 26 Jul 2026 | P4 |  | Preparation for stump in progress
Sun (26/07) | 26 Jul 2026 | DR4 |  | GCE preparing for UKP work
Sun (26/07) | 26 Jul 2026 | DR4 |  | 6/20m length TT done by LE
Sun (26/07) | 26 Jul 2026 | P48 |  | No activity
Sun (26/07) | 26 Jul 2026 | P47 |  | Access dismantling done. Continue hacking of cement grout
Sun (26/07) | 26 Jul 2026 | P40 |  | Ultracon already end work
Sun (26/07) | 26 Jul 2026 | P37 |  | Shear link to complete today. Tomorrow balance formwork closing
Sun (26/07) | 26 Jul 2026 | P29 |  | Tomorrow to continue platform after access erection done
Sun (26/07) | 26 Jul 2026 | P12-14 |  | Lowering down materials
Sun (26/07) | 26 Jul 2026 | P10 |  | Preparation for stitching work
Sun (26/07) | 26 Jul 2026 | Zone 1 |  | Preparing to shift stressing cages to P11 area. Today target two numbers
Mon (27/07) | 27 Jul 2026 | P17-18 |  | Segment painting
Mon (27/07) | 27 Jul 2026 | P13 midspan |  | SB closed. NB closing now. Target to cast on Thursday night
Mon (27/07) | 27 Jul 2026 | P11 |  | SB 2nd pair to launch tonight
Mon (27/07) | 27 Jul 2026 | P10 SB |  | 1st pair wet stitch formwork closing. To cast also on Thursday, NB U01: to launch tonight
Mon (27/07) | 27 Jul 2026 | P29 |  | Erection of working platform in progress after access has been erected
Mon (27/07) | 27 Jul 2026 | P30 |  | No activity
Mon (27/07) | 27 Jul 2026 | P33 |  | No activity
Mon (27/07) | 27 Jul 2026 | P37 |  | Shear link installation still ongoing, closing of balanced formwork will begin later in the day
Mon (27/07) | 27 Jul 2026 | P40 |  | No activity
Mon (27/07) | 27 Jul 2026 | Exit 1 stockpile |  | Continues internal transfer by 2 excavators
Mon (27/07) | 27 Jul 2026 | U3-07 |  | Rebar work in progress, target to cast together with U3-05 by this week
Mon (27/07) | 27 Jul 2026 | C2-02 |  | Dismantling of formwork for 2nd lift
Mon (27/07) | 27 Jul 2026 | C1-06 |  | Planning to cast 1st lift today
Mon (27/07) | 27 Jul 2026 | P29 |  | Access erected
Mon (27/07) | 27 Jul 2026 | CCW2 |  | U3-39 shearlinks installation in progress. Plan for final inspection & casting tmr
Mon (27/07) | 27 Jul 2026 | U3-35 |  | Excavation for ejector pit ongoing, U3-33: Soil disposal ongoing
Mon (27/07) | 27 Jul 2026 | U3-37 |  | Drilling ongoing for permeability test, BH-P1
Mon (27/07) | 27 Jul 2026 | U3-38 |  | Waterproofing works in progress
Mon (27/07) | 27 Jul 2026 | U3-36 |  | Rod installation for earth mat in progress
Mon (27/07) | 27 Jul 2026 | U3-32, U3-34 |  | Currently no activity
Mon (27/07) | 27 Jul 2026 | U3-29 |  | Exposing coupler
Mon (27/07) | 27 Jul 2026 | U3-25 |  | Formwork installation at drop area
Mon (27/07) | 27 Jul 2026 | P46 |  | 4th layer caisson wall excavation pending access shifting
Mon (27/07) | 27 Jul 2026 | P47 |  | 5th layer excavation to expose BP ongoing
Mon (27/07) | 27 Jul 2026 | P48 |  | No activity observed
Mon (27/07) | 27 Jul 2026 | U3-26, U3-28, U3-30 |  | Cast last weekend
Mon (27/07) | 27 Jul 2026 | Column C01-2 | South side | Rebar works in progress
Mon (27/07) | 27 Jul 2026 | Column C01-3 |  | Currently no activity
Mon (27/07) | 27 Jul 2026 | U3 | U3-17, GL20 | Rock coring and splitting ongoing
Mon (27/07) | 27 Jul 2026 | Column C01-6 | South side | Currently no activity
Mon (27/07) | 27 Jul 2026 | U3 | North side, GL27 | Excavation and disposal ongoing
Mon (27/07) | 27 Jul 2026 | Column C01-7 | South side | 2nd lift was cast. Now ongoing formwork dismantling
Mon (27/07) | 27 Jul 2026 | U3-09 |  | Surface cleaning ongoing
Mon (27/07) | 27 Jul 2026 | U3-07 |  | Rebar works in progress, U3-05: Side formwork installation ongoing
Mon (27/07) | 27 Jul 2026 | P10 |  | NB U01 to launch tonight, P11: SB 2nd pair to launch tonight
Mon (27/07) | 27 Jul 2026 | B2 | South side, GL32-30 | Internal wall rebar works ongoing
Mon (27/07) | 27 Jul 2026 | B2 | South side, GL10-8 | Skinwall formwork installation ongoing
Mon (27/07) | 27 Jul 2026 | Exit 3 |  | No activity
Mon (27/07) | 27 Jul 2026 | CCW1 North |  | Tunnel eye currently no activity
Mon (27/07) | 27 Jul 2026 | B1 level | B1-08 area | Formwork installation for wall rectification
Mon (27/07) | 27 Jul 2026 | B1 level |  | No other activity observed
Tue (28/07) | 28 Jul 2026 | CCW1 South |  | Tunnel eye currently no activity
Tue (28/07) | 28 Jul 2026 | CCW2 |  | U3-39 shearlinks installation in progress. Plan for final inspection this afternoon
Tue (28/07) | 28 Jul 2026 | U3-37 |  | Drilling ongoing for permeability test, BH-P1
Tue (28/07) | 28 Jul 2026 | U3-38 |  | Preparing platform for skinwall PU grouting works
Tue (28/07) | 28 Jul 2026 | U3-35 |  | Hacking ongoing
Tue (28/07) | 28 Jul 2026 | U3-36 |  | Earth mat works ongoing, Trenching ongoing for subsoil drain
Tue (28/07) | 28 Jul 2026 | U3-33 |  | Disposal works ongoing
Tue (28/07) | 28 Jul 2026 | U3-30 |  | CJ hacking in progress
Tue (28/07) | 28 Jul 2026 | P17-18 |  | Segment painting continue, 2nd coat
Tue (28/07) | 28 Jul 2026 | P29 |  | Working platform erected. No activity as of now
Tue (28/07) | 28 Jul 2026 | P30 |  | No activity
Tue (28/07) | 28 Jul 2026 | P33 |  | No activity
Tue (28/07) | 28 Jul 2026 | P37 |  | Balanced formwork closure in progress
Tue (28/07) | 28 Jul 2026 | P40 |  | No activity
Tue (28/07) | 28 Jul 2026 | U3-29 |  | Skinwall hacking ongoing, U3-25: Hacking ongoing at KP area
Tue (28/07) | 28 Jul 2026 | Column C01-2 | South side | Rebar works in progress
Tue (28/07) | 28 Jul 2026 | Column C01-3 | South side | Currently no activity
Tue (28/07) | 28 Jul 2026 | U3 | North side, GL18-19 | Hacking works
Tue (28/07) | 28 Jul 2026 | U3 | North side, GL20 | Coring and splitting ongoing
Tue (28/07) | 28 Jul 2026 | Column C01-5 | South side | Scaffold installation in progress for column works
Tue (28/07) | 28 Jul 2026 | U3-09 |  | Waterproofing membrane laying & PU grouting ongoing
Tue (28/07) | 28 Jul 2026 | U3-07 |  | Rebar works in progress
Tue (28/07) | 28 Jul 2026 | DR4 |  | No activity
Tue (28/07) | 28 Jul 2026 | P48 |  | Crosshead rebar works start
Tue (28/07) | 28 Jul 2026 | P47 |  | Excavation to expose bored pile at south side, L5 caisson rebar works at North side
Tue (28/07) | 28 Jul 2026 | P46 |  | L4 caisson rebar preparation work at north side
Tue (28/07) | 28 Jul 2026 | P13 NB |  | Midspan wet stitch formwork closing, SB completed
Tue (28/07) | 28 Jul 2026 | P10 NB |  | 1st pair alignment in progress
Tue (28/07) | 28 Jul 2026 | B2 | North side, GL30 | 2nd lift internal wall formwork installation
Tue (28/07) | 28 Jul 2026 | B2 | South side, GL30-32 | Internal wall rebar works & scaffold erection for next section of skinwall (near VS)
Tue (28/07) | 28 Jul 2026 | B2 | South side, GL19 | RGT installation at skinwall
Tue (28/07) | 28 Jul 2026 | B2 | South side, GL10-8 | Skinwall formwork installation in progress
Tue (28/07) | 28 Jul 2026 | P4 |  | Template for bearing installation
Tue (28/07) | 28 Jul 2026 | Exit 3 bomb pit |  | Clearing hardcore prior to ground levelling works
Tue (28/07) | 28 Jul 2026 | Zone 3 P29 |  | No activity observed
Tue (28/07) | 28 Jul 2026 | Zone 3 P30 | 2nd lift | No activity observed
Tue (28/07) | 28 Jul 2026 | Zone 3 P33 |  | No activity observed
Tue (28/07) | 28 Jul 2026 | Zone 3 P37 |  | Status of fwk closure, to cast tmr
Tue (28/07) | 28 Jul 2026 | Zone 3 P40 |  | FBCM works ongoing
Tue (28/07) | 28 Jul 2026 | Zone 4 P48 |  | Bottom rebar work
Tue (28/07) | 28 Jul 2026 | Zone 4 P46 |  | No activity observed
Tue (28/07) | 28 Jul 2026 | Zone 4 P47 |  | 5th layer caisson fwk closure, handover to nightshift
Wed (29/07) | 29 Jul 2026 | Zone 2 P13 |  | NB midspan stitching formwork closing
Wed (29/07) | 29 Jul 2026 | Zone 2 P11 |  | Strands installation for NB D/U 02
Wed (29/07) | 29 Jul 2026 | Zone 2 P10 |  | 1st pair segment adjustment for NB side
Wed (29/07) | 29 Jul 2026 | Zone 1 P4 |  | Bearing stump target to cast tmr
Wed (29/07) | 29 Jul 2026 | Zone 1 |  | Hoarding sheet installation
Wed (29/07) | 29 Jul 2026 | P29 |  | Wing formwork installation
Wed (29/07) | 29 Jul 2026 | P33 |  | Currently no activity
Wed (29/07) | 29 Jul 2026 | P37 |  | Installation of cast in item and adjusting. Casting will be on Friday
Wed (29/07) | 29 Jul 2026 | P40 |  | Formwork support installation for precast to place between two segments
Wed (29/07) | 29 Jul 2026 | P45 |  | New access erection and hacking of grout for caisson work
Wed (29/07) | 29 Jul 2026 | P47 |  | Caisson casting at changi bound side
Wed (29/07) | 29 Jul 2026 | P48 |  | Crosshead rebar work. 5 workers + 1 sup
Wed (29/07) | 29 Jul 2026 | Zone 4 DR4 |  | Stage 1A traffic light cable pipe laying
Wed (29/07) | 29 Jul 2026 | Zone 4 DR4 |  | Trial Trench for instrumentation
Wed (29/07) | 29 Jul 2026 | Zone 4 DR4 |  | Trial Trench for soldier pile
Wed (29/07) | 29 Jul 2026 | Zone 4 DR4 |  | Trial Trench for UKP
Wed (29/07) | 29 Jul 2026 | Zone 4 P48 |  | Crosshead rebar installation
Wed (29/07) | 29 Jul 2026 | Zone 4 P47 |  | L5 caisson casting at north
Wed (29/07) | 29 Jul 2026 | Zone 4 P46 |  | L4 caisson rebar works at north
Wed (29/07) | 29 Jul 2026 | B2 | South side, GL30-32 | Internal wall rebar works and formwork installation in progress
Wed (29/07) | 29 Jul 2026 | B2 level towards VS |  | 2nd lift internal wall rebar works ongoing
Wed (29/07) | 29 Jul 2026 | U3-05 |  | Currently no activity, U3-07: Top bar installation and side formwork ongoing, Plan to cast both slabs this week
Wed (29/07) | 29 Jul 2026 | U3-09 |  | Currently no activity
Wed (29/07) | 29 Jul 2026 | U3 | South side, GL23-25 | Scaffold erection ongoing for skinwall works
Wed (29/07) | 29 Jul 2026 | U3 | GL26-27 | Adjusting steel plates along vehicle access
Wed (29/07) | 29 Jul 2026 | Column C01-5 | South side | Currently no activity
Wed (29/07) | 29 Jul 2026 | Column C01-3 | South side | Currently no activity
Wed (29/07) | 29 Jul 2026 | Column C01-2 | South side | Currently no activity
Wed (29/07) | 29 Jul 2026 | U3-21 |  | Subsoil drain works ongoing. CJ hacking at U3-22 area
Wed (29/07) | 29 Jul 2026 | U3-30 |  | CJ roughening ongoing
Wed (29/07) | 29 Jul 2026 | U3-33 opening |  | Soil & hardcore disposal ongoing
Wed (29/07) | 29 Jul 2026 | Between U3-37 & U3-38 |  | Currently no activity for permeability test drilling (BH-P3). Tmr to resume
Wed (29/07) | 29 Jul 2026 | U3-38 |  | Bottom rebar works ongoing. Tonight night shift to start works here (14 men), CCW2 U3-39: Casting was completed this morning
Wed (29/07) | 29 Jul 2026 | U3-36 |  | Earth mat cable laying in progress. Only this area left for earth mat works
Wed (29/07) | 29 Jul 2026 | B2 | South side, GL9-7 | Skinwall formwork installation in progress
Wed (29/07) | 29 Jul 2026 | B1 level | B1-04 area | Formwork fabrication for internal wall. Currently no other activity observed at B1
Thu (30/07) | 30 Jul 2026 | P29 |  | One side formwork closing done. Cleaning of formwork and jack tightening
Thu (30/07) | 30 Jul 2026 | P33 |  | Cleaning of duct target to complete tomorrow
Thu (30/07) | 30 Jul 2026 | P40 |  | Formwork support installation for precast block placing between two segment. Try to handover to Ultracon on 5th August
Thu (30/07) | 30 Jul 2026 | Zone 2 P11 |  | 3rd pair SB segment launched last night. Strands installation in progress
Thu (30/07) | 30 Jul 2026 | P39 |  | Stressing cage and starter hanger assembling for first pair launching
Thu (30/07) | 30 Jul 2026 | Zone 2 P10 |  | 1st pair NB segment adjustment works
Thu (30/07) | 30 Jul 2026 | Zone 2 & Zone 3 |  | LTA env safety inspection walk
Thu (30/07) | 30 Jul 2026 | Zone 2 P11 |  | Strands installation SB side
Thu (30/07) | 30 Jul 2026 | Zone 2 P10 |  | NB segment adjustment ongoing
Thu (30/07) | 30 Jul 2026 | Zone 4 DR4 |  | Current status of traffic light pipe laying
Thu (30/07) | 30 Jul 2026 | Zone 4 DR4 |  | Ryobi G TT for inclinometer and water standpipe installation. GCE will do probing after TT
Thu (30/07) | 30 Jul 2026 | Zone 4 DR4 |  | GCE TT and pipe sleeves installation for UKP
Thu (30/07) | 30 Jul 2026 | Zone 4 DR4 |  | LE doing TT and found HT cable. Need to arrange SPPG for spiking
Thu (30/07) | 30 Jul 2026 | B2 | South side, GL26-25 | Skinwall formwork installation ongoing
Thu (30/07) | 30 Jul 2026 | Column C01-2 | South side | 1st lift formwork installation in progress
Thu (30/07) | 30 Jul 2026 | U3-05 |  | Cleaning ongoing, U3-07: Wall starter bars & shearlinks installation, Both slabs plan for casting tmr
Thu (30/07) | 30 Jul 2026 | U3 | South side, GL25-26 | Scaffold erection in progress for skinwall works
Thu (30/07) | 30 Jul 2026 | Column C01-5 | South side | Soffit roughening ongoing
Thu (30/07) | 30 Jul 2026 | U3 | U3-17, GL21 | Subsoil drain works ongoing
Thu (30/07) | 30 Jul 2026 | Zone 4 P48 |  | Crosshead rebar work. Target to complete on Saturday and handover to WH for ducting work
Thu (30/07) | 30 Jul 2026 | Zone 4 P47 |  | Pile head hacking at SB
Thu (30/07) | 30 Jul 2026 | Zone 4 P46 |  | Hacking and preparation for caisson at SB and excavation at SB for 4th layer
Thu (30/07) | 30 Jul 2026 | Zone 2 P13 SB |  | Midspan casting completed. Tmr night to cast at NB
Thu (30/07) | 30 Jul 2026 | Zone 2 P11 NB |  | 3rd pair to launch tonight
Thu (30/07) | 30 Jul 2026 | Zone 2 P10 SB |  | Wet stitch to cast. Waiting for concrete lorry
Fri (31/07) | 31 Jul 2026 | Zone 3 P40 |  | Formwork closing started to stitch between two segments
Fri (31/07) | 31 Jul 2026 | Zone 3 P39 |  | Starter hanger and stressing cage assembling
Fri (31/07) | 31 Jul 2026 | U3-07 |  | Shearlinks installation, U3-05: Cleaning ongoing, Both slabs plan for casting tonight
Fri (31/07) | 31 Jul 2026 | Zone 3 P29 |  | Soffit plywood installation done. To continue with GI pipe support and rebar work
Fri (31/07) | 31 Jul 2026 | Zone 4 DR4 |  | Preparation for trial trench work
Fri (31/07) | 31 Jul 2026 | Zone 4 P48 |  | Crosshead rebar installation ongoing
Fri (31/07) | 31 Jul 2026 | Zone 4 P47 |  | Bored pile hacking
Fri (31/07) | 31 Jul 2026 | Zone 4 P46 |  | L4 caisson rebar works at north, excavation at south
Fri (31/07) | 31 Jul 2026 | Zone 3 P33 |  | Tendon wire pulling done. Today target to complete stressing
Fri (31/07) | 31 Jul 2026 | Zone 3 P37 |  | Minor rectification for crosshead before casting. Tonight target to cast
Sat (01/08) | 01 Aug 2026 | Zone 3 P29 |  | Scaffolding erection
Sat (01/08) | 01 Aug 2026 | Zone 3 P33 |  | Tendon stressing in progress
Sat (01/08) | 01 Aug 2026 | Zone 3 P37 |  | Crosshead casting completed. No activity
Sat (01/08) | 01 Aug 2026 | Zone 3 P40 |  | Closing formwork for concrete blocks
Sat (01/08) | 01 Aug 2026 | Zone 3 P39 |  | Starter hanger assembly works ongoing
Sat (01/08) | 01 Aug 2026 | Zone 4 P46 |  | Lowering materials for formwork closing
Sat (01/08) | 01 Aug 2026 | Zone 4 P48 |  | Crosshead rebar works ongoing
Sat (01/08) | 01 Aug 2026 | Zone 4 P37 |  | Bored pile hacking at south side
Sat (01/08) | 01 Aug 2026 | Zone 4 DR4 |  | Pipe laying works for traffic diversion stage 1A
Sat (01/08) | 01 Aug 2026 | Zone 4 DR4 |  | No trial trench works ongoing
Sat (01/08) | 01 Aug 2026 | Zone 2 P11 |  | SB U04/D04 strand pushing in progress
Sat (01/08) | 01 Aug 2026 | Zone 2 P10 |  | Segment adjustment
Sat (01/08) | 01 Aug 2026 | P3 |  | Shifting materials to P10
Sat (01/08) | 01 Aug 2026 | P4 |  | Stump casting completed. Now formwork removal
Sat (01/08) | 01 Aug 2026 | P29 |  | Crosshead formwork installation
Sat (01/08) | 01 Aug 2026 | P33 |  | Tendon stressing work
Sat (01/08) | 01 Aug 2026 | P40 |  | Closing formwork for concrete block
Sat (01/08) | 01 Aug 2026 | P46 |  | L4 caisson formwork closing at north side
Sat (01/08) | 01 Aug 2026 | P47 |  | Bored pile hacking at south side
Sat (01/08) | 01 Aug 2026 | P48 |  | Crosshead rebar and anchor head installation
Sat (01/08) | 01 Aug 2026 | DR4 |  | Ryobi G trial trench for instrumentation
Sat (01/08) | 01 Aug 2026 | DR4 |  | Pipe laying works for 1 lane completed. Now doing the finishing
Sat (01/08) | 01 Aug 2026 | P11 |  | Preparation for stressing work
Sun (02/08) | 02 Aug 2026 | Zone 3 P29 |  | Side formwork closing done and CJ roughening also done. Rebar already delivered for crosshead
Sun (02/08) | 02 Aug 2026 | Zone 3 P33 |  | Tendon cutting and capping at SB side done. To continue at NB and complete by today
Sun (02/08) | 02 Aug 2026 | Zone 3 P37 |  | Casting done. Curing
Sun (02/08) | 02 Aug 2026 | Zone 3 P40 |  | Formwork closing for casting between two segments
Sun (02/08) | 02 Aug 2026 | Zone 3 P39 |  | Current status of starter hanger and stressing cage assembling
Sun (02/08) | 02 Aug 2026 | Zone 4 P36 |  | Formwork at NB completed. Excavation at SB in progress
Sun (02/08) | 02 Aug 2026 | Zone 4 P47 |  | Bored pile at SB side hacking
Sun (02/08) | 02 Aug 2026 | Zone 4 P48 NB |  | Ultracon started tendom box installation
Sun (02/08) | 02 Aug 2026 | Zone 4 P48 SB |  | Main bar for crosshead completed. Ducting work will start on Monday
Sun (02/08) | 02 Aug 2026 | Zone 4 DR4 |  | Hacking of premix for traffic light pipe laying. 1/2 lanes completed. Both will complete by today
Sun (02/08) | 02 Aug 2026 | Zone 4 DR4 |  | BRC placing for footpath casting. Today plan to cast 16m. Total to cast around 70m +
Sun (02/08) | 02 Aug 2026 | Zone 2 P11 |  | Stressing completed. Tendon wire cutting and preparing for capping installation
Sun (02/08) | 02 Aug 2026 | Zone 2 P10 |  | Stressing completed. Preparing for tendon cutting work. Tomorrow to continue capping
Sun (02/08) | 02 Aug 2026 | Zone 2 P7 |  | WH preparing to install lighting on crosshead
Sun (02/08) | 02 Aug 2026 | Zone 2 P6 |  | Dismantling of formwork and tidy up the area
Sun (02/08) | 02 Aug 2026 | Zone 1 |  | Today no activity
Sun (02/08) | 02 Aug 2026 | Zone 4 DR4 |  | Footpath first part casting done for pedestrian footpath and traffic light diversion
Sun (02/08) | 02 Aug 2026 | Zone 4 DR4 |  | Traffic light pipe laying done
Sun (02/08) | 02 Aug 2026 | Zone 4 DR4 |  | TT completed for soldier pile alignment. Scheduled with SPPG to come for cable spiking on Tuesday afternoon
Sun (02/08) | 02 Aug 2026 | Zone 4 P48 |  | Spiral link and tendon box installation
Sun (02/08) | 02 Aug 2026 | Zone 4 P47 |  | Pile head hacking at SB
Sun (02/08) | 02 Aug 2026 | Zone 3 P40 |  | Formwork closing for casting between segments
Mon (03/08) | 03 Aug 2026 | Zone 3 P29 |  | GI pipe support erection in progress prior to rebar works
Mon (03/08) | 03 Aug 2026 | Zone 3 P30 2nd lift |  | No activity
Mon (03/08) | 03 Aug 2026 | Zone 2 |  | USS water parade
Mon (03/08) | 03 Aug 2026 | Zone 2 P10 NB |  | 1st pair wet stitch formwork closing
Mon (03/08) | 03 Aug 2026 | Zone 2 P11 SB |  | 5th pair segment launching tonight. LF shifted
Mon (03/08) | 03 Aug 2026 | Zone 4 800mm dia water pipe link up |  | Ley choon started clearing materials. Tomorrow to start pit excavation at link up area
Mon (03/08) | 03 Aug 2026 | Zone 3 P40 |  | Preparing for FBCM grouting works
Mon (03/08) | 03 Aug 2026 | Zone 3 P37 |  | Curing
Mon (03/08) | 03 Aug 2026 | Zone 3 P33 |  | Continue polyfoam removal along sidewing & access erection ongoing
Mon (03/08) | 03 Aug 2026 | Zone 1 P4 |  | Stump formwork dismantling, USS preparing to install bearing plate
Mon (03/08) | 03 Aug 2026 | Zone 4 DR4 |  | Hand augering for probing work
Mon (03/08) | 03 Aug 2026 | Zone 4 DR4 |  | Shifting machine to start probing
Mon (03/08) | 03 Aug 2026 | Zone 4 DR4 |  | Area prepared for spiking work tomorrow
Mon (03/08) | 03 Aug 2026 | Zone 4 P46 |  | 4th layer caisson (NB) casting done
Mon (03/08) | 03 Aug 2026 | Zone 4 P47 |  | Excavation at SB side
Mon (03/08) | 03 Aug 2026 | Zone 4 P48 |  | Tendon duct installation and balance rebar work
Mon (03/08) | 03 Aug 2026 | CCW1 South |  | Tunnel eye hacking started today. Currently activity has ended for the day
Mon (03/08) | 03 Aug 2026 | CCW1 North |  | Debris clearing ongoing by Multibase
Mon (03/08) | 03 Aug 2026 | U3-38 |  | Rebar works and cast-in pipes installation in progress
Mon (03/08) | 03 Aug 2026 | U3-32 |  | Currently no activity
Mon (03/08) | 03 Aug 2026 | U3-31 |  | Hacking ongoing at skinwall area
Mon (03/08) | 03 Aug 2026 | U3-29, U3-27, U3-25, U3-23 |  | Preparation ongoing for lean con casting tonight
Mon (03/08) | 03 Aug 2026 | U3-21 |  | CJ cleaning ongoing at U3-22 side
Mon (03/08) | 03 Aug 2026 | Column C03-2 | South side | Soffit roughening ongoing
Mon (03/08) | 03 Aug 2026 | Column C04 | South side | Rebar works in progress
Mon (03/08) | 03 Aug 2026 | Column C01-2 | South side | 1st lift was cast last week
Mon (03/08) | 03 Aug 2026 | Column C01-3 | South side | Currently no activity
Mon (03/08) | 03 Aug 2026 | Column C01-4 | South side | Currently no activity
Mon (03/08) | 03 Aug 2026 | Zone 2 P11 |  | Shifting of stressing cage for segment launching tonight. Two segments planned for tonight
Mon (03/08) | 03 Aug 2026 | U3 | North side, GL21-23 | Subsoil drain works in progress
Mon (03/08) | 03 Aug 2026 | Column C01-5 | South side | Rebar works in progress
Mon (03/08) | 03 Aug 2026 | Zone 2 P10 |  | WH preparing for stitching formwork at NB. Tomorrow night Ultracon will shift starter hanger to P7
Mon (03/08) | 03 Aug 2026 | Zone 2 P7 |  | Preparing for starter hanger installation
Mon (03/08) | 03 Aug 2026 | U3 | South side, GL27 | Excavation completed. Now clearing the balance soil/hardcore
Mon (03/08) | 03 Aug 2026 | U3-09 |  | Bottom rebar works in progress
Mon (03/08) | 03 Aug 2026 | U3-07, U3-05 |  | No activity. Slabs were cast last week
Mon (03/08) | 03 Aug 2026 | Zone 1 P4 |  | Bearing plates installation and shifting materials
Mon (03/08) | 03 Aug 2026 | B2 | next to Opening 9, GL30-31 | Internal wall rebar planting in progress
Mon (03/08) | 03 Aug 2026 | B2 | South side, GL30-32 | Double slab rebar works and first lift wall formwork installation in progress
Mon (03/08) | 03 Aug 2026 | B2 | North side, GL23-24 | 2nd lift wall formwork installation ongoing
Mon (03/08) | 03 Aug 2026 | Exit 3 |  | Platform erection in progress for TKP bracing installation
Mon (03/08) | 03 Aug 2026 | B2 | South side, GL3-W7 | Skinwall formwork installation in progress
Mon (03/08) | 03 Aug 2026 | Zone 4 DR4 |  | No activity after 7PM
Mon (03/08) | 03 Aug 2026 | Zone 4 P48 |  | Continue crosshead rebar work
Mon (03/08) | 03 Aug 2026 | B1 level | along B1-04 | Double slab rebar works in progress
Mon (03/08) | 03 Aug 2026 | B1 level |  | No other activity observed
Mon (03/08) | 03 Aug 2026 | Zone 3 P29 |  | GI pipe installation for crosshead rebar work
Mon (03/08) | 03 Aug 2026 | Zone 3 P40 |  | Sealant application at formwork gap for casting
Tue (04/08) | 04 Aug 2026 | Zone 4 DR4 |  | Eng Hup on site to start cable pulling
Tue (04/08) | 04 Aug 2026 | Zone 4 DR4 |  | SPPG and the contractor on site for cable spiking
Tue (04/08) | 04 Aug 2026 | Zone 4 DR4 |  | Set up rig for probing at Water standpipe and piezometer area
Tue (04/08) | 04 Aug 2026 | Zone 2 |  | P12-13 midspan wet stitch formwork dismantling
Tue (04/08) | 04 Aug 2026 | Zone 4 800mm dia water pipe |  | TT for link up pit area
Tue (04/08) | 04 Aug 2026 | Zone 3 P29 |  | Bottom rebar work started
Tue (04/08) | 04 Aug 2026 | Zone 3 P30 | 2nd lift | No activity
Tue (04/08) | 04 Aug 2026 | Zone 3 P40 |  | Grouting works between the FBCM concrete blocks ongoing
Tue (04/08) | 04 Aug 2026 | P10 SB |  | Dismantling of SH, tonight to install at P7
Tue (04/08) | 04 Aug 2026 | P7 |  | Materials clearing for crane parking
Tue (04/08) | 04 Aug 2026 | P4 |  | Bearing installation in progress
Tue (04/08) | 04 Aug 2026 | CCW1 | South side | Tunnel eye hacking in progress
Tue (04/08) | 04 Aug 2026 | CCW1 North |  | Continue clearing debris from the tunnel eye area
Tue (04/08) | 04 Aug 2026 | U3-38 |  | Top bar and side formwork installation in progress. Plan for casting this week
Tue (04/08) | 04 Aug 2026 | U3-32 |  | Bottom rebar works in progress
Tue (04/08) | 04 Aug 2026 | U3-35, U3-33 |  | Hacking ongoing at skinwall area
Tue (04/08) | 04 Aug 2026 | U3-31 |  | Surface cleaning ongoing prior to laying waterproofing membrane
Tue (04/08) | 04 Aug 2026 | U3-29, U3-27, U3-25, U3-23 |  | Lean con casting completed last night
Tue (04/08) | 04 Aug 2026 | Column C03-2 | South side | Currently no activity
Tue (04/08) | 04 Aug 2026 | Column C04 | South side | Currently no activity
Tue (04/08) | 04 Aug 2026 | Column C01-2 | South side | 2nd lift rebar tying ongoing
Tue (04/08) | 04 Aug 2026 | Column C01-3 | South side | Preparing formwork for 1st lift
Tue (04/08) | 04 Aug 2026 | Column C01-4 | South side | Currently no activity, Skinwall hacking ongoing
Tue (04/08) | 04 Aug 2026 | U3 | North side, GL21-24 | Subsoil drain works ongoing, Preparation ongoing for permeability test borehole, BH-P10
Tue (04/08) | 04 Aug 2026 | Column C01-5 | South side | Rebar works ongoing
Tue (04/08) | 04 Aug 2026 | U3 | South side, GL26-24 | PU grouting in progress at skinwall area
Tue (04/08) | 04 Aug 2026 | U3 | GL27 | Clearing balance soil
Tue (04/08) | 04 Aug 2026 | U3-09 |  | Bottom rebar works in progress
Tue (04/08) | 04 Aug 2026 | Column C02-2a | North side | Scaffold erection in progress for column works
Tue (04/08) | 04 Aug 2026 | CCE | North side, GL-E5 | Hacking ongoing at skinwall area
Tue (04/08) | 04 Aug 2026 | CCE | North side, GL-E2 to E1 | WH start hacking for ramp removal
Tue (04/08) | 04 Aug 2026 | B2 | next to Opening 9, GL30-31 | Internal wall rebar planting in progress
Tue (04/08) | 04 Aug 2026 | B2 | South side, GL32-30 | Double slab rebar and 1st lift wall formwork installation in progress
Tue (04/08) | 04 Aug 2026 | B2 | South side, GL4-6 | Skinwall formwork installation in progress
Tue (04/08) | 04 Aug 2026 | Zone 4 P48 |  | Tendon duct installation
Tue (04/08) | 04 Aug 2026 | Zone 4 P47 |  | Last layer excavation at SB
Tue (04/08) | 04 Aug 2026 | Zone 4 P46 |  | Preparing for excavation at NB
Tue (04/08) | 04 Aug 2026 | Exit 3 |  | WH to complete scaffold erection today for TKP bracing. Pending Hirose to confirm materials delivery date
Tue (04/08) | 04 Aug 2026 | B1 level |  | Currently no activity
Tue (04/08) | 04 Aug 2026 | Zone 3 P40 |  | NB grouting completed. SB to continue tomorrow
Tue (04/08) | 04 Aug 2026 | Zone 2 P13 |  | Shifting materials to P11 for segment launching tonight
Tue (04/08) | 04 Aug 2026 | Zone 2 P11 |  | Lowering down hydraulic jack from stressing and preparing for two segments launching tonight at NB
Tue (04/08) | 04 Aug 2026 | Zone 2 P7 |  | Tonight will launch one set of starter hanger
Tue (04/08) | 04 Aug 2026 | Zone 1 P4 |  | Now no activity already
Tue (04/08) | 04 Aug 2026 | Zone 4 800mm dia water pipe |  | Current status of ERSS installation at link up area
Tue (04/08) | 04 Aug 2026 | Zone 4 DR4 |  | Eng Hup cable pulling completed for traffic light diversion
Tue (04/08) | 04 Aug 2026 | Zone 4 DR4 |  | No more work at utility risk area
Tue (04/08) | 04 Aug 2026 | Zone 4 P48 |  | Continue duting work
Tue (04/08) | 04 Aug 2026 | Zone 4 P47 |  | Base lean con done
Tue (04/08) | 04 Aug 2026 | Zone 4 P46 |  | Tomorrow to continue excavation
Tue (04/08) | 04 Aug 2026 | Zone 3 P37 |  | Curing. No activity
Tue (04/08) | 04 Aug 2026 | Zone 3 P29 |  | Continue crosshead rebar work
Wed (05/08) | 05 Aug 2026 | Zone 3 P33 |  | Preparing working platform removal
Wed (05/08) | 05 Aug 2026 | Zone 4 DR4 |  | Preparing to start probing work for instrument. Hose need to replace for this new machine
Wed (05/08) | 05 Aug 2026 | Zone 3 P40 |  | Continue with grouting works for the FBCM
Wed (05/08) | 05 Aug 2026 | Zone 3 P41 LG |  | Preparing for the SH shifting, on ground preparations ongoing
Wed (05/08) | 05 Aug 2026 | P11 NB |  | Strand Pushing for 5th pair stressing
Wed (05/08) | 05 Aug 2026 | P10 NB |  | 1st pair wet stitch formwork closing
Wed (05/08) | 05 Aug 2026 | P7 MV NB |  | SH installed last night
Wed (05/08) | 05 Aug 2026 | P4 |  | Bearing installation in progress
Wed (05/08) | 05 Aug 2026 | Zone 3 P29 |  | Access erection / working platform for rebar work ongoing
Wed (05/08) | 05 Aug 2026 | DR4 |  | Preparation work for traffic light cable pulling
Wed (05/08) | 05 Aug 2026 | DR4 |  | Preparation for probing works (for instrumentation)
Wed (05/08) | 05 Aug 2026 | 800mm PW |  | Link up Pit-2 excavation and works continued
Wed (05/08) | 05 Aug 2026 | Zone 4 P51 |  | Formwork closing for column
Wed (05/08) | 05 Aug 2026 | P47 |  | No activity
Wed (05/08) | 05 Aug 2026 | P46 |  | Bored pile hacking
Wed (05/08) | 05 Aug 2026 | P48 |  | Tendon duct installation
Wed (05/08) | 05 Aug 2026 | Zone 4 800mm dia water pipe |  | Manual excavation for link up area
Wed (05/08) | 05 Aug 2026 | Zone 4 DR4 |  | Probing in progress for instrumentation work
Wed (05/08) | 05 Aug 2026 | Zone 4 DR4 |  | Marking of teleco duct alignment
Wed (05/08) | 05 Aug 2026 | Zone 4 DR4 |  | Traffic light installed. Will continue with PC pole later
Wed (05/08) | 05 Aug 2026 | P10 NB |  | 1st pair wet stitch formwork closing continue, UC - 70% completed, DC - 50% completed
Wed (05/08) | 05 Aug 2026 | P11 NB |  | 5th pair preparation for stressing
Wed (05/08) | 05 Aug 2026 | P7 MV NB |  | Shifting of stressing cage
Wed (05/08) | 05 Aug 2026 | P51 |  | Formwork closing for column
Wed (05/08) | 05 Aug 2026 | Zone 4 P48 |  | Continue ducting installation work
Wed (05/08) | 05 Aug 2026 | Zone 4 P47 |  | Lowered down rebar for balance caisson work
Wed (05/08) | 05 Aug 2026 | Zone 4 P46 |  | Pile head hacking
Wed (05/08) | 05 Aug 2026 | CCW1 South |  | Tunnel eye hacking status
Wed (05/08) | 05 Aug 2026 | CCW1 North |  | Cutting GFRP at tunnel eye area
Wed (05/08) | 05 Aug 2026 | U3-38 |  | Wall starter bar and shearlinks installation in progress
Wed (05/08) | 05 Aug 2026 | CCW2 |  | Currently no activity
Wed (05/08) | 05 Aug 2026 | Zone 3 P29 |  | Top bar installation started
Wed (05/08) | 05 Aug 2026 | U3-32 |  | Bottom rebar works and bar chair installation in progress
Wed (05/08) | 05 Aug 2026 | U3-31 |  | Waterproofing membrane laying ongoing
Wed (05/08) | 05 Aug 2026 | Zone 3 P30 | 2nd lift | No activity observed
Wed (05/08) | 05 Aug 2026 | U3-33, U3-35 |  | Hacking ongoing at skinwall area
Wed (05/08) | 05 Aug 2026 | U3-30, U3-28 |  | CJ hacking ongoing
Wed (05/08) | 05 Aug 2026 | Zone 3 P40 |  | FBCM blocks 15/16 nos grouting completed
Wed (05/08) | 05 Aug 2026 | Column C03-2 | South side | Currently no activity
Wed (05/08) | 05 Aug 2026 | Column C04 | South side | Currently no activity
Wed (05/08) | 05 Aug 2026 | Column C01-3 | South side | Formwork installation in progress for 1st lift
Wed (05/08) | 05 Aug 2026 | U3-19 |  | Formwork installation ongoing for drop area
Wed (05/08) | 05 Aug 2026 | Column C01-4 | South side | Rebar planting in progress
Wed (05/08) | 05 Aug 2026 | U3 | North side, GL21-24 | Subsoil drain and coupler exposing at dwall area ongoing
Wed (05/08) | 05 Aug 2026 | U3-09 |  | Side formwork installation, cast-in pipes and top bar installation in progress
Wed (05/08) | 05 Aug 2026 | Column C02-2 | North side | Currently no activity. Scaffold erected
Wed (05/08) | 05 Aug 2026 | Zone 4 P46 |  | Pile head hacking ongoing
Wed (05/08) | 05 Aug 2026 | Zone 4 P47 |  | Pending to start rebar work for balance caisson wall
Wed (05/08) | 05 Aug 2026 | Zone 4 P48 |  | Duct installation status
Wed (05/08) | 05 Aug 2026 | CCE | North side, GL-E3 to E1 | Ramp removal in progress
Wed (05/08) | 05 Aug 2026 | B2 | South side, GL30 | 1st lift internal wall formwork installation
Wed (05/08) | 05 Aug 2026 | B2 | North side, GL25-26 | 1st lift internal wall formwork installation
Wed (05/08) | 05 Aug 2026 | Exit 3 |  | Currently no activity
Wed (05/08) | 05 Aug 2026 | B2 | South side, GL3-6 | Skinwall formwork installation
Wed (05/08) | 05 Aug 2026 | B1 level | B1-02, B1-04 area | Preparing casting for double slab and first lift wall
Wed (05/08) | 05 Aug 2026 | B1 level |  | No other activity
Wed (05/08) | 05 Aug 2026 | Zone 4 800mm dia water pipe |  | As-built taking for link up area. Will continue with excavation and ERSS installation
Thu (06/08) | 06 Aug 2026 | Zone 3 P29 |  | Top bar installation ongoing
Thu (06/08) | 06 Aug 2026 | Zone 3 P30 | 2nd lift | No activity observed
Thu (06/08) | 06 Aug 2026 | Zone 3 P33 |  | Current status of falsework dismantling, tower access dismantling ongoing
Thu (06/08) | 06 Aug 2026 | Zone 3 P37 |  | Preparing to remove sidewing formwork
Thu (06/08) | 06 Aug 2026 | Zone 4 DR4 |  | IS51049 drilling work started by Ryobi G
Thu (06/08) | 06 Aug 2026 | Zone 4 P48 |  | NB side tendon duct installation ongoing
Thu (06/08) | 06 Aug 2026 | Zone 4 P51 |  | Middle column 1st stage fwk closure ongoing
Thu (06/08) | 06 Aug 2026 | Zone 4 P51 |  | Exposing StarHub cables prior to local shifting. RES on standby
Thu (06/08) | 06 Aug 2026 | Zone 4 P46 |  | BP hacking ongoing
Thu (06/08) | 06 Aug 2026 | Zone 4 P47 |  | Rebar work for caisson walk ongoing
Thu (06/08) | 06 Aug 2026 | Zone 2 P11-P14 |  | Stage 2 stressing ongoing
Thu (06/08) | 06 Aug 2026 | Zone 1 P4 |  | Bearing installation ongoing
Fri (07/08) | 07 Aug 2026 | Exit 3 |  | TKP bracing installation in progress. Plan to complete today and do MPI test tmr
Fri (07/08) | 07 Aug 2026 | U3-38 |  | Casting progress
Fri (07/08) | 07 Aug 2026 | U3-32 & U3-31 |  | Rebar works in progress
Fri (07/08) | 07 Aug 2026 | U3-31 |  | RGT installation in progress at dwall side
Fri (07/08) | 07 Aug 2026 | U3-28 |  | CJ hacking ongoing
Fri (07/08) | 07 Aug 2026 | U3-17 |  | Lean con completed
Fri (07/08) | 07 Aug 2026 | U3-21 |  | Partial waterproofing membrane laying
Fri (07/08) | 07 Aug 2026 | U3-19 |  | Drilling ongoing for permeability test, BH-P9
Fri (07/08) | 07 Aug 2026 | Column C01-5 | South side | 1st lift formwork installation
Fri (07/08) | 07 Aug 2026 | Zone 2 P10 |  | Crane parking platform preparation for tonight lifter shifting from P11 to P10
Fri (07/08) | 07 Aug 2026 | U3-09 |  | Balance top bar and shearlinks installation. Plan for casting tonight
Fri (07/08) | 07 Aug 2026 | Zone 4 P51 |  | Middle column first lift, pending to cast
Fri (07/08) | 07 Aug 2026 | Zone 4 P48 |  | Tendon duct installation ongoing
Fri (07/08) | 07 Aug 2026 | Zone 4 P46 |  | Continue excavation work for 4th caisson wall
Fri (07/08) | 07 Aug 2026 | Zone 2 P7 |  | Segment adjustment for 1st pair NB segment
Fri (07/08) | 07 Aug 2026 | Zone 2 P9 |  | NR U03 segment to launch tonight
Fri (07/08) | 07 Aug 2026 | B2 | North side, GL30 | PU grouting ongoing
Fri (07/08) | 07 Aug 2026 | Zone 3 P34 |  | Falsework shifted from P33
Fri (07/08) | 07 Aug 2026 | B1 level | B1-02, B1-04 | Double slab and internal wall was cast on Wednesday. Currently no activity
Fri (07/08) | 07 Aug 2026 | B1 level |  | Currently no other activity
Fri (07/08) | 07 Aug 2026 | Zone 3 P29 |  | Top bar installation ongoing
Fri (07/08) | 07 Aug 2026 | Zone 3 P30 | 2nd lift | No activity observed
Fri (07/08) | 07 Aug 2026 | Zone 3 P33 |  | Status of falsework dismantling
Fri (07/08) | 07 Aug 2026 | Zone 3 P37 |  | Formwork dismantling ongoing
Sat (08/08) | 08 Aug 2026 | Zone 1 P4 |  | Ultracon continue shifting materials. Today they will start jack installation and adjustment for segment launching work
Sat (08/08) | 08 Aug 2026 | B2 | South side, GL21 | Skinwall rebar works ongoing
Sat (08/08) | 08 Aug 2026 | U3 Column C04 |  | 1st lift formwork installation in progress
Sat (08/08) | 08 Aug 2026 | U3 | South side, GL12-11 | Hacking ongoing at skinwall area
Sat (08/08) | 08 Aug 2026 | U3-21 |  | Partial waterproofing membrane laying, PU grouting in progress
Sat (08/08) | 08 Aug 2026 | U3-19, U3-17 |  | Coupler exposing and formwork removal at drop area
Sat (08/08) | 08 Aug 2026 | U3 | South side, GL22-21 | Scaffold erection in progress for skinwall works
Sat (08/08) | 08 Aug 2026 | Zone 2 P7 |  | Survey taken the data for 1st pair
Sat (08/08) | 08 Aug 2026 | Zone 2 P9 |  | Tendon wire pulling for stressing
Sat (08/08) | 08 Aug 2026 | Zone 2 P10 |  | Stitching formwork removal
Sat (08/08) | 08 Aug 2026 | CCE | North side, GL-E1 to E2 | Continue excavation, CCE GL-E3 to E8: Currently no activity, CCE ccess from B2 to U3 has been dismantled. New access installation currently in progress
Sat (08/08) | 08 Aug 2026 | U3-09 |  | Preparing for casting
Sat (08/08) | 08 Aug 2026 | U3-11 |  | Hacking & trenching ongoing to facilitate subsoil drain works
Sat (08/08) | 08 Aug 2026 | U3 Column C01-4 | South side | Rebar works ongoing
Sat (08/08) | 08 Aug 2026 | U3 Column C01-3 | South side | 1st lift formwork installation in progress
Sat (08/08) | 08 Aug 2026 | U3 Column C01-2 | South side | 2nd lift formwork installation in progress
Sat (08/08) | 08 Aug 2026 | U3 | North side, GL14 | Drilling ongoing for BH-P8
Sat (08/08) | 08 Aug 2026 | Zone 2 N6 |  | TT to check previous laid telecon duct. Left a small portion to connect the duct at N6 area
Sat (08/08) | 08 Aug 2026 | U3-32 |  | Top bar installation and preparing for side formwork installation, U3-31: Continue bottom rebar works, Both slabs plan for casting next week
Sat (08/08) | 08 Aug 2026 | U3-36 |  | Start waterproofing membrane laying
Sat (08/08) | 08 Aug 2026 | U3-38 |  | Yesterday cast
Sat (08/08) | 08 Aug 2026 | CCW2 |  | Hirose preparing to start cutting the S5 struts lacing
Sat (08/08) | 08 Aug 2026 | CCW1 North Tunnel Eye |  | Multibase continue clearing ard the tunnel eye
Sat (08/08) | 08 Aug 2026 | CCW1 South Tunnel Eye |  | Multibase to continue hacking the bottom part after clearing the debris from the area
Sat (08/08) | 08 Aug 2026 | Zone 4 800mm dia water pipe |  | Manual excavation and shoring for link up area
Sat (08/08) | 08 Aug 2026 | Zone 4 DR4 |  | Trial coring of services pipe and cable before start actual probing work
Sat (08/08) | 08 Aug 2026 | Zone 4 P51 |  | One column casting done
Sat (08/08) | 08 Aug 2026 | Zone 4 P48 |  | Ducting and drainage pipe support work. To complete by Tiesday
Sat (08/08) | 08 Aug 2026 | Zone 4 P47 |  | Concrete ordered for balance caisson casting
Sat (08/08) | 08 Aug 2026 | Zone 4 P46 |  | Pile head hacking
Sat (08/08) | 08 Aug 2026 | Zone 3 P40 |  | Grouting was done. Clearing materials
Sat (08/08) | 08 Aug 2026 | Zone 3 P43 |  | Current status of falsework
Sat (08/08) | 08 Aug 2026 | Zone 3 P29 |  | Current status of crosshead rebar work
Sat (08/08) | 08 Aug 2026 | Zone 1 P4 |  | Now no activity
Sat (08/08) | 08 Aug 2026 | Zone 2 N6 |  | Exposing teleco duct at both end done. Surveyor taking as-built
Sat (08/08) | 08 Aug 2026 | B1 level |  | No activity
Sat (08/08) | 08 Aug 2026 | B2 level | South side S1-1, S1-2 | Tonight plan to cast skinwall
Sat (08/08) | 08 Aug 2026 | Exit 3 |  | TKP bracing installation was completed, now ongoing welding works. This afternoon plan for MPI test
Sat (08/08) | 08 Aug 2026 | Zone 2 P10 |  | Preparing for stressing work. One lane closed for this activity
Sat (08/08) | 08 Aug 2026 | Zone 2 P9 |  | Tendon duct cutting and capping done
Sat (08/08) | 08 Aug 2026 | B2 | North side, GL3 | Skinwall rectification
Sat (08/08) | 08 Aug 2026 | U3-09 |  | Casting in progress
Sat (08/08) | 08 Aug 2026 | U3-11 |  | Continue hacking & trenching to facilitate subsoil drain works
Sat (08/08) | 08 Aug 2026 | U3-21 |  | Wendyng start rebar works for column area, Dongah continue PU grouting at dwall side
Sat (08/08) | 08 Aug 2026 | U3-31 |  | Continue bottom rebar works
Sat (08/08) | 08 Aug 2026 | Zone 4 800mm dia water pipe |  | Continue excavation and ERSS installation for link up work
Sat (08/08) | 08 Aug 2026 | Zone 4 DR4 |  | Probing 10nos done for 5 UKP
Sat (08/08) | 08 Aug 2026 | Zone 4 DR4 |  | Clearing materials for footpath diversion
Sat (08/08) | 08 Aug 2026 | CCE4 | South side | Hirose preparing for bracket installation
Sat (08/08) | 08 Aug 2026 | Zone 4 P48 |  | Continue ducting work. To complete by Tuesday
Sat (08/08) | 08 Aug 2026 | Zone 4 P47 |  | Continue casting of balance caisson
Sat (08/08) | 08 Aug 2026 | Zone 4 P46 |  | Continue hacking of pile head
Sat (08/08) | 08 Aug 2026 | Zone 3 P40 |  | Preparing for stressing work
Sat (08/08) | 08 Aug 2026 | Zone 3 P34 |  | Continue falsework assembling
Sat (08/08) | 08 Aug 2026 | Zone 3 P29 |  | Continue crosshead rebar work. To complete by Tuesday
Sat (08/08) | 08 Aug 2026 | CCE4 |  | Hirose planting bolts for struts installation at south side. Today plan to start for bracket installation
Sat (08/08) | 08 Aug 2026 | B2 | North side, GL30 | Continue PU grouting works
Tue (11/08) | 11 Aug 2026 | Zone 4 DR4 |  | Footpath casting for diversion was completed. Traffic pole also installed
Tue (11/08) | 11 Aug 2026 | Zone 4 DR4 |  | Preparing for hand augering at probing area. 2/5 probing done
Tue (11/08) | 11 Aug 2026 | B2 | South side, GL32-30 | CJ roughening ongoing at internal wall area
Tue (11/08) | 11 Aug 2026 | B2 | South side, GL18-19 | Skinwall formwork installation in progress
Tue (11/08) | 11 Aug 2026 | P10 NB |  | SH dismantled
Tue (11/08) | 11 Aug 2026 | P9 NBR |  | U04 segment to launch tonight
Tue (11/08) | 11 Aug 2026 | P7 MV SB |  | Crane setting up for SH installation
Tue (11/08) | 11 Aug 2026 | Zone 4 800mm dia water pipe |  | Pumping out water. Today plan to lean concrete after excavation done. Proper access will install after lean con
Tue (11/08) | 11 Aug 2026 | U3 Column C02-2 | North side | Rebar planting in progress
Tue (11/08) | 11 Aug 2026 | U3-09 |  | Cast last weekend
Tue (11/08) | 11 Aug 2026 | U3-11 |  | Subsoil drain works and skinwall hacking in progress
Tue (11/08) | 11 Aug 2026 | U3 | South side, GL25 | PU grouting ongoing
Tue (11/08) | 11 Aug 2026 | U3-13 |  | Trenching ongoing for subsoil drain works
Tue (11/08) | 11 Aug 2026 | U3 | South side, GL23 | Skinwall rebar installation in progress
Tue (11/08) | 11 Aug 2026 | U3-21 |  | Bottom rebar installation and PU grouting in progress
Tue (11/08) | 11 Aug 2026 | U3 | South side, GL17-15 | Scaffold erection ongoing for skinwall works
Tue (11/08) | 11 Aug 2026 | U3-19 |  | Waterproofing membrane laying in progress
Tue (11/08) | 11 Aug 2026 | U3 Column C01-3 | South side | 1st formwork installation ongoing
Tue (11/08) | 11 Aug 2026 | U3 Column C03-2 | South side | Rebar works in progress
Tue (11/08) | 11 Aug 2026 | U3-31, U3-32 |  | Formwork and shearlinks installation. Plan for casting Thursday
Tue (11/08) | 11 Aug 2026 | CCE4 |  | Bracket installation in progress and hacking ongoing
Tue (11/08) | 11 Aug 2026 | Exit 3 |  | Bracing installation and MPI test for TKP completed last Saturday. Now dismantling working platform
Tue (11/08) | 11 Aug 2026 | B1 level | along B1-02, B1-04 | Internal wall formwork dismantling ongoing
Tue (11/08) | 11 Aug 2026 | Zone 4 P48 |  | Ducting installation and polyfoam installation by WH
Tue (11/08) | 11 Aug 2026 | Zone 4 P47 |  | Continue clearing materials. All caisson casting was done
Tue (11/08) | 11 Aug 2026 | Zone 4 P46 |  | Continue excavation for 4th layer
Tue (11/08) | 11 Aug 2026 | Zone 4 DR4 |  | TT done. Preparing for probing
Tue (11/08) | 11 Aug 2026 | Zone 4 800mm dia water pipe |  | Lean concrete done. Access erection. Materials shifting to P45 area for 2nd link up pit excavation
Tue (11/08) | 11 Aug 2026 | Zone 4 DR4 |  | TT for UKP work
Tue (11/08) | 11 Aug 2026 | P7 MV SB |  | Starter hanger installation completed
Tue (11/08) | 11 Aug 2026 | P10 SB |  | Winch and spreader beam installation
Tue (11/08) | 11 Aug 2026 | Zone 4 P48 |  | Rain water drain pipe and opening rebar installation
Tue (11/08) | 11 Aug 2026 | Zone 4 P47 |  | Caisson formwork removal
Tue (11/08) | 11 Aug 2026 | Zone 4 P46 |  | Levelling on going. To hack JGP grout around UKP
Tue (11/08) | 11 Aug 2026 | P29 crosshead |  | No activity observed
Tue (11/08) | 11 Aug 2026 | P34 |  | Scaffold access and netting installation
Tue (11/08) | 11 Aug 2026 | P37 |  | Girder box formwork dismantling
Tue (11/08) | 11 Aug 2026 | P40 |  | 1st pair vertical stressing in progress
Tue (11/08) | 11 Aug 2026 | P48 |  | PT duct installation until 9pm
Tue (11/08) | 11 Aug 2026 | P11 NB |  | Preparation for LF shifting
Tue (11/08) | 11 Aug 2026 | Zone 3 P34 |  | Netting & barricade erection ongoing in the falsework
Tue (11/08) | 11 Aug 2026 | Zone 3 P32 |  | Preparing ground work for falsework footing
Tue (11/08) | 11 Aug 2026 | P11 SB |  | Wet stitch patching
Tue (11/08) | 11 Aug 2026 | Zone 3 P37 |  | Formwork removal status, preparing for post tensioning work
Tue (11/08) | 11 Aug 2026 | CCE | North side, GL-E1 to E2 | Excavation in progress at -9.1
Tue (11/08) | 11 Aug 2026 | B2 | North side, GL28-29 | Internal wall grinding works ongoing
Tue (11/08) | 11 Aug 2026 | B2 | North side, GL30 | Dongah continue PU grouting
Wed (12/08) | 12 Aug 2026 | Zone 3 P40 |  | U tendon stressing SB side ongoing, NB side completed ytd
Wed (12/08) | 12 Aug 2026 | Zone 4 DR4 |  | Hoarding panel installation
Wed (12/08) | 12 Aug 2026 | Zone 3 P39 |  | Preparing for SH shifting, tower access erected
Wed (12/08) | 12 Aug 2026 | Zone 4 800mm dia water pipe |  | 1/2 nos of link up pit excavation done. Now WH preparing to clean around waterpipe for link up work
Wed (12/08) | 12 Aug 2026 | Zone 2 P10 |  | Lifter installed for SB DC side. Tonight to install UC side
Wed (12/08) | 12 Aug 2026 | Zone 2 P9 |  | NR 4th pair segment strand installation in progress
Wed (12/08) | 12 Aug 2026 | Zone 4 DR4 |  | Preparing to start probing for instrument installation
Wed (12/08) | 12 Aug 2026 | Zone 4 P48 |  | Today to complete ducting work and handover to Wendyng
Wed (12/08) | 12 Aug 2026 | Zone 4 800mm dia water pipe |  | Fitting removal. Today will start excavation for 2nd link up pit
Wed (12/08) | 12 Aug 2026 | Zone 4 P46 |  | JGP grout hacking
Wed (12/08) | 12 Aug 2026 | Zone 4 P47 |  | Continue caisson formwork removal
Wed (12/08) | 12 Aug 2026 | CCW1 South |  | Tunnel eye debris clearing ongoing
Wed (12/08) | 12 Aug 2026 | CCW1 North |  | No activity
Wed (12/08) | 12 Aug 2026 | CCW2 |  | Hirose started to dismantle struts
Wed (12/08) | 12 Aug 2026 | U3-36 |  | Rebar works in progress
Wed (12/08) | 12 Aug 2026 | U3-34 |  | RGT installation ongoing
Wed (12/08) | 12 Aug 2026 | U3-32, U3-31 |  | Shearlinks installation and cleaning ongoing. Plan for casting tmr
Wed (12/08) | 12 Aug 2026 | P29 |  | Steel anchor head installation at SB side. Total 6/24 nos completed
Wed (12/08) | 12 Aug 2026 | P34 |  | Plywood laying for working platform. Tonight to install netting on the scaffold access
Wed (12/08) | 12 Aug 2026 | P40 SB |  | Vertical stressing in progress
Wed (12/08) | 12 Aug 2026 | U3 | North side, GL10 | BH-P7 in progress
Wed (12/08) | 12 Aug 2026 | U3-21 |  | Rebar installation in progress
Wed (12/08) | 12 Aug 2026 | U3-19 |  | Continue waterproofing membrane laying and rebar installation at dwall side in progress
Wed (12/08) | 12 Aug 2026 | P41 | LG | Front Auxiliary System (FAS) and chain hoist installation. Tmr plan to move LG to P40
Wed (12/08) | 12 Aug 2026 | U3 Column C01-4 | South side | 1st lift formwork installation ongoing
Wed (12/08) | 12 Aug 2026 | U3 | South side, GL23-24 | Skinwall works ongoing
Wed (12/08) | 12 Aug 2026 | P45 |  | Area preparation for excavation work for 800mm water pipe link up. Shoring materials on site. To continue excavation tomorrow
Wed (12/08) | 12 Aug 2026 | U3 Column C01-7 | North side | Scaffold erection ongoing
Wed (12/08) | 12 Aug 2026 | U3-15, U3-13, U3-11 |  | Currently no activity
Wed (12/08) | 12 Aug 2026 | P46 |  | 4th layer caison working platform to lean concrete tonight
Wed (12/08) | 12 Aug 2026 | P47 |  | FEL lean concrete casting tonight
Wed (12/08) | 12 Aug 2026 | P48 |  | Links installation in progress
Wed (12/08) | 12 Aug 2026 | U3 | South side, GL21 | Skinwall formwork installation in progress
Wed (12/08) | 12 Aug 2026 | Exit 3 |  | Currently no activity
Wed (12/08) | 12 Aug 2026 | B1 level | B1-06, B1-08 | Internal wall works ongoing
Wed (12/08) | 12 Aug 2026 | P11 |  | LF4 preparation for dismantling, to be shifted to P10 tonight
Wed (12/08) | 12 Aug 2026 | P12 to P13 |  | Steel blister dismantling and material lowering
Wed (12/08) | 12 Aug 2026 | Zone 3 P29 |  | Installing anchor head and bursting link ongoing, to handover to ICE Thursday
Wed (12/08) | 12 Aug 2026 | Zone 3 P32 |  | PLT conducted ytd for falsework leg
Wed (12/08) | 12 Aug 2026 | Zone 3 P34 |  | Access erection ongoing by WH & Wendyng preparing fwk
Wed (12/08) | 12 Aug 2026 | Zone 3 P37 |  | Preparing for post tensioning work
Thu (13/08) | 13 Aug 2026 | CCE4 |  | Waler installation is in progress for S6 struts
Thu (13/08) | 13 Aug 2026 | U3 | South side, GL25-24 | PU grouting ongoing at skinwall area, U3 GL23-22 (South side): Skinwall rebar works ongoing
Thu (13/08) | 13 Aug 2026 | U3 Column C01-5 | South side | 1st lift casting in progress
Thu (13/08) | 13 Aug 2026 | U3 Column C01-4 | South side | 1st lift formwork installation ongoing
Thu (13/08) | 13 Aug 2026 | U3-21, U3-19 |  | Bottom bar installation in progress
Thu (13/08) | 13 Aug 2026 | U3-15, U3-13, U3-11 |  | Today plan for lean con casting
Thu (13/08) | 13 Aug 2026 | U3-31, U3-32 |  | Cleaning ongoing. Plan for final inspection this afternoon
Thu (13/08) | 13 Aug 2026 | B2 | South side, GL21-23 | Skinwall formwork installation in progress
Thu (13/08) | 13 Aug 2026 | CCE | GLE1-E3 | Continues excavation & disposal by 3 excavators & 1 Telescopic
Thu (13/08) | 13 Aug 2026 | CCE | GLE3-E9 | No activity
Thu (13/08) | 13 Aug 2026 | Zone 4 800mm dia water pipe |  | PUB inspection of manhole and accessories for link up work
Thu (13/08) | 13 Aug 2026 | U3-31 and U3-32 |  | Final inspection ongoing. Scheduled to commence casting this evening
Thu (13/08) | 13 Aug 2026 | U3-34 |  | Waterproofing membrane laying in progress
Thu (13/08) | 13 Aug 2026 | U3-36 |  | Rebar laying is in progress
Thu (13/08) | 13 Aug 2026 | CCW2 |  | S5 strut removal in progress
Thu (13/08) | 13 Aug 2026 | P10 |  | LF 1-4 installed. Tmr to deliver segment and load test
Thu (13/08) | 13 Aug 2026 | P7 MV SB |  | U01 segment to launch tonight
Thu (13/08) | 13 Aug 2026 | CCE4 |  | Continue waler installation
Thu (13/08) | 13 Aug 2026 | CCE | GL-E1 to E3 | Continue levelling, hacking at skinwall area and disposal works ongoing
Thu (13/08) | 13 Aug 2026 | U3-15, U3-13, U3-11 |  | Currently no activity
Thu (13/08) | 13 Aug 2026 | U3 | South side, GL23-25 | Continue PU grouting and skinwall works
Thu (13/08) | 13 Aug 2026 | U3-19 |  | Bottom rebar works and inspection ongoing
Thu (13/08) | 13 Aug 2026 | P20 to P21 midspan |  | SB wet stitch formwork closing
Thu (13/08) | 13 Aug 2026 | Zone 4 800mm dia water pipe |  | Cleaning around pipe
Thu (13/08) | 13 Aug 2026 | Zone 4 DR4 |  | Boring for water standpipe was done. To continue for inclinometer tomorrow
Thu (13/08) | 13 Aug 2026 | Zone 4 P50 |  | Backfilling for crosshead platform
Thu (13/08) | 13 Aug 2026 | Zone 4 P48 |  | Shear link installation
Thu (13/08) | 13 Aug 2026 | Zone 4 P47 |  | Clearing materials and scaffold erection for S2 strut removal
Thu (13/08) | 13 Aug 2026 | Zone 4 P46 |  | Cement grout removal
Thu (13/08) | 13 Aug 2026 | Zone 3 P40 |  | Currently no activity
Thu (13/08) | 13 Aug 2026 | Zone 3 P39 |  | Access erection was done
Thu (13/08) | 13 Aug 2026 | Zone 3 P37 |  | Exposing tendon end
Thu (13/08) | 13 Aug 2026 | Zone 3 P34 |  | Netting installation below crosshead platform
Thu (13/08) | 13 Aug 2026 | Zone 3 P29 |  | Spiral link installation for tendon duct work
Thu (13/08) | 13 Aug 2026 | Zone 2 P10 |  | TPT bar stressing
Thu (13/08) | 13 Aug 2026 | Zone 2 P10 |  | Spreader beam installation
Thu (13/08) | 13 Aug 2026 | Zone 2 P11 |  | Continue lowering down materials
Thu (13/08) | 13 Aug 2026 | Zone 2 P7 |  | Shifting stressing cage for segment launching tonight
Thu (13/08) | 13 Aug 2026 | Zone 3 P34 |  | Wing formwork installation
Thu (13/08) | 13 Aug 2026 | Zone 3 P29 |  | Anchor head installation
Thu (13/08) | 13 Aug 2026 | U3-05 area |  | Hacking ongoing at skinwall area
Thu (13/08) | 13 Aug 2026 | U3 Column C02-2 | North side | Currently no activity
Thu (13/08) | 13 Aug 2026 | U3 Column C01-7 | North side | Currently no activity
Fri (14/08) | 14 Aug 2026 | P13 |  | Dismantling of TPT in preparation for concrete blocks removal
Fri (14/08) | 14 Aug 2026 | P11 to P12 midspan |  | Preparation for stitch formwork closing
Fri (14/08) | 14 Aug 2026 | P10 |  | 2nd pair tonight to launch after load test. Est segment delivery at 1030 pm
Fri (14/08) | 14 Aug 2026 | P4 |  | Drilling and installation of propping for segment launching, scheduled next week
Fri (14/08) | 14 Aug 2026 | Zone 4 DR4 |  | No activity by GCE. WH housekeeping
Fri (14/08) | 14 Aug 2026 | P48 |  | Section 2 and 3 links installation. Later today to install formwork at section 1. Cast in anchor installation 6/12 completed
Fri (14/08) | 14 Aug 2026 | P37 |  | Recess form hacking in preparation for 1st stage stressing
Fri (14/08) | 14 Aug 2026 | P34 |  | Wing form and 1 side formwork installed. Form oil application in progress
Fri (14/08) | 14 Aug 2026 | P29 |  | PT duct installation. 4 pax
Sat (15/08) | 15 Aug 2026 | Zone 3 P34 |  | No activity. Pending rebar team from P48
Sat (15/08) | 15 Aug 2026 | Zone 3 P37 |  | Strands installation in progress
Sat (15/08) | 15 Aug 2026 | Zone 4 P46 |  | Preparation for Formwork lowering for 4th layer caisson wall installation
Sat (15/08) | 15 Aug 2026 | Zone 4 P48 |  | Shear links installation and preparation works for Formwork closing at SB side
Sat (15/08) | 15 Aug 2026 | Zone 4 P50 |  | Backfilling and levelling works
Sat (15/08) | 15 Aug 2026 | Zone 4 DR4 |  | Lane marking and preparation for traffic light shifting
Sat (15/08) | 15 Aug 2026 | Zone 2 P13 |  | FBCM materials removal and lowering
Sat (15/08) | 15 Aug 2026 | Zone 2 P10 |  | Strands installation for 2nd SB side
Sat (15/08) | 15 Aug 2026 | Zone 2 P9 |  | NR U05 installed last night
Sat (15/08) | 15 Aug 2026 | P7 |  | Segment adjustment works in progress
Sat (15/08) | 15 Aug 2026 | Zone 1 P4 |  | Preparation works for segment launching next week
Sat (15/08) | 15 Aug 2026 | Zone 3 P29 |  | Tendon ducts installation
Sat (15/08) | 15 Aug 2026 | Zone 3 P37 |  | Strands pushing and installation works
Sat (15/08) | 15 Aug 2026 | Zone 4 P46 |  | Pending Formwork installation for 4th layer
Sat (15/08) | 15 Aug 2026 | Zone 4 P48 |  | Rebar installation completed. Preparation for Formwork closing for SB side
Sat (15/08) | 15 Aug 2026 | Zone 4 P50 |  | Continue backfilling and leveling works
Sat (15/08) | 15 Aug 2026 | Zone 4 DR4 |  | Preparation for probing demo location
Sat (15/08) | 15 Aug 2026 | Zone 4 DR4 |  | Pedestrian walkway diversion ongoing
Sat (15/08) | 15 Aug 2026 | Zone 1 P4 |  | Bearing stump plates installation ongoing
Sat (15/08) | 15 Aug 2026 | Zone 2 P7 |  | SB segment adjustment
Sat (15/08) | 15 Aug 2026 | Zone 2 P10 |  | SB D/U 02 stressing completed
Sat (15/08) | 15 Aug 2026 | Zone 3 P29 |  | Preparation works for tendon ducts installation at NB side ongoing
Mon (17/08) | 17 Aug 2026 | Zone 4 800mm dia water pipe |  | Painting and preparing for PUB inspection
Mon (17/08) | 17 Aug 2026 | Zone 2 S4 |  | Trial trench for drain hacking in progress
Mon (17/08) | 17 Aug 2026 | Zone 2 P10 |  | Stressing for SB D/U 03 completed
Mon (17/08) | 17 Aug 2026 | Zone 2 P9 |  | NR D/U 05 preparation for stressing
Mon (17/08) | 17 Aug 2026 | Zone 2 P7 |  | Segment adjustment completed for SB 1st pair segment
Mon (17/08) | 17 Aug 2026 | Zone 2 P7 |  | NB 1st pair segment stitching formwork closing in progress
Mon (17/08) | 17 Aug 2026 | Zone 1 P4 |  | Preparation for segment launching
Mon (17/08) | 17 Aug 2026 | Zone 4 P51 |  | Exposing Starhub cablr for localise shifting for column work
Mon (17/08) | 17 Aug 2026 | Zone 4 P48 |  | Shear link installation. To cast on Wednesday
Mon (17/08) | 17 Aug 2026 | Zone 4 P47 |  | Monitoring of instrument before strut removal
Mon (17/08) | 17 Aug 2026 | Zone 4 P46 |  | Tonight to cast
Mon (17/08) | 17 Aug 2026 | Zone 1 P4 |  | Now no activity. Tonight plan for one segment launching
Mon (17/08) | 17 Aug 2026 | CCE4 |  | 3/7 struts installed. Strain gauge installation, MPI test were witnessed by RTO and preparing for perloading
Mon (17/08) | 17 Aug 2026 | CCE | GL-E1 to E3 | Lean con was cast last week. Currently no activity
Mon (17/08) | 17 Aug 2026 | Zone 1 P7 |  | Stitching formwork closing. Tonight will have night shift by WH also
Mon (17/08) | 17 Aug 2026 | CCE | GL-E4 to E9 | No activity
Mon (17/08) | 17 Aug 2026 | U3 Column C02-2 | North side | 1st lift formwork installation in progress. Plan for casting tmr
Mon (17/08) | 17 Aug 2026 | U3 Column C01-7 | North side | Rebar installation in progress
Mon (17/08) | 17 Aug 2026 | U3-11 |  | Coupler exposing ongoing
Mon (17/08) | 17 Aug 2026 | U3 Column C01-5 | South side | 2nd lift formwork installation in progress
Mon (17/08) | 17 Aug 2026 | U3-17 |  | Waterproofing membrane laying
Mon (17/08) | 17 Aug 2026 | Zone 2 P10 |  | Tonight will launch two segments at bus lane. Now preparing to receive the segments
Mon (17/08) | 17 Aug 2026 | U3-21, U3-19 |  | Top bar & cast-in pipes installation ongoing
Mon (17/08) | 17 Aug 2026 | U3 Column C01-3 | South side | 2nd lift rebar tying ongoing
Mon (17/08) | 17 Aug 2026 | U3 Column C04 | South side | Currently no activity
Mon (17/08) | 17 Aug 2026 | U3-29, U3-27, U3-25, U3-23 |  | Currently no activity
Mon (17/08) | 17 Aug 2026 | U3 Column C03-2 | South side | Currently no activity
Mon (17/08) | 17 Aug 2026 | U3-34, U3-36 |  | Rebar works in progress
Mon (17/08) | 17 Aug 2026 | B2 | South side, GL30-28 | Rebar installation ongoing for internal wall
Mon (17/08) | 17 Aug 2026 | Zone 3 P34 |  | GI pipe installation for crosshead rebar work. Tomorrow will delivery the rebar and start also
Mon (17/08) | 17 Aug 2026 | B2 | North side, GL25 | 2nd lift internal wall dismantling
Mon (17/08) | 17 Aug 2026 | Exit 3 |  | No activity yet
Mon (17/08) | 17 Aug 2026 | Zone 3 P37 |  | Stressing work. Tomorrow plan to complete
Mon (17/08) | 17 Aug 2026 | Zone 4 P50 |  | Lean concrete for crane parking
Mon (17/08) | 17 Aug 2026 | Zone 4 P48 |  | Current status of crosshead. To cast on Wednesday
Mon (17/08) | 17 Aug 2026 | Zone 4 P47 |  | No more water ingress. Just dampenss only
Mon (17/08) | 17 Aug 2026 | B1 level | along B1-02 | Internal wall rebar & formwork installation in progress
Mon (17/08) | 17 Aug 2026 | Zone 4 P46 |  | Tomorrow plan for casting of balance caisson
Tue (18/08) | 18 Aug 2026 | Zone 4 800mm dia water pipe |  | PUB inspection in progress including PUB management for link up work
Tue (18/08) | 18 Aug 2026 | B1 level | along B1-02 | Formwork installation for internal wall ongoing
Tue (18/08) | 18 Aug 2026 | Exit 3 |  | Currently no activity
Tue (18/08) | 18 Aug 2026 | Zone 3 P34 |  | Bottom rebar work started
Tue (18/08) | 18 Aug 2026 | Zone 3 P37 |  | PT stressing ongoing
Tue (18/08) | 18 Aug 2026 | Zone 3 P40 |  | LG has moved forward to P40, preparation work ongoing for segment starter installation - _LCB connection with the main crane spreader beam and support legs release_
Tue (18/08) | 18 Aug 2026 | B2 | North side, GL30 | Currently no activity
Tue (18/08) | 18 Aug 2026 | B2-35, B2-37 |  | Skinwall area currently no activity
Tue (18/08) | 18 Aug 2026 | B2 | South side, GL30-28 | Rebar works ongoing for internal wall
Tue (18/08) | 18 Aug 2026 | B2 | South side, GL32-30 | CJ roughening ongoing for 2nd lift internal wall works
Tue (18/08) | 18 Aug 2026 | CCW2 |  | Diagonal struts dismantling ongoing
Tue (18/08) | 18 Aug 2026 | Zone 4 P46 |  | 4th layer caisson pending casting
Tue (18/08) | 18 Aug 2026 | Zone 4 P47 |  | Pending S2 strut removal
Tue (18/08) | 18 Aug 2026 | Zone 4 P48 |  | Casting tmr
Tue (18/08) | 18 Aug 2026 | Zone 4 P50 |  | PLT for falsework footing ongoing
Tue (18/08) | 18 Aug 2026 | Zone 4 P51 |  | Current status no activity observed
Tue (18/08) | 18 Aug 2026 | U3 Column C02-2 | North side | Currently no activity
Tue (18/08) | 18 Aug 2026 | U3 Column C01-7 | North side | Rebar works ongoing
Tue (18/08) | 18 Aug 2026 | U3-11, U3-13 |  | Currently no activity
Tue (18/08) | 18 Aug 2026 | U3-17 |  | Currently no activity, U3-15: Formwork removal at drop area
Tue (18/08) | 18 Aug 2026 | U3 Column C01-4 | South side | 2nd lift rebar tying ongoing
Tue (18/08) | 18 Aug 2026 | U3-27, U3-25, U3-23 |  | Currently no activity
Tue (18/08) | 18 Aug 2026 | U3-29 |  | Coupler exposing at dwall area and CJ hacking at U3-31
Tue (18/08) | 18 Aug 2026 | U3-21, U3-19 |  | Top bar and side formwork installation in progress
Tue (18/08) | 18 Aug 2026 | U3 Column C03-2 | South side | 2nd lift shearlinks installation ongoing
Tue (18/08) | 18 Aug 2026 | U3-34, U3-36 |  | Rebar works in progress
Tue (18/08) | 18 Aug 2026 | Zone 2 P10 |  | Strand pulling ongoing
Tue (18/08) | 18 Aug 2026 | Zone 1 P4 |  | Current status
Tue (18/08) | 18 Aug 2026 | Zone 2 S4 |  | TT for abandoned drain removal prior to PUB inspection tmr
Tue (18/08) | 18 Aug 2026 | Zone 4 DR4 |  | Half fencing installation at diverted footpath and traffic light area
Wed (19/08) | 19 Aug 2026 | Zone 4 P46 |  | 4th layer caisson wall cast ytd, curing ongoing
Wed (19/08) | 19 Aug 2026 | Zone 4 P47 |  | Pending strut removal
Wed (19/08) | 19 Aug 2026 | Zone 4 P48 |  | Pending to start casting, target at 1pm
Wed (19/08) | 19 Aug 2026 | Zone 4 P50 |  | Current status, no activity observed
Wed (19/08) | 19 Aug 2026 | Zone 4 P51 1/3 nos column | 1st lift | Status quo, no activity observed
Wed (19/08) | 19 Aug 2026 | Zone 2 P10 |  | LF launching forward work ongoing
Wed (19/08) | 19 Aug 2026 | Zone 2 P10 |  | SB U4/D4 strand pushing and stressing work ongoing
Wed (19/08) | 19 Aug 2026 | Zone 2 P7 |  | PVC pipes installation strand cutting and pushing work, NB stitching formwork closing work & SB segment securing work ongoing
Wed (19/08) | 19 Aug 2026 | Zone 1 P4 |  | FBCM material setup and launching preparation work
Wed (19/08) | 19 Aug 2026 | Zone 3 P29 |  | Ducting completed. Tomorrow plan for inspection
Wed (19/08) | 19 Aug 2026 | Zone 3 P34 |  | Bottom rebar work for crosshead
Wed (19/08) | 19 Aug 2026 | Zone 3 P39 |  | Preparing for start hanger installation
Wed (19/08) | 19 Aug 2026 | Zone 3 P40 |  | Assembling of LCB
Wed (19/08) | 19 Aug 2026 | Zone 3 P37 |  | Current status of falsework removal
Wed (19/08) | 19 Aug 2026 | B1 level | along B1-02 | 1st lift internal wall & double slab formwork installation in progress
Wed (19/08) | 19 Aug 2026 | Exit 3 |  | Currently no activity
Wed (19/08) | 19 Aug 2026 | B2 | South side | GL28-26: Internal wall rebar works in progress, GL30-28: Internal wall formwork installation ongoing
Wed (19/08) | 19 Aug 2026 | CCE | GL-E4 to E9 | No activity. Rig for permeability test was shifted from BH-P14 (GL-E1)
Wed (19/08) | 19 Aug 2026 | CCE | GL-E1 to E3 | Currently no activity
Wed (19/08) | 19 Aug 2026 | U3 Column C02-2 | North side | 1st lift was cast yesterday
Wed (19/08) | 19 Aug 2026 | U3 Column C01-7 | North side | Currently no activity
Wed (19/08) | 19 Aug 2026 | U3-11 |  | Clearing debris, U3-13, U3-15: Currently no activity, U3-17: CJ hacking at U3-18 area
Wed (19/08) | 19 Aug 2026 | U3-21, U3-19 |  | Rebar works in progress. Plan for casting this week
Wed (19/08) | 19 Aug 2026 | U3 | North side, GL12 | Coupler exposing ongoing
Wed (19/08) | 19 Aug 2026 | U3-29 |  | Waterproofing membrane was installed at drop area. Currently only housekeeping here
Wed (19/08) | 19 Aug 2026 | U3-36 |  | Column starter bar and shearlinks installation, U3-34: Top bar installation in progress, Both slabs plan for casting next week
Wed (19/08) | 19 Aug 2026 | Zone 3 P34 |  | Wendyng continue with bottom rebar installation
Wed (19/08) | 19 Aug 2026 | Zone 3 P37 |  | Preparing for access dismantling & bottom fwk removal
Wed (19/08) | 19 Aug 2026 | Zone 3 P40-P39 |  | Utracon continue installation of starter segment & other accessories, preparation to resume segment installation by LG ongoing
Thu (20/08) | 20 Aug 2026 | Zone 3 |  | Combined earth mat resistance test ongoing
Thu (20/08) | 20 Aug 2026 | CCE4 |  | Struts installation in progress, 4/7nos
Thu (20/08) | 20 Aug 2026 | CCE | GL-E1 | Falsework erection ongoing for B2-43 works
Thu (20/08) | 20 Aug 2026 | CCE | GL-E4 | BH-P13 drilling in progress and safety inspection by safety champion
Thu (20/08) | 20 Aug 2026 | Zone 3 P40 |  | LCB status
Thu (20/08) | 20 Aug 2026 | Zone 3 P39 |  | LCB status
Thu (20/08) | 20 Aug 2026 | Zone 3 P37 |  | Preparing for falsework dismantling to shift to Zone 4
Thu (20/08) | 20 Aug 2026 | Zone 3 P29 |  | Top rebar ongoing, LG pipe sleeve & polyfoam installation ongoing
Fri (21/08) | 21 Aug 2026 | B1 level |  | ~GL1, B1-01: Falsework installation in progress for double slab works, B1-02: Currently no activity. Partial formwork was installed
Fri (21/08) | 21 Aug 2026 | Exit 3 |  | Currently no activity yet
Fri (21/08) | 21 Aug 2026 | B2 | South side, GL30-26 | Internal wall rebar works and inner formwork installation in progress
Fri (21/08) | 21 Aug 2026 | B2 | North side, GL27-25 | Internal wall surface grinding and patch up ongoing
Fri (21/08) | 21 Aug 2026 | B2 | North side, GL30 | Currently no activity
Fri (21/08) | 21 Aug 2026 | B2-35, B2-37 |  | Skinwall currently no activity
Fri (21/08) | 21 Aug 2026 | U3 Column C02-2 | North side | Shearlinks and rebar tying ongoing for 2nd lift
Fri (21/08) | 21 Aug 2026 | U3 Column C01-7 | North side | Preparing for 1st lift casting
Fri (21/08) | 21 Aug 2026 | U3-11 |  | Step ladder installation ongoing. Currently no other activity, U3-13: Currently no activity
Fri (21/08) | 21 Aug 2026 | U3-17 |  | Waterproofing membrane installed, U3-15: Waterproofing membrane installation at drop area
Fri (21/08) | 21 Aug 2026 | P29 |  | U loops hairpin installation
Fri (21/08) | 21 Aug 2026 | P30 |  | No activity
Fri (21/08) | 21 Aug 2026 | P34 |  | Crosshead rebar works installation
Fri (21/08) | 21 Aug 2026 | P37 |  | Falsework dismantling ongoing
Fri (21/08) | 21 Aug 2026 | U3-21, U3-19 |  | Wall & column starter bar installation and RTO inspection ongoing. Plan for casting this weekend
Fri (21/08) | 21 Aug 2026 | P39 |  | Installation of starter hanger at south bound ongoing
Fri (21/08) | 21 Aug 2026 | U3-25 |  | Grouting ongoing at skinwall area, U3-23: Currently no activity
Fri (21/08) | 21 Aug 2026 | U3-27 |  | Currently no activity
Fri (21/08) | 21 Aug 2026 | U3-29 |  | Straightening rebars at KP area and preparing to start bottom rebar works
Fri (21/08) | 21 Aug 2026 | U3 Column C01-1 | North side | Falsework erection ongoing for column works
Fri (21/08) | 21 Aug 2026 | U3 Column C01-1 | South side | CJ roughening ongoing
Fri (21/08) | 21 Aug 2026 | U3-33, U3-35, U3-37 |  | Currently no activity
Fri (21/08) | 21 Aug 2026 | U3-34, U3-36 |  | Wall starter bar & shearlinks installation. Plan for casting next week
Fri (21/08) | 21 Aug 2026 | CCW1 North |  | Tunnel side: Dongah works ongoing for tunnel ring, WH side: Preparing to continue hacking at skinwall area. Have reminded them to install netting to prevent debris from flying surrounding the tunnel eye area
Fri (21/08) | 21 Aug 2026 | CCW2 |  | S5 struts dismantling completed. Now dismantling waler beams
Fri (21/08) | 21 Aug 2026 | CCW1 South |  | WH hacking ongoing at skinwall area
Fri (21/08) | 21 Aug 2026 | 800mm PW |  | Excavation completed, waiting for lean concrete
Fri (21/08) | 21 Aug 2026 | P46 |  | Formwork dismantling and housekeeping
Fri (21/08) | 21 Aug 2026 | P47 |  | No activity
Fri (21/08) | 21 Aug 2026 | P48 |  | No activity. Concrete curing
Fri (21/08) | 21 Aug 2026 | P50 |  | Assembly working platform
Fri (21/08) | 21 Aug 2026 | P13 to P12 |  | Clamping beam dismantling
Fri (21/08) | 21 Aug 2026 | P10 SB 5th pair |  | Strand pushing for stressing
Fri (21/08) | 21 Aug 2026 | P7 MV |  | 1st pair wedge plate installation. Target to stress on Sunday
Sat (22/08) | 22 Aug 2026 | U3 Column C02-2 | North side | 1st lift formwork dismantling
Sat (22/08) | 22 Aug 2026 | U3 Column C01-7 | North side | 1st lift cast yesterday
Sat (22/08) | 22 Aug 2026 | Zone 3 P29 |  | Cast-in items installation in progress at NB side
Sat (22/08) | 22 Aug 2026 | Zone 3 P34 |  | Crosshead rebar installation
Sat (22/08) | 22 Aug 2026 | Zone 3 P37 |  | Crosshead falsework and scaffold dismantling in progress
Sat (22/08) | 22 Aug 2026 | U3-11 |  | PU grouting at dwall area and CJ hacking ongoing at U3-09
Sat (22/08) | 22 Aug 2026 | U3-13 |  | PU grouting ongoing, U3-15: Partial waterproofing membrane laying
Sat (22/08) | 22 Aug 2026 | U3-17 |  | Preparing bottom rebar installation
Sat (22/08) | 22 Aug 2026 | U3-21, U3-19 |  | Rebar completed. Now ongoing cleaning and waiting final inspection
Sat (22/08) | 22 Aug 2026 | U3 | South side, GL22-23 | Continue skinwall formwork installation
Sat (22/08) | 22 Aug 2026 | Zone 3 P39 |  | Starter hangers installed
Sat (22/08) | 22 Aug 2026 | U3 Column C02-2a | South side | Coupler exposing for RC wall rebar works
Sat (22/08) | 22 Aug 2026 | U3-29 |  | Rebar works in progress at KP area
Sat (22/08) | 22 Aug 2026 | U3 Column C01-1 | U3-31 | CJ roughening ongoing
Sat (22/08) | 22 Aug 2026 | U3 Column C01-1 | U3-32 | Rebar planting in progress
Sat (22/08) | 22 Aug 2026 | Zone 4 P50 |  | Preparation for Crosshead base Falsework installation @ SB side
Sat (22/08) | 22 Aug 2026 | Zone 4 DR4 |  | Preparation for UKP drilling and installation
Sat (22/08) | 22 Aug 2026 | U3-34, U3-36 |  | Wall starter bar installation ongoing
Sat (22/08) | 22 Aug 2026 | CCW1 North |  | WH no activity. Dongah tunnel works ongoing
Sat (22/08) | 22 Aug 2026 | CCW2 |  | Waler removal in progress
Sat (22/08) | 22 Aug 2026 | CCW1 South |  | WH to reinstate barrier prior to continuing hacking works at skinwall
Sat (22/08) | 22 Aug 2026 | Zone 2 P13 |  | Stressing materials shifting in progress
Sat (22/08) | 22 Aug 2026 | Zone 2 P10 |  | SB D/U 05 strand installation
Sat (22/08) | 22 Aug 2026 | Zone 2 P7 |  | Preparation works for 1st pair stressing
Sat (22/08) | 22 Aug 2026 | Zone 1 P4 |  | 4/6 nos. of 1st pair segment installed
Sat (22/08) | 22 Aug 2026 | Zone 3 P29 |  | Continue rebar installation works
Sat (22/08) | 22 Aug 2026 | Zone 3 P34 |  | Crosshead rebar installation ongoing
Sat (22/08) | 22 Aug 2026 | Zone 3 P37 |  | Continue Falsework dismantling
Sat (22/08) | 22 Aug 2026 | Zone 4 P46-P47 |  | Washout pipe laying for upcoming water pipe link up works
Sat (22/08) | 22 Aug 2026 | Zone 4 P50 |  | Continue crosshead base falsework installation
Sat (22/08) | 22 Aug 2026 | Zone 4 DR4 |  | DR4-UPD4-39 drilling works stopped due to suction pump breakdown. Target to complete 1 no. installation today
Sat (22/08) | 22 Aug 2026 | Zone 2 P13 |  | Slope backfilling in progress
Sat (22/08) | 22 Aug 2026 | Zone 2 P10 |  | Stressing and stitching formworks dismantling completed
Sat (22/08) | 22 Aug 2026 | Zone 2 P7 |  | Continue preparation works for 1st pair stressing
Sat (22/08) | 22 Aug 2026 | B1 level |  | B1-01 (GL1), B1-02: Formwork installation in progress for double slab & first lift internal wall
Sat (22/08) | 22 Aug 2026 | Exit 2 |  | Hacking ongoing at dwall area to expose starter bars
Sat (22/08) | 22 Aug 2026 | Exit 3 |  | No activity yet
Sat (22/08) | 22 Aug 2026 | B2 | South side | GL26-25: Internal wall rebar installation in progress, GL30: Continue wall formwork closing
Sat (22/08) | 22 Aug 2026 | B2 | North side, GL30 | Currently housekeeping
Sat (22/08) | 22 Aug 2026 | B2-35, B2-37 |  | Skinwall kicker cast yesterday
Sun (23/08) | 23 Aug 2026 | P29 |  | No activity
Sun (23/08) | 23 Aug 2026 | P34 |  | Crosshead rebar installation ongoing
Sun (23/08) | 23 Aug 2026 | P37 |  | Current falsework dismantling status
Sun (23/08) | 23 Aug 2026 | P39-P40 |  | No activity
Sun (23/08) | 23 Aug 2026 | P46 |  | Excavation to L5 caisson started, currently shifting access
Sun (23/08) | 23 Aug 2026 | P47 |  | No activity
Sun (23/08) | 23 Aug 2026 | P50 |  | Crosshead falsework installation
Sun (23/08) | 23 Aug 2026 | P48 |  | Installing barricade on top of crosshead
Sun (23/08) | 23 Aug 2026 | DR4 |  | No activity. Only housekeeping
Sun (23/08) | 23 Aug 2026 | P13 |  | Material shifting
Sun (23/08) | 23 Aug 2026 | P11 |  | Preparation for grouting works
Sun (23/08) | 23 Aug 2026 | P10 |  | Preparation for stressing works
Sun (23/08) | 23 Aug 2026 | P7 |  | Preparation for stressing works..waiting for cube test result
Sun (23/08) | 23 Aug 2026 | P4 |  | No activity
Sun (23/08) | 23 Aug 2026 | P29 |  | No activity
Sun (23/08) | 23 Aug 2026 | P34 |  | Crosshead rebar installation ongoing
Sun (23/08) | 23 Aug 2026 | P46 |  | Scaffolding erection ongoing, no excavation work
Sun (23/08) | 23 Aug 2026 | P48 |  | No activity
Sun (23/08) | 23 Aug 2026 | P50 |  | Crosshead falsework installation ongoing
Sun (23/08) | 23 Aug 2026 | P11 |  | Grouting works ongoing
Sun (23/08) | 23 Aug 2026 | P10 |  | Stressing work ongoing
Sun (23/08) | 23 Aug 2026 | P7 |  | No activity
Mon (24/08) | 24 Aug 2026 | P48 |  | Crosshead working platform installation ongoing
Mon (24/08) | 24 Aug 2026 | P47 |  | No activity
Mon (24/08) | 24 Aug 2026 | P46 |  | No activity
Mon (24/08) | 24 Aug 2026 | B2-43 |  | Will continue to erect falsework later
Mon (24/08) | 24 Aug 2026 | P7 SBR |  | SH installed. 600T crane will shift to P10 later for LF Dismantling
Mon (24/08) | 24 Aug 2026 | Zone 4 800mm dia water pipe |  | Checking for wash out pipe installation
Mon (24/08) | 24 Aug 2026 | Zone 4 DR4 |  | Grouting for UKP installation
Mon (24/08) | 24 Aug 2026 | P29 |  | Rebar installation works
Mon (24/08) | 24 Aug 2026 | P34 |  | Rebar installation works
Mon (24/08) | 24 Aug 2026 | P37 |  | Dismantling crosshead falsework
Mon (24/08) | 24 Aug 2026 | P40 |  | Preparation for segment launching
Mon (24/08) | 24 Aug 2026 | U3 Column C01-7 | U3-09 | Cleaning ongoing for 2nd lift
Mon (24/08) | 24 Aug 2026 | U3-11 |  | CJ hacking ongoing at U3-09 side
Mon (24/08) | 24 Aug 2026 | U3-10 area |  | CJ hacking ongoing for wall rebar works
Mon (24/08) | 24 Aug 2026 | U3 | South side, GL24-26 | Skinwall rebar works ongoing
Mon (24/08) | 24 Aug 2026 | U3 | South side, GL22-24 | Skinwall formwork installation in progress
Mon (24/08) | 24 Aug 2026 | U3-13 |  | Partial bottom rebar works and continue waterproofing membrane installation
Mon (24/08) | 24 Aug 2026 | U3-17, U3-15 |  | Bottom rebar works ongoing
Mon (24/08) | 24 Aug 2026 | U3-21, U3-19 |  | Cast last Saturday
Mon (24/08) | 24 Aug 2026 | U3-25, U3-23 |  | No activity yet
Mon (24/08) | 24 Aug 2026 | U3-29, U3-27 |  | Rebar works in progress
Mon (24/08) | 24 Aug 2026 | U3-33 |  | Coupler exposing ongoing
Mon (24/08) | 24 Aug 2026 | U3 Column C01-1 | U3-31 | Currently no activity
Mon (24/08) | 24 Aug 2026 | U3-34, U3-36 |  | Preparing for casting
Mon (24/08) | 24 Aug 2026 | U3 Column C01-1 | U3-32 | Rebar works ongoing
Mon (24/08) | 24 Aug 2026 | B2 level | South side | GL30-26: Wall formwork installation in progress, GL26-23: Wall rebar works in progress
Mon (24/08) | 24 Aug 2026 | Exit 3 |  | No activity yet
Mon (24/08) | 24 Aug 2026 | B1 level | B1-02 area | 1st lift internal wall & double slab formwork installation in progress
Mon (24/08) | 24 Aug 2026 | P46 |  | No activity
Mon (24/08) | 24 Aug 2026 | P47 |  | No activity
Mon (24/08) | 24 Aug 2026 | P48 |  | Crosshead falsework installation
Mon (24/08) | 24 Aug 2026 | DR4 |  | Completed 1 UKP today, now preparation for UKP point tomorrow
Mon (24/08) | 24 Aug 2026 | P4 |  | No activity
Mon (24/08) | 24 Aug 2026 | P7 |  | No activity
Mon (24/08) | 24 Aug 2026 | P10 |  | Preparation to bring down LF tonight
Tue (25/08) | 25 Aug 2026 | P10 |  | 600T crane dismantling, use to lower stressing cage and LF from P10
Tue (25/08) | 25 Aug 2026 | Zone 3 P29 |  | Crosshead shear links installation
Tue (25/08) | 25 Aug 2026 | Zone 3 P34 |  | Tendon duct installation
Tue (25/08) | 25 Aug 2026 | Zone 3 P37 |  | Current falsework dismantling status. No activity
Tue (25/08) | 25 Aug 2026 | Zone 3 P40 |  | Stressing works ongoing
Tue (25/08) | 25 Aug 2026 | Zone 4 P46 |  | Excavation to L5 caisson layer
Tue (25/08) | 25 Aug 2026 | Zone 4 P47 |  | S2 strut removal
Tue (25/08) | 25 Aug 2026 | Zone 4 P48 |  | Formwork dismantling ongoing + crane setting for dismantling work
Tue (25/08) | 25 Aug 2026 | Zone 4 P50 |  | Base formwork installation ongoing
Tue (25/08) | 25 Aug 2026 | Zone 4 DR4 |  | Completed 1 no. UKP, now drilling for 2nd UKP
Wed (26/08) | 26 Aug 2026 | Zone 2 P13 |  | Hacking and removal of concrete block ongoing
Wed (26/08) | 26 Aug 2026 | Zone 2 P10 |  | 600 ton crane parking for LF lowering and shifting to P7
Wed (26/08) | 26 Aug 2026 | Zone 2 P7 |  | 1/4 nos. of LF installed. Stitching Formwork dismantling in progress
Wed (26/08) | 26 Aug 2026 | Zone 4 P50 |  | Soffit plywood laying and adjusting jack
Wed (26/08) | 26 Aug 2026 | Zone 4 P51 |  | Preparing for services diversion
Wed (26/08) | 26 Aug 2026 | Zone 4 P48 |  | Side formwork removal. Will be reuse at P50
Wed (26/08) | 26 Aug 2026 | Zone 4 P47 |  | S2 strut removal. Today to complete
Wed (26/08) | 26 Aug 2026 | Zone 4 P46 |  | Continue excavation work for last layer
Wed (26/08) | 26 Aug 2026 | Zone 3 P40 |  | Current status
Wed (26/08) | 26 Aug 2026 | Zone 3 P34 |  | Ducting installation. To cast this Saturday
Wed (26/08) | 26 Aug 2026 | Zone 3 P29 |  | Crosshead rebar works (shear links & stump)
Wed (26/08) | 26 Aug 2026 | Zone 3 P34 |  | Tendon duct installation
Wed (26/08) | 26 Aug 2026 | Zone 3 P37 |  | Falsework dismantling completed
Wed (26/08) | 26 Aug 2026 | Zone 3 P40 |  | Segment stressing works
Wed (26/08) | 26 Aug 2026 | Zone 4 P48 |  | Formwork and scaffolding dismantling ongoing
Wed (26/08) | 26 Aug 2026 | Zone 4 P50 |  | Crosshead bottom formwork installation
Wed (26/08) | 26 Aug 2026 | Zone 4 DR4 |  | Pedestrian walkway shelter installation
Wed (26/08) | 26 Aug 2026 | Zone 4 DR4 |  | Completed 1 nos UKP installation, preparation for 2nd UKP..LE marking for soldier pile location, tomorrow start probing for soldier pile
Wed (26/08) | 26 Aug 2026 | Exit 1 linkway |  | Hacking ongoing at skinwall area
Wed (26/08) | 26 Aug 2026 | CCE4 |  | Rebar works in progress for RC strut
Wed (26/08) | 26 Aug 2026 | CCE | GL-E1 to E3 | Falsework installation ongoing to concourse slab works
Wed (26/08) | 26 Aug 2026 | B2 | North side, GL30-E9 | Scaffold was dismantled to facilitate moveable formwork installation for skinwall
Wed (26/08) | 26 Aug 2026 | U3 Column C02-2 | U3-07 | 2nd lift plan for casting tonight
Wed (26/08) | 26 Aug 2026 | U3 Column C01-7 | U3-09 | 2nd lift plan for casting tonight
Wed (26/08) | 26 Aug 2026 | U3-13, U3-11 |  | Currently no activity
Wed (26/08) | 26 Aug 2026 | U3 | South side, GL22-24 | Skinwall was cast earlier today
Wed (26/08) | 26 Aug 2026 | U3-15, U3-17 |  | Bottom rebar works in progress, U3-17: Cleaning ongoing near U3-19 CJ side prior to installing balance waterproofing membrane
Wed (26/08) | 26 Aug 2026 | U3-25, U3-23 |  | Currently no activity
Wed (26/08) | 26 Aug 2026 | U3-29, U3-27 |  | Top bar and cast-in pipes installation in progress
Wed (26/08) | 26 Aug 2026 | U3 Column C01-1 | U3-31 | Rebar works in progress
Wed (26/08) | 26 Aug 2026 | U3 | South side, GL14-16 | Skinwall rebar works in progress
Wed (26/08) | 26 Aug 2026 | B2 | South side, GL26-22 | 1st lift internal wall rebar and formwork installation in progress
Wed (26/08) | 26 Aug 2026 | Exit 3 |  | Currently no activity
Wed (26/08) | 26 Aug 2026 | B1 level | B1-02 area | Double slab & 1st lift internal wall formwork in progress
Thu (27/08) | 27 Aug 2026 | Zone 2 P10 |  | Preparation to lower last LF to shift to P7 SB
Thu (27/08) | 27 Aug 2026 | Zone 2 P7 |  | 3/4 LFs installed. Stitching formwork dismantled. To resume segment launching tonight
Thu (27/08) | 27 Aug 2026 | Zone 4 P50 |  | GI pipe installation for the base
Thu (27/08) | 27 Aug 2026 | Zone 4 P48 |  | Continue opening formwork removal
Thu (27/08) | 27 Aug 2026 | Zone 4 P47 |  | Pile cap rebar work in progress
Thu (27/08) | 27 Aug 2026 | Zone 4 DR3 |  | Formwork installation to seal the gap
Thu (27/08) | 27 Aug 2026 | Zone 4 P46 |  | Today KTC will handover to HSL for pile head hacking
Thu (27/08) | 27 Aug 2026 | Zone 4 800mm dia water pipe |  | Welding of reducer
Thu (27/08) | 27 Aug 2026 | Zone 4 DR4 |  | TT for pipe sleeves installation for probing work
Thu (27/08) | 27 Aug 2026 | B2 level | North side | GL30-32: Currently no activity
Thu (27/08) | 27 Aug 2026 | U3 Columns | North side | C01-7 & C02-2 2nd lifts cast last night
Thu (27/08) | 27 Aug 2026 | U3-13, U3-11 |  | Currently no activity
Thu (27/08) | 27 Aug 2026 | U3 | South side, GL22-24 | Skinwall formwork dismantling
Thu (27/08) | 27 Aug 2026 | U3-17, U3-15 |  | Rebar works in progress, U3-17: Balance waterproofing membrane installation at drop area
Thu (27/08) | 27 Aug 2026 | U3 | North side, GL16-14 | Skinwall PU grouting, drilling ongoing for tie rod holes and cleaning at kicker area
Thu (27/08) | 27 Aug 2026 | U3 Column C01-2 | U3-24 | Formwork dismantled
Thu (27/08) | 27 Aug 2026 | U3-25, U3-23 |  | Currently no activity
Thu (27/08) | 27 Aug 2026 | Zone 2 P7 |  | Last LF from P10 installed
Thu (27/08) | 27 Aug 2026 | U3-29, U3-27 |  | Top bar and side formwork installation in progress. Plan for casting next week
Thu (27/08) | 27 Aug 2026 | U3 Column C01-1 | U3-32 | 1st lift cast last night
Thu (27/08) | 27 Aug 2026 | U3 Column C01-1 | U3-31 | Shearlinks installation in progress
Thu (27/08) | 27 Aug 2026 | U3-34 |  | Formwork dismantling and CJ hacking
Thu (27/08) | 27 Aug 2026 | U3 Column C01-3 | U3-22 | Formwork dismantled
Thu (27/08) | 27 Aug 2026 | B2 level | South side | GL30-25: Double slab and 1st lift wall formwork installation in progress, GL25-22: Wall rebar and preparing formwork in progress
Thu (27/08) | 27 Aug 2026 | Zone 4 P50 |  | Platform and netting installed. Wingform to install from P48
Thu (27/08) | 27 Aug 2026 | Zone 4 P48 |  | Wingform removal
Thu (27/08) | 27 Aug 2026 | Zone 4 P47 |  | Pile cap rebar work
Thu (27/08) | 27 Aug 2026 | Exit 2 |  | Continue hacking at dwall area
Thu (27/08) | 27 Aug 2026 | Zone 4 P47 |  | Pile cap rebar work
Thu (27/08) | 27 Aug 2026 | Exit 2 |  | Continue hacking at dwall area
Thu (27/08) | 27 Aug 2026 | Zone 4 P50 |  | Platform and netting installed. Wingform to install from P48
Thu (27/08) | 27 Aug 2026 | U3 Column C01-3 | U3-22 | Formwork dismantled
Thu (27/08) | 27 Aug 2026 | B2 level | South side | GL30-25: Double slab and 1st lift wall formwork installation in progress, GL25-22: Wall rebar and preparing formwork in progress
Thu (27/08) | 27 Aug 2026 | Zone 4 DR4 |  | 6nos of UKP installed. Now preparing for the next one
Thu (27/08) | 27 Aug 2026 | Zone 4 DR4 |  | Marking for soldier pile location
Fri (28/08) | 28 Aug 2026 | U3-11 & U3-13 |  | Plan to start waterprrofinh today
Fri (28/08) | 28 Aug 2026 | U3-14 |  | Skinwall rebar work is in progress
Fri (28/08) | 28 Aug 2026 | U3-16 |  | Skillwall formwork removal is in progress
Fri (28/08) | 28 Aug 2026 | U3-22 |  | Grouting work in progress
Fri (28/08) | 28 Aug 2026 | U3-22 & U3-24 |  | Rebar work in progress for skinwall
Fri (28/08) | 28 Aug 2026 | U3-27 & U3-29 |  | Rebar & formwork in progress, target to cast upcoming Monday
Fri (28/08) | 28 Aug 2026 | Zone 3 P29 |  | NB bearing stump, tie rod & polyfoam installation ongoing
Fri (28/08) | 28 Aug 2026 | Zone 3 P34 |  | Tendon duct installation ongoing
Fri (28/08) | 28 Aug 2026 | Zone 3 P32 |  | Falsework erection ongoing, primary beam started
Fri (28/08) | 28 Aug 2026 | Zone 2 P7 |  | 4 segments launched last night (SBR D/U 01 & NB D/U 02). Strand installation for stressing at NB ongoing
Fri (28/08) | 28 Aug 2026 | Zone 4 P46 |  | Bored pile hacking
Fri (28/08) | 28 Aug 2026 | Zone 4 P48 |  | Formwork dismantling completed, preparation to install at P50
Fri (28/08) | 28 Aug 2026 | Zone 4 P50 |  | Preparation for formwork installation
Fri (28/08) | 28 Aug 2026 | Zone 3 P29 |  | Shear link to complete tomorrow. Side formwork half done
Fri (28/08) | 28 Aug 2026 | Zone 3 P32 |  | Platform installation in progress
Fri (28/08) | 28 Aug 2026 | Zone 3 P43 |  | Tendon duct installation. Next week to cast
Fri (28/08) | 28 Aug 2026 | Zone 4 DR4 |  | Walkway shelter assembly work ongoing, completed 3/9 nos
Fri (28/08) | 28 Aug 2026 | Zone 4 DR4 |  | Completed 2 sets (3nos each) of soldier pile probing..trial trench for next UKP point completed, preparing for probing of UKP point
Fri (28/08) | 28 Aug 2026 | Zone 4 P51 |  | No activity
Fri (28/08) | 28 Aug 2026 | Zone 4 P50 |  | Preparation of crosshead formwork
Fri (28/08) | 28 Aug 2026 | Zone 4 P48 |  | Crosshead formwork dismantling
Fri (28/08) | 28 Aug 2026 | Zone 4 P47 |  | Pile cap bottom rebar installation
Fri (28/08) | 28 Aug 2026 | Zone 4 P46 |  | Bored pile hacking
Fri (28/08) | 28 Aug 2026 | CCE4/RS |  | Will continue rebar work for the arc strut, target to cast tomorrow
Fri (28/08) | 28 Aug 2026 | Exit 1 linkway |  | Hacking in progress for skinwall by 3 excavators
Fri (28/08) | 28 Aug 2026 | B2-43 |  | Current falsework status
Sat (29/08) | 29 Aug 2026 | Zone 3 P29 |  | Shear links installation
Sat (29/08) | 29 Aug 2026 | Zone 3 P32 |  | Crosshead falsework installation
Sat (29/08) | 29 Aug 2026 | Zone 3 P34 |  | Tendon duct installation
Sat (29/08) | 29 Aug 2026 | Zone 3 P40 |  | Strand pushing ongoing
Sat (29/08) | 29 Aug 2026 | Zone 3 P39 |  | No activity
Sat (29/08) | 29 Aug 2026 | Zone 4 P46 |  | Bored pile hacking at north side
Sat (29/08) | 29 Aug 2026 | Zone 4 P47 |  | Bar chair installation ongoing
Sat (29/08) | 29 Aug 2026 | Zone 4 P48 |  | Painting barricade on top of crosshead
Sat (29/08) | 29 Aug 2026 | Zone 4 P50 |  | Current formwork installation status
Sat (29/08) | 29 Aug 2026 | Zone 4 DR4 |  | Completed 4/9 nos shelter
Sat (29/08) | 29 Aug 2026 | Zone 4 DR4 |  | Preparation for UKP probing works
Sat (29/08) | 29 Aug 2026 | Zone 2 South Ramp |  | Hardcore shifting & levelling works
Sat (29/08) | 29 Aug 2026 | Zone 2 P11 |  | Scaffolding dismantling ongoing
Sat (29/08) | 29 Aug 2026 | Zone 2 P7 |  | Crane parking setting up..prepare to shift stressing cage from NB to SB
Sat (29/08) | 29 Aug 2026 | Zone 3 P29 |  | Preparation for formwork closing
Sat (29/08) | 29 Aug 2026 | Zone 3 P32 |  | Crosshead falsework installation
Sat (29/08) | 29 Aug 2026 | Zone 3 P34 |  | Tendon duct inspection ongoing
Sat (29/08) | 29 Aug 2026 | Zone 3 P40 |  | No activity
Sat (29/08) | 29 Aug 2026 | Zone 4 P46 |  | Bored pile hacking
Sat (29/08) | 29 Aug 2026 | Zone 3 P48 |  | No activity
Sat (29/08) | 29 Aug 2026 | Zone 3 P47 |  | Pile cap top rebar installation
Sat (29/08) | 29 Aug 2026 | Zone 4 P50 |  | Formwork adjustment and oil coating
Sat (29/08) | 29 Aug 2026 | Zone 4 DR4 |  | No activity
Sat (29/08) | 29 Aug 2026 | Zone 2 P7 |  | Preparation for stressing work
Mon (31/08) | 31 Aug 2026 | Zone 3 P29 |  | Plan for casting tomorrow
Mon (31/08) | 31 Aug 2026 | Zone 3 P32 |  | Falsework erection done. WH shifting materials for access erection
Mon (31/08) | 31 Aug 2026 | Zone 3 P34 |  | Preparation for formwork support installation
Mon (31/08) | 31 Aug 2026 | Zone 3 P40 |  | Current status of launching
Mon (31/08) | 31 Aug 2026 | CCE4/RS |  | RC strut casted over the weekend
Mon (31/08) | 31 Aug 2026 | Zone 4 800mm dia water pipe |  | Pipe accessories preparation
Mon (31/08) | 31 Aug 2026 | Zone 4 P46 NB |  | Pile head hacking
Mon (31/08) | 31 Aug 2026 | Zone 4 P47 |  | Pile cap rebar work. Tonight to cast
Mon (31/08) | 31 Aug 2026 | Zone 4 P48 |  | Current status of formwork removal
Mon (31/08) | 31 Aug 2026 | Zone 4 P50 |  | Working platform and one side formwork closed. Waiting for main bar delivery
Mon (31/08) | 31 Aug 2026 | B2-49B |  | Ongoing excavation & internal transfer by 2 excavators
Mon (31/08) | 31 Aug 2026 | B2-43 |  | Continues installing of falsework
Mon (31/08) | 31 Aug 2026 | U3-07 |  | Dismantling of column 2nd lift formwork is in progress
Mon (31/08) | 31 Aug 2026 | U3-11 & U3-13 |  | Laying of membrane & CJ hacking in progress
Mon (31/08) | 31 Aug 2026 | U3-14 |  | Formwork installation in progress for skinwall
Mon (31/08) | 31 Aug 2026 | U3-15 & U3-17 |  | Rebar work is in progress
Mon (31/08) | 31 Aug 2026 | U3-24 & U3-26 |  | Rebar work in progress for skinwall
Mon (31/08) | 31 Aug 2026 | U3-27 & U3-29 |  | Target to cast it tonight, final inspection arranged @ 5pm
Mon (31/08) | 31 Aug 2026 | U3-32 |  | Dismantling of 2nd lift column formwork
Mon (31/08) | 31 Aug 2026 | U3-33 |  | Started rebar work
Mon (31/08) | 31 Aug 2026 | U3-35 |  | Roughening of CJ in progress
Mon (31/08) | 31 Aug 2026 | Zone 4 DR4 |  | TT for probing. Found LT cable. WH to check after 7PM
Mon (31/08) | 31 Aug 2026 | Zone 4 DR4 |  | Status of pipe sleeve installed
Mon (31/08) | 31 Aug 2026 | Zone 4 800mm dia water pipe |  | Prepare pipes for link up
Mon (31/08) | 31 Aug 2026 | Zone 4 DR4 |  | Linkway shelter will start installation today
Mon (31/08) | 31 Aug 2026 | CCW1 South |  | No activity
Mon (31/08) | 31 Aug 2026 | CCW1 North |  | No activity
Mon (31/08) | 31 Aug 2026 | CCW2 South |  | Wall rebar planting in progress
Mon (31/08) | 31 Aug 2026 | U3-33 |  | Rebar works in progress
Mon (31/08) | 31 Aug 2026 | U3 Column C01-1 | U3-31 | Dismantling 1st lift formwork
Mon (31/08) | 31 Aug 2026 | U3-29, U3-27 |  | Preparing for casting
Mon (31/08) | 31 Aug 2026 | U3 | South side, GL12-14 | Skinwall rebar works in progress
Mon (31/08) | 31 Aug 2026 | Zone 3 P29 |  | No activity
Mon (31/08) | 31 Aug 2026 | Zone 3 P32 |  | No activity
Mon (31/08) | 31 Aug 2026 | Zone 3 P34 |  | Preparation for formwork closing
Mon (31/08) | 31 Aug 2026 | Zone 3 P40 |  | Preparation for segment launching
Mon (31/08) | 31 Aug 2026 | U3-17, U3-15 |  | Bar chair and cast-in pipes installation in progress
Mon (31/08) | 31 Aug 2026 | U3 | South side, GL24-26 | Skinwall formwork installation in progress
Mon (31/08) | 31 Aug 2026 | U3-11 |  | CJ hacking ongoing at U3-12 area & partial waterproofing membrane installation
Mon (31/08) | 31 Aug 2026 | Zone 4 P46 |  | No activity
Mon (31/08) | 31 Aug 2026 | Zone 4 P47 |  | Ready for casting, pump truck done setting up on site..waiting for concrete
Mon (31/08) | 31 Aug 2026 | Zone 4 P48 |  | No activity
Mon (31/08) | 31 Aug 2026 | Zone 4 P50 |  | No activity
Mon (31/08) | 31 Aug 2026 | Zone 4 DR4 |  | No activity
Mon (31/08) | 31 Aug 2026 | B2 | North side, GL31-32 | Skinwall formwork installation
Mon (31/08) | 31 Aug 2026 | B2 | South side | GL30-26: 1st lift wall and double slab cast. Now ongoing formwork dismantling, GL26-22: 1st lift wall rebar & formwork installation
Mon (31/08) | 31 Aug 2026 | Exit 3 |  | No activity
Mon (31/08) | 31 Aug 2026 | Zone 2 P7 |  | Preparation for stressing work at north bound
Mon (31/08) | 31 Aug 2026 | Zone 2 P7 |  | Preparation for segment launching at south bound
Mon (31/08) | 31 Aug 2026 | Zone 2 South ramp |  | Slope cutting ongoing
Tue (01/09) | 01 Sep 2026 | CCW1 South |  | No activity
Tue (01/09) | 01 Sep 2026 | CCW1 North |  | Works ongoing inside tunnel. No activity at WH side
Tue (01/09) | 01 Sep 2026 | CCW2 | South side | Wall rebar works, CJ hacking and continue scaffold erection ongoing
Tue (01/09) | 01 Sep 2026 | U3-33 |  | Rebar works in progress
Tue (01/09) | 01 Sep 2026 | U3 Column C01-1 | U3-31 | 2nd lift formwork installation in progress
Tue (01/09) | 01 Sep 2026 | U3 | South side, GL7-5 | Skinwall hacking ongoing
Tue (01/09) | 01 Sep 2026 | U3-29, U3-27 |  | Casting ongoing
Tue (01/09) | 01 Sep 2026 | U3-17 |  | Cast-in pipes installation ongoing, U3-15: Rebar and bar chair installation in progress
Tue (01/09) | 01 Sep 2026 | U3 | South side, GL24-26 | Skinwall formwork installation in progress
Tue (01/09) | 01 Sep 2026 | U3-11 |  | Waterproofing membrane laying, CJ hacking at U3-12 area, PU grouting & RGT installation
Tue (01/09) | 01 Sep 2026 | CCE | GL-E1 to E3 | Continue falsework installation
Tue (01/09) | 01 Sep 2026 | B2 | GL-E9 towards VS | 2nd lift wall formwork installation ongoing
Tue (01/09) | 01 Sep 2026 | B2 | South side | GL26-23: Wall formwork installation, GL23-22: Wall rebar works ongoing
Tue (01/09) | 01 Sep 2026 | Exit 3 |  | Currently no activity
Tue (01/09) | 01 Sep 2026 | B1 level | B1-02 area | Plan to cast 1st lift wall and double slab this week
Tue (01/09) | 01 Sep 2026 | Zone 3 P29 |  | Preparing for crosshead casting
Tue (01/09) | 01 Sep 2026 | Zone 3 P32 |  | Access erection. Tomorrow can continue soffit plywood laying
Tue (01/09) | 01 Sep 2026 | Zone 3 P34 |  | Shear link installation. Plan to complete installation this week
Tue (01/09) | 01 Sep 2026 | Zone 3 P29 |  | Car pump setting up for casting
Tue (01/09) | 01 Sep 2026 | Zone 4 P46 |  | BP removal ongoing for caisson work
Tue (01/09) | 01 Sep 2026 | Zone 4 P47 |  | Pile cap curing ongoing
Tue (01/09) | 01 Sep 2026 | Zone 4 P48 |  | No activity observed
Tue (01/09) | 01 Sep 2026 | Zone 4 P50 |  | No activity observed
Tue (01/09) | 01 Sep 2026 | Zone 4 DR4 |  | SP-1 ongoing
Tue (01/09) | 01 Sep 2026 | Zone 2 P7 |  | NB/SB strand cutting ongoing, NBR segment adjusting, preparing for segment launching tonight
Tue (01/09) | 01 Sep 2026 | Zone 1 P4 |  | No. 5 segment on ground
Tue (01/09) | 01 Sep 2026 | Zone 1 P4 |  | FBCM blocks fabrication status